## Sheet1
Team Code | Discipline | Serial | Document No | Title | Pur | First Plan | Final Plan | SA | ESOD | HAZOP | PKG Code | First Actual | Final Actual
EM(02) | Engineering Management | 020001 | T16182-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION | IFI | 2017-01-30 |  |  | O |  |  | 2017-01-06 | #VALUE!
EM(02) | Engineering Management | 020002 | T16182-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | IFI | 2017-01-30 |  |  | O |  |  | 2017-01-06 | #VALUE!
EM(02) | Project Management | 020003 | T16182-VA08-P0ZEN-020003 | CONTRACTORS ADMIN PLAN | IFI | 2016-12-23 | [5 empty] | 2016-12-23 | #VALUE!
EM(02) | Project Management | 020004 | T16182-DP00-P0ZEN-020004 | PAINTING SPECIFICATION | IFR | 2017-04-30 | 2017-07-30 |  |  |  |  | 2017-06-07 | 2017-06-21
EM(02) | Project Management | 020005 | T16182-DP00-P0ZEN-020005 | PACKING SPECIFICATION | IFI | 2017-05-01 | [5 empty] | 2017-04-24 | #VALUE!
EM(02) | Engineering Management | 020006 | T16182-DP00-P0ZEN-020006 | NAME AND TAG PLATE | IFI | 2017-06-01 | [5 empty] | 2017-05-25 | #VALUE!
EM(02) | Engineering Management | 020007 | T16182-DP00-P0ZEN-020007 | ABBREVIATION LIST | IFI | 2017-05-01 | [5 empty] | 2017-05-23 | #VALUE!
EM(02) | Engineering Management | 020008 | T16182-YK08-P0ZEN-020008 | LABELING LAYOUT FOR WATER STORAGE TANKS | IFI | 2018-06-04 | 2018-09-07 |  |  |  |  | 2018-06-04 | 2018-06-18
EM(02) | Project Management | 020009 | T16182-DP00-P0ZEN-020009 | TYPICAL DANGER SIGN DRAWING | IFI | 2018-07-25 | [5 empty] | 2018-07-19 | #VALUE!
EM(02) | Engineering Management | 020010 | T16182-CA07-P0ZEN-020010 | UNDERGROUND PIPE MARKER DETAIL | IFC | 2019-07-26 | 2019-07-26 |  |  |  |  | 2019-07-26 | 2019-07-26
EM(02) | Engineering Management | 020020 | T16182-BV02-P0ZEN-020020 | MAINTAINABILITY STUDY | IFI | 2018-09-20 | [5 empty] | 2018-09-25 | #VALUE!
EM(02) | Engineering Management | 020030 | T16182-BV02-P0ZEN-020030 | CORROSION AND MATERIAL STUDY | IFI | 2018-09-20 | [5 empty] | 2018-09-25 | #VALUE!
EM(02) | Engineering Management | 020040 | T16182-BV02-P0ZEN-020040 | FIRE STUDY | IFI | 2018-09-18 |  |  |  |  | PKG-030-FF | 2018-09-18 | #VALUE!
S&A(18) | Structural & Architectural | 050001 | T16182-BV02-P0ZEN-050001 | BUILDING RISK ASSESSMENT | IFI | 2017-05-25 |  | O |  |  |  | 2017-05-26 | #VALUE!
GA(10) | General | 100001 | T16182-UC07-P0ZEN-100001 | SITE PLAN | IFR | 2016-10-30 | 2017-02-14 |  | O | O |  | 2016-11-03 | 2017-03-09
GA(10) | General | 100002 | T16182-UC07-P0ZEN-100002 | OVERALL PLOT PLAN WITH ESF AREA | IFR | 2016-10-30 | 2017-02-14 |  | O |  |  | 2016-11-03 | 2017-03-09
GA(10) | General | 100003 | T16182-UC07-P0ZEN-100003 | OVERALL PLOT PLAN | IFR | 2016-10-30 | 2017-02-14 | O | O | O |  | 2016-11-03 | 2017-03-09
GA(10) | General | 100004 | T16182-UE00-P0MB-100004 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 1&2 (PLAN VIEW) | IFR | 2016-10-30 | 2017-05-04 | O | O | O |  | 2016-11-03 | 2017-05-10
GA(10) | General | 100005 | T16182-UE00-P0MB-100005 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 3&4&5 (PLAN VIEW) | IFR | 2016-10-30 | 2017-05-04 | O | O | O |  | 2016-11-03 | 2017-05-10
GA(10) | General | 100006 | T16182-UE00-P0MB-100006 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION A - A) | IFR | 2016-10-30 | 2017-05-04 |  | O | O |  | 2016-11-03 | 2017-05-10
GA(10) | General | 100007 | T16182-UE00-P0MB-100007 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION B - B) | IFR | 2016-10-30 | 2017-05-04 |  | O | O |  | 2016-11-03 | 2017-05-10
GA(10) | General | 100008 | T16182-UE00-P0UMA-100008 | PLANT GENERAL ARRANGEMENT FOR STG AREA (PLAN VIEW) | IFR | 2016-10-30 | 2017-05-04 | O | O | O |  | 2016-11-03 | 2017-05-10
GA(10) | General | 100009 | T16182-UE00-P0UMA-100009 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION A - A) | IFR | 2016-10-30 | 2017-05-04 |  | O | O |  | 2016-11-03 | 2017-05-10
GA(10) | General | 100010 | T16182-UE00-P0UMA-100010 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION B - B) | IFR | 2016-10-30 | 2017-05-04 |  | O | O |  | 2016-11-03 | 2017-05-10
PS(11) | Mechanical | 110001 | T16182-XG05-P0ZEN-110001 | HEAT BALANCE DIAGRAMS | IFR | 2016-12-14 | 2017-04-25 | O | O |  |  | 2016-12-15 | 2017-05-10
PS(11) | Mechanical | 110002 | T16182-XG02-P0ZEN-110002 | P&I DIAGRAM FOR SYMBOL AND LEGEND | IFR | 2016-10-28 | 2017-03-27 |  | O | O |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110003 | T16182-XG02-P0LBA-110003 | P&I DIAGRAM FOR HP STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O |  | 2016-11-03 | 2017-05-24
PS(11) | Mechanical | 110004 | T16182-XG02-P0LBC-110004 | P&I DIAGRAM FOR IP STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O |  | 2016-11-03 | 2017-05-24
PS(11) | Mechanical | 110005 | T16182-XG02-P0LBG-110005 | P&I DIAGRAM FOR LP STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O |  | 2016-11-03 | 2017-05-24
PS(11) | Mechanical | 110006 | T16182-XG02-P0LBS-110006 | P&I DIAGRAM FOR PROCESS STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O |  | 2016-11-03 | 2017-05-24
PS(11) | Mechanical | 110007 | T16182-XG02-P6LCM-110007 | P&I DIAGRAM FOR STEAM DRAIN SYSTEM | IFR | 2016-10-28 | 2017-04-28 |  | O | O |  | 2016-11-03 | 2017-05-24
PS(11) | Mechanical | 110008 | T16182-XG02-P6LCA-110008 | P&I DIAGRAM FOR CONDENSATE SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110009 | T16182-XG02-P0LAA-110009 | P&I DIAGRAM FOR FEEDWATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O |  | O |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110010 | T16182-XG02-P0PGB-110010 | P&I DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O | O | O |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110011 | T16182-XG02-P0GHC-110011 | P&I DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O | O |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110012 | T16182-XG02-P0QJA-110012 | P&I DIAGRAM FOR NITROGEN GAS SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O | O | PKG-006-N2 | 2016-11-03 | 2017-04-12
PT(12) | Mechanical | 110013 | T16182-XG02-P1MBH-110013 | GTG - P&I DIAGRAM FOR GT ROTOR COOLING AIR COOLER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O | PKG-011-GTG | 2016-11-03 | 2017-06-16
PS(11) | Mechanical | 110014 | T16182-XG02-P1EKC-110014 | P&I DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110031 | T16182-XG07-P0LA-110031 | PROCESS FLOW DIAGRAM FOR STEAM/CONDENSATE/FW SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  |  |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110032 | T16182-XG07-P0PG-110032 | PROCESS FLOW DIAGRAM FOR CCW SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  |  |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110033 | T16182-XG07-P0GHC-110033 | PROCESS FLOW DIAGRAM FOR DM WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  |  |  | 2016-11-03 | 2017-04-04
PS(11) | Mechanical | 110035 | T16182-XW01-P0LB-110035 | DESIGN CRITERIA FOR STEAM AND BYPASS SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O |  |  | 2016-11-03 | 2017-04-24
PS(11) | Mechanical | 110036 | T16182-XW01-P0LC-110036 | DESIGN CRITERIA FOR CONDENSATE SYSTEM | IFR | 2016-10-28 | 2017-04-28 |  |  |  |  | 2016-11-03 | 2017-04-29
PS(11) | Mechanical | 110037 | T16182-XW01-P0LA-110037 | DESIGN CRITERIA FOR FEEDWATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  |  |  | 2016-11-03 | 2017-04-05
PS(11) | Mechanical | 110038 | T16182-XW01-P0PGB-110038 | DESIGN CRITERIA FOR CLOSED COOLING WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O |  |  | 2016-11-03 | 2017-04-05
PS(11) | Mechanical | 110039 | T16182-XW01-P0GHC-110039 | DESIGN CRITERIA FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O |  |  | 2016-11-03 | 2017-04-05
PS(11) | Mechanical | 110040 | T16182-XS00-P0LB-110040 | SYSTEM DESCRIPTION FOR STEAM AND BYPASS SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O | O | O |  | 2016-11-03 | 2017-04-29
PS(11) | Mechanical | 110041 | T16182-XS00-P0LC-110041 | SYSTEM DESCRIPTION FOR CONDENSATE SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O |  | 2016-11-03 | 2017-04-14
PS(11) | Mechanical | 110042 | T16182-XS00-P0LA-110042 | SYSTEM DESCRIPTION FOR FEEDWATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O |  | O |  | 2016-11-03 | 2017-04-12
PS(11) | Mechanical | 110043 | T16182-XS00-P0PGB-110043 | SYSTEM DESCRIPTION FOR CLOSED COOLING WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O | O | O |  | 2016-11-03 | 2017-04-12
PS(11) | Mechanical | 110044 | T16182-XS00-P0GHC-110044 | SYSTEM DESCRIPTION FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O | O |  | 2016-11-03 | 2017-04-12
PS(11) | Mechanical | 110045 | T16182-XW03-P0LB-110045 | PRESSURE LOSS CALCULATIONS FOR MAIN STEAM SYSTEM | IFR | 2017-01-19 | 2017-06-11 |  |  |  |  | 2017-02-14 | 2017-04-17
PS(11) | Mechanical | 110046 | T16182-XW03-P0LC-110046 | SIZING CALCULATION FOR CONDENSATE EXTRACTION PUMP | IFR | 2017-03-01 | 2017-07-29 |  |  |  |  | 2017-02-28 | 2017-07-17
PS(11) | Mechanical | 110047 | T16182-XW03-P0LC-110047 | SIZING CALCULATION FOR FGP CONDENSATE PUMP | IFR | 2017-03-01 | 2017-07-29 |  |  |  |  | 2017-02-28 | 2017-07-17
PS(11) | Mechanical | 110048 | T16182-XW03-P0LA-110048 | SIZING CALCULATION FOR HRSG FEEDWATER PUMP | IFR | 2017-01-19 | 2017-04-12 |  |  |  |  | 2017-01-11 | 2017-04-14
PS(11) | Mechanical | 110049 | T16182-XW03-P0LA-110049 | SIZING CALCULATION FOR FGP FEEDWATER PUMP | IFR | 2017-01-19 | 2017-04-12 |  |  |  |  | 2017-01-11 | 2017-04-14
PS(11) | Mechanical | 110050 | T16182-XW03-P0PGB-110050 | SIZING CALCULATION FOR CLOSED COOLING WATER SYSTEM | IFR | 2017-02-28 | 2017-07-28 |  | O |  |  | 2017-02-28 | 2017-07-13
PS(11) | Mechanical | 110051 | T16182-XW03-P0GHC-110051 | SIZING CALCULATION FOR CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP | IFR | 2017-02-28 | 2017-07-28 |  | O |  |  | 2017-02-28 | 2017-07-13
PS(11) | Mechanical | 110052 | T16182-XW03-P0QJA-110052 | SIZING CALCULATION FOR NITROGEN GAS SYSTEM | IFR | 2017-03-31 | 2017-06-30 |  | O |  | PKG-006-N2 | 2017-04-05 | 2017-05-29
PS(11) | Mechanical | 110053 | T16182-XW03-P0MJ-110053 | BSEDG - CALCULATION | IFR | 2017-02-28 | 2017-05-29 |  | O |  | PKG-007-BSDG | 2017-03-08 | 2017-06-05
PS(11) | Mechanical | 110061 | T16182-XW03-P0LA-110061 | HRSG/FGP FEEDWATER PUMP NPSH TRANSIENT ANALYSIS | IFI | 2017-07-20 | [5 empty] | 2017-07-14 | #VALUE!
PS(11) | Mechanical | 110101 | T16182-YT01-P0LF-110101 | DATA SHEET FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | IFI | 2017-05-31 |  |  |  |  | PKG-001-SRV | 2017-06-29 | #VALUE!
PS(11) | Mechanical | 110102 | T16182-YK08-P0LF-110102 | OUTLINE DRAWING FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | IFI | 2017-05-31 | 2017-07-30 |  |  |  | PKG-001-SRV | 2017-06-29 | 2017-08-21
PS(11) | Mechanical | 110153 | T16182-YT01-P0MAN-110153 | DATA SHEET FOR BYPASS AND PRDS | IFI | 2017-06-30 |  |  |  |  | PKG-002-PRDS | 2017-09-21 | #VALUE!
PS(11) | Mechanical | 110154 | T16182-YK08-P0MAN-110154 | OUTLINE DRAWING FOR BYPASS AND PRDS | IFI | 2017-06-30 | 2017-08-29 |  |  |  | PKG-002-PRDS | 2017-09-21 | 2018-01-04
PS(11) | Mechanical | 110201 | T16182-YR01-P0ZEN-110201 | STEAM BLOWING - OUT PROCEDURE | IFR | 2017-06-30 | 2017-09-18 |  |  |  |  | 2017-11-02 | 2018-01-10
PS(11) | Mechanical | 110251 | T16182-YT01-P0LBG-110251 | DATA SHEET FOR SILENCER | IFI | 2017-07-31 |  |  |  |  | PKG-003-SILENCER | 2017-09-21 | #VALUE!
PS(11) | Mechanical | 110252 | T16182-YK08-P0LBG-110252 | OUTLINE DRAWING FOR SILENCER | IFI | 2017-07-31 | 2017-09-29 |  |  |  | PKG-003-SILENCER | 2017-09-21 | 2017-11-09
PS(11) | Mechanical | 110301 | T16182-YT01-P0LCP-110301 | DATA SHEET FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | IFR | 2017-05-15 | 2017-09-14 |  |  |  | PKG-004-PHE | 2017-05-17 | 2017-06-14
PS(11) | Mechanical | 110302 | T16182-YD00-P0LCP-110302 | OUTLINE DRAWING FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | IFR | 2017-05-15 | 2017-09-14 |  |  |  | PKG-004-PHE | 2017-05-17 | 2017-06-14
PS(11) | Mechanical | 110401 | T16182-YD00-P0PGB-110401 | GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | IFR | 2017-04-30 | 2017-07-28 |  | O |  | PKG-005-CCWP | 2017-05-02 | 2017-06-13
PS(11) | Mechanical | 110402 | T16182-YL22-P0PGB-110402 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP | 2017-05-02 | #VALUE!
PS(11) | Mechanical | 110403 | T16182-YT01-P0PGB-110403 | DATA SHEET FOR CLOSED COOLING WATER PUMP | IFR | 2017-04-30 | 2017-07-28 |  | O |  | PKG-005-CCWP | 2017-05-02 | 2017-06-13
PS(11) | Electrical | 110404 | T16182-YD00-P0PGB-110404 | OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP | 2017-05-02 | #VALUE!
PS(11) | Electrical | 110405 | T16182-YD00-P0PGB-110405 | MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP | 2017-05-02 | #VALUE!
PS(11) | Electrical | 110406 | T16182-YL22-P0PGB-110406 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP | 2017-05-15 | #VALUE!
PS(11) | Electrical | 110407 | T16182-YT01-P0PGB-110407 | DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP | 2017-05-02 | #VALUE!
PS(11) | Mechanical | 110500 | T16182-XS00-P0QJA-110500 | SYSTEM DESCRIPTION FOR NITROGEN GAS SYSTEM | IFR | 2017-06-15 | 2017-08-30 |  | O |  | PKG-006-N2 | 2017-07-18 | 2017-09-29
PS(11) | Mechanical | 110501 | T16182-YK08-P0QJA-110501 | EQUIPMENT ASSEMBLY AND DETAIL DRAWING FOR NITROGEN GAS SYSTEM | IFI | 2017-06-15 | 2017-08-14 |  | O |  | PKG-006-N2 | 2017-07-18 | 2017-09-29
PS(11) | Mechanical | 110502 | T16182-YD00-P0QJA-110502 | GENERAL ARRANGEMENT DRAWING FOR NITROGEN GAS SYSTEM | IFR | 2017-06-15 | 2017-07-31 |  | O |  | PKG-006-N2 | 2017-07-18 | 2017-09-29
PS(11) | Mechanical | 110503 | T16182-YT01-P0QJA-110503 | DATA SHEET FOR NITROGEN GAS SYSTEM | IFR | 2017-06-15 | 2017-08-30 |  | O |  | PKG-006-N2 | 2017-07-18 | 2017-09-29
PS(11) | Mechanical | 110504 | T16182-YD00-P0MJ-110504 | BSEDG - GENERAL ARRANGEMENT DRAWING | IFR | 2017-04-30 | 2017-07-31 | O | O |  | PKG-007-BSDG | 2017-05-11 | 2017-07-27
PS(11) | Mechanical | 110505 | T16182-XG02-P0MJ-110505 | BSEDG - P&I DIAGRAM | IFR | 2017-04-30 | 2017-07-31 | O | O |  | PKG-007-BSDG | 2017-05-11 | 2017-07-28
PS(11) | Mechanical | 110506 | T16182-YK08-P0MJ-110506 | BSEDG - OUTLINE DRAWING | IFR | 2017-04-30 | 2017-07-31 |  | O |  | PKG-007-BSDG | 2017-05-11 | 2017-07-28
PS(11) | Electrical | 110507 | T16182-YU02-P0MJ-110507 | BSEDG - SINGLE LINE DIAGRAM | IFI | 2017-04-30 |  |  | O |  | PKG-007-BSDG | 2017-05-19 | #VALUE!
PS(11) | Mechanical | 110508 | T16182-YT01-P0MJ-110508 | BSEDG - DATA SHEET | IFR | 2017-04-30 | 2017-07-31 |  | O |  | PKG-007-BSDG | 2017-05-11 | 2017-07-28
PS(11) | Mechanical | 110509 | T16182-XG01-P0MJ-110509 | BSEDG - PIPING ISOMETRIC DRAWING | IFI | 2017-04-30 | 2017-06-30 |  | O |  | PKG-007-BSDG | 2017-05-17 | 2017-07-27
PS(11) | Mechanical | 110510 | T16182-XS00-P0MJ-110510 | BSEDG - SYSTEM DESCRIPTION | IFR | 2017-05-15 | 2017-08-17 | O | O |  | PKG-007-BSDG | 2017-06-30 | 2017-07-28
PS(11) | Instrumentation & Control | 110511 | T16182-YF00-P0MJ-110511 | BSEDG - CONTROL LOGIC DIAGRAM | IFR | 2017-05-15 | 2017-08-17 |  |  |  | PKG-007-BSDG | 2017-05-19 | 2017-09-29
PS(11) | Electrical | 110512 | T16182-YE00-P0MJ-110512 | BSEDG - EMBEDDED CONDUIT LAYOUT | IFI | 2017-06-30 | 2017-10-11 |  | O |  | PKG-007-BSDG | 2017-07-04 | 2017-07-27
PS(11) | Electrical | 110561 | T16182-YM02-P0MJ-110561 | BSEDG - CONTROL PANEL OUTLINE DRAWING | IFI | 2018-06-12 |  |  |  |  | PKG-007-BSDG | 2018-06-14 | #VALUE!
PS(11) | Electrical | 110564 | T16182-XG11-P0MJ-110564 | BSEDG - SCHEMATIC DIAGRAM | IFI | 2018-06-12 |  |  |  |  | PKG-007-BSDG | 2018-06-14 | #VALUE!
PS(11) | Electrical | 110568 | T16182-YT10-P0MJ-110568 | BSEDG - PROTECTION RELAY SETTING REPORT | IFI | 2018-06-12 |  |  |  |  | PKG-007-BSDG | 2018-06-14 | #VALUE!
PS(11) | Electrical | 110578 | T16182-YM02-P0MJ-110578 | BSEDG – MV SWGR DRAWING | IFI | 2018-06-21 |  |  |  |  | PKG-007-BSDG | 2018-06-21 | #VALUE!
PS(11) | Mechanical | 110601 | T16182-YT01-P0LF-110601 | VALVE LIST & DATA SHEET FOR MOV (G&G) | IFR | 2017-04-17 | 2017-09-14 |  | O |  | PKG-009-MOVG | 2017-05-02 | 2017-12-05
PS(11) | Mechanical | 110602 | T16182-YK10-P0LF-110602 | OUTLINE DRAWING FOR MOV (G&G) | IFR | 2017-04-17 | 2017-09-14 |  | O |  | PKG-009-MOVG | 2017-05-02 | 2017-12-05
PS(11) | Mechanical | 110603 | T16182-YT01-P0LF-110603 | VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | IFR | 2017-04-30 | 2017-09-14 |  | O |  | PKG-010-MOVB | 2017-05-02 | 2017-07-27
PS(11) | Mechanical | 110604 | T16182-YK10-P0LF-110604 | OUTLINE DRAWING FOR MOV (BUTTERFLY) | IFR | 2017-04-30 | 2017-09-14 |  | O |  | PKG-010-MOVB | 2017-05-02 | 2017-07-27
PS(11) | General | 110701 | T16182-CN00-P0ZEN-110701 | OPERATION PHILOSOPHY OF OVERALL PLANT | IFR | 2017-04-15 | 2017-07-03 |  |  |  |  | 2017-04-28 | 2017-07-07
PS(11) | General | 110702 | T16182-CN00-P0ZEN-110702 | PLANT START-UP AND SHUT-DOWN PROCEDURE | IFR | 2017-04-15 | 2017-07-03 |  |  |  |  | 2017-06-30 | 2017-12-05
PS(11) | General | 110703 | T16182-CN00-P0ZEN-110703 | HAZARD AND OPERABILITY STUDY | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-08-21 | 2017-09-05
PS(11) | General | 110704 | T16182-CN00-P0ZEN-110704 | SAFETY INTEGRITY LEVEL STUDY | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-08-21 | 2017-09-05
PS(11) | General | 110705 | T16182-CN00-P0ZEN-110705 | HAZARDOUS AREA CLASSIFICATION REPORT | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-08-29 | 2017-12-13
PS(11) | General | 110706 | T16182-CN00-P0ZEN-110706 | HAZOP AND SIL STUDY PROCEDURE | IFI | 2017-03-06 |  |  | O | O |  | 2017-03-24 | #VALUE!
PT(12) | Mechanical | 120001 | T16182-XG02-P0GKB-120001 | P&I DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O |  | 2016-11-03 | 2017-04-07
PT(12) | Mechanical | 120002 | T16182-XG02-P0GKC-120002 | P&I DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O |  | 2016-11-03 | 2017-04-07
PT(12) | Mechanical | 120004 | T16182-XG02-P0SCA-120004 | P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O |  | 2016-11-03 | 2017-06-05
PT(12) | Mechanical | 120005 | T16182-XG02-P0SCA-120005 | P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O |  | 2016-11-03 | 2017-04-03
PT(12) | Mechanical | 120006 | T16182-XG02-P0SCA-120006 | P&I DIAGRAM FOR SERVICE AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O |  | 2016-11-03 | 2017-04-03
PT(12) | Mechanical | 120007 | T16182-XG02-P0EK-120007 | P&I DIAGRAM FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O | O | PKG-014-FGS | 2016-11-03 | 2017-05-29
PT(12) | Mechanical | 120008 | T16182-XG02-P0GM-120008 | P&I DIAGRAM FOR WASTE WATER TRANSFER SYSTEM | IFR | 2017-05-30 | 2017-08-28 |  |  | O |  | 2017-05-31 | 2017-09-05
PT(12) | Mechanical | 120012 | T16182-XS00-P0GKS-120012 | DESIGN CRITERIA FOR POTABLE WATER SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O |  |  | 2016-11-03 | 2017-03-31
PT(12) | Mechanical | 120013 | T16182-XW03-P0GKS-120013 | SIZING CALCULATION - POTABLE WATER DISTRIBUTION PUMP | IFR | 2017-01-30 | 2017-04-30 |  | O |  |  | 2017-02-17 | 2017-06-19
PT(12) | Mechanical | 120014 | T16182-XG07-P0SCA-120014 | PROCESS FLOW DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O |  |  | 2016-11-03 | 2017-05-29
PT(12) | Mechanical | 120015 | T16182-XS00-P0SCA-120015 | SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O | O |  | 2016-11-03 | 2017-05-29
PT(12) | Mechanical | 120016 | T16182-XS00-P0SCA-120016 | DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O |  |  | 2016-11-03 | 2017-05-29
PT(12) | Mechanical | 120017 | T16182-XW03-P0SCA-120017 | SIZING CALCULATION - COMPRESSED AIR SYSTEM | IFR | 2017-02-10 | 2017-05-31 |  | O |  |  | 2017-02-24 | 2017-06-09
PT(12) | Mechanical | 120018 | T16182-XG07-P0EKG-120018 | PROCESS FLOW DIAGRAM FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O |  | PKG-014-FGS | 2016-11-03 | 2017-05-29
PT(12) | Mechanical | 120019 | T16182-XS00-P0EKG-120019 | SYSTEM DESCRIPTION FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O | O | PKG-014-FGS | 2016-11-03 | 2017-07-03
PT(12) | Mechanical | 120020 | T16182-XS00-P0EKG-120020 | DESIGN CRITERIA FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O |  | PKG-014-FGS | 2016-11-03 | 2017-11-15
PT(12) | Mechanical | 120021 | T16182-XW03-P0EKG-120021 | SIZING CALCULATION - FUEL GAS SYSTEM | IFR | 2017-02-28 | 2017-05-31 |  | O |  | PKG-014-FGS | 2017-03-28 | 2017-09-01
PT(12) | Mechanical | 120022 | T16182-XS00-P0GM-120022 | SYSTEM DESCRIPTION FOR WASTE WATER TRANSFER SYSTEM | IFR | 2017-05-30 | 2017-08-28 |  |  | O |  | 2017-05-31 | 2017-09-18
PT(12) | Mechanical | 120023 | T16182-XS00-P0GM-120023 | DESIGN CRITERIA FOR WASTE WATER TRANSFER SYSTEM | IFR | 2017-05-30 | 2017-08-28 |  |  |  |  | 2017-05-31 | 2017-09-18
PT(12) | Mechanical | 120050 | T16182-XG07-P0ZEN-120050 | WATER BALANCE DIAGRAM | IFR | 2017-01-30 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-04-14
PT(12) | Mechanical | 120051 | T16182-XS00-P0GKS-120051 | SYSTEM DESCRIPTION FOR POTABLE WATER SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O |  | 2016-11-03 | 2017-03-31
PT(12) | Mechanical | 121001 | T16182-YD00-P0MBA-121001 | GTG - EQUIPMENT ARRANGEMENT | IFR | 2017-03-15 | 2017-05-29 | O |  |  | PKG-011-GTG | 2017-02-14 | 2017-04-29
PT(12) | Mechanical | 121002 | T16182-YL25-P0MBA-121002 | GTG - GT EXHAUST MECHANICAL INTERFACE REQUIREMENTS | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG | 2017-03-16 | #VALUE!
PT(12) | Mechanical | 121003 | T16182-XG02-P0MBA-121003 | GTG - P&I DIAGRAM | IFR | 2017-04-04 | 2017-06-18 | O |  | O | PKG-011-GTG | 2017-04-04 | 2017-06-12
PT(12) | Mechanical | 121004 | T16182-XW01-P0MBA-121004 | GTG - ROTOR COOLING AIR SYSTEM REQUIREMENTS | IFI | 2017-03-30 |  |  |  |  | PKG-011-GTG | 2017-03-31 | #VALUE!
PT(12) | Electrical | 121005 | T16182-XW01-P0MBA-121005 | GTG - GOVERNOR AND TURBINE MODEL | IFI | 2017-04-04 |  |  |  |  | PKG-011-GTG | 2017-04-04 | #VALUE!
PT(12) | Electrical | 121006 | T16182-XW01-P0MBA-121006 | GTG - GENERATOR, EXCITATION SYSTEM, AND POWER SYSTEM STABILIZER MODEL | IFI | 2017-04-04 |  |  |  |  | PKG-011-GTG | 2017-04-04 | #VALUE!
PT(12) | Civil | 121007 | T16182-XB00-P0MBA-121007 | GTG - AUXILIARY EQUIPMENT FOUNDATION INTERFACE DRAWINGS | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG | 2017-04-14 | #VALUE!
PT(12) | Mechanical | 121008 | T16182-XJ00-P0MBA-121008 | GTG - CUSTOMER PIPING CONNECTIONS PHYSICAL AND PROCESS DATA | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG | 2017-04-14 | #VALUE!
PT(12) | Mechanical | 121009 | T16182-YK08-P0MBA-121009 | GTG - INLET FILTER AND DUCT SUPPLIER DRAWINGS | IFI | 2017-06-13 | 2017-10-13 |  |  |  | PKG-011-GTG | 2017-06-12 | 2017-09-27
PT(12) | General | 121010 | T16182-DM02-P0MBA-121010 | GTG_STG-PAC INSTRUCTION BOOK VOLUME I (GAS TURBINE AND AUXILIARIES | IFI | 2018-10-06 |  | O |  |  | PKG-011-GTG | 2019-02-18 | #VALUE!
PT(12) | General | 121011 | T16182-XS00-P0MBA-121011 | GTG - SYSTEM DESCRIPTION | IFR | 2017-02-13 | 2017-04-29 | O |  | O | PKG-011-GTG | 2017-02-13 | 2017-06-07
PT(12) | Electrical | 121012 | T16182-YU02-P0MBA-121012 | GTG - GENERATOR/MEDIUM VOLTAGE SINGLE LINE DIAGRAM | IFI | 2017-02-28 |  |  |  |  | PKG-011-GTG | 2017-02-28 | #VALUE!
PT(12) | Electrical | 121013 | T16182-YT01-P0MBA-121013 | GTG - GENERATOR CAPABILITY CURVES AND DATA | IFI | 2017-02-28 |  |  |  |  | PKG-011-GTG | 2017-02-28 | #VALUE!
PT(12) | Electrical | 121014 | T16182-YL25-P0MBA-121014 | GTG - GENERATOR ISOPHASE BUS INTERFACE | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG | 2017-03-16 | #VALUE!
PT(12) | Electrical | 121015 | T16182-XW01-P0MBA-121015 | GTG - DESIGN REQUIREMENTS FOR VT & SURGE, BAB36 | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG | 2017-03-16 | #VALUE!
PT(12) | Electrical | 121016 | T16182-YL06-P0MBA-121016 | GTG - ELECTRICAL LOAD LIST | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG | 2017-04-14 | #VALUE!
PT(12) | Electrical | 121017 | T16182-YU05-P0MBA-121017 | GTG - THREE - LINE SCHEMATICS | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG | 2017-04-14 | #VALUE!
PT(12) | Electrical | 121018 | T16182-YU02-P0MBA-121018 | GTG - MCC & 125VDC SINGLE LINE DIAGRAM | IFI | 2017-05-09 |  |  |  |  | PKG-011-GTG | 2017-05-11 | #VALUE!
PT(12) | Electrical | 121019 | T16182-YB03-P0MBA-121019 | GTG - CUSTOMER ELECTRICAL CONNECTIONS | IFI | 2017-05-09 |  |  |  |  | PKG-011-GTG | 2017-05-11 | #VALUE!
PT(12) | Electrical | 121020 | T16182-YS00-P0MBA-121020 | GTG - ELECTRICAL SCHEMATICS | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG | 2018-02-12 | #VALUE!
PT(12) | Electrical | 121021 | T16182-YD02-P0MBA-121021 | GTG - ABOVE - GRADE FIELD CONDUIT PLAN | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG | 2018-02-12 | #VALUE!
PT(12) | Electrical | 121022 | T16182-YL01-P0MBA-121022 | GTG - CABLE AND CONDUIT LIST | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG | 2018-02-12 | #VALUE!
PT(12) | Electrical | 121023 | T16182-YT01-P0MBA-121023 | GTG_ELECTRICAL PROTECTION AND OPERATION SETTINGS | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG | 2018-02-23 | #VALUE!
PT(12) | Instrumentation & Control | 121024 | T16182-YL25-P0MBA-121024 | GTG - DCS SIGNAL INTERFACE INFORMATION | IFI | 2017-02-28 |  |  |  |  | PKG-011-GTG | 2017-02-28 | #VALUE!
PT(12) | Instrumentation & Control | 121025 | T16182-YL01-P0MBA-121025 | GTG - INSTRUMENT, VALVE AND CONTROL SETTINGS LIST | IFI | 2017-12-10 |  |  |  |  | PKG-011-GTG | 2017-12-11 | #VALUE!
PT(12) | Instrumentation & Control | 121026 | T16182-XS01-P0MBA-121026 | GTG - CONTROL PHILOSOPHY | IFI | 2018-08-15 |  |  |  |  | PKG-011-GTG | 2018-12-10 | #VALUE!
PT(12) | Instrumentation & Control | 121027 | T16182-XS01-P0MBA-121027 | GTG - CONTROL SYSTEM DESCRIPTION | IFI | 2018-08-15 |  |  |  |  | PKG-011-GTG | 2018-12-10 | #VALUE!
PT(12) | Instrumentation & Control | 121028 | T16182-YL01-P0MBA-121028 | GTG - CONTROL SYSTEM INPUT/OUTPUT DATABASE (I/O DATABASE) | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG | 2017-04-14 | #VALUE!
PT(12) | Instrumentation & Control | 121029 | T16182-YS00-P0MBA-121029 | GTG - POWER SUPPLY DISTRIBUTION DRAWING | IFI | 2017-03-11 |  |  |  |  | PKG-011-GTG | 2017-03-13 | #VALUE!
PT(12) | Instrumentation & Control | 121030 | T16182-YT01-P0MBA-121030 | GTG - DATA SHEETS FOR I&C EQUIPMENT | IFI | 2017-04-08 |  |  |  |  | PKG-011-GTG | 2017-04-07 | #VALUE!
PT(12) | Instrumentation & Control | 121031 | T16182-YR05-P0MBA-121031 | GTG - CABINET / PANEL TERMINAL BLOCK DETAILS | IFI | 2017-04-08 |  |  |  |  | PKG-011-GTG | 2017-04-07 | #VALUE!
PT(12) | Instrumentation & Control | 121032 | T16182-YD05-P0MBA-121032 | GTG - HMI GRAPHIC | IFI | 2018-08-15 |  |  |  |  | PKG-011-GTG | 2018-12-12 | #VALUE!
PT(12) | Instrumentation & Control | 121033 | T16182-XS01-P0MBA-121033 | GTG - CONTROL SYSTEM OVERVIEW | IFI | 2017-02-13 |  |  |  |  | PKG-011-GTG | 2017-02-16 | #VALUE!
PT(12) | Civil | 121034 | T16182-XS01-P0MBA-121034 | GTG - FOUNDATION DESIGN BASIS DOCUMENT | IFI | 2017-03-28 |  |  |  |  | PKG-011-GTG | 2017-03-28 | #VALUE!
PT(12) | Civil | 121035 | T16182-XS01-P0MBA-121035 | GTG - POWER BLOCK FOUNDATION GENERAL NOTES | IFI | 2017-03-28 |  |  |  |  | PKG-011-GTG | 2017-03-28 | #VALUE!
PT(12) | Electrical | 121036 | T16182-YQ03-P0CY-121036 | GTG – ELECTRICAL PACKAGE COMMUNICATION LAYOUT DRAWING | IFI | 2018-12-03 |  |  |  |  | PKG-011-GTG | 2018-12-04 | #VALUE!
PT(12) | Electrical | 121037 | T16182-XW01-P0MBA-121037 | GTG - PSS STUDY REPORT_DRAFT | IFR | 2019-01-16 | 2019-04-30 |  |  |  | PKG-011-GTG | 2019-01-16 | 2020-02-17
PT(12) | General | 121038 | T16182-DM02-P0MBA-121038 | GTG_STG-PAC INSTRUCTION BOOK VOLUME II (GENERATOR AND AUXILIARIES) | IFI | 2019-02-18 |  |  |  |  | PKG-011-GTG | 2019-02-18 | #VALUE!
PT(12) | Mechanical | 121044 | T16182-VN01-P0MBA-121044 | GTG - ACCESS PLATFORM LAYOUT | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG | 2017-03-16 | #VALUE!
PT(12) | Mechanical | 121051 | T16182-CQ02-P0MBA-121051 | GTG_GAS TURBINE AND AUXILIARIES INSTALLATION MANUAL | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG | 2018-07-27 | #VALUE!
PT(12) | Mechanical | 121073 | T16182-CQ02-P0MBA-121073 | GTG_GAS TURBINE AND AUXILIARIES COMMISSIOINING MANUAL | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG | 2018-07-27 | #VALUE!
PT(12) | General | 121076 | T16182-CQ02-P0MBA-121076 | GTG_INSTALLATION MANUAL | IFI | 2018-02-28 |  |  |  |  | PKG-011-GTG | 2018-02-02 | #VALUE!
PT(12) | General | 121077 | T16182-CQ02-P0MBA-121077 | GTG_GENERATOR REMOVAL PROCEDURE | IFI | 2019-06-25 | [5 empty] | 2019-06-26 | #VALUE!
PT(12) |  | 121099 | T16182-CQ02-P0MBA-121099 | GTG ERECTION DRAWING PACKAGE | Internal | [6 empty] | 2017-11-29 | #VALUE!
PT(12) | Mechanical | 121100 | T16182-XG02-P0GM-121100 | GTG – DRAIN INTERFACE FLOW DIAGRAM | IFI | 2018-12-03 |  |  |  |  | PKG-011-GTG | 2018-12-03 | #VALUE!
PT(12) | Instrumentation & Control | 121555 | T16182-YT01-P0MBA-121555 | GTG_CONDUIT LAYOUT DRAWING | IFI | 2017-09-22 | 2017-12-22 |  |  |  | PKG-011-GTG | 2017-09-07 | 2017-09-08
PT(12) | Mechanical | 121677 | T16182-YT01-P0MBA-121677 | GTG_GAS TURBINE GENERATOR COMMISSIOINING MANUAL | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG | 2018-07-27 | #VALUE!
PT(12) | Instrumentation & Control | 121678 | T16182-YS00-P0MBA-121678 | GTG_I&C SCHEMATICS | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG | 2018-08-09 | #VALUE!
PT(12) | Mechanical | 121824 | T16182-YT01-P0MBA-121824 | GTG_FIRE PROTECTION SYSTEM DRAWING | IFI | 2018-04-30 |  |  |  |  | PKG-011-GTG | 2018-04-05 | #VALUE!
PT(12) | Electrical | 121971 | T16182-YT01-P0MBA-121971 | GTG – SFC / SEE CIRCUIT DIAGRAM | IFI | 2018-09-10 |  |  |  |  | PKG-011-GTG | 2018-09-10 | #VALUE!
PT(12) | Mechanical | 122001 | T16182-CQ02-P0LB-122001 | HRSG - INSTALLATION AND INSTRUCTION MANUAL | IFI | 2019-09-05 |  |  |  |  | PKG-012-HRSG | 2019-09-02 | #VALUE!
PT(12) | Mechanical | 122003 | T16182-DF04-P0LB-122003 | HRSG - STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | IFI | 2017-03-18 |  |  |  |  | PKG-012-HRSG | 2017-03-31 | #VALUE!
PT(12) | Mechanical | 122004 | T16182-DF04-P0LB-122004 | HRSG - CFD REPORT FOR INLET DUCT | IFI | 2017-04-30 |  |  |  |  | PKG-012-HRSG | 2017-04-19 | #VALUE!
PT(12) | Mechanical | 122005 | T16182-DF04-P0LB-122005 | HRSG - CFD REPORT FOR DUCT BURNER SYSTEM | IFI | 2017-07-15 |  |  |  |  | PKG-012-HRSG | 2017-07-13 | #VALUE!
PT(12) | Mechanical | 122006 | T16182-YD00-P0LB-122006 | HRSG - SPEC. & DRAWING FOR HOIST | IFI | 2018-01-01 | 2018-02-02 |  |  |  | PKG-012-HRSG | 2017-12-12 | 2018-01-23
PT(12) | Mechanical | 122007 | T16182-UE00-P0LB-122007 | HRSG - GENERAL ARRANGEMENT | IFR | 2017-01-31 | 2017-05-01 | O |  |  | PKG-012-HRSG | 2017-01-06 | 2017-05-24
PT(12) | Mechanical | 122008 | T16182-UE00-P0LB-122008 | HRSG - ARRANGEMENT OF CASING & FIELD ERECTION | IFR | 2017-04-30 | 2017-07-29 |  |  |  | PKG-012-HRSG | 2017-04-24 | 2017-08-29
PT(12) | Mechanical | 122009 | T16182-UE00-P0LB-122009 | HRSG - ARRANGEMENT OF INLET DUCT | IFR | 2017-04-30 | 2017-07-29 |  |  |  | PKG-012-HRSG | 2017-04-24 | 2017-08-30
PT(12) | Mechanical | 122010 | T16182-UE00-P0LB-122010 | HRSG - ARRANGEMENT OF MAIN STACK& FIELD ERECTION | IFR | 2017-04-30 | 2017-07-29 |  |  |  | PKG-012-HRSG | 2017-04-24 | 2017-08-30
PT(12) | Mechanical | 122011 | T16182-UE00-P0LB-122011 | HRSG - GENERAL ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-012-HRSG | 2017-07-13 | 2017-12-19
PT(12) | Mechanical | 122012 | T16182-UE00-P0LB-122012 | HRSG - DETAIL ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-012-HRSG | 2017-07-13 | 2017-12-08
PT(12) | Mechanical | 122013 | T16182-UE00-P0LB-122013 | HRSG - FUEL GAS SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-012-HRSG | 2017-05-23 | 2017-11-07
PT(12) | Mechanical | 122014 | T16182-UE00-P0LB-122014 | HRSG - COOLING AIR SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-08-15 | 2017-11-13 |  |  |  | PKG-012-HRSG | 2017-05-23 | 2017-11-07
PT(12) | Structural & Architectural | 122015 | T16182-VN03-P0LB-122015 | HRSG - ARRANGEMENT FOR PLATFORM STRUCTURE | IFI | 2017-05-31 | 2017-10-28 |  |  |  | PKG-012-HRSG | 2017-05-11 | 2017-10-13
PT(12) | Civil | 122016 | T16182-XB02-P0LB-122016 | HRSG - COLUMN LOCATION FOR STEEL STRUCTURE AND STACK | IFI | 2017-02-28 | 2017-08-31 |  |  |  | PKG-012-HRSG | 2017-01-05 | 2017-09-07
PT(12) | Civil | 122017 | T16182-XB02-P0LB-122017 | HRSG - FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | IFI | 2017-02-28 | 2017-06-29 |  |  |  | PKG-012-HRSG | 2017-01-05 | 2017-06-29
PT(12) | Civil | 122018 | T16182-XB02-P0LB-122018 | HRSG - BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | IFI | 2017-02-28 | 2017-08-31 |  |  |  | PKG-012-HRSG | 2017-02-28 | 2017-06-15
PT(12) | Civil | 122019 | T16182-XB02-P0LB-122019 | HRSG - ANCHOR BOLT & TEMPLATE DETAIL FOR STACK | IFI | 2017-02-28 | 2017-08-31 |  |  |  | PKG-012-HRSG | 2017-02-28 | 2017-06-29
PT(12) | Mechanical | 122020 | T16182-XB02-P0LB-122020 | HRSG - FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | IFI | 2017-04-30 | 2017-10-30 |  |  |  | PKG-012-HRSG | 2017-04-24 | 2017-11-07
PT(12) | Mechanical | 122021 | T16182-XG01-P0LB-122021 | HRSG - LARGE BORE PIPING ARRANGEMENT | IFI | 2017-08-31 | 2018-01-28 |  |  |  | PKG-012-HRSG | 2017-09-04 | 2018-01-09
PT(12) | Mechanical | 122022 | T16182-XG02-P0LB-122022 | HRSG - P&I DIAGRAM | IFR | 2017-01-31 | 2017-05-01 | O |  | O | PKG-012-HRSG | 2017-02-16 | 2017-05-23
PT(12) | Mechanical | 122023 | T16182-XG02-P0LB-122023 | HRSG - P&I DIAGRAM FOR HRSG DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  | O | PKG-012-HRSG | 2017-05-17 | 2017-10-24
PT(12) | Mechanical | 122024 | T16182-XH01-P0LB-122024 | HRSG - PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | IFI | 2017-08-31 | 2018-01-28 |  |  |  | PKG-012-HRSG | 2017-09-28 | 2017-12-21
PT(12) | Mechanical | 122025 | T16182-XH01-P0LB-122025 | HRSG - TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | IFI | 2017-08-31 | 2018-01-28 |  |  |  | PKG-012-HRSG | 2017-10-11 | 2018-01-23
PT(12) | Mechanical | 122026 | T16182-XH01-P0LB-122026 | HRSG - PIPE SUPPORT DRAWINGS | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-012-HRSG | 2017-08-08 | 2017-10-31
PT(12) | Mechanical | 122027 | T16182-XJ00-P0LB-122027 | HRSG - LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG | 2017-08-23 | 2017-12-11
PT(12) | Mechanical | 122028 | T16182-XJ00-P0LB-122028 | HRSG - SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-012-HRSG | 2017-08-29 | 2018-02-07
PT(12) | Mechanical | 122029 | T16182-XJ00-P0LB-122029 | HRSG - VENT & DRAIN LINE (MODULE /FIELD WELD) | IFI | 2017-04-30 | 2017-09-27 |  |  |  | PKG-012-HRSG | 2017-04-28 | 2017-10-31
PT(12) | Mechanical | 122030 | T16182-XL00-P0LB-122030 | HRSG - LINE LIST | IFI | 2017-03-31 | 2017-08-28 |  |  |  | PKG-012-HRSG | 2017-04-12 | 2017-10-20
PT(12) | Mechanical | 122031 | T16182-XL00-P0LB-122031 | HRSG - LINE LIST FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 | 2018-01-12 |  |  |  | PKG-012-HRSG | 2017-08-28 | 2017-10-24
PT(12) | Mechanical | 122032 | T16182-XN00-P0LB-122032 | HRSG - MANUAL VALVE LIST | IFI | 2017-03-31 |  |  |  |  | PKG-012-HRSG | 2017-04-12 | #VALUE!
PT(12) | Instrumentation & Control | 122033 | T16182-XN00-P0LB-122033 | HRSG - MOV & CV LIST | IFI | 2017-03-31 |  |  |  |  | PKG-012-HRSG | 2017-04-12 | #VALUE!
PT(12) | Mechanical | 122034 | T16182-XN00-P0LB-122034 | HRSG - VALVE LIST FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG | 2017-09-26 | #VALUE!
PT(12) | General | 122035 | T16182-XS00-P0LB-122035 | HRSG - SYSTEM DESCRIPTION | IFR | 2017-02-28 | 2017-05-29 | O |  | O | PKG-012-HRSG | 2017-03-10 | 2017-05-29
PT(12) | General | 122036 | T16182-XS00-P0LB-122036 | HRSG - SYSTEM DESCRIPTION FOR HRSG DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  | O | PKG-012-HRSG | 2017-05-23 | 2017-11-02
PT(12) | General | 122037 | T16182-XS00-P0LB-122037 | HRSG - BLOWDOWN SYSTEM SUMMARY | IFR | 2017-01-31 | 2017-05-01 |  |  |  | PKG-012-HRSG | 2017-02-20 | 2017-06-02
PT(12) | Electrical | 122038 | T16182-XV00-P0LB-122038 | HRSG - BMS PANEL PART LIST FOR DUCT BURNER SYSTEM | IFI | 2017-10-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | General | 122039 | T16182-XV00-P0LB-122039 | HRSG - EQUIPMENT LIST | IFI | 2017-01-31 | 2017-06-30 | O |  |  | PKG-012-HRSG | 2017-03-10 | 2017-09-26
PT(12) | General | 122040 | T16182-CN00-P0LB-122040 | HRSG - HAZARDOUS AREA CLASSIFICATION SPECIFICATION & DRAWING FOR DUCT BURNER SYSTEM | IFR | 2017-08-15 | 2017-11-13 |  |  |  | PKG-012-HRSG | 2017-06-22 | 2017-11-07
PT(12) | Electrical | 122041 | T16182-XW01-P0LB-122041 | HRSG - TECHNICAL SPECIFICATION FOR AC & DC DISTRIBUTION BOARD | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-21 | #VALUE!
PT(12) | Mechanical | 122042 | T16182-YT01-P0LB-122042 | HRSG - COOLING AIR FAN & MOTOR DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-08-31 | 2019-08-27 |  |  |  | PKG-012-HRSG | 2017-06-19 | 2019-08-27
PT(12) | Mechanical | 122044 | T16182-YD00-P0LB-122044 | HRSG - BMS SHELTER LAYOUT FOR DUCT BURNER SYSTEM | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG | 2017-09-04 | #VALUE!
PT(12) | Electrical | 122045 | T16182-XW01-P0LB-122045 | HRSG - TECHNICAL SPECIFICATION FOR EARTHING & LIGHTNING PROTECTION SYSTEM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Electrical | 122046 | T16182-XW01-P0LB-122046 | HRSG - TECHNICAL SPECIFICATION FOR COMMUNICATION SYSTEM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-10-16 | #VALUE!
PT(12) | Electrical | 122047 | T16182-YB03-P0LB-122047 | HRSG - CABLE CONNECTION DIAGRAM | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG | 2017-09-12 | #VALUE!
PT(12) | Mechanical | 122048 | T16182-YB03-P0LB-122048 | HRSG - PRESSURE PART ARRANGEMENT | IFI | 2017-02-28 | 2017-07-28 |  |  |  | PKG-012-HRSG | 2017-02-28 | 2017-09-07
PT(12) | Mechanical | 122049 | T16182-YD00-P0LB-122049 | HRSG - SPEC. & DRAWING FOR STEAM DRUM | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG | 2017-06-19 | 2017-11-07
PT(12) | Mechanical | 122050 | T16182-YD00-P0LB-122050 | HRSG - SPEC. & DRAWING FOR BLOWDOWN PUMP | IFI | 2017-06-30 | 2017-10-30 |  |  |  | PKG-012-HRSG | 2017-06-20 | 2017-10-31
PT(12) | Mechanical | 122051 | T16182-YT01-P0LB-122051 | HRSG - SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | IFI | 2017-06-30 | 2017-10-16 |  |  |  | PKG-012-HRSG | 2017-06-19 | 2017-10-16
PT(12) | Mechanical | 122052 | T16182-YD00-P0LB-122052 | HRSG - SPEC. & DRAWING FOR STACK DAMPER | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG | 2017-06-20 | 2017-09-07
PT(12) | Mechanical | 122053 | T16182-YD00-P0LB-122053 | HRSG - SPEC. & DRAWING FOR VENT SILENCER | IFI | 2017-06-30 | 2017-10-16 |  |  |  | PKG-012-HRSG | 2017-05-23 | 2017-10-16
PT(12) | Mechanical | 122054 | T16182-YD00-P0LB-122054 | HRSG - SPEC. & DRAWING FOR DEAERATOR & STORAGE TANK | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG | 2017-07-13 | 2017-12-08
PT(12) | Mechanical | 122055 | T16182-YD00-P0LB-122055 | HRSG - EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | IFI | 2017-05-31 | 2017-10-28 |  |  |  | PKG-012-HRSG | 2017-05-23 | 2017-11-07
PT(12) | Electrical | 122056 | T16182-YD00-P0LB-122056 | HRSG - POWER DISTRIBUTION PANEL DRAWINGS | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG | 2017-08-08 | #VALUE!
PT(12) | Mechanical | 122057 | T16182-YD00-P0LB-122057 | HRSG - HEADER AND SUPPORT DRAWING FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 | 2018-01-12 |  |  |  | PKG-012-HRSG | 2017-08-16 | 2017-11-07
PT(12) | Instrumentation & Control | 122058 | T16182-YD00-P0LB-122058 | HRSG - BMS PANEL LAYOUT FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Instrumentation & Control | 122059 | T16182-YD05-P0LB-122059 | HRSG - HMI SCREEN LAYOUT FOR DUCT BURNER SYSTEM | IFI | 2017-10-15 |  |  |  |  | PKG-012-HRSG | 2017-10-20 | #VALUE!
PT(12) | Instrumentation & Control | 122060 | T16182-YT01-P0LB-122060 | HRSG - JUNCTION BOX DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Instrumentation & Control | 122061 | T16182-XW01-P0LB-122061 | HRSG - FLAME SCANNER & IGNITION BURNER SPECIFICATION FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG | 2017-06-19 | #VALUE!
PT(12) | Mechanical | 122062 | T16182-UE00-P0LB-122062 | HRSG - ARRANGEMENT OF STACK SILENCER | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG | 2017-05-23 | 2017-09-22
PT(12) | Electrical | 122063 | T16182-YD02-P0LB-122063 | HRSG - CONDUIT LAYOUT DRAWING | IFI | 2017-08-31 | 2018-03-21 |  |  |  | PKG-012-HRSG | 2017-08-28 | 2018-03-19
PT(12) | Electrical | 122064 | T16182-YD02-P0LB-122064 | HRSG - CABLE TRAY & RACEWAY LAYOUT DIAGRAM | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG | 2017-09-19 | 2018-03-19
PT(12) | Electrical | 122065 | T16182-YD02-P0LB-122065 | HRSG - GROUNDING AND LIGHTNING PLAN DIAGRAMS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 122066 | T16182-YF00-P0LB-122066 | HRSG - CONTROL LOGIC DIAGRAM | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG | 2017-08-08 | #VALUE!
PT(12) | Instrumentation & Control | 122067 | T16182-YE03-P0LB-122067 | HRSG - CONTROL LOOP DIAGRAM | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG | 2017-08-08 | #VALUE!
PT(12) | Instrumentation & Control | 122068 | T16182-YF00-P0LB-122068 | HRSG - LOGIC DIAGRAM FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG | 2017-09-26 | #VALUE!
PT(12) | Instrumentation & Control | 122069 | T16182-YM03-P0LB-122069 | HRSG - INSTRUMENT LOCATION | IFI | 2017-07-15 | 2018-11-06 |  |  |  | PKG-012-HRSG | 2017-07-13 | 2018-10-16
PT(12) | Instrumentation & Control | 122070 | T16182-YF00-P0LB-122070 | HRSG - BMS SYSTEM CONFIGURATION FOR DUCT BURNER SYSTEM | IFI | 2017-07-15 |  |  |  |  | PKG-012-HRSG | 2017-07-13 | #VALUE!
PT(12) | Mechanical | 122071 | T16182-YK00-P0LB-122071 | HRSG - LINK ASSEMBLY DRAWING | IFI | 2017-04-30 | 2017-10-30 |  |  |  | PKG-012-HRSG | 2017-04-28 | 2017-10-31
PT(12) | Instrumentation & Control | 122072 | T16182-YK00-P0LB-122072 | HRSG - INSTRUMENT INSTALLATION DETAIL DRAWINGS | IFI | 2017-05-31 | 2019-01-17 |  |  |  | PKG-012-HRSG | 2017-06-05 | 2018-10-16
PT(12) | Mechanical | 122073 | T16182-YK00-P0LB-122073 | HRSG - SPECIALTY DRAWING FOR EXTERNAL PIPING | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG | 2017-09-28 | #VALUE!
PT(12) | Mechanical | 122074 | T16182-YK01-P0LB-122074 | HRSG - MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG | 2017-10-25 | #VALUE!
PT(12) | Instrumentation & Control | 122075 | T16182-YL00-P0LB-122075 | HRSG - INSTRUMENT LIST | IFI | 2017-03-31 |  |  |  |  | PKG-012-HRSG | 2017-04-12 | #VALUE!
PT(12) | Instrumentation & Control | 122076 | T16182-YL00-P0LB-122076 | HRSG - INSTRUMENT LIST FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Instrumentation & Control | 122077 | T16182-YK10-P0LB-122077 | HRSG - ALARM AND TRIP SETTING LIST FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Electrical | 122078 | T16182-YL16-P0LB-122078 | HRSG - CABLE SCHEDULE | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG | 2017-09-12 | #VALUE!
PT(12) | Electrical | 122079 | T16182-YL00-P0LB-122079 | HRSG - LIGHTING PLAN DIAGRAMS | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG | 2017-07-11 | 2018-03-29
PT(12) | Electrical | 122080 | T16182-YL01-P0LB-122080 | HRSG - COMMUNICATION BLOCK DIAGRAM | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG | 2017-10-16 | 2018-03-19
PT(12) | Electrical | 122081 | T16182-US02-P0LB-122081 | HRSG - COMMUNICATION LAYOUT DRAWING | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG | 2017-07-11 | 2018-03-19
PT(12) | Mechanical | 122082 | T16182-YR01-P0LB-122082 | HRSG - CHEMICAL CLEANING PROCEDURE | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG | 2017-09-04 | #VALUE!
PT(12) | General | 122083 | T16182-YL08-P0LB-122083 | HRSG - PRESERVATION AND STORAGE PROCEDURE | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG | 2017-09-04 | #VALUE!
PT(12) | Electrical | 122084 | T16182-YR05-P0LB-122084 | HRSG - PANEL ELECTRIC SCHEME FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Electrical | 122085 | T16182-YQ01-P0LB-122085 | HRSG - WIRING & SCHEMATIC DIAGRAM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 122086 | T16182-YQ03-P0LB-122086 | HRSG - DATA & BOM OF INSULATION FOR BLOWDOWN TANK | IFI | 2017-05-31 |  |  |  |  | PKG-012-HRSG | 2017-05-23 | #VALUE!
PT(12) | Mechanical | 122087 | T16182-YQ03-P0LB-122087 | HRSG - DATA & BOM OF INSULATION FOR INTERNAL PIPING | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG | 2017-08-08 | #VALUE!
PT(12) | General | 122088 | T16182-YQ03-P0LB-122088 | HRSG - PERFORMANCE AND OPERATIONAL DATA | IFI | 2017-02-28 |  |  |  |  | PKG-012-HRSG | 2017-03-03 | #VALUE!
PT(12) | Instrumentation & Control | 122089 | T16182-VN02-P0LB-122089 | HRSG - MOV DATASHEET & DRAWINGS | IFI | 2017-05-31 |  |  |  |  | PKG-012-HRSG | 2017-06-29 | #VALUE!
PT(12) | Instrumentation & Control | 122090 | T16182-VN02-P0LB-122090 | HRSG - CV DATASHEET & DRAWINGS | IFI | 2017-05-31 |  |  |  |  | PKG-012-HRSG | 2017-07-21 | #VALUE!
PT(12) | Mechanical | 122091 | T16182-YS00-P0LB-122091 | HRSG - DESH. DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-06-19 | #VALUE!
PT(12) | Electrical | 122092 | T16182-YS00-P0LB-122092 | HRSG - AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | IFI | 2017-06-30 | 2018-03-15 |  |  |  | PKG-012-HRSG | 2017-07-03 | 2018-03-07
PT(12) | Instrumentation & Control | 122093 | T16182-YT01-P0LB-122093 | HRSG - CEMS DATASHEET & DRAWINGS | IFR | 2017-06-30 | 2017-09-28 |  |  |  | PKG-012-HRSG | 2017-07-21 | 2017-12-19
PT(12) | Instrumentation & Control | 122094 | T16182-YT02-P0LB-122094 | HRSG - LOCAL INSTRUMENT DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-12 | #VALUE!
PT(12) | Instrumentation & Control | 122095 | T16182-YT01-P0LB-122095 | HRSG - TRANSMITTER DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 122096 | T16182-YT01-P0LB-122096 | HRSG - DRUM LEVEL GAUGE DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 122097 | T16182-YT01-P0LB-122097 | HRSG - FLOW ELEMENT DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-13 | #VALUE!
PT(12) | Instrumentation & Control | 122098 | T16182-YT01-P0LB-122098 | HRSG - REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-11 | #VALUE!
PT(12) | Electrical | 122099 | T16182-YT01-P0LB-122099 | HRSG - TECHNICAL SPECIFICATION FOR LIGHTING & SMALL POWER SYSTEM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Electrical | 122100 | T16182-YT01-P0LB-122100 | HRSG - ELECTRICAL SINGLE LINE DIAGRAMS | IFI | 2017-04-30 |  |  |  |  | PKG-012-HRSG | 2017-04-28 | #VALUE!
PT(12) | Electrical | 122101 | T16182-YT01-P0LB-122101 | HRSG - ILLUMINATION CALCULATION | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-07-18 | #VALUE!
PT(12) | Instrumentation & Control | 122102 | T16182-YT01-P0LB-122102 | HRSG - I/O LIST FOR BMS AND CEMS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG | 2017-10-12 | #VALUE!
PT(12) | Mechanical | 122103 | T16182-YT01-P0LB-122103 | HRSG - ARRANGEMENT OF PARTITION PLATE & GAS BAFFLE | IFI | 2017-04-30 | 2017-09-27 |  |  |  | PKG-012-HRSG | 2017-04-24 | 2017-08-29
PT(12) | Mechanical | 122104 | T16182-YT02-P0LB-122104 | HRSG - PIPING MATERIAL CLASSIFICATION | IFI | 2017-04-30 |  |  |  |  | PKG-012-HRSG | 2017-04-24 | #VALUE!
PT(12) | Mechanical | 122105 | T16182-YT01-P0LB-122105 | HRSG - INSTRUMENT SPECIFICATION & DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Mechanical | 122106 | T16182-YT01-P0LB-122106 | HRSG - SHUT OFF AND CONTROL VALVE DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG | 2017-06-19 | #VALUE!
PT(12) | Mechanical | 122107 | T16182-YQ01-P0LB-122107 | HRSG - INTERCONNECTION WIRING DIAGRAM FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG | 2017-08-16 | #VALUE!
PT(12) | Mechanical | 122108 | T16182-YT01-P0LB-122108 | HRSG - BMS SPECIFICATION FOR DUCT BURNER SYSTEM | IFR | 2017-08-15 | 2017-11-13 |  |  |  | PKG-012-HRSG | 2017-08-28 | 2017-12-21
PT(12) | Electrical | 122109 | T16182-YD00-P0LB-122109 | HRSG - UNDERGROUND EARTHING CABLE LAYOUT DRAWING | IFI | 2017-04-15 | 2018-03-21 |  |  |  | PKG-012-HRSG | 2017-04-12 | 2018-03-19
PT(12) | Structural & Architectural | 122110 | T16182-XW03-P0LB-122110 | HRSG - STRENGTH CALCULATION REPORT FOR STEEL STRUCTURE | IFI | 2018-03-21 | 2018-07-25 |  |  |  | PKG-012-HRSG | 2019-03-29 | 2019-04-16
PT(12) | Mechanical | 122111 | T16182-UE00-P0LB-122111 | HRSG – PERPENDICULAR BAFFLE AND TIE PLATE ASSY DRAWINGS | IFR | 2018-10-19 | 2018-11-15 |  |  |  | PKG-012-HRSG | 2018-10-22 | 2019-04-16
PT(12) | Mechanical | 122112 | T16182-XG02-P0GM-122112 | HRSG – DRAIN FLOW DIAGRAM | IFI | 2018-10-19 | 2018-11-15 |  |  |  | PKG-012-HRSG | 2018-10-24 | 2019-04-01
PT(12) | Mechanical | 123001 | T16182-YD00-P0MAG-123001 | ACC - GENERAL ARRANGEMENT DRAWING | IFR | 2017-03-09 | 2017-06-07 | O |  |  | PKG-013-ACC | 2017-06-05 | 2017-11-01
PT(12) | Mechanical | 123002 | T16182-XG02-P0MAG-123002 | ACC - P&I DIAGRAM | IFR | 2017-03-19 | 2017-06-17 | O |  | O | PKG-013-ACC | 2017-04-28 | 2017-10-16
PT(12) | Mechanical | 123004 | T16182-XS00-P0MAG-123004 | ACC - PERFORMANCE CURVE | IFR | 2017-05-18 | 2017-08-16 |  |  |  | PKG-013-ACC | 2017-05-23 | 2017-11-29
PT(12) | General | 123005 | T16182-XS00-P0MAG-123005 | ACC - EQUIPMENT LIST | IFI | 2017-03-09 |  |  |  |  | PKG-013-ACC | 2017-05-15 | #VALUE!
PT(12) | Mechanical | 123006 | T16182-VN02-P0MAG-123006 | ACC - FAN SPECIFICATION | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 123007 | T16182-XW01-P0MAG-123007 | ACC - CONDENSATE COLLECTING TANK OUTLINE DRAWING | IFI | 2017-06-07 | 2017-11-04 |  |  |  | PKG-013-ACC | 2017-06-15 | 2018-01-30
PT(12) | Electrical | 123008 | T16182-XK00-P0MAG-123008 | ACC - GEARBOX DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC | 2017-07-11 | #VALUE!
PT(12) | Electrical | 123009 | T16182-XK00-P0MAG-123009 | ACC - FAN MOTOR DATA SHEET | IFI | 2017-04-28 |  |  |  |  | PKG-013-ACC | 2017-05-10 | #VALUE!
PT(12) | Mechanical | 123010 | T16182-XS00-P0MAG-123010 | ACC - CONDENSATE DRAIN PUMP SPECIFICATION | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 123011 | T16182-DH02-P0MAG-123011 | ACC - SJAE DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 123012 | T16182-YT01-P0MAJ-123012 | ACC - CLEANING WATER PUMP DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC | 2017-07-21 | #VALUE!
PT(12) | Mechanical | 123013 | T16182-XR00-P0MAG-123013 | ACC - ELECTRICAL LIFTING HOIST DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC | 2017-07-21 | #VALUE!
PT(12) | Mechanical | 123014 | T16182-YT01-P0MAG-123014 | ACC - MANUAL VALVE LIST | IFI | 2017-06-07 | 2017-11-04 |  |  |  | PKG-013-ACC | 2017-06-12 | 2018-01-25
PT(12) | Mechanical | 123015 | T16182-XH02-P0MAG-123015 | ACC - MANUAL VALVE OUTLINE DRAWING | IFI | 2017-08-16 | 2018-01-13 |  |  |  | PKG-013-ACC | 2018-02-28 | 2018-04-18
PT(12) | Mechanical | 123016 | T16182-XH01-P0MAG-123016 | ACC - PIPING ARRANGEMENT DRAWING | IFI | 2017-07-22 | 2017-12-19 |  |  |  | PKG-013-ACC | 2017-09-07 | 2018-03-30
PT(12) | Mechanical | 123017 | T16182-YK08-P0MAG-123017 | ACC - PIPING ISOMETRIC DRAWING | IFI | 2017-10-05 | 2018-03-04 |  |  |  | PKG-013-ACC | 2017-11-29 | 2018-04-18
PT(12) | Mechanical | 123019 | T16182-XJ00-P0MAG-123019 | ACC - LINE LIST | IFI | 2017-07-22 |  |  |  |  | PKG-013-ACC | 2017-09-04 | #VALUE!
PT(12) | Civil | 123020 | T16182-DE00-P0MAG-123020 | ACC - STEEL STRUCTURE SPECIFICATION | IFI | 2017-04-28 |  |  |  |  | PKG-013-ACC | 2017-05-12 | #VALUE!
PT(12) | Civil | 123021 | T16182-XL00-P0MAG-123021 | ACC - FOUNDATION DRAWINGS / CIVIL LOADING DATA | IFI | 2017-03-09 | 2017-08-06 |  |  |  | PKG-013-ACC | 2017-06-05 | 2017-11-07
PT(12) | Civil | 123022 | T16182-VN02-P0MAG-123022 | ACC - EMBEDDED MATERIAL SPECIFICATION | IFI | 2017-03-09 |  |  |  |  | PKG-013-ACC | 2017-06-15 | #VALUE!
PT(12) | Electrical | 123023 | T16182-XB00-P0MAG-123023 | ACC - ELECTRICAL LOAD LIST | IFI | 2017-03-19 |  |  |  |  | PKG-013-ACC | 2017-04-28 | #VALUE!
PT(12) | Mechanical | 123025 | T16182-YM01-P0MAG-123025 | ACC - MOTOR THERMAL LIMIT CURVE | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC | 2017-09-27 | #VALUE!
PT(12) | Mechanical | 123026 | T16182-YU02-P0MAG-123026 | ACC - SPEED - TORQUE & CURRENT CURVE | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC | 2017-09-27 | #VALUE!
PT(12) | Instrumentation & Control | 123027 | T16182-XK00-P0MAG-123027 | ACC - FUNCTIONAL DESCRIPTION | IFR | 2017-04-08 | 2019-11-01 | O |  |  | PKG-013-ACC | 2017-04-28 | 2020-03-03
PT(12) | Instrumentation & Control | 123029 | T16182-YM02-P0MAG-123029 | ACC - CONTROL LOGIC & LOOP DIAGRAM | IFI | 2017-06-17 |  |  |  |  | PKG-013-ACC | 2017-10-16 | #VALUE!
PT(12) | Instrumentation & Control | 123030 | T16182-YR04-P0MAG-123030 | ACC - I&C WIRING DIAGRAMS | IFI | 2017-07-27 |  |  |  |  | PKG-013-ACC | 2017-09-27 | #VALUE!
PT(12) | Instrumentation & Control | 123031 | T16182-YL00-P0MAG-123031 | ACC - INSTRUMENT LIST | IFI | 2017-05-08 |  |  |  |  | PKG-013-ACC | 2017-05-10 | #VALUE!
PT(12) | Instrumentation & Control | 123032 | T16182-YF00-P0MAG-123032 | ACC - INSTRUMENT DATASHEET | IFI | 2017-06-17 |  |  |  |  | PKG-013-ACC | 2017-08-18 | #VALUE!
PT(12) | Instrumentation & Control | 123033 | T16182-YV02-P0MAG-123033 | ACC - INSTRUMENT DRAWING | IFI | 2017-10-05 |  |  |  |  | PKG-013-ACC | 2018-02-28 | #VALUE!
PT(12) | Instrumentation & Control | 123034 | T16182-YL01-P0MAG-123034 | ACC - INSTRUMENT CALIBRATION SHEET | IFI | 2017-12-16 |  |  |  |  | PKG-013-ACC | 2018-02-28 | #VALUE!
PT(12) | Instrumentation & Control | 123035 | T16182-YT02-P0MAG-123035 | ACC - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC | 2017-10-16 | #VALUE!
PT(12) | Instrumentation & Control | 123036 | T16182-YT01-P0MAG-123036 | ACC-MOTORISED VALVE SPECIFICATION | IFI | 2017-06-07 | 2017-09-05 |  |  |  | PKG-013-ACC | 2017-08-17 | 2017-11-29
PT(12) | Electrical | 123037 | T16182-YK00-P0MAG-123037 | ACC - I&C JB OUTLINE AND LAYOUT DRAWING | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC | 2017-10-16 | #VALUE!
PT(12) | General | 123038 | T16182-YT01-P0MAG-123038 | ACC - TERMINAL POINT LIST | IFI | 2017-04-28 |  |  |  |  | PKG-013-ACC | 2017-05-10 | #VALUE!
PT(12) | General | 123039 | T16182-YD00-P0MAG-123039 | ACC - UTILITY CONSUMPTION LIST | IFI | 2017-04-18 |  |  |  |  | PKG-013-ACC | 2017-04-28 | #VALUE!
PT(12) |  | 123045 | T16182-VN01-P0MAG-123045 | ACC ERECTION DRAWING | Internal | [6 empty] | 2017-12-06 | #VALUE!
PT(12) |  | 123046 | T16182-VN01-P0MAG-123046 | ACC REFERENCE DRAWING | Internal | [6 empty] | 2017-12-21 | #VALUE!
PT(12) |  | 123047 | T16182-VN01-P0MAG-123047 | ACC ERECTION MANUAL | Internal | [6 empty] | 2017-12-21 | #VALUE!
PT(12) | Mechanical | 123048 | T16182-XA00-P0MAG-123048 | ACC - HOLDING EJECTOR DRAWING | IFI | 2018-03-30 |  |  |  |  | PKG-013-ACC | 2018-03-30 | #VALUE!
PT(12) | Mechanical | 123049 | T16182-XA00-P0MAG-123049 | ACC - HOGGING EJECTOR DRAWING | IFI | 2018-03-30 |  |  |  |  | PKG-013-ACC | 2018-03-30 | #VALUE!
PT(12) | Mechanical | 123050 | T16182-VN01-P0MAG-123050 | ACC - WINDWALL DRAWING | IFI | 2018-05-29 | 2018-06-29 |  |  |  | PKG-013-ACC | 2018-06-01 | 2019-09-26
PT(12) | Electrical | 123051 | T16182-YD00-P0MAG-123051 | ACC CABLE TRAY LAYOUT DRAWING | IFI | 2018-10-25 | 2018-11-12 |  |  |  | PKG-013-ACC | 2018-08-28 | 2018-11-12
PT(12) | Mechanical | 123052 | T16182-YQ01-P0ZEN-123052 | ACC_LIGHTING & SMALL POWER LAYOUT DRAWING | IFI | 2018-10-18 |  |  |  |  | PKG-013-ACC | 2018-10-18 | #VALUE!
PT(12) | Mechanical | 123053 | T16182-DS00-P0MAG-123053 | ACC – CLEANING PROCEDURE | IFI | 2018-11-13 |  |  |  |  | PKG-013-ACC | 2018-11-13 | #VALUE!
PT(12) | Mechanical | 123054 | T16182-YD00-P0MAG-123054 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COOLED CONDENSER | IFI | 2019-01-14 |  |  |  |  | PKG-013-ACC | 2019-01-14 | #VALUE!
PT(12) | General | 123055 | T16182-VN01-P0MAG-123055 | WINDWALL LOGO FOR AIR COOLED CONDENSER | IFI | 2019-04-10 | [5 empty] | 2019-04-08 | #VALUE!
PT(12) | Mechanical | 124001 | T16182-XG01-P0EKG-124001 | FGS - FUEL GAS SYSTEM GENERAL LAYOUT DRAWING | IFR | 2017-02-28 | 2017-05-31 | O | O |  | PKG-014-FGS | 2017-04-04 | 2017-06-08
PT(12) | Mechanical | 124002 | T16182-XH01-P0EKG-124002 | FGS - P&I DIAGRAM | IFR | 2017-02-28 | 2017-05-31 | O | O | O | PKG-014-FGS | 2017-03-28 | 2017-11-01
PT(12) | Mechanical | 124003 | T16182-XG07-P0EKG-124003 | FGS - GAS FILTER & SEPARATOR ASSEMBLY DRAWING | IFI | 2017-02-28 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-27 | 2017-09-01
PT(12) | Mechanical | 124004 | T16182-YD00-P0EKG-124004 | FGS - GAS HEATER ASSEMBLY DRAWING | IFI | 2017-05-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-05-12 | 2017-09-05
PT(12) | Mechanical | 124005 | T16182-YK10-P0EKG-124005 | FGS - MAIN GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-27 | 2017-10-13
PT(12) | Mechanical | 124006 | T16182-YK10-P0EKG-124006 | FGS - 2ND GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-27 | 2017-09-06
PT(12) | Mechanical | 124007 | T16182-YK10-P0EKG-124007 | FGS - COLD VENT STACK ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-28 | 2017-09-06
PT(12) | Mechanical | 124008 | T16182-YK10-P0EKG-124008 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-28 | 2017-09-06
PT(12) | Electrical | 124009 | T16182-YD00-P0EKG-124009 | FGS - PANEL LAYOUT FOR LOCAL ELECTRICAL ROOM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-28 | #VALUE!
PT(12) | Instrumentation & Control | 124010 | T16182-YK10-P0EKG-124010 | FGS - GAS CHROMATOGRAPH OUTLINE DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-27 | 2017-10-13
PT(12) | Mechanical | 124011 | T16182-YD00-P0EKG-124011 | FGS - ESD VALVE ASSEMBLY DRAWING | IFI | 2017-05-28 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-27 | 2017-09-05
PT(12) | Electrical | 124012 | T16182-YD00-P0EKG-124012 | FGS - CABLE ROUTE LAYOUT FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 | 2018-01-29 |  | O |  | PKG-014-FGS | 2017-10-18 | 2018-01-29
PT(12) | Civil | 124013 | T16182-YK10-P0EKG-124013 | FGS - FOUDATION & LOADS FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-28 | 2017-11-01
PT(12) | Instrumentation & Control | 124014 | T16182-YE00-P0EKG-124014 | FGS - CONTROL LOOP, LOGIC DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS | 2017-11-01 | #VALUE!
PT(12) | Electrical | 124015 | T16182-XB02-P0EKG-124015 | FGS - CABLE BLOCK DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-28 | #VALUE!
PT(12) | Electrical | 124016 | T16182-YF00-P0EKG-124016 | FGS - TERMINAL BOX DRAWING FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS | 2017-09-01 | #VALUE!
PT(12) | Electrical | 124017 | T16182-YB03-P0EKG-124017 | FGS - SINGLE LINE DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS | 2017-09-18 | #VALUE!
PT(12) | Instrumentation & Control | 124018 | T16182-YD00-P0EKG-124018 | FGS - MEASUREMENT LIST FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS | 2017-07-11 | #VALUE!
PT(12) | Electrical | 124020 | T16182-BX03-P0EKG-124020 | FGS - WIRING DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS | 2017-10-18 | #VALUE!
PT(12) | Mechanical | 124021 | T16182-XS00-P0EKG-124021 | FGS - VALVE LIST | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-27 | #VALUE!
PT(12) | Mechanical | 124022 | T16182-YV02-P0EKG-124022 | FGS - VALVE DATA SHEET | IFI | 2017-06-30 |  |  | O |  | PKG-014-FGS | 2017-09-01 | #VALUE!
PT(12) | Mechanical | 124023 | T16182-XN00-P0EKG-124023 | FGS - BUFFER TANK OUTLINE DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-28 | 2017-09-05
PT(12) | Mechanical | 124024 | T16182-YT01-P0EKG-124024 | FGS - BOOSTER COMPRESSOR OUTLINE DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS | 2017-04-27 | 2017-10-23
PT(12) | Mechanical | 124025 | T16182-YD00-P0EKG-124025 | FGS - GAS HEATER DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Mechanical | 124026 | T16182-YD00-P0EKG-124026 | FGS - MAIN GAS PRESSURE REDUCING STATION DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Mechanical | 124027 | T16182-YT01-P0EKG-124027 | FGS - 2ND GAS PRESSURE REDUCING STATION DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Mechanical | 124028 | T16182-YT01-P0EKG-124028 | FGS - COLD VENT STACK DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-27 | #VALUE!
PT(12) | Mechanical | 124029 | T16182-YT01-P0EKG-124029 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Instrumentation & Control | 124030 | T16182-YT01-P0EKG-124030 | FGS - GAS CHROMATOGRAPH DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Mechanical | 124031 | T16182-YT01-P0EKG-124031 | FGS - ESD VALVE DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Mechanical | 124032 | T16182-YT01-P0EKG-124032 | FGS - BOOSTER COMPRESSOR DATA SHEET | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Mechanical | 124033 | T16182-YT01-P0EKG-124033 | FGS - BUFFER TANK DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS | 2017-04-21 | #VALUE!
PT(12) | Mechanical | 124039 | T16182-CH01-P0EKG-124039 | INSTALLATION & ERECTION MANUAL | Internal | [6 empty] | 2018-03-26 | #VALUE!
PT(12) | Mechanical | 124040 | T16182-YT01-P0EKG-124040 | FGS_DATASHEET AND OUTLINE DRAWING FOR GTG INLET STRAINERS | IFR | 2019-09-25 | 2019-10-25 |  |  |  |  | 2019-10-07 | 2019-10-29
PT(12) | Instrumentation & Control | 124048 | T16182-YS02-P0EKG-124048 | CABLE CONNECTION DIAGRAM | Internal | [6 empty] | 2018-04-05 | #VALUE!
PT(12) | Instrumentation & Control | 124075 | T16182-UB01-P0EKG-124075 | FGS - FUNCTIONAL DESCRIPTION | IFI | 2017-11-01 | 2018-03-09 |  |  |  | PKG-014-FGS | 2017-11-01 | 2018-05-11
PT(12) | Mechanical | 124077 | T16182-XJ00-P0EKG-124077 | FGS – ISO DRAWING | Internal | [6 empty] | 2017-12-13 | #VALUE!
PT(12) | Mechanical | 124078 | T16182-YL30-P0EKG-124078 | FGS – SALES GAS CONTROL VALVE STATION DOCUMENT & DRAWING | IFI | 2019-11-15 | [5 empty] | 2019-11-18 | #VALUE!
PT(12) | Mechanical | 124079 | T16182-YT01-P0EKG-124079 | FGS – DUPLEX STRAINER INSTRUMENT DATA & DRAWING | IFI | 2019-11-20 | [5 empty] | 2019-11-13 | #VALUE!
PT(12) |  | 124161 | T16182-DN04-P0EKG-124161 | INSULATION PROCEDURE FOR FGSS AREA AND HEATER SKIDS | Internal | [6 empty] | 2018-03-21 | #VALUE!
PT(12) | Mechanical | 124180 | T16182-YB03-P0EKG-124180 | FGS - 120V TR PANEL FOR GAS CHROMATOGRAPH | IFI | 2018-08-16 |  |  |  |  | PKG-014-FGS | 2018-08-13 | #VALUE!
PT(12) | Mechanical | 125001 | T16182-XV00-P8ZEN-125001 | RESERVE BOILER - SUPPLY/EQUIPMENT LIST | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB | 2017-07-21 | #VALUE!
PT(12) | Mechanical | 125002 | T16182-XS00-P8QHA-125002 | RESERVE BOILER - SYSTEM DESCRIPTION | IFR | 2017-05-19 | 2017-08-17 | O | O | O | PKG-015-RB | 2017-06-05 | 2017-09-27
PT(12) | Mechanical | 125012 | T16182-XW03-P8ZEN-125012 | RESERVE BOILER - BOILER PREDICTED PERFORMANCE DATA & CURVE | IFR | 2017-05-12 | 2017-06-29 |  | O |  | PKG-015-RB | 2017-05-12 | 2017-10-24
PT(12) | Mechanical | 125014 | T16182-XW03-P8ZEN-125014 | RESERVE BOILER - BOILER START - UP CURVE | IFR | 2017-03-03 | 2017-06-01 |  | O |  | PKG-015-RB | 2017-03-14 | 2017-10-24
PT(12) |  | 125019 | T16182-CQ02-P8ZEN-125019 | RESERVE BOILER_ERECTION MANUAL | Internal | [6 empty] | 2017-11-29 | #VALUE!
PT(12) | Mechanical | 125101 | T16182-CC00-P8QHA-125101 | RESERVE BOILER - GENERAL ARRANGEMENT DRAWING | IFR | 2017-01-13 | 2017-04-13 | O | O |  | PKG-015-RB | 2017-01-05 | 2017-09-27
PT(12) | Civil | 125151 | T16182-CC08-P8QHB-125151 | RESERVE BOILER - FOUNDATION LOADING DATA FOR STEEL STRUCTURE & STACK | IFI | 2017-01-13 |  |  | O |  | PKG-015-RB | 2017-01-05 | #VALUE!
PT(12) | Civil | 125152 | T16182-XT00-P8QHB-125152 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STEEL STRUCTURE | IFI | 2017-03-10 | 2017-09-26 |  | O |  | PKG-015-RB | 2017-03-31 | 2017-09-27
PT(12) | Civil | 125153 | T16182-XT00-P8QHB-125153 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STACK | IFI | 2017-03-10 | 2017-09-26 |  | O |  | PKG-015-RB | 2017-03-31 | 2017-09-27
PT(12) | Mechanical | 125161 | T16182-CC05-P8QHB-125161 | RESERVE BOILER - DESIGN CRITERIA FOR STEEL STRUCTURE | IFI | 2017-02-10 |  |  | O |  | PKG-015-RB | 2017-03-02 | #VALUE!
PT(12) | Mechanical | 125162 | T16182-CC05-P8QHB-125162 | RESERVE BOILER - CONNECTION DETAIL DRAWING FOR STEEL STRUCTURE | IFI | 2017-02-10 | 2017-08-29 |  | O |  | PKG-015-RB | 2017-03-02 | 2017-09-06
PT(12) | Mechanical | 125164 | T16182-CC02-P8QHB-125164 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STEEL STRUCTURE | IFI | 2017-05-12 | 2017-11-28 |  | O |  | PKG-015-RB | 2017-05-12 | 2017-09-06
PT(12) | Mechanical | 125172 | T16182-CC02-P8QHB-125172 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STACK | IFI | 2017-05-12 | 2017-11-28 |  | O |  | PKG-015-RB | 2017-05-12 | 2017-12-20
PT(12) | Mechanical | 125201 | T16182-YD07-P8QHA-125201 | RESERVE BOILER - PRESSURE PART ARRANGEMENT OF BOILER DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB | 2017-02-24 | 2017-09-27
PT(12) | Mechanical | 125202 | T16182-YK10-P8QHA-125202 | RESERVE BOILER - DESUPERHEATER DRAWING | IFI | 2017-04-28 | 2017-11-14 |  | O |  | PKG-015-RB | 2017-02-24 | 2018-01-04
PT(12) | Mechanical | 125207 | T16182-YK10-P8QHA-125207 | RESERVE BOILER - ECONOMIZER DRAWING | IFI | 2017-06-19 | 2018-01-20 |  | O |  | PKG-015-RB | 2017-06-16 | 2018-02-01
PT(12) | Civil | 125300 | T16182-CC08-P8QHA-125300 | RESERVE BOILER - FOUNDATION LOADING DATA FOR BOILER PROPER | IFI | 2017-01-13 |  |  | O |  | PKG-015-RB | 2017-01-05 | #VALUE!
PT(12) | Mechanical | 125303 | T16182-UC02-P8QHA-125303 | RESERVE BOILER - REFRACTORY LINING PROCEDURE FOR BOILER PROPER | IFI | 2017-05-12 | 2017-12-14 |  | O |  | PKG-015-RB | 2017-05-12 | 2017-12-14
PT(12) | Mechanical | 125304 | T16182-UC02-P8QHA-125304 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR BOILER PROPER | IFI | 2017-05-12 | 2017-11-28 |  | O |  | PKG-015-RB | 2017-05-12 | 2018-01-09
PT(12) | Mechanical | 125308 | T16182-YK10-P8QHA-125308 | RESERVE BOILER - NAME PLATE DRAWING OF BOILER PROPER | IFI | 2017-10-06 |  |  | O |  | PKG-015-RB | 2017-10-20 | #VALUE!
PT(12) | Mechanical | 125310 | T16182-DP00-P8ZEN-125310 | RESERVE BOILER - NAME PLATE DRAWING OF VALVE | IFI | 2017-06-09 |  |  | O |  | PKG-015-RB | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 125400 | T16182-XH02-P8QHL-125400 | RESERVE BOILER - GAS & AIR DUCT ARRANGEMENT DRAWING | IFI | 2017-04-28 | 2017-11-14 |  | O |  | PKG-015-RB | 2017-04-28 | 2017-09-15
PT(12) | Mechanical | 125401 | T16182-XA00-P8QHL-125401 | RESERVE BOILER - DAMPER DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB | 2017-03-31 | 2017-09-27
PT(12) | Mechanical | 125402 | T16182-XA00-P8QHL-125402 | RESERVE BOILER - EXPANSION JOINT DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB | 2017-03-31 | 2017-09-27
PT(12) | Mechanical | 125403 | T16182-YK08-P8QHL-125403 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR DUCT | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB | 2017-03-31 | 2017-09-27
PT(12) | Mechanical | 125502 | T16182-DE00-P8ZEN-125502 | RESERVE BOILER - PMS (PIPE MATERIAL SPECIFICATION) | IFI | 2017-04-28 |  |  | O |  | PKG-015-RB | 2017-04-28 | #VALUE!
PT(12) | Mechanical | 125503 | T16182-XN00-P8ZEN-125503 | RESERVE BOILER - LINE LIST | IFI | 2017-04-28 |  |  | O |  | PKG-015-RB | 2017-04-28 | #VALUE!
PT(12) | Mechanical | 125504 | T16182-XN00-P8ZEN-125504 | RESERVE BOILER - VALVE LIST | IFI | 2017-04-28 |  |  | O |  | PKG-015-RB | 2017-04-28 | #VALUE!
PT(12) | Mechanical | 125505 | T16182-XV00-P8ZEN-125505 | RESERVE BOILER - PIPING SPECIALITY DRAWING & LIST | IFI | 2017-06-09 | 2017-12-26 |  | O |  | PKG-015-RB | 2017-07-11 | 2017-09-07
PT(12) | Mechanical | 125506 | T16182-DP00-P8ZEN-125506 | RESERVE BOILER - MANUAL VALVE DRAWING | IFI | 2017-06-09 | 2017-12-26 |  | O |  | PKG-015-RB | 2017-07-11 | 2017-09-07
PT(12) | Mechanical | 125507 | T16182-YD00-P8ZEN-125507 | RESERVE BOILER - PIPING & PIPING SUPPORT PLAN DRAWING | IFI | 2017-08-25 | 2018-03-13 |  | O |  | PKG-015-RB | 2017-09-27 | 2018-02-28
PT(12) | Mechanical | 125509 | T16182-XK00-P8ZEN-125509 | RESERVE BOILER - PIPING SUPPORT DETAIL DRAWING FOR SMALL BORE PIPING. | IFI | 2017-09-08 | 2018-03-27 |  | O |  | PKG-015-RB | 2017-10-18 | 2018-02-05
PT(12) | Instrumentation & Control | 125514 | T16182-YL30-P8ZEN-125514 | RESERVE BOILER - CONTROL VALVE DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-07-11 | 2017-09-07
PT(12) | Mechanical | 125520 | T16182-XJ00-P8ZEN-125520 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125521 | T16182-XJ00-P8ZEN-125521 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125522 | T16182-XJ00-P8ZEN-125522 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125523 | T16182-XJ00-P8ZEN-125523 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125524 | T16182-XJ00-P8ZEN-125524 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125525 | T16182-XJ00-P8ZEN-125525 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125526 | T16182-XJ00-P8ZEN-125526 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125527 | T16182-XJ00-P8ZEN-125527 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-06 | 2018-01-29
PT(12) | Mechanical | 125530 | T16182-XK00-P8ZEN-125530 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125531 | T16182-XK00-P8ZEN-125531 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125532 | T16182-XK00-P8ZEN-125532 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125533 | T16182-XK00-P8ZEN-125533 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125534 | T16182-XK00-P8ZEN-125534 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125535 | T16182-XK00-P8ZEN-125535 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125536 | T16182-XK00-P8ZEN-125536 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125537 | T16182-XK00-P8ZEN-125537 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-09-19 | 2018-01-30
PT(12) | Mechanical | 125540 | T16182-XJ00-P8ZEN-125540 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(DEAERATOR SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125541 | T16182-XJ00-P8ZEN-125541 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(FEEDWATER PUMP SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125542 | T16182-XJ00-P8ZEN-125542 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER WATER SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125543 | T16182-XJ00-P8ZEN-125543 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER STEAM SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125544 | T16182-XJ00-P8ZEN-125544 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(COMBUSTION AIR & FLUE GAS SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125545 | T16182-XJ00-P8ZEN-125545 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BURNER SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125546 | T16182-XJ00-P8ZEN-125546 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BLOWDOWN SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125547 | T16182-XJ00-P8ZEN-125547 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CHEMICAL DOSING SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125548 | T16182-XJ00-P8ZEN-125548 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-06 | 2018-02-23
PT(12) | Mechanical | 125549 | T16182-XJ00-P8ZEN-125549 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(INSTRUMENT AIR SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-17 | 2018-02-23
PT(12) | Mechanical | 125550 | T16182-XJ00-P8ZEN-125550 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB | 2017-11-17 | 2018-02-23
PT(12) | Mechanical | 125570 | T16182-XJ00-P8ZEN-125570 | RESERVE BOILER_ FUEL SKID DETAIL DRAWING | IFI | 2018-01-12 | 2018-01-30 |  |  |  | PKG-015-RB | 2018-01-08 | 2018-01-30
PT(12) | Mechanical | 125571 | T16182-XG05-P8ZEN-125571 | RESERVE BOILER - HEAT & MASS BLANCE DIAGRAM | IFR | 2017-01-13 | 2017-04-13 |  | O |  | PKG-015-RB | 2017-03-14 | 2017-09-18
PT(12) | Mechanical | 125582 | T16182-XG02-P8ZEN-125582 | RESERVE BOILER - P&ID OF DEAERATOR SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-05-31
PT(12) | Mechanical | 125583 | T16182-XG02-P8ZEN-125583 | RESERVE BOILER - P&ID OF FEEDWATER PUMP SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-05-31
PT(12) | Mechanical | 125584 | T16182-XG02-P8ZEN-125584 | RESERVE BOILER - P&ID OF BOILER WATER SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-05-31
PT(12) | Mechanical | 125585 | T16182-XG02-P8ZEN-125585 | RESERVE BOILER - P&ID OF BOILER STEAM SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-05-31
PT(12) | Mechanical | 125586 | T16182-XG02-P8ZEN-125586 | RESERVE BOILER - P&ID OF COMBUSTION AIR & FLUE GAS SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-09-27
PT(12) | Mechanical | 125587 | T16182-XG02-P8ZEN-125587 | RESERVE BOILER - P&ID OF BURNER & FUEL GAS SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-05-31
PT(12) | Mechanical | 125588 | T16182-XG02-P8ZEN-125588 | RESERVE BOILER - P&ID OF BLOWDOWN SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-05-31
PT(12) | Mechanical | 125589 | T16182-XG02-P8ZEN-125589 | RESERVE BOILER - P&ID OF SAMPLING SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-05-31
PT(12) | Mechanical | 125590 | T16182-XG02-P8ZEN-125590 | RESERVE BOILER - P&ID OF CHEMICAL DOSING SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-09-27
PT(12) | Mechanical | 125591 | T16182-XG02-P8ZEN-125591 | RESERVE BOILER - P&ID OF CLOSED COOLING WATER & SERVICE WATER SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-06-16
PT(12) | Mechanical | 125592 | T16182-XG02-P8ZEN-125592 | RESERVE BOILER - P&ID OF INSTRUMENT AIR SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-06-16
PT(12) | Mechanical | 125593 | T16182-XG02-P8ZEN-125593 | RESERVE BOILER - P&ID OF SERVICE AIR & SEALING AIR SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB | 2017-02-17 | 2017-06-16
PT(12) | General | 125597 | T16182-YR01-P8ZEN-125597 | METHODS STATEMENTS OF STEAM FLUSHING FOR RESERVE BOILER | IFR | 2018-09-10 | 2018-10-30 |  |  |  | PKG-015-RB | 2018-09-10 | 2018-10-12
PT(12) | Mechanical | 125601 | T16182-CV03-P8ZEN-125601 | RESERVE BOILER - F.D FAN DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-06-16 | 2018-01-30
PT(12) | Mechanical | 125602 | T16182-CV03-P8ZEN-125602 | RESERVE BOILER - BURNER DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-06-14 | 2018-02-14
PT(12) | Mechanical | 125604 | T16182-CV03-P8ZEN-125604 | RESERVE BOILER - BFP DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-06-16 | 2018-02-12
PT(12) | Mechanical | 125605 | T16182-CV03-P8ZEN-125605 | RESERVE BOILER - DEAERATOR WITH STORAGE TANK DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-06-14 | 2017-09-28
PT(12) | Mechanical | 125606 | T16182-CV03-P8ZEN-125606 | RESERVE BOILER - SILENCER DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB | 2017-04-17 | 2017-12-22
PT(12) | Mechanical | 125607 | T16182-CV03-P8ZEN-125607 | RESERVE BOILER - SAMPLING SYSTEM DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-07-11 | 2018-01-30
PT(12) | Mechanical | 125608 | T16182-CV03-P8ZEN-125608 | RESERVE BOILER - CHEMICAL DOSING SYSTEM DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-07-25 | 2018-02-14
PT(12) | Mechanical | 125609 | T16182-CV03-P8ZEN-125609 | RESERVE BOILER - MONORAIL HOIST DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-07-11 | 2018-01-30
PT(12) | Mechanical | 125610 | T16182-CV03-P8ZEN-125610 | RESERVE BOILER - SRV DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB | 2017-04-17 | 2017-12-22
PT(12) | Mechanical | 125611 | T16182-CV03-P8ZEN-125611 | RESERVE BOILER - BLOWDOWN TANK DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB | 2017-06-16 | 2017-09-06
PT(12) | Mechanical | 125612 | T16182-CV03-P8ZEN-125612 | RESERVE BOILER - LEVEL GAUGE DOCUMENT & DRAWING | IFI | 2017-03-24 | 2018-03-12 |  | O |  | PKG-015-RB | 2017-04-11 | 2018-03-12
PT(12) | Civil | 125614 | T16182-CC08-P8ZEN-125614 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR F.D FAN | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB | 2017-04-11 | #VALUE!
PT(12) | Civil | 125615 | T16182-CC08-P8ZEN-125615 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BOILER FEED WATER PUMP | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB | 2017-04-11 | #VALUE!
PT(12) | Civil | 125616 | T16182-CC08-P8ZEN-125616 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR FUEL SKID | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB | 2017-04-11 | #VALUE!
PT(12) | Civil | 125617 | T16182-CC08-P8ZEN-125617 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR SAMPLING SYSTEM | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB | 2017-04-11 | #VALUE!
PT(12) | Civil | 125618 | T16182-CC08-P8ZEN-125618 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR CHEMICAL DOSING SYSTEM | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB | 2017-04-11 | #VALUE!
PT(12) | Civil | 125619 | T16182-CC08-P8ZEN-125619 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BLOW DOWN TANK | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB | 2017-04-11 | #VALUE!
PT(12) | Civil | 125620 | T16182-CC08-P8ZEN-125620 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR ELECTRICAL & CONTROL ROOM | IFI | 2017-05-12 |  |  | O |  | PKG-015-RB | 2017-06-05 | #VALUE!
PT(12) | Mechanical | 125650 | T16182-CV03-P8SGK-125650 | RESERVE BOILER_ FM GAS SYSTEM CALCULATION & DOCUMENT | IFR | 2018-06-05 | 2018-08-01 |  |  |  | PKG-015-RB | 2018-06-01 | 2018-08-13
PT(12) | Instrumentation & Control | 125700 | T16182-XS01-P8ZEN-125700 | RESERVE BOILER - OPERATION PHILOSOPHY | IFR | 2017-06-02 | 2017-09-02 |  | O | O | PKG-015-RB | 2017-09-28 | 2017-12-20
PT(12) | Instrumentation & Control | 125701 | T16182-YF02-P8ZEN-125701 | RESERVE BOILER - CONTROL SYSTEM CONFIGURATION | IFR | 2017-06-02 | 2017-09-02 |  | O |  | PKG-015-RB | 2017-09-28 | 2017-10-20
PT(12) | Instrumentation & Control | 125702 | T16182-DP00-P8ZEN-125702 | RESERVE BOILER - BMS SPECIFICATION | IFR | 2017-06-02 | 2017-08-31 |  | O |  | PKG-015-RB | 2017-06-14 | 2017-10-23
PT(12) | Instrumentation & Control | 125703 | T16182-YL01-P8ZEN-125703 | RESERVE BOILER - BMS I/O LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-06-14 | #VALUE!
PT(12) | Instrumentation & Control | 125704 | T16182-YL01-P8ZEN-125704 | RESERVE BOILER - BCS I/O LIST | IFI | 2017-06-02 | 2017-09-21 |  | O |  | PKG-015-RB | 2017-06-14 | 2017-09-21
PT(12) | Instrumentation & Control | 125705 | T16182-YL01-P8ZEN-125705 | RESERVE BOILER - VMS I/O LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-06-14 | #VALUE!
PT(12) | Instrumentation & Control | 125706 | T16182-YL01-P8ZEN-125706 | RESERVE BOILER - DATALINK I/O LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-06-14 | #VALUE!
PT(12) | Instrumentation & Control | 125707 | T16182-YL00-P8ZEN-125707 | RESERVE BOILER - INSTRUMENT LIST | IFI | 2017-06-02 | 2018-04-23 |  | O |  | PKG-015-RB | 2017-06-14 | 2018-04-23
PT(12) | Instrumentation & Control | 125708 | T16182-YL00-P8ZEN-125708 | RESERVE BOILER - ALARM AND TRIP SETTING LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-06-14 | #VALUE!
PT(12) | Instrumentation & Control | 125709 | T16182-YF00-P8ZEN-125709 | RESERVE BOILER - CONTROL LOGIC DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 125710 | T16182-YF00-P8ZEN-125710 | RESERVE BOILER - CONTROL LOOP DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 125711 | T16182-YF00-P8ZEN-125711 | RESERVE BOILER - BMS LOGIC DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 125713 | T16182-YT02-P8ZEN-125713 | RESERVE BOILER - MOV DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-12-07 |  | O |  | PKG-015-RB | 2017-07-21 | 2017-09-29
PT(12) | Instrumentation & Control | 125714 | T16182-YT02-P8ZEN-125714 | RESERVE BOILER - TRANSMITTER SPECIFICATION | IFI | 2017-07-02 | 2017-09-18 |  | O |  | PKG-015-RB | 2017-07-21 | 2017-09-18
PT(12) | Instrumentation & Control | 125715 | T16182-YT02-P8ZEN-125715 | RESERVE BOILER - LOCAL GAUGE SPECIFICATION | IFI | 2017-07-02 | 2017-09-29 |  | O |  | PKG-015-RB | 2017-07-21 | 2017-09-29
PT(12) | Instrumentation & Control | 125716 | T16182-YT02-P8ZEN-125716 | RESERVE BOILER - TEMP. ELEMENT SPECIFICATION | IFI | 2017-07-02 | 2017-09-29 |  | O |  | PKG-015-RB | 2017-07-21 | 2017-09-29
PT(12) | Instrumentation & Control | 125717 | T16182-YT02-P8ZEN-125717 | RESERVE BOILER - FLOW ELEMENT SPECIFICATION | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-07-21 | #VALUE!
PT(12) | Instrumentation & Control | 125718 | T16182-YT02-P8ZEN-125718 | RESERVE BOILER - REMOTE DRUM LEVEL INDICATOR SPECIFICATION | IFI | 2017-07-02 | 2017-12-06 |  | O |  | PKG-015-RB | 2017-07-21 | 2017-12-06
PT(12) | Instrumentation & Control | 125719 | T16182-YT02-P8ZEN-125719 | RESERVE BOILER - AIR OPERATED VALVE DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-12-07 |  | O |  | PKG-015-RB | 2017-07-06 | 2017-07-21
PT(12) | Instrumentation & Control | 125720 | T16182-YK00-P8ZEN-125720 | RESERVE BOILER - INSTRUMENT INSTALLATION DETAIL DRAWING | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-09-29 | #VALUE!
PT(12) | Instrumentation & Control | 125721 | T16182-YM03-P8ZEN-125721 | RESERVE BOILER - INSTRUMENT LOCATION DRAWING | IFI | 2017-07-02 | 2018-03-26 |  | O |  | PKG-015-RB | 2017-07-25 | 2018-03-26
PT(12) | Instrumentation & Control | 125722 | T16182-YT10-P8ZEN-125722 | RESERVE BOILER - TRANSMITTER CALIBRATION SHEET | IFI | 2017-12-22 |  |  | O |  | PKG-015-RB | 2018-02-14 | #VALUE!
PT(12) | Instrumentation & Control | 125723 | T16182-YT10-P8ZEN-125723 | RESERVE BOILER - FLOW ELEMENT CALIBRATION SHEET | IFI | 2017-12-22 |  |  | O |  | PKG-015-RB | 2018-02-14 | #VALUE!
PT(12) | Instrumentation & Control | 125724 | T16182-YF00-P8ZEN-125724 | RESERVE BOILER - MONITOR SCREEN DIAGRAM | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 125725 | T16182-YT02-P8ZEN-125725 | RESERVE BOILER - GAS LEAK DETECTION SYSTEM DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-09-27 |  | O |  | PKG-015-RB | 2017-07-25 | 2017-09-27
PT(12) | Instrumentation & Control | 125726 | T16182-YT02-P8ZEN-125726 | RESERVE BOILER - O2 ANALYZER DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-09-22 |  | O |  | PKG-015-RB | 2017-07-21 | 2017-09-22
PT(12) | Instrumentation & Control | 125727 | T16182-YT02-P8ZEN-125727 | RESERVE BOILER - CEMS DOCUMENT & DRAWING | IFR | 2017-06-02 | 2017-08-17 |  | O |  | PKG-015-RB | 2017-07-21 | 2017-10-20
PT(12) | Instrumentation & Control | 125728 | T16182-YD00-P8ZEN-125728 | RESERVE BOILER - CONTROL ROOM & ELECTRICAL ROOM ARRANGEMENT DRAWING | IFI | 2017-07-02 | 2018-05-31 |  | O |  | PKG-015-RB | 2017-08-30 | 2018-05-31
PT(12) | Instrumentation & Control | 125729 | T16182-XF00-P8ZEN-125729 | RESERVE BOILER - JUNCTION BOX DRAWING | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB | 2017-07-25 | 2018-04-23
PT(12) | Instrumentation & Control | 125731 | T16182-YL16-P8ZEN-125731 | RESERVE BOILER - I&C CABLE SCHEDULE | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB | 2017-08-30 | 2018-04-23
PT(12) | Instrumentation & Control | 125732 | T16182-YB03-P8ZEN-125732 | RESERVE BOILER - I&C CABLE CONNECTION DIAGRAM | IFI | 2017-07-02 | 2019-04-09 |  | O |  | PKG-015-RB | 2017-08-30 | 2019-04-09
PT(12) | Instrumentation & Control | 125734 | T16182-DP00-P8ZEN-125734 | RESERVE BOILER - BCS SPECIFICATION | IFI | 2017-06-02 | 2017-10-23 |  | O |  | PKG-015-RB | 2017-06-14 | 2017-10-23
PT(12) | Engineering Management | 125735 | T16182-YD00-P8ZEN-125735 | RESERVE BOILER - HAZARDOUS AREA CLASSFICATION | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB | 2017-09-29 | #VALUE!
PT(12) | Mechanical | 125737 | T16182-DP00-P8ZEN-125737 | RESERVE BOILER _ VMS SPECIFICATION | IFI | 2017-10-13 |  |  |  |  | PKG-015-RB | 2017-09-28 | #VALUE!
PT(12) | Electrical | 125749 | T16182-DP00-P8ZEN-125749 | RESERVE BOILER - MOTOR LIST | IFI | 2017-05-19 |  |  | O |  | PKG-015-RB | 2017-07-06 | #VALUE!
PT(12) | Electrical | 125750 | T16182-YD00-P8ZEN-125750 | RESERVE BOILER - POWER DISTRIBUTION PANEL DRAWING | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB | 2017-08-30 | 2018-04-23
PT(12) | Electrical | 125751 | T16182-YE00-P8ZEN-125751 | RESERVE BOILER - RACEWAY PLAN DRAWING | IFI | 2017-06-16 | 2018-03-26 |  | O |  | PKG-015-RB | 2017-09-29 | 2018-03-26
PT(12) | Electrical | 125752 | T16182-YE00-P8ZEN-125752 | RESERVE BOILER - RACEWAY DOCUMENT & DRAWING | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB | 2017-09-29 | #VALUE!
PT(12) | Electrical | 125754 | T16182-DP00-P8ZEN-125754 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR MCC | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-07-25 | #VALUE!
PT(12) | Electrical | 125755 | T16182-YU02-P8ZEN-125755 | RESERVE BOILER - MCC SINGLE LINE DIAGRAM | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-07-25 | #VALUE!
PT(12) | Electrical | 125756 | T16182-YU03-P8ZEN-125756 | RESERVE BOILER - MCC SCHEMATIC DIAGRAM | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-07-25 | #VALUE!
PT(12) | Electrical | 125757 | T16182-DP00-P8ZEN-125757 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLE | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-07-25 | #VALUE!
PT(12) | Electrical | 125758 | T16182-DP00-P8ZEN-125758 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-07-25 | #VALUE!
PT(12) | Electrical | 125759 | T16182-DP00-P8ZEN-125759 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR FIRE STOP MATERIALS | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB | 2017-07-25 | #VALUE!
PT(12) | Electrical | 125760 | T16182-YL16-P8ZEN-125760 | RESERVE BOILER - POWER CABLE SCHEDULE | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB | 2017-08-30 | 2018-04-23
PT(12) | Electrical | 125761 | T16182-YB03-P8ZEN-125761 | RESERVE BOILER - POWER CABLE CONNECTION DIAGRAM | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB | 2017-08-30 | 2018-04-23
PT(12) | Electrical | 125762 | T16182-YD02-P8ZEN-125762 | RESERVE BOILER - EMBEDDED CONDUIT LAYOUT DRAWING | IFI | 2017-02-10 | 2017-07-05 |  | O |  | PKG-015-RB | 2017-04-12 | 2017-07-05
PT(12) | Electrical | 125763 | T16182-DP00-P8ZEN-125763 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR LIGHTING SYSTEM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB | 2017-07-06 | #VALUE!
PT(12) | Electrical | 125764 | T16182-YT10-P8ZEN-125764 | RESERVE BOILER - ILLUMINATION CALCULATION | IFI | 2017-07-28 |  |  | O |  | PKG-015-RB | 2017-07-25 | #VALUE!
PT(12) | Electrical | 125765 | T16182-YQ01-P8ZEN-125765 | RESERVE BOILER - LIGHTING LAYOUT DRAWING | IFI | 2017-07-28 | 2018-03-26 |  | O |  | PKG-015-RB | 2017-07-25 | 2018-03-26
PT(12) | Electrical | 125766 | T16182-DP00-P8ZEN-125766 | RESERVE BOILER - AIRCRAFT WARNING LIGHT DRAWING | IFI | 2017-07-02 | 2017-09-18 |  | O |  | PKG-015-RB | 2017-07-06 | 2017-09-18
PT(12) | Electrical | 125767 | T16182-YE03-P8ZEN-125767 | RESERVE BOILER - EARTHING DOCUMENT & DRAWING | IFI | 2017-01-13 | 2017-07-11 |  | O |  | PKG-015-RB | 2017-04-12 | 2017-07-11
PT(12) | Electrical | 125768 | T16182-YE01-P8ZEN-125768 | RESERVE BOILER - LIGHTNING PROTECTION DOCUMENT & DRAWING | IFI | 2017-06-30 | 2018-03-26 |  | O |  | PKG-015-RB | 2017-07-06 | 2018-03-26
PT(12) | Electrical | 125769 | T16182-YQ03-P8ZEN-125769 | RESERVE BOILER - COMMUNICATION SYSTEM DOCUMENT & DRAWING | IFI | 2017-07-28 | 2017-09-18 |  | O |  | PKG-015-RB | 2017-08-30 | 2017-09-18
PT(12) | Mechanical | 126001 | T16182-YD00-P0LAC-126001 | HRSG FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-04-14 | 2017-07-27 | O |  |  | PKG-016-HFWP | 2017-04-12 | 2017-12-21
PT(12) | Mechanical | 126003 | T16182-XG02-P0LAC-126003 | HRSG FEEDWATER PUMP - P&I DIAGRAM | IFR | 2017-04-14 | 2017-07-27 | O |  |  | PKG-016-HFWP | 2017-04-12 | 2017-12-08
PT(12) | Mechanical | 126004 | T16182-YT01-P0LAC-126004 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | IFR | 2017-04-14 | 2017-07-27 | O |  |  | PKG-016-HFWP | 2017-04-12 | 2017-08-16
PT(12) | Electrical | 126005 | T16182-YT01-P0LAC-126005 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | IFI | 2017-05-16 | 2017-12-06 |  |  |  | PKG-016-HFWP | 2017-09-08 | 2017-12-06
PT(12) | Mechanical | 126006 | T16182-YK01-P0LAC-126006 | HRSG FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | IFI | 2017-05-16 |  |  |  |  | PKG-016-HFWP | 2017-05-26 | #VALUE!
PT(12) | Mechanical | 126007 | T16182-YD00-P0LAC-126007 | HRSG FEEDWATER PUMP - NAME PLATE DRAWING | IFI | 2017-06-28 |  |  |  |  | PKG-016-HFWP | 2017-08-30 | #VALUE!
PT(12) | Mechanical | 126009 | T16182-YT01-P0LAC-126009 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | IFI | 2017-06-28 | 2017-12-28 |  |  |  | PKG-016-HFWP | 2017-09-28 | 2018-07-16
PT(12) | Mechanical | 126010 | T16182-YD00-P0LAC-126010 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | IFI | 2017-06-28 | 2017-11-08 |  |  |  | PKG-016-HFWP | 2017-08-25 | 2017-11-08
PT(12) | Instrumentation & Control | 126011 | T16182-YT02-P0LAC-126011 | HRSG FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | IFI | 2017-08-30 |  |  |  |  | PKG-016-HFWP | 2017-09-08 | #VALUE!
PT(12) | Mechanical | 126012 | T16182-DM01-P0LAC-126012 | HRSG FEEDWATER PUMP - INSTALLATION MANUAL | IFI | 2017-12-27 | 2018-07-17 |  |  |  | PKG-016-HFWP | 2018-01-23 | 2018-07-17
PT(12) | Mechanical | 126016 | T16182-YT01-P0LAC-126016 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | IFI | 2017-06-28 |  |  |  |  | PKG-016-HFWP | 2017-11-10 | #VALUE!
PT(12) | Electrical | 126019 | T16182-YD00-P0LAC-126019 | HRSG FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | IFI | 2017-07-28 |  |  |  |  | PKG-016-HFWP | 2017-11-07 | #VALUE!
PT(12) | Mechanical | 126027 | T16182-YK08-P0LAC-126027 | HRSG FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-016-HFWP | 2017-08-28 | #VALUE!
PT(12) | Mechanical | 126051 | T16182-YD00-P0LAC-126051 | FGP FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-08-08 | 2017-11-05 | O |  |  | PKG-017-FFWP | 2017-10-24 | 2018-03-21
PT(12) | Mechanical | 126053 | T16182-XG02-P0LAC-126053 | FGP FEEDWATER PUMP - P&I DIAGRAM | IFR | 2017-08-08 | 2017-11-05 | O |  |  | PKG-017-FFWP | 2017-09-07 | 2018-03-13
PT(12) | Mechanical | 126054 | T16182-YT01-P0LAC-126054 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | IFR | 2017-08-08 | 2017-11-05 | O |  |  | PKG-017-FFWP | 2017-08-16 | 2017-09-19
PT(12) | Electrical | 126055 | T16182-YT01-P0LAC-126055 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | IFI | 2017-08-08 | 2017-11-05 |  |  |  | PKG-017-FFWP | 2017-09-08 | 2017-12-06
PT(12) | Mechanical | 126056 | T16182-YK01-P0LAC-126056 | FGP FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | IFI | 2017-08-08 | 2018-07-16 |  |  |  | PKG-017-FFWP | 2017-11-30 | 2018-07-16
PT(12) | Mechanical | 126057 | T16182-YD00-P0LAC-126057 | FGP FEEDWATER PUMP - NAME PLATE DRAWING | IFI | 2017-08-08 |  |  |  |  | PKG-017-FFWP | 2017-08-30 | #VALUE!
PT(12) | Mechanical | 126059 | T16182-YT01-P0LAC-126059 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | IFI | 2017-08-08 | 2018-07-16 |  |  |  | PKG-017-FFWP | 2017-09-28 | 2018-07-16
PT(12) | Mechanical | 126060 | T16182-YD00-P0LAC-126060 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | IFI | 2017-08-08 | 2017-11-08 |  |  |  | PKG-017-FFWP | 2017-08-25 | 2017-11-08
PT(12) | Instrumentation & Control | 126061 | T16182-YT02-P0LAC-126061 | FGP FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | IFI | 2017-08-08 |  |  |  |  | PKG-017-FFWP | 2017-09-08 | #VALUE!
PT(12) | Mechanical | 126062 | T16182-DM01-P0LAC-126062 | FGP FEEDWATER PUMP - INSTALLATION MANUAL | IFI | 2017-09-25 | 2018-07-26 |  |  |  | PKG-017-FFWP | 2018-01-23 | 2018-07-26
PT(12) | Mechanical | 126066 | T16182-YT01-P0LAC-126066 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | IFI | 2017-09-16 |  |  |  |  | PKG-017-FFWP | 2017-11-10 | #VALUE!
PT(12) | Electrical | 126069 | T16182-YD00-P0LAC-126069 | FGP FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | IFI | 2017-07-29 |  |  |  |  | PKG-017-FFWP | 2017-11-07 | #VALUE!
PT(12) | Mechanical | 126077 | T16182-YK08-P0LAC-126077 | FGP FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-017-FFWP | 2017-08-28 | #VALUE!
PT(12) | Instrumentation & Control | 126301 | T16182-YB11-P0LAC-126301 | HRSG FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | IFI | 2017-12-15 |  |  |  |  | PKG-016-HFWP | 2017-11-24 | #VALUE!
PT(12) | Instrumentation & Control | 126302 | T16182-YS02-P0LAC-126302 | HRSG FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | IFI | 2017-12-15 |  |  |  |  | PKG-016-HFWP | 2017-11-28 | #VALUE!
PT(12) | Instrumentation & Control | 126351 | T16182-YB11-P0LAC-126351 | FGP FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | IFI | 2018-02-15 |  |  |  |  | PKG-017-FFWP | 2017-11-24 | #VALUE!
PT(12) | Instrumentation & Control | 126352 | T16182-YS02-P0LAC-126352 | FGP FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | IFI | 2018-02-15 |  |  |  |  | PKG-017-FFWP | 2017-11-28 | #VALUE!
PT(12) | Mechanical | 126501 | T16182-XS00-P0PCA-126501 | FIN FAN COOLER - SYSTEM DESCRIPTION | IFR | 2017-06-04 | 2017-09-02 | O | O |  | PKG-018-FFC | 2017-05-30 | 2017-10-27
PT(12) | Mechanical | 126502 | T16182-XG02-P0PCA-126502 | FIN FAN COOLER - P&I DIAGRAM | IFR | 2017-06-04 | 2017-09-02 | O | O |  | PKG-018-FFC | 2017-06-05 | 2017-10-16
PT(12) | Mechanical | 126503 | T16182-YD00-P0PCA-126503 | FIN FAN COOLER - GENERAL ARRANGEMENT & PLOT PLAN DRAWING | IFR | 2017-05-05 | 2017-08-03 | O | O |  | PKG-018-FFC | 2017-05-02 | 2017-09-21
PT(12) | Mechanical | 126504 | T16182-XS00-P0PCA-126504 | FIN FAN COOLER - PERFORMANCE CURVE | IFR | 2017-06-04 | 2017-09-02 |  | O |  | PKG-018-FFC | 2017-06-05 | 2017-11-08
PT(12) | Mechanical | 126505 | T16182-YL25-P0PCA-126505 | FIN FAN COOLER - TERMINAL POINT LIST & DRAWING | IFI | 2017-05-05 |  |  | O |  | PKG-018-FFC | 2017-05-02 | #VALUE!
PT(12) | Mechanical | 126506 | T16182-XV00-P0PCA-126506 | FIN FAN COOLER - EQUIPMENT LIST | IFI | 2017-05-05 |  |  | O |  | PKG-018-FFC | 2017-04-28 | #VALUE!
PT(12) | Mechanical | 126507 | T16182-XN00-P0PCA-126507 | FIN FAN COOLER - VALVE LIST | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC | 2017-08-10 | #VALUE!
PT(12) | Mechanical | 126508 | T16182-XK00-P0PCA-126508 | FIN FAN COOLER - BELT PULLEY DATA SHEET | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC | 2017-08-30 | #VALUE!
PT(12) | Mechanical | 126509 | T16182-XS00-P0PCA-126509 | FIN FAN COOLER - FAN MOTOR DATA SHEET | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC | 2017-07-25 | #VALUE!
PT(12) | Mechanical | 126512 | T16182-YK08-P0PCA-126512 | FIN FAN COOLER - FAN OUTLINE DRAWING (WITH MOTOR) | IFI | 2017-08-03 | 2017-12-20 |  | O |  | PKG-018-FFC | 2017-08-14 | 2017-09-15
PT(12) | Mechanical | 126513 | T16182-YK08-P0PCA-126513 | FIN FAN COOLER - VALVE OUTLINE DRAWING | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC | 2017-08-18 | #VALUE!
PT(12) | Mechanical | 126514 | T16182-YK08-P0PCA-126514 | FIN FAN COOLER - PIPING ARRANGEMENT DRAWING | IFI | 2017-08-03 | 2017-12-20 |  | O |  | PKG-018-FFC | 2017-07-28 | 2017-10-16
PT(12) | Mechanical | 126515 | T16182-YK08-P0PCA-126515 | FIN FAN COOLER - PIPING ISOMETRIC DRAWRING | IFI | 2017-10-04 | 2018-01-15 |  | O |  | PKG-018-FFC | 2017-10-16 | 2017-11-23
PT(12) | Mechanical | 126516 | T16182-YK08-P0PCA-126516 | FIN FAN COOLER - PIPE MATERIAL SPECIFICATION | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC | 2017-07-28 | #VALUE!
PT(12) | Mechanical | 126517 | T16182-XH01-P0PCA-126517 | FIN FAN COOLER - PIPE LINE LIST | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC | 2017-08-30 | #VALUE!
PT(12) | Instrumentation & Control | 126519 | T16182-DE00-P0PCA-126519 | FIN FAN COOLER - CONTROL DESCRIPTION (PHILOSOPHY) | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC | 2017-07-28 | #VALUE!
PT(12) | Instrumentation & Control | 126522 | T16182-YF00-P0PCA-126522 | FIN FAN COOLER - LOGIC / FUNCTIONAL LOOP DIAGRAMS | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC | 2017-10-13 | #VALUE!
PT(12) | Instrumentation & Control | 126523 | T16182-YL00-P0PCA-126523 | FIN FAN COOLER - INSTRUMENT LIST | IFI | 2017-06-04 |  |  | O |  | PKG-018-FFC | 2017-06-05 | #VALUE!
PT(12) | Instrumentation & Control | 126524 | T16182-YL01-P0PCA-126524 | FIN FAN COOLER - INSTRUMENT CATALOG | IFI | 2017-06-04 |  |  | O |  | PKG-018-FFC | 2017-06-05 | #VALUE!
PT(12) | Instrumentation & Control | 126525 | T16182-YK00-P0PCA-126525 | FIN FAN COOLER - INSTRUMENT INSTALLATION DETAIL DRAWING | IFI | 2017-06-20 |  |  | O |  | PKG-018-FFC | 2017-07-12 | #VALUE!
PT(12) | Instrumentation & Control | 126526 | T16182-YL01-P0PCA-126526 | FIN FAN COOLER - INSTRUMENT DATA SHEET | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC | 2017-07-07 | #VALUE!
PT(12) | Electrical | 126527 | T16182-YL01-P0PCA-126527 | FIN FAN COOLER - DRIVE LIST (MOVS, MOTORS, CONTROL VALVES, SOLENOID VALVES, ETC..) | IFI | 2017-06-04 |  |  | O |  | PKG-018-FFC | 2017-05-30 | #VALUE!
PT(12) | Electrical | 126529 | T16182-YT02-P0PCA-126529 | FIN FAN COOLER - RACEWAY DRAWING | IFI | 2017-08-03 | 2018-11-27 |  | O |  | PKG-018-FFC | 2017-10-13 | 2018-11-27
PT(12) | Electrical | 126530 | T16182-YD00-P0PCA-126530 | JUNCTION BOX OUTLINE AND LAYOUT DRAWING | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC | 2017-07-11 | #VALUE!
PT(12) | Electrical | 126533 | T16182-YB03-P0PCA-126533 | FIN FAN COOLER - WIRING DIAGRAMS FOR JUNCTION BOXES | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC | 2017-07-13 | #VALUE!
PT(12) | Civil | 126538 | T16182-XK00-P0PCA-126538 | FIN FAN COOLER - FOUNDATION DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING (INCLUDE AUXILIARY EQUIPMENT) | IFI | 2017-06-20 | 2017-08-24 |  | O |  | PKG-018-FFC | 2017-06-14 | 2017-08-24
PT(12) | Civil | 126539 | T16182-XK00-P0PCA-126539 | FIN FAN COOLER - STEEL STRUCTURE CALCULATION | IFI | 2017-05-21 |  |  | O |  | PKG-018-FFC | 2017-05-23 | #VALUE!
PT(12) | Electrical | 126540 | T16182-YK09-P0PCA-126540 | FIN FAN COOLER – DETAIL DRAWING FOR CLEANING COMPRESSOR | IFI | 2018-11-01 |  |  |  |  | PKG-018-FFC | 2018-11-02 | #VALUE!
PT(12) | Mechanical | 127001 | T16182-YD00-P0LCB-127001 | FGP COP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-019-COP | 2017-07-27 | 2017-11-14
PT(12) | Mechanical | 127002 | T16182-XG02-P0LCB-127002 | FGP COP - P&I DIAGRAM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-019-COP | 2017-08-30 | 2017-11-17
PT(12) | Mechanical | 127003 | T16182-YT01-P0LCB-127003 | FGP COP - DATA SHEET & CHARACTERISTIC CURVE | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-019-COP | 2017-07-27 | 2017-09-01
PT(12) | Mechanical | 127004 | T16182-YK09-P0LCB-127004 | FGP COP - PUMP SECTIONAL DRAWING | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-019-COP | 2017-08-30 | 2017-11-21
PT(12) | Mechanical | 127005 | T16182-YT01-P0LCB-127005 | FGP COP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP | 2017-09-15 | #VALUE!
PT(12) | Mechanical | 127006 | T16182-YT01-P0LCB-127006 | FGP COP - COUPLING SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP | 2017-09-15 | #VALUE!
PT(12) | Mechanical | 127007 | T16182-YT01-P0LCB-127007 | FGP COP - SUCTION STRAINER SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP | 2017-09-01 | #VALUE!
PT(12) | Mechanical | 127009 | T16182-YD00-P0LCB-127009 | FGP COP - FOUNDATION DRAWINGS | IFI | 2017-07-15 | 2017-12-12 |  |  |  | PKG-019-COP | 2017-07-27 | 2017-11-14
PT(12) | Electrical | 127010 | T16182-YM01-P0LCB-127010 | FGP COP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-15 |  |  |  |  | PKG-019-COP | 2017-07-27 | #VALUE!
PT(12) | Instrumentation & Control | 127011 | T16182-YK09-P0LCB-127011 | FGP COP - EMERGENCY PUSH BUTTON DRAWING | IFI | 2017-07-15 |  |  |  |  | PKG-019-COP | 2017-09-27 | #VALUE!
PT(12) | Instrumentation & Control | 127013 | T16182-YL00-P0LCB-127013 | FGP COP - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-07-15 |  |  |  |  | PKG-019-COP | 2017-09-15 | #VALUE!
PT(12) | Instrumentation & Control | 127015 | T16182-YK00-P0LCB-127015 | FGP COP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-019-COP | 2017-09-29 | #VALUE!
PT(12) | Instrumentation & Control | 127016 | T16182-YT01-P0LCB-127016 | FGP COP - VMS SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP | 2017-09-27 | #VALUE!
PT(12) | Mechanical | 127018 | T16182-YL22-P0LCB-127018 | FGP COP - NAME PLATE DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-019-COP | 2017-08-30 | #VALUE!
PT(12) | Mechanical | 127031 | T16182-YD00-P0LCB-127031 | CEP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-020-CEP | 2017-07-27 | 2017-09-01
PT(12) | Mechanical | 127032 | T16182-XG02-P0LCB-127032 | CEP - P&I DIAGRAM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-020-CEP | 2017-08-30 | 2017-12-14
PT(12) | Mechanical | 127033 | T16182-YT01-P0LCB-127033 | CEP - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-15 |  |  |  |  | PKG-020-CEP | 2017-07-27 | #VALUE!
PT(12) | Mechanical | 127034 | T16182-YK09-P0LCB-127034 | CEP - PUMP SECTIONAL DRAWING | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-020-CEP | 2017-07-27 | 2017-09-01
PT(12) | Mechanical | 127035 | T16182-YT01-P0LCB-127035 | CEP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-020-CEP | 2017-09-15 | #VALUE!
PT(12) | Mechanical | 127036 | T16182-YT01-P0LCB-127036 | CEP - COUPLING SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-020-CEP | 2017-09-15 | #VALUE!
PT(12) | Mechanical | 127037 | T16182-YT01-P0LCB-127037 | CEP - SUCTION STRAINER SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-020-CEP | 2017-08-30 | #VALUE!
PT(12) | Mechanical | 127038 | T16182-YD00-P0LCB-127038 | CEP - FOUNDATION DRAWINGS | IFI | 2017-07-15 | 2017-12-12 |  |  |  | PKG-020-CEP | 2017-07-27 | 2017-09-01
PT(12) | Electrical | 127039 | T16182-YM01-P0LCB-127039 | CEP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-15 |  |  |  |  | PKG-020-CEP | 2017-08-30 | #VALUE!
PT(12) | Instrumentation & Control | 127040 | T16182-YL00-P0LCB-127040 | CEP - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-07-15 |  |  |  |  | PKG-020-CEP | 2017-09-15 | #VALUE!
PT(12) | Instrumentation & Control | 127041 | T16182-YK00-P0LCB-127041 | CEP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-020-CEP | 2017-10-13 | #VALUE!
PT(12) | Mechanical | 127042 | T16182-YL22-P0LCB-127042 | CEP - NAME PLATE DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-020-CEP | 2017-08-30 | #VALUE!
PT(12) | Mechanical | 127501 | T16182-YD00-P0LCB-127501 | AIR COMPRESSOR - GENERAL ARRANGEMENT DRAWING | IFR | 2017-04-26 | 2017-06-25 | O | O |  | PKG-021-AC | 2017-04-26 | 2017-09-07
PT(12) | Mechanical | 127502 | T16182-XG02-P0SCA-127502 | AIR COMPRESSOR - P&I DIAGRAM | IFR | 2017-04-26 | 2017-06-15 | O | O | O | PKG-021-AC | 2017-04-26 | 2017-09-05
PT(12) | Mechanical | 127503 | T16182-XW01-P0SCA-127503 | AIR COMPRESSOR - AIR COMPRESSOR SPECIFICATION | IFR | 2017-04-26 | 2017-07-25 |  | O |  | PKG-021-AC | 2017-04-26 | 2017-09-01
PT(12) | Mechanical | 127504 | T16182-XW01-P0SCA-127504 | AIR COMPRESSOR - AIR DRYER SPECIFICATION | IFI | 2017-04-26 |  |  | O |  | PKG-021-AC | 2017-04-26 | #VALUE!
PT(12) | Mechanical | 127505 | T16182-XW01-P0SCA-127505 | AIR COMPRESSOR - AIR RECEIVER SPECIFICATION | IFI | 2017-04-26 |  |  | O |  | PKG-021-AC | 2017-04-26 | #VALUE!
PT(12) | Mechanical | 127506 | T16182-XW01-P0SCA-127506 | AIR COMPRESSOR - AIR FILTER SPECIFICATION | IFI | 2017-04-26 |  |  | O |  | PKG-021-AC | 2017-04-26 | #VALUE!
PT(12) | Civil | 127509 | T16182-XB00-P0SCA-127509 | AIR COMPRESSOR - FOUNDATION DRAWINGS | IFI | 2017-04-26 | 2017-07-07 |  | O |  | PKG-021-AC | 2017-04-26 | 2017-09-12
PT(12) | Electrical | 127510 | T16182-YU02-P0SCA-127510 | AIR COMPRESSOR - SINGLE LINE DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-021-AC | 2017-05-30 | #VALUE!
PT(12) | Electrical | 127511 | T16182-YV02-P0SCA-127511 | AIR COMPRESSOR - SCHEMATIC & WIRING DIAGRAM | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC | 2017-05-30 | #VALUE!
PT(12) | Instrumentation & Control | 127514 | T16182-YF02-P0SCA-127514 | AIR COMPRESSOR - CONTROL DESCRIPTION (PHILOSOPHY) | IFI | 2017-05-26 |  |  | O | O | PKG-021-AC | 2017-05-29 | #VALUE!
PT(12) | Instrumentation & Control | 127515 | T16182-YD05-P0SCA-127515 | AIR COMPRESSOR - PLC HMI GRAPHICS | IFI | 2017-06-25 |  |  | O |  | PKG-021-AC | 2017-06-26 | #VALUE!
PT(12) | Instrumentation & Control | 127516 | T16182-YL01-P0SCA-127516 | AIR COMPRESSOR - PLC HARDWIRED IO LIST | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC | 2017-05-29 | #VALUE!
PT(12) | Instrumentation & Control | 127517 | T16182-YL01-P0SCA-127517 | AIR COMPRESSOR - DATALINK INTERFACE IO LIST | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC | 2017-05-29 | #VALUE!
PT(12) | Instrumentation & Control | 127518 | T16182-YF00-P0SCA-127518 | AIR COMPRESSOR - CONTROL LOGIC & LOOP DIAGRAM | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC | 2017-05-29 | #VALUE!
PT(12) | Instrumentation & Control | 127520 | T16182-YL00-P0SCA-127520 | AIR COMPRESSOR - INSTRUMENT LIST | IFI | 2017-06-16 |  |  | O |  | PKG-021-AC | 2017-06-12 | #VALUE!
PT(12) | Instrumentation & Control | 127521 | T16182-CV03-P0SCA-127521 | AIR COMPRESSOR - INSTRUMENT SPECIFICATION | IFI | 2017-06-16 |  |  | O |  | PKG-021-AC | 2017-06-12 | #VALUE!
PT(12) | Instrumentation & Control | 127522 | T16182-YK00-P0SCA-127522 | AIR COMPRESSOR - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-06-16 | 2018-07-05 |  | O |  | PKG-021-AC | 2017-06-16 | 2018-07-05
PT(12) | Instrumentation & Control | 127523 | T16182-YR05-P0SCA-127523 | AIR COMPRESSOR - PLC PANEL DRAWING | IFI | 2017-06-02 |  |  | O |  | PKG-021-AC | 2017-05-29 | #VALUE!
PT(12) | Mechanical | 127524 | T16182-XF00-P0SCA-127524 | AIR COMPRESSOR - NAME PLATE DRAWING | IFI | 2017-07-28 |  |  | O |  | PKG-021-AC | 2017-07-25 | #VALUE!
PT(12) | Mechanical | 127525 | T16182-XN00-P0SCA-127525 | AIR COMPRESSOR - VALVE LIST | IFI | 2017-06-13 |  |  | O |  | PKG-021-AC | 2017-06-12 | #VALUE!
PT(12) | Mechanical | 127526 | T16182-YT01-P0SCA-127526 | AIR COMPRESSOR - VALVE SPECIFICATION | IFI | 2017-06-13 |  |  | O |  | PKG-021-AC | 2017-06-12 | #VALUE!
PT(12) | Instrumentation & Control | 127546 | T16182-YD16-P0SCA-127546 | AIR COMPRESSOR - EMBEDDED CONDUIT LAYOUT FOR CONTROL CABLES (FROM MCP TO EQUIPMENT) | IFI | 2017-07-11 |  |  | O |  | PKG-021-AC | 2017-07-11 | #VALUE!
PT(12) | Instrumentation & Control | 127548 | T16182-YV02-P0SCA-127548 | AIR COMPRESSOR – I&C CABLE INTERCONNECTION WIRING DIAGRAM | IFI | 2019-02-15 |  |  |  |  | PKG-021-AC | 2019-02-14 | #VALUE!
PT(12) | Mechanical | 127555 | T16182-YD00-P0LCB-127555 | AIR COMPRESSOR - AIR CHILLER - GENERAL ARRANGEMENT DRAWING | IFR | 2018-12-17 | 2019-02-28 |  |  |  | PKG-021-AC | 2018-12-17 | 2019-06-05
PT(12) | Mechanical | 127556 | T16182-XW01-P0SCA-127556 | AIR COMPRESSOR - AIR CHILLER - DATA SHEET | IFR | 2018-12-17 | 2019-02-28 |  |  |  | PKG-021-AC | 2018-12-17 | 2019-06-04
PT(12) | Mechanical | 127557 | T16182-XG02-P0SCA-127557 | AIR COMPRESSOR - AIR CHILLER - P&I DIAGRAM | IFR | 2018-12-17 | 2019-02-28 |  |  |  | PKG-021-AC | 2018-12-17 | 2019-06-21
PT(12) | Mechanical | 128001 | T16182-YD00-P0SMM-128001 | CRANE - GA DRAWING FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-05-10 | 2017-11-28 |  |  |  | PKG-022-CR | 2017-05-12 | 2017-09-15
PT(12) | Mechanical | 128002 | T16182-YD00-P0SMS-128002 | CRANE - GA DRAWING FOR WORKSHOP CRANE | IFI | 2017-09-29 | 2017-11-28 |  |  |  | PKG-022-CR | 2017-07-18 | 2017-11-08
PT(12) | Mechanical | 128004 | T16182-YT01-P0SMM-128004 | CRANE - DATA SHEETS FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-05-10 | 2017-09-15 |  |  |  | PKG-022-CR | 2017-05-12 | 2017-09-15
PT(12) | Mechanical | 128005 | T16182-YT01-P0SMS-128005 | CRANE - DATA SHEETS FOR WORKSHOP CRANE | IFI | 2017-09-29 | 2017-11-08 |  |  |  | PKG-022-CR | 2017-07-18 | 2017-11-08
PT(12) | Mechanical | 128007 | T16182-YK09-P0SMM-128007 | CRANE - MECHNICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-07-29 | 2018-01-19 |  |  |  | PKG-022-CR | 2017-09-12 | 2018-01-19
PT(12) | Mechanical | 128008 | T16182-YK09-P0SMS-128008 | CRANE - MECHNICAL DETAIL FOR WORKSHOP CRANE | IFI | 2017-12-29 | 2018-01-19 |  |  |  | PKG-022-CR | 2017-11-21 | 2018-01-19
PT(12) | Electrical | 128010 | T16182-YS18-P0SMM-128010 | CRANE - ELECTRICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-07-29 | 2018-01-19 |  |  |  | PKG-022-CR | 2017-09-13 | 2018-01-19
PT(12) | Electrical | 128011 | T16182-YS18-P0SMS-128011 | CRANE - ELECTRICAL DETAIL FOR WORKSHOP CRANE | IFI | 2017-12-29 | 2018-01-19 |  |  |  | PKG-022-CR | 2017-11-21 | 2018-01-19
PT(12) | Mechanical | 128013 | T16182-YD00-P0SML-128013 | CRANE - GA DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-09-29 | 2017-11-28 |  |  |  | PKG-022-CR | 2017-05-29 | 2017-11-02
PT(12) | Mechanical | 128014 | T16182-YD00-P0SMQ-128014 | HOIST - GA DRAWING FOR FF PUMP HOUSE HOIST | IFI | 2017-10-29 | 2018-03-28 |  |  |  | PKG-022-CR | 2017-12-12 | 2018-02-23
PT(12) | Mechanical | 128015 | T16182-YD00-P0SMU-128015 | HOIST - GA DRAWING FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2017-11-29 | 2018-03-28 |  |  |  | PKG-022-CR | 2017-12-12 | 2018-02-23
PT(12) | Mechanical | 128016 | T16182-YD00-P0SMG-128016 | HOIST - GA DRAWING FOR DM WATER TREATMENT HOIST | IFI | 2017-12-29 | 2018-03-28 |  |  |  | PKG-022-CR | 2017-12-12 | 2018-02-23
PT(12) | Mechanical | 128017 | T16182-YD00-P0SMU-128017 | HOIST - GA DRAWING FOR CHAIN BLOCK | IFI | 2018-01-29 |  |  |  |  | PKG-022-CR | 2018-02-23 | 2018-03-29
PT(12) | Mechanical | 128018 | T16182-YT01-P0SML-128018 | CRANE - DATA SHEETS FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-09-29 | 2017-11-02 |  |  |  | PKG-022-CR | 2017-05-29 | 2017-11-02
PT(12) | Mechanical | 128019 | T16182-YT01-P0SMQ-128019 | HOIST - DATA SHEETS FOR FF PUMP HOUSE HOIST | IFI | 2017-10-29 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128020 | T16182-YT01-P0SMU-128020 | HOIST - DATA SHEETS FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2017-11-29 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128021 | T16182-YT01-P0SMG-128021 | HOIST - DATA SHEETS FOR DM WATER TREATMENT HOIST | IFI | 2017-12-29 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128022 | T16182-YT01-P0SMU-128022 | HOIST - DATA SHEETS FOR CHAIN BLOCK | IFI | 2018-01-29 |  |  |  |  | PKG-022-CR | 2018-02-23 | 2018-03-29
PT(12) | Mechanical | 128023 | T16182-YK09-P0SML-128023 | CRANE - MECHNICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-12-29 | 2018-05-28 |  |  |  | PKG-022-CR | 2017-09-12 | 2018-01-19
PT(12) | Mechanical | 128024 | T16182-YK09-P0SMQ-128024 | HOIST - MECHANICAL DETAIL FOR FF PUMP HOUSE HOIST | IFI | 2018-01-29 | 2018-05-28 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Mechanical | 128025 | T16182-YK09-P0SMU-128025 | HOIST - MECHANICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2018-02-28 | 2018-05-28 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Mechanical | 128026 | T16182-YK09-P0SMG-128026 | HOIST - MECHANICAL DETAIL FOR DM WATER TREATMENT HOIST | IFI | 2018-03-29 | 2018-05-28 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Electrical | 128027 | T16182-YS18-P0SML-128027 | CRANE - ELECTRICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-12-29 | 2018-01-19 |  |  |  | PKG-022-CR | 2017-09-13 | 2018-01-19
PT(12) | Mechanical | 128028 | T16182-YD00-P0SMC-128028 | HOIST - GA DRAWING FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2017-12-12 | 2018-02-23
PT(12) | Mechanical | 128029 | T16182-YD00-P0SMS-128029 | HOIST - GA DRAWING FOR WAREHOUSE HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2017-12-12 | 2018-02-23
PT(12) | Mechanical | 128030 | T16182-YD00-P0SMG-128030 | HOIST - GA DRAWING FOR WASTE WATER TREATMENT HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2017-12-12 | 2018-02-23
PT(12) | Mechanical | 128031 | T16182-YD00-P0SMM-128031 | HOIST - GA DRAWING FOR CPP HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2017-12-12 | 2018-02-23
PT(12) | Mechanical | 128032 | T16182-YD00-P0SMU-128032 | JIB CRANE - GA DRAWING FOR AIR COOLED CONDENSER JIB CRANE | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-01-03 | 2018-02-23
PT(12) | Mechanical | 128033 | T16182-YT01-P0SMC-128033 | HOIST - DATA SHEETS FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128034 | T16182-YT01-P0SMS-128034 | HOIST - DATA SHEETS FOR WAREHOUSE HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128035 | T16182-YT01-P0SMG-128035 | HOIST - DATA SHEETS FOR WASTE WATER TREATMENT HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128036 | T16182-YT01-P0SMM-128036 | HOIST - DATA SHEETS FOR CPP HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128037 | T16182-YT01-P0SMU-128037 | JIB CRANE - DATA SHEETS FOR AIR COOLED CONDENSER JIB CRANE | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR | 2017-12-21 | 2018-02-09
PT(12) | Mechanical | 128038 | T16182-YK09-P0SMC-128038 | HOIST - MECHANICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Mechanical | 128039 | T16182-YK09-P0SMS-128039 | HOIST - MECHANICAL DETAIL FOR WAREHOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Mechanical | 128040 | T16182-YK09-P0SMG-128040 | HOIST - MECHANICAL DETAIL FOR WASTE WATER TREATMENT HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Mechanical | 128041 | T16182-YK09-P0SMM-128041 | HOIST - MECHANICAL DETAIL FOR CPP HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Mechanical | 128042 | T16182-YK09-P0SMU-128042 | JIB CRANE - MECHANICAL DETAIL FOR AIR COOLED CONDENSER JIB CRANE | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-01-29 | 2018-02-23
PT(12) | Electrical | 128043 | T16182-YS18-P0SMC-128043 | HOIST - ELECTRICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Electrical | 128044 | T16182-YS18-P0SMS-128044 | HOIST - ELECTRICAL DETAIL FOR WAREHOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Electrical | 128045 | T16182-YS18-P0SMQ-128045 | HOIST - ELECTRICAL DETAIL FOR FF PUMP HOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Electrical | 128046 | T16182-YS18-P0SMU-128046 | HOIST - ELECTRICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Electrical | 128047 | T16182-YS18-P0SMG-128047 | HOIST - ELECTRICAL DETAIL FOR DM WATER TREATMENT HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Electrical | 128048 | T16182-YS18-P0SMG-128048 | HOIST - ELECTRICAL DETAIL FOR WASTE WATER TREATMENT HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Electrical | 128049 | T16182-YS18-P0SMM-128049 | HOIST - ELECTRICAL DETAIL FOR CPP HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Mechanical | 128051 | T16182-YD00-P0SMG-128051 | JIB CRANE - GA DRAWING FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | IFI | 2018-01-30 | 2018-03-30 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Mechanical | 128052 | T16182-YD00-P0SMG-128052 | JIB CRANE - DATA SHEETS FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | IFI | 2018-01-30 | 2018-03-30 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Mechanical | 128053 | T16182-YD00-P0SMG-128053 | JIB CRANE - MECHANICAL DETAIL FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | IFI | 2018-01-30 | 2018-03-30 |  |  |  | PKG-022-CR | 2018-02-02 | 2018-02-23
PT(12) | Mechanical | 128060 | T16182-YD00-P0SMS-128060 | PORTABLE GANTRY - GA DRAWING | IFI | 2020-01-10 | [5 empty] | 2020-01-09 | #VALUE!
PT(12) | Mechanical | 128070 | T16182-YD00-P0SMU-128070 | HOIST - GA DRAWING FOR ST GSUT | IFI | 2020-01-10 | [5 empty] | 2020-01-09 | #VALUE!
PT(12) | Mechanical | 128101 | T16182-YD00-P0SMM-128101 | CRANE - NAME PLATE DRAWING FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-12-29 |  |  |  |  | PKG-022-CR | 2017-10-18 | #VALUE!
PT(12) | Mechanical | 128102 | T16182-YD00-P0SMS-128102 | CRANE - NAME PLATE DRAWING FOR WORKSHOP CRANE | IFI | 2017-12-29 |  |  |  |  | PKG-022-CR | 2017-10-18 | #VALUE!
PT(12) | Mechanical | 128103 | T16182-YD00-P0SML-128103 | CRANE - NAME PLATE DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-12-29 |  |  |  |  | PKG-022-CR | 2017-10-18 | #VALUE!
PT(12) | Mechanical | 128501 | T16182-YD00-P0GM-128501 | SUMP PUMP - PUMP OUTLINE DRAWING | IFI | 2017-08-07 | 2017-11-10 |  |  |  | PKG-023-SUP | 2017-08-29 | 2017-11-23
PT(12) | Mechanical | 128502 | T16182-YT01-P0GM-128502 | SUMP PUMP - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-08-07 |  |  |  |  | PKG-023-SUP | 2017-08-29 | #VALUE!
PT(12) | Mechanical | 128503 | T16182-YD00-P0GM-128503 | SUMP PUMP - PUMP SECTIONAL DRAWING | IFI | 2017-08-07 |  |  |  |  | PKG-023-SUP | 2017-08-29 | #VALUE!
PT(12) | Mechanical | 128504 | T16182-XK00-P0GM-128504 | SUMP PUMP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-09-18 |  |  |  |  | PKG-023-SUP | 2017-09-11 | #VALUE!
PT(12) | Mechanical | 128505 | T16182-XK00-P0GM-128505 | SUMP PUMP - COUPLING SPECIFICATION | IFI | 2017-09-18 |  |  |  |  | PKG-023-SUP | 2017-09-11 | #VALUE!
PT(12) | Civil | 128506 | T16182-XB00-P0GM-128506 | SUMP PUMP - FOUNDATION DRAWINGS | IFI | 2017-08-07 | 2017-11-10 |  |  |  | PKG-023-SUP | 2017-08-29 | 2018-01-04
PT(12) | Electrical | 128507 | T16182-XW01-P0GM-128507 | SUMP PUMP - MOTOR SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP | 2017-09-01 | #VALUE!
PT(12) | Instrumentation & Control | 128508 | T16182-CV03-P0GM-128508 | SUMP PUMP - INSTRUMENT SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP | 2017-09-07 | #VALUE!
PT(12) | Instrumentation & Control | 128509 | T16182-YK00-P0GM-128509 | SUMP PUMP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP | 2017-09-07 | 2018-10-16
PT(12) | Mechanical | 128510 | T16182-XF00-P0GM-128510 | SUMP PUMP - NAME PLATE DRAWING | IFI | 2017-09-29 |  |  |  |  | PKG-023-SUP | 2017-09-11 | #VALUE!
PT(12) | Electrical | 128511 | T16182-YR05-P0GM-128511 | SUMP PUMP - SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING FOR WASTE WATER TRANSFER SYSTEM | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP | 2017-09-08 | #VALUE!
PT(12) | Instrumentation & Control | 128512 | T16182-YL00-P0GM-128512 | SUMP PUMP - INSTRUMENT LIST | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP | 2017-09-07 | #VALUE!
PT(12) | Mechanical | 129001 | T16182-YD00-P0GHC-129001 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - GENERAL ARRANGEMENT DRAWING | IFI | 2017-04-28 | 2017-09-25 |  | O |  | PKG-024-BOPP | 2017-05-02 | 2017-09-01
PT(12) | Mechanical | 129002 | T16182-YT01-P0GHC-129002 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-04-28 |  |  | O |  | PKG-024-BOPP | 2017-04-28 | #VALUE!
PT(12) | Mechanical | 129003 | T16182-YK09-P0GHC-129003 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - PUMP SECTIONAL DRAWING | IFI | 2017-04-30 | 2017-09-27 |  | O |  | PKG-024-BOPP | 2017-04-28 | 2017-10-18
PT(12) | Mechanical | 129004 | T16182-YT01-P0GHC-129004 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MECHANICAL SEAL SPECIFICATION | IFI | 2017-05-31 |  |  | O |  | PKG-024-BOPP | 2017-06-14 | #VALUE!
PT(12) | Electrical | 129008 | T16182-YM01-P0GHC-129008 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-05-19 |  |  | O |  | PKG-024-BOPP | 2017-06-09 | #VALUE!
PT(12) | Instrumentation & Control | 129011 | T16182-YL00-P0GHC-129011 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-05-19 |  |  | O |  | PKG-024-BOPP | 2017-06-14 | #VALUE!
PT(12) | Instrumentation & Control | 129013 | T16182-YK00-P0GHC-129013 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-06-30 |  |  | O |  | PKG-024-BOPP | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 129014 | T16182-YL22-P0GHC-129014 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - NAME PLATE DRAWING | IFI | 2017-06-30 |  |  | O |  | PKG-024-BOPP | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 129031 | T16182-YD00-P0GHC-129031 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - GENERAL ARRANGEMENT DRAWING | IFI | 2017-07-13 | 2017-12-10 |  |  |  | PKG-024-BOPP | 2017-05-02 | 2017-09-01
PT(12) | Mechanical | 129032 | T16182-YT01-P0GHC-129032 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-13 |  |  |  |  | PKG-024-BOPP | 2017-04-28 | #VALUE!
PT(12) | Mechanical | 129033 | T16182-YK09-P0GHC-129033 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - PUMP SECTIONAL DRAWING | IFI | 2017-07-29 | 2017-12-26 |  |  |  | PKG-024-BOPP | 2017-04-28 | 2017-10-18
PT(12) | Mechanical | 129034 | T16182-YT01-P0GHC-129034 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MECHANICAL SEAL SPECIFICATION | IFI | 2017-08-29 |  |  |  |  | PKG-024-BOPP | 2017-06-14 | #VALUE!
PT(12) | Electrical | 129035 | T16182-YM01-P0GHC-129035 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-13 |  |  |  |  | PKG-024-BOPP | 2017-06-09 | #VALUE!
PT(12) | Instrumentation & Control | 129036 | T16182-YL00-P0GHC-129036 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-07-13 |  |  |  |  | PKG-024-BOPP | 2017-06-14 | #VALUE!
PT(12) | Instrumentation & Control | 129037 | T16182-YK00-P0GHC-129037 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-024-BOPP | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 129038 | T16182-YL22-P0GHC-129038 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - NAME PLATE DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-024-BOPP | 2017-07-11 | #VALUE!
PT(12) | Mechanical | 129050 | T16182-YT01-P0GHC-129050 | CHILLED WATER DISTRIBUTION PUMP - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-10-11 |  |  |  |  | PKG-024-BOPP | 2017-10-16 | #VALUE!
PT(12) | Mechanical | 129051 | T16182-YD00-P0GHC-129051 | CHILLED WATER DISTRIBUTION PUMP - GENERAL ARRANGEMENT DRAWING | IFI | 2017-10-11 | 2017-12-11 |  |  |  | PKG-024-BOPP | 2017-10-16 | 2017-11-28
PT(12) | Mechanical | 129053 | T16182-YK09-P0GHC-129053 | CHILLED WATER DISTRIBUTION PUMP - PUMP SECTIONAL DRAWING | IFI | 2017-10-11 | 2017-12-11 |  |  |  | PKG-024-BOPP | 2017-10-13 | 2017-11-28
PT(12) | Mechanical | 129055 | T16182-YT01-P0GHC-129055 | CHILLED WATER DISTRIBUTION PUMP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-10-18 |  |  |  |  | PKG-024-BOPP | 2017-11-01 | #VALUE!
PT(12) | Mechanical | 129056 | T16182-YL22-P0GHC-129056 | CHILLED WATER DISTRIBUTION PUMP - NAME PLATE DRAWING | IFI | 2017-10-11 |  |  |  |  | PKG-024-BOPP | 2017-10-13 | #VALUE!
PT(12) | Mechanical | 129060 | T16182-YM01-P0GHC-129060 | CHILLED WATER DISTRIBUTION PUMP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-10-11 |  |  |  |  | PKG-024-BOPP | 2017-10-13 | #VALUE!
PT(12) | Instrumentation & Control | 129063 | T16182-YL00-P0GHC-129063 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-10-18 |  |  |  |  | PKG-024-BOPP | 2017-11-01 | #VALUE!
PT(12) | Instrumentation & Control | 129064 | T16182-YK00-P0GHC-129064 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-10-18 |  |  |  |  | PKG-024-BOPP | 2017-11-01 | #VALUE!
MCH(13) | Mechanical | 130001 | T16182-XS00-P0GCF-130001 | SYSTEM DESCRIPTION FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 | O | O |  | PKG-025-WT | 2016-11-03 | 2017-06-29
MCH(13) | Mechanical | 130002 | T16182-YD00-P0GCF-130002 | GENERAL ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 | O | O |  | PKG-025-WT | 2017-02-15 | 2017-07-11
MCH(13) | Mechanical | 130003 | T16182-XG07-P0GCF-130003 | PROCESS FLOW DIAGRAM FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 |  | O |  | PKG-025-WT | 2017-02-15 | 2017-07-11
MCH(13) | Mechanical | 130004 | T16182-XG02-P0GCF-130004 | PIPING & INSTRUMENT DIAGRAM FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 | O | O |  | PKG-025-WT | 2017-02-15 | 2017-07-11
MCH(13) | Mechanical | 130005 | T16182-XW03-P0GCF-130005 | CALCULATION SHEET FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-05 |  | O |  | PKG-025-WT | 2017-02-15 | 2017-07-11
MCH(13) | Electrical | 130006 | T16182-YD00-P0GCF-130006 | MCC ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-07-25 |  | O |  | PKG-025-WT | 2017-04-07 | 2017-09-08
MCH(13) | Instrumentation & Control | 130007 | T16182-YR05-P0GCF-130007 | CONTROL PANEL ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-07-07 |  | O |  | PKG-025-WT | 2017-02-22 | 2017-09-12
MCH(13) | Mechanical | 130008 | T16182-XN00-P0GCF-130008 | VALVE LIST FOR WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-06-30 |  | O |  | PKG-025-WT | 2017-02-22 | 2017-08-28
MCH(13) | Instrumentation & Control | 130009 | T16182-YL00-P0GCF-130009 | INSTRUMENT LIST FOR WATER TREATMENT PLANT | IFI | 2017-03-06 |  |  | O |  | PKG-025-WT | 2017-02-22 | #VALUE!
MCH(13) | Electrical | 130010 | T16182-YU02-P0GCF-130010 | SINGLE LINE DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-07-25 |  | O |  | PKG-025-WT | 2017-04-07 | 2017-09-08
MCH(13) | Instrumentation & Control | 130011 | T16182-YF02-P0GCF-130011 | CONTROL CONFIGURATION DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 |  |  | O |  | PKG-025-WT | 2017-02-22 | #VALUE!
MCH(13) | Mechanical | 130012 | T16182-YK09-P0GCF-130012 | EQUIPMENT ASSEMBLY DRAWING FOR WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT | 2017-04-03 | 2017-08-28
MCH(13) | Mechanical | 130013 | T16182-XH01-P0GCF-130013 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-07-28 |  | O |  | PKG-025-WT | 2017-04-03 | 2017-09-29
MCH(13) | Mechanical | 130014 | T16182-YT01-P0GCF-130014 | TEHCNICAL DATA SHEET FOR WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-07-20 |  | O |  | PKG-025-WT | 2017-04-03 | 2017-08-31
MCH(13) | Electrical | 130015 | T16182-YE00-P0GCF-130015 | CABLE TRAY LAYOUT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 | 2018-03-30 |  | O |  | PKG-025-WT | 2017-04-28 | 2018-03-30
MCH(13) | Instrumentation & Control | 130016 | T16182-YK00-P0GCF-130016 | HOOK - UP DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 |  |  | O |  | PKG-025-WT | 2017-04-28 | #VALUE!
MCH(13) | Electrical | 130017 | T16182-YU03-P0GCF-130017 | SCHEMATIC AND WIRING DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 | 2017-08-31 |  | O |  | PKG-025-WT | 2017-04-28 | 2017-09-12
MCH(13) | Instrumentation & Control | 130018 | T16182-YF00-P0GCF-130018 | CONTROL LOOP & LOGIC DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 |  |  | O |  | PKG-025-WT | 2017-04-28 | #VALUE!
MCH(13) | Mechanical | 130019 | T16182-YD00-P0GCF-130019 | SLEEVE AND WALL OPENING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT | 2017-04-03 | 2017-07-11
MCH(13) | Instrumentation & Control | 130035 | T16182-YL01-P0GCF-130035 | PLC IO LIST FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 |  |  | O |  | PKG-025-WT | 2017-04-07 | #VALUE!
MCH(13) | Mechanical | 130042 | T16182-XB02-P0GCF-130042 | FOUNDATION AND LOADING DATA FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT | 2017-04-03 | 2017-07-11
MCH(13) | Mechanical | 130055 | T16182-CV03-P0GCF-130055 | PIPING MATERIAL CLASSIFICATION FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 |  |  | O |  | PKG-025-WT | 2017-04-03 | #VALUE!
MCH(13) | Mechanical | 130101 | T16182-XS00-P0GNR-130101 | SYSTEM DESCRIPTION FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-18 | O | O |  | PKG-025-WT | 2017-02-15 | 2017-06-29
MCH(13) | Mechanical | 130102 | T16182-XG07-P0GNR-130102 | PROCESS FLOW DIAGRAM FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-18 |  | O |  | PKG-025-WT | 2017-02-15 | 2017-06-29
MCH(13) | Mechanical | 130103 | T16182-XG02-P0GNR-130103 | PIPING & INSTRUMENT DIAGRAM FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-18 | O | O |  | PKG-025-WT | 2017-02-15 | 2017-06-29
MCH(13) | Mechanical | 130104 | T16182-XW03-P0GNR-130104 | CALCULATION SHEET FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-04 |  | O |  | PKG-025-WT | 2017-02-15 | 2017-07-11
MCH(13) | Mechanical | 130105 | T16182-XN00-P0GNR-130105 | VALVE LIST FOR WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-12-22 |  | O |  | PKG-025-WT | 2017-02-22 | 2017-08-28
MCH(13) | Instrumentation & Control | 130106 | T16182-YL00-P0GNR-130106 | INSTRUMENT LIST FOR WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 |  |  | O |  | PKG-025-WT | 2017-02-22 | #VALUE!
MCH(13) | Mechanical | 130107 | T16182-XN00-P0GNR-130107 | EQUIPMENT ASSEMBLY DRAWING FOR WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT | 2017-04-03 | 2017-08-28
MCH(13) | Mechanical | 130108 | T16182-YT01-P0GNR-130108 | TEHCNICAL DATA SHEET FOR WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-07-20 |  | O |  | PKG-025-WT | 2017-04-03 | 2017-08-31
MCH(13) | Mechanical | 130201 | T16182-XS00-P0LD-130201 | SYSTEM DESCRIPTION FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 | O |  |  | PKG-026-CPP | 2017-07-06 | 2017-12-06
MCH(13) | Mechanical | 130202 | T16182-YD00-P0LD-130202 | GENERAL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 | O |  |  | PKG-026-CPP | 2017-07-05 | 2017-10-24
MCH(13) | Mechanical | 130203 | T16182-XG07-P0LD-130203 | PROCESS FLOW DIAGRAM FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 |  |  |  | PKG-026-CPP | 2017-07-05 | 2017-10-24
MCH(13) | Mechanical | 130204 | T16182-XG02-P0LD-130204 | PIPING & INSTRUMENT DIAGRAM FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 | O |  |  | PKG-026-CPP | 2017-07-26 | 2018-02-08
MCH(13) | Mechanical | 130205 | T16182-XW03-P0LD-130205 | CALCULATION SHEET FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 |  |  |  | PKG-026-CPP | 2017-07-05 | 2017-12-06
MCH(13) | Electrical | 130206 | T16182-YD00-P0LD-130206 | MCC ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 | 2018-11-19 |  |  |  | PKG-026-CPP | 2017-09-22 | 2018-11-19
MCH(13) | Instrumentation & Control | 130207 | T16182-YR05-P0LD-130207 | CONTROL PANEL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 | 2018-11-22 |  |  |  | PKG-026-CPP | 2017-07-24 | 2018-11-22
MCH(13) | Mechanical | 130208 | T16182-XN00-P0LD-130208 | VALVE LIST FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP | 2017-07-28 | #VALUE!
MCH(13) | Instrumentation & Control | 130209 | T16182-YL00-P0LD-130209 | INSTRUMENT LIST FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP | 2017-08-30 | #VALUE!
MCH(13) | Electrical | 130210 | T16182-YU02-P0LD-130210 | SINGLE LINE DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP | 2017-07-24 | #VALUE!
MCH(13) | Instrumentation & Control | 130211 | T16182-YF02-P0LD-130211 | CONTROL CONFIGURATION DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP | 2017-07-24 | #VALUE!
MCH(13) | Mechanical | 130212 | T16182-YK09-P0LD-130212 | EQUIPMENT ASSEMBLY DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-08-02 | 2017-10-01 |  |  |  | PKG-026-CPP | 2017-09-29 | 2017-12-19
MCH(13) | Mechanical | 130213 | T16182-XH01-P0LD-130213 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-15 | 2017-11-15 |  |  |  | PKG-026-CPP | 2017-10-24 | 2018-05-25
MCH(13) | Mechanical | 130214 | T16182-YT01-P0LD-130214 | TECHNICAL DATA SHEET FOR CONDENSATE POLISHING PLANT | IFI | 2017-08-02 |  |  |  |  | PKG-026-CPP | 2017-08-30 | #VALUE!
MCH(13) | Electrical | 130215 | T16182-YE00-P0LD-130215 | CABLE TRAY LAYOUT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 | 2018-11-14 |  |  |  | PKG-026-CPP | 2017-09-29 | 2018-11-14
MCH(13) | Instrumentation & Control | 130216 | T16182-YK00-P0LD-130216 | HOOK - UP DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 |  |  |  |  | PKG-026-CPP | 2017-09-27 | #VALUE!
MCH(13) | Electrical | 130217 | T16182-YU03-P0LD-130217 | SCHEMATIC & WIRING DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 |  |  |  |  | PKG-026-CPP | 2017-09-29 | #VALUE!
MCH(13) | Instrumentation & Control | 130218 | T16182-YF00-P0LD-130218 | CONTROL LOOP & LOGIC DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 |  |  |  |  | PKG-026-CPP | 2017-10-23 | #VALUE!
MCH(13) | Mechanical | 130219 | T16182-CV03-P0LD-130219 | PIPING MATERIAL SPECIFICATION FOR CONDENSATE POLISHING PLANT | IFI | 2017-12-08 |  |  |  |  | PKG-026-CPP | 2017-12-14 | #VALUE!
MCH(13) | Mechanical | 130220 | T16182-XB02-P0LD-130220 | FOUNDATION AND LOADING DATA FOR CONDENSATE POLISHING PLANT | IFI | 2018-10-05 | 2018-12-05 |  |  |  | PKG-026-CPP | 2018-11-09 | 2018-11-26
MCH(13) | Instrumentation & Control | 130221 | T16182-YM03-P0LD-130221 | INSTRUMENT LOCATION DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2019-03-15 | [5 empty] | 2019-03-07 | #VALUE!
MCH(13) | Mechanical | 130301 | T16182-XS00-P0QC-130301 | SYSTEM DESCRIPTION FOR CHEMICAL DOSING SYSTEM | IFR | 2017-10-05 | 2018-01-17 |  |  |  | PKG-027-CDS | 2017-09-15 | 2017-10-30
MCH(13) | Mechanical | 130302 | T16182-YD00-P0QC-130302 | GENERAL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | IFR | 2017-10-05 | 2018-01-17 |  |  |  | PKG-027-CDS | 2017-09-15 | 2018-01-30
MCH(13) | Mechanical | 130303 | T16182-XG02-P0QC-130303 | PIPING & INSTRUMENT DIAGRAM FOR CHEMICAL DOSING SYSTEM | IFR | 2017-10-05 | 2018-01-17 |  |  |  | PKG-027-CDS | 2017-09-15 | 2017-12-11
MCH(13) | Mechanical | 130304 | T16182-XW03-P0QC-130304 | CALCULATION SHEET FOR CHEMICAL DOSING SYSTEM | IFI | 2017-10-05 |  |  |  |  | PKG-027-CDS | 2017-09-15 | #VALUE!
MCH(13) | Instrumentation & Control | 130305 | T16182-YL00-P0QC-130305 | INSTRUMENT LIST FOR CHEMICAL DOSING SYSTEM | IFI | 2017-11-04 |  |  |  |  | PKG-027-CDS | 2017-11-10 | #VALUE!
MCH(13) | Instrumentation & Control | 130306 | T16182-YR05-P0QC-130306 | CONTROL PANEL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | IFI | 2017-11-04 |  |  |  |  | PKG-027-CDS | 2017-11-10 | #VALUE!
MCH(13) | Mechanical | 130307 | T16182-YT01-P0QC-130307 | TECHNICAL DATA SHEET FOR CHEMICAL DOSING SYSTEM | IFI | 2017-12-04 |  |  |  |  | PKG-027-CDS | 2017-12-08 | #VALUE!
MCH(13) | Electrical | 130308 | T16182-YU03-P0QC-130308 | SCHEMATIC & WIRING DIAGRAM FOR CHEMICAL DOSING SYSTEM | IFI | 2018-01-03 |  |  |  |  | PKG-027-CDS | 2017-12-18 | #VALUE!
MCH(13) | Instrumentation & Control | 130309 | T16182-YF00-P0QC-130309 | CONTROL LOOP & LOGIC DIAGRAM FOR CHEMICAL DOSING SYSTEM | IFI | 2018-01-03 |  |  |  |  | PKG-027-CDS | 2017-12-18 | #VALUE!
MCH(13) | Mechanical | 130401 | T16182-XS00-P0QU-130401 | SYSTEM DESCRIPTION FOR SAMPLING SYSTEM | IFR | 2017-10-04 | 2018-01-16 |  |  |  | PKG-028-SP | 2017-09-29 | 2018-02-13
MCH(13) | Mechanical | 130402 | T16182-YD00-P0QU-130402 | GENERAL ARRANGEMENT DRAWING FOR SAMPLING SYSTEM | IFR | 2017-10-04 | 2018-01-16 |  |  |  | PKG-028-SP | 2017-09-29 | 2018-02-01
MCH(13) | Mechanical | 130403 | T16182-XG02-P0QU-130403 | PIPING & INSTRUMENT DIAGRAM FOR SAMPLING SYSTEM | IFR | 2017-10-04 | 2018-01-16 |  |  |  | PKG-028-SP | 2017-09-29 | 2018-02-01
MCH(13) | Instrumentation & Control | 130404 | T16182-YL00-P0QU-130404 | INSTRUMENT LIST FOR SAMPLING SYSTEM | IFI | 2017-11-03 |  |  |  |  | PKG-028-SP | 2017-11-10 | #VALUE!
MCH(13) | Mechanical | 130405 | T16182-YT01-P0QU-130405 | TECHNICAL DATA SHEET FOR SAMPLING SYSTEM | IFI | 2017-12-03 |  |  |  |  | PKG-028-SP | 2017-12-19 | #VALUE!
MCH(13) | Electrical | 130406 | T16182-YU03-P0QU-130406 | SCHEMATIC & WIRING DIAGRAM FOR SAMPLING SYSTEM | IFI | 2018-01-02 |  |  |  |  | PKG-028-SP | 2018-01-11 | #VALUE!
MCH(13) | Instrumentation & Control | 130407 | T16182-YF00-P0QU-130407 | CONTROL LOOP & LOGIC DIAGRAM FOR SAMPLING SYSTEM | IFI | 2018-01-02 |  |  |  |  | PKG-028-SP | 2018-01-11 | #VALUE!
MCH(13) | Mechanical | 130501 | T16182-XW01-P0STG-130501 | EQUIPMENT SPECIFICATION FOR CHEMICAL LABORATORY | IFI | 2017-08-04 |  |  |  |  | PKG-029-CLAB | 2017-08-17 | #VALUE!
MCH(13) | Mechanical | 130502 | T16182-YD00-P0STG-130502 | ARRANGEMENT DRAWING FOR CHEMICAL LABORATORY EQUIPMENT | IFR | 2017-08-04 | 2017-11-16 |  |  |  | PKG-029-CLAB | 2017-08-17 | 2017-11-10
MCH(13) | Mechanical | 130503 | T16182-XL00-P0STG-130503 | EQUIPMENT LIST FOR CHEMICAL LABORATORY | IFR | 2017-08-04 | 2017-11-30 |  |  |  | PKG-029-CLAB | 2017-08-17 | 2017-11-30
MCH(13) | Mechanical | 130601 | T16182-YD00-P0GK-130601 | GENERAL ARRANGEMENT DRAWING FOR POTABLE WATER CHILLER | IFR | 2017-12-08 | 2018-01-26 |  |  |  |  | 2018-01-11 | 2018-02-12
MCH(13) | Mechanical | 130602 | T16182-YS01-P0GK-130602 | ELECTRICAL DRAWING FOR POTABLE WATER CHILLER | IFI | 2017-12-08 | [5 empty] | 2018-01-11 | #VALUE!
MCH(13) | Mechanical | 133301 | T16182-XW01-P0SAA-133301 | DESIGN CRITERIA FOR HVAC SYSTEM | IFR | 2017-01-25 | 2017-04-15 |  | O |  | PKG-041-HVAC | 2017-01-26 | 2017-04-04
MCH(13) | Mechanical | 133302 | T16182-YK09-P0SAA-133302 | STANDARD DRAIWNG FOR HVAC SYSTEM | IFR | 2017-01-25 | 2017-04-15 |  | O |  | PKG-041-HVAC | 2017-01-26 | 2017-03-06
MCH(13) | Mechanical | 133401 | T16182-XW03-P0SAH-133401 | LOAD CALCULATION OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC | 2017-07-04 | 2017-08-10
MCH(13) | Mechanical | 133402 | T16182-XG07-P0SAH-133402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC | 2017-07-04 | 2017-08-10
MCH(13) | Mechanical | 133403 | T16182-XW03-P0SAH-133403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC | 2017-07-04 | 2017-08-10
MCH(13) | Mechanical | 133404 | T16182-XH02-P0SAH-133404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC | 2017-07-04 | 2017-08-10
MCH(13) | Mechanical | 133501 | T16182-XW03-P0SAC-133501 | LOAD CALCULATION OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC | 2017-03-16 | 2017-05-02
MCH(13) | Mechanical | 133502 | T16182-XG07-P0SAC-133502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC | 2017-03-16 | 2017-05-10
MCH(13) | Mechanical | 133503 | T16182-XW03-P0SAC-133503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC | 2017-03-16 | 2017-05-10
MCH(13) | Mechanical | 133504 | T16182-XH02-P0SAC-133504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC | 2017-03-16 | 2017-05-10
MCH(13) | Mechanical | 133601 | T16182-XW03-P0SAK-133601 | LOAD CALCULATION OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-05-24
MCH(13) | Mechanical | 133602 | T16182-XG07-P0SAK-133602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-05-24
MCH(13) | Mechanical | 133603 | T16182-XW03-P0SAK-133603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-05-24
MCH(13) | Mechanical | 133604 | T16182-XH02-P0SAK-133604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-05-24
MCH(13) | Mechanical | 133701 | T16182-XW03-P0SAJ-133701 | LOAD CALCULATION OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC | 2017-04-13 | 2017-05-23
MCH(13) | Mechanical | 133702 | T16182-XG07-P0SAJ-133702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC | 2017-04-13 | 2017-05-23
MCH(13) | Mechanical | 133703 | T16182-XW03-P0SAJ-133703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC | 2017-04-13 | 2017-05-23
MCH(13) | Mechanical | 133704 | T16182-XH02-P0SAJ-133704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC | 2017-04-13 | 2017-05-23
MCH(13) | Mechanical | 133801 | T16182-XW03-P0SAI-133801 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC | 2017-03-24 | 2017-04-29
MCH(13) | Mechanical | 133802 | T16182-XG07-P0SAI-133802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC | 2017-03-24 | 2017-04-29
MCH(13) | Mechanical | 133803 | T16182-XW03-P0SAI-133803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC | 2017-03-24 | 2017-04-29
MCH(13) | Mechanical | 133804 | T16182-XH02-P0SAI-133804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC | 2017-03-24 | 2017-04-29
MCH(13) | Mechanical | 133901 | T16182-XW03-P0SAI-133901 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC | 2017-04-24 | 2017-05-29
MCH(13) | Mechanical | 133902 | T16182-XG07-P0SAI-133902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC | 2017-04-24 | 2017-05-29
MCH(13) | Mechanical | 133903 | T16182-XW03-P0SAI-133903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC | 2017-04-24 | 2017-05-29
MCH(13) | Mechanical | 133904 | T16182-XH02-P0SAI-133904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC | 2017-04-24 | 2017-05-29
MCH(13) | Mechanical | 134001 | T16182-XW03-P0SAL-134001 | LOAD CALCULATION OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2017-09-29 | 2017-11-17
MCH(13) | Mechanical | 134002 | T16182-XG07-P0SAL-134002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2017-09-29 | 2017-11-17
MCH(13) | Mechanical | 134003 | T16182-XW03-P0SAL-134003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2017-09-29 | 2017-11-17
MCH(13) | Mechanical | 134004 | T16182-XH02-P0SAL-134004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2017-09-29 | 2017-11-17
MCH(13) | Mechanical | 134101 | T16182-XW03-P0SAR-134101 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC | 2017-06-15 | 2017-07-21
MCH(13) | Mechanical | 134102 | T16182-XG07-P0SAR-134102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC | 2017-06-15 | 2017-07-21
MCH(13) | Mechanical | 134103 | T16182-XW03-P0SAR-134103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC | 2017-06-15 | 2017-07-21
MCH(13) | Mechanical | 134104 | T16182-XH02-P0SAR-134104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC | 2017-06-15 | 2017-07-21
MCH(13) | Mechanical | 134201 | T16182-XW03-P0SAR-134201 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC | 2017-06-27 | 2017-07-21
MCH(13) | Mechanical | 134202 | T16182-XG07-P0SAR-134202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC | 2017-06-27 | 2017-07-21
MCH(13) | Mechanical | 134203 | T16182-XW03-P0SAR-134203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC | 2017-06-27 | 2017-07-21
MCH(13) | Mechanical | 134204 | T16182-XH02-P0SAR-134204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC | 2017-06-27 | 2017-07-21
MCH(13) | Mechanical | 134301 | T16182-XW03-P0SAE-134301 | LOAD CALCULATION OF HVAC SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-09 | 2018-03-30
MCH(13) | Mechanical | 134302 | T16182-XG07-P0SAE-134302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-09 | 2018-03-30
MCH(13) | Mechanical | 134303 | T16182-XW03-P0SAE-134303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-09 | 2018-03-30
MCH(13) | Mechanical | 134304 | T16182-XH02-P0SAE-134304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-09 | 2018-03-30
MCH(13) | Mechanical | 134401 | T16182-XW03-P0SAN-134401 | LOAD CALCULATION OF HVAC SYSTEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-03-19 | 2018-04-27
MCH(13) | Mechanical | 134402 | T16182-XG07-P0SAN-134402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-03-19 | 2018-04-27
MCH(13) | Mechanical | 134403 | T16182-XW03-P0SAN-134403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-03-19 | 2018-04-27
MCH(13) | Mechanical | 134404 | T16182-XH02-P0SAN-134404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-03-19 | 2018-04-27
MCH(13) | Mechanical | 134501 | T16182-XW03-P0SAD-134501 | LOAD CALCULATION OF HVAC SYSTEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC | 2018-05-17 | 2018-06-14
MCH(13) | Mechanical | 134502 | T16182-XG07-P0SAD-134502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC | 2018-05-17 | 2018-06-14
MCH(13) | Mechanical | 134503 | T16182-XW03-P0SAD-134503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC | 2018-05-17 | 2018-06-14
MCH(13) | Mechanical | 134504 | T16182-XH02-P0SAD-134504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC | 2018-05-17 | 2018-06-14
MCH(13) | Mechanical | 134601 | T16182-XW03-P0SAE-134601 | LOAD CALCULATION OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-19 | 2018-05-25
MCH(13) | Mechanical | 134602 | T16182-XG07-P0SAE-134602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-19 | 2018-05-25
MCH(13) | Mechanical | 134603 | T16182-XW03-P0SAE-134603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-19 | 2018-05-25
MCH(13) | Mechanical | 134604 | T16182-XH02-P0SAE-134604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-19 | 2018-05-25
MCH(13) | Mechanical | 134701 | T16182-XW03-P0SAF-134701 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC | 2017-11-24 | 2017-12-22
MCH(13) | Mechanical | 134702 | T16182-XG07-P0SAF-134702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC | 2017-11-24 | 2017-12-22
MCH(13) | Mechanical | 134703 | T16182-XW03-P0SAF-134703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC | 2017-11-24 | 2017-12-22
MCH(13) | Mechanical | 134704 | T16182-XH02-P0SAF-134704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC | 2017-11-24 | 2017-12-22
MCH(13) | Mechanical | 134801 | T16182-XW03-P0SAB-134801 | LOAD CALCULATION OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC | 2017-09-15 | 2017-11-10
MCH(13) | Mechanical | 134802 | T16182-XG07-P0SAB-134802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC | 2017-09-15 | 2017-11-10
MCH(13) | Mechanical | 134803 | T16182-XW03-P0SAB-134803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC | 2017-09-15 | 2017-11-10
MCH(13) | Mechanical | 134804 | T16182-XH02-P0SAB-134804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC | 2017-09-15 | 2017-11-10
MCH(13) | Mechanical | 134901 | T16182-XW03-P0SAG-134901 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC | 2017-04-21 | 2017-06-13
MCH(13) | Mechanical | 134902 | T16182-XG07-P0SAG-134902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC | 2017-04-21 | 2017-06-13
MCH(13) | Mechanical | 134903 | T16182-XW03-P0SAG-134903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC | 2017-04-21 | 2017-06-13
MCH(13) | Mechanical | 134904 | T16182-XH02-P0SAG-134904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC | 2017-04-21 | 2017-06-13
MCH(13) | Mechanical | 135001 | T16182-XW03-P0SAM-135001 | LOAD CALCULATION OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC | 2017-08-29 | 2017-10-20
MCH(13) | Mechanical | 135002 | T16182-XG07-P0SAM-135002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC | 2017-08-29 | 2017-10-20
MCH(13) | Mechanical | 135003 | T16182-XW03-P0SAM-135003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC | 2017-08-29 | 2017-10-23
MCH(13) | Mechanical | 135004 | T16182-XH02-P0SAM-135004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC | 2017-08-29 | 2017-10-23
MCH(13) | Mechanical | 135101 | T16182-XW03-P0SAV-135101 | LOAD CALCULATION OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-07-17
MCH(13) | Mechanical | 135102 | T16182-XG07-P0SAV-135102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-07-17
MCH(13) | Mechanical | 135103 | T16182-XW03-P0SAV-135103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-07-17
MCH(13) | Mechanical | 135104 | T16182-XH02-P0SAV-135104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC | 2017-04-14 | 2017-07-17
MCH(13) | Mechanical | 135201 | T16182-XW03-P0SAQ-135201 | LOAD CALCULATION OF HVAC SYSTEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC | 2017-12-15 | 2018-01-29
MCH(13) | Mechanical | 135202 | T16182-XG07-P0SAQ-135202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC | 2017-12-15 | 2018-01-29
MCH(13) | Mechanical | 135203 | T16182-XW03-P0SAQ-135203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC | 2017-12-15 | 2018-01-29
MCH(13) | Mechanical | 135204 | T16182-XH02-P0SAQ-135204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC | 2017-12-15 | 2018-01-29
MCH(13) | Mechanical | 135301 | T16182-XW03-P0SAE-135301 | LOAD CALCULATION OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-27 | 2018-04-11
MCH(13) | Mechanical | 135302 | T16182-XG07-P0SAE-135302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-27 | 2018-04-11
MCH(13) | Mechanical | 135303 | T16182-XW03-P0SAE-135303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-27 | 2018-04-11
MCH(13) | Mechanical | 135304 | T16182-XH02-P0SAE-135304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC | 2018-02-27 | 2018-04-11
MCH(13) | Mechanical | 135401 | T16182-XW03-P0SAE-135401 | LOAD CALCULATION OF HVAC SYSTEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-10 | 2018-04-25
MCH(13) | Mechanical | 135402 | T16182-XG07-P0SAE-135402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-10 | 2018-04-25
MCH(13) | Mechanical | 135403 | T16182-XW03-P0SAE-135403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-10 | 2018-04-25
MCH(13) | Mechanical | 135404 | T16182-XH02-P0SAE-135404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC | 2018-04-10 | 2018-04-25
MCH(13) | Mechanical | 136001 | T16182-YT01-P0SAA-136001 | VENDOR PRINT FOR HVAC EQUIPMENT-1 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC | 2017-10-11 | 2017-11-30
MCH(13) | Mechanical | 136002 | T16182-YT01-P0SAA-136002 | VENDOR PRINT FOR HVAC EQUIPMENT-2 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC | 2018-01-19 | 2018-02-27
MCH(13) | Mechanical | 136003 | T16182-YT01-P0SAA-136003 | VENDOR PRINT FOR HVAC EQUIPMENT-3 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC | 2018-04-26 | 2018-05-15
MCH(13) | Mechanical | 136004 | T16182-YT01-P0SAA-136004 | VENDOR PRINT FOR HVAC EQUIPMENT-4 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC | 2018-06-22 | 2018-07-12
MCH(13) | Mechanical | 136005 | T16182-YT01-P0SAA-136005 | VENDOR PRINT FOR HVAC EQUIPMENT-5 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC | 2018-07-27 | 2018-09-19
MCH(13) | Mechanical | 136601 | T16182-XS00-P0SG-136601 | FIRE FIGHTING SYSTEM CONCEPTUAL DESIGN | IFR | 2017-05-01 | 2017-07-30 |  | O |  | PKG-030-FF | 2017-03-10 | 2017-05-23
MCH(13) | Mechanical | 136602 | T16182-XS00-P0SG-136602 | FIRE RISK EVALUATION | IFR | 2017-05-01 | 2017-07-30 |  | O |  | PKG-030-FF | 2017-03-10 | 2017-06-19
MCH(13) | Mechanical | 136603 | T16182-XG02-P0SGA-136603 | FIRE SERVICE RING MAIN SYSTEM - P&ID | IFR | 2017-05-01 | 2017-07-01 | O | O |  | PKG-030-FF | 2017-04-07 | 2017-06-15
MCH(13) | Mechanical | 136604 | T16182-XH01-P0SGA-136604 | FIRE SERVICE RING MAIN SYSTEM - PIPE LAYOUT AND DETAIL DRAWING | IFR | 2017-05-01 | 2017-07-01 |  |  |  | PKG-030-FF | 2016-12-23 | 2017-06-15
MCH(13) | Mechanical | 136605 | T16182-YT10-P0SGA-136605 | FIRE SERVICE RING MAIN SYSTEM - HYDRAULIC CALCULATION | IFR | 2017-05-25 | 2017-08-23 |  | O |  | PKG-030-FF | 2017-05-22 | 2017-08-22
MCH(13) | Instrumentation & Control | 136606 | T16182-YU03-P0CYE-136606 | FIRE DETECTION AND ALARM SYSTEM - BLOCK DIAGRAM | IFR | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF | 2017-04-04 | 2017-06-09
MCH(13) | Instrumentation & Control | 136607 | T16182-YU02-P0CYE-136607 | FIRE DETECTION AND ALARM SYSTEM - NETWORK SINGLE LINE DIAGRAM | IFR | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF | 2017-04-06 | 2017-06-09
MCH(13) | Mechanical | 136609 | T16182-YT01-P0SGA-136609 | FIRE FIGHTING PUMP SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-07-28
MCH(13) | Mechanical | 136610 | T16182-YT01-P0SGA-136610 | OUTDOOR HYDRANT SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Mechanical | 136611 | T16182-YT01-P0SGA-136611 | STAND PIPE SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Mechanical | 136612 | T16182-YT01-P0SGE-136612 | SPRINKLER SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Mechanical | 136613 | T16182-YT01-P0SGC-136613 | WATER SPRAY SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Mechanical | 136614 | T16182-YT01-P0SGK-136614 | CLEAN AGENT SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Mechanical | 136615 | T16182-YT01-P0SGZ-136615 | FIRE EXTINGUISHER SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Mechanical | 136616 | T16182-YT01-P0SGX-136616 | PIPE AND BULK MATERIAL - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Instrumentation & Control | 136617 | T16182-YT01-P0CYE-136617 | FIRE DETECTION AND ALARM SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Instrumentation & Control | 136618 | T16182-YT01-P0CYE-136618 | CABLE AND BULK MATERIAL - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-13
MCH(13) | Commissioning | 136620 | T16182-DN05-P0SG-136620 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR ESOD | IFR | 2017-07-25 | 2017-10-23 | O |  |  | PKG-030-FF | 2017-06-20 | 2017-10-20
MCH(13) | Mechanical | 136621 | T16182-CV03-P0SG-136621 | PIPING MATERIAL SPECIFICATION FOR FIRE FIGHTING SYSTEM | IFI | 2017-06-23 |  |  |  |  | PKG-030-FF | 2017-06-26 | #VALUE!
MCH(13) | Commissioning | 136622 | T16182-XJ00-P0SGA-136622 | ISOMETRIC DRAWING FOR FIRE SERVICE RING MAIN SYSTEM | IFI | 2018-07-25 | 2018-10-23 |  |  |  | PKG-030-FF | 2018-06-28 | 2019-04-01
MCH(13) | Commissioning | 136623 | T16182-DN05-P0SG-136623 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR NON ESOD | IFR | 2018-07-25 | 2018-10-23 |  |  |  | PKG-030-FF | 2018-08-07 | 2019-03-26
MCH(13) | Instrumentation & Control | 136624 | T16182-YD00-P0CYE-136624 | FIRE DETECTION AND ALARM SYSTEM LAYOUT FOR YARD AREA | IFI | 2019-01-04 | 2019-02-08 |  |  |  | PKG-030-FF | 2019-01-03 | 2019-01-28
MCH(13) | Mechanical | 136631 | T16182-YD00-P0SGZ-136631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SUPPORT BUILDING | IFI | 2018-06-15 | 2018-09-13 |  |  |  | PKG-030-FF | 2018-06-27 | 2018-09-18
MCH(13) | Instrumentation & Control | 136641 | T16182-YD00-P0CYE-136641 | FIRE ALARM SYSTEM LAYOUT FOR SUPPORT BUILDING | IFI | 2018-06-15 | 2018-09-13 |  |  |  | PKG-030-FF | 2018-05-04 | 2018-06-05
MCH(13) | Instrumentation & Control | 136642 | T16182-YU02-P0CYE-136642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SUPPORT BUILDING | IFR | 2018-06-15 | 2018-09-13 |  |  |  | PKG-030-FF | 2018-05-04 | 2018-06-05
MCH(13) | Mechanical | 136701 | T16182-XG02-P0SGA-136701 | P&ID OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-17 | 2017-06-15
MCH(13) | Mechanical | 136702 | T16182-XG02-P0SGE-136702 | P&ID OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-17 | 2017-06-15
MCH(13) | Mechanical | 136703 | T16182-XG02-P0SGK-136703 | P&ID OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-17 | 2017-06-26
MCH(13) | Mechanical | 136711 | T16182-XH01-P0SGA-136711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-09-28
MCH(13) | Mechanical | 136712 | T16182-XH01-P0SGE-136712 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-09-28
MCH(13) | Mechanical | 136713 | T16182-XH01-P0SGK-136713 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-09-28
MCH(13) | Mechanical | 136722 | T16182-YT10-P0SGE-136722 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-10-16
MCH(13) | Mechanical | 136723 | T16182-YT10-P0SGK-136723 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-10-16
MCH(13) | Mechanical | 136731 | T16182-YD00-P0SGZ-136731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-15
MCH(13) | Instrumentation & Control | 136741 | T16182-YD00-P0CYE-136741 | FIRE ALARM SYSTEM LAYOUT FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 | O | O |  | PKG-030-FF | 2017-06-14 | 2017-11-06
MCH(13) | Instrumentation & Control | 136742 | T16182-YU02-P0CYE-136742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF | 2017-04-17 | 2017-06-19
MCH(13) | Instrumentation & Control | 136743 | T16182-YT10-P0CYE-136743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2018-01-20 |  |  | O |  | PKG-030-FF | 2017-08-29 | #VALUE!
MCH(13) | Instrumentation & Control | 136744 | T16182-XG02-P0CYE-136744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2018-01-20 | 2018-04-20 |  | O |  | PKG-030-FF | 2017-10-25 | 2017-11-20
MCH(13) | Mechanical | 136801 | T16182-XG02-P0SGA-136801 | P&ID OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-19
MCH(13) | Mechanical | 136802 | T16182-XG02-P0SGE-136802 | P&ID OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-19
MCH(13) | Mechanical | 136803 | T16182-XG02-P0SGK-136803 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-05-12 | 2017-06-13
MCH(13) | Mechanical | 136811 | T16182-XH01-P0SGA-136811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-05-12 | 2017-10-10
MCH(13) | Mechanical | 136812 | T16182-XH01-P0SGE-136812 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-05-12 | 2017-10-10
MCH(13) | Mechanical | 136813 | T16182-XH01-P0SGK-136813 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-05-12 | 2017-10-10
MCH(13) | Mechanical | 136822 | T16182-YT10-P0SGE-136822 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-10-16
MCH(13) | Mechanical | 136823 | T16182-YT10-P0SGK-136823 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-10-16
MCH(13) | Mechanical | 136831 | T16182-YD00-P0SGZ-136831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-13
MCH(13) | Instrumentation & Control | 136841 | T16182-YD00-P0CYE-136841 | FIRE ALARM SYSTEM LAYOUT FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 | O | O |  | PKG-030-FF | 2017-06-13 | 2017-10-24
MCH(13) | Instrumentation & Control | 136842 | T16182-YU02-P0CYE-136842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF | 2017-06-13 | 2017-10-24
MCH(13) | Instrumentation & Control | 136843 | T16182-YT10-P0CYE-136843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | IFI | 2018-01-20 |  |  | O |  | PKG-030-FF | 2017-10-25 | #VALUE!
MCH(13) | Instrumentation & Control | 136844 | T16182-XG02-P0CYE-136844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | IFR | 2018-01-20 | 2018-04-20 |  | O |  | PKG-030-FF | 2017-10-25 | 2017-11-20
MCH(13) | Mechanical | 136901 | T16182-XG02-P0SGA-136901 | P&ID OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-08
MCH(13) | Mechanical | 136902 | T16182-XG02-P0SGE-136902 | P&ID OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-08
MCH(13) | Mechanical | 136903 | T16182-XG02-P0SGK-136903 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-07-24 | 2017-11-20
MCH(13) | Mechanical | 136911 | T16182-XH01-P0SGA-136911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-08
MCH(13) | Mechanical | 136912 | T16182-XH01-P0SGE-136912 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-08
MCH(13) | Mechanical | 136913 | T16182-XH01-P0SGK-136913 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-07-24 | 2017-11-20
MCH(13) | Mechanical | 136922 | T16182-YT10-P0SGE-136922 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-08
MCH(13) | Mechanical | 136923 | T16182-YT10-P0SGK-136923 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-07-24 | 2017-11-20
MCH(13) | Mechanical | 136931 | T16182-YD00-P0SGZ-136931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-11-20
MCH(13) | Instrumentation & Control | 136941 | T16182-YD00-P0CYE-136941 | FIRE ALARM SYSTEM LAYOUT FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 | O |  |  | PKG-030-FF | 2017-06-12 | 2018-02-14
MCH(13) | Instrumentation & Control | 136942 | T16182-YU02-P0CYE-136942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-05
MCH(13) | Instrumentation & Control | 136943 | T16182-YT10-P0CYE-136943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2018-01-24 | #VALUE!
MCH(13) | Instrumentation & Control | 136944 | T16182-XG02-P0CYE-136944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2018-02-14 | 2018-04-17
MCH(13) | Mechanical | 137001 | T16182-XG02-P0SGC-137001 | P&ID OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-02 | 2017-07-21
MCH(13) | Mechanical | 137011 | T16182-XH01-P0SGC-137011 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-07-21
MCH(13) | Mechanical | 137021 | T16182-YT10-P0SGC-137021 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-07-21
MCH(13) | Mechanical | 137031 | T16182-YD00-P0SGZ-137031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  |  |  | PKG-030-FF | 2017-05-11 | 2017-06-13
MCH(13) | Instrumentation & Control | 137041 | T16182-YD00-P0CYE-137041 | FIRE ALARM SYSTEM LAYOUT FOR GTG GSU TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF | 2017-05-11 | 2017-06-13
MCH(13) | Instrumentation & Control | 137042 | T16182-YU02-P0CYE-137042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-06-13
MCH(13) | Mechanical | 137101 | T16182-XG02-P0SGC-137101 | P&ID OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-02 | 2017-06-20
MCH(13) | Mechanical | 137111 | T16182-XH01-P0SGC-137111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-06-20
MCH(13) | Mechanical | 137121 | T16182-YT10-P0SGC-137121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-06-20
MCH(13) | Mechanical | 137131 | T16182-YD00-P0SGZ-137131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG UNIT AUX. TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 |  |  |  | PKG-030-FF | 2017-05-02 | 2017-06-14
MCH(13) | Instrumentation & Control | 137141 | T16182-YD00-P0CYE-137141 | FIRE ALARM SYSTEM LAYOUT FOR GTG UNIT AUX. TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF | 2017-05-11 | 2017-06-15
MCH(13) | Instrumentation & Control | 137142 | T16182-YU02-P0CYE-137142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-06-14
MCH(13) | Mechanical | 137201 | T16182-XG02-P0SGC-137201 | P&ID OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF | 2017-06-27 | 2017-11-20
MCH(13) | Mechanical | 137211 | T16182-XH01-P0SGC-137211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF | 2017-06-27 | 2017-11-20
MCH(13) | Mechanical | 137221 | T16182-YT10-P0SGC-137221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | IFR | 2017-09-03 | 2017-12-02 |  |  |  | PKG-030-FF | 2017-06-27 | 2017-11-20
MCH(13) | Mechanical | 137231 | T16182-YD00-P0SGZ-137231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG GSU TRANSFORMER | IFI | 2017-09-03 | 2017-11-02 |  |  |  | PKG-030-FF | 2017-06-13 | 2017-11-06
MCH(13) | Instrumentation & Control | 137241 | T16182-YD00-P0CYE-137241 | FIRE ALARM SYSTEM LAYOUT FOR STG GSU TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 | O |  |  | PKG-030-FF | 2017-06-12 | 2017-12-04
MCH(13) | Instrumentation & Control | 137242 | T16182-YU02-P0CYE-137242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG GSU TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-04
MCH(13) | Mechanical | 137301 | T16182-XG02-P0SGA-137301 | P&ID OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-15
MCH(13) | Mechanical | 137302 | T16182-XG02-P0SGE-137302 | P&ID OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-15
MCH(13) | Mechanical | 137303 | T16182-XG02-P0SGE-137303 | P&ID OF FIRE WATER PUMP FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-04-24 | 2017-06-08
MCH(13) | Mechanical | 137311 | T16182-XH01-P0SGA-137311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-14
MCH(13) | Mechanical | 137312 | T16182-XH01-P0SGE-137312 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-15
MCH(13) | Mechanical | 137322 | T16182-YT10-P0SGE-137322 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-06-26
MCH(13) | Mechanical | 137331 | T16182-YD00-P0SGZ-137331 | FIRE WATER PUMP ARRANGEMENT FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-04-03 | 2017-06-08
MCH(13) | Mechanical | 137332 | T16182-YD00-P0SGZ-137332 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-04-28 | 2017-06-15
MCH(13) | Instrumentation & Control | 137341 | T16182-YD00-P0CYE-137341 | FIRE ALARM SYSTEM LAYOUT FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 | O | O |  | PKG-030-FF | 2017-05-11 | 2017-06-15
MCH(13) | Instrumentation & Control | 137342 | T16182-YU02-P0CYE-137342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF | 2017-05-11 | 2017-06-15
MCH(13) | Mechanical | 137401 | T16182-XG02-P0SGC-137401 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | IFR | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF | 2017-06-26 | 2017-11-20
MCH(13) | Mechanical | 137411 | T16182-XH01-P0SGC-137411 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | IFI | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF | 2017-06-26 | 2017-12-08
MCH(13) | Mechanical | 137421 | T16182-YT10-P0SGC-137421 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | IFR | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF | 2017-06-26 | 2017-12-08
MCH(13) | Mechanical | 137431 | T16182-YD00-P0SGZ-137431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR RESERVE BOILER | IFI | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF | 2017-06-26 | 2017-11-27
MCH(13) | Instrumentation & Control | 137441 | T16182-YD00-P0CYE-137441 | FIRE ALARM SYSTEM LAYOUT FOR RESERVE BOILER | IFI | 2017-10-18 | 2018-01-16 | O | O |  | PKG-030-FF | 2017-06-30 | 2018-01-12
MCH(13) | Instrumentation & Control | 137442 | T16182-YU02-P0CYE-137442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR RESERVE BOILER | IFR | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF | 2017-06-30 | 2018-01-17
MCH(13) | Mechanical | 137603 | T16182-XG02-P0SGK-137603 | P&ID OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF | 2017-06-19 | 2017-10-31
MCH(13) | Mechanical | 137613 | T16182-XH01-P0SGK-137613 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | IFI | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF | 2017-06-19 | 2017-10-31
MCH(13) | Mechanical | 137623 | T16182-YT10-P0SGK-137623 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF | 2017-06-19 | 2017-10-31
MCH(13) | Mechanical | 137631 | T16182-YD00-P0SGZ-137631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FGS ELECTRICAL BUILDING | IFI | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF | 2017-06-19 | 2017-11-17
MCH(13) | Instrumentation & Control | 137641 | T16182-YD00-P0CYE-137641 | FIRE ALARM SYSTEM LAYOUT FOR FGS ELECTRICAL BUILDING | IFI | 2017-11-12 | 2018-02-10 | O | O |  | PKG-030-FF | 2017-06-13 | 2017-11-17
MCH(13) | Instrumentation & Control | 137642 | T16182-YU02-P0CYE-137642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF | 2017-06-13 | 2017-11-17
MCH(13) | Instrumentation & Control | 137643 | T16182-YT10-P0CYE-137643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2018-01-23 | #VALUE!
MCH(13) | Instrumentation & Control | 137644 | T16182-XG02-P0CYE-137644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2018-01-29 | 2018-04-03
MCH(13) | Mechanical | 137701 | T16182-XG02-P0SGA-137701 | P&ID OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | IFR | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF | 2017-06-12 | 2017-11-23
MCH(13) | Mechanical | 137711 | T16182-XH01-P0SGA-137711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | IFI | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF | 2017-06-12 | 2017-11-23
MCH(13) | Mechanical | 137731 | T16182-YD00-P0SGZ-137731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AIR COMPRESSOR SHELTER | IFI | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF | 2017-06-12 | 2017-11-23
MCH(13) | Instrumentation & Control | 137741 | T16182-YD00-P0CYE-137741 | FIRE ALARM SYSTEM LAYOUT FOR AIR COMPRESSOR SHELTER | IFI | 2018-01-01 | 2018-04-01 | O | O |  | PKG-030-FF | 2017-06-05 | 2017-12-13
MCH(13) | Instrumentation & Control | 137742 | T16182-YU02-P0CYE-137742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AIR COMPRESSOR SHELTER | IFR | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF | 2017-06-05 | 2017-12-08
MCH(13) | Mechanical | 137801 | T16182-XG02-P0SGA-137801 | P&ID OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFR | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-10-31
MCH(13) | Mechanical | 137811 | T16182-XH01-P0SGA-137811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-10-31
MCH(13) | Mechanical | 137831 | T16182-YD00-P0SGZ-137831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-11-20
MCH(13) | Instrumentation & Control | 137841 | T16182-YD00-P0CYE-137841 | FIRE ALARM SYSTEM LAYOUT FORSHELTER FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-11-22 | 2018-02-20 | O | O |  | PKG-030-FF | 2017-06-21 | 2017-10-30
MCH(13) | Instrumentation & Control | 137842 | T16182-YU02-P0CYE-137842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFR | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF | 2017-06-21 | 2017-10-30
MCH(13) | Mechanical | 137901 | T16182-XG02-P0SGA-137901 | P&ID OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF | 2017-05-25 | 2017-11-14
MCH(13) | Mechanical | 137902 | T16182-XG02-P0SGK-137902 | P&ID OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-10-25
MCH(13) | Mechanical | 137903 | T16182-XG02-P0SGE-137903 | P&ID OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  |  |  | PKG-030-FF | 2017-05-25 | 2017-06-20
MCH(13) | Mechanical | 137911 | T16182-XH01-P0SGA-137911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF | 2017-05-25 | 2017-11-14
MCH(13) | Mechanical | 137912 | T16182-XH01-P0SGK-137912 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | IFI | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-11-14
MCH(13) | Mechanical | 137913 | T16182-XH01-P0SGE-137913 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  |  |  | PKG-030-FF | 2017-05-25 | 2017-11-14
MCH(13) | Mechanical | 137922 | T16182-YT10-P0SGK-137922 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF | 2017-06-14 | 2017-11-14
MCH(13) | Mechanical | 137923 | T16182-YT10-P0SGE-137923 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | IFI | 2017-09-11 | 2017-12-10 |  |  |  | PKG-030-FF | 2017-05-25 | 2017-11-14
MCH(13) | Mechanical | 137931 | T16182-YD00-P0SGZ-137931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF | 2017-05-25 | 2017-10-25
MCH(13) | Instrumentation & Control | 137941 | T16182-YD00-P0CYE-137941 | FIRE ALARM SYSTEM LAYOUT FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 | O | O |  | PKG-030-FF | 2017-05-25 | 2017-10-30
MCH(13) | Instrumentation & Control | 137942 | T16182-YU02-P0CYE-137942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF | 2017-05-25 | 2017-10-30
MCH(13) | Instrumentation & Control | 137943 | T16182-YT10-P0CYE-137943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2017-08-29 | #VALUE!
MCH(13) | Instrumentation & Control | 137944 | T16182-XG02-P0CYE-137944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-11-20
MCH(13) | Mechanical | 138001 | T16182-XG02-P0SGA-138001 | P&ID OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | IFR | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF | 2017-08-07 | 2017-10-31
MCH(13) | Mechanical | 138011 | T16182-XH01-P0SGA-138011 | PIPE LAYOUT AND DETAIL OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF | 2017-08-07 | 2017-10-31
MCH(13) | Mechanical | 138031 | T16182-YD00-P0SGZ-138031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR N2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF | 2017-08-07 | 2017-10-31
MCH(13) | Instrumentation & Control | 138041 | T16182-YD00-P0CYE-138041 | FIRE ALARM SYSTEM LAYOUT FOR N2 GAS STORAGE SHELTER | IFI | 2017-07-03 | 2017-10-30 | O |  |  | PKG-030-FF | 2017-06-21 | 2017-10-20
MCH(13) | Instrumentation & Control | 138042 | T16182-YU02-P0CYE-138042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR N2 GAS STORAGE SHELTER | IFR | 2017-07-03 | 2017-10-30 |  |  |  | PKG-030-FF | 2017-06-21 | 2017-10-20
MCH(13) | Mechanical | 138101 | T16182-XG02-P0SGC-138101 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF | 2017-11-08 | 2017-12-08
MCH(13) | Mechanical | 138102 | T16182-XG02-P0SGC-138102 | P&ID OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | IFR | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF | 2019-01-07 | 2019-02-19
MCH(13) | Mechanical | 138111 | T16182-XH01-P0SGC-138111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | IFI | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF | 2017-11-08 | 2017-12-08
MCH(13) | Mechanical | 138112 | T16182-XH01-P0SGC-138112 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | IFI | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF | 2019-01-21 | 2019-02-19
MCH(13) | Mechanical | 138121 | T16182-YT10-P0SGC-138121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF | 2017-11-08 | 2017-12-21
MCH(13) | Mechanical | 138122 | T16182-YT10-P0SGC-138122 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | IFR | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF | 2019-01-21 | 2019-02-27
MCH(13) | Mechanical | 138131 | T16182-YD00-P0SGZ-138131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF | 2017-11-08 | 2017-12-08
MCH(13) | Instrumentation & Control | 138141 | T16182-YD00-P0CYE-138141 | FIRE ALARM SYSTEM LAYOUT FOR HRSG | IFI | 2017-11-12 | 2018-02-10 | O |  |  | PKG-030-FF | 2017-11-07 | 2017-12-21
MCH(13) | Instrumentation & Control | 138142 | T16182-YU02-P0CYE-138142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF | 2017-11-07 | 2017-12-21
MCH(13) | Instrumentation & Control | 138143 | T16182-YD00-P0CYE-138143 | FIRE ALARM SYSTEM LAYOUT FOR GTG LUBE OIL UNIT | IFI | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF | 2019-01-04 | 2019-02-25
MCH(13) | Instrumentation & Control | 138144 | T16182-YU02-P0CYE-138144 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG LUBE OIL UNIT | IFR | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF | 2019-01-04 | 2019-02-25
MCH(13) | Mechanical | 138201 | T16182-XG02-P0SGC-138201 | P&ID OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFR | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF | 2017-06-26 | 2017-10-13
MCH(13) | Mechanical | 138211 | T16182-XH01-P0SGC-138211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFI | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF | 2017-06-26 | 2017-10-13
MCH(13) | Mechanical | 138221 | T16182-YT10-P0SGC-138221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFR | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF | 2017-06-26 | 2017-10-13
MCH(13) | Mechanical | 138231 | T16182-YD00-P0SGZ-138231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR BSDG DIESEL OIL DAY TANK | IFI | 2017-07-21 | 2017-09-19 |  |  |  | PKG-030-FF | 2017-06-20 | 2017-09-12
MCH(13) | Instrumentation & Control | 138241 | T16182-YD00-P0CYE-138241 | FIRE ALARM SYSTEM LAYOUT FOR BSDG DIESEL OIL DAY TANK | IFI | 2017-07-21 | 2017-10-19 | O |  |  | PKG-030-FF | 2017-07-03 | 2017-10-13
MCH(13) | Instrumentation & Control | 138242 | T16182-YU02-P0CYE-138242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFR | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF | 2017-07-03 | 2017-10-13
MCH(13) | Mechanical | 138301 | T16182-XG02-P0SGC-138301 | P&ID OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | IFR | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF | 2017-06-26 | 2017-10-13
MCH(13) | Mechanical | 138311 | T16182-XH01-P0SGC-138311 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | IFI | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF | 2017-06-26 | 2017-10-13
MCH(13) | Mechanical | 138321 | T16182-YT10-P0SGC-138321 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | IFR | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF | 2017-06-26 | 2017-10-13
MCH(13) | Mechanical | 138331 | T16182-YD00-P0SGZ-138331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GPRS AREA | IFI | 2017-07-19 | 2017-09-17 |  |  |  | PKG-030-FF | 2017-06-20 | 2017-09-12
MCH(13) | Instrumentation & Control | 138341 | T16182-YD00-P0CYE-138341 | FIRE ALARM SYSTEM LAYOUT FOR GPRS AREA | IFI | 2017-07-19 | 2017-10-17 | O |  |  | PKG-030-FF | 2017-07-03 | 2017-10-18
MCH(13) | Instrumentation & Control | 138342 | T16182-YU02-P0CYE-138342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GPRS AREA | IFR | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF | 2017-07-03 | 2017-10-18
MCH(13) | Mechanical | 138401 | T16182-XG02-P0SGA-138401 | P&ID of Standpipe system for H2, CO2 Gas Storage Shelter | IFR | 2017-08-03 | 2017-10-30 |  |  |  | PKG-030-FF | 2017-08-28 | 2017-10-31
MCH(13) | Mechanical | 138411 | T16182-XH01-P0SGA-138411 | Pipe layout and detail of Standpipe system for H2, CO2 Gas Storage Shelter | IFI | 2017-08-03 | 2017-10-30 |  |  |  | PKG-030-FF | 2017-08-28 | 2017-10-31
MCH(13) | Mechanical | 138431 | T16182-YD00-P0SGZ-138431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR H2, CO2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-11-06
MCH(13) | Instrumentation & Control | 138441 | T16182-YD00-P0CYE-138441 | FIRE ALARM SYSTEM LAYOUT FOR H2, CO2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 | O |  |  | PKG-030-FF | 2017-08-28 | 2017-11-01
MCH(13) | Instrumentation & Control | 138442 | T16182-YU02-P0CYE-138442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR H2, CO2 GAS STORAGE SHELTER | IFR | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF | 2017-08-28 | 2017-11-01
MCH(13) | Mechanical | 138502 | T16182-XG02-P0SGK-138502 | P&ID OF CLEAN AGENT SYSTEM FOR AUX. LEB | IFR | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF | 2017-11-27 | 2018-01-10
MCH(13) | Mechanical | 138512 | T16182-XH01-P0SGK-138512 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR AUX. LEB | IFI | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF | 2017-11-27 | 2018-01-10
MCH(13) | Mechanical | 138522 | T16182-YT10-P0SGK-138522 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR AUX. LEB | IFR | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF | 2017-11-27 | 2018-01-10
MCH(13) | Mechanical | 138531 | T16182-YD00-P0SGZ-138531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AUX. LEB | IFI | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF | 2017-12-04 | 2018-01-10
MCH(13) | Instrumentation & Control | 138541 | T16182-YD00-P0CYE-138541 | FIRE ALARM SYSTEM LAYOUT FOR AUX. LEB | IFI | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF | 2017-11-30 | 2018-01-10
MCH(13) | Instrumentation & Control | 138542 | T16182-YU02-P0CYE-138542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AUX. LEB | IFR | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF | 2017-11-30 | 2018-01-10
MCH(13) | Mechanical | 138601 | T16182-XG02-P0SGA-138601 | P&ID OF STAND PIPE SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-02-02
MCH(13) | Mechanical | 138602 | T16182-XG02-P0SGE-138602 | P&ID OF SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-13 | 2018-02-02
MCH(13) | Mechanical | 138603 | T16182-XG02-P0SGE-138603 | P&ID OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2018-03-03 | 2018-06-01 |  |  |  | PKG-030-FF | 2018-01-02 | 2018-02-02
MCH(13) | Mechanical | 138604 | T16182-XG02-P0SGC-138604 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-02-02
MCH(13) | Mechanical | 138606 | T16182-XG02-P0SGC-138606 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-02-02
MCH(13) | Mechanical | 138608 | T16182-XG02-P0SGK-138608 | P&ID of Clean agent system for Excitation Panel Room for ST Building | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-15 | 2018-02-02
MCH(13) | Mechanical | 138611 | T16182-XH01-P0SGA-138611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-02-20
MCH(13) | Mechanical | 138612 | T16182-XH01-P0SGE-138612 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-13 | 2018-02-20
MCH(13) | Mechanical | 138613 | T16182-XH01-P0SGE-138613 | PIPE LAYOUT AND DETAIL OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | IFI | 2018-03-03 | 2018-03-10 |  |  |  | PKG-030-FF | 2018-01-02 | 2018-03-09
MCH(13) | Mechanical | 138614 | T16182-XH01-P0SGC-138614 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-02-20
MCH(13) | Mechanical | 138616 | T16182-XH01-P0SGC-138616 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-02-20
MCH(13) | Mechanical | 138618 | T16182-XH01-P0SGK-138618 | Pipe Layout and detail of Clean agent system for Excitation Panel Room for ST Building | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-15 | 2018-02-20
MCH(13) | Mechanical | 138622 | T16182-YT10-P0SGE-138622 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-13 | 2018-03-09
MCH(13) | Mechanical | 138623 | T16182-YT10-P0SGE-138623 | HYDRAULIC CALCULATION OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2018-03-03 | 2018-06-01 |  |  |  | PKG-030-FF | 2018-01-02 | 2018-03-09
MCH(13) | Mechanical | 138624 | T16182-YT10-P0SGC-138624 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-03-09
MCH(13) | Mechanical | 138626 | T16182-YT10-P0SGC-138626 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-03-09
MCH(13) | Mechanical | 138628 | T16182-YT10-P0SGK-138628 | Flow calculation of Clean Agent system for Excitation Panel Room for ST Building | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-15 | 2018-02-20
MCH(13) | Mechanical | 138631 | T16182-YD00-P0SGZ-138631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-19 | 2018-01-31
MCH(13) | Instrumentation & Control | 138641 | T16182-YD00-P0CYE-138641 | FIRE ALARM SYSTEM LAYOUT FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 | O |  |  | PKG-030-FF | 2017-12-15 | 2018-01-18
MCH(13) | Instrumentation & Control | 138642 | T16182-YU02-P0CYE-138642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF | 2017-12-15 | 2018-01-18
MCH(13) | Instrumentation & Control | 138643 | T16182-YT10-P0CYE-138643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2018-01-23 | #VALUE!
MCH(13) | Instrumentation & Control | 138644 | T16182-XG02-P0CYE-138644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2018-01-29 | 2018-04-03
MCH(13) | Mechanical | 138702 | T16182-XG02-P0SGK-138702 | P&ID OF CLEAN AGENT SYSTEM FOR ST#1 LEB | IFR | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-11-20
MCH(13) | Mechanical | 138712 | T16182-XH01-P0SGK-138712 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#1 LEB | IFI | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-12-08
MCH(13) | Mechanical | 138722 | T16182-YT10-P0SGK-138722 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#1 LEB | IFR | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-12-08
MCH(13) | Mechanical | 138731 | T16182-YD00-P0SGZ-138731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#1 LEB | IFI | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-11-20
MCH(13) | Instrumentation & Control | 138741 | T16182-YD00-P0CYE-138741 | FIRE ALARM SYSTEM LAYOUT FOR ST#1 LEB | IFI | 2017-12-15 | 2018-03-15 | O |  |  | PKG-030-FF | 2017-06-08 | 2017-12-08
MCH(13) | Instrumentation & Control | 138742 | T16182-YU02-P0CYE-138742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#1 LEB | IFR | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-12-08
MCH(13) | Instrumentation & Control | 138743 | T16182-YT10-P0CYE-138743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#1 LEB | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2018-01-24 | #VALUE!
MCH(13) | Instrumentation & Control | 138744 | T16182-XG02-P0CYE-138744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#1 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2018-01-23 | 2018-04-03
MCH(13) | Mechanical | 138802 | T16182-XG02-P0SGK-138802 | P&ID OF CLEAN AGENT SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-11-20
MCH(13) | Mechanical | 138812 | T16182-XH01-P0SGK-138812 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#2 LEB | IFI | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-12-08
MCH(13) | Mechanical | 138822 | T16182-YT10-P0SGK-138822 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-12-08
MCH(13) | Mechanical | 138831 | T16182-YD00-P0SGZ-138831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#2 LEB | IFI | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-11-20
MCH(13) | Instrumentation & Control | 138841 | T16182-YD00-P0CYE-138841 | FIRE ALARM SYSTEM LAYOUT FOR ST#2 LEB | IFI | 2018-01-20 | 2018-04-20 | O |  |  | PKG-030-FF | 2017-06-08 | 2018-01-17
MCH(13) | Instrumentation & Control | 138842 | T16182-YU02-P0CYE-138842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-06-08 | 2017-12-05
MCH(13) | Instrumentation & Control | 138843 | T16182-YT10-P0CYE-138843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#2 LEB | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2018-01-24 | #VALUE!
MCH(13) | Instrumentation & Control | 138844 | T16182-XG02-P0CYE-138844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2018-01-23 | 2018-04-03
MCH(13) | Mechanical | 138901 | T16182-XG02-P0SGA-138901 | P&ID OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF | 2017-07-26 | 2017-11-06
MCH(13) | Mechanical | 138902 | T16182-XG02-P0SGC-138902 | P&ID OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2018-11-19 | 2018-12-20 |  |  |  | PKG-030-FF | 2018-11-13 | 2018-11-23
MCH(13) | Mechanical | 138911 | T16182-XH01-P0SGA-138911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF | 2017-07-26 | 2017-11-06
MCH(13) | Mechanical | 138912 | T16182-XH01-P0SGC-138912 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2018-11-19 | 2018-12-20 |  |  |  | PKG-030-FF | 2018-11-13 | 2018-11-23
MCH(13) | Mechanical | 138922 | T16182-YT10-P0SGC-138922 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2018-11-19 | 2018-12-20 |  |  |  | PKG-030-FF | 2018-11-15 | 2019-01-02
MCH(13) | Mechanical | 138931 | T16182-YD00-P0SGZ-138931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF | 2017-07-26 | 2017-11-06
MCH(13) | Instrumentation & Control | 138941 | T16182-YD00-P0CYE-138941 | FIRE ALARM SYSTEM LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-07-03 | 2017-10-30 | O |  |  | PKG-030-FF | 2017-06-21 | 2017-10-31
MCH(13) | Instrumentation & Control | 138942 | T16182-YU02-P0CYE-138942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2017-07-03 | 2017-10-30 |  |  |  | PKG-030-FF | 2017-06-21 | 2017-10-31
MCH(13) | Mechanical | 139001 | T16182-XG02-P0SGA-139001 | P&ID OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF | 2017-07-21 | 2017-11-20
MCH(13) | Mechanical | 139002 | T16182-XG02-P0SGK-139002 | P&ID of Clean Agent system for Administration & Social Building | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF | 2017-07-21 | 2017-11-27
MCH(13) | Mechanical | 139011 | T16182-XH01-P0SGA-139011 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF | 2017-07-21 | 2017-11-27
MCH(13) | Mechanical | 139012 | T16182-XH01-P0SGK-139012 | Pipe Layout and detail of Clean Agent system for Administration & Social Building | IFI | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF | 2017-07-21 | 2017-11-27
MCH(13) | Mechanical | 139023 | T16182-YT10-P0SGK-139023 | Flow calculation of Clean Agent system for Administration & Social Building | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-11-27
MCH(13) | Mechanical | 139031 | T16182-YD00-P0SGZ-139031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-11-27
MCH(13) | Instrumentation & Control | 139041 | T16182-YD00-P0CYE-139041 | FIRE ALARM SYSTEM LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-17 | 2018-10-15 | O |  |  | PKG-030-FF | 2017-08-29 | 2017-11-20
MCH(13) | Instrumentation & Control | 139042 | T16182-YU02-P0CYE-139042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-12-05
MCH(13) | Instrumentation & Control | 139043 | T16182-YT10-P0CYE-139043 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2017-08-29 | #VALUE!
MCH(13) | Instrumentation & Control | 139044 | T16182-XG02-P0CYE-139044 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-11-20
MCH(13) | Mechanical | 139101 | T16182-XG02-P0SGA-139101 | P&ID OF STAND PIPE SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-06-15 | 2018-11-08
MCH(13) | Mechanical | 139103 | T16182-XG02-P0SGK-139103 | P&ID OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-06-15 | 2018-10-15
MCH(13) | Mechanical | 139111 | T16182-XH01-P0SGA-139111 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-11-08 | 2018-12-10
MCH(13) | Mechanical | 139113 | T16182-XH01-P0SGK-139113 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-06-21 | 2018-10-15
MCH(13) | Mechanical | 139123 | T16182-YT10-P0SGK-139123 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-06-21 | 2018-10-15
MCH(13) | Mechanical | 139131 | T16182-YD00-P0SGZ-139131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-04-27 | 2018-06-01
MCH(13) | Instrumentation & Control | 139141 | T16182-YD00-P0CYE-139141 | FIRE ALARM SYSTEM LAYOUT FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 | O |  |  | PKG-030-FF | 2018-06-01 | 2018-07-12
MCH(13) | Instrumentation & Control | 139142 | T16182-YU02-P0CYE-139142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-06-01 | 2018-07-12
MCH(13) | Instrumentation & Control | 139143 | T16182-YT10-P0CYE-139143 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | IFI | 2018-11-17 |  |  |  |  | PKG-030-FF | 2018-06-01 | #VALUE!
MCH(13) | Instrumentation & Control | 139144 | T16182-XG02-P0CYE-139144 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF | 2018-06-01 | 2018-07-12
MCH(13) | Mechanical | 139231 | T16182-YD00-P0SGZ-139231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR MAIN GATE HOUSE | IFI | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF | 2018-04-27 | 2018-06-01
MCH(13) | Instrumentation & Control | 139241 | T16182-YD00-P0CYE-139241 | FIRE ALARM SYSTEM LAYOUT FOR MAIN GATE HOUSE | IFI | 2018-05-03 | 2018-08-01 | O |  |  | PKG-030-FF | 2018-05-02 | 2018-06-05
MCH(13) | Instrumentation & Control | 139242 | T16182-YU02-P0CYE-139242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF | 2018-05-02 | 2018-06-05
MCH(13) | Mechanical | 139301 | T16182-XG02-P0SGA-139301 | P&ID OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | IFR | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF | 2018-05-17 | 2018-07-20
MCH(13) | Mechanical | 139311 | T16182-XH01-P0SGA-139311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | IFI | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF | 2018-05-17 | 2018-07-20
MCH(13) | Mechanical | 139331 | T16182-YD00-P0SGZ-139331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR X-RAY SEARCHING ROOM | IFI | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF | 2018-04-27 | 2018-06-01
MCH(13) | Instrumentation & Control | 139341 | T16182-YD00-P0CYE-139341 | FIRE ALARM SYSTEM LAYOUT FOR X-RAY SEARCHING ROOM | IFI | 2018-10-17 | 2019-01-15 | O |  |  | PKG-030-FF | 2018-05-02 | 2018-06-05
MCH(13) | Instrumentation & Control | 139342 | T16182-YU02-P0CYE-139342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR X-RAY SEARCHING ROOM | IFR | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF | 2018-05-02 | 2018-06-05
MCH(13) | Mechanical | 139401 | T16182-XG02-P0SGA-139401 | P&ID OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | IFR | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-12-15
MCH(13) | Mechanical | 139411 | T16182-XH01-P0SGA-139411 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | IFI | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-12-15
MCH(13) | Mechanical | 139431 | T16182-YD00-P0SGZ-139431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE BRIGADE BUILDING | IFI | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-12-21
MCH(13) | Instrumentation & Control | 139441 | T16182-YD00-P0CYE-139441 | FIRE ALARM SYSTEM LAYOUT FOR FIRE BRIGADE BUILDING | IFI | 2018-05-03 | 2018-08-01 | O |  |  | PKG-030-FF | 2017-08-29 | 2017-12-20
MCH(13) | Instrumentation & Control | 139442 | T16182-YU02-P0CYE-139442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | IFR | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-12-08
MCH(13) | Instrumentation & Control | 139443 | T16182-YT10-P0CYE-139443 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2017-08-29 | #VALUE!
MCH(13) | Instrumentation & Control | 139444 | T16182-XG02-P0CYE-139444 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2017-08-29 | 2017-12-13
MCH(13) | Mechanical | 139501 | T16182-XG02-P0SGA-139501 | P&ID OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF | 2017-11-23 | 2018-01-17
MCH(13) | Mechanical | 139502 | T16182-XG02-P0SGE-139502 | P&ID OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-23
MCH(13) | Mechanical | 139511 | T16182-XH01-P0SGA-139511 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF | 2017-11-23 | 2018-01-17
MCH(13) | Mechanical | 139512 | T16182-XH01-P0SGE-139512 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-23
MCH(13) | Mechanical | 139522 | T16182-YT10-P0SGE-139522 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2017-11-23 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-23
MCH(13) | Mechanical | 139531 | T16182-YD00-P0SGZ-139531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-20
MCH(13) | Instrumentation & Control | 139541 | T16182-YD00-P0CYE-139541 | FIRE ALARM SYSTEM LAYOUT FOR MAINTENANCE AND WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 | O |  |  | PKG-030-FF | 2018-02-23 | 2018-03-22
MCH(13) | Instrumentation & Control | 139542 | T16182-YU02-P0CYE-139542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF | 2018-02-23 | 2018-03-22
MCH(13) | Instrumentation & Control | 139543 | T16182-YT10-P0CYE-139543 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF | 2018-01-23 | #VALUE!
MCH(13) | Instrumentation & Control | 139544 | T16182-XG02-P0CYE-139544 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF | 2018-01-24 | 2018-04-03
MCH(13) | Mechanical | 139601 | T16182-XG02-P0SGA-139601 | P&ID OF STAND PIPE SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-11-23 | 2018-01-17
MCH(13) | Mechanical | 139602 | T16182-XG02-P0SGK-139602 | P&ID OF CLEAN AGENT SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-20
MCH(13) | Mechanical | 139603 | T16182-XG02-P0SGE-139603 | P&ID OF SPRINKLER SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-23
MCH(13) | Mechanical | 139611 | T16182-XH01-P0SGA-139611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-11-23 | 2018-01-17
MCH(13) | Mechanical | 139612 | T16182-XH01-P0SGK-139612 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-20
MCH(13) | Mechanical | 139613 | T16182-XH01-P0SGE-139613 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CPP BUILDING | IFI | 2018-04-16 | 2018-06-15 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-23
MCH(13) | Mechanical | 139622 | T16182-YT10-P0SGK-139622 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-20
MCH(13) | Mechanical | 139623 | T16182-YT10-P0SGE-139623 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-23
MCH(13) | Mechanical | 139631 | T16182-YD00-P0SGZ-139631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-11-20 | 2017-12-08
MCH(13) | Instrumentation & Control | 139641 | T16182-YD00-P0CYE-139641 | FIRE ALARM SYSTEM LAYOUT FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 | O |  |  | PKG-030-FF | 2017-09-06 | 2017-11-20
MCH(13) | Instrumentation & Control | 139642 | T16182-YU02-P0CYE-139642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF | 2017-09-06 | 2017-11-20
MCH(13) | Mechanical | 139731 | T16182-YD00-P0SGZ-139731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF | 2018-02-28 | 2018-04-19
MCH(13) | Instrumentation & Control | 139741 | T16182-YD00-P0CYE-139741 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-03-17 | 2018-06-15 | O |  |  | PKG-030-FF | 2018-01-17 | 2018-02-28
MCH(13) | Instrumentation & Control | 139742 | T16182-YU02-P0CYE-139742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFR | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF | 2018-01-17 | 2018-02-28
MCH(13) | Mechanical | 139831 | T16182-YD00-P0SGZ-139831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF | 2018-02-28 | 2018-04-19
MCH(13) | Instrumentation & Control | 139841 | T16182-YD00-P0CYE-139841 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-03-17 | 2018-06-15 | O |  |  | PKG-030-FF | 2018-01-17 | 2018-02-28
MCH(13) | Instrumentation & Control | 139842 | T16182-YU02-P0CYE-139842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR HRSG | IFR | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF | 2018-01-17 | 2018-02-28
MCH(13) | Mechanical | 139901 | T16182-XG02-P0SGC-139901 | P&ID OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF | 2017-07-24 | 2017-11-23
MCH(13) | Mechanical | 139911 | T16182-XH01-P0SGC-139911 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF | 2017-07-24 | 2017-11-23
MCH(13) | Mechanical | 139921 | T16182-YT10-P0SGC-139921 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | IFR | 2017-09-03 | 2017-12-02 |  |  |  | PKG-030-FF | 2017-07-24 | 2017-11-23
MCH(13) | Mechanical | 139931 | T16182-YD00-P0SGZ-139931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG EXCITATION TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF | 2017-06-13 | 2017-11-20
MCH(13) | Instrumentation & Control | 139941 | T16182-YD00-P0CYE-139941 | FIRE ALARM SYSTEM LAYOUT FOR STG EXCITATION TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 | O |  |  | PKG-030-FF | 2017-06-12 | 2017-11-20
MCH(13) | Instrumentation & Control | 139942 | T16182-YU02-P0CYE-139942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG EXCITATION TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF | 2017-06-12 | 2017-12-04
PP(14) | Mechanical | 140001 | T16182-CV03-P0ZEN-140001 | PIPING MATERIAL SPECIFICATION | IFI | 2017-01-25 |  |  | O |  |  | 2017-02-01 | #VALUE!
PP(14) | Mechanical | 140002 | T16182-CV03-P0ZEN-140002 | PIPING INSULATION SPECIFICATION | IFI | 2017-01-25 |  |  | O |  |  | 2017-02-01 | #VALUE!
PP(14) | Mechanical | 140003 | T16182-XN00-P0ZEN-140003 | MANUAL VALVE LIST | IFI | 2017-05-16 |  |  | O |  |  | 2017-05-17 | #VALUE!
PP(14) | Mechanical | 140004 | T16182-XL00-P0ZEN-140004 | PIPING SPECIALTY LIST | IFI | 2017-05-16 |  |  | O |  |  | 2017-05-17 | #VALUE!
PP(14) | Mechanical | 140005 | T16182-XL00-P0ZEN-140005 | PIPING LINE LIST | IFI | 2017-06-16 |  |  | O |  |  | 2017-06-16 | #VALUE!
PP(14) | Mechanical | 140006 | T16182-XL00-P0ZEN-140006 | PIPING TERMINAL POINT LIST BETWEEN FCHPP AND FGP | IFI | 2017-02-10 |  |  | O |  |  | 2017-03-09 | #VALUE!
PP(14) | Mechanical | 140011 | T16182-BP00-P0LBA-140011 | STRESS ANALYSIS REPORT FOR HP STEAM SYSTEM | IFR | 2017-04-28 | 2018-01-15 |  |  |  |  | 2017-04-28 | 2018-09-06
PP(14) | Mechanical | 140012 | T16182-BP00-P0LBC-140012 | STRESS ANALYSIS REPORT FOR IP STEAM SYSTEM | IFR | 2017-05-26 | 2018-01-15 |  |  |  |  | 2017-05-26 | 2018-07-03
PP(14) | Mechanical | 140013 | T16182-BP00-P0LBS-140013 | STRESS ANALYSIS REPORT FOR PROCESS STEAM SYSTEM | IFR | 2017-04-28 | 2017-12-08 |  | O |  |  | 2017-04-28 | 2018-07-06
PP(14) | Mechanical | 140014 | T16182-BP00-P0LAB-140014 | STRESS ANALYSIS REPORT FOR FEED WATER SYSTEM | IFR | 2017-04-28 | 2017-12-08 |  | O |  |  | 2017-04-28 | 2017-12-11
PP(14) | Mechanical | 140015 | T16182-BP00-P0EKG-140015 | STRESS ANALYSIS REPORT FOR FUEL SYSTEM | IFR | 2017-04-28 | 2017-12-20 |  | O |  |  | 2017-04-28 | 2018-03-26
PP(14) | Mechanical | 140016 | T16182-BP00-P0LBG-140016 | STRESS ANALYSIS REPORT FOR LP STEAM SYSTEM | IFR | 2017-06-02 | 2018-02-15 |  |  |  |  | 2017-06-05 | 2018-07-03
PP(14) | Mechanical | 140017 | T16182-BP00-P0LCA-140017 | STRESS ANALYSIS REPORT FOR CONDENSATE SYSTEM | IFR | 2019-06-05 | 2019-07-05 |  |  |  |  | 2019-06-10 | 2019-07-05
PP(14) | Mechanical | 140020 | T16182-XH01-P0ZEN-140020 | KEY PLAN DRAWING | IFI | 2017-09-29 | [5 empty] | 2017-09-29 | #VALUE!
PP(14) | Mechanical | 140021 | T16182-XH01-P6UMA-140021 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 GROUND FLOOR | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140022 | T16182-XH01-P6UMA-140022 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 OPERATING FLOOR | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140023 | T16182-XH01-P7UMA-140023 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 GROUND FLOOR | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140024 | T16182-XH01-P7UMA-140024 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 OPERATING FLOOR | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140025 | T16182-XH01-P6UMA-140025 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #1 AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140026 | T16182-XH01-P7UMA-140026 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #2 & H2 CO2 N2 STORAGE SHELTER AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140027 | T16182-XH01-P0ULY-140027 | PIPING ARRANGEMENT DRAWING FOR ST BLDG PIPE RACK AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140028 | T16182-XH01-P0ULY-140028 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #1 MAIN PIPE RACK AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140029 | T16182-XH01-P0ULY-140029 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #2 MAIN PIPE RACK AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140030 | T16182-XH01-P0ULY-140030 | PIPING ARRANGEMENT DRAWING FOR TO MAIN FCP GATE HOUSE AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140031 | T16182-XH01-P0ZEN-140031 | PIPING ARRANGEMENT DRAWING FOR TO ESF AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140032 | T16182-XH01-P1UHA-140032 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +0 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140034 | T16182-XH01-P1UHA-140034 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +106,000 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140036 | T16182-XH01-P1UHA-140036 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +108,000 & ABOVE | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140037 | T16182-XH01-P2UHA-140037 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +0 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140038 | T16182-XH01-P2UHA-140038 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +106,000 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140039 | T16182-XH01-P2UHA-140039 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +108,000 & ABOVE | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140040 | T16182-XH01-P3UHA-140040 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +0 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140041 | T16182-XH01-P3UHA-140041 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +106,000 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140042 | T16182-XH01-P3UHA-140042 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +108,000 & ABOVE | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140043 | T16182-XH01-P4UHA-140043 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +0 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140044 | T16182-XH01-P4UHA-140044 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +106,000 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140045 | T16182-XH01-P4UHA-140045 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +108,000 & ABOVE | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140046 | T16182-XH01-P5UHA-140046 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +0 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140047 | T16182-XH01-P5UHA-140047 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +106,000 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140048 | T16182-XH01-P5UHA-140048 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +108,000 & ABOVE | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140049 | T16182-XH01-P1MBA-140049 | PIPING ARRANGEMENT DRAWING FOR GT #1 AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140050 | T16182-XH01-P2MBA-140050 | PIPING ARRANGEMENT DRAWING FOR GT #2 AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140051 | T16182-XH01-P3MBA-140051 | PIPING ARRANGEMENT DRAWING FOR GT #3 AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140052 | T16182-XH01-P4MBA-140052 | PIPING ARRANGEMENT DRAWING FOR GT #4 AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140053 | T16182-XH01-P5MBA-140053 | PIPING ARRANGEMENT DRAWING FOR GT #5 AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140054 | T16182-XH01-P0ULA-140054 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +0 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140055 | T16182-XH01-P0ULA-140055 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +111,500 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140056 | T16182-XH01-P0ULA-140056 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +114,500 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140057 | T16182-XH01-P0ULA-140057 | PIPING ARRANGEMENT DRAWING FOR DEAERATOR AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140058 | T16182-XH01-P0ULY-140058 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 1 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140059 | T16182-XH01-P0ULY-140059 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 2 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140060 | T16182-XH01-P0ULY-140060 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 3 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140061 | T16182-XH01-P0ULY-140061 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 4 | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140062 | T16182-XH01-P0ZEN-140062 | PIPING ARRANGEMENT DRAWING FOR CCW FIN FAN COOLER AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140063 | T16182-XH01-P0UTF-140063 | PIPING ARRANGEMENT DRAWING FOR AIR COMPRESSOR AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140064 | T16182-XH01-P0GRK-140064 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT BLDG AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140065 | T16182-XH01-P0UGD-140065 | PIPING ARRANGEMENT DRAWING FOR DEMI & POTABLE WATER TANK AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140066 | T16182-XH01-P0UGA-140066 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK A/B AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140067 | T16182-XH01-P0UGA-140067 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK C AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140068 | T16182-XH01-P0UCB-140068 | PIPING ARRANGEMENT DRAWING FOR CCB AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140069 | T16182-XH01-P0LCA-140069 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK C AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140070 | T16182-XH01-P0LCA-140070 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A/B AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140071 | T16182-XH01-P0LDK-140071 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 1 | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140072 | T16182-XH01-P0LDK-140072 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 2 | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140073 | T16182-XH01-P0EKG-140073 | PIPING ARRANGEMENT DRAWING FOR GPRS AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140074 | T16182-XH01-P0UYE-140074 | PIPING ARRANGEMENT DRAWING FOR MAIN GATE HOUSE AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140075 | T16182-XH01-P0UYF-140075 | PIPING ARRANGEMENT DRAWING FOR SECURITY BUILDING AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140076 | T16182-XH01-P0UYC-140076 | PIPING ARRANGEMENT DRAWING FOR MAIN ADMIN BUILDING AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140077 | T16182-XH01-P0UST-140077 | PIPING ARRANGEMENT DRAWING FOR MAINTENANCE & WORKSHOP BUILDING AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140078 | T16182-XH01-P0UYP-140078 | PIPING ARRANGEMENT DRAWING FOR FIRE BRIGATE AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140079 | T16182-XH01-P7UBA-140079 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #2 AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140080 | T16182-XH01-P6UBA-140080 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #1 & SWAS CONTAINER AREA | IFI | 2017-06-30 | [5 empty] | 2017-06-30 | #VALUE!
PP(14) | Mechanical | 140081 | T16182-XH01-P0ZEN-140081 | PIPING ARRANGEMENT DRAWING FOR FGP TP AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140082 | T16182-XH01-P0ZEN-140082 | PIPING ARRANGEMENT DRAWING FOR YARD AREA TO FGP TP | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140083 | T16182-XH01-P0ZEN-140083 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A & YARD AREA | IFI | 2017-04-28 |  |  | O |  |  | 2017-04-28 | #VALUE!
PP(14) | Mechanical | 140100 | T16182-XJ00-P0ZEN-140100 | FABRICATION STANDARD DRAWING | IFI | 2017-10-20 | [5 empty] | 2017-10-20 | #VALUE!
PP(14) | Mechanical | 140101 | T16182-XJ00-P0LBA-140101 | FABRICATION ISOMETRIC DRAWING FOR HP STEAM SYSTEM | IFI | 2017-10-06 | 2017-12-08 |  |  |  |  | 2017-09-29 | 2017-12-14
PP(14) | Mechanical | 140102 | T16182-XJ00-P0LBC-140102 | FABRICATION ISOMETRIC DRAWING FOR IP STEAM SYSTEM | IFI | 2017-10-06 | 2017-12-14 |  |  |  |  | 2017-09-29 | 2017-12-14
PP(14) | Mechanical | 140103 | T16182-XJ00-P0LBG-140103 | FABRICATION ISOMETRIC DRAWING FOR LP STEAM SYSTEM | IFI | 2017-10-06 | 2017-12-20 |  | O |  |  | 2017-09-29 | 2018-01-02
PP(14) | Mechanical | 140104 | T16182-XJ00-P0LBG-140104 | FABRICATION ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM | IFI | 2017-09-08 | 2017-10-13 |  | O |  |  | 2017-09-11 | 2017-10-16
PP(14) | Mechanical | 140105 | T16182-XJ00-P0LCM-140105 | FABRICATION ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM | IFI | 2017-12-01 | 2018-02-23 |  |  |  |  | 2017-12-04 | 2018-07-16
PP(14) | Mechanical | 140106 | T16182-XJ00-P0LCA-140106 | FABRICATION ISOMETRIC DRAWING FOR CONDENSATE SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  |  |  |  | 2017-09-11 | 2017-11-06
PP(14) | Mechanical | 140108 | T16182-XJ00-P0LAB-140108 | FABRICATION ISOMETRIC DRAWING FOR FEED WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O |  |  | 2017-09-11 | 2017-11-02
PP(14) | Mechanical | 140109 | T16182-XJ00-P0PGB-140109 | FABRICATION ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O |  |  | 2017-09-11 | 2017-11-09
PP(14) | Mechanical | 140110 | T16182-XJ00-P0SCA-140110 | FABRICATION ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM | IFI | 2018-11-23 | 2018-12-14 |  |  |  |  | 2018-11-22 | 2019-02-18
PP(14) | Mechanical | 140112 | T16182-XJ00-P0GKB-140112 | FABRICATION ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O |  |  | 2017-09-11 | 2017-11-06
PP(14) | Mechanical | 140113 | T16182-XJ00-P0GHC-140113 | FABRICATION ISOMETRIC DRAWING FOR DEMI WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O |  |  | 2017-09-11 | 2017-11-09
PP(14) | Mechanical | 140114 | T16182-XJ00-P0PDA-140114 | FABRICATION ISOMETRIC DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | IFI | 2017-10-06 | 2017-11-10 |  | O |  |  | 2017-09-29 | 2017-11-10
PP(14) | Mechanical | 140116 | T16182-XJ00-P0MBH-140116 | FABRICATION ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | IFI | 2017-10-20 | 2017-11-24 |  |  |  |  | 2017-10-25 | 2017-11-24
PP(14) | Mechanical | 140117 | T16182-XJ00-P0EKC-140117 | FABRICATION ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-10-20 | 2017-11-24 |  |  |  |  | 2017-10-20 | 2017-11-28
PP(14) | Mechanical | 140118 | T16182-XJ00-P0EKG-140118 | FABRICATION ISOMETRIC DRAWING FOR FUEL GAS SYSTEM | IFI | 2017-09-08 | 2017-10-13 |  | O |  |  | 2017-09-11 | 2017-10-19
PP(14) | Mechanical | 140119 | T16182-XJ00-P0ZEN-140119 | FABRICATION ISOMETRIC DRAWING FOR TG MISCELLANEOUS SYSTEM | IFI | 2018-03-09 | 2018-04-13 |  |  |  |  | 2018-03-29 | 2018-07-27
PP(14) | Mechanical | 140120 | T16182-XJ00-P0ZEN-140120 | ISOMETRIC DRAWING FOR TG MISCELLANEOUS SMALL BORE SYSTEM | IFI | 2018-03-09 | 2018-04-13 |  |  |  |  | 2018-07-06 | 2018-10-04
PP(14) | Mechanical | 140121 | T16182-XJ00-P0GM-140121 | FABRICATION ISOMETRIC DRAWING FOR WASTE WATER SYSTEM | IFI | 2018-02-16 | 2018-03-16 |  |  |  |  | 2018-02-19 | 2018-03-26
PP(14) | Mechanical | 140201 | T16182-XJ00-P0LBA-140201 | ISOMETRIC DRAWING FOR HP STEAM SYSTEM SMALL BORE | IFI | 2018-02-09 | 2018-03-09 |  |  |  |  | 2018-07-04 | 2018-09-06
PP(14) | Mechanical | 140202 | T16182-XJ00-P0LBC-140202 | ISOMETRIC DRAWING FOR IP STEAM SYSTEM SMALL BORE | IFI | 2018-02-09 | 2018-03-09 |  |  |  |  | 2018-06-14 | 2018-09-06
PP(14) | Mechanical | 140203 | T16182-XJ00-P0LBG-140203 | ISOMETRIC DRAWING FOR LP STEAM SYSTEM SMALL BORE | IFI | 2018-02-09 | 2018-03-09 |  | O |  |  | 2018-06-14 | 2018-09-06
PP(14) | Mechanical | 140204 | T16182-XJ00-P0LBG-140204 | ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM SMALL BORE | IFI | 2017-12-15 | 2018-02-28 |  | O |  |  | 2017-12-15 | 2018-04-12
PP(14) | Mechanical | 140205 | T16182-XJ00-P0LCM-140205 | ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13 |  |  |  |  | 2018-07-06 | 2018-10-24
PP(14) | Mechanical | 140206 | T16182-XJ00-P0LCA-140206 | ISOMETRIC DRAWING FOR CONDENSATE SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13 |  |  |  |  | 2018-05-17 | 2018-09-14
PP(14) | Mechanical | 140208 | T16182-XJ00-P0LAB-140208 | ISOMETRIC DRAWING FOR FEED WATER SYSTEM SMALL BORE | IFI | 2018-01-10 | 2018-02-16 |  | O |  |  | 2018-01-10 | 2018-06-29
PP(14) | Mechanical | 140209 | T16182-XJ00-P0PGB-140209 | ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM SMALL BORE | IFI | 2018-01-10 | 2018-02-16 |  | O |  |  | 2018-01-10 | 2018-04-23
PP(14) | Mechanical | 140210 | T16182-XJ00-P0SCA-140210 | ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM SMALL BORE | IFI | 2017-12-20 | 2018-03-09 |  |  |  |  | 2017-12-20 | 2018-04-13
PP(14) | Mechanical | 140211 | T16182-XJ00-P0QFB-140211 | ISOMETRIC DRAWING FOR INSTRUMENT AIR SYSTEM SMALL BORE | IFI | 2017-12-20 | 2018-03-09 |  | O |  |  | 2017-12-20 | 2018-04-11
PP(14) | Mechanical | 140212 | T16182-XJ00-P0GKB-140212 | ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM SMALL BORE | IFI | 2017-12-15 | 2018-02-28 |  | O |  |  | 2017-12-15 | 2018-04-23
PP(14) | Mechanical | 140213 | T16182-XJ00-P0GHC-140213 | ISOMETRIC DRAWING FOR DEMI WATER SYSTEM SMALL BORE | IFI | 2017-12-15 | 2018-02-28 |  | O |  |  | 2017-12-15 | 2018-04-23
PP(14) | Mechanical | 140215 | T16182-XJ00-P0GKB-140215 | ISOMETRIC DRAWING FOR UNDERGROUND PIPING SYSTEM | IFI | 2017-11-10 | 2017-12-04 |  |  |  |  | 2017-11-10 | 2018-01-19
PP(14) | Mechanical | 140216 | T16182-XJ00-P0MBH-140216 | ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13 |  |  |  |  | 2018-02-26 | 2018-09-06
PP(14) | Mechanical | 140217 | T16182-XJ00-P0EKC-140217 | ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13 |  |  |  |  | 2018-06-18 | 2018-09-06
PP(14) | Mechanical | 140219 | T16182-XJ00-P0QUB-140219 | ISOMETRIC DRAWING FOR SAMPLING SYSTEM SMALL BORE | IFI | 2018-02-20 | 2018-03-21 |  |  |  |  | 2018-06-21 | 2018-09-05
PP(14) | Mechanical | 140221 | T16182-XJ00-P0QCA-140221 | ISOMETRIC DRAWING FOR CHEMICAL DOSING SYSTEM SMALL BORE | IFI | 2018-02-20 | 2018-03-21 |  |  |  |  | 2018-04-23 | 2018-05-14
PP(14) | Mechanical | 140223 | T16182-XJ00-P0QJA-140223 | ISOMETRIC DRAWING FOR N2 GAS SYSTEM SMALL BORE | IFI | 2017-12-20 | 2018-03-09 |  | O |  |  | 2017-12-20 | 2018-04-13
PP(14) | Mechanical | 140224 | T16182-XJ00-P0GM-140224 | ISOMETRIC DRAWING FOR WASTE WATER SYSTEM SMALL BORE | IFI | 2018-02-16 | 2018-03-16 |  |  |  |  | 2018-02-26 | 2018-05-14
PP(14) | Mechanical | 140301 | T16182-YK10-P0LF-140301 | MANUAL BUTTERFLY VALVE OUTLINE DRAWINGS | IFI | 2017-09-15 | [5 empty] | 2017-09-15 | #VALUE!
PP(14) | Mechanical | 140302 | T16182-YK10-P0LF-140302 | MANUAL LOW PRESSURE CASTING VALVE OUTLINE DRAWINGS | IFI | 2017-09-15 | [5 empty] | 2017-09-15 | #VALUE!
PP(14) | Mechanical | 140303 | T16182-YK10-P0LF-140303 | MANUAL HIGH PRESSURE CASTING VALVE OUTLINE DRAWINGS | IFI | 2017-11-17 | [5 empty] | 2017-11-20 | #VALUE!
PP(14) | Mechanical | 140304 | T16182-YK10-P0LF-140304 | MANUAL FORGING VALVE OUTLINE DRAWINGS | IFI | 2017-09-15 | [5 empty] | 2017-09-15 | #VALUE!
PP(14) | Mechanical | 140401 | T16182-XH01-P0LF-140401 | PIPING SUPPORT DETAIL DRAWING FOR HP STEAM SYSTEM | IFI | 2018-01-12 | 2018-02-06 |  |  |  |  | 2018-01-19 | 2018-02-28
PP(14) | Mechanical | 140402 | T16182-XH01-P0LF-140402 | PIPING SUPPORT DETAIL DRAWING FOR IP STEAM SYSTEM | IFI | 2018-01-12 | 2018-02-06 |  |  |  |  | 2018-01-19 | 2018-02-28
PP(14) | Mechanical | 140403 | T16182-XH01-P0LF-140403 | PIPING SUPPORT DETAIL DRAWING FOR LP STEAM SYSTEM | IFI | 2018-01-12 | 2018-02-06 |  |  |  |  | 2018-01-19 | 2018-02-28
PP(14) | Mechanical | 140404 | T16182-XH01-P0LF-140404 | PIPING SUPPORT DETAIL DRAWING FOR PROCESS STEAM SYSTEM | IFI | 2017-10-20 | 2017-11-10 |  |  |  |  | 2017-10-24 | 2017-11-22
PP(14) | Mechanical | 140405 | T16182-XH01-P0LF-140405 | PIPING SUPPORT DETAIL DRAWING FOR STEAM DRAIN SYSTEM | IFI | 2018-01-12 | 2018-02-02 |  |  |  |  | 2018-04-13 | 2018-05-30
PP(14) | Mechanical | 140406 | T16182-XH01-P0LF-140406 | PIPING SUPPORT DETAIL DRAWING FOR CONDENSATE SYSTEM | IFI | 2017-11-17 | 2017-12-15 |  |  |  |  | 2017-11-20 | 2017-12-22
PP(14) | Mechanical | 140407 | T16182-XH01-P0LF-140407 | PIPING SUPPORT DETAIL DRAWING FOR FEEDWATER SYSTEM | IFI | 2017-11-17 | 2017-12-15 |  |  |  |  | 2017-11-20 | 2017-12-22
PP(14) | Mechanical | 140408 | T16182-XH01-P0LF-140408 | PIPING SUPPORT DETAIL DRAWING FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-11-17 | 2017-12-15 |  |  |  |  | 2017-11-20 | 2017-12-22
PP(14) | Mechanical | 140410 | T16182-XH01-P0LF-140410 | PIPING SUPPORT DETAIL DRAWING FOR SERVICE AIR SYSTEM | IFI | 2018-11-30 | 2018-12-21 |  |  |  |  | 2019-04-22 | 2019-06-04
PP(14) | Mechanical | 140411 | T16182-XH01-P0LF-140411 | PIPING SUPPORT DETAIL DRAWING FOR POTABLE WATER SYSTEM | IFI | 2017-11-17 | 2017-12-15 |  |  |  |  | 2017-11-20 | 2017-12-22
PP(14) | Mechanical | 140412 | T16182-XH01-P0LF-140412 | PIPING SUPPORT DETAIL DRAWING FOR DEMI. WATER SYSTEM | IFI | 2017-11-17 | 2017-12-15 |  |  |  |  | 2017-11-20 | 2017-12-22
PP(14) | Mechanical | 140415 | T16182-XH01-P0LF-140415 | PIPING SUPPORT DETAIL DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | IFI | 2017-12-21 | 2018-02-02 |  |  |  |  | 2017-12-22 | 2018-01-19
PP(14) | Mechanical | 140416 | T16182-XH01-P0LF-140416 | PIPING SUPPORT DETAIL DRAWING FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-12-21 | 2018-02-02 |  |  |  |  | 2017-12-22 | 2018-01-19
PP(14) | Mechanical | 140417 | T16182-XH01-P0LF-140417 | PIPING SUPPORT DETAIL DRAWING FOR FUEL GAS SYSTEM | IFI | 2017-11-17 | 2017-12-15 |  |  |  |  | 2017-11-20 | 2017-12-22
PP(14) | Mechanical | 140418 | T16182-XH01-P0LF-140418 | PIPING SUPPORT DETAIL DRAWING FOR STEAM BLOWING | IFI | 2018-09-14 | 2018-10-12 |  |  |  |  | 2018-10-08 | 2018-11-13
PP(14) | Mechanical | 140419 | T16182-XH01-P0LF-140419 | PIPING SUPPORT DETAIL DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | IFI | 2017-11-17 | 2017-12-15 |  |  |  |  | 2017-11-20 | 2017-12-22
PP(14) | Mechanical | 140420 | T16182-XH01-P0LF-140420 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING ESOD AREA | IFI | 2018-02-16 | 2018-03-23 |  |  |  |  | 2018-02-19 | 2018-05-10
PP(14) | Mechanical | 140421 | T16182-XH01-P0LF-140421 | PIPING SUPPORT DETAIL DRAWING FOR WASTE WATER SYSTEM | IFI | 2018-07-27 | 2018-08-20 |  |  |  |  | 2018-07-27 | 2018-09-19
PP(14) | Mechanical | 140422 | T16182-XH01-P0LF-140422 | PIPING SUPPORT DETAIL DRAWING FOR TG MISCELLANEOUS SYSTEM | IFI | 2018-07-27 | 2018-08-20 |  |  |  |  | 2018-07-27 | 2018-09-19
PP(14) | Mechanical | 140423 | T16182-XH01-P0LF-140423 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING NON ESOD AREA | IFI | 2018-08-31 | 2018-09-24 |  |  |  |  | 2018-09-03 | 2018-10-08
EL(15) | Electrical | 150001 | T16182-YR02-P0ZEN-150001 | DESIGN CRITERIA FOR ELECTRICAL SYSTEM | IFR | 2016-12-01 | 2017-06-30 |  | O |  |  | 2016-11-03 | 2017-05-18
EL(15) | Electrical | 150101 | T16182-YL06-P0ZEN-150101 | ELECTRICAL LOAD LIST | IFR | 2017-01-31 | 2017-07-18 |  | O |  |  | 2017-01-18 | 2017-07-28
EL(15) | Electrical | 150201 | T16182-YU02-P0ZEN-150201 | SYMBOL & LEGEND FOR ELECTRICAL SYSTEM | IFR | 2017-01-31 | 2017-06-13 |  |  |  |  | 2017-02-01 | 2017-06-14
EL(15) | Electrical | 150202 | T16182-YU02-P0ZEN-150202 | KEY SINGLE LINE DIAGRAM | IFR | 2016-12-01 | 2017-05-04 | O | O | O |  | 2016-11-03 | 2017-05-10
EL(15) | Electrical | 150211 | T16182-YU02-P0ZEN-150211 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR GTG UNIT | IFR | 2017-01-31 | 2017-06-27 |  | O |  |  | 2017-02-09 | 2017-06-29
EL(15) | Electrical | 150212 | T16182-YU02-P0ZEN-150212 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR STG UNIT | IFR | 2017-01-31 | 2017-06-27 |  |  |  |  | 2017-03-24 | 2017-06-29
EL(15) | Electrical | 150221 | T16182-YU05-P0ZEN-150221 | PHASING DIAGRAM | IFR | 2017-03-31 | 2017-08-25 |  | O |  |  | 2017-04-03 | 2017-08-25
EL(15) | Electrical | 150301 | T16182-YT10-P0ZEN-150301 | SHORT CIRCUIT STUDY | IFR | 2017-04-30 | 2017-10-15 |  | O |  |  | 2017-05-11 | 2017-09-15
EL(15) | Electrical | 150302 | T16182-YT10-P0ZEN-150302 | LOAD FLOW & LARGE MOTOR STARTING STUDY | IFR | 2017-04-30 | 2017-10-15 |  | O |  |  | 2017-05-11 | 2017-09-12
EL(15) | Electrical | 150303 | T16182-YT10-P0ZEN-150303 | CT PT CALCULATION STUDY REPORT FOR HV EQUIPMENT | IFR | 2017-04-30 | 2017-10-15 |  | O |  |  | 2017-05-11 | 2017-09-12
EL(15) | Electrical | 150304 | T16182-YT10-P0ZEN-150304 | HARMONIC STUDY REPORT | IFR | 2017-07-30 | 2017-10-15 |  | O |  |  | 2017-08-21 | 2017-11-08
EL(15) | Electrical | 150305 | T16182-YT10-P0ZEN-150305 | INSULATION STUDY REPORT | IFR | 2017-07-30 | 2017-10-15 |  | O |  |  | 2017-07-28 | 2017-10-30
EL(15) | Electrical | 150306 | T16182-YT10-P0ZEN-150306 | TAP RATIO STUDY REPORT | IFR | 2017-07-30 | 2017-10-15 |  | O |  |  | 2017-07-28 | 2017-09-29
EL(15) | Electrical | 150311 | T16182-YT10-P0ZEN-150311 | PROTECTION RELAY COORDINATION STUDY - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | IFR | 2017-08-30 | 2018-02-14 |  | O |  |  | 2017-09-12 | 2018-01-30
EL(15) | Electrical | 150312 | T16182-YT10-P0ZEN-150312 | PROTECTION RELAY COORDINATION STUDY - MV SWITCHGEAR | IFR | 2017-08-30 | 2018-02-14 |  | O |  | PKG-034-MVSWGR | 2017-10-12 | 2018-01-29
EL(15) | Electrical | 150313 | T16182-YT10-P0ZEN-150313 | PROTECTION RELAY COORDINATION STUDY - LV SWITCHGEAR | IFR | 2017-08-30 | 2018-02-14 |  | O |  | PKG-035-LVSWGR | 2017-09-29 | 2018-02-26
EL(15) | Electrical | 150314 | T16182-YT10-P0ZEN-150314 | PROTECTION RELAY COORDINATION STUDY - GSUT / OVERALL PROTECTION FOR STG UNIT | IFR | 2017-08-30 | 2018-02-14 |  |  |  |  | 2017-09-12 | 2018-01-30
EL(15) | Electrical | 150401 | T16182-YF00-P0BA-150401 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | IFR | 2017-04-14 | 2017-08-25 |  | O |  |  | 2017-04-27 | 2017-08-28
EL(15) | Electrical | 150402 | T16182-YF00-P0BB-150402 | ELECTRICAL CONTROL LOGIC DIAGRAM - MV SWITCHGEAR | IFR | 2017-04-14 | 2017-08-25 |  | O |  | PKG-034-MVSWGR | 2017-04-27 | 2017-09-01
EL(15) | Electrical | 150403 | T16182-YF00-P0BB-150403 | ELECTRICAL CONTROL LOGIC DIAGRAM - LV SWITCHGEAR | IFR | 2017-04-14 | 2017-08-11 |  | O |  | PKG-035-LVSWGR | 2017-04-27 | 2017-08-28
EL(15) | Electrical | 150404 | T16182-YF00-P0BA-150404 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / OVERALL PROTECTION FOR STG UNIT | IFR | 2017-04-14 | 2017-08-25 |  |  |  |  | 2017-04-27 | 2017-08-28
EL(15) | Electrical | 150501 | T16182-YD00-P0UCA-150501 | ELECTRICAL ROOM LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFR | 2017-01-31 | 2017-06-13 |  | O |  |  | 2017-01-05 | 2017-06-14
EL(15) | Electrical | 150502 | T16182-YD00-P0UBA-150502 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #1,2 LEB | IFR | 2017-01-31 | 2017-06-13 |  | O |  |  | 2017-01-05 | 2017-06-14
EL(15) | Electrical | 150503 | T16182-YD00-P0UBA-150503 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #3,4,5 LEB | IFR | 2017-01-31 | 2017-06-13 |  |  |  |  | 2017-01-20 | 2017-06-14
EL(15) | Electrical | 150504 | T16182-YD00-P0UBA-150504 | ELECTRICAL ROOM LAYOUT DRAWING - STG #1 LEB | IFR | 2017-04-30 | 2017-09-10 |  |  |  |  | 2017-04-28 | 2017-07-04
EL(15) | Electrical | 150505 | T16182-YD00-P0UBA-150505 | ELECTRICAL ROOM LAYOUT DRAWING - STG #2 LEB | IFR | 2017-04-30 | 2017-09-10 |  |  |  |  | 2017-04-28 | 2017-07-04
EL(15) | Electrical | 150506 | T16182-YD00-P0UBA-150506 | ELECTRICAL ROOM LAYOUT DRAWING - WATER TREATMENT PLANT BUILDING | IFR | 2017-02-28 | 2017-07-11 |  | O |  |  | 2017-02-27 | 2017-07-04
EL(15) | Electrical | 150508 | T16182-YD00-P0UBA-150508 | ELECTRICAL ROOM LAYOUT DRAWING –AUX. LEB | IFR | 2017-05-31 | 2017-10-11 |  |  |  |  | 2017-06-02 | 2017-11-10
EL(15) | Electrical | 150601 | T16182-YT10-P0BAT-150601 | SIZING CALCULATION - GENERATOR STEP - UP TRANSFORMER | IFR | 2017-01-31 | 2017-06-13 |  | O |  | PKG-031-TR | 2017-01-25 | 2017-05-18
EL(15) | Electrical | 150611 | T16182-YT01-P0BAT-150611 | TECHNICAL SPECIFICATION - GENERATOR STEP - UP TRANSFORMER | IFR | 2017-03-17 | 2017-07-28 | O |  |  | PKG-031-TR | 2017-03-22 | 2017-07-24
EL(15) | Electrical | 150621 | T16182-YD00-P0BAT-150621 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (GTG) | IFI | 2017-04-14 |  | O | O |  | PKG-031-TR | 2017-04-17 | #VALUE!
EL(15) | Electrical | 150626 | T16182-YD00-P0BAT-150626 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (STG) | IFI | 2017-06-02 |  |  |  |  | PKG-031-TR | 2017-06-09 | #VALUE!
EL(15) | Electrical | 150631 | T16182-YU03-P0BAT-150631 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER | IFR | 2017-04-28 | 2017-08-26 |  |  |  | PKG-031-TR | 2017-05-11 | 2017-08-07
EL(15) | Electrical | 150636 | T16182-YU03-P0BAT-150636 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER (STG) | IFR | 2017-05-12 | 2017-08-26 |  |  |  | PKG-031-TR | 2017-05-11 | 2017-08-07
EL(15) | Electrical | 150651 | T16182-YT10-P0BBT-150651 | SIZING CALCULATION - UNIT AUXILIARY TRANSFORMER | IFR | 2017-02-28 | 2017-07-11 |  | O |  | PKG-031-TR | 2017-02-28 | 2017-05-18
EL(15) | Electrical | 150661 | T16182-YT01-P0BBT-150661 | TECHNICAL SPECIFICATION - UNIT AUXILIARY TRANSFORMER | IFR | 2017-03-17 | 2017-07-28 | O |  |  | PKG-031-TR | 2017-03-22 | 2017-08-07
EL(15) | Electrical | 150671 | T16182-YD00-P0BBT-150671 | OUTLINE DRAWING - UNIT AUXILIARY TRANSFORMER | IFI | 2017-03-17 |  | O | O |  | PKG-031-TR | 2017-03-22 | #VALUE!
EL(15) | Electrical | 150681 | T16182-YU03-P0BBT-150681 | SCHEMATIC DIAGRAM - UNIT AUXILIARY TRANSFORMER | IFR | 2017-04-28 | 2017-08-26 |  |  |  | PKG-031-TR | 2017-04-28 | 2017-07-26
EL(15) | Electrical | 150701 | T16182-YT10-P0BAA-150701 | SIZING CALCULATION - GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | IFR | 2017-01-31 | 2017-06-13 |  | O |  | PKG-032-GCB | 2017-02-02 | 2017-06-14
EL(15) | Electrical | 150711 | T16182-YT01-P0BAC-150711 | TECHNICAL SPECIFICATION - GENERATOR CIRCUIT BREAKER | IFR | 2017-05-26 | 2017-09-10 | O |  |  | PKG-032-GCB | 2017-05-29 | 2017-09-15
EL(15) | Electrical | 150721 | T16182-YD00-P0BAC-150721 | OUTLINE DRAWING - GENERATOR CIRCUIT BREAKER | IFI | 2017-05-26 |  | O | O |  | PKG-032-GCB | 2017-05-29 | #VALUE!
EL(15) | Electrical | 150731 | T16182-YU03-P0BAC-150731 | SCHEMATIC DIAGRAM - GENERATOR CIRCUIT BREAKER | IFR | 2017-06-30 | 2017-10-18 |  |  |  | PKG-032-GCB | 2017-07-18 | 2017-09-27
EL(15) | Electrical | 150751 | T16182-YT01-P0BAA-150751 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFR | 2017-05-12 | 2017-09-10 |  |  |  | PKG-033-IPB | 2017-05-17 | 2017-08-25
EL(15) | Electrical | 150752 | T16182-YT01-P0BAA-150752 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFR | 2017-06-16 | 2017-10-13 |  |  |  | PKG-033-IPB | 2017-06-21 | 2017-10-13
EL(15) | Electrical | 150761 | T16182-YD00-P0BAA-150761 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFR | 2017-05-12 | 2017-09-17 |  | O |  | PKG-033-IPB | 2017-05-19 | 2017-09-28
EL(15) | Electrical | 150762 | T16182-YD00-P0BAA-150762 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFR | 2017-06-16 | 2017-10-13 |  |  |  | PKG-033-IPB | 2017-06-21 | 2017-10-25
EL(15) | Electrical | 150766 | T16182-YD00-P0BAA-150766 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-05-31 |  |  |  |  | PKG-033-IPB | 2017-06-05 | #VALUE!
EL(15) | Electrical | 150767 | T16182-YD00-P0BAA-150767 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-06-30 |  |  |  |  | PKG-033-IPB | 2017-07-03 | #VALUE!
EL(15) | Electrical | 150771 | T16182-YD00-P0BAA-150771 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-06-30 |  |  |  |  | PKG-033-IPB | 2017-07-03 | #VALUE!
EL(15) | Electrical | 150772 | T16182-YD00-P0BAA-150772 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-07-28 |  |  |  |  | PKG-033-IPB | 2017-07-21 | #VALUE!
EL(15) | Electrical | 150776 | T16182-YD00-P0BAA-150776 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-06-30 |  |  |  |  | PKG-033-IPB | 2017-07-03 | #VALUE!
EL(15) | Electrical | 150777 | T16182-YD00-P0BAA-150777 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-07-28 |  |  |  |  | PKG-033-IPB | 2017-07-21 | #VALUE!
EL(15) | Electrical | 150781 | T16182-YD00-P0BAA-150781 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-07-28 |  |  |  |  | PKG-033-IPB | 2017-07-21 | #VALUE!
EL(15) | Electrical | 150782 | T16182-YD00-P0BAA-150782 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-08-25 |  |  |  |  | PKG-033-IPB | 2017-08-25 | #VALUE!
EL(15) | Electrical | 150801 | T16182-YT01-P0BB-150801 | TECHNICAL SPECIFICATION - MV SWITCHGEAR | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-034-MVSWGR | 2017-05-02 | 2017-10-16
EL(15) | Electrical | 150811 | T16182-YU02-P0BB-150811 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #1 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150812 | T16182-YU02-P0BB-150812 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #2 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR | 2017-07-05 | #VALUE!
EL(15) | Electrical | 150813 | T16182-YU02-P0BB-150813 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #3 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR | 2017-07-05 | #VALUE!
EL(15) | Electrical | 150814 | T16182-YU02-P0BB-150814 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #4 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR | 2017-07-05 | #VALUE!
EL(15) | Electrical | 150815 | T16182-YU02-P0BB-150815 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #5 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR | 2017-07-05 | #VALUE!
EL(15) | Electrical | 150816 | T16182-YU02-P0BB-150816 | SINGLE LINE DIAGRAM – 13.8kV COMMON SWITCHGEAR | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR | 2017-07-05 | #VALUE!
EL(15) | Electrical | 150821 | T16182-YD00-P0BB-150821 | OUTLINE DRAWING - MV SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-034-MVSWGR | 2017-04-27 | #VALUE!
EL(15) | Electrical | 150831 | T16182-YU03-P0BB-150831 | WIRING DIAGRAM - MV SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-034-MVSWGR | 2017-06-16 | #VALUE!
EL(15) | Electrical | 150836 | T16182-YU03-P0BB-150836 | DRAWINGS - HTS | IFI | 2017-06-16 |  |  |  |  | PKG-034-MVSWGR | 2017-07-18 | #VALUE!
EL(15) | Electrical | 150901 | T16182-YT01-P0BF-150901 | TECHNICAL SPECIFICATION - LV SWITCHGEAR | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-035-LVSWGR | 2017-05-02 | 2017-11-17
EL(15) | Electrical | 150902 | T16182-YT01-P0BF-150902 | TECHNICAL SPECIFICATION - 13.8/0.48kV MOLD TRANSFORMER | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-035-LVSWGR | 2017-05-02 | 2017-10-11
EL(15) | Electrical | 150903 | T16182-YT01-P0BF-150903 | TECHNICAL SPECIFICATION - 480V NON SEGREGATED PHASE BUS DUCT | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-035-LVSWGR | 2017-05-02 | 2017-09-28
EL(15) | Electrical | 150911 | T16182-YU02-P0BFA-150911 | SINGLE LINE DIAGRAM - 480V GTG/HRSG SWITCHGEAR | IFI | 2017-04-30 |  |  | O |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150912 | T16182-YU02-P0BFA-150912 | SINGLE LINE DIAGRAM - 480V STG/ACC SWITCHGEAR | IFI | 2017-06-30 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150913 | T16182-YU02-P0BFA-150913 | SINGLE LINE DIAGRAM - 480V COMMON SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150914 | T16182-YU02-P0BFA-150914 | SINGLE LINE DIAGRAM - 480V WT SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150915 | T16182-YU02-P0BFA-150915 | SINGLE LINE DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | IFI | 2017-06-30 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150916 | T16182-YU02-P0BFA-150916 | SINGLE LINE DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150917 | T16182-YU02-P0BFA-150917 | SINGLE LINE DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | IFI | 2017-06-30 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150918 | T16182-YU02-P0BFA-150918 | SINGLE LINE DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150931 | T16182-YD00-P0BF-150931 | OUTLINE DRAWING - 480V GTG/HRSG SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150932 | T16182-YD00-P0BF-150932 | OUTLINE DRAWING - 480V STG/ACC SWITCHGEAR | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150933 | T16182-YD00-P0BF-150933 | OUTLINE DRAWING - 480V COMMON SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150934 | T16182-YD00-P0BF-150934 | OUTLINE DRAWING - 480V WT SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150935 | T16182-YD00-P0BF-150935 | OUTLINE DRAWING - 480V FIRE BRIGADE SWITCHGEAR | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150936 | T16182-YD00-P0BF-150936 | OUTLINE DRAWING - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150937 | T16182-YD00-P0BF-150937 | OUTLINE DRAWING - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150938 | T16182-YD00-P0BF-150938 | OUTLINE DRAWING - 480V COMMON ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150939 | T16182-YD00-P0BF-150939 | OUTLINE DRAWING - 13.8/0.48kV MOLD TRANSFORMER | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR | 2017-05-02 | #VALUE!
EL(15) | Electrical | 150940 | T16182-YD00-P0BF-150940 | OUTLINE DRAWING - 480V NON SEGREGATED PHASE BUS DUCT | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150951 | T16182-YU03-P0BFA-150951 | WIRING DIAGRAM - 480V GTG/HRSG SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150952 | T16182-YU03-P0BFA-150952 | WIRING DIAGRAM - 480V STG/ACC SWITCHGEAR | IFI | 2017-07-31 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150953 | T16182-YU03-P0BFA-150953 | WIRING DIAGRAM - 480V COMMON SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150954 | T16182-YU03-P0BFA-150954 | WIRING DIAGRAM - 480V WT SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150955 | T16182-YU03-P0BFA-150955 | WIRING DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | IFI | 2017-07-31 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150956 | T16182-YU03-P0BFA-150956 | WIRING DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150957 | T16182-YU03-P0BFA-150957 | WIRING DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | IFI | 2017-07-31 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 150958 | T16182-YU03-P0BFA-150958 | WIRING DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR | 2017-06-21 | #VALUE!
EL(15) | Electrical | 151001 | T16182-YT10-P0BT-151001 | SIZING CALCULATION - DC & AC UPS SYSTEM | IFR | 2017-02-28 | 2017-07-25 |  | O |  | PKG-036-DCACUPS | 2017-02-22 | 2017-08-28
EL(15) | Electrical | 151011 | T16182-YT01-P0BT-151011 | TECHNICAL SPECIFICATION - DC & AC UPS SYSTEM | IFR | 2017-06-16 | 2017-09-25 |  |  |  | PKG-036-DCACUPS | 2017-06-27 | 2017-07-27
EL(15) | Electrical | 151021 | T16182-YU02-P0BT-151021 | SINGLE LINE DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | IFI | 2017-06-16 |  |  | O |  | PKG-036-DCACUPS | 2017-07-03 | #VALUE!
EL(15) | Electrical | 151026 | T16182-YU02-P0BT-151026 | SINGLE LINE DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | IFI | 2017-06-16 |  |  | O |  | PKG-036-DCACUPS | 2017-07-03 | #VALUE!
EL(15) | Electrical | 151031 | T16182-YU02-P0BT-151031 | SINGLE LINE DIAGRAM - COMMON DC & UPS SYSTEM | IFI | 2017-06-16 |  |  | O |  | PKG-036-DCACUPS | 2017-07-03 | #VALUE!
EL(15) | Electrical | 151041 | T16182-YD00-P0BT-151041 | OUTLINE DRAWING - BLOCK #1 DC & AC UPS SYSTEM | IFI | 2017-07-07 |  |  |  |  | PKG-036-DCACUPS | 2017-07-05 | #VALUE!
EL(15) | Electrical | 151046 | T16182-YD00-P0BT-151046 | OUTLINE DRAWING - BLOCK #2 DC & AC UPS SYSTEM | IFI | 2017-07-07 |  |  |  |  | PKG-036-DCACUPS | 2017-07-05 | #VALUE!
EL(15) | Electrical | 151051 | T16182-YD00-P0BT-151051 | OUTLINE DRAWING - COMMON DC & AC UPS SYSTEM | IFI | 2017-07-07 |  |  |  |  | PKG-036-DCACUPS | 2017-07-05 | #VALUE!
EL(15) | Electrical | 151061 | T16182-YU03-P0BT-151061 | SCHEMATIC DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | IFI | 2017-07-31 |  |  |  |  | PKG-036-DCACUPS | 2017-08-30 | #VALUE!
EL(15) | Electrical | 151066 | T16182-YU03-P0BT-151066 | SCHEMATIC DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | IFI | 2017-07-31 |  |  |  |  | PKG-036-DCACUPS | 2017-08-30 | #VALUE!
EL(15) | Electrical | 151071 | T16182-YU03-P0BT-151071 | SCHEMATIC DIAGRAM - COMMON DC & AC UPS SYSTEM | IFI | 2017-07-31 |  |  |  |  | PKG-036-DCACUPS | 2017-08-30 | #VALUE!
EL(15) | Electrical | 151101 | T16182-YT01-P0CHB-151101 | TECHNICAL SPECIFICATION - PROTECTION RELAY PANEL | IFR | 2017-05-15 | 2017-09-11 |  |  |  | PKG-037-PRP | 2017-05-22 | 2017-09-12
EL(15) | Electrical | 151111 | T16182-YD00-P0CHB-151111 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | IFI | 2017-05-15 |  |  |  |  | PKG-037-PRP | 2017-05-22 | #VALUE!
EL(15) | Electrical | 151112 | T16182-YD00-P0CHB-151112 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR STG UNIT | IFI | 2017-05-15 |  |  |  |  | PKG-037-PRP | 2017-05-22 | #VALUE!
EL(15) | Electrical | 151121 | T16182-YU03-P0CHB-151121 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | IFI | 2017-06-15 |  |  |  |  | PKG-037-PRP | 2017-06-21 | #VALUE!
EL(15) | Electrical | 151122 | T16182-YU03-P0CHB-151122 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR STG UNIT | IFI | 2017-06-15 |  |  |  |  | PKG-037-PRP | 2017-06-21 | #VALUE!
EL(15) | Electrical | 151131 | T16182-YD00-P0CHB-151131 | CONFIGURATION DIAGRM - FAULT MONITORING SYSTEM | IFI | 2017-05-15 |  |  |  |  | PKG-038-MP | 2017-05-22 | #VALUE!
EL(15) | Electrical | 151161 | T16182-YT01-P0CFA-151161 | TECHNICAL SPECIFICATION - METERING PANEL | IFR | 2017-05-15 | 2017-09-11 |  |  |  | PKG-038-MP | 2017-05-22 | 2017-09-12
EL(15) | Electrical | 151171 | T16182-YD00-P0CFA-151171 | OUTLINE DRAWING - METERING PANEL | IFI | 2017-05-15 |  |  |  |  | PKG-038-MP | 2017-05-22 | #VALUE!
EL(15) | Electrical | 151181 | T16182-YU03-P0CFA-151181 | WIRING DIAGRAM - METERING PANEL | IFI | 2017-06-15 |  |  |  |  | PKG-038-MP | 2017-06-21 | #VALUE!
EL(15) | Electrical | 152001 | T16182-YQ02-P0ZEN-152001 | TYPICAL INSTALLATION DRAWING - RACEWAY | IFR | 2017-01-31 | 2017-05-21 |  |  |  |  | 2017-01-25 | 2017-04-05
EL(15) | Electrical | 152002 | T16182-DE00-P0ZEN-152002 | TECHNICAL SPECIFICATION - CABLE TRAY AND ACCESSORIES | IFR | 2017-05-30 | 2017-08-09 |  |  |  |  | 2017-07-27 | 2017-08-30
EL(15) | Electrical | 152003 | T16182-YD16-P0ZEN-152003 | MAIN CABLE ROUTE PLAN | IFR | 2017-01-26 | 2017-05-16 |  | O |  |  | 2016-12-23 | 2017-06-01
EL(15) | Electrical | 152004 | T16182-YD04-P0ZEN-152004 | 380KV CABLE ROUTE PLAN | IFR | 2017-03-03 | 2017-06-21 |  | O |  |  | 2017-03-30 | 2017-08-24
EL(15) | Electrical | 152005 | T16182-YD04-P0ZEN-152005 | CABLE TRAY LAYOUT FOR CENTRAL CONTROL BUILDING | IFI | 2017-07-18 | 2017-09-16 |  | O |  |  | 2017-07-21 | 2017-09-25
EL(15) | Electrical | 152006 | T16182-YD04-P0ZEN-152006 | CABLE TRAY LAYOUT FOR GTG #1,2 LEB | IFI | 2017-08-24 | 2017-10-23 |  | O |  |  | 2017-08-30 | 2017-09-25
EL(15) | Electrical | 152007 | T16182-YD04-P0ZEN-152007 | CABLE TRAY LAYOUT FOR GTG #3,4,5 LEB | IFI | 2017-11-23 | 2018-01-22 |  |  |  |  | 2017-11-23 | 2018-02-01
EL(15) | Electrical | 152008 | T16182-YD04-P0ZEN-152008 | CABLE TRAY LAYOUT FOR ST #1 LEB | IFI | 2017-11-03 | 2018-01-02 |  |  |  |  | 2017-11-01 | 2017-12-08
EL(15) | Electrical | 152009 | T16182-YD04-P0ZEN-152009 | CABLE TRAY LAYOUT FOR ST #2 LEB | IFI | 2017-12-06 | 2018-02-04 |  |  |  |  | 2017-11-01 | 2017-12-08
EL(15) | Electrical | 152010 | T16182-YD04-P0ZEN-152010 | CABLE TRAY LAYOUT FOR ST BUILDING | IFI | 2018-04-19 | 2018-06-18 |  |  |  |  | 2018-04-10 | 2018-05-25
EL(15) | Electrical | 152011 | T16182-YD04-P0ZEN-152011 | CABLE TRAY LAYOUT FOR WATER TREATMENT BUILDING | IFI | 2017-07-20 | 2017-09-18 |  |  |  |  | 2017-07-21 | 2017-09-25
EL(15) | Electrical | 152012 | T16182-YD04-P0ZEN-152012 | CABLE TRAY LAYOUT FOR FGS ELECTRICAL BUILDING | IFI | 2017-12-06 | 2018-02-04 |  | O |  |  | 2017-11-01 | 2017-12-08
EL(15) | Electrical | 152013 | T16182-YD04-P0ZEN-152013 | CABLE TRAY LAYOUT FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-02-22 | 2018-04-23 |  |  |  |  | 2018-02-21 | 2018-04-24
EL(15) | Electrical | 152014 | T16182-YD04-P0ZEN-152014 | CABLE TRAY LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-06-08 | 2018-08-07 |  |  |  |  | 2018-03-09 | 2018-04-13
EL(15) | Electrical | 152015 | T16182-YD04-P0ZEN-152015 | CABLE TRAY LAYOUT FOR PIPE RACK | IFI | 2017-09-07 | 2017-11-06 |  |  |  |  | 2017-09-25 | 2017-11-14
EL(15) | Electrical | 152016 | T16182-YD04-P0ZEN-152016 | CABLE TRAY LAYOUT FOR AUX LEB | IFI | 2018-01-26 | 2018-04-26 |  |  |  |  | 2018-01-29 | 2018-04-10
EL(15) | Electrical | 152017 | T16182-YD04-P0ZEN-152017 | CABLE TRAY LAYOUT FOR GTG PCC #1,2,3,4,5 | IFI | 2018-01-26 | 2018-04-26 |  |  |  |  | 2018-02-06 | 2018-05-03
EL(15) | Electrical | 152018 | T16182-YD04-P0ZEN-152018 | CABLE TRAY LAYOUT FOR TANK SLEEPER AREA | IFI | 2018-01-08 | 2018-04-08 |  |  |  |  | 2018-01-09 | 2018-04-10
EL(15) | Electrical | 152019 | T16182-YD04-P0ZEN-152019 | CABLE TRAY LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2018-01-26 | 2018-04-26 |  |  |  |  | 2018-01-29 | 2018-03-26
EL(15) | Electrical | 152020 | T16182-YD04-P0ZEN-152020 | CABLE TRAY LAYOUT FOR SECURITY BUILDING | IFI | 2019-02-28 | 2019-05-28 |  |  |  |  | 2019-02-21 | 2019-04-16
EL(15) | Electrical | 152052 | T16182-YB03-P0ZEN-152052 | CONTROL CABLE CONNECTION DIAGRAM | IFI | 2017-09-15 | [5 empty] | 2017-10-12 | #VALUE!
EL(15) | Electrical | 152201 | T16182-YQ01-P0ZEN-152201 | TYPICAL INSTALLATION DRAWING - LIGHTING AND SMALL POWER | IFR | 2017-01-31 | 2017-05-01 |  |  |  |  | 2017-01-26 | 2017-04-29
EL(15) | Electrical | 152202 | T16182-DE00-P0ZEN-152202 | TECHNICAL SPECIFICATION - LIGHTING AND SMALL POWER | IFR | 2017-08-22 | 2017-11-30 |  |  |  |  | 2017-09-01 | 2017-10-24
EL(15) | Electrical | 152203 | T16182-YT10-P0ZEN-152203 | ILLUMINATION CALCULATION - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 |  |  | O |  |  | 2017-04-10 | #VALUE!
EL(15) | Electrical | 152204 | T16182-YT10-P0ZEN-152204 | ILLUMINATION CALCULATION - GTG #1,2 LEB | IFI | 2017-09-03 |  |  | O |  |  | 2017-04-17 | #VALUE!
EL(15) | Electrical | 152205 | T16182-YT10-P0ZEN-152205 | ILLUMINATION CALCULATION - GTG #3,4,5 LEB | IFI | 2017-12-23 | [5 empty] | 2017-05-29 | #VALUE!
EL(15) | Electrical | 152206 | T16182-YT10-P0ZEN-152206 | ILLUMINATION CALCULATION - ST #1 LEB | IFI | 2017-12-03 | [5 empty] | 2017-12-11 | #VALUE!
EL(15) | Electrical | 152207 | T16182-YT10-P0ZEN-152207 | ILLUMINATION CALCULATION - ST #2 LEB | IFI | 2018-01-05 | [5 empty] | 2018-01-08 | #VALUE!
EL(15) | Electrical | 152208 | T16182-YT10-P0ZEN-152208 | ILLUMINATION CALCULATION - ST BUILDING | IFI | 2018-05-19 | [5 empty] | 2018-05-17 | #VALUE!
EL(15) | Electrical | 152209 | T16182-YT10-P0ZEN-152209 | ILLUMINATION CALCULATION - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 |  |  | O |  |  | 2017-05-29 | #VALUE!
EL(15) | Electrical | 152210 | T16182-YT10-P0ZEN-152210 | ILLUMINATION CALCULATION - ADMINISTRATION | IFI | 2018-07-02 | [5 empty] | 2018-03-05 | #VALUE!
EL(15) | Electrical | 152211 | T16182-YT10-P0ZEN-152211 | ILLUMINATION CALCULATION - SECURITY BUILDING | IFI | 2018-12-01 | [5 empty] | 2018-04-25 | #VALUE!
EL(15) | Electrical | 152212 | T16182-YT10-P0ZEN-152212 | ILLUMINATION CALCULATION - MAIN GATE HOUSE | IFI | 2018-04-21 | [5 empty] | 2018-04-25 | #VALUE!
EL(15) | Electrical | 152213 | T16182-YT10-P0ZEN-152213 | ILLUMINATION CALCULATION - SUPPORT BUILDING | IFI | 2018-04-21 | [5 empty] | 2018-04-25 | #VALUE!
EL(15) | Electrical | 152214 | T16182-YT10-P0ZEN-152214 | ILLUMINATION CALCULATION - X-RAY SEARCHING ROOM | IFI | 2018-04-21 | [5 empty] | 2018-04-25 | #VALUE!
EL(15) | Electrical | 152215 | T16182-YT10-P0ZEN-152215 | ILLUMINATION CALCULATION - MAIN GATE HOUSE SUNSHADE | IFI | 2018-04-21 | [5 empty] | 2018-04-25 | #VALUE!
EL(15) | Electrical | 152216 | T16182-YT10-P0ZEN-152216 | ILLUMINATION CALCULATION - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03 | [5 empty] | 2018-01-08 | #VALUE!
EL(15) | Electrical | 152217 | T16182-YT10-P0ZEN-152217 | ILLUMINATION CALCULATION - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19 | [5 empty] | 2017-11-27 | #VALUE!
EL(15) | Electrical | 152218 | T16182-YT10-P0ZEN-152218 | ILLUMINATION CALCULATION - H2, CO2, N2 STORAGE SHELTER | IFI | 2017-08-25 | [5 empty] | 2017-08-25 | #VALUE!
EL(15) | Electrical | 152219 | T16182-YT10-P0ZEN-152219 | ILLUMINATION CALCULATION - AIR COMPRESSOR SHELTER | IFI | 2018-01-05 | [5 empty] | 2018-01-08 | #VALUE!
EL(15) | Electrical | 152220 | T16182-YT10-P0ZEN-152220 | ILLUMINATION CALCULATION - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-12-15 | [5 empty] | 2017-12-18 | #VALUE!
EL(15) | Electrical | 152221 | T16182-YT10-P0ZEN-152221 | ILLUMINATION CALCULATION - FIRE WATER PUMP HOUSE | IFI | 2017-09-03 | [5 empty] | 2017-09-11 | #VALUE!
EL(15) | Electrical | 152222 | T16182-YT10-P0ZEN-152222 | ILLUMINATION CALCULATION - WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-10-30 | [5 empty] | 2017-11-07 | #VALUE!
EL(15) | Electrical | 152223 | T16182-YT10-P0ZEN-152223 | ILLUMINATION CALCULATION - WATER TREATMENT BUILDING | IFI | 2017-08-29 |  |  | O |  |  | 2017-08-21 | #VALUE!
EL(15) | Electrical | 152224 | T16182-YT10-P0ZEN-152224 | ILLUMINATION CALCULATION - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23 | [5 empty] | 2018-03-27 | #VALUE!
EL(15) | Electrical | 152225 | T16182-YT10-P0ZEN-152225 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-04-17 | [5 empty] | 2018-04-23 | #VALUE!
EL(15) | Electrical | 152226 | T16182-YT10-P0ZEN-152226 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-05-11 | [5 empty] | 2018-05-11 | #VALUE!
EL(15) | Electrical | 152229 | T16182-YT10-P0ZEN-152229 | ILLUMINATION CALCULATION - YARD | IFI | 2018-03-14 | [5 empty] | 2018-03-30 | #VALUE!
EL(15) | Electrical | 152230 | T16182-YT10-P0ZEN-152230 | ILLUMINATION CALCULATION – TANK AREA | IFI | 2018-01-22 | [5 empty] | 2018-01-24 | #VALUE!
EL(15) | Electrical | 152231 | T16182-YT10-P0ZEN-152231 | ILLUMINATION CALCULATION – GTG #1, 2 TRANSFORMER AREA | IFI | 2018-01-22 | [5 empty] | 2018-01-24 | #VALUE!
EL(15) | Electrical | 152232 | T16182-YT10-P0ZEN-152232 | ILLUMINATION CALCULATION – GTG #3, 4, 5 TRANSFORMER AREA | IFI | 2018-03-02 | [5 empty] | 2018-03-08 | #VALUE!
EL(15) | Electrical | 152233 | T16182-YT10-P0ZEN-152233 | ILLUMINATION CALCULATION – STG #1, 2 TRANSFORMER AREA | IFI | 2018-03-02 | [5 empty] | 2018-03-08 | #VALUE!
EL(15) | Electrical | 152234 | T16182-YT10-P0ZEN-152234 | ILLUMINATION CALCULATION – FUEL GAS SYSTEM AREA | IFI | 2018-04-06 | [5 empty] | 2018-03-30 | #VALUE!
EL(15) | Electrical | 152301 | T16182-YQ01-P0ZEN-152301 | LIGHTING & SMALL POWER LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 | 2017-10-14 |  | O |  |  | 2017-04-10 | 2017-07-12
EL(15) | Electrical | 152302 | T16182-YQ01-P0ZEN-152302 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #1,2 LEB | IFI | 2017-09-03 | 2017-11-02 |  | O |  |  | 2017-04-17 | 2017-07-12
EL(15) | Electrical | 152303 | T16182-YQ01-P0ZEN-152303 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-12-23 | 2018-02-21 |  |  |  |  | 2017-05-29 | 2017-07-12
EL(15) | Electrical | 152304 | T16182-YQ01-P0ZEN-152304 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #1 LEB | IFI | 2017-12-03 | 2018-02-01 |  |  |  |  | 2017-12-11 | 2018-02-05
EL(15) | Electrical | 152305 | T16182-YQ01-P0ZEN-152305 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #2 LEB | IFI | 2018-01-05 | 2018-03-06 |  |  |  |  | 2018-01-08 | 2018-03-12
EL(15) | Electrical | 152306 | T16182-YQ01-P0ZEN-152306 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST BUILDING | IFI | 2018-05-19 | 2018-07-18 |  |  |  |  | 2018-05-17 | 2018-07-16
EL(15) | Electrical | 152307 | T16182-YQ01-P0ZEN-152307 | LIGHTING & SMALL POWER LAYOUT DRAWING - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 | 2018-03-06 |  | O |  |  | 2017-05-29 | 2017-07-12
EL(15) | Electrical | 152308 | T16182-YQ01-P0ZEN-152308 | LIGHTING & SMALL POWER LAYOUT DRAWING - ADMINISTRATION | IFI | 2018-07-02 | 2018-03-27 |  |  |  |  | 2018-03-05 | 2018-03-27
EL(15) | Electrical | 152309 | T16182-YQ01-P0ZEN-152309 | LIGHTING & SMALL POWER LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-12-01 | 2018-10-24 |  |  |  |  | 2018-04-25 | 2018-10-24
EL(15) | Electrical | 152310 | T16182-YQ01-P0ZEN-152310 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE | IFI | 2018-04-21 | 2018-10-24 |  |  |  |  | 2018-04-25 | 2018-10-24
EL(15) | Electrical | 152311 | T16182-YQ01-P0ZEN-152311 | LIGHTING & SMALL POWER LAYOUT DRAWING - SUPPORT BUILDING | IFI | 2018-04-21 | 2018-10-24 |  |  |  |  | 2018-04-25 | 2018-10-24
EL(15) | Electrical | 152312 | T16182-YQ01-P0ZEN-152312 | LIGHTING & SMALL POWER LAYOUT DRAWING - X-RAY SEARCHING ROOM | IFI | 2018-04-21 | 2018-10-24 |  |  |  |  | 2018-04-25 | 2018-10-24
EL(15) | Electrical | 152313 | T16182-YQ01-P0ZEN-152313 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE SUNSHADE | IFI | 2018-04-21 | 2018-10-24 |  |  |  |  | 2018-04-25 | 2018-10-24
EL(15) | Electrical | 152314 | T16182-YQ01-P0ZEN-152314 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03 | 2018-05-17 |  |  |  |  | 2018-01-08 | 2018-05-17
EL(15) | Electrical | 152315 | T16182-YQ01-P0ZEN-152315 | LIGHTING & SMALL POWER LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19 | 2018-05-18 |  |  |  |  | 2017-11-27 | 2018-05-11
EL(15) | Electrical | 152316 | T16182-YQ01-P0ZEN-152316 | LIGHTING & SMALL POWER LAYOUT DRAWING - H2, CO2, N2 STORAGE SHELTER | IFI | 2017-08-25 | 2018-04-25 |  |  |  |  | 2017-08-25 | 2018-04-25
EL(15) | Electrical | 152317 | T16182-YQ01-P0ZEN-152317 | LIGHTING & SMALL POWER LAYOUT DRAWING - AIR COMPRESSOR SHELTER | IFI | 2018-01-05 | 2018-03-06 |  |  |  |  | 2018-01-08 | 2018-03-12
EL(15) | Electrical | 152318 | T16182-YQ01-P0ZEN-152318 | LIGHTING & SMALL POWER LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-12-15 | 2018-02-13 |  |  |  |  | 2017-12-18 | 2018-02-26
EL(15) | Electrical | 152319 | T16182-YQ01-P0ZEN-152319 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE WATER PUMP HOUSE | IFI | 2017-09-03 | 2017-11-02 |  |  |  |  | 2017-09-11 | 2017-11-07
EL(15) | Electrical | 152320 | T16182-YQ01-P0ZEN-152320 | LIGHTING & SMALL POWER LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-10-30 | 2017-12-29 |  |  |  |  | 2017-11-07 | 2017-12-22
EL(15) | Electrical | 152321 | T16182-YQ01-P0ZEN-152321 | LIGHTING & SMALL POWER LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-08-29 | 2017-10-28 |  | O |  |  | 2017-08-21 | 2017-11-02
EL(15) | Electrical | 152322 | T16182-YQ01-P0ZEN-152322 | LIGHTING & SMALL POWER LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23 | 2018-05-22 |  |  |  |  | 2018-03-27 | 2018-05-18
EL(15) | Electrical | 152323 | T16182-YQ01-P0ZEN-152323 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-04-17 | 2018-06-16 |  |  |  |  | 2018-04-23 | 2018-05-11
EL(15) | Electrical | 152324 | T16182-YQ01-P0ZEN-152324 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-05-11 | 2018-07-10 |  |  |  |  | 2018-05-11 | 2018-07-16
EL(15) | Electrical | 152327 | T16182-YQ01-P0ZEN-152327 | LIGHTING & SMALL POWER LAYOUT DRAWING - YARD | IFR | 2018-03-14 | 2018-07-12 |  |  |  |  | 2018-03-30 | 2018-05-28
EL(15) | Electrical | 152328 | T16182-YQ01-P0ZEN-152328 | LIGHTING & SMALL POWER LAYOUT DRAWING – TANK AREA | IFI | 2018-01-22 | 2018-03-22 |  |  |  |  | 2018-01-24 | 2018-03-27
EL(15) | Electrical | 152329 | T16182-YQ01-P0ZEN-152329 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #1, 2 TRANSFORMER AREA | IFI | 2018-01-22 | 2018-03-22 |  |  |  |  | 2018-01-24 | 2018-03-27
EL(15) | Electrical | 152330 | T16182-YQ01-P0ZEN-152330 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #3, 4, 5 TRANSFORMER AREA | IFI | 2018-03-02 | 2018-06-01 |  |  |  |  | 2018-03-08 | 2018-06-15
EL(15) | Electrical | 152331 | T16182-YQ01-P0ZEN-152331 | LIGHTING & SMALL POWER LAYOUT DRAWING – STG #1, 2 TRANSFORMER AREA | IFI | 2018-03-02 | 2018-06-01 |  |  |  |  | 2018-03-08 | 2018-06-15
EL(15) | Electrical | 152332 | T16182-YQ01-P0ZEN-152332 | LIGHTING & SMALL POWER LAYOUT DRAWING – FUEL GAS SYSTEM AREA | IFI | 2018-04-06 | 2018-07-06 |  |  |  |  | 2018-03-30 | 2018-05-18
EL(15) | Electrical | 152333 | T16182-YQ01-P0ZEN-152333 | LIGHTING & SMALL POWER LAYOUT DRAWING – WELDING SHED AND CONTAINER AT OPEN STORAGE AREA | IFI | 2020-01-10 | 2020-02-07 |  |  |  |  | 2020-01-03 | 2020-03-06
EL(15) | Electrical | 152401 | T16182-YB11-P0ZEN-152401 | LIGHTING PANEL BOARD SCHEDULE - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 | 2018-04-23 |  | O |  |  | 2017-04-10 | 2018-04-23
EL(15) | Electrical | 152402 | T16182-YB11-P0ZEN-152402 | LIGHTING PANEL BOARD SCHEDULE - GTG #1,2 LEB | IFI | 2017-09-03 | 2018-04-23 |  | O |  |  | 2017-04-17 | 2018-04-23
EL(15) | Electrical | 152403 | T16182-YB11-P0ZEN-152403 | LIGHTING PANEL BOARD SCHEDULE - GTG #3,4,5 LEB | IFI | 2017-12-23 | 2018-04-23 |  |  |  |  | 2017-05-29 | 2018-04-23
EL(15) | Electrical | 152404 | T16182-YB11-P0ZEN-152404 | LIGHTING PANEL BOARD SCHEDULE - ST #1 LEB | IFI | 2017-12-03 | 2018-04-23 |  |  |  |  | 2017-12-11 | 2018-04-23
EL(15) | Electrical | 152405 | T16182-YB11-P0ZEN-152405 | LIGHTING PANEL BOARD SCHEDULE - ST #2 LEB | IFI | 2018-01-05 | 2018-04-23 |  |  |  |  | 2018-01-08 | 2018-04-23
EL(15) | Electrical | 152406 | T16182-YB11-P0ZEN-152406 | LIGHTING PANEL BOARD SCHEDULE - ST BUILDING | IFI | 2018-05-19 | 2018-07-26 |  |  |  |  | 2018-05-17 | 2018-07-26
EL(15) | Electrical | 152407 | T16182-YB11-P0ZEN-152407 | LIGHTING PANEL BOARD SCHEDULE - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 | 2018-04-23 |  | O |  |  | 2017-05-29 | 2018-04-23
EL(15) | Electrical | 152408 | T16182-YB11-P0ZEN-152408 | LIGHTING PANEL BOARD SCHEDULE - ADMINISTRATION | IFI | 2018-07-02 | 2018-04-23 |  |  |  |  | 2018-03-05 | 2018-04-23
EL(15) | Electrical | 152409 | T16182-YB11-P0ZEN-152409 | LIGHTING PANEL BOARD SCHEDULE - SECURITY BUILDING | IFI | 2018-12-01 | 2019-03-12 |  |  |  |  | 2018-04-25 | 2019-03-12
EL(15) | Electrical | 152411 | T16182-YB11-P0ZEN-152411 | LIGHTING PANEL BOARD SCHEDULE - SUPPORT BUILDING | IFI | 2018-04-21 | 2019-03-12 |  |  |  |  | 2018-04-25 | 2019-03-12
EL(15) | Electrical | 152414 | T16182-YB11-P0ZEN-152414 | LIGHTING PANEL BOARD SCHEDULE - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03 | 2018-04-23 |  |  |  |  | 2018-01-08 | 2018-04-23
EL(15) | Electrical | 152415 | T16182-YB11-P0ZEN-152415 | LIGHTING PANEL BOARD SCHEDULE - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19 | 2018-06-30 |  |  |  |  | 2017-11-27 | 2018-05-11
EL(15) | Electrical | 152418 | T16182-YB11-P0ZEN-152418 | LIGHTING PANEL BOARD SCHEDULE - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-12-15 | 2018-04-23 |  |  |  |  | 2017-12-18 | 2018-04-23
EL(15) | Electrical | 152419 | T16182-YB11-P0ZEN-152419 | LIGHTING PANEL BOARD SCHEDULE - FIRE WATER PUMP HOUSE | IFI | 2017-09-03 | 2018-04-23 |  |  |  |  | 2017-09-11 | 2018-04-23
EL(15) | Electrical | 152421 | T16182-YB11-P0ZEN-152421 | LIGHTING PANEL BOARD SCHEDULE - WATER TREATMENT BUILDING | IFI | 2017-08-29 | 2018-04-23 |  | O |  |  | 2017-08-21 | 2018-04-23
EL(15) | Electrical | 152422 | T16182-YB11-P0ZEN-152422 | LIGHTING PANEL BOARD SCHEDULE - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23 | 2018-06-30 |  |  |  |  | 2018-03-27 | 2018-05-28
EL(15) | Electrical | 152427 | T16182-YB11-P0ZEN-152427 | LIGHTING PANEL BOARD SCHEDULE - YARD | IFI | 2018-03-14 | 2018-06-30 |  |  |  |  | 2018-03-30 | 2018-05-28
EL(15) | Electrical | 152428 | T16182-YB11-P0ZEN-152428 | LIGHTING PANEL BOARD SCHEDULE – TANK AREA | IFI | 2018-01-22 | 2018-07-26 |  |  |  |  | 2018-01-24 | 2018-07-26
EL(15) | Electrical | 152501 | T16182-YE04-P0BAU-152501 | TYPICAL INSTALLATION DRAWING - EARTHING AND LIGHTNING PROTECTION | IFR | 2017-01-31 | 2017-04-17 |  |  |  |  | 2017-01-25 | 2017-03-30
EL(15) | Electrical | 152502 | T16182-DE00-P0BAU-152502 | TECHNICAL SPECIFICATION - EARTHING AND LIGHTNING PROTECTION SYSTEM | IFR | 2017-02-15 | 2017-05-02 |  |  |  |  | 2017-01-19 | 2017-02-10
EL(15) | Electrical | 152503 | T16182-YT10-P0BAU-152503 | MAIN EARTHING GRID CALCULATION | IFR | 2017-01-26 | 2017-04-08 |  | O |  |  | 2017-01-11 | 2017-02-10
EL(15) | Electrical | 152504 | T16182-YE03-P0BAU-152504 | EARTHING LAYOUT DRAWING - MAIN GRID | IFR | 2017-01-26 | 2017-04-08 |  | O |  |  | 2017-01-11 | 2017-02-10
EL(15) | Electrical | 152505 | T16182-YE03-P0BAU-152505 | EARTHING LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFR | 2017-01-26 | 2017-04-08 |  | O |  |  | 2017-01-18 | 2017-02-23
EL(15) | Electrical | 152506 | T16182-YE03-P0BAU-152506 | EARTHING LAYOUT DRAWING - GTG #1,2 LEB | IFR | 2017-02-04 | 2017-04-30 |  | O |  |  | 2017-01-25 | 2017-02-23
EL(15) | Electrical | 152507 | T16182-YE03-P0BAU-152507 | EARTHING LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-03-15 | 2017-06-30 |  |  |  |  | 2017-03-10 | 2017-07-07
EL(15) | Electrical | 152508 | T16182-YE03-P6BAU-152508 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #1 LEB | IFI | 2017-04-26 | 2017-06-30 |  |  |  |  | 2017-04-21 | 2017-06-29
EL(15) | Electrical | 152509 | T16182-YE03-P7BAU-152509 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #2 LEB | IFI | 2017-04-26 | 2017-06-30 |  |  |  |  | 2017-04-21 | 2017-06-29
EL(15) | Electrical | 152510 | T16182-YE03-P0BAU-152510 | EARTHING LAYOUT DRAWING - ST BUILDING | IFI | 2017-05-16 | 2017-07-15 |  |  |  |  | 2017-04-20 | 2017-09-07
EL(15) | Electrical | 152511 | T16182-YE03-P0BAU-152511 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | IFI | 2017-06-06 | 2017-08-05 |  | O |  |  | 2017-04-28 | 2017-06-29
EL(15) | Electrical | 152512 | T16182-YE03-P0BAU-152512 | EARTHING LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | IFI | 2017-09-16 | 2017-11-15 |  |  |  |  | 2017-08-24 | 2017-08-25
EL(15) | Electrical | 152513 | T16182-YE03-P0BAU-152513 | EARTHING LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-07-01 | 2018-08-30 |  |  |  |  | 2018-02-13 | 2018-04-27
EL(15) | Electrical | 152514 | T16182-YE03-P0BAU-152514 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GATE HOUSE | IFI | 2018-02-06 | 2018-04-27 |  |  |  |  | 2018-02-07 | 2018-04-27
EL(15) | Electrical | 152515 | T16182-YE03-P0BAU-152515 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SUPPORT BUILDING | IFI | 2018-02-06 | 2018-02-02 |  |  |  |  | 2017-12-08 | 2018-02-02
EL(15) | Electrical | 152516 | T16182-YE03-P0BAU-152516 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SEARCH FACILITY AND VISITORS CENTRE | IFI | 2018-02-06 | 2018-04-27 |  |  |  |  | 2018-02-07 | 2018-04-27
EL(15) | Electrical | 152517 | T16182-YE03-P0BAU-152517 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE BRIGADE | IFI | 2017-09-13 | 2017-11-15 |  |  |  |  | 2017-08-25 | 2017-11-15
EL(15) | Electrical | 152518 | T16182-YE03-P0BAU-152518 | EARTHING LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2017-11-11 | 2018-01-10 |  |  |  |  | 2017-08-18 | 2017-08-24
EL(15) | Electrical | 152519 | T16182-YE03-P0BAU-152519 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - N2 STORAGE SHELTER | IFI | 2017-07-09 | 2017-09-07 |  |  |  |  | 2017-05-25 | 2017-07-07
EL(15) | Electrical | 152520 | T16182-YE03-P0BAU-152520 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COMPRESSOR SHELTER | IFI | 2017-07-01 | 2017-08-30 |  |  |  |  | 2017-06-16 | 2017-07-07
EL(15) | Electrical | 152521 | T16182-YE03-P0BAU-152521 | EARTHING LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-05-23 | 2017-07-22 |  |  |  |  | 2017-03-30 | 2017-07-07
EL(15) | Electrical | 152522 | T16182-YE03-P0BAU-152522 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | IFI | 2017-06-29 | 2017-08-28 |  |  |  |  | 2017-06-16 | 2017-07-07
EL(15) | Electrical | 152523 | T16182-YE03-P0BAU-152523 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-05-31 | 2017-07-30 |  |  |  |  | 2017-05-30 | 2017-07-11
EL(15) | Electrical | 152524 | T16182-YE03-P0BAU-152524 | EARTHING LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-02-25 | 2017-06-30 |  | O |  |  | 2017-02-27 | 2017-07-07
EL(15) | Electrical | 152525 | T16182-YE03-P0BAU-152525 | EARTHING LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2017-08-15 | 2017-09-29 |  |  |  |  | 2017-08-18 | 2017-09-29
EL(15) | Electrical | 152526 | T16182-YE03-P0BAU-152526 | EARTHING LAYOUT DRAWING - PIPE RACK FOR HRSG | IFI | 2017-11-02 | 2018-02-02 |  |  |  |  | 2017-11-02 | 2017-12-08
EL(15) | Electrical | 152527 | T16182-YE03-P0BAU-152527 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AUX. LEB | IFI | 2017-12-14 | 2018-03-14 |  |  |  |  | 2017-12-08 | 2018-02-02
EL(15) | Electrical | 152528 | T16182-YE03-P0BAU-152528 | EARTHING LAYOUT DRAWING - TANK AREA | IFI | 2017-06-30 | 2017-08-29 |  |  |  |  | 2017-06-30 | 2017-07-07
EL(15) | Electrical | 152529 | T16182-YE03-P0BAU-152529 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #1,2 AREA | IFI | 2017-08-01 | 2017-09-30 |  |  |  |  | 2017-07-20 | 2017-08-22
EL(15) | Electrical | 152530 | T16182-YE03-P0BAU-152530 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #3,4,5 AREA | IFI | 2017-09-01 | 2017-10-31 |  |  |  |  | 2017-08-25 | 2017-10-30
EL(15) | Electrical | 152531 | T16182-YE03-P0BAU-152531 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - STG TR AREA | IFI | 2018-01-20 | 2018-03-21 |  |  |  |  | 2017-08-25 | 2017-10-30
EL(15) | Electrical | 152532 | T16182-YE03-P0BAU-152532 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-1 | IFI | 2017-05-25 | 2017-07-24 |  |  |  |  | 2017-05-25 | 2017-07-07
EL(15) | Electrical | 152533 | T16182-YE03-P0BAU-152533 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-2 | IFI | 2017-07-25 | 2017-09-23 |  |  |  |  | 2017-07-21 | 2017-09-28
EL(15) | Electrical | 152534 | T16182-YE03-P0BAU-152534 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIN FAN COOLER & CCW PUMP AREA | IFI | 2017-07-25 | 2017-09-23 |  |  |  |  | 2017-07-21 | 2017-08-22
EL(15) | Electrical | 152535 | T16182-YE03-P0BAU-152535 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS AREA | IFI | 2017-08-15 | 2017-10-14 |  |  |  |  | 2017-08-14 | 2017-09-29
EL(15) | Electrical | 152536 | T16182-YE03-P0BAU-152536 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - BLACK START DIESEL GENERATOR AREA | IFI | 2017-09-14 | 2017-12-13 |  |  |  |  | 2017-08-25 | 2017-11-16
EL(15) | Electrical | 152537 | T16182-YE03-P0BAU-152537 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - H2, CO2 STORAGE SHELTER | IFI | 2017-11-14 | 2018-02-12 |  |  |  |  | 2017-08-24 | 2017-08-25
EL(15) | Electrical | 152538 | T16182-YE03-P0BAU-152538 | EARTHING LAYOUT DRAWING - 380kV EHV CABLE INSULATION JOINT AREA | IFI | 2017-11-14 | 2018-02-12 |  |  |  |  | 2017-08-24 | 2017-08-25
EL(15) | Electrical | 152539 | T16182-YE03-P0BAU-152539 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - CHEMICAL DOSING SYSTEM | IFI | 2017-12-14 | 2018-03-14 |  |  |  |  | 2017-09-29 | 2017-11-15
EL(15) | Electrical | 152540 | T16182-YE03-P0BAU-152540 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - PRELIMINARY INSPECTION CHECK POINT (PIC) | IFI | 2018-06-14 | 2018-09-14 |  |  |  |  | 2018-04-27 | 2018-07-06
EL(15) | Electrical | 152600 | T16182-YE01-P0BAU-152600 | LIGHTNING PROTECTION LAYOUT DRAWING - OVERALL AREA | IFI | 2017-12-15 | 2018-01-23 |  |  |  |  | 2017-12-15 | 2018-01-23
EL(15) | Electrical | 152601 | T16182-YE01-P0BAU-152601 | LIGHTNING PROTECTION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFI | 2017-11-30 | 2018-02-02 |  | O |  |  | 2017-11-15 | 2018-02-02
EL(15) | Electrical | 152602 | T16182-YE01-P0BAU-152602 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #1,2 LEB | IFI | 2017-06-29 | 2017-08-22 |  | O |  |  | 2017-06-29 | 2017-08-22
EL(15) | Electrical | 152603 | T16182-YE01-P0BAU-152603 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-09-18 | 2017-11-15 |  |  |  |  | 2017-09-18 | 2017-11-15
EL(15) | Electrical | 152606 | T16182-YE01-P0BAU-152606 | LIGHTNING PROTECTION LAYOUT DRAWING - ST BUILDING | IFI | 2018-04-14 | 2018-07-14 |  |  |  |  | 2018-02-13 | 2018-03-12
EL(15) | Electrical | 152608 | T16182-YE01-P0BAU-152608 | LIGHTNING PROTECTION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-16 | 2018-03-26 |  |  |  |  | 2017-12-08 | 2018-03-26
EL(15) | Electrical | 152609 | T16182-YE01-P0BAU-152609 | LIGHTNING PROTECTION LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-09-01 | 2018-07-24 |  |  |  |  | 2018-07-06 | 2018-07-25
EL(15) | Electrical | 152614 | T16182-YE01-P0BAU-152614 | LIGHTNING PROTECTION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2018-05-15 | 2018-03-26 |  |  |  |  | 2017-12-08 | 2018-03-26
EL(15) | Electrical | 152620 | T16182-YE01-P0BAU-152620 | LIGHTNING PROTECTION LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-07-29 | 2018-02-02 |  | O |  |  | 2017-07-21 | 2017-08-22
EL(15) | Electrical | 152621 | T16182-YE01-P0BAU-152621 | LIGHTNING PROTECTION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2017-09-28 | 2017-11-15 |  |  |  |  | 2017-09-29 | 2017-11-15
EL(15) | Electrical | 152701 | T16182-DE00-P0ZEN-152701 | TECHNICAL SPECIFICATION - PVC CONDUIT AND ACCESSORIES | IFI | 2017-02-03 | [5 empty] | 2017-02-01 | #VALUE!
EL(15) | Electrical | 152702 | T16182-DE00-P0ZEN-152702 | TECHNICAL SPECIFICATION - STEEL CONDUIT AND ACCESSORIES | IFI | 2017-05-31 | [5 empty] | 2017-07-21 | #VALUE!
EL(15) | Electrical | 152705 | T16182-YE00-P0ZEN-152705 | EMBEDDED CONDUIT LAYOUT FOR ST #1 LEB | IFI | 2017-04-28 | 2017-06-30 |  |  |  |  | 2017-05-02 | 2017-07-07
EL(15) | Electrical | 152706 | T16182-YE00-P0ZEN-152706 | EMBEDDED CONDUIT LAYOUT FOR ST #2 LEB | IFI | 2017-04-28 | 2017-06-30 |  |  |  |  | 2017-05-02 | 2017-07-07
EL(15) | Electrical | 152707 | T16182-YE00-P0ZEN-152707 | EMBEDDED CONDUIT LAYOUT FOR ST BUILDING | IFI | 2017-05-17 | 2017-07-16 |  |  |  |  | 2017-05-23 | 2017-08-30
EL(15) | Electrical | 152708 | T16182-YE00-P0ZEN-152708 | EMBEDDED CONDUIT LAYOUT FOR FGS ELECTRICAL BUILDING | IFI | 2017-05-22 | 2017-07-21 |  | O |  |  | 2017-04-28 | 2017-07-07
EL(15) | Electrical | 152709 | T16182-YE00-P0ZEN-152709 | EMBEDDED CONDUIT LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2017-09-01 | 2017-10-31 |  |  |  |  | 2017-09-04 | 2017-10-30
EL(15) | Electrical | 152710 | T16182-YE00-P0ZEN-152710 | EMBEDDED CONDUIT LAYOUT FOR SECURITY BUILDING | IFI | 2018-06-16 | 2018-07-10 |  |  |  |  | 2018-05-10 | 2018-07-10
EL(15) | Electrical | 152711 | T16182-YE00-P0ZEN-152711 | EMBEDDED CONDUIT LAYOUT FOR MAIN GATE HOUSE AREA | IFI | 2018-01-22 | 2018-05-15 |  |  |  |  | 2018-01-25 | 2018-05-15
EL(15) | Electrical | 152715 | T16182-YE00-P0ZEN-152715 | EMBEDDED CONDUIT LAYOUT FOR FIRE BRIGADE | IFI | 2017-08-29 | 2017-12-08 |  |  |  |  | 2017-09-04 | 2017-12-08
EL(15) | Electrical | 152716 | T16182-YE00-P0ZEN-152716 | EMBEDDED CONDUIT LAYOUT FOR WORKSHOP & STORAGE BUILDING | IFI | 2017-10-27 | 2017-12-26 |  |  |  |  | 2017-09-27 | 2017-11-23
EL(15) | Electrical | 152717 | T16182-YE00-P0ZEN-152717 | EMBEDDED CONDUIT LAYOUT FOR H2, CO2, N2 STORAGE SHELTER | IFI | 2017-06-24 | 2017-08-23 |  |  |  |  | 2017-06-29 | 2017-08-24
EL(15) | Electrical | 152718 | T16182-YE00-P0ZEN-152718 | EMBEDDED CONDUIT LAYOUT FOR AIR COMPRESSOR SHELTER | IFI | 2017-07-01 | 2017-08-30 |  |  |  |  | 2017-06-16 | 2017-09-13
EL(15) | Electrical | 152719 | T16182-YE00-P0ZEN-152719 | EMBEDDED CONDUIT LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-05-23 | 2017-07-22 |  |  |  |  | 2017-04-05 | 2017-07-07
EL(15) | Electrical | 152720 | T16182-YE00-P0ZEN-152720 | EMBEDDED CONDUIT LAYOUT FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER(CPP) | IFI | 2017-06-29 | 2017-08-28 |  |  |  |  | 2017-06-16 | 2017-07-21
EL(15) | Electrical | 152721 | T16182-YE00-P0ZEN-152721 | EMBEDDED CONDUIT LAYOUT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-05-31 | 2017-07-30 |  |  |  |  | 2017-06-02 | 2017-07-07
EL(15) | Electrical | 152722 | T16182-YE00-P0ZEN-152722 | EMBEDDED CONDUIT LAYOUT FOR WATER TREATMENT BUILDING | IFI | 2017-02-28 | 2017-06-30 |  | O |  |  | 2017-03-09 | 2017-07-07
EL(15) | Electrical | 152724 | T16182-YE00-P0ZEN-152724 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2017-10-18 | 2017-12-08 |  |  |  |  | 2017-10-24 | 2017-12-08
EL(15) | Electrical | 152725 | T16182-YE00-P0ZEN-152725 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2017-10-25 | 2017-12-08 |  |  |  |  | 2017-10-20 | 2017-12-08
EL(15) | Electrical | 152726 | T16182-YE00-P0ZEN-152726 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | IFI | 2017-05-23 | 2017-07-22 |  |  |  |  | 2017-04-05 | 2017-07-07
EL(15) | Electrical | 152727 | T16182-YE00-P0ZEN-152727 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | IFI | 2017-08-21 | 2017-10-20 |  |  |  |  | 2017-08-24 | 2017-09-25
EL(15) | Electrical | 152728 | T16182-YE00-P0ZEN-152728 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | IFI | 2017-08-21 | 2017-10-20 |  |  |  |  | 2017-08-24 | 2017-09-25
EL(15) | Electrical | 152729 | T16182-YE00-P0ZEN-152729 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | IFI | 2017-05-23 | 2017-07-22 |  |  |  |  | 2017-04-28 | 2017-08-24
EL(15) | Electrical | 152730 | T16182-YE00-P0ZEN-152730 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | IFI | 2017-08-21 | 2017-10-20 |  |  |  |  | 2017-08-24 | 2017-09-25
EL(15) | Electrical | 152731 | T16182-YE00-P0ZEN-152731 | EMBEDDED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | IFI | 2017-06-09 | 2017-08-08 |  |  |  |  | 2017-06-19 | 2017-07-21
EL(15) | Electrical | 152732 | T16182-YE00-P0ZEN-152732 | EMBEDDED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | IFI | 2017-06-09 | 2017-08-08 |  |  |  |  | 2017-06-19 | 2017-07-21
EL(15) | Electrical | 152733 | T16182-YE00-P0ZEN-152733 | EMBEDDED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | IFI | 2017-07-14 | 2017-09-12 |  |  |  |  | 2017-06-19 | 2017-07-21
EL(15) | Electrical | 152735 | T16182-YE00-P0ZEN-152735 | EMBEDDED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | IFI | 2017-07-07 | 2017-09-05 |  |  |  |  | 2017-07-12 | 2017-09-27
EL(15) | Electrical | 152736 | T16182-YE00-P0ZEN-152736 | EMBEDDED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | IFI | 2017-06-16 | 2017-08-15 |  |  |  |  | 2017-06-26 | 2017-08-24
EL(15) | Electrical | 152750 | T16182-YE00-P0ZEN-152750 | ELECTRICAL DUCT BANK LAYOUT DRAWING CENTRAL CONTROL BUILDING AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-26 | 2017-07-12
EL(15) | Electrical | 152751 | T16182-YE00-P0ZEN-152751 | ELECTRICAL DUCT BANK LAYOUT GTG #1 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152752 | T16182-YE00-P0ZEN-152752 | ELECTRICAL DUCT BANK LAYOUT GTG #2 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152753 | T16182-YE00-P0ZEN-152753 | ELECTRICAL DUCT BANK LAYOUT GTG #3,#4 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152754 | T16182-YE00-P0ZEN-152754 | ELECTRICAL DUCT BANK LAYOUT GTG #5 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152755 | T16182-YE00-P0ZEN-152755 | ELECTRICAL DUCT BANK LAYOUT HRSG #1 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152756 | T16182-YE00-P0ZEN-152756 | ELECTRICAL DUCT BANK LAYOUT HRSG #2 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152757 | T16182-YE00-P0ZEN-152757 | ELECTRICAL DUCT BANK LAYOUT HRSG #3,#4 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152758 | T16182-YE00-P0ZEN-152758 | ELECTRICAL DUCT BANK LAYOUT HRSG #5 AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152759 | T16182-YE00-P0ZEN-152759 | ELECTRICAL DUCT BANK LAYOUT AIR COMPRESSOR & ACC AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152760 | T16182-YE00-P0ZEN-152760 | ELECTRICAL DUCT BANK LAYOUT ST #1 LEB | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152761 | T16182-YE00-P0ZEN-152761 | ELECTRICAL DUCT BANK LAYOUT ST #2 LEB | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152762 | T16182-YE00-P0ZEN-152762 | ELECTRICAL DUCT BANK LAYOUT TANK AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152763 | T16182-YE00-P0ZEN-152763 | ELECTRICAL DUCT BANK LAYOUT WATER TREATMENT BUILDING AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152764 | T16182-YE00-P0ZEN-152764 | ELECTRICAL DUCT BANK LAYOUT CPP REGEN BUILDING AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152765 | T16182-YE00-P0ZEN-152765 | ELECTRICAL DUCT BANK LAYOUT FGS & RESERVE BOILER AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152766 | T16182-YE00-P0ZEN-152766 | ELECTRICAL DUCT BANK LAYOUT ADMINISTRATION & SOCIAL BUILDING AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152767 | T16182-YE00-P0ZEN-152767 | ELECTRICAL DUCT BANK LAYOUT SECURITY BUILDING AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152768 | T16182-YE00-P0ZEN-152768 | ELECTRICAL DUCT BANK LAYOUT MAIN GATE HOUSE AREA | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152769 | T16182-YE00-P0ZEN-152769 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 1 | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152770 | T16182-YE00-P0ZEN-152770 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 2 | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152771 | T16182-YE00-P0ZEN-152771 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 3 | IFI | 2017-01-26 | 2017-09-25 |  |  |  |  | 2017-01-20 | 2017-09-25
EL(15) | Electrical | 152791 | T16182-YE00-P0ZEN-152791 | RACEWAY DRAWING FOR HCIS – MAIN GATE HOUSE | IFI | 2018-06-30 | 2018-09-28 |  |  |  |  | 2018-06-20 | 2018-07-16
EL(15) | Electrical | 152792 | T16182-YE00-P0ZEN-152792 | RACEWAY DRAWING FOR HCIS – PLANT ACCESS GATE HOUSE | IFI | 2018-07-13 | 2018-10-12 |  |  |  |  | 2018-06-29 | 2018-07-27
EL(15) | Electrical | 152793 | T16182-YE00-P0ZEN-152793 | RACEWAY DRAWING FOR HCIS – SEARCH FACILITY & VISITOR CENTRE | IFI | 2018-06-30 | 2018-09-28 |  |  |  |  | 2018-06-20 | 2018-07-16
EL(15) | Electrical | 152794 | T16182-YE00-P0ZEN-152794 | RACEWAY DRAWING FOR HCIS – SUPPORT BUILDING | IFI | 2018-07-13 | 2018-10-12 |  |  |  |  | 2018-06-29 | 2018-07-27
EL(15) | Electrical | 152795 | T16182-YE00-P0ZEN-152795 | RACEWAY DRAWING FOR HCIS – PRELIMINARY INSPECTION CHECKPOINT | IFI | 2018-07-13 | 2018-10-12 |  |  |  |  | 2018-06-29 | 2018-07-27
EL(15) | Electrical | 152801 | T16182-YR02-P0ZEN-152801 | SIZING CALCULATION - MV/LV POWER CABLES | IFR | 2017-01-13 | 2017-05-30 |  | O |  |  | 2017-02-06 | 2017-08-18
EL(15) | Electrical | 152810 | T16182-YT10-P0ZEN-152810 | SIZING CALCULATION - 380KV EHV CABLE AND ACCESSOIRES | IFR | 2017-02-28 | 2017-05-16 |  | O |  |  | 2017-03-13 | 2017-05-18
EL(15) | Electrical | 152820 | T16182-DE00-P0ZEN-152820 | TECHNICAL SPECIFICATION - 380KV EHV CABLE AND ACCESSORIES | IFR | 2017-02-28 | 2017-05-16 | O | O |  |  | 2017-03-13 | 2017-05-24
EL(15) | Electrical | 152822 | T16182-YD00-P0ZEN-152822 | OUTLINE & SCHEMATIC DRAWING - 380KV EHV CABLE AND ACCESSOIRES | IFR | 2017-03-10 | 2017-05-26 |  |  |  |  | 2017-03-13 | 2017-05-18
EL(15) | Electrical | 152823 | T16182-DE00-P0ZEN-152823 | INSTALLATION DRAWING - 380KV EHV CABLE AND ACCESSOIRES | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-10-16 | 2017-12-21
EL(15) | Electrical | 152830 | T16182-DE00-P0ZEN-152830 | TECHNICAL SPECIFICATION - POWER & CONTROL & F/O CABLE | IFR | 2017-05-31 | 2017-08-09 |  |  |  |  | 2017-06-16 | 2017-07-25
EL(15) | Electrical | 152840 | T16182-DE00-P0ZEN-152840 | TECHNICAL SPECIFICATION - CABLING ACCESSORIES | IFR | 2017-05-31 | 2017-08-09 |  |  |  |  | 2017-07-14 | 2017-07-25
EL(15) | Electrical | 152850 | T16182-YL16-P0ZEN-152850 | POWER CABLE SCHEDULE | IFI | 2017-08-29 |  |  | O |  |  | 2017-09-07 | #VALUE!
EL(15) | Electrical | 152860 | T16182-YL16-P0ZEN-152860 | CONTROL CABLE SCHEDULE | IFI | 2017-08-29 |  |  | O |  |  | 2017-10-18 | #VALUE!
EL(15) | Electrical | 152870 | T16182-DE00-P0ZEN-152870 | TECHNICAL SPECIFICATION - FIRE STOP MATERIAL | IFR | 2017-07-31 | 2017-10-09 |  |  |  |  | 2017-10-25 | 2017-11-23
EL(15) | Electrical | 154001 | T16182-DE00-P0CY-154001 | TECHNICAL SPECIFICATION - COMMUNICATION SYSTEM | IFR | 2017-10-15 | 2018-02-25 |  |  |  |  | 2017-10-23 | 2018-02-26
EL(15) | Electrical | 154011 | T16182-YU02-P0CYA-154011 | CONFIGURATION DIAGRAM - OFFICE TELEPHONE & LAN SYSTEM | IFR | 2017-04-07 | 2017-08-11 |  |  |  |  | 2017-04-07 | 2017-06-05
EL(15) | Electrical | 154013 | T16182-YU02-P0CYM-154013 | CONFIGURATION DIAGRAM - PUBLIC ADDRESS SYSTEM (SIREN SYSTEM) | IFR | 2017-04-07 | 2017-08-11 |  |  |  |  | 2017-04-07 | 2017-06-05
EL(15) | Electrical | 154021 | T16182-YQ03-P0CY-154021 | TYPICAL INSTALLATION DRAWING - COMMUNICATION SYSTEM | IFR | 2017-04-07 | 2017-07-09 |  |  |  |  | 2017-04-07 | 2017-06-05
EL(15) | Electrical | 154031 | T16182-YQ08-P0CY-154031 | COMMUNICATION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 | 2017-10-14 |  | O |  |  | 2017-04-24 | 2017-07-06
EL(15) | Electrical | 154032 | T16182-YQ08-P0CY-154032 | COMMUNICATION LAYOUT DRAWING - GTG #1,2 LEB | IFI | 2017-09-03 | 2017-11-02 |  | O |  |  | 2017-04-24 | 2017-07-06
EL(15) | Electrical | 154033 | T16182-YQ08-P0CY-154033 | COMMUNICATION LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-12-23 | 2018-02-21 |  |  |  |  | 2017-04-24 | 2017-07-06
EL(15) | Electrical | 154034 | T16182-YQ08-P0CY-154034 | COMMUNICATION LAYOUT DRAWING - ST #1 LEB | IFI | 2017-12-03 | 2018-02-01 |  |  |  |  | 2017-06-26 | 2017-07-06
EL(15) | Electrical | 154035 | T16182-YQ08-P0CY-154035 | COMMUNICATION LAYOUT DRAWING - ST #2 LEB | IFI | 2018-01-05 | 2018-03-06 |  |  |  |  | 2017-06-26 | 2017-07-06
EL(15) | Electrical | 154036 | T16182-YQ08-P0CY-154036 | COMMUNICATION LAYOUT DRAWING - ST BUILDING | IFI | 2018-05-19 | 2018-07-18 |  |  |  |  | 2018-05-02 | 2018-05-25
EL(15) | Electrical | 154037 | T16182-YQ08-P0CY-154037 | COMMUNICATION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 | 2018-03-06 |  | O |  |  | 2017-06-26 | 2017-07-06
EL(15) | Electrical | 154038 | T16182-YQ08-P0CY-154038 | COMMUNICATION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-02 | 2018-08-31 |  |  |  |  | 2017-08-30 | 2017-09-28
EL(15) | Electrical | 154039 | T16182-YQ08-P0CY-154039 | COMMUNICATION LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-12-01 | 2018-06-29 |  |  |  |  | 2018-04-23 | 2018-06-29
EL(15) | Electrical | 154040 | T16182-YQ08-P0CY-154040 | COMMUNICATION LAYOUT DRAWING – MAIN GATE & PLANT ACCESS GATE HOUSE | IFI | 2018-04-21 | 2018-06-29 |  |  |  |  | 2018-04-23 | 2018-06-29
EL(15) | Electrical | 154041 | T16182-YQ08-P0CY-154041 | COMMUNICATION LAYOUT DRAWING - SUPPORT BUILDING | IFI | 2018-04-21 | 2018-06-29 |  |  |  |  | 2018-04-23 | 2018-06-29
EL(15) | Electrical | 154042 | T16182-YQ08-P0CY-154042 | COMMUNICATION LAYOUT DRAWING - X-RAY SEARCHING ROOM | IFI | 2018-04-21 | 2018-06-29 |  |  |  |  | 2018-04-23 | 2018-06-29
EL(15) | Electrical | 154044 | T16182-YQ08-P0CY-154044 | COMMUNICATION LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03 | 2018-07-13 |  |  |  |  | 2018-05-02 | 2018-07-16
EL(15) | Electrical | 154045 | T16182-YQ08-P0CY-154045 | COMMUNICATION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19 | 2018-05-18 |  |  |  |  | 2018-03-21 | 2018-04-23
EL(15) | Electrical | 154049 | T16182-YQ08-P0CY-154049 | COMMUNICATION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | IFI | 2017-09-03 | 2017-11-02 |  |  |  |  | 2017-08-31 | 2017-09-28
EL(15) | Electrical | 154051 | T16182-YQ08-P0CY-154051 | COMMUNICATION LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-08-29 | 2017-10-28 |  | O |  |  | 2017-06-26 | 2017-07-06
EL(15) | Electrical | 154052 | T16182-YQ08-P0CY-154052 | COMMUNICATION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23 | 2018-04-23 |  |  |  |  | 2018-03-26 | 2018-04-23
EL(15) | Electrical | 154053 | T16182-YQ08-P0CY-154053 | COMMUNICATION LAYOUT DRAWING – PIPE RACK | IFI | 2018-07-30 | 2018-10-30 |  |  |  |  | 2018-07-27 | 2018-11-19
EL(15) | Electrical | 155001 | T16182-YT01-P0ASS-155001 | RELAY SETTING CALCULATION OF 380kV SYNCHRONIZING SYSTEM | IFI | 2018-07-20 | [5 empty] | 2018-07-20 | #VALUE!
EL(15) | Electrical | 155011 | T16182-YT10-P0ASR-155011 | RELAY SETTING CALCULATION FOR GTG1 & GTG2 CABLE PROTECTION | IFR | 2018-07-25 | 2018-08-31 |  |  |  |  | 2018-07-25 | 2018-09-07
EL(15) | Electrical | 155012 | T16182-YT10-P0ASR-155012 | RELAY SETTING CALCULATION FOR GTG #3, 4, 5 CABLE PROTECTION | IFR | 2018-11-27 | [5 empty] | 2018-11-28 | 2018-12-14
EL(15) | Electrical | 155013 | T16182-YT10-P0ASR-155013 | RELAY SETTING CALCULATION FOR STG #1, 2 CABLE PROTECTION | IFR | 2019-03-11 | 2019-04-04 |  |  |  |  | 2019-03-11 | 2019-04-04
EL(15) | Electrical | 155014 | T16182-YT10-P0ASR-155014 | RELAY SETTING CALCULATION FOR 13.8kV CABLE PROTECTION – COGEN TO ESF | IFR | 2018-12-21 | 2019-01-25 |  |  |  |  | 2018-12-21 | 2019-01-30
I&C(16) | Instrumentation & Control | 161001 | T16182-XW01-P0ZEN-161001 | DESIGN CRITERIA FOR GENERAL I&C SYSTEM | IFR | 2016-10-28 | 2017-04-30 |  |  |  |  | 2016-11-03 | 2017-05-02
I&C(16) | Instrumentation & Control | 161011 | T16182-YR05-P0ZEN-161011 | MASTER CLOCK CONCEPT DIAGRAM | IFR | 2017-03-15 | 2017-07-28 |  | O |  |  | 2017-03-16 | 2017-08-17
I&C(16) | Instrumentation & Control | 161021 | T16182-YF00-P0CJD-161021 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM – SYMBOL & LEGEND | IFR | 2017-05-30 | 2017-09-27 |  | O |  |  | 2017-05-31 | 2017-11-27
I&C(16) | Instrumentation & Control | 161022 | T16182-YF00-P0CJD-161022 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR START - UP | IFR | 2017-05-30 | 2017-09-27 |  | O |  |  | 2017-05-31 | 2017-12-13
I&C(16) | Instrumentation & Control | 161025 | T16182-YF00-P0CJD-161025 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR SHUTDOWN | IFR | 2017-05-30 | 2017-09-27 |  | O |  |  | 2017-05-31 | 2017-12-13
I&C(16) | Instrumentation & Control | 161031 | T16182-YF02-P0ZEN-161031 | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | IFR | 2016-12-30 | 2017-05-15 | O |  |  |  | 2016-12-21 | 2017-05-24
I&C(16) | Instrumentation & Control | 161041 | T16182-YF00-P0CJA-161041 | PLANT MASTER CONTROL DIAGRAM | IFR | 2017-05-30 | 2017-09-27 | O | O |  |  | 2017-05-30 | 2017-11-30
I&C(16) | Instrumentation & Control | 161051 | T16182-YF01-P0BYA-161051 | PLANT PROTECTION & INTERLOCK DIAGRAM | IFR | 2017-05-15 | 2017-09-13 |  | O |  |  | 2017-05-17 | 2018-01-12
I&C(16) | Instrumentation & Control | 161101 | T16182-YL01-P0CBA-161101 | DCS I/O DATABASE | IFR | 2017-02-28 | 2017-07-28 |  | O |  |  | 2017-03-06 | 2017-08-21
B.I&C(16) | Instrumentation & Control | 161102 | T16182-YF02-P0CRV-161102 | DCS - LAN CONFIGURATION DIAGRAM | IFR | 2017-02-01 | 2017-04-02 |  | O |  | PKG-039-DCS | 2017-02-14 | 2017-09-18
B.I&C(16) | Instrumentation & Control | 161103 | T16182-CV03-P0CRN-161103 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HARDWARE | IFR | 2017-02-01 | 2017-05-17 |  | O |  | PKG-039-DCS | 2017-02-14 | 2017-06-29
B.I&C(16) | Instrumentation & Control | 161104 | T16182-CV03-P0CRN-161104 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR SOFTWARE | IFR | 2017-02-01 | 2017-05-17 |  | O |  | PKG-039-DCS | 2017-02-14 | 2017-06-29
B.I&C(16) | Instrumentation & Control | 161105 | T16182-CV03-P0CRN-161105 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HMI GRAPHIC | IFR | 2017-02-15 | 2017-05-31 |  | O |  | PKG-039-DCS | 2017-02-14 | 2017-07-05
I&C(16) | Instrumentation & Control | 161111 | T16182-YR04-P0CUQ-161111 | DCS POWER DISTRIBUTION CONCEPT DIAGRAM | IFR | 2017-02-01 | 2017-04-02 |  | O |  |  | 2017-02-01 | 2017-04-17
B.I&C(16) | Instrumentation & Control | 161112 | T16182-YD00-P0CUQ-161112 | DCS - POWER DISTRIBUTION DRAWING | IFR | 2017-02-01 | 2017-04-02 |  | O |  | PKG-039-DCS | 2017-02-14 | 2017-08-08
B.I&C(16) | Instrumentation & Control | 161113 | T16182-YD00-P0CRN-161113 | DCS - IO & MODULE ALLOCATION | IFI | 2017-04-21 | 2017-09-29 |  | O |  | PKG-039-DCS | 2017-05-11 | 2017-09-29
B.I&C(16) | Instrumentation & Control | 161114 | T16182-YB03-P0CRN-161114 | DCS - INTERNAL CABLE CONNECTION DIAGRAM | IFI | 2017-05-15 | 2017-10-12 |  | O |  | PKG-039-DCS | 2017-07-05 | 2017-10-12
B.I&C(16) | Instrumentation & Control | 161115 | T16182-YL16-P0CRN-161115 | DCS - CABLE LIST | IFI | 2017-04-30 | 2017-09-29 |  | O |  | PKG-039-DCS | 2017-07-05 | 2017-09-29
B.I&C(16) | Instrumentation & Control | 161116 | T16182-YD05-P0CRN-161116 | DCS - HMI GRAPHIC DISPLAY DIAGRAM | IFR | 2017-06-30 | 2017-09-22 |  | O |  | PKG-039-DCS | 2017-07-17 | 2018-03-15
I&C(16) | Instrumentation & Control | 161117 | T16182-YL01-P0CRN-161117 | 3RD PARTY DATA - LINK INTERFACE SIGNAL DATABASE | IFR | 2017-07-15 | 2017-11-12 |  | O |  |  | 2017-08-30 | 2018-01-12
I&C(16) | Instrumentation & Control | 161118 | T16182-YR04-P0CUQ-161118 | I&C GROUNDING CONCEPT DIAGRAM | IFR | 2017-02-15 | 2017-04-16 |  | O |  |  | 2017-02-16 | 2017-03-23
B.I&C(16) | Instrumentation & Control | 161119 | T16182-YD00-P0CUQ-161119 | DCS - GROUNDING DRAWING | IFR | 2017-02-01 | 2017-04-02 |  | O |  | PKG-039-DCS | 2017-02-14 | 2017-08-08
B.I&C(16) | Instrumentation & Control | 161121 | T16182-CV03-P0CWQ-161121 | DCS - PERFORMANCE MONITORING SYSTEM | IFR | 2017-04-07 | 2017-06-23 |  | O |  | PKG-039-DCS | 2017-06-15 | 2018-10-01
B.I&C(16) | Instrumentation & Control | 161122 | T16182-CV03-P0CWQ-161122 | DCS - PLANT INFORMATION HISTORIAN | IFR | 2017-04-15 | 2017-06-30 |  | O |  | PKG-039-DCS | 2017-07-14 | 2018-02-23
B.I&C(16) | Instrumentation & Control | 161123 | T16182-CV03-P0CWQ-161123 | DCS - FIELD INSTRUMENT MONITORING SYSTEM | IFR | 2017-03-15 | 2017-05-29 |  | O |  | PKG-039-DCS | 2017-04-12 | 2017-06-30
B.I&C(16) | Instrumentation & Control | 161132 | T16182-CV03-P0CWQ-161132 | DCS - TECHNICAL SPECIFICATION FOR TIME SYNCHRONIZATION | IFR | 2017-03-15 | 2017-06-28 |  | O |  | PKG-039-DCS | 2017-03-31 | 2017-07-05
B.I&C(16) | Instrumentation & Control | 161133 | T16182-CV03-P0CWQ-161133 | DCS - TECHNICAL SPECIFICATION FOR EMERGENCY PUSH BUTTON | IFR | 2017-05-08 | 2017-06-16 |  | O |  | PKG-039-DCS | 2017-05-11 | 2017-07-24
I&C(16) | Instrumentation & Control | 161134 | T16182-CV03-P0CWQ-161134 | TECHNICAL SPECIFICATION & DATA SHEET FOR SETTLEMENT SYSTEM | IFR | 2017-06-01 | 2017-10-15 | O |  |  |  | 2017-08-10 | 2018-01-08
B.I&C(16) | Instrumentation & Control | 161135 | T16182-CV03-P0CWQ-161135 | DCS - TECHNICAL SPECIFICATION FOR LARGE SCREEN DISPLAY | IFR | 2017-05-08 | 2017-06-16 |  | O |  | PKG-039-DCS | 2017-05-15 | 2017-06-26
B.I&C(16) | Instrumentation & Control | 161141 | T16182-YR05-P0CWQ-161141 | DCS - OUTLINE & DETAIL DRAWING FOR DCS SYSTEM CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS | 2017-03-29 | 2017-09-18
B.I&C(16) | Instrumentation & Control | 161142 | T16182-YR05-P0CWQ-161142 | DCS - OUTLINE & DETAIL DRAWING FOR LAN/SERVER CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS | 2017-03-29 | 2017-09-18
B.I&C(16) | Instrumentation & Control | 161143 | T16182-YR05-P0CWQ-161143 | DCS - OUTLINE & DETAIL DRAWING FOR MARSHALLING CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS | 2017-03-29 | 2017-09-18
B.I&C(16) | Instrumentation & Control | 161146 | T16182-YR05-P0CWQ-161146 | DCS - OUTLINE & DETAIL DRAWING FOR DCS CONSOLE & DESK | IFR | 2017-05-08 | 2017-07-21 |  | O |  | PKG-039-DCS | 2017-05-11 | 2017-06-26
B.I&C(16) | Instrumentation & Control | 161147 | T16182-YR05-P0CWQ-161147 | DCS - OUTLINE & DETAIL DRAWING FOR DCS POWER DISTRIBUTION CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS | 2017-03-29 | 2017-08-08
B.I&C(16) | Instrumentation & Control | 161148 | T16182-YR05-P0CWQ-161148 | DCS - OUTLINE & DETAIL DRAWING FOR DCS GROUNDING BOX | IFR | 2017-05-08 | 2017-07-21 |  | O |  | PKG-039-DCS | 2017-04-28 | 2017-09-18
B.I&C(16) | Instrumentation & Control | 161149 | T16182-CV03-P0CRT-161149 | DCS - TECHNICAL SPECIFICATION FOR FIELDBUS MOV | IFR | 2017-04-28 | 2017-07-28 |  | O |  | PKG-039-DCS | 2017-07-07 | 2018-02-21
B.I&C(16) | Instrumentation & Control | 161150 | T16182-YR01-P0CRU-161150 | INTEGRATED SAT(SITE ACCEPTANCE TEST) PROCEDURE FOR DCS | IFR | 2018-07-09 | 2018-08-13 |  |  |  | PKG-039-DCS | 2018-07-04 | 2019-01-15
I&C(16) | Instrumentation & Control | 161201 | T16182-YF00-P0CBA-161201 | CONTROL LOGIC DIAGRAM - SYMBOL & LEGEND | IFR | 2017-04-30 | 2017-08-13 |  | O |  |  | 2017-04-27 | 2017-08-18
I&C(16) | Instrumentation & Control | 161202 | T16182-YF00-P0CBA-161202 | CONTROL LOGIC DIAGRAM - TYPICAL FUNCTION | IFR | 2017-04-30 | 2017-08-13 |  | O |  |  | 2017-04-27 | 2017-08-30
I&C(16) | Instrumentation & Control | 161203 | T16182-YF00-P0CBA-161203 | CONTROL LOGIC DIAGRAM FOR HP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-04-27 | 2017-08-31
I&C(16) | Instrumentation & Control | 161204 | T16182-YF00-P0CBA-161204 | CONTROL LOGIC DIAGRAM FOR IP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-31
I&C(16) | Instrumentation & Control | 161205 | T16182-YF00-P0CBA-161205 | CONTROL LOGIC DIAGRAM FOR LP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-31
I&C(16) | Instrumentation & Control | 161206 | T16182-YF00-P0CBA-161206 | CONTROL LOGIC DIAGRAM FOR PROCESS STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O | O |  | 2017-05-19 | 2017-08-31
I&C(16) | Instrumentation & Control | 161207 | T16182-YF00-P0CBA-161207 | CONTROL LOGIC DIAGRAM FOR STEAM DRAIN SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-31
I&C(16) | Instrumentation & Control | 161208 | T16182-YF00-P0CBA-161208 | CONTROL LOGIC DIAGRAM FOR CONDENSATE SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-28
I&C(16) | Instrumentation & Control | 161209 | T16182-YF00-P0CBA-161209 | CONTROL LOGIC DIAGRAM FOR FEEDWATER SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-09-01
I&C(16) | Instrumentation & Control | 161210 | T16182-YF00-P0CBA-161210 | CONTROL LOGIC DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-09-11
I&C(16) | Instrumentation & Control | 161211 | T16182-YF00-P0CBA-161211 | CONTROL LOGIC DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-09-11
I&C(16) | Instrumentation & Control | 161212 | T16182-YF00-P0CBA-161212 | CONTROL LOGIC DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O |  | 2017-04-21 | 2017-08-31
I&C(16) | Instrumentation & Control | 161213 | T16182-YF00-P0CBA-161213 | CONTROL LOGIC DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O |  | 2017-04-21 | 2017-08-31
I&C(16) | Instrumentation & Control | 161214 | T16182-YF00-P0CBA-161214 | CONTROL LOGIC DIAGRAM FOR POTABLE WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-08-28
I&C(16) | Instrumentation & Control | 161216 | T16182-YF00-P0CBA-161216 | CONTROL LOGIC DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-08-28
I&C(16) | Instrumentation & Control | 161220 | T16182-YF00-P0CBA-161220 | CONTROL LOGIC DIAGRAM FOR ELECTRICAL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O |  |  | 2017-05-17 | 2017-08-30
I&C(16) | Instrumentation & Control | 161221 | T16182-YF00-P0CBA-161221 | CONTROL LOGIC DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O |  |  | 2017-05-19 | 2017-11-10
I&C(16) | Instrumentation & Control | 161222 | T16182-YF00-P0CBA-161222 | CONTROL LOGIC DIAGRAM FOR MISCELLANEOUS SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  |  |  | 2017-05-17 | 2017-08-28
I&C(16) | Instrumentation & Control | 161301 | T16182-YF00-P0CGA-161301 | CONTROL LOOP DIAGRAM - SYMBOL & LEGEND | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-27 | 2017-08-18
I&C(16) | Instrumentation & Control | 161302 | T16182-YF00-P0CGA-161302 | CONTROL LOOP DIAGRAM - TYPICAL FUNCTION | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-27 | 2017-08-18
I&C(16) | Instrumentation & Control | 161303 | T16182-YF00-P0CGA-161303 | CONTROL LOOP DIAGRAM FOR HP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-04-27 | 2017-08-31
I&C(16) | Instrumentation & Control | 161304 | T16182-YF00-P0CGA-161304 | CONTROL LOOP DIAGRAM FOR IP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-31
I&C(16) | Instrumentation & Control | 161305 | T16182-YF00-P0CGA-161305 | CONTROL LOOP DIAGRAM FOR LP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-31
I&C(16) | Instrumentation & Control | 161306 | T16182-YF00-P0CGA-161306 | CONTROL LOOP DIAGRAM FOR PROCESS STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O | O |  | 2017-05-19 | 2017-08-31
I&C(16) | Instrumentation & Control | 161307 | T16182-YF00-P0CGA-161307 | CONTROL LOOP DIAGRAM FOR STEAM DRAIN SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-31
I&C(16) | Instrumentation & Control | 161308 | T16182-YF00-P0CGA-161308 | CONTROL LOOP DIAGRAM FOR CONDENSATE SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-08-28
I&C(16) | Instrumentation & Control | 161309 | T16182-YF00-P0CGA-161309 | CONTROL LOOP DIAGRAM FOR FEEDWATER SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O |  | 2017-05-17 | 2017-09-01
I&C(16) | Instrumentation & Control | 161310 | T16182-YF00-P0CGA-161310 | CONTROL LOOP DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-08-30
I&C(16) | Instrumentation & Control | 161311 | T16182-YF00-P0CGA-161311 | CONTROL LOOP DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-08-30
I&C(16) | Instrumentation & Control | 161312 | T16182-YF00-P0CGA-161312 | CONTROL LOOP DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O |  | 2017-04-21 | 2017-08-31
I&C(16) | Instrumentation & Control | 161313 | T16182-YF00-P0CGA-161313 | CONTROL LOOP DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O |  | 2017-04-21 | 2017-08-31
I&C(16) | Instrumentation & Control | 161314 | T16182-YF00-P0CGA-161314 | CONTROL LOOP DIAGRAM FOR POTABLE WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-08-28
I&C(16) | Instrumentation & Control | 161316 | T16182-YF00-P0CGA-161316 | CONTROL LOOP DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O |  | 2017-04-21 | 2017-08-28
I&C(16) | Instrumentation & Control | 161320 | T16182-YF00-P0CGA-161320 | CONTROL LOOP DIAGRAM FOR ELECTRICAL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O |  |  | 2017-05-17 | 2017-09-11
I&C(16) | Instrumentation & Control | 161321 | T16182-YF00-P0CGA-161321 | CONTROL LOOP DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O |  |  | 2017-05-19 | 2017-11-10
I&C(16) | Instrumentation & Control | 161322 | T16182-YF00-P0CGA-161322 | CONTROL LOOP DIAGRAM FOR MISCELLANEOUS SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  |  |  | 2017-05-17 | 2017-08-28
I&C(16) | Instrumentation & Control | 161401 | T16182-YD00-P0CWQ-161401 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL CONTROL ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O |  |  | 2017-01-05 | 2017-05-10
I&C(16) | Instrumentation & Control | 161402 | T16182-YD00-P0CWQ-161402 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL ELECTRONIC ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O |  |  | 2017-01-05 | 2017-04-29
I&C(16) | Instrumentation & Control | 161403 | T16182-YD00-P0CWQ-161403 | I&C EQUIPMENT LAYOUT DRAWING FOR COMPUTER ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O |  |  | 2017-01-05 | 2017-04-29
I&C(16) | Instrumentation & Control | 161404 | T16182-YD00-P0CWQ-161404 | I&C EQUIPMENT LAYOUT DRAWING FOR IT & COMMUNICATION ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O |  |  | 2017-01-05 | 2017-04-29
I&C(16) | Instrumentation & Control | 161405 | T16182-YD00-P0CWQ-161405 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #1,2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O |  |  | 2017-01-05 | 2017-04-29
I&C(16) | Instrumentation & Control | 161406 | T16182-YD00-P0CWQ-161406 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #3,4,5 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O |  |  | 2017-01-18 | 2017-04-29
I&C(16) | Instrumentation & Control | 161407 | T16182-YD00-P0CWQ-161407 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #1 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-04-01 | 2017-07-15 |  |  |  |  | 2017-04-05 | 2017-07-11
I&C(16) | Instrumentation & Control | 161408 | T16182-YD00-P0CWQ-161408 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-05-01 | 2017-08-14 |  |  |  |  | 2017-04-05 | 2017-07-11
I&C(16) | Instrumentation & Control | 161409 | T16182-YD00-P0CWQ-161409 | I&C EQUIPMENT LAYOUT DRAWING FOR FGS ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM | IFR | 2017-03-10 | 2017-06-23 |  | O |  |  | 2017-03-09 | 2017-07-11
I&C(16) | Instrumentation & Control | 163101 | T16182-YL00-P0ZEN-163101 | FIELD INSTRUMENT LIST FOR BOP | IFR | 2017-02-01 | 2017-09-15 |  | O |  |  | 2017-02-02 | 2018-01-08
I&C(16) | Instrumentation & Control | 163102 | T16182-CV03-P0ZEN-163102 | TECHNICAL SPECIFICATION & DATA SHEET FOR LOCAL INSTRUMENT - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O |  |  | 2017-05-31 | 2018-01-08
I&C(16) | Instrumentation & Control | 163103 | T16182-CV03-P0ZEN-163103 | TECHNICAL SPECIFICATION & DATA SHEET FOR PROCESS TRANSMITTER - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O |  |  | 2017-05-31 | 2018-01-08
I&C(16) | Instrumentation & Control | 163104 | T16182-CV03-P0ZEN-163104 | TECHNICAL SPECIFICATION & DATA SHEET FOR FLOW ELEMENT - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O |  |  | 2017-05-31 | 2018-01-08
I&C(16) | Instrumentation & Control | 163201 | T16182-CV03-P0ZEN-163201 | TECHNICAL SPECIFICATION & DATA SHEET FOR CONTROL VALVE - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O |  |  | 2017-06-14 | 2018-02-07
I&C(16) | Instrumentation & Control | 163202 | T16182-CV03-P0EKU-163202 | TECHNICAL SPECIFICATION & DATA SHEET FOR GAS METERING SYSTEM | IFR | 2017-04-07 | 2017-11-15 |  | O |  |  | 2017-04-07 | 2017-12-22
I&C(16) | Instrumentation & Control | 163203 | T16182-CV03-P0UCL-163203 | TECHNICAL SPECIFICATION & DATA SHEET FOR STEAM/WATER METERING SYSTEM | IFR | 2017-06-14 | 2017-12-15 |  | O |  |  | 2017-06-15 | 2017-12-22
I&C(16) | Instrumentation & Control | 163204 | T16182-CV03-P0ZEN-163204 | TECHNICAL SPECIFICATION & DATA SHEET FOR WEATHER STATION | IFR | 2017-07-14 | 2018-01-14 |  | O |  |  | 2017-07-19 | 2017-12-22
I&C(16) | Instrumentation & Control | 163301 | T16182-YS00-P0ZEN-163301 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM - INDEX | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-06-15
I&C(16) | Instrumentation & Control | 163302 | T16182-YS00-P0ZEN-163302 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR INCOMER | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-06-27
I&C(16) | Instrumentation & Control | 163303 | T16182-YS00-P0ZEN-163303 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR MOTOR FEEDER | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-05-23
I&C(16) | Instrumentation & Control | 163304 | T16182-YS00-P0ZEN-163304 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR TR FEEDER | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-06-27
I&C(16) | Instrumentation & Control | 163305 | T16182-YS00-P0ZEN-163305 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR BUS TIE | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-05-24
I&C(16) | Instrumentation & Control | 163306 | T16182-YS00-P0ZEN-163306 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR UNIT/COMMON TIE | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-05-23
I&C(16) | Instrumentation & Control | 163307 | T16182-YS00-P0ZEN-163307 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PT PANEL | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163308 | T16182-YS00-P0ZEN-163308 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR INCOMER | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-06-27
I&C(16) | Instrumentation & Control | 163309 | T16182-YS00-P0ZEN-163309 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (ACB) | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-06-27
I&C(16) | Instrumentation & Control | 163310 | T16182-YS00-P0ZEN-163310 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (MCCB) | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-14
I&C(16) | Instrumentation & Control | 163311 | T16182-YS00-P0ZEN-163311 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (ACB) | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163312 | T16182-YS00-P0ZEN-163312 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (MCCB EHS) | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163313 | T16182-YS00-P0ZEN-163313 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR BUS TIE | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-05-23
I&C(16) | Instrumentation & Control | 163314 | T16182-YS00-P0ZEN-163314 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG INPUT | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163315 | T16182-YS00-P0ZEN-163315 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG OUTPUT | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163316 | T16182-YS00-P0ZEN-163316 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY INPUT | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-03-20
I&C(16) | Instrumentation & Control | 163317 | T16182-YS00-P0ZEN-163317 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY OUTPUT | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-05-24
I&C(16) | Instrumentation & Control | 163318 | T16182-YS00-P0ZEN-163318 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC CONTROL VALVE - MODULATING | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163319 | T16182-YS00-P0ZEN-163319 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC SHUT - OFF VALVE (SOLENOID VALVE) | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163320 | T16182-YS00-P0ZEN-163320 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - INTERNAL MCC | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163321 | T16182-YS00-P0ZEN-163321 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - FIELDBUS | IFR | 2017-02-01 | 2017-05-15 |  |  |  |  | 2017-02-09 | 2017-04-29
I&C(16) | Instrumentation & Control | 163331 | T16182-CV03-P0ZEN-163331 | TECHNICAL SPECIFICATION & DATA SHEET FOR VIBRATION MONITORING SYSTEM | IFR | 2017-08-01 | 2017-11-14 |  |  |  |  | 2017-07-19 | 2017-11-21
I&C(16) | Instrumentation & Control | 163401 | T16182-YF02-P0SAY-163401 | CONTROL SYSTEM CONFIGURATION DIAGRAM FOR HVAC | IFR | 2017-03-10 | 2017-06-23 |  | O |  | PKG-041-HVAC | 2017-03-13 | 2017-04-24
I&C(16) | Instrumentation & Control | 163402 | T16182-YL01-P0SAY-163402 | I/O LIST FOR HVAC | IFI | 2017-06-15 |  |  | O |  | PKG-041-HVAC | 2017-06-19 | #VALUE!
I&C(16) | Instrumentation & Control | 163403 | T16182-CV03-P0SAY-163403 | TECHNICAL SPECIFICATION & DATA SHEET FOR FIELD INSTRUMENT - HVAC | IFI | 2017-07-01 |  |  | O |  | PKG-041-HVAC | 2017-06-30 | #VALUE!
I&C(16) | Instrumentation & Control | 163404 | T16182-YK00-P0SAY-163404 | INSTRUMENT INSTALLATION DETAIL DRAWING FOR HVAC | IFI | 2017-08-15 | 2017-11-13 |  | O |  | PKG-041-HVAC | 2017-08-17 | 2017-11-01
I&C(16) | Instrumentation & Control | 163405 | T16182-YF00-P0SAY-163405 | CONTROL LOGIC & LOOP DIAGRAM FOR HVAC | IFI | 2017-08-30 |  |  | O |  | PKG-041-HVAC | 2017-09-06 | #VALUE!
I&C(16) | Instrumentation & Control | 163406 | T16182-YL16-P0SAY-163406 | I&C CABLE SCHEDULE FOR HVAC | IFI | 2017-11-01 | 2018-01-30 |  | O |  | PKG-041-HVAC | 2017-11-09 | 2018-02-23
I&C(16) | Instrumentation & Control | 163407 | T16182-YB03-P0SAY-163407 | I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HVAC | IFI | 2017-11-01 | 2018-01-30 |  | O |  | PKG-041-HVAC | 2017-11-09 | 2018-03-07
I&C(16) | Instrumentation & Control | 163408 | T16182-YD02-P0SAC-163408 | HVAC I&C CABLE RACEWAY DRAWING FOR CCB | IFI | 2017-11-15 | 2018-06-28 |  | O |  | PKG-041-HVAC | 2017-09-22 | 2017-11-06
I&C(16) | Instrumentation & Control | 163409 | T16182-YD02-P0SAC-163409 | HVAC I&C CABLE RACEWAY DRAWING FOR STEAM TURBINE BUILDING | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-11-21 | 2018-05-02
I&C(16) | Instrumentation & Control | 163411 | T16182-YD02-P0SAC-163411 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #1 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-11-21 | 2018-02-19
I&C(16) | Instrumentation & Control | 163412 | T16182-YD02-P0SAC-163412 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #2 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-11-21 | 2018-02-19
I&C(16) | Instrumentation & Control | 163413 | T16182-YD02-P0SAC-163413 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #1,2 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-11-21 | 2018-01-25
I&C(16) | Instrumentation & Control | 163414 | T16182-YD02-P0SAC-163414 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #3, 4, 5 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-11-21 | 2018-01-25
I&C(16) | Instrumentation & Control | 163415 | T16182-YD02-P0SAC-163415 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING | IFI | 2018-06-15 | 2018-08-14 |  | O |  | PKG-041-HVAC | 2018-06-15 | 2018-08-24
I&C(16) | Instrumentation & Control | 163416 | T16182-YD02-P0SAC-163416 | HVAC I&C CABLE RACEWAY DRAWING FOR SECURITY BUILDING | IFI | 2018-06-15 | 2018-08-14 |  | O |  | PKG-041-HVAC | 2018-06-22 | 2018-08-24
I&C(16) | Instrumentation & Control | 163417 | T16182-YD02-P0SAC-163417 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE BRIGADE & AUX LEB | IFI | 2018-02-15 | 2018-04-16 |  | O |  | PKG-041-HVAC | 2018-03-07 | 2018-04-26
I&C(16) | Instrumentation & Control | 163418 | T16182-YD02-P0SAC-163418 | HVAC I&C CABLE RACEWAY DRAWING FOR MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE | IFI | 2018-02-15 | 2018-04-16 |  | O |  | PKG-041-HVAC | 2018-03-21 | 2018-04-26
I&C(16) | Instrumentation & Control | 163419 | T16182-YD02-P0SAC-163419 | HVAC I&C CABLE RACEWAY DRAWING FOR FGS ELECTRICAL BUILDING | IFI | 2017-12-15 | 2018-02-13 |  | O |  | PKG-041-HVAC | 2017-12-11 | 2018-02-20
I&C(16) | Instrumentation & Control | 163420 | T16182-YD02-P0SAC-163420 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE WATER PUMP HOUSE | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-11-21 | 2018-01-25
I&C(16) | Instrumentation & Control | 163421 | T16182-YD02-P0SAC-163421 | HVAC I&C CABLE RACEWAY DRAWING FOR WATER TREATMENT BUILDING /W MAIN LABORATORY | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-09-22 | 2018-04-26
I&C(16) | Instrumentation & Control | 163422 | T16182-YD02-P0SAC-163422 | HVAC I&C CABLE RACEWAY DRAWING FOR CPP BUILDING | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC | 2017-11-21 | 2018-01-25
I&C(16) | Instrumentation & Control | 163423 | T16182-YR05-P0SAY-163423 | CONTROL PANEL OUTLINE & DETAIL DRAWING FOR HVAC | IFI | 2017-07-15 |  |  | O |  | PKG-041-HVAC | 2017-07-20 | #VALUE!
I&C(16) | Instrumentation & Control | 163424 | T16182-YD05-P0SAY-163424 | HMI GRAPHIC DISPLAY DIAGRAM FOR HVAC | IFI | 2017-09-15 |  |  | O |  | PKG-041-HVAC | 2017-09-25 | #VALUE!
I&C(16) | Instrumentation & Control | 163425 | T16182-YR05-P0SAY-163425 | TECHNICAL SPECIFICATION - HVAC CONTROL SYSTEM | IFI | 2017-09-30 |  |  |  |  | PKG-041-HVAC | 2017-09-25 | #VALUE!
I&C(16) | Instrumentation & Control | 163426 | T16182-YD02-P0SAC-163426 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN GATE HOUSE AREA | IFI | 2018-09-30 | 2018-11-30 |  |  |  | PKG-041-HVAC | 2018-09-03 | 2019-02-12
I&C(16) | Instrumentation & Control | 165001 | T16182-XW01-P0ZEN-165001 | DESIGN CRITERIA FOR I&C CABLE | IFR | 2016-11-30 | 2017-03-15 |  |  |  |  | 2016-12-21 | 2017-04-14
I&C(16) | Instrumentation & Control | 165011 | T16182-YL02-P0ZEN-165011 | I&C CABLE PRINCIPLE DIAGRAM | IFR | 2016-11-30 | 2017-03-15 |  |  |  |  | 2016-12-21 | 2017-04-29
I&C(16) | Instrumentation & Control | 165301 | T16182-YK00-P0ZEN-165301 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONTROL VALVE | IFR | 2017-04-01 | 2017-07-15 |  | O |  |  | 2017-03-23 | 2017-04-29
I&C(16) | Instrumentation & Control | 165302 | T16182-YK00-P0ZEN-165302 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - MOV | IFR | 2017-04-01 | 2017-07-15 |  | O |  |  | 2017-03-23 | 2017-04-29
I&C(16) | Instrumentation & Control | 165303 | T16182-YK00-P0ZEN-165303 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - INSTRUMENT RACK AND JUNCTION BOX | IFR | 2017-04-01 | 2017-07-15 |  | O |  |  | 2017-03-23 | 2017-05-24
I&C(16) | Instrumentation & Control | 165304 | T16182-YK00-P0ZEN-165304 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - FIELD INSTRUMENT | IFR | 2017-04-01 | 2017-07-15 |  | O |  |  | 2017-03-23 | 2017-04-29
I&C(16) | Instrumentation & Control | 165305 | T16182-YK00-P0ZEN-165305 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONDUIT SUPPORT | IFR | 2017-04-01 | 2017-07-15 |  | O |  |  | 2017-03-23 | 2017-04-29
I&C(16) | Instrumentation & Control | 165311 | T16182-YK00-P0ZEN-165311 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - GENERAL NOTE | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-07-18
I&C(16) | Instrumentation & Control | 165312 | T16182-YK00-P0ZEN-165312 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - SYMBOL & LEGEND | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-07-18
I&C(16) | Instrumentation & Control | 165313 | T16182-YK00-P0ZEN-165313 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - MATERIAL LISTS | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-07-18
I&C(16) | Instrumentation & Control | 165314 | T16182-YK00-P0ZEN-165314 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR FLOW TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165315 | T16182-YK00-P0ZEN-165315 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR LEVEL TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165316 | T16182-YK00-P0ZEN-165316 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165317 | T16182-YK00-P0ZEN-165317 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR DIFF. PRESSURE TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165318 | T16182-YK00-P0ZEN-165318 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE GAUGE | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165319 | T16182-YK00-P0ZEN-165319 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE TRANSMITTER (RTD/TC) | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165320 | T16182-YK00-P0ZEN-165320 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE GAUGE | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165321 | T16182-YK00-P0ZEN-165321 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEST WELL | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165322 | T16182-YK00-P0ZEN-165322 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PNEUMATIC CONTROL VALVES | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165323 | T16182-YK00-P0ZEN-165323 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR STANCHION & RACK | IFI | 2017-02-01 | 2017-07-01 |  | O |  |  | 2017-02-08 | 2017-08-17
I&C(16) | Instrumentation & Control | 165501 | T16182-YD02-P0ZEN-165501 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-14 | 2017-12-13 |  | O |  |  | 2017-07-11 | 2017-12-08
I&C(16) | Instrumentation & Control | 165502 | T16182-YD02-P0ZEN-165502 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #1,2 LEB | IFI | 2017-10-17 | 2018-01-15 |  | O |  |  | 2017-09-15 | 2017-12-08
I&C(16) | Instrumentation & Control | 165503 | T16182-YD02-P0ZEN-165503 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #3,4,5 LEB | IFI | 2018-01-22 | 2018-04-22 |  | O |  |  | 2017-12-08 | 2018-02-12
I&C(16) | Instrumentation & Control | 165504 | T16182-YD02-P0ZEN-165504 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #1 LEB | IFI | 2018-05-09 | 2018-08-07 |  | O |  |  | 2018-02-12 | 2018-03-29
I&C(16) | Instrumentation & Control | 165505 | T16182-YD02-P0ZEN-165505 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #2 LEB | IFI | 2018-06-07 | 2018-09-05 |  | O |  |  | 2018-02-12 | 2018-03-29
I&C(16) | Instrumentation & Control | 165506 | T16182-YD02-P0ZEN-165506 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST BUILDING | IFI | 2018-05-09 | 2018-08-07 |  | O |  |  | 2018-03-26 | 2018-07-16
I&C(16) | Instrumentation & Control | 165507 | T16182-YD02-P0ZEN-165507 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FGS ELECTRICAL BUILDING | IFI | 2018-02-04 | 2018-05-05 |  | O |  |  | 2017-12-08 | 2018-02-12
I&C(16) | Instrumentation & Control | 165508 | T16182-YD02-P0ZEN-165508 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-08-01 | 2018-10-30 |  | O |  |  | 2018-02-12 | 2018-03-26
I&C(16) | Instrumentation & Control | 165509 | T16182-YD02-P0ZEN-165509 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR SECURITY BUILDING | IFI | 2019-01-06 | 2019-04-06 |  | O |  |  | 2018-03-26 | 2018-07-03
I&C(16) | Instrumentation & Control | 165510 | T16182-YD02-P0ZEN-165510 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR MAIN GATE HOUSE AREA | IFI | 2018-05-21 | 2018-08-19 |  | O |  |  | 2018-05-30 | 2019-01-09
I&C(16) | Instrumentation & Control | 165514 | T16182-YD02-P0ZEN-165514 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE BRIGADE | IFI | 2018-09-13 | 2018-12-12 |  | O |  |  | 2018-02-12 | 2018-03-26
I&C(16) | Instrumentation & Control | 165515 | T16182-YD02-P0ZEN-165515 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-04-18 | 2018-07-17 |  | O |  |  | 2018-02-21 | 2018-03-26
I&C(16) | Instrumentation & Control | 165516 | T16182-YD02-P0ZEN-165516 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR H2, CO2, N2 STORAGE SHELTER | IFI | 2017-09-24 | 2017-12-23 |  | O |  |  | 2017-09-27 | 2018-02-12
I&C(16) | Instrumentation & Control | 165517 | T16182-YD02-P0ZEN-165517 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COMPRESSOR SHELTER | IFI | 2018-02-04 | 2018-05-05 |  | O |  |  | 2017-12-08 | 2018-02-27
I&C(16) | Instrumentation & Control | 165518 | T16182-YD02-P0ZEN-165518 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2018-01-29 | 2018-04-29 |  | O |  |  | 2018-01-31 | 2018-05-24
I&C(16) | Instrumentation & Control | 165519 | T16182-YD02-P0ZEN-165519 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER (CPP) | IFI | 2017-09-07 | 2017-12-06 |  | O |  |  | 2017-09-12 | 2017-11-29
I&C(16) | Instrumentation & Control | 165520 | T16182-YD02-P0ZEN-165520 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-12-26 | 2018-03-26 |  | O |  |  | 2017-12-08 | 2018-02-27
I&C(16) | Instrumentation & Control | 165521 | T16182-YD02-P0ZEN-165521 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WATER TREATMENT BUILDING | IFI | 2017-09-28 | 2017-12-27 |  | O |  |  | 2017-09-29 | 2017-11-27
I&C(16) | Instrumentation & Control | 165522 | T16182-YD02-P0ZEN-165522 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CPP & CPP REGENERATION BUILDING | IFI | 2018-04-02 | 2018-07-01 |  | O |  |  | 2018-02-12 | 2018-03-26
I&C(16) | Instrumentation & Control | 165523 | T16182-YD02-P0ZEN-165523 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-06-04 | 2018-09-02 |  | O |  |  | 2018-02-27 | 2018-07-16
I&C(16) | Instrumentation & Control | 165524 | T16182-YD02-P0ZEN-165524 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-02-19 | 2018-05-20 |  | O |  |  | 2018-02-23 | 2018-07-09
I&C(16) | Instrumentation & Control | 165525 | T16182-YD02-P0ZEN-165525 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | IFI | 2017-11-05 | 2018-02-03 |  |  |  |  | 2017-11-10 | 2018-02-23
I&C(16) | Instrumentation & Control | 165526 | T16182-YD02-P0ZEN-165526 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | IFI | 2017-12-05 | 2018-03-05 |  |  |  |  | 2017-12-08 | 2018-02-27
I&C(16) | Instrumentation & Control | 165527 | T16182-YD02-P0ZEN-165527 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | IFI | 2018-01-02 | 2018-04-02 |  |  |  |  | 2017-12-08 | 2018-03-26
I&C(16) | Instrumentation & Control | 165528 | T16182-YD02-P0ZEN-165528 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | IFI | 2018-02-16 | 2018-05-17 |  |  |  |  | 2017-12-08 | 2018-03-26
I&C(16) | Instrumentation & Control | 165529 | T16182-YD02-P0ZEN-165529 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | IFI | 2018-04-10 | 2018-07-09 |  |  |  |  | 2017-12-08 | 2018-03-26
I&C(16) | Instrumentation & Control | 165531 | T16182-YB03-P0ZEN-165531 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM - GENERAL INFORMATION | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-19 | 2017-11-07
I&C(16) | Instrumentation & Control | 165532 | T16182-YB03-P0ZEN-165532 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HP STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165533 | T16182-YB03-P0ZEN-165533 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR IP STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165534 | T16182-YB03-P0ZEN-165534 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR LP STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165535 | T16182-YB03-P0ZEN-165535 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR PROCESS STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165536 | T16182-YB03-P0ZEN-165536 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR STEAM DRAIN SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165537 | T16182-YB03-P0ZEN-165537 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CONDENSATE SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165538 | T16182-YB03-P0ZEN-165538 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FEEDWATER SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-19
I&C(16) | Instrumentation & Control | 165539 | T16182-YB03-P0ZEN-165539 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165540 | T16182-YB03-P0ZEN-165540 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165541 | T16182-YB03-P0ZEN-165541 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165542 | T16182-YB03-P0ZEN-165542 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165543 | T16182-YB03-P0ZEN-165543 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165544 | T16182-YB03-P0ZEN-165544 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  |  |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165545 | T16182-YB03-P0ZEN-165545 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR COMPRESSED AIR SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-19 | 2017-12-15
I&C(16) | Instrumentation & Control | 165546 | T16182-YB03-P0ZEN-165546 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FUEL GAS SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-19 | 2017-12-19
I&C(16) | Instrumentation & Control | 165547 | T16182-YB03-P0ZEN-165547 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR ELECTRICAL SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O |  |  | 2017-09-27 | 2017-12-19
I&C(16) | Instrumentation & Control | 165548 | T16182-YB03-P0ZEN-165548 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFI | 2017-12-15 | 2018-03-15 |  | O |  |  | 2018-01-09 | 2018-03-29
I&C(16) | Instrumentation & Control | 165551 | T16182-YL16-P0ZEN-165551 | BOP - I&C CABLE SCHEDULE - GENERAL INFORMATION | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2017-11-07
I&C(16) | Instrumentation & Control | 165552 | T16182-YL16-P0ZEN-165552 | BOP - I&C CABLE SCHEDULE FOR HP STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165553 | T16182-YL16-P0ZEN-165553 | BOP - I&C CABLE SCHEDULE FOR IP STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165554 | T16182-YL16-P0ZEN-165554 | BOP - I&C CABLE SCHEDULE FOR LP STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165555 | T16182-YL16-P0ZEN-165555 | BOP - I&C CABLE SCHEDULE FOR PROCESS STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165556 | T16182-YL16-P0ZEN-165556 | BOP - I&C CABLE SCHEDULE FOR STEAM DRAIN SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165557 | T16182-YL16-P0ZEN-165557 | BOP - I&C CABLE SCHEDULE FOR CONDENSATE SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165558 | T16182-YL16-P0ZEN-165558 | BOP - I&C CABLE SCHEDULE FOR FEEDWATER SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165559 | T16182-YL16-P0ZEN-165559 | BOP - I&C CABLE SCHEDULE FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165560 | T16182-YL16-P0ZEN-165560 | BOP - I&C CABLE SCHEDULE FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165561 | T16182-YL16-P0ZEN-165561 | BOP - I&C CABLE SCHEDULE FOR GT ROTOR COOLING AIR SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165562 | T16182-YL16-P0ZEN-165562 | BOP - I&C CABLE SCHEDULE FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165563 | T16182-YL16-P0ZEN-165563 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165564 | T16182-YL16-P0ZEN-165564 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER DISTRIBUTION SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  |  |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165565 | T16182-YL16-P0ZEN-165565 | BOP - I&C CABLE SCHEDULE FOR COMPRESSED AIR SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165566 | T16182-YL16-P0ZEN-165566 | BOP - I&C CABLE SCHEDULE FOR FUEL GAS SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165567 | T16182-YL16-P0ZEN-165567 | BOP - I&C CABLE SCHEDULE FOR ELECTRICAL SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O |  |  | 2017-10-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165568 | T16182-YL16-P0ZEN-165568 | BOP - I&C CABLE SCHEDULE FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFI | 2017-12-15 | 2018-03-15 |  | O |  |  | 2017-12-18 | 2018-01-19
I&C(16) | Instrumentation & Control | 165571 | T16182-YD02-P0ZEN-165571 | BOP EXPOSED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | IFI | 2017-08-20 | 2017-11-18 |  |  |  |  | 2017-08-23 | 2017-12-08
I&C(16) | Instrumentation & Control | 165572 | T16182-YD02-P0ZEN-165572 | BOP EXPOSED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | IFI | 2017-08-28 | 2017-11-26 |  |  |  |  | 2017-08-23 | 2017-12-08
I&C(16) | Instrumentation & Control | 165573 | T16182-YD02-P0ZEN-165573 | BOP EXPOSED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | IFI | 2017-10-19 | 2018-01-17 |  |  |  |  | 2017-10-23 | 2017-12-08
I&C(16) | Instrumentation & Control | 165575 | T16182-YD02-P0ZEN-165575 | BOP EXPOSED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | IFI | 2018-01-25 | 2018-04-25 |  |  |  |  | 2017-12-08 | 2018-02-21
I&C(16) | Instrumentation & Control | 165576 | T16182-YD02-P0ZEN-165576 | BOP EXPOSED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | IFI | 2018-05-09 | 2018-08-07 |  |  |  |  | 2018-03-26 | 2019-01-09
I&C(16) | Instrumentation & Control | 165577 | T16182-YD02-P0ZEN-165577 | BOP EXPOSED CONDUIT LAYOUT FOR PIPE RACK AREA | IFI | 2018-05-09 | 2018-08-07 |  |  |  |  | 2018-03-26 | 2018-10-02
I&C(16) | Instrumentation & Control | 165701 | T16182-CV03-P0ZEN-165701 | TECHNICAL SPECIFICATION FOR I&C CABLE | IFR | 2017-07-15 | 2017-10-28 |  | O |  |  | 2017-06-26 | 2017-08-18
I&C(16) | Instrumentation & Control | 165711 | T16182-CV03-P0ZEN-165711 | TECHNICAL SPECIFICATION FOR JUNCTION BOX & RACK | IFR | 2017-07-15 | 2017-10-20 |  | O |  |  | 2017-07-13 | 2017-08-17
I&C(16) | Instrumentation & Control | 165731 | T16182-CV03-P0ZEN-165731 | TECHNICAL SPECIFICATION FOR INSTRUMENT INSTALLATION MATERIALS | IFR | 2017-08-15 | 2017-11-20 |  | O |  |  | 2017-07-06 | 2017-07-28
I&C(16) | Instrumentation & Control | 165900 | T16182-YR02-P0ZEN-165900 | DESCRIPTION OF SETTLEMENT SYSTEM | IFR | 2016-12-23 | 2017-08-01 |  |  |  |  | 2016-12-23 | 2017-05-18
I&C(16) | Instrumentation & Control | 167001 | T16182-YF00-P0ZEN-167001 | CYBER SECURITY PLAN | IFI | 2019-06-30 | [5 empty] | 2019-06-27 | #VALUE!
CV(17) | Civil | 170101 | T16182-BF05-P0ZEN-170101 | SOIL INVESTIGATION REPORT | IFI | 2016-10-24 |  |  | O |  |  | 2016-12-13 | #VALUE!
CV(17) | Civil | 170102 | T16182-BF05-P0ZEN-170102 | TOPOGRAPHIC SURVEY REPORT | IFI | 2016-10-24 |  |  | O |  |  | 2017-01-03 | #VALUE!
CV(17) | Civil | 170103 | T16182-VE04-P0ZEN-170103 | PILE CAPACITY CALCULATION | IFR | 2016-10-24 | 2017-01-18 |  |  |  |  | 2016-12-21 | 2017-02-09
CV(17) | Civil | 170104 | T16182-VK02-P0ZEN-170104 | WORKING PILE DETAIL | IFR | 2016-10-24 | 2017-01-18 |  |  |  |  | 2016-12-21 | 2017-02-03
CV(17) | Civil | 170105 | T16182-BF05-P0ZEN-170105 | REPORT FOR PILE LOAD TEST OF BORED CAST - IN - PLACE PILE | IFI | 2016-10-24 |  |  | O |  |  | 2017-01-03 | #VALUE!
CV(17) | Civil | 171001 | T16182-VE04-P0UMX-171001 | GTG FOUNDATION - PILE CALCULATION SHEET | IFR | 2017-03-28 | 2017-05-12 |  | O |  |  | 2017-02-14 | 2017-03-10
CV(17) | Civil | 171002 | T16182-XB02-P0UMX-171002 | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | IFR | 2017-03-28 | 2017-05-12 |  | O |  |  | 2017-02-14 | 2017-03-10
CV(17) | Civil | 171004 | T16182-VE04-P0UMX-171004 | GTG FOUNDATION - DESIGN REPORT | IFR | 2017-06-15 | 2017-09-13 |  | O |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171005 | T16182-XB02-P0UMX-171005 | GT FDN GENERAL NOTES FORMWORK DWG | IFR | 2017-06-15 | 2017-09-13 |  | O |  |  | 2017-04-21 | 2017-11-23
CV(17) | Civil | 171006 | T16182-XB02-P0UMX-171006 | GT FDN TOP PLAN VIEW INSERT PLATE ARRANGEMENT AND DETAILS FORMWORK DWG, PART 1/6 | IFR | 2017-06-15 | 2017-09-13 |  | O |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171007 | T16182-XB02-P0UMX-171007 | GT FDN TOP PLAN VIEW ANCHOR BOLT ARRANGEMENT AND DETAILS FORMWORK DRAWING, PART 2/6 | IFR | 2017-06-15 | 2017-09-13 |  | O |  |  | 2017-04-21 | 2017-06-27
CV(17) | Civil | 171008 | T16182-XB02-P0UMX-171008 | GT FDN TOP PLAN VIEW EXPANSION BOLT ARRGMNT AND DETAIL FORMWORK DWG, 3/6 | IFR | 2017-06-15 | 2017-09-13 |  | O |  |  | 2017-04-21 | 2017-06-27
CV(17) | Civil | 171009 | T16182-XB02-P0UMX-171009 | GT FDN VIEWS & SECTIONS FORMWORK DWG, PART 4/6 | IFR | 2017-06-15 | 2017-09-13 |  | O |  |  | 2017-04-21 | 2017-06-27
CV(17) | Civil | 171010 | T16182-XB02-P0UMX-171010 | GT FDN ANCHOR BOLT DETAILS FORMWORK DWG, PART 5/6 | IFR | 2017-06-15 | 2017-09-13 |  | O |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171011 | T16182-XB02-P0UMX-171011 | GT FDN TOP PLAN VIEW SCHEDULE OF EMBEDDED PARTS FORMWORK DRAWING, PART 6/6 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171012 | T16182-VK02-P0UMX-171012 | GT FDN BOTTOM LONGITUDINAL & LATERAL REINFORCEMENT REINFORCEMENT DRAWING BASEMAT, PART 1/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-27
CV(17) | Civil | 171013 | T16182-VK02-P0UMX-171013 | GT FDN TOP LOGITUDINAL & LATERAL REINFORCEMENT DWG BASEMAT, PART 2/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171014 | T16182-VK02-P0UMX-171014 | GT FDN BOTTOM & TOP (3rd + 4th LAYER) LATERAL & LONGITUDINAL REINFORCEMENT, PART 3/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171015 | T16182-VK02-P0UMX-171015 | GT FDN CONNECTION AND SIDE FACE REINFORCEMENT PLAN AT +0.152M & 1.099M LEVEL REINFORCEMENT DRAWING BASEMAT, PART 4/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171016 | T16182-VK02-P0UMX-171016 | GT FDN SPACER REBARS AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 5/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171017 | T16182-VK02-P0UMX-171017 | GT FDN SECTION 1-1 AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 6/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171018 | T16182-VK02-P0UMX-171018 | GT FDN REINFORCEMENT SECTION 2-2 AND 3-3 REINFORCEMENT DRAWING BASEMAT, PART 7/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-28 | 2017-06-20
CV(17) | Civil | 171019 | T16182-VK02-P0UMX-171019 | GT FDN REINFORCEMENT DETAILS SECTION 4-4 AND 5-5 REINFORCEMENT DRAWING BASEMAT, PART 8/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-28 | 2017-06-20
CV(17) | Civil | 171020 | T16182-VK02-P0UMX-171020 | GT FDN REINFORCEMENT PLAN & SECTIONS FOR COMPRESSION SUPPORT, TURNING GEAR PEDESTAL AND MOUNTING PAD PEDESTAL REINFORCEMENT DRAWING BASEMAT, PART 9/9 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-28 | 2017-06-20
CV(17) | Civil | 171021 | T16182-VK02-P0UMX-171021 | GT FDN REINFORCEMENT PLAN AT +1.099M LEVEL AND SPACER & SIDE FACE REBARS GENERATOR DECK REINFORCEMENT, PART 1/2 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171022 | T16182-VK02-P0UMX-171022 | GT FDN SECTIONS & DETAILS GENERATOR DECK REINFORCEMENT, PART 2/2 | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-21 | 2017-06-20
CV(17) | Civil | 171023 | T16182-VK02-P0UMX-171023 | GTG FOUNDATION BAR BENDING SCHEDULE | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-28 | 2017-06-20
CV(17) | Civil | 171024 | T16182-VK02-P0UMX-171024 | GT FDN BENDING SCHEDULES - GENERATOR DECK | IFR | 2017-06-15 | 2017-09-13 |  |  |  |  | 2017-04-28 | 2017-06-20
CV(17) | Civil | 171051 | T16182-VE04-P0UMX-171051 | GTG AUXILIARY FOUNDATION - DESIGN REPORT | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-08-21 | 2017-10-30
CV(17) | Civil | 171052 | T16182-XB02-P0UMX-171052 | GTG AUXILIARY FOUNDATION - GENERAL ARRANGEMENT | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-08-21 | 2017-10-30
CV(17) | Civil | 171053 | T16182-XB02-P0UMX-171053 | FOUNDATION FOR SFC & SEE TRANSFORMER PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171054 | T16182-XB02-P0UMX-171054 | FOUNDATION FOR EXHAUST TRANSITION DUCT & COMPRESSOR BLEED PIPE SUPPORT PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171055 | T16182-XB02-P0UMX-171055 | FOUNDATION FOR WOBBE METER CABINET, GT ENCLOSURE RIGHT SIDE EXHAUST END EXTERIOR PLATFORM & AIR COMPRESSOR SKID(DAIS) PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171056 | T16182-XB02-P0UMX-171056 | FOUNDATION FOR SEE/ SFC PACKAGE FOUNDATION INTERFACE-SEE ONLY PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171057 | T16182-XB02-P0UMX-171057 | FOUNDATION FOR SEE/ SFC PACKAGE SEE WITH SFC NORMAL START PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171058 | T16182-XB02-P0UMX-171058 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS FORMWORK DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171059 | T16182-VK02-P0UMX-171059 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171060 | T16182-VK02-P0UMX-171060 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM BAR BENDING SCHEDULE | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-07-12 | 2017-10-30
CV(17) | Civil | 171061 | T16182-XB02-P0UMX-171061 | FOUNDATION FOR ROTOR AIR COOLER(KETTLE BOILER) & ROTOR COOLING AIR PIPE SUPPORTS PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-08-21 | 2017-10-30
CV(17) | Civil | 171062 | T16182-XB02-P0UMX-171062 | FOUNDATION FOR SFC CROSSOVER SWITCH & FIRE PROTECTION SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-08-21 | 2017-10-30
CV(17) | Civil | 171063 | T16182-XB02-P0UMX-171063 | FOUNDATION FOR PULSE AIR COMPRESSIOR SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  |  | 2017-08-21 | 2017-10-30
CV(17) | Civil | 171101 | T16182-VE04-P0MPA-171101 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION PILE DESIGN | IFR | 2017-02-28 | 2017-05-14 |  |  |  |  | 2017-01-25 | 2017-02-13
CV(17) | Civil | 171102 | T16182-VE04-P0MPA-171102 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION DYNAMIC ANALYSIS | IFR | 2017-03-28 | 2017-06-11 |  |  |  |  | 2017-02-09 | 2017-03-24
CV(17) | Civil | 171103 | T16182-VE04-P0MPA-171103 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION R.C DESIGN | IFR | 2017-06-28 | 2017-09-11 |  |  |  |  | 2017-03-07 | 2017-04-10
CV(17) | Civil | 171104 | T16182-XB02-P0MPA-171104 | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | IFR | 2017-06-28 | 2017-09-11 |  |  |  |  | 2017-01-25 | 2017-02-13
CV(17) | Civil | 171105 | T16182-XB02-P0MPA-171105 | STEAM TURBINE GENERATOR FOUNDATION PILE ARRANGEMENT | IFR | 2017-02-28 | 2017-05-14 |  |  |  |  | 2017-01-25 | 2017-02-13
CV(17) | Civil | 171106 | T16182-XB02-P0MPA-171106 | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | IFR | 2017-06-28 | 2017-09-11 |  |  |  |  | 2017-03-07 | 2017-04-10
CV(17) | Civil | 171113 | T16182-XB02-P0MPA-171113 | STEAM TURBINE GENERATOR FOUNDATION ANCHOR BOLTS AND EMBEDMENT | IFR | 2017-07-28 | 2017-11-15 |  |  |  |  | 2017-03-07 | 2017-06-26
CV(17) | Civil | 171117 | T16182-VK02-P0MPA-171117 | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | IFR | 2017-06-28 | 2017-09-11 |  |  |  |  | 2017-03-07 | 2017-04-10
CV(17) | Civil | 171201 | T16182-VE04-P0ULX-171201 | CALCULATION OF CCW FIN FAN COOLER FOUNDATION | IFR | 2017-05-24 | 2017-08-06 |  |  |  |  | 2017-05-23 | 2017-07-04
CV(17) | Civil | 171202 | T16182-XB02-P0ULX-171202 | CCW FIN FAN COOLER FOUNDATION LAYOUT | IFR | 2017-05-24 | 2017-08-06 |  | O |  |  | 2017-05-23 | 2017-07-04
CV(17) | Civil | 171203 | T16182-XB02-P0ULX-171203 | CCW FIN FAN COOLER FOUNDATION PLAN AND SECTION | IFR | 2017-05-24 | 2017-08-06 |  | O |  |  | 2017-05-23 | 2017-07-04
CV(17) | Civil | 171221 | T16182-VE04-P0ULX-171221 | CALCULATION OF CPP FIN FAN COOLER FOUNDATION | IFR | 2017-07-31 | 2017-10-31 |  | O |  |  | 2017-06-12 | 2017-07-21
CV(17) | Civil | 171222 | T16182-XB02-P0ULX-171222 | CPP FIN FAN COOLER FOUNDATION LAYOUT | IFR | 2017-07-31 | 2017-10-31 |  | O |  |  | 2017-06-12 | 2017-07-21
CV(17) | Civil | 171223 | T16182-XB02-P0ULX-171223 | CPP FIN FAN COOLER FOUNDATION PLAN AND SECTION | IFR | 2017-07-31 | 2017-10-31 |  | O |  |  | 2017-06-12 | 2017-07-21
CV(17) | Civil | 171301 | T16182-VE04-P0ULC-171301 | CALCULATION OF AIR COOLED CONDENSER FOUNDATION | IFR | 2017-03-15 | 2017-05-31 |  |  |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171302 | T16182-XB02-P0ULC-171302 | AIR COOLED CONDENSER FOUNDATION LAYOUT | IFR | 2017-03-15 | 2017-05-31 |  |  |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171303 | T16182-XB02-P0ULC-171303 | AIR COOLED CONDENSER FOUNDATION PLAN AND SECTION | IFR | 2017-03-15 | 2017-05-31 |  |  |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171308 | T16182-VK02-P0ULC-171308 | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | IFR | 2017-03-15 | 2017-05-31 |  |  |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171309 | T16182-VK02-P0ULC-171309 | AIR COOLED CONDENSER DRAIN WATER PUMP PIT DETAIL | IFR | 2017-06-15 | 2017-08-15 |  |  |  |  | 2017-05-31 | 2017-06-21
CV(17) | Civil | 171401 | T16182-VE04-P0UNX-171401 | CALCULATION OF PIPE SLEEPER FOUNDATION | IFR | 2017-05-05 | 2017-07-04 |  |  |  |  | 2017-05-10 | 2017-06-30
CV(17) | Civil | 171402 | T16182-XB02-P0UNX-171402 | PIPE SLEEPER FOUNDATION OVERALL LAYOUT | IFR | 2017-05-05 | 2017-07-04 |  | O |  |  | 2017-05-10 | 2017-06-30
CV(17) | Civil | 171403 | T16182-XB02-P0UNX-171403 | PIPE SLEEPER FOUNDATION LAYOUT | IFR | 2017-05-05 | 2017-07-04 |  |  |  |  | 2017-05-10 | 2017-06-30
CV(17) | Civil | 171410 | T16182-XB02-P0UNX-171410 | PIPE SLEEPER FOUNDATION PLAN AND SECTION | IFR | 2017-05-05 | 2017-07-04 |  | O |  |  | 2017-05-10 | 2017-06-30
CV(17) | Civil | 171501 | T16182-VE04-P0UEG-171501 | FGS AREA FOUNDATION CALCULATION | IFR | 2017-04-29 | 2017-06-30 |  | O |  |  | 2017-04-28 | 2017-06-30
CV(17) | Civil | 171502 | T16182-XB02-P0UEG-171502 | FGS AREA LAYOUT | IFR | 2017-04-29 | 2017-06-30 |  | O |  |  | 2017-04-28 | 2017-06-30
CV(17) | Civil | 171504 | T16182-XB02-P0UEG-171504 | FGS AREA PLAN AND SECTION | IFR | 2017-04-29 | 2017-06-30 |  | O |  |  | 2017-04-28 | 2017-06-30
CV(17) | Civil | 171601 | T16182-VE04-P0ULX-171601 | CALCULATION OF GT PERFORMANCE HEATER FOUNDATION | IFR | 2017-08-18 | 2017-11-18 |  | O |  |  | 2017-07-21 | 2017-11-14
CV(17) | Civil | 171602 | T16182-XB02-P0ULX-171602 | GT PERFORMANCE HEATER FOUNDATION LAYOUT | IFR | 2017-08-18 | 2017-11-18 |  | O |  |  | 2017-07-21 | 2017-11-14
CV(17) | Civil | 171603 | T16182-XB02-P0ULX-171603 | GT PERFORMANCE HEATER FOUNDATION PLAN AND SECTION | IFR | 2017-08-18 | 2017-11-18 |  | O |  |  | 2017-07-21 | 2017-11-14
CV(17) | Civil | 171604 | T16182-VK02-P0ULX-171604 | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | IFR | 2017-08-18 | 2017-11-18 |  | O |  |  | 2017-07-21 | 2017-11-14
CV(17) | Civil | 171701 | T16182-VE04-P0UEM-171701 | CALCULATION OF WASTE WATER TREATMENT PLANT | IFR | 2017-03-15 | 2017-05-16 |  | O |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171702 | T16182-XB02-P0UEM-171702 | WASTE WATER TREATMENT PLANT PLAN AND SECTION | IFR | 2017-03-15 | 2017-05-16 |  | O |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171708 | T16182-XB02-P0UEM-171708 | WASTE WATER TREATMENT PLANT EMBEDMENT DETAIL | IFR | 2017-03-15 | 2017-05-16 |  | O |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171711 | T16182-VK02-P0UEM-171711 | WASTE WATER TREATMENT R.C DETAIL | IFR | 2017-03-15 | 2017-05-16 |  | O |  |  | 2017-03-16 | 2017-05-02
CV(17) | Civil | 171801 | T16182-VE04-P0UHA-171801 | CALCULATION OF HRSG FOUNDATION PILING | IFR | 2017-01-25 | 2017-04-25 |  |  |  |  | 2016-12-26 | 2017-02-09
CV(17) | Civil | 171802 | T16182-VE04-P0UHA-171802 | CALCULATION OF HRSG FOUNDATION | IFR | 2017-04-27 | 2017-07-26 |  |  |  |  | 2017-03-21 | 2017-04-21
CV(17) | Civil | 171803 | T16182-XB02-P0UHA-171803 | HRSG FOUNDATION ARRANGEMENT | IFR | 2017-01-25 | 2017-04-25 |  |  |  |  | 2016-12-26 | 2017-02-09
CV(17) | Civil | 171804 | T16182-XB02-P0UHA-171804 | HRSG FOUNDATION PILE ARRANGEMENT PLAN | IFR | 2017-01-25 | 2017-04-25 |  |  |  |  | 2016-12-26 | 2017-02-09
CV(17) | Civil | 171805 | T16182-XB02-P0UHA-171805 | HRSG FOUNDATION LAYOUT | IFR | 2017-04-27 | 2017-07-26 |  |  |  |  | 2017-03-21 | 2017-04-21
CV(17) | Civil | 171806 | T16182-XB02-P0UHA-171806 | HRSG FOUNDATION PLAN SECTION & DETAIL | IFR | 2017-04-27 | 2017-07-26 |  |  |  |  | 2017-03-21 | 2017-04-21
CV(17) | Civil | 171807 | T16182-XB02-P0UHA-171807 | HRSG FOUNDATION REBAR DETAIL | IFR | 2017-04-27 | 2017-07-26 |  |  |  |  | 2017-03-21 | 2017-04-21
CV(17) | Civil | 171815 | T16182-XB02-P0UHA-171815 | HRSG MISC. FOUNDATION PLAN | IFR | 2017-06-16 | 2017-09-14 |  |  |  |  | 2017-07-07 | 2017-08-18
CV(17) | Civil | 171816 | T16182-XB02-P0UHA-171816 | HRSG MISC. FOUNDATION DETAILS | IFR | 2017-06-16 | 2017-09-14 |  |  |  |  | 2017-07-07 | 2017-08-18
CV(17) | Civil | 171819 | T16182-VE04-P0UHA-171819 | CALCULATION OF HRSG MISC. FOUNDATION | IFR | 2017-06-16 | 2017-09-14 |  |  |  |  | 2017-07-07 | 2017-08-18
CV(17) | Civil | 172001 | T16182-VE04-P8UTH-172001 | CALCULATION OF RESERVE BOILER FOUNDATION | IFR | 2017-02-28 | 2017-05-29 |  |  |  |  | 2016-12-15 | 2017-02-10
CV(17) | Civil | 172003 | T16182-XB02-P8UTH-172003 | RESERVE BOILER FOUNDATION LAYOUT | IFR | 2017-02-28 | 2017-05-29 |  | O |  |  | 2016-12-15 | 2017-02-10
CV(17) | Civil | 172004 | T16182-XB02-P8UTH-172004 | RESERVE BOILER FOUNDATION SECTION & DETAIL | IFR | 2017-02-28 | 2017-05-29 |  | O |  |  | 2016-12-15 | 2017-02-10
CV(17) | Civil | 172005 | T16182-VK02-P8UTH-172005 | RESERVE BOILER FOUNDATION REBAR DETAIL | IFR | 2017-02-28 | 2017-05-29 |  | O |  |  | 2017-01-25 | 2017-03-21
CV(17) | Civil | 172007 | T16182-XB02-P8UTH-172007 | RESERVE BOILER GRADE SLAB PLAN & SECTION | IFR | 2017-06-01 | 2017-09-01 |  | O |  |  | 2017-06-01 | 2017-06-21
CV(17) | Civil | 172008 | T16182-VK02-P8UTH-172008 | RESERVE BOILER GRADE SLAB REBAR DETAIL | IFR | 2017-06-01 | 2017-09-01 |  | O |  |  | 2017-06-01 | 2017-06-21
CV(17) | Civil | 172011 | T16182-VE04-P8UTH-172011 | CALCULATION OF FD FAN AND MISC. FOUNDATION | IFR | 2017-04-01 | 2017-07-01 |  | O |  |  | 2017-03-31 | 2017-05-31
CV(17) | Civil | 172012 | T16182-XB02-P8UTH-172012 | RESERVE BOILER FD FAN FOUNDATION | IFR | 2017-04-01 | 2017-07-01 |  | O |  |  | 2017-03-31 | 2017-05-31
CV(17) | Civil | 172013 | T16182-XB02-P8UTH-172013 | RESERVE BOILER MISC. FOUNDATION | IFR | 2017-04-01 | 2017-07-01 |  | O |  |  | 2017-03-31 | 2017-05-31
CV(17) | Civil | 172100 | T16182-XB02-P0UAG-172100 | TRANSFORMER FOUNDATION ARRANGEMENT PLAN | IFR | 2017-04-25 | 2017-07-24 |  |  |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172101 | T16182-VE04-P0UAG-172101 | CALCULATION OF STG STEP - UP AND EXCITATION TRANSFORMER FOUNDATION | IFR | 2017-04-25 | 2017-07-24 |  |  |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172102 | T16182-XB02-P0UAG-172102 | STG STEP UP AND EXCITATION TRANSFORMER PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24 |  |  |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172108 | T16182-XB02-P0UAG-172108 | STG STEP UP AND EXCITATION TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24 |  |  |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172109 | T16182-VK02-P0UAG-172109 | STG STEP UP AND EXCITATION TRANSFORMER RE-BAR DETAIL | IFR | 2017-04-25 | 2017-07-24 |  |  |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172151 | T16182-VE04-P0UAG-172151 | CALCULATION OF GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION | IFR | 2017-04-25 | 2017-07-24 |  | O |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172162 | T16182-XB02-P0UAG-172162 | GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24 |  | O |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172168 | T16182-XB02-P0UAG-172168 | GTG STEP UP & UNIT AUX. TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24 |  | O |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172170 | T16182-VK02-P0UAG-172170 | GTG STEP UP & UNIT AUX. TRANSFORMER RE-BAR DETAIL | IFR | 2017-04-25 | 2017-07-24 |  | O |  |  | 2017-04-27 | 2017-06-30
CV(17) | Civil | 172201 | T16182-VE04-P0UBN-172201 | CALCULATION OF BSDG FOUNDATION | IFR | 2017-09-04 | 2017-11-03 |  | O |  |  | 2017-07-11 | 2017-07-25
CV(17) | Civil | 172202 | T16182-XB02-P0UBN-172202 | BSDG FOUNDATION PLAN & SECTION | IFR | 2017-09-04 | 2017-11-03 |  | O |  |  | 2017-07-11 | 2017-07-25
CV(17) | Civil | 172203 | T16182-VK02-P0UBN-172203 | BSDG FOUNDATION R.C DETAIL | IFR | 2017-09-04 | 2017-11-03 |  | O |  |  | 2017-07-11 | 2017-07-25
CV(17) | Civil | 172401 | T16182-VE04-P0BAA-172401 | CALCULATION OF IPB FOUNDATION | IFR | 2017-04-23 | 2017-07-22 |  |  |  |  | 2017-04-24 | 2017-10-13
CV(17) | Civil | 172402 | T16182-XB02-P0BAA-172402 | IPB FOUNDATION PLAN & SECTION | IFR | 2017-04-23 | 2017-07-22 |  |  |  |  | 2017-04-24 | 2017-10-13
CV(17) | Civil | 172403 | T16182-VK02-P0BAA-172403 | IPB FOUNDATION R.C DETAIL | IFR | 2017-04-23 | 2017-07-22 |  |  |  |  | 2017-04-24 | 2017-10-13
CV(17) | Civil | 172501 | T16182-VE04-P0ULC-172501 | CALCULATION OF CONDENSATE WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31 |  |  |  |  | 2017-03-31 | 2017-05-24
CV(17) | Civil | 172502 | T16182-XB02-P0ULC-172502 | CONDENSATE WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31 |  |  |  |  | 2017-03-31 | 2017-05-24
CV(17) | Civil | 172503 | T16182-VK02-P0ULC-172503 | CONDENSATE WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31 |  |  |  |  | 2017-03-31 | 2017-05-24
CV(17) | Civil | 172521 | T16182-VE04-P0UGF-172521 | CALCULATION OF POTABLE & FIRE FIGHTING WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-13 | 2017-04-18
CV(17) | Civil | 172522 | T16182-XB02-P0UGF-172522 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-13 | 2017-04-18
CV(17) | Civil | 172523 | T16182-VK02-P0UGF-172523 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-13 | 2017-04-18
CV(17) | Civil | 172541 | T16182-VE04-P0UGD-172541 | CALCULATION OF DEMINERALIZED WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-20 | 2017-04-18
CV(17) | Civil | 172542 | T16182-XB02-P0UGD-172542 | DEMINERALIZED WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-20 | 2017-04-18
CV(17) | Civil | 172543 | T16182-VK02-P0UGD-172543 | DEMINERALIZED WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-20 | 2017-04-18
CV(17) | Civil | 172561 | T16182-VE04-P0UGG-172561 | CALCULATION OF POTABLE WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-20 | 2017-04-18
CV(17) | Civil | 172562 | T16182-XB02-P0UGG-172562 | POTABLE WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-20 | 2017-04-18
CV(17) | Civil | 172563 | T16182-VK02-P0UGG-172563 | POTABLE WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-03-20 | 2017-04-18
CV(17) | Civil | 172581 | T16182-VE04-P0ULX-172581 | CALCULATION OF GENERAL SERVICE PUMP FOUNDATION | IFR | 2017-08-16 | 2017-10-20 |  |  |  |  | 2017-07-28 | 2017-09-01
CV(17) | Civil | 172582 | T16182-XB02-P0ULX-172582 | GENERAL SERVICE PUMP FOUNDATIONS LAYOUT | IFR | 2017-08-16 | 2017-10-20 |  |  |  |  | 2017-07-28 | 2017-09-01
CV(17) | Civil | 172583 | T16182-XB02-P0ULX-172583 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (1) | IFR | 2017-08-16 | 2017-10-20 |  |  |  |  | 2017-07-28 | 2017-09-01
CV(17) | Civil | 172584 | T16182-XB02-P0ULX-172584 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (2) | IFR | 2017-08-16 | 2017-10-20 |  |  |  |  | 2017-07-28 | 2017-09-01
CV(17) | Civil | 172585 | T16182-XB02-P0ULX-172585 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (3) | IFR | 2017-08-16 | 2017-10-20 |  |  |  |  | 2017-07-28 | 2017-09-01
CV(17) | Civil | 172601 | T16182-VE04-P0UAZ-172601 | CALCULATION OF EHV CABLE TRENCH & DIRECT BURIED CABLE | IFR | 2017-04-11 | 2017-07-02 |  | O |  |  | 2017-04-12 | 2017-06-15
CV(17) | Civil | 172602 | T16182-XB02-P0UAZ-172602 | EHV CABLE TRENCH & DIRECT BURIED CABLE OVERALL LAYOUT | IFR | 2017-04-11 | 2017-07-02 |  | O |  |  | 2017-04-12 | 2017-06-15
CV(17) | Civil | 172603 | T16182-XB02-P0UAZ-172603 | EHV CABLE TRENCH & DIRECT BURIED CABLE LAYOUT | IFR | 2017-04-11 | 2017-07-02 |  | O |  |  | 2017-04-12 | 2017-06-15
CV(17) | Civil | 172608 | T16182-XB02-P0UAZ-172608 | EHV CABLE TRENCH & DIRECT BURIED CABLE PLAN & SECTION | IFR | 2017-04-11 | 2017-07-02 |  | O |  |  | 2017-04-12 | 2017-06-15
CV(17) | Civil | 172613 | T16182-VK02-P0UAZ-172613 | EHV CABLE TRENCH & DIRECT BURIED CABLE DETAIL | IFR | 2017-04-11 | 2017-07-02 |  | O |  |  | 2017-04-12 | 2017-06-15
CV(17) | Civil | 172701 | T16182-VE04-P0UZT-172701 | CALCULATION OF ELECTRICAL DUCT BANK MANHOLE | IFR | 2017-07-01 | 2017-09-15 |  |  |  |  | 2017-04-28 | 2017-05-30
CV(17) | Civil | 172702 | T16182-XB02-P0UZT-172702 | ELECTRICAL DUCT BANK OVERALL LAYOUT | IFR | 2017-07-01 | 2017-09-15 |  |  |  |  | 2017-04-28 | 2017-05-30
CV(17) | Civil | 172703 | T16182-XB02-P0UZT-172703 | ELECTRICAL DUCT BANK LAYOUT | IFR | 2017-07-01 | 2017-09-15 |  |  |  |  | 2017-04-28 | 2017-05-30
CV(17) | Civil | 172704 | T16182-VK02-P0UZT-172704 | ELECTRICAL DUCT BANK TYPICAL SECTION & R.C DETAILS | IFR | 2017-07-01 | 2017-09-15 |  |  |  |  | 2017-04-28 | 2017-05-30
CV(17) | Civil | 172713 | T16182-VK02-P0UZT-172713 | ELECTRICAL DUCT BANK MANHOLE SCHEDULE | IFR | 2017-07-01 | 2017-09-15 |  |  |  |  | 2017-04-28 | 2017-05-30
CV(17) | Civil | 172716 | T16182-XB02-P0UZT-172716 | ELECTRICAL DUCT BANK MANHOLE PLAN, SECTION & R.C DETAILS | IFR | 2017-07-01 | 2017-09-15 |  |  |  |  | 2017-04-28 | 2017-05-30
CV(17) | Civil | 172801 | T16182-VE04-P0GUC-172801 | CALCULATION OF STORMWATER POND | IFR | 2017-06-30 | 2017-08-29 |  |  |  |  | 2017-07-03 | 2017-10-30
CV(17) | Civil | 172802 | T16182-XB02-P0GUC-172802 | CLEAN STORM WATER PONDS OVERALL LAYOUT | IFR | 2017-06-30 | 2017-08-29 |  |  |  |  | 2017-07-03 | 2017-10-30
CV(17) | Civil | 172803 | T16182-XB02-P0GUC-172803 | CLEAN STORM WATER PONDS PLAN AND SECTION | IFR | 2017-06-30 | 2017-08-29 |  |  |  |  | 2017-07-03 | 2017-10-30
CV(17) | Civil | 172804 | T16182-VK02-P0GUC-172804 | STORMWATER POND DETAIL | IFR | 2017-06-30 | 2017-08-29 |  |  |  |  | 2017-07-03 | 2017-10-30
CV(17) | Civil | 172901 | T16182-VE04-P0UZA-172901 | CALCULATION OF ROAD AND PAVING | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2016-12-21 | 2017-08-18
CV(17) | Civil | 172902 | T16182-XB02-P0UZA-172902 | ROAD AND PAVING OVERALL LAYOUT | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2016-12-21 | 2017-08-18
CV(17) | Civil | 172903 | T16182-XB02-P0UZA-172903 | ROAD AND PAVING LAYOUT | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2016-12-21 | 2017-08-18
CV(17) | Civil | 172904 | T16182-XB02-P0UZA-172904 | ROAD AND PAVING - GRAVEL PAVEMENT PLAN & SECTION | IFR | 2017-12-20 | 2018-08-29 |  |  |  |  | 2017-12-19 | 2018-05-04
CV(17) | Civil | 172908 | T16182-VK02-P0UZA-172908 | ROAD AND PAVING DETAIL | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2016-12-21 | 2017-08-18
CV(17) | Civil | 172911 | T16182-XB02-P0UZA-172911 | ROAD MARKING AND SIGN BOARD LAYOUT | IFR | 2019-04-30 | 2019-07-30 |  |  |  |  | 2019-04-17 | 2019-06-27
CV(17) | Civil | 172912 | T16182-VK02-P0UZA-172912 | ROAD MARKING AND SIGN BOARD DETAIL | IFR | 2019-04-30 | 2019-07-30 |  |  |  |  | 2019-04-17 | 2019-06-27
CV(17) | Civil | 173001 | T16182-VE04-P0UZT-173001 | CALCULATION OF LIGHTING POLE FOUNDATION | IFR | 2018-04-13 | 2018-07-13 |  |  |  |  | 2018-04-27 | 2018-05-17
CV(17) | Civil | 173002 | T16182-XB02-P0UZT-173002 | LIGHTING POLE FOUNDATION OVERALL LAYOUT | IFR | 2018-04-13 | 2018-07-13 |  |  |  |  | 2018-04-27 | 2018-05-17
CV(17) | Civil | 173003 | T16182-XB02-P0UZT-173003 | LIGHTING POLE FOUNDATION LAYOUT | IFR | 2018-04-13 | 2018-07-13 |  |  |  |  | 2018-04-27 | 2018-05-17
CV(17) | Civil | 173008 | T16182-VK02-P0UZT-173008 | LIGHTING POLE FOUNDATION PLAN & DETAIL | IFR | 2018-04-13 | 2018-07-13 |  |  |  |  | 2018-04-27 | 2018-05-17
CV(17) | Civil | 173101 | T16182-XB02-P0UGF-173101 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS OVERALL LAYOUT | IFR | 2017-04-30 | 2017-07-30 |  | O |  |  | 2017-04-28 | 2017-06-13
CV(17) | Civil | 173102 | T16182-XB02-P0UGF-173102 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS LAYOUT | IFR | 2017-04-30 | 2017-07-30 |  | O |  |  | 2017-04-28 | 2017-06-13
CV(17) | Civil | 173107 | T16182-VK02-P0UGF-173107 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS | IFR | 2017-04-30 | 2017-07-30 |  | O |  |  | 2017-04-28 | 2017-06-13
CV(17) | Civil | 173202 | T16182-XB02-P0UZJ-173202 | FENCE AND GATE OVERALL LAYOUT | IFR | 2018-07-01 | 2018-09-29 |  |  |  |  | 2017-04-14 | 2018-02-27
CV(17) | Civil | 173208 | T16182-VK02-P0UZJ-173208 | FENCE AND GATE PLAN AND DETAIL | IFR | 2018-07-01 | 2018-09-29 |  |  |  |  | 2017-04-14 | 2018-02-27
CV(17) | Civil | 173209 | T16182-VK02-P0UZJ-173209 | INTERNAL FENCE AND GATE PLAN AND DETAIL | IFR | 2018-01-30 | 2018-06-30 |  |  |  |  | 2017-12-19 | 2018-01-29
CV(17) | Civil | 173301 | T16182-VE04-P0GUB-173301 | CALCULATION OF STORMWATER DRAINAGE | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2017-04-06 | 2017-06-14
CV(17) | Civil | 173302 | T16182-XB02-P0GUB-173302 | STORMWATER DRAINAGE OVERALL LAYOUT | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2017-04-06 | 2017-06-14
CV(17) | Civil | 173303 | T16182-XB02-P0GUB-173303 | STORMWATER DRAINAGE LAYOUT | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2017-04-06 | 2017-06-14
CV(17) | Civil | 173313 | T16182-VK02-P0GUB-173313 | STORMWATER DRAINAGE STRUCTURAL DETAIL | IFR | 2017-07-01 | 2018-08-29 |  |  |  |  | 2017-04-06 | 2017-06-14
CV(17) | Civil | 173401 | T16182-VE04-P0GQB-173401 | CALCULATION OF WASTE WATER DRAINAGE OVERALL LAYOUT | IFR | 2017-12-31 | 2018-03-31 |  | O |  |  | 2017-06-13 | 2017-06-30
CV(17) | Civil | 173402 | T16182-UT01-P0GQB-173402 | WASTE WATER DRAINAGE OVERALL LAYOUT | IFR | 2017-12-31 | 2018-03-31 |  | O |  |  | 2017-06-13 | 2017-06-30
CV(17) | Civil | 173403 | T16182-UT01-P0GQB-173403 | WASTE WATER DRAINAGE LAYOUT | IFR | 2017-12-31 | 2018-03-31 |  | O |  |  | 2017-06-13 | 2017-06-30
CV(17) | Civil | 173413 | T16182-UT01-P0GQB-173413 | WASTE WATER DRAINAGE MANHOLE SCHEDULE | IFR | 2017-12-31 | 2018-03-31 |  | O |  |  | 2017-06-13 | 2017-07-11
CV(17) | Civil | 173417 | T16182-VK02-P0GQB-173417 | WASTE WATER DRAINAGE STRUCTURE MANHOLE RE-BAR DETAIL | IFR | 2017-12-31 | 2018-03-31 |  | O |  |  | 2017-06-13 | 2017-06-30
CV(17) | Civil | 173501 | T16182-XB02-P0UZK-173501 | LANDSCAPE LAYOUT | IFR | 2019-03-01 | 2018-09-29 |  |  |  |  | 2019-04-03 | 2019-05-28
CV(17) | Civil | 173502 | T16182-VK02-P0UZK-173502 | LANDSCAPING CROSS SECTION & DETAIL | IFR | 2019-03-01 | 2018-09-29 |  |  |  |  | 2019-04-03 | 2019-05-28
CV(17) | Civil | 173503 | T16182-VK02-P0UZK-173503 | WATER TANK SECTION & DETAIL | IFR | 2019-06-01 | 2019-09-01 |  |  |  |  | 2019-05-28 | 2019-05-28
CV(17) | Civil | 173504 | T16182-VK02-P0UZK-173504 | PAVILION PLAN & DETAIL | IFR | 2019-06-01 | 2019-09-01 |  |  |  |  | 2019-05-28 | 2019-05-28
CV(17) | Civil | 173505 | T16182-VK02-P0UZK-173505 | PUMP ROOM PLAN AND DETAIL | IFR | 2019-06-01 | 2019-09-01 |  |  |  |  | 2019-05-28 | 2019-05-28
CV(17) | Civil | 173601 | T16182-VE04-P0GKC-173601 | CALCULATION OF CHILLED WATER STORAGE TANK FOUNDATION | IFR | 2017-11-24 | 2018-02-02 |  |  |  |  | 2017-11-17 | 2018-01-19
CV(17) | Civil | 173602 | T16182-XB02-P0GKC-173602 | CHILLED WATER STORAGE TANK FOUNDATION DETAIL | IFR | 2017-11-24 | 2018-02-02 |  |  |  |  | 2017-11-17 | 2018-01-19
CV(17) | Civil | 173702 | T16182-XB02-P0GKC-173702 | POTABLE WATER CHILLER FOUNDATION DETAIL | IFR | 2017-11-24 | 2018-02-02 |  |  |  |  | 2017-11-17 | 2018-01-19
CV(17) | Civil | 173801 | T16182-VE04-P0GHC-173801 | CALCULATION OF ATM FLASH TANK & DRAIN PUMP PIT | IFR | 2017-11-30 | 2018-02-02 |  |  |  |  | 2017-12-04 | 2018-01-12
CV(17) | Civil | 173802 | T16182-XB02-P0GHC-173802 | ATM FLASH TANK & DRAIN PUMP PIT DETAIL | IFR | 2017-11-30 | 2018-02-02 |  |  |  |  | 2017-12-04 | 2018-01-12
CV(17) | Civil | 173902 | T16182-XB02-P0UZJ-173902 | POWER PLANT DIESEL GENERATOR FOUNDATION PLAN | IFR | 2019-05-10 | 2019-08-10 |  |  |  |  | 2019-04-30 | 2019-07-10
CV(17) | Civil | 173903 | T16182-VK02-P0UZJ-173903 | POWER PLANT DIESEL GENERATOR FOUNDATION REINF. DETAIL | IFR | 2019-05-10 | 2019-08-10 |  |  |  |  | 2019-04-30 | 2019-07-10
S&A(18) | Structural & Architectural | 180001 | T16182-CC05-P0ZEN-180001 | STANDARD DRAWING - GENERAL NOTES, ABBREVIATION, LEGEND & SIMBOLS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180002 | T16182-CC05-P0ZEN-180002 | STANDARD DRAWING - INTERIOR FINISH DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180006 | T16182-CC05-P0ZEN-180006 | STANDARD DRAWING - CLADDING JOINT DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180008 | T16182-CC05-P0ZEN-180008 | STANDARD DRAWING - MISC. ARCHITECTURAL DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180019 | T16182-CC05-P0ZEN-180019 | STANDARD DRAWING - DOOR SCHEDULE | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180020 | T16182-CC05-P0ZEN-180020 | STANDARD DRAWING - DOOR DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180024 | T16182-CC05-P0ZEN-180024 | STANDARD DRAWING - WINDOW SCHEDULE | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180025 | T16182-CC05-P0ZEN-180025 | STANDARD DRAWING - WINDOW DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180030 | T16182-CC05-P0ZEN-180030 | STANDARD DRAWING - RE - BAR STANDARD | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180033 | T16182-CC05-P0ZEN-180033 | STANDARD DRAWING - GENERAL NOTES, MATERIALS, CONNECTIONS & MEMBER SIZE DESIGNATION | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180034 | T16182-CC05-P0ZEN-180034 | STANDARD DRAWING - ABBREVIATIONS & WELDING | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180035 | T16182-CC05-P0ZEN-180035 | STANDARD DRAWING - MOMENT CONNECTION DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180036 | T16182-CC05-P0ZEN-180036 | STANDARD DRAWING - SHEAR CONNECTION DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180037 | T16182-CC05-P0ZEN-180037 | STANDARD DRAWING - TYPICAL VERTICAL & HORIZONTAL BRACING CONNECTION DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180038 | T16182-CC05-P0ZEN-180038 | STANDARD DRAWING - TYPICAL STAIR & HANDRAIL DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180039 | T16182-CC05-P0ZEN-180039 | STANDARD DRAWING - TYPICAL STAIR STRINGER CONNECTION DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180040 | T16182-CC05-P0ZEN-180040 | STANDARD DRAWING - GIRTH & PURLIN CONNECTION DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180041 | T16182-CC05-P0ZEN-180041 | STANDARD DRAWING - TYPICAL GRATING AND CHK'D PLATE DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180042 | T16182-CC05-P0ZEN-180042 | STANDARD DRAWING - LADDER DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180043 | T16182-CC05-P0ZEN-180043 | STANDARD DRAWING - PLUMBING STANDARD SYMBOL & ABBREVIATION | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180044 | T16182-CC05-P0ZEN-180044 | STANDARD DRAWING - PLUMBING STANDARD GENERAL DETAILS | IFI | 2016-11-30 | [5 empty] | 2016-12-13 | #VALUE!
S&A(18) | Structural & Architectural | 180401 | T16182-CA00-P0UMA-180401 | ST BUILDING - GROUND FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180402 | T16182-CA00-P0UMA-180402 | ST BUILDING - ROOF PLAN | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180403 | T16182-CA00-P0UMA-180403 | ST BUILDING - ELEVATION | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180404 | T16182-CA00-P0UMA-180404 | ST BUILDING - SECTION | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180405 | T16182-CA00-P0UMA-180405 | ST BUILDING - INTERIOR FINISH SCHEDULE | IFR | 2017-08-15 | 2017-10-15 |  |  |  |  | 2017-09-08 | 2017-10-30
S&A(18) | Structural & Architectural | 180406 | T16182-CA00-P0UMA-180406 | ST BUILDING - DOOR SCHEDULE | IFR | 2017-08-15 | 2017-10-15 |  |  |  |  | 2017-09-08 | 2017-10-30
S&A(18) | Structural & Architectural | 180408 | T16182-CA00-P0UMA-180408 | ST BUILDING - WALL SECTION | IFR | 2017-08-15 | 2017-10-15 |  |  |  |  | 2017-09-08 | 2017-10-30
S&A(18) | Structural & Architectural | 180451 | T16182-CA01-P0UMA-180451 | ST BUILDING - PILE ARRANGEMENT | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180452 | T16182-CA01-P0UMA-180452 | ST BUILDING - FOUNDATION LOCATION PLAN | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180454 | T16182-CA01-P0UMA-180454 | ST BUILDING - PILE CAP & FOUNDATION REINFORCEMENT DETAIL | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180458 | T16182-CA03-P0UMA-180458 | ST BUILDING - COLUMN LOCATION PLAN | IFR | 2017-01-31 | 2017-03-31 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180459 | T16182-CA03-P0UMA-180459 | ST BUILDING - BASE PLATE DETAIL | IFR | 2017-01-31 | 2017-03-31 |  |  |  |  | 2017-01-26 | 2017-02-10
S&A(18) | Structural & Architectural | 180460 | T16182-CA03-P0UMA-180460 | ST BUILDING - CRANE GIRDER FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180462 | T16182-CA03-P0UMA-180462 | ST BUILDING - ROOF FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180463 | T16182-CA03-P0UMA-180463 | ST BUILDING - FRAMING ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180464 | T16182-CA03-P0UMA-180464 | ST BUILDING - GIRT NORTH - SOUTH ELEVATION | IFR | 2017-04-30 | 2017-05-30 |  |  |  |  | 2017-05-22 | 2017-07-21
S&A(18) | Structural & Architectural | 180465 | T16182-CA03-P0UMA-180465 | ST BUILDING - GIRT EAST - WEST ELEVATION | IFR | 2017-04-30 | 2017-05-30 |  |  |  |  | 2017-05-22 | 2017-07-21
S&A(18) | Structural & Architectural | 180466 | T16182-CA03-P0UMA-180466 | ST BUILDING - MISC. PLATFORM PLAN & SECTION | IFR | 2017-04-30 | 2017-05-30 |  |  |  |  | 2017-05-22 | 2017-09-21
S&A(18) | Structural & Architectural | 180467 | T16182-CA03-P0UMA-180467 | ST BUILDING - STAIR PLAN, ELEVATION & DETAIL | IFR | 2017-04-30 | 2017-05-30 |  |  |  |  | 2017-08-08 | 2017-09-01
S&A(18) | Structural & Architectural | 180468 | T16182-CA03-P0UMA-180468 | ST BUILDING – MAIN TRUSS DETAIL | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180469 | T16182-CA03-P0UMA-180469 | ST BUILDING - ROOF WALKWAY FRAMING PLAN | IFR | 2017-04-30 | 2017-05-30 |  |  |  |  | 2017-05-22 | 2017-07-21
S&A(18) | Structural & Architectural | 180471 | T16182-CA03-P0UMA-180471 | ST BUILDING - ROOF PURLIN PLAN | IFR | 2017-04-30 | 2017-05-30 |  |  |  |  | 2017-05-22 | 2017-07-21
S&A(18) | Structural & Architectural | 180481 | T16182-CA05-P0UMA-180481 | ST BUILDING - EQUIPMENT DRAIN PLAN | IFR | 2017-04-15 | 2017-06-15 |  |  |  |  | 2017-04-14 | 2017-05-31
S&A(18) | Structural & Architectural | 180482 | T16182-CA05-P0UMA-180482 | ST BUILDING - EQUIPMENT DRAIN PLAN (ISO) | IFR | 2017-04-15 | 2017-06-15 |  |  |  |  | 2017-04-14 | 2017-05-31
S&A(18) | Structural & Architectural | 180490 | T16182-CA06-P0UMA-180490 | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | IFR | 2016-11-30 | 2017-01-24 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 180491 | T16182-CA06-P0UMA-180491 | ST BUILDING - DESIGN CALCULATION FOR BASE PLATE, COLUMN, BEAM & ROOF TRUSS | IFR | 2017-01-31 | 2017-03-31 |  |  |  |  | 2017-01-26 | 2017-02-10
S&A(18) | Structural & Architectural | 180492 | T16182-CA06-P0UMA-180492 | ST BUILDING - DESIGN CALCULATION FOR CRANE GIRDER, PURLIN & SIDE GIRT | IFR | 2017-04-30 | 2017-05-30 |  |  |  |  | 2017-06-05 | 2017-07-21
S&A(18) | Structural & Architectural | 180500 | T16182-CA06-P0BAT-180500 | ROOF FOR GTG TR - CALCULATION | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-05-17 | 2017-05-29
S&A(18) |  | 180500 | T16182-CA03-P0UMA-180500 | ST BUILDING_MISC. PLATFORM PLAN & SECTION | Internal | [6 empty] | 2018-02-28 | #VALUE!
S&A(18) | Structural & Architectural | 180511 | T16182-CA00-P1BAT-180511 | ROOF FOR GTG #1 TR - PLAN, SECTION, ELEVATION | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-05-17 | 2017-07-14
S&A(18) | Structural & Architectural | 180512 | T16182-CA03-P1BAT-180512 | ROOF FOR GTG #1 TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-05-17 | 2017-05-29
S&A(18) | Structural & Architectural | 180513 | T16182-CA03-P1BAT-180513 | ROOF FOR GTG #1 TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-05-17 | 2017-05-29
S&A(18) | Structural & Architectural | 180600 | T16182-CA06-P0UCB-180600 | CENTRAL CONTROL BUILDING - CALCULATION | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180601 | T16182-CA00-P0UCB-180601 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-03-02
S&A(18) | Structural & Architectural | 180602 | T16182-CA00-P0UCB-180602 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-03-02
S&A(18) | Structural & Architectural | 180603 | T16182-CA00-P0UCB-180603 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-03-10
S&A(18) | Structural & Architectural | 180604 | T16182-CA00-P0UCB-180604 | CENTRAL CONTROL BUILDING - ROOF PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-03-02
S&A(18) | Structural & Architectural | 180605 | T16182-CA00-P0UCB-180605 | CENTRAL CONTROL BUILDING - SIDE WALL ELEVATION | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-03-02
S&A(18) | Structural & Architectural | 180606 | T16182-CA00-P0UCB-180606 | CENTRAL CONTROL BUILDING - MAIN SECTION | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-03-02
S&A(18) | Structural & Architectural | 180607 | T16182-CA00-P0UCB-180607 | CENTRAL CONTROL BUILDING - INTERIOR FINISH SCHEDULE | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-20 | 2017-04-04
S&A(18) | Structural & Architectural | 180608 | T16182-CA00-P0UCB-180608 | CENTRAL CONTROL BUILDING - DOOR & WINDOW SCHEDULE | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-20 | 2017-04-04
S&A(18) | Structural & Architectural | 180609 | T16182-CA00-P0UCB-180609 | CENTRAL CONTROL BUILDING - STAIRCASE#1 ENLARGED PLAN | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-04-04 | 2017-06-02
S&A(18) | Structural & Architectural | 180610 | T16182-CA00-P0UCB-180610 | CENTRAL CONTROL BUILDING - STAIRCASE#2 ENLARGED PLAN | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-04-04 | 2017-06-02
S&A(18) | Structural & Architectural | 180611 | T16182-CA00-P0UCB-180611 | CENTRAL CONTROL BUILDING - ENLARGED TOILET PLAN & ELEVATION | IFR | 2017-03-31 | 2017-05-31 |  | O |  |  | 2017-04-04 | 2017-06-02
S&A(18) | Structural & Architectural | 180612 | T16182-CA00-P0UCB-180612 | CENTRAL CONTROL BUILDING - WALL OPENING ELEVATION | IFR | 2017-05-31 | 2017-07-31 |  | O |  |  | 2017-06-02 | 2017-07-28
S&A(18) | Structural & Architectural | 180613 | T16182-CA00-P0UCB-180613 | CENTRAL CONTROL BUILDING - CEILING PLAN | IFR | 2017-05-31 | 2017-07-31 |  | O |  |  | 2017-06-02 | 2017-07-28
S&A(18) | Structural & Architectural | 180614 | T16182-CA00-P0UCB-180614 | CENTRAL CONTROL BUILDING - MISC. DETAIL | IFR | 2017-05-31 | 2017-07-31 |  | O |  |  | 2017-06-02 | 2017-07-28
S&A(18) | Structural & Architectural | 180651 | T16182-CA01-P0UCB-180651 | CENTRAL CONTROL BUILDING - FDN & COLUMN ARRANGEMENT PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180652 | T16182-CA01-P0UCB-180652 | CENTRAL CONTROL BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180653 | T16182-CA01-P0UCB-180653 | CENTRAL CONTROL BUILDING - 1ST FLOOR FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180654 | T16182-CA01-P0UCB-180654 | CENTRAL CONTROL BUILDING - 2ND FLOOR FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180655 | T16182-CA01-P0UCB-180655 | CENTRAL CONTROL BUILDING - ROOF FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180656 | T16182-CA01-P0UCB-180656 | CENTRAL CONTROL BUILDING - LINE FRAMING ELEVATION | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180657 | T16182-CA01-P0UCB-180657 | CENTRAL CONTROL BUILDING - ROW FRAMING ELEVATION | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180658 | T16182-CA01-P0UCB-180658 | CENTRAL CONTROL BUILDING - STAIRCASE#1 FRAMING PLAN & ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-20 | 2017-04-04
S&A(18) | Structural & Architectural | 180659 | T16182-CA01-P0UCB-180659 | CENTRAL CONTROL BUILDING - STAIRCASE#2 FRAMING PLAN & ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-20 | 2017-04-04
S&A(18) | Structural & Architectural | 180660 | T16182-CA01-P0UCB-180660 | CENTRAL CONTROL BUILDING - 1ST FLOOR OPENING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-20 | 2017-03-28
S&A(18) | Structural & Architectural | 180661 | T16182-CA01-P0UCB-180661 | CENTRAL CONTROL BUILDING - 2ND FLOOR OPENING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-20 | 2017-03-28
S&A(18) | Structural & Architectural | 180664 | T16182-CA02-P0UCB-180664 | CENTRAL CONTROL BUILDING - FOUNDATION RE - BAR DETAIL | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180665 | T16182-CA02-P0UCB-180665 | CENTRAL CONTROL BUILDING - COLUMN RE - BAR SCHEDULE | IFR | 2016-11-30 | 2017-01-24 |  | O |  |  | 2016-12-07 | 2017-02-09
S&A(18) | Structural & Architectural | 180666 | T16182-CA02-P0UCB-180666 | CENTRAL CONTROL BUILDING - BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-01-31 | 2017-02-28 |  | O |  |  | 2017-02-20 | 2017-03-14
S&A(18) | Structural & Architectural | 180667 | T16182-CA02-P0UCB-180667 | CENTRAL CONTROL BUILDING - SLAB & MISC. RE - BAR SCHEDULE | IFR | 2017-01-31 | 2017-02-28 |  | O |  |  | 2017-02-20 | 2017-03-14
S&A(18) | Structural & Architectural | 180668 | T16182-CA02-P0UCB-180668 | CENTRAL CONTROL BUILDING - STRUCTURAL MISC. DETAIL | IFR | 2017-01-31 | 2017-02-28 |  | O |  |  | 2017-02-20 | 2017-03-14
S&A(18) | Structural & Architectural | 180681 | T16182-CA05-P0UCB-180681 | CENTRAL CONTROL BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-02-09 | 2017-04-09 |  |  |  |  | 2017-02-09 | 2017-03-24
S&A(18) | Structural & Architectural | 180682 | T16182-CA05-P0UCB-180682 | CENTRAL CONTROL BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-02-09 | 2017-04-09 |  |  |  |  | 2017-02-09 | 2017-03-24
S&A(18) | Structural & Architectural | 180683 | T16182-CA05-P0UCB-180683 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09 |  |  |  |  | 2017-02-09 | 2017-03-24
S&A(18) | Structural & Architectural | 180684 | T16182-CA05-P0UCB-180684 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09 |  |  |  |  | 2017-02-09 | 2017-03-24
S&A(18) | Structural & Architectural | 180685 | T16182-CA05-P0UCB-180685 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09 |  |  |  |  | 2017-02-09 | 2017-03-24
S&A(18) | Structural & Architectural | 180686 | T16182-CA05-P0UCB-180686 | CENTRAL CONTROL BUILDING - ROOF PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09 |  |  |  |  | 2017-02-09 | 2017-03-24
S&A(18) | Structural & Architectural | 180687 | T16182-CA05-P0UCB-180687 | CENTRAL CONTROL BUILDING - ENLARGED TOILET & SHOWER PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09 |  |  |  |  | 2017-02-09 | 2017-03-24
S&A(18) | Structural & Architectural | 181000 | T16182-CA06-P0UBA-181000 | ST #1 LEB - CALCULATION | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-06-13
S&A(18) | Structural & Architectural | 181001 | T16182-CA00-P0UBA-181001 | ST #1 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-06-29
S&A(18) | Structural & Architectural | 181002 | T16182-CA00-P0UBA-181002 | ST #1 LEB - ROOF PLAN | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-05-17
S&A(18) | Structural & Architectural | 181003 | T16182-CA00-P0UBA-181003 | ST #1 LEB - SIDE WALL ELEVATION | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-06-13
S&A(18) | Structural & Architectural | 181004 | T16182-CA00-P0UBA-181004 | ST #1 LEB - MAIN SECTION | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-09-11
S&A(18) | Structural & Architectural | 181005 | T16182-CA00-P0UBA-181005 | ST #1 LEB - ARCHITECTURAL MISC. DETAIL | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-05-17
S&A(18) | Structural & Architectural | 181051 | T16182-CA01-P0UBA-181051 | ST #1 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-05-17
S&A(18) | Structural & Architectural | 181052 | T16182-CA01-P0UBA-181052 | ST #1 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-05-17
S&A(18) | Structural & Architectural | 181053 | T16182-CA01-P0UBA-181053 | ST #1 LEB - ROOF FLOOR FRAMING PLAN | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-05-17
S&A(18) | Structural & Architectural | 181054 | T16182-CA01-P0UBA-181054 | ST #1 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-06-29
S&A(18) | Structural & Architectural | 181055 | T16182-CA02-P0UBA-181055 | ST #1 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-05-17
S&A(18) | Structural & Architectural | 181056 | T16182-CA02-P0UBA-181056 | ST #1 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-04-01 | 2017-06-01 |  |  |  |  | 2017-04-03 | 2017-06-13
S&A(18) | Structural & Architectural | 181100 | T16182-CA06-P0UBA-181100 | ST #2 LEB - CALCULATION | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181101 | T16182-CA00-P0UBA-181101 | ST #2 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181102 | T16182-CA00-P0UBA-181102 | ST #2 LEB - ROOF PLAN | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181103 | T16182-CA00-P0UBA-181103 | ST #2 LEB - SIDE WALL ELEVATION | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181104 | T16182-CA00-P0UBA-181104 | ST #2 LEB - MAIN SECTION | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-09-11
S&A(18) | Structural & Architectural | 181105 | T16182-CA00-P0UBA-181105 | ST #2 LEB - ARCHITECTURAL MISC. DETAIL | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181151 | T16182-CA01-P0UBA-181151 | ST #2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181152 | T16182-CA01-P0UBA-181152 | ST #2 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181153 | T16182-CA01-P0UBA-181153 | ST #2 LEB - ROOF FLOOR FRAMING PLAN | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-07-04
S&A(18) | Structural & Architectural | 181154 | T16182-CA01-P0UBA-181154 | ST #2 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-07-04
S&A(18) | Structural & Architectural | 181155 | T16182-CA02-P0UBA-181155 | ST #2 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181156 | T16182-CA02-P0UBA-181156 | ST #2 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-05-01 | 2017-07-01 |  |  |  |  | 2017-04-28 | 2017-06-05
S&A(18) | Structural & Architectural | 181200 | T16182-CA06-P0UBA-181200 | GTG #1,2 LEB - CALCULATION | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181201 | T16182-CA00-P0UBA-181201 | GTG #1,2 LEB - BASEMENT FLOOR PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181202 | T16182-CA00-P0UBA-181202 | GTG #1,2 LEB - GROUND FLOOR PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181203 | T16182-CA00-P0UBA-181203 | GTG #1,2 LEB - ROOF PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181204 | T16182-CA00-P0UBA-181204 | GTG #1,2 LEB - SIDE WALL ELEVATION | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181205 | T16182-CA00-P0UBA-181205 | GTG #1,2 LEB - MAIN SECTION | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181206 | T16182-CA00-P0UBA-181206 | GTG #1,2 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | IFR | 2017-02-15 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-03-08
S&A(18) | Structural & Architectural | 181207 | T16182-CA00-P0UBA-181207 | GTG #1,2 LEB - STAIR PLAN & SECTION | IFR | 2017-02-15 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-03-08
S&A(18) | Structural & Architectural | 181208 | T16182-CA00-P0UBA-181208 | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | IFR | 2017-02-15 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-06-30
S&A(18) | Structural & Architectural | 181251 | T16182-CA01-P0UBA-181251 | GTG #1,2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181252 | T16182-CA01-P0UBA-181252 | GTG #1,2 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181253 | T16182-CA01-P0UBA-181253 | GTG #1,2 LEB - ROOF FRAMING PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181254 | T16182-CA01-P0UBA-181254 | GTG #1,2 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181255 | T16182-CA01-P0UBA-181255 | GTG #1,2 LEB - STAIR FRAMING PLAN & ELEVATION | IFR | 2017-02-15 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-03-08
S&A(18) | Structural & Architectural | 181256 | T16182-CA01-P0UBA-181256 | GTG #1,2 LEB - GROUND FLOOR OPENING PLAN | IFR | 2017-02-15 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-03-24
S&A(18) | Structural & Architectural | 181257 | T16182-CA02-P0UBA-181257 | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-03-24
S&A(18) | Structural & Architectural | 181258 | T16182-CA02-P0UBA-181258 | GTG #1,2 LEB - COLUMN RE - BAR SCHEDULE | IFR | 2016-12-15 | 2017-02-08 |  | O |  |  | 2016-12-15 | 2017-02-10
S&A(18) | Structural & Architectural | 181259 | T16182-CA02-P0UBA-181259 | GTG #1,2 LEB - BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-02-15 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-03-24
S&A(18) | Structural & Architectural | 181260 | T16182-CA02-P0UBA-181260 | GTG #1,2 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-02-15 | 2017-04-30 |  | O |  |  | 2017-02-16 | 2017-03-08
S&A(18) | Structural & Architectural | 181281 | T16182-CA05-P0UBA-181281 | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-01-28 | 2017-03-30 |  | O |  |  | 2017-02-03 | 2017-03-28
S&A(18) | Structural & Architectural | 181282 | T16182-CA05-P0UBA-181282 | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-01-28 | 2017-03-30 |  | O |  |  | 2017-02-03 | 2017-03-28
S&A(18) | Structural & Architectural | 181284 | T16182-CA05-P0UBA-181284 | GTG #1,2 LEB - GROUND FLOOR PLUMBING PLAN | IFR | 2017-01-28 | 2017-03-30 |  | O |  |  | 2017-02-03 | 2017-03-28
S&A(18) | Structural & Architectural | 181300 | T16182-CA06-P0UBA-181300 | GTG #3,4,5 LEB - CALCULATION | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-31
S&A(18) | Structural & Architectural | 181301 | T16182-CA00-P0UBA-181301 | GTG #3,4,5 LEB - BASEMENT FLOOR PLAN | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181302 | T16182-CA00-P0UBA-181302 | GTG #3,4,5 LEB - GROUND FLOOR PLAN | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181303 | T16182-CA00-P0UBA-181303 | GTG #3,4,5 LEB - ROOF PLAN | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181304 | T16182-CA00-P0UBA-181304 | GTG #3,4,5 LEB - SIDE WALL ELEVATION | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181305 | T16182-CA00-P0UBA-181305 | GTG #3,4,5 LEB - MAIN SECTION | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181306 | T16182-CA00-P0UBA-181306 | GTG #3,4,5 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | IFR | 2017-09-21 | 2017-11-21 |  |  |  |  | 2017-04-28 | 2017-06-20
S&A(18) | Structural & Architectural | 181307 | T16182-CA00-P0UBA-181307 | GTG #3,4,5 LEB - STAIR PLAN & SECTION | IFR | 2017-09-21 | 2017-11-21 |  |  |  |  | 2017-04-28 | 2017-06-08
S&A(18) | Structural & Architectural | 181351 | T16182-CA01-P0UBA-181351 | GTG #3,4,5 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181352 | T16182-CA01-P0UBA-181352 | GTG #3,4,5 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181353 | T16182-CA01-P0UBA-181353 | GTG #3,4,5 LEB - ROOF FRAMING PLAN | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181354 | T16182-CA01-P0UBA-181354 | GTG #3,4,5 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181355 | T16182-CA01-P0UBA-181355 | GTG #3,4,5 LEB - STAIR FRAMING PLAN & ELEVATION | IFR | 2017-04-28 | 2017-05-29 |  |  |  |  | 2017-04-28 | 2017-05-30
S&A(18) | Structural & Architectural | 181356 | T16182-CA01-P0UBA-181356 | GTG #3,4,5 LEB - GROUND FLOOR OPENING PLAN | IFR | 2017-04-28 | 2017-05-29 |  |  |  |  | 2017-04-28 | 2017-05-30
S&A(18) | Structural & Architectural | 181357 | T16182-CA02-P0UBA-181357 | GTG #3,4,5 LEB - FOUNDATION RE - BAR DETAIL | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181358 | T16182-CA02-P0UBA-181358 | GTG #3,4,5 LEB - COLUMN RE - BAR SCHEDULE | IFR | 2017-01-15 | 2017-03-15 |  |  |  |  | 2017-02-09 | 2017-03-10
S&A(18) | Structural & Architectural | 181359 | T16182-CA02-P0UBA-181359 | GTG #3,4,5 LEB - BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-04-28 | 2017-05-29 |  |  |  |  | 2017-04-28 | 2017-05-30
S&A(18) | Structural & Architectural | 181360 | T16182-CA02-P0UBA-181360 | GTG #3,4,5 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-04-28 | 2017-05-29 |  |  |  |  | 2017-04-28 | 2017-06-08
S&A(18) | Structural & Architectural | 181381 | T16182-CA05-P0UBA-181381 | GTG#3,4,5LEB - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-02-28 | 2017-03-31
S&A(18) | Structural & Architectural | 181382 | T16182-CA05-P0UBA-181382 | GTG#3,4,5LEB - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-02-28 | 2017-03-31
S&A(18) | Structural & Architectural | 181384 | T16182-CA05-P0UBA-181384 | GTG#3,4,5LEB - GROUND FLOOR PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-02-28 | 2017-03-31
S&A(18) | Structural & Architectural | 181800 | T16182-CA06-P0BAT-181800 | ROOF FOR STG TR - CALCULATION | IFR | 2017-09-08 | 2017-11-08 |  |  |  |  | 2017-08-31 | 2017-10-13
S&A(18) | Structural & Architectural | 181811 | T16182-CA00-P6BAT-181811 | ROOF FOR STG TR - PLAN, SECTION, ELEVATION | IFR | 2017-09-08 | 2017-11-08 |  |  |  |  | 2017-08-31 | 2017-10-13
S&A(18) | Structural & Architectural | 181812 | T16182-CA03-P6BAT-181812 | ROOF FOR STG TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | IFR | 2017-09-08 | 2017-11-08 |  |  |  |  | 2017-08-31 | 2017-10-13
S&A(18) | Structural & Architectural | 181813 | T16182-CA03-P6BAT-181813 | ROOF FOR STG TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | IFR | 2017-09-08 | 2017-11-08 |  |  |  |  | 2017-08-31 | 2017-10-13
S&A(18) | Structural & Architectural | 181900 | T16182-CA06-P0UGD-181900 | WATER TREATMENT BUILDING - CALCULATION | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181901 | T16182-CA00-P0UGD-181901 | WATER TREATMENT BUILDING - GROUND FLOOR PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-01-26 | 2017-02-28
S&A(18) | Structural & Architectural | 181902 | T16182-CA00-P0UGD-181902 | WATER TREATMENT BUILDING - 1ST FLOOR PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-01-26 | 2017-02-28
S&A(18) | Structural & Architectural | 181903 | T16182-CA00-P0UGD-181903 | WATER TREATMENT BUILDING - ROOF FLOOR PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-01-26 | 2017-02-28
S&A(18) | Structural & Architectural | 181904 | T16182-CA00-P0UGD-181904 | WATER TREATMENT BUILDING - ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-01-26 | 2017-02-28
S&A(18) | Structural & Architectural | 181905 | T16182-CA00-P0UGD-181905 | WATER TREATMENT BUILDING - SECTION | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-01-26 | 2017-02-28
S&A(18) | Structural & Architectural | 181906 | T16182-CA00-P0UGD-181906 | WATER TREATMENT BUILDING - INTERIOR FINISH & DOOR SCHEDULE | IFR | 2017-02-28 | 2017-04-30 |  | O |  |  | 2017-02-28 | 2017-04-04
S&A(18) | Structural & Architectural | 181908 | T16182-CA00-P0UGD-181908 | WATER TREATMENT BUILDING - WALL SECTION DETAIL | IFR | 2017-06-30 | 2017-08-31 |  | O |  |  | 2017-06-30 | 2017-09-21
S&A(18) | Structural & Architectural | 181909 | T16182-CA00-P0UGD-181909 | WATER TREATMENT BUILDING - TOILET ENLARGED PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O |  |  | 2017-06-30 | 2017-09-21
S&A(18) | Structural & Architectural | 181910 | T16182-CA00-P0UGD-181910 | WATER TREATMENT BUILDING - WALL OPENING PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O |  |  | 2017-06-30 | 2017-09-08
S&A(18) | Structural & Architectural | 181911 | T16182-CA00-P0UGD-181911 | WATER TREATMENT BUILDING - CEILING PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O |  |  | 2017-06-30 | 2017-09-08
S&A(18) | Structural & Architectural | 181912 | T16182-CA00-P0UGD-181912 | WATER TREATMENT BUILDING - STAIR ENLARGED PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O |  |  | 2017-06-30 | 2017-09-08
S&A(18) | Structural & Architectural | 181913 | T16182-CA00-P0UGD-181913 | WATER TREATMENT BUILDING - STAIR ENLARGED SECTION | IFR | 2017-06-30 | 2017-08-31 |  | O |  |  | 2017-06-30 | 2017-09-08
S&A(18) | Structural & Architectural | 181914 | T16182-CA00-P0UGD-181914 | WATER TREATMENT BUILDING - ARCHITECTURAL MISC. | IFR | 2017-06-30 | 2017-08-31 |  | O |  |  | 2017-06-30 | 2017-09-08
S&A(18) | Structural & Architectural | 181951 | T16182-CA01-P0UGD-181951 | WATER TREATMENT BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181952 | T16182-CA01-P0UGD-181952 | WATER TREATMENT BUILDING - GROUND FLOOR FRAMING | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181953 | T16182-CA01-P0UGD-181953 | WATER TREATMENT BUILDING - 1ST FLOOR FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181954 | T16182-CA01-P0UGD-181954 | WATER TREATMENT BUILDING - ROOF FLOOR FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181955 | T16182-CA01-P0UGD-181955 | WATER TREATMENT BUILDING - FRAMING ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181956 | T16182-CA01-P0UGD-181956 | WATER TREATMENT BUILDING - STAIR FRAMING PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-17 | 2017-05-23
S&A(18) | Structural & Architectural | 181957 | T16182-CA01-P0UGD-181957 | WATER TREATMENT BUILDING - STAIR FRAMING SECTION | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-17 | 2017-05-23
S&A(18) | Structural & Architectural | 181958 | T16182-CA02-P0UGD-181958 | WATER TREATMENT BUILDING - FOUNDATION REBAR DETAIL | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-04-04
S&A(18) | Structural & Architectural | 181959 | T16182-CA02-P0UGD-181959 | WATER TREATMENT BUILDING - COLUMN REBAR DETAIL | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-04-04
S&A(18) | Structural & Architectural | 181960 | T16182-CA02-P0UGD-181960 | WATER TREATMENT BUILDING - GIRDER & BEAM REBAR SCHEDULE | IFR | 2017-02-28 | 2017-04-30 |  | O |  |  | 2017-03-13 | 2017-04-04
S&A(18) | Structural & Architectural | 181961 | T16182-CA02-P0UGD-181961 | WATER TREATMENT BUILDING - SLAB REBAR DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-13 | 2017-04-04
S&A(18) | Structural & Architectural | 181962 | T16182-CA02-P0UGD-181962 | WATER TREATMENT BUILDING - EQUIPMENT FOUNDTAION ARRANGEMENT PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-04-04 | 2017-05-23
S&A(18) | Structural & Architectural | 181963 | T16182-CA02-P0UGD-181963 | WATER TREATMENT BUILDING - EMBEDDED PLATE & SLEEVE PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-04-04 | 2017-05-23
S&A(18) | Structural & Architectural | 181964 | T16182-CA02-P0UGD-181964 | WATER TREATMENT BUILDING - MISC. REBAR DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-04-04 | 2017-05-23
S&A(18) | Structural & Architectural | 181965 | T16182-CA03-P0UGD-181965 | WATER TREATMENT BUILDING - ROOF COLUMN LOCATION PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181966 | T16182-CA03-P0UGD-181966 | WATER TREATMENT BUILDING - ENLARGED ROOF FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O |  |  | 2017-02-06 | 2017-03-13
S&A(18) | Structural & Architectural | 181967 | T16182-CA03-P0UGD-181967 | WATER TREATMENT BUILDING - GIRT LINE & ROW ELEVATION | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-13 | 2017-04-04
S&A(18) | Structural & Architectural | 181968 | T16182-CA03-P0UGD-181968 | WATER TREATMENT BUILDING - STEEL CONNECTION DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-04-04 | 2017-05-23
S&A(18) | Structural & Architectural | 181981 | T16182-CA05-P0UGD-181981 | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-03-02 | 2017-06-05
S&A(18) | Structural & Architectural | 181982 | T16182-CA05-P0UGD-181982 | WATER TREATMENT BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-03-02 | 2017-06-02
S&A(18) | Structural & Architectural | 181983 | T16182-CA05-P0UGD-181983 | WATER TREATMENT BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-03-02 | 2017-06-02
S&A(18) | Structural & Architectural | 181984 | T16182-CA05-P0UGD-181984 | WATER TREATMENT BUILDING - 1ST FLOOR PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-03-02 | 2017-06-02
S&A(18) | Structural & Architectural | 181985 | T16182-CA05-P0UGD-181985 | WATER TREATMENT BUILDING - ROOF PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-03-02 | 2017-06-05
S&A(18) | Structural & Architectural | 181986 | T16182-CA05-P0UGD-181986 | WATER TREATMENT BUILDING - ENLARGED PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30 |  |  |  |  | 2017-03-02 | 2017-06-02
S&A(18) | Structural & Architectural | 182000 | T16182-CA06-P0UST-182000 | WORKSHOP & STORAGE BUILDING - CALCULATION | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182001 | T16182-CA00-P0UST-182001 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLAN | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-04-27 | 2017-05-19
S&A(18) | Structural & Architectural | 182002 | T16182-CA00-P0UST-182002 | WORKSHOP & STORAGE BUILDING - ROOF PLAN | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-04-27 | 2017-05-19
S&A(18) | Structural & Architectural | 182003 | T16182-CA00-P0UST-182003 | WORKSHOP & STORAGE BUILDING - ELEVATION | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-04-27 | 2017-05-19
S&A(18) | Structural & Architectural | 182004 | T16182-CA00-P0UST-182004 | WORKSHOP & STORAGE BUILDING - SECTION | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-04-27 | 2017-05-19
S&A(18) | Structural & Architectural | 182005 | T16182-CA00-P0UST-182005 | WORKSHOP & STORAGE BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | IFR | 2018-04-15 | 2018-06-15 |  |  |  |  | 2017-04-27 | 2017-07-28
S&A(18) | Structural & Architectural | 182006 | T16182-CA00-P0UST-182006 | WORKSHOP & STORAGE BUILDING - ENLARGED PLAN, CEILING PLAN | IFR | 2018-04-15 | 2018-06-15 |  |  |  |  | 2017-12-07 | 2018-01-25
S&A(18) | Structural & Architectural | 182051 | T16182-CA01-P0UST-182051 | WORKSHOP & STORAGE BUILDING - FOUNDATION PLAN | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182052 | T16182-CA01-P0UST-182052 | WORKSHOP & STORAGE BUILDING - COLUMN LOCATION PLAN | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182053 | T16182-CA01-P0UST-182053 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182054 | T16182-CA03-P0UST-182054 | WORKSHOP & STORAGE BUILDING - ROOF FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182055 | T16182-CA03-P0UST-182055 | WORKSHOP & STORAGE BUILDING - STEEL ROOF FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182056 | T16182-CA03-P0UST-182056 | WORKSHOP & STORAGE BUILDING - FRAMING ELEVATION | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182058 | T16182-CA02-P0UST-182058 | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182059 | T16182-CA02-P0UST-182059 | WORKSHOP & STORAGE BUILDING - RC COLUMN DETAIL | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182060 | T16182-CA02-P0UST-182060 | WORKSHOP & STORAGE BUILDING - SLAB DETAIL | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182061 | T16182-CA02-P0UST-182061 | WORKSHOP & STORAGE BUILDING - CRANE GIRDER & MISC. DETAIL | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182062 | T16182-CA03-P0UST-182062 | WORKSHOP & STORAGE BUILDING - STEEL COLUMN & BASE PLATE DETAIL | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182063 | T16182-CA03-P0UST-182063 | WORKSHOP & STORAGE BUILDING - CONNECTION DETAIL | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-05-26 | 2017-07-28
S&A(18) | Structural & Architectural | 182081 | T16182-CA05-P0UST-182081 | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-07-30 | 2017-10-15 |  |  |  |  | 2017-06-22 | 2017-09-08
S&A(18) | Structural & Architectural | 182082 | T16182-CA05-P0UST-182082 | WORKSHOP & STORAGE BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-07-30 | 2017-10-15 |  |  |  |  | 2017-06-22 | 2017-08-18
S&A(18) | Structural & Architectural | 182083 | T16182-CA05-P0UST-182083 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-07-30 | 2017-10-15 |  |  |  |  | 2017-06-22 | 2017-08-18
S&A(18) | Structural & Architectural | 182084 | T16182-CA05-P0UST-182084 | WORKSHOP & STORAGE BUILDING - ROOF PLUMBING PLAN | IFR | 2017-07-30 | 2017-10-15 |  |  |  |  | 2017-06-22 | 2017-08-18
S&A(18) | Structural & Architectural | 182085 | T16182-CA05-P0UST-182085 | WORKSHOP & STORAGE BUILDING - ENLARGED PLUMBING PLAN | IFR | 2017-07-30 | 2017-10-15 |  |  |  |  | 2017-06-22 | 2017-09-08
S&A(18) | Structural & Architectural | 182151 | T16182-CA01-P0ULA-182151 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION PLAN | IFR | 2016-12-15 | 2017-02-15 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 182152 | T16182-CA03-P0ULA-182152 | DEAERATOR SUPPORT STRUCTURE - COLUMN LOCATION PLAN | IFR | 2016-12-15 | 2017-02-15 |  |  |  |  | 2016-12-19 | 2017-05-10
S&A(18) | Structural & Architectural | 182153 | T16182-CA03-P0ULA-182153 | DEAERATOR SUPPORT STRUCTURE - GROUND FLOOR FRAMING PLAN | IFR | 2017-02-10 | 2017-07-10 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 182154 | T16182-CA03-P0ULA-182154 | DEAERATOR SUPPORT STRUCTURE - DEAERATOR FLOOR FRAMING PLAN | IFR | 2017-02-10 | 2017-04-10 |  |  |  |  | 2016-12-19 | 2017-05-10
S&A(18) | Structural & Architectural | 182155 | T16182-CA03-P0ULA-182155 | DEAERATOR SUPPORT STRUCTURE - FRAMING ELEVATION | IFR | 2017-02-10 | 2017-04-10 |  |  |  |  | 2016-12-19 | 2017-05-10
S&A(18) | Structural & Architectural | 182157 | T16182-CA03-P0ULA-182157 | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | IFR | 2016-12-15 | 2017-02-15 |  |  |  |  | 2016-12-19 | 2017-02-10
S&A(18) | Structural & Architectural | 182160 | T16182-CA03-P0ULA-182160 | DEAERATOR SUPPORT STRUCTURE - BASE PLATE DETAIL | IFR | 2017-02-10 | 2017-04-10 |  |  |  |  | 2017-02-15 | 2017-05-10
S&A(18) | Structural & Architectural | 182190 | T16182-CA06-P0ULA-182190 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION CALCULATION | IFR | 2016-12-15 | 2017-02-15 |  |  |  |  | 2016-12-19 | 2017-06-13
S&A(18) | Structural & Architectural | 182191 | T16182-CA06-P0ULA-182191 | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | IFR | 2017-02-10 | 2017-04-10 |  |  |  |  | 2017-02-15 | 2017-06-13
S&A(18) | Structural & Architectural | 182700 | T16182-CA06-P0USG-182700 | FIRE WATER PUMP HOUSE - CALCULATION | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182701 | T16182-CA00-P0USG-182701 | FIRE WATER PUMP HOUSE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182702 | T16182-CA00-P0USG-182702 | FIRE WATER PUMP HOUSE - ROOF PLAN | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182703 | T16182-CA00-P0USG-182703 | FIRE WATER PUMP HOUSE - ELEVATION | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182704 | T16182-CA00-P0USG-182704 | FIRE WATER PUMP HOUSE - MAIN SECTION | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182751 | T16182-CA01-P0USG-182751 | FIRE WATER PUMP HOUSE - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182752 | T16182-CA01-P0USG-182752 | FIRE WATER PUMP HOUSE - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182753 | T16182-CA01-P0USG-182753 | FIRE WATER PUMP HOUSE - FRAMING ELEVATION | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182754 | T16182-CA02-P0USG-182754 | FIRE WATER PUMP HOUSE - FOUNDATION REBAR SCHEDULE, SLAB REBAR DETAIL | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-05
S&A(18) | Structural & Architectural | 182755 | T16182-CA02-P0USG-182755 | FIRE WATER PUMP HOUSE - COLUMN, GIRDER, BEAM SHEDULE | IFR | 2017-04-01 | 2017-06-02 |  | O |  |  | 2017-04-03 | 2017-06-07
S&A(18) | Structural & Architectural | 182800 | T16182-CA06-P0UTF-182800 | AIR COMPRESSOR SHELTER - CALCULATION SHEET | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182801 | T16182-CA00-P0UTF-182801 | AIR COMPRESSOR SHELTER - GROUND FLOOR PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182802 | T16182-CA00-P0UTF-182802 | AIR COMPRESSOR SHELTER - ROOF PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182803 | T16182-CA00-P0UTF-182803 | AIR COMPRESSOR SHELTER - SIDE ELEVATION | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-12
S&A(18) | Structural & Architectural | 182804 | T16182-CA00-P0UTF-182804 | AIR COMPRESSOR SHELTER - MAIN SECTION | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-12
S&A(18) | Structural & Architectural | 182851 | T16182-CA01-P0UTF-182851 | AIR COMPRESSOR SHELTER - FOUNDATION ARRANGEMENT PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182852 | T16182-CA01-P0UTF-182852 | AIR COMPRESSOR SHELTER - COLUMN ARRANGEMENT PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-12
S&A(18) | Structural & Architectural | 182853 | T16182-CA01-P0UTF-182853 | AIR COMPRESSOR SHELTER - GROUND FLOOR FRAMING PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182854 | T16182-CA01-P0UTF-182854 | AIR COMPRESSOR SHELTER - ROOF FRAMING PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182855 | T16182-CA01-P0UTF-182855 | AIR COMPRESSOR SHELTER - LINE FRAMING ELEVATION | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182856 | T16182-CA01-P0UTF-182856 | AIR COMPRESSOR SHELTER - ROW FRAMING ELEVATION | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182857 | T16182-CA02-P0UTF-182857 | AIR COMPRESSOR SHELTER - REBAR DETAIL | IFR | 2017-04-15 | 2017-06-15 |  | O |  |  | 2017-04-27 | 2017-06-01
S&A(18) | Structural & Architectural | 182900 | T16182-CA06-P0UYC-182900 | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182901 | T16182-CA00-P0UYC-182901 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLAN | IFR | 2017-05-20 | 2017-08-20 |  |  |  |  | 2017-04-07 | 2017-08-29
S&A(18) | Structural & Architectural | 182902 | T16182-CA00-P0UYC-182902 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | IFR | 2017-05-20 | 2017-08-20 |  |  |  |  | 2017-04-07 | 2017-07-06
S&A(18) | Structural & Architectural | 182903 | T16182-CA00-P0UYC-182903 | ADMINISTRATION & SOCIAL BUILDING - SIDE ELEVATION | IFR | 2017-05-20 | 2017-08-20 |  |  |  |  | 2017-04-07 | 2017-08-08
S&A(18) | Structural & Architectural | 182904 | T16182-CA00-P0UYC-182904 | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | IFR | 2017-05-20 | 2017-08-20 |  |  |  |  | 2017-04-07 | 2017-07-06
S&A(18) | Structural & Architectural | 182905 | T16182-CA00-P0UYC-182905 | ADMINISTRATION & SOCIAL BUILDING - INTERIOR FINISH & DOOR / WINDOW SCHEDULE | IFR | 2017-05-20 | 2017-08-20 |  |  |  |  | 2017-04-07 | 2017-08-08
S&A(18) | Structural & Architectural | 182906 | T16182-CA00-P0UYC-182906 | ADMINISTRATION & SOCIAL BUILDING - WALL SECTION | IFR | 2018-04-15 | 2018-06-15 |  |  |  |  | 2017-04-07 | 2017-08-08
S&A(18) | Structural & Architectural | 182907 | T16182-CA00-P0UYC-182907 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED REST ROOM PLAN & ELEVATION | IFR | 2018-04-15 | 2018-06-15 |  |  |  |  | 2017-09-22 | 2017-11-06
S&A(18) | Structural & Architectural | 182908 | T16182-CA00-P0UYC-182908 | ADMINISTRATION & SOCIAL BUILDING - CEILING PLAN | IFR | 2018-04-15 | 2018-06-15 |  |  |  |  | 2017-09-22 | 2017-11-06
S&A(18) | Structural & Architectural | 182951 | T16182-CA01-P0UYC-182951 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182952 | T16182-CA01-P0UYC-182952 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182953 | T16182-CA01-P0UYC-182953 | ADMINISTRATION & SOCIAL BUILDING - ROOF FRAMING PLAN | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182954 | T16182-CA01-P0UYC-182954 | ADMINISTRATION & SOCIAL BUILDING - LINE FRAMING ELEVATION | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182955 | T16182-CA01-P0UYC-182955 | ADMINISTRATION & SOCIAL BUILDING - ROW FRAMING ELEVATION | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182956 | T16182-CA01-P0UYC-182956 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN REBAR DETAIL | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182957 | T16182-CA02-P0UYC-182957 | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182958 | T16182-CA02-P0UYC-182958 | ADMINISTRATION & SOCIAL BUILDING - SLAB & MISC REBAR DETAIL | IFR | 2017-06-20 | 2017-08-20 |  |  |  |  | 2017-04-28 | 2017-07-06
S&A(18) | Structural & Architectural | 182981 | T16182-CA05-P0UYC-182981 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-06-20 | 2017-09-20 |  |  |  |  | 2017-06-15 | 2017-07-17
S&A(18) | Structural & Architectural | 182982 | T16182-CA05-P0UYC-182982 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-06-20 | 2017-09-20 |  |  |  |  | 2017-06-15 | 2017-07-17
S&A(18) | Structural & Architectural | 182983 | T16182-CA05-P0UYC-182983 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-06-20 | 2017-09-20 |  |  |  |  | 2017-06-15 | 2017-07-17
S&A(18) | Structural & Architectural | 182984 | T16182-CA05-P0UYC-182984 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLUMBING PLAN | IFR | 2017-06-20 | 2017-09-20 |  |  |  |  | 2017-06-15 | 2017-07-17
S&A(18) | Structural & Architectural | 182985 | T16182-CA05-P0UYC-182985 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED PLUMBING PLAN | IFR | 2017-06-20 | 2017-09-20 |  |  |  |  | 2017-06-15 | 2017-09-13
S&A(18) | Structural & Architectural | 183100 | T16182-CA06-P0UYA-183100 | SECURITY BUILDING - CALCULATION | IFR | 2018-05-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183101 | T16182-CA00-P0UYA-183101 | SECURITY BUILDING - GROUND FLOOR PLAN | IFR | 2018-04-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183102 | T16182-CA00-P0UYA-183102 | SECURITY BUILDING - ROOF PLAN | IFR | 2018-04-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183103 | T16182-CA00-P0UYA-183103 | SECURITY BUILDING - SIDE WALL ELEVATION | IFR | 2018-04-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183104 | T16182-CA00-P0UYA-183104 | SECURITY BUILDING - MAIN SECTION | IFR | 2018-04-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183105 | T16182-CA00-P0UYA-183105 | SECURITY BUILDING - INTERIOR FINISH SCHEDULE | IFR | 2018-10-01 | 2018-12-01 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183151 | T16182-CA01-P0UYA-183151 | SECURITY BUILDING - FOUNDATION & COLUMN LOCATION PLAN | IFR | 2018-05-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183152 | T16182-CA01-P0UYA-183152 | SECURITY BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2018-05-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183153 | T16182-CA01-P0UYA-183153 | SECURITY BUILDING - ROOF FLOOR FRAMING PLAN | IFR | 2018-05-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183154 | T16182-CA01-P0UYA-183154 | SECURITY BUILDING - FRAMING ELEVATION | IFR | 2018-05-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183155 | T16182-CA02-P0UYA-183155 | SECURITY BUILDING - RE - BAR DETAIL | IFR | 2018-05-18 | 2018-07-18 |  |  |  |  | 2018-01-05 | 2018-04-13
S&A(18) | Structural & Architectural | 183181 | T16182-CA05-P0UYA-183181 | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2018-06-18 | 2018-09-18 |  |  |  |  | 2018-04-06 | 2018-04-27
S&A(18) | Structural & Architectural | 183182 | T16182-CA05-P0UYA-183182 | SECURITY BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2018-06-18 | 2018-09-18 |  |  |  |  | 2018-04-06 | 2018-04-27
S&A(18) | Structural & Architectural | 183183 | T16182-CA05-P0UYA-183183 | SECURITY BUILDING - PLUMBING PLAN | IFR | 2018-06-18 | 2018-09-18 |  |  |  |  | 2018-04-06 | 2018-04-27
S&A(18) | Structural & Architectural | 183200 | T16182-CA06-P0UYP-183200 | FIRE BRIGADE - CALCULATION | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-18
S&A(18) | Structural & Architectural | 183201 | T16182-CA00-P0UYP-183201 | FIRE BRIGADE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-06-08 | 2017-09-18
S&A(18) | Structural & Architectural | 183202 | T16182-CA00-P0UYP-183202 | FIRE BRIGADE - ROOF PLAN | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-06-08 | 2017-09-18
S&A(18) | Structural & Architectural | 183203 | T16182-CA00-P0UYP-183203 | FIRE BRIGADE - ELEVATION | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-06-08 | 2017-09-18
S&A(18) | Structural & Architectural | 183204 | T16182-CA00-P0UYP-183204 | FIRE BRIGADE - MAIN SECTION | IFR | 2017-06-15 | 2017-09-15 |  |  |  |  | 2017-06-08 | 2017-09-18
S&A(18) | Structural & Architectural | 183205 | T16182-CA00-P0UYP-183205 | FIRE BRIGADE - ENLARGED PLAN, CEILING PLAN | IFR | 2018-03-15 | 2018-05-15 |  |  |  |  | 2018-02-05 | 2018-03-22
S&A(18) | Structural & Architectural | 183251 | T16182-CA01-P0UYP-183251 | FIRE BRIGADE - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-05
S&A(18) | Structural & Architectural | 183252 | T16182-CA01-P0UYP-183252 | FIRE BRIGADE - GROUND FLOOR FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-05
S&A(18) | Structural & Architectural | 183253 | T16182-CA01-P0UYP-183253 | FIRE BRIGADE - ROOF FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-05
S&A(18) | Structural & Architectural | 183254 | T16182-CA01-P0UYP-183254 | FIRE BRIGADE - FRAMING ELEVATION | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-05
S&A(18) | Structural & Architectural | 183255 | T16182-CA01-P0UYP-183255 | FIRE BRIGADE - MISC. STRUCTURAL DETAIL | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-05
S&A(18) | Structural & Architectural | 183256 | T16182-CA02-P0UYP-183256 | FIRE BRIGADE - FOUNDATION, SLAB REBAR SCHEDULE | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-05
S&A(18) | Structural & Architectural | 183257 | T16182-CA02-P0UYP-183257 | FIRE BRIGADE - COLUMN, GIRDER, BEAM SHEDULE | IFR | 2017-07-15 | 2017-09-15 |  |  |  |  | 2017-07-14 | 2017-09-05
S&A(18) | Structural & Architectural | 183281 | T16182-CA05-P0UYP-183281 | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-08 | 2017-12-07
S&A(18) | Structural & Architectural | 183282 | T16182-CA05-P0UYP-183282 | FIRE BRIGADE - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-08 | 2017-12-07
S&A(18) | Structural & Architectural | 183283 | T16182-CA05-P0UYP-183283 | FIRE BRIGADE - GROUND FLOOR PLUMBING PLAN | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-08 | 2017-12-07
S&A(18) | Structural & Architectural | 183284 | T16182-CA05-P0UYP-183284 | FIRE BRIGADE - ROOF PLUMBING PLAN | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-08 | 2017-12-07
S&A(18) | Structural & Architectural | 183285 | T16182-CA05-P0UYP-183285 | FIRE BRIGADE - ENLARGED PLUMBING PLAN | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-08 | 2017-12-07
S&A(18) | Structural & Architectural | 183300 | T16182-CA06-P0UYE-183300 | MAIN GATE HOUSE - CALCULATION | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-24 | 2018-01-22
S&A(18) | Structural & Architectural | 183301 | T16182-CA00-P0UYE-183301 | MAIN GATE HOUSE - GROUND FLOOR , ROOF PLAN, INTERIOR FINISH, DOOR & WINDOW SCHEDULES | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-09-13 | 2017-11-24
S&A(18) | Structural & Architectural | 183302 | T16182-CA00-P0UYE-183302 | MAIN GATE HOUSE - ELEVATIONS | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-09-13 | 2017-11-24
S&A(18) | Structural & Architectural | 183303 | T16182-CA00-P0UYE-183303 | MAIN GATE HOUSE - SECTIONS & DETAILS | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-09-13 | 2017-11-24
S&A(18) | Structural & Architectural | 183351 | T16182-CA01-P0UYE-183351 | MAIN GATE HOUSE - FOUNDATION ARRANGEMENT, GROUND FLOOR FRAMING PLAN | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-24 | 2018-01-22
S&A(18) | Structural & Architectural | 183352 | T16182-CA01-P0UYE-183352 | MAIN GATE HOUSE - ROOF FRAMING PLAN | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-24 | 2018-01-22
S&A(18) | Structural & Architectural | 183353 | T16182-CA01-P0UYE-183353 | MAIN GATE HOUSE - FRAMING ELEVATION | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-24 | 2018-01-22
S&A(18) | Structural & Architectural | 183354 | T16182-CA02-P0UYE-183354 | MAIN GATE HOUSE - COLUMN, GIRDER & BEAM RE - BAR DETAIL | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-24 | 2018-01-22
S&A(18) | Structural & Architectural | 183355 | T16182-CA02-P0UYE-183355 | MAIN GATE HOUSE - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-24 | 2018-01-22
S&A(18) | Structural & Architectural | 183361 | T16182-CA00-P0UTX-183361 | MAIN GATE HOUSE SUNSHADE - GROUND FLOOR, ROOF PLAN & ELEVATION | IFR | 2018-04-25 | 2018-06-25 |  |  |  |  | 2017-12-22 | 2018-03-29
S&A(18) | Structural & Architectural | 183371 | T16182-CA03-P0UTX-183371 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (TOP CHORD) | IFR | 2018-04-25 | 2018-06-25 |  |  |  |  | 2017-12-22 | 2018-03-29
S&A(18) | Structural & Architectural | 183372 | T16182-CA03-P0UTX-183372 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (BOTTOM CHORD) | IFR | 2018-04-25 | 2018-06-25 |  |  |  |  | 2017-12-22 | 2018-03-29
S&A(18) | Structural & Architectural | 183373 | T16182-CA03-P0UTX-183373 | MAIN GATE HOUSE SUNSHADE - FRAMING ELEVATION | IFR | 2018-04-25 | 2018-06-25 |  |  |  |  | 2017-12-22 | 2018-03-29
S&A(18) | Structural & Architectural | 183375 | T16182-CA03-P0UTX-183375 | MAIN GATE HOUSE SUNSHADE - BASE PLATE & CONNECTION DETAIL | IFR | 2018-04-25 | 2018-06-25 |  |  |  |  | 2017-12-22 | 2018-03-29
S&A(18) | Structural & Architectural | 183377 | T16182-CA02-P0UTX-183377 | MAIN GATE HOUSE SUNSHADE - FOUNDATION RE - BAR DETAIL | IFR | 2018-04-25 | 2018-06-25 |  |  |  |  | 2017-12-22 | 2018-03-29
S&A(18) | Structural & Architectural | 183390 | T16182-CA06-P0UTX-183390 | MAIN GATE HOUSE SUNSHADE - CALCULATION | IFR | 2018-04-25 | 2018-06-25 |  |  |  |  | 2017-12-22 | 2018-03-29
S&A(18) | Structural & Architectural | 183500 | T16182-CA06-P0UYB-183500 | SUPPORT BUILDING - CALCULATION | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-23 | 2018-01-29
S&A(18) | Structural & Architectural | 183501 | T16182-CA00-P0UYB-183501 | SUPPORT BUILDING - GROUND FLOOR PLAN, ROOF PLAN, ELEVATIONS & MAIN SECTION | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-23 | 2018-01-29
S&A(18) | Structural & Architectural | 183502 | T16182-CA00-P0UYB-183502 | SUPPORT BUILDING - TOILET PLAN & ELEVATION | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-23 | 2018-01-29
S&A(18) | Structural & Architectural | 183551 | T16182-CA01-P0UYB-183551 | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-23 | 2018-01-29
S&A(18) | Structural & Architectural | 183552 | T16182-CA01-P0UYB-183552 | SUPPORT BUILDING - FRAMING ELEVATIONS | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-23 | 2018-01-29
S&A(18) | Structural & Architectural | 183553 | T16182-CA02-P0UYB-183553 | SUPPORT BUILDING - COLUMN, GIRDER & BEAM RE - BAR DETAIL | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-23 | 2018-01-29
S&A(18) | Structural & Architectural | 183554 | T16182-CA02-P0UYB-183554 | SUPPORT BUILDING - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | IFR | 2018-01-15 | 2018-03-15 |  |  |  |  | 2017-11-23 | 2018-01-29
S&A(18) | Structural & Architectural | 183581 | T16182-CA05-P0UYB-183581 | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | IFR | 2018-02-01 | 2018-03-30 |  |  |  |  | 2018-01-29 | 2018-04-11
S&A(18) | Structural & Architectural | 183582 | T16182-CA05-P0UYB-183582 | SUPPORT BUILDING - PLUMBING PLAN | IFR | 2018-02-01 | 2018-03-30 |  |  |  |  | 2018-01-29 | 2018-04-11
S&A(18) | Structural & Architectural | 183600 | T16182-CA06-P0UYF-183600 | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-03-16 | 2018-05-25
S&A(18) | Structural & Architectural | 183601 | T16182-CA00-P0UYF-183601 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR PLAN | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183602 | T16182-CA00-P0UYF-183602 | SEARCH FACILITY & VISITORS CENTRE - ROOF PLAN | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183603 | T16182-CA00-P0UYF-183603 | SEARCH FACILITY & VISITORS CENTRE - ELEVATION | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183604 | T16182-CA00-P0UYF-183604 | SEARCH FACILITY & VISITORS CENTRE - MAIN SECTION | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183651 | T16182-CA01-P0UYF-183651 | SEARCH FACILITY & VISITORS CENTRE - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183652 | T16182-CA01-P0UYF-183652 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR & ROOF FRAMING PLAN | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183653 | T16182-CA01-P0UYF-183653 | SEARCH FACILITY & VISITORS CENTRE - FRAMING ELEVATION | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183654 | T16182-CA02-P0UYF-183654 | SEARCH FACILITY & VISITORS CENTRE - REBAR SCHEDULE & DETAIL | IFR | 2018-04-01 | 2018-06-01 |  |  |  |  | 2018-01-29 | 2018-03-16
S&A(18) | Structural & Architectural | 183681 | T16182-CA05-P0UYF-183681 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | IFR | 2018-04-15 | 2018-06-15 |  |  |  |  | 2018-03-27 | 2018-04-16
S&A(18) | Structural & Architectural | 183682 | T16182-CA05-P0UYF-183682 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING PLAN | IFR | 2018-04-15 | 2018-06-15 |  |  |  |  | 2018-03-27 | 2018-04-16
S&A(18) | Structural & Architectural | 183900 | T16182-CA06-P0ULD-183900 | CPP & CPP REGEN BUILDING - CALCULATION | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-18
S&A(18) | Structural & Architectural | 183902 | T16182-CA00-P0ULD-183902 | CPP & CPP REGEN BUILDING - GROUND FLOOR PLAN | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-23
S&A(18) | Structural & Architectural | 183903 | T16182-CA00-P0ULD-183903 | CPP & CPP REGEN BUILDING - ROOF FLOOR PLAN | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183904 | T16182-CA00-P0ULD-183904 | CPP & CPP REGEN BUILDING - ELEVATION | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-23
S&A(18) | Structural & Architectural | 183905 | T16182-CA00-P0ULD-183905 | CPP & CPP REGEN BUILDING - SECTION | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183906 | T16182-CA00-P0ULD-183906 | CPP & CPP REGEN BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183908 | T16182-CA00-P0ULD-183908 | CPP & CPP REGEN BUILDING - WALL SECTION DETAIL | IFR | 2018-04-30 | 2018-06-28 |  |  |  |  | 2017-08-11 | 2017-09-05
S&A(18) | Structural & Architectural | 183909 | T16182-CA00-P0ULD-183909 | CPP & CPP REGEN BUILDING - WALL OPENING PLAN | IFR | 2018-04-30 | 2018-06-28 |  |  |  |  | 2017-11-01 | 2017-11-24
S&A(18) | Structural & Architectural | 183910 | T16182-CA00-P0ULD-183910 | CPP & CPP REGEN BUILDING - ARCHITECTURAL MISC. DETAIL | IFR | 2018-04-30 | 2018-06-28 |  |  |  |  | 2017-08-11 | 2017-09-05
S&A(18) | Structural & Architectural | 183951 | T16182-CA01-P0ULD-183951 | CPP & CPP REGEN BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-05-26 | 2017-08-14
S&A(18) | Structural & Architectural | 183952 | T16182-CA01-P0ULD-183952 | CPP & CPP REGEN BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183953 | T16182-CA01-P0ULD-183953 | CPP & CPP REGEN BUILDING - ROOF FLOOR FRAMING PLAN | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183954 | T16182-CA01-P0ULD-183954 | CPP & CPP REGEN BUILDING - FRAMING ELEVATION | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-23
S&A(18) | Structural & Architectural | 183955 | T16182-CA02-P0ULD-183955 | CPP & CPP REGEN BUILDING - FOUNDATION REBAR DETAIL | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-05-26 | 2017-06-21
S&A(18) | Structural & Architectural | 183956 | T16182-CA02-P0ULD-183956 | CPP & CPP REGEN BUILDING - COLUMN REBAR DETAIL | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183957 | T16182-CA02-P0ULD-183957 | CPP & CPP REGEN BUILDING - GIRDER & BEAM REBAR SCHEDULE | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183958 | T16182-CA02-P0ULD-183958 | CPP & CPP REGEN BUILDING - SLAB REBAR DETAIL | IFR | 2017-05-15 | 2017-07-15 |  |  |  |  | 2017-07-27 | 2017-08-14
S&A(18) | Structural & Architectural | 183959 | T16182-CA02-P0ULD-183959 | CPP & CPP REGEN BUILDING - EQUIPMENT FOUNDTAION REBAR DETAIL | IFR | 2017-06-14 | 2017-08-14 |  |  |  |  | 2017-08-11 | 2017-08-23
S&A(18) | Structural & Architectural | 183960 | T16182-CA02-P0ULD-183960 | CPP & CPP REGEN BUILDING - EMBEDDED PLATE & SLEEVE PLAN | IFR | 2017-06-14 | 2017-08-14 |  |  |  |  | 2017-08-11 | 2017-08-23
S&A(18) | Structural & Architectural | 183961 | T16182-CA02-P0ULD-183961 | CPP & CPP REGEN BUILDING - MISC. REBAR DETAIL | IFR | 2017-06-14 | 2017-08-14 |  |  |  |  | 2017-08-11 | 2017-08-23
S&A(18) | Structural & Architectural | 183962 | T16182-CA03-P0ULD-183962 | CPP & CPP REGEN BUILDING - ROOF COLUMN LOCATION PLAN | IFR | 2017-06-14 | 2017-08-14 |  |  |  |  | 2017-08-11 | 2017-08-23
S&A(18) | Structural & Architectural | 183963 | T16182-CA03-P0ULD-183963 | CPP & CPP REGEN BUILDING - ENLARGED ROOF FRAMING PLAN | IFR | 2017-06-14 | 2017-08-14 |  |  |  |  | 2017-08-11 | 2017-09-05
S&A(18) | Structural & Architectural | 183964 | T16182-CA03-P0ULD-183964 | CPP & CPP REGEN BUILDING - GIRT LINE & ROW ELEVATION | IFR | 2017-06-14 | 2017-08-14 |  |  |  |  | 2017-08-11 | 2017-09-05
S&A(18) | Structural & Architectural | 183965 | T16182-CA03-P0ULD-183965 | CPP & CPP REGEN BUILDING - STEEL CONNECTION DETAIL | IFR | 2017-06-14 | 2017-08-14 |  |  |  |  | 2017-08-11 | 2017-08-23
S&A(18) | Structural & Architectural | 184700 | T16182-CA06-P0USR-184700 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | IFR | 2017-03-15 | 2017-05-15 |  | O |  |  | 2017-03-16 | 2017-05-18
S&A(18) | Structural & Architectural | 184701 | T16182-CA00-P0USR-184701 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - GROUND & ROOF FLOOR PLAN | IFR | 2017-03-15 | 2017-05-15 |  | O |  |  | 2017-03-16 | 2017-05-18
S&A(18) | Structural & Architectural | 184702 | T16182-CA00-P0USR-184702 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - ELEVATIONS & SECTIONS | IFR | 2017-03-15 | 2017-05-15 |  | O |  |  | 2017-03-16 | 2017-05-18
S&A(18) | Structural & Architectural | 184751 | T16182-CA03-P0USR-184751 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL COLUMN LOCATION & ROOF PLAN | IFR | 2017-03-15 | 2017-05-15 |  | O |  |  | 2017-03-16 | 2017-05-18
S&A(18) | Structural & Architectural | 184752 | T16182-CA03-P0USR-184752 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL FRAMING ELEVATIONS | IFR | 2017-03-15 | 2017-05-15 |  | O |  |  | 2017-03-16 | 2017-05-18
S&A(18) | Structural & Architectural | 184800 | T16182-CA06-P0QJA-184800 | N2 STORAGE SHELTER - CALCULATION | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184801 | T16182-CA00-P0QJA-184801 | N2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184802 | T16182-CA00-P0QJA-184802 | N2 STORAGE SHELTER - ELEVATION | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184803 | T16182-CA00-P0QJA-184803 | N2 STORAGE SHELTER - MAIN SECTION | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184851 | T16182-CA01-P0QJA-184851 | N2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184852 | T16182-CA01-P0QJA-184852 | N2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184853 | T16182-CA01-P0QJA-184853 | N2 STORAGE SHELTER - FRAMING ELEVATION | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184854 | T16182-CA02-P0QJA-184854 | N2 STORAGE SHELTER - REBAR DETAIL | IFR | 2017-03-25 | 2017-05-25 |  |  |  |  | 2017-03-24 | 2017-04-19
S&A(18) | Structural & Architectural | 184900 | T16182-CA06-P0UTG-184900 | H2, CO2 STORAGE SHELTER - CALCULATION | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 184901 | T16182-CA00-P0UTG-184901 | H2, CO2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 184902 | T16182-CA00-P0UTG-184902 | H2, CO2 STORAGE SHELTER - ELEVATION | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 184903 | T16182-CA00-P0UTG-184903 | H2, CO2 STORAGE SHELTER - MAIN SECTION | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 184951 | T16182-CA01-P0UTG-184951 | H2, CO2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 184952 | T16182-CA01-P0UTG-184952 | H2, CO2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 184953 | T16182-CA01-P0UTG-184953 | H2, CO2 STORAGE SHELTER - FRAMING ELEVATION | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 184954 | T16182-CA02-P0UTG-184954 | H2, CO2 STORAGE SHELTER - REBAR DETAIL | IFR | 2017-07-31 | 2017-09-30 |  |  |  |  | 2017-07-04 | 2017-08-22
S&A(18) | Structural & Architectural | 185151 | T16182-CA03-P0UMY-185151 | PIPE RACK #1 - FOUNDATION PLAN | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-06-14 | 2017-09-06
S&A(18) | Structural & Architectural | 185152 | T16182-CA03-P0UMY-185152 | PIPE RACK #1 - COLUMN LOCATION PLAN & BASE PLATE DETAIL | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-06-14 | 2017-09-06
S&A(18) | Structural & Architectural | 185153 | T16182-CA03-P0UMY-185153 | PIPE RACK #1 - FRAMING PLAN | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-06-14 | 2017-09-06
S&A(18) | Structural & Architectural | 185154 | T16182-CA03-P0UMY-185154 | PIPE RACK #1 - ELEVATION | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-06-14 | 2017-09-06
S&A(18) | Structural & Architectural | 185155 | T16182-CA03-P0UMY-185155 | PIPE RACK #1 - FOUNDATION & PEDETAL DETAIL | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-06-14 | 2017-09-06
S&A(18) | Structural & Architectural | 185160 | T16182-CA03-P0UMY-185160 | PIPE RACK #2 - FOUNDATION PLAN | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185161 | T16182-CA03-P0UMY-185161 | PIPE RACK #2 - COLUMN LOCATION PLAN | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185162 | T16182-CA03-P0UMY-185162 | PIPE RACK #2 - FRAMING PLAN - 1 | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185163 | T16182-CA03-P0UMY-185163 | PIPE RACK #2 - FRAMING PLAN - 2 | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185164 | T16182-CA03-P0UMY-185164 | PIPE RACK #2 - LINE ELEVATION | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185165 | T16182-CA03-P0UMY-185165 | PIPE RACK #2 - ROW ELEVATION | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185166 | T16182-CA03-P0UMY-185166 | PIPE RACK #2 - FOUNDATION DETAIL | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185167 | T16182-CA03-P0UMY-185167 | PIPE RACK #2 - PEDETAL DETAIL | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185168 | T16182-CA03-P0UMY-185168 | PIPE RACK #2 - BASE PLATE DETAIL | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-07-21
S&A(18) | Structural & Architectural | 185169 | T16182-CA03-P0UMY-185169 | PIPE RACK #3 - FOUNDATION PLAN | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185170 | T16182-CA03-P0UMY-185170 | PIPE RACK #3 - COLUMN LOCATION PLAN | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185171 | T16182-CA03-P0UMY-185171 | PIPE RACK #3 - FRAMING PLAN - 1 | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185172 | T16182-CA03-P0UMY-185172 | PIPE RACK #3 - FRAMING PLAN - 2 | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185173 | T16182-CA03-P0UMY-185173 | PIPE RACK #3 - LINE ELEVATION | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185174 | T16182-CA03-P0UMY-185174 | PIPE RACK #3 - ROW SECTION | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185175 | T16182-CA03-P0UMY-185175 | PIPE RACK #3 - FOUNDATION DETAIL | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185176 | T16182-CA03-P0UMY-185176 | PIPE RACK #3 - PEDETAL & TIE GIRDER DETAIL | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185177 | T16182-CA03-P0UMY-185177 | PIPE RACK #3 - BASE PLATE DETAIL | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185178 | T16182-CA03-P0UMY-185178 | PIPE RACK - MISC DETAIL | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-07-21
S&A(18) | Structural & Architectural | 185190 | T16182-CA06-P0UMY-185190 | PIPE RACK #1 - CALCULATION | IFR | 2017-06-01 | 2017-08-01 |  | O |  |  | 2017-06-14 | 2017-09-06
S&A(18) | Structural & Architectural | 185191 | T16182-CA06-P0UMY-185191 | PIPE RACK #2 - CALCULATION | IFR | 2017-05-02 | 2017-07-02 |  |  |  |  | 2017-05-02 | 2017-06-27
S&A(18) | Structural & Architectural | 185192 | T16182-CA06-P0UMY-185192 | PIPE RACK #3 - CALCULATION | IFR | 2017-08-25 | 2017-10-25 |  |  |  |  | 2017-08-31 | 2017-12-15
S&A(18) | Structural & Architectural | 185701 | T16182-CA00-P0GEN-185701 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-22 | 2017-10-31
S&A(18) | Structural & Architectural | 185751 | T16182-CA01-P0GEN-185751 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR FRAMING PLAN | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-22 | 2017-10-31
S&A(18) | Structural & Architectural | 185800 | T16182-CA06-P0GEN-185800 | CHEMICAL DOSING SHELTER FOR STG & HRSG - CALCULATION | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 185801 | T16182-CA00-P0GEN-185801 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 185802 | T16182-CA00-P0GEN-185802 | CHEMICAL DOSING SHELTER FOR STG & HRSG - ELEVATION | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 185803 | T16182-CA00-P0GEN-185803 | CHEMICAL DOSING SHELTER FOR STG & HRSG - MAIN SECTION | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 185851 | T16182-CA01-P0GEN-185851 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 185852 | T16182-CA01-P0GEN-185852 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 185853 | T16182-CA01-P0GEN-185853 | CHEMICAL DOSING SHELTER FOR STG & HRSG - FRAMING ELEVATION | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 185854 | T16182-CA02-P0GEN-185854 | CHEMICAL DOSING SHELTER FOR STG & HRSG - REBAR DETAIL | IFR | 2017-09-15 | 2017-10-15 |  |  |  |  | 2017-09-19 | 2017-10-16
S&A(18) | Structural & Architectural | 186100 | T16182-CA06-P0UBA-186100 | FGS ELECTRICAL BUILDING - CALCULATION | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-05-15
S&A(18) | Structural & Architectural | 186101 | T16182-CA00-P0UBA-186101 | FGS ELECTRICAL BUILDING - GROUND FLOOR, ROOF PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186103 | T16182-CA00-P0UBA-186103 | FGS ELECTRICAL BUILDING - SIDE WALL ELEVATION | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186104 | T16182-CA00-P0UBA-186104 | FGS ELECTRICAL BUILDING - MAIN SECTION | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186151 | T16182-CA01-P0UBA-186151 | FGS ELECTRICAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186152 | T16182-CA01-P0UBA-186152 | FGS ELECTRICAL BUILDING - GROUND FLOOR & ROOF FRAMING PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186154 | T16182-CA01-P0UBA-186154 | FGS ELECTRICAL BUILDING - LINE & ROW FRAMING ELEVATION | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186155 | T16182-CA02-P0UBA-186155 | FGS ELECTRICAL BUILDING - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186156 | T16182-CA02-P0UBA-186156 | FGS ELECTRICAL BUILDING - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-10 | 2017-04-06
S&A(18) | Structural & Architectural | 186600 | T16182-CA06-P0UGD-186600 | NAOCL DOSING SKID SHELTER - CALCULATION | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-15 | 2017-10-19
S&A(18) | Structural & Architectural | 186601 | T16182-CA00-P0UGD-186601 | NAOCL DOSING SKID SHELTER - GROUND & ROOF FLOOR PLAN | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-15 | 2017-10-19
S&A(18) | Structural & Architectural | 186602 | T16182-CA00-P0UGD-186602 | NAOCL DOSING SKID SHELTER - ELEVATION & SECTION | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-15 | 2017-10-19
S&A(18) | Structural & Architectural | 186651 | T16182-CA01-P0UGD-186651 | NAOCL DOSING SKID SHELTER - FND, GROUND, ROOF FRAMING PLAN & FRAMING ELEVATION | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-15 | 2017-10-19
S&A(18) | Structural & Architectural | 186652 | T16182-CA01-P0UGD-186652 | NAOCL DOSING SKID SHELTER - REBAR DETAIL | IFR | 2017-09-15 | 2017-11-15 |  |  |  |  | 2017-09-15 | 2017-10-19
S&A(18) | Structural & Architectural | 186800 | T16182-CA06-P0UBA-186800 | AUX. LEB - CALCULATION | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 186801 | T16182-CA00-P0UBA-186801 | AUX. LEB - GROUND FLOOR PLAN & ROOF PLAN | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 186802 | T16182-CA00-P0UBA-186802 | AUX. LEB - SIDE WALL ELEVATION | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 186803 | T16182-CA00-P0UBA-186803 | AUX. LEB - MAIN SECTION | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 186851 | T16182-CA01-P0UBA-186851 | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 186852 | T16182-CA01-P0UBA-186852 | AUX. LEB - GROUND FLOOR FRAMING PLAN & ROOF FRAMING PLAN | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 186853 | T16182-CA01-P0UBA-186853 | AUX. LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 186854 | T16182-CA02-P0UBA-186854 | AUX. LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-12-14
S&A(18) | Structural & Architectural | 186855 | T16182-CA02-P0UBA-186855 | AUX. LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-11-20 | 2017-12-20 |  |  |  |  | 2017-11-09 | 2017-11-21
S&A(18) | Structural & Architectural | 189000 | T16182-CA07-P0ZEN-189000 | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | IFR | 2016-10-27 | 2017-01-31 |  |  |  |  | 2016-11-03 | 2017-02-02
S&A(18) |  | 189001 | T16182-CA03-P0HBD-189001 | YARD PLATFORM | Internal | [6 empty] | 2017-12-04 | #VALUE!
S&A(18) |  | 189002 | T16182-CA03-P0HBD-189002 | PEECC PLATFORM | Internal | [6 empty] | 2017-12-07 | #VALUE!
TG-MCH(22) | Civil | 220001 | T16182-VL00-P0MPA-220001 | CIVIL - STG FOUNDATION - SHAPE UNIT P6 | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG | 2017-01-25 | #VALUE!
TG-MCH(22) | Civil | 220002 | T16182-VL00-P7MPA-220002 | CIVIL - STG FOUNDATION - SHAPE - UNIT P7 | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG | 2017-08-18 | #VALUE!
TG-MCH(22) | Civil | 220003 | T16182-UF00-P0MAA-220003 | ST FOUNDATION LOAD - PLAN | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG | 2017-01-25 | #VALUE!
TG-MCH(22) | Mechanical | 220015 | T16182-XM00-P0MAA-220015 | LAYDOWN PLAN - UNIT P6 & P7 | IFI | 2017-02-24 |  |  |  |  | PKG-040-STG | 2017-06-01 | #VALUE!
TG-MCH(22) | Civil | 220023 | T16182-CA07-P0MPA-220023 | STG FOUNDATION - DESIGN CRITERIA - UNIT P6 & P7 | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG | 2017-01-25 | #VALUE!
TG-MCH(22) | Mechanical | 220025 | T16182-XG02-P6MAA-220025 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P6 | IFR | 2017-03-17 | 2017-09-22 | O |  | O | PKG-040-STG | 2017-06-01 | 2018-02-28
TG-MCH(22) | Mechanical | 220026 | T16182-XG02-P7MAA-220026 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P7 | IFR | 2018-02-21 | 2018-03-21 |  |  |  | PKG-040-STG | 2018-01-05 | 2018-02-28
TG-MCH(22) | Mechanical | 220027 | T16182-XG02-P6MAA-220027 | P&I DIAGRAM HPH - UNIT P6 | IFR | 2017-03-17 | 2017-09-22 |  |  | O | PKG-040-STG | 2017-06-01 | 2018-01-17
TG-MCH(22) | Mechanical | 220028 | T16182-XG02-P7MAA-220028 | P&I DIAGRAMS HPH - UNIT P7 | IFR | 2018-02-21 | 2018-03-21 |  |  |  | PKG-040-STG | 2018-01-05 | 2018-01-17
TG-MCH(22) | Mechanical | 220029 | T16182-XG02-P6MAA-220029 | P&I DIAGRAM LUBRICATION OIL - UNIT P6 | IFR | 2017-03-17 | 2017-09-22 |  |  | O | PKG-040-STG | 2017-06-01 | 2018-01-17
TG-MCH(22) | Mechanical | 220030 | T16182-XG02-P7MAA-220030 | P&I DIAGRAM LUBRICATION OIL - UNIT P7 | IFR | 2018-02-21 | 2018-03-21 |  |  |  | PKG-040-STG | 2018-01-05 | 2018-01-17
TG-MCH(22) | Mechanical | 220047 | T16182-VE01-P6MAA-220047 | ALLOWABLE LOADINGS AND DISPLACEMENTS | IFI | 2017-03-17 |  |  |  |  | PKG-040-STG | 2017-11-07 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220073 | T16182-YR00-P6MAA-220073 | CONTROL SYSTEM ARCHITECTURE | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG | 2018-08-22 | #VALUE!
TG-MCH(22) | Mechanical | 220089 | T16182-XG01-P6MAA-220089 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P6 | IFI | 2018-02-04 |  |  |  |  | PKG-040-STG | 2017-09-29 | #VALUE!
TG-MCH(22) | Mechanical | 220090 | T16182-XG01-P7MAA-220090 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P7 | IFI | 2018-03-20 |  |  |  |  | PKG-040-STG | 2018-05-11 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220093 | T16182-XS01-P6MAA-220093 | CONTROL SYSTEM FUNCTIONS PHILOSOPHY | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG | 2017-09-29 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220095 | T16182-YL13-P6MAA-220095 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (HW) | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG | 2017-09-29 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220097 | T16182-YF00-P6MAA-220097 | LOGIC DIAGRAMS FOR ST | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG | 2017-10-24 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220143 | T16182-YL13-P6MAA-220143 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (SW) - UNIT 1+2 | IFI | 2017-11-30 |  |  |  |  | PKG-040-STG | 2017-11-07 | #VALUE!
TG-MCH(22) | Mechanical | 220205 | T16182-CM01-P6MAA-220205 | DRAWINGS, PART LISTS OF TURBINE – UNIT P6 | IFI | 2018-05-15 |  |  |  |  | PKG-040-STG | 2018-05-03 | #VALUE!
TG-MCH(22) | Mechanical | 220206 | T16182-CM01-P7MAA-220206 | DRAWINGS, PART LISTS OF TURBINE – UNIT P7 | IFI | 2018-05-15 |  |  |  |  | PKG-040-STG | 2018-05-03 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220207 | T16182-YL08-P6MAA-220207 | TRIPS & ALARMS SETTINGS UNIT P6+P7 | IFI | 2017-11-30 |  |  |  |  | PKG-040-STG | 2017-11-07 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220275 | T16182-YF02-P6CJJ-220275 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P6 | IFI | 2018-05-20 |  |  |  |  | PKG-040-STG | 2018-05-30 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220276 | T16182-YF02-P7CJJ-220276 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P7 | IFI | 2018-05-20 |  |  |  |  | PKG-040-STG | 2018-05-30 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220277 | T16182-YV02-P6CJJ-220277 | HMI DESIGN – UNIT P6 | IFI | 2017-11-30 |  |  |  |  | PKG-040-STG | 2018-05-30 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220278 | T16182-YV02-P7CJJ-220278 | HMI DESIGN – UNIT P7 | IFI | 2018-05-20 |  |  |  |  | PKG-040-STG | 2018-05-30 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220293 | T16182-YT02-P6CJJ-220293 | INSTRUMENTATION DATA SHEETS - UNIT P6 | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG | 2018-05-11 | #VALUE!
TG-MCH(22) | Instrumentation & Control | 220294 | T16182-YT02-P7CJJ-220294 | INSTRUMENTATION DATA SHEETS - UNIT P7 | IFI | 2018-03-20 |  |  |  |  | PKG-040-STG | 2018-05-11 | #VALUE!
TG-MCH(22) | Mechanical | 220383 | T16182-XJ00-P6MAA-220383 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P6 | IFI | 2018-10-26 |  |  |  |  | PKG-040-STG | 2018-10-26 | #VALUE!
TG-MCH(22) | Mechanical | 220384 | T16182-XJ00-P7MAA-220384 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P7 | IFI | 2018-10-26 |  |  |  |  | PKG-040-STG | 2018-10-26 | #VALUE!
TG-MCH(22) | Mechanical | 220801 | T16182-YD00-P0MAA-220801 | STEAM TURBINE OUTLINE DRAWING | IFR | 2017-06-30 | 2017-12-29 | O |  |  | PKG-040-STG | 2017-11-07 | 2018-01-11
GN-MCH(25) | Mechanical | 250001 | T16182-XB00-P6MKA-250001 | ST GENERATOR UNIT#P6 FOUNDATION ARRANGEMENT DRAWING | IFI | 2016-12-17 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-01-12 | 2017-07-11
GN-MCH(25) | Mechanical | 250002 | T16182-XB00-P7MKA-250002 | ST GENERATOR UNIT#P7 FOUNDATION ARRANGEMENT DRAWING | IFI | 2016-12-17 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-01-12 | 2017-07-11
GN-MCH(25) | Mechanical | 250003 | T16182-UF00-P6MKA-250003 | ST GENERATOR FOUNDATION LOADING | IFI | 2016-12-17 |  |  |  |  | PKG-040-STG | 2017-01-12 | #VALUE!
GN-MCH(25) | Mechanical | 250004 | T16182-YD00-P0MKA-250004 | GENERATOR PIPING CONNECTION | IFI | 2017-03-30 |  |  |  |  | PKG-040-STG | 2017-01-12 | #VALUE!
GN-MCH(25) | Mechanical | 250005 | T16182-YD00-P0MKA-250005 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG | 2017-04-07 | #VALUE!
GN-MCH(25) | Mechanical | 250006 | T16182-YD00-P0MKA-250006 | HANDLING DIMENSION FOR GENERATOR ROTOR | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG | 2017-09-19 | #VALUE!
GN-MCH(25) | Mechanical | 250007 | T16182-YK10-P0MKA-250007 | BRUSH HOLDER RIGGING ASSEMBLY | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG | 2017-09-19 | #VALUE!
GN-MCH(25) | Mechanical | 250008 | T16182-YD00-P6MKA-250008 | ST GENERATOR UNIT HYDROGEN COOLER OUTLINE | IFI | 2017-01-05 |  |  |  |  | PKG-040-STG | 2017-04-03 | #VALUE!
GN-MCH(25) | Mechanical | 250009 | T16182-YT01-P0MKA-250009 | GENERATOR DATA SHEET | IFI | 2017-03-30 |  | O |  |  | PKG-040-STG | 2017-03-28 | #VALUE!
GN-MCH(25) | Mechanical | 250010 | T16182-UC02-P0MKA-250010 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG | 2017-04-21 | #VALUE!
GN-MCH(25) | Mechanical | 250011 | T16182-UC02-P6MKA-250011 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P6) | IFI | 2016-12-08 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-05-25 | 2017-07-18
GN-MCH(25) | Mechanical | 250012 | T16182-UC02-P7MKA-250012 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P7) | IFI | 2016-12-08 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-05-25 | 2017-07-18
GN-MCH(25) | Mechanical | 250013 | T16182-UC02-P0MKA-250013 | CURRENT TRANSFORMER ASSEMBLY | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG | 2017-04-19 | #VALUE!
GN-MCH(25) | Mechanical | 250014 | T16182-UC02-P0MKA-250014 | STATOR WINDING DIAGRAM | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG | 2017-04-19 | #VALUE!
GN-MCH(25) | Mechanical | 250015 | T16182-UC02-P0MKA-250015 | FIELD CLEARANCE DIAGRAM | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG | 2017-09-19 | #VALUE!
GN-MCH(25) | Mechanical | 250016 | T16182-YD00-P0MKA-250016 | ST GENERATOR MECHANICAL OUTLINE | IFI | 2017-03-30 | 2017-11-20 |  |  |  | PKG-040-STG | 2017-07-11 | 2017-11-20
GN-MCH(25) | Mechanical | 250017 | T16182-YD00-P0MKA-250017 | STG SOLE PLATE LAYOUT | IFI | 2017-03-30 | 2017-11-20 |  |  |  | PKG-040-STG | 2017-04-07 | 2017-11-20
GN-MCH(25) | Mechanical | 250018 | T16182-YD00-P0MKA-250018 | STG FLOOR PLATE LAYOUT | IFI | 2017-03-30 | 2017-11-20 |  |  |  | PKG-040-STG | 2017-04-07 | 2017-11-20
GN-MCH(25) | Mechanical | 250019 | T16182-DM02-P0MKA-250019 | SUGGESTIONS FOR GROUTING STG WITH FLOWABLE GROUT | IFI | 2017-03-30 |  |  |  |  | PKG-040-STG | 2017-04-07 | #VALUE!
GN-MCH(25) | Mechanical | 250020 | T16182-YD00-P0MKA-250020 | ST GENERATOR TERMINAL BOX ASSEMBLY | IFI | 2017-03-30 |  |  |  |  | PKG-040-STG | 2017-04-07 | #VALUE!
GN-MCH(25) | Mechanical | 250021 | T16182-DM02-P0MKA-250021 | ROTOR ASSEMBLY DISASSEMBLY NOTE | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG | 2017-04-19 | #VALUE!
GN-MCH(25) | Mechanical | 250022 | T16182-UC02-P0MKA-250022 | ROTOR ASSEMBLY DISASSEMBLY DIAGRAM | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG | 2017-04-19 | #VALUE!
GN-MCH(25) | Mechanical | 250023 | T16182-YD00-P0MKA-250023 | ST GENERATOR END SHIELD ASSY CE | IFI | 2017-11-14 |  |  |  |  | PKG-040-STG | 2017-11-15 | #VALUE!
GN-MCH(25) | Mechanical | 250024 | T16182-YD00-P0MKA-250024 | ST GENERATOR END SHIELD ASSY TE | IFI | 2017-11-14 |  |  |  |  | PKG-040-STG | 2017-11-15 | #VALUE!
GN-SYS(26) | Mechanical | 260001 | T16182-YD00-P0MKW-260001 | SEAL OIL DRAIN ENLARGEMENT OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-02 | 2017-11-01
GN-SYS(26) | Mechanical | 260002 | T16182-YD00-P0MKW-260002 | BEARING OIL DRAIN ENLARGEMENT OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-02 | 2017-11-01
GN-SYS(26) | Mechanical | 260003 | T16182-XJ00-P6MKA-260003 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ISO | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG | 2017-08-16 | 2017-11-23
GN-SYS(26) | Mechanical | 260004 | T16182-XH01-P6MKA-260004 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ARRANGEMENT | IFR | 2017-06-30 | 2017-12-30 |  |  |  | PKG-040-STG | 2017-06-30 | 2017-11-15
GN-SYS(26) | Mechanical | 260005 | T16182-XK00-P6MKA-260005 | ST GENERATOR UNIT#P6 AUX SYSTEM HANGER & SUPPORT | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG | 2017-07-28 | 2017-11-15
GN-SYS(26) | Mechanical | 260006 | T16182-XJ00-P7MKA-260006 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ISO | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG | 2017-08-16 | 2017-11-23
GN-SYS(26) | Mechanical | 260007 | T16182-XH01-P7MKA-260007 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ARRANGEMENT | IFR | 2017-06-30 | 2017-12-30 |  |  |  | PKG-040-STG | 2017-06-30 | 2017-11-15
GN-SYS(26) | Mechanical | 260008 | T16182-XK00-P7MKA-260008 | ST GENERATOR UNIT#P7 AUX SYSTEM HANGER & SUPPORT | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG | 2017-07-28 | 2017-11-15
GN-SYS(26) | Mechanical | 260011 | T16182-YD00-P0MKW-260011 | H2 SEAL OIL UNIT OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-11-06
GN-SYS(26) | Mechanical | 260012 | T16182-YD00-P0MKW-260012 | FLOAT TRAP OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-11-07
GN-SYS(26) | Mechanical | 260013 | T16182-YD00-P0MKW-260013 | LIQUID LEVEL DETECTOR OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-11-07
GN-SYS(26) | Mechanical | 260014 | T16182-YD00-P0MKG-260014 | GAS CONTROL VALVE STATION OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-10-11
GN-SYS(26) | Mechanical | 260015 | T16182-YD00-P0MKG-260015 | H2 BOTTLE MANIFOLD OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-10-11
GN-SYS(26) | Mechanical | 260016 | T16182-YD00-P0MKG-260016 | CO2 BOTTLE MANIFOLD OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-10-11
GN-SYS(26) | Mechanical | 260017 | T16182-YD00-P0MKG-260017 | H2 CONTROL CABINET OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-11-09
GN-SYS(26) | Mechanical | 260018 | T16182-YD00-P0MKG-260018 | H2 GAS DRYER OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-09-28
GN-SYS(26) | Mechanical | 260019 | T16182-YT01-P0MKA-260019 | GENERATOR AUX SYSTEM MOTOR & PUMP DATA SHEET | IFR | 2017-04-30 | 2017-07-30 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-12-08
GN-SYS(26) | Mechanical | 260020 | T16182-YT01-P0MKA-260020 | GENERATOR AUX SYSTEM INSTRUMENT DATA SHEET | IFI | 2017-08-08 |  |  |  |  | PKG-040-STG | 2017-10-19 | #VALUE!
GN-SYS(26) | Mechanical | 260021 | T16182-YV02-P0MKW-260021 | H2 SEAL OIL SYSTEM - WIRING DIAGRAMS | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-11-22
GN-SYS(26) | Mechanical | 260022 | T16182-YV02-P0MKG-260022 | GAS CONTROL SYSTEM - WIRING DIAGRAMS | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG | 2017-06-08 | 2017-11-22
GN-SYS(26) | Mechanical | 260031 | T16182-CY03-P0MKW-260031 | H2 SEAL OIL SYSTEM - SYSTEM DESCRIPTION | IFR | 2017-04-30 | 2017-07-31 |  |  |  | PKG-040-STG | 2017-06-12 | 2017-11-29
GN-SYS(26) | Mechanical | 260032 | T16182-CY03-P0MKG-260032 | GAS CONTROL SYSTEM - SYSTEM DESCRIPTION | IFR | 2017-04-30 | 2017-07-31 |  |  |  | PKG-040-STG | 2017-06-12 | 2017-11-29
GN-SYS(26) | Mechanical | 260033 | T16182-XG02-P0MKW-260033 | H2 SEAL OIL SYTSEM P&ID | IFR | 2017-04-30 | 2017-06-30 |  |  |  | PKG-040-STG | 2017-03-29 | 2017-09-28
GN-SYS(26) | Mechanical | 260034 | T16182-XG02-P0MKG-260034 | GAS CONTROL SYSTEM P&ID | IFR | 2017-03-21 | 2017-06-30 |  |  |  | PKG-040-STG | 2017-03-29 | 2017-09-28
GN-SYS(26) | Mechanical | 260035 | T16182-XL00-P0MKA-260035 | LINE LIST FOR ST GENERATOR | IFR | 2017-04-30 | 2017-07-30 |  |  |  | PKG-040-STG | 2017-06-12 | 2017-11-27
GN-SYS(26) | Mechanical | 260036 | T16182-XN00-P0MKA-260036 | VALVE LIST FOR ST GENERATOR | IFI | 2017-04-30 | 2017-06-30 |  |  |  | PKG-040-STG | 2017-06-12 | 2017-12-06
GN-I&C(29) | Instrumentation & Control | 290001 | T16182-YS00-P0CJN-290001 | ELECTRICAL DIAGRAM STATIC EXCITATION SYSTEM FOR ST | IFR | 2017-04-10 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-04-12 | 2017-11-29
GN-I&C(29) | Instrumentation & Control | 290002 | T16182-YR05-P0CJN-290002 | EXCITER PANEL OUTLINE DRAWING FOR ST | IFR | 2017-03-10 | 2017-05-10 |  |  |  | PKG-040-STG | 2017-02-20 | 2017-05-18
GN-I&C(29) | Instrumentation & Control | 290003 | T16182-BV02-P0CJN-290003 | PSS STUDY REPORT FOR ST | IFR | 2018-01-26 | 2018-09-30 |  |  |  | PKG-040-STG | 2018-01-30 | 2019-12-20
GN-I&C(29) | Instrumentation & Control | 290004 | T16182-YR05-P0CJN-290004 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST | IFR | 2017-03-10 | 2017-05-10 |  |  |  | PKG-040-STG | 2017-03-16 | 2017-09-15
GN-I&C(29) | Instrumentation & Control | 290005 | T16182-YE00-P0CJN-290005 | AC/DC POWER CABLE/RACEWAY LAYOUT | IFR | 2017-06-30 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-06-30 | 2017-11-10
GN-I&C(29) | Instrumentation & Control | 290006 | T16182-YU02-P0MKY-290006 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-03-30 | 2017-07-06
GN-I&C(29) | Instrumentation & Control | 290007 | T16182-YF00-P0MKY-290007 | LOGIC DIAGRAMS OF GENERATOR CONTROL PANEL FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-06-02 | 2017-12-15
GN-I&C(29) | Instrumentation & Control | 290008 | T16182-YS01-P0MKY-290008 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-06-02 | 2017-11-27
GN-I&C(29) | Instrumentation & Control | 290009 | T16182-YS01-P0MKY-290009 | SCHEMATIC DIAGRAMS FOR GENERATOR CONTROL PANEL | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-06-02 | 2018-01-30
GN-I&C(29) | Instrumentation & Control | 290010 | T16182-YT10-P0MKY-290010 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG | IFR | 2017-08-14 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-08-24 | 2018-07-11
GN-I&C(29) | Instrumentation & Control | 290011 | T16182-YS01-P0MKY-290011 | SCHEMATIC DIAGRAMS FOR EMERGENCY SEAL OIL DC MOTOR STARTER PANEL | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-04-21 | 2017-07-07
GN-I&C(29) | Instrumentation & Control | 290012 | T16182-YS01-P0MKY-290012 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-06-12 | 2017-12-20
GN-I&C(29) | Instrumentation & Control | 290013 | T16182-YS01-P0MKY-290013 | SCHEMATIC DIAGRAMS FOR PT/SA PANEL FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG | 2017-06-12 | 2017-09-25
GN-I&C(29) | Instrumentation & Control | 290014 | T16182-YR02-P0CJN-290014 | TECHNICAL SPECIFICATION OF EXCITATION SYSTEM FOR ST | IFR | 2017-04-07 | 2017-10-13 |  |  |  | PKG-040-STG | 2017-04-07 | 2017-10-13
TK(40) | Mechanical | 410001 | T16182-YK10-P0LCP-410001 | OUTLINE DRAWING FOR CONDENSATE STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Mechanical | 410002 | T16182-YT10-P0LCP-410002 | STRENGTH CALCULATION FOR CONDENSATE STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Mechanical | 410011 | T16182-YK10-P0GHC-410011 | OUTLINE DRAWING FOR DEMINERALIZED WATER STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Mechanical | 410012 | T16182-YT10-P0GHC-410012 | STRENGTH CALCULATION FOR DEMINERALIZED WATER STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Mechanical | 410021 | T16182-YK10-P0GKB-410021 | OUTLINE DRAWING FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Mechanical | 410022 | T16182-YT10-P0GKB-410022 | STRENGTH CALCULATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Mechanical | 410031 | T16182-YK10-P0GKB-410031 | OUTLINE DRAWING FOR POTABLE WATER STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Mechanical | 410032 | T16182-YT10-P0GKB-410032 | STRENGTH CALCULATION FOR POTABLE WATER STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O |  |  | 2017-02-16 | 2017-05-29
TK(40) | Electrical | 411001 | T16182-CV03-P0PUR-411001 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR CONDENSATE STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-20 | 2017-06-08
TK(40) | Electrical | 411011 | T16182-CV03-P0PUR-411011 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR DEMINERALIZED WATER STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-20 | 2017-06-08
TK(40) | Electrical | 411021 | T16182-CV03-P0PUR-411021 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-20 | 2017-06-08
TK(40) | Electrical | 411031 | T16182-CV03-P0PUR-411031 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE WATER STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O |  |  | 2017-03-20 | 2017-06-08
TK(40) | Mechanical | 420010 | T16182-YK08-P0PGB-420010 | OUTLINE DRAWING FOR CCW EXPANSION HEAD TANK | IFR | 2017-03-10 | 2017-09-15 |  | O |  |  | 2017-03-10 | 2017-09-15
TK(40) | Mechanical | 420020 | T16182-YK08-P0PGB-420020 | OUTLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | IFR | 2017-03-10 | 2017-09-15 |  | O |  |  | 2017-03-10 | 2017-09-15
TK(40) | Mechanical | 420030 | T16182-YK08-P0LCM-420030 | OUTLINE DRAWING FOR ATMOSPHERIC FLASH TANK | IFR | 2017-04-14 | 2017-09-29 |  |  |  |  | 2017-03-22 | 2017-07-21
TK(40) | Mechanical | 420040 | T16182-YK08-P0LCM-420040 | OUTLINE DRAWING FOR VACUUM FLASH TANK | IFR | 2017-04-14 | 2017-09-29 |  |  |  |  | 2017-03-22 | 2017-10-31
TK(40) | Mechanical | 420050 | T16182-YK08-P0GKC-420050 | OUTLINE DRAWING FOR CHILLED WATER STORAGE TANK | IFR | 2017-10-31 | 2017-12-15 |  |  |  |  | 2017-11-01 | 2018-01-02
TK(40) | Mechanical | 420051 | T16182-YK08-P0GKC-420051 | INSULATION DETAIL DRAWING FOR CHILLED WATER STORAGE TANK | IFI | 2018-01-05 | 2018-03-05 |  |  |  |  | 2018-01-03 | 2018-01-29
|  | 755001 | T16182-DD09-P0ZEN-755001 | SAT Procedure for Isolated Phase Busbar (IPB) | [7 empty] | 2020-02-12 | #VALUE!
|  | 755002 | T16182-DD09-P0ZEN-755002 | SAT Procedure for GSUT | [7 empty] | 2020-02-12 | #VALUE!
|  | 755003 | T16182-DD09-P0ZEN-755003 | SAT Procedure for 380kv EHV Cable and Accessories | [7 empty] | 2020-02-12 | #VALUE!
|  | 755004 | T16182-DD09-P0ZEN-755004 | SAT Procedure for Non Segregated Phase Busduct (NSPBD) | [7 empty] | 2020-02-12 | #VALUE!
|  | 755005 | T16182-DD09-P0ZEN-755005 | SAT Procedure for Unit Auxillary Transformer (UAT) | [7 empty] | 2020-02-12 | #VALUE!
|  | 755006 | T16182-DD09-P0ZEN-755006 | SAT Procedure for Protection Relay Panel, GSUT HV Side Energy Metering Panel | [7 empty] | 2020-02-12 | #VALUE!
|  | 755007 | T16182-DD09-P0ZEN-755007 | SAT Procedure for AC-UPS System | [7 empty] | 2020-02-12 | #VALUE!
|  | 755008 | T16182-DD09-P0ZEN-755008 | SAT Procedure for DC Battery Charger System | [7 empty] | 2020-02-12 | #VALUE!
|  | 755009 | T16182-DD09-P0ZEN-755009 | SAT Procedure for Generator Circuit Breaker (GCB) | [7 empty] | 2020-02-12 | #VALUE!
|  | 755010 | T16182-DD09-P0ZEN-755010 | SAT Procedure for LV Cable | [7 empty] | 2020-02-12 | #VALUE!
|  | 755011 | T16182-DD09-P0ZEN-755011 | SAT Procedure for MV Cable | [7 empty] | 2020-02-12 | #VALUE!
|  | 755012 | T16182-DD09-P0ZEN-755012 | SAT Procedure for 480V Motor Control Center | [7 empty] | 2020-02-12 | #VALUE!
|  | 755013 | T16182-DD09-P0ZEN-755013 | SAT Procedure for 13.8 kV MV Switch Gear | [7 empty] | 2020-02-12 | #VALUE!
|  | 755014 | T16182-DD09-P0ZEN-755014 | SAT Procedure for LV Switchgear | [7 empty] | 2020-02-12 | #VALUE!
|  | 755015 | T16182-DD09-P0ZEN-755015 | SAT Procedure for Lighting Distribution Board (LDB) | [7 empty] | 2020-02-12 | #VALUE!
|  | 755016 | T16182-DD09-P0ZEN-755016 | SAT Procedure for Mold / Dry Transformer | [7 empty] | 2020-02-12 | #VALUE!
|  | 755017 | T16182-DD09-P0ZEN-755017 | SAT Procedure for MV & LV Motors | [7 empty] | 2020-02-12 | #VALUE!
|  | 755019 | T16182-DD09-P0ZEN-755019 | SAT Procedure for STG Excitation Transformer (Oil Type) | [7 empty] | 2020-02-12 | #VALUE!
|  | 755020 | T16182-DD09-P0ZEN-755020 | SAT Procedure for Neutral Grounding Transformer (NGTR) Neutral Grounding Resistor (NGR) | [7 empty] | 2020-02-12 | #VALUE!
|  | 755021 | T16182-DD09-P0ZEN-755021 | SAT Procedure for Ground, Step & touch Voltage | [7 empty] | 2020-02-12 | #VALUE!
|  | 755022 | T16182-DD09-P0ZEN-755022 | Site Acceptance Test Procedure for Generator & Exc. TR Protection Relay, Control Panel | [7 empty] | 2020-02-12 | #VALUE!
|  | 755023 | T16182-DD09-P0ZEN-755023 | Site Acceptance Test Procedure for HCIS Security System | [7 empty] | 2020-02-12 | #VALUE!
|  | 810006 | T16182-DN05-P8MB-810006 | GAS TURBINE FUEL CHANGE-OVER TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 810030 | T16182-DN05-P8ZEN-810030 | PLANT EMERGENCY FUEL CHANGE-OVER TEST | [7 empty] | #VALUE! | #VALUE!
|  | 860001 | T16182-DN05-P0ZEN-860001 | GT LOAD REJECTION TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860002 | T16182-DN05-P0ZEN-860002 | TRIAL RUN TEST OF THE PLANT | [7 empty] | 2020-07-15 | #VALUE!
|  | 860003 | T16182-DN05-P0ZEN-860003 | ST LOAD REJECTION TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860004 | T16182-DN05-P0ZEN-860004 | ACTIVE POWER RESPONSE AND VOLTAGE CONTROL RESPONSE TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860006 | T16182-DN05-P0ZEN-860006 | ISLAND MODE TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860007 | T16182-DN05-P0ZEN-860007 | LOAD SWING TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860008 | T16182-DN05-P0ZEN-860008 | LDC Integration | [7 empty] | 2020-07-15 | #VALUE!
|  | 860009 | T16182-DN05-P0ZEN-860009 | STARTUP TIME TEST (COLD/WARM/HOT) | [7 empty] | 2020-07-15 | #VALUE!
|  | 860010 | T16182-DN05-P0ZEN-860010 | MINIMUM LOAD TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860011 | T16182-DN05-P0ZEN-860011 | AGC | [7 empty] | 2020-07-15 | #VALUE!
|  | 860012 | T16182-DN05-P0ZEN-860012 | PERFORMANCE TEST PROCEDURE FOR THERMAL PERFORMANCE | [7 empty] | 2020-07-15 | #VALUE!
|  | 860013 | T16182-DN05-P0ZEN-860013 | RELIABILITY TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860014 | T16182-DN05-P0ZEN-860014 | NET DEPENDABLE CAPACITY TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860015 | T16182-DN05-P0ZEN-860015 | REACTIVE POWER TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860016 | T16182-DN05-P0ZEN-860016 | PRIMARY RESPONSE TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860017 | T16182-DN05-P0ZEN-860017 | BLACK START-UP TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860018 | T16182-DN05-P0ZEN-860018 | PSS TEST | [7 empty] | 2020-07-15 | #VALUE!
|  | 860019 | T16182-DN05-P0ZEN-860019 | RESERVE BOILER THERMAL PERFORMANCE TEST PROCEDURE | [7 empty] | 2020-07-15 | #VALUE!
|  | 860020 | T16182-DN05-P0ZEN-860020 | PERFORMANCE TEST PROCEDURE FOR NOISE EMISSION | [7 empty] | 2020-07-15 | #VALUE!
|  | 860021 | T16182-DN05-P0ZEN-860021 | PERFORMANCE TEST PROCEDURE FOR AIR EMISSION | [7 empty] | 2020-07-15 | #VALUE!
|  | 860022 | T16182-DN05-P0ZEN-860022 | SUPPLEMENTARY FIRING FOR HRSG | [7 empty] | 2020-07-15 | #VALUE!
|  | 860027 | T16182-DN05-P0ZEN-860027 | REACTIVE POWER TEST OF STG | [7 empty] | 2020-07-15 | #VALUE!
|  | 860028 | T16182-DN05-P0ZEN-860028 | PSS TEST OF STG | [7 empty] | 2020-07-15 | #VALUE!
|  | 860029 | T16182-DN05-P0ZEN-860029 | SECONDARY RESPONSE TEST | [7 empty] | 2020-07-15 | #VALUE!
Formulas:
First Actual = CHOOSECOLS(CHOOSEROWS(_xlws.FILTER(표2[], 표2[DT_DOC_NO] = [Document No], ""),1),3)
Final Actual = CHOOSECOLS(CHOOSEROWS(_xlws.FILTER(표2[], (표2[DT_DOC_NO] = [Document No])*(표2[DT_DOC_PUR] = "IFC"), ""),1),3)

## Sheet3
ID | DT_DOC_NO | DT_SUBM_DATE | DT_NO | DT_DOC_PUR | DT_DOC_REV | DT_ATT | DT_ATT_DOC | DT_ATT_REP | DT_REMARK | DT_DOC_EIM_URL | DT_ATT_NOM | Item Type | Path
10 | T16182-UE00-P0MB-100006 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11 | T16182-UE00-P0MB-100007 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12 | T16182-UE00-P0UMA-100008 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
13 | T16182-UE00-P0UMA-100009 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
14 | T16182-UE00-P0UMA-100010 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
16 | T16182-XG02-P0ZEN-110002 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=751a8c4f-187f-4c6a-a47e-02a2d4ab0e07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
168 | T16182-XS00-P0GCF-130001 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99e325ea-65c6-4093-a29b-92b4a8d77bd0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
17 | T16182-XG02-P0LBA-110003 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
18 | T16182-XG02-P0LBC-110004 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
19 | T16182-XG02-P0LBG-110005 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
20 | T16182-XG02-P0LBS-110006 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
21 | T16182-XG02-P6LCM-110007 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
22 | T16182-XG02-P6LCA-110008 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
23 | T16182-XG02-P0LAA-110009 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
24 | T16182-XG02-P0PGB-110010 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
249 | T16182-YR02-P0ZEN-150001 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29009ab5-c147-4bb6-88cf-67873550b88a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
25 | T16182-XG02-P0GHC-110011 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
252 | T16182-YU02-P0ZEN-150202 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de01d558-286e-4f27-97de-e3406bec5a1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
26 | T16182-XG02-P0QJA-110012 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
27 | T16182-XG02-P1EKC-110014 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
28 | T16182-XG07-P0LA-110031 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=657e8d57-a3b5-44db-99f6-e453424c8031 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
29 | T16182-XG07-P0PG-110032 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bf89949-cfb0-4446-a0e5-2332e5db8e36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
30 | T16182-XG07-P0GHC-110033 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fb63361-5bb3-4e8a-8533-730be0b7670c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
31 | T16182-XW01-P0LB-110035 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=121f0702-dd67-47d3-bc17-b091949376a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
32 | T16182-XW01-P0LC-110036 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b7a6f77-eb12-4117-bf48-507ce075bbcc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
323 | T16182-XW01-P0ZEN-161001 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76909e73-9820-4572-a099-f4a915a478a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
33 | T16182-XW01-P0LA-110037 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3ecc544-9f71-4b80-8868-a96214281051 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
34 | T16182-XW01-P0PGB-110038 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b99e0b41-60c2-42a0-b0c5-91305236e0d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
35 | T16182-XW01-P0GHC-110039 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fe8f5e2-3903-408f-9af7-623c33fa70e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
36 | T16182-XS00-P0LB-110040 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4000297-72e8-484b-bcaa-f293c43e9174 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
37 | T16182-XS00-P0LC-110041 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1e335f1-a841-45c5-bd80-934f0b2aad6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
38 | T16182-XS00-P0LA-110042 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=817aa969-8bf5-49cf-b880-c512581488dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
39 | T16182-XS00-P0PGB-110043 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6509372-f890-4ee7-9b93-0bb194fdc2ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
40 | T16182-XS00-P0GHC-110044 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f9d92f4-fc40-4923-a56d-a1e8c9ab4835 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5 | T16182-UC07-P0ZEN-100001 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
51 | T16182-XG02-P0GKB-120001 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
52 | T16182-XG02-P0GKC-120002 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
53 | T16182-XG02-P0SCA-120004 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7805d83-8f62-417f-aec1-6c3fe5cbb45d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
54 | T16182-XG02-P0SCA-120005 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55b90c61-5f73-424a-9fec-820da56b93f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
55 | T16182-XG02-P0SCA-120006 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a90df0cb-8abc-404c-b028-c6d27e62849c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
56 | T16182-XG02-P0EK-120007 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
57 | T16182-XS00-P0GKS-120012 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d84cf647-dad1-47c0-969c-60e5b5fded24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
59 | T16182-XG07-P0SCA-120014 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=493ec2b0-deb4-439e-bb70-37a0a87dbf14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6 | T16182-UC07-P0ZEN-100002 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
60 | T16182-XS00-P0SCA-120015 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1523c901-0b60-497a-9e66-8820adde1061 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
61 | T16182-XS00-P0SCA-120016 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32267489-8c32-4790-a902-cc8c127c2a6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
63 | T16182-XG07-P0EKG-120018 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a772627d-d6c0-4862-8167-afdc1ad25e0f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
64 | T16182-XS00-P0EKG-120019 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d62d43c3-6b02-4bb3-9e3d-510c2f30724f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
65 | T16182-XS00-P0EKG-120020 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc806871-f1e4-46ff-99bd-7e42629df63b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
68 | T16182-XS00-P0GKS-120051 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a01e3e4-7717-44e8-b063-2270ff51beca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
689 | T16182-CA07-P0ZEN-189000 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7 | T16182-UC07-P0ZEN-100003 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
72 | T16182-XG02-P1MBH-110013 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d79f63b-9e81-48f7-9d7c-bb5f1b6c0e4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8 | T16182-UE00-P0MB-100004 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9 | T16182-UE00-P0MB-100005 | 2016-11-03 | EMAIL-161103-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
527 | T16182-CA06-P0UCB-180600 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
528 | T16182-CA00-P0UCB-180601 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
529 | T16182-CA00-P0UCB-180602 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
530 | T16182-CA00-P0UCB-180603 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
531 | T16182-CA00-P0UCB-180604 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
532 | T16182-CA00-P0UCB-180605 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
533 | T16182-CA00-P0UCB-180606 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
539 | T16182-CA01-P0UCB-180651 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
540 | T16182-CA01-P0UCB-180652 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
541 | T16182-CA01-P0UCB-180653 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
542 | T16182-CA01-P0UCB-180654 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
543 | T16182-CA01-P0UCB-180655 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
544 | T16182-CA01-P0UCB-180656 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
545 | T16182-CA01-P0UCB-180657 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
550 | T16182-CA02-P0UCB-180664 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
551 | T16182-CA02-P0UCB-180665 | 2016-12-07 | EMAIL-161207-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
406 | T16182-BF05-P0ZEN-170101 | 2016-12-13 | EMAIL-161213-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99bcd315-c74b-4956-8b5a-de58296823fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
489 | T16182-CC05-P0ZEN-180001 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
490 | T16182-CC05-P0ZEN-180002 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
491 | T16182-CC05-P0ZEN-180006 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
492 | T16182-CC05-P0ZEN-180008 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
493 | T16182-CC05-P0ZEN-180019 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
494 | T16182-CC05-P0ZEN-180020 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
495 | T16182-CC05-P0ZEN-180024 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
496 | T16182-CC05-P0ZEN-180025 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
497 | T16182-CC05-P0ZEN-180030 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
498 | T16182-CC05-P0ZEN-180033 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
499 | T16182-CC05-P0ZEN-180034 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
500 | T16182-CC05-P0ZEN-180035 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
501 | T16182-CC05-P0ZEN-180036 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
502 | T16182-CC05-P0ZEN-180037 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
503 | T16182-CC05-P0ZEN-180038 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
504 | T16182-CC05-P0ZEN-180039 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
505 | T16182-CC05-P0ZEN-180040 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
506 | T16182-CC05-P0ZEN-180041 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
507 | T16182-CC05-P0ZEN-180042 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
508 | T16182-CC05-P0ZEN-180043 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
509 | T16182-CC05-P0ZEN-180044 | 2016-12-13 | EMAIL-161213-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
15 | T16182-XG05-P0ZEN-110001 | 2016-12-15 | EMAIL-161215-03 | IFI | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
452 | T16182-VE04-P8UTH-172001 | 2016-12-15 | EMAIL-161215-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
453 | T16182-XB02-P8UTH-172003 | 2016-12-15 | EMAIL-161215-02 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2d083be-92c4-4ea7-8a61-36546cbdb78f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
454 | T16182-XB02-P8UTH-172004 | 2016-12-15 | EMAIL-161215-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
574 | T16182-CA06-P0UBA-181200 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
575 | T16182-CA00-P0UBA-181201 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
576 | T16182-CA00-P0UBA-181202 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
577 | T16182-CA00-P0UBA-181203 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
578 | T16182-CA00-P0UBA-181204 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
579 | T16182-CA00-P0UBA-181205 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fb4e1a7-1e01-4f9b-8dbc-2627c30e062d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
583 | T16182-CA01-P0UBA-181251 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb1f54ca-3959-4b7d-8411-6eaabeaae91a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
584 | T16182-CA01-P0UBA-181252 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ea22d8e-0a9e-488c-9bba-6df15f6bc8dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
585 | T16182-CA01-P0UBA-181253 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
586 | T16182-CA01-P0UBA-181254 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
589 | T16182-CA02-P0UBA-181257 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35ad6bc3-076c-4c5f-a5b7-087ec653dfdc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
590 | T16182-CA02-P0UBA-181258 | 2016-12-15 | EMAIL-161215-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
510 | T16182-CA00-P0UMA-180401 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
511 | T16182-CA00-P0UMA-180402 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
512 | T16182-CA00-P0UMA-180403 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
513 | T16182-CA00-P0UMA-180404 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
514 | T16182-CA01-P0UMA-180451 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
515 | T16182-CA01-P0UMA-180452 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
516 | T16182-CA01-P0UMA-180454 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
517 | T16182-CA03-P0UMA-180458 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
519 | T16182-CA03-P0UMA-180460 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
520 | T16182-CA03-P0UMA-180462 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
521 | T16182-CA03-P0UMA-180463 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
522 | T16182-CA03-P0UMA-180468 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
525 | T16182-CA06-P0UMA-180490 | 2016-12-19 | EMAIL-161219-02 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
642 | T16182-CA01-P0ULA-182151 | 2016-12-19 | EMAIL-161219-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
643 | T16182-CA03-P0ULA-182152 | 2016-12-19 | EMAIL-161219-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
644 | T16182-CA03-P0ULA-182153 | 2016-12-19 | EMAIL-161219-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
645 | T16182-CA03-P0ULA-182154 | 2016-12-19 | EMAIL-161219-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
646 | T16182-CA03-P0ULA-182155 | 2016-12-19 | EMAIL-161219-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
647 | T16182-CA03-P0ULA-182157 | 2016-12-19 | EMAIL-161219-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
649 | T16182-CA06-P0ULA-182190 | 2016-12-19 | EMAIL-161219-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
325 | T16182-YF02-P0ZEN-161031 | 2016-12-21 | EMAIL-161221-02 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bccf4ea-5fe4-4385-8bbe-0ae972596305 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
385 | T16182-XW01-P0ZEN-165001 | 2016-12-21 | EMAIL-161221-02 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df6914b4-ade8-4702-975c-d6144250ad26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
386 | T16182-YL02-P0ZEN-165011 | 2016-12-21 | EMAIL-161221-02 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cf6ae6a-cdd8-4e8c-9bce-04f8ac83162c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
408 | T16182-VE04-P0ZEN-170103 | 2016-12-21 | EMAIL-161221-03 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bcb013d-7413-4375-8923-18e3684dcdbd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
409 | T16182-VK02-P0ZEN-170104 | 2016-12-21 | EMAIL-161221-03 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d7019ef-e523-4c17-9584-f220caf46d80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
479 | T16182-VE04-P0UZA-172901 | 2016-12-21 | EMAIL-161221-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
480 | T16182-XB02-P0UZA-172902 | 2016-12-21 | EMAIL-161221-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
481 | T16182-XB02-P0UZA-172903 | 2016-12-21 | EMAIL-161221-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
482 | T16182-VK02-P0UZA-172908 | 2016-12-21 | EMAIL-161221-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
227 | T16182-XH01-P0SGA-136604 | 2016-12-23 | EMAIL-161223-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c090727d-8ada-42b6-b834-21d0e7116579 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
268 | T16182-YD16-P0ZEN-152003 | 2016-12-23 | EMAIL-161223-01 | IFI | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3 | T16182-VA08-P0ZEN-020003 | 2016-12-23 | EMAIL-161223-01 | IFI | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
405 | T16182-YR02-P0ZEN-165900 | 2016-12-23 | EMAIL-161223-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7dadfa00-4d93-4f06-bb0a-e3a7ba0644cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
445 | T16182-VE04-P0UHA-171801 | 2016-12-26 | EMAIL-161226-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
447 | T16182-XB02-P0UHA-171803 | 2016-12-26 | EMAIL-161226-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
448 | T16182-XB02-P0UHA-171804 | 2016-12-26 | EMAIL-161226-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1092 | T16182-CA07-P0ZEN-189000 | 2016-12-27 | EMAIL-161227-01 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
746 | T16182-XG05-P0ZEN-110001 | 2017-01-02 | EMAIL-170102-01 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
407 | T16182-BF05-P0ZEN-170102 | 2017-01-03 | EMAIL-170103-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20b59980-e9e1-4b87-8da8-a3b3396d0530 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
410 | T16182-BF05-P0ZEN-170105 | 2017-01-03 | EMAIL-170103-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1750256c-d5b6-4d16-973b-aaca06aedb11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
100 | T16182-XB02-P0LB-122016 | 2017-01-05 | EMAIL-170105-04 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1006 | T16182-CA06-P0UBA-181200 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1007 | T16182-CA00-P0UBA-181201 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1008 | T16182-CA00-P0UBA-181202 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1009 | T16182-CA00-P0UBA-181203 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
101 | T16182-XB02-P0LB-122017 | 2017-01-05 | EMAIL-170105-04 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1010 | T16182-CA00-P0UBA-181204 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1011 | T16182-CA00-P0UBA-181205 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f0230ac-5c63-4a30-818c-9662f6fbd3b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1015 | T16182-CA01-P0UBA-181251 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48dd5b5b-6760-4935-8056-926cf674a5bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1016 | T16182-CA01-P0UBA-181252 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b91eb8c5-feaa-47d2-a9e8-3d475a99da93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1017 | T16182-CA01-P0UBA-181253 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1018 | T16182-CA01-P0UBA-181254 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1021 | T16182-CA02-P0UBA-181257 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25bb8cf0-a8d5-4e71-b2f2-c2f1a050181e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1022 | T16182-CA02-P0UBA-181258 | 2017-01-05 | EMAIL-170105-05 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1246 | T16182-CA06-P0UCB-180600 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1247 | T16182-CA00-P0UCB-180601 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1248 | T16182-CA00-P0UCB-180602 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1249 | T16182-CA00-P0UCB-180603 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1250 | T16182-CA00-P0UCB-180604 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1251 | T16182-CA00-P0UCB-180605 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1252 | T16182-CA00-P0UCB-180606 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1253 | T16182-CA01-P0UCB-180651 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1254 | T16182-CA01-P0UCB-180652 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1255 | T16182-CA01-P0UCB-180653 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1256 | T16182-CA01-P0UCB-180654 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1257 | T16182-CA01-P0UCB-180655 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1258 | T16182-CA01-P0UCB-180656 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1259 | T16182-CA01-P0UCB-180657 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1260 | T16182-CA02-P0UCB-180664 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1261 | T16182-CA02-P0UCB-180665 | 2017-01-05 | EMAIL-170105-09 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
129 | T16182-CC00-P8QHA-125101 | 2017-01-05 | EMAIL-170105-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c30e9c6-4610-4ccb-acdb-590639726a96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
130 | T16182-CC08-P8QHB-125151 | 2017-01-05 | EMAIL-170105-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67c90110-6ac5-4e4a-b8e7-0c0048ada05f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
137 | T16182-CC08-P8QHA-125300 | 2017-01-05 | EMAIL-170105-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3280ec5d-caf7-4fc4-8f2f-e5cb8b363cb6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
256 | T16182-YD00-P0UCA-150501 | 2017-01-05 | EMAIL-170105-07 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
257 | T16182-YD00-P0UBA-150502 | 2017-01-05 | EMAIL-170105-07 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
352 | T16182-YD00-P0CWQ-161401 | 2017-01-05 | EMAIL-170105-03 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
353 | T16182-YD00-P0CWQ-161402 | 2017-01-05 | EMAIL-170105-03 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
354 | T16182-YD00-P0CWQ-161403 | 2017-01-05 | EMAIL-170105-03 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
355 | T16182-YD00-P0CWQ-161404 | 2017-01-05 | EMAIL-170105-03 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
356 | T16182-YD00-P0CWQ-161405 | 2017-01-05 | EMAIL-170105-03 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
747 | T16182-XG02-P0ZEN-110002 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2d347f5-69fc-4ac8-9478-043d647ef858 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
748 | T16182-XG02-P0LBA-110003 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
749 | T16182-XG02-P0LBC-110004 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
750 | T16182-XG02-P0LBG-110005 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
751 | T16182-XG02-P0LBS-110006 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
752 | T16182-XG02-P6LCM-110007 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
753 | T16182-XG02-P6LCA-110008 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
754 | T16182-XG02-P0LAA-110009 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
755 | T16182-XG02-P0PGB-110010 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
756 | T16182-XG02-P0GHC-110011 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
757 | T16182-XG02-P0QJA-110012 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
758 | T16182-XG02-P1EKC-110014 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
759 | T16182-XG07-P0LA-110031 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43752dfb-e254-45f4-a606-0c6e0cd63c1a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
760 | T16182-XG07-P0PG-110032 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9f40e93-d26a-4230-9be8-20ccf67c68a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
761 | T16182-XG07-P0GHC-110033 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59067680-e0cf-42bf-9443-c98b0586ea89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
762 | T16182-XW01-P0LB-110035 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7edd082-77e7-4ce0-bba5-0a84c189b336 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
763 | T16182-XW01-P0LC-110036 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b637189b-84ef-40cb-a656-d9d0f116745a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
764 | T16182-XW01-P0LA-110037 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=507aca95-9b4f-407c-9397-2286d855cf56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
765 | T16182-XW01-P0PGB-110038 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1451f89-aae2-4426-a4e1-e515182b0caa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
766 | T16182-XW01-P0GHC-110039 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c48eda3-20eb-4cfb-a832-8557b47c6033 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
767 | T16182-XS00-P0LB-110040 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd0eabc9-9d71-4fd4-a31f-711361a83f9f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
768 | T16182-XS00-P0LC-110041 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35137a09-5253-43f0-81a1-5988912a241a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
769 | T16182-XS00-P0LA-110042 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62b39930-64c3-4419-b08b-8f0acef18304 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
770 | T16182-XS00-P0PGB-110043 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f297f06a-dfa3-47be-83b1-ded197208179 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
771 | T16182-XS00-P0GHC-110044 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=849bfedf-f4f7-4eab-956b-5f964925c78a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
776 | T16182-XG02-P0GKB-120001 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b67d4d09-01e0-422c-9ab6-d5d7c8c3d6a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
777 | T16182-XG02-P0GKC-120002 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09e47c64-74a3-4639-87b1-7df8613b3675 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
778 | T16182-XG02-P0SCA-120004 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50a46865-2588-4cef-ae21-1daafec18148 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
779 | T16182-XG02-P0SCA-120005 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9baf86c1-5902-47d7-adba-b0c2a6d47d69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
780 | T16182-XG02-P0SCA-120006 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=704274e9-80f1-44b1-8930-3f13989aab8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
781 | T16182-XG02-P0EK-120007 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2eee4a0-286f-4ab6-b1fd-038a0d27fe5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
782 | T16182-XS00-P0GKS-120012 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e63bc688-cf91-47be-9a38-aeefdf93a9dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
784 | T16182-XS00-P0SCA-120015 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b57be51-7a2f-4f32-b73f-5afbb7e1943c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
788 | T16182-XS00-P0EKG-120019 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4428d6fd-2f79-41fe-8714-51a5a1cee5eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
789 | T16182-XS00-P0EKG-120020 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8541a8d5-0503-43bb-93b9-973f0a475774 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
791 | T16182-XS00-P0GKS-120051 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c8f7340-1277-477e-bef4-7aa581018f97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
793 | T16182-XG02-P1MBH-110013 | 2017-01-05 | EMAIL-170105-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=485dcfc9-898f-41b4-a2e0-b41db01ad05b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
825 | T16182-YU02-P0ZEN-150202 | 2017-01-05 | EMAIL-170105-08 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e96e880-1c85-4965-9666-c09a6db1569d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
919 | T16182-VE04-P0ZEN-170103 | 2017-01-05 | EMAIL-170105-06 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
930 | T16182-VE04-P0UHA-171801 | 2017-01-05 | EMAIL-170105-04 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
932 | T16182-XB02-P0UHA-171803 | 2017-01-05 | EMAIL-170105-04 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
933 | T16182-XB02-P0UHA-171804 | 2017-01-05 | EMAIL-170105-04 | IFR | B | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1 | T16182-DA01-P0ZEN-020001 | 2017-01-06 | EMAIL-170106-02 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=822bf58c-e1ca-4d9a-b779-cd416f40639b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2 | T16182-DA01-P0ZEN-020002 | 2017-01-06 | EMAIL-170106-02 | IFI | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
96 | T16182-UE00-P0LB-122007 | 2017-01-06 | EMAIL-170106-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=948a9e4d-7ef1-482b-95e5-3ff1387662df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
937 | T16182-VE04-P8UTH-172001 | 2017-01-10 | EMAIL-170110-01 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9694450a-41f4-41e8-a797-7cb43f0f6c12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
938 | T16182-XB02-P8UTH-172003 | 2017-01-10 | EMAIL-170110-01 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfb01c3f-ec05-4519-91dc-0de2c0b13635 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
939 | T16182-XB02-P8UTH-172004 | 2017-01-10 | EMAIL-170110-01 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecaae6c4-1452-4b83-b740-40b073a334d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
279 | T16182-YT10-P0BAU-152503 | 2017-01-11 | EMAIL-170111-02 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a9bc907-6430-49bd-a969-cc90c5fda85f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
280 | T16182-YE03-P0BAU-152504 | 2017-01-11 | EMAIL-170111-02 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5f5912c-aa80-415e-a998-92df2b0f1bc3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
44 | T16182-XW03-P0LA-110048 | 2017-01-11 | EMAIL-170111-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de7779fa-2b1f-46b6-b63c-aa7dec7505a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
45 | T16182-XW03-P0LA-110049 | 2017-01-11 | EMAIL-170111-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e063c623-6f68-4af6-868f-f47f2572a53b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
693 | T16182-XB00-P6MKA-250001 | 2017-01-12 | EMAIL-170112-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98d15ed1-e413-4a44-917e-48776cfd358a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
694 | T16182-XB00-P7MKA-250002 | 2017-01-12 | EMAIL-170112-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=735ce570-6aaa-491b-b8f9-a4611396a2a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
695 | T16182-UF00-P6MKA-250003 | 2017-01-12 | EMAIL-170112-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bc9df75-e400-4e52-a7db-d21805204f89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
696 | T16182-YD00-P0MKA-250004 | 2017-01-12 | EMAIL-170112-01 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1097 | T16182-UF00-P6MKA-250003 | 2017-01-18 | EMAIL-170118-04 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19bb2125-00ef-479d-b08a-4c3a7e4bb553 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1263 | T16182-CA00-P0UBA-181201 | 2017-01-18 | EMAIL-170118-07 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f03c9319-2edf-4109-b8b8-83eaad60784a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1264 | T16182-CA00-P0UBA-181202 | 2017-01-18 | EMAIL-170118-07 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=862fbcd0-c43f-41ed-99f9-5c8c72590bb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1265 | T16182-CA00-P0UBA-181203 | 2017-01-18 | EMAIL-170118-07 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad2d1ac0-0430-4c86-9b89-eaf1bb1871ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1266 | T16182-CA00-P0UBA-181204 | 2017-01-18 | EMAIL-170118-07 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15d6694a-7cec-44af-9bb9-cd143cb5dd5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1267 | T16182-CA00-P0UBA-181205 | 2017-01-18 | EMAIL-170118-07 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f72f8696-f2de-49b8-b808-f893a6bbd2d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1291 | T16182-CA07-P0ZEN-189000 | 2017-01-18 | EMAIL-170118-02 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6327655c-fc63-4261-9414-b21676ffe5b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1333 | T16182-CA00-P0UCB-180601 | 2017-01-18 | EMAIL-170118-08 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe06a37b-c4ce-4136-be8d-8175d450d319 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1334 | T16182-CA00-P0UCB-180602 | 2017-01-18 | EMAIL-170118-08 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5e833c8-4dcf-4ed2-b1ff-9d4369a09231 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1335 | T16182-CA00-P0UCB-180603 | 2017-01-18 | EMAIL-170118-08 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39dbafab-b1df-418b-ba65-39d6072ccdbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1336 | T16182-CA00-P0UCB-180604 | 2017-01-18 | EMAIL-170118-08 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da10a263-c3d5-4f5a-98cd-9c119dd6f035 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1337 | T16182-CA00-P0UCB-180605 | 2017-01-18 | EMAIL-170118-08 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47e1c1ac-a251-4da4-ac49-811f77187726 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1338 | T16182-CA00-P0UCB-180606 | 2017-01-18 | EMAIL-170118-08 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed4919c1-74fe-4368-a277-961064297cd6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
250 | T16182-YL06-P0ZEN-150101 | 2017-01-18 | EMAIL-170118-06 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f8b4ee8-5a3d-4fbf-8c63-61b51e01f07b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
281 | T16182-YE03-P0BAU-152505 | 2017-01-18 | EMAIL-170118-01 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdbe1de0-7835-42a3-964c-6ff4519eb106 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
357 | T16182-YD00-P0CWQ-161406 | 2017-01-18 | EMAIL-170118-05 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ff8c512-568d-46b0-b63c-899b7eb80e29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
703 | T16182-YD00-P6MKA-250016 | 2017-01-18 | EMAIL-170118-04 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66db350a-9220-461d-a931-ae8795fc3bd9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
736 | T16182-UC07-P0ZEN-100001 | 2017-01-18 | EMAIL-170118-09 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85e73808-314f-4440-96c3-6894dece391b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
737 | T16182-UC07-P0ZEN-100002 | 2017-01-18 | EMAIL-170118-09 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef5a97eb-c8e5-45c0-a790-517cf9501357 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
738 | T16182-UC07-P0ZEN-100003 | 2017-01-18 | EMAIL-170118-09 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be18d447-c3dc-43df-8f31-e2dc36761bbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
827 | T16182-YD00-P0UCA-150501 | 2017-01-18 | EMAIL-170118-06 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a558dbbd-f50c-4580-adc2-f6643c9b44d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
828 | T16182-YD00-P0UBA-150502 | 2017-01-18 | EMAIL-170118-06 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc666c7b-1b1f-4bfa-881b-88e61ccc5448 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
869 | T16182-YF02-P0ZEN-161031 | 2017-01-18 | EMAIL-170118-03 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d5cafad-374e-4323-9db8-9b4b6ca54aa1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
875 | T16182-YD00-P0CWQ-161401 | 2017-01-18 | EMAIL-170118-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc62e776-3b0a-417b-ab70-25bfb3519e66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
876 | T16182-YD00-P0CWQ-161402 | 2017-01-18 | EMAIL-170118-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95ac6e22-a28a-4dd3-bb21-be579a0c964f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
877 | T16182-YD00-P0CWQ-161403 | 2017-01-18 | EMAIL-170118-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb0488b8-ea43-4aaf-b65b-166c821213c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
878 | T16182-YD00-P0CWQ-161404 | 2017-01-18 | EMAIL-170118-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e4e5f13-7bf2-424e-811f-1b5816a3adde | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
879 | T16182-YD00-P0CWQ-161405 | 2017-01-18 | EMAIL-170118-05 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8386c3d-0d37-4738-8aef-aecc135d0b90 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
278 | T16182-DE00-P0BAU-152502 | 2017-01-19 | EMAIL-170119-01 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da208bd8-77ea-4d5e-9aac-3589349e4efc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1199 | T16182-VE04-P0ZEN-170103 | 2017-01-20 | EMAIL-170120-02 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b6eea03-6b02-4058-b580-dc2e5849382e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1201 | T16182-VE04-P0UHA-171801 | 2017-01-20 | EMAIL-170120-01 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7babef1f-d203-4f55-85c5-d505299bb737 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1202 | T16182-XB02-P0UHA-171803 | 2017-01-20 | EMAIL-170120-01 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=634e5556-b35f-44d1-91b6-6f93d904470e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1203 | T16182-XB02-P0UHA-171804 | 2017-01-20 | EMAIL-170120-01 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00486c9d-471d-4cd5-8e5a-044c3f722f03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
258 | T16182-YD00-P0UBA-150503 | 2017-01-20 | EMAIL-170120-03 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03f270a1-7244-461b-99a5-714afb73b0b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
293 | T16182-YE00-P0ZEN-152754 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9480e978-bf81-4e2b-83ea-564a21c65ad2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
294 | T16182-YE00-P0ZEN-152755 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bc1bf45-ed38-41e7-ab45-e8b50580cc8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
295 | T16182-YE00-P0ZEN-152756 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4c98ee8-271d-460f-882c-deede584cc01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
296 | T16182-YE00-P0ZEN-152757 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6999fb30-3c4b-4b6e-a18a-36053c2e3e1a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
297 | T16182-YE00-P0ZEN-152758 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f36d5b5-8c06-445a-bff0-7cfccc686b4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
298 | T16182-YE00-P0ZEN-152759 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7324b95-ea74-4194-b8be-c0616165d591 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
299 | T16182-YE00-P0ZEN-152760 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d631cde2-046d-49be-9ff3-6311159f2b5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
300 | T16182-YE00-P0ZEN-152761 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e479bf6c-cf77-4a80-8319-be2261c1e011 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
301 | T16182-YE00-P0ZEN-152762 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a825572-03d7-447d-a9aa-a716135fd4f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
302 | T16182-YE00-P0ZEN-152763 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e857d897-f345-4e50-969c-ee1c2ba324f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
303 | T16182-YE00-P0ZEN-152764 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd3a201e-9c53-4d4d-b847-2e5895809854 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
304 | T16182-YE00-P0ZEN-152765 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74675b82-cc9b-41a8-a10f-0f7d6fba1047 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
305 | T16182-YE00-P0ZEN-152766 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2231fdac-b41d-435d-8d91-5a462563ba08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
306 | T16182-YE00-P0ZEN-152767 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da2652e0-ed25-4bb0-9a98-a4d7efa2af53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
307 | T16182-YE00-P0ZEN-152768 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c65df96-4183-4b45-9014-3a925b190318 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
308 | T16182-YE00-P0ZEN-152769 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7783b8a-aecb-4ca3-87e7-899b4f6ba167 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
309 | T16182-YE00-P0ZEN-152770 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd36d832-cbdd-4190-810c-162aad179548 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
310 | T16182-YE00-P0ZEN-152771 | 2017-01-20 | EMAIL-170120-04 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b82a5ea5-986f-4c0c-88a0-ab5c3053e62b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
920 | T16182-VK02-P0ZEN-170104 | 2017-01-20 | EMAIL-170120-02 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6e6e319-b5f0-4f09-973b-20de65f12b70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1161 | T16182-YD16-P0ZEN-152003 | 2017-01-25 | FCHPP-DH-FPCC-T-0007 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f89a18d-e822-4185-99a6-7cef7fb65417 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1204 | T16182-VE04-P8UTH-172001 | 2017-01-25 | FCHPP-DH-FPCC-T-0004 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc493d81-c984-42af-a431-efecf56d0156 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1205 | T16182-XB02-P8UTH-172003 | 2017-01-25 | FCHPP-DH-FPCC-T-0004 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3b3f06a-1740-4008-b048-d9cd1ba91fae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1206 | T16182-XB02-P8UTH-172004 | 2017-01-25 | FCHPP-DH-FPCC-T-0004 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15dd2ff3-b829-4b83-8f07-2bbdb03ec394 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1262 | T16182-CA06-P0UBA-181200 | 2017-01-25 | FCHPP-DH-FPCC-T-0001 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ac8c9cb-ce34-45aa-9668-b466f35db3af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1268 | T16182-CA01-P0UBA-181251 | 2017-01-25 | FCHPP-DH-FPCC-T-0001 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3796685d-fc22-4650-b742-c56140e39408 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1269 | T16182-CA01-P0UBA-181252 | 2017-01-25 | FCHPP-DH-FPCC-T-0001 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1f92421-98a9-4b9b-881b-a9e35c4f806c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1270 | T16182-CA01-P0UBA-181253 | 2017-01-25 | FCHPP-DH-FPCC-T-0001 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=180aa5e7-6c32-435d-8b02-ac719252ede5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1271 | T16182-CA01-P0UBA-181254 | 2017-01-25 | FCHPP-DH-FPCC-T-0001 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2526b2a7-9dd3-4456-aedb-74e5780a0776 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1273 | T16182-CA02-P0UBA-181257 | 2017-01-25 | FCHPP-DH-FPCC-T-0001 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7387ac22-88f5-4eff-b18b-9da669c72d94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1274 | T16182-CA02-P0UBA-181258 | 2017-01-25 | FCHPP-DH-FPCC-T-0001 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f196162-46cc-4e69-8448-086a6c6a8bb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1332 | T16182-CA06-P0UCB-180600 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ad4a13c-79d3-4c3a-acf4-b5c2d78743b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1339 | T16182-CA01-P0UCB-180651 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03817ac5-6223-494b-82f3-8363e2fea3d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1340 | T16182-CA01-P0UCB-180652 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ce2c652-e738-43a4-bc5b-f00f176eb28e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1341 | T16182-CA01-P0UCB-180653 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9b969d0-bc32-48cb-ad83-8bcf1d81e183 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1342 | T16182-CA01-P0UCB-180654 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74b10d1e-08d3-40a5-b890-f1a5c2b6b3f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1343 | T16182-CA01-P0UCB-180655 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61826a44-35b1-40ea-9f4a-22e352f65457 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1344 | T16182-CA01-P0UCB-180656 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fca6f541-6256-4b99-b317-3ee55bcb24ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1345 | T16182-CA01-P0UCB-180657 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5429d14a-986d-47ce-8eb2-bb4fc56a5ac8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1346 | T16182-CA02-P0UCB-180664 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2271756-322f-4087-b30c-8e7835922b0d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1347 | T16182-CA02-P0UCB-180665 | 2017-01-25 | FCHPP-DH-FPCC-T-0002 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd603f79-9267-489a-aadf-597d3ee60ddc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
260 | T16182-YT10-P0BAT-150601 | 2017-01-25 | FCHPP-DH-FPCC-T-0006 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0394190-39b4-43d6-8e37-7bcd464aa12f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
277 | T16182-YE04-P0BAU-152501 | 2017-01-25 | FCHPP-DH-FPCC-T-0005 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=002f8c5e-5a87-49cf-8abd-fa4d362cde87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
282 | T16182-YE03-P0BAU-152506 | 2017-01-25 | FCHPP-DH-FPCC-T-0005 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f8c8622-be39-4b3d-a834-cecd2de06368 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
429 | T16182-VE04-P0MPA-171101 | 2017-01-25 | FCHPP-DH-FPCC-T-0003 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
432 | T16182-XB02-P0MPA-171104 | 2017-01-25 | FCHPP-DH-FPCC-T-0003 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
433 | T16182-XB02-P0MPA-171105 | 2017-01-25 | FCHPP-DH-FPCC-T-0003 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
455 | T16182-VK02-P8UTH-172005 | 2017-01-25 | FCHPP-DH-FPCC-T-0004 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3604fbf4-fa89-4fb7-8fe2-bd3c9f1a57e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
690 | T16182-VL00-P0MPA-220001 | 2017-01-25 | FCHPP-DH-FPCC-T-0003 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01d4423c-f554-4d3b-9b01-625d65982e49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
691 | T16182-CA07-P0MPA-220023 | 2017-01-25 | FCHPP-DH-FPCC-T-0003 | IFI | 0 | D | TRUE | FALSE | 2017-08-07_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68d883c0-5fcf-4a2d-89b3-e8335e2b6231 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
692 | T16182-UF00-P0MAA-220003 | 2017-01-25 | FCHPP-DH-FPCC-T-0003 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f06eb597-a589-465d-a60f-c201ad86aaa4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
834 | T16182-YQ02-P0ZEN-152001 | 2017-01-25 | FCHPP-DH-FPCC-T-0007 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54a699bd-28d0-47e0-9efe-27a746564731 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
194 | T16182-XW01-P0SAA-133301 | 2017-01-26 | FCHPP-DH-FPCC-T-0008 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b228d7fe-4ab9-470a-8e8f-f898f2c66a66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
195 | T16182-YK09-P0SAA-133302 | 2017-01-26 | FCHPP-DH-FPCC-T-0008 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d0e2af3-eff9-4be2-9156-f9fb740fdab4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
270 | T16182-YQ01-P0ZEN-152201 | 2017-01-26 | FCHPP-DH-FPCC-T-0009 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa962be0-3821-437a-90c4-42e960ff48e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
518 | T16182-CA03-P0UMA-180459 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc9a05eb-529c-4602-b13c-bacbf44dfb9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
526 | T16182-CA06-P0UMA-180491 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad575ea8-9752-4fda-97af-17c413e672c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
612 | T16182-CA00-P0UGD-181901 | 2017-01-26 | FCHPP-DH-FPCC-T-0012 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
613 | T16182-CA00-P0UGD-181902 | 2017-01-26 | FCHPP-DH-FPCC-T-0012 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
614 | T16182-CA00-P0UGD-181903 | 2017-01-26 | FCHPP-DH-FPCC-T-0012 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
615 | T16182-CA00-P0UGD-181904 | 2017-01-26 | FCHPP-DH-FPCC-T-0012 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
616 | T16182-CA00-P0UGD-181905 | 2017-01-26 | FCHPP-DH-FPCC-T-0012 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
844 | T16182-YE00-P0ZEN-152750 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
845 | T16182-YE00-P0ZEN-152751 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
846 | T16182-YE00-P0ZEN-152752 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
847 | T16182-YE00-P0ZEN-152753 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
848 | T16182-YE00-P0ZEN-152754 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
849 | T16182-YE00-P0ZEN-152755 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
850 | T16182-YE00-P0ZEN-152756 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
851 | T16182-YE00-P0ZEN-152757 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
852 | T16182-YE00-P0ZEN-152758 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
853 | T16182-YE00-P0ZEN-152759 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
854 | T16182-YE00-P0ZEN-152760 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
855 | T16182-YE00-P0ZEN-152761 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
856 | T16182-YE00-P0ZEN-152762 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
857 | T16182-YE00-P0ZEN-152763 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
858 | T16182-YE00-P0ZEN-152764 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
859 | T16182-YE00-P0ZEN-152765 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
860 | T16182-YE00-P0ZEN-152766 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
861 | T16182-YE00-P0ZEN-152767 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
862 | T16182-YE00-P0ZEN-152768 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
863 | T16182-YE00-P0ZEN-152769 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
864 | T16182-YE00-P0ZEN-152770 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
865 | T16182-YE00-P0ZEN-152771 | 2017-01-26 | FCHPP-DH-FPCC-T-0010 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
975 | T16182-CA00-P0UMA-180401 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9761c285-e7a7-40fd-a864-017434d8362e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
976 | T16182-CA00-P0UMA-180402 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c024c21b-2974-4341-9453-8b45a1f9ad73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
977 | T16182-CA00-P0UMA-180403 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc81702f-84cf-41b0-8d54-ff0a2c663e01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
978 | T16182-CA00-P0UMA-180404 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd740a1a-6cc4-42c7-94dc-9b11fe278a99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
979 | T16182-CA01-P0UMA-180451 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ff06152-2d6a-4397-8619-a09c4405b4de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
980 | T16182-CA01-P0UMA-180452 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
981 | T16182-CA01-P0UMA-180454 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56c7b4f3-f3be-4595-8484-c3f29854a5ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
982 | T16182-CA03-P0UMA-180458 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e11b13d-994e-4b84-9e6d-3f47e5507771 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
984 | T16182-CA03-P0UMA-180460 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dec6a348-de59-43ba-9ec0-17b789b4813e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
985 | T16182-CA03-P0UMA-180462 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d480082-4ae5-4c46-8e8d-1b1708975239 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
986 | T16182-CA03-P0UMA-180463 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bcf81a1c-a26d-4161-8f15-194d6d102153 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
987 | T16182-CA03-P0UMA-180468 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a236f97c-cb36-4b8e-a89d-fe6878b07959 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
988 | T16182-CA06-P0UMA-180490 | 2017-01-26 | FCHPP-DH-FPCC-T-0011 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bd1d8db-c34b-428f-99f8-223083bbe881 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
246 | T16182-CV03-P0ZEN-140001 | 2017-02-01 | FCHPP-DH-FPCC-T-0016 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=060bde8c-b993-4038-a761-496570ecf1c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
247 | T16182-CV03-P0ZEN-140002 | 2017-02-01 | FCHPP-DH-FPCC-T-0016 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b84df51-6739-4151-8e4b-789e0e638133 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
251 | T16182-YU02-P0ZEN-150201 | 2017-02-01 | FCHPP-DH-FPCC-T-0013 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
289 | T16182-DE00-P0ZEN-152701 | 2017-02-01 | FCHPP-DH-FPCC-T-0014 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b670bd65-eb36-433e-a33c-9c27f399c171 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
331 | T16182-YR04-P0CUQ-161111 | 2017-02-01 | FCHPP-DH-FPCC-T-0015 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7865b7c9-d11e-415b-89f8-eacfad1a7a07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1360 | T16182-CA07-P0ZEN-189000 | 2017-02-02 | FCHPP-DH-FPCC-T-0019 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=179ab2b8-403c-4683-825d-85fc142eab11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
266 | T16182-YT10-P0BAA-150701 | 2017-02-02 | FCHPP-DH-FPCC-T-0018 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0818533f-a4bd-4307-afa1-1c23f1a87881 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
361 | T16182-YL00-P0ZEN-163101 | 2017-02-02 | FCHPP-DH-FPCC-T-0017 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6baed25-1f22-445e-b479-d78e1709e3ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1200 | T16182-VK02-P0ZEN-170104 | 2017-02-03 | FCHPP-DH-FPCC-T-0022 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94ab6f6c-392a-4aab-b5ce-ebd7ad1d2ade | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
593 | T16182-CA05-P0UBA-181281 | 2017-02-03 | FCHPP-DH-FPCC-T-0020 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e18923b-c43f-434b-81e5-0b3cbadb6289 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
594 | T16182-CA05-P0UBA-181282 | 2017-02-03 | FCHPP-DH-FPCC-T-0020 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc9a3ad4-6fd2-4993-b0ca-97f0c885d98d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
595 | T16182-CA05-P0UBA-181284 | 2017-02-03 | FCHPP-DH-FPCC-T-0020 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=884f5ed9-0b26-46f5-b629-10bf445d4a61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
311 | T16182-YR02-P0ZEN-152801 | 2017-02-06 | FCHPP-DH-FPCC-T-0024 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99768ae5-0865-4814-8e0a-0e5de37fb67e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
611 | T16182-CA06-P0UGD-181900 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08858f91-97d1-4773-9cb6-290467c0187f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
618 | T16182-CA01-P0UGD-181951 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbb61fc5-899e-4bc7-9fc3-6763d8fa96a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
619 | T16182-CA01-P0UGD-181952 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49200482-173e-4f06-a13e-6beb7e51cd53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
620 | T16182-CA01-P0UGD-181953 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f4d2a85-c42c-44c3-ba60-fce24885ad2c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
621 | T16182-CA01-P0UGD-181954 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=286eaedf-4a07-4113-af31-5972b9aa9643 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
622 | T16182-CA01-P0UGD-181955 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55d14dfc-8157-4e82-9429-3a2d9f929e18 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
625 | T16182-CA02-P0UGD-181958 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0fb10c4b-4925-4801-9843-1cf291b4cca2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
626 | T16182-CA02-P0UGD-181959 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3281ca2-38b4-4246-b584-46294857d87b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
632 | T16182-CA03-P0UGD-181965 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fffb7cc-f35d-482b-aa1d-09290ca144b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
633 | T16182-CA03-P0UGD-181966 | 2017-02-06 | FCHPP-DH-FPCC-T-0023 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=761384f6-5d6d-4b2d-ae20-739816efd722 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
734 | T16182-DA01-P0ZEN-020001 | 2017-02-06 | FCHPP-DH-FPCC-T-0025 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adcb2002-8d2f-499c-8806-05268bc56d4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
735 | T16182-DA01-P0ZEN-020002 | 2017-02-06 | FCHPP-DH-FPCC-T-0025 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab216f55-66b1-4b95-8ee4-01d062252941 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
392 | T16182-YK00-P0ZEN-165311 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bf599cf-af7b-4fbd-a8e7-89eb4549fec0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
393 | T16182-YK00-P0ZEN-165312 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3318660-de94-4c39-8428-83922484b885 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
394 | T16182-YK00-P0ZEN-165313 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=064096c7-2177-4c52-bd71-97fae656390d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
395 | T16182-YK00-P0ZEN-165314 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44634701-529a-459d-a7e2-f37312adfc17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
396 | T16182-YK00-P0ZEN-165315 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04593108-b3ee-4be6-9ff1-8ce4c4c0180c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
397 | T16182-YK00-P0ZEN-165316 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d04ec1a3-3a14-4f29-8227-c8852e1bdced | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
398 | T16182-YK00-P0ZEN-165317 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16b06c62-8791-48ac-885a-9f2552613058 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
399 | T16182-YK00-P0ZEN-165318 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9725fedb-4ae7-4dd3-845f-1b8d45da8f41 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
400 | T16182-YK00-P0ZEN-165319 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=518aed85-9e55-4d9a-ba40-0bdd7c59d1ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
401 | T16182-YK00-P0ZEN-165320 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1002904-f275-4d43-8fa9-8920516db1c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
402 | T16182-YK00-P0ZEN-165321 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=015d03a4-7910-4376-8c53-bec904406433 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
403 | T16182-YK00-P0ZEN-165322 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79eab753-437f-4013-a6da-c2c1b61866ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
404 | T16182-YK00-P0ZEN-165323 | 2017-02-08 | T16182-DHI-LI-T-0027 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a40110d-a569-4b37-8961-62b09371b04b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1111 | T16182-UC07-P0ZEN-100001 | 2017-02-09 | T16182-DHI-LI-T-0040 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c739e3d-520b-4e0f-9023-f563dadc9897 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1112 | T16182-UC07-P0ZEN-100002 | 2017-02-09 | T16182-DHI-LI-T-0040 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5edc36d5-987c-4a9b-a793-c35b8d5132bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1113 | T16182-UC07-P0ZEN-100003 | 2017-02-09 | T16182-DHI-LI-T-0040 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3040dd8-751a-4b90-b643-6a7510e6283a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1323 | T16182-VE04-P0ZEN-170103 | 2017-02-09 | T16182-DHI-LI-T-0039 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7e7fe87-f228-4671-9571-446cb2b21413 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1325 | T16182-VE04-P0UHA-171801 | 2017-02-09 | T16182-DHI-LI-T-0035 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9f031ce-453a-421c-896b-5dc25ea7869a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1326 | T16182-XB02-P0UHA-171803 | 2017-02-09 | T16182-DHI-LI-T-0035 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77d40a3e-504c-4644-8734-ac67aa86ce5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1327 | T16182-XB02-P0UHA-171804 | 2017-02-09 | T16182-DHI-LI-T-0035 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48d7fa0f-9579-468c-96e9-212f0e342f5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1365 | T16182-CA06-P0UCB-180600 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36c50af9-926a-423a-8eff-7974e6581d23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1366 | T16182-CA00-P0UCB-180601 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82ce87cd-137a-4658-8189-551ff3b51f13 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1367 | T16182-CA00-P0UCB-180602 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d757e682-8f18-4bec-9e38-005c4a6acf0d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1368 | T16182-CA00-P0UCB-180603 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=474f2878-4016-48b9-878e-569c82a68d7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1369 | T16182-CA00-P0UCB-180604 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ccce0e9-7702-4e70-9341-fa412b49bb08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1370 | T16182-CA00-P0UCB-180605 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f65f8b78-bea3-41eb-a42b-04ed567281d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1371 | T16182-CA00-P0UCB-180606 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5ebdc0f-a8bf-48e8-9b96-36b85394e086 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1372 | T16182-CA01-P0UCB-180651 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6da0be7-2896-40af-9019-3c3fd0b08922 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1373 | T16182-CA01-P0UCB-180652 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8256580-0577-4ff7-810e-034221de1eb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1374 | T16182-CA01-P0UCB-180653 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa0c4e38-317c-40f3-8f1a-3a87d7eae441 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1375 | T16182-CA01-P0UCB-180654 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8985d2c7-a617-495e-9a29-5b72c949c5be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1376 | T16182-CA01-P0UCB-180655 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8c6282e-99cc-4f30-a7fc-5fb21f53eced | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1377 | T16182-CA01-P0UCB-180656 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2da4e22c-144c-4cb7-9389-f2a38d274e05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1378 | T16182-CA01-P0UCB-180657 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5063953d-136e-4920-8d44-f9dc51a919d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1379 | T16182-CA02-P0UCB-180664 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54c5a6ab-1b30-4260-b77a-33551b6b9d98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1380 | T16182-CA02-P0UCB-180665 | 2017-02-09 | T16182-DHI-LI-T-0032 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d78e6c85-f969-41c7-aa5d-6d0e29dd0c57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
253 | T16182-YU02-P0ZEN-150211 | 2017-02-09 | T16182-DHI-LI-T-0029 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=445ec331-4394-4751-8d8f-d66ae4e5fe33 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
363 | T16182-YS00-P0ZEN-163301 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1c33053-f71e-408a-bc62-cfa34395698f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
364 | T16182-YS00-P0ZEN-163302 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1967911-50c8-4698-84b6-785a4f6da442 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
365 | T16182-YS00-P0ZEN-163303 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6c7f13a-bc78-480d-9351-325784611fce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
366 | T16182-YS00-P0ZEN-163304 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63980b07-1a67-4059-89e1-7423ac12a989 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
367 | T16182-YS00-P0ZEN-163305 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18d2e590-9d6f-477d-90f5-9b258009ea8a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
368 | T16182-YS00-P0ZEN-163306 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97da713c-7d8b-4595-9c3d-0531d47bfd00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
369 | T16182-YS00-P0ZEN-163307 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b44907fd-8b08-407c-9011-b19a3a760897 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
370 | T16182-YS00-P0ZEN-163308 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee568005-c0f1-43cc-a292-3e8b8e27a0b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
371 | T16182-YS00-P0ZEN-163309 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc30b494-242c-41d7-b788-7fe14c86252d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
372 | T16182-YS00-P0ZEN-163310 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c24bd7b-3f27-4d60-97e6-326913534f7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
373 | T16182-YS00-P0ZEN-163311 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aab22db2-f790-4130-b75c-59ccecabd879 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
374 | T16182-YS00-P0ZEN-163312 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79497156-e395-4e49-b3fc-cc8d08079a20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
375 | T16182-YS00-P0ZEN-163313 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d66de3a-e43e-4861-824c-f97025659166 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
376 | T16182-YS00-P0ZEN-163314 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=764ac16c-d578-43cd-bd30-93de1154a1d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
377 | T16182-YS00-P0ZEN-163315 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eadd5565-7242-4ad7-8d76-444efb7fe310 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
378 | T16182-YS00-P0ZEN-163316 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d6f458b-355c-4274-a0a9-dda266fbd7ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
379 | T16182-YS00-P0ZEN-163317 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=827c0f1d-9a73-4077-8ef9-88b92dba8a06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
380 | T16182-YS00-P0ZEN-163318 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9fed76d-f055-442b-b9b5-0f26fd609776 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
381 | T16182-YS00-P0ZEN-163319 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efb9fad7-d2f8-4fb1-8348-24b0aec43ae3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
382 | T16182-YS00-P0ZEN-163320 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18048777-30b6-42ad-b85f-3f405f55d3d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
383 | T16182-YS00-P0ZEN-163321 | 2017-02-09 | T16182-DHI-LI-T-0030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4974e1d5-f72e-4ed6-bf11-10a316438701 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
430 | T16182-VE04-P0MPA-171102 | 2017-02-09 | T16182-DHI-LI-T-0028 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f05a3477-8ed0-4ff2-b3b9-02efff699ede | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
555 | T16182-CA05-P0UCB-180681 | 2017-02-09 | T16182-DHI-LI-T-0036 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b791f62-6fdf-48e1-b1ac-4381e030c41c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
556 | T16182-CA05-P0UCB-180682 | 2017-02-09 | T16182-DHI-LI-T-0036 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=570c4bdd-7b87-40dd-904c-8066689906b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
557 | T16182-CA05-P0UCB-180683 | 2017-02-09 | T16182-DHI-LI-T-0036 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=506ec71f-8c4e-4095-a8cb-9edcb3a289b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
558 | T16182-CA05-P0UCB-180684 | 2017-02-09 | T16182-DHI-LI-T-0036 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f6fb53e-92e9-439a-a2cc-7f871b2d038c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
559 | T16182-CA05-P0UCB-180685 | 2017-02-09 | T16182-DHI-LI-T-0036 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e778e48-ee04-4d44-95d3-ed8dace151f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
560 | T16182-CA05-P0UCB-180686 | 2017-02-09 | T16182-DHI-LI-T-0036 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69cfa199-95aa-4499-b235-06fc7265ae09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
561 | T16182-CA05-P0UCB-180687 | 2017-02-09 | T16182-DHI-LI-T-0036 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=191acb37-0ac2-4280-a9ac-bd750771bb8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
596 | T16182-CA06-P0UBA-181300 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=323591c1-03a9-4036-a392-e21e5cb76611 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
597 | T16182-CA00-P0UBA-181301 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=114a1158-4266-4e7e-a91e-c25b428cc3f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
598 | T16182-CA00-P0UBA-181302 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5065b6bd-e097-4743-a864-cf039f22db48 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
599 | T16182-CA00-P0UBA-181303 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7ee3ca9-b941-4454-9ebe-29622f4e6362 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
600 | T16182-CA00-P0UBA-181304 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1781151-5ec5-4900-aae6-6f21dce279e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
601 | T16182-CA00-P0UBA-181305 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee3583ef-6bf9-4fd5-a64f-456394ef0b4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
602 | T16182-CA01-P0UBA-181351 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f13bbd09-cf00-4c1a-a8f5-f958022e61f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
603 | T16182-CA01-P0UBA-181352 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a173e12-db33-419a-94d5-8151deb8f0ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
604 | T16182-CA01-P0UBA-181353 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0730f26-f25a-4170-b827-1063d95cbb29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
605 | T16182-CA01-P0UBA-181354 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0854a7b8-04f7-42e4-9a45-2accb38925fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
606 | T16182-CA02-P0UBA-181357 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4617530-83ba-46c8-b065-8c83eeed8052 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
607 | T16182-CA02-P0UBA-181358 | 2017-02-09 | T16182-DHI-LI-T-0026 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51f3da7b-622c-4dc9-a43e-d23981590ded | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
796 | T16182-UE00-P0LB-122007 | 2017-02-09 | T16182-DHI-LI-T-0038 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05fb6751-593c-45f5-b9ae-998c0af3c9f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
797 | T16182-XB02-P0LB-122016 | 2017-02-09 | T16182-DHI-LI-T-0037 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa125908-7431-4083-b5f6-f4ae451dadd7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
798 | T16182-XB02-P0LB-122017 | 2017-02-09 | T16182-DHI-LI-T-0037 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07c1d092-f898-47cc-9454-6a7dc3393021 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
954 | T16182-CC05-P0ZEN-180001 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41d2cca9-21ff-417e-87b6-a51022b52ed9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
955 | T16182-CC05-P0ZEN-180002 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1603c912-c6b8-4475-867c-49efe030dc14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
956 | T16182-CC05-P0ZEN-180006 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dc4d796-522c-46bf-9381-b68134ade90b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
957 | T16182-CC05-P0ZEN-180008 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c09190f7-0053-40ad-81be-24ffb88588c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
958 | T16182-CC05-P0ZEN-180019 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eabac81a-6001-40e5-b2b7-2a349ac0eb16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
959 | T16182-CC05-P0ZEN-180020 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61bf4db8-3a94-4518-a6e9-85cdada4bb0b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
960 | T16182-CC05-P0ZEN-180024 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e142f335-174b-48ba-a8d7-7e3d537e5bf7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
961 | T16182-CC05-P0ZEN-180025 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d3af83e-36b4-4352-a56e-d76b0566a68d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
962 | T16182-CC05-P0ZEN-180030 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acac66ab-921c-46f8-be88-976329850762 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
963 | T16182-CC05-P0ZEN-180033 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=433813c1-f0c3-45f9-af1b-db48778d63c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
964 | T16182-CC05-P0ZEN-180034 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dacdf574-1f8a-4f8e-a9ed-bbc1540224ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
965 | T16182-CC05-P0ZEN-180035 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de786c02-40af-46db-842b-81bae335992d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
966 | T16182-CC05-P0ZEN-180036 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62fae213-57b0-49e5-a112-7134cd5ab406 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
967 | T16182-CC05-P0ZEN-180037 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c6f355a-b57f-4fd8-a616-4b61d056fcd7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
968 | T16182-CC05-P0ZEN-180038 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dd6751c-b5d8-4944-a7d3-4753f1a5a6cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
969 | T16182-CC05-P0ZEN-180039 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f0e3019-b378-419b-bc30-edf5b3b55fee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
970 | T16182-CC05-P0ZEN-180040 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11807e40-3a0f-45c3-8440-7946aacc1851 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
971 | T16182-CC05-P0ZEN-180041 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=782a1e7a-07b3-44fa-acaf-6a0a01136bf1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
972 | T16182-CC05-P0ZEN-180042 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8f7d667-33fc-45c7-94da-8d90eff17ab4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
973 | T16182-CC05-P0ZEN-180043 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3bc04d4-cf12-429c-8046-5f64e9e3e412 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
974 | T16182-CC05-P0ZEN-180044 | 2017-02-09 | T16182-DHI-LI-T-0031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b062e97-a99d-4629-b2f7-69b36d661959 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1068 | T16182-CA01-P0ULA-182151 | 2017-02-10 | T16182-DHI-LI-T-0033 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5873066-72ee-4a15-a040-5dc10cf40ecf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1070 | T16182-CA03-P0ULA-182153 | 2017-02-10 | T16182-DHI-LI-T-0033 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=338ad8dc-56ad-4844-b778-76562bc35134 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1073 | T16182-CA03-P0ULA-182157 | 2017-02-10 | T16182-DHI-LI-T-0033 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12c9bda0-12eb-4c8a-8962-06cf25b59eab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1074 | T16182-CA06-P0ULA-182190 | 2017-02-10 | T16182-DHI-LI-T-0033 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d5ed1c8-aa51-4f71-901c-15d59b7a4d55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1233 | T16182-CA00-P0UMA-180401 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f3ee795-96c3-4282-82ec-2b3a11b50a24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1234 | T16182-CA00-P0UMA-180402 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0360d172-a490-4756-a1a0-746bbff2e07a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1235 | T16182-CA00-P0UMA-180403 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42fd8b7c-dc5c-44b9-bc10-8605cd9ce22e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1236 | T16182-CA00-P0UMA-180404 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10536b4f-2ad0-4437-b882-bf29fa39d945 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1237 | T16182-CA01-P0UMA-180451 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad378f10-dbc3-4925-8c69-b3d20fcca12d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1238 | T16182-CA01-P0UMA-180452 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bef4fee9-99ac-4127-8991-3d3c24ccf843 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1239 | T16182-CA01-P0UMA-180454 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19b01b7c-137a-4aea-b225-40e08b477d48 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1240 | T16182-CA03-P0UMA-180458 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=450ee361-d654-4d24-8c2c-a90f09c6c4f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1241 | T16182-CA03-P0UMA-180460 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=479a7a4f-3545-4017-ba56-937e3ad2d5dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1242 | T16182-CA03-P0UMA-180462 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d3c1753-f174-461e-b6ca-4d6888bf6a67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1243 | T16182-CA03-P0UMA-180463 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7377ccb-fcf2-4d2e-92ed-bcd6e30e280d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1244 | T16182-CA03-P0UMA-180468 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b5b8604-1d1a-48d8-a929-0fc6a07288ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1245 | T16182-CA06-P0UMA-180490 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52e0919c-f609-4d85-b0ac-12f967b33af6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1328 | T16182-VE04-P8UTH-172001 | 2017-02-10 | T16182-DHI-LI-T-0044 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53e8ccb9-738b-4882-85d1-94beaea7b30c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1329 | T16182-XB02-P8UTH-172003 | 2017-02-10 | T16182-DHI-LI-T-0044 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20e24deb-10ad-4473-b920-e88afaf1b5a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1330 | T16182-XB02-P8UTH-172004 | 2017-02-10 | T16182-DHI-LI-T-0044 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ca21ccc-f627-4538-a4d4-cd2c322504f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1348 | T16182-CA06-P0UBA-181200 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70855831-7c5c-4e55-9701-091b5e9bb145 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1349 | T16182-CA00-P0UBA-181201 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70cbd115-b1f5-43e1-ae2b-aac92d3cfa78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1350 | T16182-CA00-P0UBA-181202 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f03c7296-8491-4a07-82ba-1712aa4f1e21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1351 | T16182-CA00-P0UBA-181203 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0443f097-aa0c-4bdf-8394-13c87905828d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1352 | T16182-CA00-P0UBA-181204 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee6ad71e-548e-4348-8c1d-28828932f305 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1353 | T16182-CA00-P0UBA-181205 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b211f941-65d1-4e70-872e-023a9c4462ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1354 | T16182-CA01-P0UBA-181251 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bd98b65-3a88-4d46-a6d2-c9926274865a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1355 | T16182-CA01-P0UBA-181252 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a0d9bb3-710e-47d0-a32e-b27527daa93b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1356 | T16182-CA01-P0UBA-181253 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf573eef-6171-4654-a9ac-4dd85ddafdf8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1357 | T16182-CA01-P0UBA-181254 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45c932b3-c2c4-47b5-a8cb-c6dfbdf20b3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1358 | T16182-CA02-P0UBA-181257 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3621fd5-05dc-4394-816f-51c5bc0c2c73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1359 | T16182-CA02-P0UBA-181258 | 2017-02-10 | T16182-DHI-LI-T-0034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1caa68a-1b68-441d-b0f5-1af71c2e6d58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
819 | T16182-YK09-P0SAA-133302 | 2017-02-10 | T16182-DHI-LI-T-0043 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f82aab2-7d40-4f4f-9446-bf2aa09f68b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
837 | T16182-DE00-P0BAU-152502 | 2017-02-10 | T16182-DHI-LI-T-0041 | IFC | 0 | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
838 | T16182-YT10-P0BAU-152503 | 2017-02-10 | T16182-DHI-LI-T-0041 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1355259d-d05c-41bb-ba1b-214b16d8dd9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
839 | T16182-YE03-P0BAU-152504 | 2017-02-10 | T16182-DHI-LI-T-0041 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a273210-8d81-449c-8e30-2d3ce1c30913 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
940 | T16182-VK02-P8UTH-172005 | 2017-02-10 | T16182-DHI-LI-T-0044 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3023a7cf-ace0-4664-b96a-b38b8ebff361 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
983 | T16182-CA03-P0UMA-180459 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e726a81-ab6d-421b-a857-51bcb7d84280 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
989 | T16182-CA06-P0UMA-180491 | 2017-02-10 | T16182-DHI-LI-T-0042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8913f0b7-0ef8-464c-9679-88ea1c5c9410 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
78 | T16182-XS00-P0MBA-121011 | 2017-02-13 | T16182-DHI-LI-T-0045 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59ccff29-5387-4c89-a369-235fa00f4d47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
923 | T16182-VE04-P0MPA-171101 | 2017-02-13 | T16182-DHI-LI-T-0046 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88e31492-d566-42a0-8c3a-d256f0a14ec6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
926 | T16182-XB02-P0MPA-171104 | 2017-02-13 | T16182-DHI-LI-T-0046 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd02f6b2-8adc-4457-88a9-5214a49f8436 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
927 | T16182-XB02-P0MPA-171105 | 2017-02-13 | T16182-DHI-LI-T-0046 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23442eb0-1c46-4aa1-9c64-cfce4061959a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
327 | T16182-YF02-P0CRV-161102 | 2017-02-14 | T16182-DHI-LI-T-0047 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b224db3-957e-49cc-895c-c79b146f2c1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
328 | T16182-CV03-P0CRN-161103 | 2017-02-14 | T16182-DHI-LI-T-0047 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d01f773-fb03-41e7-9ca4-7031a703c90f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
329 | T16182-CV03-P0CRN-161104 | 2017-02-14 | T16182-DHI-LI-T-0047 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aad82dba-0b58-4dea-9718-5a43e785d6bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
330 | T16182-CV03-P0CRN-161105 | 2017-02-14 | T16182-DHI-LI-T-0047 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a0aedf1-6307-48c6-987e-bd8953c5d09e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
332 | T16182-YD00-P0CUQ-161112 | 2017-02-14 | T16182-DHI-LI-T-0047 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da6e5bc3-898a-4af3-b3e6-0c63966e4022 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
334 | T16182-YD00-P0CUQ-161119 | 2017-02-14 | T16182-DHI-LI-T-0047 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34e27b9d-6a80-4a00-bbdc-ed64a6acd902 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
41 | T16182-XW03-P0LB-110045 | 2017-02-14 | T16182-DHI-LI-T-0048 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c5cf3c3-6a29-4eea-a4ad-8b9f3ab3a2df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
411 | T16182-VE04-P0UMX-171001 | 2017-02-14 | T16182-DHI-LI-T-0049 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=205365a1-aeec-457b-b2d5-50ac40d5a1c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
412 | T16182-XB02-P0UMX-171002 | 2017-02-14 | T16182-DHI-LI-T-0049 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85889cdb-06e5-4e7b-9eaf-8476636c140c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
69 | T16182-YD00-P0MBA-121001 | 2017-02-14 | T16182-DHI-LI-T-0050 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52ae5ed9-edf1-4aba-ae4e-5b8fc750a3a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1069 | T16182-CA03-P0ULA-182152 | 2017-02-15 | T16182-DHI-LI-T-0051 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=867cb054-75fb-4e25-a6f1-d7103b29e0f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1071 | T16182-CA03-P0ULA-182154 | 2017-02-15 | T16182-DHI-LI-T-0051 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f983e2a-485d-4b79-a9b1-cd30eb414eba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1072 | T16182-CA03-P0ULA-182155 | 2017-02-15 | T16182-DHI-LI-T-0051 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19fe187e-2617-49b6-956c-85d615dc140f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
169 | T16182-YD00-P0GCF-130002 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed450186-c9bc-43a4-ae98-fd1b26707659 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
170 | T16182-XG07-P0GCF-130003 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c15a234-ec5a-45a3-8e84-de08383b08b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
171 | T16182-XG02-P0GCF-130004 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71862ad0-064a-4832-9814-096a78e84343 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
172 | T16182-XW03-P0GCF-130005 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3b81c9c-2c49-444d-a85c-938e35b5d3d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
186 | T16182-XS00-P0GNR-130101 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb513059-e49a-4d3d-9d7e-433961c5c7cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
187 | T16182-XG07-P0GNR-130102 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=697eca74-1115-46be-a344-922c095e6e1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
188 | T16182-XG02-P0GNR-130103 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e664864a-f41c-4f3a-a481-98dac1149d51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
189 | T16182-XW03-P0GNR-130104 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2365359-9c6a-4c2d-ba0b-927e941e7c29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
648 | T16182-CA03-P0ULA-182160 | 2017-02-15 | T16182-DHI-LI-T-0051 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6338ca8-24ce-4522-9d3a-f6c0d9179d68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
650 | T16182-CA06-P0ULA-182191 | 2017-02-15 | T16182-DHI-LI-T-0051 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23aeea03-f599-4bf7-9e1b-07d9505ba7b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
805 | T16182-XS00-P0GCF-130001 | 2017-02-15 | T16182-DHI-LI-T-0054 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf10d0c6-2a29-40ee-a49a-51d7a498516e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
818 | T16182-XW01-P0SAA-133301 | 2017-02-15 | T16182-DHI-LI-T-0052 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4f0674c-0bed-4ce9-8eb4-10c56f8d1d36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
105 | T16182-XG02-P0LB-122022 | 2017-02-16 | T16182-DHI-LI-T-0059 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60d8fecc-6881-484a-9673-f20f4c4a4164 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
333 | T16182-YR04-P0CUQ-161118 | 2017-02-16 | T16182-DHI-LI-T-0058 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=523dd65d-12fd-441c-9ed8-3881562d0801 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
580 | T16182-CA00-P0UBA-181206 | 2017-02-16 | T16182-DHI-LI-T-0057 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef53e00c-7635-4022-b1a0-700169c94ce1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
581 | T16182-CA00-P0UBA-181207 | 2017-02-16 | T16182-DHI-LI-T-0057 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcb2a6fb-3f1a-43af-a065-186e17e419c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
582 | T16182-CA00-P0UBA-181208 | 2017-02-16 | T16182-DHI-LI-T-0057 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d510db28-4653-45a7-a01d-59cd11660f76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
587 | T16182-CA01-P0UBA-181255 | 2017-02-16 | T16182-DHI-LI-T-0057 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=028e0887-b0e6-49b9-a56a-168b34f82aa0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
588 | T16182-CA01-P0UBA-181256 | 2017-02-16 | T16182-DHI-LI-T-0057 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce083f43-a509-41dd-8c34-6242a1c90f55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
591 | T16182-CA02-P0UBA-181259 | 2017-02-16 | T16182-DHI-LI-T-0057 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e37aad30-a63a-4323-b2ea-4c456c3c29fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
592 | T16182-CA02-P0UBA-181260 | 2017-02-16 | T16182-DHI-LI-T-0057 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46f9a544-78a0-4fc1-b6a8-5430d20ad7af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
67 | T16182-XG07-P0ZEN-120050 | 2017-02-16 | T16182-DHI-LI-T-0056 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8ad02d5-5429-4684-887c-a7eb44dfa49b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
718 | T16182-YK10-P0LCP-410001 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b267a7bf-c1d6-493a-8514-1042f51ee1b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
719 | T16182-YK10-P0GHC-410011 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdbf8ac8-5ec7-40ed-8e79-a7903f99a427 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
720 | T16182-YK10-P0GKB-410021 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5740a76-dba3-48c7-b60f-8250cc972037 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
721 | T16182-YK10-P0GKB-410031 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74630dae-e33a-4cbe-951a-9409a3301f76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
722 | T16182-YT10-P0LCP-410002 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cba08a2-8af5-4ab5-ad09-14b8e6825a44 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
723 | T16182-YT10-P0GHC-410012 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75bc599e-2a08-4b0a-afdc-f70760cc2de3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
724 | T16182-YT10-P0GKB-410022 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5405033-38c0-4dcf-aab8-a1a8eedaa19c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
725 | T16182-YT10-P0GKB-410032 | 2017-02-16 | T16182-DHI-LI-T-0053 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=390737df-2e8e-499d-b7b6-aa93d6bb3594 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
90 | T16182-XS01-P0MBA-121033 | 2017-02-16 | T16182-DHI-LI-T-0055 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e91c4fc-9060-4683-8e67-a8096e9a35d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
142 | T16182-XG02-P8ZEN-125582 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db438f0e-3e5d-46e5-b2df-54c9ab12185d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
143 | T16182-XG02-P8ZEN-125583 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90a6666e-9c3a-4c66-903a-bb608a5f2aaa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
144 | T16182-XG02-P8ZEN-125584 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e32d6adb-f536-4574-bf2a-3294ae7e922d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
145 | T16182-XG02-P8ZEN-125585 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5d116da-7e7e-48bb-9969-bd08657c171f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
146 | T16182-XG02-P8ZEN-125586 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3b4c092-5cdf-4119-94e6-ebe6df561246 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
147 | T16182-XG02-P8ZEN-125587 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50be6f22-aaab-40bf-b6e5-f7ead9e2ac39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
148 | T16182-XG02-P8ZEN-125588 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daa80ab6-69c5-44e6-966a-405cf39cfec1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
149 | T16182-XG02-P8ZEN-125589 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1458b0c-8e81-41a8-8d69-4ea63c133eb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
150 | T16182-XG02-P8ZEN-125590 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94a5a958-fd7e-4456-9c7b-3fa5c17df810 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
151 | T16182-XG02-P8ZEN-125591 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dff086a2-e0c1-412f-bef7-3ec2213451c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
152 | T16182-XG02-P8ZEN-125592 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ba9f9ea-a07e-4b7b-999d-cb721115cb6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
153 | T16182-XG02-P8ZEN-125593 | 2017-02-17 | T16182-DHI-LI-T-0060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bfb8756-f9e1-4ef8-be11-02f40cfdd8f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
58 | T16182-XW03-P0GKS-120013 | 2017-02-17 | T16182-DHI-LI-T-0062 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=962d2ca3-3284-4311-8ee1-52deb08ab10d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
110 | T16182-XS00-P0LB-122037 | 2017-02-20 | T16182-DHI-LI-T-0063 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=592ac6d9-3008-4bbb-810b-9cc29247bc71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
534 | T16182-CA00-P0UCB-180607 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=392a29c8-f12f-4c2e-b51d-c565da1b71d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
535 | T16182-CA00-P0UCB-180608 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff9c1fbd-25b5-4af7-ae1f-cbecdae5246b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
546 | T16182-CA01-P0UCB-180658 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e8c278-6baf-4d23-bf70-8c7bb6e3d407 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
547 | T16182-CA01-P0UCB-180659 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c86055c3-9528-4d8c-891e-65ab7b7e07c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
548 | T16182-CA01-P0UCB-180660 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f891a9d9-85ce-4cc2-b3fd-667c57765807 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
549 | T16182-CA01-P0UCB-180661 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53dcfd0a-9007-406c-a436-1f763977b8a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
552 | T16182-CA02-P0UCB-180666 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23ebcd6d-2291-4762-ac61-07ef86a3e669 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
553 | T16182-CA02-P0UCB-180667 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69f1d10e-cdee-42dc-8bb8-c441f7b9ee49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
554 | T16182-CA02-P0UCB-180668 | 2017-02-20 | T16182-DHI-LI-T-0064 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa61ca11-0db0-44a0-bee7-b5815b07fb7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
713 | T16182-YR05-P0CJN-290002 | 2017-02-20 | T16182-DHI-LI-T-0061 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
174 | T16182-YR05-P0GCF-130007 | 2017-02-22 | T16182-DHI-LI-T-0068 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b95c16f9-2b40-4cc8-87e0-55ae6ba5f7b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
175 | T16182-XN00-P0GCF-130008 | 2017-02-22 | T16182-DHI-LI-T-0067 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd054772-7db5-471c-87b0-cf36002056ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
176 | T16182-YL00-P0GCF-130009 | 2017-02-22 | T16182-DHI-LI-T-0068 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d22f989-653a-40f6-8f68-2235c389b0a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
178 | T16182-YF02-P0GCF-130011 | 2017-02-22 | T16182-DHI-LI-T-0068 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9c282d4-7406-40e5-9f05-cd189fb7d1e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
190 | T16182-XN00-P0GNR-130105 | 2017-02-22 | T16182-DHI-LI-T-0067 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7017a5e9-4587-4e7e-b52d-716a402ad478 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
191 | T16182-YL00-P0GNR-130106 | 2017-02-22 | T16182-DHI-LI-T-0068 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53fe1bd7-c826-4a9b-ada0-2f786710cc2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
267 | T16182-YT10-P0BT-151001 | 2017-02-22 | T16182-DHI-LI-T-0066 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=863549db-7022-4284-b1fa-f14cc38ff558 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
840 | T16182-YE03-P0BAU-152505 | 2017-02-23 | T16182-DHI-LI-T-0069 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7f4d31a-d1d3-4105-908d-7e7c4475cd43 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
841 | T16182-YE03-P0BAU-152506 | 2017-02-23 | T16182-DHI-LI-T-0069 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17ac9ae6-db33-476a-8a69-5b55574031b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1123 | T16182-XG02-P0PGB-110010 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1124 | T16182-XG02-P0GHC-110011 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1128 | T16182-XG07-P0PG-110032 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1129 | T16182-XG07-P0GHC-110033 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1133 | T16182-XW01-P0PGB-110038 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1134 | T16182-XW01-P0GHC-110039 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1137 | T16182-XS00-P0PGB-110043 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1138 | T16182-XS00-P0GHC-110044 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1149 | T16182-XG02-P1MBH-110013 | 2017-02-24 | T16182-DHI-LI-T-0065 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1207 | T16182-VK02-P8UTH-172005 | 2017-02-24 | T16182-DHI-LI-T-0073 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c334489-2f3f-4a36-984d-9b6af6f37e35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
135 | T16182-YD07-P8QHA-125201 | 2017-02-24 | T16182-DHI-LI-T-0072 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1e155f2-db28-40de-b7fe-14fccee5378d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
136 | T16182-YK10-P8QHA-125202 | 2017-02-24 | T16182-DHI-LI-T-0072 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e9fa05f-fa35-4bd8-9b11-445220c4304c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
62 | T16182-XW03-P0SCA-120017 | 2017-02-24 | T16182-DHI-LI-T-0071 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0e973b2-fef9-41af-aefb-2ea6681a2915 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
873 | T16182-YR04-P0CUQ-161111 | 2017-02-24 | T16182-DHI-LI-T-0070 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8839ab7c-a485-408f-88bc-1dc2c42fdd63 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
259 | T16182-YD00-P0UBA-150506 | 2017-02-27 | T16182-DHI-LI-T-0075 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43f52805-c816-416e-9905-5ab79c522b14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
288 | T16182-YE03-P0BAU-152524 | 2017-02-27 | T16182-DHI-LI-T-0074 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8207a07-1282-4ec4-9d42-b6bc0f9d5b39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
102 | T16182-XB02-P0LB-122018 | 2017-02-28 | T16182-DHI-LI-T-0080 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c2252bf-a9b7-49b5-9ddd-85b2ddf89b14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
103 | T16182-XB02-P0LB-122019 | 2017-02-28 | T16182-DHI-LI-T-0080 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=554798f1-0cb6-4157-8495-943cab3d11c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1044 | T16182-CA00-P0UGD-181901 | 2017-02-28 | T16182-DHI-LI-T-0084 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc245203-d8fc-4eda-a4cf-f864009228ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1045 | T16182-CA00-P0UGD-181902 | 2017-02-28 | T16182-DHI-LI-T-0084 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2da507cb-1cec-447c-a95c-7cadb4988095 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1046 | T16182-CA00-P0UGD-181903 | 2017-02-28 | T16182-DHI-LI-T-0084 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a19e17a4-3416-44e0-855f-1640b8c8c78d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1047 | T16182-CA00-P0UGD-181904 | 2017-02-28 | T16182-DHI-LI-T-0084 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00e39f0f-4362-49e1-bc8a-6403d9c080b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1048 | T16182-CA00-P0UGD-181905 | 2017-02-28 | T16182-DHI-LI-T-0084 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66135cf0-21b0-4ba5-8b53-a815ebcebf74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
112 | T16182-YB03-P0LB-122048 | 2017-02-28 | T16182-DHI-LI-T-0076 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0c8f9bc-a96e-42fd-830f-f3f6adb7f8e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
263 | T16182-YT10-P0BBT-150651 | 2017-02-28 | T16182-DHI-LI-T-0078 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42a1df84-a1a4-41e8-91c5-cae60e6b0922 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
42 | T16182-XW03-P0LC-110046 | 2017-02-28 | T16182-DHI-LI-T-0079 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a2040e4-f33d-497b-b7e2-822a50eb06af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
43 | T16182-XW03-P0LC-110047 | 2017-02-28 | T16182-DHI-LI-T-0079 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=694ab2c4-c2d7-46f9-9b3d-d95dbc653eb0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
46 | T16182-XW03-P0PGB-110050 | 2017-02-28 | T16182-DHI-LI-T-0079 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24769fcf-d4b5-4d02-a9bf-1d71c6d303f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
47 | T16182-XW03-P0GHC-110051 | 2017-02-28 | T16182-DHI-LI-T-0079 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f0e90fd-360e-4908-b1b5-765a89c225eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
608 | T16182-CA05-P0UBA-181381 | 2017-02-28 | T16182-DHI-LI-T-0077 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=544e2d80-71d4-4f5f-8ec5-e18eb2194773 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
609 | T16182-CA05-P0UBA-181382 | 2017-02-28 | T16182-DHI-LI-T-0077 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29ffb7fc-611f-4021-9822-31e862886ba2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
610 | T16182-CA05-P0UBA-181384 | 2017-02-28 | T16182-DHI-LI-T-0077 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d54c6540-40b6-42bd-949b-2f2b549c1d79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
617 | T16182-CA00-P0UGD-181906 | 2017-02-28 | T16182-DHI-LI-T-0084 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef4530aa-78a2-4ef1-a145-e52e0d0abeb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
79 | T16182-YU02-P0MBA-121012 | 2017-02-28 | T16182-DHI-LI-T-0081 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9f28149-f7e4-4705-b92d-c7fbf7464eb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
80 | T16182-YT01-P0MBA-121013 | 2017-02-28 | T16182-DHI-LI-T-0081 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2105d4ff-9e77-4093-80e8-f4f66e7ba41c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
85 | T16182-YL25-P0MBA-121024 | 2017-02-28 | T16182-DHI-LI-T-0082 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=650db3e2-977c-493c-8b35-8eff7535bc40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
133 | T16182-CC05-P8QHB-125161 | 2017-03-02 | T16182-DHI-LI-T-0085 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a919038-18ea-476c-9730-d18c589a460e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
134 | T16182-CC05-P8QHB-125162 | 2017-03-02 | T16182-DHI-LI-T-0085 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eee7bd5b-fb4e-4640-b2db-3aca8de46dd9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1391 | T16182-CA00-P0UCB-180601 | 2017-03-02 | T16182-DHI-LI-T-0083 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d9655b3-9c9f-462a-847d-62a741fb3034 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1392 | T16182-CA00-P0UCB-180602 | 2017-03-02 | T16182-DHI-LI-T-0083 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=645b646c-037f-415e-b562-a644ed8c77e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1393 | T16182-CA00-P0UCB-180603 | 2017-03-02 | T16182-DHI-LI-T-0083 | IFR | E | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8565944-7058-4f32-8bd5-464044b0a429 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1394 | T16182-CA00-P0UCB-180604 | 2017-03-02 | T16182-DHI-LI-T-0083 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b2deea0-c446-411b-9e1c-6c0734f80258 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1395 | T16182-CA00-P0UCB-180605 | 2017-03-02 | T16182-DHI-LI-T-0083 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b991f830-a7a5-453c-b9d0-ed9df9c5af10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1396 | T16182-CA00-P0UCB-180606 | 2017-03-02 | T16182-DHI-LI-T-0083 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=881d92aa-0f51-4c2b-96c8-17487453af07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
636 | T16182-CA05-P0UGD-181981 | 2017-03-02 | T16182-DHI-LI-T-0086 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=282d449f-a208-40d9-9f74-b4483ea8ca60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
637 | T16182-CA05-P0UGD-181982 | 2017-03-02 | T16182-DHI-LI-T-0086 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b917c9f5-ac11-494e-82b8-df8dbeb8374c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
638 | T16182-CA05-P0UGD-181983 | 2017-03-02 | T16182-DHI-LI-T-0086 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b697360-dd9c-41aa-a841-fda5f7954590 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
639 | T16182-CA05-P0UGD-181984 | 2017-03-02 | T16182-DHI-LI-T-0086 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acb27abe-d080-4df8-95c9-60ad0955b31c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
640 | T16182-CA05-P0UGD-181985 | 2017-03-02 | T16182-DHI-LI-T-0086 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6291c1e1-edf4-4dfd-9f7a-075194e3c8d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
641 | T16182-CA05-P0UGD-181986 | 2017-03-02 | T16182-DHI-LI-T-0086 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc2359a4-719c-423e-982c-c20a740fb06a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
114 | T16182-YQ03-P0LB-122088 | 2017-03-03 | T16182-DHI-LI-T-0088 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d205f583-db15-4e69-9fad-2ac3904c2264 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
836 | T16182-YE04-P0BAU-152501 | 2017-03-03 | T16182-DHI-LI-T-0087 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1155 | T16182-YK09-P0SAA-133302 | 2017-03-06 | T16182-DHI-LI-T-0089 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9d7a5a2-6ce3-484f-8a5e-1ea464503c49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1186 | T16182-YF02-P0ZEN-161031 | 2017-03-06 | T16182-DHI-LI-T-0090 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd7383fc-2f3d-43fd-994f-7658a7a1612a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
326 | T16182-YL01-P0CBA-161101 | 2017-03-06 | T16182-DHI-LI-T-0095 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a03b8f50-6d03-45a0-9d7d-0a8a33c3939a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
867 | T16182-XW01-P0ZEN-161001 | 2017-03-06 | T16182-DHI-LI-T-0091 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96348294-a960-43ca-9eb6-c111d1eea643 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
882 | T16182-YL00-P0ZEN-163101 | 2017-03-06 | T16182-DHI-LI-T-0092 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
908 | T16182-YK00-P0ZEN-165312 | 2017-03-06 | T16182-DHI-LI-T-0094 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1151 | T16182-XB02-P0LB-122016 | 2017-03-07 | T16182-DHI-LI-T-0096 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1152 | T16182-XB02-P0LB-122017 | 2017-03-07 | T16182-DHI-LI-T-0096 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
431 | T16182-VE04-P0MPA-171103 | 2017-03-07 | T16182-DHI-LI-T-0098 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c80b73e7-0696-47dd-be70-1b3fb2634980 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
434 | T16182-XB02-P0MPA-171106 | 2017-03-07 | T16182-DHI-LI-T-0098 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2502c6cf-df99-4a9a-a0d6-fe3da7c86f4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
435 | T16182-XB02-P0MPA-171113 | 2017-03-07 | T16182-DHI-LI-T-0098 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b665141-7529-40a5-a9ae-3c73553e4f99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
436 | T16182-VK02-P0MPA-171117 | 2017-03-07 | T16182-DHI-LI-T-0098 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57184ff5-c33e-4bf5-a16a-a1aef8b1fa92 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
830 | T16182-YT10-P0BAT-150601 | 2017-03-07 | T16182-DHI-LI-T-0099 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1012 | T16182-CA00-P0UBA-181206 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d14c299-d8f2-4493-8c18-cb8938294917 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1013 | T16182-CA00-P0UBA-181207 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79110829-d984-406c-b596-9cae9d4d0640 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1014 | T16182-CA00-P0UBA-181208 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b79ba7a6-b832-43c2-866f-c083646ac23a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1019 | T16182-CA01-P0UBA-181255 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c5fa023-7c12-4016-8bfe-698e3997f7b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1020 | T16182-CA01-P0UBA-181256 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1023 | T16182-CA02-P0UBA-181259 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd777d0d-35f0-47da-b76a-8d26fe3c107b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1024 | T16182-CA02-P0UBA-181260 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d8414b1-d63d-4187-b140-18e46f9ef984 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1146 | T16182-XS00-P0SCA-120015 | 2017-03-08 | T16182-DHI-LI-T-0103 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d227b587-4091-4882-8143-9b38e5cdb56e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1164 | T16182-YE00-P0ZEN-152750 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1165 | T16182-YE00-P0ZEN-152751 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1166 | T16182-YE00-P0ZEN-152752 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1167 | T16182-YE00-P0ZEN-152753 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1168 | T16182-YE00-P0ZEN-152754 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1169 | T16182-YE00-P0ZEN-152755 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1170 | T16182-YE00-P0ZEN-152756 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1171 | T16182-YE00-P0ZEN-152757 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1172 | T16182-YE00-P0ZEN-152758 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1173 | T16182-YE00-P0ZEN-152759 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1174 | T16182-YE00-P0ZEN-152760 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1175 | T16182-YE00-P0ZEN-152761 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1176 | T16182-YE00-P0ZEN-152762 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1177 | T16182-YE00-P0ZEN-152763 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1178 | T16182-YE00-P0ZEN-152764 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1179 | T16182-YE00-P0ZEN-152765 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1180 | T16182-YE00-P0ZEN-152766 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1181 | T16182-YE00-P0ZEN-152767 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1182 | T16182-YE00-P0ZEN-152768 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1183 | T16182-YE00-P0ZEN-152769 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1184 | T16182-YE00-P0ZEN-152770 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1185 | T16182-YE00-P0ZEN-152771 | 2017-03-08 | T16182-DHI-LI-T-0102 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1388 | T16182-CA02-P0UBA-181257 | 2017-03-08 | T16182-DHI-LI-T-0104 | IFR | E | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8b881f6-8926-4d17-a7c0-c9968f8fc2cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
49 | T16182-XW03-P0MJ-110053 | 2017-03-08 | T16182-DHI-LI-T-0100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42f947a5-7ec2-4c4b-b71f-21828b724254 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
783 | T16182-XG07-P0SCA-120014 | 2017-03-08 | T16182-DHI-LI-T-0103 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42548ca1-aeeb-4a95-bfff-527fce4b4f53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
785 | T16182-XS00-P0SCA-120016 | 2017-03-08 | T16182-DHI-LI-T-0103 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88bc0a4f-d0cd-4b14-9fec-3d73c06fd349 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
905 | T16182-XW01-P0ZEN-165001 | 2017-03-08 | T16182-DHI-LI-T-0093 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bb14d24-56a5-4dbc-a736-01292768e1f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
906 | T16182-YL02-P0ZEN-165011 | 2017-03-08 | T16182-DHI-LI-T-0097 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=607af1e4-07bd-4122-a252-1c56f3471514 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1141 | T16182-XG02-P0SCA-120004 | 2017-03-09 | T16182-DHI-LI-T-0107 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4918e192-6706-4e64-a8ae-b2c095b57a86 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1189 | T16182-YD00-P0CWQ-161401 | 2017-03-09 | T16182-DHI-LI-T-0105 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a78e33b7-e281-44cb-98ed-1133bad5a71c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1190 | T16182-YD00-P0CWQ-161402 | 2017-03-09 | T16182-DHI-LI-T-0105 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=797b800c-cad6-42bd-a7d2-9040b8e0d01c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1191 | T16182-YD00-P0CWQ-161403 | 2017-03-09 | T16182-DHI-LI-T-0105 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca8b5be3-ad14-4b9d-a951-98ed09546894 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1192 | T16182-YD00-P0CWQ-161404 | 2017-03-09 | T16182-DHI-LI-T-0105 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a630929-097b-4f4c-aed4-6ea8fd22d3d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1193 | T16182-YD00-P0CWQ-161405 | 2017-03-09 | T16182-DHI-LI-T-0105 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b52fa713-7767-4720-9b41-e37231917586 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1292 | T16182-UC07-P0ZEN-100001 | 2017-03-09 | T16182-DHI-LI-T-0108 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14030edf-cb2e-4f72-a135-a2d6d5de901a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1293 | T16182-UC07-P0ZEN-100002 | 2017-03-09 | T16182-DHI-LI-T-0108 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b9fe5c5-0fbe-4927-b7c3-dd7d771d7e3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1294 | T16182-UC07-P0ZEN-100003 | 2017-03-09 | T16182-DHI-LI-T-0108 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e77c4a2d-fd5f-42af-aefb-47d0a4c2e350 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
248 | T16182-XL00-P0ZEN-140006 | 2017-03-09 | T16182-DHI-LI-T-0109 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2fa596fc-9558-4fa4-8db0-3f654c270233 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
291 | T16182-YE00-P0ZEN-152722 | 2017-03-09 | T16182-DHI-LI-T-0101 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3ce9fa0-2b50-42ab-8ce8-80193b540640 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
360 | T16182-YD00-P0CWQ-161409 | 2017-03-09 | T16182-DHI-LI-T-0105 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef794ea7-72ec-4283-8b67-83d67c2900f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
824 | T16182-YR02-P0ZEN-150001 | 2017-03-09 | T16182-DHI-LI-T-0106 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfd7970b-cf25-484e-a216-5198b2cdc8d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
880 | T16182-YD00-P0CWQ-161406 | 2017-03-09 | T16182-DHI-LI-T-0105 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d516caf-e23c-4c78-bfc0-f1ccfee513b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1028 | T16182-CA06-P0UBA-181300 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d254a5ba-6405-4a9c-bcfb-f991e022f71d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1029 | T16182-CA00-P0UBA-181301 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e62abde9-2ab1-4c75-902d-7ccc0a0ab5b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1030 | T16182-CA00-P0UBA-181302 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b9d71fc-119d-4da9-bcdb-0af31c4e88f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1031 | T16182-CA00-P0UBA-181303 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b1bb8d3-c3d7-48b8-9c8a-05edfebd92f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1032 | T16182-CA00-P0UBA-181304 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7736f691-31e6-4bd8-ab24-2ab40c7bf5b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1033 | T16182-CA00-P0UBA-181305 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b46bcaa-24fd-47f5-b875-fbea1f8e7ae0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1034 | T16182-CA01-P0UBA-181351 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=567df41c-bfff-44e5-90ad-e1a972daeaea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1035 | T16182-CA01-P0UBA-181352 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0daba2d7-3d22-4e59-8845-9767d1281a5d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1036 | T16182-CA01-P0UBA-181353 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75815623-7a61-42d3-9685-8f96e2b8464f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1037 | T16182-CA01-P0UBA-181354 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=329ca666-e21e-4a45-ab8b-6d5c8fe363d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1038 | T16182-CA02-P0UBA-181357 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1ee8606-bad8-4b0f-81a2-22ba0a081681 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1039 | T16182-CA02-P0UBA-181358 | 2017-03-10 | T16182-DHI-LI-T-0123 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6865aa2-e6cd-4b49-b999-4bee7fee7850 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
109 | T16182-XS00-P0LB-122035 | 2017-03-10 | T16182-DHI-LI-T-0115 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2ebae14-5f03-475a-82ee-f3bcec24c473 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
111 | T16182-XV00-P0LB-122039 | 2017-03-10 | T16182-DHI-LI-T-0110 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8d496fa-02aa-4b78-8ec3-063d36ca0082 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1399 | T16182-CA00-P0UCB-180603 | 2017-03-10 | T16182-DHI-LI-T-0117 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5357c23c-8427-4e93-a8c4-7dfba9ef1fd9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
224 | T16182-XS00-P0SG-136601 | 2017-03-10 | T16182-DHI-LI-T-0116 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da618812-1bb5-4cd9-8682-5e6d00402331 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
225 | T16182-XS00-P0SG-136602 | 2017-03-10 | T16182-DHI-LI-T-0116 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00005802-2ae7-4df4-8ffc-6f475f85479a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
283 | T16182-YE03-P0BAU-152507 | 2017-03-10 | T16182-DHI-LI-T-0112 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db5a4786-80dd-4772-a0ef-4533d1c79509 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
680 | T16182-CA06-P0UBA-186100 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f1b0467-f42c-456d-91f8-7662976b763f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
681 | T16182-CA00-P0UBA-186101 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daeb662f-376a-4d11-aec1-dab09eec0ea1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
682 | T16182-CA00-P0UBA-186103 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23d07257-b132-4aa7-ac17-18cb4c136dd3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
683 | T16182-CA00-P0UBA-186104 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f763eb3-c2a2-4efe-94a1-a7b30950cc0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
684 | T16182-CA01-P0UBA-186151 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9695910-ce71-41e0-a1c1-d875d6cc95bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
685 | T16182-CA01-P0UBA-186152 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bbad6e7-8bd7-4130-ae4b-e63bff60ad13 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
686 | T16182-CA01-P0UBA-186154 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2101ae0b-496f-4e05-8949-4a65b7039790 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
687 | T16182-CA02-P0UBA-186155 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f916d98-e2c3-42da-808a-51beb7af2ccf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
688 | T16182-CA02-P0UBA-186156 | 2017-03-10 | T16182-DHI-LI-T-0118 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac945d6e-e09e-495d-ac4a-41ef4da85491 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
730 | T16182-YK08-P0PGB-420010 | 2017-03-10 | T16182-DHI-LI-T-0111 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59838f2c-7d56-4299-890d-3e596c7e99e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
731 | T16182-YK08-P0PGB-420020 | 2017-03-10 | T16182-DHI-LI-T-0111 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e356672-dd80-48cc-bf65-4651d3c77686 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
907 | T16182-YK00-P0ZEN-165311 | 2017-03-10 | T16182-DHI-LI-T-0113 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2301cd6c-0a5f-4dcc-ae28-0b2d51c6648c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
909 | T16182-YK00-P0ZEN-165314 | 2017-03-10 | T16182-DHI-LI-T-0113 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99b1e2df-be8a-46d2-a303-11e77db8f369 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
910 | T16182-YK00-P0ZEN-165315 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
911 | T16182-YK00-P0ZEN-165316 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
912 | T16182-YK00-P0ZEN-165317 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
913 | T16182-YK00-P0ZEN-165318 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
914 | T16182-YK00-P0ZEN-165319 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
915 | T16182-YK00-P0ZEN-165320 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
916 | T16182-YK00-P0ZEN-165322 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
917 | T16182-YK00-P0ZEN-165323 | 2017-03-10 | T16182-DHI-LI-T-0114 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
921 | T16182-VE04-P0UMX-171001 | 2017-03-10 | T16182-DHI-LI-T-0122 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b99046ef-9893-4f23-abc7-c30bc5ce048b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
922 | T16182-XB02-P0UMX-171002 | 2017-03-10 | T16182-DHI-LI-T-0122 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ad63ce0-1c35-40ff-9344-b4c52c8505cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1043 | T16182-CA06-P0UGD-181900 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31e67fbf-7146-41a0-90fb-001bc0ad5dc2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1050 | T16182-CA01-P0UGD-181951 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ee2dbd2-de12-4aa9-a2c5-436dfffaec73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1051 | T16182-CA01-P0UGD-181952 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb7f8df3-0ba6-4589-8b60-3896d90601a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1052 | T16182-CA01-P0UGD-181953 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0de82de-6915-497d-9f31-f9e80e9c4acd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1053 | T16182-CA01-P0UGD-181954 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9f73ad5-33aa-4c8d-a111-be1a7296b4f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1054 | T16182-CA01-P0UGD-181955 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74fdcb0c-a76f-47c9-845f-0452febf2d3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1055 | T16182-CA02-P0UGD-181958 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0276efd8-0e23-47d7-afe3-03c4810b326a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1056 | T16182-CA02-P0UGD-181959 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70f0ed6e-836d-49de-a234-0d9e2582f6fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1059 | T16182-CA03-P0UGD-181965 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a56aac4-3128-41bd-97ec-69a3f9af641d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1060 | T16182-CA03-P0UGD-181966 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb08401c-99a0-4a4d-a9b2-0abd655434f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1121 | T16182-XG02-P6LCA-110008 | 2017-03-13 | T16182-DHI-LI-T-0120 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1122 | T16182-XG02-P0LAA-110009 | 2017-03-13 | T16182-DHI-LI-T-0120 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1125 | T16182-XG02-P0QJA-110012 | 2017-03-13 | T16182-DHI-LI-T-0130 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1127 | T16182-XG07-P0LA-110031 | 2017-03-13 | T16182-DHI-LI-T-0120 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1132 | T16182-XW01-P0LA-110037 | 2017-03-13 | T16182-DHI-LI-T-0120 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1135 | T16182-XS00-P0LC-110041 | 2017-03-13 | T16182-DHI-LI-T-0120 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1136 | T16182-XS00-P0LA-110042 | 2017-03-13 | T16182-DHI-LI-T-0120 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1154 | T16182-XW01-P0SAA-133301 | 2017-03-13 | T16182-DHI-LI-T-0126 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebd971bc-f5e0-48da-b94d-7af90628d02e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1212 | T16182-CC05-P0ZEN-180001 | 2017-03-13 | T16182-DHI-LI-T-0124 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce90e773-b5c1-4456-90a7-656127aee45a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1213 | T16182-CC05-P0ZEN-180002 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 1 | R | FALSE | TRUE | 2017-10-11_Changed by jisoo1.chung |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1214 | T16182-CC05-P0ZEN-180006 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1215 | T16182-CC05-P0ZEN-180008 | 2017-03-13 | T16182-DHI-LI-T-0124 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=147f3e67-cdff-4f63-a12d-a4bbef8976ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1216 | T16182-CC05-P0ZEN-180019 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1217 | T16182-CC05-P0ZEN-180020 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1218 | T16182-CC05-P0ZEN-180024 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1219 | T16182-CC05-P0ZEN-180025 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1220 | T16182-CC05-P0ZEN-180030 | 2017-03-13 | T16182-DHI-LI-T-0124 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f6f9395-139a-4418-b702-e37209094a4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1221 | T16182-CC05-P0ZEN-180033 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1222 | T16182-CC05-P0ZEN-180034 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1223 | T16182-CC05-P0ZEN-180035 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1224 | T16182-CC05-P0ZEN-180036 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1225 | T16182-CC05-P0ZEN-180037 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1226 | T16182-CC05-P0ZEN-180038 | 2017-03-13 | T16182-DHI-LI-T-0124 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e3dea85-5913-4d46-9bd7-22f5b69fc0e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1227 | T16182-CC05-P0ZEN-180039 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1228 | T16182-CC05-P0ZEN-180040 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1229 | T16182-CC05-P0ZEN-180041 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1230 | T16182-CC05-P0ZEN-180042 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1231 | T16182-CC05-P0ZEN-180043 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1232 | T16182-CC05-P0ZEN-180044 | 2017-03-13 | T16182-DHI-LI-T-0125 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
312 | T16182-YT10-P0ZEN-152810 | 2017-03-13 | T16182-DHI-LI-T-0127 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c012e25d-447a-46ce-b05a-5786922005d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
313 | T16182-DE00-P0ZEN-152820 | 2017-03-13 | T16182-DHI-LI-T-0127 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d707922-cffb-48ad-a15f-ff0f49bee395 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
314 | T16182-YD00-P0ZEN-152822 | 2017-03-13 | T16182-DHI-LI-T-0127 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea636726-4f38-436b-a79f-5e300aa35133 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
384 | T16182-YF02-P0SAY-163401 | 2017-03-13 | T16182-DHI-LI-T-0119 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38e68028-d7d3-4adb-b08d-1b18006e363d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
465 | T16182-VE04-P0UGF-172521 | 2017-03-13 | T16182-DHI-LI-T-0129 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57d5c6c8-e9a6-438b-8c82-b37b7546c5e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
466 | T16182-XB02-P0UGF-172522 | 2017-03-13 | T16182-DHI-LI-T-0129 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=573f1af0-c7b9-44c5-b192-0e591cec19b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
467 | T16182-VK02-P0UGF-172523 | 2017-03-13 | T16182-DHI-LI-T-0129 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=237df002-c831-445f-baca-e107528e04a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
627 | T16182-CA02-P0UGD-181960 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5c29f1f-433d-4386-a17a-8e142c71be3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
628 | T16182-CA02-P0UGD-181961 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba322078-cff2-410e-a9eb-1a19e30e0e58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
634 | T16182-CA03-P0UGD-181967 | 2017-03-13 | T16182-DHI-LI-T-0128 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9397415-b1a8-4c49-8247-b082f1cfff47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
87 | T16182-YS00-P0MBA-121029 | 2017-03-13 | T16182-DHI-LI-T-0121 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f55e3a0b-6033-4900-8ad8-22325d5fe0a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
128 | T16182-XW03-P8ZEN-121514 | 2017-03-14 | T16182-DHI-LI-T-0132 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
141 | T16182-XG05-P8ZEN-125571 | 2017-03-14 | T16182-DHI-LI-T-0132 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1a4de2e-7a93-432d-a6d1-5e055ab90f4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2536 | T16182-XW03-P8ZEN-125014 | 2017-03-14 | T16182-DHI-LI-T-0132 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4b64988-8326-4763-9bcd-8a74c6d9ce69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
996 | T16182-CA02-P0UCB-180666 | 2017-03-14 | T16182-DHI-LI-T-0133 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bd6588c-2b8c-499b-8a0d-6e2744e73875 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
997 | T16182-CA02-P0UCB-180667 | 2017-03-14 | T16182-DHI-LI-T-0133 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=402700da-1095-4f96-9c1e-7a4b8054d69e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
998 | T16182-CA02-P0UCB-180668 | 2017-03-14 | T16182-DHI-LI-T-0133 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22c4bc8a-180b-4694-872a-dd2e39ad1dec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
196 | T16182-XW03-P0SAC-133501 | 2017-03-16 | T16182-DHI-LI-T-0139 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4235136f-5284-4928-bd8e-4eeeafd04a3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
197 | T16182-XG07-P0SAC-133502 | 2017-03-16 | T16182-DHI-LI-T-0139 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39463124-010e-46d5-8260-6b6f1c309931 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
198 | T16182-XW03-P0SAC-133503 | 2017-03-16 | T16182-DHI-LI-T-0139 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e5a6b41-0713-49a1-946e-d5e40a5b56ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
199 | T16182-XH02-P0SAC-133504 | 2017-03-16 | T16182-DHI-LI-T-0139 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7590c300-d301-497a-8ccf-d6bf34510747 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
324 | T16182-YR05-P0ZEN-161011 | 2017-03-16 | T16182-DHI-LI-T-0138 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38b37f38-e048-4db3-bafd-cac3f0ed0b55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
437 | T16182-VE04-P0ULC-171301 | 2017-03-16 | T16182-DHI-LI-T-0144 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27e07927-dc27-4d3b-91c9-b5b691b6278d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
438 | T16182-XB02-P0ULC-171302 | 2017-03-16 | T16182-DHI-LI-T-0144 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d3f6509-2699-4908-8c52-e7b8602a586f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
439 | T16182-XB02-P0ULC-171303 | 2017-03-16 | T16182-DHI-LI-T-0144 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=113671e8-bf79-49d7-ac03-5b63b23f01d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
440 | T16182-VK02-P0ULC-171308 | 2017-03-16 | T16182-DHI-LI-T-0144 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3654ca35-3078-4662-81f9-7161107e07c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
441 | T16182-VE04-P0UEM-171701 | 2017-03-16 | T16182-DHI-LI-T-0142 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1160709f-517f-4f87-9dc8-fa8788d7c609 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
442 | T16182-XB02-P0UEM-171702 | 2017-03-16 | T16182-DHI-LI-T-0142 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97d7b2e0-49c6-498a-aa4e-0883b022ff23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
443 | T16182-XB02-P0UEM-171708 | 2017-03-16 | T16182-DHI-LI-T-0142 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27f4875f-57cb-41bc-99ed-469a7241462d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
444 | T16182-VK02-P0UEM-171711 | 2017-03-16 | T16182-DHI-LI-T-0142 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=baebe4bb-26bb-42b4-87ff-34c71a30360d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
667 | T16182-CA06-P0USR-184700 | 2017-03-16 | T16182-DHI-LI-T-0143 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f67e285-7092-4c28-8dcb-f29208544aa4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
668 | T16182-CA00-P0USR-184701 | 2017-03-16 | T16182-DHI-LI-T-0143 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e83d197-30cc-4be0-9825-7eadb5f385a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
669 | T16182-CA00-P0USR-184702 | 2017-03-16 | T16182-DHI-LI-T-0143 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b3aa7c7-7cad-41ae-a9ce-9564f7bee5b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
670 | T16182-CA03-P0USR-184751 | 2017-03-16 | T16182-DHI-LI-T-0143 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e2d6c2c-7e18-4dbf-8710-d7fbea9ab87a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
671 | T16182-CA03-P0USR-184752 | 2017-03-16 | T16182-DHI-LI-T-0143 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c47a2dab-0758-4eb2-875a-06ca64b1092f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
70 | T16182-YL25-P0MBA-121002 | 2017-03-16 | T16182-DHI-LI-T-0140 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9192f40-68b4-4932-bbb1-61af9115aa12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
714 | T16182-YR05-P0CJN-290004 | 2017-03-16 | T16182-DHI-LI-T-0131 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4a84342-f0f8-49eb-bbbc-7c7c7749b9ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
81 | T16182-YL25-P0MBA-121014 | 2017-03-16 | T16182-DHI-LI-T-0141 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b6e43f1-0e4f-45e6-917d-2f290e180945 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
82 | T16182-XW01-P0MBA-121015 | 2017-03-16 | T16182-DHI-LI-T-0141 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=798a473f-f17c-4f15-bef3-e4b3403bfc49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
843 | T16182-YE03-P0BAU-152524 | 2017-03-16 | T16182-DHI-LI-T-0137 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
93 | T16182-VN01-P0MBA-121044 | 2017-03-16 | T16182-DHI-LI-T-0140 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40d954e6-b0d4-423f-be81-7e587e0e8056 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1131 | T16182-XW01-P0LC-110036 | 2017-03-20 | T16182-DHI-LI-T-0148 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=363de013-fa97-4d2a-9b64-d46ea83a81bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
468 | T16182-VE04-P0UGD-172541 | 2017-03-20 | T16182-DHI-LI-T-0149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ae9241c-afb3-47c7-9016-53dc636e94bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
469 | T16182-XB02-P0UGD-172542 | 2017-03-20 | T16182-DHI-LI-T-0149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a3ab99b-e1a9-40ff-8c55-f21ac9c57631 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
470 | T16182-VK02-P0UGD-172543 | 2017-03-20 | T16182-DHI-LI-T-0149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5dbd9ef4-2bcd-40be-8e35-9cf2d70377ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
471 | T16182-VE04-P0UGG-172561 | 2017-03-20 | T16182-DHI-LI-T-0149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef1c0437-ff8e-4e81-af79-82ca48e13e34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
472 | T16182-XB02-P0UGG-172562 | 2017-03-20 | T16182-DHI-LI-T-0149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08c9ebd9-ee6e-4c29-aa2f-22b68a1790b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
473 | T16182-VK02-P0UGG-172563 | 2017-03-20 | T16182-DHI-LI-T-0149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c643ab4-4ef4-462f-90cd-9101c1d1a9dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
726 | T16182-CV03-P0PUR-411001 | 2017-03-20 | T16182-DHI-LI-T-0136 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51cd1d26-7fa6-4b65-b477-856c24180ec3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
727 | T16182-CV03-P0PUR-411011 | 2017-03-20 | T16182-DHI-LI-T-0136 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32c621ec-2b74-408e-87d8-cb616bc40d29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
728 | T16182-CV03-P0PUR-411021 | 2017-03-20 | T16182-DHI-LI-T-0136 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e75f55a-630e-47e6-9ecd-fb7e0206cfa6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
729 | T16182-CV03-P0PUR-411031 | 2017-03-20 | T16182-DHI-LI-T-0136 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=224a8894-bbcf-43e6-a5e0-d0e809fc305e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
883 | T16182-YS00-P0ZEN-163301 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
884 | T16182-YS00-P0ZEN-163302 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
885 | T16182-YS00-P0ZEN-163303 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
886 | T16182-YS00-P0ZEN-163304 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
887 | T16182-YS00-P0ZEN-163305 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
888 | T16182-YS00-P0ZEN-163306 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
889 | T16182-YS00-P0ZEN-163307 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
890 | T16182-YS00-P0ZEN-163308 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
891 | T16182-YS00-P0ZEN-163309 | 2017-03-20 | T16182-DHI-LI-T-0146 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a408554c-e2e8-4c1c-a16d-72aead5c1246 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
892 | T16182-YS00-P0ZEN-163310 | 2017-03-20 | T16182-DHI-LI-T-0146 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31d72832-8ea1-4ce1-b036-a62d589e6bf6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
893 | T16182-YS00-P0ZEN-163311 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
894 | T16182-YS00-P0ZEN-163312 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
895 | T16182-YS00-P0ZEN-163313 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
896 | T16182-YS00-P0ZEN-163314 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
897 | T16182-YS00-P0ZEN-163315 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
898 | T16182-YS00-P0ZEN-163316 | 2017-03-20 | T16182-DHI-LI-T-0146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e527c5e-2724-44fe-ba2d-3d94f913ff35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
899 | T16182-YS00-P0ZEN-163317 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
900 | T16182-YS00-P0ZEN-163318 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
901 | T16182-YS00-P0ZEN-163319 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
902 | T16182-YS00-P0ZEN-163320 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
903 | T16182-YS00-P0ZEN-163321 | 2017-03-20 | T16182-DHI-LI-T-0147 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1150 | T16182-UE00-P0LB-122007 | 2017-03-21 | T16182-DHI-LI-T-0151 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4af50526-924e-4148-ac3b-2e56e6d2352a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1331 | T16182-VK02-P8UTH-172005 | 2017-03-21 | T16182-DHI-LI-T-0153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c47653a1-2a8a-4658-84c3-2e88fdb8b796 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1361 | T16182-VE04-P8UTH-172001 | 2017-03-21 | T16182-DHI-LI-T-0153 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3838a48-8b33-4292-b71d-de9889486887 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1362 | T16182-XB02-P8UTH-172003 | 2017-03-21 | T16182-DHI-LI-T-0153 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=deb54003-7f47-496e-becd-62244bb40114 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1363 | T16182-XB02-P8UTH-172004 | 2017-03-21 | T16182-DHI-LI-T-0153 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e526fd8-8790-4e72-8819-06ec90ce1dcd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
446 | T16182-VE04-P0UHA-171802 | 2017-03-21 | T16182-DHI-LI-T-0150 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66db499f-2e2e-4fbd-a274-6eeaed4e1e12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
449 | T16182-XB02-P0UHA-171805 | 2017-03-21 | T16182-DHI-LI-T-0150 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd2a3b6f-7f50-4058-b102-1b97c268afea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
450 | T16182-XB02-P0UHA-171806 | 2017-03-21 | T16182-DHI-LI-T-0150 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51722614-23c8-4800-8166-a17e585a013d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
451 | T16182-XB02-P0UHA-171807 | 2017-03-21 | T16182-DHI-LI-T-0150 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c051e1c7-0b12-4b45-9a4f-794d200e6b24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
792 | T16182-YD00-P0MBA-121001 | 2017-03-21 | T16182-DHI-LI-T-0152 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1187 | T16182-YR04-P0CUQ-161111 | 2017-03-22 | T16182-DHI-LI-T-0158 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4bc4d31-9d9b-49a4-b07f-7e4b49bdc75d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
261 | T16182-YT01-P0BAT-150611 | 2017-03-22 | T16182-DHI-LI-T-0154 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7677ac18-ba91-4639-b0e8-321293c5cb06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
264 | T16182-YT01-P0BBT-150661 | 2017-03-22 | T16182-DHI-LI-T-0154 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad436037-b617-4ac5-8999-c0827e115624 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
265 | T16182-YD00-P0BBT-150671 | 2017-03-22 | T16182-DHI-LI-T-0154 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06ec1460-2373-4c94-bcd8-d8968bebe447 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
732 | T16182-YK08-P0LCM-420030 | 2017-03-22 | T16182-DHI-LI-T-0162 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23284a7a-f190-4cda-bb3c-81549394663a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
733 | T16182-YK08-P0LCM-420040 | 2017-03-22 | T16182-DHI-LI-T-0162 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70335d4d-cf3b-4e60-a17a-845a0e7cf455 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
872 | T16182-CV03-P0CRN-161105 | 2017-03-22 | T16182-DHI-LI-T-0155 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d7f405d-f556-4459-90c5-804c0ce7dab9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
874 | T16182-YD00-P0CUQ-161119 | 2017-03-22 | T16182-DHI-LI-T-0155 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d496819-1f14-4d67-a69f-ff3f26a7de55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1188 | T16182-YR04-P0CUQ-161118 | 2017-03-23 | T16182-DHI-LI-T-0163 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c8bae18-0fa9-473c-bd05-693f6c975bb2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1197 | T16182-XW01-P0ZEN-165001 | 2017-03-23 | T16182-DHI-LI-T-0160 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8c025e9-d0c9-4ce3-86bb-822545230c09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1397 | T16182-CA02-P0UCB-180664 | 2017-03-23 | T16182-DHI-LI-T-0167 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2b40983-821c-4a25-b573-619845d22ae3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
387 | T16182-YK00-P0ZEN-165301 | 2017-03-23 | T16182-DHI-LI-T-0161 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f1366b0-013c-4085-b357-eaf343a3f4e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
388 | T16182-YK00-P0ZEN-165302 | 2017-03-23 | T16182-DHI-LI-T-0161 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9b67042-b2e5-45b0-87e5-b4f3f0de6006 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
389 | T16182-YK00-P0ZEN-165303 | 2017-03-23 | T16182-DHI-LI-T-0161 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f56cf405-80e0-4f4f-a5af-6fd80d4ada8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
390 | T16182-YK00-P0ZEN-165304 | 2017-03-23 | T16182-DHI-LI-T-0161 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de51496d-ad34-4980-b047-9606284c93bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
391 | T16182-YK00-P0ZEN-165305 | 2017-03-23 | T16182-DHI-LI-T-0161 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3429c8cc-7c68-4289-ac51-34d78bbef48d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
950 | T16182-VE04-P0UZA-172901 | 2017-03-23 | T16182-DHI-LI-T-0159 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16a9026f-5e53-40df-9ceb-7800bbfe2091 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
951 | T16182-XB02-P0UZA-172902 | 2017-03-23 | T16182-DHI-LI-T-0159 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1634238-2fe9-47c1-990e-9574f8bea1b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
952 | T16182-XB02-P0UZA-172903 | 2017-03-23 | T16182-DHI-LI-T-0159 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4df90c5f-c6d4-42ca-bc8a-08876fbdd38f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
953 | T16182-VK02-P0UZA-172908 | 2017-03-23 | T16182-DHI-LI-T-0159 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85f38777-bda3-4370-83b6-b9702dd88023 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1000 | T16182-CA05-P0UCB-180682 | 2017-03-24 | T16182-DHI-LI-T-0164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d7570b7-d9f9-4911-b3dc-f3ecadc52fa3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1001 | T16182-CA05-P0UCB-180683 | 2017-03-24 | T16182-DHI-LI-T-0164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a74e682-21e5-47ce-9bb8-b26cc4b6a773 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1002 | T16182-CA05-P0UCB-180684 | 2017-03-24 | T16182-DHI-LI-T-0164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25153e69-3b8a-42b3-ab7d-e34e768ba9aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1003 | T16182-CA05-P0UCB-180685 | 2017-03-24 | T16182-DHI-LI-T-0164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65c5e8ee-f49e-4343-a0f7-2b3995779b20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1004 | T16182-CA05-P0UCB-180686 | 2017-03-24 | T16182-DHI-LI-T-0164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee12a641-884c-43f9-b1e1-efb95ec260d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1005 | T16182-CA05-P0UCB-180687 | 2017-03-24 | T16182-DHI-LI-T-0164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b09681eb-39c5-4a3d-9fc9-69b59e5494db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1272 | T16182-CA01-P0UBA-181256 | 2017-03-24 | T16182-DHI-LI-T-0174 | IFC | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=322370a9-e8cd-4407-99d6-06f9eaf29a2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1275 | T16182-CA02-P0UBA-181259 | 2017-03-24 | T16182-DHI-LI-T-0170 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7c053fc-f676-4a2f-8714-db6a9f999e00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1398 | T16182-CA02-P0UBA-181257 | 2017-03-24 | T16182-DHI-LI-T-0170 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d84a86a1-a0c8-4539-a221-4b99fe7d2a59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
208 | T16182-XW03-P0SAI-133801 | 2017-03-24 | T16182-DHI-LI-T-0169 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=753de411-4647-48b6-ac57-76c52dd0b53a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
209 | T16182-XG07-P0SAI-133802 | 2017-03-24 | T16182-DHI-LI-T-0169 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdc78795-c2f8-4b1b-ac57-41d9b094b99f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
210 | T16182-XW03-P0SAI-133803 | 2017-03-24 | T16182-DHI-LI-T-0169 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70d427d6-a047-4995-9574-4121352d6113 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
211 | T16182-XH02-P0SAI-133804 | 2017-03-24 | T16182-DHI-LI-T-0169 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29047945-3a22-4c47-b5d5-bb20aa5e8ba1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
254 | T16182-YU02-P0ZEN-150212 | 2017-03-24 | T16182-DHI-LI-T-0166 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5e3fe3c-9fb9-4d87-a02c-7e9e1b6fcaa6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
50 | T16182-CN00-P0ZEN-110706 | 2017-03-24 | T16182-DHI-LI-T-0173 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4fe6e63-d3b0-4d0d-83d9-e543718f6ff7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
672 | T16182-CA06-P0QJA-184800 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4070dd96-b99f-4b1e-9f39-9fcb4b2d2f5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
673 | T16182-CA00-P0QJA-184801 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5801caaa-c91b-440b-b36a-3a90bbac1f64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
674 | T16182-CA00-P0QJA-184802 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f705633-3409-4444-8ebc-d35ecee56760 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
675 | T16182-CA00-P0QJA-184803 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=997f506b-0da0-4a4b-8f22-9baa4d7d2eb2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
676 | T16182-CA01-P0QJA-184851 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d44e9083-56c4-4aba-b611-b6a0859e94e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
677 | T16182-CA01-P0QJA-184852 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d05bfee-08c6-4086-aa61-ce2d8cd65ef3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
678 | T16182-CA01-P0QJA-184853 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fba4c7c6-544e-47cf-aa8c-9697a7a17bcb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
679 | T16182-CA02-P0QJA-184854 | 2017-03-24 | T16182-DHI-LI-T-0165 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
795 | T16182-XS01-P0MBA-121033 | 2017-03-24 | T16182-DHI-LI-T-0175 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
799 | T16182-XB02-P0LB-122018 | 2017-03-24 | T16182-DHI-LI-T-0171 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
800 | T16182-XB02-P0LB-122019 | 2017-03-24 | T16182-DHI-LI-T-0171 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
826 | T16182-YU02-P0ZEN-150211 | 2017-03-24 | T16182-DHI-LI-T-0166 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7b86927-0452-49dc-84d8-c6aac1e4fb5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
835 | T16182-YQ01-P0ZEN-152201 | 2017-03-24 | T16182-DHI-LI-T-0172 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
924 | T16182-VE04-P0MPA-171102 | 2017-03-24 | T16182-DHI-LI-T-0168 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5755dea-b8b6-4664-9380-e3676af95160 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
999 | T16182-CA05-P0UCB-180681 | 2017-03-24 | T16182-DHI-LI-T-0164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4c1ff9e-6fa0-43da-8c41-863ea996fa4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1025 | T16182-CA05-P0UBA-181281 | 2017-03-28 | T16182-DHI-LI-T-0157 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e90afed-f26b-400f-8a0e-fcf95947e5dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1026 | T16182-CA05-P0UBA-181282 | 2017-03-28 | T16182-DHI-LI-T-0157 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ad58bb4-adb8-4143-8606-12acbbabb8e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1027 | T16182-CA05-P0UBA-181284 | 2017-03-28 | T16182-DHI-LI-T-0157 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc9bddfd-b8ea-4953-ba7c-5fb7a91601c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
119 | T16182-XH01-P0EKG-124002 | 2017-03-28 | T16182-DHI-LI-T-0156 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89c45063-63fe-43f6-a8e7-28b2b2731dfe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1198 | T16182-YL02-P0ZEN-165011 | 2017-03-28 | T16182-DHI-LI-T-0179 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
66 | T16182-XW03-P0EKG-120021 | 2017-03-28 | T16182-DHI-LI-T-0156 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9faed21d-0878-4d59-a505-fccd0b4946ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
699 | T16182-YT01-P0MKA-250009 | 2017-03-28 | T16182-DHI-LI-T-0178 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8c36ce0-3344-4358-b38a-79c71dfff57c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
787 | T16182-XG07-P0EKG-120018 | 2017-03-28 | T16182-DHI-LI-T-0156 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cadf3ba-8918-4e4e-ac43-066b2a2a9e19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
842 | T16182-YE03-P0BAU-152507 | 2017-03-28 | T16182-DHI-LI-T-0176 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
91 | T16182-XS01-P0MBA-121034 | 2017-03-28 | T16182-DHI-LI-T-0180 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbfceaa0-336d-4f4f-9a82-99956508ac42 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
92 | T16182-XS01-P0MBA-121035 | 2017-03-28 | T16182-DHI-LI-T-0180 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0704f89-ec2e-4633-b305-3a8e099e2014 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
994 | T16182-CA01-P0UCB-180660 | 2017-03-28 | T16182-DHI-LI-T-0177 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f94e9a6f-8daa-4097-a422-26fe27efa0a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
995 | T16182-CA01-P0UCB-180661 | 2017-03-28 | T16182-DHI-LI-T-0177 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14db2ae5-4282-4012-86b1-40754bfa54c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
336 | T16182-YR05-P0CWQ-161141 | 2017-03-29 | T16182-DHI-LI-T-0186 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=671fedf7-de4a-4a3f-a384-d9986fc0f1f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
337 | T16182-YR05-P0CWQ-161142 | 2017-03-29 | T16182-DHI-LI-T-0186 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=306ae11c-51f8-4077-accb-73a8f1b3901a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
338 | T16182-YR05-P0CWQ-161143 | 2017-03-29 | T16182-DHI-LI-T-0186 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c49b3ac8-c00e-4912-bba3-631e0b36d129 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
339 | T16182-YR05-P0CWQ-161147 | 2017-03-29 | T16182-DHI-LI-T-0186 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f7a9228-7c42-4967-bce6-601f7fc2d566 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
710 | T16182-XG02-P0MKW-260033 | 2017-03-29 | T16182-DHI-LI-T-0188 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d067339f-aadb-45b4-8ea4-bed7fe1c4985 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
711 | T16182-XG02-P0MKG-260034 | 2017-03-29 | T16182-DHI-LI-T-0188 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f17de1e-5b64-4e18-8863-02a293eff729 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
871 | T16182-CV03-P0CRN-161104 | 2017-03-29 | T16182-DHI-LI-T-0186 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=494b9ef0-5d4c-4888-9454-e7f06e4f830c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1162 | T16182-YE04-P0BAU-152501 | 2017-03-30 | T16182-DHI-LI-T-0181 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d57fd018-c15e-4f54-a3a1-3f8ed49dd4dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1315 | T16182-YF02-P0ZEN-161031 | 2017-03-30 | T16182-DHI-LI-T-0182 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
269 | T16182-YD04-P0ZEN-152004 | 2017-03-30 | T16182-DHI-LI-T-0145 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a22e1d4d-0bc4-4df4-b737-ca1463d53d75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
287 | T16182-YE03-P0BAU-152521 | 2017-03-30 | T16182-DHI-LI-T-0185 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f49be82f-54f8-4f88-8651-83812e86843a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
715 | T16182-YU02-P0MKY-290006 | 2017-03-30 | T16182-DHI-LI-T-0184 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01a4bccc-cadf-4559-8a24-d72b6af9d76e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1040 | T16182-CA05-P0UBA-181381 | 2017-03-31 | T16182-DHI-LI-T-0196 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb8cfc9f-85dc-447a-8803-d74379aca13a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1041 | T16182-CA05-P0UBA-181382 | 2017-03-31 | T16182-DHI-LI-T-0196 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88a3e758-1798-4ba8-8aea-82d9adc202dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1042 | T16182-CA05-P0UBA-181384 | 2017-03-31 | T16182-DHI-LI-T-0196 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18d92a03-2603-4a84-bdb4-78420e973f64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1144 | T16182-XS00-P0GKS-120012 | 2017-03-31 | T16182-DHI-LI-T-0195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9f57717-0b3f-4906-814c-68989271e534 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1148 | T16182-XS00-P0GKS-120051 | 2017-03-31 | T16182-DHI-LI-T-0195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc480074-4523-452e-a6b9-a144aed41909 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1276 | T16182-CA06-P0UBA-181300 | 2017-03-31 | T16182-DHI-LI-T-0192 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69204297-ae01-48e5-baae-1a3aeb0daf6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
131 | T16182-XT00-P8QHB-125152 | 2017-03-31 | T16182-DHI-LI-T-0187 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2f48fd0-321b-4a35-b31d-29095d12c1c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
132 | T16182-XT00-P8QHB-125153 | 2017-03-31 | T16182-DHI-LI-T-0187 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb1d0de3-8b63-4483-85ce-b1130807e597 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
138 | T16182-XA00-P8QHL-125401 | 2017-03-31 | T16182-DHI-LI-T-0194 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e4208d7-3907-48f9-b4e0-a080238ab320 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
139 | T16182-XA00-P8QHL-125402 | 2017-03-31 | T16182-DHI-LI-T-0194 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1b93ba3-4c39-4da0-ac5b-e0235312dd19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
140 | T16182-YK08-P8QHL-125403 | 2017-03-31 | T16182-DHI-LI-T-0193 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0b5dddb-b4f9-4494-84e6-7ebd4d5034ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2107 | T16182-CV03-P0CWQ-161132 | 2017-03-31 | T16182-DHI-LI-T-0186 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cf4a151-b959-4193-a694-0027505ee26c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
456 | T16182-VE04-P8UTH-172011 | 2017-03-31 | T16182-DHI-LI-T-0191 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60346a1c-13ac-472e-bdff-36bfae662300 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
457 | T16182-XB02-P8UTH-172012 | 2017-03-31 | T16182-DHI-LI-T-0191 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef4b852c-e1b6-4e8e-8574-4ddc3dadba2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
458 | T16182-XB02-P8UTH-172013 | 2017-03-31 | T16182-DHI-LI-T-0191 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=535bce13-ad39-4fcf-a2ca-3248b6488887 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
462 | T16182-VE04-P0ULC-172501 | 2017-03-31 | T16182-DHI-LI-T-0190 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3702853-0f30-4a8c-82f8-c548c9c5ce20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
463 | T16182-XB02-P0ULC-172502 | 2017-03-31 | T16182-DHI-LI-T-0190 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2792c1c4-5145-47c0-8dc8-9bc238ac0e57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
464 | T16182-VK02-P0ULC-172503 | 2017-03-31 | T16182-DHI-LI-T-0190 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5379ed28-8291-412b-a6b2-9110dd461d4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
73 | T16182-XW01-P0MBA-121004 | 2017-03-31 | T16182-DHI-LI-T-0197 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=395ae641-7ade-4e7c-befe-cfa6a2d27a79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
823 | T16182-CV03-P0ZEN-140002 | 2017-03-31 | T16182-DHI-LI-T-0189 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fefa3cf3-6c85-4a30-bd96-69ceda588376 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
94 | T16182-DF04-P0LB-122003 | 2017-03-31 | T16182-DHI-LI-T-0198 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=762e445f-15a5-4a37-b9f3-e87e0ef4a3ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1142 | T16182-XG02-P0SCA-120005 | 2017-04-03 | T16182-DHI-LI-T-0207 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bba2aee-1ed6-413c-a8fd-16732ca53a52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1143 | T16182-XG02-P0SCA-120006 | 2017-04-03 | T16182-DHI-LI-T-0207 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98c2d723-415b-4bec-8239-998e180d373f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1153 | T16182-XS00-P0GCF-130001 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b676faf1-2d5e-4363-8dcc-153d8496b5a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
179 | T16182-YK09-P0GCF-130012 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81372ab3-846d-49c7-811a-794531b1f995 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
180 | T16182-XH01-P0GCF-130013 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95e15309-0def-48ab-b26a-a5693c124596 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
181 | T16182-YT01-P0GCF-130014 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acc80386-b373-41c0-af63-6536ef1a9ac9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
182 | T16182-YD00-P0GCF-130019 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f8b753c-c873-4356-abdf-c997d1fda3ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
184 | T16182-XB02-P0GCF-130042 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e7a76ff-982b-4f89-875e-b5a61ac37009 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
185 | T16182-CV03-P0GCF-130055 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85f63ea2-b56d-450b-adbf-848133a3c258 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
192 | T16182-XN00-P0GNR-130107 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0634c692-8550-4d20-b41e-4f17e6523219 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
193 | T16182-YT01-P0GNR-130108 | 2017-04-03 | T16182-DHI-LI-T-0210 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22876e0a-1ee4-4c1f-871e-ea5b44621e06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
230 | T16182-YT01-P0SGA-136609 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4b9837e-a783-4e29-b499-f2be5401b7e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
231 | T16182-YT01-P0SGA-136610 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c656827f-810e-4f87-8b5a-3e6541bf9b04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
232 | T16182-YT01-P0SGA-136611 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ed8c81d-bc4a-4aa3-ac48-1ff46415ed4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
233 | T16182-YT01-P0SGE-136612 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=259abe96-2005-40bd-b7f0-fec22a3f8159 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
234 | T16182-YT01-P0SGC-136613 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4af5b84e-f95e-4458-8e8f-e8894c9b34bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
235 | T16182-YT01-P0SGK-136614 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd31e3ef-7c95-4a99-8099-be0e279b7cff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
236 | T16182-YT01-P0SGZ-136615 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5498e48e-0338-4c21-b305-4daa7d596db6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
237 | T16182-YT01-P0SGX-136616 | 2017-04-03 | T16182-DHI-LI-T-0200 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bd9cfd9-7533-417e-a6e4-d837f1b98e32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
238 | T16182-YT01-P0CYE-136617 | 2017-04-03 | T16182-DHI-LI-T-0201 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=756f0081-a378-4660-9235-795f4ead2478 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
239 | T16182-YT01-P0CYE-136618 | 2017-04-03 | T16182-DHI-LI-T-0201 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a03108ed-72ca-4d38-b935-dff233f6b780 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
245 | T16182-YD00-P0SGZ-137331 | 2017-04-03 | T16182-DHI-LI-T-0206 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0a901b0-e4fc-452c-b8dc-5cc80e43d1db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
255 | T16182-YU05-P0ZEN-150221 | 2017-04-03 | T16182-DHI-LI-T-0205 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1770633a-1ab2-4b3c-bd34-5f77097cac35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
562 | T16182-CA06-P0UBA-181000 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=660720f0-32fb-4874-966a-d4ac968bbfda | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
563 | T16182-CA00-P0UBA-181001 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a219ac5-ca25-45cb-99af-32e338b59462 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
564 | T16182-CA00-P0UBA-181002 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1908fcbc-e78d-46a9-8492-4c1b04b39457 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
565 | T16182-CA00-P0UBA-181003 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0940b63c-8c4d-498a-ab38-ffd5c6f4287c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
566 | T16182-CA00-P0UBA-181004 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa7eaab0-cd77-45e4-9d33-d1bc6862eede | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
567 | T16182-CA00-P0UBA-181005 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=730d0e00-795e-4874-829b-a5662822eeef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
568 | T16182-CA01-P0UBA-181051 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7d4762d-381b-4f3a-bcb7-dfbfc06513f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
569 | T16182-CA01-P0UBA-181052 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14fc1a6a-d7e8-4688-93ce-4bf019f55e68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
570 | T16182-CA01-P0UBA-181053 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33ed9bed-5d2c-428b-bd93-bad30109c2b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
571 | T16182-CA01-P0UBA-181054 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11106d35-7ad8-4b22-9068-b6411e5cd0a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
572 | T16182-CA02-P0UBA-181055 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8e8fda0-8e5e-4b73-aa32-63b1d0f40aae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
573 | T16182-CA02-P0UBA-181056 | 2017-04-03 | T16182-DHI-LI-T-0208 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41193063-9f64-4b46-a06c-4a0dcb01bae7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
651 | T16182-CA06-P0USG-182700 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89044b06-c531-4383-834e-a7addc317de6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
652 | T16182-CA00-P0USG-182701 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c560cb73-e271-40b7-a88c-9ddcc96683fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
653 | T16182-CA00-P0USG-182702 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34ea9057-8047-4c35-9246-ca0b623f5735 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
654 | T16182-CA00-P0USG-182703 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dcea716-fcd1-4dc0-8345-0680ded51c17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
655 | T16182-CA00-P0USG-182704 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=198b8475-8a57-424c-aabd-ab8aed1c4ea3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
656 | T16182-CA01-P0USG-182751 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a30c749-3027-4e41-b319-e2532e0087d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
657 | T16182-CA01-P0USG-182752 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b23b3dab-5a33-4a63-a47c-36df37b251cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
658 | T16182-CA01-P0USG-182753 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db939bf2-be70-4538-b28d-0bfc39480e43 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
659 | T16182-CA02-P0USG-182754 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=534c3759-0760-49cc-a075-c109e35c186c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
660 | T16182-CA02-P0USG-182755 | 2017-04-03 | T16182-DHI-LI-T-0204 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce9692c5-db73-4527-9788-12875cec415b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
698 | T16182-YD00-P6MKA-250008 | 2017-04-03 | T16182-DHI-LI-T-0183 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b65a0228-2a7f-431c-b95d-6deb9bc7e1fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
794 | T16182-YU02-P0MBA-121012 | 2017-04-03 | T16182-DHI-LI-T-0203 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
806 | T16182-YD00-P0GCF-130002 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b7f17d0-0736-4cb1-8ae1-c41c707aed05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
807 | T16182-XG07-P0GCF-130003 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=962b390e-60a4-4347-a8d8-74efaf430a3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
808 | T16182-XG02-P0GCF-130004 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0775001-54d9-4adc-ab8a-bf0b87291222 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
809 | T16182-XW03-P0GCF-130005 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2649d43b-815f-4c70-b434-d23f47bee8aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
810 | T16182-XN00-P0GCF-130008 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82952963-3f6d-4d22-8669-a1f676478b72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
812 | T16182-XS00-P0GNR-130101 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54016713-cec5-4e64-b292-a8e24d136b47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
813 | T16182-XG07-P0GNR-130102 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=556c9daf-0546-438b-9d4d-35b1637a288a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
814 | T16182-XG02-P0GNR-130103 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f74e4108-d7ae-4aaa-a704-ea22bee8fc0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
815 | T16182-XW03-P0GNR-130104 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed3f6f8b-767f-4ab1-9f2b-e47348dd6828 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
816 | T16182-XN00-P0GNR-130105 | 2017-04-03 | T16182-DHI-LI-T-0209 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4508b088-0aa1-4f12-b3fd-ebb471dc7f40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
831 | T16182-YT10-P0BBT-150651 | 2017-04-03 | T16182-DHI-LI-T-0202 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d2f3a27-0b78-41d4-b67b-979642044386 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1049 | T16182-CA00-P0UGD-181906 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fa2fec8-5760-4c2b-a7c3-e9953fc45d8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1057 | T16182-CA02-P0UGD-181960 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bffe92ff-c656-42aa-a3a7-6943e816ae58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1058 | T16182-CA02-P0UGD-181961 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e98ef8b-618c-494b-8faa-230ed7635557 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1061 | T16182-CA03-P0UGD-181967 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f885ee55-cc82-4be1-ba1f-f165df94a002 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1115 | T16182-XG02-P0ZEN-110002 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e047824d-3b30-4e96-b54f-e56254007ef8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1126 | T16182-XG02-P1EKC-110014 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6207580d-4e99-4c37-8d9b-1e6b2e26fd76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1157 | T16182-YU02-P0ZEN-150202 | 2017-04-04 | T16182-DHI-LI-T-0213 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c2d763a-4c50-40b9-82b5-bb0d7ccc8cfe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
118 | T16182-XG01-P0EKG-124001 | 2017-04-04 | T16182-DHI-LI-T-0217 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e76f07f9-6dfa-4262-843f-bb28cbbd8a3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1277 | T16182-CA00-P0UGD-181901 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13b35779-be83-4a44-b67c-078d689d6925 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1278 | T16182-CA00-P0UGD-181902 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e50107c0-6d2f-4bf6-a4db-755987c25ae0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1279 | T16182-CA00-P0UGD-181903 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8253aac-5263-487a-9e77-47f88d342061 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1280 | T16182-CA00-P0UGD-181904 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48172591-caef-4fc4-9de5-82ce9ea4b6e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1281 | T16182-CA00-P0UGD-181905 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e886764-36b3-47ee-8589-13c7873a77f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1282 | T16182-CA01-P0UGD-181951 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e47944-6c8c-4aaa-9866-a2157b257824 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1283 | T16182-CA01-P0UGD-181952 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e91a2071-a1ce-44eb-a23c-df6f32e2ef87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1284 | T16182-CA01-P0UGD-181953 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4b1f0a4-3593-491b-a986-c40b546163f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1285 | T16182-CA01-P0UGD-181954 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b6c4aa0-5432-4815-94fb-58feb43907d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1286 | T16182-CA01-P0UGD-181955 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e17bf16f-81cc-4bd1-8c41-e3f9b6a64b5d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1287 | T16182-CA02-P0UGD-181958 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=070cc64a-54a7-4587-9074-c4cd7c2cc213 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1288 | T16182-CA02-P0UGD-181959 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b15d1a68-1429-451e-b173-3832e83413eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1289 | T16182-CA03-P0UGD-181965 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6508477-eb59-4db8-aa82-9f1db1ca9da5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1290 | T16182-CA03-P0UGD-181966 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2fb054b1-5866-4877-906d-4490d696da89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1295 | T16182-XG02-P6LCA-110008 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4d15e6e-3359-451c-a9c9-ca97dd47ca59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1296 | T16182-XG02-P0LAA-110009 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c06c0ae8-969c-4c35-96fc-5d474d938a73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1297 | T16182-XG02-P0PGB-110010 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2f7ea6f-aa20-428c-9f7a-817bfada42c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1298 | T16182-XG02-P0GHC-110011 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=764a3654-503c-4323-b6b2-4a72bfffa85f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1300 | T16182-XG07-P0LA-110031 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=623f5fbe-fe0e-4daa-9837-028a2c248468 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1301 | T16182-XG07-P0PG-110032 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcd27cee-8cda-4658-a41e-b267b8bb790e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1302 | T16182-XG07-P0GHC-110033 | 2017-04-04 | T16182-DHI-LI-T-0215 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b33cae60-1632-4109-a03a-765bf8985596 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1311 | T16182-XW01-P0SAA-133301 | 2017-04-04 | T16182-DHI-LI-T-0223 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df28ee27-8b7d-4ac6-9150-dd16cc65eff4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
228 | T16182-YU03-P0CYE-136606 | 2017-04-04 | T16182-DHI-LI-T-0212 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8166ae8-dc2b-4333-8bcd-4fccc1b63ad7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
536 | T16182-CA00-P0UCB-180609 | 2017-04-04 | T16182-DHI-LI-T-0214 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85fe53e6-7f53-4c65-b297-8007e95a6123 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
537 | T16182-CA00-P0UCB-180610 | 2017-04-04 | T16182-DHI-LI-T-0214 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1d9005c-32b2-4ed8-818b-10e9fb643b97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
538 | T16182-CA00-P0UCB-180611 | 2017-04-04 | T16182-DHI-LI-T-0214 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d72dadd-f867-4d58-b58b-0adf6c7134f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
629 | T16182-CA02-P0UGD-181962 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4173637-b07e-4c13-be85-cf1c96852974 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
630 | T16182-CA02-P0UGD-181963 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c828b4c-540e-4c98-b70f-aff38d898f8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
631 | T16182-CA02-P0UGD-181964 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f6cd975-8b52-4b2b-a3aa-9d7f11988d8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
635 | T16182-CA03-P0UGD-181968 | 2017-04-04 | T16182-DHI-LI-T-0216 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bb313d8-bba0-4675-84c4-fc45cd10795f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
71 | T16182-XG02-P0MBA-121003 | 2017-04-04 | T16182-DHI-LI-T-0220 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d13dd7b-9ecf-4c29-aaf5-0ef70ce33511 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
74 | T16182-XW01-P0MBA-121005 | 2017-04-04 | T16182-DHI-LI-T-0221 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aef3aff8-acb2-4f51-99f3-0f88381cf17f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
75 | T16182-XW01-P0MBA-121006 | 2017-04-04 | T16182-DHI-LI-T-0221 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b398e38-5565-471b-9bc7-3af573f40645 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
990 | T16182-CA00-P0UCB-180607 | 2017-04-04 | T16182-DHI-LI-T-0214 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7dcae889-3472-4c33-9a1d-2e3b392519f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
991 | T16182-CA00-P0UCB-180608 | 2017-04-04 | T16182-DHI-LI-T-0214 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b12b6894-3504-4970-8144-18c95af1f81e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
992 | T16182-CA01-P0UCB-180658 | 2017-04-04 | T16182-DHI-LI-T-0214 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c90b2841-a1e1-472e-8f7b-76c67c16e864 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
993 | T16182-CA01-P0UCB-180659 | 2017-04-04 | T16182-DHI-LI-T-0214 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=092d3586-ca7b-4c20-b965-d74a551c3fdc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1099 | T16182-XG02-P0MKW-260033 | 2017-04-05 | T16182-DHI-LI-T-0188 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1100 | T16182-XG02-P0MKG-260034 | 2017-04-05 | T16182-DHI-LI-T-0188 | IFR | A | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1160 | T16182-YQ02-P0ZEN-152001 | 2017-04-05 | T16182-DHI-LI-T-0227 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea4e5529-58f6-4c79-b596-382786e39cbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1194 | T16182-YD00-P0CWQ-161406 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46cc7aba-7b3f-4537-bd7b-e2f8f86df4d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1304 | T16182-XW01-P0LA-110037 | 2017-04-05 | T16182-DHI-LI-T-0226 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12ff1dc0-daaa-410f-83fe-26c455f558cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1305 | T16182-XW01-P0PGB-110038 | 2017-04-05 | T16182-DHI-LI-T-0226 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00ce2443-0452-478d-b377-10cf89a0e121 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1306 | T16182-XW01-P0GHC-110039 | 2017-04-05 | T16182-DHI-LI-T-0226 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32fbf1c1-6e93-46a1-8817-a8c60e9755c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1312 | T16182-YD16-P0ZEN-152003 | 2017-04-05 | T16182-DHI-LI-T-0227 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1318 | T16182-YD00-P0CWQ-161402 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1659f7c-43d4-4acf-8e6e-056d33396f20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1319 | T16182-YD00-P0CWQ-161403 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=434fb1ee-10cb-4104-a78c-1600c4e9e846 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1320 | T16182-YD00-P0CWQ-161404 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7052d5b7-9149-4de5-bfa7-5cf3296a9ef7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1321 | T16182-YD00-P0CWQ-161405 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6794f71d-e62e-4083-8b50-eef7e48b32e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
290 | T16182-YE00-P0ZEN-152719 | 2017-04-05 | T16182-DHI-LI-T-0229 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8d407a9-0156-4d49-8081-f32bdd0d3572 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
292 | T16182-YE00-P0ZEN-152726 | 2017-04-05 | T16182-DHI-LI-T-0229 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9739331-337e-4306-a88d-1fd270b3be89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
358 | T16182-YD00-P0CWQ-161407 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5a7c8c0-c9b4-4dd4-a619-a8455b0b3496 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
359 | T16182-YD00-P0CWQ-161408 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e039eb1-ab1b-4ddc-89c5-62ee8cd044f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
48 | T16182-XW03-P0QJA-110052 | 2017-04-05 | T16182-DHI-LI-T-0224 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a680b87-93dd-4ee0-8e5c-dc31a3c6283b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
833 | T16182-YT10-P0BT-151001 | 2017-04-05 | T16182-DHI-LI-T-0225 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
881 | T16182-YD00-P0CWQ-161409 | 2017-04-05 | T16182-DHI-LI-T-0222 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d968b3f9-ab65-4fcd-bfde-bf921aa0de50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1083 | T16182-CA06-P0UBA-186100 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c7f28c0-bf94-4751-98a2-0da8256734db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1084 | T16182-CA00-P0UBA-186101 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e53b14c9-0112-4dc7-b1ca-1c903350eaf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1085 | T16182-CA00-P0UBA-186103 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ad66ba5-5704-4b3c-ba2e-3c866ab58150 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1086 | T16182-CA00-P0UBA-186104 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43eb906b-bdf1-4784-85b9-d23cc0abac17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1087 | T16182-CA01-P0UBA-186151 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19d8879d-0e73-43b1-9035-640df678e7f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1088 | T16182-CA01-P0UBA-186152 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd7ed4f1-28b1-4c8e-8d21-c9eb339034a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1089 | T16182-CA01-P0UBA-186154 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21ecd841-a095-4ed5-a148-736496a7dba1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1090 | T16182-CA02-P0UBA-186155 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bf1a1cb-e26a-4a13-8f9c-de76ec456d88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1091 | T16182-CA02-P0UBA-186156 | 2017-04-06 | T16182-DHI-LI-T-0236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b22fc882-ba64-40ce-8bd1-17db69272c7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1101 | T16182-YK10-P0LCP-410001 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c2e62f2-407f-4fb6-acc8-5061346c3694 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1102 | T16182-YK10-P0GHC-410011 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=342f0b47-a431-4442-ba6e-8fde6762747e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1103 | T16182-YK10-P0GKB-410021 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be149888-7925-4822-9983-d9e8ae48e6da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1104 | T16182-YK10-P0GKB-410031 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4d5de9d-8624-40ca-b240-b31d05f529c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1105 | T16182-YT10-P0LCP-410002 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc8a4990-c193-46a6-9514-5bd63a6b9b0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1106 | T16182-YT10-P0GHC-410012 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a5ae1bb-df15-42e4-9d2f-eefad9604fee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1107 | T16182-YT10-P0GKB-410022 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ec46684-4919-4890-9d4f-34a7555c5cbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1108 | T16182-YT10-P0GKB-410032 | 2017-04-06 | T16182-DHI-LI-T-0211 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f6ee5fc-e114-4e37-bd89-ed17bd5c5564 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1158 | T16182-YD00-P0UCA-150501 | 2017-04-06 | T16182-DHI-LI-T-0234 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15c1ee71-6b29-4393-872e-a9450d97c212 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1159 | T16182-YD00-P0UBA-150502 | 2017-04-06 | T16182-DHI-LI-T-0234 | IFR | C | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c77bc1a3-3cd7-48b1-97f6-4bc58e6a3516 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1208 | T16182-VE04-P0UZA-172901 | 2017-04-06 | T16182-DHI-LI-T-0232 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b135caf3-15a7-43e0-b66a-730e0694dbb9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1209 | T16182-XB02-P0UZA-172902 | 2017-04-06 | T16182-DHI-LI-T-0232 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=281daa32-c7e0-4d28-98a5-82d22aa213d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1210 | T16182-XB02-P0UZA-172903 | 2017-04-06 | T16182-DHI-LI-T-0232 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51a1ca28-78e0-4659-9187-a04c2a70b01e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1211 | T16182-VK02-P0UZA-172908 | 2017-04-06 | T16182-DHI-LI-T-0232 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f69e55a4-ba09-4fa8-b791-6af4f2b168ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
229 | T16182-YU02-P0CYE-136607 | 2017-04-06 | T16182-DHI-LI-T-0230 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f03fa6d-0732-420a-8a22-000ac8c4f970 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
485 | T16182-VE04-P0GUB-173301 | 2017-04-06 | T16182-DHI-LI-T-0233 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b0e91bc-c93d-4b18-bedb-f0310640f9ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
486 | T16182-XB02-P0GUB-173302 | 2017-04-06 | T16182-DHI-LI-T-0233 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5f23dc3-6e43-4b47-ad98-f850321136ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
487 | T16182-XB02-P0GUB-173303 | 2017-04-06 | T16182-DHI-LI-T-0233 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0efb647b-293f-451b-a37c-88e7dca85209 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
488 | T16182-VK02-P0GUB-173313 | 2017-04-06 | T16182-DHI-LI-T-0233 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5cf8cb0-6ed2-45c4-989f-b0f8e9501277 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
820 | T16182-XW03-P0SAC-133501 | 2017-04-06 | T16182-DHI-LI-T-0231 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6d6b5f9-6bda-4814-a7e4-1e4301f9f09e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
868 | T16182-YR05-P0ZEN-161011 | 2017-04-06 | T16182-DHI-LI-T-0235 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8c4009c-bbe0-4ee5-b7f7-b31eef12ac2d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1095 | T16182-XB00-P6MKA-250001 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=474eedc2-6a44-424d-950d-f0cc60ecd3a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1096 | T16182-XB00-P7MKA-250002 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7f4d65e-e5cb-4ecb-b12d-f606a7241211 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1098 | T16182-YD00-P0MKA-250004 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27a145a9-d10a-4094-bf7e-a455e4a33c03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1139 | T16182-XG02-P0GKB-120001 | 2017-04-07 | T16182-DHI-LI-T-0219 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c575bb1-c438-4fb5-bf4b-70fcb34cd811 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1140 | T16182-XG02-P0GKC-120002 | 2017-04-07 | T16182-DHI-LI-T-0219 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37e11eae-2227-4e6d-92aa-100c8f2aeca3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1324 | T16182-VK02-P0ZEN-170104 | 2017-04-07 | T16182-DHI-LI-T-0239 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6258be07-0d68-447c-bbcb-77bfe5f5b574 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1381 | T16182-CA00-P0UBA-181202 | 2017-04-07 | T16182-DHI-LI-T-0243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=244c6de6-0279-4ed2-854a-ce55eb111dd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1382 | T16182-CA00-P0UBA-181203 | 2017-04-07 | T16182-DHI-LI-T-0243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d075d22-5767-46ce-a378-60c30d786ce3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1383 | T16182-CA00-P0UBA-181204 | 2017-04-07 | T16182-DHI-LI-T-0243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ff20fd7-80a1-447b-9ce5-43ef4126b7ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1384 | T16182-CA01-P0UBA-181251 | 2017-04-07 | T16182-DHI-LI-T-0243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9fab07c-ec97-4971-a214-8fb6aac5368f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1385 | T16182-CA01-P0UBA-181252 | 2017-04-07 | T16182-DHI-LI-T-0243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31fc4dca-0e5e-458c-9ee2-7b4c782a66cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1386 | T16182-CA01-P0UBA-181253 | 2017-04-07 | T16182-DHI-LI-T-0243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88ce43b5-f427-4801-b7b4-37c32d7450a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1387 | T16182-CA01-P0UBA-181254 | 2017-04-07 | T16182-DHI-LI-T-0243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93a80407-98ea-4709-9136-b67204bd8b0e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
173 | T16182-YD00-P0GCF-130006 | 2017-04-07 | T16182-DHI-LI-T-0245 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d09b570-65aa-4cc5-8519-15140a2100f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
177 | T16182-YU02-P0GCF-130010 | 2017-04-07 | T16182-DHI-LI-T-0245 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e4a732e-7afd-431b-bdae-c9b7a76edffd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
183 | T16182-YL01-P0GCF-130035 | 2017-04-07 | T16182-DHI-LI-T-0246 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8fc7831-a86e-40ff-9f35-e012865ba1b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
226 | T16182-XG02-P0SGA-136603 | 2017-04-07 | T16182-DHI-LI-T-0237 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b106ec1c-6502-40c7-af21-877c3169fc53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
315 | T16182-YU02-P0CYA-154011 | 2017-04-07 | T16182-DHI-LI-T-0238 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7aeb97ea-c318-4a0f-a694-7af524bc6207 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
316 | T16182-YU02-P0CYA-154012 | 2017-04-07 | T16182-DHI-LI-T-0238 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0cdbd54-7cba-4604-af78-eb818bda52b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
317 | T16182-YU02-P0CYM-154013 | 2017-04-07 | T16182-DHI-LI-T-0238 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1c4448f-60c5-4976-a443-ff29514763b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
318 | T16182-YQ03-P0CY-154021 | 2017-04-07 | T16182-DHI-LI-T-0238 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6578af97-fe73-4e2b-947d-79a996b2cc29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
362 | T16182-CV03-P0EKU-163202 | 2017-04-07 | T16182-DHI-LI-T-0240 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71cf30b0-53a3-4ed5-b438-04e9beb03036 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
661 | T16182-CA00-P0UYC-182901 | 2017-04-07 | T16182-DHI-LI-T-0244 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c1ff27c-7441-4c32-8df9-6952a29067dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
662 | T16182-CA00-P0UYC-182902 | 2017-04-07 | T16182-DHI-LI-T-0244 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c0e4da4-7697-4662-a628-8cbb8750a9de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
663 | T16182-CA00-P0UYC-182903 | 2017-04-07 | T16182-DHI-LI-T-0244 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3434f486-b20e-403a-9b4f-ce35bb0f343c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
664 | T16182-CA00-P0UYC-182904 | 2017-04-07 | T16182-DHI-LI-T-0244 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d65304e9-ecba-4671-af29-d249b34130be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
665 | T16182-CA00-P0UYC-182905 | 2017-04-07 | T16182-DHI-LI-T-0244 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72600338-030a-4e67-bcf8-4f18090875c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
666 | T16182-CA00-P0UYC-182906 | 2017-04-07 | T16182-DHI-LI-T-0244 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16c0d7cf-9e04-45d9-9af3-db49561d4365 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
697 | T16182-YD00-P0MKA-250005 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8af4336c-f23d-4199-ba88-547a3650c126 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
704 | T16182-YD00-P0MKA-250017 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69caf1db-2e3f-4441-9364-84f6cc828d02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
705 | T16182-YD00-P0MKA-250018 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54f13b61-dac3-4f64-a962-b0b5aab739fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
706 | T16182-DM02-P0MKA-250019 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a37d6af-c1e6-46f4-af6f-74acff3283da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
707 | T16182-YD00-P0MKA-250020 | 2017-04-07 | T16182-DHI-LI-T-0199 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59c97000-187d-4063-a9ed-09436995fddf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
717 | T16182-YR02-P0CJN-290014 | 2017-04-07 | T16182-DHI-LI-T-0228 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5811aa31-537f-4a26-8536-61c174102e29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
811 | T16182-YL00-P0GCF-130009 | 2017-04-07 | T16182-DHI-LI-T-0246 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c7884cb-3026-4f1b-8693-411a9c775391 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
817 | T16182-YL00-P0GNR-130106 | 2017-04-07 | T16182-DHI-LI-T-0246 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=796eac0b-34e3-4a94-8091-b41657fad819 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
821 | T16182-XH01-P0SGA-136604 | 2017-04-07 | T16182-DHI-LI-T-0237 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=322c8a77-32bd-4fc2-8086-7c18f9dca772 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
88 | T16182-YT01-P0MBA-121030 | 2017-04-07 | T16182-DHI-LI-T-0241 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e457c5b7-e69e-4b1c-a218-77e47433d32e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
89 | T16182-YR05-P0MBA-121031 | 2017-04-07 | T16182-DHI-LI-T-0241 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6936b89b-e692-489d-b645-c32efcc2d93c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1156 | T16182-YR02-P0ZEN-150001 | 2017-04-10 | T16182-DHI-LI-T-0250 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=590c71f5-f049-4ee3-b30c-67a9cc1d3317 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1364 | T16182-VK02-P8UTH-172005 | 2017-04-10 | T16182-DHI-LI-T-0218 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7895dc4-9ce2-4bc2-bf38-798cc58fe9a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1389 | T16182-XB02-P8UTH-172003 | 2017-04-10 | T16182-DHI-LI-T-0218 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4500d3cf-c243-428f-a8ae-53abbdf0a58f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1390 | T16182-XB02-P8UTH-172004 | 2017-04-10 | T16182-DHI-LI-T-0218 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f0b8c83-7bcc-41fe-b671-66c0be0ebb93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
271 | T16182-YT10-P0ZEN-152203 | 2017-04-10 | T16182-DHI-LI-T-0249 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e826b44f-a21a-4441-b090-ec47f3621ec2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
273 | T16182-YQ01-P0ZEN-152301 | 2017-04-10 | T16182-DHI-LI-T-0249 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e373d13-5846-42ed-b893-c1e2c2e54de0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
275 | T16182-YB11-P0ZEN-152401 | 2017-04-10 | T16182-DHI-LI-T-0249 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e26c40c4-c968-49d0-b43a-c72e4e5dd54c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
832 | T16182-YT10-P0BAA-150701 | 2017-04-10 | T16182-DHI-LI-T-0248 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d56f5a4f-9e8b-43d5-977b-00139c8e9f7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
925 | T16182-VE04-P0MPA-171103 | 2017-04-10 | T16182-DHI-LI-T-0247 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7fdbca6-24c4-4ba7-b14a-bdb4e3480cce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
928 | T16182-XB02-P0MPA-171106 | 2017-04-10 | T16182-DHI-LI-T-0247 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e38cd916-8b84-4aa0-973c-f40ece7ac385 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
929 | T16182-VK02-P0MPA-171117 | 2017-04-10 | T16182-DHI-LI-T-0247 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6df27529-e059-4a26-bb6b-a01d13f2f5c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1062 | T16182-CA05-P0UGD-181981 | 2017-04-11 | T16182-DHI-LI-T-0257 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d572d87-a765-4a6b-bada-99a73c274405 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1063 | T16182-CA05-P0UGD-181982 | 2017-04-11 | T16182-DHI-LI-T-0257 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ac45e9c-42da-4421-95c7-86ac200b76bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1064 | T16182-CA05-P0UGD-181983 | 2017-04-11 | T16182-DHI-LI-T-0257 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5afdd2ae-0198-4fb6-930d-1060177f9cc0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1065 | T16182-CA05-P0UGD-181984 | 2017-04-11 | T16182-DHI-LI-T-0257 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f136a2a9-18af-46be-8898-529b15ae9d14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1066 | T16182-CA05-P0UGD-181985 | 2017-04-11 | T16182-DHI-LI-T-0257 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4131518-c0fc-450f-9410-44eb0f6986dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1067 | T16182-CA05-P0UGD-181986 | 2017-04-11 | T16182-DHI-LI-T-0257 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce56b590-34f0-47af-af4a-ce65fbdeec6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
156 | T16182-CV03-P8ZEN-125612 | 2017-04-11 | T16182-DHI-LI-T-0253 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=412ed8cd-a530-4897-8f45-a6d85bf2ddcf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
157 | T16182-CC08-P8ZEN-125614 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=831063a2-626f-45cd-924c-ef379c791d75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
158 | T16182-CC08-P8ZEN-125615 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=003a85ac-7e24-4c88-aa09-e25d8dfdc85b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
159 | T16182-CC08-P8ZEN-125616 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49aa0bfe-3b46-49b1-9ff9-15b53b73891d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
160 | T16182-CC08-P8ZEN-125617 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f27a774c-59a8-4a8a-a355-07e67ea7fe36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
161 | T16182-CC08-P8ZEN-125618 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=367e5e6e-711a-4255-abe9-27a602cd89bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
162 | T16182-CC08-P8ZEN-125619 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f928e3c3-43da-4b0f-8440-fa7dd156e632 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
803 | T16182-CC08-P8QHB-125151 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89f33df2-4dba-42c2-aac3-d9d88d9a7dd0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
804 | T16182-CC08-P8QHA-125300 | 2017-04-11 | T16182-DHI-LI-T-0251 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c47ec71-6970-4817-88e3-344042243b09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
106 | T16182-XL00-P0LB-122030 | 2017-04-12 | T16182-DHI-LI-T-0267 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a5af7e8-5b1e-41c8-9503-b4d8a5bcf9db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
107 | T16182-XN00-P0LB-122032 | 2017-04-12 | T16182-DHI-LI-T-0267 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4163ab42-4d58-4e7f-8c85-ee7224507c20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
108 | T16182-XN00-P0LB-122033 | 2017-04-12 | T16182-DHI-LI-T-0266 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc1fc4c0-0116-4050-9993-888e7c522389 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1116 | T16182-XG02-P0LBA-110003 | 2017-04-12 | T16182-DHI-LI-T-0265 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b690c32-c7e3-41ed-875a-1e7a2b7709da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1117 | T16182-XG02-P0LBC-110004 | 2017-04-12 | T16182-DHI-LI-T-0265 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c67d846c-eebe-4505-9d64-bc566053cdc9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1118 | T16182-XG02-P0LBG-110005 | 2017-04-12 | T16182-DHI-LI-T-0265 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9cddc99-b1a3-4121-a400-f1c876be308a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1119 | T16182-XG02-P0LBS-110006 | 2017-04-12 | T16182-DHI-LI-T-0265 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4ef3cdb-681c-4fc7-a176-caa9b116f687 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1120 | T16182-XG02-P6LCM-110007 | 2017-04-12 | T16182-DHI-LI-T-0265 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b3dc191-0053-4bc4-805f-5107e0f40a1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
113 | T16182-YL00-P0LB-122075 | 2017-04-12 | T16182-DHI-LI-T-0266 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fabdaa6a-5847-49e2-93b9-7ba5949d8585 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
117 | T16182-YD00-P0LB-122109 | 2017-04-12 | T16182-DHI-LI-T-0254 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2fdce8bb-c7b9-4c87-902d-2099b1b22b7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1299 | T16182-XG02-P0QJA-110012 | 2017-04-12 | T16182-DHI-LI-T-0260 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74035ad9-24e8-45ec-8a56-71614e713a7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1303 | T16182-XW01-P0LC-110036 | 2017-04-12 | T16182-DHI-LI-T-0264 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52e7f651-c966-497d-9aa6-177ce59d2e26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1308 | T16182-XS00-P0LA-110042 | 2017-04-12 | T16182-DHI-LI-T-0256 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b89d664d-7ca0-4cbd-8ec2-30d121f8da5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1309 | T16182-XS00-P0PGB-110043 | 2017-04-12 | T16182-DHI-LI-T-0256 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cf20814-807b-444e-8270-00ca9676049f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1310 | T16182-XS00-P0GHC-110044 | 2017-04-12 | T16182-DHI-LI-T-0256 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=167c26b6-ef78-4169-ae73-d2a83735ff6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
163 | T16182-YD02-P8ZEN-125762 | 2017-04-12 | T16182-DHI-LI-T-0263 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc07f350-f4e6-4c3f-bbea-c074e634c757 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
164 | T16182-YE03-P8ZEN-125767 | 2017-04-12 | T16182-DHI-LI-T-0263 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c20b0654-b8e4-4f46-936d-8850af1060ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
165 | T16182-YD00-P0LAC-126001 | 2017-04-12 | T16182-DHI-LI-T-0259 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6bfdd23-2fcd-4eda-9481-95ebf0a4c210 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
166 | T16182-XG02-P0LAC-126003 | 2017-04-12 | T16182-DHI-LI-T-0259 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b033003-9153-445f-a8c2-49e611fef9d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
167 | T16182-YT01-P0LAC-126004 | 2017-04-12 | T16182-DHI-LI-T-0259 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91007af6-a7e2-4f5b-8042-a558c7a9d76e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
335 | T16182-CV03-P0CWQ-161123 | 2017-04-12 | T16182-DHI-LI-T-0255 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03433695-c07e-4bfd-a3fe-cc37f70decfa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
474 | T16182-VE04-P0UAZ-172601 | 2017-04-12 | T16182-DHI-LI-T-0268 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=684c066e-f01c-42ed-a973-ebe068365b24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
475 | T16182-XB02-P0UAZ-172602 | 2017-04-12 | T16182-DHI-LI-T-0268 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a86e8824-92c1-461c-88c3-e36578b1b428 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
476 | T16182-XB02-P0UAZ-172603 | 2017-04-12 | T16182-DHI-LI-T-0268 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20cc996c-6472-4837-bad0-aa826b0a3469 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
477 | T16182-XB02-P0UAZ-172608 | 2017-04-12 | T16182-DHI-LI-T-0268 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29f60fea-ce30-4b1c-beb9-f592f0ea0d67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
478 | T16182-VK02-P0UAZ-172613 | 2017-04-12 | T16182-DHI-LI-T-0268 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1a65678-f041-433b-b0ce-a6cd6eb9e45c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
712 | T16182-YS00-P0CJN-290001 | 2017-04-12 | T16182-DHI-LI-T-0269 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab9bb688-5ae6-4148-94f4-c395b5257bc8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
739 | T16182-UE00-P0MB-100004 | 2017-04-12 | T16182-DHI-LI-T-0258 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dace4bac-8c22-4980-91ad-2a3ea3789970 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
740 | T16182-UE00-P0MB-100005 | 2017-04-12 | T16182-DHI-LI-T-0258 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c114fc8-5f69-4eb5-a450-51a725d54eb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
741 | T16182-UE00-P0MB-100006 | 2017-04-12 | T16182-DHI-LI-T-0258 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b6192e5-b660-485e-87de-cb0683c54f83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
742 | T16182-UE00-P0MB-100007 | 2017-04-12 | T16182-DHI-LI-T-0258 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c415c2ed-f20f-43bc-bd59-8b3fa30a8365 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
743 | T16182-UE00-P0UMA-100008 | 2017-04-12 | T16182-DHI-LI-T-0258 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5554f7ed-2314-4b80-8f02-d0341536a39d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
744 | T16182-UE00-P0UMA-100009 | 2017-04-12 | T16182-DHI-LI-T-0258 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94705926-0232-4c32-bf44-edea24e820f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
745 | T16182-UE00-P0UMA-100010 | 2017-04-12 | T16182-DHI-LI-T-0258 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2de67a9-84ac-4a6f-adc8-4d63a260d6d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
802 | T16182-YB03-P0LB-122048 | 2017-04-12 | T16182-DHI-LI-T-0261 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
204 | T16182-XW03-P0SAJ-133701 | 2017-04-13 | T16182-DHI-LI-T-0272 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a17fa7b-c191-4a5f-9ec7-f236c9d10b64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
205 | T16182-XG07-P0SAJ-133702 | 2017-04-13 | T16182-DHI-LI-T-0272 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33a8f136-dd35-41db-9aa9-67452540fb74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
206 | T16182-XW03-P0SAJ-133703 | 2017-04-13 | T16182-DHI-LI-T-0272 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a681661f-cb2d-4235-bf25-75e089f6aa5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
207 | T16182-XH02-P0SAJ-133704 | 2017-04-13 | T16182-DHI-LI-T-0272 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65a4afd2-f46e-46af-8df3-3a2629050a5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
322 | T16182-YQ08-P0CY-154048 | 2017-04-13 | T16182-DHI-LI-T-0270 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e2682e1-bfca-4dc2-aedd-17f46dc24d50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
801 | T16182-XG02-P0LB-122022 | 2017-04-13 | T16182-DHI-LI-T-0271 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e245cf55-d776-469e-ae03-45a441a0e365 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
822 | T16182-CV03-P0ZEN-140001 | 2017-04-13 | T16182-DHI-LI-T-0262 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a66f7f1-13de-44b6-863b-b3938ea36195 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
829 | T16182-YD00-P0UBA-150506 | 2017-04-13 | T16182-DHI-LI-T-0274 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1395b87-2799-44f9-9e89-47505e3fbe1e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
870 | T16182-YL01-P0CBA-161101 | 2017-04-13 | T16182-DHI-LI-T-0273 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1195 | T16182-YS00-P0ZEN-163309 | 2017-04-14 | T16182-DHI-LI-T-0277 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bbd47f0-a303-4d79-a547-d72e20bdcc27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1196 | T16182-YS00-P0ZEN-163310 | 2017-04-14 | T16182-DHI-LI-T-0277 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09848110-0de9-482c-ac6d-2a61a8343f53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1307 | T16182-XS00-P0LC-110041 | 2017-04-14 | T16182-DHI-LI-T-0290 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4748db7b-a4e1-4d19-828f-c2a2af526b9f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1322 | T16182-XW01-P0ZEN-165001 | 2017-04-14 | T16182-DHI-LI-T-0288 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=102a2107-1a32-43b2-b388-00be01053b4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
200 | T16182-XW03-P0SAK-133601 | 2017-04-14 | T16182-DHI-LI-T-0289 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5716e9b-ae70-4a23-a823-45b600c1ddb0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
201 | T16182-XG07-P0SAK-133602 | 2017-04-14 | T16182-DHI-LI-T-0289 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=837da337-a0eb-4fe3-af7f-fb6755600ddc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
202 | T16182-XW03-P0SAK-133603 | 2017-04-14 | T16182-DHI-LI-T-0289 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bac42495-bedc-45d6-a995-d48dbe49e4f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
203 | T16182-XH02-P0SAK-133604 | 2017-04-14 | T16182-DHI-LI-T-0289 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26406d10-a419-4525-9ac1-c33537e71b52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
220 | T16182-XW03-P0SAV-135101 | 2017-04-14 | T16182-DHI-LI-T-0285 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b6ab9df-d311-4e90-802d-e3afa40c1bdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
221 | T16182-XG07-P0SAV-135102 | 2017-04-14 | T16182-DHI-LI-T-0285 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfc5cd92-efe5-4e84-b355-beb0bd1f788e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
222 | T16182-XW03-P0SAV-135103 | 2017-04-14 | T16182-DHI-LI-T-0285 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16f71175-42c3-4c0b-a41a-3c9be6c6b0f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
223 | T16182-XH02-P0SAV-135104 | 2017-04-14 | T16182-DHI-LI-T-0285 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adc51b7b-69e2-4b61-a93a-e17abe40b888 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
483 | T16182-XB02-P0UZJ-173202 | 2017-04-14 | T16182-DHI-LI-T-0279 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2f20df8-bd9d-4cc8-b252-3e7beb0ac878 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
484 | T16182-VK02-P0UZJ-173208 | 2017-04-14 | T16182-DHI-LI-T-0279 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c272a79d-8832-4a79-829f-65c9de2b75ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
523 | T16182-CA05-P0UMA-180481 | 2017-04-14 | T16182-DHI-LI-T-0287 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83279c62-28fc-4a29-b9fc-4779842b8169 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
524 | T16182-CA05-P0UMA-180482 | 2017-04-14 | T16182-DHI-LI-T-0287 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ca2a3cf-efd4-4d22-a91e-46d5061e1f3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
76 | T16182-XB00-P0MBA-121007 | 2017-04-14 | T16182-DHI-LI-T-0281 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ded178bf-0a1b-4875-893b-4bf6bfd9a9fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
77 | T16182-XJ00-P0MBA-121008 | 2017-04-14 | T16182-DHI-LI-T-0282 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74db63da-13f0-4a25-b3af-6d9d9b6f672b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
773 | T16182-XW03-P0LA-110048 | 2017-04-14 | T16182-DHI-LI-T-0278 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e254d50b-c593-4b3a-b3ab-18fd5836e734 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
774 | T16182-XW03-P0LA-110049 | 2017-04-14 | T16182-DHI-LI-T-0278 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ce1a258-c539-4d98-a963-90bfa7435c9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
790 | T16182-XG07-P0ZEN-120050 | 2017-04-14 | T16182-DHI-LI-T-0280 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b2a43ee-4c26-4861-ab7e-0b04f9d2dd09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
83 | T16182-YL06-P0MBA-121016 | 2017-04-14 | T16182-DHI-LI-T-0283 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc1c47be-98a4-43b3-b176-529d3c6d59f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
84 | T16182-YU05-P0MBA-121017 | 2017-04-14 | T16182-DHI-LI-T-0283 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77c77800-25e5-478a-99d4-f2f0ab82597a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
86 | T16182-YL01-P0MBA-121028 | 2017-04-14 | T16182-DHI-LI-T-0284 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ee453ef-6e96-4a10-8fb4-856892d24960 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1109 | T16182-DA01-P0ZEN-020001 | 2017-04-17 | T16182-DHI-LI-T-0302 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec79d35a-844e-4cfd-90e6-3db79cfd137c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1110 | T16182-DA01-P0ZEN-020002 | 2017-04-17 | T16182-DHI-LI-T-0302 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb71d2e9-4cb3-425b-9bed-b222c0c64d96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1163 | T16182-YE03-P0BAU-152524 | 2017-04-17 | T16182-DHI-LI-T-0292 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c906f9b-08bd-4e39-85b0-1ab85b612f14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1316 | T16182-YR04-P0CUQ-161111 | 2017-04-17 | T16182-DHI-LI-T-0291 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f448e9f-03f1-4b61-b745-666190dd4c27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1317 | T16182-YD00-P0CWQ-161401 | 2017-04-17 | T16182-DHI-LI-T-0291 | IFR | D | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84ef5b9d-7ead-4308-8e6a-f4bb868a6017 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
154 | T16182-CV03-P8ZEN-125606 | 2017-04-17 | T16182-DHI-LI-T-0301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d7139b2-cc59-4948-bcf4-4cdb97bf800b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
155 | T16182-CV03-P8ZEN-125610 | 2017-04-17 | T16182-DHI-LI-T-0301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=512bfbad-c0f6-47d1-b332-50d4c4bdbcc2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
240 | T16182-XG02-P0SGA-136701 | 2017-04-17 | T16182-DHI-LI-T-0295 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfecebc1-cfe1-40b3-a48b-d9f889d3ee1a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
241 | T16182-XG02-P0SGE-136702 | 2017-04-17 | T16182-DHI-LI-T-0295 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06d030bd-aa01-4ed4-9919-cecd7cfd6295 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
242 | T16182-XG02-P0SGK-136703 | 2017-04-17 | T16182-DHI-LI-T-0295 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=280c97bf-df25-442b-b5eb-491240ff38db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
243 | T16182-YU02-P0CYE-136742 | 2017-04-17 | T16182-DHI-LI-T-0296 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3ca68c3-2d20-4dfd-afe5-a4be757a3090 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
262 | T16182-YD00-P0BAT-150621 | 2017-04-17 | T16182-DHI-LI-T-0298 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5184d7d9-2cec-437d-a116-933c82e924b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
272 | T16182-YT10-P0ZEN-152204 | 2017-04-17 | T16182-DHI-LI-T-0297 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eabd8162-882e-4f96-be00-bcfa1fa8265a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
274 | T16182-YQ01-P0ZEN-152302 | 2017-04-17 | T16182-DHI-LI-T-0297 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58f87fb6-bce3-4cb5-9695-a7a8f1fc871a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
276 | T16182-YB11-P0ZEN-152402 | 2017-04-17 | T16182-DHI-LI-T-0297 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65195a36-92b1-4f66-9815-171e0c2b53a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
623 | T16182-CA01-P0UGD-181956 | 2017-04-17 | T16182-DHI-LI-T-0293 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b5769ea-03e4-451b-9307-06f72d9ce606 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
624 | T16182-CA01-P0UGD-181957 | 2017-04-17 | T16182-DHI-LI-T-0293 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d9dba81-2967-40f2-a608-a0da26049855 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
772 | T16182-XW03-P0LB-110045 | 2017-04-17 | T16182-DHI-LI-T-0299 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fd2fc0c-4b3c-44b5-b824-e98c529be4c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
918 | T16182-YR02-P0ZEN-165900 | 2017-04-17 | T16182-DHI-LI-T-0291 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7607b0df-ce04-41e2-bc82-832c976b8150 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
941 | T16182-VE04-P0UGF-172521 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=977dcf0a-378a-46ee-b967-4269ce2ad9e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
942 | T16182-XB02-P0UGF-172522 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=787a7f3f-a4aa-4b0d-aca3-3cc54aedc814 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
943 | T16182-VK02-P0UGF-172523 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f439bf2-61c8-47b4-8dc6-eb178d12e065 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
944 | T16182-VE04-P0UGD-172541 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8583020e-2a1d-4340-a55c-6b036f3ecca1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
945 | T16182-XB02-P0UGD-172542 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7a9de3f-8106-4ef8-ba31-40318c53d7da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
946 | T16182-VK02-P0UGD-172543 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db1a1ba6-5e78-4b31-a659-664943c8d8db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
947 | T16182-VE04-P0UGG-172561 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96894448-3fc8-4645-96f3-ac1dd0f1602f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
948 | T16182-XB02-P0UGG-172562 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e19fc189-3bac-4dde-9d8d-8b33f77bf0ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
949 | T16182-VK02-P0UGG-172563 | 2017-04-18 | T16182-DHI-LI-T-0275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f128a32-b746-49e3-a78f-fc1ea5fd108d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1075 | T16182-CA06-P0QJA-184800 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b80f583a-91d5-462c-a876-94942880aea0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1076 | T16182-CA00-P0QJA-184801 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e16635a2-dcce-4ca4-9450-fa69beebb14e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1077 | T16182-CA00-P0QJA-184802 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4b3ac8d-a449-4730-93b3-87cfe0b4ac8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1078 | T16182-CA00-P0QJA-184803 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40856f62-750e-46c1-a294-e89712c82990 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1079 | T16182-CA01-P0QJA-184851 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d86209f7-f846-4987-b183-8435f96889c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1080 | T16182-CA01-P0QJA-184852 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24269424-8669-4d9d-8b01-d5f1bc0e13f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1081 | T16182-CA01-P0QJA-184853 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0fe6d2a-e91b-4f9d-852c-bde9426f3e5d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1082 | T16182-CA02-P0QJA-184854 | 2017-04-19 | T16182-DHI-LI-T-0307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88bb3201-d712-42f2-9eaf-84fa8a65ddb2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1145 | T16182-XG07-P0SCA-120014 | 2017-04-19 | T16182-DHI-LI-T-0304 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69b259f2-66ef-4b50-be23-e568320d62b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1147 | T16182-XS00-P0SCA-120016 | 2017-04-19 | T16182-DHI-LI-T-0304 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=caff858e-8f89-4a75-9180-fa029b412633 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
701 | T16182-UC02-P0MKA-250013 | 2017-04-19 | T16182-DHI-LI-T-0300 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35e970fa-e71b-4bdd-8fb4-03655b6cd85b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
702 | T16182-UC02-P0MKA-250014 | 2017-04-19 | T16182-DHI-LI-T-0300 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1b4876c-81f9-421c-a58a-9a8c8b4243f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
708 | T16182-DM02-P0MKA-250021 | 2017-04-19 | T16182-DHI-LI-T-0300 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66bb33a4-10eb-4cfc-b7fd-51ad69560d71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
709 | T16182-UC02-P0MKA-250022 | 2017-04-19 | T16182-DHI-LI-T-0300 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e2bdc38-cdfd-4333-acb9-5b88fd9e2175 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
775 | T16182-XW03-P0GHC-110051 | 2017-04-19 | T16182-DHI-LI-T-0305 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=053a5657-ab86-4497-8f45-94f7492fb613 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
786 | T16182-XW03-P0SCA-120017 | 2017-04-19 | T16182-DHI-LI-T-0304 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20a85900-c52e-4e55-b253-75627d582546 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
866 | T16182-YR02-P0ZEN-152801 | 2017-04-19 | T16182-DHI-LI-T-0309 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
95 | T16182-DF04-P0LB-122004 | 2017-04-19 | T16182-DHI-LI-T-0303 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0acfce85-4f4d-4847-aa91-bc054b2057a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1093 | T16182-VL00-P0MPA-220001 | 2017-04-20 | T16182-DHI-LI-T-0308 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3126f59-2d4b-486f-ae48-748aa75b3c05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1094 | T16182-UF00-P0MAA-220003 | 2017-04-20 | T16182-DHI-LI-T-0308 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5736d6e-3b85-4e70-9752-813bbcfef73b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
286 | T16182-YE03-P0BAU-152510 | 2017-04-20 | T16182-DHI-LI-T-0306 | IFI | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
120 | T16182-YD00-P0EKG-124025 | 2017-04-21 | T16182-DHI-LI-T-0317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65271144-4c66-4281-b7f3-4405739e720c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
121 | T16182-YD00-P0EKG-124026 | 2017-04-21 | T16182-DHI-LI-T-0317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=920b55c1-93ac-4656-a631-718266c9f38a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
122 | T16182-YT01-P0EKG-124027 | 2017-04-21 | T16182-DHI-LI-T-0317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=459037be-7d58-4ea7-b688-7150d03154d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
123 | T16182-YT01-P0EKG-124029 | 2017-04-21 | T16182-DHI-LI-T-0317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfe8fd39-bc66-4019-b955-a92dbd80a868 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
124 | T16182-YT01-P0EKG-124030 | 2017-04-21 | T16182-DHI-LI-T-0318 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6f4ab96-0e5e-4d7e-a58d-93065f060fd2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
125 | T16182-YT01-P0EKG-124031 | 2017-04-21 | T16182-DHI-LI-T-0317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9bc97b9-0475-4099-9163-7ddd4946bed3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
126 | T16182-YT01-P0EKG-124032 | 2017-04-21 | T16182-DHI-LI-T-0317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91235ab2-ba0b-4e2e-9b7f-75679e030868 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
127 | T16182-YT01-P0EKG-124033 | 2017-04-21 | T16182-DHI-LI-T-0317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a7b3161-f475-4289-81a5-3fc9e7e49367 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1313 | T16182-YE03-P0BAU-152505 | 2017-04-21 | T16182-DHI-LI-T-0315 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cadc837-fcc5-4f1b-a363-a8ca42c27fa0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1314 | T16182-YE03-P0BAU-152506 | 2017-04-21 | T16182-DHI-LI-T-0315 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1668911-b835-4967-aee9-049c08702099 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
216 | T16182-XW03-P0SAG-134901 | 2017-04-21 | T16182-DHI-LI-T-0312 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bce6d16-b41e-43bb-878c-3ebe16872c60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
217 | T16182-XG07-P0SAG-134902 | 2017-04-21 | T16182-DHI-LI-T-0312 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80dbeb25-bdd8-4d3b-aadd-076b44f2eca3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
218 | T16182-XW03-P0SAG-134903 | 2017-04-21 | T16182-DHI-LI-T-0312 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e04890b-5ec7-4b32-b972-cde387cb160d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
219 | T16182-XH02-P0SAG-134904 | 2017-04-21 | T16182-DHI-LI-T-0312 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=212ab1f4-1c53-42a2-bbf1-eb0e991a5d6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
284 | T16182-YE03-P6BAU-152508 | 2017-04-21 | T16182-DHI-LI-T-0315 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75ed12f6-7e1f-4a1f-a9f4-c91382f53b2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
285 | T16182-YE03-P7BAU-152509 | 2017-04-21 | T16182-DHI-LI-T-0315 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d192adc0-e8d3-44b9-aa79-838eb89846a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
340 | T16182-YF00-P0CBA-161210 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f16e3816-87bb-48bf-8554-97fe675f75b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
341 | T16182-YF00-P0CBA-161211 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=003ca809-28c0-4230-a1cd-a9519518d255 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
342 | T16182-YF00-P0CBA-161212 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23a64781-d9da-425c-b92b-bd03b095ce58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
343 | T16182-YF00-P0CBA-161213 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4c2f189-021a-4971-8302-a391f0f01cf2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
344 | T16182-YF00-P0CBA-161214 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5873fff-e441-416c-80a8-d650ce10cb63 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
345 | T16182-YF00-P0CBA-161216 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cec61028-f131-4c35-984c-09881498ea49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
346 | T16182-YF00-P0CGA-161310 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a311d05-9520-4c45-9e3b-60868a8b0465 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
347 | T16182-YF00-P0CGA-161311 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16aaad32-67f3-45aa-a0ee-bc648a25d4fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
348 | T16182-YF00-P0CGA-161312 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ce8798c-8d0a-4644-add2-2c88c3d4a15e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
349 | T16182-YF00-P0CGA-161313 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55f569cf-8c1b-4f35-978c-3739dc41f1e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
350 | T16182-YF00-P0CGA-161314 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=495e2b30-613b-43ab-a093-a0fe02373502 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
351 | T16182-YF00-P0CGA-161316 | 2017-04-21 | T16182-DHI-LI-T-0311 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93105da6-99f9-4da3-b759-34e4fadf855f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
413 | T16182-VE04-P0UMX-171004 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf189e7e-e58f-4f7e-abe0-07cf548df465 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
414 | T16182-XB02-P0UMX-171005 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18ed80ea-00f2-44a8-9adf-047a8f89f3e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
415 | T16182-XB02-P0UMX-171006 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=288838ae-6383-4d10-bc17-d6666845c653 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
416 | T16182-XB02-P0UMX-171007 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7dc6a82d-d0f9-460a-ac68-60ee7601ff52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
417 | T16182-XB02-P0UMX-171008 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6004efe5-7a03-4a57-adf5-44c787122399 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
418 | T16182-XB02-P0UMX-171009 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c05fc5e6-4e0f-4b2f-90b4-ab7480e43fc2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
419 | T16182-XB02-P0UMX-171010 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53216f04-fb33-4cd7-bc56-ab8dce59b62a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
420 | T16182-XB02-P0UMX-171011 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5bef032-4fd4-4a7c-924e-668519565be7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
421 | T16182-VK02-P0UMX-171012 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=520067a4-477f-42c3-b625-32ffd2570758 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
422 | T16182-VK02-P0UMX-171013 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1be0c05-e98a-4c7d-8352-de93f592ba95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
423 | T16182-VK02-P0UMX-171014 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=967a8e8b-55af-4ef4-84d3-9d6b27dda6cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
424 | T16182-VK02-P0UMX-171015 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0bf1157-fcc0-4549-a4a0-9365e1c8c9fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
425 | T16182-VK02-P0UMX-171016 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af9348e4-0458-4ed8-acfd-5f3a79716666 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
426 | T16182-VK02-P0UMX-171017 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=892588bc-4110-4b21-afb0-c72a30a68615 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
427 | T16182-VK02-P0UMX-171021 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c385578-6977-485d-bc97-d94b5eaec214 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
428 | T16182-VK02-P0UMX-171022 | 2017-04-21 | T16182-DHI-LI-T-0313 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e129cd58-5823-4b72-b00a-ecf18eacea7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
700 | T16182-UC02-P0MKA-250010 | 2017-04-21 | T16182-DHI-LI-T-0310 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=170a1cf2-c597-4165-9cb2-72410cef7932 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
716 | T16182-YS01-P0MKY-290011 | 2017-04-21 | T16182-DHI-LI-T-0314 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12077cab-c7d7-49af-a746-4542d3c8b186 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
931 | T16182-VE04-P0UHA-171802 | 2017-04-21 | T16182-DHI-LI-T-0316 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30721d1a-27d8-4050-a935-a966fd2f3d4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
934 | T16182-XB02-P0UHA-171805 | 2017-04-21 | T16182-DHI-LI-T-0316 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3599d676-b1da-481a-a793-ab6920f5b817 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
935 | T16182-XB02-P0UHA-171806 | 2017-04-21 | T16182-DHI-LI-T-0316 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f315db17-3ada-46c1-8fc6-a0daa14c0f78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
936 | T16182-XB02-P0UHA-171807 | 2017-04-21 | T16182-DHI-LI-T-0316 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e4f08d5-0e52-4106-9478-2e7512388491 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
104 | T16182-XB02-P0LB-122020 | 2017-04-24 | T16182-DHI-LI-T-0327 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d80e9ef-8583-44ea-9bab-12aca94d675d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1114 | T16182-XG05-P0ZEN-110001 | 2017-04-24 | T16182-DHI-LI-T-0323 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1130 | T16182-XW01-P0LB-110035 | 2017-04-24 | T16182-DHI-LI-T-0325 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44a89987-1519-4fa2-94df-3f0d312d6f59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
115 | T16182-YT01-P0LB-122103 | 2017-04-24 | T16182-DHI-LI-T-0327 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afba1b86-a480-42cb-a136-da6207dc7189 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
116 | T16182-YT02-P0LB-122104 | 2017-04-24 | T16182-DHI-LI-T-0327 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fd30f42-fefe-4290-bb43-dcb2b7fe1af9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
212 | T16182-XW03-P0SAI-133901 | 2017-04-24 | T16182-DHI-LI-T-0319 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=107d114f-526c-4559-8733-b287db15b460 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
213 | T16182-XG07-P0SAI-133902 | 2017-04-24 | T16182-DHI-LI-T-0319 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6b15a4a-2c22-42aa-b6a0-a6893e7e6225 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
214 | T16182-XW03-P0SAI-133903 | 2017-04-24 | T16182-DHI-LI-T-0319 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=579c1be5-1a92-4144-8859-68de7a8662f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
215 | T16182-XH02-P0SAI-133904 | 2017-04-24 | T16182-DHI-LI-T-0319 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a13c3dbe-b2b1-4a62-89e6-77ab590c6e39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
244 | T16182-XG02-P0SGE-137303 | 2017-04-24 | T16182-DHI-LI-T-0320 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f01231f8-28a3-4350-a045-f59473d77c02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
319 | T16182-YQ08-P0CY-154031 | 2017-04-24 | T16182-DHI-LI-T-0322 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b96b827f-5e8c-44a6-ad1b-a285996f1631 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
320 | T16182-YQ08-P0CY-154032 | 2017-04-24 | T16182-DHI-LI-T-0322 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69ed1b31-1170-462d-9833-f454d81df395 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
321 | T16182-YQ08-P0CY-154033 | 2017-04-24 | T16182-DHI-LI-T-0322 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=980f6e21-2bb4-4f43-93a9-f118e6b367c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4 | T16182-DP00-P0ZEN-020005 | 2017-04-24 | T16182-DHI-LI-T-0276 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9926bc51-9522-4bc3-9f35-632ca2c12551 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
459 | T16182-VE04-P0BAA-172401 | 2017-04-24 | T16182-DHI-LI-T-0324 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ba960d5-79da-4627-b08b-ef7833348d28 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
460 | T16182-XB02-P0BAA-172402 | 2017-04-24 | T16182-DHI-LI-T-0324 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b222786-10d6-46f7-9573-680bf7486cc6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
461 | T16182-VK02-P0BAA-172403 | 2017-04-24 | T16182-DHI-LI-T-0324 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2ddfe86-9ab5-418b-bee8-6dd69a2fbb53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
904 | T16182-YF02-P0SAY-163401 | 2017-04-24 | T16182-DHI-LI-T-0321 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d679c34-b00c-400b-b325-b998441f7f3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
97 | T16182-UE00-P0LB-122008 | 2017-04-24 | T16182-DHI-LI-T-0326 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da7c31ea-0bad-45bc-9ccb-a464efc7210f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
98 | T16182-UE00-P0LB-122009 | 2017-04-24 | T16182-DHI-LI-T-0326 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab937b13-779a-49df-a489-699951269bfe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
99 | T16182-UE00-P0LB-122010 | 2017-04-24 | T16182-DHI-LI-T-0326 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0d8abb2-f06f-4fc0-9d2a-89add603d1b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1400 | T16182-YD00-P0LCB-127501 | 2017-04-26 | DHI-WTRAN-000002 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10cddcbb-c1a1-4b40-9412-dbe055fbb221 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1401 | T16182-XG02-P0SCA-127502 | 2017-04-26 | DHI-WTRAN-000002 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d884032-1e73-4c69-aabb-9ed3c93a9151 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1402 | T16182-XW01-P0SCA-127503 | 2017-04-26 | DHI-WTRAN-000002 | IFI | 0 | DR | TRUE | FALSE | 2017-07-21_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9be18b47-d6e5-41e4-b952-58433466745f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1403 | T16182-XW01-P0SCA-127504 | 2017-04-26 | DHI-WTRAN-000002 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=614451df-e3ea-4262-9cb0-1e12ef901b5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1404 | T16182-XW01-P0SCA-127505 | 2017-04-26 | DHI-WTRAN-000002 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4e7f4f4-57ff-4920-922c-d07898f8c821 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1405 | T16182-XW01-P0SCA-127506 | 2017-04-26 | DHI-WTRAN-000002 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04f50d52-267d-487b-92d2-bb395a29caa6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1687 | T16182-XB00-P0SCA-127509 | 2017-04-26 | DHI-WTRAN-000001 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=917e53fd-e8a5-4375-ae43-c0611c5c4001 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1564 | T16182-CA06-P0UTF-182800 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d49f6913-7884-47e0-8251-ad7f1551730a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1565 | T16182-CA00-P0UTF-182801 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ad6193f-ed80-4db9-b99f-06649f39ef25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1566 | T16182-CA00-P0UTF-182802 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5753213c-53d6-4610-8134-6adfb0f2eab3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1567 | T16182-CA00-P0UTF-182803 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75249df0-de1a-408b-a459-e19fef80c2bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1568 | T16182-CA00-P0UTF-182804 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0babbf83-1fe5-44c7-aa7b-224fa48e2c8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1569 | T16182-CA01-P0UTF-182851 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3eb50ad5-250d-413c-8e5e-20b6211014f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1570 | T16182-CA01-P0UTF-182852 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa5d1314-27c1-4f35-b7e1-4edcb617ac2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1571 | T16182-CA01-P0UTF-182853 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af2f5f8d-44da-456e-9709-0b253d2b4ad0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1572 | T16182-CA01-P0UTF-182854 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3abfaf24-a308-4a0c-8fa3-7e4616e4ffff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1573 | T16182-CA01-P0UTF-182855 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6015a97-0167-4a04-a3fc-306ebbc5ec35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1574 | T16182-CA01-P0UTF-182856 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f017877-e8f8-4389-b456-ad021d3f2d3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1575 | T16182-CA02-P0UTF-182857 | 2017-04-27 | DHI-WTRAN-000012 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efc506ba-2fab-4d77-bd30-20300a1a0029 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1576 | T16182-CA00-P0UST-182001 | 2017-04-27 | DHI-WTRAN-000011 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17f0d13a-f08b-4af3-ba2e-06d4ac102dc8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1577 | T16182-CA00-P0UST-182002 | 2017-04-27 | DHI-WTRAN-000011 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d9de27a-12fe-4e36-9a90-fc064996c8d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1578 | T16182-CA00-P0UST-182003 | 2017-04-27 | DHI-WTRAN-000011 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=068f99c2-00f0-4cb5-a7e3-e34bcca82001 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1579 | T16182-CA00-P0UST-182004 | 2017-04-27 | DHI-WTRAN-000011 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2408e64-f179-4268-b6d5-4e79a15a420f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1580 | T16182-CA00-P0UST-182005 | 2017-04-27 | DHI-WTRAN-000011 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e42418f1-c140-439c-b329-a2660c2dc1f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1581 | T16182-YD00-P0BB-150821 | 2017-04-27 | DHI-WTRAN-000010 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=baecdd62-d29e-4343-a1ce-02771f5bf77d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1582 | T16182-YF00-P0BB-150403 | 2017-04-27 | DHI-WTRAN-000009 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ced40cf-2b73-40e1-b27e-fb8931ee1232 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1583 | T16182-YF00-P0CBA-161201 | 2017-04-27 | DHI-WTRAN-000008 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9d0fa41-347b-48c4-ab44-b60dfd3bcee9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1584 | T16182-YF00-P0CBA-161202 | 2017-04-27 | DHI-WTRAN-000008 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2f45f58-fdfe-4b47-8030-87002b0ff101 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1585 | T16182-YF00-P0CBA-161203 | 2017-04-27 | DHI-WTRAN-000008 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed548669-50f5-4ac5-af01-7ec44f4ae3ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1586 | T16182-YF00-P0CGA-161301 | 2017-04-27 | DHI-WTRAN-000008 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a043590c-48a7-46e8-a499-2b83cfd28e99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1587 | T16182-YF00-P0CGA-161302 | 2017-04-27 | DHI-WTRAN-000008 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b154d38f-4aee-42c7-b3e1-09c4044c2a00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1588 | T16182-YF00-P0CGA-161303 | 2017-04-27 | DHI-WTRAN-000008 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcc8ee4d-50a0-4a84-b7eb-a1f92e34c749 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1589 | T16182-YF00-P0BB-150402 | 2017-04-27 | DHI-WTRAN-000007 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e85f70c8-9000-42c0-a766-c8cbc97647bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1590 | T16182-VE04-P0UAG-172101 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4611619f-0c26-420b-be99-1f927304e967 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1591 | T16182-VE04-P0UAG-172151 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb3069ac-3362-4832-b56e-aa8db0344354 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1592 | T16182-VK02-P0UAG-172109 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d0c5805-717f-4412-b4a1-dfd1c6f1c109 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1593 | T16182-VK02-P0UAG-172170 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6d37e95-53f1-4b4f-bd8c-6304d2176b51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1594 | T16182-XB02-P0UAG-172100 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2d0a2fe-75bc-4964-a2e8-d50803bb1082 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1595 | T16182-XB02-P0UAG-172102 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd1a10c4-ba6e-4f5a-99d0-38d4bdb06a21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1596 | T16182-XB02-P0UAG-172108 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b507288a-0f81-4ada-b4b9-c2b830fb9d24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1597 | T16182-XB02-P0UAG-172162 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4da7988c-7a25-4a64-8747-ddfda469d8e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1598 | T16182-XB02-P0UAG-172168 | 2017-04-27 | DHI-WTRAN-000006 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d461772d-e73c-461d-bd8a-a3a06aa8738d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1599 | T16182-YF00-P0BA-150401 | 2017-04-27 | DHI-WTRAN-000005 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c4d7416-e50a-4195-a9e2-3805d396937d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1600 | T16182-YF00-P0BA-150404 | 2017-04-27 | DHI-WTRAN-000005 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=467e3e2f-b66a-4a4e-9cd0-f326ef493412 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1601 | T16182-YK10-P0EKG-124010 | 2017-04-27 | DHI-WTRAN-000004 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb9f1981-56e9-41ad-8c61-668ec049dc68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1602 | T16182-XG07-P0EKG-124003 | 2017-04-27 | DHI-WTRAN-000003 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88fdfcd7-b94b-46fd-9584-e24ad98aced9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1603 | T16182-XS00-P0EKG-124021 | 2017-04-27 | DHI-WTRAN-000003 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fac6b6e4-3150-4689-90db-21f775d0cb7a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1604 | T16182-YD00-P0EKG-124011 | 2017-04-27 | DHI-WTRAN-000003 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23df7642-86a7-4e53-a152-d4c978c99fb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1605 | T16182-YK10-P0EKG-124005 | 2017-04-27 | DHI-WTRAN-000003 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17d50aa3-88c3-49cb-b69a-9413f8255a42 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1606 | T16182-YK10-P0EKG-124006 | 2017-04-27 | DHI-WTRAN-000003 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea40f032-0ef3-4ed2-9244-d63a72d517a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1607 | T16182-YT01-P0EKG-124024 | 2017-04-27 | DHI-WTRAN-000003 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b93f56f7-492a-49c2-8a60-2d1600e2168a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1608 | T16182-YT01-P0EKG-124028 | 2017-04-27 | DHI-WTRAN-000003 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b9d4515-6a4c-48ba-96d9-2ffca11742fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1454 | T16182-YE00-P0ZEN-152729 | 2017-04-28 | DHI-WTRAN-000046 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8ef48ea-065c-4c2a-a26e-bfb8295f8c71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1455 | T16182-YE00-P0ZEN-152708 | 2017-04-28 | DHI-WTRAN-000045 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b29285b1-668f-407d-a959-daab77259394 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1456 | T16182-YE03-P0BAU-152511 | 2017-04-28 | DHI-WTRAN-000045 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21117ada-ef35-4cc9-985c-92bbd6cd2507 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1457 | T16182-VK02-P0UMX-171018 | 2017-04-28 | DHI-WTRAN-000044 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0f65cff-9111-4847-9a30-8ff24e168661 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1458 | T16182-VK02-P0UMX-171019 | 2017-04-28 | DHI-WTRAN-000044 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9dc781f5-9c24-472e-862e-f038ce8d9ee7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1459 | T16182-VK02-P0UMX-171020 | 2017-04-28 | DHI-WTRAN-000044 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d5ed142-79b2-48dc-aa95-90b5952a5e6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1460 | T16182-VK02-P0UMX-171023 | 2017-04-28 | DHI-WTRAN-000044 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84df5844-9f0a-4fd1-a22a-f8f118f03c55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1461 | T16182-VK02-P0UMX-171024 | 2017-04-28 | DHI-WTRAN-000044 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f176b3a0-388e-4185-b32c-8e2d3f2283a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1462 | T16182-YD00-P0MAG-123039 | 2017-04-28 | DHI-WTRAN-000043 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b10e0174-64f1-4540-800d-a70fe0988a70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1463 | T16182-XK00-P0MAG-123027 | 2017-04-28 | DHI-WTRAN-000042 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c104fa2e-72a1-41de-b3e7-62ea834abf1e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1464 | T16182-XG02-P0MAG-123002 | 2017-04-28 | DHI-WTRAN-000041 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe7a1ddb-7493-43ab-9b22-02d7e23cdb51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1465 | T16182-XB00-P0MAG-123023 | 2017-04-28 | DHI-WTRAN-000040 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ac8d2a6-588a-4a3d-b9ff-46a65f0aeab5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1466 | T16182-YE00-P0GCF-130015 | 2017-04-28 | DHI-WTRAN-000038 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22a7599e-9997-4056-963a-9becf9b14b10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1467 | T16182-YU03-P0GCF-130017 | 2017-04-28 | DHI-WTRAN-000038 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccce4d61-7ff0-4dd9-bac6-c44dbe02415e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1468 | T16182-XJ00-P0LB-122029 | 2017-04-28 | DHI-WTRAN-000036 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=812ce560-8aab-430b-bf80-9714fd6c8e3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1469 | T16182-YK00-P0LB-122071 | 2017-04-28 | DHI-WTRAN-000036 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c83825e9-5012-4e41-bc28-26396cecaaaa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1470 | T16182-YT01-P0LB-122100 | 2017-04-28 | DHI-WTRAN-000037 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45648c95-d21d-4188-ac7c-9504de136ff2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1471 | T16182-DE00-P8ZEN-125502 | 2017-04-28 | DHI-WTRAN-000035 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99e7b0bd-0f6f-419d-a786-d0485cdc0991 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1472 | T16182-XH02-P8QHL-125400 | 2017-04-28 | DHI-WTRAN-000035 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08862552-b153-40bc-bd90-4b5c2e0f8fcf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1473 | T16182-XN00-P8ZEN-125503 | 2017-04-28 | DHI-WTRAN-000035 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63105407-abe6-41af-84f6-df64b5cdf94a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1474 | T16182-XN00-P8ZEN-125504 | 2017-04-28 | DHI-WTRAN-000035 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08e09386-db53-49c9-bfb5-506016af0d17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1475 | T16182-VE04-P0UZT-172701 | 2017-04-28 | DHI-WTRAN-000033 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f6f2c75-6b85-4760-bb3b-37b3dfc0aa1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1476 | T16182-VK02-P0UZT-172704 | 2017-04-28 | DHI-WTRAN-000033 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53a92441-5815-4e13-a06e-9d45038753ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1477 | T16182-VK02-P0UZT-172713 | 2017-04-28 | DHI-WTRAN-000033 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=527f248b-bea2-47d1-bcf0-4aeea4793343 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1478 | T16182-XB02-P0UZT-172702 | 2017-04-28 | DHI-WTRAN-000033 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cecb2a5-d8cd-4206-935b-ae506257477d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1479 | T16182-XB02-P0UZT-172703 | 2017-04-28 | DHI-WTRAN-000033 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8337ae7b-c2b7-412f-b6b7-d4d32b8283e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1480 | T16182-XB02-P0UZT-172716 | 2017-04-28 | DHI-WTRAN-000033 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7ec6445-c47d-411a-a8d3-c57cc74166dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1481 | T16182-VK02-P0UGF-173107 | 2017-04-28 | DHI-WTRAN-000034 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=504b73b6-6e3f-4a1c-8224-dc97569808a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1482 | T16182-XB02-P0UGF-173101 | 2017-04-28 | DHI-WTRAN-000034 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00142143-c177-453b-b0ab-c9572cf2f951 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1483 | T16182-XB02-P0UGF-173102 | 2017-04-28 | DHI-WTRAN-000034 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d96874f-34fc-4675-a97c-b030e2c2055e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1484 | T16182-CN00-P0ZEN-110701 | 2017-04-28 | DHI-WTRAN-000032 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3a3aac0-4af2-46b7-b652-cef49926786d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1485 | T16182-BP00-P0EKG-140015 | 2017-04-28 | DHI-WTRAN-000031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2152106b-26f0-40e5-83a4-187743c3c0b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1486 | T16182-BP00-P0LAB-140014 | 2017-04-28 | DHI-WTRAN-000031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90468d64-2f50-44d8-804a-21ab98c79ca8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1487 | T16182-BP00-P0LBA-140011 | 2017-04-28 | DHI-WTRAN-000031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=281cd6cc-0c5f-4608-aede-e36c5ee88713 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1488 | T16182-BP00-P0LBS-140013 | 2017-04-28 | DHI-WTRAN-000031 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b312e118-717c-46b0-b9d4-1dc1545395dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1489 | T16182-VE04-P0UEG-171501 | 2017-04-28 | DHI-WTRAN-000030 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bc411dc-8bcc-414e-a0ed-4763229e2990 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1490 | T16182-XB02-P0UEG-171502 | 2017-04-28 | DHI-WTRAN-000030 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6275b5e9-7b06-4b3a-aa04-5d411d1243b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1491 | T16182-XB02-P0UEG-171504 | 2017-04-28 | DHI-WTRAN-000030 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=830873f8-c0f0-4ea5-b262-4239e9bedb08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1492 | T16182-CA00-P0UBA-181306 | 2017-04-28 | DHI-WTRAN-000029 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64c1ca5d-0815-4bd3-bee2-fb872c9c904f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1493 | T16182-CA00-P0UBA-181307 | 2017-04-28 | DHI-WTRAN-000029 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ba19fa0-a950-4549-8416-46e24b739b04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1494 | T16182-CA01-P0UBA-181355 | 2017-04-28 | DHI-WTRAN-000029 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=307c4262-6e81-401d-b3e4-a6fcdbd06f8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1495 | T16182-CA01-P0UBA-181356 | 2017-04-28 | DHI-WTRAN-000029 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8793e46-b83d-4627-b905-3fdac90a5da9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1496 | T16182-CA02-P0UBA-181359 | 2017-04-28 | DHI-WTRAN-000029 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a4dc100-1d4b-4e5d-8225-9b0b3bd90f60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1497 | T16182-CA02-P0UBA-181360 | 2017-04-28 | DHI-WTRAN-000029 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e53e9953-a5b9-4e22-b3c9-f282768ab6d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1498 | T16182-YU03-P0BBT-150681 | 2017-04-28 | DHI-WTRAN-000028 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30320f0b-f27a-4a68-a198-f7fc16fb9453 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1499 | T16182-YK09-P0GHC-129003 | 2017-04-28 | DHI-WTRAN-000027 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef6baf5e-2278-46e7-b623-1715f439ffec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1500 | T16182-YK09-P0GHC-129033 | 2017-04-28 | DHI-WTRAN-000027 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=511fcfd5-ded1-4382-b999-bb14519299a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1501 | T16182-YT01-P0GHC-129002 | 2017-04-28 | DHI-WTRAN-000027 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de11303b-bd01-451c-af8a-324b0bfa4ffe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1502 | T16182-YT01-P0GHC-129032 | 2017-04-28 | DHI-WTRAN-000027 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cf2fd74-893c-4d94-ad4e-39efa03354ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1503 | T16182-XH01-P0ZEN-140062 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b675f61-8138-4c56-a9c9-e5c57b889f84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1504 | T16182-XH01-P0UTF-140063 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cf8796f-4018-4366-94c3-b965575b9040 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1505 | T16182-XH01-P0GRK-140064 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16e36578-784a-40ec-9370-13509d29cda8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1506 | T16182-XH01-P0UGD-140065 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c802d6ae-4940-4c2c-9dd4-99d6f0cd2bc1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1507 | T16182-XH01-P0UGA-140066 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE | 2017-09-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eecf6ee5-0bc9-4804-9f85-1c044453f4ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1508 | T16182-XH01-P0UGA-140067 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE | 2017-09-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=befb2a86-4576-45a0-89c1-808f9a0c594c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1509 | T16182-XH01-P0UCB-140068 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2acf38c2-a92f-4edb-a4bd-bbc2db688072 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1510 | T16182-XH01-P0LCA-140069 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62d7aa4a-f6d1-4d76-aa8d-ea1dd36e2700 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1511 | T16182-XH01-P0LCA-140070 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84c8b717-e2bf-435c-a6e0-9b47b5549d15 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1512 | T16182-XH01-P0LDK-140071 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59d018c9-caf4-43ac-9706-6a5611793528 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1513 | T16182-XH01-P0LDK-140072 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=943a1f5d-8b35-4f79-9337-a1414951ae3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1514 | T16182-XH01-P0EKG-140073 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f0e180a-07bf-41ca-9192-cf4ddc66b4a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1515 | T16182-XH01-P0ZEN-140081 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d60bcbc7-bc19-4b61-a3e8-1473169f9d2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1516 | T16182-XH01-P0ZEN-140082 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b32c18c5-8024-44d8-8c38-efdfc09d5232 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1517 | T16182-XH01-P0ZEN-140083 | 2017-04-28 | DHI-WTRAN-000026 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95c6e0e6-4c39-4307-8ad4-a4ef4ad59666 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1518 | T16182-XG02-P0SGA-137301 | 2017-04-28 | DHI-WTRAN-000025 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8efb0736-71ab-4851-be3b-9b5ae4a066f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1519 | T16182-XG02-P0SGE-137302 | 2017-04-28 | DHI-WTRAN-000025 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6ff65b6-f2aa-4b5c-9c4b-cdb6ce99d355 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1520 | T16182-XH01-P0SGA-137311 | 2017-04-28 | DHI-WTRAN-000025 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a835afd2-2571-4cb1-bff9-9d20349b8970 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1521 | T16182-XH01-P0SGE-137312 | 2017-04-28 | DHI-WTRAN-000025 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b6d03e7-8ce8-4425-ba74-5552d6a1ccd6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1522 | T16182-YD00-P0SGZ-137332 | 2017-04-28 | DHI-WTRAN-000025 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7b54e54-75e0-4e10-8f26-a9982165df2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1523 | T16182-XH01-P0SGA-136711 | 2017-04-28 | DHI-WTRAN-000023 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a21684c9-b408-49ee-b702-652d8a583f36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1524 | T16182-XH01-P0SGE-136712 | 2017-04-28 | DHI-WTRAN-000023 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be1dd03e-e0a7-44dc-993f-13e990ddc97b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1525 | T16182-XH01-P0SGK-136713 | 2017-04-28 | DHI-WTRAN-000023 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a2a67ca-7dfb-4d27-bdde-7ab5c44c1e83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1526 | T16182-YD00-P0SGZ-136731 | 2017-04-28 | DHI-WTRAN-000023 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=522d37c5-4902-4915-816f-4d42a67fd48e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1527 | T16182-YT10-P0SGE-136722 | 2017-04-28 | DHI-WTRAN-000023 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81617109-4d15-4abc-9cc3-5dc6b6ed8c76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1528 | T16182-YT10-P0SGK-136723 | 2017-04-28 | DHI-WTRAN-000023 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d66263ff-4dcb-4e70-a9af-773f13d42f53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1529 | T16182-XG02-P0SGA-136801 | 2017-04-28 | DHI-WTRAN-000024 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8dd4f16-424c-477c-9f9f-87175af3ba72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1530 | T16182-XG02-P0SGE-136802 | 2017-04-28 | DHI-WTRAN-000024 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00f482bc-bdef-4b45-8564-1759cab04cf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1531 | T16182-YD00-P0SGZ-136831 | 2017-04-28 | DHI-WTRAN-000024 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eaa72ff8-bf0e-4d28-b749-f5353f684679 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1532 | T16182-CV03-P0ZEN-140002 | 2017-04-28 | DHI-WTRAN-000022 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af4c537c-36fb-43ec-bd4e-c4718666350c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1533 | T16182-YD00-P0UBA-150505 | 2017-04-28 | DHI-WTRAN-000021 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d494ed41-18bb-462c-9530-ce6b9bcf8a13 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1534 | T16182-CA06-P0UBA-181100 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15315e3d-4ae3-47e7-b139-da71271cfafd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1535 | T16182-CA00-P0UBA-181101 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e952a35d-fc0c-4e98-b267-41a04310cb59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1536 | T16182-CA00-P0UBA-181102 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21a85775-e512-47b9-af19-b9e0336bdf17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1537 | T16182-CA00-P0UBA-181103 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20723ef8-cdfc-4423-8f07-24e13f54d5a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1538 | T16182-CA00-P0UBA-181104 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4adaff6-57f7-411c-be85-be831d648b2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1539 | T16182-CA00-P0UBA-181105 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b5ada17-c23b-4433-a87f-941447418ed5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1540 | T16182-CA01-P0UBA-181151 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e12f5fd-687b-4bc3-8ece-98ed28537fc9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1541 | T16182-CA01-P0UBA-181152 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=301c620b-6957-4a06-aa1b-68ca0e0f0ea1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1542 | T16182-CA01-P0UBA-181153 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f610be3-9aa2-41f9-b1a3-38b124bd6e94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1543 | T16182-CA01-P0UBA-181154 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65db7cc4-ae3c-4d1b-8fdc-3c379858bc47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1544 | T16182-CA02-P0UBA-181155 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93f2770e-739c-480a-91ac-ed1b7729afd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1545 | T16182-CA02-P0UBA-181156 | 2017-04-28 | DHI-WTRAN-000019 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1932c43e-0226-4ade-8aa0-3481f4ea05b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1546 | T16182-YD00-P0UBA-150504 | 2017-04-28 | DHI-WTRAN-000020 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0c87637-a9b4-4906-8411-5743f436dd88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1547 | T16182-CA01-P0UYC-182951 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=027a3fc9-e126-4c5a-b0d3-fdddea7aadb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1548 | T16182-CA01-P0UYC-182952 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa1b9001-728f-467a-888c-d7619fb947f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1549 | T16182-CA01-P0UYC-182953 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cf73ca5-ba23-47c0-b02a-51f1132dde12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1550 | T16182-CA01-P0UYC-182954 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5af9f467-01dd-4d45-bcc6-1a63f8d373a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1551 | T16182-CA01-P0UYC-182955 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf03f387-1300-4140-87e0-04815305c17b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1552 | T16182-CA01-P0UYC-182956 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0f68567-722b-4339-94d1-0b7aab91f058 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1553 | T16182-CA02-P0UYC-182957 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e89f012-7407-4afe-a340-c208196954b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1554 | T16182-CA02-P0UYC-182958 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b8aca8f-e5cb-4a67-b4cd-9b7323de9576 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1555 | T16182-CA06-P0UYC-182900 | 2017-04-28 | DHI-WTRAN-000017 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f0bbc19-5059-485c-beae-36ca049f65ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1556 | T16182-XV00-P0PCA-126506 | 2017-04-28 | DHI-WTRAN-000018 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4aac4e92-be9c-4918-8b81-58e65ab8f7a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1557 | T16182-YR05-P0CWQ-161148 | 2017-04-28 | DHI-WTRAN-000016 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a48a685b-da6f-4e5f-a1d3-81b2a4139c5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1558 | T16182-YK10-P0EKG-124013 | 2017-04-28 | DHI-WTRAN-000015 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76796a81-a2e4-43d2-9135-b36fa3c99f96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1559 | T16182-XN00-P0EKG-124023 | 2017-04-28 | DHI-WTRAN-000014 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faf8af6c-bdc0-45a9-b42f-71fa709a25dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1560 | T16182-YK10-P0EKG-124007 | 2017-04-28 | DHI-WTRAN-000014 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b35a7da7-21d7-453e-a708-c74ae08283cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1561 | T16182-YK10-P0EKG-124008 | 2017-04-28 | DHI-WTRAN-000014 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04fd52cc-720d-4f1d-8e06-d66fa8a8e14e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1562 | T16182-XB02-P0EKG-124015 | 2017-04-28 | DHI-WTRAN-000013 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cded4d2-0d65-46a1-9d44-a9926195cee2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1563 | T16182-YD00-P0EKG-124009 | 2017-04-28 | DHI-WTRAN-000013 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9931718c-4627-4860-85ae-16c8d5fbfb03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1685 | T16182-YK00-P0GCF-130016 | 2017-04-28 | DHI-WTRAN-000039 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9d239ea-d2e7-4ab5-b1e5-17de9fb2d671 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1686 | T16182-YF00-P0GCF-130018 | 2017-04-28 | DHI-WTRAN-000039 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e8e2ec2-b3b8-4426-bae0-56cb07f3d209 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1406 | T16182-YK09-P0SAA-133302 | 2017-04-29 | T16182-DHI-LI-T-0338 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b336f0d-6c9c-41cc-b75f-12bd7c73e7f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1407 | T16182-YS00-P0ZEN-163302 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88c69d7a-f31c-4591-9d34-3fd7d93ad1fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1408 | T16182-YS00-P0ZEN-163303 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5570a8f5-30f8-4b6e-a0bc-c03c6a35f9a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1409 | T16182-YS00-P0ZEN-163304 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=097f86c2-1a4d-47ca-bc9c-00a845de000b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1410 | T16182-YS00-P0ZEN-163305 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fef67df-9dec-40c7-8a93-6e0a152d4c71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1411 | T16182-YS00-P0ZEN-163306 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59ee24e3-eaae-48b0-b05f-5685df14aead | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1412 | T16182-YS00-P0ZEN-163307 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=283a74f6-c1dc-4696-979d-13d501e0337e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1413 | T16182-YS00-P0ZEN-163308 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33e38b66-3de2-40bb-84f6-5f43d8893d6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1414 | T16182-YS00-P0ZEN-163311 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62ed562f-f38a-420b-9bd9-d4e23a15965e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1415 | T16182-YS00-P0ZEN-163312 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b76cede-1461-4806-830a-46f2711e6185 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1416 | T16182-YS00-P0ZEN-163313 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a187bbd5-33d6-410d-907c-29cd833a22ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1417 | T16182-YS00-P0ZEN-163314 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=158cc7a8-797b-4620-9361-6019f06f1b23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1418 | T16182-YS00-P0ZEN-163315 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8bc6afa-0582-47eb-9481-5ca97e7583a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1419 | T16182-YS00-P0ZEN-163317 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0f1e4e3-24c3-4882-9f2e-552e2fae6e32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1420 | T16182-YS00-P0ZEN-163318 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37334877-9c65-4c3f-ba76-99428866b2f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1421 | T16182-YS00-P0ZEN-163319 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bba1bb30-1f61-462f-bac1-24c33222b433 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1422 | T16182-YS00-P0ZEN-163320 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5805dcb3-ffe9-4d15-aa5c-7122969f2ecb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1423 | T16182-YS00-P0ZEN-163321 | 2017-04-29 | T16182-DHI-LI-T-0342 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6aa00194-5df7-4451-9392-e223dc3db181 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1424 | T16182-XS00-P0LB-122037 | 2017-04-29 | T16182-DHI-LI-T-0343 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6916fef-ea76-4396-a007-b0559fd30bb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1425 | T16182-YD00-P0MBA-121001 | 2017-04-29 | T16182-DHI-LI-T-0344 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2c6ebf5-1670-41de-9db1-aaa43ac17261 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1426 | T16182-YD00-P0CWQ-161402 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea7779a7-3911-443c-8252-8e415a9ad81c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1427 | T16182-YD00-P0CWQ-161403 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8800007c-baf9-4ef4-845a-7fd49fa24e6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1428 | T16182-YD00-P0CWQ-161404 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86aeb5b3-1a82-4823-a0d4-ec549403cd12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1429 | T16182-YD00-P0CWQ-161405 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8222208a-ffb4-4800-952f-faeb7033fe8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1430 | T16182-YD00-P0CWQ-161406 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ec780fe-9f4d-4ed9-aa6e-177fca8f9422 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1431 | T16182-YD00-P0CWQ-161407 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5266b12a-06f2-469e-845f-34c88905db4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1432 | T16182-YD00-P0CWQ-161408 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d79af5f4-7234-4079-9a56-5e802c7b22d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1433 | T16182-YD00-P0CWQ-161409 | 2017-04-29 | T16182-DHI-LI-T-0345 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70a7519f-b43a-4657-aedd-ea2b62971534 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1434 | T16182-YL02-P0ZEN-165011 | 2017-04-29 | T16182-DHI-LI-T-0346 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62b63eb3-4f83-425a-b61d-479d53d0942b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1435 | T16182-YK00-P0ZEN-165301 | 2017-04-29 | T16182-DHI-LI-T-0346 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=637f4ec9-b53f-4107-9065-4349439ec7c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1436 | T16182-YK00-P0ZEN-165302 | 2017-04-29 | T16182-DHI-LI-T-0346 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47268006-7161-4c9b-a49a-5e3e2ffbf61e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1437 | T16182-YK00-P0ZEN-165303 | 2017-04-29 | T16182-DHI-LI-T-0346 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57e10d19-8898-4ef5-b214-61f1073cb60a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1438 | T16182-YK00-P0ZEN-165304 | 2017-04-29 | T16182-DHI-LI-T-0346 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=935f44f0-90c2-4b33-93c9-2bafc4287e6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1439 | T16182-YK00-P0ZEN-165305 | 2017-04-29 | T16182-DHI-LI-T-0346 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6b0cdb9-efa3-496e-b043-4761c568bb3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1440 | T16182-XS00-P0LB-110040 | 2017-04-29 | T16182-DHI-LI-T-0347 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e4f0bf1-eb4b-473f-bfec-12d8b824b901 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1441 | T16182-XG02-P0EK-120007 | 2017-04-29 | T16182-DHI-LI-T-0348 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d6f6114-0b8d-4c5b-bc57-665af7b67f31 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1442 | T16182-XW01-P0LC-110036 | 2017-04-29 | T16182-DHI-LI-T-0349 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c9d33a1-450f-4ee9-b112-28418aadc67b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1443 | T16182-YU02-P0ZEN-150211 | 2017-04-29 | T16182-DHI-LI-T-0350 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=862c98da-8f20-401d-b24f-4afb0cc328b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1444 | T16182-YU02-P0ZEN-150212 | 2017-04-29 | T16182-DHI-LI-T-0350 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe0d3d4a-65e6-434d-8b19-8369c64380aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1445 | T16182-YD00-P0UBA-150503 | 2017-04-29 | T16182-DHI-LI-T-0351 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=345745a6-79a4-43b2-879d-8b8839e87ae4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1446 | T16182-XW03-P0SAI-133801 | 2017-04-29 | T16182-DHI-LI-T-0352 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc841919-38c5-4a58-99db-152181a58118 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1447 | T16182-XG07-P0SAI-133802 | 2017-04-29 | T16182-DHI-LI-T-0352 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5cbf1516-4ece-4ec1-8952-e6290a4ae0f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1448 | T16182-XW03-P0SAI-133803 | 2017-04-29 | T16182-DHI-LI-T-0352 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c272b8b-a31e-4e07-bd2a-d7ae11332a93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1449 | T16182-XH02-P0SAI-133804 | 2017-04-29 | T16182-DHI-LI-T-0352 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0dd64a7-d608-41d2-bb0e-954fddf35fc3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1450 | T16182-YQ01-P0ZEN-152201 | 2017-04-29 | T16182-DHI-LI-T-0353 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f86ae4b-6906-4322-ab1d-d578d394c8dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1451 | T16182-YE03-P0BAU-152507 | 2017-04-29 | T16182-DHI-LI-T-0354 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff6c5b95-8fe5-49a6-a453-5b50a586105f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1452 | T16182-YE00-P0ZEN-152722 | 2017-04-29 | T16182-DHI-LI-T-0355 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f05c90d-952d-4ac5-90ed-a69809a4e957 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1453 | T16182-YE00-P0ZEN-152726 | 2017-04-29 | T16182-DHI-LI-T-0355 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e36f58ff-0003-4d9f-b17c-7699865a84d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1609 | T16182-YT01-P0BF-150901 | 2017-05-02 | DHI-WTRAN-000056 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90655d13-3174-4589-b479-513f48674e7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1610 | T16182-YT01-P0BF-150902 | 2017-05-02 | DHI-WTRAN-000056 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b393c043-03ca-4533-8d69-90ec1d23b05c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1611 | T16182-YT01-P0BF-150903 | 2017-05-02 | DHI-WTRAN-000056 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc44987e-cb4a-48c1-aba0-b7198d91411a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1612 | T16182-YD00-P0PCA-126503 | 2017-05-02 | DHI-WTRAN-000053 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8ef909a-c4f1-4e19-a7df-f5f64eaa47bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1613 | T16182-YL25-P0PCA-126505 | 2017-05-02 | DHI-WTRAN-000053 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0db9390-9699-4b15-8863-5cfa08068531 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1614 | T16182-YD00-P0GHC-129001 | 2017-05-02 | DHI-WTRAN-000051 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebbfe252-5cbe-4300-96c5-f924c2312e5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1615 | T16182-YD00-P0GHC-129031 | 2017-05-02 | DHI-WTRAN-000051 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe649694-9d99-4f21-8d2d-18e384b4e306 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1616 | T16182-YE00-P0ZEN-152705 | 2017-05-02 | DHI-WTRAN-000050 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56949bcd-10e6-41be-ad8b-ec55c0b3965e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1617 | T16182-YE00-P0ZEN-152706 | 2017-05-02 | DHI-WTRAN-000050 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=894d513a-2e5a-49bb-8712-020d527e37ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1618 | T16182-XG02-P0SGC-137001 | 2017-05-02 | DHI-WTRAN-000049 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b87e368-7167-4a78-8870-fdd149fd7538 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1619 | T16182-XG02-P0SGC-137101 | 2017-05-02 | DHI-WTRAN-000049 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=285b41c6-1d72-402f-8cf9-12689465a945 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1620 | T16182-YD00-P0SGZ-137131 | 2017-05-02 | DHI-WTRAN-000049 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad58ee8a-238d-4db2-83e1-03f06bfa372c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1621 | T16182-YD00-P0PGB-110404 | 2017-05-02 | DHI-WTRAN-000048 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1900d284-f4b6-457c-b4be-b9aaa16ada12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1622 | T16182-YD00-P0PGB-110405 | 2017-05-02 | DHI-WTRAN-000048 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7171cfd7-af3f-40aa-a793-ecbb2c537d98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1623 | T16182-YT01-P0PGB-110407 | 2017-05-02 | DHI-WTRAN-000048 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a45019b3-79c1-4f7a-9ba2-1baeccc040f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1624 | T16182-YD00-P0PGB-110401 | 2017-05-02 | DHI-WTRAN-000047 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecba3361-5574-4f9b-8e71-55fa2edd948e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1625 | T16182-YL22-P0PGB-110402 | 2017-05-02 | DHI-WTRAN-000047 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c933bef2-627f-4eae-828c-fd14148207fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1626 | T16182-YT01-P0PGB-110403 | 2017-05-02 | DHI-WTRAN-000047 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e9938a5-a9a5-46cc-a6f8-9f9f6cb45e42 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1627 | T16182-YU02-P0BFA-150911 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18715418-2fdb-4daa-82d5-a09dbb533733 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1628 | T16182-YU02-P0BFA-150913 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=533ea54f-0bff-42ae-b502-59663445850c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1629 | T16182-YU02-P0BFA-150914 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d56a60cf-f718-47d7-bf87-75a95deab6fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1630 | T16182-YU02-P0BFA-150916 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0db1426a-9952-4cec-b744-4596caf8e429 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1631 | T16182-YU02-P0BFA-150918 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2bcded8-a724-4c7b-a9ef-11224e4cf1f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1632 | T16182-YD00-P0BF-150931 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdac8648-9646-4572-a137-fbd52e9c63e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1633 | T16182-YD00-P0BF-150933 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daa2cffa-fcb1-4b62-bbaa-e78b9d8e5efb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1634 | T16182-YD00-P0BF-150934 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8314853-0f85-4dc9-b1c9-d36886c603b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1635 | T16182-YD00-P0BF-150936 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea8bfee8-345a-43ac-adc5-545f6dc2595c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1636 | T16182-YD00-P0BF-150938 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1029bba9-0248-4448-baae-4d4526d1e473 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1637 | T16182-YD00-P0BF-150939 | 2017-05-02 | DHI-WTRAN-000057 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d946202b-533a-4c57-ae5c-e4b28243c859 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1638 | T16182-XW01-P0ZEN-161001 | 2017-05-02 | T16182-DHI-LI-T-0356 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4b53fef-e2e1-4650-a0fe-b80939b9ae0f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1639 | T16182-XW03-P0SAC-133501 | 2017-05-02 | T16182-DHI-LI-T-0357 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9785d241-4c75-4da8-9ea2-607fdd9e0c0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1640 | T16182-UE00-P0LB-122007 | 2017-05-02 | T16182-DHI-LI-T-0358 | IFR | D | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7335799-ae80-428d-9086-2987f118a083 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1641 | T16182-VE04-P0UEM-171701 | 2017-05-02 | T16182-DHI-LI-T-0359 | IFC | 0 | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1642 | T16182-XB02-P0UEM-171702 | 2017-05-02 | T16182-DHI-LI-T-0359 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62729f7a-2647-4b55-b7a3-5fde117b1f41 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1643 | T16182-XB02-P0UEM-171708 | 2017-05-02 | T16182-DHI-LI-T-0359 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d55e3ea2-9fdf-47ba-b720-41126b6b658e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1644 | T16182-VK02-P0UEM-171711 | 2017-05-02 | T16182-DHI-LI-T-0359 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cab22a1-335f-468e-912d-320623273ff0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1645 | T16182-XW03-P0GKS-120013 | 2017-05-02 | T16182-DHI-LI-T-0360 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a341e791-ca92-4aba-9924-d41d0147b4fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1646 | T16182-VE04-P0ULC-171301 | 2017-05-02 | T16182-DHI-LI-T-0361 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=944f9e03-7a0c-4ca7-8635-41ab37e0b8b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1647 | T16182-XB02-P0ULC-171302 | 2017-05-02 | T16182-DHI-LI-T-0361 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5232859e-2901-4cfc-9c2a-1c23b6e01325 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1648 | T16182-XB02-P0ULC-171303 | 2017-05-02 | T16182-DHI-LI-T-0361 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ea8f0a7-0c9c-4a4f-bb0f-0b4a811a21b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1649 | T16182-VK02-P0ULC-171308 | 2017-05-02 | T16182-DHI-LI-T-0361 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe53c423-a683-4489-b3bf-129bf8d3fca8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1650 | T16182-XS00-P0LB-122035 | 2017-05-02 | T16182-DHI-LI-T-0363 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d70ac711-500d-4f2a-bbd3-67e309b5b45d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1670 | T16182-CA03-P0UMY-185160 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7edce92a-b860-49f7-b1ac-6e63cbb84221 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1671 | T16182-CA03-P0UMY-185161 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c1e3d0b-6637-46d1-beba-09d42ac4b994 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1672 | T16182-CA03-P0UMY-185162 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdc1620d-098b-4afc-8767-f42bd3df8a97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1673 | T16182-CA03-P0UMY-185163 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14f8d5e4-f3b7-4cad-bedf-b7dc7f562dfe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1674 | T16182-CA03-P0UMY-185164 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb648af3-76b5-4857-af6e-95533a38ab78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1675 | T16182-CA03-P0UMY-185165 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44580e90-31ba-4e26-9d45-a08b2e2c3d2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1676 | T16182-CA03-P0UMY-185166 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b96c18d-852b-4991-9ba0-4eaea51d2f4b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1677 | T16182-CA03-P0UMY-185167 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b8f28f7-a699-4bb8-af49-4ca3c1ee32dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1678 | T16182-CA03-P0UMY-185168 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68889b65-1e72-4da6-8586-60bbac7015f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1679 | T16182-CA03-P0UMY-185178 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fbff946-327a-4ebe-9ce2-a2b8241e88aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1680 | T16182-CA06-P0UMY-185191 | 2017-05-02 | DHI-WTRAN-000052 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e4360a0-4cd6-4b05-8f60-9e3e1c9088be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1691 | T16182-YT01-P0BB-150801 | 2017-05-02 | DHI-WTRAN-000054 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d2d5a57-82b0-4975-aa30-45abfad592d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1692 | T16182-YU02-P0BB-150811 | 2017-05-02 | DHI-WTRAN-000054 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f7b1ab5-cd57-4116-9310-5975aeaae7cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1693 | T16182-YT01-P0LF-110601 | 2017-05-02 | DHI-WTRAN-000055 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf1d8db2-183c-4f9c-8bab-a2ae3957cabb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1694 | T16182-YK10-P0LF-110602 | 2017-05-02 | DHI-WTRAN-000055 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00a317f2-f9ee-4c02-bb11-e1d2c40cc1bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1695 | T16182-YT01-P0LF-110603 | 2017-05-02 | DHI-WTRAN-000055 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e3d849c-c55c-4cf6-98e8-142172f4da00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1696 | T16182-YK10-P0LF-110604 | 2017-05-02 | DHI-WTRAN-000055 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dd578e9-dc37-415d-be54-dbba768f1afd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1681 | T16182-VE04-P0UNX-171401 | 2017-05-10 | DHI-WTRAN-000071 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02de3c25-d709-411a-ace8-2fec039286e6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1682 | T16182-XB02-P0UNX-171402 | 2017-05-10 | DHI-WTRAN-000071 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c18c157-6837-440e-b1af-a4e28c8990c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1683 | T16182-XB02-P0UNX-171403 | 2017-05-10 | DHI-WTRAN-000071 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fd1cef2-cbdd-4205-b7d2-d55aa4383368 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1684 | T16182-XB02-P0UNX-171410 | 2017-05-10 | DHI-WTRAN-000071 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cb3f998-dac2-401f-9fef-d4072f768bf8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1688 | T16182-YT01-P0MAG-123038 | 2017-05-10 | DHI-WTRAN-000072 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6717032a-7f61-4d9a-9fc5-257de6a0e62f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1689 | T16182-XK00-P0MAG-123009 | 2017-05-10 | DHI-WTRAN-000074 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a905a50-7fdb-4f50-afd9-6e0a9c69ba15 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1690 | T16182-YL00-P0MAG-123031 | 2017-05-10 | DHI-WTRAN-000073 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c3cef1d-3fc6-4649-a92a-7995589c4f47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1697 | T16182-CA03-P0ULA-182152 | 2017-05-10 | T16182-DHI-LI-T-0362 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec30ac0c-1098-415f-bfa1-19ce4fbede10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1698 | T16182-CA03-P0ULA-182154 | 2017-05-10 | T16182-DHI-LI-T-0362 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9789e65-3e2e-4a84-8712-a6f47b2f1777 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1699 | T16182-CA03-P0ULA-182155 | 2017-05-10 | T16182-DHI-LI-T-0362 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de321771-e42e-4165-b11a-02155bfb22c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1700 | T16182-CA03-P0ULA-182160 | 2017-05-10 | T16182-DHI-LI-T-0362 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a32af12f-7f1e-4cd4-819f-960bd3ed84a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1701 | T16182-CA06-P0ULA-182191 | 2017-05-10 | T16182-DHI-LI-T-0362 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64915825-35b6-44ee-934a-ae806d4f8baa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1702 | T16182-YU02-P0ZEN-150202 | 2017-05-10 | T16182-DHI-LI-T-0364 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63706dc0-f4f4-4244-a188-1933dff48ebd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1703 | T16182-UE00-P0MB-100004 | 2017-05-10 | T16182-DHI-LI-T-0365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88ec2572-e929-4217-ac1b-d1bdc25dcaa0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1704 | T16182-UE00-P0MB-100005 | 2017-05-10 | T16182-DHI-LI-T-0365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf6d6a61-128c-42dd-a7ed-a6b2d3eaf0d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1705 | T16182-UE00-P0MB-100006 | 2017-05-10 | T16182-DHI-LI-T-0365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=021e0520-9b1b-42a9-bc48-0cd5cfc7b6e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1706 | T16182-UE00-P0MB-100007 | 2017-05-10 | T16182-DHI-LI-T-0365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7003059-8f43-4a15-b5f3-05a256f376d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1707 | T16182-UE00-P0UMA-100008 | 2017-05-10 | T16182-DHI-LI-T-0365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6eb56078-b983-456a-be97-2898fb0cf1ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1708 | T16182-UE00-P0UMA-100009 | 2017-05-10 | T16182-DHI-LI-T-0365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5a6c8e8-c4f4-475a-a387-c9fdd1dc9c64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1709 | T16182-UE00-P0UMA-100010 | 2017-05-10 | T16182-DHI-LI-T-0365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a05082cf-e31f-4564-b1c9-7dbc60640c9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1710 | T16182-YD00-P0CWQ-161401 | 2017-05-10 | T16182-DHI-LI-T-0366 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe6c7917-a74f-47ff-b028-815cbb537c91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1711 | T16182-XG05-P0ZEN-110001 | 2017-05-10 | T16182-DHI-LI-T-0367 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af82fa1a-58e4-4f4d-9248-24b7c8b820b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1733 | T16182-XG07-P0SAC-133502 | 2017-05-10 | T16182-DHI-LI-T-0372 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c75d25f-068d-4acc-bdc2-7d7e60e17ac0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1734 | T16182-XW03-P0SAC-133503 | 2017-05-10 | T16182-DHI-LI-T-0372 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38936e7e-50fb-461f-b58a-45b6d175845c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1735 | T16182-XH02-P0SAC-133504 | 2017-05-10 | T16182-DHI-LI-T-0372 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f0b95bf-878d-489d-b7bf-465f561eab98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1736 | T16182-YR05-P0CJN-290002 | 2017-05-10 | T16182-DHI-LI-T-0369 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91d2e4e2-ca60-4b74-ab2e-9ea5f278d925 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1737 | T16182-XB00-P6MKA-250001 | 2017-05-10 | T16182-DHI-LI-T-0370 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44d8744f-4bb1-4652-b0f6-23b7d9f1e5b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1738 | T16182-XB00-P7MKA-250002 | 2017-05-10 | T16182-DHI-LI-T-0370 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=783b34de-995a-4d6b-a160-0f90b14c3ec0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1739 | T16182-YD00-P0MKA-250004 | 2017-05-10 | T16182-DHI-LI-T-0370 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=240a1bde-cd8c-423f-a5e2-d6f76b0abef4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1740 | T16182-DM02-P0MKA-250019 | 2017-05-10 | T16182-DHI-LI-T-0370 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d967ed8-09cd-42b5-9038-2adf4ff782d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1651 | T16182-XH01-P0SGC-137011 | 2017-05-11 | DHI-WTRAN-000061 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=806598b7-695b-4756-b54e-093a9060418f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1652 | T16182-YT10-P0SGC-137021 | 2017-05-11 | DHI-WTRAN-000061 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19595f04-0513-49b8-a876-2f175c8aa2dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1653 | T16182-YD00-P0SGZ-137031 | 2017-05-11 | DHI-WTRAN-000061 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=980e4644-ac9c-466b-8171-ca766228c314 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1654 | T16182-YD00-P0CYE-137041 | 2017-05-11 | DHI-WTRAN-000060 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c75b71a-d7ce-4167-8c56-76bc1ecf8d20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1655 | T16182-YU02-P0CYE-137042 | 2017-05-11 | DHI-WTRAN-000060 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b15f537-f217-4247-ac97-3086e420f14a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1656 | T16182-XH01-P0SGC-137111 | 2017-05-11 | DHI-WTRAN-000063 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24821f36-637f-4dfa-a00d-6ebadf951cdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1657 | T16182-YT10-P0SGC-137121 | 2017-05-11 | DHI-WTRAN-000063 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aec4b5bd-ed7f-4ed6-bbc7-517cc49f4dfd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1658 | T16182-YD00-P0CYE-137141 | 2017-05-11 | DHI-WTRAN-000062 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57de45dc-be67-4ffc-b3dc-97074e6c9fb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1659 | T16182-YU02-P0CYE-137142 | 2017-05-11 | DHI-WTRAN-000062 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55455299-8db8-4e44-862a-6d743eaf0993 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1660 | T16182-YR05-P0CWQ-161146 | 2017-05-11 | DHI-WTRAN-000064 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=907c2f8e-687f-4f72-9489-3192252c30b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1661 | T16182-CV03-P0CWQ-161133 | 2017-05-11 | DHI-WTRAN-000064 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ba1133a-6135-41eb-80f8-cf6467f0c781 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1662 | T16182-YD00-P0CRN-161113 | 2017-05-11 | DHI-WTRAN-000064 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66a6cbcb-abde-4023-9ddc-3d7bd3691ba2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1663 | T16182-YD00-P0MJ-110504 | 2017-05-11 | DHI-WTRAN-000065 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40a5741d-a406-423c-afe8-f0da05964b8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1664 | T16182-XG02-P0MJ-110505 | 2017-05-11 | DHI-WTRAN-000065 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=403c15bb-cbf4-4ea8-a6e4-1949c4e8df5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1665 | T16182-YK08-P0MJ-110506 | 2017-05-11 | DHI-WTRAN-000065 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c2f4f04-a9df-4f09-8876-7d70b5db4c57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1666 | T16182-YT01-P0MJ-110508 | 2017-05-11 | DHI-WTRAN-000065 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25d77446-fc29-47d7-933a-ff702d17f777 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1667 | T16182-YU03-P0BAT-150631 | 2017-05-11 | DHI-WTRAN-000066 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cb23eea-5b01-4e36-b9fd-a7cafed34e89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1668 | T16182-YU03-P0BAT-150636 | 2017-05-11 | DHI-WTRAN-000066 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=018a5eec-d457-4de9-9f51-baebd1df2e83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1669 | T16182-VN03-P0LB-122015 | 2017-05-11 | DHI-WTRAN-000067 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b14d22c7-aad7-4850-aaff-0171e14d1eef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1712 | T16182-YU02-P0MBA-121018 | 2017-05-11 | DHI-WTRAN-000070 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e8910cd-b7cf-4a6d-9da9-fa61f231ce02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1713 | T16182-YT10-P0ZEN-150301 | 2017-05-11 | DHI-WTRAN-000068 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7beb601b-90c6-456f-b40e-805e4457bb4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1714 | T16182-YT10-P0ZEN-150302 | 2017-05-11 | DHI-WTRAN-000068 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8cad5ae-4da4-41a3-8661-d7cf7afb5062 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1715 | T16182-YT10-P0ZEN-150303 | 2017-05-11 | DHI-WTRAN-000068 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52e34d60-7228-4e12-8bd0-458571396e35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1716 | T16182-YB03-P0MBA-121019 | 2017-05-11 | DHI-WTRAN-000069 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d38d217-2a11-45a3-b2bf-0510a478f141 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1717 | T16182-YD00-P0CYE-137341 | 2017-05-11 | DHI-WTRAN-000059 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eab02dcd-2089-4816-aeb4-64513c2fd799 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1718 | T16182-YU02-P0CYE-137342 | 2017-05-11 | DHI-WTRAN-000059 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3b29207-2e16-4ac0-9a40-267fc7cc09d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1719 | T16182-YT10-P0SGE-137322 | 2017-05-11 | DHI-WTRAN-000058 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2403d01a-8e85-4a06-8294-8e3a33085fcf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1720 | T16182-YD00-P0EKG-124004 | 2017-05-12 | DHI-WTRAN-000075 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd9cfe10-d0fd-4e1a-a04d-685b68b33a1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1721 | T16182-YD00-P0SMM-128001 | 2017-05-12 | DHI-WTRAN-000076 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50a981dd-0daf-48c5-b775-9f0a7e2ed6dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1722 | T16182-YT01-P0SMM-128004 | 2017-05-12 | DHI-WTRAN-000076 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cef4ae0-b23b-4be3-8a08-fe9fd3361e97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1723 | T16182-XG02-P0SGK-136803 | 2017-05-12 | DHI-WTRAN-000077 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=616f3cd2-9f10-43d5-82c1-e1a4960d61c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1724 | T16182-XH01-P0SGA-136811 | 2017-05-12 | DHI-WTRAN-000077 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41c4c8cf-8fde-4908-9a2b-b30ec290e195 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1725 | T16182-XH01-P0SGE-136812 | 2017-05-12 | DHI-WTRAN-000077 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ec5f15d-cec4-4d4a-b61f-3bead69227bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1726 | T16182-XH01-P0SGK-136813 | 2017-05-12 | DHI-WTRAN-000077 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c27f51e8-bcb6-4e91-9572-c519b8f1accc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1727 | T16182-DE00-P0MAG-123020 | 2017-05-12 | DHI-WTRAN-000078 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aaea5ae8-e5c3-4d61-b8bb-b19a1e9acb7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1728 | T16182-CC02-P8QHB-125172 | 2017-05-12 | DHI-WTRAN-000079 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aec97cc1-b18d-4b3b-82c3-03a2f4875edf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1729 | T16182-UC02-P8QHA-125303 | 2017-05-12 | DHI-WTRAN-000079 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42bfc821-1062-4443-a8f1-a8d35d0798d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1730 | T16182-UC02-P8QHA-125304 | 2017-05-12 | DHI-WTRAN-000079 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc5d325b-089c-4a2e-a410-e584110bef6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1731 | T16182-CC02-P8QHB-125164 | 2017-05-12 | DHI-WTRAN-000080 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01b00631-96f0-4f48-8054-20269b8f9325 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1732 | T16182-XW03-P8ZEN-125012 | 2017-05-12 | DHI-WTRAN-000081 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de2a8f15-b276-4094-9946-878c6857ec19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1741 | T16182-YL22-P0PGB-110406 | 2017-05-15 | DHI-WTRAN-000082 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=105e6f99-5cf0-4726-9f46-2c0db1a45a16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1742 | T16182-XS00-P0MAG-123005 | 2017-05-15 | DHI-WTRAN-000083 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a55a34ad-e5e1-434d-b5c8-2e00bb48bba2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1743 | T16182-CV03-P0CWQ-161135 | 2017-05-15 | DHI-WTRAN-000084 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e2e49cd-9984-43a3-8a30-517db2f10992 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1776 | T16182-CA06-P0UBA-186100 | 2017-05-15 | DHI-TRANSMIT-000013 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b72cf781-0fd8-4b90-a162-2fac34a255be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1744 | T16182-YT01-P0BAA-150751 | 2017-05-17 | DHI-WTRAN-000093 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f1ab848-fb5f-4776-b5a7-1a8bc3aef6b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1745 | T16182-XG01-P0MJ-110509 | 2017-05-17 | DHI-WTRAN-000092 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3532156b-4475-4507-abcb-4e2e252178e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1746 | T16182-XL00-P0ZEN-140004 | 2017-05-17 | DHI-WTRAN-000091 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4331a418-9019-4fcc-8c5e-ade51b032666 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1747 | T16182-XN00-P0ZEN-140003 | 2017-05-17 | DHI-WTRAN-000091 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=006a0789-c798-4fc0-a663-d1f79f775528 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1748 | T16182-CA00-P1BAT-180511 | 2017-05-17 | DHI-WTRAN-000090 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89ce8116-a9fc-49a8-a2f2-98ce49799a46 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1749 | T16182-CA03-P1BAT-180512 | 2017-05-17 | DHI-WTRAN-000090 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efd01f32-7900-4a80-ab6b-ceaa8add1025 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1750 | T16182-CA03-P1BAT-180513 | 2017-05-17 | DHI-WTRAN-000090 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a63ecf7b-9f17-4d8e-9b2b-aa6dbdb2e346 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1751 | T16182-CA06-P0BAT-180500 | 2017-05-17 | DHI-WTRAN-000090 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cc66ec4-fde9-48c1-b229-12d6d1e91aca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1752 | T16182-YF00-P0CBA-161204 | 2017-05-17 | DHI-WTRAN-000089 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0906d098-11b0-4e35-b098-3eef51624335 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1753 | T16182-YF00-P0CBA-161205 | 2017-05-17 | DHI-WTRAN-000089 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42d44586-4b4f-4540-be27-07b225a226d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1754 | T16182-YF00-P0CBA-161207 | 2017-05-17 | DHI-WTRAN-000089 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2776bd98-ba02-4557-a3d9-f83332e4418a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1755 | T16182-YF00-P0CBA-161208 | 2017-05-17 | DHI-WTRAN-000089 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53a2c79a-2e09-4da4-97f7-2abdfb2f0498 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1756 | T16182-YF00-P0CBA-161209 | 2017-05-17 | DHI-WTRAN-000089 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85f987e0-8397-4f48-b1ce-9f8b742dbae1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1757 | T16182-YF00-P0CBA-161220 | 2017-05-17 | DHI-WTRAN-000089 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48b4e8ff-5e7b-4843-97a0-864c63e9fd6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1758 | T16182-YF00-P0CBA-161222 | 2017-05-17 | DHI-WTRAN-000089 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9984460f-656c-4af4-a590-f58b14bcba68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1759 | T16182-YF00-P0CGA-161304 | 2017-05-17 | DHI-WTRAN-000088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c5c3a89-0767-488b-87ab-712fead7c460 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1760 | T16182-YF00-P0CGA-161305 | 2017-05-17 | DHI-WTRAN-000088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5938fb71-b46d-47ee-8de8-0ec699d0c9cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1761 | T16182-YF00-P0CGA-161307 | 2017-05-17 | DHI-WTRAN-000088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44fa2e19-0d94-4c36-917d-82a5191a5cad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1762 | T16182-YF00-P0CGA-161308 | 2017-05-17 | DHI-WTRAN-000088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fecfa5e-221b-457b-8457-45d7cae05a7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1763 | T16182-YF00-P0CGA-161309 | 2017-05-17 | DHI-WTRAN-000088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=260fd155-ff1f-4161-b3c3-e34315321d91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1764 | T16182-YF00-P0CGA-161320 | 2017-05-17 | DHI-WTRAN-000088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc71e859-58eb-4ebc-9bcc-c2adfd0d3302 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1765 | T16182-YF00-P0CGA-161322 | 2017-05-17 | DHI-WTRAN-000088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6faa5c0-3bbe-48a5-9a9a-2aef81392897 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1766 | T16182-YD00-P0LCP-110302 | 2017-05-17 | DHI-WTRAN-000087 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99242d3c-7556-4982-99f6-5184660c730d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1767 | T16182-YT01-P0LCP-110301 | 2017-05-17 | DHI-WTRAN-000087 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=314fefde-8d66-44fa-b053-f93e53bb80f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1768 | T16182-XG02-P0LB-122023 | 2017-05-17 | DHI-WTRAN-000086 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33fb73f0-e0d0-499c-86f4-79bd54a9d8c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1769 | T16182-YF01-P0BYA-161051 | 2017-05-17 | DHI-WTRAN-000085 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c84cd8af-bb8f-49d9-8517-4073844f4d11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1770 | T16182-CA02-P0UBA-181055 | 2017-05-17 | DHI-TRANSMIT-000019 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82459ef2-6297-4258-8f6a-3c915258c792 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1771 | T16182-CA01-P0UBA-181053 | 2017-05-17 | DHI-TRANSMIT-000018 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=389a14da-9fdc-4ba8-bafe-da42cd7802e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1772 | T16182-CA01-P0UBA-181052 | 2017-05-17 | DHI-TRANSMIT-000017 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d91184fa-3028-4b95-b540-19c5a7054fef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1773 | T16182-CA01-P0UBA-181051 | 2017-05-17 | DHI-TRANSMIT-000016 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09906488-b6b9-4fb6-b09e-3a6aad62227f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1774 | T16182-CA00-P0UBA-181005 | 2017-05-17 | DHI-TRANSMIT-000015 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d613dead-213f-4f48-ac48-ad78bac9f7c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1775 | T16182-CA00-P0UBA-181002 | 2017-05-17 | DHI-TRANSMIT-000014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ec6c878-99c0-4d46-a063-71f7919a1aca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1777 | T16182-YD00-P0CUQ-161112 | 2017-05-17 | DHI-WTRAN-000105 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25826e03-3de8-4193-bd32-524736a25ae6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1778 | T16182-CA02-P0UBA-181056 | 2017-05-17 | DHI-WTRAN-000104 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e7e525c-51f6-4e8e-8385-636be6e8e43b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1779 | T16182-CA01-P0UBA-181054 | 2017-05-17 | DHI-WTRAN-000103 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65969271-ec16-4e52-bae5-818b2bd65b2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1780 | T16182-CA00-P0UBA-181004 | 2017-05-17 | DHI-WTRAN-000102 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9dd1d298-274a-421b-8886-f464924879bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1781 | T16182-CA00-P0UBA-181003 | 2017-05-17 | DHI-WTRAN-000101 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab838b37-f954-4f9b-9194-478cf2e8335e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1782 | T16182-CA00-P0UBA-181001 | 2017-05-17 | DHI-WTRAN-000100 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76d10ced-b502-456e-bb27-527547b16226 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1783 | T16182-CA06-P0UBA-181000 | 2017-05-17 | DHI-WTRAN-000099 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e45c9389-6152-4706-817e-06f7a4e6bd53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1784 | T16182-XW03-P0GNR-130104 | 2017-05-17 | DHI-WTRAN-000098 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7377b20-23ed-488b-a185-08396dfc7aa5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1785 | T16182-XW03-P0GCF-130005 | 2017-05-17 | DHI-WTRAN-000097 | IFI | 2 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f330626-23ae-4d6f-9539-30329d14c1c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1786 | T16182-XG07-P0GCF-130003 | 2017-05-17 | DHI-WTRAN-000096 | IFR | C | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8c2211a-baa4-4dcc-a1f5-919925ff27ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1787 | T16182-YD00-P0GCF-130002 | 2017-05-17 | DHI-WTRAN-000095 | IFR | C | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7c9c954-29bc-4b68-93c2-966dc236499a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1788 | T16182-YR02-P0ZEN-165900 | 2017-05-18 | DHI-TRANSMIT-000020 | IFC | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1789 | T16182-YR02-P0ZEN-150001 | 2017-05-18 | DHI-TRANSMIT-000021 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d9b9acc-b711-4663-9498-1ce91c32557b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1790 | T16182-YT10-P0BBT-150651 | 2017-05-18 | DHI-TRANSMIT-000022 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1eac6e6c-1140-41d8-a766-29669db7171b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1791 | T16182-YT10-P0BAT-150601 | 2017-05-18 | DHI-TRANSMIT-000023 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56ae368c-6cb4-4096-b836-f50522a8e95c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1792 | T16182-YR05-P0CJN-290002 | 2017-05-18 | DHI-TRANSMIT-000024 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6fe4d8a-6c9e-4929-971a-b97bccfda349 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1793 | T16182-YT10-P0ZEN-152810 | 2017-05-18 | DHI-TRANSMIT-000025 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4024d516-3b1b-4079-8434-ef270e3ec973 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1794 | T16182-YD00-P0ZEN-152822 | 2017-05-18 | DHI-TRANSMIT-000026 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dad0f6a2-ec36-4e1d-9e0c-0f532779e68d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1795 | T16182-CA06-P0USR-184700 | 2017-05-18 | DHI-TRANSMIT-000027 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e941166-3802-4143-a93b-401c75f4bcbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1796 | T16182-CA00-P0USR-184701 | 2017-05-18 | DHI-TRANSMIT-000028 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba4995f4-7dbf-4a5a-9e3c-fcaed9259e84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1797 | T16182-CA00-P0USR-184702 | 2017-05-18 | DHI-TRANSMIT-000029 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67528df9-98ee-4bab-9927-e2690e7359cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1798 | T16182-CA03-P0USR-184751 | 2017-05-18 | DHI-TRANSMIT-000030 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eefd77ee-2d1a-480d-8740-f1f3c7fddcdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1799 | T16182-CA03-P0USR-184752 | 2017-05-18 | DHI-TRANSMIT-000031 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe079db8-da1c-463d-aa9e-0f057b38ac25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1825 | T16182-YF00-P0CBA-161206 | 2017-05-19 | DHI-WTRAN-000107 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=021ff868-72a9-450b-b015-9552d7eb3c6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1826 | T16182-YF00-P0CBA-161221 | 2017-05-19 | DHI-WTRAN-000107 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81132508-e1cd-4c01-bf74-38488896671e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1827 | T16182-YF00-P0CGA-161306 | 2017-05-19 | DHI-WTRAN-000107 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=162d7494-6c24-494c-acd1-e93499613dce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1828 | T16182-YF00-P0CGA-161321 | 2017-05-19 | DHI-WTRAN-000107 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbfc0e98-0c9d-4251-98b6-37e189c5fce8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1829 | T16182-YU02-P0MJ-110507 | 2017-05-19 | DHI-WTRAN-000109 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc726279-246d-42ac-9214-cfabbfaba8a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1830 | T16182-YD00-P0BAA-150761 | 2017-05-19 | DHI-WTRAN-000111 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca7ec305-61b5-4dbe-b9ba-dc3b7bfe43cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1831 | T16182-CA00-P0UST-182001 | 2017-05-19 | DHI-TRANSMIT-000032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0825c268-c8fd-41ce-bdb7-81902bb3227a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1832 | T16182-CA00-P0UST-182002 | 2017-05-19 | DHI-TRANSMIT-000032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=491186c8-8a59-4e01-8c16-42be6969499c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1833 | T16182-CA00-P0UST-182003 | 2017-05-19 | DHI-TRANSMIT-000032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6096389e-3505-40f2-9a8e-49379cb5ac39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1834 | T16182-CA00-P0UST-182004 | 2017-05-19 | DHI-TRANSMIT-000032 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5850ec97-5887-4449-b900-e1d925c57659 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1835 | T16182-CA00-P0UST-182005 | 2017-05-19 | DHI-WTRAN-000108 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07412ca4-1bc3-4ed5-81ec-4c8d67aa4507 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2869 | T16182-YF00-P0MJ-110511 | 2017-05-19 | DHI-WTRAN-000110 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fcc53a5-40fe-4b89-94fb-b8156453bf4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1802 | T16182-XW03-P0SAV-135101 | 2017-05-22 | DHI-WTRAN-000116 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91016cdd-01f7-40be-9830-c9e31002f70f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1803 | T16182-XG07-P0SAV-135102 | 2017-05-22 | DHI-WTRAN-000117 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cd2c8c1-bd9a-407f-8c8f-03a49dbe3d9a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1804 | T16182-XW03-P0SAV-135103 | 2017-05-22 | DHI-WTRAN-000118 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b4ef89a-de7c-4284-b344-372a6398c603 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1805 | T16182-XH02-P0SAV-135104 | 2017-05-22 | DHI-WTRAN-000119 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7050a90b-a2a8-46b3-970c-ca4ca947b31a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1806 | T16182-YU02-P0MKY-290006 | 2017-05-22 | DHI-WTRAN-000120 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ee64530-0087-49f6-bc40-6c771b45e10a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1807 | T16182-XS00-P0GCF-130001 | 2017-05-22 | DHI-WTRAN-000121 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abc2127d-fcda-467a-b265-795523600fba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1808 | T16182-XG02-P0GCF-130004 | 2017-05-22 | DHI-WTRAN-000122 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d57c24e8-8db6-42e4-a8cd-ca9414abc3f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1809 | T16182-XS00-P0GNR-130101 | 2017-05-22 | DHI-WTRAN-000123 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89e1f323-970f-49e8-b2fa-c6860c21a124 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1810 | T16182-XG02-P0GNR-130103 | 2017-05-22 | DHI-WTRAN-000125 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98a1a9e5-2bc7-4aec-809b-75b4347f5783 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1811 | T16182-XG07-P0GNR-130102 | 2017-05-22 | DHI-WTRAN-000124 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a51b7e1-612f-4061-8b23-97c06aa84440 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1812 | T16182-XV00-P0LB-122039 | 2017-05-22 | DHI-WTRAN-000126 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=022a32fd-6acf-44fe-88be-87939485ee07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1814 | T16182-XH01-P0SGA-136604 | 2017-05-22 | DHI-WTRAN-000129 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9528b173-98c0-4aeb-aa1d-61287370d473 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1815 | T16182-XG02-P0SGA-136603 | 2017-05-22 | DHI-WTRAN-000130 | IFR | B | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f78d801b-55a3-4167-a7ac-99c098e2e422 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1823 | T16182-YU02-P0ZEN-150211 | 2017-05-22 | DHI-WTRAN-000127 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a662c108-e490-43f9-8374-af05b5b7271b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1824 | T16182-YU02-P0ZEN-150212 | 2017-05-22 | DHI-WTRAN-000128 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b45ecbd-a8f1-444e-af80-6a0c96404b08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1840 | T16182-CA03-P0UMA-180464 | 2017-05-22 | DHI-WTRAN-000112 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b93c563e-6137-4865-8aa1-0cad955a0d8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1841 | T16182-CA03-P0UMA-180465 | 2017-05-22 | DHI-WTRAN-000112 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13264394-e452-49d3-ac6e-a49322b77cf8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1842 | T16182-CA03-P0UMA-180466 | 2017-05-22 | DHI-WTRAN-000112 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1577f49b-e4df-4483-86ba-a31cf97e8b38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1843 | T16182-CA03-P0UMA-180469 | 2017-05-22 | DHI-WTRAN-000112 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d52ababd-e8fe-426c-8294-06572236859d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1844 | T16182-YT10-P0SGA-136605 | 2017-05-22 | DHI-WTRAN-000113 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67e2726c-ddfb-454c-9e10-a992a43945a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1845 | T16182-YT01-P0CFA-151161 | 2017-05-22 | DHI-WTRAN-000114 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c865ae56-d7bf-44dd-b0d9-1bb6bd463e4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1846 | T16182-YT01-P0CHB-151101 | 2017-05-22 | DHI-WTRAN-000114 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b23873e8-112f-4466-a558-15db275d7640 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1850 | T16182-YD00-P0CHB-151111 | 2017-05-22 | DHI-WTRAN-000115 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1231acc-1bcf-486f-962e-c023caf0c135 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1851 | T16182-YD00-P0CHB-151112 | 2017-05-22 | DHI-WTRAN-000115 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14afbdae-ebc1-4b89-a036-e28f21d9c090 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1852 | T16182-YD00-P0CFA-151171 | 2017-05-22 | DHI-WTRAN-000115 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86eb9cd0-0e36-43a0-9869-a3a683635417 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1853 | T16182-YD00-P0CHB-151131 | 2017-05-22 | DHI-WTRAN-000115 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef1fd75d-b196-4185-b888-8e1237d7f604 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2106 | T16182-CA03-P0UMA-180471 | 2017-05-22 | DHI-WTRAN-000112 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98cba456-2a11-408d-a541-5d0a1c0be010 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1813 | T16182-XG02-P0LB-122022 | 2017-05-23 | DHI-TRANSMIT-000033 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d71d5336-b44e-46f3-9046-8dc897ebb6bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1816 | T16182-YS00-P0ZEN-163303 | 2017-05-23 | DHI-TRANSMIT-000038 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a4bf3e6-c8f4-4685-a2e7-bda6c86baa4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1817 | T16182-YS00-P0ZEN-163306 | 2017-05-23 | DHI-TRANSMIT-000039 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b927413-9c9a-420d-a911-43f03b20cdb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1818 | T16182-YS00-P0ZEN-163313 | 2017-05-23 | DHI-TRANSMIT-000040 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7509a24-0503-4e72-a609-1b0b5f2e064f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1819 | T16182-XW03-P0SAJ-133701 | 2017-05-23 | DHI-TRANSMIT-000034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e36de03-f3cb-4fdf-a83b-61c7555fda5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1820 | T16182-XG07-P0SAJ-133702 | 2017-05-23 | DHI-TRANSMIT-000035 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d4917b8-929e-4328-86c3-e66ef5e0e054 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1821 | T16182-XW03-P0SAJ-133703 | 2017-05-23 | DHI-TRANSMIT-000036 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bd4acd0-898c-47bd-8ad8-bef705c81cbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1822 | T16182-XH02-P0SAJ-133704 | 2017-05-23 | DHI-TRANSMIT-000037 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a30dba28-d1e8-4395-9240-f888f5df712c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1836 | T16182-CA03-P0UGD-181968 | 2017-05-23 | DHI-TRANSMIT-000046 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e731082-b08f-424c-bd15-b388c5284c03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1837 | T16182-CA02-P0UGD-181964 | 2017-05-23 | DHI-TRANSMIT-000045 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bc00d16-10df-480b-b9d5-8893ef9f5571 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1838 | T16182-CA02-P0UGD-181963 | 2017-05-23 | DHI-TRANSMIT-000044 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65114b91-910f-489b-8638-640c56575924 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1839 | T16182-CA02-P0UGD-181962 | 2017-05-23 | DHI-TRANSMIT-000043 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62267d28-3208-442b-aaac-893bfc8914a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1847 | T16182-CA01-P0UGD-181956 | 2017-05-23 | DHI-TRANSMIT-000041 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=664f1649-7280-480e-879c-7d7364828fb4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1848 | T16182-CA01-P0UGD-181957 | 2017-05-23 | DHI-TRANSMIT-000042 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f2ba162-ed36-47e9-93ee-0a2e4e9bb5fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1849 | T16182-XS00-P0SG-136601 | 2017-05-23 | DHI-TRANSMIT-000047 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40041426-1de2-4627-92d2-badb1c4c9fbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1854 | T16182-UE00-P0LB-122062 | 2017-05-23 | DHI-WTRAN-000131 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c908ebc3-cae4-4202-bd94-1550375cf7b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1855 | T16182-YD00-P0LB-122053 | 2017-05-23 | DHI-WTRAN-000132 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=115af14a-36c0-4c45-a3a6-2cbabfdf3f2b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1856 | T16182-YD00-P0LB-122055 | 2017-05-23 | DHI-WTRAN-000133 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c6531c2-345a-453b-9cc2-6554f704d064 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1857 | T16182-YQ03-P0LB-122086 | 2017-05-23 | DHI-WTRAN-000134 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e34500e6-645f-4078-b1f8-c259c34126f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1858 | T16182-UE00-P0LB-122013 | 2017-05-23 | DHI-WTRAN-000135 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e6e7d72-7738-46be-affe-14f9f6a1e367 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1859 | T16182-UE00-P0LB-122014 | 2017-05-23 | DHI-WTRAN-000136 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85ff1628-7919-446e-ab5f-7bc02d17fae2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1860 | T16182-XS00-P0LB-122036 | 2017-05-23 | DHI-WTRAN-000137 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0b0a338-ef83-46fc-ae45-0d2b596d937c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1861 | T16182-YE00-P0ZEN-152707 | 2017-05-23 | DHI-WTRAN-000138 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8694c72-5b00-4f25-90c2-e210095b9120 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1862 | T16182-XS00-P0MAG-123004 | 2017-05-23 | DHI-WTRAN-000139 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c840648-844a-4a7a-a11e-05b6c313f474 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1863 | T16182-XK00-P0PCA-126539 | 2017-05-23 | DHI-WTRAN-000140 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f36c0a9-6e3a-4874-9485-3bf3a864ebd1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1864 | T16182-VE04-P0ULX-171201 | 2017-05-23 | DHI-WTRAN-000141 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ca01abb-9424-461f-ba9a-6487c5f3b005 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1865 | T16182-XB02-P0ULX-171202 | 2017-05-23 | DHI-WTRAN-000141 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c065c83-2d85-43aa-b4d7-b977fee30cca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1866 | T16182-XB02-P0ULX-171203 | 2017-05-23 | DHI-WTRAN-000141 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5cd467bd-c264-4535-9039-8383df2b5e81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1867 | T16182-DP00-P0ZEN-020007 | 2017-05-23 | DHI-WTRAN-000142 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8965b3c-06ca-4caf-b329-a272f90d5ba6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1801 | T16182-DE00-P0ZEN-152820 | 2017-05-24 | DHI-TRANSMIT-000048 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb74a93f-f773-430d-a24e-70eacbd20d25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1868 | T16182-XH02-P0SAK-133604 | 2017-05-24 | DHI-TRANSMIT-000068 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eafad703-9226-4fb1-bdd5-eb834ae8dfb6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1869 | T16182-XW03-P0SAK-133603 | 2017-05-24 | DHI-TRANSMIT-000067 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b21f330-a841-4b4e-b5e9-5f9d8fb7c8dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1870 | T16182-XG07-P0SAK-133602 | 2017-05-24 | DHI-TRANSMIT-000066 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cbe25d6-2d29-422e-98c2-7500624c4287 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1871 | T16182-XW03-P0SAK-133601 | 2017-05-24 | DHI-TRANSMIT-000065 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ee1ff3d-c15d-4199-87bf-44bb1d979df0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1872 | T16182-VK02-P0ULC-172503 | 2017-05-24 | DHI-TRANSMIT-000064 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a6383b5-df13-46ec-ac36-d81e51965d10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1873 | T16182-XB02-P0ULC-172502 | 2017-05-24 | DHI-TRANSMIT-000063 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d84ea53-f8c9-4d00-8bc5-1cc2bca8e659 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1874 | T16182-VE04-P0ULC-172501 | 2017-05-24 | DHI-TRANSMIT-000062 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ec65e86-659e-4a3f-ba11-80d9147a15da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1875 | T16182-CA01-P0UCB-180652 | 2017-05-24 | DHI-TRANSMIT-000061 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bce4bea-e15e-4665-88af-595e75052513 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1876 | T16182-UE00-P0LB-122007 | 2017-05-24 | DHI-TRANSMIT-000060 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2c5e9a6-578f-4d3c-9d82-0b993b7fc811 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1877 | T16182-YK00-P0ZEN-165303 | 2017-05-24 | DHI-TRANSMIT-000059 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc4c7c36-769b-4191-8706-c175d56d4125 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1878 | T16182-YF02-P0ZEN-161031 | 2017-05-24 | DHI-TRANSMIT-000058 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8010eea-f343-40f0-9459-7f792f3918cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1879 | T16182-XG02-P6LCM-110007 | 2017-05-24 | DHI-TRANSMIT-000057 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eaf38ae6-9c56-4437-b875-9efbb282ccdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1880 | T16182-XG02-P0LBS-110006 | 2017-05-24 | DHI-TRANSMIT-000056 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bec56b0e-5a4a-449f-bb2c-b75de89d4b17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1881 | T16182-XG02-P0LBG-110005 | 2017-05-24 | DHI-TRANSMIT-000055 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f806667-a767-41f6-a326-02528d47ffca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1882 | T16182-XG02-P0LBC-110004 | 2017-05-24 | DHI-TRANSMIT-000054 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1d49aa7-2c61-436b-8ade-0ca354080f71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1883 | T16182-XG02-P0LBA-110003 | 2017-05-24 | DHI-TRANSMIT-000053 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07424541-bfb4-4ca7-a446-d21fee04b1f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1884 | T16182-YS00-P0ZEN-163317 | 2017-05-24 | DHI-TRANSMIT-000052 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6ac0eb7-ce44-494e-a4e3-ee2e43cd0d45 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1885 | T16182-YS00-P0ZEN-163305 | 2017-05-24 | DHI-TRANSMIT-000051 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=479ff357-2cae-42c8-8f99-532b6d8044de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1886 | T16182-CA02-P0UBA-186155 | 2017-05-24 | DHI-TRANSMIT-000050 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49adbd90-7488-4dfa-8904-7a63e2c42f07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1887 | T16182-CA01-P0UBA-186152 | 2017-05-24 | DHI-TRANSMIT-000049 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=823c3817-9165-4e76-a284-1876b7a2c7a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1888 | T16182-XG02-P0SGA-137901 | 2017-05-25 | DHI-WTRAN-000173 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30091330-a34c-4599-a6fa-912e42e8aa7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1889 | T16182-XG02-P0SGE-137903 | 2017-05-25 | DHI-WTRAN-000173 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2937fd9e-d6c9-4854-ac7e-bb2cb42e88f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1890 | T16182-XH01-P0SGA-137911 | 2017-05-25 | DHI-WTRAN-000173 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0a0170a-31f4-4d56-aa02-a17c0121580e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1891 | T16182-XH01-P0SGE-137913 | 2017-05-25 | DHI-WTRAN-000173 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c834aca-246f-475f-80e1-77f6c25c1e0b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1892 | T16182-YD00-P0SGZ-137931 | 2017-05-25 | DHI-WTRAN-000173 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e491d69-355f-4490-b62d-b94c266cae7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1893 | T16182-YT10-P0SGE-137923 | 2017-05-25 | DHI-WTRAN-000173 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f58017e7-b7d3-4401-b5e4-bee7b60483dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1894 | T16182-YD00-P0CYE-137941 | 2017-05-25 | DHI-WTRAN-000172 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=375bbc74-bf37-495d-a23d-cea1cd10ce1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1895 | T16182-YU02-P0CYE-137942 | 2017-05-25 | DHI-WTRAN-000172 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e8e0bc7-38ef-490e-8cd5-1d586119a6e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1896 | T16182-DP00-P0ZEN-020006 | 2017-05-25 | DHI-WTRAN-000171 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84fe8a51-514a-40cd-9870-66631e41368a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1897 | T16182-YE03-P0BAU-152519 | 2017-05-25 | DHI-WTRAN-000170 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c93f805-cf1e-4ccb-b70d-51a3dc1567ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1898 | T16182-YE03-P0BAU-152532 | 2017-05-25 | DHI-WTRAN-000170 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a8af7b3-f4ca-4d11-894d-5aca1ce96683 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1899 | T16182-UC02-P6MKA-250011 | 2017-05-25 | DHI-WTRAN-000169 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0521827-08b3-4976-ac92-7987b75a3fc3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1900 | T16182-UC02-P7MKA-250012 | 2017-05-25 | DHI-WTRAN-000169 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87e87805-e3d6-4d6f-bce3-7db5f6e4c533 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1901 | T16182-YS00-P0ZEN-163309 | 2017-05-25 | DHI-WTRAN-000168 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1902 | T16182-YS00-P0ZEN-163308 | 2017-05-25 | DHI-WTRAN-000167 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1903 | T16182-YS00-P0ZEN-163304 | 2017-05-25 | DHI-WTRAN-000166 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1904 | T16182-YS00-P0ZEN-163302 | 2017-05-25 | DHI-WTRAN-000165 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1905 | T16182-YT01-P0CYE-136618 | 2017-05-25 | DHI-WTRAN-000164 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1906 | T16182-YT01-P0CYE-136617 | 2017-05-25 | DHI-WTRAN-000163 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1907 | T16182-YT01-P0SGX-136616 | 2017-05-25 | DHI-WTRAN-000162 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1908 | T16182-YT01-P0SGZ-136615 | 2017-05-25 | DHI-WTRAN-000161 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1909 | T16182-YT01-P0SGK-136614 | 2017-05-25 | DHI-WTRAN-000160 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1910 | T16182-YT01-P0SGC-136613 | 2017-05-25 | DHI-WTRAN-000159 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1911 | T16182-YT01-P0SGE-136612 | 2017-05-25 | DHI-WTRAN-000158 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1912 | T16182-YT01-P0SGA-136611 | 2017-05-25 | DHI-WTRAN-000157 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1913 | T16182-YT01-P0SGA-136610 | 2017-05-25 | DHI-WTRAN-000156 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1914 | T16182-YT01-P0SGA-136609 | 2017-05-25 | DHI-WTRAN-000155 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1915 | T16182-YT01-P0GNR-130108 | 2017-05-25 | DHI-WTRAN-000154 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1916 | T16182-XN00-P0GNR-130107 | 2017-05-25 | DHI-WTRAN-000153 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1917 | T16182-XN00-P0GNR-130105 | 2017-05-25 | DHI-WTRAN-000152 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1918 | T16182-CV03-P0GCF-130055 | 2017-05-25 | DHI-WTRAN-000151 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1919 | T16182-XB02-P0GCF-130042 | 2017-05-25 | DHI-WTRAN-000150 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1920 | T16182-YD00-P0GCF-130019 | 2017-05-25 | DHI-WTRAN-000149 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1921 | T16182-YT01-P0GCF-130014 | 2017-05-25 | DHI-WTRAN-000148 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1922 | T16182-XH01-P0GCF-130013 | 2017-05-25 | DHI-WTRAN-000147 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1923 | T16182-YK09-P0GCF-130012 | 2017-05-25 | DHI-WTRAN-000146 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1924 | T16182-XN00-P0GCF-130008 | 2017-05-25 | DHI-WTRAN-000145 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1925 | T16182-YL25-P0MBA-121024 | 2017-05-25 | DHI-WTRAN-000144 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1926 | T16182-XW03-P0GHC-110051 | 2017-05-25 | DHI-WTRAN-000143 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1927 | T16182-CA02-P0ULD-183955 | 2017-05-26 | DHI-WTRAN-000180 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e84ed47-7e04-45db-aa57-a83cd56a74e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1928 | T16182-CA01-P0ULD-183951 | 2017-05-26 | DHI-WTRAN-000180 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f54dc6e-fe66-4c95-b606-15a0c320ae96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1929 | T16182-CA02-P0UST-182060 | 2017-05-26 | DHI-WTRAN-000179 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0470c92-7866-471c-ae62-1eb8200d784a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1930 | T16182-CA02-P0UST-182061 | 2017-05-26 | DHI-WTRAN-000179 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=783789fc-4282-4cca-81b0-4ad5db18e389 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1931 | T16182-CA03-P0UST-182062 | 2017-05-26 | DHI-WTRAN-000179 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beb8c3db-d00d-4ba2-a6b7-8da5d6ecf168 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1932 | T16182-CA03-P0UST-182063 | 2017-05-26 | DHI-WTRAN-000179 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6eb4f0da-798e-4c89-9e0f-fedab8a46ad8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1933 | T16182-CA01-P0UST-182051 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30e802af-15da-43cd-b7f1-d2e780232536 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1934 | T16182-CA01-P0UST-182052 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3eae37f3-c387-46eb-8654-e2f0345f0f98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1935 | T16182-CA01-P0UST-182053 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5aba4da-d7a2-4741-bd74-a8963bb24fdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1936 | T16182-CA02-P0UST-182058 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9002631b-0e78-4bc9-b890-93a5063d208f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1937 | T16182-CA02-P0UST-182059 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13b18f14-bdb3-409b-8703-d49a7b6a4a62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1938 | T16182-CA03-P0UST-182054 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=548f4f28-d05b-4a98-b452-b1cd19e846b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1939 | T16182-CA03-P0UST-182055 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24b41d8c-a81b-41dd-9681-940f4970fd2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1940 | T16182-CA03-P0UST-182056 | 2017-05-26 | DHI-WTRAN-000178 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a91eb517-fd82-47ee-a75e-130694974f46 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1941 | T16182-CA06-P0UST-182000 | 2017-05-26 | DHI-WTRAN-000177 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c6e5518-d4e1-4e6c-ad5a-99a5c17ba7a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1942 | T16182-YK01-P0LAC-126006 | 2017-05-26 | DHI-WTRAN-000176 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3aca912d-7100-4750-8d28-7f9a94096e02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1943 | T16182-BP00-P0LBC-140012 | 2017-05-26 | DHI-WTRAN-000175 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f140ee6-0b39-4951-af13-edb452628f73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1944 | T16182-BV02-P0ZEN-050001 | 2017-05-26 | DHI-WTRAN-000174 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56e846af-a615-4426-857f-1e07f9276544 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1945 | T16182-CA03-P1BAT-180512 | 2017-05-29 | DHI-TRANSMIT-000100 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=654532d3-6258-4f2b-9e4b-c1e7843946fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1946 | T16182-CA03-P1BAT-180513 | 2017-05-29 | DHI-TRANSMIT-000100 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8b8950a-68a5-42cd-8906-d495a8355088 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1947 | T16182-CA06-P0BAT-180500 | 2017-05-29 | DHI-TRANSMIT-000100 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e59f1d1-175c-4a02-ad47-ad918158e798 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1948 | T16182-XS00-P0LB-122035 | 2017-05-29 | DHI-TRANSMIT-000099 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ad77e4a-3cfc-46e4-a1b6-a6646a60ad0d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1949 | T16182-CA00-P1BAT-180511 | 2017-05-29 | DHI-WTRAN-000191 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ee5f834-582f-456b-86f8-bbabb9bff92a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1950 | T16182-CV03-P0PUR-411001 | 2017-05-29 | DHI-WTRAN-000190 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=696ead64-02a5-4ed2-b2c1-ef74eee1e62c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1951 | T16182-CV03-P0PUR-411011 | 2017-05-29 | DHI-WTRAN-000190 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba5c8bb8-95b3-4662-baad-405cd4328eea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1952 | T16182-CV03-P0PUR-411021 | 2017-05-29 | DHI-WTRAN-000190 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97ae09fd-5f3c-40ce-9336-49baebbbda1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1953 | T16182-CV03-P0PUR-411031 | 2017-05-29 | DHI-WTRAN-000190 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf935d56-5038-47c4-a933-77ad91f3664e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1954 | T16182-YD00-P0CWQ-161407 | 2017-05-29 | DHI-WTRAN-000189 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=459d4b85-9413-4f69-ba61-6de975872793 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1955 | T16182-YD00-P0CWQ-161408 | 2017-05-29 | DHI-WTRAN-000189 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccfaf894-c5b8-4c33-a900-e85e6e35896d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1956 | T16182-YD00-P0CWQ-161409 | 2017-05-29 | DHI-WTRAN-000189 | IFR | D | DR | TRUE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1957 | T16182-CN00-P0ZEN-110701 | 2017-05-29 | DHI-WTRAN-000188 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1958 | T16182-YU02-P0ZEN-150211 | 2017-05-29 | DHI-WTRAN-000187 | IFR | D | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1959 | T16182-YU02-P0ZEN-150212 | 2017-05-29 | DHI-WTRAN-000187 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1960 | T16182-YT01-P0BAC-150711 | 2017-05-29 | DHI-WTRAN-000186 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05013528-169b-4923-830e-488cae06f08c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1961 | T16182-YD00-P0BAC-150721 | 2017-05-29 | DHI-WTRAN-000186 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb916d0a-cd8e-4aa2-aa6d-3d8b88ee8ca4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1962 | T16182-YT10-P0ZEN-152205 | 2017-05-29 | DHI-WTRAN-000185 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f4df98b-223a-4223-ae7f-fd905d79f56a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1963 | T16182-YB11-P0ZEN-152403 | 2017-05-29 | DHI-WTRAN-000185 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a71bbba-f758-48c0-a72d-553c0d8513d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1964 | T16182-YQ01-P0ZEN-152303 | 2017-05-29 | DHI-WTRAN-000185 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f08e692a-586d-43ed-a03e-6293ea07a477 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1965 | T16182-YT10-P0ZEN-152209 | 2017-05-29 | DHI-WTRAN-000184 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0700db97-8234-48ad-8135-f932b162098a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1966 | T16182-YB11-P0ZEN-152407 | 2017-05-29 | DHI-WTRAN-000184 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22565686-3358-416b-ab97-567abf8e82b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1967 | T16182-YQ01-P0ZEN-152307 | 2017-05-29 | DHI-WTRAN-000184 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4625e0e-e253-45e9-ab05-7548dfab91dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1968 | T16182-YD00-P0SML-128013 | 2017-05-29 | DHI-WTRAN-000183 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de307b8c-617c-4330-9dd0-226208c0052f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1969 | T16182-YT01-P0SML-128018 | 2017-05-29 | DHI-WTRAN-000183 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64815c92-db47-4730-90ba-5be9293d9e80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1970 | T16182-YF00-P0SCA-127518 | 2017-05-29 | DHI-WTRAN-000182 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=988dfbd7-1576-474c-a2c2-552580eb5368 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1971 | T16182-YF02-P0SCA-127514 | 2017-05-29 | DHI-WTRAN-000182 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=321c3ead-c28b-4f92-8cbb-44c67096a382 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1972 | T16182-YL01-P0SCA-127516 | 2017-05-29 | DHI-WTRAN-000182 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a938de6-d3b0-4a5c-9178-b10a15318541 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1973 | T16182-YL01-P0SCA-127517 | 2017-05-29 | DHI-WTRAN-000182 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=760e9d5c-7641-4abf-9f91-b732c75ed855 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1974 | T16182-YR05-P0SCA-127523 | 2017-05-29 | DHI-WTRAN-000182 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adbf850b-b977-4c3f-9fea-a9bfab612bd9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1975 | T16182-XW03-P0QJA-110052 | 2017-05-29 | DHI-TRANSMIT-000107 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b122c518-6929-44cf-a965-5040b5012bd7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1976 | T16182-XG07-P0SCA-120014 | 2017-05-29 | DHI-TRANSMIT-000108 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5755d365-7beb-45f0-8a7f-71e800a2c83f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1977 | T16182-XS00-P0SCA-120015 | 2017-05-29 | DHI-TRANSMIT-000108 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ac86882-5c79-41a4-8ded-fc2170c57ba1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1978 | T16182-XS00-P0SCA-120016 | 2017-05-29 | DHI-TRANSMIT-000108 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c46eb288-9973-4a58-955d-eeba65fa6f63 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1979 | T16182-XG07-P0EKG-120018 | 2017-05-29 | DHI-TRANSMIT-000106 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd5e0517-7ade-4763-96f1-84bd9ecefd6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2003 | T16182-YK10-P0LCP-410001 | 2017-05-29 | DHI-TRANSMIT-000105 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c52e395d-9575-4c53-b11e-9394a46a7285 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2004 | T16182-YK10-P0GHC-410011 | 2017-05-29 | DHI-TRANSMIT-000105 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bacec10-3428-42e7-ba71-ad0170169add | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2005 | T16182-YK10-P0GKB-410021 | 2017-05-29 | DHI-TRANSMIT-000105 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68293908-bf3c-4b51-a3ea-1ecdda0e7888 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2006 | T16182-YK10-P0GKB-410031 | 2017-05-29 | DHI-TRANSMIT-000105 | IFC | 0 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=171bcad2-5e0b-4e84-be1d-0e6b01b250fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2007 | T16182-YT10-P0LCP-410002 | 2017-05-29 | DHI-TRANSMIT-000104 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be1bf941-3276-4154-9c51-1192f69f149f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2008 | T16182-YT10-P0GHC-410012 | 2017-05-29 | DHI-TRANSMIT-000104 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=657ac168-ac2e-4709-b3f9-ccf36cac15a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2009 | T16182-YT10-P0GKB-410022 | 2017-05-29 | DHI-TRANSMIT-000104 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bcd8c585-f4b9-4b47-9da4-fac97cd7ccec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2010 | T16182-YT10-P0GKB-410032 | 2017-05-29 | DHI-TRANSMIT-000104 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c15a5ff5-3f54-48aa-a8f4-37a4cdc393cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2011 | T16182-XG02-P0EK-120007 | 2017-05-29 | DHI-TRANSMIT-000103 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84af5614-0c5e-4a26-8037-bcadf84549b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2012 | T16182-XW03-P0SAI-133901 | 2017-05-29 | DHI-TRANSMIT-000102 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f35fac15-2583-4f91-a062-90fdeb9563eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2013 | T16182-XH02-P0SAI-133904 | 2017-05-29 | DHI-TRANSMIT-000102 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faef8d9f-da2e-4421-8db6-1a8c4da5b19f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2014 | T16182-XG07-P0SAI-133902 | 2017-05-29 | DHI-TRANSMIT-000102 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bf1ccc1-3af9-4573-8947-82b9a2de575a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2015 | T16182-XG02-P1MBH-110013 | 2017-05-29 | DHI-WTRAN-000193 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43a6000d-dab9-4461-adf9-8f6498dd3c14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2016 | T16182-YR05-P0ZEN-161011 | 2017-05-29 | DHI-WTRAN-000192 | IFR | B | DR | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2017 | T16182-XW03-P0SAI-133903 | 2017-05-29 | DHI-TRANSMIT-000102 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1bfde08-5ee9-4de0-a17d-41383a583b54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2018 | T16182-VE04-P0UZT-172701 | 2017-05-30 | DHI-TRANSMIT-000114 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f8bcf21-bed0-41bd-9ecc-94a7cac0f6f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2019 | T16182-XB02-P0UZT-172702 | 2017-05-30 | DHI-TRANSMIT-000114 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e99cce0-a8b7-4455-9a44-bc20cf25f473 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2020 | T16182-XB02-P0UZT-172703 | 2017-05-30 | DHI-TRANSMIT-000114 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66ee3d57-f5f5-4d6e-b2d4-73fd4b5622a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2021 | T16182-VK02-P0UZT-172704 | 2017-05-30 | DHI-TRANSMIT-000114 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fe1ec06-700e-4c83-bc72-4ef6a51f9fef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2022 | T16182-VK02-P0UZT-172713 | 2017-05-30 | DHI-TRANSMIT-000114 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b325e48f-76dc-4a6f-97fe-f6833cc3aa0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2023 | T16182-XB02-P0UZT-172716 | 2017-05-30 | DHI-TRANSMIT-000114 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50edecf6-abe3-4b81-8c54-08c9880e3fb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2024 | T16182-YF00-P0CJA-161041 | 2017-05-30 | DHI-WTRAN-000207 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46bee064-5efd-49af-b5ea-2be83053e340 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2025 | T16182-YL01-P0PCA-126527 | 2017-05-30 | DHI-WTRAN-000206 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c58dc477-a6c0-44da-b02a-fc3cce21dea3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2026 | T16182-YE03-P0BAU-152523 | 2017-05-30 | DHI-WTRAN-000205 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b809cb35-f9d2-4a01-8b07-4a3bd4f5c9f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2027 | T16182-XS00-P0PCA-126501 | 2017-05-30 | DHI-WTRAN-000203 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98ac8959-ead8-4f0b-84f1-33e355f52ec2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2028 | T16182-YU02-P0SCA-127510 | 2017-05-30 | DHI-WTRAN-000204 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c929c63-0eeb-4fbd-ad71-a3f72543ed08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2029 | T16182-YV02-P0SCA-127511 | 2017-05-30 | DHI-WTRAN-000204 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e92aff8c-88bf-4842-8f97-08c553edb5db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2030 | T16182-CA02-P0UBA-181359 | 2017-05-30 | DHI-TRANSMIT-000113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd03a08b-e9f9-4dee-9a17-725b437efb78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2031 | T16182-CA01-P0UBA-181355 | 2017-05-30 | DHI-TRANSMIT-000113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8986e0d-3056-4453-94b4-bd350dcaa532 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2032 | T16182-CA01-P0UBA-181356 | 2017-05-30 | DHI-TRANSMIT-000113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=857ad3e2-d0d7-45fc-a4e9-a07294ca8064 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2033 | T16182-CA00-P0UBA-181307 | 2017-05-30 | DHI-WTRAN-000202 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72ff3722-77bb-4627-92ca-24b8ca4cf259 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2034 | T16182-CA02-P0UBA-181360 | 2017-05-30 | DHI-WTRAN-000202 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7becf6c-1c44-468d-af18-761729bc5902 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2035 | T16182-CV03-P0ZEN-163103 | 2017-05-31 | DHI-WTRAN-000212 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb10d645-954e-4c79-8d10-1393604de32a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2036 | T16182-CV03-P0ZEN-163104 | 2017-05-31 | DHI-WTRAN-000212 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f84db7b0-5c4a-4998-a324-20a8d4fd5334 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2037 | T16182-CV03-P0ZEN-163102 | 2017-05-31 | DHI-WTRAN-000211 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f5a5d70-2b22-4d48-90d5-4af249c5c114 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2038 | T16182-YF00-P0CJD-161021 | 2017-05-31 | DHI-WTRAN-000210 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea73d1da-4849-4373-a4a2-16d66c7ef9ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2039 | T16182-YF00-P0CJD-161022 | 2017-05-31 | DHI-WTRAN-000210 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59c723c0-0611-41aa-beee-84cc6d189f38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2040 | T16182-YF00-P0CJD-161025 | 2017-05-31 | DHI-WTRAN-000210 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=144e23be-76e6-4ce9-a1d1-d79515d2210b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2041 | T16182-XG02-P0GM-120008 | 2017-05-31 | DHI-WTRAN-000209 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=301a2f31-b638-4fb8-8c5e-960bca832525 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2042 | T16182-XS00-P0GM-120022 | 2017-05-31 | DHI-WTRAN-000209 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd1df3b8-bd5f-4fb3-a8f6-b3dd4f3b7875 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2043 | T16182-XS00-P0GM-120023 | 2017-05-31 | DHI-WTRAN-000209 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fedcd3db-2605-4005-9500-9fa79887722e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2044 | T16182-VK02-P0ULC-171309 | 2017-05-31 | DHI-WTRAN-000208 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41ff1143-cc76-405e-a52e-ed35f0cb3ea2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2045 | T16182-XG02-P8ZEN-125582 | 2017-05-31 | DHI-TRANSMIT-000137 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f03a742-e6d2-4b4a-be92-3a776b120ba8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2046 | T16182-XG02-P8ZEN-125583 | 2017-05-31 | DHI-TRANSMIT-000137 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be6a5335-0a2f-4ed1-8547-524ec255a5cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2047 | T16182-XG02-P8ZEN-125584 | 2017-05-31 | DHI-TRANSMIT-000137 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=760da67a-4294-4807-9dd5-1cd6c8ce27d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2048 | T16182-XG02-P8ZEN-125585 | 2017-05-31 | DHI-TRANSMIT-000137 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1421afc1-a960-4664-8192-563db3ebc390 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2049 | T16182-XG02-P8ZEN-125586 | 2017-05-31 | DHI-WTRAN-000213 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1412c82a-2a2f-44ed-b54c-f5e4e346a972 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2050 | T16182-XG02-P8ZEN-125587 | 2017-05-31 | DHI-TRANSMIT-000137 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8b27b05-1146-4c97-befa-c92fb09dc42e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2051 | T16182-XG02-P8ZEN-125588 | 2017-05-31 | DHI-TRANSMIT-000137 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a4f7404-8421-4bd5-9a38-333ff8b5ae81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2052 | T16182-XG02-P8ZEN-125589 | 2017-05-31 | DHI-TRANSMIT-000137 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fcaa6bf-fb87-49e0-bc40-e0e8180835a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2053 | T16182-XG02-P8ZEN-125590 | 2017-05-31 | DHI-WTRAN-000213 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2841166-432c-48a5-b320-812e339a9d03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2058 | T16182-VE04-P8UTH-172011 | 2017-05-31 | DHI-TRANSMIT-000138 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57c0488a-6c84-4832-86bc-ca8af9a6a73b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2059 | T16182-XB02-P8UTH-172012 | 2017-05-31 | DHI-TRANSMIT-000138 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60783333-a5bf-40bc-9484-3af522356b6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2060 | T16182-XB02-P8UTH-172013 | 2017-05-31 | DHI-TRANSMIT-000138 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ad7c43d-7e3f-4342-8298-743b5da5fae0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2061 | T16182-CA05-P0UMA-180481 | 2017-05-31 | DHI-TRANSMIT-000136 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00ca244c-0caa-4620-93d3-f2988f60b1e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2062 | T16182-YK08-P0PGB-420010 | 2017-05-31 | DHI-WTRAN-000214 | IFR | B | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fcc37f3-eb0e-457f-b30d-520f6a3067db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2063 | T16182-YK08-P0PGB-420020 | 2017-05-31 | DHI-WTRAN-000214 | IFR | B | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4aafcaf2-5428-41aa-bdd2-9016f9e2126c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2064 | T16182-CA05-P0UMA-180482 | 2017-05-31 | DHI-TRANSMIT-000136 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daa69d6a-f0d1-4093-a78d-5ca211795568 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1980 | T16182-YD16-P0ZEN-152003 | 2017-06-01 | DHI-TRANSMIT-000139 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74fb1ae6-aad2-4247-9dc9-90d52a765c6a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1981 | T16182-YE00-P0ZEN-152750 | 2017-06-01 | DHI-WTRAN-000215 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beda94c4-9ca3-4ea2-8554-c07fb4638558 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1982 | T16182-YE00-P0ZEN-152751 | 2017-06-01 | DHI-WTRAN-000215 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5af5dca2-a636-411c-960d-2c68dd0cc9a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1983 | T16182-YE00-P0ZEN-152752 | 2017-06-01 | DHI-WTRAN-000215 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12e50e26-237e-4112-b3cb-b08c454769de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1984 | T16182-YE00-P0ZEN-152753 | 2017-06-01 | DHI-WTRAN-000215 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47d12d08-d424-4973-b8b6-758c79b34e10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1985 | T16182-YE00-P0ZEN-152754 | 2017-06-01 | DHI-WTRAN-000215 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=399785b7-db8f-4c89-aca6-1d067d95deb0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1986 | T16182-YE00-P0ZEN-152755 | 2017-06-01 | DHI-WTRAN-000216 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=249f73a7-1bc8-4ae1-a324-123ca1b5de16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1987 | T16182-YE00-P0ZEN-152756 | 2017-06-01 | DHI-WTRAN-000216 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50a6aceb-5f14-4a8b-90d2-f72559de6590 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1988 | T16182-YE00-P0ZEN-152757 | 2017-06-01 | DHI-WTRAN-000216 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c515f7d3-3faf-4a3b-97f9-7e9e67cc0df6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1989 | T16182-YE00-P0ZEN-152758 | 2017-06-01 | DHI-WTRAN-000216 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34f2448f-298e-4198-a37e-be87dc0e007f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1990 | T16182-YE00-P0ZEN-152759 | 2017-06-01 | DHI-WTRAN-000217 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2a619f9-e91f-410e-ba15-509142e36133 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1991 | T16182-YE00-P0ZEN-152760 | 2017-06-01 | DHI-WTRAN-000218 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87cb633a-27dc-4a8c-a0ef-cf886228f1c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1992 | T16182-YE00-P0ZEN-152761 | 2017-06-01 | DHI-WTRAN-000218 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ddcf7dd-a22a-4c5f-8991-86668923e637 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1993 | T16182-YE00-P0ZEN-152762 | 2017-06-01 | DHI-WTRAN-000218 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fed0845-66a4-4d41-89a6-920a3dafebff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1994 | T16182-YE00-P0ZEN-152763 | 2017-06-01 | DHI-WTRAN-000218 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4125b9c7-b5a1-4248-8c37-7c4dae9b7f11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1995 | T16182-YE00-P0ZEN-152764 | 2017-06-01 | DHI-WTRAN-000218 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90add459-7685-45ed-8cdd-2aed713a7061 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1996 | T16182-YE00-P0ZEN-152765 | 2017-06-01 | DHI-WTRAN-000219 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1997 | T16182-YE00-P0ZEN-152766 | 2017-06-01 | DHI-WTRAN-000219 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d2a50aa-a91d-4c8f-b1f2-375ca9f42db9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1998 | T16182-YE00-P0ZEN-152767 | 2017-06-01 | DHI-WTRAN-000219 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e656bc0-476a-4d86-b5b6-f6e544137f26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1999 | T16182-YE00-P0ZEN-152768 | 2017-06-01 | DHI-WTRAN-000219 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b30de067-9a79-49f4-9462-976c006f4b7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2000 | T16182-YE00-P0ZEN-152769 | 2017-06-01 | DHI-WTRAN-000220 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7b73786-7515-43d6-a7ce-d0e1a48bf6a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2001 | T16182-YE00-P0ZEN-152770 | 2017-06-01 | DHI-WTRAN-000220 | IFI | 1 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=904d90ee-4b72-4b0f-a848-ccf2dd2bb202 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2002 | T16182-YE00-P0ZEN-152771 | 2017-06-01 | DHI-WTRAN-000220 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2057 | T16182-CV03-P0CRN-161103 | 2017-06-01 | DHI-WTRAN-000223 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5edaec54-794b-4a55-89e5-be146d7c65c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2065 | T16182-VK02-P8UTH-172008 | 2017-06-01 | DHI-WTRAN-000225 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13fce414-2865-43c9-86f5-133499c2386b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2066 | T16182-XB02-P8UTH-172007 | 2017-06-01 | DHI-WTRAN-000225 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=553263ea-de29-49ad-990d-b25974477950 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2067 | T16182-XG02-P6MAA-220025 | 2017-06-01 | DHI-WTRAN-000224 | IFR | A | DR | TRUE | TRUE | 2017-08-07_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85024b50-144a-441e-961d-88aeabd89137 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2068 | T16182-XG02-P6MAA-220029 | 2017-06-01 | DHI-WTRAN-000224 | IFR | A | DR | TRUE | TRUE | 2017-08-07_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=483d0e5c-2049-4026-8e1e-605d3fee285a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2069 | T16182-XG02-P6MAA-220027 | 2017-06-01 | DHI-WTRAN-000224 | IFR | A | DR | TRUE | TRUE | 2017-08-07_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=147d2df8-3dd3-4f66-b72e-58a924ea5b5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2070 | T16182-XM00-P0MAA-220015 | 2017-06-01 | DHI-WTRAN-000224 | IFI | 0 | DR | TRUE | TRUE | 2017-08-07_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung 2017-10-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cef70f08-1b9f-4162-86da-12e6a88db343 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2071 | T16182-CA00-P0UTF-182803 | 2017-06-01 | DHI-WTRAN-000222 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d09e06a7-dea7-44c0-be53-799312685e32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2072 | T16182-CA00-P0UTF-182804 | 2017-06-01 | DHI-WTRAN-000222 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ab0a818-7e32-41a8-ada6-3ac022b262ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2073 | T16182-CA01-P0UTF-182852 | 2017-06-01 | DHI-WTRAN-000222 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a3ced53-e21b-4098-972c-5337c1af40d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2074 | T16182-CA06-P0UTF-182800 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94e2c9c5-2da7-4ee3-889d-ee64d047bc3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2075 | T16182-CA00-P0UTF-182801 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c73f84e-0e3c-41fc-884c-a2aa9e5094cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2076 | T16182-CA00-P0UTF-182802 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11687368-0379-4c11-97a4-8fbc1b6ec68f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2077 | T16182-CA01-P0UTF-182851 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ef0bd7f-d13b-46fb-bb63-7688a5d79b85 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2078 | T16182-CA01-P0UTF-182853 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=066aacd8-24b5-467a-8287-19c1fe496b39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2079 | T16182-CA01-P0UTF-182854 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b703da7f-0058-4727-a90c-c1d2160a104c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2080 | T16182-CA01-P0UTF-182855 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9d977a1-8248-4646-bcd8-10c70163b308 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2081 | T16182-CA01-P0UTF-182856 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1df0e877-b805-411b-b60d-c4cb5fa6930e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2082 | T16182-CA02-P0UTF-182857 | 2017-06-01 | DHI-TRANSMIT-000141 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6af23bee-6a62-4695-a9c4-774fdf55510c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2083 | T16182-DP00-P0ZEN-020005 | 2017-06-01 | DHI-WTRAN-000221 | IFI | 1 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c15db39-1bd0-4dfe-9a11-51370bf51247 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2084 | T16182-XS00-P0LB-122037 | 2017-06-02 | DHI-TRANSMIT-000144 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e94ecb90-4296-4113-abb3-125d5ae90e33 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2085 | T16182-XS00-P0EKG-120019 | 2017-06-02 | DHI-WTRAN-000234 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96428848-7243-4e1a-9474-13d060f61027 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2086 | T16182-YL06-P0MBA-121016 | 2017-06-02 | DHI-WTRAN-000233 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2087 | T16182-CA05-P0UGD-181982 | 2017-06-02 | DHI-TRANSMIT-000143 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=935c89a3-4845-4cd1-91eb-97d217146291 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2088 | T16182-CA05-P0UGD-181986 | 2017-06-02 | DHI-TRANSMIT-000143 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03656b04-51cb-49a9-9c60-ea10931cdd27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2089 | T16182-CA05-P0UGD-181984 | 2017-06-02 | DHI-TRANSMIT-000143 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e70f44c-3765-4467-ba72-09bc510022fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2090 | T16182-CA05-P0UGD-181983 | 2017-06-02 | DHI-TRANSMIT-000143 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8548cfa6-e706-4afe-93ab-84e8094fc3fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2091 | T16182-YE03-P0BAU-152524 | 2017-06-02 | DHI-WTRAN-000232 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3cfd4495-1366-4558-8a27-79f47ddc17d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2092 | T16182-CA00-P0UCB-180609 | 2017-06-02 | DHI-TRANSMIT-000142 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fc5eccf-adc2-40e2-8e7e-3b7aae6e174c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2093 | T16182-CA00-P0UCB-180611 | 2017-06-02 | DHI-TRANSMIT-000142 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d22f55cd-b579-4456-8cef-28e0af9e04a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2094 | T16182-CA00-P0UCB-180610 | 2017-06-02 | DHI-TRANSMIT-000142 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85216949-e2e1-48e6-b397-c27ec367309b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2095 | T16182-YE00-P0ZEN-152721 | 2017-06-02 | DHI-WTRAN-000231 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ab07d8a-1551-4f17-86a8-c46026410b75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2096 | T16182-CA00-P0UBA-181306 | 2017-06-02 | DHI-WTRAN-000230 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd596ce1-94e8-4922-9ced-9b63e6b2370d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2097 | T16182-YD00-P0MKW-260001 | 2017-06-02 | DHI-WTRAN-000229 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cada8ef-5f43-4cfe-b71d-5ad3cebad2c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2098 | T16182-YD00-P0MKW-260002 | 2017-06-02 | DHI-WTRAN-000229 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff36dcd9-c2df-4572-bae3-40a55b7fb9c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2099 | T16182-YF00-P0MKY-290007 | 2017-06-02 | DHI-WTRAN-000228 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80866b96-0224-4e4f-b6ca-4c1a44c1ae78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2100 | T16182-YS01-P0MKY-290008 | 2017-06-02 | DHI-WTRAN-000228 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=feaf581f-7d71-46f5-9725-8934a970df66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2101 | T16182-YS01-P0MKY-290009 | 2017-06-02 | DHI-WTRAN-000228 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3828eb8-72fc-4f2e-a640-3ecdc3878456 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2102 | T16182-YD00-P0UBA-150508 | 2017-06-02 | DHI-WTRAN-000227 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=491832ae-ca69-4a45-a19f-ea2502d0fef0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2103 | T16182-CA00-P0UCB-180612 | 2017-06-02 | DHI-WTRAN-000226 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b1d13f5-a2f0-4354-875d-fba52be46894 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2104 | T16182-CA00-P0UCB-180613 | 2017-06-02 | DHI-WTRAN-000226 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e186daa4-be4f-46f2-bf88-7b93c505064c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2105 | T16182-CA00-P0UCB-180614 | 2017-06-02 | DHI-WTRAN-000226 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c46da681-32d6-4f4f-b590-a7c9964c0402 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2108 | T16182-BP00-P0LBG-140016 | 2017-06-05 | DHI-WTRAN-000241 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3579a470-6178-4cf2-8bd2-d87e8a105cba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2109 | T16182-YD00-P0BAA-150766 | 2017-06-05 | DHI-WTRAN-000240 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1abf455e-fafc-4fcf-b045-d1d13e735164 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2110 | T16182-YD00-P0MAG-123001 | 2017-06-05 | DHI-WTRAN-000239 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f1aa51c-57b9-46a8-a732-e5abe1b5cecf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2111 | T16182-XS00-P8QHA-125002 | 2017-06-05 | DHI-WTRAN-000238 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42446110-b0fc-4ea3-88d0-52b4b4aaeb4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2112 | T16182-CA06-P0UMA-180492 | 2017-06-05 | DHI-WTRAN-000237 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36173661-cff6-4a0c-b47f-d911077a1af9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2113 | T16182-XL00-P0MAG-123021 | 2017-06-05 | DHI-WTRAN-000236 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd11962f-c198-412a-a0b4-b9b097379bf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2114 | T16182-CA00-P0UBA-181104 | 2017-06-05 | DHI-WTRAN-000242 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=617bc9fb-f59f-4b07-a992-2363a66f5b42 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2115 | T16182-CA01-P0UBA-181153 | 2017-06-05 | DHI-WTRAN-000242 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1646c846-214d-4465-9af9-85e6d6bc89c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2116 | T16182-CA01-P0UBA-181154 | 2017-06-05 | DHI-WTRAN-000242 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54f3f9a4-6568-461d-9dd6-8d4438118c53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2117 | T16182-CA06-P0UBA-181100 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75e8806d-e254-4016-b1da-24f8637d75ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2118 | T16182-CA00-P0UBA-181101 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=302a2d50-6e64-4f5e-b231-076c9220436f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2119 | T16182-CA00-P0UBA-181102 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0fef67c-d60d-4094-ba0b-336037705f43 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2120 | T16182-CA00-P0UBA-181103 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=159260ee-e088-40e0-ade6-75f635286058 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2121 | T16182-CA00-P0UBA-181105 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71c57719-e0a9-49bb-ad44-b55ba93a8091 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2122 | T16182-CA01-P0UBA-181151 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29b2797b-04a5-4d48-b350-44b0f75e4497 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2123 | T16182-CA01-P0UBA-181152 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fdc9fb5-b9dd-439a-ba52-69ecd67014d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2124 | T16182-CA02-P0UBA-181155 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b8533d9-252b-4d28-92e4-144a950b42fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2125 | T16182-CA02-P0UBA-181156 | 2017-06-05 | DHI-TRANSMIT-000145 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4db318b1-0741-4e55-83ed-38d0b37b137e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2126 | T16182-XS00-P0EKG-120020 | 2017-06-05 | DHI-WTRAN-000244 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b45d11c5-42c2-40d0-bd85-eaf24e1a5f46 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2127 | T16182-YU02-P0CYA-154012 | 2017-06-05 | DHI-WTRAN-000243 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2128 | T16182-YQ03-P0CY-154021 | 2017-06-05 | DHI-TRANSMIT-000150 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6343f3e9-42e0-499c-bc1f-5ac76b9b62cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2129 | T16182-YU02-P0CYA-154011 | 2017-06-05 | DHI-TRANSMIT-000150 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b03978e-ab59-457b-b9a7-f30ba0a1641f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2130 | T16182-YU02-P0CYM-154013 | 2017-06-05 | DHI-TRANSMIT-000150 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82df1b37-b910-4321-b122-e18f62500307 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2131 | T16182-XG02-P0SCA-120004 | 2017-06-05 | DHI-TRANSMIT-000149 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c71c4502-587e-4567-b63d-8faa8f567b8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2132 | T16182-XW03-P0MJ-110053 | 2017-06-05 | DHI-TRANSMIT-000148 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=270a1148-ca20-4278-a6c1-f793241bb991 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2133 | T16182-CA06-P0UMA-180491 | 2017-06-05 | DHI-TRANSMIT-000147 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c95e479-5974-4f78-83d4-c4803e46fe05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2134 | T16182-CA06-P0USG-182700 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b231046-9849-4f6f-89d6-af41075a0899 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2135 | T16182-CA00-P0USG-182701 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48a901d4-ada0-41c4-b02f-8ca20f4f0594 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2136 | T16182-CA00-P0USG-182702 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=240b09c2-3e66-41f6-b80f-1829f1e0578c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2137 | T16182-CA00-P0USG-182703 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a613a3ef-a026-4eed-a9d8-fc318b4e1e79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2138 | T16182-CA00-P0USG-182704 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c59cae5d-6b94-49ba-baf2-be093964bfd1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2139 | T16182-CA01-P0USG-182751 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d7c472a-813e-4717-8598-ccf5f4dd69ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2140 | T16182-CA01-P0USG-182752 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da511cca-73e5-468f-8c38-faeff8c6c9be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2141 | T16182-CA01-P0USG-182753 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ebcb0ca-9839-41f2-bc20-0f99c4cb753a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2142 | T16182-CA02-P0USG-182754 | 2017-06-05 | DHI-TRANSMIT-000146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95d1cabe-2ac8-4537-a002-1d936a44b282 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2143 | T16182-CA05-P0UGD-181981 | 2017-06-05 | DHI-TRANSMIT-000151 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d552490-0b48-4b20-8ff3-5e51a67308b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2144 | T16182-CA05-P0UGD-181985 | 2017-06-05 | DHI-TRANSMIT-000151 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29f34169-6f50-4ae0-b4c2-75b4a92b2131 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2145 | T16182-CC08-P8ZEN-125620 | 2017-06-05 | DHI-WTRAN-000245 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92097c0f-62b0-497c-b9c7-e610013151b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2146 | T16182-YD00-P0CYE-137741 | 2017-06-05 | DHI-WTRAN-000246 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4931160d-566c-4267-95c6-c29c6392b2a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2147 | T16182-YU02-P0CYE-137742 | 2017-06-05 | DHI-WTRAN-000246 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e715b81-eb5f-4200-adb6-48615ba550d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2148 | T16182-YK00-P0LB-122072 | 2017-06-05 | DHI-WTRAN-000247 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=539c34f7-3a60-44e9-9f68-e2cca4e95ddc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2149 | T16182-YF00-P0CBA-161213 | 2017-06-05 | DHI-WTRAN-000248 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b580240-577c-4ef3-8195-965c14e506b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2150 | T16182-YF00-P0CBA-161216 | 2017-06-05 | DHI-WTRAN-000248 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70f102be-9caf-48ef-abc6-d416929cc756 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2151 | T16182-YL00-P0PCA-126523 | 2017-06-05 | DHI-WTRAN-000250 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9e246e9-4862-41d1-b4c0-285b474f0a0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2152 | T16182-YL01-P0PCA-126524 | 2017-06-05 | DHI-WTRAN-000250 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96050d22-a9b9-4669-811b-3ddd282a1961 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2153 | T16182-XG02-P0PCA-126502 | 2017-06-05 | DHI-WTRAN-000249 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4de283d1-2595-44f8-9613-4c14244e6e57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2154 | T16182-XS00-P0PCA-126504 | 2017-06-05 | DHI-WTRAN-000249 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c708ead8-29d3-4427-a52d-62a8acf019e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2155 | T16182-YF00-P0CBA-161210 | 2017-06-07 | DHI-WTRAN-000251 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2156 | T16182-YF00-P0CBA-161211 | 2017-06-07 | DHI-WTRAN-000251 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2157 | T16182-YF00-P0CBA-161212 | 2017-06-07 | DHI-WTRAN-000251 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2158 | T16182-YF00-P0CBA-161214 | 2017-06-07 | DHI-WTRAN-000251 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2159 | T16182-YF00-P0CGA-161311 | 2017-06-07 | DHI-WTRAN-000252 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2160 | T16182-YF00-P0CGA-161312 | 2017-06-07 | DHI-WTRAN-000252 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2161 | T16182-YF00-P0CGA-161313 | 2017-06-07 | DHI-WTRAN-000252 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2162 | T16182-YF00-P0CGA-161316 | 2017-06-07 | DHI-WTRAN-000252 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2163 | T16182-YF00-P0CBA-161202 | 2017-06-07 | DHI-WTRAN-000253 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2164 | T16182-YF00-P0CBA-161203 | 2017-06-07 | DHI-WTRAN-000253 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2165 | T16182-YF00-P0CGA-161302 | 2017-06-07 | DHI-WTRAN-000254 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2166 | T16182-YF00-P0CGA-161303 | 2017-06-07 | DHI-WTRAN-000254 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2167 | T16182-CA02-P0USG-182755 | 2017-06-07 | DHI-TRANSMIT-000164 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d097b675-6fa7-4747-b197-890cc9304cdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2168 | T16182-XS00-P0MBA-121011 | 2017-06-07 | DHI-TRANSMIT-000165 | IFC | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24ea9821-0bcf-40f7-b947-a3a3ed44f1f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2169 | T16182-CC05-P0ZEN-180044 | 2017-06-07 | DHI-WTRAN-000255 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=868fe880-4cfe-4d0c-a576-57be27596eec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2170 | T16182-DP00-P0ZEN-020004 | 2017-06-07 | DHI-WTRAN-000256 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=335aa938-8665-47d0-995f-b32014b84b7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2171 | T16182-CV03-P0PUR-411021 | 2017-06-08 | DHI-TRANSMIT-000184 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ad6be48-d26f-4d04-8ff2-d865502c55d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2172 | T16182-CV03-P0PUR-411011 | 2017-06-08 | DHI-TRANSMIT-000184 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e5649c4-89b5-45c1-9c36-007f6bf2e0ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2173 | T16182-CV03-P0PUR-411001 | 2017-06-08 | DHI-TRANSMIT-000184 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03abeb06-fa46-4a7a-a83d-d3ded61f5a17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2174 | T16182-CV03-P0PUR-411031 | 2017-06-08 | DHI-TRANSMIT-000184 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f12b8187-37ad-4d2a-9fd6-271fb41730f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2175 | T16182-CA02-P0UBA-181360 | 2017-06-08 | DHI-TRANSMIT-000183 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a298703-fade-4e50-b1af-e1b8ab552692 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2176 | T16182-CA00-P0UBA-181307 | 2017-06-08 | DHI-TRANSMIT-000183 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=553648c3-4d03-4c54-aa7e-dfcc62bcbe94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2177 | T16182-XG02-P0SGK-138702 | 2017-06-08 | DHI-WTRAN-000259 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc79b368-34ad-4906-8c20-87956659332e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2178 | T16182-XH01-P0SGK-138712 | 2017-06-08 | DHI-WTRAN-000259 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd6f2742-2682-422a-8424-b37694804bb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2179 | T16182-YD00-P0SGZ-138731 | 2017-06-08 | DHI-WTRAN-000259 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4255c887-dc82-4838-8462-d0fff6ed61f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2180 | T16182-YT10-P0SGK-138722 | 2017-06-08 | DHI-WTRAN-000259 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a80ffb1-7f84-4a29-8609-5f7a47d56982 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2181 | T16182-YD00-P0CYE-138741 | 2017-06-08 | DHI-WTRAN-000258 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2c5c684-0f66-4695-a4c7-54d45c3fa1b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2182 | T16182-YU02-P0CYE-138742 | 2017-06-08 | DHI-WTRAN-000258 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9af2c955-4155-492b-baf7-8cd382cb3f0e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2183 | T16182-YD00-P0MKW-260011 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2621490f-dfe5-42f6-b62b-d88f2ad3b43d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2184 | T16182-YD00-P0MKW-260012 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad82027e-4cd3-4d87-8fcf-7b2d37575698 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2185 | T16182-YD00-P0MKW-260013 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f56fd2b8-91e2-4e5a-b333-4d054f3ccdc7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2186 | T16182-YD00-P0MKG-260014 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61b0b25f-6260-4dbb-9dc4-fdc28827cd50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2187 | T16182-YD00-P0MKG-260015 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=010ab876-e250-4379-b3f1-41f781a9e8b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2188 | T16182-YD00-P0MKG-260016 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d33eb498-10f8-4ac3-908b-16062cc19f35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2189 | T16182-YD00-P0MKG-260017 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd2c9529-05f4-489b-aca3-7112cd3ea6da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2190 | T16182-YD00-P0MKG-260018 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67b14575-32c5-4ef9-88c2-e08d1fa49939 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2191 | T16182-YT01-P0MKA-260019 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=801b2f35-583d-4a52-aee0-257398be8f07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2192 | T16182-YV02-P0MKW-260021 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=266eac40-40a7-4694-8866-fc5953bc8658 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2193 | T16182-YV02-P0MKG-260022 | 2017-06-08 | DHI-WTRAN-000257 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=038e14d5-0951-4859-b397-5886270535bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2194 | T16182-YD00-P0SGZ-137331 | 2017-06-08 | DHI-TRANSMIT-000201 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a651373-dc83-482b-8f02-284709c0b0e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2195 | T16182-XG02-P0SGE-137303 | 2017-06-08 | DHI-TRANSMIT-000201 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beb24817-e827-4d5b-bbae-af0f4adc9b44 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2196 | T16182-CA00-P0UYC-182901 | 2017-06-08 | DHI-WTRAN-000263 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f75fa475-aab4-47aa-99da-e0dd4eec9db5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2197 | T16182-CA00-P0UYC-182902 | 2017-06-08 | DHI-WTRAN-000263 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=903b16f0-340d-41fa-b513-81248daf6aed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2198 | T16182-CA00-P0UYC-182903 | 2017-06-08 | DHI-WTRAN-000263 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=008ad7f6-9b6f-4c49-a77f-feffd3fb5dfb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2199 | T16182-CA00-P0UYC-182904 | 2017-06-08 | DHI-WTRAN-000263 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e838e086-e0ab-4b47-9719-9632e966c650 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2200 | T16182-CA00-P0UYC-182905 | 2017-06-08 | DHI-WTRAN-000263 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31e069ed-c575-44ce-9bf5-2ad293105817 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2201 | T16182-CA00-P0UYC-182906 | 2017-06-08 | DHI-WTRAN-000263 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df05d784-32ce-4691-bfd7-a941db4712ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2202 | T16182-XG01-P0EKG-124001 | 2017-06-08 | DHI-TRANSMIT-000200 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15009b27-70cd-4ede-84d9-ae2a8cfad814 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2203 | T16182-YK00-P0ZEN-165302 | 2017-06-08 | DHI-TRANSMIT-000199 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5cc53b4-7ff3-4cc8-9ad3-1353a0255b5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2204 | T16182-XG02-P0SGK-138802 | 2017-06-08 | DHI-WTRAN-000262 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb1e14d9-3c3c-4ff4-9bd8-ad6c549e45e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2205 | T16182-XH01-P0SGK-138812 | 2017-06-08 | DHI-WTRAN-000262 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08d52e9e-d65f-4ea2-8cba-2dd6d2bf1836 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2206 | T16182-YD00-P0SGZ-138831 | 2017-06-08 | DHI-WTRAN-000262 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=690cf9b0-bb8b-4941-b2d5-678ae70a59f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2207 | T16182-YT10-P0SGK-138822 | 2017-06-08 | DHI-WTRAN-000262 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e18c4fc0-f8a2-4b51-8bbf-d08c7277bc7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2208 | T16182-YD00-P0CYE-138841 | 2017-06-08 | DHI-WTRAN-000261 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a30e513-0edf-40ae-814f-758940e23dad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2209 | T16182-YU02-P0CYE-138842 | 2017-06-08 | DHI-WTRAN-000261 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a42aa6d8-3bf4-4bb8-961f-067f17d13976 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2210 | T16182-CA00-P0UYP-183201 | 2017-06-08 | DHI-WTRAN-000260 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1122143d-a265-4ab5-9085-02becf56fdc1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2211 | T16182-CA00-P0UYP-183202 | 2017-06-08 | DHI-WTRAN-000260 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e9861f9-6151-4eef-a23b-9585c24dfb7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2212 | T16182-CA00-P0UYP-183203 | 2017-06-08 | DHI-WTRAN-000260 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86e71277-8f33-4121-9a9b-7ddccabe1ddc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2213 | T16182-CA00-P0UYP-183204 | 2017-06-08 | DHI-WTRAN-000260 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7103cad-cef5-496e-af17-8fc8a3e6a4d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
1800 | T16182-YD00-P0BB-150821 | 2017-06-09 | DHI-WTRAN-000264 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2214 | T16182-YM01-P0GHC-129008 | 2017-06-09 | DHI-WTRAN-000265 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0edccb67-1262-4202-b426-398e2e1f9e9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2215 | T16182-YM01-P0GHC-129035 | 2017-06-09 | DHI-WTRAN-000265 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7b5cb41-325d-45d9-a094-9aead2e3a60f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2216 | T16182-YD00-P0BAT-150621 | 2017-06-09 | DHI-WTRAN-000266 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=475cff12-2262-467b-8a1d-f3e30de6186e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2217 | T16182-YD00-P0BAT-150626 | 2017-06-09 | DHI-WTRAN-000266 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=062546f7-7167-437c-94af-c91534ef253c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2218 | T16182-YF00-P0BA-150401 | 2017-06-09 | DHI-WTRAN-000267 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=202ae421-535c-4462-bdf4-b7f2f5e9dab7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2219 | T16182-YF00-P0BA-150404 | 2017-06-09 | DHI-WTRAN-000267 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f242292-d4a4-456e-91fe-9e1e931d115c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2220 | T16182-YF00-P0BB-150402 | 2017-06-09 | DHI-WTRAN-000268 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b861ea9-7de9-4f7a-b1da-1e10b80ec9c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2221 | T16182-YU02-P0CYE-136607 | 2017-06-09 | DHI-TRANSMIT-000213 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e65a08-5742-4e56-b8ec-18c1f09bd877 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2222 | T16182-XW03-P0SCA-120017 | 2017-06-09 | DHI-TRANSMIT-000215 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44646452-6a1a-4938-a3d3-542b832cf393 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2223 | T16182-YU03-P0CYE-136606 | 2017-06-09 | DHI-TRANSMIT-000214 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdb9176f-e84c-412e-8979-c35ae6f94094 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2224 | T16182-YT01-P0MAG-123014 | 2017-06-12 | DHI-WTRAN-000271 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f435ea21-3858-4ce6-89e8-895369eef515 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2225 | T16182-YK08-P0MBA-121009 | 2017-06-12 | DHI-WTRAN-000272 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95caf54a-acab-4be4-a655-a6fd03bbc33b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2226 | T16182-VE04-P0ULX-171221 | 2017-06-12 | DHI-WTRAN-000273 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df552e4e-38c5-4653-bf76-59584bf568ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2227 | T16182-XB02-P0ULX-171222 | 2017-06-12 | DHI-WTRAN-000273 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41c6827d-10e8-410f-bf4c-3dd5e684ca15 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2228 | T16182-XB02-P0ULX-171223 | 2017-06-12 | DHI-WTRAN-000273 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a951e78e-6067-42b7-96a6-7e4bb722ce4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2229 | T16182-XS00-P0MAG-123003 | 2017-06-12 | DHI-WTRAN-000274 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e24e7778-accf-498a-908a-b473e5f58635 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2230 | T16182-YS01-P0MKY-290012 | 2017-06-12 | DHI-WTRAN-000275 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c7ab2e2-c90e-460b-a67d-3ec6046ab35d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2231 | T16182-YS01-P0MKY-290013 | 2017-06-12 | DHI-WTRAN-000275 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91f78616-ad8c-4f1c-9e12-fb5d894336b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2232 | T16182-YU02-P0CYE-137242 | 2017-06-12 | DHI-WTRAN-000276 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ebb4c8b-85a6-4009-a6e3-d645cd915f80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2233 | T16182-YD00-P0CYE-137241 | 2017-06-12 | DHI-WTRAN-000276 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23a97528-145a-45da-838e-3a77192619c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2234 | T16182-YU02-P0CYE-139942 | 2017-06-12 | DHI-WTRAN-000277 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0659524-63ad-48df-8ff0-f21e790ae523 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2235 | T16182-YD00-P0CYE-139941 | 2017-06-12 | DHI-WTRAN-000277 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb75eae8-bd17-428c-b5ba-6b2b116da3f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2236 | T16182-YU02-P0CYE-136942 | 2017-06-12 | DHI-WTRAN-000278 | IFR | A | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62c9066d-0f97-46dc-84b9-3267feb1dd5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2237 | T16182-YD00-P0CYE-136941 | 2017-06-12 | DHI-WTRAN-000278 | IFI | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef26ae6c-bbb0-4dee-9493-1bc2e948e384 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2238 | T16182-YD00-P0SGZ-136931 | 2017-06-12 | DHI-WTRAN-000279 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=823945f7-37e9-4430-94dc-76f21d195635 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2239 | T16182-YT10-P0SGE-136922 | 2017-06-12 | DHI-WTRAN-000279 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2f63bc2-98ac-4be9-bc65-cf86bb4a95c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2240 | T16182-XG02-P0SGA-136901 | 2017-06-12 | DHI-WTRAN-000279 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8159faf-1874-4b2a-9a59-0823ba26a27d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2241 | T16182-XG02-P0SGE-136902 | 2017-06-12 | DHI-WTRAN-000279 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bc1b69b-4172-4a08-8182-263d61885f26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2242 | T16182-XH01-P0SGA-136911 | 2017-06-12 | DHI-WTRAN-000279 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03dcec57-61f7-426d-9ee7-e48fd42ac6cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2243 | T16182-XH01-P0SGE-136912 | 2017-06-12 | DHI-WTRAN-000279 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2244 | T16182-CY03-P0MKG-260032 | 2017-06-12 | DHI-WTRAN-000280 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1617a1b-dc38-46e4-80f0-271bea60d2be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2245 | T16182-CY03-P0MKW-260031 | 2017-06-12 | DHI-WTRAN-000280 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e86957e-89d9-48eb-ac50-d5111ed7b758 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2246 | T16182-XL00-P0MKA-260035 | 2017-06-12 | DHI-WTRAN-000280 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad171a06-d36d-4794-a0ee-bdf982df748f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2247 | T16182-XN00-P0MKA-260036 | 2017-06-12 | DHI-WTRAN-000280 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17d42c91-9f37-4b7b-87ba-5f3816216fa2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2248 | T16182-YT01-P0CFA-151161 | 2017-06-12 | DHI-WTRAN-000281 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2249 | T16182-YT01-P0CHB-151101 | 2017-06-12 | DHI-WTRAN-000281 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2250 | T16182-YD00-P0SGZ-137731 | 2017-06-12 | DHI-WTRAN-000282 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ca3fba2-f03a-49f2-9b64-ef824073bd99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2251 | T16182-XG02-P0SGA-137701 | 2017-06-12 | DHI-WTRAN-000282 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=579791df-a353-464e-af95-412665027a63 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2252 | T16182-XH01-P0SGA-137711 | 2017-06-12 | DHI-WTRAN-000282 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4045e729-49b0-4cf0-9b8d-2908cb27aa14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2253 | T16182-CV03-P0SCA-127521 | 2017-06-12 | DHI-WTRAN-000283 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce151e20-fa5e-4705-b304-dbd883af7549 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2254 | T16182-YL00-P0SCA-127520 | 2017-06-12 | DHI-WTRAN-000283 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca007247-af71-43c2-b065-a8650012b2b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2255 | T16182-XN00-P0SCA-127525 | 2017-06-12 | DHI-WTRAN-000284 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0416691-470f-46fe-9c18-49d3ba46aae9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2256 | T16182-YT01-P0SCA-127526 | 2017-06-12 | DHI-WTRAN-000284 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=523d5db4-67f9-4591-b09a-3f499f3d1ea0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2257 | T16182-XG02-P0MBA-121003 | 2017-06-12 | DHI-TRANSMIT-000274 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3baaaef-f670-432d-9c97-8ee53a4746c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2258 | T16182-CA01-P0UTF-182852 | 2017-06-12 | DHI-TRANSMIT-000275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=592a797c-1d24-4b92-89c5-07d0fff435d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2259 | T16182-CA00-P0UTF-182803 | 2017-06-12 | DHI-TRANSMIT-000275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71ab5743-8c51-4405-a86d-91b51d344b10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2260 | T16182-CA00-P0UTF-182804 | 2017-06-12 | DHI-TRANSMIT-000275 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3c0f5cb-3d94-40db-af84-4222e8957f74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2261 | T16182-YD00-P0SGZ-137031 | 2017-06-13 | DHI-TRANSMIT-000277 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0351a08b-8bdb-4648-b9a3-ec0c8ae45f42 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2262 | T16182-YD00-P0CYE-137041 | 2017-06-13 | DHI-TRANSMIT-000278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1b5ab63-ebeb-4663-9f77-f1a7f28f71ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2263 | T16182-YU02-P0CYE-137042 | 2017-06-13 | DHI-TRANSMIT-000278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02bab674-cfa8-4542-8f99-28cac41f5d36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2264 | T16182-XG02-P0SGK-136803 | 2017-06-13 | DHI-TRANSMIT-000279 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47737927-40ea-4f77-9fd4-7bf52616dc8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2265 | T16182-YD00-P0SGZ-136831 | 2017-06-13 | DHI-TRANSMIT-000279 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1930112e-cb00-4f8b-982c-af795e77932a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2266 | T16182-YT01-P0CYE-136617 | 2017-06-13 | DHI-TRANSMIT-000280 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=511ac5ef-03a2-4a19-aef5-01b0414bb132 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2267 | T16182-YT01-P0CYE-136618 | 2017-06-13 | DHI-TRANSMIT-000280 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff982829-f0d7-4e64-af1b-9a8ac2bdd68e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2268 | T16182-YT01-P0SGA-136610 | 2017-06-13 | DHI-TRANSMIT-000281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13af0d9c-19de-4fbd-9745-8024c1475280 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2269 | T16182-YT01-P0SGA-136611 | 2017-06-13 | DHI-TRANSMIT-000281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36167e0a-fdec-4d11-a7ad-ade4d68ff797 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2270 | T16182-YT01-P0SGC-136613 | 2017-06-13 | DHI-TRANSMIT-000281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bd24aad-130a-4189-b827-40087c0d2639 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2271 | T16182-YT01-P0SGE-136612 | 2017-06-13 | DHI-TRANSMIT-000281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7463fad-3966-4550-ae86-623ec0757708 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2272 | T16182-YT01-P0SGK-136614 | 2017-06-13 | DHI-TRANSMIT-000281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9f4090f-edab-4627-a628-afa3d0b21635 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2273 | T16182-YT01-P0SGX-136616 | 2017-06-13 | DHI-TRANSMIT-000281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7363113-355c-4561-bdd8-17ee2affafd7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2274 | T16182-YT01-P0SGZ-136615 | 2017-06-13 | DHI-TRANSMIT-000281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5360ce93-90dd-4fe0-a27c-18eca0e9f254 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2275 | T16182-YD00-P0PGB-110401 | 2017-06-13 | DHI-TRANSMIT-000282 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e2ac460-5359-48f9-9df9-0af754d5c879 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2276 | T16182-YT01-P0PGB-110403 | 2017-06-13 | DHI-TRANSMIT-000282 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41942d83-e569-4394-aea9-3e26fc3a33c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2277 | T16182-VK02-P0UGF-173107 | 2017-06-13 | DHI-TRANSMIT-000283 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=041bed2d-48c9-48f0-8559-f4d04fa8b601 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2278 | T16182-XB02-P0UGF-173101 | 2017-06-13 | DHI-TRANSMIT-000283 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30e6b7c0-d059-46c8-ac76-65d348fa5823 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2279 | T16182-XB02-P0UGF-173102 | 2017-06-13 | DHI-TRANSMIT-000283 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ce790cc-3016-4836-94b0-6aac7e38fb1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2280 | T16182-CA06-P0ULA-182190 | 2017-06-13 | DHI-TRANSMIT-000284 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1700cf7-7909-42c4-9fda-24a6d9cc7ef7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2281 | T16182-CA06-P0ULA-182191 | 2017-06-13 | DHI-TRANSMIT-000284 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae181d6c-3096-4949-af49-a8fcd269af77 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2282 | T16182-XG07-P0SAG-134902 | 2017-06-13 | DHI-TRANSMIT-000285 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dfedc81-1eb6-43b0-a658-51a58a6c0426 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2283 | T16182-XH02-P0SAG-134904 | 2017-06-13 | DHI-TRANSMIT-000285 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b097d555-9b26-4039-b399-421d8da7b92b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2284 | T16182-XW03-P0SAG-134901 | 2017-06-13 | DHI-TRANSMIT-000285 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=057710c3-461a-4069-b207-00ce6b22721e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2285 | T16182-XW03-P0SAG-134903 | 2017-06-13 | DHI-TRANSMIT-000285 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9228821b-2fbb-46c2-9261-d0a45c6f89ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2286 | T16182-CA00-P0UBA-181003 | 2017-06-13 | DHI-TRANSMIT-000294 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b26cadc-0c31-4d3a-9a19-b1583dc141e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2287 | T16182-CA02-P0UBA-181056 | 2017-06-13 | DHI-TRANSMIT-000294 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a5f5460-4718-43a2-ac21-45cc2703a8c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2288 | T16182-CA06-P0UBA-181000 | 2017-06-13 | DHI-TRANSMIT-000294 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=355eab5c-7588-40f7-b31a-62a495db5f82 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2289 | T16182-CA00-P0UBA-181001 | 2017-06-13 | DHI-WTRAN-000292 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=781484c6-34a9-4c57-9ef2-e6b01fb415b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2290 | T16182-CA00-P0UBA-181004 | 2017-06-13 | DHI-WTRAN-000292 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a91ff6b7-0fb8-464c-9f35-cd1728e104b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2291 | T16182-CA01-P0UBA-181054 | 2017-06-13 | DHI-WTRAN-000292 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9edbc239-67c1-409d-833d-90e0d528317e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2292 | T16182-YD00-P0BBT-150671 | 2017-06-13 | DHI-WTRAN-000285 | IFI | 1 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e88a4bf-080a-4aea-b5e4-72f2d447a4e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2293 | T16182-XG07-P0SAV-135102 | 2017-06-13 | DHI-WTRAN-000291 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2294 | T16182-XH02-P0SAV-135104 | 2017-06-13 | DHI-WTRAN-000291 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2295 | T16182-XW03-P0SAV-135101 | 2017-06-13 | DHI-WTRAN-000291 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2296 | T16182-XW03-P0SAV-135103 | 2017-06-13 | DHI-WTRAN-000291 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2439 | T16182-YD00-P0SGZ-137231 | 2017-06-13 | DHI-WTRAN-000286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ad28fce-43f3-4f74-92d5-e9e48a5055dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2440 | T16182-YD00-P0SGZ-139931 | 2017-06-13 | DHI-WTRAN-000286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5518cb0f-ffd5-4b9c-82e6-a9fa9033ff73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2489 | T16182-YD00-P0CYE-137641 | 2017-06-13 | DHI-WTRAN-000287 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=072d68f1-768e-4bcc-8637-ff94fdf7be07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2490 | T16182-YU02-P0CYE-137642 | 2017-06-13 | DHI-WTRAN-000287 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33825ca9-330d-41e7-8e72-d149fb578215 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2491 | T16182-YD00-P0CYE-136841 | 2017-06-13 | DHI-WTRAN-000289 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3e24911-2945-4ba3-a351-6e4cfad26951 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2492 | T16182-YU02-P0CYE-136842 | 2017-06-13 | DHI-WTRAN-000289 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5c36102-d531-4c86-bdf8-3a93c7f929f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2594 | T16182-VE04-P0GQB-173401 | 2017-06-13 | DHI-WTRAN-000288 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17ec8c64-fdef-4609-87fb-5c39acea9854 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2595 | T16182-VK02-P0GQB-173417 | 2017-06-13 | DHI-WTRAN-000288 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6320035e-ebc9-4c56-91dc-c5a600c2a789 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2596 | T16182-UT01-P0GQB-173402 | 2017-06-13 | DHI-WTRAN-000288 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d650f489-4de1-4a09-a15c-279b56830cea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2597 | T16182-UT01-P0GQB-173403 | 2017-06-13 | DHI-WTRAN-000288 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50d7200a-051b-47c2-b75a-851802b1004d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2598 | T16182-UT01-P0GQB-173413 | 2017-06-13 | DHI-WTRAN-000288 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1750e78-8ec1-4a8a-82fe-6d97281c2838 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2297 | T16182-YD00-P0UBA-150503 | 2017-06-14 | DHI-TRANSMIT-000304 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=934bfa81-08d8-4644-8b9f-04063556d370 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2298 | T16182-YD00-P0UCA-150501 | 2017-06-14 | DHI-TRANSMIT-000304 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc735680-7711-47dc-a9e8-67f9f1919944 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2299 | T16182-YD00-P0UBA-150502 | 2017-06-14 | DHI-TRANSMIT-000304 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d68cb55-638e-4524-bae3-2b4ce0319a70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2300 | T16182-DP00-P8ZEN-125702 | 2017-06-14 | DHI-WTRAN-000301 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da14e2cb-673f-4449-a504-66bc261a5250 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2301 | T16182-DP00-P8ZEN-125734 | 2017-06-14 | DHI-WTRAN-000301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=239aa275-5380-4d1e-aac8-d42a507f2f7a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2302 | T16182-YL00-P8ZEN-125707 | 2017-06-14 | DHI-WTRAN-000301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4253b1b9-c67d-4954-aedd-7a211e4899ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2303 | T16182-YL00-P8ZEN-125708 | 2017-06-14 | DHI-WTRAN-000301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=680b33d1-17bf-4d01-b39b-993400b709e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2304 | T16182-YL01-P8ZEN-125703 | 2017-06-14 | DHI-WTRAN-000301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f9f6353-d3bf-4474-bfd8-a35deb208c7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2305 | T16182-YL01-P8ZEN-125704 | 2017-06-14 | DHI-WTRAN-000301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e81a1332-801c-4cb6-91b3-419a029ffeb6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2306 | T16182-YL01-P8ZEN-125705 | 2017-06-14 | DHI-WTRAN-000301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31aeb603-2f78-4b8f-ab20-dcd81d951135 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2307 | T16182-YL01-P8ZEN-125706 | 2017-06-14 | DHI-WTRAN-000301 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2be2aa12-9825-49a8-a098-b2b0242e9086 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2308 | T16182-YU02-P0ZEN-150201 | 2017-06-14 | DHI-TRANSMIT-000303 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07902619-ccb0-4ce4-8880-b355f21888bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2309 | T16182-YU02-P0CYE-137142 | 2017-06-14 | DHI-TRANSMIT-000302 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3bb9418-dac8-4b1a-8ec1-eabedf02347f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2310 | T16182-XH01-P0SGA-137311 | 2017-06-14 | DHI-TRANSMIT-000301 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d6ec30c-5bd5-40c3-81dc-1bd86f7add60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2311 | T16182-YD00-P0SGZ-137131 | 2017-06-14 | DHI-TRANSMIT-000301 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9d94695-4de8-42fc-a563-0098caabac8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2312 | T16182-XB02-P0GUB-173302 | 2017-06-14 | DHI-TRANSMIT-000300 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8aa566a-ea95-4fc1-a596-a2ec6a1d1d87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2313 | T16182-VE04-P0GUB-173301 | 2017-06-14 | DHI-TRANSMIT-000300 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fa4c399-6085-4e32-8547-f9575b806ae2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2314 | T16182-XB02-P0GUB-173303 | 2017-06-14 | DHI-TRANSMIT-000300 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2db9885-b956-4c8c-adab-0be9c56c9b31 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2315 | T16182-VK02-P0GUB-173313 | 2017-06-14 | DHI-TRANSMIT-000300 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c97ee09-76bd-4265-b7c9-962a1181f7c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2316 | T16182-YT01-P0LCP-110301 | 2017-06-14 | DHI-TRANSMIT-000299 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9d7b5d8-4728-4056-9b71-ac34df33e04b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2317 | T16182-YD00-P0LCP-110302 | 2017-06-14 | DHI-TRANSMIT-000299 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99eddf64-ba1d-49e5-80e6-aa6a78af44eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2318 | T16182-YT10-P0BAA-150701 | 2017-06-14 | DHI-TRANSMIT-000298 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d5c0e3b-7237-47d9-b5e9-aab848030eab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2319 | T16182-VE04-P0ULC-171301 | 2017-06-14 | DHI-TRANSMIT-000297 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57907c6c-6346-42c6-8b4c-4d7c55a66dad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2320 | T16182-XB02-P0ULC-171303 | 2017-06-14 | DHI-TRANSMIT-000297 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0607d1e9-feab-4962-acef-76ce1ad99a21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2321 | T16182-XB02-P0ULC-171302 | 2017-06-14 | DHI-TRANSMIT-000297 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d46cd4c9-94ba-4166-9755-9398f3020933 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2322 | T16182-VK02-P0ULC-171308 | 2017-06-14 | DHI-TRANSMIT-000297 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2c404e4-40a9-4c03-a6d4-5950bd52c1eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2323 | T16182-YT01-P0GHC-129004 | 2017-06-14 | DHI-WTRAN-000300 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be55d5fd-9e63-4c40-b182-fd7745d56201 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2324 | T16182-YT01-P0GHC-129034 | 2017-06-14 | DHI-WTRAN-000300 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0839911d-3a3f-42fb-90fc-000a1e631399 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2325 | T16182-YL00-P0GHC-129011 | 2017-06-14 | DHI-WTRAN-000299 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79af459f-f66f-48b9-988d-4c282319d742 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2326 | T16182-YL00-P0GHC-129036 | 2017-06-14 | DHI-WTRAN-000299 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8cfd5d0-d42a-4fb1-b38a-d08857ebcfce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2327 | T16182-YD00-P0CYE-136741 | 2017-06-14 | DHI-WTRAN-000298 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80fcace8-2df5-4c7e-b61a-1072b614e777 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2328 | T16182-YT10-P0SGE-136822 | 2017-06-14 | DHI-WTRAN-000297 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=474d56c8-817c-444b-8111-0bb43e8d77bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2329 | T16182-YT10-P0SGK-136823 | 2017-06-14 | DHI-WTRAN-000297 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fad98e20-0ddf-49ad-96d0-d1350ad88a0d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2330 | T16182-CV03-P8ZEN-125602 | 2017-06-14 | DHI-WTRAN-000296 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=940536d6-f34e-4182-948d-dd34632490f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2331 | T16182-CV03-P8ZEN-125605 | 2017-06-14 | DHI-WTRAN-000296 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ec8b5e5-c5df-4cc4-a791-81f547873bfb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2332 | T16182-CA03-P0UMY-185151 | 2017-06-14 | DHI-WTRAN-000302 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee7fbd43-3092-4031-9122-1b5b52656960 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2333 | T16182-CA03-P0UMY-185152 | 2017-06-14 | DHI-WTRAN-000302 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2918e6e-90ed-4986-aa0c-f54d06ca01fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2334 | T16182-CA03-P0UMY-185153 | 2017-06-14 | DHI-WTRAN-000302 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f3656f9-7c76-4524-99f0-26b7fa0f8a2d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2335 | T16182-CA03-P0UMY-185154 | 2017-06-14 | DHI-WTRAN-000302 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a81f9172-9ebb-45cf-89f9-cb3dd3c57822 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2336 | T16182-CA03-P0UMY-185155 | 2017-06-14 | DHI-WTRAN-000302 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b363b99-31bb-4f1a-ba99-966b22d39afd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2337 | T16182-CA06-P0UMY-185190 | 2017-06-14 | DHI-WTRAN-000302 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f741fa2-e7aa-4e04-879f-921a32e3dc18 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2338 | T16182-XG02-P0SGK-137902 | 2017-06-14 | DHI-WTRAN-000303 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e0bdac4-0ca9-4c2c-b644-8b270e075442 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2339 | T16182-XH01-P0SGK-137912 | 2017-06-14 | DHI-WTRAN-000303 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6868bcbe-60d4-4bba-8dbb-a7235b673308 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2340 | T16182-YT10-P0SGK-137922 | 2017-06-14 | DHI-WTRAN-000303 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ef1500e-888f-4c26-b343-aaf38c7e1688 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2341 | T16182-XG02-P0SGA-137801 | 2017-06-14 | DHI-WTRAN-000304 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd2e2eae-4d51-4f19-bbdd-4d8098cf93dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2342 | T16182-XH01-P0SGA-137811 | 2017-06-14 | DHI-WTRAN-000304 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b41ef668-b741-45a9-a9f2-b8b3e5d2deae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2343 | T16182-YD00-P0SGZ-137831 | 2017-06-14 | DHI-WTRAN-000304 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95ff89e3-a037-4071-b8ca-31719735d9b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2592 | T16182-CV03-P0ZEN-163201 | 2017-06-14 | DHI-WTRAN-000294 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fe3bdcb-5dc1-44b8-9b8d-2c213852f28c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2593 | T16182-XK00-P0PCA-126538 | 2017-06-14 | DHI-WTRAN-000295 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0990b294-dc14-4eb7-878e-8bb4dffaf495 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2344 | T16182-VN02-P0MAG-123022 | 2017-06-15 | DHI-WTRAN-000306 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9a22990-648a-4b56-bb8d-c107c240dd81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2345 | T16182-CA05-P0UYC-182981 | 2017-06-15 | DHI-WTRAN-000305 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ed94d7b-94f8-40a9-9c10-e41711a188eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2346 | T16182-CA05-P0UYC-182982 | 2017-06-15 | DHI-WTRAN-000305 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49dda52b-b74b-4c3f-90f0-dd3e25a50400 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2347 | T16182-CA05-P0UYC-182983 | 2017-06-15 | DHI-WTRAN-000305 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90c0f623-3ced-4748-bbb5-1a59316eb843 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2348 | T16182-CA05-P0UYC-182984 | 2017-06-15 | DHI-WTRAN-000305 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfd154ed-2fab-4933-8e8c-575ca4de9e8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2349 | T16182-CA05-P0UYC-182985 | 2017-06-15 | DHI-WTRAN-000305 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e04e1618-fa43-472b-bf4b-88ceb7f5540d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2350 | T16182-XB02-P0UAZ-172608 | 2017-06-15 | DHI-TRANSMIT-000313 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf561b18-8927-4719-a68f-253c04692529 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2351 | T16182-VE04-P0UAZ-172601 | 2017-06-15 | DHI-TRANSMIT-000313 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b857e8e-bd36-41ac-97bd-d110845ef02d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2352 | T16182-XB02-P0UAZ-172602 | 2017-06-15 | DHI-TRANSMIT-000313 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=269f729b-858e-424d-ab07-64a687bc0228 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2353 | T16182-VK02-P0UAZ-172613 | 2017-06-15 | DHI-TRANSMIT-000313 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2aad940f-3bf5-4787-bc95-c330dd7a8e78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2354 | T16182-XB02-P0UAZ-172603 | 2017-06-15 | DHI-TRANSMIT-000313 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b167d5e-c348-4095-b7fa-28057fd20308 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2355 | T16182-XH01-P0SGA-136604 | 2017-06-15 | DHI-TRANSMIT-000312 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7306b349-150f-4bde-8c8e-42e94495a69f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2356 | T16182-XG02-P0SGA-136603 | 2017-06-15 | DHI-TRANSMIT-000312 | IFC | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=323f9ecb-6908-49bb-aca4-e66a49d13657 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2357 | T16182-YD00-P0CYE-137141 | 2017-06-15 | DHI-TRANSMIT-000311 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9b8d463-3dd1-4bec-8b85-90bde7cb8edf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2358 | T16182-XH01-P0SGE-137312 | 2017-06-15 | DHI-TRANSMIT-000310 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49688916-8898-4a0c-a076-d42e17fd371f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2359 | T16182-XG02-P0SGA-137301 | 2017-06-15 | DHI-TRANSMIT-000310 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7628e648-2199-46a4-8ebd-deb3bbf432c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2360 | T16182-XG02-P0SGE-137302 | 2017-06-15 | DHI-TRANSMIT-000310 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56d17103-3586-4946-b842-e4a8c8abe2fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2361 | T16182-YD00-P0SGZ-137332 | 2017-06-15 | DHI-TRANSMIT-000310 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=763ee170-dde3-4117-8103-2ebd1869132c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2362 | T16182-YD00-P0CYE-137341 | 2017-06-15 | DHI-TRANSMIT-000309 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35809eb9-1d1d-4683-8218-d5b2143c6ce7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2363 | T16182-YU02-P0CYE-137342 | 2017-06-15 | DHI-TRANSMIT-000309 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7796931-72aa-4a70-a43d-f3857690e31e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2364 | T16182-XG02-P0SGE-136702 | 2017-06-15 | DHI-TRANSMIT-000308 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6de98b20-eb7c-49bb-abcd-6791d7581e07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2365 | T16182-YD00-P0SGZ-136731 | 2017-06-15 | DHI-TRANSMIT-000308 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=024909e6-0ce1-45cc-948e-99eb36f865e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2366 | T16182-XG02-P0SGA-136701 | 2017-06-15 | DHI-TRANSMIT-000308 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0797fc1e-8fe4-49ea-8f0a-839e77df4225 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2367 | T16182-YS00-P0ZEN-163301 | 2017-06-15 | DHI-TRANSMIT-000316 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0dc1bcc2-90be-476f-b082-092331615bc5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2368 | T16182-CA03-P0ULA-182153 | 2017-06-15 | DHI-TRANSMIT-000315 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59196af2-3939-4789-b17b-068b4f01fd3a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2369 | T16182-CA03-P0ULA-182157 | 2017-06-15 | DHI-TRANSMIT-000315 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5f66e73-7736-4008-8c2a-8e1ae2394e09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2370 | T16182-CA02-P0QJA-184854 | 2017-06-15 | DHI-TRANSMIT-000317 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3eb181fa-9e9f-44ae-9fe4-25a2a1347381 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2371 | T16182-XB02-P0LB-122018 | 2017-06-15 | DHI-TRANSMIT-000329 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ffb5ca1-013c-41c8-9180-dd1aa70ba818 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2372 | T16182-CV03-P0CWQ-161121 | 2017-06-15 | DHI-WTRAN-000308 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e7a7c0e-35bf-4041-a158-8f3d55c82e5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2373 | T16182-XG07-P0SAR-134102 | 2017-06-15 | DHI-WTRAN-000309 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5523d5f-a7b4-41eb-bd7e-a80da6d3e21b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2374 | T16182-XH02-P0SAR-134104 | 2017-06-15 | DHI-WTRAN-000309 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6597b7a3-63de-4c73-b7a9-8c368ca7f6d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2375 | T16182-XW03-P0SAR-134101 | 2017-06-15 | DHI-WTRAN-000309 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f61811c5-522b-4c04-8e94-714cb2182f30 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2376 | T16182-XW03-P0SAR-134103 | 2017-06-15 | DHI-WTRAN-000309 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b08204bc-4e25-4f92-af57-dd5e0f0c601e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2377 | T16182-CV03-P0UCL-163203 | 2017-06-15 | DHI-WTRAN-000310 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dab2396-c9d2-49ea-976e-6646d2badc5d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2378 | T16182-XW01-P0MAG-123007 | 2017-06-15 | DHI-WTRAN-000307 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f5b6a00-5561-41b0-9f71-46754b79453d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2417 | T16182-XG02-P0SGA-136603 | 2017-06-15 | DHI-TRANSMIT-000312 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2054 | T16182-XG02-P8ZEN-125591 | 2017-06-16 | DHI-TRANSMIT-000341 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cce66299-11d6-441b-8e08-5ec670b8e32b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2055 | T16182-XG02-P8ZEN-125592 | 2017-06-16 | DHI-TRANSMIT-000342 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=850ce1a2-60be-47ab-87f7-668aa7c49215 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2056 | T16182-XG02-P8ZEN-125593 | 2017-06-16 | DHI-TRANSMIT-000343 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8acfea0b-2e57-4084-994e-1a617ac8fbb9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2379 | T16182-YE00-P0ZEN-152718 | 2017-06-16 | DHI-WTRAN-000317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cca28384-7dc7-46d4-b292-7f5644582621 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2380 | T16182-YE00-P0ZEN-152720 | 2017-06-16 | DHI-WTRAN-000317 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32a24fed-a7b1-406f-96d2-5b14bf460955 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2381 | T16182-YK00-P0SCA-127522 | 2017-06-16 | DHI-WTRAN-000316 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cce76463-5769-41f0-904a-525521adbb99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2382 | T16182-XL00-P0ZEN-140005 | 2017-06-16 | DHI-WTRAN-000315 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=929ec7c3-d528-4da5-872a-a02a374f38d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2383 | T16182-CV03-P8ZEN-125601 | 2017-06-16 | DHI-WTRAN-000314 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0a91deb-8edc-4884-8667-115d10fae316 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2384 | T16182-CV03-P8ZEN-125604 | 2017-06-16 | DHI-WTRAN-000314 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cafedf63-bafe-4409-aded-5545b50ab9c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2385 | T16182-CV03-P8ZEN-125611 | 2017-06-16 | DHI-WTRAN-000314 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=258217b4-ede2-412d-b4af-76a50a002be8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2386 | T16182-YD07-P8QHA-125201 | 2017-06-16 | DHI-WTRAN-000313 | IFI | 1 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e82b371-454a-48fc-a949-e0c10e98ba65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2387 | T16182-YK08-P0LCM-420030 | 2017-06-16 | DHI-WTRAN-000312 | IFR | B | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0af0d0ab-b91e-4f09-96ea-3082a89db62b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2388 | T16182-YK08-P0LCM-420040 | 2017-06-16 | DHI-WTRAN-000312 | IFR | B | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a8ec7e0-2cf0-49da-bf1e-190929b47edc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2389 | T16182-YE03-P0BAU-152520 | 2017-06-16 | DHI-WTRAN-000311 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a66b616c-b1fe-4a8c-89db-9115903aa31b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2390 | T16182-YE03-P0BAU-152522 | 2017-06-16 | DHI-WTRAN-000311 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c363bad-2e6a-4d10-ac3a-859b3522e806 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2391 | T16182-YK08-P0LCM-420040 | 2017-06-16 | DHI-TRANSMIT-000330 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2392 | T16182-YK08-P0LCM-420030 | 2017-06-16 | DHI-TRANSMIT-000330 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2393 | T16182-YK08-P0PGB-420020 | 2017-06-16 | DHI-TRANSMIT-000330 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2394 | T16182-YK08-P0PGB-420010 | 2017-06-16 | DHI-TRANSMIT-000330 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2395 | T16182-YD07-P8QHA-125201 | 2017-06-16 | DHI-TRANSMIT-000332 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2396 | T16182-YU03-P0BB-150831 | 2017-06-16 | DHI-WTRAN-000321 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2813bd8f-c58c-46e9-ab2c-a61157e2afff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2397 | T16182-CA02-P0UBA-186155 | 2017-06-16 | DHI-TRANSMIT-000334 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49b601f7-bfc8-43ba-a5bf-2d1208732430 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2398 | T16182-CA00-P0UBA-186101 | 2017-06-16 | DHI-TRANSMIT-000334 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60dea3ae-fb62-4670-9ae0-b30b2a872242 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2399 | T16182-CA00-P0UBA-186104 | 2017-06-16 | DHI-TRANSMIT-000334 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab5b2b43-2e32-47fc-89e6-12c33d698066 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2400 | T16182-CA01-P0UBA-186152 | 2017-06-16 | DHI-TRANSMIT-000334 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c1497f2-540e-40d0-a039-f73751ea461d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2401 | T16182-XG02-P1MBH-110013 | 2017-06-16 | DHI-TRANSMIT-000333 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e0b0beb-f31d-44cc-8dc3-58c289fcd770 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2402 | T16182-YD00-P0PCA-126503 | 2017-06-16 | DHI-WTRAN-000320 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c1e4510-7336-4b13-b084-edc308cc2aa7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2403 | T16182-DE00-P0ZEN-152830 | 2017-06-16 | DHI-WTRAN-000319 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f05e04d0-a6fe-4c0f-ac31-171c6e118271 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2441 | T16182-DP00-P0ZEN-020005 | 2017-06-16 | DHI-TRANSMIT-000335 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2808 | T16182-YK10-P8QHA-125207 | 2017-06-16 | DHI-WTRAN-000318 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4696bdc4-fe78-454c-ac68-b74117cc07c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2404 | T16182-YL01-P0SAY-163402 | 2017-06-19 | DHI-WTRAN-000322 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2c2c759-b833-4494-b7a4-c02856db4904 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2405 | T16182-XG02-P0SGK-137603 | 2017-06-19 | DHI-WTRAN-000323 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1343ec5-a10e-4986-911a-698c4daccbed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2406 | T16182-XH01-P0SGK-137613 | 2017-06-19 | DHI-WTRAN-000323 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f67338bd-a4d7-440f-883d-10b2b4722cb2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2407 | T16182-YD00-P0SGZ-137631 | 2017-06-19 | DHI-WTRAN-000323 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc6f6367-23bf-4b23-a914-e0b81e6ae3ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2408 | T16182-YT10-P0SGK-137623 | 2017-06-19 | DHI-WTRAN-000323 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1793b552-f80b-46b7-9a13-a588d8bafff4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2409 | T16182-YT01-P0SGA-136609 | 2017-06-19 | DHI-TRANSMIT-000345 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2410 | T16182-YT01-P0SGA-136609 | 2017-06-19 | DHI-WTRAN-000324 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f3a358f-4e50-450a-8833-eb39fa573ac8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2411 | T16182-XS00-P0SG-136602 | 2017-06-19 | DHI-TRANSMIT-000346 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5983995f-71dd-483c-98bc-2ce3774a7438 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2412 | T16182-YU02-P0CYE-136742 | 2017-06-19 | DHI-TRANSMIT-000347 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c677629d-7fa5-47cc-b5ae-3fd6c90176d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2413 | T16182-YT01-P0BAT-150611 | 2017-06-19 | DHI-TRANSMIT-000348 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2414 | T16182-YT01-P0BBT-150661 | 2017-06-19 | DHI-TRANSMIT-000349 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2415 | T16182-YT01-P0BAT-150611 | 2017-06-19 | DHI-WTRAN-000325 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69684641-242b-4d7e-bbe6-993b4875717c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2416 | T16182-YT01-P0BBT-150661 | 2017-06-19 | DHI-WTRAN-000326 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4c9c130-6909-46f5-a2df-a14c08572f50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2418 | T16182-XW03-P0GCF-130005 | 2017-06-19 | DHI-TRANSMIT-000355 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2419 | T16182-XG07-P0GCF-130003 | 2017-06-19 | DHI-TRANSMIT-000353 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2420 | T16182-YD00-P0GCF-130002 | 2017-06-19 | DHI-TRANSMIT-000352 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2421 | T16182-YE00-P0ZEN-152731 | 2017-06-19 | DHI-WTRAN-000335 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdcd85f0-3963-418f-b829-194b6d2f2404 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2422 | T16182-YE00-P0ZEN-152732 | 2017-06-19 | DHI-WTRAN-000335 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=850c0c27-db0b-44b1-aca3-afd3a47c97cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2423 | T16182-YE00-P0ZEN-152733 | 2017-06-19 | DHI-WTRAN-000335 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=459a34cb-e58a-4de7-a241-cf95f5acb49f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2424 | T16182-YT01-P0LB-122106 | 2017-06-19 | DHI-WTRAN-000334 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70e95cf8-971a-436f-a783-3a9b04f525d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2425 | T16182-YD00-P0BBT-150671 | 2017-06-19 | DHI-WTRAN-000332 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2426 | T16182-XG02-P0GCF-130004 | 2017-06-19 | DHI-WTRAN-000331 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c49bee03-83fc-40e6-bbad-9eb31c249845 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2427 | T16182-XW03-P0GNR-130104 | 2017-06-19 | DHI-WTRAN-000331 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4dd63a58-4f79-49c3-a255-cad684407f74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2428 | T16182-YD00-P0LB-122049 | 2017-06-19 | DHI-WTRAN-000330 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ef85bac-f82a-4bc5-8def-14b58a437a17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2429 | T16182-YS00-P0LB-122091 | 2017-06-19 | DHI-WTRAN-000330 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3942b589-415d-4116-a789-0e9831c7f0a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2430 | T16182-YT01-P0LB-122042 | 2017-06-19 | DHI-WTRAN-000330 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3daba34-7eeb-401b-936a-50895656c361 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2431 | T16182-YT01-P0LB-122051 | 2017-06-19 | DHI-WTRAN-000330 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=835edc72-9ffc-43d1-a598-ed2960613034 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2432 | T16182-XW01-P0LB-122061 | 2017-06-19 | DHI-WTRAN-000329 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90ed39dd-c1a3-4580-86fb-c20f7ad83c00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2433 | T16182-XW03-P0GHC-110051 | 2017-06-19 | DHI-WTRAN-000328 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5294502d-56d8-45c8-a601-aa12705ad7a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2434 | T16182-YT01-P0BB-150801 | 2017-06-19 | DHI-WTRAN-000327 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f606f3ab-499f-456a-84cb-5d8af6c3e2fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2435 | T16182-XW03-P0GKS-120013 | 2017-06-19 | DHI-TRANSMIT-000373 | IFC | 0 | DR | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f5b4751-5c57-4718-94c6-edac2e087ca6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2436 | T16182-XW03-P0GKS-120013 | 2017-06-19 | DHI-TRANSMIT-000372 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2437 | T16182-XG02-P0SGE-136802 | 2017-06-19 | DHI-TRANSMIT-000371 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=564167c0-4666-437a-ae0e-43fb45b1638f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2438 | T16182-XG02-P0SGA-136801 | 2017-06-19 | DHI-TRANSMIT-000371 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77577428-45fd-4eed-b06b-ab26cdad0b9c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2442 | T16182-CA00-P0UBA-181302 | 2017-06-20 | DHI-TRANSMIT-000374 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e70414fd-2238-4ab3-9578-702cbae16935 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2443 | T16182-CA00-P0UBA-181304 | 2017-06-20 | DHI-TRANSMIT-000374 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26c158ba-2ffc-4a5c-a6d5-4fdb7ab3e792 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2444 | T16182-CA00-P0UBA-181305 | 2017-06-20 | DHI-TRANSMIT-000374 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d039b37d-386e-4d2d-bfb0-23903d9fc6b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2445 | T16182-CA01-P0UBA-181351 | 2017-06-20 | DHI-TRANSMIT-000375 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8cb8572-55af-405a-b3a5-2c0ce21eac16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2446 | T16182-CA01-P0UBA-181352 | 2017-06-20 | DHI-TRANSMIT-000375 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd44ef82-2280-40c5-a267-57515b9b41aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2447 | T16182-CA01-P0UBA-181354 | 2017-06-20 | DHI-TRANSMIT-000375 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37ffbe96-bf53-4356-b740-c04004054402 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2448 | T16182-CA02-P0UBA-181357 | 2017-06-20 | DHI-TRANSMIT-000375 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f58d348-8356-4ae5-bd2f-f0cb27b82c0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2449 | T16182-CA00-P0UBA-181205 | 2017-06-20 | DHI-TRANSMIT-000376 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60d777f9-f113-47fb-a9de-3b043b77559d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2450 | T16182-CA00-P0UBA-181206 | 2017-06-20 | DHI-TRANSMIT-000376 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7f90a12-e8f6-4d9b-9886-d2b8355b884f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2451 | T16182-CA00-P0UBA-181207 | 2017-06-20 | DHI-TRANSMIT-000376 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e2b33b4-1d8d-4480-ad93-05fbf515f790 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2452 | T16182-CA01-P0UBA-181251 | 2017-06-20 | DHI-TRANSMIT-000377 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=581bfb95-c518-42fc-8978-2fd54c9a1fc7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2453 | T16182-CA01-P0UBA-181252 | 2017-06-20 | DHI-TRANSMIT-000377 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9fba782-cafd-4bd2-bdfb-f86c046ea698 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2454 | T16182-CA01-P0UBA-181256 | 2017-06-20 | DHI-TRANSMIT-000377 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e42326f-0f77-48b6-9d3a-eca3e9a730b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2455 | T16182-CA02-P0UBA-181257 | 2017-06-20 | DHI-TRANSMIT-000377 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32b6a2b0-a842-4a06-8c1e-d674d4cb010d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2456 | T16182-CA02-P0UBA-181259 | 2017-06-20 | DHI-TRANSMIT-000377 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=315b06f0-26d4-4048-820b-fd5ec6123ee5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2457 | T16182-CA00-P0UBA-181306 | 2017-06-20 | DHI-TRANSMIT-000381 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d2902ad-efb1-4616-92a1-d0d9d1e63aab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2458 | T16182-VE04-P0UMX-171004 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e346dd5-0239-4c7d-92e1-d5de4d7e25a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2459 | T16182-XB02-P0UMX-171006 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb9b8ca8-d1cc-4d40-a337-d819b365e23f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2460 | T16182-XB02-P0UMX-171010 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45b4293a-347b-448d-b6f4-91d4983a6c12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2461 | T16182-XB02-P0UMX-171011 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4f5c082-41d2-4603-936c-bdd7aeee2465 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2462 | T16182-VK02-P0UMX-171013 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0522a1d8-4bfb-4374-bd65-e16bf2ab96e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2463 | T16182-VK02-P0UMX-171014 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c902c0e-8b62-497d-8a46-414726fb3771 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2464 | T16182-VK02-P0UMX-171015 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4d687bb-aa95-43f3-8eba-86a809028189 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2465 | T16182-VK02-P0UMX-171016 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=606f0d00-b858-415b-9c99-8b1eba1f8518 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2466 | T16182-VK02-P0UMX-171017 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e121171-8e56-4b2b-b37d-601f5ac56567 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2467 | T16182-VK02-P0UMX-171018 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5e9b8de-386e-4a12-9573-e9632ceaf524 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2468 | T16182-VK02-P0UMX-171019 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5d2d1ef-cb8d-4439-8cdc-141d36ae12e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2469 | T16182-VK02-P0UMX-171020 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a3da9f3-4ac1-4336-81c6-70d67c444f96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2470 | T16182-VK02-P0UMX-171021 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7085a37c-e5b0-490d-b911-642d39fb6bb4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2471 | T16182-VK02-P0UMX-171022 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cce9a11-40d9-4d5f-8e46-44f64b997bb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2472 | T16182-VK02-P0UMX-171023 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a21c3ba4-8e68-47a1-bcbb-0860e95f2963 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2473 | T16182-VK02-P0UMX-171024 | 2017-06-20 | DHI-TRANSMIT-000380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2883fdb4-3c18-4885-9205-a409870acb65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2474 | T16182-XG02-P0SGC-137101 | 2017-06-20 | DHI-TRANSMIT-000379 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4678150-335c-411e-aea3-35e411907b27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2475 | T16182-XG02-P0SGE-137903 | 2017-06-20 | DHI-TRANSMIT-000379 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa7e25ce-21ca-40f3-b881-237b4f08727d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2476 | T16182-YT10-P0SGC-137121 | 2017-06-20 | DHI-TRANSMIT-000379 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c316f4c2-8481-434a-bdbc-245906508964 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2477 | T16182-XH01-P0SGC-137111 | 2017-06-20 | DHI-TRANSMIT-000379 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12c4e438-3f13-4809-93d9-6465e2437502 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2478 | T16182-XG02-P0SGA-136603 | 2017-06-20 | DHI-TRANSMIT-000378 | IFC | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2479 | T16182-XH01-P0SGA-136604 | 2017-06-20 | DHI-TRANSMIT-000378 | IFC | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2480 | T16182-DN05-P0SG-136620 | 2017-06-20 | DHI-WTRAN-000339 | IFR | A | D | TRUE | FALSE | 2018-04-05_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9ad8d78-5cbd-4f96-a195-0465d097c7e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2481 | T16182-YD00-P0SGZ-138231 | 2017-06-20 | DHI-WTRAN-000339 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0963f78-0019-4349-a83d-5bb0e1e06845 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2482 | T16182-YD00-P0SGZ-138331 | 2017-06-20 | DHI-WTRAN-000339 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b777e458-8b1b-4d5c-b078-2c27ecc5a97b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2483 | T16182-VK02-P0UMX-171012 | 2017-06-20 | DHI-WTRAN-000338 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2484 | T16182-XB02-P0UMX-171007 | 2017-06-20 | DHI-WTRAN-000338 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2485 | T16182-XB02-P0UMX-171008 | 2017-06-20 | DHI-WTRAN-000338 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2486 | T16182-XB02-P0UMX-171009 | 2017-06-20 | DHI-WTRAN-000338 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2487 | T16182-YD00-P0LB-122050 | 2017-06-20 | DHI-WTRAN-000337 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba33698a-00d4-4703-898d-df479ab3a605 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2488 | T16182-YD00-P0LB-122052 | 2017-06-20 | DHI-WTRAN-000337 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f711130-614f-4dc2-b745-75f6ff76ac01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2493 | T16182-YU03-P0CHB-151121 | 2017-06-21 | DHI-WTRAN-000340 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4abd8975-0b31-4eae-9335-e30cf4717eb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2494 | T16182-YU03-P0CHB-151122 | 2017-06-21 | DHI-WTRAN-000340 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9317ca3d-c563-4a1f-97f5-26b20ee5d2b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2495 | T16182-YU03-P0CFA-151181 | 2017-06-21 | DHI-WTRAN-000340 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb84bf91-df82-486c-855f-8d3fdee62a15 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2496 | T16182-YD00-P0CYE-137841 | 2017-06-21 | DHI-WTRAN-000341 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2236fa8f-d400-481f-9e9a-5210576849e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2497 | T16182-YU02-P0CYE-137842 | 2017-06-21 | DHI-WTRAN-000341 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94af7c19-8a64-4135-9e06-e2e4663fdb7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2498 | T16182-YD00-P0CYE-138041 | 2017-06-21 | DHI-WTRAN-000342 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=561918e3-d757-412d-a219-d97abc2b99b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2499 | T16182-YU02-P0CYE-138042 | 2017-06-21 | DHI-WTRAN-000342 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=015f5c12-b64c-4ac1-b161-cfa7fa66453c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2500 | T16182-YD00-P0CYE-138941 | 2017-06-21 | DHI-WTRAN-000343 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07053559-909c-4bb6-9a08-87261c9945ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2501 | T16182-YU02-P0CYE-138942 | 2017-06-21 | DHI-WTRAN-000343 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ca82d7f-e248-4877-95df-c73edde6fb48 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2502 | T16182-YF00-P0BB-150403 | 2017-06-21 | DHI-WTRAN-000344 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdb972c2-fd9a-4b70-860d-e6ceb753dab7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2503 | T16182-YU03-P0BFA-150951 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9921bdb-62e1-4e83-8171-284fcda3c0c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2504 | T16182-YU03-P0BFA-150952 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be8bce4b-8020-442e-aca3-9cd12541978f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2505 | T16182-YU03-P0BFA-150953 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8fd23c1-066f-4903-85ae-8f3262a174db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2506 | T16182-YU03-P0BFA-150954 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=851c4393-c3e9-4353-902c-d7fd1efb2861 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2507 | T16182-YU03-P0BFA-150955 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d8f041a-5b00-44a5-8a15-00dec1179e71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2508 | T16182-YU03-P0BFA-150956 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9634292f-a45b-4962-9bcb-a5f28963bccd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2509 | T16182-YU03-P0BFA-150957 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c1e8f7c-5eea-41de-a637-8b05ef2286e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2510 | T16182-YU03-P0BFA-150958 | 2017-06-21 | DHI-WTRAN-000345 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6a8e448-b310-44d7-a151-3b33d80dc4bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2511 | T16182-YU02-P0BFA-150912 | 2017-06-21 | DHI-WTRAN-000346 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0c715fe-b5fe-4b6d-8dc3-5a90a966bc28 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2512 | T16182-YU02-P0BFA-150915 | 2017-06-21 | DHI-WTRAN-000346 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c34e835-d097-4183-b51b-61fedbfd08c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2513 | T16182-YU02-P0BFA-150917 | 2017-06-21 | DHI-WTRAN-000346 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88125f48-656e-4ebc-84aa-d9e0f37f3ce1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2514 | T16182-YD00-P0BF-150932 | 2017-06-21 | DHI-WTRAN-000347 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a639265d-e1aa-47dd-a519-557e7978ce60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2515 | T16182-YD00-P0BF-150935 | 2017-06-21 | DHI-WTRAN-000347 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f65d025-be97-4f36-acf5-38853cf283bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2516 | T16182-YD00-P0BF-150937 | 2017-06-21 | DHI-WTRAN-000347 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89e942c5-fb4c-4cfb-927f-baaaa6decd82 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2517 | T16182-YD00-P0BF-150940 | 2017-06-21 | DHI-WTRAN-000347 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc1e9ea5-6ac3-4e8d-a5b8-4c23f627b64b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2518 | T16182-CA00-P0UBA-181104 | 2017-06-21 | DHI-WTRAN-000348 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2519 | T16182-VK02-P0ULC-171309 | 2017-06-21 | DHI-TRANSMIT-000382 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c79a6def-8e72-4951-8bc7-2f18ad24932b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2520 | T16182-VK02-P8UTH-172008 | 2017-06-21 | DHI-TRANSMIT-000383 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f60e695-fb58-4bd6-b86c-455777531ece | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2521 | T16182-XB02-P8UTH-172007 | 2017-06-21 | DHI-TRANSMIT-000383 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcd59db4-0c0f-499d-a9dc-0c97e5d32d50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2522 | T16182-YD00-P0BAA-150762 | 2017-06-21 | DHI-WTRAN-000349 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64f27024-7f21-4cc2-91e9-6e95c245528f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2523 | T16182-YT01-P0BAA-150752 | 2017-06-21 | DHI-WTRAN-000349 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ba4287d-cdce-4973-b563-517a1ce60df0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2524 | T16182-YF00-P0GCF-130018 | 2017-06-21 | DHI-WTRAN-000350 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c4553fe-a777-45c3-b21e-34367e51c577 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2525 | T16182-YK00-P0GCF-130016 | 2017-06-21 | DHI-WTRAN-000350 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88b19a8c-b62d-4eda-9fb3-bfe03cdc01bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2526 | T16182-YL00-P0GNR-130106 | 2017-06-21 | DHI-WTRAN-000350 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=375f3c89-e8ac-4cbe-bc5f-05e84dd213f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2527 | T16182-YR05-P0GCF-130007 | 2017-06-21 | DHI-WTRAN-000352 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=883e1177-8168-4573-8ebe-490f94ecc730 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2528 | T16182-YL00-P0GCF-130009 | 2017-06-21 | DHI-WTRAN-000352 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac4afc73-565f-44cc-a4ab-7b4bc2a78f50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2529 | T16182-YF02-P0GCF-130011 | 2017-06-21 | DHI-WTRAN-000352 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e45156e9-974d-4ace-bf80-bc0498ef41c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2530 | T16182-YL01-P0GCF-130035 | 2017-06-21 | DHI-WTRAN-000352 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=008bc8dc-0a1d-4523-9f5b-4f84de990d27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2531 | T16182-YE00-P0GCF-130015 | 2017-06-21 | DHI-WTRAN-000351 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a86cd63-315a-44e6-a9dc-a29f4103b1e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2532 | T16182-YU03-P0GCF-130017 | 2017-06-21 | DHI-WTRAN-000351 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=272e5302-4d7b-4699-9e62-1de4ef983b37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2533 | T16182-YU02-P0GCF-130010 | 2017-06-21 | DHI-WTRAN-000353 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a942f4c8-c8d8-4df1-9046-78bc2b6880ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2534 | T16182-DP00-P0ZEN-020004 | 2017-06-21 | DHI-TRANSMIT-000384 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f678e772-00a8-4808-9974-fea4db59115d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2535 | T16182-CA02-P0ULD-183955 | 2017-06-21 | DHI-TRANSMIT-000385 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b82bc6a9-8d40-4982-94c5-5c2eeb72c51a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2537 | T16182-CA05-P0UST-182081 | 2017-06-22 | DHI-WTRAN-000354 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80ead589-131b-4a22-a308-67112073444a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2538 | T16182-CA05-P0UST-182082 | 2017-06-22 | DHI-WTRAN-000354 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46df782f-dbc9-44b2-882f-28be2dba35d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2539 | T16182-CA05-P0UST-182083 | 2017-06-22 | DHI-WTRAN-000354 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cff537a4-7d41-43a2-98fd-aea3353757ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2540 | T16182-CA05-P0UST-182084 | 2017-06-22 | DHI-WTRAN-000354 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab67ddf8-663a-4473-9366-b15e95727128 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2541 | T16182-CA05-P0UST-182085 | 2017-06-22 | DHI-WTRAN-000354 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cb0b7c1-2dd2-4190-8fba-6f5a280fbc64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2542 | T16182-CN00-P0LB-122040 | 2017-06-22 | DHI-WTRAN-000355 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb273830-5a38-46c6-8214-cddbc9c7c174 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2543 | T16182-XG02-P0LB-122023 | 2017-06-22 | DHI-WTRAN-000356 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50722e30-833d-41af-879b-93e2ceef2eeb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2544 | T16182-CN00-P0ZEN-110701 | 2017-06-22 | DHI-WTRAN-000357 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76eb97a0-eb13-4c9b-b623-eacc72df805d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2545 | T16182-CA01-P0UGD-181952 | 2017-06-22 | DHI-TRANSMIT-000396 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1b2e41d-d99e-49a6-96dd-74e4dec422f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2546 | T16182-CA01-P0UGD-181953 | 2017-06-22 | DHI-TRANSMIT-000396 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2148f52b-782d-4970-8e39-04707758644c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2547 | T16182-YD00-P0GHC-129001 | 2017-06-26 | DHI-WTRAN-000358 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=780486b4-035b-42e9-93fc-35675a4eecc6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2548 | T16182-YT01-P0GHC-129002 | 2017-06-26 | DHI-WTRAN-000358 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f38931d-90c6-4b63-884c-3b7e0dab2ee6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2549 | T16182-YD00-P0GHC-129031 | 2017-06-26 | DHI-WTRAN-000358 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=149a06ea-87dc-4bca-9cb1-91f28fea51b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2550 | T16182-YT01-P0GHC-129032 | 2017-06-26 | DHI-WTRAN-000358 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=451bed4d-6863-4831-8652-1090488aa7da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2551 | T16182-CV03-P0ZEN-165701 | 2017-06-26 | DHI-WTRAN-000359 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a1ccd88-30a7-4367-86f1-8fe398f627bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2552 | T16182-XG02-P0SGC-138201 | 2017-06-26 | DHI-WTRAN-000360 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5af9dbd2-c348-4b62-9a18-be0fb1cff881 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2553 | T16182-XH01-P0SGC-138211 | 2017-06-26 | DHI-WTRAN-000360 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f868637e-3e58-4680-9f7c-06d04287982d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2554 | T16182-YT10-P0SGC-138221 | 2017-06-26 | DHI-WTRAN-000360 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc7815d1-1b39-4b44-9c77-954f1c472cbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2555 | T16182-XG02-P0SGC-137401 | 2017-06-26 | DHI-WTRAN-000361 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff72fa1d-40dd-4ab4-9089-6d87af9455f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2556 | T16182-XH01-P0SGC-137411 | 2017-06-26 | DHI-WTRAN-000361 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43ad3b7b-866f-4d02-aae2-e5aea152f9c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2557 | T16182-YT10-P0SGC-137421 | 2017-06-26 | DHI-WTRAN-000361 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a27140ee-1a2b-455f-b57e-465fcad8a31f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2558 | T16182-YD00-P0SGZ-137431 | 2017-06-26 | DHI-WTRAN-000361 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41c304cc-9669-4ef7-a637-9897b26d9bee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2559 | T16182-XG02-P0SGC-138301 | 2017-06-26 | DHI-WTRAN-000363 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e192a6b3-f88d-4af2-b24b-5651dd8f5e3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2560 | T16182-XH01-P0SGC-138311 | 2017-06-26 | DHI-WTRAN-000363 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=588bc951-15fe-4f89-89e1-57b6b2eba6fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2561 | T16182-YT10-P0SGC-138321 | 2017-06-26 | DHI-WTRAN-000363 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85b06925-109d-4f19-a71d-70be3fe04e0f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2562 | T16182-YD05-P0SCA-127515 | 2017-06-26 | DHI-WTRAN-000364 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7c59ead-6bff-4f35-a186-7ee2333b5ac5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2563 | T16182-YE00-P0ZEN-152736 | 2017-06-26 | DHI-WTRAN-000365 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d1c4082-2f0e-42b8-bf75-4e6a5c149bbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2564 | T16182-YQ08-P0CY-154034 | 2017-06-26 | DHI-WTRAN-000366 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65681a1d-0c5f-43b3-a60c-8df889b11bcf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2565 | T16182-YQ08-P0CY-154035 | 2017-06-26 | DHI-WTRAN-000366 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbd54150-df05-48dc-8625-dc4b5b50b430 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2566 | T16182-YQ08-P0CY-154037 | 2017-06-26 | DHI-WTRAN-000366 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93927f8f-8481-4567-94d6-624ca04aab14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2567 | T16182-YQ08-P0CY-154051 | 2017-06-26 | DHI-WTRAN-000366 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=423562e5-4418-475b-bac0-5afdd21709b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2568 | T16182-YT10-P0ZEN-150301 | 2017-06-26 | DHI-WTRAN-000367 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e0f99f8-38e2-4040-b910-fb6feacc2729 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2569 | T16182-YT10-P0ZEN-150302 | 2017-06-26 | DHI-WTRAN-000367 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=769960ac-afd3-418e-92b5-a57be7f3a164 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2570 | T16182-YF00-P0BA-150401 | 2017-06-26 | DHI-WTRAN-000368 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2571 | T16182-YF00-P0BA-150404 | 2017-06-26 | DHI-WTRAN-000368 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2572 | T16182-CA00-P0UMA-180401 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=579da825-ff28-4e6f-91ee-25f7249b15a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2573 | T16182-CA00-P0UMA-180402 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c76be002-2b28-4043-ac43-a8980c3219ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2574 | T16182-CA00-P0UMA-180403 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6996cd3c-7ddc-4346-8abd-cfcb5b480a95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2575 | T16182-CA00-P0UMA-180404 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85eeb4ae-6cfc-483f-b7d1-fc237a513cf4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2576 | T16182-CA01-P0UMA-180451 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0498ec92-eebd-4a28-a8c3-966ac75870f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2577 | T16182-CA01-P0UMA-180452 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4d0ac24-38e1-43f2-91ab-61bd070bf92f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2578 | T16182-CA01-P0UMA-180454 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d8b2013-079b-4bc1-8839-11a0bf4e483a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2579 | T16182-CA03-P0UMA-180458 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=277fc6ab-8fc2-4b12-b1b5-b97ebe5a1ff1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2580 | T16182-CA03-P0UMA-180462 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1c358d7-582a-44c3-b222-51626c40b69e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2581 | T16182-CA03-P0UMA-180463 | 2017-06-26 | DHI-TRANSMIT-000397 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=969c03b9-bc9a-4268-a6d3-08bfa738cf40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2582 | T16182-VE04-P0UEM-171701 | 2017-06-26 | DHI-TRANSMIT-000398 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bdef00e-c320-4ef1-a3e3-0729a54e1b01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2583 | T16182-VK02-P0UEM-171711 | 2017-06-26 | DHI-TRANSMIT-000398 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21575f17-e641-45ed-b9e5-d09f091011c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2584 | T16182-XB02-P0UEM-171702 | 2017-06-26 | DHI-TRANSMIT-000398 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=295720af-002b-4b66-abfe-e7820a812d24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2585 | T16182-XB02-P0UEM-171708 | 2017-06-26 | DHI-TRANSMIT-000398 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf5b3f0c-90a7-4ee3-9d97-9337932d4032 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2586 | T16182-YT10-P0SGE-137322 | 2017-06-26 | DHI-TRANSMIT-000399 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c8d2901-ec2d-485a-9c94-a517685dc482 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2587 | T16182-XG02-P0SGK-136703 | 2017-06-26 | DHI-TRANSMIT-000400 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7198f9a0-3873-4557-9f84-d337109c128e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2588 | T16182-CV03-P0CWQ-161135 | 2017-06-26 | DHI-TRANSMIT-000401 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=646f5fe8-9d12-45ee-8f96-89789c3a384c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2589 | T16182-YR05-P0CWQ-161146 | 2017-06-26 | DHI-TRANSMIT-000401 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=047f1a2a-a728-435a-823c-efedd504dfca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2590 | T16182-XB02-P0MPA-171113 | 2017-06-26 | DHI-TRANSMIT-000402 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2591 | T16182-XB02-P0MPA-171113 | 2017-06-26 | DHI-TRANSMIT-000403 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=471f952a-ca48-43e8-b728-853473c422a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2809 | T16182-CV03-P0SG-136621 | 2017-06-26 | DHI-WTRAN-000362 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37561742-1290-4afe-840e-b8dc62da2e75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2599 | T16182-YS00-P0ZEN-163302 | 2017-06-27 | DHI-TRANSMIT-000404 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1c1dba5-8040-446f-850b-726f46cfc27c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2600 | T16182-YS00-P0ZEN-163304 | 2017-06-27 | DHI-TRANSMIT-000404 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11d7fcd9-8dd0-444c-85b4-2c92c6152077 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2601 | T16182-YS00-P0ZEN-163308 | 2017-06-27 | DHI-TRANSMIT-000404 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a15df8d-0ea6-438d-88f2-a93db7a50b65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2602 | T16182-YS00-P0ZEN-163309 | 2017-06-27 | DHI-TRANSMIT-000404 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d63f8ecc-89ed-4940-be5a-68c54410f634 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2603 | T16182-DP00-P0ZEN-020005 | 2017-06-27 | DHI-WTRAN-000369 | IFI | 2 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2604 | T16182-CA03-P0UMY-185160 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dba4f6aa-57b0-4784-9914-19fed3cec6aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2605 | T16182-CA03-P0UMY-185161 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d9c8071-5c67-462f-8a72-eacaa8884212 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2606 | T16182-CA03-P0UMY-185162 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78a3c1da-c9d6-4075-89a3-d95dd77d36e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2607 | T16182-CA03-P0UMY-185163 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82859beb-f1b5-4fd3-8a77-7c9a9a6fbaea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2608 | T16182-CA03-P0UMY-185164 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba84ab8b-d4bb-4767-a913-acd3a3a91293 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2609 | T16182-CA03-P0UMY-185165 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d469c739-4fab-434e-8a66-046367c46a2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2610 | T16182-CA03-P0UMY-185166 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=329ca144-d2ea-415c-beca-0366a2c77e54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2611 | T16182-CA03-P0UMY-185167 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e621573f-c983-45a9-b862-d9dc59c46127 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2612 | T16182-CA06-P0UMY-185191 | 2017-06-27 | DHI-TRANSMIT-000405 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f94077fe-6e10-4d1a-bc19-d6df43fc8cef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2613 | T16182-YT01-P0BT-151011 | 2017-06-27 | DHI-WTRAN-000370 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b83de576-6711-4086-a8c4-7f772ff03fe5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2614 | T16182-XW03-P0SAR-134201 | 2017-06-27 | DHI-WTRAN-000371 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1c746bc-887e-49f6-887b-b06b6b5cb3e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2615 | T16182-XG07-P0SAR-134202 | 2017-06-27 | DHI-WTRAN-000371 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3354bf75-b4f1-4e3e-99be-349f218b3a83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2616 | T16182-XW03-P0SAR-134203 | 2017-06-27 | DHI-WTRAN-000371 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7f264ae-b626-43b0-9bf6-47ef28354e2d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2617 | T16182-XH02-P0SAR-134204 | 2017-06-27 | DHI-WTRAN-000371 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d462095-3389-444d-9487-d74d1ce20d45 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2618 | T16182-XG02-P0SGC-137201 | 2017-06-27 | DHI-WTRAN-000372 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19e87aad-38c7-43c2-84fa-cdf098e0ae99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2619 | T16182-XH01-P0SGC-137211 | 2017-06-27 | DHI-WTRAN-000372 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5163d1b2-4369-4b14-80a6-d8420720de1a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2620 | T16182-YT10-P0SGC-137221 | 2017-06-27 | DHI-WTRAN-000372 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=537ecc87-e234-4bf0-bfd1-e84ad2aeb8c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2621 | T16182-XB02-P0UMX-171007 | 2017-06-27 | DHI-TRANSMIT-000406 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd92ab03-c6de-423f-a0b2-94e9ed8f43e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2622 | T16182-XB02-P0UMX-171008 | 2017-06-27 | DHI-TRANSMIT-000406 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df7347f3-2647-4f35-ad5e-474d1ebd7005 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2623 | T16182-XB02-P0UMX-171009 | 2017-06-27 | DHI-TRANSMIT-000406 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11dbfb50-4a7e-4c13-be8f-09597d581a0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2624 | T16182-VK02-P0UMX-171012 | 2017-06-27 | DHI-TRANSMIT-000406 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b40d2ab-d9a5-4ae1-aaff-afdc43a778bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2625 | T16182-YF00-P0GCF-130018 | 2017-06-29 | DHI-WTRAN-000374 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2626 | T16182-YK00-P0GCF-130016 | 2017-06-29 | DHI-WTRAN-000375 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2627 | T16182-YE01-P0BAU-152602 | 2017-06-29 | DHI-WTRAN-000385 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beafe7d2-c491-464e-b67f-3da25ff9d3d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2628 | T16182-YE00-P0ZEN-152717 | 2017-06-29 | DHI-WTRAN-000384 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ea3ca42-46be-43d8-befd-609ca5c6accd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2629 | T16182-YR02-P0CJN-290014 | 2017-06-29 | DHI-WTRAN-000383 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5867c9b-f2c9-4f2d-ae40-221b6122558b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2630 | T16182-YB11-P0ZEN-152402 | 2017-06-29 | DHI-WTRAN-000382 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7008295a-815c-47d2-bda2-09218d8d086a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2631 | T16182-YU03-P0BAT-150631 | 2017-06-29 | DHI-WTRAN-000381 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19d52d1e-10a9-4aba-926f-da9fb042695b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2632 | T16182-YU03-P0BAT-150636 | 2017-06-29 | DHI-WTRAN-000381 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c053dc9f-e600-4d86-a6bf-4921c8cb2b8a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2633 | T16182-YU03-P0BBT-150681 | 2017-06-29 | DHI-WTRAN-000381 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edf25be2-2cb2-4a41-821e-29a336c9344a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2634 | T16182-YT01-P0LF-110101 | 2017-06-29 | DHI-WTRAN-000380 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81039e84-eccb-4b5b-b118-2ed0ea973931 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2635 | T16182-YK08-P0LF-110102 | 2017-06-29 | DHI-WTRAN-000380 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3029c81-d6a4-484c-873a-37c044b2fdb6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2636 | T16182-VN02-P0LB-122089 | 2017-06-29 | DHI-WTRAN-000379 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=636a90c2-5fa3-4ee3-938d-ca6766c524a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2637 | T16182-CV03-P0CWQ-161132 | 2017-06-29 | DHI-WTRAN-000378 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2217b63-2206-4fa1-8af4-9577b3b0729d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2638 | T16182-YS01-P0MKY-290011 | 2017-06-29 | DHI-WTRAN-000377 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70d922e5-f3f9-44c2-9e3c-8165c067a370 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2639 | T16182-XG02-P8ZEN-125586 | 2017-06-29 | DHI-WTRAN-000376 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2640 | T16182-XG02-P8ZEN-125590 | 2017-06-29 | DHI-WTRAN-000376 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2641 | T16182-YE03-P0BAU-152511 | 2017-06-29 | DHI-TRANSMIT-000432 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d37e1503-eb2f-4c25-b335-64c810897d98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2642 | T16182-YE03-P6BAU-152508 | 2017-06-29 | DHI-TRANSMIT-000432 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f9c0ff1-f2c8-4736-9c6c-7c3b4afa3a9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2643 | T16182-YE03-P7BAU-152509 | 2017-06-29 | DHI-TRANSMIT-000432 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e980584-a040-4e73-bd97-41530e12e76e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2644 | T16182-YS01-P0MKY-290011 | 2017-06-29 | DHI-TRANSMIT-000421 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2645 | T16182-YR02-P0CJN-290014 | 2017-06-29 | DHI-TRANSMIT-000422 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2646 | T16182-CV03-P0CRN-161103 | 2017-06-29 | DHI-TRANSMIT-000423 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b1b19c7-2b57-4672-81e3-08542a5bf9f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2647 | T16182-CV03-P0CWQ-161132 | 2017-06-29 | DHI-TRANSMIT-000424 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2648 | T16182-YU02-P0ZEN-150211 | 2017-06-29 | DHI-TRANSMIT-000425 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c205871-7774-481d-a6e9-f1d6fd8f4dea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2649 | T16182-YU02-P0ZEN-150212 | 2017-06-29 | DHI-TRANSMIT-000425 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=512ae29f-9b58-4b13-82de-8c9541d0913a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2650 | T16182-CV03-P0CRN-161104 | 2017-06-29 | DHI-TRANSMIT-000426 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=763a29f3-e319-4b00-8fd5-3621e24c9ad7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2651 | T16182-XB02-P0LB-122017 | 2017-06-29 | DHI-TRANSMIT-000427 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de32ccda-bb89-4edc-a807-ccda6ebbd229 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2652 | T16182-XB02-P0LB-122019 | 2017-06-29 | DHI-TRANSMIT-000427 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=076dd3ed-b5b9-422e-abf1-0870324b11e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2653 | T16182-XG02-P0GNR-130103 | 2017-06-29 | DHI-TRANSMIT-000428 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29c9b028-9642-4400-89a9-9f008f09a2fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2654 | T16182-XG07-P0GNR-130102 | 2017-06-29 | DHI-TRANSMIT-000428 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88dcf549-a842-4b12-a915-fe1024a69fff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2655 | T16182-XS00-P0GCF-130001 | 2017-06-29 | DHI-TRANSMIT-000428 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4de58dd-0606-4626-b145-384dbf027c38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2656 | T16182-XS00-P0GNR-130101 | 2017-06-29 | DHI-TRANSMIT-000428 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1134e5b5-91b1-43bd-9caf-69e2a2d36359 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2657 | T16182-YB11-P0ZEN-152402 | 2017-06-29 | DHI-TRANSMIT-000429 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2658 | T16182-YQ01-P0ZEN-152201 | 2017-06-29 | DHI-TRANSMIT-000430 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe4266c3-98f1-484c-a59b-09c9390c429a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2659 | T16182-CA00-P0UBA-181001 | 2017-06-29 | DHI-TRANSMIT-000431 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=330c81c7-2ccf-4720-8d23-f2aab6edd32c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2660 | T16182-CA01-P0UBA-181054 | 2017-06-29 | DHI-TRANSMIT-000431 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7383600c-0ad9-4dad-ba19-1f2021443e1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2940 | T16182-CA00-P0UBA-181208 | 2017-06-29 | DHI-TRANSMIT-000433 | IFR | C | DR | TRUE | TRUE | 2017-10-11_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77f744e2-6633-4aae-924b-146ef6591570 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2661 | T16182-CA00-P0UBA-181208 | 2017-06-30 | DHI-TRANSMIT-000433 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=794863b3-7e58-4449-8186-8f59fc8f381f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2662 | T16182-YL06-P0ZEN-150101 | 2017-06-30 | DHI-TRANSMIT-000434 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2663 | T16182-VE04-P0UNX-171401 | 2017-06-30 | DHI-TRANSMIT-000435 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1897fbe7-2556-4c24-bb6d-5877e1bda77f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2664 | T16182-XB02-P0UNX-171402 | 2017-06-30 | DHI-TRANSMIT-000435 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b40dfa0-fbc3-4598-b652-c9b84a53055c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2665 | T16182-XB02-P0UNX-171403 | 2017-06-30 | DHI-TRANSMIT-000435 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4643ce5a-977b-48db-ab69-3a2047020977 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2666 | T16182-XB02-P0UNX-171410 | 2017-06-30 | DHI-TRANSMIT-000435 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c25d1cdd-7598-417f-be39-7b52277691d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2667 | T16182-VE04-P0UAG-172101 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=837bf45c-f281-4172-977a-824fc1f2860a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2668 | T16182-VE04-P0UAG-172151 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=133a98bc-cd50-4150-b434-7d867d20e6ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2669 | T16182-VK02-P0UAG-172109 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad875e0c-adfa-4092-a784-0aff4bc2b447 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2670 | T16182-VK02-P0UAG-172170 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b27bf8a-cff9-489c-8e4c-1c568323032c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2671 | T16182-XB02-P0UAG-172100 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e306af4-9d20-47e7-b9c3-46878dae79f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2672 | T16182-XB02-P0UAG-172102 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6976a979-ad39-4fdb-a6e9-65586519155f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2673 | T16182-XB02-P0UAG-172108 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3b1b5fd-6eb1-425e-b2fb-d42282e47c71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2674 | T16182-XB02-P0UAG-172162 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d055ebd-486a-4883-b1c3-b249d6bc913d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2675 | T16182-XB02-P0UAG-172168 | 2017-06-30 | DHI-TRANSMIT-000436 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a6c41ab-c502-4414-a46c-7c71a883e6cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2676 | T16182-CV03-P0CWQ-161123 | 2017-06-30 | DHI-TRANSMIT-000437 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d628850-0b9f-461d-ac42-4bbe4df6da13 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2677 | T16182-YL06-P0ZEN-150101 | 2017-06-30 | DHI-WTRAN-000392 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4928e7a-1b95-4b2f-a31c-65dbb43c2376 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2678 | T16182-YE03-P0BAU-152528 | 2017-06-30 | DHI-WTRAN-000391 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ef1feb4-76fc-46d7-b4b1-4a51ba38d20c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2679 | T16182-XH01-P6MKA-260004 | 2017-06-30 | DHI-WTRAN-000390 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99fc7827-945b-403b-b526-84654127e135 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2680 | T16182-XH01-P7MKA-260007 | 2017-06-30 | DHI-WTRAN-000390 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f24275e9-bcfb-4b73-acb4-bf2f4403bd47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2681 | T16182-YD00-P0CYE-137441 | 2017-06-30 | DHI-WTRAN-000389 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1ed79ee-cd08-46ef-989b-6421afd8bcb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2682 | T16182-YU02-P0CYE-137442 | 2017-06-30 | DHI-WTRAN-000389 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c44c005-d31e-43c8-b802-9bb9864a544d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2683 | T16182-CV03-P0SAY-163403 | 2017-06-30 | DHI-WTRAN-000388 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d06bc7b-67e4-41da-bb1e-fedd9f352b9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2684 | T16182-CN00-P0ZEN-110702 | 2017-06-30 | DHI-WTRAN-000387 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a0c6c48-5441-4bd7-bd37-a7e464af595b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2685 | T16182-XS00-P0MJ-110510 | 2017-06-30 | DHI-WTRAN-000386 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24a6ddbf-1e13-41ff-97f0-d1530ad489db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2686 | T16182-CA00-P0UGD-181908 | 2017-06-30 | DHI-WTRAN-000395 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9edb3189-31df-413e-99ee-3a1df66b62df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2687 | T16182-CA00-P0UGD-181909 | 2017-06-30 | DHI-WTRAN-000395 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38f0d517-de8f-487c-9318-1880b08ce17e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2688 | T16182-CA00-P0UGD-181910 | 2017-06-30 | DHI-WTRAN-000395 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2b9c951-70cf-4b9e-89d9-83828e8002a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2689 | T16182-CA00-P0UGD-181911 | 2017-06-30 | DHI-WTRAN-000395 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67c3851e-f928-493e-a396-389b9c9d18d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2690 | T16182-CA00-P0UGD-181912 | 2017-06-30 | DHI-WTRAN-000395 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34204532-cd1e-4f06-8ce6-31b4277bfbe6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2691 | T16182-CA00-P0UGD-181913 | 2017-06-30 | DHI-WTRAN-000395 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8d5064c-34d8-4d1b-bb6e-5cab5149f698 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2692 | T16182-CA00-P0UGD-181914 | 2017-06-30 | DHI-WTRAN-000395 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1583356-2098-41b1-b326-859643e2f95e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2693 | T16182-YE00-P0CJN-290005 | 2017-06-30 | DHI-WTRAN-000394 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2832de95-de8a-42d5-8b3f-1c1c5ba6ec83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2694 | T16182-XH01-P6UMA-140021 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37496bb9-b144-4441-bbee-5450a6d34b35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2695 | T16182-XH01-P6UMA-140022 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ba2f9da-6e8f-4553-989f-a24006de27cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2696 | T16182-XH01-P7UMA-140023 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f606da0a-c8f3-4888-88dd-b31d6fbbbb62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2697 | T16182-XH01-P7UMA-140024 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26a8b0a1-d123-4539-a1fe-8f846552e41b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2698 | T16182-XH01-P6UMA-140025 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=901140d4-e8e3-44a0-a1ee-754cd3adb2b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2699 | T16182-XH01-P7UMA-140026 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c8a9c96-2add-46ff-86ce-202e93b0d1be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2700 | T16182-XH01-P0ULY-140027 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b691a74b-b427-4788-9c6d-8ff4cec3ecb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2701 | T16182-XH01-P0ULY-140028 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df5d949c-a272-4393-b81c-5ca0d3b6fe1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2702 | T16182-XH01-P0ULY-140029 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92e5e768-b25f-4c92-9df8-363cfc733d5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2703 | T16182-XH01-P0ULY-140030 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b87c8ff1-c12e-4bc8-a518-3e9c61821da1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2704 | T16182-XH01-P0ZEN-140031 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b20831f-e666-470d-a1c3-cbac68b06b76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2705 | T16182-XH01-P1UHA-140032 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b84cedda-c7fb-46cd-9fb5-061c21bd42ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2706 | T16182-XH01-P1UHA-140034 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad7ed7d6-3de8-4835-8685-3c6b7a34391c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2707 | T16182-XH01-P1UHA-140036 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53c40301-d61b-4f35-b20d-1113ef67e8ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2708 | T16182-XH01-P2UHA-140037 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=529321c2-8d3c-4dc0-a023-7a328d45aa7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2709 | T16182-XH01-P2UHA-140038 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d073fdc-4104-4ff4-9f65-6f54ce6f48ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2710 | T16182-XH01-P2UHA-140039 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a29999e2-ec1f-46e1-9828-80d9af23df06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2711 | T16182-XH01-P3UHA-140040 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5eabc1ea-c437-4a52-ba2a-80d54abc4212 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2712 | T16182-XH01-P3UHA-140041 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09f39b40-9a1f-4d34-b9ab-48c29043571c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2713 | T16182-XH01-P3UHA-140042 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4318b08-2d2b-4c76-a24c-7e1797edccc8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2714 | T16182-XH01-P4UHA-140043 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e737803-009e-41f8-a017-6b6c133a7c95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2715 | T16182-XH01-P4UHA-140044 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a1b822c-4392-4e45-adfb-d0ae181e7a38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2716 | T16182-XH01-P4UHA-140045 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=102b5a5a-ccc4-4a79-9545-47e9c17bd083 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2717 | T16182-XH01-P5UHA-140046 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95e85727-9cb4-4c3d-96c8-35dc8946eeca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2718 | T16182-XH01-P5UHA-140047 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=424b548b-27c0-4fc1-aaad-aa0882614ebc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2719 | T16182-XH01-P5UHA-140048 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f09d2959-b7d5-4def-9a96-33e9d81c9b61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2720 | T16182-XH01-P1MBA-140049 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e9589e2-4d7d-4d71-be5c-ae97a887320e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2721 | T16182-XH01-P2MBA-140050 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a9b3347-535f-4cbd-ae05-1f49980d81cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2722 | T16182-XH01-P3MBA-140051 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6b789d1-686e-4f97-b377-a451e3160f38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2723 | T16182-XH01-P4MBA-140052 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee040084-99e6-4d15-860e-0f978edd1655 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2724 | T16182-XH01-P5MBA-140053 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99ec0033-3088-483a-878b-c61313b04402 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2725 | T16182-XH01-P0ULA-140054 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8caea211-1b1b-44e1-b74a-0aa2c5f561c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2726 | T16182-XH01-P0ULA-140055 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6217211-c319-4d61-b938-79f48de1ce5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2727 | T16182-XH01-P0ULA-140056 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67122d5f-e17c-4e78-b85b-5ad2cb68648b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2728 | T16182-XH01-P0ULA-140057 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abc87c8e-2df6-4c88-96f5-5c14d17a6574 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2729 | T16182-XH01-P0ULY-140058 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b1d6d5a-bd46-4fcf-a63c-373b831bfe5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2730 | T16182-XH01-P0ULY-140059 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7390ec47-faeb-450a-919c-b127d38ee73e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2731 | T16182-XH01-P0ULY-140060 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b2662d3-cec0-4c89-901c-1d436823af89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2732 | T16182-XH01-P0ULY-140061 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e56bdcf1-a439-4006-8403-5fb8d4ac1534 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2733 | T16182-XH01-P0UYE-140074 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c203257c-aaf4-4e4d-879f-6e4f889a4921 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2734 | T16182-XH01-P0UYF-140075 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4ed50f5-91db-4345-8a29-c5ed80632de7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2735 | T16182-XH01-P0UYC-140076 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe87d2cf-cb93-4b57-9122-ec199a7699e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2736 | T16182-XH01-P0UST-140077 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb3b996f-0226-4e40-9407-b1c7aa3988c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2737 | T16182-XH01-P0UYP-140078 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d405f168-55ef-42a6-968a-fe3c930d2c1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2738 | T16182-XH01-P7UBA-140079 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e6fc598-56ac-4988-9504-a490aa096b4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2739 | T16182-XH01-P6UBA-140080 | 2017-06-30 | DHI-WTRAN-000393 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74ebbf59-6df7-4b89-adba-0e4811b0bbe3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2740 | T16182-UT01-P0GQB-173413 | 2017-06-30 | DHI-WTRAN-000396 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eebaab37-3b8a-4541-8940-9c0f9c93b0bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2741 | T16182-VE04-P0GQB-173401 | 2017-06-30 | DHI-TRANSMIT-000439 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1d8b73b-b6b3-46f7-a4a6-d3ba94cae40e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2742 | T16182-UT01-P0GQB-173402 | 2017-06-30 | DHI-TRANSMIT-000439 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cfae9f9-2601-4af6-8a6f-6d00e8eff4eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2743 | T16182-UT01-P0GQB-173403 | 2017-06-30 | DHI-TRANSMIT-000439 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=079e2d9e-b5c2-4aab-9989-647aff3dd862 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2744 | T16182-VK02-P0GQB-173417 | 2017-06-30 | DHI-TRANSMIT-000439 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=742f3a35-4503-4f86-aba0-c0361be4483e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2745 | T16182-VE04-P0UEG-171501 | 2017-06-30 | DHI-TRANSMIT-000438 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd492897-29bd-4e41-9648-1d45567b5e71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2746 | T16182-XB02-P0UEG-171502 | 2017-06-30 | DHI-TRANSMIT-000438 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04bef802-6cee-442f-90bd-0a82d1104870 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2747 | T16182-XB02-P0UEG-171504 | 2017-06-30 | DHI-TRANSMIT-000438 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=508f2e62-72e3-4881-90fa-996d086c08c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2748 | T16182-YU02-P0BT-151021 | 2017-07-03 | DHI-WTRAN-000397 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c7c89c3-c705-4038-8feb-6e8e635fc642 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2749 | T16182-YU02-P0BT-151026 | 2017-07-03 | DHI-WTRAN-000397 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f6798a6-747b-4f14-b2d1-f7cc5f6b1b0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2750 | T16182-YU02-P0BT-151031 | 2017-07-03 | DHI-WTRAN-000397 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=280e5233-5aea-4037-99b4-7c3a6d24c250 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2751 | T16182-VE04-P0GUC-172801 | 2017-07-03 | DHI-WTRAN-000398 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e0ae96c-e87d-4eb8-a126-98bf95da12c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2752 | T16182-XB02-P0GUC-172802 | 2017-07-03 | DHI-WTRAN-000398 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e770145-3b68-4aaa-a83e-5a8037592b6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2753 | T16182-VK02-P0GUC-172804 | 2017-07-03 | DHI-WTRAN-000398 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2090130-8405-43a9-9f89-ad756dfa9d80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2754 | T16182-YD00-P0BAA-150767 | 2017-07-03 | DHI-WTRAN-000399 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=234e3f75-bd3f-4862-81a2-f15f82342942 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2755 | T16182-YD00-P0BAA-150771 | 2017-07-03 | DHI-WTRAN-000399 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53824290-721a-4162-9bbe-c72375189a5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2756 | T16182-YD00-P0BAA-150776 | 2017-07-03 | DHI-WTRAN-000399 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0483e5c3-c96d-4939-a358-059b8e1bb7e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2757 | T16182-YD00-P0CYE-138241 | 2017-07-03 | DHI-WTRAN-000400 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e13b587-76a2-4f47-8ef5-ac61639183e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2758 | T16182-YU02-P0CYE-138242 | 2017-07-03 | DHI-WTRAN-000400 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4070beb7-b0c8-49c4-95db-6727b29539e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2759 | T16182-YD00-P0CYE-138341 | 2017-07-03 | DHI-WTRAN-000401 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7754167d-c009-4357-a677-f5c703e8206b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2760 | T16182-YU02-P0CYE-138342 | 2017-07-03 | DHI-WTRAN-000401 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=103800da-9cad-44fc-bc53-cc8efffe59a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2761 | T16182-YT10-P0ZEN-150301 | 2017-07-03 | DHI-WTRAN-000402 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a802882a-5586-4518-98ed-aaa3056becee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2762 | T16182-YT10-P0ZEN-150302 | 2017-07-03 | DHI-WTRAN-000402 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3423ae78-84cd-4b36-886e-4718d1b37f12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2763 | T16182-YS00-P0LB-122092 | 2017-07-03 | DHI-WTRAN-000403 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6256c75a-9249-488e-9ba0-b8561e1dae12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2764 | T16182-XS00-P0EKG-120019 | 2017-07-03 | DHI-TRANSMIT-000443 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b8c71ee-7bb2-4024-b2ef-89161d77fae5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2807 | T16182-XB02-P0GUC-172803 | 2017-07-03 | DHI-WTRAN-000398 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae27ce17-070e-451b-841e-af93d74e1d4b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2765 | T16182-CA06-P0UTG-184900 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a78452c5-168c-4b9e-a2d9-6ac44aba78de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2766 | T16182-CA00-P0UTG-184901 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05d770d9-819d-4d38-bb9e-25fe80b0e48a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2767 | T16182-CA00-P0UTG-184902 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b13bc4da-ebdd-4c8c-85c4-f6893a51d1fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2768 | T16182-CA00-P0UTG-184903 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50f8b146-d4f4-440f-8aef-fcd279557d5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2769 | T16182-CA01-P0UTG-184951 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=311f1394-8e31-402e-8ea1-c75b3a22a46a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2770 | T16182-CA01-P0UTG-184952 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e81cf4a4-321f-430a-bdaf-ae3182fcb274 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2771 | T16182-CA01-P0UTG-184953 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f2a139e-2875-45e6-8eca-8a0150d419f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2772 | T16182-CA02-P0UTG-184954 | 2017-07-04 | DHI-WTRAN-000405 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1150793e-6e4e-4190-95be-641421d9bc61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2773 | T16182-XG07-P0SAH-133402 | 2017-07-04 | DHI-WTRAN-000406 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=083812b5-bd90-4487-8aa7-13edc1750f7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2774 | T16182-XH02-P0SAH-133404 | 2017-07-04 | DHI-WTRAN-000406 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee30f25c-2ff7-48d0-a58a-742df5ea9070 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2775 | T16182-XW03-P0SAH-133401 | 2017-07-04 | DHI-WTRAN-000406 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25a79510-7378-4122-b912-790464cfbbe8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2776 | T16182-XW03-P0SAH-133403 | 2017-07-04 | DHI-WTRAN-000406 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adf5b922-d907-4c9b-b3ab-b98bb62b66c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2777 | T16182-VE04-P0ULX-171201 | 2017-07-04 | DHI-TRANSMIT-000444 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1382e303-dae2-466b-bad8-63e91dbed945 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2778 | T16182-XB02-P0ULX-171202 | 2017-07-04 | DHI-TRANSMIT-000444 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63cb1b10-abae-4adf-a54c-6b2bc05edae6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2779 | T16182-XB02-P0ULX-171203 | 2017-07-04 | DHI-TRANSMIT-000444 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ad78a53-b117-43d0-800d-6f3a9b60affa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2780 | T16182-CA01-P0UBA-181153 | 2017-07-04 | DHI-TRANSMIT-000445 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8d6f540-efb0-4477-8ae5-77bb6f1155d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2781 | T16182-CA01-P0UBA-181154 | 2017-07-04 | DHI-TRANSMIT-000445 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55b239d3-215c-47d4-8dac-265097c976cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2782 | T16182-YD00-P0UBA-150506 | 2017-07-04 | DHI-TRANSMIT-000446 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2783 | T16182-YD00-P0UBA-150506 | 2017-07-04 | DHI-TRANSMIT-000447 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61510c11-d5f5-4c04-8456-1c1e79176c7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2784 | T16182-YD00-P0UBA-150504 | 2017-07-04 | DHI-TRANSMIT-000448 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=301e6ec5-573e-4ada-85a0-353d4c808b67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2785 | T16182-YD00-P0UBA-150505 | 2017-07-04 | DHI-TRANSMIT-000448 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33cf5cbd-e8cf-438f-91e7-233c5386fba7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2786 | T16182-YR05-P0CJN-290004 | 2017-07-04 | DHI-TRANSMIT-000449 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2787 | T16182-YR05-P0CJN-290004 | 2017-07-04 | DHI-WTRAN-000407 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15703298-c55a-42b6-84c9-766fdb38879a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2806 | T16182-YE00-P0MJ-110512 | 2017-07-04 | DHI-WTRAN-000404 | IFI | 0 | D | TRUE | FALSE | 2017-07-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bacc6d3-b336-4157-b62d-bd2abd6bfd2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2788 | T16182-XW03-P0LD-130205 | 2017-07-05 | DHI-WTRAN-000409 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e49947fa-1c3a-4a47-abbf-1da6f0d6078c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2789 | T16182-YD00-P0LD-130202 | 2017-07-05 | DHI-WTRAN-000409 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=549c8569-42fa-4e01-a326-75de7f70db09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2790 | T16182-XG07-P0LD-130203 | 2017-07-05 | DHI-WTRAN-000409 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5fc9c2e-d7f9-4e4d-bb9e-318ac45a36f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2791 | T16182-YD00-P0BT-151041 | 2017-07-05 | DHI-WTRAN-000410 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ac9e0f1-f87e-4bac-9935-06984cbcd0c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2792 | T16182-YD00-P0BT-151046 | 2017-07-05 | DHI-WTRAN-000410 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9cbd648d-3f1f-4a5e-83d1-7fa275092d60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2793 | T16182-YD00-P0BT-151051 | 2017-07-05 | DHI-WTRAN-000410 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82a0846d-443f-4ec7-b723-5bba4c42604d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2794 | T16182-YD00-P0BB-150821 | 2017-07-05 | DHI-WTRAN-000411 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32e93eb8-abd1-4237-80c9-16445bdfef2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2795 | T16182-YU02-P0BB-150811 | 2017-07-05 | DHI-WTRAN-000411 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c01d0684-2311-499a-a2b3-887fbeddbb34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2796 | T16182-CA00-P0UBA-181104 | 2017-07-05 | DHI-WTRAN-000408 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2797 | T16182-YB03-P0CRN-161114 | 2017-07-05 | DHI-WTRAN-000412 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a542b6c1-b71f-4ba8-9b2c-b014ce48ddcb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2798 | T16182-YL16-P0CRN-161115 | 2017-07-05 | DHI-WTRAN-000412 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41dc07be-fc32-4920-aaa9-55ad539a2df2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2799 | T16182-CV03-P0CWQ-161133 | 2017-07-05 | DHI-WTRAN-000412 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a7a3c66-f8cf-4118-a8c1-544488765082 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2800 | T16182-CV03-P0CWQ-161132 | 2017-07-05 | DHI-TRANSMIT-000450 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9065b5d5-2444-49f2-b4bf-a9991b4cf8e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2801 | T16182-CV03-P0CRN-161105 | 2017-07-05 | DHI-TRANSMIT-000450 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=becbb331-a35f-4c99-972e-f49ea2648eea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2802 | T16182-CA00-P0UBA-186101 | 2017-07-05 | DHI-TRANSMIT-000451 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=352bf69d-87bd-4ef5-8da7-9ac5a54eb919 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2803 | T16182-CA00-P0UBA-186104 | 2017-07-05 | DHI-TRANSMIT-000451 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e999e7a8-6ce5-4b5d-a5ca-daaab7fb8677 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2804 | T16182-CA01-P0UBA-186152 | 2017-07-05 | DHI-TRANSMIT-000451 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88e426e7-cc6c-4175-acdb-6c9d7dc266e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2805 | T16182-YD02-P8ZEN-125762 | 2017-07-05 | DHI-TRANSMIT-000452 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5acfec3-2db2-46c2-884f-b000277dadac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2810 | T16182-YU02-P0BB-150812 | 2017-07-05 | DHI-WTRAN-000411 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11b47bc5-af5f-4979-8f7f-eecc6d37dcfd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2811 | T16182-YU02-P0BB-150813 | 2017-07-05 | DHI-WTRAN-000411 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3735be16-d1ed-4ed3-ab17-6a1f3a0b5f22 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2812 | T16182-YU02-P0BB-150814 | 2017-07-05 | DHI-WTRAN-000411 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f7c6c0e-9192-49af-88a0-9d9b0ad84626 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2813 | T16182-YU02-P0BB-150815 | 2017-07-05 | DHI-WTRAN-000411 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fc25953-9ad3-426b-985f-05e8d81e4944 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2814 | T16182-YU02-P0BB-150816 | 2017-07-05 | DHI-WTRAN-000411 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5fb4a15-aa59-4f31-98b7-eb2b88eb4dd9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2815 | T16182-YQ08-P0CY-154031 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=398d9dd3-5230-47f3-9712-09276d8742e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2816 | T16182-YQ08-P0CY-154032 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74d39e0b-8174-48a8-b62e-444a5364f392 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2817 | T16182-YQ08-P0CY-154033 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e8a3e1c-0b09-43b5-8b0c-b86ca106c156 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2818 | T16182-YQ08-P0CY-154034 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fca51ca4-9f12-4f3b-81df-666d6b64fa6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2819 | T16182-YQ08-P0CY-154035 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04f2024b-421f-4308-bbc0-8393f22875e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2820 | T16182-YQ08-P0CY-154037 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe8f8b10-a9f3-4aa8-9b0b-feefb9f380f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2821 | T16182-YQ08-P0CY-154048 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08e654c0-864f-4c7f-a739-59a01cbe5bf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2822 | T16182-YQ08-P0CY-154051 | 2017-07-06 | DHI-TRANSMIT-000453 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5739b78b-da57-4ba6-ae37-0c0a86dcbf7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2823 | T16182-CA06-P0UYC-182900 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa55939f-7169-4f8c-94a8-9453e0d5ecd4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2824 | T16182-CA01-P0UYC-182951 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5875de6c-cf34-4ae5-98a0-df37f6374225 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2825 | T16182-CA01-P0UYC-182952 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=560d424b-1328-4e4a-95bb-dfc11782bae9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2826 | T16182-CA01-P0UYC-182953 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4a34cec-b8f2-4e27-b972-e4d421679cbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2827 | T16182-CA01-P0UYC-182954 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2d7ba36-c2d5-4735-a434-2ad89a9faa1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2828 | T16182-CA01-P0UYC-182955 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd45d2fb-93af-4d6c-8fc9-469490f00a60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2829 | T16182-CA01-P0UYC-182956 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c855c7af-a73a-429f-8f7e-78f7309f7bdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2830 | T16182-CA02-P0UYC-182957 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afb6af63-7292-47e6-9acb-a22c1eefa3a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2831 | T16182-CA02-P0UYC-182958 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0759d298-c106-432c-acdb-6c3bb2c8a716 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2832 | T16182-CA00-P0UYC-182902 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=536d9b73-445b-4402-b64b-83bdc6b683eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2833 | T16182-CA00-P0UYC-182904 | 2017-07-06 | DHI-TRANSMIT-000454 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a6e3976-e186-4d74-81a7-e4d0e2227bc1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2834 | T16182-CA00-P0UYC-182901 | 2017-07-06 | DHI-WTRAN-000413 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0be7ecb-0795-4d1c-878b-1a0444d4d1b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2835 | T16182-CA00-P0UYC-182903 | 2017-07-06 | DHI-WTRAN-000413 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5458f3eb-054d-4769-bc46-f0f731ff441d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2836 | T16182-CA00-P0UYC-182905 | 2017-07-06 | DHI-WTRAN-000413 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75cd60a7-b859-42cf-8f25-d50aeda9dced | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2837 | T16182-CA00-P0UYC-182906 | 2017-07-06 | DHI-WTRAN-000413 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a624baa-785a-4a93-b63e-62944bd7f876 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2838 | T16182-CV03-P0ZEN-165731 | 2017-07-06 | DHI-WTRAN-000414 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87f38697-d353-4f23-a6df-10eadb53445d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2839 | T16182-XS00-P0LD-130201 | 2017-07-06 | DHI-WTRAN-000415 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=008c10e8-79f7-484f-bf1c-d4823bee62d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2840 | T16182-YU02-P0MKY-290006 | 2017-07-06 | DHI-TRANSMIT-000455 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b598287-44d3-4656-8139-bbc644f10151 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2841 | T16182-DP00-P8ZEN-125749 | 2017-07-06 | DHI-WTRAN-000416 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4cb3372-bec3-41e8-bdd2-a4f87205e9f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2842 | T16182-DP00-P8ZEN-125763 | 2017-07-06 | DHI-WTRAN-000416 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a6f4096-5520-4d43-b09e-44a7eac60099 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2843 | T16182-DP00-P8ZEN-125766 | 2017-07-06 | DHI-WTRAN-000416 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea0d84bd-821a-41cc-9502-8bef3c5c21dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2844 | T16182-YE01-P8ZEN-125768 | 2017-07-06 | DHI-WTRAN-000416 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d122c39a-b901-4cd2-90e9-711ac9c1e77f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2845 | T16182-YT02-P8ZEN-125719 | 2017-07-06 | DHI-WTRAN-000417 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=654e4b9d-4158-4992-8696-33897969cf7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2846 | T16182-YE03-P0BAU-152519 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30e64b26-5e04-4a36-9854-b8c6fb519135 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2847 | T16182-YE03-P0BAU-152520 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2b6c6c3-5a63-4526-822a-163cdfdf14cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2848 | T16182-YE03-P0BAU-152521 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8a4c49c-d380-490b-8e90-d24daa9b4586 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2849 | T16182-YE03-P0BAU-152522 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=163c17cc-3e02-4813-9699-1e90c101fdb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2850 | T16182-YE03-P0BAU-152524 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b629fd8-3f3b-44d5-bb1a-9bae4c040a83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2851 | T16182-YE03-P0BAU-152528 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bca669c8-5879-4221-a44a-8cd3bc43ba2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2852 | T16182-YE03-P0BAU-152532 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6ecc02c-ce0f-4a5a-8ebe-2b9933238611 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2853 | T16182-YE03-P0BAU-152507 | 2017-07-07 | DHI-TRANSMIT-000456 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b5d7efd-ced2-44f4-9c7b-58c9d316e9b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2854 | T16182-YS01-P0MKY-290011 | 2017-07-07 | DHI-TRANSMIT-000457 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a106fede-c4f2-4898-a708-331c0204cb5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2855 | T16182-YS01-P0MKY-290012 | 2017-07-07 | DHI-WTRAN-000418 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ca18d8f-d590-42e6-97d9-eaf44ba80c10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2856 | T16182-YS01-P0MKY-290013 | 2017-07-07 | DHI-WTRAN-000418 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=880e2c32-0e32-4c5c-bbc4-a27b7c7f80b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2857 | T16182-YL01-P0PCA-126526 | 2017-07-07 | DHI-WTRAN-000419 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc93c380-8064-476e-ae16-dd22ba2d6522 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2858 | T16182-CV03-P0CRT-161149 | 2017-07-07 | DHI-WTRAN-000420 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74ec87ea-6a05-4394-b391-a1d0887054cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2859 | T16182-CN00-P0ZEN-110701 | 2017-07-07 | DHI-TRANSMIT-000458 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8042be57-75ed-4ef2-bde5-279ef22fc997 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2860 | T16182-XB02-P0UHA-171815 | 2017-07-07 | DHI-WTRAN-000421 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=396da43d-914a-4978-b2f4-e0e32945c0e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2861 | T16182-XB02-P0UHA-171816 | 2017-07-07 | DHI-WTRAN-000421 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85ac98a0-d1ac-494f-be4e-8609b19089d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2862 | T16182-YE00-P0ZEN-152705 | 2017-07-07 | DHI-TRANSMIT-000459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be222492-823d-42e9-8b0a-4fd1f952ad20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2863 | T16182-YE00-P0ZEN-152706 | 2017-07-07 | DHI-TRANSMIT-000459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=163f3e3e-f10c-4fc3-9c9f-f37466264d5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2864 | T16182-YE00-P0ZEN-152708 | 2017-07-07 | DHI-TRANSMIT-000459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c54aacf-2d8c-4fdb-9f60-06b554593574 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2865 | T16182-YE00-P0ZEN-152719 | 2017-07-07 | DHI-TRANSMIT-000459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=373223d2-edd7-44ef-a5c0-fe9d30736e88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2866 | T16182-YE00-P0ZEN-152721 | 2017-07-07 | DHI-TRANSMIT-000459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=899be22b-a459-4756-8c10-33fbcdc839ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2867 | T16182-YE00-P0ZEN-152722 | 2017-07-07 | DHI-TRANSMIT-000459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17e0a4b5-363f-4937-9ac4-a51b319c989d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2868 | T16182-YE00-P0ZEN-152726 | 2017-07-07 | DHI-TRANSMIT-000459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d973942-c221-4a8f-a28c-f8db84686601 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2923 | T16182-VE04-P0UHA-171819 | 2017-07-07 | DHI-WTRAN-000421 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13d083b6-f99e-4e8c-82d6-d1409b20887c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2870 | T16182-VN02-P0MAG-123006 | 2017-07-11 | DHI-WTRAN-000422 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60b2b8bf-943d-4883-b5f0-dbb06b55f409 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2871 | T16182-XK00-P0MAG-123008 | 2017-07-11 | DHI-WTRAN-000422 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ca4ae67-04ad-4a51-8866-fdecbe71cc19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2872 | T16182-XS00-P0MAG-123010 | 2017-07-11 | DHI-WTRAN-000422 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=450676ab-385a-4a1e-8c48-34a2ffcb0771 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2873 | T16182-DH02-P0MAG-123011 | 2017-07-11 | DHI-WTRAN-000422 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de939267-1168-4990-be7f-30e51dbd1ed9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2874 | T16182-VE04-P0UBN-172201 | 2017-07-11 | DHI-WTRAN-000423 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3226e10a-110f-46a3-be55-717434fc28b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2875 | T16182-XB02-P0UBN-172202 | 2017-07-11 | DHI-WTRAN-000423 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0bf093c-767b-4f2d-b4c0-74f0eec102c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2876 | T16182-VK02-P0UBN-172203 | 2017-07-11 | DHI-WTRAN-000423 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=106ab1c5-9212-4e55-bb6d-cd2506c3c9b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2877 | T16182-YD00-P0EKG-124018 | 2017-07-11 | DHI-WTRAN-000424 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5eaa0b78-34ab-42a1-8dff-46514b348cbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2878 | T16182-YD00-P0GCF-130002 | 2017-07-11 | DHI-TRANSMIT-000460 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ebf1e3d-154e-4ddc-80ff-359bfa22b5f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2879 | T16182-XG07-P0GCF-130003 | 2017-07-11 | DHI-TRANSMIT-000460 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16040cd3-2f68-482e-ad7c-9b4e870702a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2880 | T16182-XG02-P0GCF-130004 | 2017-07-11 | DHI-TRANSMIT-000460 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4b7195f-dc83-44e9-afd4-ee5949d73df2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2881 | T16182-XW03-P0GCF-130005 | 2017-07-11 | DHI-TRANSMIT-000460 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=809c9d95-9fd0-441d-b726-7d54d5e1ceac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2882 | T16182-XW03-P0GNR-130104 | 2017-07-11 | DHI-TRANSMIT-000460 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e417343c-4566-4cf5-ac92-1f9b21154407 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2883 | T16182-YD00-P0GCF-130019 | 2017-07-11 | DHI-TRANSMIT-000460 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df10e1d5-96a6-47e5-b5c8-40efab04d0a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2884 | T16182-XB02-P0GCF-130042 | 2017-07-11 | DHI-TRANSMIT-000460 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d72a15e9-eb68-4811-9373-b3361d61523e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2885 | T16182-YD16-P0SCA-127546 | 2017-07-11 | DHI-WTRAN-000425 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72531815-11b9-4377-85dc-f204b6b1d292 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2886 | T16182-YD00-P0CWQ-161407 | 2017-07-11 | DHI-TRANSMIT-000461 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be803554-00db-41f8-aec8-a5b2f4b0dc8a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2887 | T16182-YD00-P0CWQ-161408 | 2017-07-11 | DHI-TRANSMIT-000461 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b63b03ce-814b-40b8-add0-0e40caab1222 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2888 | T16182-YD00-P0CWQ-161409 | 2017-07-11 | DHI-TRANSMIT-000461 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42d48c78-8c92-4014-923f-83e9642a5e86 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2889 | T16182-XB02-P8UTH-172003 | 2017-07-11 | DHI-TRANSMIT-000462 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=004207fa-80cc-4d8f-8a61-72f24331eabe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2890 | T16182-YE03-P0BAU-152523 | 2017-07-11 | DHI-TRANSMIT-000463 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e73f747a-aba0-4299-8e9e-8663e61b2a68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2891 | T16182-XB00-P6MKA-250001 | 2017-07-11 | DHI-TRANSMIT-000464 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20c58937-1cf6-462a-8d62-ec15dc4fd365 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2892 | T16182-XB00-P7MKA-250002 | 2017-07-11 | DHI-TRANSMIT-000464 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63ece756-fb93-42cd-8821-4e575275fcae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2893 | T16182-YD00-P0MKA-250016 | 2017-07-11 | DHI-WTRAN-000426 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07ba74cc-c209-4b39-a2d7-7984a7291c70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2894 | T16182-YD00-P0MKA-250004 | 2017-07-11 | DHI-WTRAN-000426 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f11869f-b06c-4ee4-bfbf-b87e793c320c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2895 | T16182-YK00-P0GHC-129013 | 2017-07-11 | DHI-WTRAN-000427 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3f0663d-e831-46f4-a23b-c0cec2766e56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2896 | T16182-YK00-P0GHC-129037 | 2017-07-11 | DHI-WTRAN-000427 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9c1a7ce-230c-4cf1-a526-2244e7f3e0d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2897 | T16182-YL22-P0GHC-129014 | 2017-07-11 | DHI-WTRAN-000428 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8b38f81-d80b-4ec7-a5a4-ebad92a49488 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2898 | T16182-YL22-P0GHC-129038 | 2017-07-11 | DHI-WTRAN-000428 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67fe05e7-fb7f-4048-98ec-27322439151b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2899 | T16182-YD02-P0ZEN-165501 | 2017-07-11 | DHI-WTRAN-000429 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6eb76c1-0d07-4abb-8401-ed8c4f44d509 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2900 | T16182-VE04-P0ULX-171221 | 2017-07-11 | DHI-WTRAN-000430 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c5d1330-eee8-42b1-8962-1ba9695f850f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2901 | T16182-XB02-P0ULX-171222 | 2017-07-11 | DHI-WTRAN-000430 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=949ccde4-e731-43eb-890d-c4eb6847e0e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2902 | T16182-XB02-P0ULX-171223 | 2017-07-11 | DHI-WTRAN-000430 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0abd04e2-155e-4a82-97fb-9ea2202feab6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2903 | T16182-UT01-P0GQB-173413 | 2017-07-11 | DHI-TRANSMIT-000465 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=954783d9-99b1-47bc-8cdf-9c52864dfa14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2904 | T16182-YE03-P8ZEN-125767 | 2017-07-11 | DHI-TRANSMIT-000466 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab8735fe-ae61-4ac2-bc64-96c18e498c69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2905 | T16182-YF00-P8ZEN-125709 | 2017-07-11 | DHI-WTRAN-000431 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6c65b8c-c260-4ede-9e03-988cdbd0241b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2906 | T16182-YF00-P8ZEN-125710 | 2017-07-11 | DHI-WTRAN-000431 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2a8facf-227d-4ee0-83fd-09d7a3579fdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2907 | T16182-YF00-P8ZEN-125711 | 2017-07-11 | DHI-WTRAN-000431 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b035ad1-2b22-4aec-8a9d-f9a99671b0e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2908 | T16182-YF00-P8ZEN-125724 | 2017-07-11 | DHI-WTRAN-000431 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c009ec24-bb92-4dd3-8531-8527b2c33f09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2909 | T16182-YL30-P8ZEN-125514 | 2017-07-11 | DHI-WTRAN-000432 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d869452-9dd5-43fe-abba-61bb298cec6c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2910 | T16182-DP00-P8ZEN-125310 | 2017-07-11 | DHI-WTRAN-000433 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=660ba0ef-be0d-476a-812a-8215dab312c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2911 | T16182-CV03-P8ZEN-125607 | 2017-07-11 | DHI-WTRAN-000433 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f31fe8ac-0695-4054-b139-4028cfda7401 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2912 | T16182-CV03-P8ZEN-125609 | 2017-07-11 | DHI-WTRAN-000433 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aef8a2ed-a9b6-4862-92f4-40048e19dc3a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2913 | T16182-DP00-P8ZEN-125506 | 2017-07-11 | DHI-WTRAN-000433 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf7b92c0-285b-4bb9-99d5-f3416c148d34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2914 | T16182-XV00-P8ZEN-125505 | 2017-07-11 | DHI-WTRAN-000433 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d662829-483f-453e-b063-76198696bb4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2915 | T16182-YT01-P0LB-122095 | 2017-07-11 | DHI-WTRAN-000434 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c379aeb5-3924-4eb4-99f3-8344df1b694f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2916 | T16182-YT01-P0LB-122096 | 2017-07-11 | DHI-WTRAN-000434 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfa5e0f0-c049-4887-8449-9f938144b0de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2917 | T16182-YT01-P0LB-122098 | 2017-07-11 | DHI-WTRAN-000434 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a7c6e51-9f40-48e5-9a71-762af43927ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2918 | T16182-US02-P0LB-122081 | 2017-07-11 | DHI-WTRAN-000435 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51233fb6-b3c4-4c6d-aba8-c2709e8e8f9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2919 | T16182-YD02-P0LB-122065 | 2017-07-11 | DHI-WTRAN-000435 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a8667a6-3fcf-470f-92c8-9afec5fa5fc5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2920 | T16182-YL00-P0LB-122079 | 2017-07-11 | DHI-WTRAN-000435 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81ac71a0-1e45-4541-8ef0-77b1fef2b224 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2921 | T16182-YQ01-P0LB-122085 | 2017-07-11 | DHI-WTRAN-000435 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45f71a9f-bcc7-4ff4-a0da-037abc88d242 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2922 | T16182-YD00-P0PCA-126530 | 2017-07-11 | DHI-WTRAN-000436 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=348334e8-dd69-4970-9bb7-5caff40a245a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2924 | T16182-YT02-P0LB-122094 | 2017-07-12 | DHI-WTRAN-000437 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53cd4dc4-a46c-4006-ac75-6e7d53ff44e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2925 | T16182-YK00-P0PCA-126525 | 2017-07-12 | DHI-WTRAN-000438 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3226f5b3-399d-40b8-9b2e-e37de4b04be2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2926 | T16182-XB02-P0UMX-171053 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d908a4d0-da19-40d1-9b7b-6fad22f437cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2927 | T16182-XB02-P0UMX-171054 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8c7819f-d0a0-478a-9a14-070c8efa61f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2928 | T16182-XB02-P0UMX-171055 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4046c95-301d-43d6-9bd1-64a4499159bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2929 | T16182-XB02-P0UMX-171056 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dca636e9-ee0b-4d58-aa6e-889704442773 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2930 | T16182-XB02-P0UMX-171057 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e02f0026-9a51-464e-adb2-f2dd2abba173 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2931 | T16182-XB02-P0UMX-171058 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28e5d618-50bd-466a-820e-269cd15723ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2932 | T16182-VK02-P0UMX-171059 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d51bc464-30e7-445b-9ed5-651b0d291f7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2933 | T16182-VK02-P0UMX-171060 | 2017-07-12 | DHI-WTRAN-000439 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac4b2032-871d-4226-a5ed-ecffaddd6eec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2934 | T16182-YE00-P0ZEN-152735 | 2017-07-12 | DHI-WTRAN-000440 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=485d4c8d-2603-44e5-8f57-8644845e4ef3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2935 | T16182-YE00-P0ZEN-152750 | 2017-07-12 | DHI-TRANSMIT-000467 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5253b0ab-7bf9-4731-8f02-e117a5872b56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2936 | T16182-YQ01-P0ZEN-152301 | 2017-07-12 | DHI-TRANSMIT-000468 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e8d8c83-16f4-497c-a7fb-f258b1f3ec9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2937 | T16182-YQ01-P0ZEN-152307 | 2017-07-12 | DHI-TRANSMIT-000468 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57a6053a-c726-469c-aa1b-8973c445f445 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2938 | T16182-YQ01-P0ZEN-152302 | 2017-07-12 | DHI-TRANSMIT-000468 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa48cdd8-bff1-4446-913b-3274e72b33aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2939 | T16182-YQ01-P0ZEN-152303 | 2017-07-12 | DHI-TRANSMIT-000468 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b93729dc-f0cf-41f1-a974-0d0d17509556 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2941 | T16182-YB03-P0PCA-126533 | 2017-07-13 | DHI-WTRAN-000441 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32a0cf92-1737-4405-b9bf-594e706fbe05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2942 | T16182-XS00-P0GM-120022 | 2017-07-13 | DHI-WTRAN-000442 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cc1eae1-e3cd-4d12-b8f0-712d00be5827 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2943 | T16182-XS00-P0GM-120023 | 2017-07-13 | DHI-WTRAN-000442 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16fdfbd4-9caa-41b4-a9bc-0a252a246c9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2944 | T16182-YT01-P0LB-122097 | 2017-07-13 | DHI-WTRAN-000443 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17816dda-7335-4a44-b4db-0f8b6f6dfb3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2945 | T16182-XW03-P0GHC-110051 | 2017-07-13 | DHI-TRANSMIT-000469 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18687095-a171-4170-86df-bb6a2933b00e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2946 | T16182-XW03-P0PGB-110050 | 2017-07-13 | DHI-TRANSMIT-000469 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea784c04-dcd7-4ef0-8177-65d9c8e085f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2947 | T16182-BV02-P0ZEN-050001 | 2017-07-13 | DHI-WTRAN-000444 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d2d3d6f-6910-4528-b75e-f2988b060245 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2948 | T16182-CV03-P0ZEN-165711 | 2017-07-13 | DHI-WTRAN-000445 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3501ed79-353d-41f2-bd0f-dc0c48868ebb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2949 | T16182-DF04-P0LB-122005 | 2017-07-13 | DHI-WTRAN-000446 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86862566-9d16-421c-92a3-9a51b6c5e027 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2950 | T16182-UE00-P0LB-122011 | 2017-07-13 | DHI-WTRAN-000446 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a90ac205-d45e-4070-9503-6ebf5949be96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2951 | T16182-UE00-P0LB-122012 | 2017-07-13 | DHI-WTRAN-000446 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aba138af-d451-4873-bc0d-3ad2d8051485 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2952 | T16182-YD00-P0LB-122054 | 2017-07-13 | DHI-WTRAN-000446 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5dffdad8-8ee3-4d70-a8d5-ecd3d1870175 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2953 | T16182-YF00-P0LB-122070 | 2017-07-13 | DHI-WTRAN-000447 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1019cc91-7ae8-4d01-b324-da380e92287f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2954 | T16182-YM03-P0LB-122069 | 2017-07-13 | DHI-WTRAN-000447 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=300f72ed-56af-4997-96e8-441997523f6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2955 | T16182-XG02-P0SCA-127502 | 2017-07-14 | DHI-WTRAN-000448 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6890e7b5-b8ca-4dff-b9f5-63d671027f93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2956 | T16182-YD00-P0LCB-127501 | 2017-07-14 | DHI-WTRAN-000448 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=193b4222-e5ca-4a2c-bb5c-9f66ef86895c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2957 | T16182-YT01-P0BAT-150611 | 2017-07-14 | DHI-WTRAN-000449 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d016e06-07d5-49a6-8810-35ab49f937d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2958 | T16182-YD00-P0MJ-110504 | 2017-07-14 | DHI-WTRAN-000450 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cd1da87-c759-4107-a9ee-fa6051c8eb37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2959 | T16182-YT01-P0BBT-150661 | 2017-07-14 | DHI-WTRAN-000451 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33dcba39-1cfa-4eb6-b7f6-bef6b438d531 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2960 | T16182-YD00-P0PCA-126503 | 2017-07-14 | DHI-WTRAN-000452 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a656d2c5-c2a6-4293-834c-5e30c9d8ee87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2961 | T16182-XW03-P0LA-110061 | 2017-07-14 | DHI-WTRAN-000453 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37a3082b-e18c-4b82-8a95-aa1a5ad8cc5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2962 | T16182-CA00-P0UYP-183201 | 2017-07-14 | DHI-WTRAN-000454 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf016939-f940-4c2d-b616-572e0703bad5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2963 | T16182-CA00-P0UYP-183202 | 2017-07-14 | DHI-WTRAN-000454 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3588726-3dc0-497c-aa83-a67c32979ff4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2964 | T16182-CA00-P0UYP-183203 | 2017-07-14 | DHI-WTRAN-000454 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20aba371-d2b7-4d34-b209-6b46aa0e3ba1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2965 | T16182-CA00-P0UYP-183204 | 2017-07-14 | DHI-WTRAN-000454 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e07ce751-a861-42a4-85ec-be49cdc4ff0e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2966 | T16182-CA01-P0UYP-183251 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=199717b3-3398-4838-86f5-2d98a05c5c22 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2967 | T16182-CA01-P0UYP-183252 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66b6799c-9612-451a-b1ce-6c41752efda8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2968 | T16182-CA01-P0UYP-183253 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17cab919-d9f5-405e-81ce-2ca421a8bd81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2969 | T16182-CA01-P0UYP-183254 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06fc8d0d-ae2e-4e10-94ff-126b60c546e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2970 | T16182-CA01-P0UYP-183255 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62e2e73b-aad9-4629-b2c7-4a0558c44d21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2971 | T16182-CA02-P0UYP-183256 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=309a7677-539b-4330-861b-8de1237c5c86 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2972 | T16182-CA02-P0UYP-183257 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c63e3aed-49c1-4f87-bb08-fc60a397077e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2973 | T16182-CA06-P0UYP-183200 | 2017-07-14 | DHI-WTRAN-000454 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afeba03c-46f4-430e-ab16-ccc7bbc9bda1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2974 | T16182-CA00-P1BAT-180511 | 2017-07-14 | DHI-TRANSMIT-000473 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec82d671-38cd-4a63-bd0c-797658ab3606 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2975 | T16182-CA03-P1BAT-180512 | 2017-07-14 | DHI-TRANSMIT-000473 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fc92fc9-bb8f-4794-858d-90931586db84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2976 | T16182-CA03-P1BAT-180513 | 2017-07-14 | DHI-TRANSMIT-000473 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc576846-3d8f-4460-965e-6404a3dcea83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2977 | T16182-CV03-P0CWQ-161122 | 2017-07-14 | DHI-WTRAN-000455 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e655bd0-df03-40c9-a2d4-d5f29c051363 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2978 | T16182-DE00-P0ZEN-152840 | 2017-07-14 | DHI-WTRAN-000456 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cc44f71-4e9e-4266-9b72-a4d2f3b9728e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2979 | T16182-YD05-P0CRN-161116 | 2017-07-17 | DHI-WTRAN-000457 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9857d491-a50c-444e-a595-d85e8083a626 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2980 | T16182-XG07-P0SAV-135102 | 2017-07-17 | DHI-TRANSMIT-000475 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4e3df79-b101-485f-9036-ba347f4f7979 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2981 | T16182-XH02-P0SAV-135104 | 2017-07-17 | DHI-TRANSMIT-000475 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e7eb085-bb24-4b73-8169-d71a798adb3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2982 | T16182-XW03-P0SAV-135101 | 2017-07-17 | DHI-TRANSMIT-000475 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84eaea9e-824b-462e-9ece-75a4e149aa92 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2983 | T16182-XW03-P0SAV-135103 | 2017-07-17 | DHI-TRANSMIT-000475 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44a1424b-10ed-4100-b7d3-1eccae75da20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2984 | T16182-XN00-P0EKG-124023 | 2017-07-17 | DHI-WTRAN-000458 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f8d8f5e-0c86-4bfc-89c2-58c60e5b82f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2985 | T16182-YD00-P0BAT-150621 | 2017-07-17 | DHI-WTRAN-000459 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=167114ab-9d80-4613-a85d-cceec5b2685e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2986 | T16182-YD00-P0BAT-150626 | 2017-07-17 | DHI-WTRAN-000459 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1c32878-76ca-4595-8954-734cc4198973 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2987 | T16182-CA05-P0UYC-182981 | 2017-07-17 | DHI-TRANSMIT-000476 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a53b7639-6484-484d-9874-338a76ddb2d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2988 | T16182-CA05-P0UYC-182982 | 2017-07-17 | DHI-TRANSMIT-000476 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c35de49c-a35c-47c9-b6fc-4b849e5b7878 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2989 | T16182-CA05-P0UYC-182983 | 2017-07-17 | DHI-TRANSMIT-000476 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5332d68-c28e-4c70-ba88-336d8a93b142 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2990 | T16182-CA05-P0UYC-182984 | 2017-07-17 | DHI-TRANSMIT-000476 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6300408a-ebb6-4851-b25f-457a57194a42 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2991 | T16182-CA05-P0UYC-182985 | 2017-07-17 | DHI-WTRAN-000460 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54e0f75f-4ae9-4520-a3c3-38bc8caaa613 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2992 | T16182-VK02-P8UTH-172008 | 2017-07-17 | DHI-TRANSMIT-000477 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e5a4ccf-9f4c-4df0-bb83-aba403bde4e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2993 | T16182-XB02-P8UTH-172004 | 2017-07-17 | DHI-TRANSMIT-000477 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35385ad9-b4d6-44cc-8b4c-8297bf78c1a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2994 | T16182-XB02-P8UTH-172007 | 2017-07-17 | DHI-TRANSMIT-000477 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a6d2efd-511b-4948-8eba-e6d3017ad0b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2995 | T16182-XW03-P0LC-110046 | 2017-07-17 | DHI-TRANSMIT-000478 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7115392e-c05c-4665-820d-a259d073b7c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2996 | T16182-XW03-P0LC-110047 | 2017-07-17 | DHI-TRANSMIT-000478 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a920a9c1-4146-4519-bd2c-18069ca6d726 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2997 | T16182-VK02-P0UAZ-172613 | 2017-07-17 | DHI-TRANSMIT-000479 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fee09e27-f5dc-4d9e-b523-d74f099293e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2998 | T16182-XB02-P0UAZ-172602 | 2017-07-17 | DHI-TRANSMIT-000479 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0943d8d5-69f8-4a4c-90d7-00d01217302d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
2999 | T16182-XB02-P0UAZ-172603 | 2017-07-17 | DHI-TRANSMIT-000479 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01965ccc-f03d-4f10-9a1f-d20cc2292193 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3000 | T16182-XB02-P0UAZ-172608 | 2017-07-17 | DHI-TRANSMIT-000479 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1750dc40-bdf2-4b43-8041-0ac77a66c4aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3003 | T16182-YF02-P0GCF-130011 | 2017-07-17 | DHI-WTRAN-000462 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f899949-d150-40dd-ada7-e44a752e4821 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3004 | T16182-CV03-P0GCF-130055 | 2017-07-17 | DHI-WTRAN-000463 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf5cfe1d-2c4d-46a8-b9e7-50e020ef6a44 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3005 | T16182-XN00-P0GCF-130008 | 2017-07-17 | DHI-WTRAN-000463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=184cae78-e030-4e1a-a8d1-9882cb36a19a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3006 | T16182-XN00-P0GNR-130105 | 2017-07-17 | DHI-WTRAN-000463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=428572e4-8295-4c7b-b4c8-3c274f3c79d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3007 | T16182-XN00-P0GNR-130107 | 2017-07-17 | DHI-WTRAN-000463 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d42c4de7-c1a1-4f13-940b-93d6724468b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3008 | T16182-YK09-P0GCF-130012 | 2017-07-17 | DHI-WTRAN-000463 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edaa8539-514d-440a-b071-1b135b5f219d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3009 | T16182-YT01-P0GCF-130014 | 2017-07-17 | DHI-WTRAN-000463 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ef1a4d9-a857-4b09-9f4d-652cd413b8fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3010 | T16182-YT01-P0GNR-130108 | 2017-07-17 | DHI-WTRAN-000463 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdfa9d4e-9aa0-40e7-92a2-d2df8e427de0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3011 | T16182-YR05-P0ZEN-161011 | 2017-07-17 | DHI-WTRAN-000464 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a085ca87-f8f2-4dc1-a015-9c502e1564d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3012 | T16182-XS00-P0QJA-110500 | 2017-07-18 | DHI-WTRAN-000465 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1d5c31d-ab8f-410a-8e9c-944804f1d41d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3013 | T16182-YD00-P0QJA-110502 | 2017-07-18 | DHI-WTRAN-000465 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1af72b2b-50a4-4e68-860a-bae8632b5620 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3014 | T16182-YK08-P0QJA-110501 | 2017-07-18 | DHI-WTRAN-000465 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e00c6113-5062-49a4-8677-b1a378ba8520 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3015 | T16182-YT01-P0QJA-110503 | 2017-07-18 | DHI-WTRAN-000465 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa0511e1-86fe-4349-8882-ae608431087f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3016 | T16182-UC02-P6MKA-250011 | 2017-07-18 | DHI-TRANSMIT-000481 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0521827-08b3-4976-ac92-7987b75a3fc3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3017 | T16182-UC02-P7MKA-250012 | 2017-07-18 | DHI-TRANSMIT-000481 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87e87805-e3d6-4d6f-bce3-7db5f6e4c533 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3018 | T16182-YK00-P0ZEN-165311 | 2017-07-18 | DHI-WTRAN-000466 | IFC | 0 | R | TRUE | TRUE | 2017-08-07_Changed by jisoo1.chung 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acf14561-ab7e-4247-9cea-8888820db24c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3019 | T16182-YK00-P0ZEN-165312 | 2017-07-18 | DHI-WTRAN-000466 | IFC | 0 | R | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4ab9515-984c-426a-a0aa-c1800e6d0c88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3020 | T16182-YK00-P0ZEN-165313 | 2017-07-18 | DHI-WTRAN-000466 | IFC | 0 | R | TRUE | TRUE | 2017-08-07_Changed by jisoo1.chung 2017-08-08_Changed by pilhwan.jung 2017-08-23_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c9abec4-bc96-409f-b62d-ca81070ea3f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3021 | T16182-YK00-P0ZEN-165314 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 2 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f499c38-27dc-4409-8116-56f276ed6dd2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3022 | T16182-YK00-P0ZEN-165315 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung 2017-08-08_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f895235-d331-4d32-b3bd-bfbcab897122 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3023 | T16182-YK00-P0ZEN-165316 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=155888eb-18f2-4dd5-84b6-1252accf685c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3024 | T16182-YK00-P0ZEN-165317 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f84e30a-13b5-4154-b23c-8f6ed1eb2686 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3025 | T16182-YK00-P0ZEN-165318 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e902c236-99c8-4be2-9470-48a35f9269d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3026 | T16182-YK00-P0ZEN-165319 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ca76535-2804-469e-bbc9-f947129e2476 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3027 | T16182-YK00-P0ZEN-165320 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d019cf4-60e1-415b-8220-bf409f57fd73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3028 | T16182-YK00-P0ZEN-165321 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45c6073c-7c7c-4a2c-b1b5-ed0454fed563 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3029 | T16182-YK00-P0ZEN-165322 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1bed887f-6a06-4fb4-90dc-329e747f5d2c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3030 | T16182-YK00-P0ZEN-165323 | 2017-07-18 | DHI-WTRAN-000466 | IFI | 1 | R | TRUE | TRUE | 2017-08-08_Changed by pilhwan.jung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62cc62b6-250f-4c46-bf2c-864477a6d90b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3031 | T16182-XB00-P0SCA-127509 | 2017-07-18 | DHI-WTRAN-000467 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b17f61a-dfe0-4fb0-9211-2a6e4e4aa0c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3036 | T16182-CV03-P0ZEN-165701 | 2017-07-18 | DHI-WTRAN-000469 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3412aaa-90be-4382-b5a6-f8f3f96c3243 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3037 | T16182-YD00-P0SMS-128002 | 2017-07-18 | DHI-WTRAN-000470 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b8f42d4-152a-41e5-950c-0342ecd51026 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3038 | T16182-YT01-P0SMS-128005 | 2017-07-18 | DHI-WTRAN-000470 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc2b94d0-7581-4735-ab11-0cabc86682fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3039 | T16182-YD00-P0BAC-150721 | 2017-07-18 | DHI-WTRAN-000471 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12d481d4-ee77-4a33-a21c-92fe6b41aec4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3040 | T16182-YU03-P0BAC-150731 | 2017-07-18 | DHI-WTRAN-000471 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=403555b5-03ed-44a3-87ba-5bd2e538a3f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3041 | T16182-YU03-P0BB-150836 | 2017-07-18 | DHI-WTRAN-000472 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b75e011-0715-490c-8b84-b7823bdfe0b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3044 | T16182-YT01-P0LB-122101 | 2017-07-18 | DHI-WTRAN-000475 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=012b80e1-03ae-44f0-86b7-5bb9222d0754 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3045 | T16182-CV03-P0ZEN-163204 | 2017-07-19 | DHI-WTRAN-000476 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76f5b683-5350-4ee6-934d-82e9cebccb8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3046 | T16182-CV03-P0ZEN-163331 | 2017-07-19 | DHI-WTRAN-000477 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a5cd355-d8e0-484a-b633-6c813f97307e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3001 | T16182-YD00-P0GCF-130006 | 2017-07-20 | DHI-WTRAN-000461 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29c537f3-2a3c-454e-8185-8515a72415fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3002 | T16182-YU02-P0GCF-130010 | 2017-07-20 | DHI-WTRAN-000461 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9934661-5675-4f25-bf3b-9db76c6015db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3032 | T16182-XW01-P0SCA-127503 | 2017-07-20 | DHI-WTRAN-000468 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce626599-1d4e-445b-b677-d72e4748a402 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3033 | T16182-XW01-P0SCA-127504 | 2017-07-20 | DHI-WTRAN-000468 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=333140d3-16e6-4694-8241-5420909d818a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3034 | T16182-XW01-P0SCA-127505 | 2017-07-20 | DHI-WTRAN-000468 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5af58d4-c4d4-4edf-beda-551edb4a564b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3035 | T16182-XW01-P0SCA-127506 | 2017-07-20 | DHI-WTRAN-000468 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c099f731-f847-4983-a0fa-b529089472b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3042 | T16182-YR05-P0SAY-163423 | 2017-07-20 | DHI-WTRAN-000473 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c3d9656-24b5-41f2-a1c4-b06e92ae69ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3043 | T16182-YE03-P0BAU-152529 | 2017-07-20 | DHI-WTRAN-000474 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65d58897-719d-4191-9f6f-8930407799db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3047 | T16182-XH01-P0GRK-140064 | 2017-07-21 | DHI-WTRAN-000478 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3048 | T16182-XH01-P0LDK-140071 | 2017-07-21 | DHI-WTRAN-000478 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3049 | T16182-XH01-P0LDK-140072 | 2017-07-21 | DHI-WTRAN-000478 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3050 | T16182-XH01-P0UCB-140068 | 2017-07-21 | DHI-WTRAN-000478 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3051 | T16182-XH01-P0UGD-140065 | 2017-07-21 | DHI-WTRAN-000478 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3052 | T16182-XH01-P0UGA-140066 | 2017-07-21 | DHI-WTRAN-000478 | IFI | 0 | R | FALSE | TRUE | 2017-09-27_Changed by jisoo1.chung |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3053 | T16182-XH01-P0UGA-140067 | 2017-07-21 | DHI-WTRAN-000478 | IFI | 0 | R | FALSE | TRUE | 2017-09-27_Changed by jisoo1.chung |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3054 | T16182-YF00-P0CJD-161022 | 2017-07-21 | DHI-WTRAN-000479 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3055 | T16182-YF00-P0CJD-161025 | 2017-07-21 | DHI-WTRAN-000479 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3056 | T16182-YT01-P0BAC-150711 | 2017-07-21 | DHI-WTRAN-000480 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3057 | T16182-DP00-P0ZEN-020005 | 2017-07-21 | DHI-WTRAN-000481 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=214085ab-cb36-45b3-975e-6f4008801243 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3058 | T16182-DP00-P0ZEN-020005 | 2017-07-21 | DHI-TRANSMIT-000482 | IFI | 2 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3059 | T16182-CA03-P0UMY-185168 | 2017-07-21 | DHI-TRANSMIT-000483 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b9bbf1c-2228-45c9-911d-a8ed735db0a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3060 | T16182-CA03-P0UMY-185178 | 2017-07-21 | DHI-TRANSMIT-000483 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48aa128a-e95f-4d0a-8bd7-4c6ab569a53d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3061 | T16182-CA00-P0UTF-182801 | 2017-07-21 | DHI-TRANSMIT-000484 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9b6fea0-0b4a-4736-b92f-97b731f14f06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3062 | T16182-CA01-P0UTF-182854 | 2017-07-21 | DHI-TRANSMIT-000484 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=592695c1-9b3a-4cdd-8af2-98dd19a3e21c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3063 | T16182-CA01-P0UTF-182856 | 2017-07-21 | DHI-TRANSMIT-000484 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c872b01e-d519-48a5-998b-2885ee8eb619 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3064 | T16182-CA02-P0UTF-182857 | 2017-07-21 | DHI-TRANSMIT-000484 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fb8e39f-6d5d-4455-932c-ec6290f09f5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3065 | T16182-XW01-P0LB-122041 | 2017-07-21 | DHI-WTRAN-000483 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b261bf32-350b-4bec-b926-383027efb7cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3066 | T16182-XG07-P0SAR-134202 | 2017-07-21 | DHI-TRANSMIT-000485 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c8d8611-44f7-4d53-9bb7-840f94779195 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3067 | T16182-XH02-P0SAR-134204 | 2017-07-21 | DHI-TRANSMIT-000485 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2888d6dc-a0aa-42bf-8012-cfb30ee002f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3068 | T16182-XW03-P0SAR-134201 | 2017-07-21 | DHI-TRANSMIT-000485 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9252989-0408-4597-b941-7b5a52186625 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3069 | T16182-XW03-P0SAR-134203 | 2017-07-21 | DHI-TRANSMIT-000485 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b96699b-307e-4eeb-b0d9-759b0603e79e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3070 | T16182-XG07-P0SAR-134102 | 2017-07-21 | DHI-TRANSMIT-000486 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3ba16bf-4b9c-4a22-8410-8fab9ae131b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3071 | T16182-XH02-P0SAR-134104 | 2017-07-21 | DHI-TRANSMIT-000486 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca3c9090-8ee5-4474-be44-37bbd86e24a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3072 | T16182-XW03-P0SAR-134101 | 2017-07-21 | DHI-TRANSMIT-000486 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3bd9962-d834-48e3-8341-2603db320ebc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3073 | T16182-XW03-P0SAR-134103 | 2017-07-21 | DHI-TRANSMIT-000486 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd232464-45fa-4789-9a55-4cbd511af6dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3074 | T16182-CA03-P0UMA-180464 | 2017-07-21 | DHI-TRANSMIT-000487 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=610f7290-3977-4b9c-908b-d298ed3621fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3075 | T16182-CA03-P0UMA-180465 | 2017-07-21 | DHI-TRANSMIT-000487 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30950bc2-3598-40a3-8748-55261f282748 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3076 | T16182-CA03-P0UMA-180469 | 2017-07-21 | DHI-TRANSMIT-000487 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f67ea51a-67f4-40c8-b385-a180e2898dec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3077 | T16182-CA03-P0UMA-180471 | 2017-07-21 | DHI-TRANSMIT-000487 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f78de91f-2751-4895-8c49-ccfa113a3c68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3078 | T16182-CA06-P0UMA-180492 | 2017-07-21 | DHI-TRANSMIT-000487 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ebdacd1-00ec-463a-85f5-9decffaff6f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3079 | T16182-VE04-P0ULX-171601 | 2017-07-21 | DHI-WTRAN-000484 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd5b3447-0023-4166-b346-29f8d4807881 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3080 | T16182-VK02-P0ULX-171604 | 2017-07-21 | DHI-WTRAN-000484 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b6ab116-a1da-44cf-9f55-8f9eb9642a7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3081 | T16182-XB02-P0ULX-171602 | 2017-07-21 | DHI-WTRAN-000484 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=497aa611-e3e5-4d9c-8658-2c77e3018a25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3082 | T16182-XB02-P0ULX-171603 | 2017-07-21 | DHI-WTRAN-000484 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db0a38cb-bf5a-4481-9c22-fb9e91cef5ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3083 | T16182-YT01-P0LB-122093 | 2017-07-21 | DHI-WTRAN-000485 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7ea73a4-bcc3-42fd-9540-8273fe50e924 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3084 | T16182-DE00-P0ZEN-152702 | 2017-07-21 | DHI-WTRAN-000486 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90d0cb5b-f204-46f5-be3e-6f7ba765abc3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3085 | T16182-YD04-P0ZEN-152005 | 2017-07-21 | DHI-WTRAN-000486 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd6ef1eb-72ce-48ca-84e3-c867c852b892 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3086 | T16182-YD04-P0ZEN-152011 | 2017-07-21 | DHI-WTRAN-000486 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4142f71f-b94d-4d38-ad6e-095990df8309 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3087 | T16182-YE00-P0ZEN-152720 | 2017-07-21 | DHI-TRANSMIT-000488 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad5352d2-098d-41e3-b222-a09aa7d0a183 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3088 | T16182-YE00-P0ZEN-152731 | 2017-07-21 | DHI-TRANSMIT-000488 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=171eb1ad-4b30-4de7-a8bb-0a0380bde90d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3089 | T16182-YE00-P0ZEN-152732 | 2017-07-21 | DHI-TRANSMIT-000488 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3b4bcb6-064e-4a2e-bed2-37e34d63bb6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3090 | T16182-YE00-P0ZEN-152733 | 2017-07-21 | DHI-TRANSMIT-000488 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c8898f4-f416-4a19-b17b-112623e72a91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3091 | T16182-YD00-P0BAA-150772 | 2017-07-21 | DHI-WTRAN-000487 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a909ff2d-1c6a-494f-940a-19e06d6bcfb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3092 | T16182-YD00-P0BAA-150777 | 2017-07-21 | DHI-WTRAN-000487 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21c9868d-8f3c-487a-9e8c-9b3418928272 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3093 | T16182-YD00-P0BAA-150781 | 2017-07-21 | DHI-WTRAN-000487 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=baa6a658-0a77-4acd-8e67-d151eaa822e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3094 | T16182-CA02-P0UBA-181258 | 2017-07-21 | DHI-TRANSMIT-000489 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8219c826-0ea6-43e5-8e69-05c7b0427b1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3095 | T16182-CA02-P0UBA-181260 | 2017-07-21 | DHI-TRANSMIT-000489 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=209e52e3-ae14-4405-a8f5-3c604c613322 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3096 | T16182-XS00-P0PCA-126501 | 2017-07-21 | DHI-WTRAN--000488 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d158df7-eabb-41aa-b1c5-3221cf31bb21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3097 | T16182-XG02-P0PCA-126502 | 2017-07-21 | DHI-WTRAN-000489 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d960c5fa-3e3b-46e8-a5c9-09725178ba3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3098 | T16182-XV00-P8ZEN-125001 | 2017-07-21 | DHI-WTRAN-000490 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1917b327-536c-4609-80cf-50f53a687f8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3099 | T16182-YT02-P8ZEN-125713 | 2017-07-21 | DHI-WTRAN-000491 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85fa378b-f8e7-4c2d-a926-966a99a5f8b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3100 | T16182-YT02-P8ZEN-125714 | 2017-07-21 | DHI-WTRAN-000491 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a1a578a-33d9-4bba-aa5f-ea3f1012c1ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3101 | T16182-YT02-P8ZEN-125715 | 2017-07-21 | DHI-WTRAN-000491 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18aa4ea6-fae4-416d-b09c-950668766fdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3102 | T16182-YT02-P8ZEN-125716 | 2017-07-21 | DHI-WTRAN-000491 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e1eba8b-41a3-4c02-a8e2-a21250ea7482 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3103 | T16182-YT02-P8ZEN-125717 | 2017-07-21 | DHI-WTRAN-000491 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbc298d0-4bf2-4105-a89f-76f124378166 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3104 | T16182-YT02-P8ZEN-125718 | 2017-07-21 | DHI-WTRAN-000491 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecbeab4e-aabc-4dd2-a270-a03c4df12174 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3105 | T16182-YT02-P8ZEN-125726 | 2017-07-21 | DHI-WTRAN-000491 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed4c8d5d-1c9d-4463-b7a6-7292ecd86910 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3106 | T16182-XG02-P0SGA-139001 | 2017-07-21 | DHI-WTRAN-000492 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c215a4cb-d46e-435e-8d4e-ebb1c1915698 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3107 | T16182-XG02-P0SGK-139002 | 2017-07-21 | DHI-WTRAN-000492 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a31aef74-677b-47fe-8b81-a594cf7ff2fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3108 | T16182-XH01-P0SGA-139011 | 2017-07-21 | DHI-WTRAN-000492 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e52b944b-1b36-44d7-acfa-9bec4a4a36df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3109 | T16182-XH01-P0SGK-139012 | 2017-07-21 | DHI-WTRAN-000492 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d204bf65-8e05-4f20-aff8-5979fa2ef333 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3110 | T16182-XG02-P0SGK-139402 | 2017-07-21 | DHI-WTRAN-000493 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9d8f661-d76b-4fe6-97ef-f427f446cdfb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3111 | T16182-XH01-P0SGK-139412 | 2017-07-21 | DHI-WTRAN-000493 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58bb83ee-430e-4d8d-851b-9f933c2c1b13 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3112 | T16182-YT10-P0SGK-139422 | 2017-07-21 | DHI-WTRAN-000493 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35a89390-0200-4159-835b-f44ff5d51c95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3113 | T16182-YT02-P8ZEN-125719 | 2017-07-21 | DHI-TRANSMIT-000490 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d48915b3-b52b-4cf8-b4cb-df0f84958feb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3114 | T16182-YT02-P8ZEN-125727 | 2017-07-21 | DHI-WTRAN-000494 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cebe717-9f15-4d0e-87b2-8214f4f2ec7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3115 | T16182-VN02-P0LB-122090 | 2017-07-21 | DHI-WTRAN-000495 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea7d6091-abd8-44bc-9866-9f6880973079 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3116 | T16182-YK08-P0LCM-420030 | 2017-07-21 | DHI-TRANSMIT-000491 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b010fa90-9494-459f-ad19-ede382294365 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3117 | T16182-YE01-P0BAU-152620 | 2017-07-21 | DHI-WTRAN-000496 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb08e68c-d2c6-4c09-bfff-3e74bd5f6ef5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3118 | T16182-YE03-P0BAU-152533 | 2017-07-21 | DHI-WTRAN-000496 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=945a51f9-7925-487e-83bb-f55a29d64134 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3119 | T16182-YE03-P0BAU-152534 | 2017-07-21 | DHI-WTRAN-000496 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e17d7965-e107-4154-89e2-030c8575bc52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3120 | T16182-XG02-P0SGC-137001 | 2017-07-21 | DHI-TRANSMIT-000492 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb468221-8297-46b3-a2e6-c54db113dff0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3121 | T16182-XH01-P0SGC-137011 | 2017-07-21 | DHI-TRANSMIT-000492 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2c0611e-39b5-4628-863f-12989a1acef4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3122 | T16182-YT10-P0SGC-137021 | 2017-07-21 | DHI-TRANSMIT-000492 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4369cda-70f0-4e16-b152-5cfef5450645 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3123 | T16182-CV03-P0UCL-163203 | 2017-07-21 | DHI-WTRAN-000497 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=492a68e0-24d5-4d66-85ea-a3ae2d8507cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3124 | T16182-CV03-P0EKU-163202 | 2017-07-21 | DHI-WTRAN-000498 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58b0d003-66c1-4f59-8261-6b99d39ecf10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3125 | T16182-VE04-P0ULX-171221 | 2017-07-21 | DHI-TRANSMIT-000493 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75ffaae5-6799-4776-9df3-52f3902469d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3126 | T16182-XB02-P0ULX-171222 | 2017-07-21 | DHI-TRANSMIT-000493 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09d1e1a4-85aa-406a-826f-28a9eec91f1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3127 | T16182-XB02-P0ULX-171223 | 2017-07-21 | DHI-TRANSMIT-000493 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0538b20b-efcb-449d-a27a-207bf4273f0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3277 | T16182-XR00-P0MAG-123013 | 2017-07-21 | DHI-WTRAN-000482 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dee01893-9a20-417e-be0b-84d10fbe82df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3278 | T16182-YT01-P0MAJ-123012 | 2017-07-21 | DHI-WTRAN-000482 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed6720fb-f5b3-420a-97ab-0c1835c7d569 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3128 | T16182-YT01-P0BBT-150661 | 2017-07-24 | DHI-WTRAN-000499 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3129 | T16182-XG02-P0SGC-139901 | 2017-07-24 | DHI-WTRAN-000500 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86e1d243-39e3-449a-b64f-76e2d1ea82bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3130 | T16182-XH01-P0SGC-139911 | 2017-07-24 | DHI-WTRAN-000500 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85df52df-0f91-4c03-8967-5b194ae5bc4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3131 | T16182-YT10-P0SGC-139921 | 2017-07-24 | DHI-WTRAN-000500 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75251de2-0357-4274-ba63-f52db31a1f36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3132 | T16182-YF02-P0LD-130211 | 2017-07-24 | DHI-WTRAN-000501 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f4e5c37-2c64-4ffa-ac6b-c6a6ecbeef0d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3133 | T16182-YR05-P0LD-130207 | 2017-07-24 | DHI-WTRAN-000501 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db89d623-e7a6-44c5-ad7f-1a432ba8b989 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3134 | T16182-YU02-P0LD-130210 | 2017-07-24 | DHI-WTRAN-000502 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebc146e6-3f2e-4e9a-9c64-a17a3d9b4d77 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3135 | T16182-CV03-P0CWQ-161133 | 2017-07-24 | DHI-TRANSMIT-000494 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42c8e0fe-aa7f-468c-b236-2cb2b7afde02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3136 | T16182-YD00-P0CUQ-161112 | 2017-07-24 | DHI-WTRAN-000503 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f03c90a0-faa2-449e-8b61-e7cdc19eaa14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3137 | T16182-YD00-P0CUQ-161119 | 2017-07-24 | DHI-WTRAN-000503 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61b40e68-bc3f-43fd-8a13-cc057e3cce23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3138 | T16182-YR05-P0CWQ-161147 | 2017-07-24 | DHI-WTRAN-000503 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec7e59d5-eb37-4f3a-a95d-d52280c5d8a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3139 | T16182-XG02-P0SGK-136903 | 2017-07-24 | DHI-WTRAN-000504 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e17b4f8-b19f-4369-81f0-5e2d68d9f06a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3140 | T16182-XH01-P0SGK-136913 | 2017-07-24 | DHI-WTRAN-000504 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb827d19-d319-431c-8b1c-9dbef59814a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3141 | T16182-YT10-P0SGK-136923 | 2017-07-24 | DHI-WTRAN-000504 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ab9259e-ecf8-42bd-8a2a-e67aabd188f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3142 | T16182-YD00-P0MKW-260001 | 2017-07-24 | DHI-WTRAN-000505 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93ea31a5-4304-4aee-b276-7157e34c2b5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3143 | T16182-YD00-P0MKW-260002 | 2017-07-24 | DHI-WTRAN-000505 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdf1dce8-406c-449e-9a5f-1ef5d14b68d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3144 | T16182-YT01-P0BAT-150611 | 2017-07-24 | DHI-TRANSMIT-000495 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d910aa94-43b1-4cb9-a992-cb7aa822fa76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3145 | T16182-XG02-P0GM-120008 | 2017-07-24 | DHI-WTRAN-000506 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15af1242-c0dd-44ce-b378-c0f3a55c1202 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3146 | T16182-VE04-P0UBN-172201 | 2017-07-25 | DHI-TRANSMIT-000496 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c048401-19b6-4919-9c01-9c2f2ec9ea41 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3147 | T16182-VK02-P0UBN-172203 | 2017-07-25 | DHI-TRANSMIT-000496 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1389bc2-a642-43dd-8047-2b250f55be49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3148 | T16182-XB02-P0UBN-172202 | 2017-07-25 | DHI-TRANSMIT-000496 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12e80e91-d799-4203-8c4f-66799ea70855 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3149 | T16182-DP00-P8ZEN-125754 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50e5490b-016c-4e15-a5db-46d3d2e09d1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3150 | T16182-YU02-P8ZEN-125755 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c2630e7-35e5-4293-b28a-c1a51eb06902 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3151 | T16182-YU03-P8ZEN-125756 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f00b93b5-2233-41bf-9da7-10dc93e6aed8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3152 | T16182-DP00-P8ZEN-125757 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d36f584-3fca-446d-95ab-cdbea339e3dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3153 | T16182-DP00-P8ZEN-125758 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a45abf2b-c52b-4ae1-9c4b-eded030b2201 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3154 | T16182-DP00-P8ZEN-125759 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6aa06c36-e4aa-4c92-a3a9-39d0171a16cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3155 | T16182-YT10-P8ZEN-125764 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=212f5a8c-9b81-4431-96d6-3d3e0e082877 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3156 | T16182-YQ01-P8ZEN-125765 | 2017-07-25 | DHI-WTRAN-000507 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=067bd123-5c68-4721-94d3-6a35e4f2b7fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3157 | T16182-XF00-P8ZEN-125729 | 2017-07-25 | DHI-WTRAN-000508 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d0ccbda-e852-4e7c-abb6-73491919aab2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3158 | T16182-YM03-P8ZEN-125721 | 2017-07-25 | DHI-WTRAN-000508 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d47d8e6-d1a1-4831-8f13-aa557725a0d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3159 | T16182-YT02-P8ZEN-125725 | 2017-07-25 | DHI-WTRAN-000508 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb2a54ff-c657-4a70-8d7d-be4aaa150e5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3160 | T16182-XS00-P0PCA-126509 | 2017-07-25 | DHI-WTRAN-000509 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2fff344e-4728-4733-96af-38c9c846b3f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3161 | T16182-CV03-P8ZEN-125608 | 2017-07-25 | DHI-WTRAN-000510 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71afaffb-e38f-4358-874d-1041cd7a93f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3162 | T16182-DE00-P0ZEN-152830 | 2017-07-25 | DHI-TRANSMIT-000497 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6b03198-a798-4426-945c-ee017188f8f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3163 | T16182-DE00-P0ZEN-152840 | 2017-07-25 | DHI-TRANSMIT-000497 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55ff37c9-2983-4fcc-9042-dbb616d4b7e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3164 | T16182-XF00-P0SCA-127524 | 2017-07-25 | DHI-WTRAN-000511 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e251117-9d93-4bfe-a8c3-a0d311c1861e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3165 | T16182-CA05-P0UBA-181281 | 2017-07-26 | DHI-TRANSMIT-000498 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2f257d3-76e2-4799-b832-f2196671be4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3166 | T16182-CA05-P0UBA-181284 | 2017-07-26 | DHI-TRANSMIT-000498 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebaa70e8-942a-4a75-87ac-ede943020127 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3167 | T16182-CA05-P0UBA-181381 | 2017-07-26 | DHI-TRANSMIT-000499 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9b736a2-3a4c-498c-949e-01e49b0fbaaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3168 | T16182-CA05-P0UBA-181384 | 2017-07-26 | DHI-TRANSMIT-000499 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83ff735e-7f77-4f1c-b2b4-acf8e56bf31e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3169 | T16182-XG02-P0LD-130204 | 2017-07-26 | DHI-WTRAN-000512 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e64a17f-44c1-4023-93c9-c3cbc60f7752 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3170 | T16182-XG02-P0SGA-138901 | 2017-07-26 | DHI-WTRAN-000513 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da4bf687-d506-4656-9dc9-b94281d62663 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3171 | T16182-XH01-P0SGA-138911 | 2017-07-26 | DHI-WTRAN-000513 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fa49d83-5f97-43b6-b3bd-2db14493dbaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3172 | T16182-YD00-P0SGZ-138931 | 2017-07-26 | DHI-WTRAN-000513 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9b95385-5412-4d19-8213-b7a7a88f0e80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3173 | T16182-YU03-P0BBT-150681 | 2017-07-26 | DHI-TRANSMIT-000500 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=499f54c8-0e30-4e96-9d89-1e64974beec1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3174 | T16182-YT01-P0BT-151011 | 2017-07-27 | DHI-TRANSMIT-000502 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bd24ccd-de60-4075-b93b-b4f22196ea9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3175 | T16182-YK10-P0LF-110604 | 2017-07-27 | DHI-TRANSMIT-000503 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5b18014-ab5c-4606-a48d-47526af7cd0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3176 | T16182-YT01-P0LF-110603 | 2017-07-27 | DHI-TRANSMIT-000503 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11b1563c-82b0-4d78-8237-fc6e7956344e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3177 | T16182-CA06-P0ULD-183900 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74be67bc-1290-43a6-9c83-c9f8ef0f77c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3178 | T16182-CA00-P0ULD-183902 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=834f1e0a-6632-483d-9ecb-c6421c3184e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3179 | T16182-CA00-P0ULD-183903 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42807b0d-7a78-42a6-8151-8f8119d136a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3180 | T16182-CA00-P0ULD-183904 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5107bf12-ea6b-4bc8-9dd1-7efb34a70bce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3181 | T16182-CA00-P0ULD-183905 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85643f51-3e1e-4fe7-9d1c-b5c69bd5ca11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3182 | T16182-CA00-P0ULD-183906 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25334e74-1ac4-49e9-9b00-25930b6b27d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3183 | T16182-CA01-P0ULD-183951 | 2017-07-27 | DHI-WTRAN-000514 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d7d012b-08a9-4199-b6eb-10ccfe3e021b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3184 | T16182-CA01-P0ULD-183952 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee27ecc3-1ba3-42a3-a27a-d3d139a0e561 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3185 | T16182-CA01-P0ULD-183953 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9855bd4-6cc1-4cbd-a608-0e92f9fa5218 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3186 | T16182-CA01-P0ULD-183954 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2fc54f2-7ea8-4bf4-9e4d-dd677eb44ad2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3187 | T16182-CA02-P0ULD-183956 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1f3f773-8e85-4337-9209-5ffd26f21a55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3188 | T16182-CA02-P0ULD-183957 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32ab4501-084b-4ea4-bd62-8217c0bdb54b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3189 | T16182-CA02-P0ULD-183958 | 2017-07-27 | DHI-WTRAN-000514 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dfe4b75-e2a2-4c9d-a3ce-a26cf9c16986 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3190 | T16182-CA02-P0ULD-183955 | 2017-07-27 | DHI-TRANSMIT-000504 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e74fb82-6c2d-4974-b06d-9fa31719a9e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3191 | T16182-YD00-P0LCB-127001 | 2017-07-27 | DHI-WTRAN-000515 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b5ee614-507c-4a7f-b2c5-efcedbb7d905 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3192 | T16182-YT01-P0LCB-127003 | 2017-07-27 | DHI-WTRAN-000515 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4711029c-79fc-4546-85b4-5b715f41f9b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3193 | T16182-YD00-P0LCB-127009 | 2017-07-27 | DHI-WTRAN-000515 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a8a1fcf-c188-461b-bc87-e68bce00d203 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3194 | T16182-YD00-P0LCB-127031 | 2017-07-27 | DHI-WTRAN-000515 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69bd9d94-3d95-4281-98f2-0dd39f1e32c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3195 | T16182-YT01-P0LCB-127033 | 2017-07-27 | DHI-WTRAN-000515 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d342e503-15fc-4c8d-90c4-bb45cdff4480 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3196 | T16182-YK09-P0LCB-127034 | 2017-07-27 | DHI-WTRAN-000515 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00e5de47-e47e-4f8e-8453-05b2eb49e0b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3197 | T16182-YD00-P0LCB-127038 | 2017-07-27 | DHI-WTRAN-000515 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2f125fe-6bc0-4de3-aad8-9af8e74f06f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3198 | T16182-YM01-P0LCB-127010 | 2017-07-27 | DHI-WTRAN-000516 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebf7916c-6adb-4db4-953d-db4c5b44e431 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3199 | T16182-DE00-P0ZEN-152002 | 2017-07-27 | DHI-WTRAN-000517 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ec9348b-1423-4cda-aaaa-40534f25c546 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3200 | T16182-XG01-P0MJ-110509 | 2017-07-27 | DHI-TRANSMIT-000505 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b6f4271-20f2-425b-9e94-aa8cb3e75d51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3201 | T16182-YD00-P0MJ-110504 | 2017-07-27 | DHI-TRANSMIT-000505 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63c73818-95aa-4daa-9d83-0fd3e820f339 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3202 | T16182-YE00-P0MJ-110512 | 2017-07-27 | DHI-TRANSMIT-000506 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d322b57-f049-45d6-b0c0-f144cddae38d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3203 | T16182-YD00-P0SMM-128001 | 2017-07-27 | DHI-WTRAN-000518 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dc26d9b-a307-410e-b174-f159061c62af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3204 | T16182-YT01-P0SMM-128004 | 2017-07-27 | DHI-WTRAN-000518 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9951f01-6e68-4135-aeab-d4fb0bbb6964 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3205 | T16182-YR02-P0CJN-290014 | 2017-07-28 | DHI-WTRAN-000519 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7aff5d4-95d7-48a6-92f1-8d07b9d013a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3206 | T16182-CA00-P0UCB-180612 | 2017-07-28 | DHI-TRANSMIT-000507 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b3b043a-1a2e-4221-acfa-43890e163148 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3207 | T16182-CA00-P0UCB-180613 | 2017-07-28 | DHI-TRANSMIT-000507 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db5bec18-f523-4a9f-b34f-40e53f67f108 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3208 | T16182-CA00-P0UCB-180614 | 2017-07-28 | DHI-TRANSMIT-000507 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d136ec8-7e4c-4d47-b4ff-771b29983c95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3209 | T16182-YT01-P0SGA-136609 | 2017-07-28 | DHI-TRANSMIT-000508 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4cdd170-815d-484c-975b-4f36212de424 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3210 | T16182-VE04-P0ULX-172581 | 2017-07-28 | DHI-WTRAN-000520 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89337958-cede-4e90-9eb2-c88967ab768c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3211 | T16182-XB02-P0ULX-172582 | 2017-07-28 | DHI-WTRAN-000520 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10206edd-2fc3-4204-8d29-2df6fd66b349 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3212 | T16182-XB02-P0ULX-172583 | 2017-07-28 | DHI-WTRAN-000520 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=232cc916-dc47-48ee-b5b9-78c511bff955 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3213 | T16182-XB02-P0ULX-172584 | 2017-07-28 | DHI-WTRAN-000520 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=753792a1-8178-46e5-8448-a22af845ce93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3214 | T16182-XB02-P0ULX-172585 | 2017-07-28 | DHI-WTRAN-000520 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71ce4180-c501-4ace-bd13-c8c632dd8bff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3215 | T16182-XG02-P0MJ-110505 | 2017-07-28 | DHI-TRANSMIT-000509 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d02e3bf-692a-4275-8137-460ebd3650d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3216 | T16182-XS00-P0MJ-110510 | 2017-07-28 | DHI-TRANSMIT-000509 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4d2eb4c-d8dd-4b5b-9606-38de1e7c3862 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3217 | T16182-YK08-P0MJ-110506 | 2017-07-28 | DHI-TRANSMIT-000509 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ea54690-49de-4195-a30a-4cdb9a18190b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3218 | T16182-YT01-P0MJ-110508 | 2017-07-28 | DHI-TRANSMIT-000509 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03390722-2531-49ce-98fd-d077be25b29a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3219 | T16182-VE04-P0UZA-172901 | 2017-07-28 | DHI-WTRAN-000521 | IFR | D | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19d7da65-740f-4879-83c1-c0aec71e46b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3220 | T16182-VK02-P0UZA-172908 | 2017-07-28 | DHI-WTRAN-000521 | IFR | D | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f879e6f3-a8c4-4dec-a492-da19e2ad805c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3221 | T16182-XB02-P0UZA-172902 | 2017-07-28 | DHI-WTRAN-000521 | IFR | D | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e223a4b-d7b0-436d-832f-1d3f8a84b3f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3222 | T16182-XB02-P0UZA-172903 | 2017-07-28 | DHI-WTRAN-000521 | IFR | D | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16002e24-73d4-4807-8548-65625da19ed9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3223 | T16182-CA00-P0UST-182001 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19397cd7-00f6-424d-b97b-c2e6417db260 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3224 | T16182-CA00-P0UST-182002 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f2034c2-68ab-404b-b570-4e202041d111 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3225 | T16182-CA00-P0UST-182003 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b55a002f-dd19-469a-aefa-ce5e0fe17d7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3226 | T16182-CA00-P0UST-182004 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef14c93a-d6ff-4944-84c9-2ca1a29addbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3227 | T16182-CA00-P0UST-182005 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce07ce08-aa58-4a55-a3d5-32058a0d84e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3228 | T16182-CA01-P0UST-182051 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94848070-6a48-4f71-9004-9576ab64406c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3229 | T16182-CA01-P0UST-182052 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b7ebc18-066d-4177-b50a-baf510b12ce4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3230 | T16182-CA01-P0UST-182053 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e36261f-862f-4b38-b699-235918f8f1f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3231 | T16182-CA02-P0UST-182058 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6f924bf-b4dc-4e71-89e5-0c3bc43cc611 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3232 | T16182-CA02-P0UST-182059 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5c6bd20-161d-4a96-8078-a40cdc4ff782 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3233 | T16182-CA02-P0UST-182060 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c60469fd-e102-445a-af40-aa545f5b99ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3234 | T16182-CA02-P0UST-182061 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb091140-fa52-4cae-bc5e-961a13bc87e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3235 | T16182-CA03-P0UST-182054 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=218a8cb0-2e7e-4320-8170-e657b149aef5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3236 | T16182-CA03-P0UST-182055 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=576839f3-35de-4568-bdf3-50b70907d3dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3237 | T16182-CA03-P0UST-182056 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=872086a7-7e02-4095-8b07-f79a81c29ff7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3238 | T16182-CA03-P0UST-182062 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75d12f63-2804-4657-99a6-ff352c7e4a37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3239 | T16182-CA03-P0UST-182063 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c1ad449-45db-49ee-815a-6663db35059d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3240 | T16182-CA06-P0UST-182000 | 2017-07-28 | DHI-TRANSMIT-000510 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd5e8f92-4309-4aa9-b962-dc2c70f9a793 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3241 | T16182-YK08-P0PCA-126514 | 2017-07-28 | DHI-WTRAN-000522 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39756624-4123-4245-abbc-edeceddb14a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3242 | T16182-YK08-P0PCA-126516 | 2017-07-28 | DHI-WTRAN-000522 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3545f6d9-1ca9-4a7a-a63f-449a17b14916 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3243 | T16182-CV03-P0ZEN-165731 | 2017-07-28 | DHI-TRANSMIT-000511 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db373971-ab74-40e1-9dc0-0877311eee98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3244 | T16182-YT10-P0ZEN-150305 | 2017-07-28 | DHI-WTRAN-000523 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a28016e4-d671-4325-8620-7372f76c69c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3245 | T16182-YT10-P0ZEN-150306 | 2017-07-28 | DHI-WTRAN-000523 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42a6208b-f28f-4ecb-8613-4d77bbc20dcc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3246 | T16182-YU03-P0CFA-151181 | 2017-07-28 | DHI-WTRAN-000523 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ae67f4b-5e0c-4d6c-b0cc-2f0222a8ab7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3247 | T16182-YU03-P0CHB-151121 | 2017-07-28 | DHI-WTRAN-000523 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=647b19fb-3946-44ed-b475-2792b0835d10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3248 | T16182-YU03-P0CHB-151122 | 2017-07-28 | DHI-WTRAN-000523 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=228b0a30-999e-4770-8a1c-ecc9748ada78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3249 | T16182-YD00-P0CHB-151131 | 2017-07-28 | DHI-WTRAN-000523 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a702658c-2d67-4189-b9d9-8e1e1e047ddf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3250 | T16182-YR02-P0ZEN-152801 | 2017-07-28 | DHI-WTRAN-000524 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81f6ae67-b3ea-4fac-abb6-66f361b7b550 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3251 | T16182-YK10-P0LF-110602 | 2017-07-28 | DHI-WTRAN-000525 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fb9195f-8616-44c7-aa59-e46f8ab0e7c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3252 | T16182-YT01-P0LF-110601 | 2017-07-28 | DHI-WTRAN-000525 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a9fd9f6-1d2b-498f-87a6-d00f9c38ea70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3253 | T16182-YD00-P0BAT-150621 | 2017-07-28 | DHI-WTRAN-000526 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3be44321-2993-4699-a6e1-48148be4926d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3254 | T16182-YD00-P0BAT-150626 | 2017-07-28 | DHI-WTRAN-000526 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afca77eb-5933-4506-b70b-ce9937fe62c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3255 | T16182-YL06-P0ZEN-150101 | 2017-07-28 | DHI-TRANSMIT-000512 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50e655e6-45c1-4e0b-b2de-01fc19f4a442 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3256 | T16182-DE00-P0PCA-126519 | 2017-07-28 | DHI-WTRAN-000527 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b35677bd-337a-46ec-bc5f-68612caabd74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3257 | T16182-VK02-P0MPA-171117 | 2017-07-28 | DHI-TRANSMIT-000513 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae93fd16-e34e-4970-8b8b-36fa611763e6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3258 | T16182-XB02-P0MPA-171106 | 2017-07-28 | DHI-TRANSMIT-000513 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db2c708a-c895-4c65-8c30-ae2439df871f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3259 | T16182-XB02-P0MPA-171113 | 2017-07-28 | DHI-TRANSMIT-000513 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abc00420-b61c-4cab-8528-de9e625318c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3260 | T16182-XN00-P0LD-130208 | 2017-07-28 | DHI-WTRAN-000528 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d790bc97-c5b6-4e80-8d62-004137dd9a68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3261 | T16182-XK00-P6MKA-260005 | 2017-07-28 | DHI-WTRAN-000529 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a05399ea-5615-47b5-8a27-bd7d17f209c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3262 | T16182-XK00-P7MKA-260008 | 2017-07-28 | DHI-WTRAN-000529 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81c38cdb-206f-4f32-9b59-0b65b8a59886 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3269 | T16182-CA07-P0MPA-220023 | 2017-07-30 | DHI-WTRAN-000530 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23616fa3-cf25-4579-9597-e647254423db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3270 | T16182-VL00-P0MPA-220001 | 2017-07-30 | DHI-WTRAN-000530 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e89090e6-d8ef-4d71-b2ef-8bae4cb30a2d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3263 | T16182-CA03-P0UMY-185151 | 2017-08-07 | DHI-WTRAN-000531 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9cf33b1e-f8db-48ef-bed0-609b5e6e7ac8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3264 | T16182-CA03-P0UMY-185152 | 2017-08-07 | DHI-WTRAN-000531 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e767ec2-d505-4457-8663-3ffda75933e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3265 | T16182-CA03-P0UMY-185153 | 2017-08-07 | DHI-WTRAN-000531 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af75d38f-2470-4817-ba38-3b957808ad32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3266 | T16182-CA03-P0UMY-185154 | 2017-08-07 | DHI-WTRAN-000531 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=822c2baa-2bc1-43d9-bd97-9f5ce3262a5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3267 | T16182-CA03-P0UMY-185155 | 2017-08-07 | DHI-WTRAN-000531 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae286ed6-4c9c-4714-ac92-8a92a4c62a1e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3268 | T16182-CA06-P0UMY-185190 | 2017-08-07 | DHI-WTRAN-000531 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a08a56ac-6df4-4e74-9e6d-eba25721d7d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3271 | T16182-YT01-P0BBT-150661 | 2017-08-07 | DHI-TRANSMIT-000533 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63b7cd9c-5c99-4e44-8d8c-653900a0f751 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3272 | T16182-YU03-P0BAT-150631 | 2017-08-07 | DHI-TRANSMIT-000534 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6d96c03-0d32-4fe0-a8be-f81b1c50744c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3273 | T16182-YU03-P0BAT-150636 | 2017-08-07 | DHI-TRANSMIT-000534 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=685c5fb8-0ab9-4eea-b501-49780a5d045f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3274 | T16182-XG02-P0SGA-138001 | 2017-08-07 | DHI-WTRAN-000532 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f05adb2-2ff9-43c5-a626-e3494f54ac47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3275 | T16182-XH01-P0SGA-138011 | 2017-08-07 | DHI-WTRAN-000532 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7e03197-9cfc-4adb-a662-d131415f71ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3276 | T16182-YD00-P0SGZ-138031 | 2017-08-07 | DHI-WTRAN-000532 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e096f66b-8c83-497c-bf3b-948a97152068 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3279 | T16182-CA03-P0UMA-180467 | 2017-08-08 | DHI-WTRAN-000533 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=958f4fe9-2407-42e0-b0a6-fe65623acfe8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3280 | T16182-CA00-P0UYC-182901 | 2017-08-08 | DHI-WTRAN-000534 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf6a80bf-4fec-43cb-a3d8-cea70ed64fb3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3281 | T16182-CA00-P0UYC-182903 | 2017-08-08 | DHI-TRANSMIT-000537 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad07d2e4-fa1b-41c9-b6f3-7ab9734effa4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3282 | T16182-CA00-P0UYC-182905 | 2017-08-08 | DHI-TRANSMIT-000537 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72feb92c-b6cc-46a6-8488-b0982362903d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3283 | T16182-CA00-P0UYC-182906 | 2017-08-08 | DHI-TRANSMIT-000537 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2630bba9-9966-483a-a3bb-c91c9f60e620 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3284 | T16182-YD00-P0LB-122056 | 2017-08-08 | DHI-WTRAN-000535 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59924673-5086-4da2-bf33-c0a8c663ac73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3285 | T16182-XH01-P0LB-122026 | 2017-08-08 | DHI-WTRAN-000536 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84b00b32-b048-4f86-8bba-67ef519a6994 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3286 | T16182-YQ03-P0LB-122087 | 2017-08-08 | DHI-WTRAN-000536 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=415becea-cbde-4159-823b-1f29e34ac142 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3287 | T16182-YE03-P0LB-122067 | 2017-08-08 | DHI-WTRAN-000537 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c25fc153-3863-4c15-a4a2-1167dc3943b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3288 | T16182-YF00-P0LB-122066 | 2017-08-08 | DHI-WTRAN-000537 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae6e766a-177f-451d-b60d-adb7f619eecc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3289 | T16182-YD00-P0CUQ-161112 | 2017-08-08 | DHI-TRANSMIT-000538 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49d658d4-9cd8-47bd-a1f8-65a611a4753c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3290 | T16182-YD00-P0CUQ-161119 | 2017-08-08 | DHI-TRANSMIT-000538 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa9f9317-7cbc-49fa-9a24-958b4738cce1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3291 | T16182-YR05-P0CWQ-161147 | 2017-08-08 | DHI-TRANSMIT-000538 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92eea5a9-6afb-46f4-9b09-854b9b20b43d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3292 | T16182-BP00-P0LAB-140014 | 2017-08-08 | DHI-WTRAN-000538 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b971b46-4868-48e6-bc99-2291488c3e30 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3293 | T16182-XG07-P0SAH-133402 | 2017-08-10 | DHI-TRANSMIT-000547 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d5d355a-7dca-4feb-9db8-e338f170e101 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3294 | T16182-XH02-P0SAH-133404 | 2017-08-10 | DHI-TRANSMIT-000547 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33373c49-6a30-419f-b3fb-a3cdc556f5ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3295 | T16182-XW03-P0SAH-133401 | 2017-08-10 | DHI-TRANSMIT-000547 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5fe6393-3d08-4e3f-873c-2e1cd3cef478 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3296 | T16182-XW03-P0SAH-133403 | 2017-08-10 | DHI-TRANSMIT-000547 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d815e7e6-fa1c-48f9-aee2-0889d6340a11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3297 | T16182-CA00-P0ULD-183902 | 2017-08-10 | DHI-WTRAN-000539 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c39bf6a7-ce80-4077-b4c5-38149bb621be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3298 | T16182-CA00-P0ULD-183904 | 2017-08-10 | DHI-WTRAN-000539 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a53c531e-a009-4b10-8955-9216e753c595 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3299 | T16182-CA01-P0ULD-183954 | 2017-08-10 | DHI-WTRAN-000539 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a50458b2-ce35-4161-a9aa-61cbcf0dc49a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3300 | T16182-XN00-P0PCA-126507 | 2017-08-10 | DHI-WTRAN-000540 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99d593a1-fce7-41b7-a676-a11d5d23847e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3301 | T16182-CV03-P0CWQ-161134 | 2017-08-10 | DHI-WTRAN-000541 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9372e1ef-7c54-498d-aed5-cdb737689982 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3302 | T16182-CA00-P0ULD-183908 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7844f24-597d-483d-a48b-5f649c27b5ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3303 | T16182-CA00-P0ULD-183910 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7466554a-c895-43d3-b7c4-08663de03fbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3304 | T16182-CA02-P0ULD-183959 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36e3b6ba-9c76-4e86-ad6a-cd89cf3a3476 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3305 | T16182-CA02-P0ULD-183960 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ead0fd54-787f-4333-8bd3-a50419e124e6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3306 | T16182-CA02-P0ULD-183961 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc2485bf-0417-4fe7-8caf-0d970954c172 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3307 | T16182-CA03-P0ULD-183962 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8a07fe2-b983-40c9-ae47-eb2ddd0a19b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3308 | T16182-CA03-P0ULD-183963 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04a582b7-b7af-4a6f-a3b5-c875fa76a3b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3309 | T16182-CA03-P0ULD-183964 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=474b8fc9-fbfc-4cce-b4f1-f8d809eecdb4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3310 | T16182-CA03-P0ULD-183965 | 2017-08-11 | DHI-WTRAN-000542 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bd3a50b-c6b6-432a-9e31-9f64f1b1e4a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3311 | T16182-YE03-P0BAU-152535 | 2017-08-14 | DHI-WTRAN-000543 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6fa5a1d-9e7e-4b63-839d-4a2e90b440c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3312 | T16182-XH01-P6MKA-260004 | 2017-08-14 | DHI-WTRAN-000544 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a38d527-c087-465b-bdec-9575774084bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3313 | T16182-XH01-P7MKA-260007 | 2017-08-14 | DHI-WTRAN-000544 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b05e1371-8b28-482a-ba4c-79c976c7e14a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3314 | T16182-CA00-P0UBA-186101 | 2017-08-14 | DHI-TRANSMIT-000553 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=807893fa-86c4-4877-bafe-6bce7ae1e633 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3315 | T16182-CA00-P0UBA-186103 | 2017-08-14 | DHI-TRANSMIT-000553 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbc40f43-7116-4645-84bf-49657350b1bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3316 | T16182-CA00-P0UBA-186104 | 2017-08-14 | DHI-TRANSMIT-000553 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8af3bd4-db6e-4f25-ad8f-be2ad1d5805c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3317 | T16182-CA01-P0UBA-186152 | 2017-08-14 | DHI-TRANSMIT-000553 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d719ae7-746d-437d-9650-54f5a05b3b48 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3318 | T16182-CA01-P0UBA-186154 | 2017-08-14 | DHI-TRANSMIT-000553 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afe606fd-72b7-47b0-9f95-5391bd951c1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3319 | T16182-CA00-P0ULD-183903 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa925496-cb9c-454f-9152-ecba0f8e04b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3320 | T16182-CA00-P0ULD-183905 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ea4a5c6-27a9-48ee-a01c-76453407b83b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3321 | T16182-CA00-P0ULD-183906 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=721ed31d-3ecc-450c-b06a-3ad196984dbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3322 | T16182-CA01-P0ULD-183951 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a7ea40d-3df0-470c-ad2a-925eb4cbbd49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3323 | T16182-CA01-P0ULD-183952 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16e80e7e-1e01-4f35-a518-73dfbdc615c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3324 | T16182-CA01-P0ULD-183953 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c36102e-dcf8-4456-991c-a2241ff5f3d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3325 | T16182-CA02-P0ULD-183955 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9efbfc8-18d1-4473-931e-da4331071e7a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3326 | T16182-CA02-P0ULD-183956 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ee6696b-0907-4635-bb95-90b6a4de4369 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3327 | T16182-CA02-P0ULD-183957 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0cfaf91-c9c1-427f-bf82-ddc49c0d8988 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3328 | T16182-CA02-P0ULD-183958 | 2017-08-14 | DHI-TRANSMIT-000554 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21d711cb-25b2-4202-963b-eceda7ecd471 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3329 | T16182-YK08-P0PCA-126512 | 2017-08-14 | DHI-WTRAN-000545 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6636f22f-dca5-4bf6-8ebb-330960470f15 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3330 | T16182-YT01-P0LAC-126004 | 2017-08-16 | DHI-TRANSMIT-000556 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8c4a6f7-b8f0-4720-8812-06612ac5b659 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3331 | T16182-YT01-P0LAC-126054 | 2017-08-16 | DHI-WTRAN-000546 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb136f2b-f2b1-4a05-aba7-172a2718fe35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3332 | T16182-XJ00-P6MKA-260003 | 2017-08-16 | DHI-WTRAN-000547 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=675d5ee9-de22-47ad-9e60-e267da782406 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3333 | T16182-XJ00-P7MKA-260006 | 2017-08-16 | DHI-WTRAN-000547 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b80d6308-6d30-4da1-b23e-a39d4859d9b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3334 | T16182-YT01-P0LB-122099 | 2017-08-16 | DHI-WTRAN-000548 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e399fe5f-b1c6-41e4-a77d-8477009322c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3335 | T16182-XW01-P0LB-122045 | 2017-08-16 | DHI-WTRAN-000548 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af573304-3b5a-4561-885f-68eabe55b4f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3336 | T16182-XV00-P0LB-122038 | 2017-08-16 | DHI-WTRAN-000548 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26349ebd-c756-42df-91b4-e849a872b25a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3337 | T16182-YR05-P0LB-122084 | 2017-08-16 | DHI-WTRAN-000548 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f896f3f-134d-417e-a072-08ade1918690 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3338 | T16182-YL00-P0LB-122076 | 2017-08-16 | DHI-WTRAN-000549 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6496ddf5-c464-4acc-a23d-f7f19f2c61f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3339 | T16182-YK10-P0LB-122077 | 2017-08-16 | DHI-WTRAN-000549 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f65decb0-7672-4bd4-9cc6-76e0b03d4172 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3340 | T16182-YD00-P0LB-122058 | 2017-08-16 | DHI-WTRAN-000549 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5d6479f-6cc4-420b-8ae3-15d1872f993b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3341 | T16182-YT01-P0LB-122060 | 2017-08-16 | DHI-WTRAN-000549 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a503a29-47c5-44f8-8a46-28228fdc8910 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3342 | T16182-YD00-P0LB-122057 | 2017-08-16 | DHI-WTRAN-000550 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ade92e4-1dea-436d-82ec-3529964b69a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3343 | T16182-YT01-P0LB-122105 | 2017-08-16 | DHI-WTRAN-000550 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0a92e55-9ae2-4e8b-861e-a59359ac3677 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3344 | T16182-YQ01-P0LB-122107 | 2017-08-16 | DHI-WTRAN-000550 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a258d4dd-f4a0-4a28-9d79-14e1739ccbf2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3345 | T16182-XL00-P0STG-130503 | 2017-08-17 | DHI-WTRAN-000551 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfe52e60-fb01-4871-859d-a2e296807851 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3346 | T16182-XW01-P0STG-130501 | 2017-08-17 | DHI-WTRAN-000551 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c04c8a7-b708-48a7-b9bd-1c677c092a5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3347 | T16182-YD00-P0STG-130502 | 2017-08-17 | DHI-WTRAN-000551 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ae3b9a8-11f1-4195-9f3d-79fd084e543d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3348 | T16182-YT01-P0MAG-123036 | 2017-08-17 | DHI-WTRAN-000552 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c02f523-ccd8-4547-836a-7f3c25da5de0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3349 | T16182-YK00-P0ZEN-165314 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea6890f3-fab2-41b0-8e99-7554f90f2b54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3350 | T16182-YK00-P0ZEN-165315 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e466891f-d9be-49e9-81bc-de947c5b2ee2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3351 | T16182-YK00-P0ZEN-165316 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c418eaf-c78a-4065-afb2-0c145a67493a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3352 | T16182-YK00-P0ZEN-165317 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e092226-cb9b-4769-a0c4-7d34d7d4709e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3353 | T16182-YK00-P0ZEN-165318 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb0e92f7-508e-446f-a050-9d857f352ace | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3354 | T16182-YK00-P0ZEN-165319 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f456a26-17f9-4f9d-aae2-b31e2214c053 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3355 | T16182-YK00-P0ZEN-165320 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f4a3eb1-e080-467e-baff-6e7dbb77e389 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3356 | T16182-YK00-P0ZEN-165321 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58900c3d-c422-4868-a253-bb520628409b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3357 | T16182-YK00-P0ZEN-165322 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63796352-b56c-49ef-adaa-dff5115dee2c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3358 | T16182-YK00-P0ZEN-165323 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e88e2ab9-1185-4659-8651-b39938b35288 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3359 | T16182-CV03-P0ZEN-165711 | 2017-08-17 | DHI-TRANSMIT-000558 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6014a3f0-8222-4e7f-90ec-10852c1696ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3360 | T16182-YR05-P0ZEN-161011 | 2017-08-17 | DHI-TRANSMIT-000559 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51327459-3cc8-494b-898e-2b8978682f38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3361 | T16182-YK00-P0SAY-163404 | 2017-08-17 | DHI-WTRAN-000553 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38ed8a59-5bf7-46c6-b3c3-fe71973d8848 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3362 | T16182-YF00-P0CBA-161201 | 2017-08-18 | DHI-TRANSMIT-000562 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f366651-2f04-4cdf-a2a8-d143899bb3a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3363 | T16182-YF00-P0CGA-161301 | 2017-08-18 | DHI-TRANSMIT-000562 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dfdad42-17d8-41c2-92b9-005657ec70f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3364 | T16182-YF00-P0CGA-161302 | 2017-08-18 | DHI-TRANSMIT-000562 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b834216f-0e27-493f-8ade-30e9cebaa31d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3365 | T16182-YF00-P0CBA-161202 | 2017-08-18 | DHI-WTRAN-000554 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20c35cf8-75eb-4eb3-aeb4-f4f9d5fef71f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3366 | T16182-YF00-P0CBA-161210 | 2017-08-18 | DHI-WTRAN-000554 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d576058-62a6-4c4d-bebc-3b60b6f09bd2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3367 | T16182-YF00-P0CBA-161211 | 2017-08-18 | DHI-WTRAN-000554 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4d75c7e-13c3-4ea9-9b5f-483bc9a278c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3368 | T16182-YF00-P0CBA-161220 | 2017-08-18 | DHI-WTRAN-000554 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=332b6511-f00d-4517-90ec-2481f5c40cf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3369 | T16182-YF00-P0CGA-161310 | 2017-08-18 | DHI-WTRAN-000554 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7033d226-bb5a-4d77-ac51-b71f9ffa35e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3370 | T16182-YF00-P0CGA-161311 | 2017-08-18 | DHI-WTRAN-000554 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=338f6629-f503-43d5-855c-8b1ffe405853 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3371 | T16182-YF00-P0CGA-161320 | 2017-08-18 | DHI-WTRAN-000554 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4dea111c-e415-49b8-a09f-9851d0f45983 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3372 | T16182-VL00-P7MPA-220002 | 2017-08-18 | DHI-WTRAN-000555 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cabd912f-2e1f-4a42-af68-5570812f94f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3373 | T16182-CA06-P0ULD-183900 | 2017-08-18 | DHI-TRANSMIT-000563 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75f2283d-3eac-4e1e-98c7-4e5b00bc02fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3374 | T16182-CA05-P0UST-182082 | 2017-08-18 | DHI-TRANSMIT-000564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c6c5c5a-7246-47a2-87cb-6ffcd372567e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3375 | T16182-CA05-P0UST-182083 | 2017-08-18 | DHI-TRANSMIT-000564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9575d79-c1b9-45eb-8c5e-98344599eda0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3376 | T16182-CA05-P0UST-182084 | 2017-08-18 | DHI-TRANSMIT-000564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f49cf7f-cce5-4a77-a0d2-5e9741119884 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3377 | T16182-CA05-P0UST-182081 | 2017-08-18 | DHI-WTRAN-000556 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eab67b2e-6885-42c7-8b35-582db25a7fe0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3378 | T16182-CA05-P0UST-182085 | 2017-08-18 | DHI-WTRAN-000556 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61be543f-513e-4c25-bc78-19bdadc2b4f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3379 | T16182-YL00-P0GHC-129011 | 2017-08-18 | DHI-WTRAN-000557 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e0b9b93-9048-476a-92ea-6379cf0de0bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3380 | T16182-YL00-P0GHC-129036 | 2017-08-18 | DHI-WTRAN-000557 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b246627f-dee8-42c1-9c2b-fd2d0608460a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3381 | T16182-YT01-P0GHC-129004 | 2017-08-18 | DHI-WTRAN-000558 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea555df3-5050-47b8-a509-a222d10b85f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3382 | T16182-YT01-P0GHC-129034 | 2017-08-18 | DHI-WTRAN-000558 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7eb9f1d-00ed-4db9-9fc2-f2bc6ddab485 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3383 | T16182-XB02-P0ULX-171223 | 2017-08-18 | DHI-TRANSMIT-000565 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d49277be-b4a7-4ed2-ba26-7b6ff1418023 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3384 | T16182-YK09-P0SAA-133302 | 2017-08-18 | DHI-TRANSMIT-000566 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49764f5a-d876-4892-b338-460b122c0325 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3385 | T16182-CA01-P0UCB-180653 | 2017-08-18 | DHI-TRANSMIT-000567 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2181bfe-e5ac-4215-a730-88aa073492af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3386 | T16182-CA01-P0UCB-180654 | 2017-08-18 | DHI-TRANSMIT-000567 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d40816fd-0c4a-4839-9163-3b434ab0aa98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3387 | T16182-CA01-P0UCB-180660 | 2017-08-18 | DHI-TRANSMIT-000567 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8e2bf24-2d9e-425c-b140-92a03230b875 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3388 | T16182-CA01-P0UCB-180661 | 2017-08-18 | DHI-TRANSMIT-000567 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f2c40c0-21b8-4d33-ab78-c68c170fb16c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3389 | T16182-CA02-P0UCB-180666 | 2017-08-18 | DHI-TRANSMIT-000567 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8313359a-98b7-4671-8958-0028cde32f67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3390 | T16182-YK08-P0PCA-126513 | 2017-08-18 | DHI-WTRAN-000559 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fad9d4e-a5a6-4476-b577-5b2cdc411b20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3391 | T16182-XB02-P0ULX-171203 | 2017-08-18 | DHI-TRANSMIT-000568 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1088fe39-277a-4cfd-ae08-b5fccb565068 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3392 | T16182-YF00-P0MAG-123032 | 2017-08-18 | DHI-WTRAN-000560 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0645004-52ee-47d8-92b1-993b924d93aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3393 | T16182-VE04-P0UZA-172901 | 2017-08-18 | DHI-TRANSMIT-000569 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6f09516-04e5-46a0-9b64-17fd675b4e03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3394 | T16182-VK02-P0UZA-172908 | 2017-08-18 | DHI-TRANSMIT-000569 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6eac4c29-8773-4818-acbb-5e2606c8e6ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3395 | T16182-XB02-P0UZA-172902 | 2017-08-18 | DHI-TRANSMIT-000569 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d55772d4-ec23-42a1-8852-23ee7bcf76e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3396 | T16182-XB02-P0UZA-172903 | 2017-08-18 | DHI-TRANSMIT-000569 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6696dcf1-becb-4913-b43c-d8f122127c77 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3397 | T16182-CA05-P0UMA-180481 | 2017-08-18 | DHI-TRANSMIT-000570 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8b95f10-ce8f-4ba6-9510-615cbe0fce33 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3398 | T16182-CA05-P0UMA-180482 | 2017-08-18 | DHI-TRANSMIT-000570 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5fc4280-9525-4005-a701-8334aa2eba54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3399 | T16182-CV03-P0ZEN-165701 | 2017-08-18 | DHI-TRANSMIT-000571 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64325141-3c37-4319-91e4-23320bd61218 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3400 | T16182-VE04-P8UTH-172011 | 2017-08-18 | DHI-TRANSMIT-000572 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2395c28-0fcb-4a74-af62-212539b9297a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3401 | T16182-XB02-P8UTH-172012 | 2017-08-18 | DHI-TRANSMIT-000572 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3c65afa-0bcf-492e-b81b-9c9cc5a3bcf7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3402 | T16182-YE03-P0BAU-152522 | 2017-08-18 | DHI-TRANSMIT-000573 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=224c3169-c4f0-4ab5-ae7d-e7722290a235 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3403 | T16182-YE03-P0BAU-152518 | 2017-08-18 | DHI-WTRAN-000561 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bfeed1a-c78f-4c03-9fed-df0e5ed7621c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3404 | T16182-YE03-P0BAU-152525 | 2017-08-18 | DHI-WTRAN-000561 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f208220-5755-4a4d-9a2c-0fa62f540210 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3405 | T16182-VE04-P0UHA-171819 | 2017-08-18 | DHI-TRANSMIT-000574 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4dd166a-ed6a-425e-aa01-3c68a36dba3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3406 | T16182-XB02-P0UHA-171815 | 2017-08-18 | DHI-TRANSMIT-000574 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5853fcce-0fa3-4e3a-a621-bfe1aa8b0468 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3407 | T16182-XB02-P0UHA-171816 | 2017-08-18 | DHI-TRANSMIT-000574 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a49f994-8ebe-4523-b50b-6a617ad8f7a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3408 | T16182-YR02-P0ZEN-152801 | 2017-08-18 | DHI-TRANSMIT-000575 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfdf174b-1970-450c-a954-67d6c8082a7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3409 | T16182-YD00-P0GCF-130006 | 2017-08-21 | DHI-WTRAN-000562 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23dd183c-d689-4c31-9e72-721b7bdbfe67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3410 | T16182-YU02-P0GCF-130010 | 2017-08-21 | DHI-WTRAN-000562 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75e4936e-eea6-4850-8583-fa4ca01ddf6c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3411 | T16182-YF00-P0GCF-130018 | 2017-08-21 | DHI-WTRAN-000563 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b099ecfa-cea1-4731-80df-419a4f18c7f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3412 | T16182-YK00-P0GCF-130016 | 2017-08-21 | DHI-WTRAN-000563 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9f07636-0f09-4066-bee5-4e4bc871f9a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3413 | T16182-YM01-P0GHC-129008 | 2017-08-21 | DHI-WTRAN-000564 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=610dc3d2-8008-49d5-8ffe-df535f50760e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3414 | T16182-YM01-P0GHC-129035 | 2017-08-21 | DHI-WTRAN-000564 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00fa6f87-19a7-4622-868b-d873911d13a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3415 | T16182-YK09-P0GHC-129003 | 2017-08-21 | DHI-WTRAN-000565 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc3e1257-6dcf-4440-b6fe-ed48fa573a56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3416 | T16182-YK09-P0GHC-129033 | 2017-08-21 | DHI-WTRAN-000565 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49bc4786-4368-4f4b-9e83-46a066ab0332 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3417 | T16182-CA00-P0USG-182701 | 2017-08-21 | DHI-TRANSMIT-000577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4da9cf77-7dcf-418c-ac77-8314da378bef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3418 | T16182-CA00-P0USG-182702 | 2017-08-21 | DHI-TRANSMIT-000577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f21afaab-b168-4665-b3ff-5fc2a7d2b378 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3419 | T16182-CA00-P0USG-182703 | 2017-08-21 | DHI-TRANSMIT-000577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1e5f46e-d33f-403b-b20d-bd12b6b9f943 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3420 | T16182-CA00-P0USG-182704 | 2017-08-21 | DHI-TRANSMIT-000577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78704631-1f56-43c7-a84e-de36bb276106 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3421 | T16182-CA01-P0USG-182752 | 2017-08-21 | DHI-TRANSMIT-000577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7c27de2-b241-4d20-8827-bfc747ac0baa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3422 | T16182-YT01-P0GHC-129002 | 2017-08-21 | DHI-WTRAN-000566 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f8fae2e-7437-490c-982d-66c6594cce01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3423 | T16182-YT01-P0GHC-129032 | 2017-08-21 | DHI-WTRAN-000566 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=648ba1e8-dcbf-4829-84b5-12f8b092f769 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3424 | T16182-CA05-P0UYC-182985 | 2017-08-21 | DHI-WTRAN-000567 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f87dfb7-c07a-4454-8433-2c174f4e07e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3425 | T16182-YK08-P0LF-110102 | 2017-08-21 | DHI-TRANSMIT-000578 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a32df0cc-cbbd-4e5e-9360-14b91d28127d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3426 | T16182-YT01-P0LF-110101 | 2017-08-21 | DHI-WTRAN-000568 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdd667bb-7be5-4aae-bcef-9192675117c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3427 | T16182-YT10-P0ZEN-150304 | 2017-08-21 | DHI-WTRAN-000569 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f38ec3ab-a103-4f41-80c4-963bab35aa19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3428 | T16182-YT10-P0ZEN-152223 | 2017-08-21 | DHI-WTRAN-000570 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7974e57c-d93c-41b4-a66c-d49c949ac06d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3429 | T16182-YB11-P0ZEN-152421 | 2017-08-21 | DHI-WTRAN-000570 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=466a8b9c-938b-452a-8da9-7159c9a27049 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3430 | T16182-YQ01-P0ZEN-152321 | 2017-08-21 | DHI-WTRAN-000570 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a6b9de4-d8e4-4695-a661-d7b49ba20850 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3431 | T16182-CN00-P0ZEN-110703 | 2017-08-21 | DHI-WTRAN-000571 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4d5ccfe-704f-4412-9e6c-54a2389b0d03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3432 | T16182-CN00-P0ZEN-110704 | 2017-08-21 | DHI-WTRAN-000571 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=734f8b9c-7b68-4928-93f8-c46a0d1fba21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3433 | T16182-CN00-P0ZEN-110706 | 2017-08-21 | DHI-WTRAN-000571 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc21a16e-45c7-4001-a92b-ce51dad1091b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3434 | T16182-YL01-P0CBA-161101 | 2017-08-21 | DHI-TRANSMIT-000579 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5be2178-1f1f-44b5-b24e-dece29c213f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3435 | T16182-VE04-P0UMX-171051 | 2017-08-21 | DHI-WTRAN-000572 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b558f460-46c3-4599-9d9f-292a47b6de99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3436 | T16182-XB02-P0UMX-171052 | 2017-08-21 | DHI-WTRAN-000572 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=625d27e4-1f69-43f5-ac5b-c7753fb37eb6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3437 | T16182-XB02-P0UMX-171053 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2890ac90-85f4-49a7-83f8-f7bcf966b031 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3438 | T16182-XB02-P0UMX-171054 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a41876f-e444-4089-a7e6-6b40f9a47a25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3439 | T16182-XB02-P0UMX-171055 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62981f93-a6bf-4a65-8c1c-e567537786d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3440 | T16182-XB02-P0UMX-171056 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4a3981e-73ad-4452-b383-4a1544ed31b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3441 | T16182-XB02-P0UMX-171057 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fcee46e-98be-4453-8cdd-5429af4068aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3442 | T16182-XB02-P0UMX-171058 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c09dd92-bfe1-491c-ab4b-39f50710d7fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3443 | T16182-VK02-P0UMX-171059 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cca0baf-6f43-4739-b0a4-93d7be75a976 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3444 | T16182-VK02-P0UMX-171060 | 2017-08-21 | DHI-WTRAN-000572 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16708307-f7f2-4ce8-adb1-c0d3cd022b3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3445 | T16182-XB02-P0UMX-171061 | 2017-08-21 | DHI-WTRAN-000572 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22812d53-bc7d-4652-b4c2-0a8c8395e4f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3446 | T16182-XB02-P0UMX-171062 | 2017-08-21 | DHI-WTRAN-000572 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=724a1aa4-f621-427b-bbc9-3603723d2604 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3447 | T16182-XB02-P0UMX-171063 | 2017-08-21 | DHI-WTRAN-000572 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cda9cd4b-2aee-40ff-842b-97cb19e35d7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3448 | T16182-YE01-P0BAU-152602 | 2017-08-22 | DHI-TRANSMIT-000580 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b1379f0-8e99-4bae-92c8-7b15449d39a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3449 | T16182-YE01-P0BAU-152620 | 2017-08-22 | DHI-TRANSMIT-000580 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b659d179-2d2c-435e-9224-d026ec1b3a88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3450 | T16182-YE03-P0BAU-152529 | 2017-08-22 | DHI-TRANSMIT-000580 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ee2cfc7-c3fb-47ca-a24d-6c406113a965 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3451 | T16182-YE03-P0BAU-152534 | 2017-08-22 | DHI-TRANSMIT-000580 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1888eb05-ef71-44a5-b69a-17ef4e6bc1b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3452 | T16182-CA06-P0UTG-184900 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdeed684-1593-4865-bede-a29f06e23606 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3453 | T16182-CA00-P0UTG-184901 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ab65049-33f8-4191-be64-01c782c0bc9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3454 | T16182-CA00-P0UTG-184902 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2411b72f-96c5-48a8-8ce9-b041a9bf68a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3455 | T16182-CA00-P0UTG-184903 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af5ec3fc-ad11-46df-80be-ae5615dfda92 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3456 | T16182-CA01-P0UTG-184951 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eddb02b6-13d7-4bca-a718-1ec67a34da1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3457 | T16182-CA01-P0UTG-184952 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e354a341-327b-4634-a494-a784a7219143 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3458 | T16182-CA01-P0UTG-184953 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0554189a-feca-45dc-96da-892f1228ac19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3459 | T16182-CA02-P0UTG-184954 | 2017-08-22 | DHI-TRANSMIT-000581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67940d7b-1b84-4934-998e-81243c755623 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3460 | T16182-XB02-P0UMX-171006 | 2017-08-22 | DHI-TRANSMIT-000582 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cebb4d3-aa58-4fdf-965a-6f6f54c4fd2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3461 | T16182-XB02-P0UMX-171007 | 2017-08-22 | DHI-TRANSMIT-000582 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3da8f121-7e26-4216-8616-5cce2944c266 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3462 | T16182-XB02-P0UMX-171008 | 2017-08-22 | DHI-TRANSMIT-000582 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b953a871-bf28-48aa-99c0-b9291f20c4f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3463 | T16182-XB02-P0UMX-171011 | 2017-08-22 | DHI-TRANSMIT-000582 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ae5ac2d-e14c-4a25-aa0d-634ae5224bf5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3464 | T16182-XW03-P0LA-110061 | 2017-08-22 | DHI-WTRAN-000573 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eea3ea00-dae2-4eac-bceb-5d4c2c2c8853 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3465 | T16182-YK09-P0LCB-127034 | 2017-08-22 | DHI-WTRAN-000574 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cf70e64-bc90-455e-a366-7daac74780c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3466 | T16182-YT10-P0SGA-136605 | 2017-08-22 | DHI-TRANSMIT-000583 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=647e020a-4b74-46d1-b338-0f4e01adae2b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3467 | T16182-YD00-P0SGZ-137331 | 2017-08-22 | DHI-TRANSMIT-000584 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06eac06f-4a10-4de6-81d9-36c717bab717 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3468 | T16182-YT01-P0SGA-136610 | 2017-08-22 | DHI-TRANSMIT-000585 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef0a8b53-7daf-42b5-b173-9c21bfcb2fdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3469 | T16182-YD02-P0ZEN-165501 | 2017-08-23 | DHI-WTRAN-000575 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e8896b5-b623-48b7-9d3a-70c5f3449496 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3470 | T16182-CA00-P0ULD-183902 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbd4eb13-d56f-4c7c-bbf0-3eb1a0ec59c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3471 | T16182-CA00-P0ULD-183904 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7841ace8-3be8-424e-b87b-9715461b7433 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3472 | T16182-CA01-P0ULD-183952 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=707f3901-ac5d-4ddd-8e67-714c730b2627 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3473 | T16182-CA01-P0ULD-183954 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ca1ab2d-9d77-49ce-adb1-9f9d4e550129 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3474 | T16182-CA02-P0ULD-183959 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7abbf7d9-f2c4-4679-a967-0ce7daf58859 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3475 | T16182-CA02-P0ULD-183960 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86eedb98-13c7-4ca4-b4f6-c88ce1d69cb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3476 | T16182-CA02-P0ULD-183961 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efcc0c26-5c57-43e1-9e56-91bed62f1c74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3477 | T16182-CA03-P0ULD-183962 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b2ad143-e57d-4b11-b323-f8b91756808a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3478 | T16182-CA03-P0ULD-183965 | 2017-08-23 | DHI-TRANSMIT-000586 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4862993d-7ba0-460a-9e4b-d306a50a79d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3479 | T16182-XJ00-P0LB-122027 | 2017-08-23 | DHI-WTRAN-000576 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d2a5efd-e1cd-4c3a-8513-e21cf5dc28a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3480 | T16182-YD02-P0ZEN-165571 | 2017-08-23 | DHI-WTRAN-000577 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6f80c98-d40a-4a73-8440-4861e0d53547 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3481 | T16182-YD02-P0ZEN-165572 | 2017-08-23 | DHI-WTRAN-000577 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbc33086-8cc6-42f5-84da-4f3c298da1b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3482 | T16182-YD00-P0SML-128013 | 2017-08-24 | DHI-WTRAN-000578 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91cd0c7e-3bcd-4bc0-8265-4094636e1e16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3483 | T16182-YT01-P0SML-128018 | 2017-08-24 | DHI-WTRAN-000578 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=360d5078-5fd7-4d77-9fb3-e9582b1cdc5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3484 | T16182-YT10-P0MKY-290010 | 2017-08-24 | DHI-WTRAN-000579 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3d10d3b-315c-402d-9cd1-83132a425827 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3485 | T16182-YE03-P0BAU-152518 | 2017-08-24 | DHI-TRANSMIT-000587 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=665203da-8a9c-437b-ad59-d68830bc841d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3486 | T16182-YE03-P0BAU-152512 | 2017-08-24 | DHI-WTRAN-000580 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb9e17ff-977f-45ed-b50f-15400d36b70b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3487 | T16182-YE03-P0BAU-152537 | 2017-08-24 | DHI-WTRAN-000580 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4c05087-3b9f-46bf-bb43-2ae6a5505c2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3488 | T16182-YE03-P0BAU-152538 | 2017-08-24 | DHI-WTRAN-000580 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c8b472f-17fc-456c-8393-8541d97448c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3489 | T16182-XK00-P0PCA-126538 | 2017-08-24 | DHI-TRANSMIT-000588 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4405bf53-daa4-42c9-98f2-dd6be53eb819 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3490 | T16182-CA00-P0ULD-183908 | 2017-08-24 | DHI-WTRAN-000581 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95edc726-b963-46f4-b96e-a99ef1b965f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3491 | T16182-CA00-P0ULD-183910 | 2017-08-24 | DHI-WTRAN-000581 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2bb28e1-69b6-49e5-b966-27a22d9afb74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3492 | T16182-CA03-P0ULD-183963 | 2017-08-24 | DHI-WTRAN-000581 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7dfe3d7-6707-43b3-ab5f-ad262aa9cdb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3493 | T16182-CA03-P0ULD-183964 | 2017-08-24 | DHI-WTRAN-000581 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a91b664-c321-4b69-af9a-939d5d14c5a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3494 | T16182-YD04-P0ZEN-152004 | 2017-08-24 | DHI-TRANSMIT-000589 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2fc71781-3984-4794-b252-08dd56023501 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3495 | T16182-YE00-P0ZEN-152717 | 2017-08-24 | DHI-TRANSMIT-000589 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=730123de-311a-41c7-aaad-3f8be93f39dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3496 | T16182-YE00-P0ZEN-152726 | 2017-08-24 | DHI-TRANSMIT-000589 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6a201c8-d5c0-465e-926d-b797a974b19e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3497 | T16182-YE00-P0ZEN-152729 | 2017-08-24 | DHI-TRANSMIT-000589 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=908f650b-a55f-4299-a9f9-6193a25040a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3498 | T16182-YE00-P0ZEN-152736 | 2017-08-24 | DHI-TRANSMIT-000589 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9afbd289-d577-4937-9647-095668533781 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3499 | T16182-YE00-P0ZEN-152727 | 2017-08-24 | DHI-WTRAN-000582 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=455f8aec-3efc-40f7-82ee-90e0496ec72c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3500 | T16182-YE00-P0ZEN-152728 | 2017-08-24 | DHI-WTRAN-000582 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=564be732-68c8-4d58-a57a-7abad3bbd22c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3501 | T16182-YE00-P0ZEN-152730 | 2017-08-24 | DHI-WTRAN-000582 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01b77a3a-8316-45a0-bfde-b619207246c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3502 | T16182-YT01-P0BAA-150751 | 2017-08-25 | DHI-TRANSMIT-000592 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45194d23-1cd1-441c-8e75-2cf8adee4bf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3503 | T16182-YU05-P0ZEN-150221 | 2017-08-25 | DHI-TRANSMIT-000592 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5cdaf2f-1262-4541-aa9b-60ded424ef31 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3504 | T16182-YD00-P0BAA-150782 | 2017-08-25 | DHI-WTRAN-000583 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40cee781-a89d-47ab-b590-35653444e475 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3505 | T16182-YF00-P0MJ-110511 | 2017-08-25 | DHI-WTRAN-000584 | IFR | B | DR | TRUE | TRUE | 2017-08-25_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a5af417-95f0-4985-91fa-60fb168c9fde | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3506 | T16182-CA00-P0UYP-183201 | 2017-08-25 | DHI-WTRAN-000585 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c8557be-d9a0-447e-b1e9-209941ba1c2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3507 | T16182-CA00-P0UYP-183202 | 2017-08-25 | DHI-WTRAN-000585 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bcc77a4c-de42-404b-9c5b-a461b5a989f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3508 | T16182-CA00-P0UYP-183203 | 2017-08-25 | DHI-WTRAN-000585 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01fed1c0-f13d-45dd-97ef-80bb7c75f74b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3509 | T16182-CA00-P0UYP-183204 | 2017-08-25 | DHI-WTRAN-000585 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3245d8d4-5e27-49f2-973f-45accc3af8c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3510 | T16182-CA06-P0UYP-183200 | 2017-08-25 | DHI-WTRAN-000585 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24998fdb-b4e4-488a-8cd8-e616644c1919 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3511 | T16182-YE03-P0BAU-152517 | 2017-08-25 | DHI-WTRAN-000586 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cf721fd-d925-4aef-a1c2-29394ce0b047 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3512 | T16182-YE03-P0BAU-152530 | 2017-08-25 | DHI-WTRAN-000586 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29580b2d-2676-4378-a6ae-5007cecf1eeb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3513 | T16182-YE03-P0BAU-152531 | 2017-08-25 | DHI-WTRAN-000586 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=511a8511-f57f-45c5-90f3-d331352430e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3514 | T16182-YE03-P0BAU-152536 | 2017-08-25 | DHI-WTRAN-000586 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41da00ae-31b3-4ee4-a367-ef17a88dbd84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3515 | T16182-YE03-P0BAU-152512 | 2017-08-25 | DHI-TRANSMIT-000593 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f21b031-f5de-4493-860f-07e24631c1c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3516 | T16182-YE03-P0BAU-152537 | 2017-08-25 | DHI-TRANSMIT-000593 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d026937-2dda-4220-ba2e-335c830c27b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3517 | T16182-YE03-P0BAU-152538 | 2017-08-25 | DHI-TRANSMIT-000593 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a3c701a-9701-44bf-90e9-b067c27ac854 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3518 | T16182-YE03-P0BAU-152529 | 2017-08-25 | DHI-TRANSMIT-000593 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b9c1d02-aa67-4ce5-be1b-8b866f6c245b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3519 | T16182-CA00-P0QJA-184801 | 2017-08-25 | DHI-TRANSMIT-000594 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0974dade-3049-4864-87f7-4268bb2ef54b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3520 | T16182-CA00-P0QJA-184802 | 2017-08-25 | DHI-TRANSMIT-000594 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff0c4931-4cbd-4119-be9e-64ae71c3faf3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3521 | T16182-CA00-P0QJA-184803 | 2017-08-25 | DHI-TRANSMIT-000594 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5b392bb-f06f-4e49-a599-c15604e922bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3522 | T16182-YQ08-P0CY-154046 | 2017-08-25 | DHI-WTRAN-000587 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db4f6668-e7cf-4a33-ae6e-d8d964c0e229 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3523 | T16182-YQ01-P0ZEN-152316 | 2017-08-25 | DHI-WTRAN-000588 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ed25e8c-7425-452f-a6cb-f7842ffba5ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3524 | T16182-YT10-P0ZEN-152218 | 2017-08-25 | DHI-WTRAN-000588 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca43c50f-7ae6-4f13-96cb-d5e7e15225d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3525 | T16182-YD00-P0LAC-126010 | 2017-08-25 | DHI-WTRAN-000589 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa7bb22d-9da7-450c-bda2-71cddcdb86b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3526 | T16182-YD00-P0LAC-126060 | 2017-08-25 | DHI-WTRAN-000589 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebeb7eab-df63-4ad3-a63d-59125fb0f64c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3527 | T16182-CA00-P0UBA-181104 | 2017-08-28 | DHI-WTRAN-000590 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3528 | T16182-YD00-P0BT-151041 | 2017-08-28 | DHI-WTRAN-000591 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dda74206-d4bf-49ee-ab69-9e035f8b8271 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3529 | T16182-YD00-P0BT-151046 | 2017-08-28 | DHI-WTRAN-000591 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ed9cc0f-683f-4727-acee-77c1352d2118 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3530 | T16182-YD00-P0BT-151051 | 2017-08-28 | DHI-WTRAN-000591 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c64f243-4a93-4fef-b33d-81b8821fa62b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3531 | T16182-YT10-P0BT-151001 | 2017-08-28 | DHI-TRANSMIT-000595 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad6a4971-a07c-4177-95e1-beb6b82953c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3532 | T16182-YF00-P0BA-150401 | 2017-08-28 | DHI-TRANSMIT-000596 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd492003-534d-49c4-bb0f-64b49cbd24ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3533 | T16182-YF00-P0BA-150404 | 2017-08-28 | DHI-TRANSMIT-000596 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e390eec-1e8e-40a8-b8f8-17a3b5791558 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3534 | T16182-YK08-P0LAC-126027 | 2017-08-28 | DHI-WTRAN-000592 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a518b87-dd36-4498-a2b4-02cddc704728 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3535 | T16182-YK08-P0LAC-126077 | 2017-08-28 | DHI-WTRAN-000592 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0811e0bd-782f-4bba-8ef7-8cabf1547ca3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3536 | T16182-YF00-P0CBA-161216 | 2017-08-28 | DHI-TRANSMIT-000597 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b206bb2-e576-4022-a886-0953c9c2ad56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3537 | T16182-YF00-P0CGA-161316 | 2017-08-28 | DHI-TRANSMIT-000597 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39ea0117-60f3-4292-ba53-642a14016c9f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3538 | T16182-YF00-P0CBA-161222 | 2017-08-28 | DHI-TRANSMIT-000598 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae606a4e-fc1d-4575-8d7b-515de09e23f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3539 | T16182-YF00-P0CGA-161322 | 2017-08-28 | DHI-TRANSMIT-000598 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b80ef3f6-31fa-482b-9bce-98ff443a2ab6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3540 | T16182-CA03-P0UMY-185151 | 2017-08-28 | DHI-WTRAN-000593 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0773c85f-9c2e-4f81-8182-8cd66218b258 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3541 | T16182-CA03-P0UMY-185152 | 2017-08-28 | DHI-WTRAN-000593 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a266e73-b3a8-4bb5-bc63-f40bfa9901a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3542 | T16182-CA03-P0UMY-185153 | 2017-08-28 | DHI-WTRAN-000593 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9a7a0f9-694e-4ce9-8a94-a9928968732c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3543 | T16182-CA03-P0UMY-185154 | 2017-08-28 | DHI-WTRAN-000593 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a02a1236-d355-4abf-b055-5d6463845754 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3544 | T16182-CA03-P0UMY-185155 | 2017-08-28 | DHI-WTRAN-000593 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c693e7d5-8587-412d-8ddc-a192479cc790 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3545 | T16182-CA06-P0UMY-185190 | 2017-08-28 | DHI-WTRAN-000593 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=670ab9e9-d39b-44f4-b444-b97d2b32c5ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3546 | T16182-YF00-P0CBA-161208 | 2017-08-28 | DHI-TRANSMIT-000599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf981c26-556b-4d02-91aa-58b7dc0dc670 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3547 | T16182-YF00-P0CGA-161308 | 2017-08-28 | DHI-TRANSMIT-000599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b945692a-6d4c-4af6-ba98-e29a2d62d438 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3548 | T16182-YF00-P0BB-150403 | 2017-08-28 | DHI-TRANSMIT-000600 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecc4c0f1-19ba-4134-9f21-7a44dff430ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3549 | T16182-YT01-P0BF-150901 | 2017-08-28 | DHI-WTRAN-000594 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df61b37b-89bf-4539-bb4c-69982f011ea5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3550 | T16182-YD02-P0LB-122063 | 2017-08-28 | DHI-WTRAN-000595 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8b4afcc-8fe1-40f9-9ab0-ed353d69d1e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3551 | T16182-YU02-P0BFA-150918 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97a39b4a-0a95-4c11-ad25-a6fc48896cb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3552 | T16182-YU02-P0BFA-150911 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54dc58f6-5b86-410b-b9d8-51a0523ab2b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3553 | T16182-YU02-P0BFA-150912 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7499463-2de7-481a-b3db-619abd4ccbb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3554 | T16182-YU02-P0BFA-150913 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c7857cb-a036-4468-a214-04cfcd025cad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3555 | T16182-YU02-P0BFA-150914 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f40b3be-4ab2-48ec-95b6-2ef865103cc2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3556 | T16182-YU02-P0BFA-150915 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dab09f31-ec97-4e47-89b8-d79c825d0976 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3557 | T16182-YU02-P0BFA-150916 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ba1f21c-83f6-4752-a81f-10aaef0db3d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3558 | T16182-YU02-P0BFA-150917 | 2017-08-28 | DHI-WTRAN-000596 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bf24146-a811-4543-98d6-b2b9cd10b6ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3559 | T16182-YD00-P0BF-150931 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b41a04b-8f20-41e9-aab5-701780ad8692 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3560 | T16182-YD00-P0BF-150932 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4f675d0-e3f0-46a9-b739-8c3079c045e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3561 | T16182-YD00-P0BF-150933 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60e98f59-25c6-41e0-9001-3d62cce3b816 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3562 | T16182-YD00-P0BF-150934 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6ed6d6a-784f-4195-8d3b-1febb7db7700 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3563 | T16182-YD00-P0BF-150935 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dda59dbc-4060-45c4-8f87-9478f344160b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3564 | T16182-YD00-P0BF-150936 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d430720-2a49-4bf6-947d-d5fdc7122b72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3565 | T16182-YD00-P0BF-150937 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf4a679c-7999-47e1-b0a7-c3597e3cb8d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3566 | T16182-YD00-P0BF-150938 | 2017-08-28 | DHI-WTRAN-000597 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c06cea71-aef6-4968-9e87-d46a76854250 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3567 | T16182-YU03-P0BFA-150951 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdebb831-363b-4e91-bb31-cb7d42a3f16f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3568 | T16182-YU03-P0BFA-150952 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cbfc6ea-4162-485c-a401-42ae81f1b7fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3569 | T16182-YU03-P0BFA-150953 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32b8a58a-875b-49d2-9442-a90659d19795 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3570 | T16182-YU03-P0BFA-150954 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2254c4c-8266-401e-99b8-a34c8b050365 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3571 | T16182-YU03-P0BFA-150955 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c2aae94-d014-4954-92ba-96449a6c3777 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3572 | T16182-YU03-P0BFA-150956 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5898c3cd-bab3-4b8d-b29b-ea3c029567c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3573 | T16182-YU03-P0BFA-150957 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf98adb6-5288-41c3-8547-506c3d58c9b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3574 | T16182-YU03-P0BFA-150958 | 2017-08-28 | DHI-WTRAN-000598 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee21934a-932a-4395-a11b-536df724540f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3575 | T16182-YD00-P0PGB-110404 | 2017-08-28 | DHI-WTRAN-000599 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a2a2cc6-c36c-401f-8018-f5591cd9c3b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3576 | T16182-YD00-P0PGB-110405 | 2017-08-28 | DHI-WTRAN-000599 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08ecfca4-9159-459e-98fa-dcdc971001cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3577 | T16182-YL22-P0PGB-110406 | 2017-08-28 | DHI-WTRAN-000599 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99abf747-ba51-4f00-999c-6f7c4bb35d95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3578 | T16182-YT01-P0PGB-110407 | 2017-08-28 | DHI-WTRAN-000599 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48114cc5-5202-4307-b32f-06bcd261d2d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3579 | T16182-YF00-P0CBA-161214 | 2017-08-28 | DHI-TRANSMIT-000601 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbc111fa-ebea-46eb-9259-1e28442e7274 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3580 | T16182-YF00-P0CGA-161314 | 2017-08-28 | DHI-TRANSMIT-000601 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6924d90-f8f8-448f-9b6f-e1d363295c69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3581 | T16182-YT01-P0LB-122108 | 2017-08-28 | DHI-WTRAN-000600 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99b8b1f9-4c40-4dbb-acbc-2058a2ba8314 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3582 | T16182-XL00-P0LB-122031 | 2017-08-28 | DHI-WTRAN-000600 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=230c535d-8197-4ca2-9a57-081d79156051 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3583 | T16182-XG02-P0SGA-138401 | 2017-08-28 | DHI-WTRAN-000601 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec175888-15a4-4322-a80f-81238a6c6377 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3584 | T16182-XH01-P0SGA-138411 | 2017-08-28 | DHI-WTRAN-000601 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=563823e8-cb97-46a2-8099-3e028ff2bd3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3585 | T16182-YD00-P0CYE-138441 | 2017-08-28 | DHI-WTRAN-000602 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4dca3b9f-a753-4396-b63a-2da26260a3f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3586 | T16182-YU02-P0CYE-138442 | 2017-08-28 | DHI-WTRAN-000602 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba545bd7-22ea-448b-9274-752b94885b8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3587 | T16182-DN05-P0SG-136620 | 2017-08-28 | DHI-WTRAN-000603 | IFR | B | DR | TRUE | TRUE | 2018-04-05_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4613e1dc-3752-4d39-bd47-a22f9d445dba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3588 | T16182-DP00-P0ZEN-020007 | 2017-08-28 | DHI-WTRAN-000604 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faf7096d-1ec6-4134-aca4-0f2fe749e00d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3589 | T16182-YK09-P0GCF-130012 | 2017-08-28 | DHI-TRANSMIT-000602 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3cb413b4-bc1f-49cd-b3fe-7423514f414e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3590 | T16182-XN00-P0GNR-130107 | 2017-08-28 | DHI-TRANSMIT-000602 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4982868c-9f48-4182-9da6-149987e53307 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3591 | T16182-XN00-P0GCF-130008 | 2017-08-28 | DHI-TRANSMIT-000602 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dad70335-db35-4663-bc29-47ae2852ec09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3592 | T16182-XN00-P0GNR-130105 | 2017-08-28 | DHI-TRANSMIT-000602 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aac0f6c3-bfb9-4262-a087-a00734052e4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3593 | T16182-XH01-P0GCF-130013 | 2017-08-28 | DHI-WTRAN-000605 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38d1b456-40ee-4724-9c13-da70fd5458c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3594 | T16182-CV03-P0GCF-130055 | 2017-08-28 | DHI-WTRAN-000605 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4743399-bbac-45a3-887f-e84a2ea2a6f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3595 | T16182-YF02-P0GCF-130011 | 2017-08-28 | DHI-WTRAN-000606 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d9ae3af-ce00-4e86-a008-29fec1f3e909 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3596 | T16182-YL25-P0MBA-121024 | 2017-08-29 | DHI-WTRAN-000607 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3597 | T16182-YU02-P0MBA-121012 | 2017-08-29 | DHI-WTRAN-000607 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3598 | T16182-YD00-P0CYE-137941 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3599 | T16182-YU02-P0CYE-136842 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3600 | T16182-YU02-P0CYE-136942 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3601 | T16182-YU02-P0CYE-137242 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3602 | T16182-YU02-P0CYE-137642 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3603 | T16182-YU02-P0CYE-137742 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3604 | T16182-YU02-P0CYE-137942 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3605 | T16182-YU02-P0CYE-138742 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3606 | T16182-YU02-P0CYE-138842 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3607 | T16182-YU02-P0CYE-139942 | 2017-08-29 | DHI-WTRAN-000608 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3608 | T16182-XH01-P0SGA-136711 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3609 | T16182-XH01-P0SGE-136712 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3610 | T16182-XH01-P0SGK-136713 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3611 | T16182-XH01-P0SGA-136811 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3612 | T16182-XH01-P0SGE-136812 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3613 | T16182-XH01-P0SGK-136813 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3614 | T16182-YT10-P0SGE-136822 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3615 | T16182-YT10-P0SGK-136823 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3616 | T16182-XG02-P0SGA-136901 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3617 | T16182-XG02-P0SGE-136902 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3618 | T16182-XG02-P0SGK-136903 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3619 | T16182-YT10-P0SGE-136922 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3620 | T16182-YT10-P0SGK-136923 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3621 | T16182-XG02-P0SGC-137201 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3622 | T16182-XH01-P0SGC-137211 | 2017-08-29 | DHI-WTRAN-000609 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3623 | T16182-XG02-P0SGK-137603 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3624 | T16182-YT10-P0SGK-137623 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3625 | T16182-XG02-P0SGA-137701 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3626 | T16182-XG02-P0SGA-137801 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3627 | T16182-XG02-P0SGA-137901 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3628 | T16182-XG02-P0SGK-137902 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3629 | T16182-XH01-P0SGA-137911 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3630 | T16182-XH01-P0SGE-137913 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3631 | T16182-YT10-P0SGK-137922 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3632 | T16182-YD00-P0SGZ-137931 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3633 | T16182-XG02-P0SGC-138201 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3634 | T16182-XG02-P0SGK-138702 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3635 | T16182-YT10-P0SGK-138722 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3636 | T16182-XG02-P0SGK-138802 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3637 | T16182-YT10-P0SGK-138822 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3638 | T16182-XG02-P0SGA-138901 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3639 | T16182-XG02-P0SGA-139001 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3640 | T16182-XG02-P0SGC-139901 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3641 | T16182-YT10-P0SGC-139921 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3642 | T16182-XG02-P0SGK-139002 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3643 | T16182-XG02-P0SGK-139402 | 2017-08-29 | DHI-WTRAN-000609 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3644 | T16182-VK02-P0UGD-172543 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29b6455c-ccc2-426f-8c16-b5cf460e940c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3645 | T16182-VK02-P0UGF-172523 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e08d384-823e-47fd-bc43-c15b2873c7e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3646 | T16182-VK02-P0UGG-172563 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9cf50a3b-6230-489f-88d1-b6de34e43479 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3647 | T16182-VK02-P0ULC-172503 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=242fe6fc-4924-43dc-8535-4df59046f710 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3648 | T16182-XB02-P0UGD-172542 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de5107de-d18e-4e48-846a-f87b167d4bed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3649 | T16182-XB02-P0UGF-172522 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=479e3423-90d3-4d46-963e-73c31845c416 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3650 | T16182-XB02-P0UGG-172562 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beb74abd-c722-4fcd-8ffd-7284d7904724 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3651 | T16182-XB02-P0ULC-172502 | 2017-08-29 | DHI-TRANSMIT-000605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15403897-c9fa-431c-a9ef-7c4118f2564c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3652 | T16182-CA00-P0UYC-182901 | 2017-08-29 | DHI-TRANSMIT-000606 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bafd1e6-a1a8-4463-8571-7bce43eb982e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3653 | T16182-XG07-P0SAM-135002 | 2017-08-29 | DHI-WTRAN-000610 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd12837c-5cbe-4685-a9a5-bdf16827675d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3654 | T16182-XH02-P0SAM-135004 | 2017-08-29 | DHI-WTRAN-000610 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee4b9223-5db1-46f1-8ee4-8be6513ea264 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3655 | T16182-XW03-P0SAM-135001 | 2017-08-29 | DHI-WTRAN-000610 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4267a934-102d-4715-8d49-d2933f4d0f8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3656 | T16182-XW03-P0SAM-135003 | 2017-08-29 | DHI-WTRAN-000610 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d85e2da8-3bfa-4ffd-962f-6b2deb193763 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3657 | T16182-YU02-P0BT-151021 | 2017-08-29 | DHI-WTRAN-000611 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0fa3b231-6dcd-494f-9d7e-dc808e9ca0a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3658 | T16182-YU02-P0BT-151031 | 2017-08-29 | DHI-WTRAN-000611 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f7a42d1-4748-4803-8335-9c0677d5c668 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3659 | T16182-YT10-P0CYE-136743 | 2017-08-29 | DHI-WTRAN-000612 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=390de744-7001-4c00-b781-6e61dc330e37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3660 | T16182-YT10-P0CYE-137943 | 2017-08-29 | DHI-WTRAN-000612 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3365e349-17cf-44f9-ac09-3e26f2938a10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3661 | T16182-XG02-P0CYE-137944 | 2017-08-29 | DHI-WTRAN-000612 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=734d1411-85d6-4697-9a10-083bcf70a578 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3662 |  | 2017-08-29 | DHI-WTRAN-000612 |  |  |  | FALSE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3663 | T16182-YD00-P0GM-128501 | 2017-08-29 | DHI-WTRAN-000613 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24f91a31-28d6-4ab3-a09c-e028ca059bbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3664 | T16182-YT01-P0GM-128502 | 2017-08-29 | DHI-WTRAN-000613 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eca05dbc-b39c-4011-ab5c-cf2ff92dc7c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3665 | T16182-YD00-P0GM-128503 | 2017-08-29 | DHI-WTRAN-000613 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34a97747-ff2d-497a-9701-519538a24967 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3666 | T16182-YD00-P0CYE-139041 | 2017-08-29 | DHI-WTRAN-000614 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91a811e5-0042-4fb0-803b-d8538760577d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3667 | T16182-YU02-P0CYE-139042 | 2017-08-29 | DHI-WTRAN-000614 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6a89800-14d9-4fb9-839b-cbe363451976 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3668 | T16182-YT10-P0CYE-139043 | 2017-08-29 | DHI-WTRAN-000614 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9195f93-1983-4924-957e-eb5c240a8b80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3669 | T16182-XG02-P0CYE-139044 | 2017-08-29 | DHI-WTRAN-000614 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c009a36-edd1-445f-801b-e05fb7c04873 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3670 | T16182-YT10-P0SGK-139023 | 2017-08-29 | DHI-WTRAN-000615 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adbe499c-3e8e-4b1d-aea7-45ecb8a2f1a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3671 | T16182-YD00-P0SGZ-139031 | 2017-08-29 | DHI-WTRAN-000615 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7cd6fac-9120-49d5-a1eb-0ddff89d05b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3672 | T16182-YD00-P0SGZ-138431 | 2017-08-29 | DHI-WTRAN-000616 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5d01f4f-e793-434e-9b97-94feee03ed6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3673 | T16182-YU02-P0BT-151026 | 2017-08-29 | DHI-WTRAN-000617 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18802575-f0fa-42dc-bbe3-a9efea2a2094 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3674 | T16182-XB00-P0GM-128506 | 2017-08-29 | DHI-WTRAN-000618 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e983914f-2996-403d-a62d-1856d92e1189 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3675 | T16182-VK02-P8UTH-172008 | 2017-08-29 | DHI-TRANSMIT-000607 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3fd5ba5-27ce-4d47-ae42-342eb1c97fec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3676 | T16182-XJ00-P0LB-122028 | 2017-08-29 | DHI-WTRAN-000619 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05066266-7e52-446f-9a0d-ea1a2b0e5a61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3677 | T16182-YT01-P0LB-122103 | 2017-08-29 | DHI-TRANSMIT-000609 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bf56534-5e88-43ab-a87d-d70661c5287b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3678 | T16182-UE00-P0LB-122008 | 2017-08-29 | DHI-TRANSMIT-000609 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=197fc401-615c-400c-ab96-07752a1202c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3679 | T16182-CN00-P0ZEN-110705 | 2017-08-29 | DHI-WTRAN-000620 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51fc07bf-f3b4-4308-9fa5-0043af50cdf3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3680 | T16182-XG02-P0SGA-139401 | 2017-08-29 | DHI-WTRAN-000621 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e76f4b5-fdc9-42e3-8d2f-646c83c4dec2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3681 | T16182-XH01-P0SGA-139411 | 2017-08-29 | DHI-WTRAN-000621 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b88e3e6-1246-44fc-bc99-e926390760ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3682 | T16182-YD00-P0SGZ-139431 | 2017-08-29 | DHI-WTRAN-000621 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccdb1674-5da2-469c-a67d-8256ac57d326 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3683 | T16182-XG02-P0CYE-139444 | 2017-08-29 | DHI-WTRAN-000622 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dad34352-7a3b-4bb4-bd8e-e58f2700f91c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3684 | T16182-YD00-P0CYE-139441 | 2017-08-29 | DHI-WTRAN-000622 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04f63556-f427-4c33-89dd-848f5c691584 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3685 | T16182-YT10-P0CYE-139443 | 2017-08-29 | DHI-WTRAN-000622 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a4254cf-29fe-4aa7-9633-10dd635783c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3686 | T16182-YU02-P0CYE-139442 | 2017-08-29 | DHI-WTRAN-000622 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bb59dea-63ce-4753-9f28-be4dce4e43ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3687 | T16182-XK00-P0PCA-126508 | 2017-08-30 | DHI-WTRAN-000623 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2675284a-0622-42c9-90db-5b9c09accdaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3688 | T16182-YD00-P0LAC-126007 | 2017-08-30 | DHI-WTRAN-000624 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=102ed83a-2d97-422f-8c4d-6fc13b8458bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3689 | T16182-YD00-P0LAC-126057 | 2017-08-30 | DHI-WTRAN-000624 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8994c4ca-23d4-4319-959d-2d60e825a461 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3690 | T16182-XH01-P0PCA-126517 | 2017-08-30 | DHI-WTRAN-000625 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dec650c1-a5e3-41bc-ac5c-3accfb041f48 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3691 | T16182-YD00-P8ZEN-125750 | 2017-08-30 | DHI-WTRAN-000626 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4aae8300-7a65-4eca-833e-d84c010c17f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3692 | T16182-YL16-P8ZEN-125760 | 2017-08-30 | DHI-WTRAN-000626 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9da2f554-69cb-420b-a1aa-be481f649788 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3693 | T16182-YB03-P8ZEN-125761 | 2017-08-30 | DHI-WTRAN-000626 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43543cfd-2b3f-4a0b-a0d8-a80c2b3d0691 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3694 | T16182-YQ03-P8ZEN-125769 | 2017-08-30 | DHI-WTRAN-000626 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f7c450b-09a5-446a-9df5-e577521b3198 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3695 | T16182-YD00-P8ZEN-125728 | 2017-08-30 | DHI-WTRAN-000627 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bead23ff-09ec-4f0e-9ffa-e6fcc5c80bea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3696 | T16182-YL16-P8ZEN-125731 | 2017-08-30 | DHI-WTRAN-000627 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc08546e-3e15-40cf-90b3-128c9cbbeb8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3697 | T16182-YB03-P8ZEN-125732 | 2017-08-30 | DHI-WTRAN-000627 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28708700-fad2-4014-bc45-0b8903d48d8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3698 | T16182-CC08-P8QHB-125151 | 2017-08-30 | DHI-WTRAN-000628 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=373f464e-d232-416d-9933-cc0d9195078b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3699 | T16182-CC08-P8ZEN-125614 | 2017-08-30 | DHI-WTRAN-000628 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd004cb1-e715-4203-b37b-727802dd279c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3700 | T16182-YD04-P0ZEN-152006 | 2017-08-30 | DHI-WTRAN-000629 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c34188ac-b750-4f13-abd4-5102bfe53f37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3701 | T16182-DE00-P0ZEN-152002 | 2017-08-30 | DHI-TRANSMIT-000613 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c462b26-16f1-4c07-a1ea-fb701f2cb780 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3702 | T16182-YE00-P0ZEN-152707 | 2017-08-30 | DHI-TRANSMIT-000613 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=564d2d54-c229-43e9-9c42-dffef21818ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3703 | T16182-YU03-P0BT-151061 | 2017-08-30 | DHI-WTRAN-000630 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12377797-9456-4e9d-8719-b71404fcbdb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3704 | T16182-YU03-P0BT-151066 | 2017-08-30 | DHI-WTRAN-000630 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1da69390-d49a-49cc-a6fd-6189839b38ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3705 | T16182-YU03-P0BT-151071 | 2017-08-30 | DHI-WTRAN-000630 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d86635e2-c53b-4188-b570-bed15d284930 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3706 | T16182-YQ08-P0CY-154038 | 2017-08-30 | DHI-WTRAN-000631 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aae02d8e-299a-46d3-8a52-dc37894e20e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3707 | T16182-YQ08-P0CY-154046 | 2017-08-30 | DHI-TRANSMIT-000614 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed848b1c-f54c-4a6f-91a4-782f9ddab79b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3708 | T16182-YM01-P0LCB-127039 | 2017-08-30 | DHI-WTRAN-000632 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=582f60b7-ec5f-4998-a28b-e83f9cdb9a9c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3709 | T16182-XG02-P0LCB-127002 | 2017-08-30 | DHI-WTRAN-000633 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd48c867-ce3b-4cc5-8107-1e7b295aa026 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3710 | T16182-YK09-P0LCB-127004 | 2017-08-30 | DHI-WTRAN-000633 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d5be08a-8183-4c3b-9f34-b14519c5c80e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3711 | T16182-YL22-P0LCB-127018 | 2017-08-30 | DHI-WTRAN-000633 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1ce42b8-fde1-458f-a0f6-7d1b810ee3e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3712 | T16182-XG02-P0LCB-127032 | 2017-08-30 | DHI-WTRAN-000633 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ebd7c83-e6a5-4044-9005-384265d63077 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3713 | T16182-YT01-P0LCB-127037 | 2017-08-30 | DHI-WTRAN-000633 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79b9dffa-bb35-42fb-9733-a34bed00bffc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3714 | T16182-YL22-P0LCB-127042 | 2017-08-30 | DHI-WTRAN-000633 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5440ff55-88d7-4dce-91ab-73d1859c9904 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3715 | T16182-YL00-P0LD-130209 | 2017-08-30 | DHI-WTRAN-000634 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96971a04-56ee-47e6-b5b2-c9f835dde356 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3716 | T16182-YT01-P0LD-130214 | 2017-08-30 | DHI-WTRAN-000635 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=385fcfc9-e42f-4549-916e-69667c97e21b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3717 | T16182-UE00-P0LB-122009 | 2017-08-30 | DHI-TRANSMIT-000615 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a30e6933-7fec-45dd-bc25-a7470b816234 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3718 | T16182-UE00-P0LB-122010 | 2017-08-30 | DHI-TRANSMIT-000615 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2122a606-1dcc-4f22-8023-7ac4a1f9c16a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3719 | T16182-YK08-P0PGB-420010 | 2017-08-30 | DHI-WTRAN-000636 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c84f18a-3fe0-40da-addf-69d545d86c56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3720 | T16182-YK08-P0PGB-420020 | 2017-08-30 | DHI-WTRAN-000636 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=090276a7-3209-47a6-8d5c-462ae9008610 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3721 | T16182-YD00-P0PCA-126503 | 2017-08-30 | DHI-WTRAN-000637 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1e9b433-12d8-4eb1-8bec-a03ac9603104 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3722 | T16182-YL01-P0CRN-161117 | 2017-08-30 | DHI-WTRAN-000638 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=873bb093-f7f9-4797-9ae8-2b9c57ca28ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3723 | T16182-YF00-P0CBA-161202 | 2017-08-30 | DHI-TRANSMIT-000616 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4975114d-45af-4fa2-b30d-17a9a49e0b02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3724 | T16182-YF00-P0CBA-161220 | 2017-08-30 | DHI-TRANSMIT-000616 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef6ee989-c222-494b-8046-6381cfe97c2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3725 | T16182-YF00-P0CGA-161310 | 2017-08-30 | DHI-TRANSMIT-000616 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f9d6aa6-f68c-4e4a-81a9-f83cdec153b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3726 | T16182-YF00-P0CGA-161311 | 2017-08-30 | DHI-TRANSMIT-000616 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fa7a575-1cfb-4036-9cb4-b9acd8bad59e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3727 | T16182-CC05-P8QHB-125162 | 2017-08-31 | DHI-WTRAN-000639 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3728 | T16182-YF00-P0CBA-161210 | 2017-08-31 | DHI-WTRAN-000640 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3729 | T16182-YF00-P0CGA-161320 | 2017-08-31 | DHI-WTRAN-000640 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3730 | T16182-YQ08-P0CY-154049 | 2017-08-31 | DHI-WTRAN-000641 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06602dff-1dd8-4eec-8640-88bab3b53bbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3731 | T16182-CC05-P8QHB-125161 | 2017-08-31 | DHI-WTRAN-000642 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bf00789-111d-4245-b4bf-de2645dfabbd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3732 | T16182-XT00-P8QHB-125152 | 2017-08-31 | DHI-WTRAN-000643 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8eb67742-3939-4e0c-8a52-62008210c685 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3733 | T16182-XT00-P8QHB-125153 | 2017-08-31 | DHI-WTRAN-000643 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2314375-85f2-4326-b7d9-deb6f9d70273 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3734 | T16182-YD00-P0BF-150939 | 2017-08-31 | DHI-WTRAN-000644 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f32045c1-f678-45d7-8dfb-3ded2b086f51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3735 | T16182-YD00-P0BF-150940 | 2017-08-31 | DHI-WTRAN-000644 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=397e778a-1835-4d0b-84fa-1e67b597cd6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3736 | T16182-YT01-P0BF-150902 | 2017-08-31 | DHI-WTRAN-000644 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55d92eae-bb56-4b3f-907a-3692bfb2f541 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3737 | T16182-YT01-P0BF-150903 | 2017-08-31 | DHI-WTRAN-000644 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1dfee35-3a04-4143-9ad1-9f205b13f139 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3738 | T16182-YF00-P0CBA-161211 | 2017-08-31 | DHI-WTRAN-000645 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49f8d408-db61-41bf-8854-6aa15d48f83f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3739 | T16182-YF00-P0CBA-161203 | 2017-08-31 | DHI-TRANSMIT-000619 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2f850bf-bb86-4a9f-9aee-8aac911d85e6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3740 | T16182-YF00-P0CBA-161204 | 2017-08-31 | DHI-TRANSMIT-000619 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f86acbd-2981-4c43-b3d3-dfacac1dea40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3741 | T16182-YF00-P0CBA-161205 | 2017-08-31 | DHI-TRANSMIT-000619 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfea9087-d0f4-4102-8839-fa8a390f0a51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3742 | T16182-YF00-P0CBA-161206 | 2017-08-31 | DHI-TRANSMIT-000619 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b8474ab-425b-481f-8a2b-448d1a6cc7c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3743 | T16182-YF00-P0CBA-161207 | 2017-08-31 | DHI-TRANSMIT-000619 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6967e059-a975-4a8f-a29d-42c9a28a970f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3744 | T16182-YF00-P0CBA-161212 | 2017-08-31 | DHI-TRANSMIT-000619 | IFC | 0 | DR | TRUE | FALSE | 2017-08-31_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0715f29-37ac-44d8-87dc-54ec43004b69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3745 | T16182-YF00-P0CBA-161213 | 2017-08-31 | DHI-TRANSMIT-000619 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f15dcf5-078f-45e9-9c5f-68740e2bde38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3746 | T16182-YF00-P0CGA-161303 | 2017-08-31 | DHI-TRANSMIT-000620 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41c188d4-7333-43a1-9592-c8108a3538de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3747 | T16182-YF00-P0CGA-161304 | 2017-08-31 | DHI-TRANSMIT-000620 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7776da60-49a7-4e0c-93ae-dfd7347d1a2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3748 | T16182-YF00-P0CGA-161305 | 2017-08-31 | DHI-TRANSMIT-000620 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=432d19ae-12bc-442d-ac0e-5c15ce33649b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3749 | T16182-YF00-P0CGA-161306 | 2017-08-31 | DHI-TRANSMIT-000620 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14177e5e-3317-430d-8f6e-05800e7cc9e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3750 | T16182-YF00-P0CGA-161307 | 2017-08-31 | DHI-TRANSMIT-000620 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16532d42-e13d-4008-a329-120b3fcd5516 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3751 | T16182-YF00-P0CGA-161312 | 2017-08-31 | DHI-TRANSMIT-000620 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b456f834-46c3-4df9-9928-95b95540a7a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3752 | T16182-YF00-P0CGA-161313 | 2017-08-31 | DHI-TRANSMIT-000620 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=561b4f43-a512-495a-8a3a-2f088d61f021 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3753 | T16182-CA03-P0UMY-185175 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d195669-21a6-4110-a4e3-db70c06a1a4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3754 | T16182-CA03-P0UMY-185176 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6eab0372-bd58-4274-bf2a-dfa340c051c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3755 | T16182-CA03-P0UMY-185177 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b6c51b4-fe0a-4b37-8259-e0649cf8ec9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3756 | T16182-CA06-P0UMY-185192 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df9451dc-b04c-4599-8d6a-3568d8323968 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3757 | T16182-CA03-P0UMY-185169 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1233833b-e8d0-458f-893d-4b21ec134265 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3758 | T16182-CA03-P0UMY-185170 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccbc8ca8-9761-49c9-841a-48676001c0ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3759 | T16182-CA03-P0UMY-185171 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa5dc113-2d0f-403a-ad53-cbc3ddae6d4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3760 | T16182-CA03-P0UMY-185172 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b251482c-b397-45d1-b8eb-6d241b1903cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3761 | T16182-CA03-P0UMY-185173 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77ac876d-9c42-4286-b1ab-f23e4db8af8a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3762 | T16182-CA03-P0UMY-185174 | 2017-08-31 | DHI-WTRAN-000646 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86212751-9829-467c-8586-8c6f2bd6887a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3763 | T16182-YT01-P0GCF-130014 | 2017-08-31 | DHI-TRANSMIT-000621 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83650e8e-0513-4840-8cad-431fe48ef78a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3764 | T16182-YT01-P0GNR-130108 | 2017-08-31 | DHI-TRANSMIT-000621 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8eb137de-fcac-4433-804d-f4856f091588 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3765 | T16182-CA00-P6BAT-181811 | 2017-08-31 | DHI-WTRAN-000647 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc7d17c4-09ad-4b8c-b203-eb6bdf03a27d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3766 | T16182-CA03-P6BAT-181812 | 2017-08-31 | DHI-WTRAN-000647 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48a762b8-b89e-4f03-b27d-60deadca8fe5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3767 | T16182-CA03-P6BAT-181813 | 2017-08-31 | DHI-WTRAN-000647 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e56f4ac4-8c72-4f58-9262-748a887d055a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3768 | T16182-CA06-P0BAT-181800 | 2017-08-31 | DHI-WTRAN-000647 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beecc0fb-cde8-488d-9718-f1ac266e0cfd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3769 | T16182-YF00-P0BB-150402 | 2017-09-01 | DHI-TRANSMIT-000622 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a667a783-2404-4bc9-bd49-59d85a05c3b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3770 | T16182-XW01-P0MBA-121006 | 2017-09-01 | DHI-WTRAN-000648 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3771 | T16182-CA03-P0UMA-180467 | 2017-09-01 | DHI-TRANSMIT-000623 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31f0e1c6-3be7-41ca-9893-a7f8a5034e0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3772 | T16182-CC05-P0ZEN-180001 | 2017-09-01 | DHI-WTRAN-000649 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3773 | T16182-CC05-P0ZEN-180038 | 2017-09-01 | DHI-WTRAN-000649 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3774 | T16182-CC05-P0ZEN-180002 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f64b3829-219e-45fb-9772-23a1cc9457b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3775 | T16182-CC05-P0ZEN-180008 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b315276-2717-4238-b120-a54390e800ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3776 | T16182-CC05-P0ZEN-180019 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27c97083-9b09-40e2-a846-8ede963870b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3777 | T16182-CC05-P0ZEN-180030 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=211d8cac-609e-4ce2-bd65-123bbbfe7b18 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3778 | T16182-CC05-P0ZEN-180033 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97c86866-77b6-464b-8316-c3ab732c2ac5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3779 | T16182-CC05-P0ZEN-180035 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b28e7a94-98c9-497d-9acd-bf3a6bef1ca8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3780 | T16182-CC05-P0ZEN-180041 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a4d47fd-4695-433a-ba74-c09603295351 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3781 | T16182-CC05-P0ZEN-180042 | 2017-09-01 | DHI-WTRAN-000650 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e02a424-9237-4d79-8116-ce427299d4d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3782 | T16182-XB02-P0UHA-171815 | 2017-09-01 | DHI-TRANSMIT-000626 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0b46f8a-917a-4026-8e29-0a98ce8427b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3783 | T16182-XB02-P0UHA-171816 | 2017-09-01 | DHI-TRANSMIT-000626 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdfe1dd6-7578-4cd5-9c1b-791f09e50490 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3784 | T16182-VE04-P0ULX-172581 | 2017-09-01 | DHI-TRANSMIT-000627 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3852ef9-b6fa-416e-b72c-b6ad01ee2424 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3785 | T16182-XB02-P0ULX-172582 | 2017-09-01 | DHI-TRANSMIT-000627 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b1f0500-6ed6-421a-bcf8-3b3cc608a598 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3786 | T16182-XB02-P0ULX-172583 | 2017-09-01 | DHI-TRANSMIT-000627 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7dccf9de-58c0-4354-b64a-8a251cdc6393 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3787 | T16182-XB02-P0ULX-172584 | 2017-09-01 | DHI-TRANSMIT-000627 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c489e614-6d27-47c9-b7e6-02a37a4e8681 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3788 | T16182-XB02-P0ULX-172585 | 2017-09-01 | DHI-TRANSMIT-000627 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2603af8-1db5-4feb-af94-25a1dbb9b03c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3789 | T16182-XG02-P0PCA-126502 | 2017-09-01 | DHI-WTRAN-000651 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=266ad083-e3ae-47b7-bae6-8389252bb135 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3790 | T16182-BP00-P0EKG-140015 | 2017-09-01 | DHI-WTRAN-000652 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59641d0e-1789-41fb-9a4d-72f61722bde4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3791 | T16182-YF00-P0CBA-161209 | 2017-09-01 | DHI-TRANSMIT-000628 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0b4b209-adc0-42b8-931d-f727a4c778d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3792 | T16182-YF00-P0CGA-161309 | 2017-09-01 | DHI-TRANSMIT-000628 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9748f823-250c-469a-84cb-d4175f865229 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3793 | T16182-YK08-P8QHL-125403 | 2017-09-01 | DHI-WTRAN-000653 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c59972e-64d1-4aa5-b166-9202c9bb0ce7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3794 | T16182-XW01-P0GM-128507 | 2017-09-01 | DHI-WTRAN-000654 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bbf27d7-57b8-4d1b-82bd-d7c851b4fd05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3795 | T16182-XW01-P0SCA-127503 | 2017-09-01 | DHI-TRANSMIT-000629 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38d7a673-08e3-4287-a150-e6bddacb79ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3796 | T16182-XS00-P0PCA-126501 | 2017-09-01 | DHI-WTRAN-000655 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebae2fed-b61e-4c59-a6c0-7180c56756dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3797 | T16182-XS00-P0GM-120022 | 2017-09-01 | DHI-WTRAN-000656 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a43bce16-1386-458e-b407-61eb58965d57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3798 | T16182-XS00-P0GM-120023 | 2017-09-01 | DHI-WTRAN-000656 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21948e19-b836-40cf-89a3-414b9aab12cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3799 | T16182-YF00-P0EKG-124016 | 2017-09-01 | DHI-WTRAN-000657 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae361ab0-8231-44ef-9176-5c9f1c248d9a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3800 | T16182-YV02-P0EKG-124022 | 2017-09-01 | DHI-WTRAN-000658 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1bd658f-4810-4e7f-abf1-9ab149ded69a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3801 | T16182-XG07-P0EKG-124003 | 2017-09-01 | DHI-TRANSMIT-000630 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=439831bf-570e-4725-876e-758d3bf3189e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3802 | T16182-XW03-P0EKG-120021 | 2017-09-01 | DHI-TRANSMIT-000630 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7cad195-7d6d-42ad-9b0f-b80d245c395b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3803 | T16182-YD00-P0GHC-129001 | 2017-09-01 | DHI-TRANSMIT-000631 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50cde5a1-3375-4c7d-b03c-7ac6652d1c84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3804 | T16182-YD00-P0GHC-129031 | 2017-09-01 | DHI-TRANSMIT-000631 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f3e9f95-a5f6-4f0c-8bcd-bd1517d115e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3805 | T16182-XS00-P0QJA-110500 | 2017-09-01 | DHI-WTRAN-000659 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fa5d6e7-8f98-4a16-bb11-0efd9820002f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3806 | T16182-YK08-P0QJA-110501 | 2017-09-01 | DHI-WTRAN-000659 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=168a0ebe-935f-4790-b138-60ea1e65bdd0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3807 | T16182-YD00-P0QJA-110502 | 2017-09-01 | DHI-WTRAN-000659 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18b442f1-05f4-4a1d-a01e-dc8821657fc6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3808 | T16182-YT01-P0QJA-110503 | 2017-09-01 | DHI-WTRAN-000659 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=feca16e2-cf0a-47b4-b43a-16e3e7aff7be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3809 | T16182-YK08-P0PCA-126514 | 2017-09-01 | DHI-WTRAN-000660 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2714b937-1e1b-44d3-8492-e2cf72802a5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3810 | T16182-YD00-P0LCB-127001 | 2017-09-01 | DHI-WTRAN-000661 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2fd379e-8914-458c-86b0-979ea2aaf4f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3811 | T16182-YD00-P0LCB-127009 | 2017-09-01 | DHI-WTRAN-000661 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d39fa808-b19e-4526-a112-76875b80abc8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3812 | T16182-YT01-P0LCB-127007 | 2017-09-01 | DHI-WTRAN-000661 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6ca4fca-bcf2-49a0-ac66-630e9fedd331 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3813 | T16182-YD00-P0LCB-127031 | 2017-09-01 | DHI-TRANSMIT-000632 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=071d5a95-0d69-4bf4-87e0-2ebc221c6455 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3814 | T16182-YD00-P0LCB-127038 | 2017-09-01 | DHI-TRANSMIT-000632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79f5ccd9-a1f0-4336-912a-02a96ca68110 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3815 | T16182-YK09-P0LCB-127034 | 2017-09-01 | DHI-TRANSMIT-000632 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb747673-6232-4e10-9c5a-0824d5b4b21b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3816 | T16182-YT01-P0LCB-127003 | 2017-09-01 | DHI-TRANSMIT-000632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf19be34-7b7d-46e6-b183-4ad373d209e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3817 | T16182-DE00-P0ZEN-152202 | 2017-09-01 | DHI-WTRAN-000662 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4cc1558-e491-4aba-a49c-aee7aeb65ff8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3818 | T16182-XA00-P8QHL-125402 | 2017-09-04 | DHI-WTRAN-000663 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c61f6c5-c94e-4d11-bbbf-18f0c1a6b453 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3819 | T16182-XA00-P8QHL-125401 | 2017-09-04 | DHI-WTRAN-000663 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8c87bc4-e449-4881-a6fa-bdab6fefa75a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3820 | T16182-XJ00-P0MAG-123019 | 2017-09-04 | DHI-WTRAN-000664 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40d5a683-bbbd-4b04-9fbc-e4511788ef3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3821 | T16182-CQ02-P0GHC-129016 | 2017-09-04 | DHI-WTRAN-000665 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c3f9c75-109b-4c81-854c-7a188274fe67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3822 | T16182-CQ02-P0GHC-129039 | 2017-09-04 | DHI-WTRAN-000665 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5404262e-9815-42d9-a1b3-5d559259b92f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3823 | T16182-XG01-P0LB-122021 | 2017-09-04 | DHI-WTRAN-000666 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec657ce8-7ab8-42a7-91fa-bccf8c7a01ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3824 | T16182-YD00-P0LB-122044 | 2017-09-04 | DHI-WTRAN-000666 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=928ec458-5771-4355-a712-21e219a6ec0f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3825 | T16182-YR01-P0LB-122082 | 2017-09-04 | DHI-WTRAN-000666 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e544aff-026a-48fd-bc0e-8b92ae3f0aa4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3826 | T16182-YL08-P0LB-122083 | 2017-09-04 | DHI-WTRAN-000667 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=591f441d-3534-4479-b0f6-b7ff58f4dd97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3827 | T16182-YE00-P0ZEN-152709 | 2017-09-04 | DHI-WTRAN-000668 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af2294e6-8259-4e22-b00e-1c2c1bb192c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3828 | T16182-YE00-P0ZEN-152715 | 2017-09-04 | DHI-WTRAN-000668 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c5dc1af-578e-4489-8466-96b32c60d960 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3829 | T16182-CC08-P8QHA-125300 | 2017-09-04 | DHI-WTRAN-000669 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3830 | T16182-CC08-P8ZEN-125615 | 2017-09-04 | DHI-WTRAN-000669 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3831 | T16182-CC08-P8ZEN-125616 | 2017-09-04 | DHI-WTRAN-000669 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3832 | T16182-CC08-P8ZEN-125618 | 2017-09-04 | DHI-WTRAN-000669 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3833 | T16182-CC08-P8ZEN-125619 | 2017-09-04 | DHI-WTRAN-000669 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3834 | T16182-CN00-P0ZEN-110703 | 2017-09-05 | DHI-TRANSMIT-000633 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=101825c0-43ff-40a9-b46d-b31cbd04c77f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3835 | T16182-CN00-P0ZEN-110704 | 2017-09-05 | DHI-TRANSMIT-000633 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe1f173b-0a4e-49f4-9329-52048552081a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3836 | T16182-XN00-P0EKG-124023 | 2017-09-05 | DHI-TRANSMIT-000634 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8515c86e-25fd-41f3-b382-4e76b41a7d39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3837 | T16182-YD00-P0EKG-124004 | 2017-09-05 | DHI-TRANSMIT-000634 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aad20c9b-57e4-4a7f-8818-4b45ac7630b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3838 | T16182-YD00-P0EKG-124011 | 2017-09-05 | DHI-TRANSMIT-000634 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a4a3c41-81d6-4ba2-8f93-bea6dec2e131 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3839 | T16182-XG02-P0SCA-127502 | 2017-09-05 | DHI-TRANSMIT-000635 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=100fa10d-cca4-474c-bc68-9202edf03ce2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3840 | T16182-XG02-P0GM-120008 | 2017-09-05 | DHI-TRANSMIT-000636 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=518da613-8c67-4c58-969f-a0635f4ac9ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3841 | T16182-DA01-P0ZEN-020001 | 2017-09-05 | DHI-WTRAN-000670 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2e68a72-fa77-441e-91bf-97a6443a8662 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3842 | T16182-DA01-P0ZEN-020002 | 2017-09-05 | DHI-WTRAN-000670 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b2b08fe-e977-464b-b560-0823e29b9adf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3843 | T16182-YD00-P0PGB-110404 | 2017-09-05 | DHI-WTRAN-000671 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=209ae393-b48c-47d0-84d5-a88f6d1cc521 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3844 | T16182-YD00-P0PGB-110405 | 2017-09-05 | DHI-WTRAN-000671 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc6a15d3-9db7-4c9b-b211-6d87c94584b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3845 | T16182-YT01-P0PGB-110407 | 2017-09-05 | DHI-WTRAN-000671 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c03c89e7-555c-45a5-8a25-de007952ce2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3846 | T16182-CA00-P0ULD-183908 | 2017-09-05 | DHI-TRANSMIT-000637 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3e1e439-b7f1-4658-bdf6-61d361f2d0a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3847 | T16182-CA00-P0ULD-183910 | 2017-09-05 | DHI-TRANSMIT-000637 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e767ec05-dd63-4019-a12b-d5f26ae3b46a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3848 | T16182-CA03-P0ULD-183963 | 2017-09-05 | DHI-TRANSMIT-000637 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ba84d08-2ea3-45a4-a7a5-919b170b8249 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3849 | T16182-CA03-P0ULD-183964 | 2017-09-05 | DHI-TRANSMIT-000637 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec0a5e7a-1387-450e-89e2-05e5a54bbcfa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3850 | T16182-CA01-P0UYP-183251 | 2017-09-05 | DHI-TRANSMIT-000638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=644a933e-2abb-4de6-aa0a-fca02eb2e8ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3851 | T16182-CA01-P0UYP-183252 | 2017-09-05 | DHI-TRANSMIT-000638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beeec2f6-4b6e-4bc9-a114-5e80909eb0a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3852 | T16182-CA01-P0UYP-183253 | 2017-09-05 | DHI-TRANSMIT-000638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b99a5d7c-f6e8-4658-a963-450a3010d313 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3853 | T16182-CA01-P0UYP-183254 | 2017-09-05 | DHI-TRANSMIT-000638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27ed812c-5133-4810-b7e9-d212d3349ef4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3854 | T16182-CA01-P0UYP-183255 | 2017-09-05 | DHI-TRANSMIT-000638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74829392-ddf7-44a7-b3a5-c61580f24d04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3855 | T16182-CA02-P0UYP-183256 | 2017-09-05 | DHI-TRANSMIT-000638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e25c3c41-57a9-41ce-9c6b-e99e3eef02d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3856 | T16182-CA02-P0UYP-183257 | 2017-09-05 | DHI-TRANSMIT-000638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76ab1fc8-c338-4a0f-ba6c-3ce11b730272 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3857 | T16182-UC02-P8QHA-125304 | 2017-09-06 | DHI-WTRAN-000672 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4f62be9-45fe-4548-9d53-d1a8a497587a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3858 | T16182-CC02-P8QHB-125164 | 2017-09-06 | DHI-TRANSMIT-000640 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e7ea237-b4be-4de1-b97d-8fea395c474b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3859 | T16182-CC05-P8QHB-125162 | 2017-09-06 | DHI-TRANSMIT-000640 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93665765-eaa9-4871-b253-4ce3fe09cedd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3860 | T16182-YF00-P0SAY-163405 | 2017-09-06 | DHI-WTRAN-000673 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f1bf127-dad9-400a-8388-ea5c74caa855 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3861 | T16182-XJ00-P8ZEN-125520 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e0d6203-81e3-4578-80d9-0963be1b1aef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3862 | T16182-XJ00-P8ZEN-125521 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e295b5a8-0dd8-40f8-8b81-c3c9a69a6136 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3863 | T16182-XJ00-P8ZEN-125522 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d779033-8663-4926-b219-0d9e6b8c870b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3864 | T16182-XJ00-P8ZEN-125523 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36ab900b-0f06-4548-a127-24614fb52444 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3865 | T16182-XJ00-P8ZEN-125524 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24e11070-24b2-4958-8fad-bea688047862 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3866 | T16182-XJ00-P8ZEN-125525 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1bc77f78-5c67-4a17-9b57-eafd33c96d99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3867 | T16182-XJ00-P8ZEN-125526 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b42ae07-8c6a-4a69-b5c3-c8f743427a03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3868 | T16182-XJ00-P8ZEN-125527 | 2017-09-06 | DHI-WTRAN-000674 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6a4d277-c914-4372-9a0d-6390d948382d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3869 | T16182-CA03-P1BAT-180512 | 2017-09-06 | DHI-TRANSMIT-000641 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bbfb190-96f5-4f36-b9f4-6ffce848c8ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3870 | T16182-CA03-P1BAT-180513 | 2017-09-06 | DHI-TRANSMIT-000641 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2db7ed95-4ed7-4691-a0a5-03a2e874fd46 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3871 | T16182-CV03-P8ZEN-125611 | 2017-09-06 | DHI-TRANSMIT-000642 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbb97225-67f8-4546-a679-01976cc1cbaa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3872 | T16182-XG02-P0SGE-139502 | 2017-09-06 | DHI-WTRAN-000675 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d2ae97b-529d-4996-b69f-cd8e90dcdd40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3873 | T16182-XH01-P0SGE-139512 | 2017-09-06 | DHI-WTRAN-000675 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=260d3292-cdff-4ffa-bab8-086cafa14a3a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3874 | T16182-YT10-P0SGE-139522 | 2017-09-06 | DHI-WTRAN-000675 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=771bdbfc-be71-4025-adb0-c9ba9f2634fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3875 | T16182-YD00-P0SGZ-139531 | 2017-09-06 | DHI-WTRAN-000675 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea786415-6f99-496e-bee5-f01f0b54693c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3876 | T16182-YD00-P0CYE-139641 | 2017-09-06 | DHI-WTRAN-000676 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7ed379c-2118-484b-af0e-1bc7b8601665 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3877 | T16182-YU02-P0CYE-139642 | 2017-09-06 | DHI-WTRAN-000676 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=795cd676-fc54-4c5f-96cc-54e2ed7f9879 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3878 | T16182-XG02-P0SGK-139602 | 2017-09-06 | DHI-WTRAN-000677 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec52d1bb-e900-422c-953e-30a7ada698a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3879 | T16182-XG02-P0SGE-139603 | 2017-09-06 | DHI-WTRAN-000677 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ded46ba-88f6-48cd-83f9-dfd140318e2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3880 | T16182-XH01-P0SGK-139612 | 2017-09-06 | DHI-WTRAN-000677 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29e55450-d733-4612-9878-60a9d46c02de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3881 | T16182-XH01-P0SGE-139613 | 2017-09-06 | DHI-WTRAN-000677 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6daed9d7-50d2-4a8e-b685-61a3162bf28e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3882 | T16182-YT10-P0SGK-139622 | 2017-09-06 | DHI-WTRAN-000677 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e321cff5-ebe6-4d95-bb04-898c2807697b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3883 | T16182-YT10-P0SGE-139623 | 2017-09-06 | DHI-WTRAN-000677 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f2bec07-8e5d-4989-b84d-d0c7316e2e29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3884 | T16182-DF04-P0LB-122003 | 2017-09-06 | DHI-WTRAN-000678 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cbdc797-3cae-44ea-ab7d-9331c1160253 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3885 | T16182-UE00-P0LB-122013 | 2017-09-06 | DHI-WTRAN-000678 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdb6c367-df4b-4442-a267-1308d0ff5b06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3886 | T16182-UE00-P0LB-122014 | 2017-09-06 | DHI-WTRAN-000678 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a1791c1-d04e-4964-8888-90f7850896fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3887 | T16182-YK10-P0EKG-124006 | 2017-09-06 | DHI-TRANSMIT-000643 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c878b87e-7c09-4cb9-ab5b-75c924d1e5d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3888 | T16182-YK10-P0EKG-124007 | 2017-09-06 | DHI-TRANSMIT-000643 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b430d572-74a1-42b1-8755-85bdc4226e10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3889 | T16182-YK10-P0EKG-124008 | 2017-09-06 | DHI-TRANSMIT-000643 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d6173ab-536c-44d2-8b90-d985d6f73ddd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3890 | T16182-CA01-P0ULD-183951 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c1caabc-3183-4f5e-a464-505b5aad8824 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3891 | T16182-CA01-P0ULD-183952 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfdc6369-8a5c-44a5-af3b-9d8057af9ba7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3892 | T16182-CA01-P0ULD-183953 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c4eec44-9de5-4b23-95c5-123950272921 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3893 | T16182-CA01-P0ULD-183954 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d9206b4-ae44-41d2-893f-882a50cbc841 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3894 | T16182-CA02-P0ULD-183955 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7e614a3-bf09-4760-aaf7-69def04b20ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3895 | T16182-CA02-P0ULD-183956 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eac44307-28af-4ca2-b4af-ae7226224480 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3896 | T16182-CA02-P0ULD-183957 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22caaba7-7017-4674-9351-73fee2190dee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3897 | T16182-CA02-P0ULD-183961 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=973a3f81-a728-4059-bac6-ae25289fcd1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3898 | T16182-CA03-P0ULD-183962 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=641cd7cf-048d-49b2-98bc-5904b48199b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3899 | T16182-CA03-P0ULD-183965 | 2017-09-06 | DHI-TRANSMIT-000644 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2027275-7866-4ee6-8935-85ade617cf04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3900 | T16182-CA03-P0UMY-185151 | 2017-09-06 | DHI-TRANSMIT-000645 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59c1cf10-24f5-4d31-9053-06e791e4f4d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3901 | T16182-CA03-P0UMY-185152 | 2017-09-06 | DHI-TRANSMIT-000645 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17def8d5-e375-4906-bb3e-8c98029a34c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3902 | T16182-CA03-P0UMY-185153 | 2017-09-06 | DHI-TRANSMIT-000645 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb2e050e-2e1e-451e-b799-408df0696e5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3903 | T16182-CA03-P0UMY-185154 | 2017-09-06 | DHI-TRANSMIT-000645 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59aa1f7b-d5db-471d-a738-8a6008eb59b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3904 | T16182-CA03-P0UMY-185155 | 2017-09-06 | DHI-TRANSMIT-000645 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=608201bf-2976-4f7a-878e-39461ac1acf6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3905 | T16182-CA06-P0UMY-185190 | 2017-09-06 | DHI-TRANSMIT-000645 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37ea7e2a-237b-4eb4-b824-7e54998307c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3906 | T16182-YU02-P0SCA-127510 | 2017-09-06 | DHI-WTRAN-000679 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5134e948-f7a0-48bc-8599-641e768ff1e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3907 | T16182-CV03-P0SG-136621 | 2017-09-07 | DHI-WTRAN-000680 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3642d67-89bd-4ad7-a58e-53d2e95065b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3908 | T16182-XG02-P0LAC-126053 | 2017-09-07 | DHI-WTRAN-000681 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92271988-e822-44ce-b575-9deaf5cd7a71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3909 | T16182-XB02-P0ULX-171222 | 2017-09-07 | DHI-TRANSMIT-000646 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed00a12d-6cbc-448f-bee6-8270ac4fabf0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3910 | T16182-XB02-P0ULX-171223 | 2017-09-07 | DHI-TRANSMIT-000646 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bb929e8-371b-45c8-bfa3-92c1c78cc498 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3911 | T16182-YB03-P0LB-122048 | 2017-09-07 | DHI-TRANSMIT-000647 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62dbfbd8-48ec-4f9d-bdd5-31693cf72743 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3912 | T16182-YD00-P0LCB-127501 | 2017-09-07 | DHI-TRANSMIT-000648 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac523a81-eae5-41f5-899e-95206ce1d32c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3913 | T16182-YT01-P0MBA-121555 | 2017-09-07 | DHI-WTRAN-000682 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d72169ed-bb6b-456e-af78-4d20b10e803b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3914 | T16182-YL00-P0GM-128512 | 2017-09-07 | DHI-WTRAN-000683 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d6ea13a-5add-4c6d-83af-3365850904e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3915 | T16182-CV03-P0GM-128508 | 2017-09-07 | DHI-WTRAN-000683 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccf06428-465b-4fa8-9e23-3a10b1cf5235 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3916 | T16182-YK00-P0GM-128509 | 2017-09-07 | DHI-WTRAN-000683 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09f17a35-b8fe-41b8-8a0d-8cc9216a0d05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3917 | T16182-XV00-P8ZEN-125505 | 2017-09-07 | DHI-TRANSMIT-000649 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59505327-72be-4b9c-8bda-c9b06a78410d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3918 | T16182-DP00-P8ZEN-125506 | 2017-09-07 | DHI-TRANSMIT-000649 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b2ee4ee-06dc-498f-b9b1-52808732d450 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3919 | T16182-YL30-P8ZEN-125514 | 2017-09-07 | DHI-TRANSMIT-000650 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59d884ce-6e14-4049-a031-fdb6cbbe8e7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3920 | T16182-XK00-P6MKA-260005 | 2017-09-07 | DHI-WTRAN-000684 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00b74e59-a0d8-46ae-a69a-ce0120a41456 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3921 | T16182-XK00-P7MKA-260008 | 2017-09-07 | DHI-WTRAN-000684 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbe350ff-89c5-43c1-88a4-415b1a8f9932 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3922 | T16182-YE03-P0BAU-152505 | 2017-09-07 | DHI-TRANSMIT-000651 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b0979fa-a541-4d17-a906-47991a73bcdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3923 | T16182-YE03-P0BAU-152510 | 2017-09-07 | DHI-TRANSMIT-000651 | IFC | 0 | D | TRUE | FALSE | 2017-09-07_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5db4aa5c-d733-4a51-95f6-e528130312cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3924 | T16182-XB02-P0LB-122016 | 2017-09-07 | DHI-TRANSMIT-000652 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3303372f-1bdb-4983-8210-fba184fed3bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3925 | T16182-XS00-P0LB-122036 | 2017-09-07 | DHI-WTRAN-000685 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ddf8e245-9f3a-43c4-8934-a2e7f78822ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3926 | T16182-YD00-P0LB-122052 | 2017-09-07 | DHI-TRANSMIT-000653 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=489d02e4-2f17-410b-bf8a-988cf8f81bf6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3927 | T16182-YL16-P0ZEN-152850 | 2017-09-07 | DHI-WTRAN-000686 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=590897ed-a53e-4c76-9a64-1f4c3b4fb16f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3928 | T16182-XH01-P0MAG-123016 | 2017-09-07 | DHI-WTRAN-000687 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3099f37d-e520-4c74-9e84-050557930ca0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3929 | T16182-YK08-P0MBA-121009 | 2017-09-07 | DHI-WTRAN-000688 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3930 | T16182-CA05-P0UST-182081 | 2017-09-08 | DHI-TRANSMIT-000655 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b17f6c0-f617-4863-b752-92ae80291c1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3931 | T16182-CA05-P0UST-182085 | 2017-09-08 | DHI-TRANSMIT-000655 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d305632-da73-4f44-a438-13a166f3c3a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3932 | T16182-YT01-P0BB-150801 | 2017-09-08 | DHI-WTRAN-000689 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aaa4e931-fca7-459e-ab3c-a18a6fd72311 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3933 | T16182-XB02-P0UMX-171002 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5d5deb0-1eab-48d6-b817-33929f895638 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3934 | T16182-XB02-P0UMX-171009 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=097c9d1a-f126-4110-a650-952a6af5423d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3935 | T16182-VK02-P0UMX-171012 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5687b5ef-0734-45a2-9a0c-993d78f1b2f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3936 | T16182-VK02-P0UMX-171013 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=164e8916-059e-4eab-93ab-a42cb84d3bb2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3937 | T16182-VK02-P0UMX-171014 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=982ba7f0-b73b-4610-9dd7-f2c108c4f15d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3938 | T16182-VK02-P0UMX-171015 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e97b84ed-869e-42ad-bb32-4edc3cee6927 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3939 | T16182-VK02-P0UMX-171016 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9de22bc7-68c5-4a98-b373-83e3e3d7217e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3940 | T16182-VK02-P0UMX-171017 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba244da4-abf8-46f5-85d8-483bf0da7557 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3941 | T16182-VK02-P0UMX-171018 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cacd79c-36a6-44d9-bb1c-e9f83e18f865 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3942 | T16182-VK02-P0UMX-171019 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c64615c8-437d-4a8c-9af8-ce9d255fee0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3943 | T16182-VK02-P0UMX-171020 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c91e136-98e2-448b-874c-d3250633d90a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3944 | T16182-VK02-P0UMX-171021 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7afcf6ab-b65b-47da-886d-8884be93cb79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3945 | T16182-VK02-P0UMX-171022 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=032c6a9d-8fd9-4ce5-b4e9-6cd9a1c996b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3946 | T16182-VK02-P0UMX-171023 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4545ab9d-27bf-41a5-9c6f-f53c2b398f40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3947 | T16182-VK02-P0UMX-171024 | 2017-09-08 | DHI-TRANSMIT-000656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49cd7a85-1669-487a-b25e-eb4f25628076 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3948 | T16182-CA00-P0UGD-181908 | 2017-09-08 | DHI-WTRAN-000690 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f695a78b-adcf-4f15-a46d-446825d532c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3949 | T16182-CA00-P0UGD-181909 | 2017-09-08 | DHI-WTRAN-000690 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5c32005-6961-42cc-b7e6-765ec8c8dccf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3950 | T16182-CA00-P0UGD-181910 | 2017-09-08 | DHI-TRANSMIT-000657 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba169d86-442e-4f36-a618-564dcb28395d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3951 | T16182-CA00-P0UGD-181911 | 2017-09-08 | DHI-TRANSMIT-000657 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=701872d3-6d70-4b4b-a4db-8175ccd7569e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3952 | T16182-CA00-P0UGD-181912 | 2017-09-08 | DHI-TRANSMIT-000657 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1744632d-25f5-4139-b161-b65ec5a4bf79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3953 | T16182-CA00-P0UGD-181913 | 2017-09-08 | DHI-TRANSMIT-000657 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8dbd1ab2-a9c4-4d15-9396-09886f95a632 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3954 | T16182-CA00-P0UGD-181914 | 2017-09-08 | DHI-TRANSMIT-000657 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5693a4db-78c9-46cc-8899-42d25052a132 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3955 | T16182-YD00-P0GCF-130006 | 2017-09-08 | DHI-TRANSMIT-000658 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e3c7556-b316-42a2-8c09-ea70e3fda8d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3956 | T16182-YU02-P0GCF-130010 | 2017-09-08 | DHI-TRANSMIT-000658 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc282090-45d2-4b0f-8325-c16b99e55f36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3957 | T16182-VK02-P0UZT-172704 | 2017-09-08 | DHI-TRANSMIT-000659 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e51ed6d5-51d8-4970-9966-7e8906752449 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3958 | T16182-VK02-P0UZT-172713 | 2017-09-08 | DHI-TRANSMIT-000659 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c372fc3-fc30-4a91-a80b-54945ccee8c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3959 | T16182-XB02-P0UZT-172702 | 2017-09-08 | DHI-TRANSMIT-000659 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98b1350a-dff6-43fa-9451-71b4934e7ce6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3960 | T16182-XB02-P0UZT-172703 | 2017-09-08 | DHI-TRANSMIT-000659 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ca55c91-05ac-4f14-9bdc-695373784586 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3961 | T16182-XB02-P0UZT-172716 | 2017-09-08 | DHI-TRANSMIT-000659 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55eab180-02ee-4297-af7a-c0cc9bba86d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3962 | T16182-YD00-P0BAT-150621 | 2017-09-08 | DHI-WTRAN-000691 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa2509c4-39e9-4db7-a702-ba5469ef01bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3963 | T16182-YD00-P0BAT-150626 | 2017-09-08 | DHI-WTRAN-000691 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cc7572a-0d19-4ddb-ae9c-28f309a48aa5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3964 | T16182-YD00-P0BBT-150671 | 2017-09-08 | DHI-WTRAN-000691 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5856f3cd-831a-4de9-9117-f5c65cb8723a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3965 | T16182-YT01-P0MBA-121555 | 2017-09-08 | DHI-TRANSMIT-000660 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96656e87-83fa-44ab-bab2-1111fbbd680a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3966 | T16182-YR05-P0GM-128511 | 2017-09-08 | DHI-WTRAN-000692 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8db0da15-3eee-42d5-92e4-47dbb4fefad7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3967 | T16182-CA00-P0USG-182701 | 2017-09-08 | DHI-TRANSMIT-000661 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d60f8f41-6f43-4994-8a40-c4b90e30ee75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3968 | T16182-CA00-P0USG-182702 | 2017-09-08 | DHI-TRANSMIT-000661 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33027c97-ad22-4ea0-a73b-9ebe7d560603 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3969 | T16182-CA00-P0USG-182704 | 2017-09-08 | DHI-TRANSMIT-000661 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6595e0c3-0ba2-4bd0-810d-b6346e7c942a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3970 | T16182-CA01-P0USG-182752 | 2017-09-08 | DHI-TRANSMIT-000661 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b8d0731-b42e-4b2f-8ef7-ded6997e16e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3971 | T16182-YT01-P0LAC-126005 | 2017-09-08 | DHI-WTRAN-000693 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3761acbc-4f39-4bfb-9e73-38e9f4392e3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3972 | T16182-YT01-P0LAC-126055 | 2017-09-08 | DHI-WTRAN-000693 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=307bda28-5d60-476c-9daa-ae84851e3e62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3973 | T16182-CA05-P0UYP-183281 | 2017-09-08 | DHI-WTRAN-000694 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a85cd670-ddfd-42bc-941e-444dd84e7fa2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3974 | T16182-CA05-P0UYP-183282 | 2017-09-08 | DHI-WTRAN-000694 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=225a0b02-3707-4ec2-8a94-dadfc429f948 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3975 | T16182-CA05-P0UYP-183283 | 2017-09-08 | DHI-WTRAN-000694 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94e68dc5-0d86-4710-8216-7858ba794d66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3976 | T16182-CA05-P0UYP-183284 | 2017-09-08 | DHI-WTRAN-000694 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62271100-cdf8-46c9-9dc9-5be551914e40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3977 | T16182-CA05-P0UYP-183285 | 2017-09-08 | DHI-WTRAN-000694 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6e7ac7e-1d2d-4292-8b0c-1c3cb0e3cf79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3978 | T16182-YT02-P0LAC-126011 | 2017-09-08 | DHI-WTRAN-000695 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=311372e4-7c24-4921-9dec-ce24692cf859 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3979 | T16182-YT02-P0LAC-126061 | 2017-09-08 | DHI-WTRAN-000695 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bccfe094-06e7-459a-af81-3fa6e511921a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3980 | T16182-CA00-P0UMA-180405 | 2017-09-08 | DHI-WTRAN-000696 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3cb9278-d103-4105-a0a6-7ec28c0e6155 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3981 | T16182-CA00-P0UMA-180406 | 2017-09-08 | DHI-WTRAN-000696 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=332bbb15-303e-48a4-8805-9e2e5b591a82 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3982 | T16182-CA00-P0UMA-180408 | 2017-09-08 | DHI-WTRAN-000696 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3039689e-2599-4dab-a7a0-febbe83eccac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3983 | T16182-YF00-P0CBA-161210 | 2017-09-11 | DHI-TRANSMIT-000666 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a579c4a-cf2b-48ae-8a77-0d0e866f825e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3984 | T16182-YF00-P0CBA-161211 | 2017-09-11 | DHI-TRANSMIT-000666 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c729564-6457-42cf-9091-4fe9f1187e8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3985 | T16182-YF00-P0CGA-161320 | 2017-09-11 | DHI-TRANSMIT-000666 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d430fef9-5186-4ec4-a766-e3c091565eb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3986 | T16182-XJ00-P0EKG-140118 | 2017-09-11 | DHI-WTRAN-000697 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b478639-2c1e-4732-af16-5aeb5e8d34e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3987 | T16182-XJ00-P0GHC-140113 | 2017-09-11 | DHI-WTRAN-000697 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3507d594-3d72-4204-971a-27da9f7fe03e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3988 | T16182-XJ00-P0GKB-140112 | 2017-09-11 | DHI-WTRAN-000697 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cfbc225-d8ac-4c64-a7ed-e8cd6bf76ca7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3989 | T16182-XJ00-P0LAB-140108 | 2017-09-11 | DHI-WTRAN-000697 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d8586e4-4d95-42be-a4e8-12aa5fb0563d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3990 | T16182-XJ00-P0LBG-140104 | 2017-09-11 | DHI-WTRAN-000697 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28f9c62b-1b06-4de5-9c5b-eef0ac945e94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3991 | T16182-XJ00-P0LCA-140106 | 2017-09-11 | DHI-WTRAN-000697 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2905d2b-e4ac-4017-8485-5ab1384e9ecb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3992 | T16182-XJ00-P0PGB-140109 | 2017-09-11 | DHI-WTRAN-000697 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7923d513-4e3f-4318-9ee2-07f43b0093ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3993 | T16182-XF00-P0GM-128510 | 2017-09-11 | DHI-WTRAN-000698 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a29eddf-1d76-4761-b804-251ce76cf060 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3994 | T16182-XK00-P0GM-128504 | 2017-09-11 | DHI-WTRAN-000698 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=634e4684-bda5-4e82-99c6-8d5329d43b4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3995 | T16182-XK00-P0GM-128505 | 2017-09-11 | DHI-WTRAN-000698 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a0e27b8-6732-48b5-b963-55f09aa57753 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3996 | T16182-CA00-P0UBA-181004 | 2017-09-11 | DHI-TRANSMIT-000668 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0ef8f91-dcf6-4f50-8129-434428bbac52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3997 | T16182-CA00-P0UBA-181104 | 2017-09-11 | DHI-TRANSMIT-000668 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b53bea2a-88ef-4cd5-95ef-cae5e7dbd283 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3998 | T16182-YT10-P0ZEN-152221 | 2017-09-11 | DHI-WTRAN-000699 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f148e200-2d6b-4ed4-a0b2-e942a28b1e00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
3999 | T16182-YB11-P0ZEN-152419 | 2017-09-11 | DHI-WTRAN-000699 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc607023-0d14-460f-adfd-d9c2ab9f955f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4000 | T16182-YQ01-P0ZEN-152319 | 2017-09-11 | DHI-WTRAN-000699 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2257c73a-f6ad-4163-8bb5-603f0cf3eb69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4001 | T16182-YL22-P0PGB-110402 | 2017-09-11 | DHI-WTRAN-000700 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a664814b-9a19-46d9-9368-d44b566fc8ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4002 | T16182-YD00-P0PGB-110401 | 2017-09-11 | DHI-TRANSMIT-000670 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad650727-49d4-4345-b965-3de74c981a62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4003 | T16182-YT01-P0PGB-110403 | 2017-09-11 | DHI-TRANSMIT-000670 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36829cf1-5ecb-4b3c-af52-dbf0d8fc726e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4004 | T16182-CA00-P0UBA-181303 | 2017-09-11 | DHI-TRANSMIT-000671 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58d386f5-c51f-420f-8629-8343d57edf80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4005 | T16182-CA00-P0UBA-181305 | 2017-09-11 | DHI-TRANSMIT-000671 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77052092-234a-40c3-871f-6132c356882f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4006 | T16182-CA00-P0UBA-181307 | 2017-09-11 | DHI-TRANSMIT-000671 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dca898d2-34ce-40ea-afcc-9b1624065229 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4007 | T16182-CA01-P0UBA-181351 | 2017-09-11 | DHI-TRANSMIT-000671 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1edeb90-b619-4643-a33e-6af8f414b7fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4008 | T16182-CA01-P0UBA-181352 | 2017-09-11 | DHI-TRANSMIT-000671 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e9c64a6-93c0-4856-8559-3883e2e1a126 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4009 | T16182-CA01-P0UBA-181353 | 2017-09-11 | DHI-TRANSMIT-000671 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=736455d9-c915-43b1-b90e-e96f6caa8a3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4010 | T16182-YD00-P0CHB-151131 | 2017-09-12 | DHI-WTRAN-000701 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87bd5661-1d5d-472a-b45d-6e14c4aa440c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4011 | T16182-YT10-P0ZEN-150311 | 2017-09-12 | DHI-WTRAN-000701 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5804ab9e-bd11-4fe6-86d5-960b5ab9b240 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4012 | T16182-YT10-P0ZEN-150314 | 2017-09-12 | DHI-WTRAN-000701 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ab371fc-d1c6-4372-883e-9ae46857ab6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4013 | T16182-YF00-P0BA-150404 | 2017-09-12 | DHI-TRANSMIT-000672 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0761e179-dc15-4dad-af98-42ed51287a6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4014 | T16182-YT01-P0CFA-151161 | 2017-09-12 | DHI-TRANSMIT-000672 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8dc571a1-6c9c-40f7-854a-829c580d0178 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4015 | T16182-YT01-P0CHB-151101 | 2017-09-12 | DHI-TRANSMIT-000672 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d80ad4a-b824-455f-ae9a-dab9405266ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4016 | T16182-YT10-P0ZEN-150302 | 2017-09-12 | DHI-TRANSMIT-000672 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a4522b3-4036-4fff-adea-251fd7a5c05d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4017 | T16182-YT10-P0ZEN-150303 | 2017-09-12 | DHI-TRANSMIT-000672 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d083db1-bb4d-4b99-9bd3-6de612353edb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4018 | T16182-XB00-P0SCA-127509 | 2017-09-12 | DHI-TRANSMIT-000673 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72f1e50a-392c-457a-a714-b3b42162d5c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4019 | T16182-YK00-P0SCA-127522 | 2017-09-12 | DHI-WTRAN-000702 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71c5be9c-59a2-42d9-b035-c2679cc38109 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4020 | T16182-YV02-P0SCA-127511 | 2017-09-12 | DHI-WTRAN-000703 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23c6d4e4-5c97-42b9-a1ef-b49e968684c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4021 | T16182-YK09-P0SML-128023 | 2017-09-12 | DHI-WTRAN-000704 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12706d83-7c92-4129-8ec4-2dde9e5a17a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4022 | T16182-YK09-P0SMM-128007 | 2017-09-12 | DHI-WTRAN-000704 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ecb871a-8777-4581-8763-06d4dd2776f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4023 | T16182-CA00-P0UBA-186101 | 2017-09-12 | DHI-TRANSMIT-000674 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07f940a8-219d-45d1-8e2e-af5be19b82f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4024 | T16182-CA00-P0UBA-186104 | 2017-09-12 | DHI-TRANSMIT-000674 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab34c7c1-6de8-4535-86eb-30f7410f204c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4025 | T16182-CA01-P0UBA-186152 | 2017-09-12 | DHI-TRANSMIT-000674 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93125889-3929-45c8-b443-6177adbc2b89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4026 | T16182-CA01-P0UBA-186154 | 2017-09-12 | DHI-TRANSMIT-000674 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d08ea5a-192b-481e-bf5e-5ab2b25ab5c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4027 | T16182-CA02-P0UBA-186155 | 2017-09-12 | DHI-TRANSMIT-000674 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a4a57b5-38f0-450a-b803-ef9cd0941c6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4028 | T16182-YL00-P0GCF-130009 | 2017-09-12 | DHI-WTRAN-000705 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9b55f1b-20e9-4e5b-b9c3-8baf0ecb474e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4029 | T16182-YR05-P0GCF-130007 | 2017-09-12 | DHI-TRANSMIT-000675 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7662dfb0-0733-4d25-ad03-eb7b6351bdf7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4030 | T16182-YU03-P0GCF-130017 | 2017-09-12 | DHI-TRANSMIT-000676 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b25481e-de79-4ad7-a2b3-59cba69e6aea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4031 | T16182-YD00-P0SGZ-138231 | 2017-09-12 | DHI-TRANSMIT-000677 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a6c3507-d3a0-427a-9720-efb176841745 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4032 | T16182-YD00-P0SGZ-138331 | 2017-09-12 | DHI-TRANSMIT-000677 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90c94b66-59d9-422e-a4db-2f864b557266 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4033 | T16182-YD02-P0ZEN-165519 | 2017-09-12 | DHI-WTRAN-000706 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc2c17c1-c4a1-46e7-aff4-ab6bc3ce8b07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4034 | T16182-YR05-P0SAY-163423 | 2017-09-12 | DHI-WTRAN-000707 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e5a0ce6-5adc-4744-b2c3-b27473196f1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4035 | T16182-XJ00-P0LB-122029 | 2017-09-12 | DHI-WTRAN-000708 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75c1d875-08a9-401f-b3a5-e769173652c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4036 | T16182-YK00-P0LB-122071 | 2017-09-12 | DHI-WTRAN-000708 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce342d03-01ea-4228-9cd4-95fc7cf5d5c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4037 | T16182-YT01-P0LB-122108 | 2017-09-12 | DHI-WTRAN-000708 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7165db0-22b2-4d06-be80-0a3bc65af436 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4038 | T16182-YB03-P0LB-122047 | 2017-09-12 | DHI-WTRAN-000709 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12e927a7-3222-4fb6-9b3b-8e58f59988fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4039 | T16182-YL16-P0LB-122078 | 2017-09-12 | DHI-WTRAN-000709 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=098151f5-2e87-457d-b23c-92093764a889 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4040 | T16182-CA00-P0UTF-182801 | 2017-09-13 | DHI-TRANSMIT-000678 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca80cb62-3cac-43c9-86ae-908877362c8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4041 | T16182-CA01-P0UTF-182853 | 2017-09-13 | DHI-TRANSMIT-000678 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0600d744-bbfd-4a06-9aff-dfdf8e860119 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4042 | T16182-CA01-P0UTF-182854 | 2017-09-13 | DHI-TRANSMIT-000678 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7f6dcd6-6054-4de7-a928-d43cba36d335 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4043 | T16182-CA01-P0UTF-182856 | 2017-09-13 | DHI-TRANSMIT-000678 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f46560c2-c5f3-4bf8-bef7-8b1c7f75bc34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4044 | T16182-CA02-P0UTF-182857 | 2017-09-13 | DHI-TRANSMIT-000678 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d795a52c-0649-4a5d-aaa4-ed8266715833 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4045 | T16182-CA05-P0UYC-182985 | 2017-09-13 | DHI-TRANSMIT-000679 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35d0e68e-8b5f-4123-8418-39d224702ab9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4046 | T16182-CA00-P0UYE-183301 | 2017-09-13 | DHI-WTRAN-000710 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9e47e60-52ca-4582-a8a0-d909ea9a667d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4047 | T16182-CA00-P0UYE-183302 | 2017-09-13 | DHI-WTRAN-000710 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=425ede6f-c28e-4433-a70a-6de5f343afee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4048 | T16182-CA00-P0UYE-183303 | 2017-09-13 | DHI-WTRAN-000710 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b7376cc-20d5-4473-af15-d8f2a93c0d84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4049 | T16182-VN03-P0LB-122015 | 2017-09-13 | DHI-WTRAN-000711 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14222524-8d37-49a3-b14b-123ff2b45883 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4050 | T16182-YE00-P0ZEN-152718 | 2017-09-13 | DHI-TRANSMIT-000680 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10c98d8e-5c72-4bc6-8eeb-62991611e75b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4051 | T16182-YS18-P0SML-128027 | 2017-09-13 | DHI-WTRAN-000712 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c101b83-b5ed-4b9a-8e9d-0c687f5affdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4052 | T16182-YS18-P0SMM-128010 | 2017-09-13 | DHI-WTRAN-000712 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd615cca-4a9c-482b-8b8c-f6e37984bfa4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4053 | T16182-YK08-P0PGB-420010 | 2017-09-15 | DHI-TRANSMIT-000687 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2239b62-f24d-44fd-bfa8-20570b848223 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4054 | T16182-YK08-P0PGB-420020 | 2017-09-15 | DHI-TRANSMIT-000687 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e49f1091-4971-4590-8e8c-5f293099e5d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4055 | T16182-CA06-P0UYC-182900 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f00e6815-a465-4244-b0b2-796362de4ee9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4056 | T16182-CA00-P0UYC-182902 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3299fe33-d854-4c66-ad3c-6df3b4e040cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4057 | T16182-CA00-P0UYC-182904 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e932e976-0f55-44dc-9da1-b8c18a8126f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4058 | T16182-CA01-P0UYC-182951 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a8efb07-026f-4a4c-a659-c75d7e03baa6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4059 | T16182-CA01-P0UYC-182952 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d41cea3-177e-4bae-9352-63c077f27ba6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4060 | T16182-CA01-P0UYC-182953 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17f7db43-9229-469c-91be-e817a1c6ef96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4061 | T16182-CA01-P0UYC-182954 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c67f763-faa6-4f40-89a3-80f66cd0c6cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4062 | T16182-CA01-P0UYC-182955 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6142326d-17cd-454f-b8a5-baab30971528 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4063 | T16182-CA01-P0UYC-182956 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c6b324a-269a-4c2a-847e-fe21c64b20a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4064 | T16182-CA02-P0UYC-182957 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3026871e-f1ec-454a-bf7a-3be1ab58781d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4065 | T16182-CA02-P0UYC-182958 | 2017-09-15 | DHI-TRANSMIT-000688 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fecae94e-589c-4636-a759-af90631fed39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4066 | T16182-XF00-P0SCA-127524 | 2017-09-15 | DHI-WTRAN-000713 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cacb9aa-b6af-4188-88a8-354d7e56536c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4067 | T16182-XW01-P0SCA-127505 | 2017-09-15 | DHI-WTRAN-000713 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82a51b30-5c7f-495e-ba2a-79e65467802e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4068 | T16182-XW01-P0SCA-127506 | 2017-09-15 | DHI-WTRAN-000713 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a5c8525-af85-4cae-99fd-1258a3f1c90a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4069 | T16182-XH02-P8QHL-125400 | 2017-09-15 | DHI-TRANSMIT-000689 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7dc172a1-c632-4b57-8354-a5dd59cbc77e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4070 | T16182-CV03-P8ZEN-125606 | 2017-09-15 | DHI-WTRAN-000714 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6b9d0c0-99cc-4704-92cb-6612b7849941 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4071 | T16182-XS00-P8QHA-125002 | 2017-09-15 | DHI-WTRAN-000714 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d22806c-6b4b-4db6-bf91-20f4396bfb00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4072 | T16182-XG07-P0SAB-134802 | 2017-09-15 | DHI-WTRAN-000715 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c442f204-9d87-4380-8838-bc1f309587ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4073 | T16182-XH02-P0SAB-134804 | 2017-09-15 | DHI-WTRAN-000715 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9924def-6404-424f-8588-f775d467a26d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4074 | T16182-XW03-P0SAB-134801 | 2017-09-15 | DHI-WTRAN-000715 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ced23d5c-a11c-4944-a2a0-9afe2ad8f97b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4075 | T16182-XW03-P0SAB-134803 | 2017-09-15 | DHI-WTRAN-000715 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efb14be6-9e68-4a4b-8e24-3e81a9a0231a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4076 | T16182-CA06-P0UGD-186600 | 2017-09-15 | DHI-WTRAN-000716 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f031fe9-03d2-46b0-9588-88d34db10639 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4077 | T16182-CA00-P0UGD-186601 | 2017-09-15 | DHI-WTRAN-000716 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f79ff5b-4aa9-4ff1-81e9-edb2a0f653d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4078 | T16182-CA00-P0UGD-186602 | 2017-09-15 | DHI-WTRAN-000716 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5886b6e-3123-43fe-aac8-151d10e1bb5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4079 | T16182-CA01-P0UGD-186651 | 2017-09-15 | DHI-WTRAN-000716 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdd8742c-12df-4c4a-9224-c363096b3532 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4080 | T16182-CA01-P0UGD-186652 | 2017-09-15 | DHI-WTRAN-000716 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=172e8891-017f-4b2c-b754-a0e73a1a2eb2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4081 | T16182-YD02-P0ZEN-165502 | 2017-09-15 | DHI-WTRAN-000717 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31ff7ee5-20e4-444a-895f-c936ab907451 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4082 | T16182-CA00-P0UBA-181001 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1f7f028-453c-4bb8-9ac2-fcc1673e609b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4083 | T16182-CA00-P0UBA-181002 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d254fe6f-3cfb-460a-ade0-02c69c0420b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4084 | T16182-CA00-P0UBA-181003 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d4be5a5-0e07-42f2-a230-62383e6faf30 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4085 | T16182-CA00-P0UBA-181005 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e9ee7be-74d3-4cac-8e52-e4d9e0f2360f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4086 | T16182-CA01-P0UBA-181052 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecc7f804-c77d-4cbc-812c-93ec6a34e684 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4087 | T16182-CA01-P0UBA-181053 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=213651fa-fd2f-4dfe-9519-47754e78a71a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4088 | T16182-CA01-P0UBA-181054 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51459d9e-ea67-4d11-b8b5-ce2fbb9c3564 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4089 | T16182-CA02-P0UBA-181055 | 2017-09-15 | DHI-TRANSMIT-000690 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbc32565-3fe5-4643-8cd1-a6fe5ee05384 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4090 | T16182-CA00-P0UBA-181101 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1319c07b-14f3-4cb4-bfa0-873d7a33b75d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4091 | T16182-CA00-P0UBA-181102 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f352cf9d-5dc2-4f9f-91c0-e3ab7391cb5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4092 | T16182-CA00-P0UBA-181103 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5c4cc91-d51f-4754-8e7a-d06ca2f09df0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4093 | T16182-CA00-P0UBA-181105 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7ce9f31-489f-417a-878f-718ab64bec84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4094 | T16182-CA01-P0UBA-181152 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56b96ec8-0a14-48a5-9526-f19f2578befb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4095 | T16182-CA01-P0UBA-181153 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=679375fc-a0a4-4185-92e6-3d0274dad7ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4096 | T16182-CA01-P0UBA-181154 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04ebafe2-7af2-4b76-a19d-0cf3d9a85eb2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4097 | T16182-CA02-P0UBA-181155 | 2017-09-15 | DHI-TRANSMIT-000691 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d93497bf-040d-458c-8a05-d903b555c32d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4098 | T16182-YK10-P0LF-140301 | 2017-09-15 | DHI-WTRAN-000718 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f80c1459-2735-415b-b1e3-16b4b9fa2d70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4099 | T16182-YK10-P0LF-140302 | 2017-09-15 | DHI-WTRAN-000718 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8ed8e92-7c70-4e8f-aedd-fe9e4ad51ea8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4100 | T16182-YK10-P0LF-140304 | 2017-09-15 | DHI-WTRAN-000718 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0a897f5-a4db-413a-985d-12f6f57fe30f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4101 | T16182-YL00-P0LCB-127013 | 2017-09-15 | DHI-WTRAN-000719 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=208910d0-297a-441e-b96f-49b78376ba5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4102 | T16182-YL00-P0LCB-127040 | 2017-09-15 | DHI-WTRAN-000719 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a4ad50d-5c28-4af6-9202-0e5b70a8b356 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4103 | T16182-YT01-P0LCB-127005 | 2017-09-15 | DHI-WTRAN-000720 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fe568b0-d394-4efc-a3dc-16c763d258c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4104 | T16182-YT01-P0LCB-127006 | 2017-09-15 | DHI-WTRAN-000720 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50544cdd-10cf-4136-8602-f10368be5798 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4105 | T16182-YT01-P0LCB-127035 | 2017-09-15 | DHI-WTRAN-000720 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8086b323-38ca-40e7-b0e2-e0c4c84f7616 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4106 | T16182-YT01-P0LCB-127036 | 2017-09-15 | DHI-WTRAN-000720 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67b94831-e167-498c-8477-72bce8e708e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4107 | T16182-YT10-P0ZEN-150304 | 2017-09-15 | DHI-WTRAN-000721 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e10ea1b-6763-4445-9022-eb47da1726bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4108 | T16182-YT10-P0ZEN-150301 | 2017-09-15 | DHI-TRANSMIT-000692 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65ba5d04-4e45-4174-99a0-36c3481abf8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4109 | T16182-YK08-P0LCM-420040 | 2017-09-15 | DHI-WTRAN-000722 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf4d4ef1-2fcc-4d32-892c-02887f216d7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4110 | T16182-YK08-P0PCA-126512 | 2017-09-15 | DHI-TRANSMIT-000693 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2c6a006-1c1b-48ea-8d82-b7a1d3d4b1e6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4111 | T16182-YR05-P0CJN-290004 | 2017-09-15 | DHI-TRANSMIT-000694 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbf625a5-6d8f-456f-a58e-e0cd6ca7d533 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4112 | T16182-XS00-P0QC-130301 | 2017-09-15 | DHI-WTRAN-000723 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7862ed1b-efe7-4b25-8217-0045ee36e08e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4113 | T16182-YD00-P0QC-130302 | 2017-09-15 | DHI-WTRAN-000723 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f62829f9-e03b-450a-8469-f2f1449151d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4114 | T16182-XG02-P0QC-130303 | 2017-09-15 | DHI-WTRAN-000723 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49bba28c-7184-48ec-ad94-64ed018a8d49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4115 | T16182-XW03-P0QC-130304 | 2017-09-15 | DHI-WTRAN-000723 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4aade210-295d-42a2-8601-6c11d3b0a662 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4116 | T16182-YD00-P0BAC-150721 | 2017-09-15 | DHI-WTRAN-000724 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=827998f5-aaf6-4121-b43a-69c5e0483bf1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4117 | T16182-YT01-P0BAC-150711 | 2017-09-15 | DHI-TRANSMIT-000695 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3d677f9-9753-4b5a-869b-b960f7c3c7e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4118 | T16182-YD00-P0SMM-128001 | 2017-09-15 | DHI-TRANSMIT-000696 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ead1b90-6a64-4cc5-8fb4-9ee4e66e5158 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4119 | T16182-YT01-P0SMM-128004 | 2017-09-15 | DHI-TRANSMIT-000696 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b80722f1-e29e-470e-bdaa-76b0d9c1f9b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4120 | T16182-YF00-P0CBA-161221 | 2017-09-15 | DHI-WTRAN-000725 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f2468ab-7f88-4cd2-a704-0d19a68b9ad0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4121 | T16182-YF00-P0CGA-161321 | 2017-09-15 | DHI-WTRAN-000725 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=879a087f-9602-4436-a879-dcef14f106be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4122 | T16182-XB02-P0UEM-171702 | 2017-09-15 | DHI-TRANSMIT-000697 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aec09dc0-85e6-4ebb-9f08-fd06c4083127 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4123 | T16182-XB02-P0UEM-171708 | 2017-09-15 | DHI-TRANSMIT-000697 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be465ebe-3546-49b4-9de2-95a5f49777ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4124 | T16182-VK02-P0UEM-171711 | 2017-09-15 | DHI-TRANSMIT-000697 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dac7cc1f-2f43-49f4-ab01-94fde547c62f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4125 | T16182-VE04-P0UMX-171004 | 2017-09-15 | DHI-TRANSMIT-000698 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eafb7b53-170f-4bae-b9a4-7206e7a3ed95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4126 | T16182-XS00-P0PCA-126504 | 2017-09-18 | DHI-WTRAN-000726 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ece853d-de2f-4bbd-877b-697fe8d99372 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4127 | T16182-YM03-P8ZEN-125721 | 2017-09-18 | DHI-WTRAN-000727 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8c04a8f-bd4e-4bc1-96a1-903b2268204d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4128 | T16182-DP00-P8ZEN-125766 | 2017-09-18 | DHI-TRANSMIT-000702 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5ea8f29-3992-48ea-9903-b769ac75c28f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4129 | T16182-YQ03-P8ZEN-125769 | 2017-09-18 | DHI-TRANSMIT-000702 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c2a8b09-9cf5-4db3-a82e-b4a422859f74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4130 | T16182-YT02-P8ZEN-125714 | 2017-09-18 | DHI-TRANSMIT-000702 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f44c2f6-e0d1-4aec-a35b-6eeaab344dbd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4131 | T16182-XG05-P8ZEN-125571 | 2017-09-18 | DHI-TRANSMIT-000703 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0e7f611-6b9c-4a71-9ab0-23b37a8eafb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4132 | T16182-CA00-P0UYP-183201 | 2017-09-18 | DHI-TRANSMIT-000704 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=610312dd-c3eb-4d5e-bd3e-7e68b6ca3ffa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4133 | T16182-CA00-P0UYP-183202 | 2017-09-18 | DHI-TRANSMIT-000704 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a67d0d9-d7a9-4e6e-88dd-9084162807e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4134 | T16182-CA00-P0UYP-183203 | 2017-09-18 | DHI-TRANSMIT-000704 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd200f5b-9df5-4721-9f05-65a6393da700 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4135 | T16182-CA00-P0UYP-183204 | 2017-09-18 | DHI-TRANSMIT-000704 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db920937-22a8-4e28-ad5f-7f30bcd5f68b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4136 | T16182-CA06-P0UYP-183200 | 2017-09-18 | DHI-TRANSMIT-000704 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=797c78a1-c9ea-4002-b5f9-dc5fa0cde32f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4137 | T16182-YL01-P0SCA-127517 | 2017-09-18 | DHI-WTRAN-000728 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dcaecf9-9dbe-4054-bcde-bfab87b44c81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4138 | T16182-YR05-P0SCA-127523 | 2017-09-18 | DHI-WTRAN-000728 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92c20fb7-1bee-4118-8874-dd400609800b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4139 | T16182-YF02-P0SCA-127514 | 2017-09-18 | DHI-WTRAN-000728 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9c74c03-a926-4eb3-a270-e31c54d85956 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4140 | T16182-YR05-P0CWQ-161148 | 2017-09-18 | DHI-TRANSMIT-000705 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=532f13f8-f95e-4ec3-b8e8-429d1d28d001 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4141 | T16182-YF02-P0CRV-161102 | 2017-09-18 | DHI-TRANSMIT-000705 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adc98345-cae2-42fa-9575-ed8f32ff6d11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4142 | T16182-YR05-P0CWQ-161143 | 2017-09-18 | DHI-TRANSMIT-000705 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9036ff57-d95d-4a9e-b72e-52e9f5836a9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4143 | T16182-YR05-P0CWQ-161141 | 2017-09-18 | DHI-TRANSMIT-000705 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf869524-9cf4-4ce9-86d3-0dae92ab927f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4144 | T16182-YR05-P0CWQ-161142 | 2017-09-18 | DHI-TRANSMIT-000705 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=febe86a8-4dc0-4a70-b0b8-95902ba3f1e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4145 | T16182-YB03-P0EKG-124017 | 2017-09-18 | DHI-WTRAN-000729 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c56dc97d-f79b-4ef7-ab4f-b48d3d772ee9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4146 | T16182-YE01-P0BAU-152603 | 2017-09-18 | DHI-WTRAN-000730 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=090da74d-e78f-492f-869f-66370ad32360 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4147 | T16182-XS00-P0GM-120022 | 2017-09-18 | DHI-TRANSMIT-000706 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c67d383f-1f72-4328-a079-89ecc280a517 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4148 | T16182-XS00-P0GM-120023 | 2017-09-18 | DHI-TRANSMIT-000706 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fb1b6e5-6793-470d-b435-87247d1c802c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4149 | T16182-UC02-P0MKA-250015 | 2017-09-19 | DHI-WTRAN-000731 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32338659-4445-443d-8d54-cf52cba86975 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4150 | T16182-YD00-P0MKA-250006 | 2017-09-19 | DHI-WTRAN-000731 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aefa65df-15b1-4fba-9812-8dbf4a5c91de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4151 | T16182-YK10-P0MKA-250007 | 2017-09-19 | DHI-WTRAN-000731 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b8e9376-fa36-473f-9f96-5fd0807764db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4152 | T16182-XK00-P8ZEN-125530 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f224cd7-ea0b-451e-a7a8-14b5619ab526 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4153 | T16182-XK00-P8ZEN-125531 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b04c4c6-770d-4534-8960-df375ad4172f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4154 | T16182-XK00-P8ZEN-125532 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2c10e89-d60c-4f0d-a97f-8d34a2f53554 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4155 | T16182-XK00-P8ZEN-125533 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fdd4f7b-dd33-4fad-9827-989615285c27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4156 | T16182-XK00-P8ZEN-125534 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba9abbb6-bea6-4b90-8f85-65ddd1ce0bbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4157 | T16182-XK00-P8ZEN-125535 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca971025-1f95-4447-9093-67227da870ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4158 | T16182-XK00-P8ZEN-125536 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b1e1270-e1f6-4dfe-b89a-825c69576cd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4159 | T16182-XK00-P8ZEN-125537 | 2017-09-19 | DHI-WTRAN-000732 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd30f604-c464-4bbf-b4f6-f4a2710245ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4160 | T16182-CA00-P0GEN-185801 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d700e087-0eeb-445e-92ef-5e4a07b62d81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4161 | T16182-CA00-P0GEN-185802 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66537bc0-c4a3-4793-b283-e76c2973c6c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4162 | T16182-CA00-P0GEN-185803 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33c672a6-95fc-4f47-a404-90e7680086bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4163 | T16182-CA01-P0GEN-185851 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71ac39f2-9616-4ce2-8802-232c4445872a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4164 | T16182-CA01-P0GEN-185852 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94bf255a-7ebf-4a83-a92b-64b00f9bb4b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4165 | T16182-CA01-P0GEN-185853 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19733ccd-b61b-449e-a8ca-a0f5d244e78b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4166 | T16182-CA02-P0GEN-185854 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b1422c2-8388-4b09-b5de-ce6a3cae9cbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4167 | T16182-CA06-P0GEN-185800 | 2017-09-19 | DHI-WTRAN-000733 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b026f7af-54d2-47c7-ace1-a1ab3f5a2f38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4168 | T16182-XB02-P0ULX-171222 | 2017-09-19 | DHI-TRANSMIT-000710 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61b34076-f2ad-4794-adfb-d6786aac2953 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4169 | T16182-YB03-P0ZEN-165531 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=861532df-c97b-4f96-b1e1-e92901d75506 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4170 | T16182-YB03-P0ZEN-165532 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0c950f2-7f9b-4901-9457-8810a44f400c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4171 | T16182-YB03-P0ZEN-165533 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea73fbc1-f1ad-4b8e-8acf-fe64b95e7bf3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4172 | T16182-YB03-P0ZEN-165534 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20976d9e-d507-45db-9748-13e687a8060b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4173 | T16182-YB03-P0ZEN-165535 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc4dcbc8-5326-4f00-ac7a-968c64d2aaea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4174 | T16182-YB03-P0ZEN-165536 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81509f67-5d06-4597-bca2-ed79625ccd84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4175 | T16182-YB03-P0ZEN-165537 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=490b4563-fe0b-415b-b588-b0f17a6d5273 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4176 | T16182-YB03-P0ZEN-165538 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1bf1654-37ae-48fc-99de-41322b06ec60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4177 | T16182-YB03-P0ZEN-165539 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=896f8bed-e245-48de-b743-fbc20a465e04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4178 | T16182-YB03-P0ZEN-165540 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4929be85-28c3-4716-bc52-3228facc2d4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4179 | T16182-YB03-P0ZEN-165541 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c821484-1c29-4ab5-ac6e-7d54a6dc62e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4180 | T16182-YB03-P0ZEN-165542 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b9b6de2-4010-49a7-b2d8-41020978c2bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4181 | T16182-YB03-P0ZEN-165543 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b0af5cd-8bd7-4682-abab-e60bb33e0772 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4182 | T16182-YB03-P0ZEN-165544 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0c4600b-50db-4056-8b8a-5d3da9717cac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4183 | T16182-YB03-P0ZEN-165545 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d14d2c5e-3edd-40a0-8992-6cb41ac2fd0f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4184 | T16182-YB03-P0ZEN-165546 | 2017-09-19 | DHI-WTRAN-000734 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ee6f3cf-f3f6-4924-b4ac-c0218fc18207 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4185 | T16182-YT01-P0LAC-126054 | 2017-09-19 | DHI-TRANSMIT-000711 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe7568e7-de91-4e26-b26c-4d5ba0b675ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4186 | T16182-CA00-P0UBA-181201 | 2017-09-19 | DHI-TRANSMIT-000712 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c86d016-8322-477e-9288-1475a33996a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4187 | T16182-CA00-P0UBA-181202 | 2017-09-19 | DHI-TRANSMIT-000712 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=607cf13f-77f3-4112-9239-4db92d114821 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4188 | T16182-YK00-P0LB-122072 | 2017-09-19 | DHI-WTRAN-000735 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=884026e1-f5d1-4c87-9270-9a27fca2a63b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4189 | T16182-XB02-P0UAZ-172602 | 2017-09-19 | DHI-TRANSMIT-000713 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=748be47f-6708-449d-8936-e98eb4a1bbb0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4190 | T16182-XB02-P0UAZ-172603 | 2017-09-19 | DHI-TRANSMIT-000713 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6740951-c4fc-4509-a655-6500acea93a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4191 | T16182-XB02-P0UAZ-172608 | 2017-09-19 | DHI-TRANSMIT-000713 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=064b22a6-c280-45cc-b846-3058e9e04f94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4192 | T16182-VK02-P0UAZ-172613 | 2017-09-19 | DHI-TRANSMIT-000713 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f52829a1-e417-47b1-8830-47ffde6b7ce4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4193 | T16182-YD02-P0LB-122064 | 2017-09-19 | DHI-WTRAN-000736 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27cbe6d4-3ba7-4a37-a4ef-48ec82454ca4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4194 | T16182-XN00-P8ZEN-125503 | 2017-09-21 | DHI-WTRAN-000737 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acba7cb7-d7c5-4b0f-809f-1b9901201ff4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4195 | T16182-XN00-P8ZEN-125504 | 2017-09-21 | DHI-WTRAN-000737 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6e96c67-a383-4851-8f37-92f45f81b240 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4196 | T16182-YL00-P8ZEN-125707 | 2017-09-21 | DHI-WTRAN-000738 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb864aec-c45e-4364-a84d-ed5c4fca5eda | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4197 | T16182-YL00-P8ZEN-125708 | 2017-09-21 | DHI-WTRAN-000738 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22c31bf3-48d2-4ddb-8356-b9c67b61df81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4198 | T16182-YL01-P8ZEN-125703 | 2017-09-21 | DHI-WTRAN-000738 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18c0bf49-2873-439b-9d97-3a43a8b8b7a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4199 | T16182-YL01-P8ZEN-125706 | 2017-09-21 | DHI-WTRAN-000738 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77257a32-e9c5-477a-9aaf-3d2321e97f70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4200 | T16182-YL01-P8ZEN-125704 | 2017-09-21 | DHI-TRANSMIT-000714 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee9c8a14-2dd8-4883-9941-ef239b9f1b07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4201 | T16182-CA03-P0UMA-180466 | 2017-09-21 | DHI-TRANSMIT-000715 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50c002f7-a7d7-4ae6-b95f-1c42e4e0f007 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4202 | T16182-YT01-P0MAN-110153 | 2017-09-21 | DHI-WTRAN-000739 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61764d4a-7b12-4534-9785-eb5a855d69c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4203 | T16182-YK08-P0MAN-110154 | 2017-09-21 | DHI-WTRAN-000739 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10fc6d0d-a4ac-4bf5-83d1-2ad7fa558c49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4204 | T16182-YT01-P0LBG-110251 | 2017-09-21 | DHI-WTRAN-000739 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cecce56c-62f0-441b-bfd6-a165f3bc4eef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4205 | T16182-YK08-P0LBG-110252 | 2017-09-21 | DHI-WTRAN-000739 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=025659da-eaae-4ea9-b97e-c37c2097df24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4206 | T16182-YL00-P0ZEN-163101 | 2017-09-21 | DHI-WTRAN-000740 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8104f93e-e36e-4697-8457-29ef3b876dd0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4207 | T16182-CA00-P0UGD-181908 | 2017-09-21 | DHI-TRANSMIT-000716 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc48af04-6ec0-4c8f-8cc5-80e0d529aad2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4208 | T16182-CA00-P0UGD-181909 | 2017-09-21 | DHI-TRANSMIT-000716 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a530f221-7697-48a3-bea3-ce1035cc8db2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4209 | T16182-XV00-P0LB-122039 | 2017-09-21 | DHI-WTRAN-000741 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0dcd3cca-99ca-4719-b8a5-4015a61db395 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4210 | T16182-CV03-P0ZEN-163204 | 2017-09-21 | DHI-WTRAN-000742 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03bc6e34-2708-443f-8a54-8e8d5fd2995e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4211 | T16182-YD00-P0PCA-126503 | 2017-09-21 | DHI-TRANSMIT-000717 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e18e9480-d9bd-4507-baef-c857031a6a71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4212 | T16182-YD00-P0LB-122049 | 2017-09-21 | DHI-WTRAN-000743 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17206df0-b209-4ff7-b1a3-8a88ff91d1fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4213 | T16182-YD00-P0LB-122055 | 2017-09-21 | DHI-WTRAN-000743 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eca1ac0f-60b6-4772-9c95-5696d010a3a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4214 | T16182-YQ03-P0LB-122086 | 2017-09-21 | DHI-WTRAN-000743 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7140bdb-063c-48af-921e-c5155b015e63 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4215 | T16182-UE00-P0LB-122062 | 2017-09-22 | DHI-TRANSMIT-000719 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78c36d80-1b3d-4ef4-9832-4d639e5bb5c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4216 | T16182-CA00-P0GEN-185701 | 2017-09-22 | DHI-WTRAN-000745 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a174a29a-2cf5-4956-8756-2908c46e861c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4217 | T16182-CA01-P0GEN-185751 | 2017-09-22 | DHI-WTRAN-000745 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84505831-34cd-42c5-a5bc-4914e2368f6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4218 | T16182-XB02-P0UGF-173101 | 2017-09-22 | DHI-TRANSMIT-000720 | IFC | 1 | DR | TRUE | TRUE | 2017-09-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5542472f-0c3a-4005-bebf-7fc8bc2b8b1a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4219 | T16182-XB02-P0UGF-173102 | 2017-09-22 | DHI-TRANSMIT-000720 | IFC | 1 | DR | TRUE | TRUE | 2017-09-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1eede1a7-0f33-4653-aa78-82da564678ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4220 | T16182-VK02-P0UGF-173107 | 2017-09-22 | DHI-TRANSMIT-000720 | IFC | 1 | DR | TRUE | TRUE | 2017-09-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5eab0e8-5922-4b2e-bdb5-d1d22a7686cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4221 | T16182-CV03-P0SAY-163403 | 2017-09-22 | DHI-WTRAN-000744 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70f60b8f-2b38-48cc-8967-411757c6ceed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4222 | T16182-YD02-P0SAC-163408 | 2017-09-22 | DHI-WTRAN-000744 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df39463c-0704-49e4-bf67-1c573eb370a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4223 | T16182-YD02-P0SAC-163421 | 2017-09-22 | DHI-WTRAN-000744 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a84e7aa7-bdcf-451e-88a7-e717f41c1827 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4224 | T16182-CA00-P0UYC-182907 | 2017-09-22 | DHI-WTRAN-000746 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7edff429-8384-4984-8e0d-461d20b8857b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4225 | T16182-CA00-P0UYC-182908 | 2017-09-22 | DHI-WTRAN-000746 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab04249f-f447-41e7-8826-79b43e8e69a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4226 | T16182-DE00-P8ZEN-125502 | 2017-09-22 | DHI-WTRAN-000747 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25d81769-d7eb-4eb8-b493-8dddf20fffdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4227 | T16182-YT02-P8ZEN-125726 | 2017-09-22 | DHI-TRANSMIT-000721 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbf29158-cd69-43cc-a921-51482a2f0305 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4228 | T16182-YF01-P0BYA-161051 | 2017-09-22 | DHI-WTRAN-000748 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e346090-3807-4141-8382-b44ab2425331 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4229 | T16182-YD00-P0LD-130206 | 2017-09-22 | DHI-WTRAN-000749 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b0d3d98-5c9d-46c5-9cb1-5aa6e0cfad7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4230 | T16182-YE00-P0GCF-130015 | 2017-09-22 | DHI-WTRAN-000750 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbfc1dd1-a1f0-4f23-914a-20c8de868f6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4231 | T16182-YF00-P0GCF-130018 | 2017-09-22 | DHI-WTRAN-000751 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1041a342-ed75-4409-874e-1510998ab6dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4232 | T16182-YL01-P0GCF-130035 | 2017-09-22 | DHI-WTRAN-000751 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bbeca22-63b6-420a-aa16-9b86c89a516f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4233 | T16182-XG07-P0SAI-133802 | 2017-09-22 | DHI-TRANSMIT-000722 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a20eab0b-9bc8-4b86-8bb8-140aaf0a9ca3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4234 | T16182-XH02-P0SAI-133804 | 2017-09-22 | DHI-TRANSMIT-000722 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=797f4513-fdfa-42c7-bb5d-f8cf654c11df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4235 | T16182-XW03-P0SAI-133801 | 2017-09-22 | DHI-TRANSMIT-000722 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e50c553-7564-4df2-923a-b8fca31cdb95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4236 | T16182-XW03-P0SAI-133803 | 2017-09-22 | DHI-TRANSMIT-000722 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b5b76b3-19cc-49bc-88fb-7729a1e1128d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4237 | T16182-YD04-P0ZEN-152015 | 2017-09-25 | DHI-WTRAN-000752 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6481295-1059-4c63-8ee5-e6b178fb2159 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4238 | T16182-YD04-P0ZEN-152005 | 2017-09-25 | DHI-TRANSMIT-000723 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3471e0b8-0749-4beb-94f8-eaa8e68310db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4239 | T16182-YD04-P0ZEN-152006 | 2017-09-25 | DHI-TRANSMIT-000723 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78734a2d-db92-4967-b013-99a6d8ef7812 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4240 | T16182-YD04-P0ZEN-152011 | 2017-09-25 | DHI-TRANSMIT-000723 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d417faf9-c24a-4c72-bc72-8e27dae87f3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4241 | T16182-YS01-P0MKY-290013 | 2017-09-25 | DHI-TRANSMIT-000724 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc40f1f5-0bd1-49a9-a245-c97e8cc61882 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4242 | T16182-YD05-P0SAY-163424 | 2017-09-25 | DHI-WTRAN-000753 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0c596c4-4d8e-48ec-90ec-05a8eb1743da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4243 | T16182-YR05-P0SAY-163425 | 2017-09-25 | DHI-WTRAN-000753 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6d3dd14-5726-40b8-966e-1fdcebbb0382 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4244 | T16182-XG07-P0SAC-133502 | 2017-09-25 | DHI-TRANSMIT-000725 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e2f5539-39a3-4e56-8360-69cd2750bf72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4245 | T16182-XH02-P0SAC-133504 | 2017-09-25 | DHI-TRANSMIT-000725 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f72c81b2-b25c-4f4a-8c81-07b216285445 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4246 | T16182-XW03-P0SAC-133501 | 2017-09-25 | DHI-TRANSMIT-000725 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b1a8421-798f-45d7-b66c-6ca6044daefb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4247 | T16182-XW03-P0SAC-133503 | 2017-09-25 | DHI-TRANSMIT-000725 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94af1762-bd9a-4c61-b8f6-28dfa696ac32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4248 | T16182-CC05-P0ZEN-180044 | 2017-09-25 | DHI-WTRAN-000754 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41292e42-22cc-47eb-b1c0-43e22de860b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4249 | T16182-XN00-P0SCA-127525 | 2017-09-25 | DHI-WTRAN-000755 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50cdb010-b19b-42c2-876a-7f3fe3e07e87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4250 | T16182-YT01-P0SCA-127526 | 2017-09-25 | DHI-WTRAN-000755 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c4fd732-183c-4fb9-b75e-4bf9c4a98c40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4251 | T16182-YE00-P0ZEN-152726 | 2017-09-25 | DHI-TRANSMIT-000726 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cb43457-134a-4065-8fb7-e255b9440e54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4252 | T16182-YE00-P0ZEN-152729 | 2017-09-25 | DHI-TRANSMIT-000726 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd5df603-f932-4303-8933-0702a312efd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4253 | T16182-YE00-P0ZEN-152728 | 2017-09-25 | DHI-TRANSMIT-000726 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f023ae8-627c-4f0e-8212-802468fc7b53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4254 | T16182-YE00-P0ZEN-152730 | 2017-09-25 | DHI-TRANSMIT-000726 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dfe41c2-d41f-4116-a963-3f7945864c1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4255 | T16182-YE00-P0ZEN-152727 | 2017-09-25 | DHI-TRANSMIT-000726 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4213ad9b-304f-4824-9a1e-665a234dd117 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4256 | T16182-YE00-P0ZEN-152750 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ed6571d-b2ae-400e-a018-12924253a53f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4257 | T16182-YE00-P0ZEN-152751 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1705f486-dc63-443b-8c58-7a3052b6e632 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4258 | T16182-YE00-P0ZEN-152752 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3a318fa-01f1-42b0-b56e-2f5459838d6c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4259 | T16182-YE00-P0ZEN-152753 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eba01c86-6a4f-447e-95a5-009af07dc916 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4260 | T16182-YE00-P0ZEN-152754 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a1be3d8-bcfe-4920-9fb4-d28bf54cc334 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4261 | T16182-YE00-P0ZEN-152755 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55a9d4d7-eb2e-4922-98c7-a582610e3c01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4262 | T16182-YE00-P0ZEN-152756 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0717688f-92a4-4c39-b838-972339d6fd4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4263 | T16182-YE00-P0ZEN-152757 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acc0e55a-f2b4-4058-915b-7aa01ef31efc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4264 | T16182-YE00-P0ZEN-152758 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53f322da-646f-4bc7-8397-e7861a8f9559 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4265 | T16182-YE00-P0ZEN-152759 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad079973-7693-47e0-be94-4b7f4141bb02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4266 | T16182-YE00-P0ZEN-152760 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3860ddc-0081-4856-9b28-b1b3d9849614 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4267 | T16182-YE00-P0ZEN-152761 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb4ea3f1-6bce-4e46-82fb-75ecefc3192c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4268 | T16182-YE00-P0ZEN-152762 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c81183c9-352d-40f0-8a40-ce7103f69260 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4269 | T16182-YE00-P0ZEN-152763 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5fa8544-378d-424f-91e6-41b782817ace | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4270 | T16182-YE00-P0ZEN-152764 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b7f2454-d025-4cbc-9612-841897468748 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4271 | T16182-YE00-P0ZEN-152765 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25eb9697-2160-4df1-ae20-e12644cbe0d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4272 | T16182-YE00-P0ZEN-152766 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63c9cf82-a91f-4e0b-ac77-aee4f48b0eb3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4273 | T16182-YE00-P0ZEN-152767 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a97f3353-e6ce-4e48-bc4a-24ebf6f04f26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4274 | T16182-YE00-P0ZEN-152768 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c06650b1-283a-4022-8ac7-8aab4c752faf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4275 | T16182-YE00-P0ZEN-152769 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16c9335d-5311-47e9-b5ce-a9c3e34e5721 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4276 | T16182-YE00-P0ZEN-152770 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc54665e-b422-4a20-a89b-6653d10bb193 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4277 | T16182-YE00-P0ZEN-152771 | 2017-09-25 | DHI-TRANSMIT-000727 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=def7ed4a-beb2-4f34-8b6f-75289df60350 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4278 | T16182-YU02-P0BT-151021 | 2017-09-26 | DHI-WTRAN-000756 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4279 | T16182-YU02-P0BT-151026 | 2017-09-26 | DHI-WTRAN-000756 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4280 | T16182-YU02-P0BT-151031 | 2017-09-26 | DHI-WTRAN-000756 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4281 | T16182-XN00-P0LB-122034 | 2017-09-26 | DHI-WTRAN-000757 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9d98a21-2f21-4311-9da7-67ae14fea4be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4282 | T16182-YF00-P0LB-122068 | 2017-09-26 | DHI-WTRAN-000758 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d7bc760-07c8-4505-a307-c137b4d3c434 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4283 | T16182-XV00-P0LB-122039 | 2017-09-26 | DHI-TRANSMIT-000731 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb41232a-d6e9-4bcb-b006-d797cbedcabb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4284 | T16182-YD02-P0ZEN-165519 | 2017-09-26 | DHI-WTRAN-000759 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c580132-fdd1-4d2f-a54f-c5e1c37f4d37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4285 | T16182-YK08-P0MBA-121009 | 2017-09-27 | DHI-TRANSMIT-000732 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38f01be1-d7f9-41e8-9712-e48bd639646b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4286 | T16182-YD00-P8ZEN-125507 | 2017-09-27 | DHI-WTRAN-000760 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84a0fa81-c28d-48f3-bf34-cc13bf3af69c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4287 | T16182-YK10-P8QHA-125202 | 2017-09-27 | DHI-WTRAN-000760 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cc06925-e1b9-4ecd-8506-2899c85075a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4288 | T16182-DP00-P8ZEN-125702 | 2017-09-27 | DHI-WTRAN-000761 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72df0282-8d38-490e-81fd-60230cfca013 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4289 | T16182-DP00-P8ZEN-125734 | 2017-09-27 | DHI-WTRAN-000761 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f9f40ed-9beb-47a2-9efa-63326864307d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4290 | T16182-YF00-P8ZEN-125709 | 2017-09-27 | DHI-WTRAN-000761 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4dd9236-3012-4d64-80bf-01d49ff1feea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4291 | T16182-YF00-P8ZEN-125710 | 2017-09-27 | DHI-WTRAN-000761 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18b55035-a807-4df8-9721-509cbb49260a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4292 | T16182-DP00-P8ZEN-125757 | 2017-09-27 | DHI-WTRAN-000762 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34c0133f-4ef9-444d-b5ac-cac298487121 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4293 | T16182-YD07-P8QHA-125201 | 2017-09-27 | DHI-TRANSMIT-000733 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4901a5e6-09f1-4f4a-9551-e2880e09a721 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4294 | T16182-YK08-P8QHL-125403 | 2017-09-27 | DHI-TRANSMIT-000733 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83f72384-2f15-4ac7-9164-a9684435ad36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4295 | T16182-YT02-P8ZEN-125725 | 2017-09-27 | DHI-TRANSMIT-000734 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41f839ac-1f52-4e18-b372-687bdbb429a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4296 | T16182-XL00-P0STG-130503 | 2017-09-27 | DHI-WTRAN-000763 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55810019-5d82-4ec6-8ee6-42a4fc1209b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4297 | T16182-XW01-P0STG-130501 | 2017-09-27 | DHI-WTRAN-000763 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0242baf4-63d9-4afa-ac75-7e4aabcc4b30 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4298 | T16182-YD00-P0STG-130502 | 2017-09-27 | DHI-WTRAN-000763 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=417de54d-59d4-4d0c-912c-03bf41d22b51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4299 | T16182-YK08-P0PCA-126513 | 2017-09-27 | DHI-WTRAN-000764 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68adccdd-f2cd-465b-8493-d1ce3128ac37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4300 | T16182-YU03-P0BB-150831 | 2017-09-27 | DHI-WTRAN-000765 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15651021-48dc-4025-b789-aa1f9b3c4792 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4301 | T16182-YU03-P0BB-150836 | 2017-09-27 | DHI-WTRAN-000765 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9c6f88c-ccf8-407f-b6c4-6ecc4bb48b43 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4302 | T16182-XA00-P8QHL-125402 | 2017-09-27 | DHI-TRANSMIT-000735 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6abdc80b-7dee-4d29-b9d0-ec508eb4fe49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4303 | T16182-XG02-P8ZEN-125586 | 2017-09-27 | DHI-TRANSMIT-000735 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03866f19-2996-4c42-b098-79e02d07bcbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4304 | T16182-XG02-P8ZEN-125590 | 2017-09-27 | DHI-TRANSMIT-000735 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=179ab055-5050-4413-9d43-acaabd46c5b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4305 | T16182-XS00-P8QHA-125002 | 2017-09-27 | DHI-TRANSMIT-000735 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2d660e5-e12b-4278-81b5-57465690b85b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4306 | T16182-XT00-P8QHB-125152 | 2017-09-27 | DHI-TRANSMIT-000736 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec8de19e-c474-4e13-9c8c-01d79639b5ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4307 | T16182-XT00-P8QHB-125153 | 2017-09-27 | DHI-TRANSMIT-000736 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=299e1536-eaf7-4ac7-b1da-8044eab9aff3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4308 | T16182-CV03-P8ZEN-125601 | 2017-09-27 | DHI-WTRAN-000766 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=809e4a7f-c7a3-4844-be42-ffc7bd1cab69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4309 | T16182-YK09-P0LCB-127011 | 2017-09-27 | DHI-WTRAN-000767 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=708e38b1-9ccf-4846-aba0-202dc01310c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4310 | T16182-YT01-P0LCB-127016 | 2017-09-27 | DHI-WTRAN-000767 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7d96c43-6e2e-4ed8-b85b-b89700b5b974 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4311 | T16182-YR04-P0MAG-123030 | 2017-09-27 | DHI-WTRAN-000768 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a604431-b73b-4ff6-9828-0d356799701e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4312 | T16182-YR02-P0CJN-290014 | 2017-09-27 | DHI-WTRAN-000769 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=042bd575-fce4-4189-8ce6-8da6fcfb7fa0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4313 | T16182-CN00-P0ZEN-110702 | 2017-09-27 | DHI-WTRAN-000770 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3316e7a0-675e-4477-8a9a-55ccdfae230e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4314 | T16182-YK00-P0LD-130216 | 2017-09-27 | DHI-WTRAN-000771 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a6e45eb-13d5-4441-9a2f-49bb46c2da45 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4315 | T16182-VK02-P0ULC-171309 | 2017-09-27 | DHI-TRANSMIT-000737 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef47ced3-df50-4ddf-b5fc-41e632569cd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4316 | T16182-YM01-P0MAG-123025 | 2017-09-27 | DHI-WTRAN-000772 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e6878cc-9764-46a6-956b-37f89eb5274b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4317 | T16182-YU02-P0MAG-123026 | 2017-09-27 | DHI-WTRAN-000772 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2948a869-0541-49e7-92fd-c80a62ffeb09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4318 | T16182-CA03-P1BAT-180512 | 2017-09-27 | DHI-TRANSMIT-000738 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d67d43b4-b980-43d3-aa13-56c232c2540c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4319 | T16182-CA03-P1BAT-180513 | 2017-09-27 | DHI-TRANSMIT-000738 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=564fa637-eac6-4816-bbe0-78a92af5c4f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4320 | T16182-CC00-P8QHA-125101 | 2017-09-27 | DHI-TRANSMIT-000739 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bc41a27-aa3f-4d12-85e3-ae80e44830ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4321 | T16182-XA00-P8QHL-125401 | 2017-09-27 | DHI-TRANSMIT-000739 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25ead8d1-dde6-4b2a-9e37-1330369b8221 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4322 | T16182-CC02-P8QHB-125172 | 2017-09-27 | DHI-WTRAN-000773 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bc7d8b3-51fc-4c9a-9915-af8ee3d6878c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4323 | T16182-CV03-P8ZEN-125607 | 2017-09-27 | DHI-WTRAN-000773 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0783e154-1c14-4dc8-8411-d906f0774aea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4324 | T16182-CV03-P8ZEN-125610 | 2017-09-27 | DHI-WTRAN-000773 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06fd739f-5f96-4a85-9d1f-e2a027cd774a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4325 | T16182-CC08-P8ZEN-125617 | 2017-09-27 | DHI-WTRAN-000774 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2333492-65a1-420b-af3f-d28f8d087869 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4326 | T16182-DE00-P0PCA-126519 | 2017-09-27 | DHI-WTRAN-000775 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c186bce-74b1-4011-8939-583872e8abe5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4327 | T16182-XB02-P0UEG-171502 | 2017-09-27 | DHI-TRANSMIT-000740 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc83287e-4d7d-4334-9614-05002753056e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4328 | T16182-XB02-P0UEG-171504 | 2017-09-27 | DHI-TRANSMIT-000740 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3cf639d-f8b5-4d89-afef-53b6fde15e04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4329 | T16182-YU02-P0SCA-127510 | 2017-09-27 | DHI-WTRAN-000776 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=546471aa-76f1-48d2-a630-d84c22d9068d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4330 | T16182-YB03-P0ZEN-165547 | 2017-09-27 | DHI-WTRAN-000777 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=103930a6-e507-42a8-89f5-315c604111a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4331 | T16182-YD02-P0ZEN-165516 | 2017-09-27 | DHI-WTRAN-000777 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf5b70b4-42bc-4e9b-bdb3-884c0889d4b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4332 | T16182-YU03-P0BAC-150731 | 2017-09-27 | DHI-TRANSMIT-000741 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da7a7e2e-d225-4331-a585-097aa6a932a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4333 | T16182-YV02-P0SCA-127511 | 2017-09-27 | DHI-WTRAN-000778 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21597183-565a-46d9-9c00-34b3fbe7d300 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4334 | T16182-YE00-P0ZEN-152716 | 2017-09-27 | DHI-WTRAN-000779 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17d591c9-b792-417e-a7f8-fc88d1f9c73b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4335 | T16182-YE00-P0ZEN-152735 | 2017-09-27 | DHI-TRANSMIT-000742 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ac87ac3-69a8-49b7-baaa-f1f123609af4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4336 | T16182-YK00-P0LB-122073 | 2017-09-28 | DHI-WTRAN-000780 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03f1c61a-717b-4bec-a568-7ab3bc2386ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4337 | T16182-YQ01-P8ZEN-125765 | 2017-09-28 | DHI-WTRAN-000781 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8a83320-69e0-4e53-b7b1-5a55bcfb7c21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4338 | T16182-XS01-P8ZEN-125700 | 2017-09-28 | DHI-WTRAN-000782 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d3646f4-431f-4afe-97e5-b551a98bb543 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4339 | T16182-YF02-P8ZEN-125701 | 2017-09-28 | DHI-WTRAN-000782 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a038a9a4-192f-4d18-ae9c-3a493ca6b385 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4340 | T16182-CC05-P8QHB-125161 | 2017-09-28 | DHI-WTRAN-000783 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e3fbcd2-b9e4-49fc-8739-9d1ef2262aa2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4341 | T16182-DP00-P8ZEN-125737 | 2017-09-28 | DHI-WTRAN-000783 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83bc61b5-0c9c-4789-960e-b7dd57712cda | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4342 | T16182-CV03-P8ZEN-125605 | 2017-09-28 | DHI-TRANSMIT-000743 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98b714a0-c169-4892-8765-351d65e48bc4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4343 | T16182-YE03-P0BAU-152533 | 2017-09-28 | DHI-TRANSMIT-000744 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52ce2df6-bd8e-4be1-ba7f-9cddd2d34c30 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4344 | T16182-YT01-P0BF-150903 | 2017-09-28 | DHI-TRANSMIT-000745 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cef4a0b-8aa2-4a06-8334-84ac90fe8cfe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4345 | T16182-YD00-P0BAA-150761 | 2017-09-28 | DHI-TRANSMIT-000747 | IFC | 0 | DR | TRUE | TRUE | 2017-09-28_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4733721-7bdc-455b-a477-a6413c524b23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4346 | T16182-XH01-P0SGA-136711 | 2017-09-28 | DHI-TRANSMIT-000748 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc48f8b9-c707-4496-a62e-226b12271662 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4347 | T16182-XH01-P0SGE-136712 | 2017-09-28 | DHI-TRANSMIT-000748 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca3d6973-f52b-4e0e-8dde-44bdbf779f79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4348 | T16182-XH01-P0SGK-136713 | 2017-09-28 | DHI-TRANSMIT-000748 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6aa9e9c3-5e9d-4bdf-b162-fe585d6748ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4349 | T16182-YD00-P0MKG-260018 | 2017-09-28 | DHI-TRANSMIT-000749 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47abedb5-4c91-4e5e-8c5e-6cb4312d1d1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4350 | T16182-YT01-P0MAG-123014 | 2017-09-28 | DHI-WTRAN-000784 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db1a07db-58bf-4bce-a9d5-b973f06eaefd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4351 | T16182-XK00-P0MAG-123009 | 2017-09-28 | DHI-WTRAN-000785 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1fa5cec-a2a1-4d34-ae67-c15d9f09d055 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4352 | T16182-YL00-P0MAG-123031 | 2017-09-28 | DHI-WTRAN-000786 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04b2cbc6-e4a6-43e9-8e83-6977fdccbc4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4353 | T16182-YE00-P0CJN-290005 | 2017-09-28 | DHI-WTRAN-000787 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c240cf4a-872d-452e-b5b1-67b248954ec7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4354 | T16182-CA05-P0UST-182083 | 2017-09-28 | DHI-TRANSMIT-000750 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4c4e0f8-4f20-4809-8c16-f19370de2671 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4355 | T16182-CA05-P0UYC-182981 | 2017-09-28 | DHI-TRANSMIT-000751 | IFC | 1 | R | TRUE | TRUE | 2017-09-28_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11201ed0-329d-4b50-a253-c5a4f10468e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4356 | T16182-CA05-P0UYC-182982 | 2017-09-28 | DHI-TRANSMIT-000751 | IFC | 1 | R | TRUE | TRUE | 2017-09-28_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a2c1646-f4eb-41ec-a25a-0c77a349187c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4357 | T16182-CA05-P0UYC-182983 | 2017-09-28 | DHI-TRANSMIT-000751 | IFC | 1 | R | TRUE | TRUE | 2017-09-28_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba337736-cdc3-4687-aea1-345b7411c222 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4358 | T16182-YF00-P8ZEN-125711 | 2017-09-28 | DHI-WTRAN-000788 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad272792-a1d7-47da-8465-3e0179acce5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4359 | T16182-YF00-P8ZEN-125724 | 2017-09-28 | DHI-WTRAN-000788 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99d25ea0-2f71-4597-b5de-391bdf763799 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4360 | T16182-YT01-P0LAC-126009 | 2017-09-28 | DHI-WTRAN-000789 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c0d9228-de0c-49b3-b547-ee4214406eaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4361 | T16182-YT01-P0LAC-126059 | 2017-09-28 | DHI-WTRAN-000789 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca04000b-3a91-441c-9193-1db397bc82a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4362 | T16182-XH01-P0LB-122024 | 2017-09-28 | DHI-WTRAN-000790 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0828bf4-145b-4856-a95a-d1e7df953fa8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4363 | T16182-YQ08-P0CY-154031 | 2017-09-28 | DHI-TRANSMIT-000753 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=074fdb1c-3c84-465c-acc8-432e0e98357e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4364 | T16182-YQ08-P0CY-154038 | 2017-09-28 | DHI-TRANSMIT-000753 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b8ee754-9a43-46fd-8f20-eee45c96f89a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4365 | T16182-YQ08-P0CY-154049 | 2017-09-28 | DHI-TRANSMIT-000753 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df9e3706-464f-4cf8-9c62-38c0a81acded | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4366 | T16182-VL00-P7MPA-220002 | 2017-09-28 | DHI-WTRAN-000791 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48c9a973-7e6f-4189-91c3-bdd9adba65e6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4367 | T16182-YD00-P0BAA-150766 | 2017-09-28 | DHI-WTRAN-000792 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c173e26a-6c80-44b2-8d7e-aae49f450c93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4368 | T16182-YD00-P0BAA-150781 | 2017-09-28 | DHI-WTRAN-000792 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24918e2c-b866-40c5-b2be-93d4045667a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4369 | T16182-CA00-P0UBA-181203 | 2017-09-28 | DHI-TRANSMIT-000754 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6b5f731-41cf-4e06-8d51-e094516a0605 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4370 | T16182-CA00-P0UBA-181205 | 2017-09-28 | DHI-TRANSMIT-000754 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2604293d-db19-4f82-b19f-c36d31a1afa3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4371 | T16182-CA01-P0UBA-181253 | 2017-09-28 | DHI-TRANSMIT-000754 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e277b1a7-b778-44a8-98df-25372c693191 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4372 | T16182-VE04-P0UAG-172101 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c72639f-142e-466d-a05e-eca8a34b9e1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4373 | T16182-VE04-P0UAG-172151 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab7f171a-8a38-4197-b34a-3ebf96849b22 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4374 | T16182-VK02-P0UAG-172109 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=796dc012-cf37-4e99-b4f9-fa14ea494172 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4375 | T16182-VK02-P0UAG-172170 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=526d66ef-be06-4d35-9b1c-842d78727141 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4376 | T16182-XB02-P0UAG-172100 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beae4921-242a-41ff-9d9f-362c893254c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4377 | T16182-XB02-P0UAG-172102 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7136d158-eea4-4689-af17-b173fbc05169 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4378 | T16182-XB02-P0UAG-172108 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3730ae5-c04b-4922-90c2-b096d33a3703 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4379 | T16182-XB02-P0UAG-172162 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bb92e17-7e6d-4fce-9c72-c042ea7ea0ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4380 | T16182-XB02-P0UAG-172168 | 2017-09-28 | DHI-TRANSMIT-000755 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a87d4b6-8dbf-4a37-b15c-4f31846806aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4381 | T16182-XG02-P0MKG-260034 | 2017-09-28 | DHI-TRANSMIT-000756 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bde7321-eb70-4f0e-9829-1577cbb1d683 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4382 | T16182-XG02-P0MKW-260033 | 2017-09-28 | DHI-TRANSMIT-000756 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=538be246-d4df-49d6-a8b4-986b8ef2458f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4383 | T16182-YD16-P0SCA-127546 | 2017-09-28 | DHI-WTRAN-000793 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad575d7b-ffcb-4959-9f78-4a5d8899d478 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4384 | T16182-YD00-P0BF-150939 | 2017-09-29 | DHI-WTRAN-000794 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4385 | T16182-YD00-P0BF-150940 | 2017-09-29 | DHI-WTRAN-000794 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4386 | T16182-XG02-P0LCB-127032 | 2017-09-29 | DHI-WTRAN-000795 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4387 | T16182-YT01-P0BF-150902 | 2017-09-29 | DHI-WTRAN-000796 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4388 | T16182-YD00-P0CWQ-161401 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac051cc8-82ed-42c2-b185-36d883c6d03d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4389 | T16182-YD00-P0CWQ-161402 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f01e65e-29f5-4003-91e7-3a363b9cea01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4390 | T16182-YD00-P0CWQ-161403 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7106715-f527-4d79-9065-ee6ce0b17a46 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4391 | T16182-YD00-P0CWQ-161404 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d958bb0d-d475-4f56-9d75-69d0b4603ace | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4392 | T16182-YD00-P0CWQ-161405 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dcb06be5-1990-432a-8043-7dfef1a9a7b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4393 | T16182-YD00-P0CWQ-161406 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5f3d9f2-b6dd-42af-87b0-1caee1d04ed3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4394 | T16182-YD00-P0CWQ-161407 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ffcc5df-ca24-4cfe-845e-4ddc98e85f04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4395 | T16182-YD00-P0CWQ-161408 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5261c46-aa6c-4538-ba6b-d1db66e388f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4396 | T16182-YD00-P0CWQ-161409 | 2017-09-29 | DHI-TRANSMIT-000759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21d29b9a-033f-4eed-ae24-9e25540efeb9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4397 | T16182-YT10-P0ZEN-150313 | 2017-09-29 | DHI-WTRAN-000797 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b943469-ee11-4fb4-a195-84ccb819ad16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4398 | T16182-XH01-P0GCF-130013 | 2017-09-29 | DHI-TRANSMIT-000760 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da58087f-17d0-4751-8328-e38f31709e88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4399 | T16182-DP00-P8ZEN-125754 | 2017-09-29 | DHI-WTRAN-000798 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6e59ee0-ac7f-44f2-b0a2-8a237b957240 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4400 | T16182-YU02-P8ZEN-125755 | 2017-09-29 | DHI-WTRAN-000798 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a5e4f6a-bec9-4533-a237-2b11d3d13737 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4401 | T16182-YU03-P8ZEN-125756 | 2017-09-29 | DHI-WTRAN-000798 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c688e116-24b4-4a2f-8e33-6a9cbc4e6d5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4402 | T16182-YT02-P8ZEN-125727 | 2017-09-29 | DHI-WTRAN-000799 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ca9f805-b08f-445c-a0bc-cdaf8be10e2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4403 | T16182-YT02-P8ZEN-125715 | 2017-09-29 | DHI-TRANSMIT-000761 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdfe9cd9-3e3c-446b-ab4f-3988058b4c2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4404 | T16182-YT02-P8ZEN-125716 | 2017-09-29 | DHI-TRANSMIT-000761 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e75c03a2-65e4-442b-bdcc-fa9cf6877176 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4405 | T16182-XG01-P6MAA-220089 | 2017-09-29 | DHI-WTRAN-000800 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb5bb094-2d3c-4d38-a09d-adcdf533fa99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4406 | T16182-XS01-P6MAA-220093 | 2017-09-29 | DHI-WTRAN-000801 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d01c58ee-665d-4683-8405-255526bf08dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4407 | T16182-YL13-P6MAA-220095 | 2017-09-29 | DHI-WTRAN-000801 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03c449c7-ac1e-448f-afc5-b99180fcd015 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4408 | T16182-CA05-P0UCB-180681 | 2017-09-29 | DHI-TRANSMIT-000762 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f9d0b15-de74-4fed-8dc9-e0ab5def4688 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4409 | T16182-CA05-P0UCB-180683 | 2017-09-29 | DHI-TRANSMIT-000762 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49960e33-ea64-49bf-9cbd-9dfa8e4d9549 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4410 | T16182-CA05-P0UCB-180686 | 2017-09-29 | DHI-TRANSMIT-000762 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a755a5a2-4ffb-41bf-ad1a-804383913bf4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4411 | T16182-CA05-P0UCB-180687 | 2017-09-29 | DHI-TRANSMIT-000762 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6d7d6bc-b066-4df4-9cd6-2a0ba8da70df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4412 | T16182-CA05-P0UMA-180481 | 2017-09-29 | DHI-TRANSMIT-000763 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca7d4488-e43d-4327-9e24-c9985b675220 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4413 | T16182-YE01-P0BAU-152621 | 2017-09-29 | DHI-WTRAN-000802 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89749758-f92a-43f3-9cc2-127b9b24d9ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4414 | T16182-YE03-P0BAU-152539 | 2017-09-29 | DHI-WTRAN-000802 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ffce0c1-e27e-434d-bb89-a2e1c470c9da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4415 | T16182-YE03-P0BAU-152535 | 2017-09-29 | DHI-TRANSMIT-000764 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a98fdaf4-00db-4ff6-8e9f-caf6e0435163 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4416 | T16182-XS00-P0QJA-110500 | 2017-09-29 | DHI-TRANSMIT-000765 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=406de9b0-bf75-4fe3-b330-909126a849a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4417 | T16182-YK08-P0QJA-110501 | 2017-09-29 | DHI-TRANSMIT-000765 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b486ceb-b974-401a-9fb6-446b59e6ef78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4418 | T16182-YD00-P0QJA-110502 | 2017-09-29 | DHI-TRANSMIT-000765 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40a69b71-de76-4411-b407-04db26891e84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4419 | T16182-YT01-P0QJA-110503 | 2017-09-29 | DHI-TRANSMIT-000765 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9a16474-974f-4cd5-a412-b5b55bdff423 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4420 | T16182-YT10-P0ZEN-150306 | 2017-09-29 | DHI-TRANSMIT-000766 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d921958-cf37-4b54-affe-e52dabcc56af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4421 | T16182-YT10-P0ZEN-150311 | 2017-09-29 | DHI-WTRAN-000803 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae258baf-6cd4-47c6-98ad-05cb52e3e4ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4422 | T16182-YT10-P0ZEN-150314 | 2017-09-29 | DHI-WTRAN-000803 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d253fafb-57c4-43f7-85b6-8741830a1a5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4423 | T16182-YD02-P0ZEN-165521 | 2017-09-29 | DHI-WTRAN-000804 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c0ae949-91f0-4117-bf0b-8d93bcec60aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4424 | T16182-YB03-P8ZEN-125761 | 2017-09-29 | DHI-WTRAN-000805 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd1f3d91-4379-48d4-9752-af4ab1b09d34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4425 | T16182-YL16-P8ZEN-125760 | 2017-09-29 | DHI-WTRAN-000805 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ab36ead-a285-42d4-a9cd-63b356540cda | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4426 | T16182-YK00-P8ZEN-125720 | 2017-09-29 | DHI-WTRAN-000806 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=560e58a1-3bad-4349-9918-3d3c50f1a908 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4427 | T16182-CA01-P0UCB-180655 | 2017-09-29 | DHI-TRANSMIT-000767 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88b4ec4a-b261-4481-a715-3097123585b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4428 | T16182-XS00-P0QU-130401 | 2017-09-29 | DHI-WTRAN-000807 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a8cdf1a-d15d-49d3-9c40-137ab90ee961 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4429 | T16182-YD00-P0QU-130402 | 2017-09-29 | DHI-WTRAN-000807 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fa670d4-a7ee-4a54-b295-28f60af21c73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4430 | T16182-XG02-P0QU-130403 | 2017-09-29 | DHI-WTRAN-000807 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2aa340e4-689b-4238-ad52-e6abb9699e1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4431 | T16182-YE03-P0BAU-152525 | 2017-09-29 | DHI-TRANSMIT-000768 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46e52dd1-d6e4-4a4c-b46a-0d0c27436585 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4432 | T16182-YF02-P0GCF-130011 | 2017-09-29 | DHI-WTRAN-000808 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7e8f5d8-3cf5-4ad7-b373-7b0ac2b8168a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4433 | T16182-XH01-P0ZEN-140020 | 2017-09-29 | DHI-WTRAN-000809 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8c2d14d-7492-4253-b78b-e1ccd055b11b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4434 | T16182-XH01-P0ZEN-140062 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31db844a-077e-4bce-ad8c-780a396c24fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4435 | T16182-XH01-P0UTF-140063 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c6c5903-a04a-48a5-8389-f4fa67494c91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4436 | T16182-XH01-P0GRK-140064 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdf05a0d-c0a2-45d0-9afd-7b5cc7a8c529 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4437 | T16182-XH01-P0UGD-140065 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9a938b2-b36f-4b35-99f5-93c0e7232ad7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4438 | T16182-XH01-P0UGA-140066 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95f14c67-5e9d-4091-aa7c-ab0318d9fbf2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4439 | T16182-XH01-P0UGA-140067 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb427c9d-91b1-4916-be4b-580caa0d3692 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4440 | T16182-XH01-P0UCB-140068 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ea7c56c-9621-4580-9996-079d4cbfedf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4441 | T16182-XH01-P0LCA-140069 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ea9b852-83ed-45c5-b552-d50219db768b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4442 | T16182-XH01-P0LCA-140070 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20c1235d-9ea8-42d4-9331-4055b5930aee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4443 | T16182-XH01-P0LDK-140071 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8010a2cb-0752-4126-af68-7da68ea2a1a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4444 | T16182-XH01-P0LDK-140072 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de437565-73e9-48c0-9e42-f4a00196322a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4445 | T16182-XH01-P0EKG-140073 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67638239-52e8-4477-a280-f3332ed2df95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4446 | T16182-XH01-P0ZEN-140081 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26ea104b-1bed-4963-afa1-0b4b83c3854a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4447 | T16182-XH01-P0ZEN-140082 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4aaeab5d-2572-43d7-ab10-bf25df758f9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4448 | T16182-XH01-P0ZEN-140083 | 2017-09-29 | DHI-WTRAN-000810 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb5bc475-8537-4284-bbc4-e88ebc55ed06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4449 | T16182-XJ00-P0LBA-140101 | 2017-09-29 | DHI-WTRAN-000811 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b78679a-fb5e-4870-8053-ea0a9bf2af8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4450 | T16182-XJ00-P0LBC-140102 | 2017-09-29 | DHI-WTRAN-000811 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8adce15b-24e3-4d33-bb06-5b2e362acfd7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4451 | T16182-XJ00-P0LBG-140103 | 2017-09-29 | DHI-WTRAN-000811 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b59e6e39-d5b8-4a68-b5ed-57dd1650160e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4452 | T16182-XJ00-P0PDA-140114 | 2017-09-29 | DHI-WTRAN-000811 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=440cc01d-9291-4a04-96f4-ee17e8f6ff21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4453 | T16182-XG07-P0SAL-134002 | 2017-09-29 | DHI-WTRAN-000812 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91576eb9-17e1-4b29-910a-820fcde994c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4454 | T16182-XH02-P0SAL-134004 | 2017-09-29 | DHI-WTRAN-000812 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba047e33-5057-457c-b43f-df4cc60d4ca0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4455 | T16182-XW03-P0SAL-134001 | 2017-09-29 | DHI-WTRAN-000812 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e68ae422-668b-431a-807b-22dbd040e88b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4456 | T16182-XW03-P0SAL-134003 | 2017-09-29 | DHI-WTRAN-000812 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65c2b858-2c4c-4cbf-b288-52933a43c60b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4457 | T16182-YD00-P0CRN-161113 | 2017-09-29 | DHI-TRANSMIT-000769 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=935b1fc7-5a3f-42f0-a584-b4115bc112b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4458 | T16182-YL16-P0CRN-161115 | 2017-09-29 | DHI-TRANSMIT-000769 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0decf847-de7a-408d-93a1-9e258047baf0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4459 | T16182-YD05-P0CRN-161116 | 2017-09-29 | DHI-WTRAN-000813 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb91c442-1cb9-4185-aa03-06f17615bc0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4460 | T16182-YF00-P0MJ-110511 | 2017-09-29 | DHI-TRANSMIT-000770 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf430e13-983f-494f-bcdb-f4a28b45e482 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4461 | T16182-YK00-P0LCB-127015 | 2017-09-29 | DHI-WTRAN-000814 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9ecb1e8-694e-4209-bcfd-a0fa5cc8568a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4462 | T16182-XG02-P0LCB-127002 | 2017-09-29 | DHI-WTRAN-000815 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=199cf054-b014-413e-bbca-b1c57a4d0141 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4463 | T16182-YL22-P0LCB-127018 | 2017-09-29 | DHI-WTRAN-000815 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b54da4af-4b2e-4f6e-8450-37d27eccfc1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4464 | T16182-YL22-P0LCB-127042 | 2017-09-29 | DHI-WTRAN-000815 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4428bcfe-dea7-4088-9fe5-5910ed3d0ac0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4465 | T16182-YT01-P0LCB-127007 | 2017-09-29 | DHI-WTRAN-000815 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d30984ac-7c68-4c6c-9035-e46836539bbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4466 | T16182-YD00-P8ZEN-125735 | 2017-09-29 | DHI-WTRAN-000816 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=323431bf-6ff1-4fa3-8a29-d7b864321242 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4467 | T16182-YT02-P8ZEN-125713 | 2017-09-29 | DHI-TRANSMIT-000771 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e86fecb1-ab5b-4787-804c-1db15269f461 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4468 | T16182-YD00-P0MKW-260001 | 2017-09-29 | DHI-WTRAN-000817 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c464e6c2-fbef-4164-aa84-1aee9a859e51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4469 | T16182-YD00-P0MKW-260002 | 2017-09-29 | DHI-WTRAN-000817 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcdbd4f5-0e0d-4f16-b789-ddb7aebed1c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4470 | T16182-YE00-P8ZEN-125751 | 2017-09-29 | DHI-WTRAN-000818 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f841695-f01c-4518-a4df-d1c79aadc3ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4471 | T16182-YE00-P8ZEN-125752 | 2017-09-29 | DHI-WTRAN-000818 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ebcca17-7b6b-4196-ba2f-acc613459370 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4472 | T16182-YB03-P8ZEN-125732 | 2017-09-29 | DHI-WTRAN-000819 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c986db8f-9c75-4e68-b61a-be80c6e2054c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4473 | T16182-YE00-P0LD-130215 | 2017-09-29 | DHI-WTRAN-000820 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c50d35b-0ec8-4e7a-9743-9def348518bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4474 | T16182-YU03-P0LD-130217 | 2017-09-29 | DHI-WTRAN-000820 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb35efd3-419c-4b29-9be0-7e484706daf8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4475 | T16182-XS00-P0PCA-126501 | 2017-09-29 | DHI-WTRAN-000821 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d48ad404-2d6e-4997-8855-fcd679a6f3a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4476 | T16182-XG02-P0LD-130204 | 2017-09-29 | DHI-WTRAN-000822 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4b5fbf2-c587-44d4-8c9f-a98ce25fb15f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4477 | T16182-XG07-P0LD-130203 | 2017-09-29 | DHI-WTRAN-000822 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49d16b71-83bd-40f6-bda4-77941b14b086 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4478 | T16182-YD00-P0LD-130202 | 2017-09-29 | DHI-WTRAN-000822 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98a4df32-16cd-468e-99e3-c82d5068b8f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4479 | T16182-YK09-P0LD-130212 | 2017-09-29 | DHI-WTRAN-000822 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58ef49e7-862b-4499-945d-64ca01117627 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4480 | T16182-XB02-P0UAZ-172608 | 2017-10-10 | DHI-TRANSMIT-000789 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1993e9e8-abc7-48fa-b698-688debdd7c18 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4481 | T16182-XH02-P0SAG-134904 | 2017-10-10 | DHI-TRANSMIT-000790 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ec39723-7c3e-4faa-be83-afb4a1ad7889 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4482 | T16182-XH01-P0SGA-136811 | 2017-10-10 | DHI-TRANSMIT-000791 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67165f82-65d0-4588-b8f8-c665f03385f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4483 | T16182-XH01-P0SGE-136812 | 2017-10-10 | DHI-TRANSMIT-000791 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa49bb70-8f53-4e89-bd28-56164f039d5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4484 | T16182-XH01-P0SGK-136813 | 2017-10-10 | DHI-TRANSMIT-000791 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d6a4089-5499-4bcd-9b5d-55d33f5d6213 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4485 | T16182-YD00-P0MKG-260014 | 2017-10-11 | DHI-TRANSMIT-000797 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b026d9b-f5e5-40a0-95d2-72e7d0f3dce7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4486 | T16182-YD00-P0MKG-260015 | 2017-10-11 | DHI-TRANSMIT-000797 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=499bd59b-9e81-4b6c-836e-f7fe03833b3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4487 | T16182-YD00-P0MKG-260016 | 2017-10-11 | DHI-TRANSMIT-000797 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18d9e7f2-37c8-4449-9e6e-7c77640179a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4488 | T16182-XH01-P0LB-122025 | 2017-10-11 | DHI-WTRAN-000823 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c66fd35-c9b9-4a6b-8d37-c3f283abfbf1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4489 | T16182-YT01-P0SAA-136001 | 2017-10-11 | DHI-WTRAN-000824 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12ae6404-1db1-4c9a-b40b-8db232b7b21b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4490 | T16182-XG01-P0MJ-110509 | 2017-10-11 | DHI-TRANSMIT-000798 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=932f8c66-7d02-4ff4-9792-15971c476dcd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4491 | T16182-YD00-P0MJ-110504 | 2017-10-11 | DHI-TRANSMIT-000798 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2dda35c-d328-44d9-9ffe-873dd7b9a645 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4492 | T16182-YE00-P0MJ-110512 | 2017-10-11 | DHI-TRANSMIT-000799 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33918740-baad-4ba5-8dcd-a326316acbdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4493 | T16182-DP00-P0ZEN-020004 | 2017-10-11 | DHI-TRANSMIT-000800 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5abbad33-5a3d-4a6e-94ac-4c83471ae48e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4494 | T16182-YT01-P0BF-150902 | 2017-10-11 | DHI-TRANSMIT-000801 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3cab71f-b5a8-454f-a35f-274db3c731d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4495 | T16182-YT01-P0CYE-136618 | 2017-10-12 | DHI-TRANSMIT-000809 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cea9d67-4cb2-469e-bbda-f1f6617cf9a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4496 | T16182-YB03-P0CRN-161114 | 2017-10-12 | DHI-TRANSMIT-000810 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ba7bbb7-3a39-4fcf-a48f-2f4b06433129 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4497 | T16182-CA00-P0UYP-183201 | 2017-10-12 | DHI-TRANSMIT-000811 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91e9a7da-7c3a-46da-bda8-fc3ab0dd74b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4498 | T16182-CA00-P0UYP-183203 | 2017-10-12 | DHI-TRANSMIT-000811 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4212bcdd-5c60-4cec-b67b-879d45695724 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4499 | T16182-CA00-P0UYP-183204 | 2017-10-12 | DHI-TRANSMIT-000811 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a06580e-c3df-4ed5-a4b7-150aaa69eb43 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4500 | T16182-CA01-P0UYP-183252 | 2017-10-12 | DHI-TRANSMIT-000811 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb2cee6d-75c6-4495-92cf-358df95058ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4501 | T16182-CA01-P0UYP-183255 | 2017-10-12 | DHI-TRANSMIT-000811 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46bda2fb-495f-41f9-9fc9-61ee396d85b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4502 | T16182-CA02-P0UYP-183256 | 2017-10-12 | DHI-TRANSMIT-000811 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8927c979-32df-4a2a-8281-0e7be60fef52 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4503 | T16182-CA00-P0UCB-180601 | 2017-10-12 | DHI-TRANSMIT-000812 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93567681-cb59-4e5a-8673-1fc4f6ab0355 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4504 | T16182-CA00-P0UCB-180603 | 2017-10-12 | DHI-TRANSMIT-000812 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a9c8e42-0c5c-4efe-a52b-efdcabbac315 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4505 | T16182-CA00-P0UCB-180612 | 2017-10-12 | DHI-TRANSMIT-000812 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a88d803b-9a84-4114-9278-13a2ebc2b528 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4506 | T16182-YB03-P0ZEN-152052 | 2017-10-12 | DHI-WTRAN-000825 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5dd7e251-a677-4531-8b95-dfa93934906f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4507 | T16182-YT10-P0ZEN-150312 | 2017-10-12 | DHI-WTRAN-000825 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c646a3fe-8c06-4bb3-8cd8-3a81e5f62eb6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4508 | T16182-VE04-P0ULX-171601 | 2017-10-12 | DHI-WTRAN-000826 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b244af82-4b61-414d-be3f-9b86a51bf89b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4509 | T16182-VK02-P0ULX-171604 | 2017-10-12 | DHI-WTRAN-000826 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=234f09d8-95d1-48d6-bfc9-b006585bf05d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4510 | T16182-XB02-P0ULX-171602 | 2017-10-12 | DHI-WTRAN-000826 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=196eeb6c-8526-4920-9160-75aa883bb6a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4511 | T16182-XB02-P0ULX-171603 | 2017-10-12 | DHI-WTRAN-000826 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ac9a623-3849-442c-96ab-520d864b59d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4512 | T16182-YT01-P0LB-122102 | 2017-10-12 | DHI-WTRAN-000827 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ab7d8ef-d140-49b8-9749-33ccde56cf4b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4513 | T16182-YD00-P0BAA-150781 | 2017-10-13 | DHI-WTRAN-000828 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4514 | T16182-YD00-P0BAA-150781 | 2017-10-13 | DHI-WTRAN-000828 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4515 | T16182-YK10-P0EKG-124005 | 2017-10-13 | DHI-TRANSMIT-000813 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7679d626-62f1-438a-a3ff-2eebde272464 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4516 | T16182-YK10-P0EKG-124010 | 2017-10-13 | DHI-TRANSMIT-000813 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d2960b0-1a64-416c-93c1-4fb8eb599a3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4517 | T16182-CA00-P6BAT-181811 | 2017-10-13 | DHI-TRANSMIT-000814 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1f41b65-cb0b-4a08-928a-49d89131e17f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4518 | T16182-CA03-P6BAT-181812 | 2017-10-13 | DHI-TRANSMIT-000814 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3466e994-8908-437a-9227-6823c7352581 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4519 | T16182-CA03-P6BAT-181813 | 2017-10-13 | DHI-TRANSMIT-000814 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6429be14-5b93-4e2f-a037-de2a51584a66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4520 | T16182-CA06-P0BAT-181800 | 2017-10-13 | DHI-TRANSMIT-000814 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98ed802c-1394-4863-b7d3-57946c5683a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4521 | T16182-YK00-P0LCB-127041 | 2017-10-13 | DHI-WTRAN-000829 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e131caee-7fe8-43ae-8567-c6fb0acc5f61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4525 | T16182-YK09-P0GHC-129053 | 2017-10-13 | DHI-WTRAN-000830 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=863a15c0-1312-422b-9777-b2421e5f6731 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4526 | T16182-YL22-P0GHC-129056 | 2017-10-13 | DHI-WTRAN-000830 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1048cee7-ac94-4ef9-b981-f5e444f50aa6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4527 | T16182-YM01-P0GHC-129060 | 2017-10-13 | DHI-WTRAN-000830 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=538e8e66-142d-4423-ad30-e9cd849071f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4529 | T16182-YT01-P0BAA-150752 | 2017-10-13 | DHI-TRANSMIT-000816 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9edae82a-4370-40be-8d00-706f52970812 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4530 | T16182-YF00-P0PCA-126522 | 2017-10-13 | DHI-WTRAN-000831 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19bfcbd9-0796-4f2c-9fcc-983d4c0e980d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4531 | T16182-VE04-P0UBN-172201 | 2017-10-13 | DHI-TRANSMIT-000817 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cbfa15b-c9f6-4559-a122-57ae84974ff2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4532 | T16182-XB02-P0UBN-172202 | 2017-10-13 | DHI-TRANSMIT-000817 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=feb3aa1a-df59-4e98-b45b-51a2d37ce1ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4533 | T16182-VK02-P0UBN-172203 | 2017-10-13 | DHI-TRANSMIT-000817 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1838771-aa6f-491f-ae9f-460b79dca883 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4534 | T16182-YR02-P0CJN-290014 | 2017-10-13 | DHI-TRANSMIT-000818 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ed56e6d-a965-424f-a96c-91f48caef22b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4535 | T16182-CA01-P0UMA-180454 | 2017-10-13 | DHI-TRANSMIT-000819 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cd420b0-9ab5-4f44-ba2b-0be937a339a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4536 | T16182-VE04-P0BAA-172401 | 2017-10-13 | DHI-TRANSMIT-000820 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=269bc3b6-7709-4a8e-a6b7-e5b636649b74 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4537 | T16182-XB02-P0BAA-172402 | 2017-10-13 | DHI-TRANSMIT-000820 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ee112f5-791e-4dae-b870-4ed5d0a22fef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4538 | T16182-VK02-P0BAA-172403 | 2017-10-13 | DHI-TRANSMIT-000820 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc63f12c-5428-4f2f-aed7-82643f678a9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4541 | T16182-VN03-P0LB-122015 | 2017-10-13 | DHI-TRANSMIT-000822 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4df06a91-6638-4ac2-9443-6c47bdc45afc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4542 | T16182-CA00-P0UCB-180606 | 2017-10-13 | DHI-TRANSMIT-000823 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=088ffa7c-9939-474b-97fa-6f97ca45ba4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4543 | T16182-CA00-P0UCB-180610 | 2017-10-13 | DHI-TRANSMIT-000823 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63015f39-e155-4751-8dc3-30168d8262e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4545 | T16182-CA00-P0GEN-185701 | 2017-10-13 | DHI-WTRAN-000832 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee3aa8ff-ee2d-4a5d-88bc-8983e739491c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4546 | T16182-CA01-P0GEN-185751 | 2017-10-13 | DHI-WTRAN-000832 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=617ff2fb-ba1c-4966-8ecb-08470395c89d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4547 | T16182-VE04-P0GQB-173401 | 2017-10-13 | DHI-TRANSMIT-000825 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bef11a2f-5f2b-40ca-a4f9-ba2144b36984 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4548 | T16182-UT01-P0GQB-173402 | 2017-10-13 | DHI-TRANSMIT-000825 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1057d73c-4c4a-4af2-aa2b-6e7f5cee3fcc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4549 | T16182-UT01-P0GQB-173403 | 2017-10-13 | DHI-TRANSMIT-000825 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78f8c165-821e-4947-9e14-83b352a0b66a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4550 | T16182-UT01-P0GQB-173413 | 2017-10-13 | DHI-TRANSMIT-000825 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bee79b81-fbfc-4bdc-b4b7-086cb7360607 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4551 | T16182-VK02-P0GQB-173417 | 2017-10-13 | DHI-TRANSMIT-000825 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f23c7e3f-66b5-439d-95b2-584a6a002265 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4552 | T16182-YR05-P0CJN-290002 | 2017-10-13 | DHI-TRANSMIT-000826 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4eb288e-c624-4f1c-930a-ece79ff7e912 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4553 | T16182-YT02-P0PCA-126529 | 2017-10-13 | DHI-WTRAN-000833 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed8cdd84-50b9-4be7-9c4e-d5be3b9eb153 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4554 | T16182-XG02-P0SGC-138201 | 2017-10-13 | DHI-TRANSMIT-000827 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1e424e9-66b7-481a-92c8-ad2592b4f524 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4555 | T16182-XH01-P0SGC-138211 | 2017-10-13 | DHI-TRANSMIT-000827 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db25c6a4-f633-46a5-b04d-30d9cd5257aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4556 | T16182-YT10-P0SGC-138221 | 2017-10-13 | DHI-TRANSMIT-000827 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89e4900c-1c1f-4cff-824c-a340e3a85c76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4557 | T16182-XG02-P0SGC-138301 | 2017-10-13 | DHI-TRANSMIT-000827 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4edb27d3-df8c-4d5a-9758-81c81cd40589 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4558 | T16182-XH01-P0SGC-138311 | 2017-10-13 | DHI-TRANSMIT-000827 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60a54100-cfd4-48a5-9d40-f1d60a78d4e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4559 | T16182-YT10-P0SGC-138321 | 2017-10-13 | DHI-TRANSMIT-000827 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=128e195f-2a96-4a81-89a0-76a373e1d24f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4560 | T16182-YD00-P0CYE-138241 | 2017-10-13 | DHI-TRANSMIT-000828 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c30bbda9-bc59-4779-9a72-19a8df488d63 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4561 | T16182-YU02-P0CYE-138242 | 2017-10-13 | DHI-TRANSMIT-000828 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81650692-be49-4e55-9125-a2918543ced5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4562 | T16182-CA03-P0ULA-182153 | 2017-10-13 | DHI-TRANSMIT-000829 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=599a459f-53ea-442b-bb91-b445b1bc24f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4522 | T16182-YT01-P0LCB-127037 | 2017-10-16 | DHI-WTRAN-000835 | IFI | 1 | DR | TRUE | TRUE | 2017-10-16_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2601a4e8-6fa7-4a76-9a20-5550d51e29d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4523 | T16182-YT01-P0GHC-129050 | 2017-10-16 | DHI-WTRAN-000834 | IFI | 0 | D | TRUE | FALSE | 2017-10-16_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb1d5a68-badc-477c-bd8a-2e9e42352fbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4524 | T16182-YD00-P0GHC-129051 | 2017-10-16 | DHI-WTRAN-000834 | IFI | 0 | D | TRUE | FALSE | 2017-10-16_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1613583f-2041-4289-9bc8-2c1373fc534d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4528 | T16182-YD00-P0PCA-126503 | 2017-10-16 | DHI-TRANSMIT-000832 | IFC | 1 | DR | TRUE | TRUE | 2017-10-16_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2674dcd4-740e-4a8a-85a8-1d8b4947582c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4539 | T16182-YT01-P0LB-122051 | 2017-10-16 | DHI-TRANSMIT-000832 | IFC | 0 | DR | TRUE | TRUE | 2017-10-16_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1790d781-602a-40c6-bfa6-5ce12efc4baf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4540 | T16182-YD00-P0LB-122053 | 2017-10-16 | DHI-TRANSMIT-000832 | IFC | 0 | DR | TRUE | TRUE | 2017-10-16_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=547d573b-4f3c-4112-86ed-e505cf98b971 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4544 | T16182-XJ00-P0LBG-140104 | 2017-10-16 | DHI-TRANSMIT-000832 | IFC | 0 | DR | TRUE | TRUE | 2017-10-16_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2662a09-741b-4f96-94c2-ffc12ef8b656 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4563 | T16182-YM02-P0MAG-123029 | 2017-10-16 | DHI-WTRAN-000836 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee2055bb-e666-405b-8a85-882e0e4dad89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4564 | T16182-YT01-P0BB-150801 | 2017-10-16 | DHI-TRANSMIT-000833 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2717ad1a-1e91-45fd-9c10-847b13b47567 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4565 | T16182-DE00-P0ZEN-152823 | 2017-10-16 | DHI-WTRAN-000837 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2768fc5-08c3-4df5-aa6a-4d28fb914e12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4566 | T16182-XG02-P0PCA-126502 | 2017-10-16 | DHI-TRANSMIT-000834 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=937cb6a8-de36-48c1-9d6d-52d5e73e225d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4567 | T16182-YK08-P0PCA-126515 | 2017-10-16 | DHI-WTRAN-000838 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b6740b8-5dbe-48ba-9900-cfa54e4f9203 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4568 | T16182-YD00-P0SMS-128002 | 2017-10-16 | DHI-WTRAN-000839 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b16871e-fb82-4863-891c-0cb9a0415a14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4569 | T16182-YT01-P0SMS-128005 | 2017-10-16 | DHI-WTRAN-000839 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68ddb983-d4b9-4674-b9c2-c7bf5cebb10c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4570 | T16182-CA01-P0ULD-183952 | 2017-10-16 | DHI-TRANSMIT-000835 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32526a1f-874c-4538-8c23-f74bbf55f94d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4571 | T16182-CA02-P0ULD-183955 | 2017-10-16 | DHI-TRANSMIT-000835 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=243551d6-2f6c-4451-b131-339430602873 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4572 | T16182-XW01-P0LB-122046 | 2017-10-16 | DHI-WTRAN-000840 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=359fc71e-6667-49d5-8fa1-f61daf048caa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4573 | T16182-YL01-P0LB-122080 | 2017-10-16 | DHI-WTRAN-000840 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d714f74-4da5-4e75-8351-c7053feebc75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4574 | T16182-YK08-P0PCA-126514 | 2017-10-16 | DHI-TRANSMIT-000836 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ffe88b3-517c-4e20-a1d9-c9aa062cd64d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4575 | T16182-YK00-P0MAG-123037 | 2017-10-16 | DHI-WTRAN-000841 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edc21ca8-2d85-43dc-bba3-acc3fe92a37c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4576 | T16182-YT02-P0MAG-123035 | 2017-10-16 | DHI-WTRAN-000842 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18e4f374-897c-4b9f-9d78-e759e411f68e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4577 | T16182-YQ03-P0LB-122088 | 2017-10-16 | DHI-WTRAN-000843 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d2e7d8e-09c0-479e-a5ea-2c79f402ecb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4578 | T16182-XJ00-P6MKA-260003 | 2017-10-16 | DHI-WTRAN-000844 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b80a187d-2136-4894-90c8-ef190081988c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4579 | T16182-XJ00-P7MKA-260006 | 2017-10-16 | DHI-WTRAN-000844 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df8e3c9f-4708-4f24-9320-b67d5cec2c6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4580 | T16182-XG02-P0MAG-123002 | 2017-10-16 | DHI-TRANSMIT-000837 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=524395c5-a7e6-428c-9284-45f3ea0993e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4581 | T16182-CA00-P0GEN-185801 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24a0873d-f819-481a-b956-acdca688c2f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4582 | T16182-CA00-P0GEN-185802 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d065e63-8b93-4562-bc6c-e8a1618a388d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4583 | T16182-CA00-P0GEN-185803 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=283caf49-cb6d-432d-9d9f-5a78759f5c5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4584 | T16182-CA01-P0GEN-185851 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6c5e46d-1ebd-43ec-85ef-f2c97076e8f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4585 | T16182-CA01-P0GEN-185852 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9f224de-ffbe-40d7-bc48-ac748f044201 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4586 | T16182-CA01-P0GEN-185853 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70bb1c9b-df06-4538-93ba-f5df46922918 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4587 | T16182-CA02-P0GEN-185854 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8031f45-5a86-4e7a-9a1a-1e61db793d69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4588 | T16182-CA06-P0GEN-185800 | 2017-10-16 | DHI-TRANSMIT-000838 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37b4f613-1a69-4f28-aabb-088aa3dbb8c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4589 | T16182-XS00-P0MAG-123005 | 2017-10-16 | DHI-WTRAN-000845 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8647774-04b0-4e3c-a111-74a469b8a450 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4590 | T16182-XS00-P0PCA-126509 | 2017-10-16 | DHI-WTRAN-000846 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2b1eea1-14d7-4493-a97f-c963a599534c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4591 | T16182-YT10-P0SGE-136722 | 2017-10-16 | DHI-TRANSMIT-000839 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86593fe1-e2e5-4ca6-9472-0134bf74734c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4592 | T16182-YT10-P0SGK-136723 | 2017-10-16 | DHI-TRANSMIT-000839 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=417d2422-85c7-42f3-b949-4626d06e588c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4593 | T16182-YT10-P0SGE-136822 | 2017-10-16 | DHI-TRANSMIT-000839 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72509232-ed4b-46a6-b15a-ba41c79a2b49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4594 | T16182-YT10-P0SGK-136823 | 2017-10-16 | DHI-TRANSMIT-000839 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=942a7f7e-1e2c-4362-85d5-f59071da39d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4595 | T16182-YT10-P0ZEN-150305 | 2017-10-16 | DHI-WTRAN-000847 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0fbfac4-2fa2-4176-aa27-750665eb434c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4596 | T16182-YT10-P0ZEN-150311 | 2017-10-16 | DHI-WTRAN-000847 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbca6843-3eaa-4107-878c-8b5f3b6a7c8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4597 | T16182-YT10-P0ZEN-150314 | 2017-10-16 | DHI-WTRAN-000847 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd3407ff-b5e3-444c-a3e3-8dff4f1f6ed2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4598 | T16182-XS00-P0MAG-123004 | 2017-10-18 | DHI-WTRAN-000848 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42e17012-6c73-416c-8881-fb1a200d2f2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4599 | T16182-XK00-P8ZEN-125509 | 2017-10-18 | DHI-WTRAN-000849 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f747df7d-16d7-4cf3-9258-9f57076f5a5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4600 | T16182-YE00-P0ZEN-152719 | 2017-10-18 | DHI-TRANSMIT-000847 | IFC | 1 | DR | TRUE | TRUE | 2017-10-18_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2218aaa-b6c9-43ac-a28b-9b88dfa2bdfd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4601 | T16182-CV03-P0CWQ-161134 | 2017-10-18 | DHI-WTRAN-000850 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c664d3e6-2076-450a-b098-c25f7422d097 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4602 | T16182-YE03-P0LB-122067 | 2017-10-18 | DHI-WTRAN-000851 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c256913e-2d38-4363-9830-263359070e79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4603 | T16182-YF00-P0LB-122066 | 2017-10-18 | DHI-WTRAN-000851 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69946be3-0325-47a9-8991-ffc311b12693 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4604 | T16182-YR05-P0SAY-163425 | 2017-10-18 | DHI-WTRAN-000852 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=640bf1d9-a178-498f-9918-fd92b3618ad1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4605 | T16182-YL16-P0ZEN-165551 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b452f0f5-6790-40e9-952f-bc31387dd334 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4606 | T16182-YL16-P0ZEN-165552 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96abdf95-cfe2-4be8-9e39-78a98a1c0fbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4607 | T16182-YL16-P0ZEN-165553 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24f1bd9a-38dd-416a-b08a-e7d45463b029 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4608 | T16182-YL16-P0ZEN-165554 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ba14bf5-463f-4542-a27b-d3bab23b908d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4609 | T16182-YL16-P0ZEN-165555 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e9f6328-56a4-4dd0-bdc8-d34ab43b7a64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4610 | T16182-YL16-P0ZEN-165556 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aadc802f-75af-4d42-89cf-ce1ef39b49ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4611 | T16182-YL16-P0ZEN-165557 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8cd3120-cbba-486d-943a-c605e16570d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4612 | T16182-YL16-P0ZEN-165558 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad6bac90-4960-4a8b-9c1b-08db94e53653 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4613 | T16182-YL16-P0ZEN-165559 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e04a2ea-3fb8-4089-b780-cfe8fa5071bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4614 | T16182-YL16-P0ZEN-165560 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d55d340-9d23-4d85-925c-3b80bff9d299 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4615 | T16182-YL16-P0ZEN-165561 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aefd24b6-c23d-435f-87ac-b5263c93d907 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4616 | T16182-YL16-P0ZEN-165562 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=441f896f-6831-463b-b52a-ede5c52a2c53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4617 | T16182-YL16-P0ZEN-165563 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0e619da-9a66-48df-9b4c-4497a2cc3ee4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4618 | T16182-YL16-P0ZEN-165564 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f08020a1-5789-44ae-8029-a42b76983068 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4619 | T16182-YL16-P0ZEN-165565 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=903de7dd-0c22-493c-8846-58461c1fa21e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4620 | T16182-YL16-P0ZEN-165566 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6dab40a-5b29-4a6d-a2d9-63384fc54e69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4621 | T16182-YL16-P0ZEN-165567 | 2017-10-18 | DHI-WTRAN-000853 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd02a08a-6f04-4a6e-ba35-82af901fd195 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4622 | T16182-YK09-P0GHC-129003 | 2017-10-18 | DHI-TRANSMIT-000848 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19b9c6ba-6e70-4ea3-b357-9ae000b180e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4623 | T16182-YK09-P0GHC-129033 | 2017-10-18 | DHI-TRANSMIT-000848 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14389079-f31f-4333-ab35-4c3a1b915c61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4624 | T16182-YL16-P0ZEN-152860 | 2017-10-18 | DHI-WTRAN-000854 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a15cb8a5-224b-462d-a95e-a8fe28b55c4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4625 | T16182-YD00-P0CYE-138341 | 2017-10-18 | DHI-TRANSMIT-000849 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bb6c3d3-4773-49d1-842c-a38e3ac3ce3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4626 | T16182-YU02-P0CYE-138342 | 2017-10-18 | DHI-TRANSMIT-000849 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5375606a-41fd-4caa-af12-9fda9d7c342e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4627 | T16182-YD00-P0SMM-128101 | 2017-10-18 | DHI-WTRAN-000855 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19146b45-5930-49e1-b22d-ab7f28f8e71c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4628 | T16182-YD00-P0SML-128103 | 2017-10-18 | DHI-WTRAN-000855 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbe1a3b1-ae8e-4e6e-9a10-dc314cd2b47c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4629 | T16182-YD00-P0SMS-128102 | 2017-10-18 | DHI-WTRAN-000855 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70f0d538-f55d-46b3-b0c9-0b85945cb95d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4630 | T16182-YQ01-P0ZEN-152201 | 2017-10-18 | DHI-TRANSMIT-000850 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bed7127-f687-4e48-8a48-2e409a5b6ba3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4631 | T16182-YK09-P0LCB-127004 | 2017-10-18 | DHI-WTRAN-000856 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1bd02195-dcd7-4d8d-abda-cc73e19025d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4632 | T16182-XW01-P0MAG-123007 | 2017-10-18 | DHI-WTRAN-000857 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b578d02-0a84-4261-9bd5-2f107029234c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4633 | T16182-DP00-P0ZEN-020006 | 2017-10-18 | DHI-WTRAN-000858 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=932c4f48-b065-4d0a-af7a-6aed8556085f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4634 | T16182-YD00-P0EKG-124012 | 2017-10-18 | DHI-WTRAN-000859 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bcecf60-8de1-46dc-ba6b-4598724f75ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4635 | T16182-BX03-P0EKG-124020 | 2017-10-18 | DHI-WTRAN-000859 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a7a6637-52a8-4518-bd3c-3805c19f03c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4636 | T16182-YM01-P0LCB-127010 | 2017-10-19 | DHI-WTRAN-000860 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4643931d-b81f-4c73-b627-0b09872dca9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4637 | T16182-CA03-P0UMA-180463 | 2017-10-19 | DHI-TRANSMIT-000855 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=590d028c-a88f-4aad-89a0-b25ef2978472 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4638 | T16182-CA03-P0UMA-180464 | 2017-10-19 | DHI-TRANSMIT-000855 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69c47ceb-1099-4b8a-9308-27124f3cf441 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4639 | T16182-YT01-P0MKA-260020 | 2017-10-19 | DHI-WTRAN-000861 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3469396f-956e-45e5-8858-b60d67781490 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4640 | T16182-YT10-P0MKY-290010 | 2017-10-19 | DHI-WTRAN-000862 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ffe6bd1-3f43-4d94-835e-79d76d685fdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4641 | T16182-YS01-P0MKY-290011 | 2017-10-19 | DHI-TRANSMIT-000857 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b1564d8-34d4-46a7-847e-dedce4f364df | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4642 | T16182-CA06-P0UGD-186600 | 2017-10-19 | DHI-TRANSMIT-000858 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e028265-a36d-41ed-a82b-a67d98ecf9cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4643 | T16182-CA00-P0UGD-186601 | 2017-10-19 | DHI-TRANSMIT-000858 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abd49f94-8566-455b-8eda-a97d05d3b916 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4644 | T16182-CA00-P0UGD-186602 | 2017-10-19 | DHI-TRANSMIT-000858 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbe9247a-9f79-4986-8f10-aee9a206152a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4645 | T16182-CA01-P0UGD-186651 | 2017-10-19 | DHI-TRANSMIT-000858 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdbcdcd2-d016-4c75-8a0f-2d6a63e25955 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4646 | T16182-CA01-P0UGD-186652 | 2017-10-19 | DHI-TRANSMIT-000858 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7da66770-5e82-44fa-a792-47d453640489 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4647 | T16182-XJ00-P0EKG-140118 | 2017-10-19 | DHI-TRANSMIT-000859 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a88ea48-e3c8-4b85-92ff-9f6db9816e9c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4648 | T16182-XJ00-P0GHC-140113 | 2017-10-19 | DHI-WTRAN-000863 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecf15314-93d7-4a92-8e6d-d6cdbc241868 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4649 | T16182-XJ00-P0GKB-140112 | 2017-10-19 | DHI-WTRAN-000863 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31ac3a42-0665-46fa-b0e5-1f692d23b904 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4650 | T16182-YD00-P0STG-130502 | 2017-10-19 | DHI-WTRAN-000864 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b88b9779-24b1-4367-a7c8-ae35baffe2b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4651 | T16182-XL00-P0STG-130503 | 2017-10-19 | DHI-WTRAN-000864 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b5a3166-2d40-4766-bbae-46efd7f4c784 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4653 | T16182-YE00-P0ZEN-152725 | 2017-10-20 | DHI-WTRAN-000865 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c37006a-3970-47d3-8cf6-671484395247 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4655 | T16182-YL01-P0GCF-130035 | 2017-10-20 | DHI-WTRAN-000867 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8320967-a18b-4001-b3b4-535f4402348c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4656 | T16182-YF02-P8ZEN-125701 | 2017-10-20 | DHI-TRANSMIT-000864 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=134f012d-ce4f-4163-b33b-8fab1c5e8f47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4659 | T16182-YT02-P8ZEN-125727 | 2017-10-20 | DHI-TRANSMIT-000864 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64f63b62-c18b-455b-a701-acf2cbe4e62f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4660 | T16182-DN05-P0SG-136620 | 2017-10-20 | DHI-TRANSMIT-000865 | IFC | 0 | DR | TRUE | TRUE | 2018-04-05_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=868d1020-c7e0-4f3c-990c-42c3cfc3a522 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4661 | T16182-YD00-P0CYE-138041 | 2017-10-20 | DHI-TRANSMIT-000866 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f6a7887-afde-4de5-bd37-373259500e70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4662 | T16182-YU02-P0CYE-138042 | 2017-10-20 | DHI-TRANSMIT-000866 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50205289-cf12-4001-b5ad-008a5e7f6c54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4663 | T16182-XW03-P0SAM-135001 | 2017-10-20 | DHI-TRANSMIT-000867 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f2ab987-7fb1-4424-9ba5-99db0f125ef5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4664 | T16182-XG07-P0SAM-135002 | 2017-10-20 | DHI-TRANSMIT-000867 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38691490-f9e7-438c-9416-530c1d1c59bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4670 | T16182-XB02-P0UAZ-172608 | 2017-10-20 | DHI-TRANSMIT-000869 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37c53ae9-6c36-4bc3-99fb-115ba967e777 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4672 | T16182-XL00-P0LB-122030 | 2017-10-20 | DHI-TRANSMIT-000870 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b3760b9-3430-4b83-be3a-4666da78f74e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4674 | T16182-CA00-P0UST-182001 | 2017-10-20 | DHI-TRANSMIT-000871 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=863ac909-c835-4e9c-8ca1-94f1f3a8acf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4675 | T16182-CA00-P0UST-182002 | 2017-10-20 | DHI-TRANSMIT-000871 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e35e71f-f813-4f9a-9a41-d80dfe7450a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4676 | T16182-CA00-P0UST-182003 | 2017-10-20 | DHI-TRANSMIT-000871 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=719d2615-9a26-4b81-9d51-e96cf370ee91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4684 | T16182-YT01-P0LB-122108 | 2017-10-20 | DHI-WTRAN-000870 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a1ec625-3d50-443d-a826-519feeb77624 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4685 | T16182-YT10-P0ZEN-150304 | 2017-10-20 | DHI-WTRAN-000871 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2bdcff4-19ae-462f-947a-36be4873d668 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4687 | T16182-XJ00-P0EKC-140117 | 2017-10-20 | DHI-WTRAN-000872 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=341e23f8-cb0a-4111-8e01-f61ba5988332 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4688 | T16182-XJ00-P0ZEN-140100 | 2017-10-20 | DHI-WTRAN-000872 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d428d5a-ae99-41a1-aca4-cb63f4b140ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4689 | T16182-YL30-P8ZEN-125514 | 2017-10-20 | DHI-TRANSMIT-000872 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69d3fa0f-e6c9-4d99-ac8c-8ad244580ed1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4690 | T16182-YK10-P8QHA-125308 | 2017-10-20 | DHI-WTRAN-000873 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2c2f102-6131-4d7f-ad96-8257ae1fa84b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4691 | T16182-YD05-P0LB-122059 | 2017-10-20 | DHI-WTRAN-000874 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34ca1494-de28-47c6-8f97-5646cf40480a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4692 | T16182-BP00-P0LBS-140013 | 2017-10-20 | DHI-WTRAN-000875 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c0f89e5-76ab-47c8-9a0d-6a34509ec25a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4654 | T16182-DE00-P0CY-154001 | 2017-10-23 | DHI-WTRAN-000878 | IFR | A | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90447732-2e0e-4eca-97c6-ef57cb644089 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4657 | T16182-DP00-P8ZEN-125702 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 0 | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de29fee2-39c9-4ada-af45-7cf879491c71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4658 | T16182-DP00-P8ZEN-125734 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 0 | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69f277cc-3f49-4be1-a0d2-cd5c0301d78b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4665 | T16182-XW03-P0SAM-135003 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 0 | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b60a0acf-d2ba-4e26-b992-27119f05d041 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4666 | T16182-XH02-P0SAM-135004 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 0 | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60dd9dc2-8ad5-45e8-ba1a-3317f0618233 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4667 | T16182-CA03-P1BAT-180512 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 4 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bf33175-975e-4227-a3b5-78d674753e8c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4668 | T16182-XB02-P0UAZ-172602 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 3 | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8379cebc-bf6c-4c95-9f75-c8db28b8bc39 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4669 | T16182-XB02-P0UAZ-172603 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 3 | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13cd3d2d-8466-4ce9-bbdc-52399b3040be | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4671 | T16182-VK02-P0UAZ-172613 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 3 | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2399755-1e31-470e-a5b5-a64eb7840cd8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4677 | T16182-CA00-P0UST-182004 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 2 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbb346c1-7b14-4e3b-a4a5-cbb7a9088873 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4678 | T16182-CA01-P0UST-182053 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 1 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa31cb32-4d3a-4aec-9df5-04c031f9df93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4679 | T16182-CA03-P0UST-182055 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 1 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1d47f22-d0f9-41de-b239-1a3a31a9a899 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4680 | T16182-CA02-P0UST-182061 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 1 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e4062fe-30eb-45e5-ad83-0e06ab762724 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4681 | T16182-CA03-P0UST-182062 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 1 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ef9a2d0-c30c-4dd7-b012-8b1053ce046e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4682 | T16182-CA03-P0UST-182063 | 2017-10-23 | DHI-TRANSMIT-000873 | IFC | 1 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=864b42e8-4024-41dd-8e09-4de8c5b63b07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4693 | T16182-YT01-P0EKG-124024 | 2017-10-23 | DHI-TRANSMIT-000874 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5a574ea-3cc7-4863-84ac-8514dda67661 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4694 | T16182-YF02-P0LD-130211 | 2017-10-23 | DHI-WTRAN-000876 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0391fb4-37bd-4956-baf0-e0713482fee3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4695 | T16182-YR05-P0LD-130207 | 2017-10-23 | DHI-WTRAN-000876 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b8a4a8d-54ed-4bff-bb2d-813300adf8f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4696 | T16182-YF00-P0LD-130218 | 2017-10-23 | DHI-WTRAN-000876 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74b3ba99-b33b-4551-afe9-16c8f4679115 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4697 | T16182-YK00-P0ZEN-165304 | 2017-10-23 | DHI-TRANSMIT-000875 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19a5a19a-7d50-4bc4-9971-959b7307571b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4698 | T16182-YD02-P0ZEN-165573 | 2017-10-23 | DHI-WTRAN-000877 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d67be86-abfa-4ce2-a4de-bb87697328df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4699 | T16182-CA05-P0UYC-182982 | 2017-10-23 | DHI-TRANSMIT-000876 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ef5997b-1be5-4694-a108-9dc85e0a126f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4700 | T16182-CA05-P0UYC-182983 | 2017-10-23 | DHI-TRANSMIT-000876 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=976afb6a-fc5c-4275-8d38-e93983716561 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4701 | T16182-CA05-P0UYC-182984 | 2017-10-23 | DHI-TRANSMIT-000876 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37081367-17dc-4d4e-8a5e-8f07a2039e27 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4702 | T16182-CA05-P0UYC-182985 | 2017-10-23 | DHI-TRANSMIT-000876 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ab05c8b-99d5-474a-896f-910f707a210a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4652 | T16182-YE00-P0ZEN-152724 | 2017-10-24 | DHI-WTRAN-000882 | IFI | 0 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e14b7923-2c1c-499f-8d40-6460b47e220e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4673 | T16182-YD00-P0LAC-126051 | 2017-10-24 | DHI-WTRAN-000881 | IFR | A | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a94cebc-e274-4686-b8c1-a2c26e057fc8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4683 | T16182-XS00-P0PCA-126504 | 2017-10-24 | DHI-WTRAN-000880 | IFR | C | DR | TRUE | TRUE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a0b8649-5c75-46ca-9a61-6e1191290268 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4686 | T16182-XH01-P0LF-140404 | 2017-10-24 | DHI-WTRAN-000879 | IFI | 0 | D | TRUE | FALSE | 2017-10-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71cd2d20-baea-4616-ba6a-bd92d4efb19c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4703 | T16182-YD00-P0CYE-136841 | 2017-10-24 | DHI-TRANSMIT-000880 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0325eb08-b459-475c-876f-e3569da7d285 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4704 | T16182-YU02-P0CYE-136842 | 2017-10-24 | DHI-TRANSMIT-000880 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c14027b-d379-4c22-ac68-0518b0e8b7ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4705 | T16182-XG02-P6MAA-220027 | 2017-10-24 | DHI-WTRAN-000883 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6e834b4-c7c2-4e8a-beb6-d5eb66019fc4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4706 | T16182-XW03-P8ZEN-125012 | 2017-10-24 | DHI-TRANSMIT-000881 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=662b16a6-28be-493a-896a-c57318a15979 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4707 | T16182-XW03-P8ZEN-125014 | 2017-10-24 | DHI-TRANSMIT-000881 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2f41c52-055e-4314-9b2b-12334db637a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4708 | T16182-CV03-P0ZEN-163331 | 2017-10-24 | DHI-WTRAN-000884 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d35cb7c-7640-4668-a170-4a8184aa6cbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4709 | T16182-YD00-P0MKG-260017 | 2017-10-24 | DHI-WTRAN-000885 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22455624-5aa5-4d55-b493-edf4083c671d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4710 | T16182-YF00-P6MAA-220097 | 2017-10-24 | DHI-WTRAN-000886 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c33f2fe9-a60b-4720-9b3b-227ef789d757 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4711 | T16182-XM00-P0MAA-220015 | 2017-10-24 | DHI-WTRAN-000887 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b57c3177-d329-4e28-a584-2bea56356d4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4712 | T16182-YF00-P0LB-122068 | 2017-10-24 | DHI-WTRAN-000888 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f84739d-3402-4a98-a4d2-33ba32e1fbee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4713 | T16182-XG02-P0LB-122023 | 2017-10-24 | DHI-TRANSMIT-000882 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3238e425-ce41-4af0-b71b-946dd85c4b35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4714 | T16182-XL00-P0LB-122031 | 2017-10-24 | DHI-TRANSMIT-000882 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96a02ff2-7b51-46e4-aebd-a0ab4fbf8137 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4715 | T16182-DE00-P0ZEN-152202 | 2017-10-24 | DHI-TRANSMIT-000883 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9798b945-ce6d-4a5b-abd8-ce2fe4b7ba4e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4716 | T16182-XB02-P0GUB-173302 | 2017-10-24 | DHI-TRANSMIT-000884 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34642a6a-97f2-4f4c-bd14-1e612f67b090 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4717 | T16182-XB02-P0GUB-173303 | 2017-10-24 | DHI-TRANSMIT-000884 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77143195-0f23-4e20-aea0-6eb3ad93b0ca | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4718 | T16182-VK02-P0GUB-173313 | 2017-10-24 | DHI-TRANSMIT-000884 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40d558ee-5a25-4c1c-acbb-fcb2edab51a6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4719 | T16182-XH01-P0LD-130213 | 2017-10-24 | DHI-WTRAN-000889 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1e3ca00-9ce9-4e15-b715-abb165d209de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4720 | T16182-YD00-P0LD-130202 | 2017-10-24 | DHI-TRANSMIT-000885 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=178d34d6-5f59-4323-b108-7e64818d3667 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4721 | T16182-XG07-P0LD-130203 | 2017-10-24 | DHI-TRANSMIT-000885 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7752c79c-75c8-470c-aeb6-b7ddac4bec5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4722 | T16182-CA01-P0UYC-182952 | 2017-10-24 | DHI-TRANSMIT-000886 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=227e8bf0-d544-4292-87ab-a251438d5bf5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4723 | T16182-YK01-P0LB-122074 | 2017-10-25 | DHI-WTRAN-000890 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3b2a310-893f-436e-a59e-83fe77384767 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4724 | T16182-YD00-P0BAA-150762 | 2017-10-25 | DHI-TRANSMIT-000887 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8330ab85-4e0a-4e32-9aa2-f788e4929350 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4725 | T16182-XG02-P0CYE-136744 | 2017-10-25 | DHI-WTRAN-000891 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4566cc41-b2ed-4713-8549-8f51798eda2b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4726 | T16182-YT10-P0CYE-136843 | 2017-10-25 | DHI-WTRAN-000891 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41e8de7d-6bd4-4af6-a053-aee98e208f81 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4727 | T16182-XG02-P0CYE-136844 | 2017-10-25 | DHI-WTRAN-000891 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e404116-35db-400a-9b77-d9722ccaa238 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4728 | T16182-XG02-P0SGK-137902 | 2017-10-25 | DHI-TRANSMIT-000888 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51508e2e-2472-4da6-a798-29d669c00ef5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4729 | T16182-YD00-P0SGZ-137931 | 2017-10-25 | DHI-TRANSMIT-000888 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e315d02c-0a26-494e-984f-1409bddbe5b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4730 | T16182-DE00-P0ZEN-152870 | 2017-10-25 | DHI-WTRAN-000892 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b835a7d-5521-4190-b129-1cdd45ca07be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4731 | T16182-XJ00-P0MBH-140116 | 2017-10-25 | DHI-WTRAN-000893 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c2149ef-2d4a-442e-b7c5-5e2132639344 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4732 | T16182-YU03-P0BB-150831 | 2017-10-26 | DHI-WTRAN-000894 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4733 | T16182-XG02-P0LCB-127032 | 2017-10-26 | DHI-WTRAN-000895 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4734 | T16182-YM01-P0LCB-127010 | 2017-10-26 | DHI-WTRAN-000896 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4735 | T16182-XB02-P0UEG-171502 | 2017-10-26 | DHI-TRANSMIT-000889 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2a61ce7-2883-40ee-a18f-5f00faa9a0f3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4736 | T16182-XB02-P0UEG-171504 | 2017-10-26 | DHI-TRANSMIT-000889 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46d8a2ad-07af-4a5e-91e4-1976581c71cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4737 | T16182-YT01-P0BF-150901 | 2017-10-26 | DHI-WTRAN-000897 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cbd2c79-7d3a-4f76-aef6-b9addc90d1dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4738 | T16182-YQ08-P0CY-154050 | 2017-10-26 | DHI-WTRAN-000898 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e97c11fc-2227-4f2a-819f-03e0e537b6c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4739 | T16182-YU02-P0BT-151021 | 2017-10-27 | DHI-WTRAN-000899 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4740 | T16182-YU02-P0BT-151026 | 2017-10-27 | DHI-WTRAN-000899 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4741 | T16182-YU02-P0BT-151031 | 2017-10-27 | DHI-WTRAN-000899 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4742 | T16182-XS00-P0PCA-126501 | 2017-10-27 | DHI-TRANSMIT-000890 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=020586f8-9699-4f86-b39a-35e101b57cb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4743 | T16182-XN00-P0GNR-130107 | 2017-10-27 | DHI-TRANSMIT-000891 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=485c7d33-a5c0-4a1b-807c-8a6d4a6fcea5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4744 | T16182-YK09-P0GCF-130012 | 2017-10-27 | DHI-TRANSMIT-000891 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe8db790-5548-4314-a00f-4e0fe872753c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4745 | T16182-YF00-P0CBA-161221 | 2017-10-27 | DHI-WTRAN-000900 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad77ef0d-9d4e-4436-88f0-05892ca1027f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4746 | T16182-YF00-P0CGA-161321 | 2017-10-27 | DHI-WTRAN-000900 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c41e288-2d6d-4956-b394-b3f9771935d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4747 | T16182-XG02-P0ZEN-110002 | 2017-10-27 | DHI-TRANSMIT-000892 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84e55af4-f702-4205-b363-dbe4846469d7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4748 | T16182-VE04-P0UMX-171051 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dd7612e-3bd5-438a-8899-5675ac5d201c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4749 | T16182-XB02-P0UMX-171052 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba4e3b94-ac11-4f55-8ce5-191371ad7768 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4750 | T16182-XB02-P0UMX-171053 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1edc2651-a7ed-4bf2-a133-419a98f2f139 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4751 | T16182-XB02-P0UMX-171054 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cca8138-6f19-4d90-b741-37cd83a40df1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4752 | T16182-XB02-P0UMX-171055 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a93cac14-47ef-486b-908e-5d07859d934a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4753 | T16182-XB02-P0UMX-171056 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd214a63-3121-4179-89f0-1b958bb9a8d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4754 | T16182-XB02-P0UMX-171057 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17b5deca-a957-4739-a54d-a389c8c025dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4755 | T16182-XB02-P0UMX-171058 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=759fb935-ddc2-42a6-97c1-b92e250af10a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4756 | T16182-VK02-P0UMX-171059 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4faf3f6-23d7-42d8-9d07-16099a1a25dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4757 | T16182-VK02-P0UMX-171060 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fef8d22-bf70-4027-953c-4d72dcf5f1be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4758 | T16182-XB02-P0UMX-171061 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e762f73-707b-4d52-b13f-06c7d3a354a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4759 | T16182-XB02-P0UMX-171062 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fdeffb4-f19a-4fc1-b5dd-5a23fdbb20f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4760 | T16182-XB02-P0UMX-171063 | 2017-10-30 | DHI-TRANSMIT-000898 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54d35e93-3826-4bea-9e55-fb7df981fcd0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4761 | T16182-YU02-P0MBA-121012 | 2017-10-30 | DHI-WTRAN-000901 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4762 | T16182-YE03-P0BAU-152530 | 2017-10-30 | DHI-TRANSMIT-000899 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92d8f411-3851-41bb-9b7c-f6e5d5edc8ca | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4763 | T16182-YE03-P0BAU-152531 | 2017-10-30 | DHI-TRANSMIT-000899 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2efbbcbc-2251-4d57-b8e3-2caf663368f9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4764 | T16182-YE00-P0ZEN-152709 | 2017-10-30 | DHI-TRANSMIT-000900 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afc61feb-fe56-49e3-ba88-856432f6d8c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4765 | T16182-YT10-P0ZEN-150305 | 2017-10-30 | DHI-TRANSMIT-000901 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=561cbd79-1eeb-424b-9d1b-3aec5051a9fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4766 | T16182-CV03-P8ZEN-125609 | 2017-10-30 | DHI-WTRAN-000902 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8db3ec51-17aa-4ff2-a165-e4e1d7416894 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4767 | T16182-XS00-P0QC-130301 | 2017-10-30 | DHI-TRANSMIT-000902 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5f4e6d1-cc6b-481f-9464-f3364623ef50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4768 | T16182-XG02-P0QC-130303 | 2017-10-30 | DHI-WTRAN-000903 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8be0d417-5f4a-44c2-9dab-6bd2aa64cfb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4769 | T16182-XW03-P0QC-130304 | 2017-10-30 | DHI-WTRAN-000903 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e178971-ed2f-4b49-b4c9-762648b91945 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4770 | T16182-YD00-P0QC-130302 | 2017-10-30 | DHI-WTRAN-000903 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbd5633e-c502-4917-826a-cf81e266eb97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4771 | T16182-VE04-P0GUC-172801 | 2017-10-30 | DHI-TRANSMIT-000903 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0989cca9-0f71-468e-b22e-d61404d5d90b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4772 | T16182-VK02-P0GUC-172804 | 2017-10-30 | DHI-TRANSMIT-000903 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78609c08-6fb8-44bf-b641-ed8fb442f978 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4773 | T16182-XB02-P0GUC-172802 | 2017-10-30 | DHI-TRANSMIT-000903 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea12e9cb-3eb6-45ed-8dbb-ba8ee8b85bdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4774 | T16182-XB02-P0GUC-172803 | 2017-10-30 | DHI-TRANSMIT-000903 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2348fd7f-1e59-469a-9433-f91815ed1aaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4775 | T16182-YD00-P0CYE-137841 | 2017-10-30 | DHI-TRANSMIT-000904 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d16fc119-c5de-4572-ae60-3aed175af548 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4776 | T16182-YU02-P0CYE-137842 | 2017-10-30 | DHI-TRANSMIT-000904 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6371186-c928-4773-83f4-7e12f47dc992 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4777 | T16182-YD00-P0CYE-137941 | 2017-10-30 | DHI-TRANSMIT-000904 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42101b8b-9a13-447e-b3b9-42bf89926eb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4778 | T16182-YU02-P0CYE-137942 | 2017-10-30 | DHI-TRANSMIT-000904 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22fd5b8e-593e-4875-82c9-abdca191c338 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4779 | T16182-YE03-P0BAU-152504 | 2017-10-30 | DHI-TRANSMIT-000905 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=956ea5dc-2829-4217-977e-cab4ea4cf144 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4780 | T16182-YE03-P0BAU-152510 | 2017-10-30 | DHI-TRANSMIT-000905 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f70fcea1-5949-4040-b7a4-87745fcd4d2c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4781 | T16182-XH02-P8QHL-125400 | 2017-10-30 | DHI-TRANSMIT-000906 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1da41cc0-3f35-4d8e-b06a-b96fec0e7860 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4782 | T16182-CA00-P0UMA-180405 | 2017-10-30 | DHI-TRANSMIT-000907 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f9db7af-80a7-4573-83dc-e81b5590e360 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4783 | T16182-CA00-P0UMA-180406 | 2017-10-30 | DHI-TRANSMIT-000907 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fae8c12-9f4a-4736-ac55-eacd687c9349 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4784 | T16182-CA00-P0UMA-180408 | 2017-10-30 | DHI-TRANSMIT-000907 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc317099-4b58-4a3d-9369-40331ec659d5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4785 | T16182-CA00-P0GEN-185701 | 2017-10-31 | DHI-TRANSMIT-000911 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9b7d065-530b-45be-aae6-4451ac774f8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4786 | T16182-CA01-P0GEN-185751 | 2017-10-31 | DHI-TRANSMIT-000911 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6e0dea6-5d28-4c43-8c3d-33066e6f3db1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4787 | T16182-DP00-P0ZEN-020006 | 2017-10-31 | DHI-WTRAN-000904 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c92555b-b0aa-4b77-b222-065cd52eb3ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4788 | T16182-YR01-P0LB-122082 | 2017-10-31 | DHI-WTRAN-000905 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7536e2f2-b2bf-4f33-b422-23c91b943202 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4789 | T16182-XJ00-P0LB-122029 | 2017-10-31 | DHI-TRANSMIT-000912 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a91fb24-f07c-4784-b16d-21c581a02d68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4790 | T16182-XH01-P0LB-122026 | 2017-10-31 | DHI-TRANSMIT-000912 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb204716-3d9b-47f9-95bc-0d177f228ebb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4791 | T16182-YK00-P0LB-122071 | 2017-10-31 | DHI-TRANSMIT-000912 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=707f8027-2f31-465e-bbf9-43816a5d71db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4792 | T16182-YD00-P0LB-122050 | 2017-10-31 | DHI-TRANSMIT-000912 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=463c87d0-d39a-4a99-86b8-27d15268dbeb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4793 | T16182-YD00-P0CYE-138941 | 2017-10-31 | DHI-TRANSMIT-000913 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac2d4198-9563-47a0-b401-a00c90f81b8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4794 | T16182-YU02-P0CYE-138942 | 2017-10-31 | DHI-TRANSMIT-000913 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7284f5e9-6d9b-494a-8fb5-92f9ab4488c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4795 | T16182-XG02-P0SGA-138001 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8690b6f-8ed9-4a09-a92e-fa7d96d5b453 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4796 | T16182-YT10-P0SGK-137623 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b43678a-bdf0-4465-bcae-6732dc3874d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4797 | T16182-YD00-P0SGZ-138031 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3942e125-5e7e-420c-a363-6024d8559d74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4798 | T16182-XG02-P0SGK-137603 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=426c3da8-434a-458c-ac61-f3f4230251ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4799 | T16182-XG02-P0SGA-137801 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0703dc2-ab09-45b6-b8b2-64603daba97b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4800 | T16182-XH01-P0SGA-137811 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=146cc58d-2566-4e26-acdf-075d8adcb4bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4801 | T16182-XH01-P0SGA-138411 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=351b51c1-f73e-4c21-8536-8607446b1f49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4802 | T16182-XG02-P0SGA-138401 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68f7dfb2-255a-44e1-87e6-728c257520ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4803 | T16182-XH01-P0SGA-138011 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=469104a1-1e71-403d-89f5-e36998c9ea70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4804 | T16182-XH01-P0SGK-137613 | 2017-10-31 | DHI-TRANSMIT-000914 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec16cf1e-4eab-476b-a763-4ca60c5ff388 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4805 | T16182-YK08-P0LCM-420040 | 2017-10-31 | DHI-TRANSMIT-000915 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28057508-d0cc-404e-bf83-2fd6b5c96bc1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4806 | T16182-XW03-P0SAJ-133701 | 2017-10-31 | DHI-TRANSMIT-000916 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7114b595-c51a-42dc-ab2d-7d09ae8f862d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4807 | T16182-XG07-P0SAJ-133702 | 2017-10-31 | DHI-TRANSMIT-000916 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce87bf07-8be5-43c0-966e-39917163dd6e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4808 | T16182-XW03-P0SAJ-133703 | 2017-10-31 | DHI-TRANSMIT-000916 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=192fe6f5-64db-4268-983c-7f05b027e7a3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4809 | T16182-XH02-P0SAJ-133704 | 2017-10-31 | DHI-TRANSMIT-000916 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=338f86e4-8ef4-4c86-94af-41d4e70132e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4810 | T16182-XS00-P0EKG-120020 | 2017-11-01 | DHI-WTRAN-000906 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c594b9a-001b-4691-8ad8-b382610abecb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4811 | T16182-YD04-P0ZEN-152008 | 2017-11-01 | DHI-WTRAN-000907 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdb088fe-2e49-4cb5-936e-39a30205b195 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4812 | T16182-YD04-P0ZEN-152009 | 2017-11-01 | DHI-WTRAN-000907 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac3d6280-fa59-44f6-a895-6132386aa6ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4813 | T16182-YD04-P0ZEN-152012 | 2017-11-01 | DHI-WTRAN-000907 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6198f38a-67d7-47a3-81d7-102fdc4700bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4814 | T16182-YD02-P0ZEN-165571 | 2017-11-01 | DHI-WTRAN-000908 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d829a264-8789-4816-8e5f-5931ea8fd4e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4815 | T16182-YK00-P0GHC-129064 | 2017-11-01 | DHI-WTRAN-000909 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a2da229-1415-4944-ac80-9414c9941348 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4816 | T16182-YL00-P0GHC-129063 | 2017-11-01 | DHI-WTRAN-000909 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b9ff078-d857-4d5e-bc22-f796527305bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4817 | T16182-YT01-P0GHC-129055 | 2017-11-01 | DHI-WTRAN-000910 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e823074-3d8b-443a-bc96-0a2eceb0cded | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4818 | T16182-YK08-P0GKC-420050 | 2017-11-01 | DHI-WTRAN-000911 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3982cd26-4928-4fdc-ab22-73e1097c1d62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4819 | T16182-YF00-P0MKY-290007 | 2017-11-01 | DHI-WTRAN-000912 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdb41b46-a47e-4f80-9fd0-b093d7de8c82 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4820 | T16182-XH01-P0EKG-124002 | 2017-11-01 | DHI-TRANSMIT-000918 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51b05079-1b26-4114-896a-5e5c316e6053 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4821 | T16182-YK10-P0EKG-124013 | 2017-11-01 | DHI-TRANSMIT-000919 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16bb56ad-5f11-4afe-99b3-589bb2e8a6ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4822 | T16182-XW03-P0SAV-135101 | 2017-11-01 | DHI-TRANSMIT-000920 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ed2b7b0-8dc7-47e7-bf7e-39bbb0530242 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4823 | T16182-XG07-P0SAV-135102 | 2017-11-01 | DHI-TRANSMIT-000920 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52f860bc-cec8-4da6-837f-b5930a1449d7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4824 | T16182-XW03-P0SAV-135103 | 2017-11-01 | DHI-TRANSMIT-000920 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18ec4245-f232-4870-9713-71ae698b7467 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4825 | T16182-XH02-P0SAV-135104 | 2017-11-01 | DHI-TRANSMIT-000920 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=073969b3-e2fc-4b13-8430-25874ec6b948 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4826 | T16182-YT01-P0GCF-130014 | 2017-11-01 | DHI-TRANSMIT-000921 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0e925e8-4363-421b-90ad-851a8b593d79 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4827 | T16182-YT01-P0GNR-130108 | 2017-11-01 | DHI-TRANSMIT-000921 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b922f3de-df28-4852-a06d-593673674194 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4828 | T16182-XN00-P0GCF-130008 | 2017-11-01 | DHI-TRANSMIT-000921 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77290ee2-575b-46ad-89f5-0b5f50234a81 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4829 | T16182-XN00-P0GNR-130105 | 2017-11-01 | DHI-TRANSMIT-000921 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aeb439da-41d0-4945-ad26-8f260b88a908 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4830 | T16182-YD00-P0CYE-138441 | 2017-11-01 | DHI-TRANSMIT-000922 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c7af56c-11b2-4c98-916b-11c762611c00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4831 | T16182-YU02-P0CYE-138442 | 2017-11-01 | DHI-TRANSMIT-000922 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53a8863f-0fac-493d-a89e-b96f520941be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4832 | T16182-XH01-P0SGA-136811 | 2017-11-01 | DHI-TRANSMIT-000923 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e515a21e-8d90-4ca9-953d-76ae9f9ad92f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4833 | T16182-XH01-P0SGE-136812 | 2017-11-01 | DHI-TRANSMIT-000923 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c96defe-90ec-4094-a8fe-45a377df4c44 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4834 | T16182-CA00-P0ULD-183909 | 2017-11-01 | DHI-WTRAN-000913 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e37adc0-d80d-4843-97d1-2bed46374305 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4835 | T16182-YD00-P0MKW-260001 | 2017-11-01 | DHI-TRANSMIT-000924 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6eb22086-99e6-4b0e-928b-6bdb94c7254b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4836 | T16182-YD00-P0MKW-260002 | 2017-11-01 | DHI-TRANSMIT-000924 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c942a453-c398-49b4-bdaf-10e77c58aead | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4837 | T16182-UB01-P0EKG-124075 | 2017-11-01 | DHI-WTRAN-000914 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20931141-60a8-4012-9df1-6a0663ab23aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4838 | T16182-YE00-P0EKG-124014 | 2017-11-01 | DHI-WTRAN-000914 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=518ece8e-47d0-4466-b006-5afc141180b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4839 | T16182-YK00-P0SAY-163404 | 2017-11-01 | DHI-TRANSMIT-000925 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7be39e68-1d49-4208-b928-ce3c8da36757 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4840 | T16182-YD00-P0MAG-123001 | 2017-11-01 | DHI-TRANSMIT-000926 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb701dd3-d84c-4845-886a-1424dd21f5cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4841 | T16182-XK00-P0PCA-126508 | 2017-11-02 | DHI-WTRAN-000915 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86049d26-346e-4f43-a0a1-b86dbae800d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4842 | T16182-YE03-P0BAU-152529 | 2017-11-02 | DHI-TRANSMIT-000928 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2d33999-cdd4-4e9a-b203-0cd8942b81a3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4843 | T16182-XS00-P0LB-122036 | 2017-11-02 | DHI-TRANSMIT-000929 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=858db8be-97cb-4a1b-b8b6-92afa1410bce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4844 | T16182-YK10-P0LF-110604 | 2017-11-02 | DHI-TRANSMIT-000930 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=952b7f0a-e8af-4faf-83e5-2154d0489148 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4845 | T16182-YK10-P0LF-110602 | 2017-11-02 | DHI-WTRAN-000916 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=792acf6c-260c-4cc4-bad9-dd3ae3bf5da5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4846 | T16182-YT01-P0LF-110601 | 2017-11-02 | DHI-WTRAN-000916 | IFR | C | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a794a6ef-44aa-47df-bcca-041795ad6c3a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4847 | T16182-YE03-P0BAU-152526 | 2017-11-02 | DHI-WTRAN-000917 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7faebd0-4cc8-4098-a643-cdedc4091871 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4848 | T16182-YU02-P0MKY-290006 | 2017-11-02 | DHI-TRANSMIT-000931 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4c22ca0-eb72-40bc-a3a0-40be09a43813 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4849 | T16182-YD02-P0SAC-163421 | 2017-11-02 | DHI-WTRAN-000918 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce6ad745-c5a6-4155-8dac-7e8402f6c2b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4850 | T16182-YR01-P0ZEN-110201 | 2017-11-02 | DHI-WTRAN-000919 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87154308-9c2b-4c01-9227-f678027e428e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4851 | T16182-YS01-P0MKY-290012 | 2017-11-02 | DHI-WTRAN-000920 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2414dec7-ae2a-475f-882b-7ce2c2dc5841 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4852 | T16182-YT01-P0LAC-126005 | 2017-11-02 | DHI-WTRAN-000921 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d733ca2a-cd2f-4086-bff3-d3d538c7e16c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4853 | T16182-YT01-P0LAC-126055 | 2017-11-02 | DHI-WTRAN-000921 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6115da7a-2c30-465e-b509-3da45b5f6031 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4854 | T16182-YQ01-P0ZEN-152321 | 2017-11-02 | DHI-TRANSMIT-000932 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cab2475-aeee-46a5-8405-dc04925fb854 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4855 | T16182-YB11-P0ZEN-152421 | 2017-11-02 | DHI-WTRAN-000922 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=272013dd-7b15-4033-aa0a-7b6adf0671db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4856 | T16182-YT10-P0ZEN-152223 | 2017-11-02 | DHI-WTRAN-000922 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4805ad75-7505-473e-b340-93ccef6a1d7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4857 | T16182-YD00-P0SML-128013 | 2017-11-02 | DHI-TRANSMIT-000933 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=275b8a33-120f-4d1b-917e-771a7ee8504d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4858 | T16182-YT01-P0SML-128018 | 2017-11-02 | DHI-TRANSMIT-000933 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecfdc8da-cec6-4ee6-baf9-c3777d0f7970 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4859 | T16182-XJ00-P0LAB-140108 | 2017-11-02 | DHI-TRANSMIT-000934 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd47c50b-b84d-4a1d-9a59-d9e6d185e7d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4860 | T16182-XW01-P0MBA-121006 | 2017-11-02 | DHI-WTRAN-000923 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4861 | T16182-XB00-P0GM-128506 | 2017-11-06 | DHI-WTRAN-000924 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14d26493-61d8-4d32-8800-e0069fc162f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4862 | T16182-YD00-P0GM-128501 | 2017-11-06 | DHI-WTRAN-000925 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9534fe52-d908-4f4e-82f3-1ff0cd081a50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4863 | T16182-YD00-P0GM-128503 | 2017-11-06 | DHI-WTRAN-000925 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6d403ae-2c04-4d56-8b15-ec2a4051f5fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4864 | T16182-YT01-P0GM-128502 | 2017-11-06 | DHI-WTRAN-000925 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10fbcd75-37c6-4317-8048-e8cc2854563c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4865 | T16182-YD00-P0MKW-260011 | 2017-11-06 | DHI-TRANSMIT-000936 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce73cd3e-9b38-4d35-805c-c54f74bdeb87 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4866 | T16182-YV02-P0MKW-260021 | 2017-11-06 | DHI-WTRAN-000926 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03c04b50-4b87-4a2f-8c02-d65d9fb5bc1e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4867 | T16182-XA00-P8QHL-125401 | 2017-11-06 | DHI-TRANSMIT-000937 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d865354e-a18b-428f-a863-41d09657414c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4868 | T16182-XJ00-P8ZEN-125540 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b8411a1-8b40-4ae6-b883-eba0c510946e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4869 | T16182-XJ00-P8ZEN-125541 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43e6aacb-46e0-403e-9c4c-275297ebc6a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4870 | T16182-XJ00-P8ZEN-125542 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96127d27-06f7-4dd3-8226-670eb460a8c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4871 | T16182-XJ00-P8ZEN-125543 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7d34bb7-72a3-4b67-97d2-2996953140f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4872 | T16182-XJ00-P8ZEN-125544 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64fa3736-7311-4e78-93c7-de0f7117626f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4873 | T16182-XJ00-P8ZEN-125545 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60e3416a-14ee-4c44-97c7-72824ba74f62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4874 | T16182-XJ00-P8ZEN-125546 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbb812f4-ba88-4306-b70a-8421b5e6a530 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4875 | T16182-XJ00-P8ZEN-125547 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=542b7561-0d19-45b5-b894-a3c4f7bbed5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4876 | T16182-XJ00-P8ZEN-125548 | 2017-11-06 | DHI-WTRAN-000927 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72c35c22-279a-4cea-9255-cf881c81a42a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4877 | T16182-XB02-P0UZT-172702 | 2017-11-06 | DHI-TRANSMIT-000938 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=623de0b7-4625-4463-ac48-b81f21d1c1d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4878 | T16182-XB02-P0UZT-172703 | 2017-11-06 | DHI-TRANSMIT-000938 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a118ed29-d804-4ef9-9bdd-b0c433852cba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4879 | T16182-VK02-P0UZT-172713 | 2017-11-06 | DHI-TRANSMIT-000938 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=feba955a-62bd-499f-8d07-e286a277d14d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4880 | T16182-XB02-P0UZT-172716 | 2017-11-06 | DHI-TRANSMIT-000938 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52a84ecc-4060-4d41-b8c8-dc07577f0ef0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4881 | T16182-YL00-P0PCA-126523 | 2017-11-06 | DHI-WTRAN-000928 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6c02c6b-784b-4210-a4b3-79579ce10b7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4882 | T16182-YD00-P0CYE-136741 | 2017-11-06 | DHI-TRANSMIT-000939 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3607e12c-6651-49d2-bd58-e1b8f22804c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4883 | T16182-YU02-P0CYE-136742 | 2017-11-06 | DHI-TRANSMIT-000939 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf5a6e5d-394e-4456-86b8-6043cd32615e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4884 | T16182-CA03-P0UMY-185151 | 2017-11-06 | DHI-TRANSMIT-000940 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c89ab3c-2aad-48a0-9569-951c8874f92b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4885 | T16182-CA03-P0UMY-185152 | 2017-11-06 | DHI-TRANSMIT-000940 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2ef7a78-0951-41f0-b5bf-82f9822756b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4886 | T16182-YL01-P0PCA-126524 | 2017-11-06 | DHI-WTRAN-000929 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=345ac610-caa1-4202-843d-b5acf35ee4a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4887 | T16182-XG02-P0PCA-126502 | 2017-11-06 | DHI-TRANSMIT-000941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01255650-e1d1-4787-b11d-113c47967812 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4888 | T16182-YD00-P0SGZ-137231 | 2017-11-06 | DHI-TRANSMIT-000942 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f384ed86-c3dc-4242-ae91-562584439815 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4889 | T16182-YD00-P0SGZ-138431 | 2017-11-06 | DHI-TRANSMIT-000942 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c210c2e3-6b53-4813-9c71-10f017e8ce62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4890 | T16182-YD00-P0SGZ-138931 | 2017-11-06 | DHI-TRANSMIT-000942 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b713d6c4-79fc-4015-af0c-a133946e8280 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4891 | T16182-CA00-P0UYC-182907 | 2017-11-06 | DHI-TRANSMIT-000943 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=100413ca-a9d6-43bf-a2e2-25b19488e908 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4892 | T16182-CA00-P0UYC-182908 | 2017-11-06 | DHI-TRANSMIT-000943 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54d60734-df10-4ca1-be2f-af5e21bfcab4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4893 | T16182-YV02-P0MKG-260022 | 2017-11-06 | DHI-WTRAN-000930 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b22c7bb8-a04d-4429-838e-578c572ab28b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4894 | T16182-XJ00-P0LCA-140106 | 2017-11-06 | DHI-TRANSMIT-000944 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7c4e313-4132-421d-b0ba-9ddeab70f653 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4895 | T16182-XJ00-P0GKB-140112 | 2017-11-06 | DHI-TRANSMIT-000946 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=559545db-1c3f-467f-8fbb-ac49e543fc91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4896 | T16182-XG02-P0GKB-120001 | 2017-11-06 | DHI-TRANSMIT-000947 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c6ecd9c-7573-49d1-8874-60b95736cdfa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4897 | T16182-XG02-P0GKC-120002 | 2017-11-06 | DHI-TRANSMIT-000947 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61a61bb0-e205-4f43-8f84-82176f564c9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4898 | T16182-YD02-P0SAC-163408 | 2017-11-06 | DHI-TRANSMIT-000948 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=481f7125-f5bd-4c5b-946e-792b0e7f6ed2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4899 | T16182-XG02-P0SGA-138901 | 2017-11-06 | DHI-TRANSMIT-000949 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e038d47-291b-47d6-9a8d-f13c02641841 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4900 | T16182-XH01-P0SGA-138911 | 2017-11-06 | DHI-TRANSMIT-000949 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2299f6fa-fca8-497d-96a6-cc4d7323cabd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4901 | T16182-YS01-P0MKY-290009 | 2017-11-06 | DHI-WTRAN-000931 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad7e28ea-5897-4350-bf38-52658345b5f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4902 | T16182-CN00-P0MKA-260037 | 2017-11-06 | DHI-WTRAN-000932 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=238cee2a-24a2-472c-85dc-c04b9b7781f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4903 | T16182-YU02-P0BT-151021 | 2017-11-07 | DHI-WTRAN-000933 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4904 | T16182-YU02-P0BT-151026 | 2017-11-07 | DHI-WTRAN-000933 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4905 | T16182-YU02-P0BT-151031 | 2017-11-07 | DHI-WTRAN-000933 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4906 | T16182-XS00-P0MAG-123003 | 2017-11-07 | DHI-WTRAN-000934 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4907 | T16182-YB03-P0ZEN-165531 | 2017-11-07 | DHI-TRANSMIT-000952 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0372764b-c26f-4791-beb5-4956cce23076 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4908 | T16182-YL16-P0ZEN-165551 | 2017-11-07 | DHI-TRANSMIT-000952 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51ce31db-5357-40d4-b8ce-11b9e1b71b86 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4909 | T16182-UE00-P0LB-122013 | 2017-11-07 | DHI-TRANSMIT-000953 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e082ec1-ac3f-4a3c-a147-0485928e1381 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4910 | T16182-UE00-P0LB-122014 | 2017-11-07 | DHI-TRANSMIT-000953 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=476ff20d-ac97-4322-81f8-9f50c16edb21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4911 | T16182-YD00-P0LB-122057 | 2017-11-07 | DHI-TRANSMIT-000953 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa5a9465-0e4e-46a9-9d3a-21b5fe245574 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4912 | T16182-CN00-P0LB-122040 | 2017-11-07 | DHI-TRANSMIT-000954 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0455de58-b1c2-4ac2-aab5-3466f0d99a46 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4913 | T16182-XL00-P0MAG-123021 | 2017-11-07 | DHI-TRANSMIT-000955 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba51295e-a83a-4fba-8fe2-57f09716dd6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4914 | T16182-YD00-P0LAC-126019 | 2017-11-07 | DHI-WTRAN-000935 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0dc8756-9e69-4899-b595-3828739e86d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4915 | T16182-YD00-P0LAC-126069 | 2017-11-07 | DHI-WTRAN-000935 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0e983a6-a306-4dad-85f3-a6a9e9e4be93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4916 | T16182-YD00-P0MKW-260012 | 2017-11-07 | DHI-TRANSMIT-000956 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2689fc5-e52b-4b41-aa9b-09160b602d1b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4917 | T16182-YD00-P0MKW-260013 | 2017-11-07 | DHI-TRANSMIT-000956 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=826c6a37-4938-4bb1-854b-21833a93ec87 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4918 | T16182-YD00-P0CYE-138141 | 2017-11-07 | DHI-WTRAN-000936 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4367d486-e63e-4434-9bf7-210c4ff0f394 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4919 | T16182-YU02-P0CYE-138142 | 2017-11-07 | DHI-WTRAN-000936 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e621126-b6e8-43de-88fd-1b4b09b04744 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4924 | T16182-XW01-P0GM-128507 | 2017-11-07 | DHI-WTRAN-000938 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21948a1e-869f-47bf-bad1-b544676c236f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4925 | T16182-XS01-P6MAA-220093 | 2017-11-07 | DHI-WTRAN-000939 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73241767-46f8-4d80-8509-194164a3152d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4926 | T16182-YL08-P6MAA-220207 | 2017-11-07 | DHI-WTRAN-000939 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b117303-6ce6-4234-8f44-1f7926e48984 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4927 | T16182-YL13-P6MAA-220095 | 2017-11-07 | DHI-WTRAN-000939 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e13a91b-7842-473b-bcab-5faf5aca02cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4928 | T16182-YL13-P6MAA-220143 | 2017-11-07 | DHI-WTRAN-000939 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a9e5b11-4dbc-4ce5-b918-925b89db21d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4929 | T16182-VE01-P6MAA-220047 | 2017-11-07 | DHI-WTRAN-000940 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=469f13d9-5a9b-40a5-9faa-13a6f120d3f0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4930 | T16182-YD00-P0MAA-220801 | 2017-11-07 | DHI-WTRAN-000940 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba1f1ce8-bcc9-49dc-b352-32130ad0faae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4931 | T16182-UE00-P0LB-122011 | 2017-11-07 | DHI-WTRAN-000941 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b280625-df5d-4a67-814d-f1ebef197aed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4932 | T16182-YD00-P0LB-122044 | 2017-11-07 | DHI-WTRAN-000941 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f8d7575-5b19-49f7-b012-e6472d8b2453 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4933 | T16182-XB02-P0LB-122020 | 2017-11-07 | DHI-TRANSMIT-000957 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61209eda-7903-42ec-be4b-4cfb51211b6c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4934 | T16182-YD00-P0LB-122049 | 2017-11-07 | DHI-TRANSMIT-000957 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72053cdb-ae73-4831-9219-b731986efb5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4935 | T16182-YD00-P0LB-122055 | 2017-11-07 | DHI-TRANSMIT-000957 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=159019a9-c8dc-4efe-af16-c334e1dd9df3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4936 | T16182-YD05-P0CRN-161116 | 2017-11-07 | DHI-WTRAN-000942 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=614f60f1-69c0-497d-9333-bf4e3f4fe4af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4937 | T16182-YQ01-P0ZEN-152319 | 2017-11-07 | DHI-TRANSMIT-000958 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=108f6e5c-322c-4ae3-85d3-25ed068b39a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4938 | T16182-YQ01-P0ZEN-152320 | 2017-11-07 | DHI-WTRAN-000943 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fd3ca63-f519-490f-944d-06a1166bdb4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4939 | T16182-YT10-P0ZEN-152222 | 2017-11-07 | DHI-WTRAN-000943 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7b9dab0-ef65-4c0b-9033-ec86b19d1550 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4920 | T16182-XG02-P0SGC-138101 | 2017-11-08 | DHI-WTRAN-000950 | IFR | A | D | TRUE | FALSE | 2017-11-08_Changed by jisoo1.chung 2017-11-08_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98a04f88-aa90-4f81-85c8-96e4bc83f28d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4921 | T16182-XH01-P0SGC-138111 | 2017-11-08 | DHI-WTRAN-000950 | IFI | 0 | D | TRUE | FALSE | 2017-11-08_Changed by jisoo1.chung 2017-11-08_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=558ea845-ade6-473b-af14-3fbad6bde2e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4922 | T16182-YD00-P0SGZ-138131 | 2017-11-08 | DHI-WTRAN-000950 | IFI | 0 | D | TRUE | FALSE | 2017-11-08_Changed by jisoo1.chung 2017-11-08_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67b7f785-ccd8-4cf9-b007-b62f8814008d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4923 | T16182-YT10-P0SGC-138121 | 2017-11-08 | DHI-WTRAN-000950 | IFR | A | D | TRUE | FALSE | 2017-11-08_Changed by jisoo1.chung 2017-11-08_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ee56f00-5332-4d8e-ac41-e2c93dcf9e60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4940 | T16182-YT10-P0ZEN-150311 | 2017-11-08 | DHI-WTRAN-000944 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4941 | T16182-YT10-P0ZEN-150314 | 2017-11-08 | DHI-WTRAN-000944 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4942 | T16182-YT01-P0MKA-260019 | 2017-11-08 | DHI-WTRAN-000945 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea3a687c-3e18-43a2-a740-c14447d08b8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4943 | T16182-YS01-P0MKY-290008 | 2017-11-08 | DHI-WTRAN-000946 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0431e1a-99dd-487d-860b-773cce9c1fc3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4944 | T16182-YD00-P0SMS-128002 | 2017-11-08 | DHI-TRANSMIT-000959 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9c9f14b-b18f-47d5-81f0-65aaf4a7a160 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4945 | T16182-YT01-P0SMS-128005 | 2017-11-08 | DHI-TRANSMIT-000959 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3800917e-f9fe-4610-b9f5-fde11aed0626 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4946 | T16182-YD00-P0LAC-126010 | 2017-11-08 | DHI-TRANSMIT-000960 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f412c48-d42a-498a-928e-7801f4d0d328 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4947 | T16182-YD00-P0LAC-126060 | 2017-11-08 | DHI-TRANSMIT-000960 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4131f02-54e2-4fab-827e-cd990065699b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4948 | T16182-XS00-P0PCA-126504 | 2017-11-08 | DHI-TRANSMIT-000961 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=955e5041-a052-4092-8048-118b52ec72c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4949 | T16182-XK00-P0GM-128504 | 2017-11-08 | DHI-WTRAN-000947 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b31c76a0-8bf8-4b48-84b9-8e12ba686d8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4950 | T16182-XK00-P0GM-128505 | 2017-11-08 | DHI-WTRAN-000947 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96c78c89-a5e3-48f5-b39a-1f458b285e6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4951 | T16182-YM01-P0LCB-127039 | 2017-11-08 | DHI-WTRAN-000948 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33ff5c15-cc18-47fa-8631-9a10b289d011 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4952 | T16182-YK09-P0LCB-127011 | 2017-11-08 | DHI-WTRAN-000949 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b722dd3-5f85-43cc-b6aa-3b8d14684130 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4953 | T16182-YL00-P0LCB-127013 | 2017-11-08 | DHI-WTRAN-000949 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99a6de00-4182-4a8a-9347-69aca822089c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4954 | T16182-YT10-P0ZEN-150304 | 2017-11-08 | DHI-TRANSMIT-000962 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03c5af8e-14ca-49d8-a5de-ff05a313d5c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4955 | T16182-XJ00-P0GHC-140113 | 2017-11-09 | DHI-TRANSMIT-000963 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bdd0bd1-719a-4617-811f-0ac9fd68b7a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4956 | T16182-XJ00-P0PGB-140109 | 2017-11-09 | DHI-TRANSMIT-000963 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4765eae1-6750-439c-8f29-f908b3a92dac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4957 | T16182-CA06-P0UBA-186800 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8275c20-2088-4a5d-8749-693ad5a5c9ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4958 | T16182-CA00-P0UBA-186801 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ba7b71f-bcb0-48de-a514-0f0ebe933104 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4959 | T16182-CA00-P0UBA-186802 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae51131e-4f07-4b15-9132-b838305338be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4960 | T16182-CA00-P0UBA-186803 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c38f72d6-f288-4747-a300-c155e7f8fbf1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4961 | T16182-CA01-P0UBA-186851 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44b51d40-22b5-48dc-b580-fb2bd8e7f930 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4962 | T16182-CA01-P0UBA-186852 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0dca3714-632f-4136-b3d5-c9c8eccd3f88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4963 | T16182-CA01-P0UBA-186853 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06aa5549-82aa-4d5e-8ce2-193c001d1811 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4964 | T16182-CA02-P0UBA-186854 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c9047ac-e640-4467-b528-ecd0eefdcb23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4965 | T16182-CA02-P0UBA-186855 | 2017-11-09 | DHI-WTRAN-000951 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca77d3af-5ee6-41e8-b9f3-63905e642fb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4966 | T16182-YK08-P0LBG-110252 | 2017-11-09 | DHI-TRANSMIT-000964 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55855828-c652-46b8-9101-ecfa852753ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4967 | T16182-YT01-P0LBG-110251 | 2017-11-09 | DHI-WTRAN-000952 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c096444b-e285-4458-8876-a4f4b5a008c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4968 | T16182-YL16-P0SAY-163406 | 2017-11-09 | DHI-WTRAN-000953 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e641e1f-20a2-4af3-9646-1f365a7da996 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4969 | T16182-YB03-P0SAY-163407 | 2017-11-09 | DHI-WTRAN-000954 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8a702a0-8566-454a-bed2-d6902fad1d57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4970 | T16182-YD00-P0MKG-260017 | 2017-11-09 | DHI-TRANSMIT-000965 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62594565-1afa-493b-9757-be337f1d4190 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4971 | T16182-YK00-P0GCF-130016 | 2017-11-09 | DHI-WTRAN-000955 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6f097b2-b5d7-4759-8952-397e7f0a86ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4972 | T16182-CQ02-P0SCA-127529 | 2017-11-09 | DHI-WTRAN-000956 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54793b01-c1ec-498e-8dc3-e1095daf8fce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4973 | T16182-UC07-P0ZEN-100001 | 2017-11-09 | DHI-TRANSMIT-000966 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f6a5dc5-3b14-484e-92a2-a846ef8f0f6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4974 | T16182-UC07-P0ZEN-100002 | 2017-11-09 | DHI-TRANSMIT-000966 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04a358ed-90ab-4bb4-9dff-98177d3d187f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4975 | T16182-UC07-P0ZEN-100003 | 2017-11-09 | DHI-TRANSMIT-000966 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00a57b13-f7ae-441f-b02f-67df29cc0462 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4976 | T16182-XG02-P0SGA-136901 | 2017-11-10 | DHI-WTRAN-000957 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4977 | T16182-XG02-P0SGA-139401 | 2017-11-10 | DHI-WTRAN-000957 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4978 | T16182-XG02-P0SGE-136902 | 2017-11-10 | DHI-WTRAN-000957 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4979 | T16182-XH01-P0SGA-139411 | 2017-11-10 | DHI-WTRAN-000957 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4980 | T16182-XH01-P0SGC-137411 | 2017-11-10 | DHI-WTRAN-000957 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4981 | T16182-YD00-P0SGZ-139431 | 2017-11-10 | DHI-WTRAN-000957 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4982 | T16182-YD00-P0CYE-137241 | 2017-11-10 | DHI-WTRAN-000958 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4983 | T16182-YL00-P0QC-130305 | 2017-11-10 | DHI-WTRAN-000959 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=286855af-398c-48c3-b92f-cf89cf673a35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4984 | T16182-YL00-P0QU-130404 | 2017-11-10 | DHI-WTRAN-000959 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a21b7bef-d318-4800-8dfa-c27f6394f27f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4985 | T16182-YR05-P0QC-130306 | 2017-11-10 | DHI-WTRAN-000959 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=266c469b-05e5-4fe5-bc8f-f815036e0af4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4986 | T16182-CA00-P0USR-184702 | 2017-11-10 | DHI-TRANSMIT-000967 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b891f6b-c2b4-4870-9b38-75da507ce325 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4987 | T16182-CA03-P0USR-184752 | 2017-11-10 | DHI-TRANSMIT-000967 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36f70458-d5e5-47b7-bcaf-3040f380b60a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4988 | T16182-YE00-P0CJN-290005 | 2017-11-10 | DHI-TRANSMIT-000968 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a42f3fa-43e6-4e7b-a057-6e532c599615 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4989 | T16182-XJ00-P0GKB-140215 | 2017-11-10 | DHI-WTRAN-000960 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3efe7201-0d48-4112-9afe-203528df9f17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4990 | T16182-XJ00-P0PDA-140114 | 2017-11-10 | DHI-TRANSMIT-000969 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ee8d0db-8c68-433b-8f47-c881376fea8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4991 | T16182-YT01-P0LAC-126016 | 2017-11-10 | DHI-WTRAN-000961 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22c48f40-2009-4d0e-b98e-db62c25ecfbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4992 | T16182-YT01-P0LAC-126066 | 2017-11-10 | DHI-WTRAN-000961 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88d52068-95b8-43f7-a38c-dfd2af89250f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4993 | T16182-YD02-P0ZEN-165525 | 2017-11-10 | DHI-WTRAN-000962 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccd6178b-7458-431e-9c6c-f1be202ab2c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4994 | T16182-YD00-P0STG-130502 | 2017-11-10 | DHI-TRANSMIT-000970 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce08193e-8abc-4946-b95c-1631fba7f910 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4995 | T16182-XL00-P0STG-130503 | 2017-11-10 | DHI-WTRAN-000963 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=933e62e9-1daa-4458-95ce-a8d1df3d24a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4996 | T16182-YF00-P0CBA-161221 | 2017-11-10 | DHI-TRANSMIT-000971 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d44ce8f-cc3c-4606-acb8-667b9b7e8f24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4997 | T16182-YF00-P0CGA-161321 | 2017-11-10 | DHI-TRANSMIT-000971 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebd96227-4617-440b-93dd-74c48de4ef49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4998 | T16182-XG07-P0SAB-134802 | 2017-11-10 | DHI-TRANSMIT-000972 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=710cd8fe-927d-44a3-b33a-fb3bfb6e80d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
4999 | T16182-XH02-P0SAB-134804 | 2017-11-10 | DHI-TRANSMIT-000972 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f9b967f-6a3f-4c82-872c-8f0d984a3b7c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5000 | T16182-XW03-P0SAB-134801 | 2017-11-10 | DHI-TRANSMIT-000972 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5e2b619-1858-4eb7-a3f5-a476e8a5f5cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5001 | T16182-XW03-P0SAB-134803 | 2017-11-10 | DHI-TRANSMIT-000972 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8b47747-73c2-4c57-a825-88cfe41fa5bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5002 | T16182-YD00-P0UBA-150508 | 2017-11-10 | DHI-TRANSMIT-000973 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf6206ff-dca9-40a3-b1f4-47366e387729 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5003 | T16182-XB02-P0UGD-172542 | 2017-11-13 | DHI-TRANSMIT-000977 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c7e4209-6ec6-4715-a693-11ab0dc8737f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5004 | T16182-XB02-P0UGF-172522 | 2017-11-13 | DHI-TRANSMIT-000977 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=563e0560-c24f-497b-8733-3b51278eaac4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5005 | T16182-XB02-P0UGG-172562 | 2017-11-13 | DHI-TRANSMIT-000977 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eda22471-eb1b-4be5-8c8f-3dd90187ac66 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5006 | T16182-XB02-P0ULC-172502 | 2017-11-13 | DHI-TRANSMIT-000977 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa3e8cb9-1e33-4a8b-a6b1-7bc13d44e5ff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5007 | T16182-CC08-P8QHA-125300 | 2017-11-14 | DHI-WTRAN-000964 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b976365a-e506-4c66-8e7a-cc754b81b7c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5008 | T16182-YD00-P0LCB-127001 | 2017-11-14 | DHI-TRANSMIT-000978 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e5cc758-db93-4aea-8d5f-4b2fb929ae1e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5009 | T16182-YD00-P0LCB-127009 | 2017-11-14 | DHI-TRANSMIT-000978 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9000b3f6-985a-45c9-bd78-df4885944efe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5010 | T16182-YT01-P0LCB-127007 | 2017-11-14 | DHI-WTRAN-000965 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c907744-e7d6-4ed4-b19b-c5347eb7fdf1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5011 | T16182-YT01-P0LCB-127037 | 2017-11-14 | DHI-WTRAN-000965 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffa54503-c6c5-4b11-8ca7-67bbe48adcfb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5012 | T16182-VE04-P0ULX-171601 | 2017-11-14 | DHI-TRANSMIT-000979 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74ddd995-6a6e-4197-bcd6-873d90835329 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5013 | T16182-VK02-P0ULX-171604 | 2017-11-14 | DHI-TRANSMIT-000979 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1a1f893-6a24-4940-8787-f99e5469b24b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5014 | T16182-XB02-P0ULX-171602 | 2017-11-14 | DHI-TRANSMIT-000979 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a83fad92-6a43-4cf3-a401-427b00742ad3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5015 | T16182-XB02-P0ULX-171603 | 2017-11-14 | DHI-TRANSMIT-000979 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=712416e3-8967-4fb9-ab1f-7de759dcd3eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5016 | T16182-YD04-P0ZEN-152015 | 2017-11-14 | DHI-TRANSMIT-000980 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3960d62-b214-446d-b4c1-3ca829eaee10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5017 | T16182-CN00-P0ZEN-110702 | 2017-11-14 | DHI-WTRAN-000966 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e0f9e69-69ba-4054-99a7-1079e5f6eca6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5018 | T16182-YU02-P0SCA-127510 | 2017-11-14 | DHI-WTRAN-000967 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29eef950-4e91-4ab2-9121-315622448ad1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5019 | T16182-YV02-P0SCA-127511 | 2017-11-14 | DHI-WTRAN-000967 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfc7ae1a-8c9a-44c0-a590-90723835fa84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5020 | T16182-XG02-P0SGA-137901 | 2017-11-14 | DHI-TRANSMIT-000981 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2646de8b-ba95-41fe-b297-a74fbd962edb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5021 | T16182-XH01-P0SGA-137911 | 2017-11-14 | DHI-TRANSMIT-000981 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=155cc012-a360-42fe-89fb-49d5140c892e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5022 | T16182-XH01-P0SGE-137913 | 2017-11-14 | DHI-TRANSMIT-000981 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca45195e-9e31-4f64-842a-67003bcd0157 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5023 | T16182-XH01-P0SGK-137912 | 2017-11-14 | DHI-TRANSMIT-000981 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c6c014a-a388-4b92-a68a-9a37e8a68267 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5024 | T16182-YT10-P0SGE-137923 | 2017-11-14 | DHI-TRANSMIT-000981 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01cb9193-4cc6-49ef-a867-637c759cbe42 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5025 | T16182-YT10-P0SGK-137922 | 2017-11-14 | DHI-TRANSMIT-000981 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8a70b1f-3783-41cc-9880-ce6912b9b6b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5026 | T16182-XH01-P0SGE-136712 | 2017-11-14 | DHI-TRANSMIT-000981 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed5f96a8-df4c-4c3e-b77c-7be5b8508061 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5027 | T16182-YT01-P0CYE-136617 | 2017-11-14 | DHI-TRANSMIT-000982 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cca1df24-5eed-4a63-a305-26fecfed4273 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5028 | T16182-DE00-P0PCA-126519 | 2017-11-15 | DHI-WTRAN-000968 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8c0d021-3f25-4bd0-898b-80a40345fe12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5029 | T16182-YT02-P0PCA-126529 | 2017-11-15 | DHI-WTRAN-000969 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=793d82e0-2a4f-4dfa-b16d-f51b9991f234 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5030 | T16182-YT10-P0ZEN-150313 | 2017-11-15 | DHI-WTRAN-000970 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b39da6e-c785-47c1-ad2d-0045ffab8695 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5031 | T16182-YD00-P0MKA-250023 | 2017-11-15 | DHI-WTRAN-000971 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4be32d6b-8e5b-4b74-9747-5393a7da26c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5032 | T16182-YD00-P0MKA-250024 | 2017-11-15 | DHI-WTRAN-000971 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85eb452f-0c44-463f-931a-7eece6a2ef95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5033 | T16182-XS00-P0EKG-120020 | 2017-11-15 | DHI-TRANSMIT-000983 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86e5a0c9-2cce-400f-8918-3c71a9d6a3cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5034 | T16182-XH01-P6MKA-260004 | 2017-11-15 | DHI-TRANSMIT-000984 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56e6a9cd-9c18-4414-bdd4-20222078fd80 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5035 | T16182-XH01-P7MKA-260007 | 2017-11-15 | DHI-TRANSMIT-000984 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12871e86-1dcc-4baa-b0dc-fbd393c4f910 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5036 | T16182-XK00-P6MKA-260005 | 2017-11-15 | DHI-TRANSMIT-000984 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=784b5188-e0ae-4a06-9f94-784404d8aacd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5037 | T16182-XK00-P7MKA-260008 | 2017-11-15 | DHI-TRANSMIT-000984 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fc09b53-ec61-48b7-8386-19f12bf9413c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5038 | T16182-YE01-P0BAU-152603 | 2017-11-15 | DHI-TRANSMIT-000985 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae318a95-c404-4d0f-ab68-6654ed325092 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5039 | T16182-YE01-P0BAU-152621 | 2017-11-15 | DHI-TRANSMIT-000985 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64391589-7bae-4250-bf46-ac37b0f343dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5040 | T16182-YE03-P0BAU-152517 | 2017-11-15 | DHI-TRANSMIT-000985 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=558c25ab-1672-4209-abc5-f64a4d9b8ec9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5041 | T16182-YE03-P0BAU-152539 | 2017-11-15 | DHI-TRANSMIT-000985 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b5d4f7b-3a5d-4497-9c9d-c61e39086aa0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5042 | T16182-YE01-P0BAU-152601 | 2017-11-15 | DHI-WTRAN-000972 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd4989c5-8fec-4752-98d1-5b5ff22a025b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5043 | T16182-YU03-P0BB-150831 | 2017-11-15 | DHI-WTRAN-000973 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2129ae59-b03c-4e6f-a406-e64052697fd1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5044 | T16182-CN00-P0ZEN-110705 | 2017-11-16 | DHI-WTRAN-000974 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3eeea32b-c8b8-4d64-967b-d0c4aad84b4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5045 | T16182-YF00-P0PCA-126522 | 2017-11-16 | DHI-WTRAN-000975 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5881affe-8ded-4dc0-b6ae-a4344a2202b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5046 | T16182-YE03-P0BAU-152536 | 2017-11-16 | DHI-TRANSMIT-000986 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52f48e0d-a67f-4eb4-bb04-456abb8aa43e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5047 | T16182-XJ00-P8ZEN-125549 | 2017-11-17 | DHI-WTRAN-000976 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2364a59-3688-4c3c-9baa-9d75ffa7758c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5048 | T16182-XJ00-P8ZEN-125550 | 2017-11-17 | DHI-WTRAN-000976 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35d589bd-abcd-493c-814d-38accebe8968 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5049 | T16182-YD00-P0CYE-137641 | 2017-11-17 | DHI-TRANSMIT-000991 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=563d60e5-cb2e-45b6-b8c7-7b7570d6b31f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5050 | T16182-YU02-P0CYE-137642 | 2017-11-17 | DHI-TRANSMIT-000991 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8acf461-7cf4-450d-b075-6dc94cd43d7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5051 | T16182-YD00-P0SGZ-137631 | 2017-11-17 | DHI-TRANSMIT-000992 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7685d113-1f50-49e4-a462-22c9a1fa0b3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5052 | T16182-XW03-P0SAL-134001 | 2017-11-17 | DHI-TRANSMIT-000993 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a9984cc-0e56-4ae3-b52e-232394b91faf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5053 | T16182-XG07-P0SAL-134002 | 2017-11-17 | DHI-TRANSMIT-000993 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed820571-ac8c-46ad-a3d5-d8c8f09973e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5054 | T16182-XW03-P0SAL-134003 | 2017-11-17 | DHI-TRANSMIT-000993 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00485be5-1333-4977-8665-c91d380d1c57 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5055 | T16182-XH02-P0SAL-134004 | 2017-11-17 | DHI-TRANSMIT-000993 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75098b28-fd39-4de7-a5f2-a603f3e0f984 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5056 | T16182-XG02-P0LB-122022 | 2017-11-17 | DHI-TRANSMIT-000994 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b132649a-0df4-4389-95c0-7b28e90738f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5057 | T16182-XG02-P0LCB-127002 | 2017-11-17 | DHI-TRANSMIT-000995 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f689810-1b0a-4270-b135-7a100c956e5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5058 | T16182-XB02-P0UAZ-172608 | 2017-11-17 | DHI-TRANSMIT-000996 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=834ba6d7-8a02-4642-9658-e0d33b3547ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5059 | T16182-CA00-P0UGD-181901 | 2017-11-17 | DHI-TRANSMIT-000997 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7365e1bd-70cf-4efa-8c1e-d752d494e14f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5060 | T16182-CA00-P0UGD-181902 | 2017-11-17 | DHI-TRANSMIT-000997 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02f67a9f-8031-49bf-a159-6478775d5587 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5061 | T16182-CA00-P0UGD-181903 | 2017-11-17 | DHI-TRANSMIT-000997 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c84920c-4a30-4860-9a19-d15036b5a678 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5062 | T16182-CA00-P0UGD-181904 | 2017-11-17 | DHI-TRANSMIT-000997 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b88655e1-a893-44da-af70-245dfc2e0932 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5063 | T16182-CA00-P0UGD-181905 | 2017-11-17 | DHI-TRANSMIT-000997 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1403aefc-753b-4de8-bee9-a91cf5cc9c02 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5064 | T16182-CA00-P0UGD-181906 | 2017-11-17 | DHI-TRANSMIT-000997 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36a9daac-2f4b-40a4-8a84-4e8cac8df895 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5065 | T16182-VE04-P0UNX-171401 | 2017-11-17 | DHI-TRANSMIT-000998 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f5040d7-6c43-4f90-bc79-a53ae551a4e5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5066 | T16182-XB02-P0UNX-171402 | 2017-11-17 | DHI-TRANSMIT-000998 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f6e61b8-68dd-4519-b830-c7de62372aae | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5067 | T16182-XB02-P0UNX-171403 | 2017-11-17 | DHI-TRANSMIT-000998 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1e59135-024d-4d3b-ad1a-d247e88e1e83 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5068 | T16182-XB02-P0UNX-171410 | 2017-11-17 | DHI-TRANSMIT-000998 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0a6589e-052a-4fc5-ae60-8c231f2ef660 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5069 | T16182-CA02-P0UBA-186854 | 2017-11-17 | DHI-WTRAN-000977 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22ddcf5e-f5cf-4af2-85ba-b53120bf0f92 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5070 | T16182-CA00-P0UYP-183201 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdf0ca84-8fab-4e2b-8696-38a5a3668488 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5071 | T16182-CA00-P0UYP-183202 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b1737f1-a4a1-49d2-bcb4-216b8fc6ac90 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5072 | T16182-CA00-P0UYP-183203 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3f3c2e9-852f-4f2b-94d7-549f26a86e3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5073 | T16182-CA00-P0UYP-183204 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c01817c-e400-44b2-a842-b6440e1df34e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5074 | T16182-CA01-P0UYP-183251 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2b18466-ef12-47a4-96cb-b16317a8f237 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5075 | T16182-CA01-P0UYP-183252 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f9ffffc-8291-4199-9351-b21036ac74a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5076 | T16182-CA01-P0UYP-183254 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faba4bfe-2f59-483e-bad3-743646f25f2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5077 | T16182-CA01-P0UYP-183255 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8d38849-4d58-4548-aa51-10827bbfc0ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5078 | T16182-CA02-P0UYP-183256 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=227fde8f-9183-46fc-a8d2-8f2a7298a698 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5079 | T16182-CA02-P0UYP-183257 | 2017-11-17 | DHI-TRANSMIT-000999 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2a9e012-58cd-4022-9c85-27fa4d678649 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5080 | T16182-VE04-P0GKC-173601 | 2017-11-17 | DHI-WTRAN-000978 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39cf9833-fb22-41ec-9cb7-a022f72d7406 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5081 | T16182-XB02-P0GKC-173602 | 2017-11-17 | DHI-WTRAN-000978 | IFR | A | D | TRUE | FALSE | 2018-01-19_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c51a5f0d-4dd5-423a-9a71-806158b643fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5082 | T16182-XB02-P0GKC-173702 | 2017-11-17 | DHI-WTRAN-000978 | IFR | A | D | TRUE | FALSE | 2018-01-19_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=192637e8-1a42-4f16-8208-3c75b2a2ec75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5083 | T16182-YT01-P0BF-150901 | 2017-11-17 | DHI-TRANSMIT-001000 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5e2f15e-5d85-49fc-974d-2cf9cc1ed331 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5084 | T16182-XW03-P0MJ-110053 | 2017-11-17 | DHI-TRANSMIT-001001 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebf154d5-1a50-4b7d-bc04-1ea016c95948 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5085 | T16182-YK10-P0LF-140303 | 2017-11-20 | DHI-WTRAN-000979 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2361168-ca1a-40d6-92d5-728996e5a14e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5086 | T16182-BP00-P0LBA-140011 | 2017-11-20 | DHI-WTRAN-000980 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1b7ffb0-335b-475b-a068-4818e40ff99a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5087 | T16182-BP00-P0LBC-140012 | 2017-11-20 | DHI-WTRAN-000980 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06574485-5c2c-4d5a-b7bb-802695882fac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5088 | T16182-BP00-P0LBG-140016 | 2017-11-20 | DHI-WTRAN-000980 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24ca5d31-40b1-4b33-a515-30037e0c4acf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5089 | T16182-UC02-P0MKA-250015 | 2017-11-20 | DHI-WTRAN-000981 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ae256e9-fa1a-4f51-ae66-3e3b1d401422 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5090 | T16182-YD00-P0SGZ-139631 | 2017-11-20 | DHI-WTRAN-000982 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=922f82ef-ec3b-43d6-afa9-3200699ba64e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5091 | T16182-XG02-P0SGK-136903 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99aed3e3-94a2-4fff-802c-1ae2d37cfd44 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5092 | T16182-XH01-P0SGK-136913 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99b6bbc5-fdb4-4a10-b571-9f759af2ea04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5093 | T16182-YT10-P0SGK-136923 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02bc6947-b865-45d8-9eb9-d2fece2954a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5094 | T16182-YD00-P0SGZ-136931 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1062754c-2af2-4f8a-87bf-c49e59b71b55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5095 | T16182-XG02-P0SGC-137201 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98bb1e6e-5122-4616-81a7-f3c88e13c895 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5096 | T16182-XH01-P0SGC-137211 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd3911e6-2219-4d28-949d-0590ce2205ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5097 | T16182-YT10-P0SGC-137221 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad3698fd-79b8-4c44-890b-2508c6913d32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5098 | T16182-YD00-P0SGZ-139531 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=926ec445-4cf4-416f-9b1b-75898977e4d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5099 | T16182-XG02-P0SGK-139602 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96581e1f-5485-4a51-bb2d-a1fd263e30ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5100 | T16182-XH01-P0SGK-139612 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12ace098-f86d-483b-b27a-3be74ba354c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5101 | T16182-YT10-P0SGK-139622 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6355161f-0430-414c-b73d-b4c5ee4d0c54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5102 | T16182-YD00-P0SGZ-139931 | 2017-11-20 | DHI-TRANSMIT-001006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a919a3e4-9e39-42eb-b423-d137aa45ca1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5103 | T16182-XG02-P0CYE-136744 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd27ea50-c854-42dd-8a2c-5e13bff073fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5104 | T16182-XG02-P0CYE-136844 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89f7a146-6859-4a1f-b414-c86a1b9bff1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5105 | T16182-XG02-P0CYE-137944 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bca03d9-18c4-4e7b-a03b-6b0063ee0aaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5106 | T16182-YD00-P0CYE-139041 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c786ae1a-5654-4ce4-a5bf-ff1f1892a2fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5107 | T16182-XG02-P0CYE-139044 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c35558b2-afb9-4dc6-b142-4af6b97ef603 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5108 | T16182-YD00-P0CYE-139641 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ec2e576-98df-44cb-aa84-9ce6c2113a00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5109 | T16182-YU02-P0CYE-139642 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06712c66-1c7a-4e66-ae06-cd64e4f4d69d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5110 | T16182-YD00-P0CYE-139941 | 2017-11-20 | DHI-TRANSMIT-001007 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9adbafe-3d22-4d7c-a329-ef793f66b502 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5111 | T16182-XH01-P0SGA-136604 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9adb1516-9518-4baa-900e-2284ea7e33af | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5112 | T16182-XG02-P0SGC-137401 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e140710f-afdb-4f5a-8747-31864ea20deb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5113 | T16182-YD00-P0SGZ-137831 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31e2b0ef-027f-4968-9cab-38a614635219 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5114 | T16182-XG02-P0SGK-138702 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fb930e8-c0cf-4e9f-9051-316b94b4735d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5115 | T16182-YD00-P0SGZ-138731 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea9c6662-6668-4d3f-b845-902980d12f70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5116 | T16182-XG02-P0SGK-138802 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=630cab80-bde9-48c4-a367-24b1ee77e60b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5117 | T16182-YD00-P0SGZ-138831 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=305ab84a-6f6b-4415-82e6-f66ddb48dac3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5118 | T16182-XG02-P0SGA-139001 | 2017-11-20 | DHI-TRANSMIT-001008 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba46c3ae-c514-4b66-954d-00903c534dd2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5119 | T16182-XH01-P0LF-140406 | 2017-11-20 | DHI-WTRAN-000983 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd67ed35-9b68-4618-b237-df1a3bc4c35b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5120 | T16182-XH01-P0LF-140407 | 2017-11-20 | DHI-WTRAN-000983 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8debea0d-49c2-4d37-b23a-34387fe564c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5121 | T16182-XH01-P0LF-140408 | 2017-11-20 | DHI-WTRAN-000983 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=999db622-8f14-4a89-a41f-57eb74166958 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5122 | T16182-XH01-P0LF-140411 | 2017-11-20 | DHI-WTRAN-000983 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3ffe26a-04e1-4b7d-972e-ac95215110b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5123 | T16182-XH01-P0LF-140412 | 2017-11-20 | DHI-WTRAN-000983 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12dda473-bcbb-41bb-8fe6-ed11d1813406 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5124 | T16182-XH01-P0LF-140417 | 2017-11-20 | DHI-WTRAN-000983 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c34e0c95-e9f3-4c0d-a56c-0d036b4e79cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5125 | T16182-XH01-P0LF-140419 | 2017-11-20 | DHI-WTRAN-000983 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad3ee59f-cc14-4136-9045-4ac561e985f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5126 | T16182-XS00-P0LD-130201 | 2017-11-20 | DHI-WTRAN-000984 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d43f04d-ae2a-4372-b753-ec510169d86d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5127 | T16182-XW03-P0LD-130205 | 2017-11-20 | DHI-WTRAN-000984 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7e1191f-fbc3-4084-a680-efc1c5b66357 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5128 | T16182-XS01-P8ZEN-125700 | 2017-11-20 | DHI-WTRAN-000985 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50f29a2c-f4be-4da3-b902-f4ee96d73d24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5129 | T16182-YD00-P0MKA-250016 | 2017-11-20 | DHI-TRANSMIT-001009 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46842fca-856f-4150-b2e8-9854b9deceb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5130 | T16182-YD00-P0MKA-250017 | 2017-11-20 | DHI-TRANSMIT-001009 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a3686da-85d7-4049-90ef-a1f78025df0e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5131 | T16182-YD00-P0MKA-250018 | 2017-11-20 | DHI-TRANSMIT-001009 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e88ce903-30b9-40b7-9100-af6355fa9f61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5132 | T16182-YD00-P0MKA-250020 | 2017-11-20 | DHI-WTRAN-000986 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5afcbf0a-826b-4159-8a81-fa17c1ffa7af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5133 | T16182-XG07-P0SAK-133602 | 2017-11-20 | DHI-TRANSMIT-001010 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0656b492-abbb-4cbc-8ab2-f936a31e005b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5134 | T16182-XH02-P0SAK-133604 | 2017-11-20 | DHI-TRANSMIT-001010 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdcdebc1-8392-487c-a716-02d7c30d7438 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5135 | T16182-XW03-P0SAK-133601 | 2017-11-20 | DHI-TRANSMIT-001010 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ff32df2-1181-425f-bb11-968da31706bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5136 | T16182-XW03-P0SAK-133603 | 2017-11-20 | DHI-TRANSMIT-001010 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01745bc7-1cff-44f5-a67d-18400e7656a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5137 | T16182-YS01-P0MKY-290012 | 2017-11-21 | DHI-WTRAN-000987 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5138 | T16182-CV03-P0ZEN-163331 | 2017-11-21 | DHI-TRANSMIT-001012 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a120ce0-eac0-4921-8a2b-4cc26baa9b22 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5139 | T16182-VE04-P0ULC-171301 | 2017-11-21 | DHI-TRANSMIT-001013 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e583dba1-7eb6-4b11-904f-255e4f3a1dae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5140 | T16182-XB02-P0ULC-171302 | 2017-11-21 | DHI-TRANSMIT-001013 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1656fb4a-db8e-4204-b32c-0c046b8de64f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5141 | T16182-XB02-P0ULC-171303 | 2017-11-21 | DHI-TRANSMIT-001013 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42606c4a-7a9e-417a-8657-3f44cdec3cb3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5142 | T16182-VK02-P0ULC-171308 | 2017-11-21 | DHI-TRANSMIT-001013 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=763c1911-3453-454d-8375-8257294cc1d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5143 | T16182-CA02-P0UBA-186855 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc596682-5416-4441-b892-1843c27e94e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5144 | T16182-CA06-P0UBA-186800 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6ee8cdd-9271-4534-90ca-f32b48b03ffb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5145 | T16182-CA00-P0UBA-186801 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f81c0df-530e-4575-b191-5ab029aee32f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5146 | T16182-CA00-P0UBA-186802 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd97e56d-2fcd-40ec-8116-8bf047ccaa9c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5147 | T16182-CA00-P0UBA-186803 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64692c1c-df72-4c8e-8332-288ab7ae7f07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5148 | T16182-CA01-P0UBA-186851 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=194ea18c-937b-45cd-9a62-49c59873c315 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5149 | T16182-CA01-P0UBA-186852 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40e52d8f-14d3-4531-a7ff-86e2ca507aa7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5150 | T16182-CA01-P0UBA-186853 | 2017-11-21 | DHI-TRANSMIT-001014 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d12b72e-450b-4a3b-ab5f-951566020861 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5151 | T16182-YD02-P0SAC-163409 | 2017-11-21 | DHI-WTRAN-000988 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07732b65-4ed2-4dc7-bb05-9e8cc7dffb99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5152 | T16182-YD02-P0SAC-163411 | 2017-11-21 | DHI-WTRAN-000988 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd4cfe77-8384-45cd-accd-74644f288dfa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5153 | T16182-YD02-P0SAC-163412 | 2017-11-21 | DHI-WTRAN-000988 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3118cf83-8c3e-48fd-8714-9c6a5092fcde | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5154 | T16182-YD02-P0SAC-163413 | 2017-11-21 | DHI-WTRAN-000988 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f8188fe-fefe-4983-91fb-807d641a0096 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5155 | T16182-YD02-P0SAC-163414 | 2017-11-21 | DHI-WTRAN-000988 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cf7d9c3-ba3c-4b25-9171-8617849aa471 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5156 | T16182-YD02-P0SAC-163420 | 2017-11-21 | DHI-WTRAN-000988 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=427406ce-2460-427a-a7eb-f883c6e455d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5157 | T16182-YD02-P0SAC-163422 | 2017-11-21 | DHI-WTRAN-000988 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=375a367e-4ba1-4ac8-94b0-534f9053bbf1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5158 | T16182-YK09-P0SMS-128008 | 2017-11-21 | DHI-WTRAN-000989 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbdb3e66-e8a6-400b-8106-6011514b3e41 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5159 | T16182-YS18-P0SMS-128011 | 2017-11-21 | DHI-WTRAN-000990 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbabb7af-eb7e-4988-8f84-6f860983d526 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5160 | T16182-CC05-P0ZEN-180002 | 2017-11-21 | DHI-WTRAN-000991 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53bf9fea-a9cd-4272-a876-8d492994212d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5161 | T16182-CC05-P0ZEN-180019 | 2017-11-21 | DHI-WTRAN-000991 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a44cda8b-52b9-4b22-9e05-407c02873126 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5162 | T16182-YK09-P0LCB-127004 | 2017-11-21 | DHI-TRANSMIT-001015 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b5b187a-19f7-4f08-8fad-091c04f1df27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5163 | T16182-XH01-P0LF-140404 | 2017-11-22 | DHI-TRANSMIT-001019 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0e6f389-7a9c-4c76-8d6e-8bb930a0d40f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5164 | T16182-YR05-P0CJN-290004 | 2017-11-22 | DHI-TRANSMIT-001020 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7f8a1bf-2f17-4081-a09d-695300698fd7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5165 | T16182-YS01-P0MKY-290011 | 2017-11-22 | DHI-TRANSMIT-001020 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c57a8a0-f407-4044-92bc-34bf826dd190 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5166 | T16182-YS01-P0MKY-290013 | 2017-11-22 | DHI-TRANSMIT-001020 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80892c92-ad46-4c3c-b935-062f79112533 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5167 | T16182-YV02-P0MKG-260022 | 2017-11-22 | DHI-TRANSMIT-001021 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd3b2341-e806-46c7-81a5-326ec4e5fcfe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5168 | T16182-YV02-P0MKW-260021 | 2017-11-22 | DHI-TRANSMIT-001021 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4b60680-72d4-4ee3-ba5b-521252ec365c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5169 | T16182-CA00-P0UCB-180601 | 2017-11-22 | DHI-TRANSMIT-001022 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d9382fa-ab4b-4c1a-9bcd-feb2c6bad7ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5170 | T16182-CA00-P0UCB-180602 | 2017-11-22 | DHI-TRANSMIT-001022 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f61d11c-b9a1-4321-9ce0-048fb27a0186 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5171 | T16182-CA00-P0UCB-180603 | 2017-11-22 | DHI-TRANSMIT-001022 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c886e648-ad8f-4193-bb81-b604d6223df4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5172 | T16182-CA00-P0UCB-180608 | 2017-11-22 | DHI-TRANSMIT-001022 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eefad4fd-d80c-45ca-a166-c6a3602dfb4e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5173 | T16182-CA00-P0UBA-181204 | 2017-11-22 | DHI-TRANSMIT-001023 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdbbf96c-8dad-4223-9076-70436f4eda8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5174 | T16182-CA00-P0UBA-181206 | 2017-11-22 | DHI-TRANSMIT-001023 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01f6b2a9-8532-482e-81d3-f89ea26f057f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5175 | T16182-CA00-P0UBA-181304 | 2017-11-22 | DHI-TRANSMIT-001023 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93218671-fc50-4808-a8ed-240ca5d0195b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5176 | T16182-CA00-P0UBA-181306 | 2017-11-22 | DHI-TRANSMIT-001023 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3891bd4-b47b-42b3-8c80-48713e166994 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5177 | T16182-CA00-P0UCB-180611 | 2017-11-22 | DHI-TRANSMIT-001024 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82137d39-0d4b-48e3-880b-1caf90cc74af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5178 | T16182-YU03-P0CHB-151121 | 2017-11-22 | DHI-WTRAN-000992 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d053857b-e5ac-4a39-afd2-adb6315b132a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5179 | T16182-YU03-P0CHB-151122 | 2017-11-22 | DHI-WTRAN-000992 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54b8a90d-5292-420b-b37d-40a2122ebe8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5180 | T16182-YF00-P0BA-150401 | 2017-11-22 | DHI-TRANSMIT-001025 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=645fbd8b-1711-469b-a6d2-853e03a5305d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5181 | T16182-YT10-P0ZEN-150306 | 2017-11-22 | DHI-TRANSMIT-001025 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a9b6ae8-acfd-4bd4-bf67-e0ee3501a77c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5182 | T16182-YK08-P0PCA-126515 | 2017-11-23 | DHI-TRANSMIT-001026 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6e40c96-e21b-4816-bc37-e24f07e4ccc2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5183 | T16182-XB02-P0UMX-171056 | 2017-11-23 | DHI-TRANSMIT-001027 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8868b8d7-f68c-4d89-90d6-7246a7612836 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5184 | T16182-XB02-P0UMX-171058 | 2017-11-23 | DHI-TRANSMIT-001027 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee4e6b4e-051d-4c4a-b5d2-3cabcceb4088 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5185 | T16182-XB02-P0UMX-171005 | 2017-11-23 | DHI-TRANSMIT-001028 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=765aa867-f5b1-472f-9f70-7d2d6dfb6f67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5186 | T16182-XJ00-P6MKA-260003 | 2017-11-23 | DHI-TRANSMIT-001029 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c947ff3a-6f9f-4c4d-81c0-d0ee667bd78a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5187 | T16182-XJ00-P7MKA-260006 | 2017-11-23 | DHI-TRANSMIT-001029 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74c679a6-2710-4f48-bceb-e2e073e6ba64 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5188 | T16182-CV03-P8ZEN-125604 | 2017-11-23 | DHI-WTRAN-000993 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4162a97-b8f1-4e30-a4ca-60c9633721fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5189 | T16182-CA06-P0UYB-183500 | 2017-11-23 | DHI-WTRAN-000994 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8358f2c-c40d-4297-b7ba-2bec72d6bfc9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5190 | T16182-CA00-P0UYB-183501 | 2017-11-23 | DHI-WTRAN-000994 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=638fef6b-d164-428f-bb46-b8de81e14775 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5191 | T16182-CA00-P0UYB-183502 | 2017-11-23 | DHI-WTRAN-000994 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d216ae94-f3ae-4f2f-a0e1-8ae684aeda77 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5192 | T16182-CA01-P0UYB-183551 | 2017-11-23 | DHI-WTRAN-000994 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c052be6-c66e-4b9e-81b0-eda4b4f1040f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5193 | T16182-CA01-P0UYB-183552 | 2017-11-23 | DHI-WTRAN-000994 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75dd9a03-b890-4bf6-9a2a-6ac8fc3770cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5194 | T16182-CA02-P0UYB-183553 | 2017-11-23 | DHI-WTRAN-000994 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66c364c8-584c-4663-bdc4-71f499294cba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5195 | T16182-CA02-P0UYB-183554 | 2017-11-23 | DHI-WTRAN-000994 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82a4ca21-2951-448a-954c-ce241d0eb7d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5196 | T16182-XG02-P0SGA-137701 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf100691-dee0-420a-888f-9a205a6be72f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5197 | T16182-XH01-P0SGA-137711 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2ea0f70-5c1f-4d34-8a5b-464ad6d8b218 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5198 | T16182-YD00-P0SGZ-137731 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a0d4ce6-af64-44e4-b363-980e0eafccbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5199 | T16182-XG02-P0SGE-139502 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40d32c90-277c-42f8-abe3-021934b4d5db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5200 | T16182-XH01-P0SGE-139512 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2aaf1ce8-7239-49be-8117-3201a6a7407c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5201 | T16182-YT10-P0SGE-139522 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec5a5126-da21-4dde-a150-e864a4c33ab8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5202 | T16182-XG02-P0SGE-139603 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23fc0e91-e6e0-45d3-a3fb-52f9abfc1faf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5203 | T16182-XH01-P0SGE-139613 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b91a56d5-e966-4857-bccb-de2eecd9fd98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5204 | T16182-YT10-P0SGE-139623 | 2017-11-23 | DHI-TRANSMIT-001030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47ef10fb-fed2-45d0-b302-4303005fc2fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5205 | T16182-XH01-P0SGA-139511 | 2017-11-23 | DHI-WTRAN-000995 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acec26af-a52d-4be6-993d-90cd2b52a33d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5206 | T16182-XH01-P0SGA-139611 | 2017-11-23 | DHI-WTRAN-000995 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93c13461-b297-4497-8db5-32950104e59c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5207 | T16182-XG02-P0SGA-139501 | 2017-11-23 | DHI-WTRAN-000995 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b550b947-130a-4785-a52f-b976ab4d1dc2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5208 | T16182-XG02-P0SGA-139601 | 2017-11-23 | DHI-WTRAN-000995 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87879231-971b-4701-9341-8defeb662e51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5209 | T16182-YD04-P0ZEN-152007 | 2017-11-23 | DHI-WTRAN-000996 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03f71df2-9995-46e7-87be-84ac8494a3fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5210 | T16182-YD04-P0ZEN-152011 | 2017-11-23 | DHI-TRANSMIT-001031 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b0a03fb-f063-41f7-bfa1-d395e52487cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5211 | T16182-YD04-P0ZEN-152006 | 2017-11-23 | DHI-TRANSMIT-001031 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec18deec-8118-42f7-a7f0-317cec9c684c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5212 | T16182-YD04-P0ZEN-152005 | 2017-11-23 | DHI-TRANSMIT-001031 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=972b8d95-9cce-45c9-a01b-8f2c77a21071 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5213 | T16182-YE00-P0ZEN-152709 | 2017-11-23 | DHI-TRANSMIT-001031 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ccfa878-da15-4772-bba4-cf5d1e7a695f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5214 | T16182-YE00-P0ZEN-152716 | 2017-11-23 | DHI-TRANSMIT-001031 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f4f6e6e-e412-4ce7-9dd3-ded7d6d48d5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5215 | T16182-XG02-P0SGC-139901 | 2017-11-23 | DHI-TRANSMIT-001032 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56febfe2-13ce-4297-a9cb-7181e7d42d65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5216 | T16182-XH01-P0SGC-139911 | 2017-11-23 | DHI-TRANSMIT-001032 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2965320-7084-46fc-91b6-f90a7f9cfbb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5217 | T16182-YT10-P0SGC-139921 | 2017-11-23 | DHI-TRANSMIT-001032 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51b6c5cb-ecb8-47e0-93be-0850b99b56c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5218 | T16182-YL01-P0SCA-127516 | 2017-11-23 | DHI-WTRAN-000997 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4aa0bc97-9553-4e4d-aaf0-656cbdd6b354 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5219 | T16182-YL01-P0SCA-127517 | 2017-11-23 | DHI-WTRAN-000997 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f8b0079-ec27-4079-a6fa-214af56f6f25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5220 | T16182-YR05-P0SCA-127523 | 2017-11-23 | DHI-WTRAN-000997 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a8021c8-fa51-4609-8b9b-e4d467957383 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5221 | T16182-YD00-P0GM-128501 | 2017-11-23 | DHI-TRANSMIT-001033 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a834286-845d-40d5-823d-9cdad2ba53fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5222 | T16182-DE00-P0ZEN-152870 | 2017-11-23 | DHI-TRANSMIT-001034 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4cec409-e131-4525-994f-b13cbdba4112 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5223 | T16182-CA00-P0UYE-183301 | 2017-11-24 | DHI-TRANSMIT-001035 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b41b888f-7ef2-4b24-be86-4676fcc1fdac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5224 | T16182-CA00-P0UYE-183302 | 2017-11-24 | DHI-TRANSMIT-001035 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8dff9606-98fc-4a0c-8abb-6d7aa3c8eb69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5225 | T16182-CA00-P0UYE-183303 | 2017-11-24 | DHI-TRANSMIT-001035 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c253e40-55e1-4f10-b54f-a5544830fbf5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5226 | T16182-CA01-P0UYE-183351 | 2017-11-24 | DHI-WTRAN-000998 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70f175ac-ce0d-4fdd-9aaa-11c7fec13bf2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5227 | T16182-CA01-P0UYE-183352 | 2017-11-24 | DHI-WTRAN-000998 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbc6a281-60d6-4135-9f6e-5f81c43731c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5228 | T16182-CA01-P0UYE-183353 | 2017-11-24 | DHI-WTRAN-000998 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65801fbc-aeab-495e-9a17-4bcb9505a4bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5229 | T16182-CA02-P0UYE-183354 | 2017-11-24 | DHI-WTRAN-000998 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=470e2d1b-a965-4879-aa90-9c94ef3fe29c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5230 | T16182-CA02-P0UYE-183355 | 2017-11-24 | DHI-WTRAN-000998 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f4c0eec-4ec4-478f-a0d6-d1e32d2c64d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5231 | T16182-CA00-P0ULD-183902 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31859754-aef6-4dd0-8c36-a5ec8ea6c605 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5232 | T16182-CA00-P0ULD-183903 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10773e76-3f7d-4a9d-98d1-615406e13e53 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5233 | T16182-CA00-P0ULD-183904 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bea1ba09-56d1-41cd-be66-a75d119bca2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5234 | T16182-CA00-P0ULD-183905 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5cf827e6-5e17-4023-abb7-085844981046 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5235 | T16182-CA00-P0ULD-183906 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6762eedf-6c67-4c75-9ee9-01aafadedacb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5236 | T16182-CA00-P0ULD-183908 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f30f28aa-573c-45ea-8658-3494e6bb0620 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5237 | T16182-CA00-P0ULD-183909 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df834b49-113a-4118-a1ba-50b71cbd2b54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5238 | T16182-CA00-P0ULD-183910 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c617b2a0-cce7-451e-b82c-974ad1094461 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5239 | T16182-CA01-P0ULD-183953 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8360afb3-a6c5-4bbe-997b-8e5a76fe7116 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5240 | T16182-CA02-P0ULD-183959 | 2017-11-24 | DHI-TRANSMIT-001036 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4040ca1f-9865-4bf0-9a18-53934f9449cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5241 | T16182-YD00-P0PCA-126503 | 2017-11-24 | DHI-TRANSMIT-001037 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb83c2fc-4f3d-4bf9-8b67-fb1e9119a32d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5242 | T16182-CA05-P0UYP-183281 | 2017-11-24 | DHI-WTRAN-000999 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7958deed-ae3f-4e57-bb3f-cc9e1b616005 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5243 | T16182-CA05-P0UYP-183282 | 2017-11-24 | DHI-WTRAN-000999 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d886c502-f3e9-4d97-bc45-198d7c653a52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5244 | T16182-CA05-P0UYP-183283 | 2017-11-24 | DHI-WTRAN-000999 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e42fb91f-7c81-46ac-93c0-44e032996cfb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5245 | T16182-CA05-P0UYP-183284 | 2017-11-24 | DHI-WTRAN-000999 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70c53b44-f40d-4b7d-bcee-6823dd7acf00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5246 | T16182-CA05-P0UYP-183285 | 2017-11-24 | DHI-WTRAN-000999 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94c0b73f-f189-4d01-a5f6-8a5baed0676f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5247 | T16182-XB02-P0UBN-172202 | 2017-11-24 | DHI-TRANSMIT-001038 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2edbd410-8d55-43da-b070-854262df8146 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5248 | T16182-VK02-P0UBN-172203 | 2017-11-24 | DHI-TRANSMIT-001038 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8831acad-ad92-4c11-b12d-12fdbb66154f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5249 | T16182-XF00-P0SCA-127524 | 2017-11-24 | DHI-WTRAN-001000 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d39b05d-4ce9-4a7c-967e-0291c03ff91f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5250 | T16182-YL01-P0PCA-126526 | 2017-11-24 | DHI-WTRAN-001001 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebd61e28-dbbe-48c1-8128-3e88b9ec1bf5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5251 | T16182-XB02-P0UZT-172702 | 2017-11-24 | DHI-TRANSMIT-001039 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=805ce5e8-4af2-4bc6-aadf-ccee948c93ec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5252 | T16182-XB02-P0UZT-172703 | 2017-11-24 | DHI-TRANSMIT-001039 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12972820-8c1b-4c70-b391-3795ae133423 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5253 | T16182-VK02-P0UZT-172704 | 2017-11-24 | DHI-TRANSMIT-001039 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be19f3b9-bec7-4f1b-b979-e568541ed4bb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5254 | T16182-VK02-P0UZT-172713 | 2017-11-24 | DHI-TRANSMIT-001039 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b16290be-f32c-47c7-a8ef-c7c78b8bf143 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5255 | T16182-XB02-P0UZT-172716 | 2017-11-24 | DHI-TRANSMIT-001039 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb3c5933-ace6-481c-a686-30401388959f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5256 | T16182-XJ00-P0MBH-140116 | 2017-11-24 | DHI-TRANSMIT-001040 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd929009-d233-402d-89c3-2056b67656de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5257 | T16182-XW03-P0SAF-134701 | 2017-11-24 | DHI-WTRAN-001002 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9195cbb8-7e21-401a-8eea-9c25b503255d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5258 | T16182-XG07-P0SAF-134702 | 2017-11-24 | DHI-WTRAN-001002 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1aa37f8f-cfd8-426a-a616-af52eeee683e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5259 | T16182-XW03-P0SAF-134703 | 2017-11-24 | DHI-WTRAN-001002 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0f2ec01-a61e-4133-8484-eb61e7ff83ef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5260 | T16182-XH02-P0SAF-134704 | 2017-11-24 | DHI-WTRAN-001002 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f27012ee-db35-41e4-9d13-42f5496b809f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5261 | T16182-YB11-P0LAC-126301 | 2017-11-24 | DHI-WTRAN-001003 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba61af65-6c4f-478f-911a-1051f15b1c5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5262 | T16182-YB11-P0LAC-126351 | 2017-11-24 | DHI-WTRAN-001003 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5775dc57-8291-4dc9-bff7-d160c6266772 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5600 | T16182-CA06-P0UYE-183300 | 2017-11-24 | DHI-WTRAN-000998 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=911c754c-0fdf-4c08-aa87-da7b8ba34217 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5263 | T16182-YF00-P0CJD-161022 | 2017-11-27 | DHI-WTRAN-001004 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7ae8833-4551-4ce4-9da4-f014344f5e12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5264 | T16182-YF00-P0CJD-161025 | 2017-11-27 | DHI-WTRAN-001004 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ca13218-b64b-4bb5-9e3b-b5531f5e65cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5265 | T16182-YF00-P0CJD-161021 | 2017-11-27 | DHI-TRANSMIT-001041 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0c2123d-9a40-4177-8710-8b07aaa72f04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5266 | T16182-CA00-P0UBA-181001 | 2017-11-27 | DHI-TRANSMIT-001042 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0101729e-0c82-47ec-845f-6bc8945308dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5267 | T16182-CA00-P0UBA-181101 | 2017-11-27 | DHI-TRANSMIT-001042 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6aed5b70-0b5b-4332-8c83-93c94e8c6201 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5268 | T16182-CA00-P0UBA-186101 | 2017-11-27 | DHI-TRANSMIT-001042 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b72ec95a-0e0a-4d8c-8566-5340316aa0e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5269 | T16182-XB02-P0UEM-171702 | 2017-11-27 | DHI-TRANSMIT-001043 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d6fef7c-3e13-4db0-9631-db12e97bfee2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5270 | T16182-XB02-P0UEM-171708 | 2017-11-27 | DHI-TRANSMIT-001043 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8df14e4c-b176-402a-8c3e-7b3cd35cdfd9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5271 | T16182-VK02-P0UEM-171711 | 2017-11-27 | DHI-TRANSMIT-001043 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ffed978-9a10-4f30-9e42-9994f1ac97f1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5272 | T16182-YD02-P0ZEN-165521 | 2017-11-27 | DHI-TRANSMIT-001044 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff0967b7-94be-43c0-b5d3-c323bab935e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5273 | T16182-XL00-P0MKA-260035 | 2017-11-27 | DHI-TRANSMIT-001045 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db028f6f-3135-453f-b547-65bbbbb8f850 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5274 | T16182-YQ01-P0ZEN-152315 | 2017-11-27 | DHI-WTRAN-001005 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21a658e0-dc3a-4cfd-8b32-c618282fad8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5275 | T16182-YT10-P0ZEN-152217 | 2017-11-27 | DHI-WTRAN-001005 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95f3b417-929c-428a-9926-c5399cf8c0ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5276 | T16182-YB11-P0ZEN-152415 | 2017-11-27 | DHI-WTRAN-001005 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20d3eb23-f2fd-442a-9829-41387307ae68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5277 | T16182-YS01-P0MKY-290008 | 2017-11-27 | DHI-TRANSMIT-001046 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e874e9d8-90c0-4069-b7f2-316b4f9c1ab5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5278 | T16182-XH01-P0SGK-138512 | 2017-11-27 | DHI-WTRAN-001006 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e4e64cb-0fff-48a4-bdba-e1c823eae068 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5279 | T16182-XG02-P0SGK-138502 | 2017-11-27 | DHI-WTRAN-001006 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6cdd90a-1817-495d-96fc-98d5349bbeac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5280 | T16182-YT10-P0SGK-138522 | 2017-11-27 | DHI-WTRAN-001006 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a12c2b27-dbdb-4842-a09b-e1058369227f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5281 | T16182-XG02-P0SGK-139002 | 2017-11-27 | DHI-TRANSMIT-001047 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53452f3b-c949-4bb8-bc5c-25f8f811e34d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5282 | T16182-XH01-P0SGA-139011 | 2017-11-27 | DHI-TRANSMIT-001047 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47e1c0f0-f1d7-4802-8bc6-7cd36d23c5b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5283 | T16182-XH01-P0SGK-139012 | 2017-11-27 | DHI-TRANSMIT-001047 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28b7e1c9-6ff2-4dab-8d45-3e56ada4e4bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5284 | T16182-YT10-P0SGK-139023 | 2017-11-27 | DHI-TRANSMIT-001047 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a763d031-8f70-4657-a4b0-8656f64e0dd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5285 | T16182-YD00-P0SGZ-139031 | 2017-11-27 | DHI-TRANSMIT-001047 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6b630d5-57d6-4fb0-a908-9a09864ad791 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5286 | T16182-YD00-P0SGZ-137431 | 2017-11-27 | DHI-TRANSMIT-001047 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=850790cc-ea5f-4806-8c30-e46215b43de5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5287 | T16182-YU02-P0CYA-154011 | 2017-11-27 | DHI-TRANSMIT-001048 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9af949fb-60e9-4ef9-925e-c85ae34bda04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5288 | T16182-YU02-P0CYM-154013 | 2017-11-27 | DHI-TRANSMIT-001048 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31a84365-c8e5-4967-ba0f-7504c46e3fc1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5289 | T16182-YQ08-P0CY-154031 | 2017-11-27 | DHI-TRANSMIT-001048 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=764954f0-60dd-489e-89e0-4b5a759318de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5290 | T16182-YQ08-P0CY-154050 | 2017-11-27 | DHI-TRANSMIT-001048 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c46196a-015e-4557-b251-21de5c9b4fed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5291 | T16182-CA03-P0UMY-185169 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=404ba573-1213-46d2-9bbf-63c3cf94b287 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5292 | T16182-CA03-P0UMY-185170 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d767c457-1836-4124-b21d-3f664b4026de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5293 | T16182-CA03-P0UMY-185171 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08881aa6-2c74-46c9-ad61-cf38c7f651ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5294 | T16182-CA03-P0UMY-185172 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7ba8643-4c61-4c11-8ad3-cbf883ede9fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5295 | T16182-CA03-P0UMY-185173 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=873be192-2518-48fe-ba94-ca9eeef17556 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5296 | T16182-CA03-P0UMY-185174 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57e1572a-b61a-418a-a4dc-e34c97810848 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5297 | T16182-CA03-P0UMY-185175 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=484666f5-a136-49a9-9d27-100301c37be4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5298 | T16182-CA03-P0UMY-185176 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fa80b92-3766-4430-b6fa-2f9415ae10d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5299 | T16182-CA03-P0UMY-185177 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c9671d5-07c2-4a0e-aa19-abd5f8b54ec6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5300 | T16182-CA06-P0UMY-185192 | 2017-11-28 | DHI-WTRAN-001007 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41fb0821-883a-4ed9-8aec-54945cd03a78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5301 | T16182-YR05-P0GM-128511 | 2017-11-28 | DHI-WTRAN-001008 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67e8ee8b-0860-45d8-a3b0-5a8b3d1f29f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5302 | T16182-XJ00-P0EKC-140117 | 2017-11-28 | DHI-TRANSMIT-001053 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94cafa29-1a17-4201-b346-3a54decb0ae9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5303 | T16182-YD00-P0GHC-129051 | 2017-11-28 | DHI-TRANSMIT-001054 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38d9e6ee-67ca-4eca-bb18-ec1fe049a837 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5304 | T16182-YK09-P0GHC-129053 | 2017-11-28 | DHI-TRANSMIT-001054 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3015e4c-6743-4951-bcb7-3a3f8ad4b517 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5305 | T16182-YK00-P0GHC-129064 | 2017-11-28 | DHI-WTRAN-001009 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50572ed8-2cee-4ced-8d2d-64988ca00db8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5306 | T16182-YL00-P0GHC-129063 | 2017-11-28 | DHI-WTRAN-001009 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38e5861f-42b5-40cf-a2a6-ce48e9c64247 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5307 | T16182-YS02-P0LAC-126302 | 2017-11-28 | DHI-WTRAN-001010 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eed36b20-86a4-40d5-9b6b-1368bb2e109a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5308 | T16182-YS02-P0LAC-126352 | 2017-11-28 | DHI-WTRAN-001010 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff30cbdf-1024-4d56-b0f0-b24b4d1b1ee1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5309 | T16182-YS01-P0MKY-290012 | 2017-11-29 | DHI-WTRAN-001011 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5310 | T16182-CQ02-P8ZEN-125019 | 2017-11-29 | INT-IFC-171129-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=6bd1b157-0bc8-4a36-9a6d-5ba2f33ef6f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5311 | T16182-CQ02-P0MBA-121099 | 2017-11-29 | INT-IFC-171129-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=fdc0c047-6444-4780-bc71-daa7a8b08b8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5312 | T16182-YK08-P0MAG-123017 | 2017-11-29 | DHI-WTRAN-001012 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3f77ab0-df72-4864-88aa-682caba976ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5313 | T16182-XS00-P0MAG-123004 | 2017-11-29 | DHI-TRANSMIT-001055 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70bcf90f-a812-4076-b84d-3df22e226bf8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5314 | T16182-YT01-P0MAG-123036 | 2017-11-29 | DHI-TRANSMIT-001055 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83555b5b-94b9-483a-bafe-171ade68fd79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5315 | T16182-CY03-P0MKG-260032 | 2017-11-29 | DHI-TRANSMIT-001056 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0fee62f7-49dd-456d-91ca-c1be5f9058f5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5316 | T16182-CY03-P0MKW-260031 | 2017-11-29 | DHI-TRANSMIT-001056 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=428faaba-44a2-4143-974d-5b976ad07cb9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5317 | T16182-XW03-P0SAI-133901 | 2017-11-29 | DHI-TRANSMIT-001057 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd2fff8d-5237-480d-a04e-dab138409e84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5318 | T16182-XG07-P0SAI-133902 | 2017-11-29 | DHI-TRANSMIT-001057 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3511bc2f-c532-43ec-97d4-cfa9ed1513de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5319 | T16182-XW03-P0SAI-133903 | 2017-11-29 | DHI-TRANSMIT-001057 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3dfdb2ad-7b31-4ad5-b277-486c089c256e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5320 | T16182-XH02-P0SAI-133904 | 2017-11-29 | DHI-TRANSMIT-001057 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ece783a9-c83e-4df9-ae87-16418d76f7e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5321 | T16182-YD02-P0ZEN-165519 | 2017-11-29 | DHI-TRANSMIT-001058 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef193f80-2cc2-4561-9977-a9ea43b44888 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5322 | T16182-YK08-P0GKC-420050 | 2017-11-29 | DHI-WTRAN-001013 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b73d0479-4f96-4c41-956c-3a8091e9a61e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5323 | T16182-CA03-P0UMY-185153 | 2017-11-29 | DHI-TRANSMIT-001059 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c0e0a2d-7b56-4b28-b062-a3013bd00b8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5324 | T16182-CA03-P0UMY-185154 | 2017-11-29 | DHI-TRANSMIT-001059 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1a62efc-9af5-48d1-9e09-d50c08c9b906 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5325 | T16182-CA05-P0UCB-180681 | 2017-11-29 | DHI-TRANSMIT-001060 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efdc4780-ff4a-4c96-8961-ffcd443d264f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5326 | T16182-CA05-P0UCB-180682 | 2017-11-29 | DHI-TRANSMIT-001060 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abc7f453-0ae7-4d57-8882-5b31a57a27ce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5327 | T16182-CA05-P0UCB-180685 | 2017-11-29 | DHI-TRANSMIT-001060 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b20cbff-89d3-4129-b62f-a1803ee00ba9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5328 | T16182-CA05-P0UCB-180686 | 2017-11-29 | DHI-TRANSMIT-001060 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1fa3b52-4344-4b22-bb65-65b6f1fc27d8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5329 | T16182-CA05-P0UCB-180687 | 2017-11-29 | DHI-TRANSMIT-001060 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05a80d7d-1c65-49c9-a2c3-4f2510da3a16 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5330 | T16182-CA05-P0UYC-182985 | 2017-11-29 | DHI-TRANSMIT-001061 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f6030a5-be8c-4925-b25d-68ed679cebc6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5331 | T16182-YS00-P0CJN-290001 | 2017-11-29 | DHI-TRANSMIT-001062 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae6472ff-11a8-4ec7-ab9b-60b36a177109 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5332 | T16182-YU03-P0CFA-151181 | 2017-11-30 | DHI-WTRAN-001014 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6560fea7-aeca-491e-ba5f-c4d298084faf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5333 | T16182-YD00-P0CFA-151171 | 2017-11-30 | DHI-WTRAN-001014 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=795a4ebf-f368-4f42-8c2f-7b2bb4341c2c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5334 | T16182-YD00-P0CHB-151111 | 2017-11-30 | DHI-WTRAN-001014 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d24989c9-ee9d-409d-9923-87f5a5bae7d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5335 | T16182-YD00-P0CHB-151112 | 2017-11-30 | DHI-WTRAN-001014 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35087ad1-cfea-434d-82a5-66153ce0c1b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5336 | T16182-CA00-P0UBA-181303 | 2017-11-30 | DHI-TRANSMIT-001067 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b11e8750-3f15-48cf-935f-2895d0515465 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5337 | T16182-CA01-P0UBA-181353 | 2017-11-30 | DHI-TRANSMIT-001067 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54dc7355-fcf4-406c-a7e5-a196ee9abd52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5338 | T16182-YF00-P0CJA-161041 | 2017-11-30 | DHI-TRANSMIT-001068 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76d8807a-3fd6-4bb3-9722-4b3510e35d47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5339 | T16182-YT01-P0SAA-136001 | 2017-11-30 | DHI-TRANSMIT-001069 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fc5999a-45f5-4ec4-abc1-944a2cafb160 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5340 | T16182-CA00-P0UBA-181001 | 2017-11-30 | DHI-TRANSMIT-001070 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b49b022f-687f-42e0-9409-5db9232e760e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5341 | T16182-CA00-P0UBA-181101 | 2017-11-30 | DHI-TRANSMIT-001070 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f385e8e-5485-4f16-bec8-c19b49db8daa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5342 | T16182-YK00-P0PCA-126525 | 2017-11-30 | DHI-WTRAN-001015 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfd42cb3-ce26-472f-a45c-8f2288767915 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5343 | T16182-CV03-P0ZEN-165731 | 2017-11-30 | DHI-TRANSMIT-001071 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15499e05-2412-4370-b0cb-e73f2602cd2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5344 | T16182-YF00-P0SCA-127518 | 2017-11-30 | DHI-WTRAN-001016 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa48938d-02c5-4c47-b2b4-cffa1d3878dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5345 | T16182-YF02-P0SCA-127514 | 2017-11-30 | DHI-WTRAN-001016 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c62639e-26f4-4c02-8147-1e5b2ad16f1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5346 | T16182-XL00-P0STG-130503 | 2017-11-30 | DHI-TRANSMIT-001072 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7120569f-a1e2-4b0c-bcf9-655be1da2684 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5347 | T16182-YS01-P0MKY-290009 | 2017-11-30 | DHI-WTRAN-001017 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5986f0b7-362e-4432-bdac-3e92b931b5ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5348 | T16182-CV03-P0GM-128508 | 2017-11-30 | DHI-WTRAN-001018 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=140b07fb-9f11-4ca6-8e92-a51e34b0ab54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5349 | T16182-YK00-P0GM-128509 | 2017-11-30 | DHI-WTRAN-001018 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76000807-87f7-4803-8e57-f8afb97e83bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5350 | T16182-YL00-P0GM-128512 | 2017-11-30 | DHI-WTRAN-001018 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f5daed5-d13e-4755-a720-0150c8e000af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5351 | T16182-YU03-P0BB-150836 | 2017-11-30 | DHI-WTRAN-001019 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c349571a-6c4e-47a5-a5e5-4e5add451387 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5352 | T16182-YK01-P0LAC-126056 | 2017-11-30 | DHI-WTRAN-001020 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d042b33-a629-48e1-bcf6-e71803c116d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5353 | T16182-YD00-P0CYE-138541 | 2017-11-30 | DHI-WTRAN-001021 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86d0759f-c2f8-4166-9500-9c2a8f1a17a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5354 | T16182-YU02-P0CYE-138542 | 2017-11-30 | DHI-WTRAN-001021 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aefbb8f9-ef74-4ede-8080-fdeedc302a14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5355 | T16182-CA03-P0HBD-189001 | 2017-12-04 | INT-IFC-171204-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=9a9246f0-0c45-4623-a3d8-f831bb2ed1e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5356 | T16182-XB02-P0UAZ-172608 | 2017-12-04 | DHI-TRANSMIT-001078 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fcf2b47-2d5a-4a6e-9b48-fc86e79964cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5357 | T16182-VE04-P0GHC-173801 | 2017-12-04 | DHI-WTRAN-001022 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66ce13e7-52ee-4f02-bfd8-1a74cab8c217 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5358 | T16182-XB02-P0GHC-173802 | 2017-12-04 | DHI-WTRAN-001022 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c85d8c70-a1dd-4c09-a62e-544e67c29c08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5359 | T16182-XG02-P6MAA-220027 | 2017-12-04 | DHI-WTRAN-001023 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46eea079-c099-4fb5-b1e8-6db5a946cc7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5360 | T16182-XJ00-P0LCM-140105 | 2017-12-04 | DHI-WTRAN-001024 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f93d80c-6ebc-4285-a5e5-c4c958ed43ec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5361 | T16182-XB02-P0ULX-172582 | 2017-12-04 | DHI-TRANSMIT-001079 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12e9f3a7-633f-46ce-89f9-e50733868973 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5362 | T16182-XB02-P0ULX-172583 | 2017-12-04 | DHI-TRANSMIT-001079 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7043500-866d-4738-9cc6-af202e569c0d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5363 | T16182-XB02-P0ULX-172584 | 2017-12-04 | DHI-TRANSMIT-001079 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f5da9e1-58ed-44ac-b4b6-76ad149e1ad6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5364 | T16182-XB02-P0ULX-172585 | 2017-12-04 | DHI-TRANSMIT-001079 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8eeec3a1-08d4-4df6-861c-0b08cd65aa81 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5365 | T16182-CA00-P0USG-182701 | 2017-12-04 | DHI-TRANSMIT-001080 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd84fe3f-6748-4ace-82bb-73334834981d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5366 | T16182-CA00-P0USG-182702 | 2017-12-04 | DHI-TRANSMIT-001080 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c97c93c-813a-4222-80c5-2593c910f525 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5367 | T16182-CA00-P0USG-182703 | 2017-12-04 | DHI-TRANSMIT-001080 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1359bd5b-7aca-41bc-aa4b-ad63f9870bfd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5368 | T16182-CA01-P0USG-182752 | 2017-12-04 | DHI-TRANSMIT-001080 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1ef2ea7-54b1-4b25-8984-e14c0eb7ba5a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5369 | T16182-CA00-P0UYC-182901 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba018cb2-78e1-4b0c-9df0-10185f4a2ebd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5370 | T16182-CA00-P0UYC-182902 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 2 | DR | TRUE | TRUE | 2017-12-04_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=548f6133-24ae-43a9-b216-0497356e0846 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5371 | T16182-CA00-P0UYC-182903 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4b43ddc-178f-4230-aa6b-ee89326a38e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5372 | T16182-CA00-P0UYC-182904 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 2 | DR | TRUE | TRUE | 2017-12-04_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6aa8e5d-afa8-4984-a474-eb2f28826fec | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5373 | T16182-CA00-P0UYC-182905 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc7136b9-4484-4127-83cf-96cba5901c3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5374 | T16182-CA00-P0UYC-182906 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d5279db-c64b-4bcd-8fe7-b2bbd1bcb083 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5375 | T16182-CA00-P0UYC-182907 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 1 | DR | TRUE | TRUE | 2017-12-04_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95304775-c7bb-43d8-8011-5f6a1361d07f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5376 | T16182-CA00-P0UYC-182908 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 1 | DR | TRUE | TRUE | 2017-12-04_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d229de4-0780-4a16-a643-acc0bb72bf30 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5377 | T16182-CA01-P0UYC-182952 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 3 | DR | TRUE | TRUE | 2017-12-04_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45db8b13-a29c-4dea-95b4-83659dc7b965 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5378 | T16182-CA01-P0UYC-182953 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efa81cf8-3367-4c4e-9c67-aec7fc5b7f3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5379 | T16182-CA01-P0UYC-182954 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cde2cee-ca4e-4a25-926b-b6e99837eb4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5380 | T16182-CA01-P0UYC-182955 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e414f712-04f4-4ce7-8ba4-03a583a91f6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5381 | T16182-CA02-P0UYC-182957 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=283d268f-ccb1-4ab6-a868-231d93782d1a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5382 | T16182-CA02-P0UYC-182958 | 2017-12-04 | DHI-TRANSMIT-001081 | IFC | 2 | DR | TRUE | TRUE | 2017-12-04_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a95df1bd-71a0-4796-a471-e76d7622e1b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5383 | T16182-YD00-P0SGZ-138531 | 2017-12-04 | DHI-WTRAN-001025 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bee0d3e-552d-4548-acc9-f63db149dc31 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5384 | T16182-YU02-P0CYE-139942 | 2017-12-04 | DHI-TRANSMIT-001082 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb7703e2-ce33-4442-908f-7e8a01e92595 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5385 | T16182-YU02-P0CYE-137242 | 2017-12-04 | DHI-TRANSMIT-001082 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17234c99-f360-4adc-ae43-1d13832a9485 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5386 | T16182-YD00-P0CYE-137241 | 2017-12-04 | DHI-TRANSMIT-001082 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9a29f6e-419f-4e85-84c2-b5c775c8b11e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5387 | T16182-CA03-P0UMY-185160 | 2017-12-05 | DHI-TRANSMIT-001083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c926b1b1-245e-44db-8a2f-ac015ea26f7a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5388 | T16182-CA03-P0UMY-185162 | 2017-12-05 | DHI-TRANSMIT-001083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d2e7d5d-9c9c-456b-94af-a12c337bdf25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5389 | T16182-CA03-P0UMY-185163 | 2017-12-05 | DHI-TRANSMIT-001083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3723d8f8-3bef-4e35-a0ae-d6e4abbb2fe8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5390 | T16182-CA03-P0UMY-185164 | 2017-12-05 | DHI-TRANSMIT-001083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb9e08fc-11b2-41fb-8cfa-2c35497bf7e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5391 | T16182-CA03-P0UMY-185165 | 2017-12-05 | DHI-TRANSMIT-001083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32298797-4aae-4a20-b5a0-a1a2892f798f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5392 | T16182-CA03-P0UMY-185166 | 2017-12-05 | DHI-TRANSMIT-001083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=886e9ec4-a1ad-44f4-bd5e-29506383d502 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5393 | T16182-YT01-P0LF-110601 | 2017-12-05 | DHI-TRANSMIT-001084 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72e4c1e7-bb82-4d17-8602-26b72c1e4344 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5394 | T16182-YK10-P0LF-110602 | 2017-12-05 | DHI-TRANSMIT-001084 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40582c31-a8b5-41df-a4ab-612b7413f72b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5395 | T16182-YU02-P0CYE-136942 | 2017-12-05 | DHI-TRANSMIT-001085 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3499daf9-2454-43fa-9f32-070481f6a46c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5396 | T16182-YU02-P0CYE-138842 | 2017-12-05 | DHI-TRANSMIT-001085 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5711580-8e0b-4c6d-bb24-6e3204bcf620 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5397 | T16182-YU02-P0CYE-139042 | 2017-12-05 | DHI-TRANSMIT-001085 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b251662-45e8-42b2-9b4f-fcfb459e2c2b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5398 | T16182-XB02-P0UEG-171502 | 2017-12-05 | DHI-TRANSMIT-001086 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4aad809-ec2f-4acc-89b6-316ca50cbb27 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5399 | T16182-XB02-P0UEG-171504 | 2017-12-05 | DHI-TRANSMIT-001086 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea88143a-2ec1-4ce5-a8fc-1bbcc3da0dae | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5400 | T16182-CN00-P0ZEN-110702 | 2017-12-05 | DHI-TRANSMIT-001087 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4becbb1d-fdbe-430f-aefd-716390cf55a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5401 | T16182-CN00-P0ZEN-110705 | 2017-12-05 | DHI-WTRAN-001026 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b9a82a7-0638-43d9-ac28-cce5c8dbf09e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5402 | T16182-CA00-P0UBA-181202 | 2017-12-06 | DHI-TRANSMIT-001089 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7736c3f-8058-4334-a40d-0b2b89facfea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5403 | T16182-CA00-P0UBA-181301 | 2017-12-06 | DHI-TRANSMIT-001089 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=709a0aca-4aa0-48a0-b66b-c2dd27357fb6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5404 | T16182-CA00-P0UBA-181302 | 2017-12-06 | DHI-TRANSMIT-001089 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0170d0aa-8927-4ada-8b44-e64187ad8c93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5405 | T16182-VN01-P0MAG-123045 | 2017-12-06 | INT-IFC-171206-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=5b664e9d-3014-4c8b-a8b4-ca062e435153 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5406 | T16182-XS00-P0LD-130201 | 2017-12-06 | DHI-TRANSMIT-001090 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a869083-afa7-4178-ad5e-4dc00838db84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5407 | T16182-XW03-P0LD-130205 | 2017-12-06 | DHI-TRANSMIT-001090 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db4798e9-a619-40fc-97a9-2675583dad01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5408 | T16182-CV03-P0PUR-411001 | 2017-12-06 | DHI-TRANSMIT-001091 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efd89eaf-f8ef-4fc6-921b-e87b7f0b2302 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5409 | T16182-CV03-P0PUR-411011 | 2017-12-06 | DHI-TRANSMIT-001091 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ede79ac-79a3-4243-8655-1c56fd1eec67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5410 | T16182-CV03-P0PUR-411021 | 2017-12-06 | DHI-TRANSMIT-001091 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8ba6e86-3488-4cf0-b41b-879374f3b56d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5411 | T16182-CV03-P0PUR-411031 | 2017-12-06 | DHI-TRANSMIT-001091 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbfc7090-bbc2-45e5-a283-2fe0f1005984 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5412 | T16182-CA05-P0UST-182082 | 2017-12-06 | DHI-TRANSMIT-001092 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdd9aaad-5d45-444a-abb4-784972035188 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5413 | T16182-CA05-P0UST-182083 | 2017-12-06 | DHI-TRANSMIT-001092 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0c557ce-2310-418d-a13c-486e09b8548f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5414 | T16182-CA05-P0UST-182085 | 2017-12-06 | DHI-TRANSMIT-001092 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=668aba75-66f1-430b-8294-e36549899256 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5415 | T16182-XN00-P0MKA-260036 | 2017-12-06 | DHI-TRANSMIT-001093 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df5744b0-9834-4940-a0f9-a96858ced7cd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5416 | T16182-YK10-P0LCP-410001 | 2017-12-06 | DHI-TRANSMIT-001094 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7d2de28-82a5-42e0-a282-314753715571 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5417 | T16182-YK10-P0GHC-410011 | 2017-12-06 | DHI-TRANSMIT-001094 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7efdf61f-967f-4df8-a2ff-29209c2a3921 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5418 | T16182-YK10-P0GKB-410021 | 2017-12-06 | DHI-TRANSMIT-001094 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c44b4b6-f86f-4923-b1e3-3f4c7c119b61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5419 | T16182-YK10-P0GKB-410031 | 2017-12-06 | DHI-TRANSMIT-001094 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dcf3b41f-5ca0-4bcf-a866-d50b3dcd05bc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5420 | T16182-YT01-P0MKA-260020 | 2017-12-06 | DHI-WTRAN-001027 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=898b66a1-c50f-40f4-ad25-8c588b04b7cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5421 | T16182-YT01-P0LAC-126005 | 2017-12-06 | DHI-TRANSMIT-001095 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d849a9c7-a0a1-42ba-b55e-88cd171fa114 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5422 | T16182-YT01-P0LAC-126055 | 2017-12-06 | DHI-TRANSMIT-001095 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3de770b4-6686-46b2-9b1d-f58f8ba0bf5e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5423 | T16182-XB02-P0UEM-171708 | 2017-12-06 | DHI-TRANSMIT-001096 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d95ca91-66d4-4e43-bf2c-6647a141e0bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5424 | T16182-XS00-P0GM-120022 | 2017-12-06 | DHI-TRANSMIT-001097 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2fe82ef-5787-4976-9406-cd33e55b666d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5425 | T16182-YT02-P8ZEN-125718 | 2017-12-06 | DHI-TRANSMIT-001098 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=751ef3f7-451c-453d-b740-38d1efa7e4e6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5426 | T16182-CC08-P8QHA-125300 | 2017-12-06 | DHI-WTRAN-001028 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e362af3-7a71-47f8-b490-24343bb58a50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5427 | T16182-XA00-P8QHL-125402 | 2017-12-06 | DHI-TRANSMIT-001099 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85c09bce-2abf-4010-86b3-9ce3412d7dac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5428 | T16182-CA03-P0HBD-189001 | 2017-12-07 | INT-IFC-171207-01 | INTERNAL IFC | 1 | D | TRUE | FALSE | 2017-12-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=8955c014-3f04-4aa4-bc1f-90349e5a3dbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5429 | T16182-CA03-P0HBD-189002 | 2017-12-07 | INT-IFC-171207-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=736ed01b-cb1e-478e-82ea-f5a302229f99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5430 | T16182-CA05-P0UGD-181981 | 2017-12-07 | DHI-TRANSMIT-001100 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4704ef56-83ea-4670-bbb4-1a01ab6c066e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5431 | T16182-CA05-P0UGD-181982 | 2017-12-07 | DHI-TRANSMIT-001100 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7877b3e4-6705-4cad-a10e-80237317895c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5432 | T16182-CA05-P0UGD-181983 | 2017-12-07 | DHI-TRANSMIT-001100 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40064eaa-5eef-4d98-a29c-61cb9f42e3d1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5433 | T16182-CA05-P0UGD-181984 | 2017-12-07 | DHI-TRANSMIT-001100 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de11ead4-6341-49ad-8b2e-b7fd38f77af8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5434 | T16182-CA05-P0UGD-181985 | 2017-12-07 | DHI-TRANSMIT-001100 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5070ae6-4ce1-4baf-89a4-6b3cbf8a500a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5435 | T16182-CA05-P0UGD-181986 | 2017-12-07 | DHI-TRANSMIT-001100 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b89f7961-d962-471e-9310-86c6d75119aa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5436 | T16182-CV03-P0ZEN-165711 | 2017-12-07 | DHI-TRANSMIT-001101 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=711511aa-8fb8-480e-be03-67a57dd665fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5437 | T16182-CC08-P8QHB-125151 | 2017-12-07 | DHI-WTRAN-001029 | IFI | 2 | DR | TRUE | TRUE | 2017-12-07_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a70f91b-9c4f-4593-9625-fb029ceb3e44 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5438 | T16182-YL30-P8ZEN-125514 | 2017-12-07 | DHI-TRANSMIT-001102 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0378f185-8c3d-4e6e-abb6-dd3c386c1d06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5439 | T16182-YT02-P8ZEN-125713 | 2017-12-07 | DHI-TRANSMIT-001102 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6e1823a-83b8-413a-8724-380d65a7ee43 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5440 | T16182-YT02-P8ZEN-125719 | 2017-12-07 | DHI-TRANSMIT-001102 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fa2141b-d728-4af5-88b0-fc3dfdca1e26 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5441 | T16182-CC02-P8QHB-125164 | 2017-12-07 | DHI-TRANSMIT-001103 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c500181-bd9e-489c-ac57-5e9e4d901028 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5442 | T16182-CA00-P0UST-182006 | 2017-12-07 | DHI-WTRAN-001030 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87002e15-78c1-49bd-ad49-996385e230db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5443 | T16182-XB02-P0UAG-172100 | 2017-12-07 | DHI-TRANSMIT-001104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9760bc4-6c20-4174-9fea-9304b726741a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5444 | T16182-XB02-P0UAG-172162 | 2017-12-07 | DHI-TRANSMIT-001104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a69960f-1c99-4787-a37f-3e76083b5b8a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5445 | T16182-XB02-P0UAG-172168 | 2017-12-07 | DHI-TRANSMIT-001104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0fa540d-6f53-4b56-b88f-d71c03832c77 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5446 | T16182-VE04-P0UAG-172101 | 2017-12-07 | DHI-TRANSMIT-001104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5810183b-0437-44a8-b9d6-bbc0773d49f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5447 | T16182-XB02-P0UAG-172102 | 2017-12-07 | DHI-TRANSMIT-001104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12dc40c9-84a7-43f3-ad2e-d772ecb867eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5448 | T16182-XB02-P0UAG-172108 | 2017-12-07 | DHI-TRANSMIT-001104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8361d493-19ea-4d2e-91b6-6fab817ea8b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5449 | T16182-VK02-P0UAG-172109 | 2017-12-07 | DHI-TRANSMIT-001104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d547765-4025-4f57-a264-21ff9cc0d3fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5450 | T16182-YM01-P0LCB-127010 | 2017-12-07 | DHI-WTRAN-001031 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5929def7-8e4e-4ff9-903a-9d6e6e718b96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5451 | T16182-YM01-P0LCB-127039 | 2017-12-07 | DHI-WTRAN-001031 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34adb2be-80b1-4485-9f72-a77bee2c47d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5452 | T16182-CA05-P0UYP-183281 | 2017-12-07 | DHI-TRANSMIT-001105 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0d16109-be33-405c-b7f1-efef958bdb21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5453 | T16182-CA05-P0UYP-183282 | 2017-12-07 | DHI-TRANSMIT-001105 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d6ebc2c-8ed0-4051-80dd-861cf1d3e710 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5454 | T16182-CA05-P0UYP-183283 | 2017-12-07 | DHI-TRANSMIT-001105 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5321ebd8-0c9d-418a-9e8d-7a08c6a6316e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5455 | T16182-CA05-P0UYP-183284 | 2017-12-07 | DHI-TRANSMIT-001105 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4caae00d-3b09-43c0-99f2-096003ad9baa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5456 | T16182-CA05-P0UYP-183285 | 2017-12-07 | DHI-TRANSMIT-001105 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35dc105b-d8b5-4960-ad0a-6d9f7f049214 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5457 | T16182-YK08-P0PCA-126512 | 2017-12-07 | DHI-TRANSMIT-001106 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f44975a-f241-4243-ba62-68aad6703450 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5458 | T16182-XN00-P0PCA-126507 | 2017-12-07 | DHI-WTRAN-001032 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f82ceaf7-aa81-46bf-83d6-776d8f7a1ef2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5459 | T16182-VK02-P8UTH-172008 | 2017-12-07 | DHI-TRANSMIT-001107 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e03ac8f6-8f89-4ba1-97e1-c53b0f75408e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5460 | T16182-XB02-P8UTH-172007 | 2017-12-07 | DHI-TRANSMIT-001107 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4a4ab1b-b05a-432a-97a2-4d554945d4b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5461 | T16182-YD02-P0LB-122063 | 2017-12-08 | DHI-WTRAN-001033 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32ba3472-7fa9-436a-a4e5-f9cd9f4b8647 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5462 | T16182-UE00-P0LB-122012 | 2017-12-08 | DHI-TRANSMIT-001112 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a149385f-86d2-4b53-b17c-808311cc4fbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5463 | T16182-YD00-P0LB-122054 | 2017-12-08 | DHI-TRANSMIT-001112 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdb6ff3b-0a7b-4e10-aa2f-8ad18ebd83d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5464 | T16182-YD02-P0ZEN-165503 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95727d6c-e8dd-4f53-968f-259df48dfc00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5465 | T16182-YD02-P0ZEN-165507 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abe7c853-f68e-47b5-86ad-917808f02545 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5466 | T16182-YD02-P0ZEN-165517 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23555322-5e3e-44c0-a495-7d60adc7d0cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5467 | T16182-YD02-P0ZEN-165520 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3eb1a408-949e-4731-a28b-1fe350e316cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5468 | T16182-YD02-P0ZEN-165526 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=676e9bfd-e4a4-44a5-b199-c5672aae9b3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5469 | T16182-YD02-P0ZEN-165527 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e2036f4-c8de-47e6-bbb9-5dba23ffc123 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5470 | T16182-YD02-P0ZEN-165528 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4d3db43-0621-44ba-a5a2-e2d5dc9096db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5471 | T16182-YD02-P0ZEN-165529 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2470482-6310-427b-be0c-94d6f928676c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5472 | T16182-YD02-P0ZEN-165575 | 2017-12-08 | DHI-WTRAN-001034 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e6ee58e-7c30-406d-a14c-0df12995dd63 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5473 | T16182-YD02-P0ZEN-165501 | 2017-12-08 | DHI-TRANSMIT-001113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbb44ad4-54a2-442a-8179-47be7b1b60e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5474 | T16182-YD02-P0ZEN-165502 | 2017-12-08 | DHI-TRANSMIT-001113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82bea507-ffc2-478b-8eff-deb2b3a44a00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5475 | T16182-YD02-P0ZEN-165571 | 2017-12-08 | DHI-TRANSMIT-001113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c95913e2-791e-49f0-bf63-11efcde1a67c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5476 | T16182-YD02-P0ZEN-165572 | 2017-12-08 | DHI-TRANSMIT-001113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6dde7b2-af2a-480a-96fd-3ca3c1986f8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5477 | T16182-YD02-P0ZEN-165573 | 2017-12-08 | DHI-TRANSMIT-001113 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90f76c39-c078-4a21-963f-76867a388785 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5478 | T16182-XK00-P0PCA-126508 | 2017-12-08 | DHI-WTRAN-001035 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ebd558e-6cbb-4b6d-a85c-2477f357f84d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5479 | T16182-YD00-P0CYE-138741 | 2017-12-08 | DHI-TRANSMIT-001114 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3dea3b8a-f150-4347-a333-fc46d8827fa8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5480 | T16182-YU02-P0CYE-138742 | 2017-12-08 | DHI-TRANSMIT-001114 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15b43428-2eae-4e82-957e-3db1c82b1c9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5481 | T16182-YU02-P0CYE-137742 | 2017-12-08 | DHI-TRANSMIT-001114 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1fd1db3-8ed2-46d9-91f4-be9e2b884ede | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5482 | T16182-YU02-P0CYE-139442 | 2017-12-08 | DHI-TRANSMIT-001114 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b08fa8d-d568-4efa-af0b-cf34f7db54b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5483 | T16182-YT01-P0MKA-260019 | 2017-12-08 | DHI-TRANSMIT-001115 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf3f954a-ac16-4d68-a205-e68d9d19acfa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5484 | T16182-YT01-P0SGA-136609 | 2017-12-08 | DHI-TRANSMIT-001116 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ded6dd0-01b4-432e-8dac-78e2352e6f73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5485 | T16182-YT01-P0SGA-136611 | 2017-12-08 | DHI-TRANSMIT-001116 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5cefb406-e9cc-4c66-ab2d-97b798a17ec9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5486 | T16182-YT01-P0SGE-136612 | 2017-12-08 | DHI-TRANSMIT-001116 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14762e5b-90b7-4c33-a302-2b8e859d0711 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5487 | T16182-YT01-P0SGC-136613 | 2017-12-08 | DHI-TRANSMIT-001116 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dacae59b-802f-4bb0-9333-2f8374253503 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5488 | T16182-XG02-P0LAC-126003 | 2017-12-08 | DHI-TRANSMIT-001117 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15d4ea6a-0d9a-4f58-84d0-fe3f4f720338 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5489 | T16182-XG02-P0SGA-136901 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16d60ec7-9f21-4435-ba88-e1dde1834fbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5490 | T16182-XG02-P0SGE-136902 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96a4d94a-0daa-4934-9887-97bc94128d00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5491 | T16182-XH01-P0SGA-136911 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3637803-6736-420d-a68d-ea70eae96ded | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5492 | T16182-XH01-P0SGE-136912 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7b58857-06c1-4826-bf68-a91a735d2666 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5493 | T16182-YT10-P0SGE-136922 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d3cc138-b584-4d58-8911-82c0f77662c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5494 | T16182-XH01-P0SGC-137411 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9dd8290f-7468-4ca3-9a70-320809a16c8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5495 | T16182-YT10-P0SGC-137421 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71091c47-a507-4386-97c0-201c4bf41fd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5496 | T16182-XG02-P0SGC-138101 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a79ff81-735f-46a9-915b-769ede7a0f47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5497 | T16182-XH01-P0SGC-138111 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=847c4a5d-400a-4549-b6e1-35ab79d1bad1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5498 | T16182-YD00-P0SGZ-138131 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af52edee-fe05-4fa7-9f74-4ee5d84a7e58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5499 | T16182-XH01-P0SGK-138712 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71b9e894-cde8-4b6f-9311-b0744a2df559 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5500 | T16182-YT10-P0SGK-138722 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c32a48b5-dc65-4346-a0a2-ae482ce73170 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5501 | T16182-XH01-P0SGK-138812 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae46f5a6-f90f-4eec-8cf7-28f85ec71336 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5502 | T16182-YT10-P0SGK-138822 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4421e8f-de21-4424-bf5c-9d24e4179048 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5503 | T16182-YD00-P0SGZ-139631 | 2017-12-08 | DHI-TRANSMIT-001118 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7d0de2e-0229-439d-a516-91c676a6fbcd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5504 | T16182-YE03-P0BAU-152527 | 2017-12-08 | DHI-WTRAN-001036 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd4d3a2d-cd42-4e4b-8efe-47b7cf7c0ce2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5505 | T16182-YE03-P0BAU-152512 | 2017-12-08 | DHI-TRANSMIT-001119 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80d94433-f11d-489d-9482-11758e87885b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5506 | T16182-YE03-P0BAU-152518 | 2017-12-08 | DHI-TRANSMIT-001119 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99741b06-bcf3-4ae2-90cc-404f969ad761 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5507 | T16182-YE03-P0BAU-152526 | 2017-12-08 | DHI-TRANSMIT-001119 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd1deeeb-462d-409b-8824-9c72414685b0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5508 | T16182-YE03-P0BAU-152528 | 2017-12-08 | DHI-TRANSMIT-001119 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16463257-aaef-45a9-872c-24206b12c05e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5509 | T16182-YE01-P0BAU-152608 | 2017-12-08 | DHI-WTRAN-001037 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c362343-f431-4bec-84e2-5dfd8fd1a7a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5510 | T16182-YE01-P0BAU-152614 | 2017-12-08 | DHI-WTRAN-001037 | IFI | 0 | D | TRUE | FALSE | 2018-03-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecc0e58a-51ef-4452-bc10-fc54d8ea3ecf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5511 | T16182-YE03-P0BAU-152515 | 2017-12-08 | DHI-WTRAN-001037 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7ee5913-9ca6-4da3-923c-ae941d0e4426 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5512 | T16182-YE00-P0ZEN-152725 | 2017-12-08 | DHI-TRANSMIT-001120 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=969068fe-3eba-4df4-b693-7969745456cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5513 | T16182-YE00-P0ZEN-152724 | 2017-12-08 | DHI-TRANSMIT-001120 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70100bfa-356b-4f2c-9fc9-0a6e426de217 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5514 | T16182-YE00-P0ZEN-152715 | 2017-12-08 | DHI-TRANSMIT-001120 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30922a75-1ebf-4209-97a0-3c7b733ffa7a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5515 | T16182-YD04-P0ZEN-152012 | 2017-12-08 | DHI-TRANSMIT-001120 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cbadd70-29be-4eff-b820-0f3bc84b4923 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5516 | T16182-YD04-P0ZEN-152008 | 2017-12-08 | DHI-TRANSMIT-001120 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=082274d0-9844-454d-ad74-0349cbc6672c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5517 | T16182-YD04-P0ZEN-152009 | 2017-12-08 | DHI-TRANSMIT-001120 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf56cecf-bc8a-45df-9145-f20b78f3424c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5518 | T16182-YT01-P0QC-130307 | 2017-12-08 | DHI-WTRAN-001038 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac5c2340-caa2-4726-90e3-642ff01c7af5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5519 | T16182-XW03-P0SAR-134101 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=538cdac7-41f3-4913-8446-d7e1e9300e4c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5520 | T16182-XG07-P0SAR-134102 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b68c29e-c80c-4980-9abb-1648be547977 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5521 | T16182-XW03-P0SAR-134103 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2fd52f6-74b7-4ef5-9367-207688158c0b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5522 | T16182-XH02-P0SAR-134104 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=670b693f-6fdc-4363-9939-93c9d6de5625 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5523 | T16182-XW03-P0SAR-134201 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8bf458b-f887-4a0c-96a5-5396b24297e3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5524 | T16182-XG07-P0SAR-134202 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7dd72b5c-7315-4624-99a3-c7c4897ab486 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5525 | T16182-XW03-P0SAR-134203 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abe55578-c8c7-4ad6-8fcf-6003451dfc33 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5526 | T16182-XH02-P0SAR-134204 | 2017-12-08 | DHI-TRANSMIT-001121 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a06899f7-6061-492b-91e3-13fbbb3a5529 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5527 | T16182-XJ00-P0LB-122027 | 2017-12-11 | DHI-TRANSMIT-001125 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c3bfa83-0a9f-4d30-af55-6fadf82bf269 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5528 | T16182-YB11-P0ZEN-152404 | 2017-12-11 | DHI-WTRAN-001039 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8496222b-26d6-487d-91e4-8e71d7265044 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5529 | T16182-YQ01-P0ZEN-152304 | 2017-12-11 | DHI-WTRAN-001039 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=026e4bb7-a869-4477-b7d1-6e512f8bb442 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5530 | T16182-YT10-P0ZEN-152206 | 2017-12-11 | DHI-WTRAN-001039 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb860e11-ab83-4ccc-ad0b-d38f553389a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5531 | T16182-YL01-P0MBA-121025 | 2017-12-11 | DHI-WTRAN-001040 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51653670-2acc-4e19-a486-798b4a1c1d04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5532 | T16182-BP00-P0LAB-140014 | 2017-12-11 | DHI-TRANSMIT-001126 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16df79d3-ce77-4c84-adcb-de6a8a56f2c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5533 | T16182-XG02-P0QC-130303 | 2017-12-11 | DHI-TRANSMIT-001127 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e925161-7c18-4637-9b8f-13f7a0efe1c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5534 | T16182-XW03-P0QC-130304 | 2017-12-11 | DHI-WTRAN-001041 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11fd3582-d5ea-4642-ae8e-c27209e5ad7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5535 | T16182-YD00-P0QC-130302 | 2017-12-11 | DHI-WTRAN-001041 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee2e5266-4b93-4722-8bd9-c769ce857966 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5536 | T16182-YU03-P0BAT-150631 | 2017-12-11 | DHI-TRANSMIT-001128 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a91cf4b-57e7-4b81-af07-c0dcad75b8e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5537 | T16182-YD02-P0SAC-163419 | 2017-12-11 | DHI-WTRAN-001042 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40b44531-1fb2-4fe0-93e6-5c45f5fe7926 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5538 | T16182-YR05-P0SAY-163423 | 2017-12-11 | DHI-WTRAN-001043 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beba24dd-0e80-466e-9a2c-ef96c1cbb6de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5539 | T16182-CA00-P0UBA-181001 | 2017-12-11 | DHI-TRANSMIT-001129 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43f8ffde-aa87-41a0-9769-aa2f9f9370bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5540 | T16182-CA00-P0UBA-181101 | 2017-12-11 | DHI-TRANSMIT-001129 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5633d07-869c-4b53-b038-d701c19a4572 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5541 | T16182-CA00-P0UBA-186101 | 2017-12-11 | DHI-TRANSMIT-001129 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3c50914-19d1-4307-ac00-b6926f083580 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5542 | T16182-YD02-P0SAC-163408 | 2017-12-11 | DHI-TRANSMIT-001130 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74955021-882b-4998-bf90-124bf258ecdc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5543 | T16182-YD00-P0LB-122006 | 2017-12-12 | DHI-WTRAN-001044 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3da5acd-1916-4bc7-8714-074e99c5024e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5544 | T16182-YD00-P0SMG-128016 | 2017-12-12 | DHI-WTRAN-001045 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e89a973a-2238-46ce-8a37-b9df03c2381f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5545 | T16182-YD00-P0SMS-128029 | 2017-12-12 | DHI-WTRAN-001045 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a78e1676-1efe-423d-adee-06ed51ffdf9b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5546 | T16182-YD00-P0SMM-128031 | 2017-12-12 | DHI-WTRAN-001045 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1329f219-69bd-43d5-bcdb-234e41c48904 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5547 | T16182-YD00-P0SMU-128015 | 2017-12-12 | DHI-WTRAN-001045 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=099cd40d-dee9-4a69-a56b-fc3d5cd3ada1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5548 | T16182-YD00-P0SMQ-128014 | 2017-12-12 | DHI-WTRAN-001045 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=586ddbd8-dbfe-4241-927c-8d502cb505aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5549 | T16182-YD00-P0SMC-128028 | 2017-12-12 | DHI-WTRAN-001045 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aeedd019-25f2-44a5-8846-3867e65ea1c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5550 | T16182-YD00-P0SMG-128030 | 2017-12-12 | DHI-WTRAN-001045 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23e31483-30db-4c39-aefb-6e0d01159b88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5551 | T16182-XB00-P0GM-128506 | 2017-12-12 | DHI-WTRAN-001046 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93d12c12-a670-4c45-8048-fd16ecf97254 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5552 | T16182-CC05-P8QHB-125161 | 2017-12-12 | DHI-WTRAN-001047 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cfa53cf-ff62-4f65-898c-0f49af6f50d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5553 | T16182-YU02-P0BT-151021 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b510bc4-63ec-4049-88da-1789bdaef631 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5554 | T16182-YU03-P0BT-151061 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b58164ae-890d-4184-8be2-e57cdf7779be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5555 | T16182-YU03-P0BT-151066 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=288ee93e-710e-445b-9e28-6aca9b9612c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5556 | T16182-YU03-P0BT-151071 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63c465c2-e485-4d38-b840-3d8a49a2780d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5557 | T16182-YU02-P0BT-151026 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd5cf9bf-6dff-4a7c-af35-dbf078909a11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5558 | T16182-YU02-P0BT-151031 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf9ad135-f8a3-44fa-9544-06a9265bfb58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5559 | T16182-YD00-P0BT-151041 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faeadc63-1eeb-45bd-aed8-5c772d042237 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5560 | T16182-YD00-P0BT-151046 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1387c069-f704-40f9-9c2c-0d7d91d1d2ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5561 | T16182-YD00-P0BT-151051 | 2017-12-12 | DHI-WTRAN-001048 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33e08299-10e3-4cea-9284-4c692f4e2062 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5562 | T16182-CA00-P0ULD-183902 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=196debf5-cf7d-43b0-bea7-665575131670 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5563 | T16182-CA00-P0ULD-183903 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8d557fc-49f2-498f-acc4-7a9a931c8212 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5564 | T16182-CA00-P0ULD-183904 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17417d58-e693-4af5-ac56-c69cff2a351b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5565 | T16182-CA00-P0ULD-183906 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2906bd62-d530-4bed-8679-bd3d602a97f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5566 | T16182-CA00-P0ULD-183908 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c76df88-3e69-4029-a799-2e8e2e707832 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5567 | T16182-CA00-P0ULD-183909 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 1 | D | TRUE | FALSE | 2017-12-12_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bfed64e-5b76-4b6a-ac34-1c470afa5829 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5568 | T16182-CA00-P0ULD-183910 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE | 2017-12-12_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=def9fac7-d06f-4c7c-beb9-4e1506d8a864 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5569 | T16182-CA02-P0ULD-183955 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 5 | D | TRUE | FALSE | 2017-12-12_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=037cd775-48ad-4034-b09a-407abc59a074 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5570 | T16182-CA02-P0ULD-183959 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d30903ef-d299-4737-a743-2aafda307047 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5571 | T16182-CA02-P0ULD-183961 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 2 | D | TRUE | FALSE | 2017-12-12_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b11d4115-a69b-4bb4-81aa-342ce63cc7b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5572 | T16182-CA03-P0ULD-183964 | 2017-12-12 | DHI-TRANSMIT-001131 | IFC | 1 | D | TRUE | FALSE | 2017-12-12_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=834074e0-efa6-4b14-9611-f69f5dd5eb97 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5573 | T16182-XB02-P0UZT-172702 | 2017-12-12 | DHI-TRANSMIT-001132 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff8cf534-b76c-477d-99c1-b94a0176b87d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5574 | T16182-XB02-P0UZT-172703 | 2017-12-12 | DHI-TRANSMIT-001132 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00ae5333-57e2-422e-a925-d07b25b546db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5575 | T16182-VK02-P0UZT-172704 | 2017-12-12 | DHI-TRANSMIT-001132 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46903d69-4d0e-441f-890a-d6e637df5b53 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5576 | T16182-VK02-P0UZT-172713 | 2017-12-12 | DHI-TRANSMIT-001132 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=340b8150-aca1-4e6c-9496-a788ba9cdcb7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5577 | T16182-XB02-P0UZT-172716 | 2017-12-12 | DHI-TRANSMIT-001132 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9b4a4a4-e2a8-4959-b8b7-a20e2beabf4d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5578 | T16182-YV02-P0SCA-127511 | 2017-12-12 | DHI-WTRAN-001049 | IFI | 3 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5579 | T16182-XJ00-P0EKG-124077 | 2017-12-13 | INT-IFC-171213-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=36f3f2a0-4a15-431d-97be-df1d4c005b27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5580 | T16182-YF00-P0CJD-161022 | 2017-12-13 | DHI-TRANSMIT-001133 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50afc16c-5e78-48d1-b945-e55df0ab0023 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5581 | T16182-YF00-P0CJD-161025 | 2017-12-13 | DHI-TRANSMIT-001133 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47fd0610-f1d4-4d80-b005-973dd4eb7ae4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5582 | T16182-YL01-P0CRN-161117 | 2017-12-13 | DHI-WTRAN-001050 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68ae1bd5-93c5-4f32-a044-c9ae7be47927 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5583 | T16182-YE03-P0BAU-152504 | 2017-12-13 | DHI-TRANSMIT-001134 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5cda3af-1d1f-4780-80f8-3defcd98595b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5584 | T16182-YT10-P0BAU-152503 | 2017-12-13 | DHI-TRANSMIT-001134 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41dd81db-3937-48bc-a0ca-d456a4974211 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5585 | T16182-YT10-P0CYE-139443 | 2017-12-13 | DHI-WTRAN-001051 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c8dba3f-763e-402b-abff-f9e52a3482a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5586 | T16182-XG02-P0CYE-139444 | 2017-12-13 | DHI-TRANSMIT-001135 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=809e5f0f-725b-427e-b95c-862a4a136ad0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5587 | T16182-XH01-P0SGA-136711 | 2017-12-13 | DHI-TRANSMIT-001135 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7eaf047-5f91-4a44-b6fe-2d385af68bc4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5588 | T16182-XH01-P0SGE-136712 | 2017-12-13 | DHI-TRANSMIT-001135 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01bdce02-e71d-411c-816f-db42376c9978 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5589 | T16182-XG02-P6LCA-110008 | 2017-12-13 | DHI-TRANSMIT-001136 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3d13054-5b87-4451-978f-240f89267d99 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5590 | T16182-XG02-P0LAA-110009 | 2017-12-13 | DHI-TRANSMIT-001136 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbda9ec5-394d-410a-8973-d57cf7c42d66 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5591 | T16182-XG02-P0PGB-110010 | 2017-12-13 | DHI-TRANSMIT-001136 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6fd9c47-3536-483a-ad7f-56ebf3460c19 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5592 | T16182-XG02-P0GHC-110011 | 2017-12-13 | DHI-TRANSMIT-001136 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f777fcd-ed17-4134-8d31-e6a0609ba619 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5593 | T16182-XG02-P1EKC-110014 | 2017-12-13 | DHI-TRANSMIT-001136 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46122d40-6ccd-470c-846f-4e350b52a611 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5594 | T16182-XG02-P0SGE-138602 | 2017-12-13 | DHI-WTRAN-001052 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67248327-6991-4fd8-a02f-02792d71b4c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5595 | T16182-XH01-P0SGE-138612 | 2017-12-13 | DHI-WTRAN-001052 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4678d43-e0b5-444e-babf-d1b505d51f7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5596 | T16182-YT10-P0SGE-138622 | 2017-12-13 | DHI-WTRAN-001052 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=512bbf31-a52a-4f2b-8502-506d89d37bef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5597 | T16182-XH01-P0SGA-137811 | 2017-12-13 | DHI-TRANSMIT-001137 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c041b995-23e5-4301-9564-33c490eb815c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5598 | T16182-YD00-P0CYE-137741 | 2017-12-13 | DHI-TRANSMIT-001137 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=420021bc-60d1-4136-ac43-b2751237de5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5599 | T16182-CN00-P0ZEN-110705 | 2017-12-13 | DHI-TRANSMIT-001138 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4527b53-ed7a-45c4-9990-ea255822b664 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5601 | T16182-DP00-P8ZEN-125506 | 2017-12-14 | DHI-TRANSMIT-001141 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae241834-63c7-4c3a-a47a-4cdb32d806f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5602 | T16182-UC02-P8QHA-125303 | 2017-12-14 | DHI-TRANSMIT-001141 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09670cce-66aa-41fd-ba94-6ddcc1b9c624 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5603 | T16182-XJ00-P0LBA-140101 | 2017-12-14 | DHI-TRANSMIT-001142 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cacbcd5-092a-4ce4-9740-9a06e923352d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5604 | T16182-CV03-P0LD-130219 | 2017-12-14 | DHI-WTRAN-001053 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=778f67c7-2580-41a5-88ea-9cb4ddb18bcc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5605 | T16182-CA00-P0UYC-182905 | 2017-12-14 | DHI-TRANSMIT-001143 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b0a01cd-90ae-4611-81fa-f6b86d03588e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5606 | T16182-YU02-P0BB-150811 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6585bcd9-7a88-4fb0-8711-f9e7472e277b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5607 | T16182-YU02-P0BB-150812 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cde00831-6860-4139-9e06-0e11cd005d7c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5608 | T16182-YU02-P0BB-150813 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fade20f2-bede-4849-84e8-1be6a2300812 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5609 | T16182-YU02-P0BB-150814 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a909bf46-952e-4382-840c-9f2699c55afa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5610 | T16182-YU02-P0BB-150815 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffa5d8d0-5969-433d-b302-04efbde37ac0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5611 | T16182-YU02-P0BB-150816 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b168802-2b1b-4c11-b2f1-d58414f08cba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5612 | T16182-YD00-P0BB-150821 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a685fba5-8359-4824-b574-0c7a65989b5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5613 | T16182-YU03-P0BB-150831 | 2017-12-14 | DHI-WTRAN-001054 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=311723b6-d3bc-47cd-af7a-7cf1b9f9916c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5614 | T16182-YT01-P0BB-150801 | 2017-12-14 | DHI-TRANSMIT-001144 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1ecab4d-50d0-4e9e-81c2-6e304545272c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5615 | T16182-CA01-P0UCB-180654 | 2017-12-14 | DHI-TRANSMIT-001145 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10f35c72-0937-4ff4-a40d-1e59c3bc5f6f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5616 | T16182-XG02-P0LCB-127032 | 2017-12-14 | DHI-TRANSMIT-001146 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6230d2bc-740c-432a-93b4-db8c3b669a59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5617 | T16182-CV03-P0GM-128508 | 2017-12-14 | DHI-WTRAN-001055 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35114b00-0f10-435f-8c92-0dd0289f077e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5618 | T16182-YK00-P0GM-128509 | 2017-12-14 | DHI-WTRAN-001055 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbe914c8-8e1f-4e8f-b57f-4ab2d6f4d26b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5619 | T16182-YL00-P0GM-128512 | 2017-12-14 | DHI-WTRAN-001055 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f57d6570-87d3-49cc-a966-6e8f9d9063a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5620 | T16182-XB02-P0UGF-173101 | 2017-12-14 | DHI-TRANSMIT-001147 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b22e5113-ffa4-433d-bcb0-14b4fe0f2c59 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5621 | T16182-XB02-P0UGF-173102 | 2017-12-14 | DHI-TRANSMIT-001147 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e2827f4-0ba7-4fe1-b810-ba6f0d188fd7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5622 | T16182-VK02-P0UGF-173107 | 2017-12-14 | DHI-TRANSMIT-001147 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f672818a-295b-489d-ac66-fd95d03e32c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5623 | T16182-XJ00-P0LBC-140102 | 2017-12-14 | DHI-TRANSMIT-001148 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c661065d-cc13-430e-92ce-cf7b35e62ee2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5624 | T16182-CA00-P0UYP-183201 | 2017-12-14 | DHI-TRANSMIT-001149 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=773b3206-eaa2-49a7-a3a1-f98850167914 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5625 | T16182-CA01-P0UYP-183252 | 2017-12-14 | DHI-TRANSMIT-001149 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=974d8185-649c-4c1d-bcae-166ceb77e471 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5626 | T16182-CA01-P0UYP-183255 | 2017-12-14 | DHI-TRANSMIT-001149 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=173437ba-95a6-4e92-aa8d-e1ca51311be6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5627 | T16182-CA00-P0UBA-186801 | 2017-12-14 | DHI-TRANSMIT-001150 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3337d900-18ad-4256-9031-33be8b13c8bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5628 | T16182-CA00-P0UBA-186802 | 2017-12-14 | DHI-TRANSMIT-001150 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1a5c0ce-9187-4dfb-8c00-db53d7954de2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5629 | T16182-CA00-P0UBA-186803 | 2017-12-14 | DHI-TRANSMIT-001150 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d47b74a-fbbf-4b7c-8ad3-d9a0baf77dd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5630 | T16182-CA01-P0UBA-186852 | 2017-12-14 | DHI-TRANSMIT-001150 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83444b19-6d18-43ae-8498-bb97a08313ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5631 | T16182-CA01-P0UBA-186853 | 2017-12-14 | DHI-TRANSMIT-001150 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dadcddfa-9eca-4bd5-b3d0-382d62805fad | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5632 | T16182-CA02-P0UBA-186854 | 2017-12-14 | DHI-TRANSMIT-001150 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2050a60-caf2-499c-aba2-8587c192cfb9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5633 | T16182-XF00-P0GM-128510 | 2017-12-14 | DHI-WTRAN-001056 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=206c303b-f2a6-4a48-815e-f5f023b3e2d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5634 | T16182-YE01-P0BAU-152600 | 2017-12-15 | DHI-WTRAN-001057 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=443c8695-26b9-4330-a79f-1cccba4eed87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5635 | T16182-YF00-P0MKY-290007 | 2017-12-15 | DHI-TRANSMIT-001151 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f23bf75f-6fbc-4dd5-9cc2-a4ace3eb9b8c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5636 | T16182-YS01-P0MKY-290011 | 2017-12-15 | DHI-TRANSMIT-001151 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9a78e1d-a924-423a-aa31-2aa229f47178 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5637 | T16182-CA06-P0UMY-185192 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4524c20-c497-45d6-bbf0-6295a5cf2354 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5638 | T16182-CA03-P0UMY-185169 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5af0ac8f-68b1-4bab-b7ad-90cd258b9b8a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5639 | T16182-CA03-P0UMY-185170 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f0f2668-ecbe-4e06-b55e-38b4be08e69f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5640 | T16182-CA03-P0UMY-185171 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75266406-474b-48d1-9e99-93f1be47ef22 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5641 | T16182-CA03-P0UMY-185172 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=315ec77c-0034-4f85-b015-cee04af5d17f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5642 | T16182-CA03-P0UMY-185173 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76c54fbb-fc59-44c5-99d5-eeefb6d7337d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5643 | T16182-CA03-P0UMY-185174 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e22acbad-fb65-4121-af6a-09bbec9d0a6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5644 | T16182-CA03-P0UMY-185175 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15c56ea3-d50b-424e-998c-9c14ee2a124c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5645 | T16182-CA03-P0UMY-185176 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b18bcd22-c087-420a-a4a9-41bb24c3dc7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5646 | T16182-CA03-P0UMY-185177 | 2017-12-15 | DHI-TRANSMIT-001152 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dca8c50-94a0-40fd-88e6-2db2279049c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5647 | T16182-XG02-P0SGK-138608 | 2017-12-15 | DHI-WTRAN-001058 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=206d4659-9cbf-4fb7-8635-15edb16bbbb9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5648 | T16182-XH01-P0SGK-138618 | 2017-12-15 | DHI-WTRAN-001058 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f724c12-d555-4cef-ab03-f33c05820401 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5649 | T16182-YT10-P0SGK-138628 | 2017-12-15 | DHI-WTRAN-001058 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2756867d-45da-4ec2-ad67-de71ecf230d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5650 | T16182-YD00-P0CYE-138641 | 2017-12-15 | DHI-WTRAN-001058 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b608d31-ef76-443a-b2d6-8027c6bdf0e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5651 | T16182-YU02-P0CYE-138642 | 2017-12-15 | DHI-WTRAN-001058 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63fe8393-81ef-4221-bce7-9e5c752ffdba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5652 | T16182-XJ00-P0LBG-140204 | 2017-12-15 | DHI-WTRAN-001059 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=124fed54-92bf-4db9-b46d-48b9d5060783 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5653 | T16182-XJ00-P0GKB-140212 | 2017-12-15 | DHI-WTRAN-001059 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7995afd6-0419-4c7a-8fc2-582b926d0567 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5654 | T16182-XJ00-P0GHC-140213 | 2017-12-15 | DHI-WTRAN-001059 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=285c9705-c355-4c8b-92b5-53ac746bbcdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5655 | T16182-YB03-P0ZEN-165532 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8879f51-7e5d-4759-a751-05f7aab4fba5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5656 | T16182-YB03-P0ZEN-165533 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=484dc741-a723-46eb-976b-8a5e4038612d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5657 | T16182-YB03-P0ZEN-165534 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccee88a8-9c5b-4e2a-9fb7-ff3b20150e5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5658 | T16182-YB03-P0ZEN-165535 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bc24c7f-78ec-41e7-902a-968ea9d5ee50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5659 | T16182-YB03-P0ZEN-165536 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d53f4bbe-88c4-424d-b298-1c1ab4d914b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5660 | T16182-YB03-P0ZEN-165537 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43435f24-1699-4705-bd8a-1ccb930c860d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5661 | T16182-YB03-P0ZEN-165539 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5cbb74d-7b24-4cc1-bc04-b434e5c7900b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5662 | T16182-YB03-P0ZEN-165540 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99e0c437-2d8b-4aa4-bddc-dcba3fc6cc74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5663 | T16182-YB03-P0ZEN-165541 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd19488a-1c82-41d6-98e5-57b8ea49b0aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5664 | T16182-YB03-P0ZEN-165542 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9862889e-7750-45a3-a7a0-296fbe2e3d26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5665 | T16182-YB03-P0ZEN-165543 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=835ed9bc-c9df-45fc-98bb-553b4e55da6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5666 | T16182-YB03-P0ZEN-165544 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=832a6ca8-e7c1-447e-aa20-4a913868ad5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5667 | T16182-YB03-P0ZEN-165545 | 2017-12-15 | DHI-TRANSMIT-001153 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97cc73f0-1189-4cf8-8802-4b327e039c94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5668 | T16182-XG02-P0SGA-139401 | 2017-12-15 | DHI-TRANSMIT-001154 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab0cb11f-69a2-4e26-87a8-204d333cc4cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5669 | T16182-XH01-P0SGA-139411 | 2017-12-15 | DHI-TRANSMIT-001154 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54033fff-6381-4703-a5be-1a7676aa232d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5670 | T16182-XW03-P0SAQ-135201 | 2017-12-15 | DHI-WTRAN-001060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c17ad421-3016-45f5-a7f7-fa289f3a1714 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5671 | T16182-XG07-P0SAQ-135202 | 2017-12-15 | DHI-WTRAN-001060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a58697f4-74b9-4042-930a-2cb3715fa4ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5672 | T16182-XW03-P0SAQ-135203 | 2017-12-15 | DHI-WTRAN-001060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2797b954-f61b-431e-914a-e1274ee94758 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5673 | T16182-XH02-P0SAQ-135204 | 2017-12-15 | DHI-WTRAN-001060 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebc59f8e-4f28-4000-a7fe-1367680b068b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5674 | T16182-YL16-P0ZEN-165568 | 2017-12-18 | DHI-WTRAN-001061 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32c5bbd3-f5ee-42ba-a7c5-8e8147c83eab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5675 | T16182-YF00-P0QC-130309 | 2017-12-18 | DHI-WTRAN-001062 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9bbd2aa-6f47-43ca-8a73-1a0a964bf133 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5676 | T16182-YU03-P0QC-130308 | 2017-12-18 | DHI-WTRAN-001062 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cc60d1c-22b4-451c-9e70-8317709553c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5677 | T16182-YT10-P0ZEN-152220 | 2017-12-18 | DHI-WTRAN-001063 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2c6474e-f52f-42be-b46a-a915bd4dcf20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5678 | T16182-YQ01-P0ZEN-152318 | 2017-12-18 | DHI-WTRAN-001063 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc2ad439-48ce-4be2-af6d-064da4c5274c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5679 | T16182-YB11-P0ZEN-152418 | 2017-12-18 | DHI-WTRAN-001063 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8721cc8-824e-455f-b100-7bd1a0c6d82c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5680 | T16182-YK08-P0GKC-420050 | 2017-12-18 | DHI-WTRAN-001064 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27bb1473-e368-4b94-be09-54cf78f4f0b8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5681 | T16182-YV02-P0SCA-127511 | 2017-12-19 | DHI-WTRAN-001065 | IFI | 3 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5682 | T16182-XS00-P0QU-130401 | 2017-12-19 | DHI-WTRAN-001066 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88784220-1b4b-41ea-8f83-5f46765d2c9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5683 | T16182-YD00-P0QU-130402 | 2017-12-19 | DHI-WTRAN-001066 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13469c78-8061-4684-a60a-d45f28b72c4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5684 | T16182-XG02-P0QU-130403 | 2017-12-19 | DHI-WTRAN-001066 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6981d85-b3bb-4bca-be46-c5570e341c57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5685 | T16182-YL00-P0QU-130404 | 2017-12-19 | DHI-WTRAN-001066 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08f3e8db-5b39-4b40-b50e-b4c753adbeca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5686 | T16182-YT01-P0QU-130405 | 2017-12-19 | DHI-WTRAN-001066 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b52fa17-cdca-45c8-8334-ddcf865988ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5687 | T16182-YT01-P0LB-122093 | 2017-12-19 | DHI-TRANSMIT-001157 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f390f286-97d8-4b7a-b3f5-221d62b05383 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5688 | T16182-XJ00-P0LB-122028 | 2017-12-19 | DHI-WTRAN-001067 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0fb3fb3-88f4-4e89-8919-cf07135ccd03 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5689 | T16182-VK02-P0UZJ-173209 | 2017-12-19 | DHI-WTRAN-001068 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08319f07-d535-4911-8cc4-859aa5c1c697 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5690 | T16182-XG02-P0SGA-138601 | 2017-12-19 | DHI-WTRAN-001069 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9dfefc6e-7ec3-47ef-81c4-7e6dcd6d9d93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5691 | T16182-XG02-P0SGC-138604 | 2017-12-19 | DHI-WTRAN-001069 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7ca3d45-dd07-434b-ae47-8d031e0546de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5692 | T16182-XG02-P0SGC-138606 | 2017-12-19 | DHI-WTRAN-001069 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e29a210a-b008-4a26-8b35-0d0c22102769 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5693 | T16182-XH01-P0SGA-138611 | 2017-12-19 | DHI-WTRAN-001069 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44e7bb7b-de01-48b9-b133-4254e7a987d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5694 | T16182-XH01-P0SGC-138614 | 2017-12-19 | DHI-WTRAN-001069 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00ee4049-1d21-4bb4-8214-2d3ca3f9a0c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5695 | T16182-XH01-P0SGC-138616 | 2017-12-19 | DHI-WTRAN-001069 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25507db7-7e42-4582-bae5-f54e66b14bb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5696 | T16182-YD00-P0SGZ-138631 | 2017-12-19 | DHI-WTRAN-001069 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08f4f80b-7b60-4cf9-b07d-80339e34e20a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5697 | T16182-XG07-P0LD-130203 | 2017-12-19 | DHI-TRANSMIT-001158 | IFC | 1 | D | TRUE | FALSE | 2017-12-19_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6e26c32-0a54-4a2d-9235-147d769ad36e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5698 | T16182-YK09-P0LD-130212 | 2017-12-19 | DHI-TRANSMIT-001158 | IFC | 0 | DR | TRUE | TRUE | 2017-12-19_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2753a4d-c013-4b16-bce7-ca26ae1b16e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5699 | T16182-XG02-P0LD-130204 | 2017-12-19 | DHI-WTRAN-001070 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf730afd-b589-4b4d-b57f-daca18190295 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5700 | T16182-XB02-P0UZT-172716 | 2017-12-19 | DHI-TRANSMIT-001159 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b680d145-c015-42ff-a484-8a8b530e6e7f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5701 | T16182-YT01-P0CYE-136617 | 2017-12-19 | DHI-TRANSMIT-001160 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69eae94d-716d-4d65-b6d5-af4f65c93cc9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5702 | T16182-YF01-P0BYA-161051 | 2017-12-19 | DHI-WTRAN-001071 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbdbd53b-e5a3-465f-8633-1c0a5adc0dd6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5703 | T16182-YT10-P0SGC-138624 | 2017-12-19 | DHI-WTRAN-001072 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0759400-aaeb-4bf9-bf4b-56c31ec7a044 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5704 | T16182-YT10-P0SGC-138626 | 2017-12-19 | DHI-WTRAN-001072 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38d8f144-6d83-4c48-9f6c-efc71cbc0eaa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5705 | T16182-YF02-P0ZEN-161031 | 2017-12-19 | DHI-TRANSMIT-001161 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=486fd295-9a8e-4fb8-979e-808d8b2a333c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5706 | T16182-XB02-P0UZA-172904 | 2017-12-19 | DHI-WTRAN-001073 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5030683-b7b2-4dde-9c94-680e8a66f852 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5707 | T16182-XB02-P0UZT-172702 | 2017-12-19 | DHI-TRANSMIT-001162 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06b5d911-0dc9-488d-9b82-a8bf50f2bc6e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5708 | T16182-XB02-P0UZT-172703 | 2017-12-19 | DHI-TRANSMIT-001162 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41a241b5-48e1-44b4-8a7d-99bda08917d5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5709 | T16182-YB03-P0ZEN-165538 | 2017-12-19 | DHI-TRANSMIT-001163 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41e34259-60cc-47b8-aba5-f31a57dad123 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5710 | T16182-YB03-P0ZEN-165546 | 2017-12-19 | DHI-TRANSMIT-001163 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48de9a00-787e-47a0-998b-fcf06cd3865f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5711 | T16182-YB03-P0ZEN-165547 | 2017-12-19 | DHI-TRANSMIT-001163 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3763e8a4-c73b-4b48-89c5-976d61f47373 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5712 | T16182-YD00-P0BBT-150671 | 2017-12-19 | DHI-WTRAN-001074 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c563c02-b0bf-4fa6-b8f7-4bfe05535abf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5713 | T16182-YT01-P0BBT-150661 | 2017-12-19 | DHI-TRANSMIT-001164 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abf6a6d3-c766-48db-b7bb-70278fc5f58c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5714 | T16182-UE00-P0LB-122011 | 2017-12-19 | DHI-TRANSMIT-001165 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d507ca9-d67a-41c4-8a18-6433678b7a3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5715 | T16182-XW01-P0LB-122041 | 2017-12-19 | DHI-WTRAN-001075 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c85041cb-1398-446c-963b-f983ab3eef69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5716 | T16182-VN02-P0LB-122089 | 2017-12-19 | DHI-WTRAN-001075 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec83a6e3-cea2-473b-9c2f-fed2d707c5fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5717 | T16182-VN02-P0LB-122090 | 2017-12-19 | DHI-WTRAN-001075 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af247ae9-1695-4f77-bb9e-9c77b04d8ab0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5718 | T16182-YT10-P0ZEN-150313 | 2017-12-20 | DHI-WTRAN-001076 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b788997-f15a-4725-b0ac-0d5402992d24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5719 | T16182-YS00-P0CJN-290001 | 2017-12-20 | DHI-TRANSMIT-001176 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45cacd33-f148-408a-a2c8-7848c56f20d7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5720 | T16182-YD02-P0SAC-163413 | 2017-12-20 | DHI-WTRAN-001077 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=559312b7-2ac5-4992-a458-139347ecd127 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5721 | T16182-YD02-P0SAC-163414 | 2017-12-20 | DHI-WTRAN-001077 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b06e59a-d8e4-45f3-8aeb-cf5df4948cc7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5722 | T16182-XB02-P0UGF-173101 | 2017-12-20 | DHI-TRANSMIT-001177 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47506c51-b492-4654-be67-fa5dbae273ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5723 | T16182-XB02-P0UGF-173102 | 2017-12-20 | DHI-TRANSMIT-001177 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a52aee25-6b37-4d9b-9512-deee97b4d336 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5724 | T16182-CA03-P0ULA-182154 | 2017-12-20 | DHI-TRANSMIT-001178 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ada02a75-4172-4afc-883c-d2a4d2b2d602 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5725 | T16182-YD00-P0CYE-139441 | 2017-12-20 | DHI-TRANSMIT-001179 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=678a77fc-999c-400a-b663-df70ce034354 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5726 | T16182-YS01-P0MKY-290012 | 2017-12-20 | DHI-TRANSMIT-001180 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12f2832f-406b-4f85-8c80-7c5c59b5fd73 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5727 | T16182-XJ00-P0SCA-140210 | 2017-12-20 | DHI-WTRAN-001078 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04ce7074-1a8c-4358-b79d-d0e2bc4c2483 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5728 | T16182-XJ00-P0QFB-140211 | 2017-12-20 | DHI-WTRAN-001078 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63162906-00fe-4177-a593-e2f1ac406a9f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5729 | T16182-XJ00-P0QJA-140223 | 2017-12-20 | DHI-WTRAN-001078 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27ec73a0-fd79-492e-ad14-d822219854d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5730 | T16182-YB03-P0PCA-126533 | 2017-12-20 | DHI-WTRAN-001079 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1352fef-095c-49c7-a34d-8674544f1508 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5731 | T16182-CC02-P8QHB-125172 | 2017-12-20 | DHI-TRANSMIT-001181 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de370dac-f40b-40ac-aa1b-6d3b5698ca40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5732 | T16182-XS01-P8ZEN-125700 | 2017-12-20 | DHI-TRANSMIT-001181 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a42848e3-d8d9-45a5-8d91-987bf3f35bb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5733 | T16182-VN01-P0MAG-123047 | 2017-12-21 | INT-IFC-171221-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-21_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=25945590-068b-4b58-8566-f4c9a12d259c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5734 | T16182-VN01-P0MAG-123046 | 2017-12-21 | INT-IFC-171221-01 | INTERNAL IFC | 0 | D | TRUE | FALSE | 2017-12-21_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=31470e39-8831-4c1a-95d3-b29ea202141e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5735 | T16182-CA06-P0UYE-183300 | 2017-12-21 | DHI-WTRAN-001080 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=352e6237-1e07-466c-b132-eec249a01f10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5736 | T16182-CA01-P0UYE-183352 | 2017-12-21 | DHI-WTRAN-001080 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02df4507-a64c-4e9c-be28-39b4eea168ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5737 | T16182-CA01-P0UYE-183353 | 2017-12-21 | DHI-WTRAN-001080 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=814894f9-06a0-49af-80ad-9bb02981954f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5738 | T16182-CA02-P0UYE-183355 | 2017-12-21 | DHI-WTRAN-001080 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f60516d-423a-471a-a84d-86489ef4f73a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5739 | T16182-CQ02-P0LB-122002 | 2017-12-21 | DHI-WTRAN-001082 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea057fb1-79e5-4902-bdd8-ac1bda278752 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5740 | T16182-XH01-P0LB-122024 | 2017-12-21 | DHI-TRANSMIT-001182 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4946f481-cd92-4f1b-b1bd-c672c4db75f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5741 | T16182-YT01-P0LB-122108 | 2017-12-21 | DHI-TRANSMIT-001182 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b7868e8-7f2c-48c3-aedd-3e69472729e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5742 | T16182-YD00-P0LAC-126001 | 2017-12-21 | DHI-TRANSMIT-001183 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=366398d2-ff4f-44f5-8927-5fc3b5283f07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5743 | T16182-XB02-P0GHC-173802 | 2017-12-21 | DHI-WTRAN-001083 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41677c1b-03a7-4b38-8ead-e44d0e7709db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5744 | T16182-CA00-P0UYC-182901 | 2017-12-21 | DHI-TRANSMIT-001184 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34aedee6-f847-418e-b650-0c592f77445b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5745 | T16182-CA00-P0UYC-182905 | 2017-12-21 | DHI-TRANSMIT-001184 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1f3ff67-e2c5-4977-a667-6813bee2ff59 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5746 | T16182-XH01-P0SGK-136713 | 2017-12-21 | DHI-TRANSMIT-001185 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48fcce5e-3a4f-4ec1-b422-38841aba1adf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5747 | T16182-YT10-P0SGC-138121 | 2017-12-21 | DHI-TRANSMIT-001185 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3debe2a1-7a4f-4ed2-bc78-12dae629079e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5748 | T16182-YD00-P0CYE-138141 | 2017-12-21 | DHI-TRANSMIT-001185 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77108436-1a8a-41d7-802f-45e68b32470a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5749 | T16182-YU02-P0CYE-138142 | 2017-12-21 | DHI-TRANSMIT-001185 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0fb21b0-7f5f-47aa-87ad-487ac645851d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5750 | T16182-YD00-P0SGZ-139431 | 2017-12-21 | DHI-TRANSMIT-001185 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bd931a3-a738-481f-82dd-6600d0eb8b9a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5751 | T16182-DE00-P0ZEN-152823 | 2017-12-21 | DHI-TRANSMIT-001186 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38a46b54-dbe5-42b9-9df5-450522ec40d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5752 | T16182-XB02-P0UAZ-172608 | 2017-12-21 | DHI-TRANSMIT-001188 | IFC | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e484de1-f31a-4faa-998f-aa6057c279ad | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5753 | T16182-UT01-P0GQB-173402 | 2017-12-21 | DHI-TRANSMIT-001189 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86f8dd28-efff-4850-bf75-e7f76b45f6e9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5754 | T16182-UT01-P0GQB-173403 | 2017-12-21 | DHI-TRANSMIT-001189 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a78a3c26-f466-4a2d-8ae3-7eb704efbacc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5755 | T16182-UT01-P0GQB-173413 | 2017-12-21 | DHI-TRANSMIT-001189 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fd2725b-dcce-4aa5-9118-9cf15b6d6798 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5756 | T16182-YU03-P0BBT-150681 | 2017-12-21 | DHI-TRANSMIT-001190 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a325267-a1db-455a-b9eb-b6c8f6b3cf3c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5757 | T16182-YK10-P0LF-110602 | 2017-12-21 | DHI-TRANSMIT-001191 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=208c765a-869c-4450-8e3b-e4e383170c34 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5825 | T16182-YT01-P0SMQ-128019 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=507a77ed-7f0b-42ca-a12d-22394b36ceb3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5826 | T16182-YT01-P0SMU-128020 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89018bf7-d60c-457c-86e7-918e46d5093c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5827 | T16182-YT01-P0SMG-128021 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37b2be74-b5c7-4e71-8201-1eacee396d9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5828 | T16182-YT01-P0SMC-128033 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9eba712-ff91-4b98-8477-bd8fa8ab9596 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5829 | T16182-YT01-P0SMS-128034 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc2f90dd-a28f-4f1c-8f17-670eed0cd3a5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5830 | T16182-YT01-P0SMG-128035 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41a5935d-2e8f-4df3-9db2-690f70dba4dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5831 | T16182-YT01-P0SMM-128036 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e593178-d8cd-4c30-bbca-7ad286d9dd56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5832 | T16182-YT01-P0SMU-128037 | 2017-12-21 | DHI-WTRAN-001081 | IFI | 0 | D | TRUE | FALSE | 2018-01-02_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24c6d644-da43-4b88-aec3-7a6b3f0fa176 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5758 | T16182-YD02-P0SAC-163411 | 2017-12-22 | DHI-WTRAN-001084 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc18c953-e549-471f-be88-3055ac6db6d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5759 | T16182-YD02-P0SAC-163412 | 2017-12-22 | DHI-WTRAN-001084 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b19adc76-98f0-4873-ae9f-fe5e386ac840 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5760 | T16182-YD02-P0SAC-163421 | 2017-12-22 | DHI-WTRAN-001084 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ae52468-5f41-4120-81dc-f6b4237dcb45 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5761 | T16182-CV03-P8ZEN-125606 | 2017-12-22 | DHI-TRANSMIT-001194 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=507936a5-5747-4757-b94d-e9911fb4690f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5762 | T16182-CV03-P8ZEN-125610 | 2017-12-22 | DHI-TRANSMIT-001194 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faef0fa6-bed8-4151-8485-60909ba31428 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5763 | T16182-XH01-P0LF-140415 | 2017-12-22 | DHI-WTRAN-001085 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=584855a2-693e-46bc-8b53-b839c0afb546 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5764 | T16182-XH01-P0LF-140416 | 2017-12-22 | DHI-WTRAN-001085 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=425376bb-1101-4cf8-82cc-f179e1e6190b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5765 | T16182-XH01-P0LF-140406 | 2017-12-22 | DHI-TRANSMIT-001195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e38fc8b8-fe02-46a9-b551-f007fe7999ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5766 | T16182-XH01-P0LF-140407 | 2017-12-22 | DHI-TRANSMIT-001195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eaca0d56-bc63-4566-bdc6-253d327b8472 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5767 | T16182-XH01-P0LF-140408 | 2017-12-22 | DHI-TRANSMIT-001195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4dc0de1c-2ca8-4bbd-9c0a-b2843d68b81d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5768 | T16182-XH01-P0LF-140411 | 2017-12-22 | DHI-TRANSMIT-001195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=281c8942-fed6-4dda-801e-484ce9fd8848 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5769 | T16182-XH01-P0LF-140412 | 2017-12-22 | DHI-TRANSMIT-001195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6b56f9a-2300-4803-9421-694d3c922632 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5770 | T16182-XH01-P0LF-140417 | 2017-12-22 | DHI-TRANSMIT-001195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4d0f4ed-24ff-454a-a0cd-fc0de7050a67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5771 | T16182-XH01-P0LF-140419 | 2017-12-22 | DHI-TRANSMIT-001195 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f54be4d-7b9b-485c-a3dc-0e7a717a78ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5772 | T16182-UB01-P0EKG-124075 | 2017-12-22 | DHI-WTRAN-001086 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27f13e02-181e-4fd0-80c0-3436572f1b91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5773 | T16182-CV03-P0EKU-163202 | 2017-12-22 | DHI-TRANSMIT-001196 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=368f34c6-2822-4b3a-8944-1ef65018280c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5774 | T16182-CV03-P0UCL-163203 | 2017-12-22 | DHI-TRANSMIT-001196 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b98703c8-c79b-483f-9956-8de5b2f104b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5775 | T16182-CV03-P0ZEN-163204 | 2017-12-22 | DHI-TRANSMIT-001196 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b97f5a87-fa59-484e-91a1-30b4cf8b44de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5776 | T16182-BP00-P0EKG-140015 | 2017-12-22 | DHI-WTRAN-001087 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4ad8a8a-37cc-4e40-829f-0109791962db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5777 | T16182-YT01-P0PGB-110403 | 2017-12-22 | DHI-TRANSMIT-001197 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46fa48c2-fd0a-4410-88c1-241cb22ada6e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5778 | T16182-XG07-P0SAC-133502 | 2017-12-22 | DHI-TRANSMIT-001198 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f89306b6-213d-4bc7-a3cb-de4ef7c33af7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5779 | T16182-XH02-P0SAC-133504 | 2017-12-22 | DHI-TRANSMIT-001198 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=591604f5-0c97-4875-989d-e19b3a32d0f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5780 | T16182-XW03-P0SAF-134701 | 2017-12-22 | DHI-TRANSMIT-001199 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20f67adf-86d9-49db-9033-543888062f7e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5781 | T16182-XG07-P0SAF-134702 | 2017-12-22 | DHI-TRANSMIT-001199 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8625aac-1d68-4f3f-b101-36c79885f82f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5782 | T16182-XW03-P0SAF-134703 | 2017-12-22 | DHI-TRANSMIT-001199 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbbdb9bf-99a1-433f-9eb4-ac713d7a332f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5783 | T16182-XH02-P0SAF-134704 | 2017-12-22 | DHI-TRANSMIT-001199 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6edc39c9-2d9c-4473-9eb1-132e3d78b711 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5784 | T16182-YQ01-P0ZEN-152320 | 2017-12-22 | DHI-TRANSMIT-001200 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86b26755-0c22-4014-98e9-91485396a017 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5785 | T16182-CA00-P0UTX-183361 | 2017-12-22 | DHI-WTRAN-001088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c92ea2ca-9457-4348-bbf1-306bd3e81ba2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5786 | T16182-CA03-P0UTX-183371 | 2017-12-22 | DHI-WTRAN-001088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=113930d3-ccbe-466e-a919-3b0b386a0160 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5787 | T16182-CA03-P0UTX-183372 | 2017-12-22 | DHI-WTRAN-001088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0dfef8d7-61e6-449d-86e8-0c9fbcf28507 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5788 | T16182-CA03-P0UTX-183373 | 2017-12-22 | DHI-WTRAN-001088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33845592-cb0a-414b-b5ab-c28accd317da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5789 | T16182-CA03-P0UTX-183375 | 2017-12-22 | DHI-WTRAN-001088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f672e3d-e9a1-452e-a93d-4bcee6e0a2b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5790 | T16182-CA02-P0UTX-183377 | 2017-12-22 | DHI-WTRAN-001088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f033f03-7703-4756-be66-20d9b8175883 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5791 | T16182-CA06-P0UTX-183390 | 2017-12-22 | DHI-WTRAN-001088 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0135a362-6a44-4f91-a8da-af48573e3251 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5792 | T16182-CA00-P0GEN-185701 | 2017-12-22 | DHI-TRANSMIT-001201 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4eeaacbd-e5d1-48bf-b599-4d5db55cc53d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5793 | T16182-CA01-P0GEN-185751 | 2017-12-22 | DHI-TRANSMIT-001201 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3cda0c93-267f-4428-87b4-2149d9e4b7f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5794 | T16182-CA00-P0GEN-185801 | 2017-12-22 | DHI-TRANSMIT-001202 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85f82842-c08c-400d-b5ef-7d0fde0993cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5795 | T16182-CA00-P0GEN-185802 | 2017-12-22 | DHI-TRANSMIT-001202 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de933a8e-fd79-4667-bee0-d81fb9838766 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5796 | T16182-CA00-P0GEN-185803 | 2017-12-22 | DHI-TRANSMIT-001202 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4eef3b48-8d33-498d-a9ce-31dda8c2aea6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5797 | T16182-CA01-P0GEN-185852 | 2017-12-22 | DHI-TRANSMIT-001202 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1bef24fa-2e05-4922-8149-f97df6680d4f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5798 | T16182-CA01-P0GEN-185853 | 2017-12-22 | DHI-TRANSMIT-001202 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e14b96a6-9c3b-4c0d-91b8-c8c069a5ac5e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5799 | T16182-CA02-P0GEN-185854 | 2017-12-22 | DHI-TRANSMIT-001202 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bbca9e9-e968-4352-bfca-58a58238892c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5800 | T16182-YL00-P0GCF-130009 | 2017-12-22 | DHI-WTRAN-001089 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c46a5e4e-8645-4ae4-8018-4637a7b359f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5801 | T16182-YF02-P0GCF-130011 | 2017-12-22 | DHI-WTRAN-001089 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=193f377c-f78c-48bd-9b77-f47b956800b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5802 | T16182-YK00-P0GCF-130016 | 2017-12-22 | DHI-WTRAN-001089 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3daa28e-825b-4e11-9b2e-1223fa083f34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5803 | T16182-YL01-P0GCF-130035 | 2017-12-22 | DHI-WTRAN-001089 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8733c1b8-422c-4793-8c95-987e8040914e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5804 | T16182-CV03-P0GCF-130055 | 2017-12-22 | DHI-WTRAN-001089 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52ac6f76-9440-44d3-ae77-37ccdb6c837a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5805 | T16182-YL00-P0GNR-130106 | 2017-12-22 | DHI-WTRAN-001089 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e79cb78-862d-4abf-b0a2-01dc3a9c10b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5806 | T16182-XS00-P0GCF-130001 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=257556b3-491d-4541-a597-0b044c258c80 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5807 | T16182-YD00-P0GCF-130002 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63b88e99-7558-4f70-a11d-5d97851840d0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5808 | T16182-XG02-P0GCF-130004 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f198176-d385-45d0-b9e5-9734f6cf799f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5809 | T16182-XW03-P0GCF-130005 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f01c167c-ffc2-4c38-a761-4d8a19a83ec7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5810 | T16182-YD00-P0GCF-130006 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b149421e-fb0a-4193-9351-8ab13195cedf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5811 | T16182-YR05-P0GCF-130007 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63ad5b64-6cc8-4444-87cb-f8becd88a9ca | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5812 | T16182-XN00-P0GCF-130008 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c86c8a1b-76c7-4059-9872-9c4bbb17948b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5813 | T16182-YU02-P0GCF-130010 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67b33eb4-66af-4378-853d-6381ded1ae4d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5814 | T16182-YK09-P0GCF-130012 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b219a0cc-6d39-4f65-ba88-c49e414450c1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5815 | T16182-XH01-P0GCF-130013 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19ee0f3d-1c50-401e-95ed-46e17707deb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5816 | T16182-YT01-P0GCF-130014 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=161a29cd-3246-4f72-b8d1-974de141c63d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5817 | T16182-YU03-P0GCF-130017 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=967b2599-9f13-46f7-8f8d-94a6a980878f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5818 | T16182-YD00-P0GCF-130019 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93abdd62-5330-41b2-95fc-a6b5a45728ca | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5819 | T16182-XB02-P0GCF-130042 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6de5058-0b05-42d4-9020-f664166200e2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5820 | T16182-XS00-P0GNR-130101 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0a8eea9-c91c-4cdf-8634-2e89d3876a7f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5821 | T16182-XG02-P0GNR-130103 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93ac36cb-8029-4151-b916-9a5758c0c76b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5822 | T16182-XN00-P0GNR-130105 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5f8199e-b6ea-4707-bbcc-d325d9b67af9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5823 | T16182-XN00-P0GNR-130107 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=998b2a25-cd02-49de-8e01-03811de8a666 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5824 | T16182-YT01-P0GNR-130108 | 2017-12-22 | DHI-TRANSMIT-001203 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2243f578-e993-4896-b83b-5a50636b13f7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5833 | T16182-YS01-P0MKY-290009 | 2018-01-02 | DHI-WTRAN-001090 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1b58ca7-cbcf-4eb0-a9b1-b672c674a583 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5834 | T16182-YT10-P0MKY-290010 | 2018-01-02 | DHI-WTRAN-001090 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56a3870a-5b07-479d-a99e-653ffc16e67d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5835 | T16182-DP00-P0ZEN-020004 | 2018-01-02 | DHI-TRANSMIT-001212 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b23bd902-46b4-4fee-8d5b-9722980e1181 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5836 | T16182-XG02-P0SCA-120004 | 2018-01-02 | DHI-TRANSMIT-001213 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b7c871b-7af1-45a4-b758-608c7ee7d014 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5837 | T16182-XG02-P0SCA-120005 | 2018-01-02 | DHI-TRANSMIT-001213 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bb936c0-55e0-499b-94ea-e4b32d08b0a6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5838 | T16182-XG02-P0SCA-120006 | 2018-01-02 | DHI-TRANSMIT-001213 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=096647cf-02cf-4f83-b92f-fa2768932365 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5839 | T16182-XJ00-P0LBG-140103 | 2018-01-02 | DHI-TRANSMIT-001214 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8209efa7-52ae-4414-b523-94811962e858 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5840 | T16182-XG02-P0SGC-137401 | 2018-01-02 | DHI-TRANSMIT-001215 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7bd4c5a-0ae8-4f6c-99f7-888871be57ff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5841 | T16182-XH01-P0SGA-137811 | 2018-01-02 | DHI-TRANSMIT-001215 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99d22b6a-991b-487e-ae47-b4e521f67acf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5842 | T16182-XH01-P0SGA-137911 | 2018-01-02 | DHI-TRANSMIT-001215 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40b73bba-5b8b-4ce5-b7d0-1591d416c7c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5843 | T16182-XG02-P0SGE-138603 | 2018-01-02 | DHI-WTRAN-001091 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c5acfd6-0674-4a20-a30a-9fbdfbfa48d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5844 | T16182-XH01-P0SGE-138613 | 2018-01-02 | DHI-WTRAN-001091 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8082faf5-7655-427e-8bd5-8e22fc495a25 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5845 | T16182-YT10-P0SGE-138623 | 2018-01-02 | DHI-WTRAN-001091 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66213d3d-8d10-48f2-9d31-680b9514e47e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5846 | T16182-XG02-P0GM-120008 | 2018-01-02 | DHI-TRANSMIT-001216 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49e1d864-66a2-4780-8a6f-6d254422eb17 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5847 | T16182-YK08-P0GKC-420050 | 2018-01-02 | DHI-TRANSMIT-001217 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39275327-a3fc-495c-8e32-b04f5eb0b481 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5848 | T16182-YD00-P0GM-128501 | 2018-01-02 | DHI-TRANSMIT-001218 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=796b4ef3-c509-4f44-b89f-01a89bfa92f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5849 | T16182-YK08-P0GKC-420051 | 2018-01-03 | DHI-WTRAN-001092 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd4874b7-ab26-4fae-acd5-7c29b338be3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5850 | T16182-YT01-P0MAN-110153 | 2018-01-03 | DHI-WTRAN-001094 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5e815a0-25cd-422b-8b8d-b977117b6a1a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5851 | T16182-YU03-P0CYE-136606 | 2018-01-03 | DHI-TRANSMIT-001221 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=853b2b89-a095-409f-81c0-dd6f36cc0a94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5852 | T16182-YU02-P0CYE-136607 | 2018-01-03 | DHI-TRANSMIT-001221 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84aaa7cf-22af-46c6-81b9-b09e21fd0868 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5853 | T16182-YD00-P0SMU-128032 | 2018-01-03 | DHI-WTRAN-001095 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=286d5ebf-b874-4235-b73e-30f899e64896 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5854 | T16182-XG02-P6MAA-220025 | 2018-01-03 | DHI-WTRAN-001096 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70972258-5f68-4326-b343-b43c3815298c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5855 | T16182-XG02-P6MAA-220029 | 2018-01-03 | DHI-WTRAN-001096 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e04ed346-259d-4dc7-a63d-a57d93b88498 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5856 | T16182-YK08-P0MAN-110154 | 2018-01-04 | DHI-TRANSMIT-001222 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf2328c4-7f0c-45fc-bbd3-6a56d8c412f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5857 | T16182-YK10-P8QHA-125202 | 2018-01-04 | DHI-TRANSMIT-001223 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de954c5f-3439-479a-b1a0-8ed762030108 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5858 | T16182-XV00-P8ZEN-125505 | 2018-01-04 | DHI-TRANSMIT-001223 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f65fb05-0e52-4d53-a485-1485f1655a63 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5859 | T16182-YD00-P8ZEN-125507 | 2018-01-04 | DHI-WTRAN-001097 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da7c0e44-77a3-4f7c-aec3-c2ad5b7c5846 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5860 | T16182-XK00-P8ZEN-125509 | 2018-01-04 | DHI-WTRAN-001097 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e42f0e3-2bab-4802-8387-5f91c74ad457 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5861 | T16182-UT01-P0GQB-173413 | 2018-01-04 | DHI-TRANSMIT-001224 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48452e94-3644-4f3f-8795-e358eeeb0a4b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5862 | T16182-XB00-P0GM-128506 | 2018-01-04 | DHI-TRANSMIT-001225 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9049cce-fdc2-4f05-afcb-72bc044c8514 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5863 | T16182-XF00-P0SCA-127524 | 2018-01-04 | DHI-WTRAN-001098 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22eb183d-635a-4ce5-a3a1-f2dd5b4edaf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5864 | T16182-XG02-P6MAA-220027 | 2018-01-04 | DHI-WTRAN-001099 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5865 | T16182-CA06-P0UYA-183100 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34872d09-afe3-4fab-b62c-cd5fd4a34c1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5866 | T16182-CA00-P0UYA-183101 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfccaa0e-dd90-43d1-bbb3-590629371678 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5867 | T16182-CA00-P0UYA-183102 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=954e5803-733d-416d-b162-79798a879cae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5868 | T16182-CA00-P0UYA-183103 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f80dd5cf-c7f1-459d-8f1b-c09a49e6c97b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5869 | T16182-CA00-P0UYA-183104 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e796625-22a9-4967-8ee7-dbfa46c4bffa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5870 | T16182-CA00-P0UYA-183105 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a2b9747-bb6e-4e9a-8792-5e6e32ab5c31 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5871 | T16182-CA01-P0UYA-183151 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c49cf2ad-ffd7-4dd3-a49d-3bbf1d08afa2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5872 | T16182-CA01-P0UYA-183152 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ae2d172-6ba8-4759-b252-f4c77390dff5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5873 | T16182-CA01-P0UYA-183153 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b6585ce-6523-4a09-8646-6e2557503d5d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5874 | T16182-CA01-P0UYA-183154 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=416c10fb-b1bc-4685-8203-bf7f0cad2e07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5875 | T16182-CA02-P0UYA-183155 | 2018-01-05 | DHI-WTRAN-001100 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61fc12ed-9b43-4bac-908b-bcad0b3445b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5876 | T16182-YT10-P0ZEN-150312 | 2018-01-05 | DHI-WTRAN-001101 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42aaccd9-9b09-4137-9e91-45df7538669d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5877 | T16182-XG02-P7MAA-220026 | 2018-01-05 | DHI-WTRAN-001102 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8af29ac4-9556-4cc9-9f6b-82875c47aaaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5878 | T16182-XG02-P7MAA-220030 | 2018-01-05 | DHI-WTRAN-001102 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1bc6bab1-b017-4c51-b502-be0d2a88cc7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5879 | T16182-XG02-P7MAA-220028 | 2018-01-05 | DHI-WTRAN-001102 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abdd31cd-12b9-4e52-8d30-79a09155c6b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5880 | T16182-YE00-P0CJN-290005 | 2018-01-05 | DHI-TRANSMIT-001226 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00860eae-78d8-4d4e-8b68-51d3a0b53ca0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5881 | T16182-CV03-P8ZEN-125605 | 2018-01-05 | DHI-TRANSMIT-001227 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59d5d242-9d99-41b2-a177-d51ae63b4d27 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5882 | T16182-YD00-P0BAA-150762 | 2018-01-05 | DHI-TRANSMIT-001228 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a213b948-13fe-4ba8-9f98-3a958ebe69ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5883 | T16182-YD00-P0BAA-150767 | 2018-01-05 | DHI-WTRAN-001103 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cae47668-8f7f-4023-917b-05ababc6a9cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5884 | T16182-YD00-P0BAA-150782 | 2018-01-05 | DHI-WTRAN-001103 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84e5d209-0bd5-48ed-bd54-2f84a9087bbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5885 | T16182-YT01-P0LF-110601 | 2018-01-05 | DHI-TRANSMIT-001229 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8a541dd-7c57-4b9d-b10d-f2bba4e46bdc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5886 | T16182-YL00-P0ZEN-163101 | 2018-01-08 | DHI-TRANSMIT-001233 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86e41236-b2c9-455d-b6c7-3e0fde40005d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5887 | T16182-CV03-P0ZEN-163102 | 2018-01-08 | DHI-TRANSMIT-001233 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=730c3173-f02b-4497-89e1-0e63afa419b4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5888 | T16182-CV03-P0ZEN-163103 | 2018-01-08 | DHI-TRANSMIT-001233 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a0df2bb-4892-43fb-9cd6-f22130e858b8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5889 | T16182-CV03-P0ZEN-163104 | 2018-01-08 | DHI-TRANSMIT-001233 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8d5da02-a323-4aef-b3f3-4599cc4a1dd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5890 | T16182-CV03-P0ZEN-163201 | 2018-01-08 | DHI-WTRAN-001104 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3dc815c8-620d-44f7-a7fc-68020d79ebda | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5891 | T16182-YT10-P0ZEN-152207 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=623dcf35-f54c-432e-98ab-13773aae6a3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5892 | T16182-YT10-P0ZEN-152216 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28269314-e3c7-4dfd-85ff-2009eabadb47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5893 | T16182-YT10-P0ZEN-152219 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e9f7616-5808-4bd6-9289-18c426edfb62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5894 | T16182-YQ01-P0ZEN-152305 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=083c3564-20b5-45ae-af01-ca0b747db4ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5895 | T16182-YQ01-P0ZEN-152314 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57840ce1-06ee-4cb2-8395-bd9ae18aad8d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5896 | T16182-YQ01-P0ZEN-152317 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b42d25a5-3737-4461-8ab3-030ca3c3014b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5897 | T16182-YB11-P0ZEN-152405 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdcac633-ab4b-4a15-be9b-b5b03d9840e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5898 | T16182-YB11-P0ZEN-152414 | 2018-01-08 | DHI-WTRAN-001105 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d39c033c-2d6b-49a1-b0f7-b88021f3754a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5899 | T16182-YE00-P0GCF-130015 | 2018-01-08 | DHI-WTRAN-001106 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68f1be2c-0fa9-43ae-b1df-7d0beb13c46e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5900 | T16182-YF00-P0GCF-130018 | 2018-01-08 | DHI-WTRAN-001106 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02c8377a-04bd-4a12-976b-73dc5c11c901 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5901 | T16182-CV03-P0CWQ-161134 | 2018-01-08 | DHI-TRANSMIT-001234 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b830bf7d-cd4b-49f0-8ff7-6521a807188d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5902 | T16182-XJ00-P8ZEN-125570 | 2018-01-08 | DHI-WTRAN-001108 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80ca5bd3-437b-468f-9c30-51cf3ce7700e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5903 | T16182-XJ00-P6MKA-260003 | 2018-01-08 | DHI-TRANSMIT-001235 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98ca60cf-ce98-44a0-9f9b-7c9610ab0b7b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5904 | T16182-XJ00-P7MKA-260006 | 2018-01-08 | DHI-TRANSMIT-001235 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ab22b53-5264-40e8-bab4-7d77ded9ae2c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5905 | T16182-YT02-P0PCA-126529 | 2018-01-08 | DHI-WTRAN-001109 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31a2a6fb-5df0-4cb1-bdef-ea9c22bb9404 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5906 | T16182-XG01-P0LB-122021 | 2018-01-09 | DHI-TRANSMIT-001236 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfa40cbf-8b69-4cb6-a6f0-5d0abd7da8e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5907 | T16182-YK00-P0LB-122072 | 2018-01-09 | DHI-WTRAN-001111 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5a33dd4-58ef-4808-b323-8920650afa17 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5908 | T16182-YT01-P0LB-122100 | 2018-01-09 | DHI-WTRAN-001111 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f038bbcf-b582-4ec6-9262-d4b6237a8890 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5909 | T16182-YQ01-P0LB-122107 | 2018-01-09 | DHI-WTRAN-001111 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=989604b7-132b-4f26-a1b3-edadcd5ba978 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5910 | T16182-XG02-P0SGA-138601 | 2018-01-09 | DHI-WTRAN-001112 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b3d731a-17f4-450a-a798-019c7092d06f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5911 | T16182-XG02-P0SGE-138602 | 2018-01-09 | DHI-WTRAN-001112 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2cf335b-b998-47f7-b400-54a2738c7b60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5912 | T16182-XG02-P0SGC-138604 | 2018-01-09 | DHI-WTRAN-001112 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6927941-10b0-41db-b5c4-8f1823b46c8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5913 | T16182-XG02-P0SGC-138606 | 2018-01-09 | DHI-WTRAN-001112 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a58981da-038f-4952-8603-86c25fe94609 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5914 | T16182-UC02-P8QHA-125304 | 2018-01-09 | DHI-TRANSMIT-001237 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f622ffa-cc3d-47a1-b026-49e665909587 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5915 | T16182-YD04-P0ZEN-152018 | 2018-01-09 | DHI-WTRAN-001113 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=066d40fc-b846-42da-b5a7-4eacaeb07b8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5916 | T16182-YE00-P0ZEN-152726 | 2018-01-09 | DHI-TRANSMIT-001238 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1955c14-f59a-45c3-91e6-995b59c0779c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5917 | T16182-YE00-P0ZEN-152727 | 2018-01-09 | DHI-TRANSMIT-001238 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a11dd8bf-699c-4076-83f4-f294c7b660e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5918 | T16182-YE00-P0ZEN-152728 | 2018-01-09 | DHI-TRANSMIT-001238 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1dd881d1-fca6-4776-9372-779d6d8a27cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5919 | T16182-YE00-P0ZEN-152729 | 2018-01-09 | DHI-TRANSMIT-001238 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=349a254b-5524-4c87-ad97-ceb3cd292591 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5920 | T16182-YE00-P0ZEN-152730 | 2018-01-09 | DHI-TRANSMIT-001238 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eddcb531-7664-4a03-a300-f8206557edb3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5921 | T16182-YB03-P0ZEN-165548 | 2018-01-09 | DHI-WTRAN-001114 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c573fdf3-b453-4951-b438-a8dfc99fff55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5922 | T16182-YQ08-P0CY-154047 | 2018-01-09 | DHI-WTRAN-001115 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6de4ab72-76ff-49a5-932b-1a8f014190d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5923 | T16182-YR01-P0ZEN-110201 | 2018-01-10 | DHI-TRANSMIT-001239 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90d36225-1f3b-41a9-b25f-bcbc5d523237 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5924 | T16182-XG02-P0SGK-138502 | 2018-01-10 | DHI-TRANSMIT-001240 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef5404c6-384d-4b50-8d60-390e4cfd7f99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5925 | T16182-XH01-P0SGK-138512 | 2018-01-10 | DHI-TRANSMIT-001240 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e0b7bb9-40cd-4a50-b4a6-338d22768ec1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5926 | T16182-YT10-P0SGK-138522 | 2018-01-10 | DHI-TRANSMIT-001240 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88859ea9-f50b-4156-afaf-d3fc7fb8f700 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5927 | T16182-YD00-P0CYE-138541 | 2018-01-10 | DHI-TRANSMIT-001240 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d460c68-28b1-4d59-a2dc-ee567a8267c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5928 | T16182-YU02-P0CYE-138542 | 2018-01-10 | DHI-TRANSMIT-001240 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3ce9b27-1db7-44d6-826f-6fbe358ac417 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5929 | T16182-YD00-P0SGZ-138531 | 2018-01-10 | DHI-TRANSMIT-001240 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b8b3630-2cce-4bbd-b0d6-2a6240d2eb68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5930 | T16182-CA05-P0UCB-180681 | 2018-01-10 | DHI-TRANSMIT-001241 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=087044cf-72fb-4b18-9117-4a0f4085a78a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5931 | T16182-CA05-P0UCB-180685 | 2018-01-10 | DHI-TRANSMIT-001241 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0f34c15-5e34-45cc-b6cc-9e2932a7b0eb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5932 | T16182-CA05-P0UCB-180687 | 2018-01-10 | DHI-TRANSMIT-001241 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8f1499f-2633-4108-a8d0-926036f27fad | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5933 | T16182-CA05-P0UYC-182983 | 2018-01-10 | DHI-TRANSMIT-001242 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23f4557c-aa84-40bb-84f6-617c9cec9ca5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5934 | T16182-CA05-P0UYC-182984 | 2018-01-10 | DHI-TRANSMIT-001242 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4b567df-277b-4319-89c8-2c607494d66f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5935 | T16182-CA05-P0UYC-182985 | 2018-01-10 | DHI-TRANSMIT-001242 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87aed131-dcf5-4f42-ae0f-cb934a70d779 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5936 | T16182-CA05-P0UYP-183283 | 2018-01-10 | DHI-TRANSMIT-001243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd2604e1-777f-4fcf-b0d7-870c4a37b3e2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5937 | T16182-CA05-P0UYP-183284 | 2018-01-10 | DHI-TRANSMIT-001243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b1c0b5a-53d2-4111-a6d3-6d2f26e7cd8a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5938 | T16182-CA05-P0UYP-183285 | 2018-01-10 | DHI-TRANSMIT-001243 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bfc10f0-2f8d-4ef1-8db7-97c633138326 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5939 | T16182-CA05-P0UST-182085 | 2018-01-10 | DHI-TRANSMIT-001244 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b990f576-397e-4bc7-a536-6af6da677995 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5940 | T16182-XJ00-P0LAB-140208 | 2018-01-10 | DHI-WTRAN-001116 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb82758b-cee6-41e2-a19e-1d169330cda8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5941 | T16182-XJ00-P0PGB-140209 | 2018-01-10 | DHI-WTRAN-001116 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09461fcb-f404-4d0b-a4cf-33cd189fbe72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5942 | T16182-YU03-P0QU-130406 | 2018-01-11 | DHI-WTRAN-001117 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba1e14f1-adc8-4069-b784-0d74ff152409 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5943 | T16182-YF00-P0QU-130407 | 2018-01-11 | DHI-WTRAN-001117 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42ca28b9-bbfe-4093-a9a2-72dbde0e820a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5944 | T16182-YD00-P0GK-130601 | 2018-01-11 | DHI-WTRAN-001117 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7149b2da-3332-40e0-be00-eb0449f69bde | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5945 | T16182-YS01-P0GK-130602 | 2018-01-11 | DHI-WTRAN-001117 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37cfd2ff-1b63-4c88-b524-774041f7bc3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5946 | T16182-YD00-P0MAA-220801 | 2018-01-11 | DHI-TRANSMIT-001246 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=711cbe52-5786-4b50-bab6-eae2519a4039 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5947 | T16182-YT01-P0GM-128502 | 2018-01-11 | DHI-WTRAN-001118 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a5a163d-e81e-4f56-b076-f13402c6f161 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5948 | T16182-YD00-P0GM-128503 | 2018-01-11 | DHI-WTRAN-001118 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=962dec35-6a00-4070-a932-ad0a621ac804 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5949 | T16182-XK00-P0GM-128505 | 2018-01-11 | DHI-WTRAN-001118 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d02f7a5-85eb-491f-90a1-f016ad47da7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5950 | T16182-XW01-P0GM-128507 | 2018-01-11 | DHI-WTRAN-001118 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa77c01d-9601-4691-919c-b85b779c7e1f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5951 | T16182-XS00-P0LC-110041 | 2018-01-11 | DHI-TRANSMIT-001247 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b09d60c9-9a38-41c7-8231-8025d961174a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5952 | T16182-XS00-P0LA-110042 | 2018-01-11 | DHI-TRANSMIT-001247 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e988313-15bd-4240-9fc5-5dfaee2270dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5953 | T16182-XS00-P0PGB-110043 | 2018-01-11 | DHI-TRANSMIT-001247 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4436f520-f99b-4928-bd17-21aaf8b0b428 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5954 | T16182-XS00-P0GHC-110044 | 2018-01-11 | DHI-TRANSMIT-001247 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96c12cda-b1a3-48f0-b21e-b62651f26531 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5955 | T16182-XM00-P0MAA-220015 | 2018-01-11 | DHI-WTRAN-001119 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d1de725-6322-4051-8432-5b2ceafa870b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5956 | T16182-YR05-P0GM-128511 | 2018-01-11 | DHI-WTRAN-001120 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4b86ced-ce6a-4e1e-8a5d-b25bfa414902 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5957 | T16182-CA00-P0UGD-186601 | 2018-01-11 | DHI-TRANSMIT-001248 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d1b7f09-e03d-4e31-91c6-85e8f1b788e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5958 | T16182-CA00-P0UGD-186602 | 2018-01-11 | DHI-TRANSMIT-001248 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14e653af-8e0a-4f8d-ba47-8a88eee6503c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5959 | T16182-CA01-P0UGD-186651 | 2018-01-11 | DHI-TRANSMIT-001248 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acb9eea0-090b-4f57-a5bd-2872b7a8526d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5960 | T16182-CA01-P0UGD-186652 | 2018-01-11 | DHI-TRANSMIT-001248 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=919c3003-1998-4574-91b9-0b2050ef50b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5961 | T16182-CA00-P0UGD-181914 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9482b85c-0a79-41a3-b07f-182852909717 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5962 | T16182-CA01-P0UGD-181952 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8c3e858-8c95-4e3e-a825-dae751a3093f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5963 | T16182-CA01-P0UGD-181953 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26e09be5-7f22-44dc-8367-ef23327d27f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5964 | T16182-CA01-P0UGD-181954 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b4e77ad-ba64-4e3b-aa86-93d28ca14735 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5965 | T16182-CA02-P0UGD-181960 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=441fef41-3753-4340-975e-701f3da5d6d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5966 | T16182-CA02-P0UGD-181961 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2541e6a7-bd66-4efe-8e8d-7b5de3acec73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5967 | T16182-CA02-P0UGD-181962 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6032e19-60ba-4a2d-8542-e2dd0efa16be | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5968 | T16182-CA02-P0UGD-181963 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2adeeb4-4ba2-4250-8a2e-d0685134d6ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5969 | T16182-CA02-P0UGD-181964 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=924823b5-f62a-4180-ab81-da3769128c27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5970 | T16182-CA03-P0UGD-181965 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6bfec66-17aa-46a9-bbd6-2cca82dbe74c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5971 | T16182-CA03-P0UGD-181966 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85c27e6a-3d66-45c0-8f0e-9a503cdee9b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5972 | T16182-CA03-P0UGD-181967 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1ae26de-63e7-45e1-8556-3660626d70f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5973 | T16182-CA03-P0UGD-181968 | 2018-01-11 | DHI-TRANSMIT-001249 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf57c524-4b42-4e81-9c58-9f96058996d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5974 | T16182-VK02-P0UZJ-173209 | 2018-01-12 | DHI-WTRAN-001121 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4286d31-002e-43a4-a940-e4b266c44366 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5975 | T16182-YF01-P0BYA-161051 | 2018-01-12 | DHI-TRANSMIT-001250 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6f3756b-9191-4cbd-a30a-0542386bbb18 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5976 | T16182-XG02-P0SGC-137001 | 2018-01-12 | DHI-TRANSMIT-001251 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=446c6811-9913-4d86-b8a6-94461ec17b68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5977 | T16182-XH01-P0SGC-137011 | 2018-01-12 | DHI-TRANSMIT-001251 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64627aa0-875b-4660-80e5-0a41936ddaaa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5978 | T16182-XG02-P0SGC-137101 | 2018-01-12 | DHI-TRANSMIT-001251 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfa6817b-50ab-4e22-be8a-dd78ae295c43 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5979 | T16182-XH01-P0SGC-137111 | 2018-01-12 | DHI-TRANSMIT-001251 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9eff271d-6138-4ab0-9e44-6ebf767f9389 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5980 | T16182-YD00-P0CYE-137441 | 2018-01-12 | DHI-TRANSMIT-001251 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b131cab-c816-4db3-a2b2-6fb9a7ae826a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5981 | T16182-YQ08-P0CY-154047 | 2018-01-12 | DHI-WTRAN-001122 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15d1f664-e39d-4f7b-a937-e8c15025ca90 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5982 | T16182-YQ08-P0CY-154031 | 2018-01-12 | DHI-TRANSMIT-001252 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99ece693-ec4b-4c5b-b3f1-fa6beed0f30d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5983 | T16182-YL01-P0CRN-161117 | 2018-01-12 | DHI-TRANSMIT-001253 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=822ee7b9-152a-4e2f-acb8-696d037304cc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5984 | T16182-YD00-P0CWQ-161401 | 2018-01-12 | DHI-TRANSMIT-001253 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cae16ee-37a7-4613-a3c7-3a4159d31813 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5985 | T16182-VE04-P0GHC-173801 | 2018-01-12 | DHI-TRANSMIT-001254 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6625f4f3-a5f1-4240-8e62-6c9a238893f4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5986 | T16182-XB02-P0GHC-173802 | 2018-01-12 | DHI-TRANSMIT-001254 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6801fffb-5099-4aad-a788-0c754211dc0c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5987 | T16182-YT10-P0MKY-290010 | 2018-01-15 | DHI-WTRAN-001123 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5988 | T16182-YD02-P0SAC-163408 | 2018-01-15 | DHI-TRANSMIT-001255 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=489a9937-bd9a-47f3-b288-e43ddc5fcf58 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5989 | T16182-YS01-P0MKY-290012 | 2018-01-15 | DHI-TRANSMIT-001256 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c805379c-fb23-4c7a-aa9a-d32433ed76ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5990 | T16182-XG02-P6MAA-220025 | 2018-01-17 | DHI-WTRAN-001124 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9500a70c-bdc3-4e5c-9fe1-1b7c1746db15 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5991 | T16182-XG02-P7MAA-220026 | 2018-01-17 | DHI-WTRAN-001124 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b3226dd-f88b-44d6-bc11-1540cc41988e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5992 | T16182-XG02-P6MAA-220029 | 2018-01-17 | DHI-TRANSMIT-001260 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2acde7c-0c4c-43ca-8e16-69a198b23155 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5993 | T16182-XG02-P6MAA-220027 | 2018-01-17 | DHI-TRANSMIT-001260 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91233ba6-965c-44c8-97b5-685f3dde5de4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5994 | T16182-XG02-P7MAA-220030 | 2018-01-17 | DHI-TRANSMIT-001260 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=401f39dc-71cd-41e0-bc92-4c7e5066aa9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5995 | T16182-XG02-P7MAA-220028 | 2018-01-17 | DHI-TRANSMIT-001260 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b60bd98-82b1-4b4f-b21b-0e189a63e609 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5996 | T16182-YU02-P0CYE-137442 | 2018-01-17 | DHI-TRANSMIT-001261 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c3439c3-d785-4f48-8bd1-da8aa7cfa80c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5997 | T16182-YD00-P0CYE-138841 | 2018-01-17 | DHI-TRANSMIT-001262 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8cf97b5-b601-4a6e-81d1-71e8f2f3544d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5998 | T16182-YD00-P0CYE-139741 | 2018-01-17 | DHI-WTRAN-001125 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c913555-3c05-4aad-8c1e-79408f2e170a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
5999 | T16182-YU02-P0CYE-139742 | 2018-01-17 | DHI-WTRAN-001125 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f351a747-b54c-40f1-8b71-c69c51c7f137 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6000 | T16182-YD00-P0CYE-139841 | 2018-01-17 | DHI-WTRAN-001125 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=926d302a-0d68-4917-ac7d-f8b331829ef4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6001 | T16182-YU02-P0CYE-139842 | 2018-01-17 | DHI-WTRAN-001125 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5d681d6-151d-4f07-94c7-e4898136ba2b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6002 | T16182-YD02-P0SAC-163419 | 2018-01-17 | DHI-WTRAN-001126 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a23b46a6-aa9d-42cc-89aa-0a77d7c6da0d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6003 | T16182-XG02-P0SGA-139501 | 2018-01-17 | DHI-TRANSMIT-001263 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea9e982a-0771-4d4c-8633-223282c2ac09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6004 | T16182-XH01-P0SGA-139511 | 2018-01-17 | DHI-TRANSMIT-001263 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1bf6825-fff6-479b-a13c-fe8ee9ee036a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6005 | T16182-XG02-P0SGA-139601 | 2018-01-17 | DHI-TRANSMIT-001263 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13105f1f-d606-498c-9f53-1685b9c8abb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6006 | T16182-XH01-P0SGA-139611 | 2018-01-17 | DHI-TRANSMIT-001263 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5833bbc3-87d0-4d24-976f-c1b442240752 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6007 | T16182-XB02-P0UAZ-172602 | 2018-01-17 | DHI-TRANSMIT-001264 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e38c0e3a-dbfc-4dba-b4ba-0785c02c7507 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6008 | T16182-XB02-P0UAZ-172603 | 2018-01-17 | DHI-TRANSMIT-001264 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42da9f2d-904b-42f3-b27a-b62059402fa7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6009 | T16182-XB02-P0UAZ-172608 | 2018-01-17 | DHI-TRANSMIT-001264 | IFC | 8 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=260c3691-cb2f-4e7b-9f58-915aec317fcf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6010 | T16182-VK02-P0ULC-171309 | 2018-01-17 | DHI-TRANSMIT-001265 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ad20ef2-7d0d-42f3-bf84-f622101d4c0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6011 | T16182-XB02-P0ULC-172502 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abe6b090-2d48-47af-be2c-2f0ffd331198 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6012 | T16182-VK02-P0ULC-172503 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4343e50a-80b6-42a0-8c89-790b225c031b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6013 | T16182-XB02-P0UGF-172522 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72fae47d-eb29-48dd-9288-f1b09ad4a53a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6014 | T16182-VK02-P0UGF-172523 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b38157bc-39fb-4986-bae2-e35b85526470 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6015 | T16182-XB02-P0UGD-172542 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d31a38d3-2220-40ab-87ec-b0fe8d378d6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6016 | T16182-VK02-P0UGD-172543 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c5787f4-b29a-40cf-8638-e79b85226282 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6017 | T16182-XB02-P0UGG-172562 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f77ca515-dda5-45d6-89f5-7d4d2fc59943 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6018 | T16182-VK02-P0UGG-172563 | 2018-01-17 | DHI-TRANSMIT-001266 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ff832ea-ca25-4db3-99eb-3ae5b7f49f23 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6019 | T16182-YD00-P0MKW-260011 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ff276ab-c2c8-4d3a-b0bd-d6c1ba037e5c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6020 | T16182-YD00-P0MKW-260012 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bf8418a-8cc0-43bb-a61d-434b172742f0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6021 | T16182-YD00-P0MKW-260013 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65ec68c2-2775-4726-9ffb-b790c9cfb17d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6022 | T16182-YD00-P0MKG-260014 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b0fdaa4-4e6a-42fd-a458-b895d1434fc8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6023 | T16182-YD00-P0MKG-260015 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b20ded1-0c96-455a-b4d5-ea4c94287c41 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6024 | T16182-YD00-P0MKG-260016 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c253716-1879-487e-b0b8-417c30645427 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6025 | T16182-YD00-P0MKG-260017 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89820db3-6849-4a4e-b74b-400ce207a659 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6026 | T16182-YD00-P0MKG-260018 | 2018-01-17 | DHI-TRANSMIT-001267 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c8d4370-9cea-4a6b-99a4-08557a9e6291 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6027 | T16182-XB02-P0UAG-172102 | 2018-01-17 | DHI-TRANSMIT-001268 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f4c8ac3-0d82-4471-942d-6701f92b4df9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6028 | T16182-XB02-P0UAG-172162 | 2018-01-17 | DHI-TRANSMIT-001268 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85f4285e-a009-4075-9f29-e8a3686f7409 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6029 | T16182-XF00-P0GM-128510 | 2018-01-18 | DHI-WTRAN-001127 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5532d977-0d58-4bc5-9f69-317cae64dbea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6030 | T16182-YK08-P0GKC-420051 | 2018-01-18 | DHI-WTRAN-001128 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7848ef1-6c9e-4726-a302-7f9185e6e426 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6031 | T16182-VK02-P8UTH-172008 | 2018-01-18 | DHI-TRANSMIT-001274 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba23ea9e-c340-4544-aabb-46298477bd87 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6032 | T16182-XH01-P0SGE-136912 | 2018-01-18 | DHI-TRANSMIT-001275 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=089a652b-9395-4462-a397-fd3b7e8825b8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6033 | T16182-YD00-P0CYE-138641 | 2018-01-18 | DHI-TRANSMIT-001275 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dac1655d-86db-4c47-81b7-0ea8ff2f622b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6034 | T16182-YU02-P0CYE-138642 | 2018-01-18 | DHI-TRANSMIT-001275 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b08ff10-83e2-46c5-ba7f-e06c267e25e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6035 | T16182-YD00-P0CYE-137341 | 2018-01-18 | DHI-TRANSMIT-001276 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd3709ef-0062-4c59-b248-bd489be1a075 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6036 | T16182-YD00-P0CYE-138341 | 2018-01-18 | DHI-TRANSMIT-001276 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=639d5a73-0b48-4ad1-8102-7aae7126bdd0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6037 | T16182-YU02-P0CYE-138342 | 2018-01-18 | DHI-TRANSMIT-001276 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1b62c63-ca7b-4895-9f2b-cbc2f153fbf2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6038 | T16182-YS01-P0MKY-290009 | 2018-01-19 | DHI-WTRAN-001129 | IFR | E | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=489b413f-494b-4fd5-b60c-5dac530034c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6039 | T16182-YT01-P0SAA-136002 | 2018-01-19 | DHI-WTRAN-001130 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e318706-98c1-4ad4-a91e-2b37f9640984 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6040 | T16182-YL16-P0ZEN-165552 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e74c2cd5-47e5-4422-b9f1-c3a379af2135 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6041 | T16182-YL16-P0ZEN-165553 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42f0551c-c96e-4557-b76e-5ab59877ea93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6042 | T16182-YL16-P0ZEN-165554 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13a442a3-12ed-4f31-a2d4-7e7cba828f49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6043 | T16182-YL16-P0ZEN-165555 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b49e07a2-3f11-4aea-8b29-4893a7dcb13b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6044 | T16182-YL16-P0ZEN-165556 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=397025e9-92e9-464e-a452-99fba7e3c75a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6045 | T16182-YL16-P0ZEN-165557 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4392eed3-53d4-4cf0-b9b5-d74956adcbcc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6046 | T16182-YL16-P0ZEN-165558 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b519f7e9-479d-4019-acbd-c89b48b526ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6047 | T16182-YL16-P0ZEN-165559 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80671080-9140-4f17-a85a-77e6dc82fc01 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6048 | T16182-YL16-P0ZEN-165560 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=570c4f77-5afc-4985-9710-cbcf9f51ad21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6049 | T16182-YL16-P0ZEN-165561 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ea333d1-38f3-404e-a62e-9a7d8709844c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6050 | T16182-YL16-P0ZEN-165562 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11ec3325-f2fa-4d32-826f-9bb023956355 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6051 | T16182-YL16-P0ZEN-165563 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9c9ee82-d659-4719-aeb7-75c8176c0045 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6052 | T16182-YL16-P0ZEN-165564 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b30c0e82-a33a-4f99-8200-170c5dfc5fbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6053 | T16182-YL16-P0ZEN-165565 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39c1c6d6-bc7f-4e4c-855a-329cc5e126b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6054 | T16182-YL16-P0ZEN-165566 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd566e07-6e40-49ab-924f-0d8f131655e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6055 | T16182-YL16-P0ZEN-165567 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ca0fb7a-6c88-4a8b-8be4-031826200dcf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6056 | T16182-YL16-P0ZEN-165568 | 2018-01-19 | DHI-TRANSMIT-001278 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b330c7d-54ad-4485-9592-08b0e9dcad00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6057 | T16182-XH01-P0SGE-137913 | 2018-01-19 | DHI-TRANSMIT-001279 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e571bba-5e04-4dba-b76a-966cee56ce7e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6058 | T16182-YK09-P0SMM-128007 | 2018-01-19 | DHI-TRANSMIT-001280 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67b1be7e-7782-45db-8527-60771ea13faf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6059 | T16182-YK09-P0SMS-128008 | 2018-01-19 | DHI-TRANSMIT-001280 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7353ee6-ceda-4456-9bf8-5d64048fb4ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6060 | T16182-YK09-P0SML-128023 | 2018-01-19 | DHI-TRANSMIT-001280 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cabc566-cb53-4a75-a09d-b91255eac139 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6061 | T16182-YS18-P0SMM-128010 | 2018-01-19 | DHI-TRANSMIT-001281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b90eacbe-d59f-41bb-8780-53b35721602b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6062 | T16182-YS18-P0SMS-128011 | 2018-01-19 | DHI-TRANSMIT-001281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1320446c-f4b1-4775-9a7f-7f313dff6f77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6063 | T16182-YS18-P0SML-128027 | 2018-01-19 | DHI-TRANSMIT-001281 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d523c3c-f7c4-4835-977c-87b456dd54f2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6064 | T16182-YF00-P0MKY-290007 | 2018-01-19 | DHI-TRANSMIT-001282 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a84184a0-037d-46bc-ad45-9b6a25e79d6c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6065 | T16182-YS01-P0MKY-290008 | 2018-01-19 | DHI-TRANSMIT-001283 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff0835c7-e533-4077-a57d-dd3cd8d89be1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6066 | T16182-XB02-P0GHC-173802 | 2018-01-19 | DHI-TRANSMIT-001284 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9669a3fd-ef6f-4f82-ae8f-4fd388d05df3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6067 | T16182-VE04-P0GKC-173601 | 2018-01-19 | DHI-TRANSMIT-001285 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c8933be-2f1d-474f-941c-1fb883012ea8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6068 | T16182-XB02-P0GKC-173602 | 2018-01-19 | DHI-TRANSMIT-001285 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44e97459-71d2-47c1-aac6-c935902665e5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6069 | T16182-XB02-P0GKC-173702 | 2018-01-19 | DHI-TRANSMIT-001285 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad4e3ff9-ac88-4ae7-bedf-704eb576cd41 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6070 | T16182-XH01-P0LF-140401 | 2018-01-19 | DHI-WTRAN-001131 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f2b1452-43f9-4027-92fc-617ef67c1267 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6071 | T16182-XH01-P0LF-140402 | 2018-01-19 | DHI-WTRAN-001131 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=822491ed-acb0-4389-a707-125d3ef1f153 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6072 | T16182-XH01-P0LF-140403 | 2018-01-19 | DHI-WTRAN-001132 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3abe5ec-ce7f-4e66-b648-10528230f719 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6073 | T16182-XH01-P0LF-140415 | 2018-01-19 | DHI-TRANSMIT-001286 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3f8ede5-127a-468e-a338-d61fd1375bad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6074 | T16182-XH01-P0LF-140416 | 2018-01-19 | DHI-TRANSMIT-001286 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53fd94ac-0ab6-472c-b47d-bc0c38df39e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6075 | T16182-XJ00-P0GKB-140215 | 2018-01-19 | DHI-TRANSMIT-001286 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33cb06b5-6549-4cc1-be01-3422ee8397db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6076 | T16182-XH01-P0SGK-136913 | 2018-01-22 | DHI-TRANSMIT-001287 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=170d6757-81cd-4a48-a4f5-8c9499536d19 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6077 | T16182-XH01-P0SGC-137411 | 2018-01-22 | DHI-TRANSMIT-001287 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af22082c-3f3e-4a67-88ea-0e61ea7e890b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6078 | T16182-CA06-P0UYE-183300 | 2018-01-22 | DHI-TRANSMIT-001288 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea43051d-78fd-4120-bd85-37026fdca584 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6079 | T16182-CA01-P0UYE-183351 | 2018-01-22 | DHI-TRANSMIT-001288 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69ceefce-a93b-4e46-a3fc-1b7befc37c64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6080 | T16182-CA01-P0UYE-183352 | 2018-01-22 | DHI-TRANSMIT-001288 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9368fee1-e6e5-460a-931a-09c46196a7d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6081 | T16182-CA01-P0UYE-183353 | 2018-01-22 | DHI-TRANSMIT-001288 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a8c7c84-e892-4f92-be0b-5f9b644a22e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6082 | T16182-CA02-P0UYE-183354 | 2018-01-22 | DHI-TRANSMIT-001288 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eaec8623-62a9-47ca-8e87-0eda8a1a01a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6083 | T16182-CA02-P0UYE-183355 | 2018-01-22 | DHI-TRANSMIT-001288 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c58d4265-b0c2-46d9-8f41-70e04f5a042d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6084 | T16182-YE04-P0BAU-152501 | 2018-01-23 | DHI-TRANSMIT-001289 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d1138c4-097e-4c29-9531-61920d3969e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6085 | T16182-YE01-P0BAU-152600 | 2018-01-23 | DHI-TRANSMIT-001289 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30dc750a-917b-47a1-ba6e-3426258ba1a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6086 | T16182-VN03-P0LB-122015 | 2018-01-23 | DHI-TRANSMIT-001290 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7c608d7-c177-424b-9b0b-4f706a6af0cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6087 | T16182-XH01-P0LB-122025 | 2018-01-23 | DHI-TRANSMIT-001290 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df0c06d6-1573-4c97-ac79-d08a5e14318e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6088 | T16182-YD00-P0LB-122006 | 2018-01-23 | DHI-TRANSMIT-001290 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abcaec90-5581-4924-b93f-60553edb5ab2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6089 | T16182-YT10-P0CYE-137643 | 2018-01-23 | DHI-WTRAN-001133 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0488cb13-8334-4dc5-b3fa-b3aade6760d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6090 | T16182-YT10-P0CYE-138643 | 2018-01-23 | DHI-WTRAN-001133 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d425e25-f509-415f-a3a6-02ea79cfca59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6091 | T16182-XG02-P0CYE-138744 | 2018-01-23 | DHI-WTRAN-001133 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c1d47e8-419f-4c21-8dbd-b7ea85a16e98 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6092 | T16182-XG02-P0CYE-138844 | 2018-01-23 | DHI-WTRAN-001133 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a99e003f-ac82-4db8-95b5-eb6f1be9048d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6093 | T16182-YT10-P0CYE-139543 | 2018-01-23 | DHI-WTRAN-001133 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44b19b65-7603-4c72-b0bb-4c745ee44365 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6094 | T16182-DM01-P0LAC-126012 | 2018-01-23 | DHI-WTRAN-001134 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e9c79c8-4edc-46b0-8fb9-35a0e5910d53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6095 | T16182-DM01-P0LAC-126062 | 2018-01-23 | DHI-WTRAN-001134 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6db9eaee-09fc-4da8-b937-cace756cd537 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6096 | T16182-YT10-P0ZEN-152230 | 2018-01-24 | DHI-WTRAN-001136 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9d561e2-628f-4e5d-a0a2-ffdc2325474d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6097 | T16182-YQ01-P0ZEN-152328 | 2018-01-24 | DHI-WTRAN-001136 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7f0e71f-82d8-4ec8-95b2-2653f8083176 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6098 | T16182-YB11-P0ZEN-152428 | 2018-01-24 | DHI-WTRAN-001136 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c22f818c-ce8c-418d-a766-c64664a9af9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6099 | T16182-YT10-P0ZEN-152231 | 2018-01-24 | DHI-WTRAN-001136 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc6e6cb7-2362-4dc4-86b3-637614c40372 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6100 | T16182-YQ01-P0ZEN-152329 | 2018-01-24 | DHI-WTRAN-001136 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4dd9382d-1105-4a3f-b8cc-39f03b722c4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6101 | T16182-YT01-P0LCB-127007 | 2018-01-24 | DHI-WTRAN-001137 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70234bfb-90d6-4d12-8b1c-718977e369a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6102 | T16182-YT10-P0CYE-136943 | 2018-01-24 | DHI-WTRAN-001138 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdf7a556-d665-4cba-b443-154df812326a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6103 | T16182-YT10-P0CYE-138743 | 2018-01-24 | DHI-WTRAN-001138 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b746b7a-c31c-4ded-91a9-106fbdec451a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6104 | T16182-YT10-P0CYE-138843 | 2018-01-24 | DHI-WTRAN-001138 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62999376-0b7e-41db-99dc-8ebf88df6811 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6105 | T16182-XG02-P0CYE-139544 | 2018-01-24 | DHI-WTRAN-001138 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7aa3876-7fe3-4a71-a76b-b345dab47903 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6106 | T16182-YU02-P0ZEN-150211 | 2018-01-24 | DHI-TRANSMIT-001293 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a0151b7-ce71-41dd-b3c2-a583aab7a1af | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6107 | T16182-YU02-P0ZEN-150212 | 2018-01-24 | DHI-TRANSMIT-001293 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b9dec64-b43a-44fc-805b-20724faa0503 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6108 | T16182-YU03-P0CFA-151181 | 2018-01-24 | DHI-WTRAN-001139 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22d71ec0-6ada-477e-aeeb-897723017b7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6109 | T16182-YS01-P0MKY-290011 | 2018-01-24 | DHI-TRANSMIT-001294 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8429745d-8a53-4677-b8da-ff78ef57c478 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6110 | T16182-YS01-P0MKY-290013 | 2018-01-24 | DHI-TRANSMIT-001295 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b98bda11-db6a-48de-8212-ed008360a190 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6111 | T16182-XK00-P6MKA-260005 | 2018-01-24 | DHI-TRANSMIT-001296 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d01d09a-385a-4630-b917-0a5aa374fcec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6112 | T16182-XK00-P7MKA-260008 | 2018-01-24 | DHI-TRANSMIT-001296 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31f2cb7d-2a7f-464d-ad5e-6c7d236bf4a3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6113 | T16182-CA00-P0UST-182001 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4dbf009c-af49-4226-b208-c94be7125548 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6114 | T16182-CA00-P0UST-182002 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=356a7a4f-4440-4833-8830-95ba0d798607 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6115 | T16182-CA00-P0UST-182003 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87ca5032-9842-4029-a689-1b5193262525 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6116 | T16182-CA00-P0UST-182004 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9ba22a1-3af2-4c89-913f-afec9c1629dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6117 | T16182-CA00-P0UST-182005 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a37dda2e-218f-43b6-b422-082447d54c10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6118 | T16182-CA00-P0UST-182006 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3b2bbef-5fc3-485e-bc8c-57d8f57b014e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6119 | T16182-CA01-P0UST-182051 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fb3d2f2-6f1f-49f7-bcb9-f68563534c00 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6120 | T16182-CA01-P0UST-182052 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e7ce9b2-5a37-4435-8095-f44bca04a547 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6121 | T16182-CA01-P0UST-182053 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f698a929-335e-4adf-98f1-424dfacca68f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6122 | T16182-CA03-P0UST-182054 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e6866af-edf5-48cb-819b-32a70952c43d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6123 | T16182-CA03-P0UST-182056 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39441ead-e8f3-43b4-9fe0-273fd4de83db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6124 | T16182-CA02-P0UST-182059 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f29fc5f1-4d6a-4cc4-ab6f-09062c782fdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6125 | T16182-CA02-P0UST-182060 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55285cb6-c5c5-4b88-a36b-e11a4706b266 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6126 | T16182-CA03-P0UST-182062 | 2018-01-25 | DHI-TRANSMIT-001300 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8739d510-f65c-4beb-b577-5a5581391498 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6127 | T16182-YE00-P0ZEN-152711 | 2018-01-25 | DHI-WTRAN-001140 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7db4973a-728c-4241-8395-490a3e5bd6b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6128 | T16182-YF00-P0PCA-126522 | 2018-01-25 | DHI-WTRAN-001141 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c4f206a-5d0b-4264-8d8c-f5609994f57f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6129 | T16182-XG02-P1MBH-110013 | 2018-01-25 | DHI-TRANSMIT-001301 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1d2e47f-ed8f-40e8-9765-f89366aacb3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6130 | T16182-YD02-P0SAC-163413 | 2018-01-25 | DHI-TRANSMIT-001302 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfcfd7da-0e14-4b59-be99-04581cb8c1f3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6131 | T16182-YD02-P0SAC-163414 | 2018-01-25 | DHI-TRANSMIT-001302 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48647cc3-72d4-4022-9908-2c60bd9a10f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6132 | T16182-YD02-P0SAC-163420 | 2018-01-25 | DHI-TRANSMIT-001302 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1b1db7d-d89d-42ff-a72e-668ef8e8ea04 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6133 | T16182-YD02-P0SAC-163422 | 2018-01-25 | DHI-TRANSMIT-001302 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=503d8528-19a5-4e17-a1b9-576e771bddcd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6134 | T16182-YD00-P0LAC-126051 | 2018-01-25 | DHI-WTRAN-001142 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ccdf7cd-69e4-4b3e-aca7-00ecd0880f12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6135 | T16182-XG02-P0LAC-126053 | 2018-01-25 | DHI-WTRAN-001142 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=891bca99-a733-4e33-9a09-dc2a26ddc14e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6136 | T16182-YT01-P0MAG-123014 | 2018-01-25 | DHI-TRANSMIT-001303 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=562f764e-4c53-4f4f-8b35-0eda784fed6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6137 | T16182-XK00-P0MAG-123027 | 2018-01-25 | DHI-WTRAN-001143 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=750174e7-b43c-4554-80c1-aca777ae8704 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6138 | T16182-YK09-P0SMQ-128024 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca57ed47-348b-4cd6-a494-2473259b747b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6139 | T16182-YK09-P0SMU-128025 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47e714c2-103a-4d67-8551-36382e1e9b7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6140 | T16182-YK09-P0SMG-128026 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a9ec52c-8d23-4610-a8c4-591f63a08f73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6141 | T16182-YK09-P0SMC-128038 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7617cbd3-61e4-4fe9-aa85-03a93fc7cc11 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6142 | T16182-YK09-P0SMS-128039 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a5de695-3e44-4c38-bd8f-35753fe5803d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6143 | T16182-YK09-P0SMG-128040 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6ec9659-d1a9-425e-9d4c-6a51eb1a6ea4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6144 | T16182-YK09-P0SMM-128041 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d96fc4ee-345e-4587-8c00-c74e68ab48d8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6145 | T16182-YK09-P0SMU-128042 | 2018-01-29 | DHI-WTRAN-001147 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03f49ddd-bb8a-484a-87cd-7e36af80a369 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6146 | T16182-XB02-P0UEM-171702 | 2018-01-29 | DHI-TRANSMIT-001304 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e4c5fd8-6360-4218-9cce-45bae1b2e4b6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6147 | T16182-XB02-P0UEM-171708 | 2018-01-29 | DHI-TRANSMIT-001304 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebb295ba-e649-4961-be53-10aae6fb107e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6148 | T16182-VK02-P0UEM-171711 | 2018-01-29 | DHI-TRANSMIT-001304 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c73e30f-a41e-433e-ac79-d192c158761e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6149 | T16182-CA00-P0UYF-183601 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=759495a6-1ae3-4017-a95f-a11e310411c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6150 | T16182-CA00-P0UYF-183602 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5046d2cb-28b1-4a2f-bdb1-0c4b9fa711c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6151 | T16182-CA00-P0UYF-183603 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8788d397-67d4-4603-88e6-b6d7442b7e70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6152 | T16182-CA01-P0UYF-183651 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1246def1-baca-4185-8106-4512f4fa4dbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6153 | T16182-CA01-P0UYF-183652 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71ffd0c1-73e9-4eee-a971-aa4196c2cf24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6154 | T16182-CA01-P0UYF-183653 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8e2c9ac-1fa6-4beb-82b3-9169ced4339f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6155 | T16182-CA00-P0UYF-183604 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=728f1e84-5bca-49dc-881c-45fd315bca9c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6156 | T16182-CA02-P0UYF-183654 | 2018-01-29 | DHI-WTRAN-001148 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a666ac2-ac41-407d-b34b-d71d0f059786 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6157 | T16182-XJ00-P8ZEN-125520 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37a06152-f70f-4363-bdbf-7bc4cf2cbecc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6158 | T16182-XJ00-P8ZEN-125521 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73fae593-fbe5-41e1-9d2e-c8720f5f183a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6159 | T16182-XJ00-P8ZEN-125522 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d85dd99-eed9-4b99-a08d-64d5f471c03f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6160 | T16182-XJ00-P8ZEN-125523 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=363695a8-7f67-4e6d-a3cb-15a6b38f0e14 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6161 | T16182-XJ00-P8ZEN-125524 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d7d850b-17b9-4157-9dc5-1ae2e6d3bec6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6162 | T16182-XJ00-P8ZEN-125525 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8a6e618-8190-415f-b6ae-e586f9c8ccd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6163 | T16182-XJ00-P8ZEN-125526 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70e8c582-264d-4d99-8fe7-8b91b98d3c58 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6164 | T16182-XJ00-P8ZEN-125527 | 2018-01-29 | DHI-TRANSMIT-001305 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c6d6dd0-1c76-4a83-8473-472cc3a08452 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6165 | T16182-XB00-P0GM-128506 | 2018-01-29 | DHI-TRANSMIT-001306 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e5d7de8-0441-4aea-9e92-51a496e8a2d5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6166 | T16182-CA05-P0UYB-183581 | 2018-01-29 | DHI-WTRAN-001149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4aa4a4e-c6b9-4f3f-9851-d31299c29789 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6167 | T16182-CA05-P0UYB-183582 | 2018-01-29 | DHI-WTRAN-001149 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40e0bcd0-fbe7-4b7f-adfa-02591fb11999 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6168 | T16182-XW03-P0SAQ-135201 | 2018-01-29 | DHI-TRANSMIT-001307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab5e437a-2e6c-422a-8021-f8af00d76dd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6169 | T16182-XG07-P0SAQ-135202 | 2018-01-29 | DHI-TRANSMIT-001307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76c3dd3e-0ba5-492e-931d-6ab6a4659b7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6170 | T16182-XW03-P0SAQ-135203 | 2018-01-29 | DHI-TRANSMIT-001307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8605d68f-d77b-433b-8d35-2943825d21f3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6171 | T16182-XH02-P0SAQ-135204 | 2018-01-29 | DHI-TRANSMIT-001307 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bb78937-8764-4f03-b743-49e575e26e36 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6172 | T16182-XG02-P0CYE-137644 | 2018-01-29 | DHI-WTRAN-001150 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc8e63fd-53b1-447e-9cc0-3c07ce579d77 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6173 | T16182-XG02-P0CYE-138644 | 2018-01-29 | DHI-WTRAN-001150 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c78aa9e-64de-4be7-9085-9c9390fcca3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6174 | T16182-VK02-P0UZJ-173209 | 2018-01-29 | DHI-TRANSMIT-001308 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a85f9d5-5deb-41ef-bfff-90e3b34f10b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6175 | T16182-CV03-P0CWQ-161134 | 2018-01-29 | DHI-TRANSMIT-001309 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76d49c26-2d6f-49a2-941f-21bf2de8f527 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6176 | T16182-YD00-P0CWQ-161407 | 2018-01-29 | DHI-TRANSMIT-001309 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4677ebe-ba2b-495b-a571-ef393a04683d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6177 | T16182-YD00-P0CWQ-161408 | 2018-01-29 | DHI-TRANSMIT-001309 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d2c0179-9971-47b3-8806-095994925367 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6178 | T16182-YR05-P0CJN-290002 | 2018-01-29 | DHI-TRANSMIT-001310 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58813ae0-f1e5-4b8d-9027-ec74d42a7f74 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6179 | T16182-CA06-P0UYB-183500 | 2018-01-29 | DHI-TRANSMIT-001311 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3baa24e8-f951-4a95-b3c3-b3d127a3cc29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6180 | T16182-CA00-P0UYB-183501 | 2018-01-29 | DHI-TRANSMIT-001311 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=814d13a6-b7e0-4bd6-b62b-1bb89f715da2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6181 | T16182-CA00-P0UYB-183502 | 2018-01-29 | DHI-TRANSMIT-001311 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7027fa6b-302a-4bb4-b016-61db3719f257 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6182 | T16182-CA01-P0UYB-183551 | 2018-01-29 | DHI-TRANSMIT-001311 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bd1aec3-5ee7-484a-8b1a-452e1e0eccdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6183 | T16182-CA01-P0UYB-183552 | 2018-01-29 | DHI-TRANSMIT-001311 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2e117b2-9e49-484a-896b-a472e853ea3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6184 | T16182-CA02-P0UYB-183553 | 2018-01-29 | DHI-TRANSMIT-001311 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8750d01f-1a0a-4682-99e4-1434a8592c10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6185 | T16182-CA02-P0UYB-183554 | 2018-01-29 | DHI-TRANSMIT-001311 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1755accb-9bb0-4bb5-9078-8d6399da6900 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6186 | T16182-YT10-P0ZEN-150312 | 2018-01-29 | DHI-TRANSMIT-001312 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e519814-255d-4edb-88a4-b3d18ba77c8a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6187 | T16182-YK08-P0GKC-420051 | 2018-01-29 | DHI-TRANSMIT-001313 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3b16efc-40b6-4fa2-b526-d09605752dd0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6188 | T16182-YD00-P0EKG-124012 | 2018-01-29 | DHI-TRANSMIT-001314 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a683e16f-1cf2-4ae9-98b3-93b8e6a0939e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6189 | T16182-XW03-P0MJ-110053 | 2018-01-29 | DHI-TRANSMIT-001315 | IFC | 2 | D | TRUE | FALSE | 2018-01-29_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db4a4a85-d5b2-48c1-830f-771ec2fb4aa6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6190 | T16182-YM03-P8ZEN-125721 | 2018-01-29 | DHI-WTRAN-001151 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fe94cfe-fe7a-4879-ba05-0535761f5f2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6191 | T16182-YT10-P8ZEN-125764 | 2018-01-29 | DHI-WTRAN-001151 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd9ccc47-5231-4655-b1b9-bcfcb373fa69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6192 | T16182-YD04-P0ZEN-152016 | 2018-01-29 | DHI-WTRAN-001152 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce6fb5e8-2948-4943-9475-ca2e3c1e51f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6193 | T16182-YD04-P0ZEN-152019 | 2018-01-29 | DHI-WTRAN-001152 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6b3aa81-9da6-4a04-b99a-fb306064dd3a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6194 | T16182-YF00-P0SCA-127518 | 2018-01-29 | DHI-WTRAN-001153 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6609014-0824-4f23-9f33-26f8cae239fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6195 | T16182-YL00-P0SCA-127520 | 2018-01-29 | DHI-WTRAN-001153 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ecc1958-2fdd-4a65-898c-5787d85f2e29 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6196 | T16182-CV03-P0SCA-127521 | 2018-01-29 | DHI-WTRAN-001153 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afa24f8c-9cde-4d42-a2cb-6a599aae09c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6197 | T16182-CV03-P0CRT-161149 | 2018-01-30 | DHI-WTRAN-001154 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de83d0a2-687b-4c38-8f19-929e269459d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6198 | T16182-XW01-P0MAG-123007 | 2018-01-30 | DHI-TRANSMIT-001316 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a1809c9-2355-4547-8010-550ae1ba4160 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6199 | T16182-CV03-P8ZEN-125601 | 2018-01-30 | DHI-TRANSMIT-001317 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2908615-6b71-4627-af85-7a615c53b6f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6200 | T16182-CC08-P8ZEN-125615 | 2018-01-30 | DHI-WTRAN-001155 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0d3bdb8-de86-4907-b087-d38df75d7f2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6201 | T16182-YT10-P0ZEN-150311 | 2018-01-30 | DHI-TRANSMIT-001318 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f10227c-a3d1-473b-ad40-a7b9ce31a471 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6202 | T16182-YT10-P0ZEN-150314 | 2018-01-30 | DHI-TRANSMIT-001318 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35267f46-d61a-416e-98c6-d67a42907f65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6203 | T16182-YS01-P0MKY-290009 | 2018-01-30 | DHI-TRANSMIT-001319 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b90f4db7-65c1-4548-9685-d35baf9bf776 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6204 | T16182-BV02-P0CJN-290003 | 2018-01-30 | DHI-WTRAN-001156 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20f5b820-b35f-43ce-af7f-9e0e047230bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6205 | T16182-XK00-P8ZEN-125530 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7c2a19d-472e-418f-b39d-7b2045838da5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6206 | T16182-XK00-P8ZEN-125531 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eab0388b-975d-448f-841f-a18f976f412c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6207 | T16182-XK00-P8ZEN-125532 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c83ba1fe-6652-425c-9e9a-b9760e22596e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6208 | T16182-XK00-P8ZEN-125533 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93d118b5-568e-4a06-8bd6-f29e30cc613e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6209 | T16182-XK00-P8ZEN-125534 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae0b00e6-2889-4352-adff-335db8a75de1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6210 | T16182-XK00-P8ZEN-125535 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e33f2567-0d92-4cf3-b482-b9bb3566d2da | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6211 | T16182-XK00-P8ZEN-125536 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f4756c8-5a53-4365-9f90-e5fbbe3c3b18 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6212 | T16182-XK00-P8ZEN-125537 | 2018-01-30 | DHI-TRANSMIT-001320 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=732f3c32-38ad-47d7-bda6-9b76ded0c356 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6213 | T16182-YD00-P0QC-130302 | 2018-01-30 | DHI-TRANSMIT-001321 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7cf4ee8-3994-44b1-a0ec-992e1f2942cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6214 | T16182-YS00-P0CJN-290001 | 2018-01-30 | DHI-TRANSMIT-001322 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f712cab4-3892-4fb5-910c-9c7e36c0b33c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6215 | T16182-DP00-P8ZEN-125737 | 2018-01-30 | DHI-WTRAN-001157 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e852897c-f5e4-4096-b2f1-1e35e0abdf9a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6216 | T16182-CV03-P8ZEN-125607 | 2018-01-30 | DHI-TRANSMIT-001323 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bf3216d-f442-4077-b2d8-a8f1e2f46c63 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6217 | T16182-CV03-P8ZEN-125609 | 2018-01-30 | DHI-TRANSMIT-001323 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da6b3ffd-4d90-4149-8e99-175db58e96f9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6218 | T16182-XJ00-P8ZEN-125570 | 2018-01-30 | DHI-TRANSMIT-001323 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41d1a02c-71a1-43f3-9cf5-651a17eb41e9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6219 | T16182-YD00-P0SGZ-138631 | 2018-01-31 | DHI-TRANSMIT-001324 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09e6c35f-9cb4-433c-8a6b-78884c094d92 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6220 | T16182-YD02-P0ZEN-165516 | 2018-01-31 | DHI-WTRAN-001158 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20aa5dbc-2265-40fe-b354-49a092fcdbc5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6221 | T16182-YD02-P0ZEN-165518 | 2018-01-31 | DHI-WTRAN-001158 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=926b355b-dab8-4a95-9f9e-d0ebd1367156 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6222 | T16182-XG02-P0LCB-127002 | 2018-01-31 | DHI-TRANSMIT-001325 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c6cb2f9-d070-4e19-ae40-2f6a1f9fa6c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6223 | T16182-YD00-P0LCB-127001 | 2018-01-31 | DHI-TRANSMIT-001325 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c58b1cb3-8d2e-4fd7-bbf9-c57db6a7f170 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6224 | T16182-YD00-P0LCB-127031 | 2018-01-31 | DHI-TRANSMIT-001325 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac71669c-c8fc-49e8-9fa5-9df6417e3aff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6225 | T16182-YL00-P0QU-130404 | 2018-02-01 | DHI-WTRAN-001159 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6226 | T16182-XB02-P0UAG-172102 | 2018-02-01 | DHI-TRANSMIT-001326 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9c59f14-7808-420d-8173-55d14b94cb77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6227 | T16182-XB02-P0UAG-172108 | 2018-02-01 | DHI-TRANSMIT-001326 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21ad1adc-99e9-4ae3-aaee-2cec21a155ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6228 | T16182-XB02-P0UAG-172162 | 2018-02-01 | DHI-TRANSMIT-001326 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a43cf37-2753-4101-bd9c-dff93dc4c962 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6229 | T16182-XB02-P0UAG-172168 | 2018-02-01 | DHI-TRANSMIT-001326 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b391d2a5-0750-4e73-bcc1-6852522f616b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6230 | T16182-YD00-P0BAT-150621 | 2018-02-01 | DHI-WTRAN-001160 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af5d37d4-6215-4b2d-8ede-80df3e75dff3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6231 | T16182-YD00-P0BBT-150671 | 2018-02-01 | DHI-WTRAN-001160 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26f1385f-8829-4914-acc2-43035bedf38c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6232 | T16182-YD04-P0ZEN-152007 | 2018-02-01 | DHI-TRANSMIT-001327 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8884d3bf-c682-4b57-8e84-602067f906f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6233 | T16182-XS00-P0QU-130401 | 2018-02-01 | DHI-WTRAN-001161 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3e48b13-264c-4db2-812f-f8a91c36793b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6234 | T16182-XG02-P0QU-130403 | 2018-02-01 | DHI-TRANSMIT-001328 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1c4bb05-56aa-41fc-a539-d1f9e7e2565a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6235 | T16182-YD00-P0QU-130402 | 2018-02-01 | DHI-TRANSMIT-001328 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ffa118d-308f-48a6-bfba-0e52429bda91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6236 | T16182-YK10-P8QHA-125207 | 2018-02-01 | DHI-TRANSMIT-001330 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8524a7b-43f1-4d52-80b2-9ca88e3d27e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6237 | T16182-YD00-P0BAA-150767 | 2018-02-01 | DHI-WTRAN-001162 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1985556-1d26-4349-b4c9-95675c360afc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6238 | T16182-YD00-P0BAA-150762 | 2018-02-01 | DHI-TRANSMIT-001331 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea3254c0-da3e-4173-9c7b-9ec98effff03 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6239 | T16182-CQ02-P0MBA-121076 | 2018-02-02 | DHI-WTRAN-001163 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd4a7e7a-a4bd-45ab-b487-e1d2d3f20876 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6240 | T16182-XG02-P0SGA-138601 | 2018-02-02 | DHI-TRANSMIT-001333 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68851c9e-2738-417b-a999-d6c614d5d35e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6241 | T16182-XG02-P0SGE-138602 | 2018-02-02 | DHI-TRANSMIT-001333 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=792f5792-cc0a-4e62-99e1-9a7d70c9639c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6242 | T16182-XG02-P0SGE-138603 | 2018-02-02 | DHI-TRANSMIT-001333 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=432ddcfe-14ad-41d0-adaa-98a7b09e9e00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6243 | T16182-XG02-P0SGC-138604 | 2018-02-02 | DHI-TRANSMIT-001333 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a663827b-cc33-4c81-a55a-574e91f92846 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6244 | T16182-XG02-P0SGC-138606 | 2018-02-02 | DHI-TRANSMIT-001333 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=026ba921-9514-4c61-9dfe-cb3b4fab0ef8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6245 | T16182-XG02-P0SGK-138608 | 2018-02-02 | DHI-TRANSMIT-001333 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da3da59c-3b14-4e55-9468-11fb63977419 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6246 | T16182-YS18-P0SMC-128043 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb0cd4d9-4d59-4d74-9b2f-57f69a475d44 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6247 | T16182-YS18-P0SMG-128047 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba0193b2-5763-4b55-ad4e-1614effbbb3c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6248 | T16182-YS18-P0SMG-128048 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54827a45-1815-4be5-a50a-d70b258c39b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6249 | T16182-YS18-P0SMM-128049 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c2dddb6-b04d-44b2-966e-e9ce23353f06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6250 | T16182-YS18-P0SMQ-128045 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6547a600-e48d-4509-8213-638618dd7ca0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6251 | T16182-YS18-P0SMS-128044 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f2e7a1e-c9b1-47f8-b9bc-8c6f29d72d6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6252 | T16182-YS18-P0SMU-128046 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fb4db67-4093-4c4f-9299-aae84a599e65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6253 | T16182-YD00-P0SMG-128051 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdb1121d-1842-43ba-9ab1-ab6ce923a4fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6254 | T16182-YD00-P0SMG-128052 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5716625-7e75-4f7f-a4e8-ef33a3efe340 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6255 | T16182-YD00-P0SMG-128053 | 2018-02-02 | DHI-WTRAN-001164 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8baddae4-f473-4f5d-9d3d-17316af8d91d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6256 | T16182-CA00-P0UYC-182901 | 2018-02-02 | DHI-TRANSMIT-001334 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5eb15fa-6258-43d9-8751-f855eb63c0c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6257 | T16182-CA00-P0UYC-182904 | 2018-02-02 | DHI-TRANSMIT-001334 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21090beb-f850-4c49-9fb9-dea673aff437 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6258 | T16182-CA00-P0UYC-182905 | 2018-02-02 | DHI-TRANSMIT-001334 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4d8eed5-69de-47f0-9dfc-1e5602347ca8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6259 | T16182-CA00-P0UYC-182906 | 2018-02-02 | DHI-TRANSMIT-001334 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc86972e-6785-4ad8-9f42-290ac1b8fb7c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6260 | T16182-YD00-P0STG-130502 | 2018-02-02 | DHI-TRANSMIT-001335 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=615f35cd-084c-45f7-9f81-143b349a6221 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6261 | T16182-YE03-P0BAU-152505 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3ac48c2-5b0e-46ff-bcad-4a2b4ec8b580 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6262 | T16182-YE03-P0BAU-152515 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97cb0888-c492-4e03-90b2-0eba4e1343e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6263 | T16182-YE03-P0BAU-152518 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=567cec17-2c53-404f-aa9d-7e3b7143264e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6264 | T16182-YE03-P0BAU-152520 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cfca123-4051-4cff-8a11-7e3985140fe6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6265 | T16182-YE03-P0BAU-152526 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4702c543-3ab2-42f1-bea9-9138cef2c32b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6266 | T16182-YE03-P0BAU-152527 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=395a653f-07d0-47d0-846f-106913396749 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6267 | T16182-YE03-P0BAU-152528 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3ac119b-cbee-4bc5-9333-042d7f2c170f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6268 | T16182-YE03-P0BAU-152538 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95139964-2884-437e-b499-bd053f2e1507 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6269 | T16182-YE01-P0BAU-152601 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0299e772-3f91-4512-94d5-7f5f96d3f9af | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6270 | T16182-YE01-P0BAU-152620 | 2018-02-02 | DHI-TRANSMIT-001336 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01350188-a843-41c9-88b9-a6e41268d7a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6271 | T16182-XB02-P0UZT-172702 | 2018-02-02 | DHI-TRANSMIT-001337 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=765a0524-3009-4cf6-92d6-c6e0d53944a6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6272 | T16182-XB02-P0UZT-172703 | 2018-02-02 | DHI-TRANSMIT-001337 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2a0a41d-9802-43d3-a1b3-dabd54072c9c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6273 | T16182-VK02-P0UZT-172704 | 2018-02-02 | DHI-TRANSMIT-001337 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0abbfa22-325c-474f-b3f5-eb185511fb6f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6274 | T16182-VK02-P0UZT-172713 | 2018-02-02 | DHI-TRANSMIT-001337 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f2f90ea-bdd2-456a-bf3b-4a75574bfce6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6275 | T16182-YU03-P0BB-150836 | 2018-02-02 | DHI-WTRAN-001165 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ab3b1d4-4138-4413-8f67-9a76fddebffa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6276 | T16182-XK00-P8ZEN-125509 | 2018-02-05 | DHI-TRANSMIT-001338 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=722df27c-8ea3-4aa1-9e73-96bba8360bb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6277 | T16182-YQ01-P0ZEN-152304 | 2018-02-05 | DHI-TRANSMIT-001339 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=944bd823-649a-4ed8-8681-75d616d30432 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6278 | T16182-CA00-P0UYP-183205 | 2018-02-05 | DHI-WTRAN-001166 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b25519d-f514-40b1-99a8-969f8c7ec207 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6279 | T16182-CA00-P0UYP-183201 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=640fbbfa-98c0-4805-9168-eb14e9674d78 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6280 | T16182-CA00-P0UYP-183202 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1288cffd-87a9-4147-ae83-11ebc15bd2b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6281 | T16182-CA00-P0UYP-183203 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80d913f6-0ca7-431c-88fc-c5654c67fc11 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6282 | T16182-CA00-P0UYP-183204 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93493c72-1153-433a-82b4-633d5939f4e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6283 | T16182-CA01-P0UYP-183252 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e02c6e9b-fbef-43a5-ae3e-a1846a2e42c3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6284 | T16182-CA01-P0UYP-183253 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b715abc-ee42-4b32-b2c9-cf944a17ac3c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6285 | T16182-CA01-P0UYP-183254 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bafae275-a31f-4a20-8ffc-740b7d6e5a6a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6286 | T16182-CA02-P0UYP-183257 | 2018-02-05 | DHI-TRANSMIT-001340 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad0b38b3-0c41-4b6f-a8aa-56d05823c714 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6287 | T16182-YD04-P0ZEN-152017 | 2018-02-06 | DHI-WTRAN-001167 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3219c127-150d-42b9-97df-32366aaf69c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6288 | T16182-XH02-P0SAV-135104 | 2018-02-06 | DHI-TRANSMIT-001341 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d573f0eb-a915-4b4d-bfe8-ab0cafefb2b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6289 | T16182-VK02-P0UBN-172203 | 2018-02-06 | DHI-TRANSMIT-001342 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44bccd68-ab73-4365-8091-81890cfe3d82 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6290 | T16182-XB02-P0UBN-172202 | 2018-02-06 | DHI-TRANSMIT-001342 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c818ac53-543e-4897-ad6f-b176f0a1e222 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6291 | T16182-XJ00-P0LB-122028 | 2018-02-07 | DHI-TRANSMIT-001343 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=120635fb-e1c8-4e3a-9ac8-8f48234d497f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6292 | T16182-YE03-P0BAU-152514 | 2018-02-07 | DHI-WTRAN-001168 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0fe2026e-3cde-45f4-a94a-65f6de33168b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6293 | T16182-YE03-P0BAU-152516 | 2018-02-07 | DHI-WTRAN-001168 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e9f2ea-89f7-403c-86f4-4b1878d9a00f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6294 | T16182-CA00-P0UTX-183361 | 2018-02-07 | DHI-WTRAN-001169 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfacb8c5-2308-40a7-97f5-6e622d961090 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6295 | T16182-CA03-P0UTX-183371 | 2018-02-07 | DHI-WTRAN-001169 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6003e6e-5cf5-483c-accf-f701cebb8311 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6296 | T16182-CA03-P0UTX-183372 | 2018-02-07 | DHI-WTRAN-001169 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5676f3e3-ef7e-401f-8cf1-82fc2597e34c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6297 | T16182-CA03-P0UTX-183373 | 2018-02-07 | DHI-WTRAN-001169 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df8c24f5-27d7-4176-87df-b1e2253e3fcf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6298 | T16182-CA03-P0UTX-183375 | 2018-02-07 | DHI-WTRAN-001169 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06049640-5a0b-44d4-bdee-e761378ac897 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6299 | T16182-CA02-P0UTX-183377 | 2018-02-07 | DHI-WTRAN-001169 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f0d013d-4483-48a1-a572-59f986cc07ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6300 | T16182-CA06-P0UTX-183390 | 2018-02-07 | DHI-WTRAN-001169 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0d25498-d43b-4f50-a9f6-8b4714908b84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6301 | T16182-XG02-P0GKC-120002 | 2018-02-07 | DHI-TRANSMIT-001344 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90d650e5-5d18-4cd1-9264-c4fd4a6098dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6302 | T16182-CV03-P0ZEN-163201 | 2018-02-07 | DHI-TRANSMIT-001345 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cb2e91b-60c2-4e89-b059-de8a387f0d55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6303 | T16182-XG02-P0LD-130204 | 2018-02-08 | DHI-TRANSMIT-001346 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d25911b-1197-4809-814a-8268c4173a3d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6304 | T16182-XG07-P0LD-130203 | 2018-02-08 | DHI-TRANSMIT-001346 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f4ad5a1-5aff-4b2f-8e32-d622f9d4e003 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6305 | T16182-YT01-P0CYE-136618 | 2018-02-08 | DHI-TRANSMIT-001347 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9a2eb46-deac-4c7e-aea1-cef73a361f26 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6306 | T16182-XG07-P0SAE-134302 | 2018-02-09 | DHI-WTRAN-001170 | IFR | A | D | TRUE | FALSE | 2018-02-09_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65fc9800-4a23-4793-9ba1-70323d10d636 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6307 | T16182-XH02-P0SAE-134304 | 2018-02-09 | DHI-WTRAN-001170 | IFR | A | D | TRUE | FALSE | 2018-02-09_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1faa0ffe-999c-4ce2-8e24-bf67028620fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6308 | T16182-XW03-P0SAE-134301 | 2018-02-09 | DHI-WTRAN-001170 | IFR | A | D | TRUE | FALSE | 2018-02-09_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b183894-5043-469e-aabb-07b7db6c178d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6309 | T16182-XW03-P0SAE-134303 | 2018-02-09 | DHI-WTRAN-001170 | IFR | A | D | TRUE | FALSE | 2018-02-09_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cbfba21-0a0b-4e91-8bd7-ce590fca2119 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6311 | T16182-YT01-P0SMQ-128019 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f20e261c-926d-4069-b231-80dccdce37e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6312 | T16182-YT01-P0SMU-128020 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52a37cc6-912b-4484-9197-88b2e507a622 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6313 | T16182-YT01-P0SMG-128021 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26c817ec-2bd2-4471-95c3-9e2ca2215d54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6314 | T16182-YT01-P0SMC-128033 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39e8d194-ed9f-4398-9c19-ef6b5378a77f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6315 | T16182-YT01-P0SMS-128034 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ef5e24a-fd32-43ab-971a-f66ad9523285 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6316 | T16182-YT01-P0SMG-128035 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=544708af-f761-4089-9bd2-b20a03775467 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6317 | T16182-YT01-P0SMM-128036 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2112c05b-f2a3-408f-ade4-8d11810f9393 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6318 | T16182-YT01-P0SMU-128037 | 2018-02-09 | DHI-TRANSMIT-001348 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43419754-bc75-46ff-96ab-e7f6e8f6eea5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6319 | T16182-YD02-P0ZEN-165504 | 2018-02-12 | DHI-WTRAN-001172 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9eda9a7e-1eea-4eff-80cb-7f55c1694c9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6320 | T16182-YD02-P0ZEN-165505 | 2018-02-12 | DHI-WTRAN-001172 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9718cab-f7d8-4885-a737-f366cb0c4ae8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6321 | T16182-YD02-P0ZEN-165508 | 2018-02-12 | DHI-WTRAN-001172 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1753f889-23d5-4093-888d-fc2d5e752cbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6322 | T16182-YD02-P0ZEN-165514 | 2018-02-12 | DHI-WTRAN-001172 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e60b2d7-0513-4142-a804-ee8d8b036b6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6323 | T16182-YD02-P0ZEN-165522 | 2018-02-12 | DHI-WTRAN-001172 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f6eea16-1e97-4f53-8e9e-866afb6f8da1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6324 | T16182-CA00-P0UYC-182901 | 2018-02-12 | DHI-TRANSMIT-001351 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7adbe951-c2fe-4886-b844-589e3a8fdc98 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6325 | T16182-CA00-P0UYC-182904 | 2018-02-12 | DHI-TRANSMIT-001351 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee4a2bf1-3334-4f13-a991-419238152042 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6326 | T16182-XB02-P0UAZ-172608 | 2018-02-12 | DHI-TRANSMIT-001352 | IFC | 9 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6fcbb27-cd89-4481-9777-386754a90723 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6327 | T16182-YD02-P0ZEN-165501 | 2018-02-12 | DHI-TRANSMIT-001353 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31b83ac7-a003-4c3e-babf-a3b06424292d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6328 | T16182-YD02-P0ZEN-165502 | 2018-02-12 | DHI-TRANSMIT-001353 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eea6be50-39e7-49f6-b29b-f021eeb6ac5d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6329 | T16182-YD02-P0ZEN-165503 | 2018-02-12 | DHI-TRANSMIT-001353 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ae2ef71-952e-4131-9bda-5a588fb11592 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6330 | T16182-YD02-P0ZEN-165507 | 2018-02-12 | DHI-TRANSMIT-001353 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fc9f67f-6eab-45d1-acd8-24e133b9a559 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6331 | T16182-YD02-P0ZEN-165516 | 2018-02-12 | DHI-TRANSMIT-001353 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd38f8ae-3477-4965-ba1f-9e27a8444797 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6332 | T16182-YD02-P0ZEN-165519 | 2018-02-12 | DHI-TRANSMIT-001353 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac591611-5f80-469e-93f7-dcbb545b141e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6333 | T16182-YD02-P0ZEN-165521 | 2018-02-12 | DHI-TRANSMIT-001353 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bee622b-914d-4c9d-ac7e-704ce18ebd1a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6334 | T16182-CV03-P8ZEN-125604 | 2018-02-12 | DHI-TRANSMIT-001354 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6c4a22e-61f1-4659-9b89-3fe622bf5b72 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6335 | T16182-YD02-P0MBA-121021 | 2018-02-12 | DHI-WTRAN-001173 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13b5d7b7-4f58-4410-9d21-9922429002e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6336 | T16182-YL01-P0MBA-121022 | 2018-02-12 | DHI-WTRAN-001173 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17e0d1f1-252a-46c4-98ea-9fd26dfa5157 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6337 | T16182-YS00-P0MBA-121020 | 2018-02-12 | DHI-WTRAN-001173 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc435942-3a36-43cb-ab3f-8f8666c5d636 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6338 | T16182-YD00-P0GK-130601 | 2018-02-12 | DHI-TRANSMIT-001355 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a4cdb9a-af5c-4443-82b6-9021cdf0fd9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6339 | T16182-YE03-P0BAU-152513 | 2018-02-13 | DHI-WTRAN-001174 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fef49c2-358c-4b69-9a3f-365c29eaa3fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6340 | T16182-YT10-P0MKY-290010 | 2018-02-13 | DHI-WTRAN-001175 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8e9c661-0d60-4f7e-9193-115417e481f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6341 | T16182-YT01-P0MKA-250009 | 2018-02-13 | DHI-WTRAN-001176 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39eab3bb-64ed-4b59-b99e-2184552b2b87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6342 | T16182-XS00-P0QU-130401 | 2018-02-13 | DHI-TRANSMIT-001356 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e0cd552-1120-43ba-8cf7-72cb30e0ed2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6343 | T16182-CA00-P0UBA-186801 | 2018-02-13 | DHI-TRANSMIT-001357 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=877cd0d3-7a6e-433e-9b28-eac36f8cff52 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6344 | T16182-CA00-P0UBA-186802 | 2018-02-13 | DHI-TRANSMIT-001357 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83338e28-a339-4746-8e7c-92907dac4f35 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6345 | T16182-CA00-P0UBA-186803 | 2018-02-13 | DHI-TRANSMIT-001357 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8100636b-873c-4979-90a0-1ba5de16c4b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6346 | T16182-CA01-P0UBA-186852 | 2018-02-13 | DHI-TRANSMIT-001357 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b90cd8ed-540b-42f7-a1e0-ba4ab00360ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6347 | T16182-CA01-P0UBA-186853 | 2018-02-13 | DHI-TRANSMIT-001357 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5a02cf5-7e70-4b19-9f7a-8b247c32f7dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6348 | T16182-XH01-P0SGK-137912 | 2018-02-13 | DHI-TRANSMIT-001358 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2e7a587-0bea-4097-a4ea-b31608e38cfa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6349 | T16182-YD00-P0CYE-136841 | 2018-02-13 | DHI-TRANSMIT-001358 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edc86b4e-c1bc-4557-abd9-0e1edc263b6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6350 | T16182-YU02-P0CYE-136842 | 2018-02-13 | DHI-TRANSMIT-001358 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47007cae-c6df-4a90-afc9-7e68aecafb03 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6351 | T16182-YE01-P0BAU-152606 | 2018-02-13 | DHI-WTRAN-001177 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=628b4dae-31b5-44c2-9b90-7f54c09166b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6352 | T16182-YF00-P0BA-150401 | 2018-02-14 | DHI-TRANSMIT-001359 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=828d523c-0377-4360-9b24-5e285aa09ed9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6353 | T16182-YF00-P0BA-150404 | 2018-02-14 | DHI-TRANSMIT-001359 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a0b168c-d445-4230-952d-49bffc322b37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6354 | T16182-CC05-P0ZEN-180002 | 2018-02-14 | DHI-WTRAN-001178 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f9d58e4-d513-4292-8906-568f0871d4ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6355 | T16182-CC05-P0ZEN-180008 | 2018-02-14 | DHI-WTRAN-001178 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f92b727-3b42-4c67-a96a-b2bd265489ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6356 | T16182-CC05-P0ZEN-180019 | 2018-02-14 | DHI-WTRAN-001178 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5728a756-f200-47c2-8879-d8b29c2bcf7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6357 | T16182-VK02-P0UGF-173107 | 2018-02-14 | DHI-TRANSMIT-001360 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcc38f1b-9635-4e40-84b5-514630b861cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6358 | T16182-XB02-P0UGF-173101 | 2018-02-14 | DHI-TRANSMIT-001360 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=086b930c-8ba8-4e1e-8c96-856473fecf6c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6359 | T16182-XB02-P0UGF-173102 | 2018-02-14 | DHI-TRANSMIT-001360 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2136c240-cbe4-4ecf-91e0-e1ff88473eb9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6360 | T16182-CA00-P0UTG-184901 | 2018-02-14 | DHI-TRANSMIT-001361 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1d730fd-df3a-4e62-a76d-dedd44a1b430 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6361 | T16182-CA00-P0UTG-184902 | 2018-02-14 | DHI-TRANSMIT-001361 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de6f8c0f-1339-4fed-89b2-4c029be906e5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6362 | T16182-CA00-P0UTG-184903 | 2018-02-14 | DHI-TRANSMIT-001361 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eca16210-9eaf-404a-95c4-e116266727e9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6363 | T16182-YS01-P0MKY-290008 | 2018-02-14 | DHI-TRANSMIT-001362 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=354a3d5a-231d-4b09-bb38-6a4f9d13af35 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6364 | T16182-YS01-P0MKY-290009 | 2018-02-14 | DHI-TRANSMIT-001363 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb179360-4770-4e38-a79e-dbdcdfe4fc08 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6365 | T16182-CA05-P0UCB-180681 | 2018-02-14 | DHI-TRANSMIT-001364 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4a31fd0-28b1-484b-89a8-3174cfeb643d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6366 | T16182-CA05-P0UCB-180687 | 2018-02-14 | DHI-TRANSMIT-001364 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7c634d7-7b13-4737-a353-65dbe7cf7cb9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6367 | T16182-CV03-P0CWQ-161122 | 2018-02-14 | DHI-WTRAN-001179 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26531a88-6dce-4ea4-ad76-5318a0b63573 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6368 | T16182-XG02-P0CYE-136944 | 2018-02-14 | DHI-WTRAN-001180 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81116b39-f25f-4930-9884-1f4b0119bea6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6369 | T16182-YD00-P0CYE-136941 | 2018-02-14 | DHI-TRANSMIT-001365 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f989cda-ad29-4925-9251-1631d564ed4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6370 | T16182-YT02-P8ZEN-125717 | 2018-02-14 | DHI-WTRAN-001181 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aaf32d40-0151-488f-802f-e4ca956d6890 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6371 | T16182-YT10-P8ZEN-125722 | 2018-02-14 | DHI-WTRAN-001181 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=febb8531-59ac-4436-b9ef-be1184d07bcb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6372 | T16182-YT10-P8ZEN-125723 | 2018-02-14 | DHI-WTRAN-001181 | IFI | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06ffd063-a293-4645-9320-7d7c0c7b5515 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6373 | T16182-CV03-P8ZEN-125602 | 2018-02-14 | DHI-TRANSMIT-001366 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a44aa8ae-0925-429d-97a2-cb79377d415a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6374 | T16182-CV03-P8ZEN-125608 | 2018-02-14 | DHI-TRANSMIT-001366 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53926985-af14-4161-b136-468435aeb41d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6375 | T16182-XG02-P0LBA-110003 | 2018-02-14 | DHI-TRANSMIT-001367 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e550e1c-c121-4477-9a8d-3f1abcef97bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6376 | T16182-XG02-P0LBC-110004 | 2018-02-14 | DHI-TRANSMIT-001367 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=356349a2-ceda-4b1f-946f-63c9bc648565 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6377 | T16182-XG02-P0LBG-110005 | 2018-02-14 | DHI-TRANSMIT-001367 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96e1f9ee-e1fd-4e00-bbbf-ba61397e60ab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6378 | T16182-XG02-P0LBS-110006 | 2018-02-14 | DHI-TRANSMIT-001367 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6779027b-07e7-4c3d-9805-3b61a7da97b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6379 | T16182-XG02-P6LCM-110007 | 2018-02-14 | DHI-TRANSMIT-001367 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94bbcdaf-d97a-426f-ab7e-fecfb7acb4c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6380 | T16182-DE00-P0ZEN-152823 | 2018-02-14 | DHI-TRANSMIT-001368 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43db61de-69c9-407d-8dec-7b5e892b2318 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6310 | T16182-CV03-P0LD-130219 | 2018-02-19 | DHI-WTRAN-001182 | IFI | 1 | DR | TRUE | TRUE | 2018-02-19_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70a83e20-d524-4a60-9c39-a93eb66c8ba3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6381 | T16182-CA03-P0HBD-189001 | 2018-02-19 | INT-IFC-180219-01 | INTERNAL IFC | 2 | DR | TRUE | FALSE | 2018-02-19_Changed by jisoo1.chung 2018-02-19_Changed by jisoo1.chung | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=7b76f070-6ef1-4f7b-9924-72049fa4637e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6382 | T16182-XH01-P0LF-140420 | 2018-02-19 | DHI-WTRAN-001183 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09798942-1ee7-42d1-9654-e602ea19ce43 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6383 | T16182-XJ00-P0GM-140121 | 2018-02-19 | DHI-WTRAN-001183 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ee9f224-56e3-4acd-80f8-c74134e67929 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6384 | T16182-YD02-P0SAC-163411 | 2018-02-19 | DHI-TRANSMIT-001377 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a9f58aa-7a11-43ca-a555-44dd002e03d5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6385 | T16182-YD02-P0SAC-163412 | 2018-02-19 | DHI-TRANSMIT-001377 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc96804a-4548-4588-bf2d-066a46d00105 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6386 | T16182-YD02-P0SAC-163413 | 2018-02-19 | DHI-TRANSMIT-001377 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73cf9e49-c3ca-4044-aac8-3f89b294adb7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6387 | T16182-BV02-P0CJN-290003 | 2018-02-20 | DHI-WTRAN-001184 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6388 | T16182-XH01-P0SGA-138611 | 2018-02-20 | DHI-TRANSMIT-001378 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c773ec10-4856-413b-907d-7f0711e66a9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6389 | T16182-XH01-P0SGE-138612 | 2018-02-20 | DHI-TRANSMIT-001378 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99f8e677-63f9-418b-8887-43eacfa9b820 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6390 | T16182-XH01-P0SGC-138614 | 2018-02-20 | DHI-TRANSMIT-001378 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8769d24-1b90-43b8-a160-3d9074c660e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6391 | T16182-XH01-P0SGC-138616 | 2018-02-20 | DHI-TRANSMIT-001378 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d6e391c-ba22-4c41-ad3c-4eeec2404473 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6392 | T16182-XH01-P0SGK-138618 | 2018-02-20 | DHI-TRANSMIT-001378 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53a0d599-51d5-490f-be48-8ef6ffe4e51b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6393 | T16182-YT10-P0SGK-138628 | 2018-02-20 | DHI-TRANSMIT-001378 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c720d0df-4bed-4d99-84d9-aaa140eedca5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6394 | T16182-YS01-P0MKY-290009 | 2018-02-20 | DHI-TRANSMIT-001379 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8ee8a8c-7886-4915-8d6b-ffeedacc62f2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6395 | T16182-YD02-P0SAC-163419 | 2018-02-20 | DHI-TRANSMIT-001380 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74efd4c1-a2d1-4691-9ca7-bc7d4f44b027 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6396 | T16182-YU02-P0CYE-136942 | 2018-02-20 | DHI-TRANSMIT-001381 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b34e57e-505d-46f7-a6b5-839941eed86b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6397 | T16182-YF00-P0BA-150401 | 2018-02-21 | DHI-TRANSMIT-001383 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=168d840c-445f-47bd-b7b5-981759148914 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6398 | T16182-YF00-P0BA-150404 | 2018-02-21 | DHI-TRANSMIT-001383 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a917651-54d2-465a-8e76-96ba643b56a1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6399 | T16182-VK02-P8UTH-172005 | 2018-02-21 | DHI-TRANSMIT-001384 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db3c3688-cc46-49c1-aa94-aace5dba025f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6400 | T16182-XB02-P8UTH-172003 | 2018-02-21 | DHI-TRANSMIT-001384 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d81dceb7-2be6-47c0-9707-8a16b8acb652 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6401 | T16182-XB02-P8UTH-172004 | 2018-02-21 | DHI-TRANSMIT-001384 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56326305-46a8-42f5-b0a8-aab73f3364d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6402 | T16182-CV03-P0CRT-161149 | 2018-02-21 | DHI-TRANSMIT-001385 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f323e75a-bfe4-4a90-bab9-1cc0e6af6a91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6403 | T16182-XB02-P0UHA-171815 | 2018-02-21 | DHI-TRANSMIT-001386 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=271f1a9e-78cb-4243-a24a-be0afe704158 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6404 | T16182-YD02-P0ZEN-165575 | 2018-02-21 | DHI-TRANSMIT-001387 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f8fb992-100e-44fd-a262-f4b9adec8ba6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6405 | T16182-YD02-P0ZEN-165515 | 2018-02-21 | DHI-WTRAN-001185 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea3be2e3-530c-46e8-a043-5ffc190a8719 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6406 | T16182-YK00-P0LB-122071 | 2018-02-21 | DHI-TRANSMIT-001388 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4958670c-55dc-496f-8e2e-04999bf65b2a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6407 | T16182-XH01-P0SGA-136711 | 2018-02-21 | DHI-TRANSMIT-001389 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c2f0f5c-6c12-45d2-b934-9a4afbcfdf6a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6408 | T16182-XH01-P0SGE-137913 | 2018-02-21 | DHI-TRANSMIT-001389 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21ea050e-5504-46dc-b89c-60aff34e983a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6409 | T16182-YD04-P0ZEN-152013 | 2018-02-21 | DHI-WTRAN-001186 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb2e855a-08fc-45aa-8aec-7c6ade9b2425 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6410 | T16182-YE00-P0ZEN-152735 | 2018-02-21 | DHI-TRANSMIT-001390 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93f84401-b8ae-4b46-b1b3-f4b59d039f68 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6411 | T16182-YT01-P0LAC-126004 | 2018-02-21 | DHI-TRANSMIT-001391 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2e40697-c7ec-4a4b-8c59-c715fc106463 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6412 | T16182-XB02-P0ULC-172502 | 2018-02-21 | DHI-TRANSMIT-001392 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d66484a7-a186-4f8f-b084-2847d9c4a284 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6413 | T16182-XB02-P0UGF-172522 | 2018-02-21 | DHI-TRANSMIT-001392 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23bb0173-cb0b-4243-b5cf-0ed7fefc4c37 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6414 | T16182-XB02-P0UGD-172542 | 2018-02-21 | DHI-TRANSMIT-001392 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e2b936d-3e70-4f64-8a03-c3d78458dbd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6415 | T16182-XB02-P0UGG-172562 | 2018-02-21 | DHI-TRANSMIT-001392 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0405e161-2c8e-4fa4-be42-9eb8bb50a9f1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6416 | T16182-CA05-P0UYB-183581 | 2018-02-23 | DHI-WTRAN-001187 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6417 | T16182-CA05-P0UYB-183582 | 2018-02-23 | DHI-WTRAN-001187 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6418 | T16182-XJ00-P8ZEN-125540 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a6be2e3-b14e-457f-ab22-bcf745854284 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6419 | T16182-XJ00-P8ZEN-125541 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64c64ab6-f335-4a49-ae67-b82a5605d691 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6420 | T16182-XJ00-P8ZEN-125542 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc4303d3-e3dc-4483-984f-6b9a55135d1a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6421 | T16182-XJ00-P8ZEN-125543 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2aa7b638-2563-4191-8136-65a34d6d2f4e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6422 | T16182-XJ00-P8ZEN-125544 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac2f6f2d-6cba-453c-8254-9a79cb7d2542 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6423 | T16182-XJ00-P8ZEN-125545 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdc3e576-e7c1-41b5-8341-059c6b840235 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6424 | T16182-XJ00-P8ZEN-125546 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f5de7c1-cbe6-4dd2-93a6-5a1b5cac4739 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6425 | T16182-XJ00-P8ZEN-125547 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=668ec5dc-d54a-4716-b323-7ee5d2943430 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6426 | T16182-XJ00-P8ZEN-125548 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7de7ca62-2ee7-4d24-ad27-2fe4139e3a5b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6427 | T16182-XJ00-P8ZEN-125549 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81225992-9ea0-485b-b94c-24915536403f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6428 | T16182-XJ00-P8ZEN-125550 | 2018-02-23 | DHI-TRANSMIT-001395 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dcc28437-5cee-46f5-a4f2-43095b174db6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6429 | T16182-YD00-P0SMU-128017 | 2018-02-23 | DHI-WTRAN-001188 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbc74e48-c9a3-4014-b03a-877f6a3db439 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6430 | T16182-YT01-P0SMU-128022 | 2018-02-23 | DHI-WTRAN-001188 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cbf19cb-e45f-48a8-82d9-c1415357bdd7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6431 | T16182-YT01-P0LAC-126009 | 2018-02-23 | DHI-WTRAN-001189 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d336811b-dc76-4357-b38f-1e9e92e8f788 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6432 | T16182-YT01-P0LAC-126059 | 2018-02-23 | DHI-WTRAN-001189 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53db8ed9-fb5f-4889-8973-e35184058d2b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6433 | T16182-YL16-P0SAY-163406 | 2018-02-23 | DHI-TRANSMIT-001397 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e067ce36-4504-443a-b53e-733d0dc92f93 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6434 | T16182-XG07-P0EKG-124003 | 2018-02-23 | DHI-TRANSMIT-001399 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e5c48b1-b64e-4bf2-ab99-954d142892bb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6435 | T16182-YD00-P0EKG-124004 | 2018-02-23 | DHI-TRANSMIT-001399 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ae676fc-c43a-423d-8482-09af4121bf9c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6436 | T16182-YK10-P0EKG-124005 | 2018-02-23 | DHI-TRANSMIT-001399 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=186d3c95-8b4d-448f-b727-630c39d1ec27 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6437 | T16182-YK10-P0EKG-124006 | 2018-02-23 | DHI-TRANSMIT-001399 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca5e0ff7-09e6-47f9-8263-cc7f29dbb591 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6438 | T16182-YK10-P0EKG-124007 | 2018-02-23 | DHI-TRANSMIT-001399 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c513f79d-42c6-472b-9720-c58247b9189e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6439 | T16182-YK10-P0EKG-124008 | 2018-02-23 | DHI-TRANSMIT-001399 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75e1f0b3-faab-4999-b2b1-ce285ba55fa4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6440 | T16182-XN00-P0EKG-124023 | 2018-02-23 | DHI-TRANSMIT-001399 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a70d0d11-4b1b-40a1-825b-d37a7df94ecd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6441 | T16182-YB03-P0SAY-163407 | 2018-02-23 | DHI-WTRAN-001190 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6003d8ef-79b5-424e-b1bb-9737fcb0ab90 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6442 | T16182-XB02-P0UAZ-172608 | 2018-02-23 | DHI-TRANSMIT-001400 | IFC | 10 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f8d8119-a25c-473b-b3d6-b6a4efd62a8f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6443 | T16182-CA00-P0UYC-182901 | 2018-02-23 | DHI-TRANSMIT-001402 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6b153de-2362-4a5a-99aa-4c33e810af0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6444 | T16182-CA00-P0UYC-182904 | 2018-02-23 | DHI-TRANSMIT-001402 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=833c5707-1d2e-4661-b91b-c06eaa2ac34a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6445 | T16182-CA00-P0UYC-182905 | 2018-02-23 | DHI-TRANSMIT-001402 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a194d9b-650c-4241-b07c-8de8329837f3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6446 | T16182-CA00-P0UYC-182906 | 2018-02-23 | DHI-TRANSMIT-001402 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6525c964-717d-4d09-8bc8-af2627e562d4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6447 | T16182-CA00-P0UYC-182907 | 2018-02-23 | DHI-TRANSMIT-001402 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5521b49-585c-469a-8f06-5d75e07842d2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6448 | T16182-CA00-P0UYC-182908 | 2018-02-23 | DHI-TRANSMIT-001402 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fae1274-6c21-45ba-bd68-afbf71aa5d17 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6449 | T16182-YT01-P0MBA-121023 | 2018-02-23 | DHI-WTRAN-001191 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fff3968f-2060-4ffb-a039-8adaec5901b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6450 | T16182-YR05-P0GM-128511 | 2018-02-23 | DHI-WTRAN-001192 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d97abe1-1ef4-451d-8776-65e08e967d5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6451 | T16182-YD00-P0CYE-139541 | 2018-02-23 | DHI-WTRAN-001193 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfd74965-8185-4bcc-909f-cdfc8936634c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6452 | T16182-YU02-P0CYE-139542 | 2018-02-23 | DHI-WTRAN-001193 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=082635dd-5d81-42aa-9da5-dadab44f3567 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6453 | T16182-CA03-P0UMY-185170 | 2018-02-23 | DHI-TRANSMIT-001406 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35bd65a4-05f5-4af6-acdc-b81e1bc3c571 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6454 | T16182-CA03-P0UMY-185172 | 2018-02-23 | DHI-TRANSMIT-001406 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cba4db6-14ce-4bcc-98be-4c0418423536 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6455 | T16182-CA03-P0UMY-185173 | 2018-02-23 | DHI-TRANSMIT-001406 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dff7e090-0e39-4b30-91f4-c73439099730 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6456 | T16182-CA03-P0UMY-185174 | 2018-02-23 | DHI-TRANSMIT-001406 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf2eb409-8a14-4d9e-aeca-7cb139c4f01a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6457 | T16182-CA03-P0UMY-185171 | 2018-02-23 | DHI-TRANSMIT-001407 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b16984c8-311c-4e64-b1b8-05ddffa66774 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6458 | T16182-YD00-P0SMQ-128014 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=635958b7-6e39-4b72-a738-9e788fe72ffe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6459 | T16182-YD00-P0SMU-128015 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=634f2736-e8f7-49ec-8b4f-52f544594bf1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6460 | T16182-YD00-P0SMG-128016 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a3b6ff3-38fd-44bd-9c75-1a8a7b857264 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6461 | T16182-YK09-P0SMQ-128024 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48089f8c-87d7-4cdd-bb3a-6406e13b5e40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6462 | T16182-YK09-P0SMU-128025 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0aa65ad-0968-4145-96bb-2a33fa6fcb1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6463 | T16182-YK09-P0SMG-128026 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86319d81-6abf-48e5-9b89-02e43fdf1476 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6464 | T16182-YD00-P0SMC-128028 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32214b6f-b1a6-4071-876e-a4a53c202eeb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6465 | T16182-YD00-P0SMS-128029 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9a7896c-c01b-4ed9-b5c8-3fd33c4a5962 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6466 | T16182-YD00-P0SMG-128030 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a654831-35a3-4bd7-a069-47a5d4e0aa03 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6467 | T16182-YD00-P0SMM-128031 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=966770ba-5222-41a8-9506-22f0e9d491ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6468 | T16182-YD00-P0SMU-128032 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cae9373e-14ea-456c-a038-8218c8a8239c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6469 | T16182-YK09-P0SMC-128038 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2d6af89-3f13-4bdd-bb24-c78e85fb2f64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6470 | T16182-YK09-P0SMS-128039 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e20d9e77-ea90-426e-b44f-8093aadee82e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6471 | T16182-YK09-P0SMG-128040 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74390069-4486-420b-b543-375760057e93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6472 | T16182-YK09-P0SMM-128041 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97f5b21e-c03d-4629-9a36-29f957c1d780 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6473 | T16182-YK09-P0SMU-128042 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94076d7e-2bf6-4b34-9c78-06037d22200b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6474 | T16182-YS18-P0SMC-128043 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edab4278-b69f-4aae-9c0b-b48a2487893a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6475 | T16182-YS18-P0SMS-128044 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45957c55-70e0-4c9f-9ead-e44e5f04506b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6476 | T16182-YS18-P0SMQ-128045 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e426d0ce-a7d5-4dc7-98bf-3a8d5cae438f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6477 | T16182-YS18-P0SMU-128046 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da8680dc-3036-4cf3-b096-4c7d5af04d5d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6478 | T16182-YS18-P0SMG-128047 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e3c01cd-cdd9-4fe6-bf9c-78a11eb320e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6479 | T16182-YS18-P0SMG-128048 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e20dedf3-9b9d-4e9f-ab8c-2a3775a1c386 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6480 | T16182-YS18-P0SMM-128049 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=436904c3-de4b-4faf-8b17-9f21d6485de0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6481 | T16182-YD00-P0SMG-128051 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f94ca8c7-8cf5-4543-a2df-2e62b271381a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6482 | T16182-YD00-P0SMG-128052 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c3ae53b-9bbc-475a-b4c4-71b19bc2eed0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6483 | T16182-YD00-P0SMG-128053 | 2018-02-23 | DHI-TRANSMIT-001408 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4acb0b88-ee45-4f42-a09d-e4be229e4945 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6484 | T16182-CV03-P0CWQ-161122 | 2018-02-23 | DHI-TRANSMIT-001410 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3cde92fb-ae34-4bcd-8c9e-dc18f97ee241 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6485 | T16182-UC02-P0MKA-250010 | 2018-02-23 | DHI-WTRAN-001194 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d757ba89-bfd7-4def-8437-2d639147451e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6486 | T16182-YM01-P0LCB-127039 | 2018-02-23 | DHI-WTRAN-001195 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84cd0121-cc5e-4b9b-84b1-4076c0c08a41 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6487 | T16182-YD02-P0ZEN-165525 | 2018-02-23 | DHI-TRANSMIT-001411 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8caa3c73-9cda-423b-a05e-ccf6d6e61f5b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6488 | T16182-YD02-P0ZEN-165524 | 2018-02-23 | DHI-WTRAN-001196 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=851a0b14-4bf4-4920-a6b5-adc9c04bcac5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6489 | T16182-XJ00-P0GM-140224 | 2018-02-26 | DHI-WTRAN-001197 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=264f7e15-6a82-4016-b581-70bc0f6de4c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6490 | T16182-XJ00-P0MBH-140216 | 2018-02-26 | DHI-WTRAN-001197 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1b6eca6-8702-4b77-8789-249dd8669492 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6491 | T16182-YQ01-P0ZEN-152318 | 2018-02-26 | DHI-TRANSMIT-001413 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9b54e1c-0198-4679-baa2-ec8053387fe8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6492 | T16182-YT10-P0ZEN-150313 | 2018-02-26 | DHI-TRANSMIT-001414 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=977ce4bd-0c21-4763-9a68-c2c97f1d4dfd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6493 | T16182-YD02-P0SAC-163414 | 2018-02-26 | DHI-TRANSMIT-001415 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b13f72d0-8fc5-4549-beae-c0f04e12883a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6494 | T16182-DE00-P0CY-154001 | 2018-02-26 | DHI-TRANSMIT-001416 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da2100b9-bc21-4654-ba6e-63ef17e15de6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6495 | T16182-YQ08-P0CY-154031 | 2018-02-26 | DHI-TRANSMIT-001416 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdab57c8-e206-477d-afb1-a454ef4bbe9c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6496 | T16182-YQ08-P0CY-154032 | 2018-02-26 | DHI-TRANSMIT-001416 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf9b502e-eb33-4a67-bff8-afb3cab18b9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6497 | T16182-CA00-P0UMA-180401 | 2018-02-27 | DHI-TRANSMIT-001418 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98514424-8083-4bc3-88b9-2122dba32b6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6498 | T16182-CA00-P0UMA-180402 | 2018-02-27 | DHI-TRANSMIT-001418 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce2e17d7-ca93-48e7-ab4b-e784c6757960 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6499 | T16182-CA00-P0UMA-180403 | 2018-02-27 | DHI-TRANSMIT-001418 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d69d9cbf-f79c-42ea-a8e7-e35d6ecbeb0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6500 | T16182-CA00-P0UMA-180404 | 2018-02-27 | DHI-TRANSMIT-001418 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c6ec464-8450-4b55-af14-4f1dd6088bb4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6501 | T16182-CA00-P0UMA-180405 | 2018-02-27 | DHI-TRANSMIT-001418 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce27a48d-14d5-4f6d-a09e-5ba06058b8e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6502 | T16182-CA00-P0UMA-180406 | 2018-02-27 | DHI-TRANSMIT-001418 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c87808b3-0752-40f0-a243-811e61ea018d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6503 | T16182-CA00-P0UMA-180408 | 2018-02-27 | DHI-TRANSMIT-001418 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=399191bc-7809-4e52-a07a-96acc1d6903c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6504 | T16182-VK02-P0UZJ-173208 | 2018-02-27 | DHI-TRANSMIT-001419 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=415990bc-8d70-4959-abfb-025541d333c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6505 | T16182-VK02-P0UZJ-173209 | 2018-02-27 | DHI-TRANSMIT-001419 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82f4eca6-731f-449b-b9b0-d36afe323268 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6506 | T16182-XB02-P0UZJ-173202 | 2018-02-27 | DHI-TRANSMIT-001419 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f087662-2db6-49eb-9e4b-a89fba8a71dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6507 | T16182-CA05-P0UST-182081 | 2018-02-27 | DHI-TRANSMIT-001420 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd40831b-08fe-4220-8868-cc85c8e18ea7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6508 | T16182-CA05-P0UST-182085 | 2018-02-27 | DHI-TRANSMIT-001420 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f968af8b-097e-4621-b949-8b414d9f8476 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6509 | T16182-CA05-P0UYC-182981 | 2018-02-27 | DHI-TRANSMIT-001421 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de2585c2-f519-4ccc-b223-8d62a05fa395 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6510 | T16182-CA05-P0UYC-182985 | 2018-02-27 | DHI-TRANSMIT-001421 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dcae1b73-6e74-4094-9f36-6175c9a385a2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6511 | T16182-XW03-P0SAE-135301 | 2018-02-27 | DHI-WTRAN-001201 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b7f1510-7bc5-4d87-9ef5-bb5f4a9d3596 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6512 | T16182-XG07-P0SAE-135302 | 2018-02-27 | DHI-WTRAN-001201 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6623b3c8-2816-4961-925d-0a76c76c9069 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6513 | T16182-XW03-P0SAE-135303 | 2018-02-27 | DHI-WTRAN-001201 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dcc37113-5531-4cb1-ab8e-62d54795d4f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6514 | T16182-XH02-P0SAE-135304 | 2018-02-27 | DHI-WTRAN-001201 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0caaa0d1-9851-4874-8505-f3a03b4b379a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6515 | T16182-YT01-P0SAA-136002 | 2018-02-27 | DHI-TRANSMIT-001422 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd6eaa48-567a-4ff5-97af-044cb82c1049 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6516 | T16182-YD02-P0ZEN-165523 | 2018-02-27 | DHI-WTRAN-001202 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0595285-2c09-4cdd-9f1a-0f7623d1eb87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6517 | T16182-YD02-P0ZEN-165517 | 2018-02-27 | DHI-TRANSMIT-001423 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd2e9241-009f-455d-a6e8-4cfa264256af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6518 | T16182-YD02-P0ZEN-165520 | 2018-02-27 | DHI-TRANSMIT-001423 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8ee74c2-89a2-4b82-af07-d79d31390f80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6519 | T16182-YD02-P0ZEN-165526 | 2018-02-27 | DHI-TRANSMIT-001423 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=559d1a09-37d7-4c05-8c9c-52a2d8114d16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6520 | T16182-CA03-P0UMA-180500 | 2018-02-28 | INT-IFC-180228-01 | INTERNAL IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daf0b409-89f1-4aaa-84e3-d13cb5a98a87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6521 | T16182-XG02-P6MAA-220025 | 2018-02-28 | DHI-TRANSMIT-001424 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f77be9fa-ddb4-4511-a8a8-38fb39536f08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6522 | T16182-XG02-P7MAA-220026 | 2018-02-28 | DHI-TRANSMIT-001424 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=003fe306-bf1b-4347-a2c6-1bae94f0415a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6523 | T16182-XH01-P0LF-140401 | 2018-02-28 | DHI-TRANSMIT-001425 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=479d726b-6879-4b06-9ce9-914f1242846a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6524 | T16182-XH01-P0LF-140402 | 2018-02-28 | DHI-TRANSMIT-001425 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c241e69-bb8b-4761-a9ee-a7ed633b3a02 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6525 | T16182-XH01-P0LF-140403 | 2018-02-28 | DHI-TRANSMIT-001425 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acf0fbfe-8c2b-4a4a-be45-d997c8a06581 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6526 | T16182-YD00-P8ZEN-125507 | 2018-02-28 | DHI-TRANSMIT-001426 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=354ea544-f7fd-41ed-bbdf-03ae0e1122ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6527 | T16182-XH02-P0MAG-123015 | 2018-02-28 | DHI-WTRAN-001204 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11700569-a74a-45de-b11d-57b1f38371f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6528 | T16182-YL01-P0MAG-123034 | 2018-02-28 | DHI-WTRAN-001204 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bf1af24-fe22-4720-90b8-5d4b3384fcdb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6529 | T16182-YV02-P0MAG-123033 | 2018-02-28 | DHI-WTRAN-001204 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b307c4f7-7001-4477-a737-30461fbfaa52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6530 | T16182-YD00-P0SGZ-139731 | 2018-02-28 | DHI-WTRAN-001205 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5e88aff-1269-4a64-a83a-85e49e83d148 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6531 | T16182-YD00-P0SGZ-139831 | 2018-02-28 | DHI-WTRAN-001205 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9158e082-cc71-4da6-9639-b0e6cda696f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6532 | T16182-YD00-P0CYE-136741 | 2018-02-28 | DHI-TRANSMIT-001427 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b52f294c-eb56-4713-9bf2-2ca95d4d9a7f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6533 | T16182-YD00-P0CYE-139841 | 2018-02-28 | DHI-TRANSMIT-001427 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51833485-c271-4cf2-9a81-04326344fed0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6534 | T16182-YU02-P0CYE-139842 | 2018-02-28 | DHI-TRANSMIT-001427 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0d3e72c-e931-4410-a5e8-d9a45738befd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6535 | T16182-YD00-P0CYE-139741 | 2018-02-28 | DHI-TRANSMIT-001427 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=954b1ba1-4ee5-4bbf-855f-03bf9cf802a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6536 | T16182-YU02-P0CYE-139742 | 2018-02-28 | DHI-TRANSMIT-001427 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94038f78-67bd-4191-87dc-eddcabcb4c39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6537 | T16182-CA00-P0UST-182001 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8155c8f5-f8df-4a1b-8f0e-9b5f7f6ac341 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6538 | T16182-CA00-P0UST-182002 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cab64c78-d60d-43bb-8353-1761b5e66197 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6539 | T16182-CA00-P0UST-182003 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0a56da6-f376-4ef9-b3dd-191173d785db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6540 | T16182-CA00-P0UST-182005 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=272d7ee1-4823-489d-a908-d6dceda1ed8c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6541 | T16182-CA00-P0UST-182006 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7282dd50-2290-49b3-98f8-c8ad0a88a3d1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6542 | T16182-CA01-P0UST-182053 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bf74936-410f-42de-9a7b-cc0c6a8a47bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6543 | T16182-CA03-P0UST-182054 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee4eb14f-8c68-49e1-a18b-d7461a8bbf35 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6544 | T16182-CA03-P0UST-182056 | 2018-02-28 | DHI-TRANSMIT-001428 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49fc28fe-a637-4eb1-8121-8841476df2f7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6545 | T16182-UT01-P0GQB-173402 | 2018-02-28 | DHI-TRANSMIT-001429 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb9828c8-732f-45b8-9b09-2ce48340bedd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6546 | T16182-UT01-P0GQB-173403 | 2018-02-28 | DHI-TRANSMIT-001429 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3ac69d7-5a82-44d0-9215-f8af7f251d9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6547 | T16182-UT01-P0GQB-173413 | 2018-02-28 | DHI-TRANSMIT-001429 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a492f59-dd7b-43fa-837d-d73b6ec72d0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6548 | T16182-XB02-P0GHC-173802 | 2018-02-28 | DHI-TRANSMIT-001430 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3727da7f-83d2-4b34-9aef-203b1650e19e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6549 | T16182-VK02-P0ULC-171309 | 2018-02-28 | DHI-TRANSMIT-001431 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19369bbc-956f-4d13-a820-ac029c10dfa2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6550 | T16182-YB11-P0ZEN-152408 | 2018-03-05 | DHI-WTRAN-001209 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d769b27c-42e4-49b4-8720-31694f63340d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6551 | T16182-YQ01-P0ZEN-152308 | 2018-03-05 | DHI-WTRAN-001209 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9771f35-1cee-403f-ba36-df59464ae808 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6552 | T16182-YT10-P0ZEN-152210 | 2018-03-05 | DHI-WTRAN-001209 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9965bcfd-9298-47b7-91a4-d419d1f42d80 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6553 | T16182-YU03-P0BB-150836 | 2018-03-05 | DHI-WTRAN-001210 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78131233-c172-4229-93bb-048bcac0bb91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6554 | T16182-CA00-P0ULD-183904 | 2018-03-06 | DHI-TRANSMIT-001436 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b58c9c2-7f18-4eb2-9f8e-bffb044b35fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6555 | T16182-CA01-P0ULD-183954 | 2018-03-06 | DHI-TRANSMIT-001436 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=272863a6-14b6-4ad1-a159-42a3b7c13162 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6556 | T16182-CA03-P0ULD-183964 | 2018-03-06 | DHI-TRANSMIT-001436 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff5d09e8-10b8-4279-9e23-9fde68db2332 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6557 | T16182-CA06-P0ULD-183900 | 2018-03-06 | DHI-TRANSMIT-001436 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d19294a-8545-4332-84be-335f43e6a035 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6558 | T16182-CA00-P0USG-182701 | 2018-03-06 | DHI-TRANSMIT-001437 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb354564-e969-4478-bbc4-047acf17b80b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6559 | T16182-CA00-P0USG-182703 | 2018-03-06 | DHI-TRANSMIT-001437 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adf0938c-3bfb-4f63-b80e-fdab597d940e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6560 | T16182-CA01-P0USG-182752 | 2018-03-06 | DHI-TRANSMIT-001437 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=796e48ef-ca14-4d2e-b124-86234d3e95e1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6561 | T16182-XB02-P8UTH-172003 | 2018-03-06 | DHI-TRANSMIT-001438 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3612e2e6-1855-472a-b035-f22f3369f137 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6562 | T16182-XB02-P8UTH-172004 | 2018-03-06 | DHI-TRANSMIT-001438 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9a47038-6e80-4168-b3da-369d27eaf548 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6563 | T16182-XH01-P0EKG-124002 | 2018-03-07 | DHI-TRANSMIT-001439 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fed9739-2ce2-4032-bc9c-3673f85dc004 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6564 | T16182-XB02-P0UHA-171815 | 2018-03-07 | DHI-TRANSMIT-001440 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ff2c654-7399-475e-8556-0834161fb645 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6565 | T16182-YS00-P0LB-122092 | 2018-03-07 | DHI-TRANSMIT-001441 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8f99b1b-a1ab-4ce3-95ae-ec5e53f57515 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6566 | T16182-YD02-P0SAC-163417 | 2018-03-07 | DHI-WTRAN-001215 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8295a3eb-7a3b-4df6-b2c0-6c7a7f99a1b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6567 | T16182-YB03-P0SAY-163407 | 2018-03-07 | DHI-TRANSMIT-001442 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e18e76e9-bddc-4928-869e-8dc581e16233 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6568 | T16182-XJ00-P0GM-140121 | 2018-03-08 | DHI-WTRAN-001219 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6569 | T16182-XH02-P0SAR-134104 | 2018-03-08 | DHI-TRANSMIT-001443 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f1791f7-9533-4d8e-b64b-29fcd6e38d3d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6570 | T16182-XW03-P0SAR-134101 | 2018-03-08 | DHI-TRANSMIT-001443 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86437000-6158-496d-a6fd-2879951bedce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6571 | T16182-XW03-P0SAR-134103 | 2018-03-08 | DHI-TRANSMIT-001443 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cf7666c-a8cc-42c7-b263-0d04ecfdb3bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6572 | T16182-XJ00-P0EKG-140118 | 2018-03-08 | DHI-TRANSMIT-001444 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d218752e-db59-470e-bcc8-e3918d9dd693 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6573 | T16182-XJ00-P0PDA-140114 | 2018-03-08 | DHI-TRANSMIT-001444 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a152c7a0-6784-4c72-9188-f63a418fae83 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6574 | T16182-YD02-P0ZEN-165522 | 2018-03-08 | DHI-WTRAN-001220 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89082152-5f67-47f3-b7eb-0e64c7a8dfe3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6575 | T16182-YT10-P0ZEN-152232 | 2018-03-08 | DHI-WTRAN-001221 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26af9b49-2a0f-45a3-a90b-69610b937731 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6576 | T16182-YT10-P0ZEN-152233 | 2018-03-08 | DHI-WTRAN-001221 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6d59e02-8819-431b-ba9b-d74fdbf8fb3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6577 | T16182-YQ01-P0ZEN-152330 | 2018-03-08 | DHI-WTRAN-001221 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cce74529-b0f5-40cf-85c2-2977a5469dfc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6578 | T16182-YQ01-P0ZEN-152331 | 2018-03-08 | DHI-WTRAN-001221 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e999f6d-293a-4ea1-89e6-23a3bb6e8dc3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6579 | T16182-YD00-P0LCB-127001 | 2018-03-09 | DHI-TRANSMIT-001445 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f879c2f-eb01-4b6f-94ac-67d1c7aaaad3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6580 | T16182-XB02-P0ULX-171202 | 2018-03-09 | DHI-TRANSMIT-001446 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=931b986c-0508-435b-a523-2c771b8caa21 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6581 | T16182-XB02-P0ULX-171203 | 2018-03-09 | DHI-TRANSMIT-001446 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e4907a1-83b6-4318-abae-47f5e3651818 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6582 | T16182-XH02-P0SAR-134204 | 2018-03-09 | DHI-TRANSMIT-001447 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e6d5fcc-ed58-4c9b-9f48-10e04b88f9ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6583 | T16182-XW03-P0SAR-134201 | 2018-03-09 | DHI-TRANSMIT-001447 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cae06ec-02e9-4ce6-ba36-017b37ad8e40 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6584 | T16182-XW03-P0SAR-134203 | 2018-03-09 | DHI-TRANSMIT-001447 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d162d54-99ae-4959-b2cd-a1087ee26a22 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6585 | T16182-CA00-P0UBA-181002 | 2018-03-09 | DHI-TRANSMIT-001448 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffe2550f-b302-4d1e-9ded-ad6f83560ae6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6586 | T16182-CA00-P0UBA-186101 | 2018-03-09 | DHI-TRANSMIT-001448 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55eed32c-5d10-488d-ad63-42f444c94b8a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6587 | T16182-CA00-P0UBA-181102 | 2018-03-09 | DHI-TRANSMIT-001448 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4941ae3b-7983-4e81-b441-9252704a9846 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6588 | T16182-VK02-P0UZT-172704 | 2018-03-09 | DHI-TRANSMIT-001449 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fef3994-80a7-48f5-9829-d8897971a6d8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6589 | T16182-VK02-P0UZT-172713 | 2018-03-09 | DHI-TRANSMIT-001449 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b1b13f7-8eda-4a9c-b528-03ea05e25351 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6590 | T16182-XB02-P0UZT-172702 | 2018-03-09 | DHI-TRANSMIT-001449 | IFC | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=016f6109-a0d4-4937-8317-0f75fa038ecb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6591 | T16182-XB02-P0UZT-172703 | 2018-03-09 | DHI-TRANSMIT-001449 | IFC | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1af7fca3-47e2-44c9-9c0f-16aecdb5d0a1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6592 | T16182-YT10-P0SGE-138622 | 2018-03-09 | DHI-TRANSMIT-001450 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b21b7502-3c48-461f-af3c-32c41953d124 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6593 | T16182-YT10-P0SGC-138626 | 2018-03-09 | DHI-TRANSMIT-001450 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9ad04e6-0e4b-4f98-a49f-18069cc33472 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6594 | T16182-YT10-P0SGC-138624 | 2018-03-09 | DHI-TRANSMIT-001450 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dffe1a99-f284-42db-9623-e2cda85b455b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6595 | T16182-XH01-P0SGE-138613 | 2018-03-09 | DHI-TRANSMIT-001450 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d99a576-6827-4422-8fd0-f035bbc91805 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6596 | T16182-YT10-P0SGE-138623 | 2018-03-09 | DHI-TRANSMIT-001450 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ba56e5d-dc6c-46d2-928a-77aa08dc98b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6597 | T16182-VK02-P0UBN-172203 | 2018-03-09 | DHI-TRANSMIT-001451 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3abcb143-f1cd-44ca-a244-8a38a3455e23 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6598 | T16182-XB02-P0UBN-172202 | 2018-03-09 | DHI-TRANSMIT-001451 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db1fa244-845a-42b0-b3db-84d279ca9041 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6599 | T16182-CA00-P0UGD-186601 | 2018-03-09 | DHI-TRANSMIT-001452 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b93a274f-2569-42ab-a697-4b7a30a3625b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6600 | T16182-CA00-P0UGD-186602 | 2018-03-09 | DHI-TRANSMIT-001452 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bfa1596-2828-48a9-8d97-6d80f295b826 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6601 | T16182-XJ00-P0LBC-140102 | 2018-03-09 | DHI-TRANSMIT-001453 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39850284-4ba9-4d8f-a106-cdf7ad31dab6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6602 | T16182-XJ00-P0LBG-140103 | 2018-03-09 | DHI-TRANSMIT-001453 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e98f5f0-b40d-4b49-87ec-a1842a442661 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6603 | T16182-XJ00-P0LBG-140104 | 2018-03-09 | DHI-TRANSMIT-001453 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c01b2047-b73d-4b82-8f21-8ed2938fe4e3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6604 | T16182-XJ00-P0MBH-140116 | 2018-03-09 | DHI-TRANSMIT-001453 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=171cb004-4058-4c3d-b96d-1e89212d8351 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6605 | T16182-XJ00-P0EKC-140117 | 2018-03-09 | DHI-TRANSMIT-001453 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46d33f15-9ff8-48e9-80b9-061a01383b32 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6606 | T16182-YD04-P0ZEN-152014 | 2018-03-09 | DHI-WTRAN-001222 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de858ff0-4cce-4b9c-8491-46b423bca4b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6607 | T16182-CA03-P0UMY-185171 | 2018-03-09 | DHI-TRANSMIT-001454 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5021915e-e4b2-4f7b-bfe1-5f2262a3afdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6608 | T16182-CA03-P0UMY-185172 | 2018-03-09 | DHI-TRANSMIT-001454 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3aa782a8-2849-47ba-98a7-b570680efd94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6609 | T16182-XG02-P0SGC-138201 | 2018-03-09 | DHI-TRANSMIT-001455 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2075571e-dda7-44a9-bb4d-c3c3a06874b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6610 | T16182-XH01-P0SGC-138211 | 2018-03-09 | DHI-TRANSMIT-001455 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19cba157-4cd1-4185-b2e4-83c5948aa99a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6611 | T16182-CA05-P0UYC-182985 | 2018-03-12 | DHI-TRANSMIT-001456 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2cc8db7-58f6-4771-9253-7ec7073ec83a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6612 | T16182-YD00-P0CWQ-161402 | 2018-03-12 | DHI-TRANSMIT-001457 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e419bb64-dffb-46b9-acd2-012830453047 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6613 | T16182-YD00-P0CWQ-161406 | 2018-03-12 | DHI-TRANSMIT-001457 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ad5d892-ab50-4996-a95c-6d71af5e410d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6614 | T16182-XG01-P0EKG-124001 | 2018-03-12 | DHI-TRANSMIT-001458 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=313d9c04-085d-46c5-afda-23ea219084d2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6615 | T16182-YE01-P0BAU-152606 | 2018-03-12 | DHI-TRANSMIT-001459 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24db4064-08c3-4290-adaa-3bffd1383f4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6616 | T16182-YE03-P0BAU-152505 | 2018-03-12 | DHI-TRANSMIT-001459 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2b33447-cbba-45ef-a1c3-7db556e5bf75 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6617 | T16182-YE03-P0BAU-152506 | 2018-03-12 | DHI-TRANSMIT-001459 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b12310c5-942b-4903-b991-fa8136739e6e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6618 | T16182-YE03-P0BAU-152507 | 2018-03-12 | DHI-TRANSMIT-001459 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8e062b7-59eb-41f4-b8f9-2b5ba414e63c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6619 | T16182-YE03-P0BAU-152535 | 2018-03-12 | DHI-TRANSMIT-001459 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd5862e9-ac8a-4ba9-9ada-7a1a404ad429 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6620 | T16182-DP00-P8ZEN-125759 | 2018-03-12 | DHI-WTRAN-001223 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0702f972-0eae-4dce-bbb6-4f42312b586c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6621 | T16182-CV03-P8ZEN-125612 | 2018-03-12 | DHI-TRANSMIT-001460 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbbc394b-ebf6-4c78-8519-f6455c02fdd6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6622 | T16182-YQ03-P8ZEN-125769 | 2018-03-12 | DHI-TRANSMIT-001460 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83c26268-168a-4cb7-a298-d73f4f21c328 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6623 | T16182-YT02-P8ZEN-125726 | 2018-03-12 | DHI-TRANSMIT-001460 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa2acd19-4e65-42b2-9e49-58dbf5c63b85 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6624 | T16182-YQ01-P0ZEN-152305 | 2018-03-12 | DHI-TRANSMIT-001461 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4567dbbf-f74f-4627-80d5-0a3ca89a2c5b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6625 | T16182-YQ01-P0ZEN-152317 | 2018-03-12 | DHI-TRANSMIT-001461 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=175b307e-6a92-4e60-b169-484b64920693 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6626 | T16182-YL01-P8ZEN-125703 | 2018-03-12 | DHI-WTRAN-001224 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25644a08-4293-4274-9e8d-825990c218a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6627 | T16182-YL01-P8ZEN-125705 | 2018-03-12 | DHI-WTRAN-001224 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84e381d7-429b-4a67-b3b2-661d3e2ac73a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6628 | T16182-YL01-P8ZEN-125706 | 2018-03-12 | DHI-WTRAN-001224 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c14f8c48-a298-40e7-acff-011c7232e150 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6629 | T16182-YL00-P8ZEN-125708 | 2018-03-12 | DHI-WTRAN-001224 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=113d9360-39fb-4371-abc2-9fd021e806c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6630 | T16182-YF00-P8ZEN-125709 | 2018-03-12 | DHI-WTRAN-001224 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdf06e8e-bbf3-422d-9974-08425fc9a57b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6631 | T16182-YF00-P8ZEN-125710 | 2018-03-12 | DHI-WTRAN-001224 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9907e595-f1c0-4f37-a382-7cfc168fb252 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6632 | T16182-YF00-P8ZEN-125724 | 2018-03-12 | DHI-WTRAN-001224 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=294f88df-689d-40df-88e8-85fd0bd3fda5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6633 | T16182-CA00-P0ULD-183903 | 2018-03-13 | DHI-TRANSMIT-001462 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89c57675-e143-413e-acf2-693c0275f6e0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6634 | T16182-XS00-P0SG-136601 | 2018-03-13 | DHI-TRANSMIT-001463 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0abe6e08-7e3f-46b1-9d1f-75244a0dedce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6635 | T16182-XS00-P0GKS-120051 | 2018-03-13 | DHI-TRANSMIT-001464 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8256ea3-4207-4e15-8f0f-d15fbca08288 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6636 | T16182-YD00-P0UBA-150502 | 2018-03-13 | DHI-TRANSMIT-001465 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b897a0d7-dd22-4f47-8b88-143ba7ca0069 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6637 | T16182-YD00-P0UBA-150505 | 2018-03-13 | DHI-TRANSMIT-001465 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e018e395-d938-4faf-956c-e27f58f737e0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6638 | T16182-YD00-P0UBA-150504 | 2018-03-13 | DHI-TRANSMIT-001465 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df249a14-3985-4aac-9169-8e24f5583036 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6639 | T16182-YD00-P0UBA-150506 | 2018-03-13 | DHI-TRANSMIT-001465 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5a0181c-3946-44d6-8ebc-3cd5051a8814 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6640 | T16182-YD00-P0UBA-150503 | 2018-03-13 | DHI-TRANSMIT-001465 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1b2ff41-e9f6-4dde-8147-f4dba05c04a1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6641 | T16182-YD00-P0UCA-150501 | 2018-03-13 | DHI-TRANSMIT-001465 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82af0e34-2966-4427-ac6c-c5fec987380c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6642 | T16182-XG02-P0LAC-126053 | 2018-03-13 | DHI-TRANSMIT-001466 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22a4af80-fbfe-43db-a8a1-4ddd1888d99b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6643 | T16182-CA01-P0UYC-182953 | 2018-03-13 | DHI-TRANSMIT-001467 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b58718f1-0fa1-44f7-ae2c-42476521304c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6644 | T16182-CA01-P0UYC-182955 | 2018-03-13 | DHI-TRANSMIT-001467 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=239aac1b-638f-4116-a793-edd0e5f9af78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6645 | T16182-CA02-P0UYC-182957 | 2018-03-13 | DHI-TRANSMIT-001467 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b15d1943-f873-4600-978b-63574e8b979e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6646 | T16182-CA03-P0HBD-189001 | 2018-03-14 | INT-IFC-180314-01 | INTERNAL IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d45b009-1962-4aed-b2c5-34a56c355f00 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6647 | T16182-XH01-P0SGA-137811 | 2018-03-14 | DHI-TRANSMIT-001471 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8914081c-3dd9-44c1-b833-5994fb6bc565 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6648 | T16182-XH01-P0SGA-139011 | 2018-03-14 | DHI-TRANSMIT-001471 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2337266e-e952-48ab-8ebd-390b9d29eead | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6649 | T16182-CA00-P0UYC-182901 | 2018-03-14 | DHI-TRANSMIT-001472 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84e9dd90-6d3b-44c1-bf35-8958180b677f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6650 | T16182-CA00-P0UYC-182905 | 2018-03-14 | DHI-TRANSMIT-001472 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56336fb3-49ad-41e6-a095-312f6df379c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6651 | T16182-CA02-P0UYC-182958 | 2018-03-14 | DHI-TRANSMIT-001472 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=368e8a2b-1310-4882-9032-a78b53432c5d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6652 | T16182-XH01-P0SGE-139613 | 2018-03-14 | DHI-TRANSMIT-001473 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16c1c458-1c73-4030-9fe0-265941f1f676 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6653 | T16182-YD05-P0CRN-161116 | 2018-03-15 | DHI-TRANSMIT-001477 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a1bbed6-b13b-4ba2-8fc7-966d9ee6bbaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6654 | T16182-CA00-P0UCB-180601 | 2018-03-15 | DHI-TRANSMIT-001478 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=028f34f2-45c2-44ab-908b-59f911a7282d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6655 | T16182-CA00-P0UCB-180607 | 2018-03-15 | DHI-TRANSMIT-001478 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f27c8cd9-c58a-42a0-8e63-3a1184a286f7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6656 | T16182-CA00-P0UCB-180611 | 2018-03-15 | DHI-TRANSMIT-001478 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb44809b-3037-4dc8-a47b-79a112df3a4b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6657 | T16182-CA01-P0UCB-180661 | 2018-03-15 | DHI-TRANSMIT-001478 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f7b6904-a658-4d99-aaac-6d80ec23f6e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6658 | T16182-VE04-P0UZA-172901 | 2018-03-15 | DHI-TRANSMIT-001479 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=295cbe22-6313-4cb6-9eb2-87dd90042a45 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6659 | T16182-XB02-P0UZA-172902 | 2018-03-15 | DHI-TRANSMIT-001479 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f3d2d2b-e1d5-4f12-b439-048ccb276a3f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6660 | T16182-XB02-P0UZA-172903 | 2018-03-15 | DHI-TRANSMIT-001479 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f80655ad-4472-41a0-aedd-b5d78f07cc0d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6661 | T16182-VK02-P0UZA-172908 | 2018-03-15 | DHI-TRANSMIT-001479 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=481cb6b1-3f7d-414e-803a-0bbea39076e7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6662 | T16182-CA00-P0ULD-183910 | 2018-03-15 | DHI-TRANSMIT-001480 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30c5960f-f406-4903-bc13-d9aad20e7daf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6663 | T16182-CA03-P0ULD-183964 | 2018-03-15 | DHI-TRANSMIT-001480 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04e9d89d-7443-4a46-8d64-634e80af56fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6664 | T16182-XB02-P0UAG-172102 | 2018-03-15 | DHI-TRANSMIT-001481 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d373dda-8461-45f4-b2c5-1825b0cf56cd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6665 | T16182-XB02-P0UAG-172162 | 2018-03-15 | DHI-TRANSMIT-001481 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4e617ad-475d-49ef-8b53-1ecddba5c261 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6666 | T16182-YD02-P0SAC-163408 | 2018-03-15 | DHI-TRANSMIT-001482 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c473bf76-8cd0-406b-83bd-ac7772742735 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6667 | T16182-CA00-P0USR-184701 | 2018-03-16 | DHI-TRANSMIT-001487 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=356d31a5-191d-4986-9a91-8885a9de9bbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6668 | T16182-CA00-P0USR-184702 | 2018-03-16 | DHI-TRANSMIT-001487 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6e000f0-c7e0-4716-96c1-c3f8a3b41277 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6669 | T16182-CA03-P0USR-184751 | 2018-03-16 | DHI-TRANSMIT-001487 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81de553e-1701-45b5-8abd-42c50778a86d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6670 | T16182-CA03-P0USR-184752 | 2018-03-16 | DHI-TRANSMIT-001487 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bad3324b-abe0-4de9-b57f-60f3c24f3117 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6671 | T16182-CA06-P0USR-184700 | 2018-03-16 | DHI-TRANSMIT-001487 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b72237c-b564-4658-9668-bd8bf57d593a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6672 | T16182-CA01-P0UMA-180452 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac1683b9-7b13-4c89-8482-02ea27cf2725 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6673 | T16182-CA01-P0UMA-180454 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=872ef24f-5700-46ff-b02a-09de5acfaa14 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6674 | T16182-CA03-P0UMA-180460 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89d03003-8ea5-4d88-b1ce-72bcd87503d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6675 | T16182-CA03-P0UMA-180464 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd5edca1-37ea-4cf5-ad18-4431470b9ef9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6676 | T16182-CA03-P0UMA-180465 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a77c5aaa-5850-4f60-99c8-691aba5702b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6677 | T16182-CA03-P0UMA-180466 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c5c3ae1-f881-4c4a-8699-2b260853d58b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6678 | T16182-CA03-P0UMA-180467 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98c274af-22c3-4f39-b0e3-d110fdca0c25 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6679 | T16182-CA03-P0UMA-180469 | 2018-03-16 | DHI-TRANSMIT-001488 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e541f4ca-f632-4327-8b63-98707a948e96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6680 | T16182-XB02-P0UNX-171402 | 2018-03-16 | DHI-TRANSMIT-001489 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f272b0b9-22c4-4280-aa13-cdd5213527ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6681 | T16182-XB02-P0UNX-171403 | 2018-03-16 | DHI-TRANSMIT-001489 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36a8a8fc-234b-44b9-b92d-b301c3215740 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6682 | T16182-XB02-P0UNX-171410 | 2018-03-16 | DHI-TRANSMIT-001489 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdbb5ef7-2aa4-4d00-acca-a6084c8e2fb3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6683 | T16182-CA00-P0USG-182701 | 2018-03-16 | DHI-TRANSMIT-001490 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3097ff08-345d-4f8d-8da4-6570251f855e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6684 | T16182-CA00-P0USG-182703 | 2018-03-16 | DHI-TRANSMIT-001490 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d659d1f-7103-40a8-86b1-d3119bac17e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6685 | T16182-XJ00-P0ZEN-140100 | 2018-03-16 | DHI-WTRAN-001229 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4d34118-0a95-469d-923d-1c80a8b9ba5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6686 | T16182-CA06-P0UYF-183600 | 2018-03-16 | DHI-WTRAN-001230 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e35e2b9e-6813-48ca-aed3-8ece89539863 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6687 | T16182-CA00-P0UYF-183601 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3164c13b-a7e4-4d73-9332-cfd960f86852 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6688 | T16182-CA00-P0UYF-183602 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ce95546-8834-4563-a547-39ee48084d19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6689 | T16182-CA00-P0UYF-183603 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20198f2b-ddee-40fa-89c1-4546ea51e4b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6690 | T16182-CA00-P0UYF-183604 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b74c3c95-7e32-4327-87b0-5a406c13bf66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6691 | T16182-CA01-P0UYF-183651 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fea8d037-d784-4da8-beba-395df9fc603b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6692 | T16182-CA01-P0UYF-183652 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=439b0a46-1ada-44c9-9dfa-8cad8d173554 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6693 | T16182-CA01-P0UYF-183653 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbaacc1f-b0f6-4c1f-8842-9b65790c7b8e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6694 | T16182-CA02-P0UYF-183654 | 2018-03-16 | DHI-TRANSMIT-001491 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ea8498b-3404-4917-8eef-6bd617c8ee47 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6695 | T16182-CA00-P0GEN-185701 | 2018-03-16 | DHI-TRANSMIT-001492 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95641b69-8adb-462f-973c-1b34ad69d097 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6696 | T16182-CA01-P0GEN-185751 | 2018-03-16 | DHI-TRANSMIT-001492 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9095daa8-68a7-4b10-97dc-f49f8126fa15 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6697 | T16182-CA00-P0GEN-185801 | 2018-03-16 | DHI-TRANSMIT-001493 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59e1e52e-a0ab-470e-b5fb-f931971836c5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6698 | T16182-CA00-P0GEN-185802 | 2018-03-16 | DHI-TRANSMIT-001493 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db020a65-bd3a-4d48-8c68-dbac85555f3f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6699 | T16182-CA00-P0GEN-185803 | 2018-03-16 | DHI-TRANSMIT-001493 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f5913f0-f40f-47bc-a3e8-27b6ec0ee874 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6700 | T16182-CA01-P0GEN-185852 | 2018-03-16 | DHI-TRANSMIT-001493 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3beb865c-fca7-4697-b617-45db5f19cdad | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6701 | T16182-CA01-P0GEN-185853 | 2018-03-16 | DHI-TRANSMIT-001493 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8246f614-97e7-46ef-8b81-d1c9e90125e9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6702 | T16182-XH01-P0SGA-139611 | 2018-03-16 | DHI-TRANSMIT-001494 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f2e636e-78a7-4e23-ac59-9bb89a845d3b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6703 | T16182-XH01-P0SGK-136713 | 2018-03-16 | DHI-TRANSMIT-001494 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=665102b0-7af1-418f-aafd-c582c8ecf904 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6704 | T16182-XW03-P0SAN-134401 | 2018-03-19 | DHI-WTRAN-001235 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18fc9fb1-40c8-4c06-80b5-143f5b532456 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6705 | T16182-XG07-P0SAN-134402 | 2018-03-19 | DHI-WTRAN-001235 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eab88f6b-ecdf-4a46-9ebd-70c7b040fb9f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6706 | T16182-XW03-P0SAN-134403 | 2018-03-19 | DHI-WTRAN-001235 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7305441-729f-4ed8-8eed-3180f7bd5a1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6707 | T16182-XH02-P0SAN-134404 | 2018-03-19 | DHI-WTRAN-001235 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75de66f6-8e14-4d97-9ec5-46a647fecf0e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6708 | T16182-YD02-P0LB-122063 | 2018-03-19 | DHI-TRANSMIT-001495 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c99121ba-2487-4042-bd15-0bf325ba6244 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6709 | T16182-YD02-P0LB-122064 | 2018-03-19 | DHI-TRANSMIT-001495 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbb95f7b-7325-480b-90f8-89963d10fb60 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6710 | T16182-YD00-P0LB-122109 | 2018-03-19 | DHI-TRANSMIT-001495 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c761fef-7a5d-4cae-bbae-35d490c5de1a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6711 | T16182-YL01-P0LB-122080 | 2018-03-19 | DHI-TRANSMIT-001496 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=222ed2fa-97f3-4133-ab57-05525eccfad2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6712 | T16182-US02-P0LB-122081 | 2018-03-19 | DHI-TRANSMIT-001496 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd20ce43-4f8f-41a9-ac15-1a6b8c6a3af5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6713 | T16182-XB02-P0ULX-171602 | 2018-03-19 | DHI-TRANSMIT-001497 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4597098-6ff9-4115-a9d4-137d3fea1e19 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6714 | T16182-YT01-P0LAC-126054 | 2018-03-20 | DHI-TRANSMIT-001498 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0c445e7-3c9f-461b-9ed4-2940e1e7b4d9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6715 | T16182-UC02-P0MKA-250010 | 2018-03-20 | DHI-WTRAN-001236 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4315dc10-fbd2-44f2-8c31-89dfc8ad1fd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6716 | T16182-CA03-P0UMA-180500 | 2018-03-21 | INT-IFC-180321-01 | INTERNAL IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1df9c1a9-2ae0-4c04-ad5f-60ed16567a87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6717 | T16182-DN04-P0EKG-124161 | 2018-03-21 | INT-IFC-180321-02 | INTERNAL IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8c788bb-10a0-4d72-ac74-3b77bf46a6f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6718 | T16182-YD00-P0LAC-126051 | 2018-03-21 | DHI-TRANSMIT-001499 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03c312b7-5633-4df9-99ee-c2a143775457 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6719 | T16182-YD02-P0SAC-163418 | 2018-03-21 | DHI-WTRAN-001237 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af2f29bb-0e96-461d-be74-ae7b79b2b696 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6720 | T16182-YD02-P0SAC-163422 | 2018-03-21 | DHI-TRANSMIT-001500 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5926180f-0cf2-4749-a1c2-278a9105b21b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6721 | T16182-XH01-P0SGK-137613 | 2018-03-21 | DHI-TRANSMIT-001501 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32f062ca-d799-40e8-8def-081cff1a7ac7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6722 | T16182-XH01-P0SGA-137311 | 2018-03-21 | DHI-TRANSMIT-001502 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71b92e4a-f4ea-4a9a-beef-d028265c4327 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6723 | T16182-XH01-P0SGE-137312 | 2018-03-21 | DHI-TRANSMIT-001502 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef33e390-61fd-4a8e-8fc3-bcb290593daf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6724 | T16182-YD00-P0SGZ-137331 | 2018-03-21 | DHI-TRANSMIT-001502 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b43be5ef-0407-42a7-9c60-192ba93e57ec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6725 | T16182-YQ08-P0CY-154045 | 2018-03-21 | DHI-WTRAN-001238 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d102585-99af-479b-9061-e6c53911f708 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6726 | T16182-XB00-P0GM-128506 | 2018-03-21 | DHI-TRANSMIT-001503 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35032335-f77f-4340-85f9-f447d4190435 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6727 | T16182-YF02-P0CRV-161102 | 2018-03-22 | DHI-TRANSMIT-001507 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d0a3ce2-64fd-4bde-a304-0fba75af8cd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6728 | T16182-YD00-P0CRN-161113 | 2018-03-22 | DHI-TRANSMIT-001507 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7a2a9d8-e913-410f-959c-0d6f6b47fc21 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6729 | T16182-YB03-P0CRN-161114 | 2018-03-22 | DHI-TRANSMIT-001507 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cb8afa9-f48f-49a4-8ab2-22a3c09fd1d9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6730 | T16182-YR02-P0ZEN-150001 | 2018-03-22 | DHI-TRANSMIT-001508 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d89c92cb-5c8a-461d-b40d-f3f5d28eb0cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6731 | T16182-YD00-P0CYE-139641 | 2018-03-22 | DHI-TRANSMIT-001509 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c567a0c-8689-4746-80c8-b286d77f49ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6732 | T16182-YU02-P0CYE-139642 | 2018-03-22 | DHI-TRANSMIT-001509 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42889864-d9c3-4b99-a379-2ca7dfc17022 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6733 | T16182-YD00-P0CYE-139541 | 2018-03-22 | DHI-TRANSMIT-001509 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79123aa3-7ed8-4347-a4e6-2e0e00c051d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6734 | T16182-YU02-P0CYE-139542 | 2018-03-22 | DHI-TRANSMIT-001509 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8876c296-6665-40f9-bc7c-0086d065b8bd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6735 | T16182-XH01-P0SGA-138611 | 2018-03-22 | DHI-TRANSMIT-001509 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acf77de2-67fb-4548-a3da-041b738a2984 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6736 | T16182-YD00-P0CHB-151131 | 2018-03-22 | DHI-WTRAN-001241 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a7c0a25-4c1e-4e35-a1c5-4561c0e69424 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6737 | T16182-YU03-P0CHB-151121 | 2018-03-22 | DHI-WTRAN-001241 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59130163-7284-4b45-8a7a-8e4d0f48f501 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6738 | T16182-YU03-P0CHB-151122 | 2018-03-22 | DHI-WTRAN-001241 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc0d84ff-19e5-44f3-8cc4-1f780f7af4cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6739 | T16182-YF00-P0BA-150404 | 2018-03-22 | DHI-TRANSMIT-001510 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e136cd-eecd-407c-9a52-bdc29cb5c5dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6740 | T16182-YU02-P0ZEN-150212 | 2018-03-22 | DHI-TRANSMIT-001510 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70235258-a39c-4296-8178-31003309e9ec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6741 | T16182-XW03-P0SAB-134801 | 2018-03-22 | DHI-TRANSMIT-001511 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bca97d76-b9dd-4d7c-b2f1-7360f72444d2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6742 | T16182-XG07-P0SAB-134802 | 2018-03-22 | DHI-TRANSMIT-001511 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87c1292b-2cf4-433c-afa7-7014e40db125 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6743 | T16182-XW03-P0SAB-134803 | 2018-03-22 | DHI-TRANSMIT-001511 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed9647c8-70ef-40c8-b29d-0adf31fe74f9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6744 | T16182-XH02-P0SAB-134804 | 2018-03-22 | DHI-TRANSMIT-001511 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5673498c-a4b3-4d8f-9e7b-f087f4101bdd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6745 | T16182-CA00-P0UYP-183201 | 2018-03-22 | DHI-TRANSMIT-001512 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ae7867b-8fec-4f12-bbe9-8d77c00d4fe3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6746 | T16182-CA00-P0UYP-183205 | 2018-03-22 | DHI-TRANSMIT-001512 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42268641-e85e-4db7-80ea-00d23f2ccd12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6747 | T16182-YQ08-P0CY-154052 | 2018-03-26 | DHI-WTRAN-001242 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=272d49ff-b6b5-4802-b8f6-75e9ddbfda72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6748 | T16182-YQ08-P0CY-154031 | 2018-03-26 | DHI-TRANSMIT-001521 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e138233-2184-43b9-be02-4760c0520505 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6749 | T16182-YQ08-P0CY-154032 | 2018-03-26 | DHI-TRANSMIT-001521 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d466489-86fa-4e1a-94ab-bb49d100921d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6750 | T16182-YQ08-P0CY-154034 | 2018-03-26 | DHI-TRANSMIT-001521 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e6d8717-3b0b-42d6-bd0a-5a5857eccadd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6751 | T16182-YQ08-P0CY-154035 | 2018-03-26 | DHI-TRANSMIT-001521 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3502cb0-9e76-4c37-b79b-0cec9e1c830f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6752 | T16182-YQ08-P0CY-154038 | 2018-03-26 | DHI-TRANSMIT-001521 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e92210e-3441-4da9-968d-c59d08fec5d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6753 | T16182-YQ08-P0CY-154051 | 2018-03-26 | DHI-TRANSMIT-001521 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8df4463-3d3c-4c43-af88-48b3fd3f4552 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6754 | T16182-CA05-P0UYB-183581 | 2018-03-26 | DHI-WTRAN-001243 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa1f18e2-6633-4d28-b860-c3f892f2bb9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6755 | T16182-CA05-P0UYB-183582 | 2018-03-26 | DHI-WTRAN-001243 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7de7d7fa-2db8-4486-ae91-6f90e7ae9dea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6756 | T16182-YR05-P0GM-128511 | 2018-03-26 | DHI-WTRAN-001244 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d42924d-a094-4c72-83f5-a35718e483f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6757 | T16182-BP00-P0EKG-140015 | 2018-03-26 | DHI-TRANSMIT-001522 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33f196ce-6e03-4628-9cc0-39519c93cd70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6758 | T16182-XJ00-P0GM-140121 | 2018-03-26 | DHI-TRANSMIT-001522 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=300007bf-b280-471d-83ac-b355cc217769 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6759 | T16182-XG02-P0SGC-138301 | 2018-03-26 | DHI-TRANSMIT-001523 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3736d8e4-a382-42ab-a0fb-84f952f0b041 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6760 | T16182-XH01-P0SGC-138311 | 2018-03-26 | DHI-TRANSMIT-001523 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11a06580-2512-4267-9980-bcc8ad1009b4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6761 | T16182-XW03-P0SAH-133401 | 2018-03-26 | DHI-TRANSMIT-001524 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1719744a-b5d7-41cb-b130-02b3cc2298a2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6762 | T16182-XG07-P0SAH-133402 | 2018-03-26 | DHI-TRANSMIT-001524 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4df0b278-09a1-4363-8a4a-2bf904a6c949 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6763 | T16182-XW03-P0SAH-133403 | 2018-03-26 | DHI-TRANSMIT-001524 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b36629ae-e30a-4da6-af27-797ed0d3277c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6764 | T16182-XH02-P0SAH-133404 | 2018-03-26 | DHI-TRANSMIT-001524 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b54d3d9a-1574-4e33-85e6-41d00ae080eb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6765 | T16182-YD02-P0ZEN-165506 | 2018-03-26 | DHI-WTRAN-001245 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3195c126-17f9-4430-8136-318815abc0a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6766 | T16182-YD02-P0ZEN-165509 | 2018-03-26 | DHI-WTRAN-001245 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d43c81e0-2a3e-4531-98fb-c90704586ace | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6767 | T16182-YD02-P0ZEN-165576 | 2018-03-26 | DHI-WTRAN-001245 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a357e969-3a88-4346-b74a-c3c23ea6ffee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6768 | T16182-YD02-P0ZEN-165577 | 2018-03-26 | DHI-WTRAN-001245 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f115ffc-5d29-409f-86b1-02a9f0c1831b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6769 | T16182-YD04-P0ZEN-152019 | 2018-03-26 | DHI-TRANSMIT-001525 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2a579d8-a88f-41e6-b5bf-3381576c4242 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6770 | T16182-VK02-P0UZT-172713 | 2018-03-26 | DHI-TRANSMIT-001526 | IFC | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=739a2d17-efcf-48fd-bd26-2a8329b97687 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6771 | T16182-XB02-P0UZT-172716 | 2018-03-26 | DHI-TRANSMIT-001526 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3210337f-9755-4f43-93f3-25ba5c3f21bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6772 | T16182-XH01-P0SGK-139012 | 2018-03-26 | DHI-TRANSMIT-001527 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88690f44-edb1-40cf-8d1a-c53e9b32953a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6773 | T16182-XS00-P0SG-136602 | 2018-03-26 | DHI-TRANSMIT-001527 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b2ac8f3-95ff-420b-8c5c-9d30c7c9ce97 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6774 | T16182-YE03-P6BAU-152508 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0c84dc8-eb74-4acb-a1c0-6ed2281e5156 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6775 | T16182-YE03-P7BAU-152509 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0ca9d99-6862-47b8-8ea7-bf1106aae985 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6776 | T16182-YE03-P0BAU-152511 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26c1cb99-c489-40f7-aa36-8da8406fb353 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6777 | T16182-YE03-P0BAU-152512 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 2 | D | TRUE | FALSE | 2018-03-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a32f9d3-e9ea-4472-88ce-f8c8661d55c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6778 | T16182-YE03-P0BAU-152522 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 2 | D | TRUE | FALSE | 2018-03-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7cff8cc-888a-4fc0-b022-5c68588fd87c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6779 | T16182-YE01-P0BAU-152601 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3db15947-5fef-45d7-a0c1-44162e982a2b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6780 | T16182-YE01-P0BAU-152602 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 1 | D | TRUE | FALSE | 2018-03-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d48d867-b784-4cd8-a69b-989f4cd979fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6781 | T16182-YE01-P0BAU-152603 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 1 | D | TRUE | FALSE | 2018-03-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5004a9f-e842-44a9-9c01-3d1ca0e2997b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6782 | T16182-YE01-P0BAU-152608 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 0 | D | TRUE | FALSE | 2018-03-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3dada929-1077-419c-ab70-764adf2e8eb4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6783 | T16182-YE01-P0BAU-152614 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 0 | D | TRUE | FALSE | 2018-03-26_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ddf3283-ece6-4770-8b41-551f68f859d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6784 | T16182-YE03-P0BAU-152539 | 2018-03-26 | DHI-TRANSMIT-001528 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76825de3-a6c5-4967-8f3f-5c0f1ca8b873 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6785 | T16182-YD02-P0ZEN-165502 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bef4658c-d99e-4d72-9425-5dcc6df133a2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6786 | T16182-YD02-P0ZEN-165503 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=827de43b-a536-4d00-b175-4ec09fbfb295 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6787 | T16182-YD02-P0ZEN-165507 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c11b6d60-841a-4752-9827-1d9f6ee5d504 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6788 | T16182-YD02-P0ZEN-165508 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea88ee91-94fb-4aa9-bb81-3dc43467bbbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6789 | T16182-YD02-P0ZEN-165514 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1142ebd9-346c-456e-a305-349af2a8e7d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6790 | T16182-YD02-P0ZEN-165515 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d460694-e813-4338-8164-794af4259580 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6791 | T16182-YD02-P0ZEN-165516 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32980629-60c5-4537-8308-1c85c99c1ed0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6792 | T16182-YD02-P0ZEN-165521 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8560c2f8-6ddd-444d-b8b0-24fed7076428 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6793 | T16182-YD02-P0ZEN-165522 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea9aa90b-1e37-487c-831d-3af027cf153a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6794 | T16182-YD02-P0ZEN-165527 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=920349d8-8d2a-428c-a77c-03d555f03a95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6795 | T16182-YD02-P0ZEN-165528 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87fda780-daa4-46b9-8523-7b0dab8d5e49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6796 | T16182-YD02-P0ZEN-165529 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19f68ace-7db4-4c1c-8a7a-5d469877ac3a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6797 | T16182-YD02-P0ZEN-165571 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e800fca-aee2-4a6c-9f4f-0a575104bdc6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6798 | T16182-YD02-P0ZEN-165572 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24a9339d-d428-4f96-8b96-0b0d617ed39f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6799 | T16182-YD02-P0ZEN-165573 | 2018-03-26 | DHI-TRANSMIT-001531 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2edd021-a75e-4360-8f0d-b0ff8cf8890d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6800 | T16182-CH01-P0EKG-124039 | 2018-03-26 | INT-IFC-180326-01 | INTERNAL IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf514497-d90b-4b54-8a6c-54d884ab6abb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6801 | T16182-YM03-P8ZEN-125721 | 2018-03-26 | DHI-TRANSMIT-001532 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2609de84-c3eb-4612-a75a-fbbe37cb8b4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6802 | T16182-YQ01-P8ZEN-125765 | 2018-03-26 | DHI-TRANSMIT-001532 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18e7b5f8-0593-40fd-b8db-ada75d0db0b8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6803 | T16182-YE00-P8ZEN-125751 | 2018-03-26 | DHI-TRANSMIT-001532 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3af2c4ca-020e-41ef-b351-01ab37446a08 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6804 | T16182-YE01-P8ZEN-125768 | 2018-03-26 | DHI-TRANSMIT-001532 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f0556fe-2877-4e3d-ab6a-19c11a40be6f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6805 | T16182-CA00-P0UBA-181002 | 2018-03-26 | DHI-TRANSMIT-001533 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7112bacc-cbd0-484a-aec9-7f092b3b2fb7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6806 | T16182-CA00-P0UBA-181102 | 2018-03-26 | DHI-TRANSMIT-001533 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf189489-4bf0-4c19-a6c1-cc4f8c39dbe4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6807 | T16182-CA00-P0UBA-186101 | 2018-03-26 | DHI-TRANSMIT-001533 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f6b2f35-5e57-434f-93b9-447effd1d86a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6808 | T16182-XJ00-P8ZEN-125546 | 2018-03-26 | DHI-TRANSMIT-001534 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47a88cfd-dd69-48a8-b0d3-035550cf2379 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6809 | T16182-CA05-P0UYF-183681 | 2018-03-27 | DHI-WTRAN-001246 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a788ec3-07ed-4a96-a4c9-18f5a7cab23a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6810 | T16182-CA05-P0UYF-183682 | 2018-03-27 | DHI-WTRAN-001246 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0885748-4459-4e49-9869-7fef9015ca65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6811 | T16182-YB11-P0ZEN-152422 | 2018-03-27 | DHI-WTRAN-001247 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba9fb15b-00ae-4dcf-99a3-63539d6adaef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6812 | T16182-YQ01-P0ZEN-152322 | 2018-03-27 | DHI-WTRAN-001247 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58e168f4-51dc-4097-a8e0-4f6558991ac8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6813 | T16182-YT10-P0ZEN-152224 | 2018-03-27 | DHI-WTRAN-001247 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c530d054-5718-46b4-a357-ac083bf6d828 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6814 | T16182-YQ01-P0ZEN-152308 | 2018-03-27 | DHI-TRANSMIT-001535 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e191ead4-8c0d-49a9-8ec5-5159b03af919 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6815 | T16182-YQ01-P0ZEN-152328 | 2018-03-27 | DHI-TRANSMIT-001535 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a8d6eb4-d43c-4365-ad2b-83b7080ed5dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6816 | T16182-YQ01-P0ZEN-152329 | 2018-03-27 | DHI-TRANSMIT-001535 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f954414e-06ed-4170-bf66-8cc6841e9600 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6817 | T16182-CA00-P0UYE-183301 | 2018-03-27 | DHI-TRANSMIT-001536 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad108828-60c2-4f2c-98f6-8537861a61a3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6818 | T16182-CA00-P0UYE-183302 | 2018-03-27 | DHI-TRANSMIT-001536 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82bd3a8a-483f-48b7-96d6-eea82adc5f88 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6819 | T16182-CA00-P0UYE-183303 | 2018-03-27 | DHI-TRANSMIT-001536 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a3a7f33-482b-4daa-9624-30e08d10dd9d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6820 | T16182-XG02-P0SGK-136803 | 2018-03-28 | DHI-TRANSMIT-001538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0bc0b84-f211-4e62-923e-5f8fb0a56791 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6821 | T16182-XH01-P0SGK-136813 | 2018-03-28 | DHI-TRANSMIT-001538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9831c933-644e-4ca7-815d-3dd8d94bb883 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6822 | T16182-YT10-P0SGK-136823 | 2018-03-28 | DHI-TRANSMIT-001538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68f4dd23-66d5-4918-a76f-de1c47d0e6c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6823 | T16182-XH01-P0SGA-139511 | 2018-03-28 | DHI-TRANSMIT-001538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=085cc68b-3f00-4143-81ad-633f6e32279b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6824 | T16182-XH01-P0SGE-139512 | 2018-03-28 | DHI-TRANSMIT-001538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=254a588a-3021-459d-82bf-93d6bcf5b1fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6825 | T16182-XG02-P0SGE-139502 | 2018-03-28 | DHI-TRANSMIT-001538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c884634-467c-4421-ad72-1209ff3f6313 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6826 | T16182-XG02-P0SGA-139501 | 2018-03-28 | DHI-TRANSMIT-001538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b867db81-c2f5-484c-a31f-735615f141d5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6827 | T16182-XB02-P0UHA-171815 | 2018-03-28 | DHI-TRANSMIT-001539 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b5d5eda-8583-4f32-a625-07d0b16cfd15 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6828 | T16182-CA00-P0UTF-182801 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e358c9db-d69d-46ab-a91c-3fc3701ab4a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6829 | T16182-CA00-P0UTF-182802 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55a548a1-6657-46cb-8686-e10b15a513dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6830 | T16182-CA00-P0UTF-182803 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ccec277-9322-4239-8bfe-44aa7e50a3d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6831 | T16182-CA00-P0UTF-182804 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6fe7a0a-26ea-4163-9a00-e0177c2bbda2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6832 | T16182-CA01-P0UTF-182852 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4bb3b71-0812-4f44-beb9-3317a222a248 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6833 | T16182-CA01-P0UTF-182853 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb0ab372-652b-4c44-91a6-d750b1c83a9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6834 | T16182-CA01-P0UTF-182854 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c805007-44d3-4ac6-aa3c-67ec1ce3e70f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6835 | T16182-CA01-P0UTF-182855 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c4f6274-e7cc-4962-a98a-7667aab3aa20 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6836 | T16182-CA01-P0UTF-182856 | 2018-03-28 | DHI-TRANSMIT-001540 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3d40d7d-7684-40d1-b25b-6170cc16372e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6837 | T16182-XW03-P0SAE-135301 | 2018-03-29 | DHI-WTRAN-001248 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6838 | T16182-XH02-P0SAE-135304 | 2018-03-29 | DHI-WTRAN-001248 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6839 | T16182-XG07-P0SAE-135302 | 2018-03-29 | DHI-WTRAN-001248 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6840 | T16182-XW03-P0SAE-135303 | 2018-03-29 | DHI-WTRAN-001248 | IFR | A | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6841 | T16182-CA00-P0UTX-183361 | 2018-03-29 | DHI-TRANSMIT-001541 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1f87c79-df71-4f5f-aa4d-427214bdea12 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6842 | T16182-CA02-P0UTX-183377 | 2018-03-29 | DHI-TRANSMIT-001541 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2616a12e-14c6-474a-b4de-967e658475b6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6843 | T16182-CA03-P0UTX-183371 | 2018-03-29 | DHI-TRANSMIT-001541 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91b9babe-50b0-43c5-9874-d53701de6e6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6844 | T16182-CA03-P0UTX-183372 | 2018-03-29 | DHI-TRANSMIT-001541 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7ab8d28-4318-4cbb-bc36-ef7e12fcb488 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6845 | T16182-CA03-P0UTX-183373 | 2018-03-29 | DHI-TRANSMIT-001541 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11f63738-4115-4202-a4ce-cb348a8f3bf3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6846 | T16182-CA03-P0UTX-183375 | 2018-03-29 | DHI-TRANSMIT-001541 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb52aecf-5860-498b-a31f-1f8efd16286a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6847 | T16182-CA06-P0UTX-183390 | 2018-03-29 | DHI-TRANSMIT-001541 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c34872fe-aace-4ee1-baf1-fa49812eb48d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6848 | T16182-CV03-P0CWQ-161121 | 2018-03-29 | DHI-WTRAN-001249 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e17c8dc0-9350-4017-8458-f3243aa63f6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6849 | T16182-XJ00-P0ZEN-140119 | 2018-03-29 | DHI-WTRAN-001250 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0deaf8ec-1e25-4f3b-a236-70ccbb74929f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6850 | T16182-YB03-P0ZEN-165532 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df6e6479-3ed2-4005-8b23-29bce48a4b9a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6851 | T16182-YB03-P0ZEN-165533 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=289c6ea2-e8d2-4c16-9824-10d8cb92a156 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6852 | T16182-YB03-P0ZEN-165534 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86fb8982-3d12-49f9-9021-efea47630256 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6853 | T16182-YB03-P0ZEN-165535 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f1fb10e-8217-40d0-bea0-e5ef1629d334 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6854 | T16182-YB03-P0ZEN-165536 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3f448d3-8007-4564-b7cf-f18aaa1738d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6855 | T16182-YB03-P0ZEN-165537 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52f252f2-c21c-4485-8ea2-78cf874994f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6856 | T16182-YB03-P0ZEN-165538 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=538985b3-8159-43a5-836d-e8bbbff26343 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6857 | T16182-YB03-P0ZEN-165539 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d611814-0078-4126-ae27-724d067cec07 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6858 | T16182-YB03-P0ZEN-165540 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42741c3a-cabe-4968-a5b1-ea2139bf0ef5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6859 | T16182-YB03-P0ZEN-165541 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50fed91b-5565-46ed-bd67-4ac742769863 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6860 | T16182-YB03-P0ZEN-165542 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbfad6f6-f71a-4d37-89dd-ade324e3b084 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6861 | T16182-YB03-P0ZEN-165543 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a7ec1d1-ddaa-4c3d-a886-b008d492552c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6862 | T16182-YB03-P0ZEN-165544 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=178dbf32-8c24-47d9-a0c3-e41e88a3a4e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6863 | T16182-YB03-P0ZEN-165545 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b353701b-a465-461c-b3c7-425eb1288f54 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6864 | T16182-YB03-P0ZEN-165546 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a19d7a8a-e03e-4368-9e23-602a53ffb76f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6865 | T16182-YB03-P0ZEN-165547 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d32de5c-8013-4b2d-a760-6af3ca5b7ace | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6866 | T16182-YB03-P0ZEN-165548 | 2018-03-29 | DHI-TRANSMIT-001542 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea9aec9b-1f3f-41b0-a805-8e16291d769a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6867 | T16182-YD00-P0SMU-128017 | 2018-03-29 | DHI-TRANSMIT-001543 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78311213-9e0a-452c-b5c7-3bf7239daa45 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6868 | T16182-YT01-P0SMU-128022 | 2018-03-29 | DHI-TRANSMIT-001543 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73112246-e8cf-45da-b045-e41b6f15f110 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6869 | T16182-YL00-P0LB-122079 | 2018-03-29 | DHI-TRANSMIT-001544 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bab658ce-92ad-4319-885d-edb5ac80ec9e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6870 | T16182-YD02-P0ZEN-165501 | 2018-03-29 | DHI-TRANSMIT-001545 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9d0d17e-573d-407d-a2f2-5f8d3ef8c3de | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6871 | T16182-YD02-P0ZEN-165504 | 2018-03-29 | DHI-TRANSMIT-001545 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=389de0f0-678a-410b-b84c-9037976d9fc0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6872 | T16182-YD02-P0ZEN-165505 | 2018-03-29 | DHI-TRANSMIT-001545 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84b55189-d50a-41b0-b02c-0953eb3920d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6873 | T16182-YU03-P0BAC-150731 | 2018-03-30 | DHI-TRANSMIT-001554 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99a3f087-25cc-482e-9fef-4cea4671d9ff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6874 | T16182-YB11-P0ZEN-152427 | 2018-03-30 | DHI-WTRAN-001251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a44a45c3-cfd5-4567-8d3d-06641f25e228 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6875 | T16182-YQ01-P0ZEN-152332 | 2018-03-30 | DHI-WTRAN-001251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7bc8368-6cb6-4e91-89f5-12594435084a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6876 | T16182-YT10-P0ZEN-152234 | 2018-03-30 | DHI-WTRAN-001251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36abd08b-3d07-4f1f-9ff3-0fb48ebceb58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6877 | T16182-YT10-P0ZEN-152229 | 2018-03-30 | DHI-WTRAN-001251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfa0274d-d1c9-4a13-9415-13642242bbed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6878 | T16182-YQ01-P0ZEN-152327 | 2018-03-30 | DHI-WTRAN-001251 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df63a26b-8fdc-4ed7-849a-062bccf5880f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6879 | T16182-YQ01-P0ZEN-152302 | 2018-03-30 | DHI-TRANSMIT-001555 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30fd0114-3fa6-41bb-b3cf-aedc197ef7fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6880 | T16182-YQ01-P0ZEN-152303 | 2018-03-30 | DHI-TRANSMIT-001555 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a141afe9-4d97-40a8-980b-bad82ca8a33c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6881 | T16182-XW01-P0STG-130501 | 2018-03-30 | DHI-WTRAN-001252 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4499d2c0-6260-4c0e-97e8-2f71baffb639 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6882 | T16182-XL00-P0STG-130503 | 2018-03-30 | DHI-TRANSMIT-001556 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95ec22b0-74d9-4401-b98b-20652a3ac788 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6883 | T16182-YD00-P0STG-130502 | 2018-03-30 | DHI-TRANSMIT-001556 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8fadea7-f644-4d6b-88f6-17a0e08a1700 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6884 | T16182-YK00-P0GCF-130016 | 2018-03-30 | DHI-WTRAN-001253 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=697bcf51-a34a-48f0-9589-023f0854a712 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6885 | T16182-YE00-P0GCF-130015 | 2018-03-30 | DHI-TRANSMIT-001557 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a70ba0b2-9844-4794-aa90-24d07af1a253 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6886 | T16182-XW03-P0SAE-134301 | 2018-03-30 | DHI-TRANSMIT-001558 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63bece15-22d2-4c8a-8e28-45481cacce0e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6887 | T16182-XG07-P0SAE-134302 | 2018-03-30 | DHI-TRANSMIT-001558 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=386adf82-f963-48ad-974c-9b1bc0a65702 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6888 | T16182-XW03-P0SAE-134303 | 2018-03-30 | DHI-TRANSMIT-001558 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c67bfc0b-4ea8-4d20-9071-70c75669d6cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6889 | T16182-XH02-P0SAE-134304 | 2018-03-30 | DHI-TRANSMIT-001558 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59be8a94-83c5-46fc-a179-88ffd699b2a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6890 | T16182-XA00-P0MAG-123048 | 2018-03-30 | DHI-WTRAN-001254 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0395983a-824e-4d08-8755-272788fee61e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6891 | T16182-XA00-P0MAG-123049 | 2018-03-30 | DHI-WTRAN-001254 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05e4220a-4da2-4792-97a0-e7e35f18360e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6892 | T16182-XG02-P0MAG-123002 | 2018-03-30 | DHI-TRANSMIT-001559 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2797196f-a1cd-4e7c-ad46-3cbfa099748d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6893 | T16182-XH01-P0MAG-123016 | 2018-03-30 | DHI-TRANSMIT-001559 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04211f69-7887-4ed4-ac73-1c72a165018e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6894 | T16182-YD00-P0BAT-150626 | 2018-04-02 | DHI-WTRAN-001255 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dbb889c-59e3-47e0-b39d-e77127e4114f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6895 | T16182-YD00-P0BBT-150671 | 2018-04-02 | DHI-WTRAN-001255 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7169d7ff-6577-4d5a-8c6c-bf9b5ebf5f7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6896 | T16182-YT01-P0BBT-150661 | 2018-04-02 | DHI-TRANSMIT-001560 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb6990b3-87c1-4957-9c9c-09958635b13f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6897 | T16182-YU03-P0BAT-150631 | 2018-04-02 | DHI-TRANSMIT-001560 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c04a20f1-a851-4cf8-83ff-20a5ae218ae3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6898 | T16182-YU03-P0BAT-150636 | 2018-04-02 | DHI-TRANSMIT-001560 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b546016b-3dc8-4ea3-a78d-1a1db189a94e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6899 | T16182-YD00-P0LCB-127031 | 2018-04-02 | DHI-TRANSMIT-001561 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e75956c-91d0-45fe-a436-f76af3de49a2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6900 | T16182-YD00-P0GHC-129001 | 2018-04-02 | DHI-TRANSMIT-001562 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cf8d36c-6505-4467-9650-5fc2578ef07d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6901 | T16182-YD00-P0GHC-129031 | 2018-04-02 | DHI-TRANSMIT-001562 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b2becbf-b32a-4e77-87b5-aeb03adb2635 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6902 | T16182-YD00-P0GHC-129051 | 2018-04-02 | DHI-TRANSMIT-001562 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80fae39d-f352-474f-aaea-6ee8d9391c80 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6903 | T16182-YD00-P0LCB-127001 | 2018-04-02 | DHI-TRANSMIT-001562 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f64840a-0189-48f9-8820-6d6bcc2bc375 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6904 | T16182-YD00-P0BAA-150762 | 2018-04-03 | DHI-TRANSMIT-001563 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f786abfb-0241-4f9e-b09b-1d3394f73c5c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6905 | T16182-YD00-P0BAA-150767 | 2018-04-03 | DHI-WTRAN-001257 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ab2c34d-f4ff-4b2d-a7d9-aee00dbff3e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6906 | T16182-YD00-P0CYE-136741 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=498928ca-594f-49e7-9ccd-f20c2f32256f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6907 | T16182-YD00-P0CYE-136841 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18f2cb48-24a7-4923-a8d4-5db5cf253e23 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6908 | T16182-YU02-P0CYE-136842 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5711dea9-1135-4b59-be75-6e57c54e9775 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6909 | T16182-YD00-P0CYE-136941 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be161ffe-20fc-4172-98fc-9ecbbdd7c043 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6910 | T16182-YU02-P0CYE-136942 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a2a3e7a-6752-4ca0-b0a1-7c985b49d3c6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6911 | T16182-YD00-P0CYE-137641 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c5507e5-ffab-4f90-9b97-8b2eb279072a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6912 | T16182-YU02-P0CYE-137642 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a7c2c5b-1160-44ce-9eba-c8d4b570caf4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6913 | T16182-XG02-P0CYE-137644 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a594ef0a-4078-41d0-8f47-157e853408fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6914 | T16182-XG02-P0CYE-138644 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=133af797-353c-447c-9841-2e1df8958498 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6915 | T16182-XG02-P0CYE-138744 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34a645a3-7d2d-4a76-a9be-57b9cf059764 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6916 | T16182-XG02-P0CYE-138844 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5f6b64a-74c3-4e9d-8aa5-40f0a9d6aa55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6917 | T16182-XG02-P0CYE-139544 | 2018-04-03 | DHI-TRANSMIT-001564 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2dd3f059-5bea-4486-a446-e7dc9177c55c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6918 | T16182-CC08-P8QHA-125300 | 2018-04-04 | DHI-WTRAN-001258 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1c92f96-c63c-4b06-853f-1838a3d879ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6919 | T16182-YE00-P0ZEN-152750 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e87ba954-2ddf-4852-a32c-3957c8cb6490 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6920 | T16182-YE00-P0ZEN-152751 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f881a4f-ca95-47dd-aaec-8d386b70a6f4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6921 | T16182-YE00-P0ZEN-152752 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=554e5a95-ba43-4158-a98a-fb7d23fdd174 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6922 | T16182-YE00-P0ZEN-152753 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78034e83-f435-4e4b-9a04-762c325a2cdd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6923 | T16182-YE00-P0ZEN-152754 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81c27e39-e0ff-4af6-b910-b78afb73703f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6924 | T16182-YE00-P0ZEN-152755 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5978d815-f939-4089-a932-bd21be89fff4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6925 | T16182-YE00-P0ZEN-152756 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36f71d7e-3304-49de-8b41-a7430783018f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6926 | T16182-YE00-P0ZEN-152757 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f97e4633-042a-4075-b4fb-04034e488d6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6927 | T16182-YE00-P0ZEN-152758 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c04c185-6301-49a7-ade2-d5ad56112708 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6928 | T16182-YE00-P0ZEN-152759 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e28feeb3-6716-4fab-a459-8170d67ec66d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6929 | T16182-YE00-P0ZEN-152760 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3123cacd-ce26-4b52-801d-29cf00264fa3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6930 | T16182-YE00-P0ZEN-152761 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6afdc69d-3867-4172-a489-ba9d996dac0a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6931 | T16182-YE00-P0ZEN-152762 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef35643f-014c-490c-961d-253d3775dace | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6932 | T16182-YE00-P0ZEN-152763 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17b15daa-ff86-4cd0-a61d-e5222bc6f5b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6933 | T16182-YE00-P0ZEN-152764 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cb70dda-acf9-4562-bf62-eccaf63c9da2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6934 | T16182-YE00-P0ZEN-152765 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57ab3346-4e27-4095-a315-b9b6fd02726f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6935 | T16182-YE00-P0ZEN-152766 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c28b0c65-aa92-475b-b056-5f975c35d66b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6936 | T16182-YE00-P0ZEN-152767 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44a0398d-5176-48d7-8cdb-ef2ea93f8f06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6937 | T16182-YE00-P0ZEN-152768 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c20b67f-9892-407e-a3ea-edcec3c07040 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6938 | T16182-YE00-P0ZEN-152769 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa624ac8-df3b-4907-a888-e650c1153b89 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6939 | T16182-YE00-P0ZEN-152770 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ccc7266-3864-491a-8f70-41b09b5307ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6940 | T16182-YE00-P0ZEN-152771 | 2018-04-04 | DHI-TRANSMIT-001566 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca556212-823e-41d7-9c5e-ab31960bddcb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6941 | T16182-XB00-P0SCA-127509 | 2018-04-04 | DHI-TRANSMIT-001567 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8adf3333-4fbd-4fb8-b121-b78ca3a515ed | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6942 | T16182-YD00-P0LCB-127501 | 2018-04-04 | DHI-TRANSMIT-001567 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f842b6b9-3128-4c9a-9f97-9e76b373b88c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6943 | T16182-CA01-P0ULD-183954 | 2018-04-04 | DHI-TRANSMIT-001568 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=296fb413-8693-4086-98ca-371a4ce3dbb0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6944 | T16182-YD02-P0SAC-163413 | 2018-04-04 | DHI-TRANSMIT-001569 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd4d74ee-6791-416a-8abd-59536a41a0cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6945 | T16182-YD02-P0SAC-163414 | 2018-04-04 | DHI-TRANSMIT-001569 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f21aa905-ada9-440f-beae-5582d3000b22 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6946 | T16182-YT01-P0LCP-110301 | 2018-04-04 | DHI-TRANSMIT-001570 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c54eb2b-e089-42ca-ba64-7d2c9fe06b26 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6947 | T16182-CA03-P0HBD-189001 | 2018-04-05 | INT-IFC-180405-01 | INTERNAL IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0ef3cb8-be85-411b-8d54-6000b9028733 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6948 | T16182-YS02-P0EKG-124048 | 2018-04-05 | INT-IFC-180405-02 | INTERNAL IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4eb9b04-c462-4b43-bbfa-0b88936c71a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6949 | T16182-YT01-P0MBA-121824 | 2018-04-05 | DHI-WTRAN-001259 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ee3424a-44b0-4c34-996e-f2e18b7e21e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6950 | T16182-UC07-P0ZEN-100001 | 2018-04-06 | DHI-TRANSMIT-001572 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25ee0af9-df7c-49f5-b188-16563d6fc84d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6951 | T16182-UC07-P0ZEN-100002 | 2018-04-06 | DHI-TRANSMIT-001572 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e36cf61-8cf4-48c4-b630-f7cb2abe8d36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6952 | T16182-UC07-P0ZEN-100003 | 2018-04-06 | DHI-TRANSMIT-001572 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b504ea4-8848-41c5-bc85-e4ad2b112bfb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6953 | T16182-CA00-P0UST-182001 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4439914-eb65-4fdc-b1a5-5e1d0eeeeae9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6954 | T16182-CA00-P0UST-182002 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7abb8755-eda8-4776-9c54-703838c65fb2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6955 | T16182-CA00-P0UST-182005 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=346fcabb-0bf4-4d6e-8703-c9ea7c38cd88 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6956 | T16182-CA00-P0UST-182006 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9bd914c-5c86-4c95-a06d-d536e63b0e96 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6957 | T16182-CA03-P0UST-182054 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fd2c6fb-074f-4503-998f-372b998845c9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6958 | T16182-CA03-P0UST-182056 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58791951-7358-405d-b8b0-1892bb78b31e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6959 | T16182-CA02-P0UST-182060 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a584ae47-5c98-47b2-8dd6-4a328c10e3d8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6960 | T16182-CA03-P0UST-182063 | 2018-04-06 | DHI-TRANSMIT-001573 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b44c31c-def4-4e5b-82ec-567bffc5d653 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6961 | T16182-CA00-P0UCB-180604 | 2018-04-06 | DHI-TRANSMIT-001574 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9361e05-a9e7-4573-bbcd-a8563b4b25f2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6962 | T16182-CA00-P0UCB-180607 | 2018-04-06 | DHI-TRANSMIT-001574 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5afd5f37-4a1e-48dc-b112-d268f1fb4b2e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6963 | T16182-CA00-P0UCB-180611 | 2018-04-06 | DHI-TRANSMIT-001574 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=530e520f-4594-48ca-84cb-7f0a9cd2c427 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6964 | T16182-CA00-P0UCB-180613 | 2018-04-06 | DHI-TRANSMIT-001574 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e2b901c-aed1-4468-ba5e-db22e5c5afdb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6965 | T16182-XG02-P6MAA-220025 | 2018-04-06 | DHI-TRANSMIT-001575 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21f0da64-9d1c-4801-b161-46a2bece2bb6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6966 | T16182-XG02-P7MAA-220026 | 2018-04-06 | DHI-TRANSMIT-001575 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adeeb9ae-9335-4ba0-bbce-5c0ddcd1d02b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6967 | T16182-YT02-P0PCA-126529 | 2018-04-06 | DHI-WTRAN-001260 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0ffe0b2-f55e-4150-9f9c-613bf18395df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6968 | T16182-CA05-P0UYA-183181 | 2018-04-06 | DHI-WTRAN-001261 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8ced0bf-65e3-4d28-8acc-6b90948b36ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6969 | T16182-CA05-P0UYA-183182 | 2018-04-06 | DHI-WTRAN-001261 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68c99ae5-68af-4840-b828-7c1841feab8b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6970 | T16182-CA05-P0UYA-183183 | 2018-04-06 | DHI-WTRAN-001261 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0ff9764-145a-4406-a0b1-f0163bebe332 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6971 | T16182-YD02-P0ZEN-165515 | 2018-04-09 | DHI-TRANSMIT-001576 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed0cf455-c2a1-4f4a-9fe6-8984a4c910e0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6972 | T16182-YL16-P0ZEN-165567 | 2018-04-09 | DHI-TRANSMIT-001576 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ed77cbd-1407-4f03-8aaf-2462625b5269 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6973 | T16182-UE00-P0MB-100004 | 2018-04-09 | DHI-TRANSMIT-001577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77395f50-48d7-4282-b6ff-b6bc29c22a97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6974 | T16182-UE00-P0MB-100005 | 2018-04-09 | DHI-TRANSMIT-001577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4ac70d0-6570-414b-89a5-27f70cb2eced | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6975 | T16182-UE00-P0MB-100006 | 2018-04-09 | DHI-TRANSMIT-001577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ecfa944-0ed0-429f-bf7c-89bd24ace4fa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6976 | T16182-UE00-P0MB-100007 | 2018-04-09 | DHI-TRANSMIT-001577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6320643-6498-4a7e-9e5b-8db1213727ce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6977 | T16182-UE00-P0UMA-100008 | 2018-04-09 | DHI-TRANSMIT-001577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b9e7295-d7c5-4626-8c6f-2ac56e8eecdc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6978 | T16182-UE00-P0UMA-100009 | 2018-04-09 | DHI-TRANSMIT-001577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=884d4212-dccf-4df0-ad01-810fe573b7a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6979 | T16182-UE00-P0UMA-100010 | 2018-04-09 | DHI-TRANSMIT-001577 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f1e9fe8-72f7-4ef2-9835-2c73b9a826f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6980 | T16182-XG02-P8ZEN-125582 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90683d35-700c-4d34-8d6a-f77d1273929e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6981 | T16182-XG02-P8ZEN-125583 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0822bbd5-dcdf-4936-8bbe-7d6f0dd386aa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6982 | T16182-XG02-P8ZEN-125584 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00279160-4973-417d-9bf5-368377671b22 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6983 | T16182-XG02-P8ZEN-125585 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95961b98-105f-4f9c-8330-56eb5123f356 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6984 | T16182-XG02-P8ZEN-125586 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f17cb7d-b077-4fe5-860f-54b1dfa9168b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6985 | T16182-XG02-P8ZEN-125587 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d5d80ed-d8ae-470e-8d8a-53476d65beea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6986 | T16182-XG02-P8ZEN-125588 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=104f9a18-c2d4-4c38-b1e1-a7adcab24f56 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6987 | T16182-XG02-P8ZEN-125589 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ae1183a-939f-45ee-ba9a-e9e033214036 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6988 | T16182-XG02-P8ZEN-125590 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b27faac-e5b7-4ce5-84cb-948e52283c5a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6989 | T16182-XG02-P8ZEN-125591 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f69c6aae-1205-4c05-a5a3-93041d7e4d3d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6990 | T16182-XG02-P8ZEN-125592 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c80a0a4c-e8c1-4857-b674-ce68fa038406 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6991 | T16182-XG02-P8ZEN-125593 | 2018-04-09 | DHI-TRANSMIT-001578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf8217f2-1433-4788-a1d5-5852fc3af480 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6992 | T16182-XH01-P0SGK-136713 | 2018-04-10 | DHI-TRANSMIT-001585 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5a340fe-ae4c-40bf-9ec5-3ed20dc47b16 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6993 | T16182-YD00-P0BAA-150782 | 2018-04-10 | DHI-WTRAN-001262 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91288dc3-cda4-4d9c-a6eb-ce6266dd25d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6995 | T16182-YK09-P0LD-130212 | 2018-04-10 | DHI-TRANSMIT-001586 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ac9b6c2-7397-4efc-ac7c-294fa3021d8b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6996 | T16182-YD04-P0ZEN-152010 | 2018-04-10 | DHI-WTRAN-001264 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1ecb176-6ffc-4093-9b5b-6d539898b280 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6997 | T16182-YD04-P0ZEN-152016 | 2018-04-10 | DHI-TRANSMIT-001587 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05934da1-6c6a-49ea-9fc6-af7863c92779 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6998 | T16182-YD04-P0ZEN-152018 | 2018-04-10 | DHI-TRANSMIT-001587 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a91b9f7e-dcc0-45f5-a453-926853a988e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6999 | T16182-XG02-P0LD-130204 | 2018-04-10 | DHI-TRANSMIT-001588 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f6393ad-1785-41ee-950d-617c4a1bb561 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7000 | T16182-XW03-P0SAE-135401 | 2018-04-10 | DHI-WTRAN-001265 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27274c1a-ded6-4dd4-bf91-bd472627c9c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7001 | T16182-XG07-P0SAE-135402 | 2018-04-10 | DHI-WTRAN-001265 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4904605-6d6a-41a5-829b-5c4c92bbe69c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7002 | T16182-XW03-P0SAE-135403 | 2018-04-10 | DHI-WTRAN-001265 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4149c9b2-15cd-4b9d-9764-e1afab33609a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7003 | T16182-XH02-P0SAE-135404 | 2018-04-10 | DHI-WTRAN-001265 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68fe6f25-cdcc-4f5e-9021-d17df2a91730 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7004 | T16182-CA05-P0UYB-183581 | 2018-04-11 | DHI-TRANSMIT-001589 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb5d7e16-0e2d-4d76-889c-10a5bcdb0ca8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7005 | T16182-CA05-P0UYB-183582 | 2018-04-11 | DHI-TRANSMIT-001589 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48cec281-6b48-4816-8e19-795dc0764a08 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7006 | T16182-XJ00-P0QFB-140211 | 2018-04-11 | DHI-TRANSMIT-001590 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2821d148-9b28-4205-9c79-41b869e5c172 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7007 | T16182-XB02-P0UGF-173101 | 2018-04-11 | DHI-TRANSMIT-001591 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc34c95f-467c-45bc-a2ed-097e361197c2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7008 | T16182-XB02-P0UGF-173102 | 2018-04-11 | DHI-TRANSMIT-001591 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e15898fe-14cf-44b5-8ba4-c58c2e42e470 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7009 | T16182-VK02-P0UGF-173107 | 2018-04-11 | DHI-TRANSMIT-001591 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84ab68e4-7462-488d-9e70-586c1112d9ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7010 | T16182-UT01-P0GQB-173402 | 2018-04-11 | DHI-TRANSMIT-001592 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b0fd71f-77d9-4ea2-aa88-bc2905b4d36b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7011 | T16182-UT01-P0GQB-173403 | 2018-04-11 | DHI-TRANSMIT-001592 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a40bb47e-9884-4f79-b6fd-442e1ddc5bb8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7012 | T16182-YS01-P0MKY-290008 | 2018-04-11 | DHI-TRANSMIT-001593 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c2aad75-fc76-431e-ba6f-e9982224ffd9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7013 | T16182-YS01-P0MKY-290009 | 2018-04-11 | DHI-TRANSMIT-001593 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64fb124b-4910-4371-9aca-d0db83e32eb8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7014 | T16182-XG07-P0SAE-135302 | 2018-04-11 | DHI-TRANSMIT-001594 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f71ec810-2358-488b-9362-852de17f804a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7015 | T16182-XH02-P0SAE-135304 | 2018-04-11 | DHI-TRANSMIT-001594 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a572ad1c-7cb5-4c11-8e9b-08145dd24e84 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7016 | T16182-XW03-P0SAE-135301 | 2018-04-11 | DHI-TRANSMIT-001594 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82c206da-f460-48f0-8f03-1f334558fcfc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7017 | T16182-XW03-P0SAE-135303 | 2018-04-11 | DHI-TRANSMIT-001594 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc713f0b-3abd-47ea-a904-6b114d886d6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
6994 | T16182-CV03-P0LD-130219 | 2018-04-12 | DHI-WTRAN-001269 | IFI | 2 | D | TRUE | FALSE | 2018-04-12_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b3dafe1-20b6-475d-b806-800907f83b14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7018 | T16182-XJ00-P0LBG-140204 | 2018-04-12 | DHI-TRANSMIT-001595 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e04e26de-8571-4d7f-a52e-5aa63a9a0e65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7019 | T16182-XH01-P0LD-130213 | 2018-04-13 | DHI-WTRAN-001270 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=004d8857-73ae-4b01-9628-e79fe9a5b201 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7020 | T16182-YD00-P0LD-130202 | 2018-04-13 | DHI-TRANSMIT-001597 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acc9f813-0be1-4bd0-8e70-dd2cf1700074 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7021 | T16182-YD04-P0ZEN-152014 | 2018-04-13 | DHI-TRANSMIT-001598 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=578f2874-7a9c-457f-8a6d-56dba2476f9f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7022 | T16182-CA00-P0UYA-183101 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33c39059-1147-42ba-8fb0-9cbabc3d697d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7023 | T16182-CA00-P0UYA-183102 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=590f9b33-7627-4241-ae92-5c4179156727 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7024 | T16182-CA00-P0UYA-183103 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94de81b1-59e7-4d1d-8864-871001893e92 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7025 | T16182-CA00-P0UYA-183104 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7713b61d-3451-48ea-8b59-042d810e3eb7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7026 | T16182-CA00-P0UYA-183105 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97fbdb22-0de3-4260-a6ea-5e16c877d238 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7027 | T16182-CA01-P0UYA-183151 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f670a329-7985-40d8-a212-025ad80e7a67 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7028 | T16182-CA01-P0UYA-183152 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0ec6f19-1038-44a6-84a5-ead25efec9d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7029 | T16182-CA01-P0UYA-183153 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=570a50c7-0bf7-4808-bb82-d7647592f3df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7030 | T16182-CA01-P0UYA-183154 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9d8c6c5-f646-452f-9b22-600e65229ad1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7031 | T16182-CA02-P0UYA-183155 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0d66975-fb51-4345-b192-8700b06d99c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7032 | T16182-CA06-P0UYA-183100 | 2018-04-13 | DHI-TRANSMIT-001599 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=718b67a5-89e1-4255-ad3b-c9ca286b091f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7033 | T16182-YD00-P0PGB-110401 | 2018-04-13 | DHI-TRANSMIT-001600 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9b003f0-2edb-4ea1-9087-c68a36e8186e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7034 | T16182-XH01-P0LF-140405 | 2018-04-13 | DHI-WTRAN-001271 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=206e0dce-34ff-458e-bdab-b5a5eb93a706 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7035 | T16182-XJ00-P0QJA-140223 | 2018-04-13 | DHI-TRANSMIT-001601 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf4ac156-1a04-4f49-8074-d66a63a631fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7036 | T16182-XJ00-P0SCA-140210 | 2018-04-13 | DHI-TRANSMIT-001601 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d550075-bd46-458e-a08d-6a76b336faae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7037 | T16182-VE04-P0UZA-172901 | 2018-04-13 | DHI-TRANSMIT-001602 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=555dde9c-5305-4e48-8408-93cb5fc0a989 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7038 | T16182-XB02-P0UZA-172902 | 2018-04-13 | DHI-TRANSMIT-001602 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a607fc2-93ab-44bd-b4e3-4c0fdf842c10 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7039 | T16182-XB02-P0UZA-172903 | 2018-04-13 | DHI-TRANSMIT-001602 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84482d51-12cb-4499-8190-c956edf847b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7040 | T16182-VK02-P0UZA-172908 | 2018-04-13 | DHI-TRANSMIT-001602 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d37f7d9a-c15c-421f-94d8-42c7dac36710 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7041 | T16182-CA05-P0UYF-183681 | 2018-04-16 | DHI-TRANSMIT-001604 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9d3bb16-4a5d-4bb5-a831-7e5f41c75b7f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7042 | T16182-CA05-P0UYF-183682 | 2018-04-16 | DHI-TRANSMIT-001604 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=417467fa-d361-49f0-a1fc-ec8563406b24 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7043 | T16182-YL16-P0ZEN-152860 | 2018-04-16 | DHI-WTRAN-001272 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8096035-1e7d-4c7b-99e3-dfe2231a0539 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7044 | T16182-YT01-P0LF-110101 | 2018-04-17 | DHI-WTRAN-001273 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfbc45aa-6773-4039-8d8b-20fb22fc8ed2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7045 | T16182-YK08-P0LF-110102 | 2018-04-17 | DHI-TRANSMIT-001605 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dac58a20-ebee-499f-9e94-26ff0d06fb2f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7046 | T16182-XG02-P0SCA-120006 | 2018-04-17 | DHI-TRANSMIT-001606 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4d95772-3faf-441f-8915-7e267c27aabd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7047 | T16182-YD00-P0QJA-110502 | 2018-04-17 | DHI-TRANSMIT-001607 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=259117d5-31ee-43c8-a698-b8b015e6532b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7048 | T16182-YK08-P0QJA-110501 | 2018-04-17 | DHI-TRANSMIT-001607 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53852777-ef22-48f9-af72-0f841b4be54e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7049 | T16182-YT01-P0QJA-110503 | 2018-04-17 | DHI-TRANSMIT-001607 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ba61950-b220-468c-9870-5cde4646e4a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7050 | T16182-XG02-P0QJA-110012 | 2018-04-17 | DHI-TRANSMIT-001607 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd1bd31c-44b4-4b72-9c59-20ae79e96d83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7051 | T16182-YD00-P0CYE-137041 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72cf5fad-eca0-4208-8361-5b7bf8d44ee8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7052 | T16182-YU02-P0CYE-137042 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09251976-b38f-4c0a-a32d-0432c2cb1e54 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7053 | T16182-YD00-P0CYE-137141 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54b7feb9-2e77-423f-a6e0-307426a458ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7054 | T16182-YU02-P0CYE-137142 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aeea49c3-7f90-4d8c-840c-31df84bf40df | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7055 | T16182-YD00-P0CYE-138741 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a18c205-60cf-40e1-b34f-72b897990679 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7056 | T16182-YU02-P0CYE-138742 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21d4cb7a-22c0-4277-93cb-adf3fb9fcb26 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7057 | T16182-YD00-P0CYE-138841 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d10e8381-ddda-456b-a867-e5be61e0e73d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7058 | T16182-YU02-P0CYE-138842 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44a032b0-9768-4f6b-b072-06de7135f112 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7059 | T16182-XG02-P0CYE-136944 | 2018-04-17 | DHI-TRANSMIT-001608 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=587817dd-0d0f-4531-b8e5-f3713120a23a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7060 | T16182-CC08-P8QHB-125151 | 2018-04-18 | DHI-WTRAN-001274 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3406a63d-750a-4334-b0b9-4f1f34d7299c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7061 | T16182-VK02-P0ULX-171604 | 2018-04-18 | DHI-TRANSMIT-001609 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11a61471-d68a-4549-b67c-a615bd24cb64 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7062 | T16182-XB02-P0ULX-171603 | 2018-04-18 | DHI-TRANSMIT-001609 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b320fa1-95e9-4174-9c99-a8cdc22e33e1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7063 | T16182-XH02-P0MAG-123015 | 2018-04-18 | DHI-TRANSMIT-001610 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7536880d-3b7b-4eca-91b3-0d0e4282d84b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7064 | T16182-YK08-P0MAG-123017 | 2018-04-18 | DHI-TRANSMIT-001610 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25204dfd-d345-4137-8e29-09c04fda9303 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7065 | T16182-XG01-P0MJ-110509 | 2018-04-19 | DHI-TRANSMIT-001614 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bedb8f7d-3f5b-47e5-b5f7-d670fc6e778b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7066 | T16182-XG02-P0MJ-110505 | 2018-04-19 | DHI-TRANSMIT-001614 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b65f3efe-9007-46cc-93bd-5edc61725fae | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7067 | T16182-YF00-P0MJ-110511 | 2018-04-19 | DHI-TRANSMIT-001614 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5349bd6-df58-4fbf-995f-04ee852084b6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7068 | T16182-CA00-P0UBA-186101 | 2018-04-19 | DHI-TRANSMIT-001616 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6ed4fb1-c114-47a5-9bca-f235059a24fc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7069 | T16182-CA00-P0UBA-186104 | 2018-04-19 | DHI-TRANSMIT-001616 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38122b24-aed0-4920-aa07-1cec790f1325 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7070 | T16182-CA01-P0UBA-186152 | 2018-04-19 | DHI-TRANSMIT-001616 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8668efdc-9a15-47ba-9104-159981f3deea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7071 | T16182-CA01-P0UBA-186154 | 2018-04-19 | DHI-TRANSMIT-001616 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8bb9b27-3678-4957-914f-514ee1f9f728 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7072 | T16182-YU02-P0MJ-110507 | 2018-04-19 | DHI-WTRAN-001275 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c08c0958-fcf7-40e3-8cd1-9cd7bbd5a181 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7073 | T16182-DN05-P0SG-136620 | 2018-04-19 | DHI-TRANSMIT-001617 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d229266b-b839-44dd-adf3-695757d89269 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7074 | T16182-YD00-P0SGZ-139731 | 2018-04-19 | DHI-TRANSMIT-001617 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c7e74df-9590-458a-a64c-20d0b945a683 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7075 | T16182-YD00-P0SGZ-139831 | 2018-04-19 | DHI-TRANSMIT-001617 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=834d6a1f-200e-472e-ac99-bc537359ef83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7076 | T16182-CV03-P0CWQ-161134 | 2018-04-19 | DHI-TRANSMIT-001618 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=195a00fb-8b5c-4b2b-8186-6582db8f60b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7077 | T16182-XS00-P0MAG-123010 | 2018-04-19 | DHI-WTRAN-001276 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11c5625b-4047-4ee3-b7d4-74137c6d3a74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7078 | T16182-XG07-P0SAE-134602 | 2018-04-19 | DHI-WTRAN-001277 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b920be5-1615-4c29-a48d-ea4435c610a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7079 | T16182-XH02-P0SAE-134604 | 2018-04-19 | DHI-WTRAN-001277 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9911ad2a-837e-4a7f-8b74-846f2b2c31cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7080 | T16182-XW03-P0SAE-134601 | 2018-04-19 | DHI-WTRAN-001277 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ff322f2-31e9-4984-a986-8a8b3ae5fd78 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7081 | T16182-XW03-P0SAE-134603 | 2018-04-19 | DHI-WTRAN-001277 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61ab03d9-8b9c-4fd6-a39c-7572bf41cad2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7082 | T16182-XG01-P0EKG-124001 | 2018-04-19 | DHI-EMAIL-000423 | IFC | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7083 | T16182-YB11-P0ZEN-152418 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c12eb36-9072-4bae-96ed-d1c5ae9713b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7084 | T16182-YB11-P0ZEN-152414 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=403c0618-f5e5-4ccb-9c30-7014d7049e36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7085 | T16182-YB11-P0ZEN-152404 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c620eacb-d8d4-4811-97bc-7418bf782f26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7086 | T16182-YB11-P0ZEN-152401 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d17e00ee-848c-4a46-b191-0889d69b2693 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7087 | T16182-YB11-P0ZEN-152403 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d03f57a7-b135-4ba4-8f03-f55498a89e87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7088 | T16182-YB11-P0ZEN-152402 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf52d450-a856-4b4c-b4fe-37b62710431d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7089 | T16182-YB11-P0ZEN-152421 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=359041c5-479c-4878-a5c2-40f5ab35a1aa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7090 | T16182-YB11-P0ZEN-152407 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5334ae72-bacc-4ddf-9216-8c4b640ee044 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7091 | T16182-YB11-P0ZEN-152419 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8f1847c-0048-4a7d-b2a3-2d66192e359f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7092 | T16182-YB11-P0ZEN-152408 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b811c53-1b30-4e8e-a973-991f4894b3c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7093 | T16182-YB11-P0ZEN-152405 | 2018-04-23 | DHI-TRANSMIT-001632 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20a99896-8457-436f-97a2-b584f4a710e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7094 | T16182-XF00-P8ZEN-125729 | 2018-04-23 | DHI-TRANSMIT-001633 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09c1a74f-ca12-4656-8cae-b47952487fda | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7095 | T16182-YD00-P8ZEN-125750 | 2018-04-23 | DHI-TRANSMIT-001633 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33116d69-a31b-417c-bb35-40a4b4f7ae52 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7096 | T16182-BV02-P0CJN-290003 | 2018-04-23 | DHI-WTRAN-001278 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e332842-8ca8-417c-803b-a79a35489a14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7097 | T16182-YQ08-P0CY-154039 | 2018-04-23 | DHI-WTRAN-001279 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2420ef0-e1ad-4168-9b7e-3dfd2b229c04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7098 | T16182-YQ08-P0CY-154040 | 2018-04-23 | DHI-WTRAN-001279 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbd4f08c-e9d3-4fa9-bdad-e5cca27151e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7099 | T16182-YQ08-P0CY-154041 | 2018-04-23 | DHI-WTRAN-001279 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edda9f7b-2e6f-4bba-8438-ce1aef93d634 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7100 | T16182-YQ08-P0CY-154042 | 2018-04-23 | DHI-WTRAN-001279 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e66e4c91-7b0b-425e-8904-92f4bccdbc04 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7101 | T16182-YQ08-P0CY-154033 | 2018-04-23 | DHI-TRANSMIT-001634 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f1581a6-b9ef-4769-a37a-c2dab6a637cd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7102 | T16182-YQ08-P0CY-154045 | 2018-04-23 | DHI-TRANSMIT-001634 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c3ed933-7bea-4b4d-8014-925a3ca1c0ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7103 | T16182-YQ08-P0CY-154052 | 2018-04-23 | DHI-TRANSMIT-001634 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5160ae30-fdf8-440d-999e-e03ee4721f52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7104 | T16182-YQ01-P0ZEN-152332 | 2018-04-23 | DHI-WTRAN-001280 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3327409b-0f11-4fa4-b40d-038a76fef8af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7105 | T16182-YT10-P0ZEN-152234 | 2018-04-23 | DHI-WTRAN-001280 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8fc4fbc-383a-4a5e-8c85-37a5b11d5b38 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7106 | T16182-YT10-P0ZEN-152225 | 2018-04-23 | DHI-WTRAN-001280 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2633ef3-fcfb-45ee-8f58-b9453e8a07e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7107 | T16182-YQ01-P0ZEN-152323 | 2018-04-23 | DHI-WTRAN-001280 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcb4da1e-ac92-4c19-9c04-b8cae060b21e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7108 | T16182-YB03-P8ZEN-125761 | 2018-04-23 | DHI-TRANSMIT-001635 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a503356-4f6f-468e-bd92-18bed89562b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7109 | T16182-YL16-P8ZEN-125731 | 2018-04-23 | DHI-TRANSMIT-001635 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3e54bf6-bc1f-4055-8374-54dcb0344ebb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7110 | T16182-YL16-P8ZEN-125760 | 2018-04-23 | DHI-TRANSMIT-001635 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20747c3a-a38b-4c92-957d-db73ef50319e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7111 | T16182-YL00-P8ZEN-125707 | 2018-04-23 | DHI-TRANSMIT-001636 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bb8115b-159e-4c6a-a3d8-8428e0d8d3e5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7112 | T16182-XB02-P0UZA-172904 | 2018-04-23 | DHI-WTRAN-001281 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ddf1a5d1-b564-4cb9-9429-8912ea47cc48 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7113 | T16182-YD00-P0CYE-137341 | 2018-04-23 | DHI-TRANSMIT-001637 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4792471-071e-4638-80a1-93fa099c5771 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7114 | T16182-YU02-P0CYE-137342 | 2018-04-23 | DHI-TRANSMIT-001637 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bc1153a-37ae-42f4-a151-3c4764f0bdeb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7115 | T16182-YD00-P0CYE-137941 | 2018-04-23 | DHI-TRANSMIT-001637 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96aebe2c-ff3f-46d0-9538-abb210910fb8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7116 | T16182-YU02-P0CYE-137942 | 2018-04-23 | DHI-TRANSMIT-001637 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce2a78bb-ef19-495d-80ff-fab493ee82f1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7117 | T16182-XJ00-P0QCA-140221 | 2018-04-23 | DHI-WTRAN-001282 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=225e9418-3711-486c-8da7-c3e2df67ec4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7118 | T16182-XJ00-P0PGB-140209 | 2018-04-23 | DHI-TRANSMIT-001638 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fff1b5a-dfa2-40d6-a388-c8f80c12f3a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7119 | T16182-XJ00-P0GKB-140212 | 2018-04-23 | DHI-TRANSMIT-001638 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c586e315-ac26-4b46-adc3-37081f6fd3a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7120 | T16182-XJ00-P0GHC-140213 | 2018-04-23 | DHI-TRANSMIT-001638 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5336a26d-7388-4c54-be08-1806dd64dd18 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7121 | T16182-XK00-P0MAG-123027 | 2018-04-24 | DHI-WTRAN-001283 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1da2138b-cdf4-48f5-ad10-2c10c2279f4d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7122 | T16182-YT10-P0CYE-137943 | 2018-04-24 | DHI-WTRAN-001284 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf90a372-09bb-42ba-80a9-4f3411ba4bea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7123 | T16182-XG02-P0SGK-139602 | 2018-04-24 | DHI-TRANSMIT-001640 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4f43429-2f8f-4244-a105-a262a251cc94 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7124 | T16182-XH01-P0SGK-139612 | 2018-04-24 | DHI-TRANSMIT-001640 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9fa078b4-6046-4384-980a-0da992bde938 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7125 | T16182-YT01-P0CYE-136618 | 2018-04-24 | DHI-TRANSMIT-001640 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2660d616-22a0-4c31-9318-724a693de7db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7126 | T16182-YU02-P0CYE-136742 | 2018-04-24 | DHI-TRANSMIT-001640 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=670d3a30-26de-4172-968c-840aaf4a3408 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7127 | T16182-XH02-P0SAV-135104 | 2018-04-24 | DHI-TRANSMIT-001641 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31ef599a-5877-45bf-b64e-b88880bcbfb6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7128 | T16182-XH02-P0SAF-134704 | 2018-04-24 | DHI-TRANSMIT-001642 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2660c3e8-9c0d-4582-8b54-8113d37dced8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7129 | T16182-XW03-P0SAF-134701 | 2018-04-24 | DHI-TRANSMIT-001642 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8911663-cc40-4721-94e5-9f5762d7c16d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7130 | T16182-XW03-P0SAF-134703 | 2018-04-24 | DHI-TRANSMIT-001642 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03b5bed5-0ac0-4bd4-afc5-8c92701720b0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7131 | T16182-YD04-P0ZEN-152013 | 2018-04-24 | DHI-TRANSMIT-001643 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0733034-5b59-4c30-bd57-0d79e1117470 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7132 | T16182-XW03-P0SAE-135401 | 2018-04-25 | DHI-TRANSMIT-001646 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aaaa2b0d-f22c-43bf-b607-521de4a2f4d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7133 | T16182-XG07-P0SAE-135402 | 2018-04-25 | DHI-TRANSMIT-001646 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d363807a-62de-4410-b325-f3cc9a508fc8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7134 | T16182-XW03-P0SAE-135403 | 2018-04-25 | DHI-TRANSMIT-001646 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=232071c8-3bf2-4a54-bac3-6eeb94d722c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7135 | T16182-XH02-P0SAE-135404 | 2018-04-25 | DHI-TRANSMIT-001646 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c5f25ac-067a-40e1-9cf6-1aeededadc23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7136 | T16182-YD00-P0BAT-150621 | 2018-04-25 | DHI-WTRAN-001285 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d9efc11-fe40-4f47-b8a7-0245371fe348 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7137 | T16182-YD00-P0BAT-150626 | 2018-04-25 | DHI-WTRAN-001285 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cea7452-171e-4647-8291-8b1c3d9ec207 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7138 | T16182-YD00-P0BBT-150671 | 2018-04-25 | DHI-WTRAN-001285 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf6b0ad7-5681-47f5-ba4c-d7a683237d64 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7139 | T16182-YQ01-P0ZEN-152316 | 2018-04-25 | DHI-TRANSMIT-001647 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3df692f6-e7f1-4b31-9836-4961469bd977 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7140 | T16182-YT10-P0ZEN-152212 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30b5bd15-0a18-4ef4-b338-b64610fa6bbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7141 | T16182-YQ01-P0ZEN-152313 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7e99f5c-cb18-45b6-b885-db8857e0bcf3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7142 | T16182-YQ01-P0ZEN-152310 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d04d64c2-a09e-44fa-96e4-aa143fbe33c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7143 | T16182-YT10-P0ZEN-152215 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1c78353-5339-4a82-8c33-c763977bd809 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7144 | T16182-YT10-P0ZEN-152213 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af0f4593-e928-4f95-a629-faf0ebfe9702 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7145 | T16182-YB11-P0ZEN-152411 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2050a0a3-360a-4006-900b-20016f28a589 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7146 | T16182-YQ01-P0ZEN-152311 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e9600ab-b5b2-43b2-a379-88394371377c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7147 | T16182-YB11-P0ZEN-152409 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e5462663-c52e-40d9-972b-f3de9fe34ea8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7148 | T16182-YT10-P0ZEN-152211 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=013c63f7-a899-49ab-8832-d8885fe8c088 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7149 | T16182-YT10-P0ZEN-152214 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8482f6d6-f87f-4a58-a66f-0ad44050e1a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7150 | T16182-YQ01-P0ZEN-152312 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=668fdf27-1e5d-41d1-a318-9969d81ccef5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7151 | T16182-YQ01-P0ZEN-152309 | 2018-04-25 | DHI-WTRAN-001286 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99647a7d-72c8-42be-928b-80a6d9caf653 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7152 | T16182-YD00-P0UCA-150501 | 2018-04-25 | DHI-TRANSMIT-001648 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=352b0f57-4fa6-4def-afda-aeece786f197 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7153 | T16182-YD00-P0MBA-121001 | 2018-04-26 | DHI-TRANSMIT-001656 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef5bf10f-5101-48a7-a31e-b0d6f44b985f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7154 | T16182-XG07-P0ZEN-120050 | 2018-04-26 | DHI-TRANSMIT-001657 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e2d436b-1d67-46a3-adf8-6629a488c70c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7155 | T16182-YT01-P0SAA-136003 | 2018-04-26 | DHI-WTRAN-001287 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f78b3847-e98b-4ebd-831e-d42bb34cf1e0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7156 | T16182-YD02-P0SAC-163417 | 2018-04-26 | DHI-TRANSMIT-001658 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df1c5460-ba36-413f-97cb-9a69337bae43 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7157 | T16182-YD02-P0SAC-163418 | 2018-04-26 | DHI-TRANSMIT-001658 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ddcda0ea-4f3c-4794-a420-35ca0865ce1a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7158 | T16182-YD02-P0SAC-163421 | 2018-04-26 | DHI-TRANSMIT-001658 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b1d95ee-6b7a-4f74-995f-a1fde7f9ee21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7159 | T16182-CA05-P0UYA-183181 | 2018-04-27 | DHI-TRANSMIT-001659 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=022b3930-1f3b-4e71-a7fb-fd1d65fb527d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7160 | T16182-CA05-P0UYA-183182 | 2018-04-27 | DHI-TRANSMIT-001659 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=724eec9a-8e5e-416e-bb65-7e16e839e884 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7161 | T16182-CA05-P0UYA-183183 | 2018-04-27 | DHI-TRANSMIT-001659 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d440a79f-e181-401a-a9a1-c660984725dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7162 | T16182-YD00-P0SGZ-139131 | 2018-04-27 | DHI-WTRAN-001288 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=103b56eb-c5fe-471e-a6a9-e7c67ed9440c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7163 | T16182-YD00-P0SGZ-139231 | 2018-04-27 | DHI-WTRAN-001288 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5cd824c2-ebb1-4ecb-bffc-709f50480fc8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7164 | T16182-YD00-P0SGZ-139331 | 2018-04-27 | DHI-WTRAN-001288 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3ec2ce5-9615-40b1-bb3a-28b61cc18fa0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7165 | T16182-XH01-P0SGK-136713 | 2018-04-27 | DHI-TRANSMIT-001660 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc852d8d-7997-4975-94e8-00422d08394b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7166 | T16182-YT10-P0SGK-136723 | 2018-04-27 | DHI-TRANSMIT-001660 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0f941d8-380e-47e7-9e55-ce16564b69ed | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7167 | T16182-XS00-P0SG-136602 | 2018-04-27 | DHI-TRANSMIT-001660 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e7f37e2-02b6-410b-949e-7314c7d0e473 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7168 | T16182-XH01-P0SGK-138618 | 2018-04-27 | DHI-TRANSMIT-001660 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f4dcd06-83be-408e-a1cc-ba6268fa4adb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7169 | T16182-YE03-P0BAU-152513 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b32106a-b9e6-4322-a7c4-a578f2effde8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7170 | T16182-YE03-P0BAU-152514 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb188053-1007-4017-88a4-9c401b85cb3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7171 | T16182-YE03-P0BAU-152515 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57f6c9e7-a1cf-45b9-9b6a-5d135cbae571 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7172 | T16182-YE03-P0BAU-152516 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b6a1640-89c4-4646-b740-951cfa4a0b9b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7173 | T16182-YE03-P0BAU-152517 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc334f19-ccc2-4ec9-b512-d4dcf34917d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7174 | T16182-YE03-P0BAU-152519 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dc882c0-5f79-4f4f-8929-88355bdd5982 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7175 | T16182-YE03-P0BAU-152520 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa56dd7b-f4e8-48b3-b3f2-b6110e973e61 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7176 | T16182-YE03-P0BAU-152529 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f00760a9-5aa6-4481-b2a6-998a7609fa3e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7177 | T16182-YE03-P0BAU-152537 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2af8bf69-a64b-477b-916e-36adfb6cd95b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7178 | T16182-YE03-P0BAU-152504 | 2018-04-27 | DHI-TRANSMIT-001661 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cc2e122-771a-465f-8a20-c0f9904dec57 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7179 | T16182-YE03-P0BAU-152540 | 2018-04-27 | DHI-WTRAN-001289 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6708559-cb92-42f0-81d8-634ec729a2dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7180 | T16182-XW03-P0SAN-134401 | 2018-04-27 | DHI-TRANSMIT-001662 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2f5a6a9-e789-4a2c-9b98-cdd8ca20310b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7181 | T16182-XG07-P0SAN-134402 | 2018-04-27 | DHI-TRANSMIT-001662 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2ce32be-2c8e-4dab-8b69-c7ef4453a537 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7182 | T16182-XW03-P0SAN-134403 | 2018-04-27 | DHI-TRANSMIT-001662 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3176d701-8251-4e36-bf67-3afdc7881488 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7183 | T16182-XH02-P0SAN-134404 | 2018-04-27 | DHI-TRANSMIT-001662 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d222a7c1-d518-4c5d-b729-026aeaca66fa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7184 | T16182-VE04-P0UZT-173001 | 2018-04-27 | DHI-WTRAN-001290 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16e943f6-17b8-41dc-9ca7-a5bc3ba3579b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7185 | T16182-XB02-P0UZT-173002 | 2018-04-27 | DHI-WTRAN-001290 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc15fd9f-35b5-4032-8aeb-16e99373f958 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7186 | T16182-XB02-P0UZT-173003 | 2018-04-27 | DHI-WTRAN-001290 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58d9c786-6ba3-44f6-bae7-e4dca427e2e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7187 | T16182-VK02-P0UZT-173008 | 2018-04-27 | DHI-WTRAN-001290 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d880190-337b-4cce-a459-133c54c16007 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7188 | T16182-CA06-P0UYF-183600 | 2018-04-27 | DHI-WTRAN-001291 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98184f44-401b-4072-8f52-50a9f662d67d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7189 | T16182-DN05-P0SG-136620 | 2018-05-02 | DHI-TRANSMIT-001665 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=058fa460-e9a6-40ec-9853-e8a79485acfc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7190 | T16182-YD02-P0SAC-163409 | 2018-05-02 | DHI-TRANSMIT-001666 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdb3d834-e6e7-4cd3-8c18-516616451a83 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7191 | T16182-XG02-P0SGC-137201 | 2018-05-02 | DHI-TRANSMIT-001668 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfe56cb1-97fa-4b32-a2ce-0a25988d3f63 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7192 | T16182-XG02-P0SGC-139901 | 2018-05-02 | DHI-TRANSMIT-001668 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb160928-0537-4e8a-a354-038a79c64f4d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7193 | T16182-XH01-P0SGC-137211 | 2018-05-02 | DHI-TRANSMIT-001668 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da1eba83-36b2-4f5a-b95e-5adca51d9e20 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7194 | T16182-XH01-P0SGC-139911 | 2018-05-02 | DHI-TRANSMIT-001668 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=407e00c7-3282-463e-ae0b-6234b860b454 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7195 | T16182-YD00-P0CYE-139241 | 2018-05-02 | DHI-WTRAN-001293 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43d23c86-22ff-4868-9d93-6d7463a75c61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7196 | T16182-YD00-P0CYE-139341 | 2018-05-02 | DHI-WTRAN-001293 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9508b22-f3f1-4da6-ae12-dd88a245e875 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7197 | T16182-YU02-P0CYE-139242 | 2018-05-02 | DHI-WTRAN-001293 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ab69b6d-bdd9-45be-96a4-a79a68f4d844 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7198 | T16182-YU02-P0CYE-139342 | 2018-05-02 | DHI-WTRAN-001293 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa476a29-c9a4-4bcd-8af5-ced38891ae3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7199 | T16182-XG02-P0CYE-137944 | 2018-05-02 | DHI-TRANSMIT-001669 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76572e60-b7cc-4420-a74f-9536b779bce1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7200 | T16182-XH01-P0SGK-138712 | 2018-05-02 | DHI-TRANSMIT-001669 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=930ec63d-2aba-47b7-84ec-fddc561860b6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7201 | T16182-YT10-P0SGK-139622 | 2018-05-02 | DHI-TRANSMIT-001669 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c92cb2b-8a1b-4847-854e-c4ba3c690e28 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7202 | T16182-CV03-P0CWQ-161134 | 2018-05-02 | DHI-TRANSMIT-001670 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae8cbb51-9032-4502-aa99-a10826ebcd38 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7203 | T16182-YQ08-P0CY-154036 | 2018-05-02 | DHI-WTRAN-001294 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da6fcd5e-4afe-47b4-9fb9-fa09ddbf8fe5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7204 | T16182-YQ08-P0CY-154044 | 2018-05-02 | DHI-WTRAN-001294 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37d42f00-3898-4987-b7d2-4e8b3b0fea76 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7205 | T16182-YQ08-P0CY-154037 | 2018-05-02 | DHI-TRANSMIT-001671 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adca8944-3c00-4f27-bcf8-052d3f43b047 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7206 | T16182-YQ08-P0CY-154049 | 2018-05-02 | DHI-TRANSMIT-001671 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=270d0ad7-2360-4ab6-81bc-5af85fae57ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7207 | T16182-YD04-P0ZEN-152017 | 2018-05-03 | DHI-TRANSMIT-001675 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd79f877-f7a7-4480-b40e-74a748089d4f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7208 | T16182-YQ01-P0ZEN-152319 | 2018-05-03 | DHI-TRANSMIT-001676 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bd3b841-dc79-4dc4-8ea6-8f4bbd697b98 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7209 | T16182-CM01-P6MAA-220205 | 2018-05-03 | DHI-WTRAN-001295 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=addc3592-db2e-4400-9e38-c796c63e3d54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7210 | T16182-CM01-P7MAA-220206 | 2018-05-03 | DHI-WTRAN-001295 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f4dd2bc-d8ab-4029-8777-5cc860bedfa5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7211 | T16182-XG07-P0ZEN-120050 | 2018-05-04 | DHI-EMAIL-000442 | IFC | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7212 | T16182-XB02-P0UZJ-173202 | 2018-05-04 | DHI-TRANSMIT-001678 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8da42f2e-6392-4f7e-b2f3-5ed787b54b22 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7213 | T16182-VK02-P0UZJ-173208 | 2018-05-04 | DHI-TRANSMIT-001678 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bae03a2-db00-4b1d-afa7-ea2b9ae47ab7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7214 | T16182-VK02-P0UZJ-173209 | 2018-05-04 | DHI-TRANSMIT-001678 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae338249-f955-4906-8e37-81850f95bcc4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7215 | T16182-YD00-P0CYE-136641 | 2018-05-04 | DHI-WTRAN-001296 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54857235-e29b-4b8c-97cb-7b3733b36a7f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7216 | T16182-YU02-P0CYE-136642 | 2018-05-04 | DHI-WTRAN-001296 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2f60126-df38-4e34-bbc1-3fffffc164d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7217 | T16182-YK08-P0LCM-420040 | 2018-05-04 | DHI-TRANSMIT-001679 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06aa88fb-588f-48dd-aae1-6a6127afea20 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7218 | T16182-YK08-P0LCM-420030 | 2018-05-04 | DHI-TRANSMIT-001680 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33a192b0-1964-4031-b7f4-219046853b5e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7219 | T16182-CA00-P0UBA-181001 | 2018-05-04 | DHI-TRANSMIT-001681 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ebf7da6-00ca-46f2-b656-1cc7a4e79a42 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7220 | T16182-CA00-P0UBA-181101 | 2018-05-04 | DHI-TRANSMIT-001681 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dde22e72-a2a5-4972-9bdc-9f0afc86a385 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7221 | T16182-XS00-P8QHA-125002 | 2018-05-04 | DHI-TRANSMIT-001682 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a2bd75b-0bbb-428e-b383-7c3a44c107fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7222 | T16182-VE04-P0UZA-172901 | 2018-05-04 | DHI-TRANSMIT-001683 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1ceacbb-ec39-4618-af1c-2f79955fac61 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7223 | T16182-VK02-P0UZA-172908 | 2018-05-04 | DHI-TRANSMIT-001683 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8094a19d-dd0b-42dd-908f-7f682719e6cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7224 | T16182-XB02-P0UZA-172902 | 2018-05-04 | DHI-TRANSMIT-001683 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=935804b1-0716-4b56-b111-1c43ea2a675a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7225 | T16182-XB02-P0UZA-172903 | 2018-05-04 | DHI-TRANSMIT-001683 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbe3b3a2-3f03-4f02-947d-66de2f724919 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7226 | T16182-XB02-P0UZA-172904 | 2018-05-04 | DHI-TRANSMIT-001683 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1df5fec1-ccbf-4dd3-a15b-3e9f0929cad5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7227 | T16182-YD02-P0ZEN-165517 | 2018-05-08 | DHI-TRANSMIT-001684 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfc8d9f0-9c68-482b-aeb7-655b699abb05 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7228 | T16182-DE00-P0ZEN-152830 | 2018-05-08 | DHI-TRANSMIT-001685 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=286273a6-3bdf-49c5-a69b-22ccf8b4e202 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7229 | T16182-DP00-P0ZEN-020004 | 2018-05-08 | DHI-TRANSMIT-001686 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da1b31c6-9ac7-47b5-ab57-14a44fe87d96 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7230 | T16182-XS00-P0MAG-123004 | 2018-05-08 | DHI-TRANSMIT-001687 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be060ded-533d-410b-b89e-6ffb1ee6356b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7231 | T16182-XG02-P0GKB-120001 | 2018-05-09 | DHI-TRANSMIT-001688 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b22961cc-e426-4d54-935c-29cbeaf2fe04 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7232 | T16182-XG02-P0GKC-120002 | 2018-05-09 | DHI-TRANSMIT-001688 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f598c412-4ac0-497c-9f10-2876cf6cc464 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7233 | T16182-VE04-P0UZT-173001 | 2018-05-09 | DHI-WTRAN-001297 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8ae493d-d1eb-4a50-ace4-05fe0b816bca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7234 | T16182-VK02-P0UZT-173008 | 2018-05-09 | DHI-WTRAN-001297 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c11bb59-a45b-46ed-b267-4dc9fd1f2816 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7235 | T16182-XB02-P0UZT-173002 | 2018-05-09 | DHI-WTRAN-001297 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1c11fe1-7a91-44c9-af1a-987222b967e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7236 | T16182-XB02-P0UZT-173003 | 2018-05-09 | DHI-WTRAN-001297 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b19ad183-b90f-4543-b76c-c24a5721cbf9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7237 | T16182-YK00-P0ZEN-165303 | 2018-05-09 | DHI-TRANSMIT-001689 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afaffb1f-06bf-42c2-adea-87579b06e410 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7238 | T16182-XH01-P0LF-140420 | 2018-05-10 | DHI-TRANSMIT-001690 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aaa2e9e0-4359-4cba-af2a-d4a348a5ef5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7239 | T16182-CA00-P0UGD-181914 | 2018-05-10 | DHI-TRANSMIT-001691 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c5d2603-23c4-4b22-b710-03eccd4ca8f9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7240 | T16182-YE00-P0ZEN-152710 | 2018-05-10 | DHI-WTRAN-001319 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72d68cb0-924c-4021-a951-05a95998705b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7241 | T16182-XB02-P0ULX-171603 | 2018-05-10 | DHI-TRANSMIT-001692 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=949614e5-b4ed-48d0-9aaf-455d02bc138c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7242 | T16182-YD00-P0MJ-110504 | 2018-05-10 | DHI-TRANSMIT-001693 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ff444bb-6c57-403a-a2a6-074d08fd314a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7243 | T16182-YE00-P0MJ-110512 | 2018-05-10 | DHI-TRANSMIT-001693 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74cf8439-1798-4a73-b77d-bbd711609da7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7244 | T16182-YK08-P0MJ-110506 | 2018-05-10 | DHI-TRANSMIT-001693 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1955709-207c-4806-adf6-023ddf6bf6c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7245 | T16182-XB02-P8UTH-172003 | 2018-05-10 | DHI-TRANSMIT-001694 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95213331-0442-446c-980b-b362e152994e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7246 | T16182-XB02-P8UTH-172004 | 2018-05-10 | DHI-TRANSMIT-001694 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3897f488-2edc-48c4-8178-82d13e6d60c1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7247 | T16182-XG02-P0LBS-110006 | 2018-05-10 | DHI-TRANSMIT-001695 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0bb9629-f807-4f27-bf48-6acc78610ae5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7248 | T16182-XG01-P0EKG-124001 | 2018-05-11 | DHI-TRANSMIT-001696 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f5d0be2-aa66-4501-8daf-ec7eb6f0ff83 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7249 | T16182-YQ01-P0ZEN-152301 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e2edbd5-f043-4349-9881-e8f97bf543f9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7250 | T16182-YQ01-P0ZEN-152304 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e01cc7b5-3a6d-4bfc-86b6-428064438e4f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7251 | T16182-YQ01-P0ZEN-152305 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3f02cca-b890-4815-b325-70558198c0db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7252 | T16182-YQ01-P0ZEN-152315 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e8de8b-76d5-4b81-939a-188d270aee9d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7253 | T16182-YQ01-P0ZEN-152323 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40753301-721f-4934-b50a-46ea3b55c273 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7254 | T16182-YQ01-P0ZEN-152302 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e901fed-486a-4bd0-bbab-c75b26af3d76 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7255 | T16182-YQ01-P0ZEN-152303 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d048f329-767d-4cd6-9061-d827a917dfeb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7256 | T16182-YB11-P0ZEN-152415 | 2018-05-11 | DHI-TRANSMIT-001697 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6db111a-484b-49a7-bac0-aa8673d9f42c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7257 | T16182-XG01-P6MAA-220089 | 2018-05-11 | DHI-WTRAN-001322 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de9af87d-cda1-4b2d-8743-c8fd903b18c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7258 | T16182-XG01-P7MAA-220090 | 2018-05-11 | DHI-WTRAN-001322 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f48bcd77-70ee-4076-9bbe-6e22ae83722a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7259 | T16182-YT02-P6CJJ-220293 | 2018-05-11 | DHI-WTRAN-001322 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b63b8000-bef3-4917-86ef-3b07b057a854 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7260 | T16182-YT02-P7CJJ-220294 | 2018-05-11 | DHI-WTRAN-001322 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2ef9247-b39a-47d5-9977-9521670a211e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7261 | T16182-XJ00-P0GKB-140112 | 2018-05-11 | DHI-TRANSMIT-001698 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42f248f3-5ea7-43d3-adcb-73442a6ee30a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7262 | T16182-XJ00-P0PGB-140109 | 2018-05-11 | DHI-TRANSMIT-001698 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7df604c-355a-46c5-91a8-45ef68616397 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7263 | T16182-YQ01-P0ZEN-152324 | 2018-05-11 | DHI-WTRAN-001323 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59abfd6c-003f-4110-8750-70b7f0725bb4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7264 | T16182-YT10-P0ZEN-152226 | 2018-05-11 | DHI-WTRAN-001323 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=864741fa-e113-4efc-ae78-9d09ed28f5bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7265 | T16182-CA00-P0UBA-181001 | 2018-05-11 | DHI-TRANSMIT-001699 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e91d647-411a-4e67-8238-2db620335c84 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7266 | T16182-CA00-P0UBA-181101 | 2018-05-11 | DHI-TRANSMIT-001699 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a68dd194-789d-40d7-80aa-c8ec32fa8aee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7267 | T16182-UB01-P0EKG-124075 | 2018-05-11 | DHI-TRANSMIT-001700 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f8c24ee-9bd7-4d10-8e31-2f0b3ef2905d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7268 | T16182-XH01-P0SGC-137111 | 2018-05-11 | DHI-TRANSMIT-001701 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7951b64-1d26-4077-bd42-b72ad47d79ca | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7269 | T16182-YT01-P0SGA-136609 | 2018-05-11 | DHI-TRANSMIT-001701 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=995b77fe-2002-4ddb-b851-3e145328c0e3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7270 | T16182-XB02-P0GUB-173302 | 2018-05-11 | DHI-TRANSMIT-001702 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c02247b-9966-446f-9d74-9b6626ffac09 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7271 | T16182-XB02-P0GUB-173303 | 2018-05-11 | DHI-TRANSMIT-001702 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c81b4a9-f93e-41dc-9c1e-695817cd2927 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7272 | T16182-VK02-P0GUB-173313 | 2018-05-11 | DHI-TRANSMIT-001702 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1b96bc6-4ec1-40f6-9a0f-35c44758e339 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7273 | T16182-CC08-P8QHB-125151 | 2018-05-14 | DHI-WTRAN-001324 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0335d305-9b33-4018-8c29-b5e0509119f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7274 | T16182-CC02-P8QHB-125164 | 2018-05-14 | DHI-TRANSMIT-001703 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f78c098-a18f-4567-869f-719dbfc1f69b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7275 | T16182-XG02-P0GM-120008 | 2018-05-14 | DHI-TRANSMIT-001704 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e94a5335-d5e2-41e3-a100-4c3ed5875c6b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7276 | T16182-XB02-P0UAZ-172608 | 2018-05-14 | DHI-TRANSMIT-001705 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0d2159c-8d3e-4fd8-ad91-57a08e9ed41b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7277 | T16182-XJ00-P0GM-140224 | 2018-05-14 | DHI-TRANSMIT-001706 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94f5c04e-a11b-4cdb-8fdb-8eceb098ac2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7278 | T16182-XJ00-P0QCA-140221 | 2018-05-14 | DHI-TRANSMIT-001706 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=521cbb34-c091-4b07-8b16-c540b36f6a14 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7279 | T16182-XB02-P0GUB-173302 | 2018-05-15 | DHI-TRANSMIT-001715 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58bef045-b72f-4f09-a54f-3233d0b02308 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7280 | T16182-XB02-P0GUB-173303 | 2018-05-15 | DHI-TRANSMIT-001715 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d938ddb9-b4f9-490f-8092-b01652bae203 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7281 | T16182-XH02-P0SAQ-135204 | 2018-05-15 | DHI-TRANSMIT-001716 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5ebefce-39ca-46da-b112-b7d4294fadbd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7282 | T16182-XW03-P0SAQ-135201 | 2018-05-15 | DHI-TRANSMIT-001716 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a335a5ac-5e57-4c37-ad2e-af081b3768ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7283 | T16182-XW03-P0SAQ-135203 | 2018-05-15 | DHI-TRANSMIT-001716 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=388ed54e-524f-409e-994c-8ca13c50537e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7284 | T16182-YT01-P0SAA-136003 | 2018-05-15 | DHI-TRANSMIT-001717 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d9f522b-acbd-433d-acac-45f44ff992af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7285 | T16182-YD00-P0QU-130402 | 2018-05-15 | DHI-TRANSMIT-001718 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec9ca321-318b-4f6d-ab5f-83ca387a3b8e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7286 | T16182-YE00-P0ZEN-152711 | 2018-05-15 | DHI-TRANSMIT-001719 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55f6b288-2ea1-4ec5-a93e-20fb285691bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7287 | T16182-XG02-P0SGA-136603 | 2018-05-16 | DHI-TRANSMIT-001722 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8779fbc-f426-4425-b414-c564a150b433 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7288 | T16182-XH01-P0SGE-137312 | 2018-05-16 | DHI-TRANSMIT-001722 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b71e4b5-0602-4d70-8126-b00d589113b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7289 | T16182-YD00-P0SGZ-137331 | 2018-05-16 | DHI-TRANSMIT-001722 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b081e302-5c39-4a76-9701-70fc3ebbba5b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7290 | T16182-CA00-P0QJA-184801 | 2018-05-17 | DHI-TRANSMIT-001723 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05434835-856e-4fb8-b9b3-cdb9c69561d9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7291 | T16182-CA00-P0QJA-184802 | 2018-05-17 | DHI-TRANSMIT-001723 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdf7855b-9b89-4ec7-8ca3-2f89c88b3f2b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7292 | T16182-CA00-P0QJA-184803 | 2018-05-17 | DHI-TRANSMIT-001723 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c537bae8-c90a-4ec4-bcc5-9e2b93c6708e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7293 | T16182-CA01-P0QJA-184852 | 2018-05-17 | DHI-TRANSMIT-001723 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a4b11c3-435d-46a4-aec4-5d1187405a08 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7294 | T16182-CA01-P0QJA-184853 | 2018-05-17 | DHI-TRANSMIT-001723 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e5369c-db04-4780-b6e5-67b48d89f444 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7295 | T16182-CA00-P0GEN-185801 | 2018-05-17 | DHI-TRANSMIT-001724 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78ca73c7-ecf2-4c93-b382-e822a5323213 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7296 | T16182-CA00-P0GEN-185802 | 2018-05-17 | DHI-TRANSMIT-001724 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c4afdc8-08f7-4e74-a069-1d3de0c3b9a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7297 | T16182-CA00-P0GEN-185803 | 2018-05-17 | DHI-TRANSMIT-001724 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91651fcd-a27c-4749-9e6b-64d5e980b369 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7298 | T16182-CA00-P0UTG-184901 | 2018-05-17 | DHI-TRANSMIT-001725 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76b2facd-6c45-4817-8dbc-be0de72ba816 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7299 | T16182-CA00-P0UTG-184902 | 2018-05-17 | DHI-TRANSMIT-001725 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e3855d9-a593-4a7c-a3d5-e1db5e688b50 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7300 | T16182-CA00-P0UTG-184903 | 2018-05-17 | DHI-TRANSMIT-001725 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6e116a4-b368-49c4-8541-9e6509c3bf09 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7301 | T16182-CA01-P0UTG-184952 | 2018-05-17 | DHI-TRANSMIT-001725 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21b05b7f-3d16-40d4-92c7-7173f3bdf3c3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7302 | T16182-CA01-P0UTG-184953 | 2018-05-17 | DHI-TRANSMIT-001725 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1bd5e28b-87ab-41e1-9e9a-d0c4eac3e095 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7303 | T16182-YL08-P6MAA-220207 | 2018-05-17 | DHI-WTRAN-001326 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f24de2b0-b227-44fb-a469-ea817e64a1ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7304 | T16182-YQ02-P0ZEN-152001 | 2018-05-17 | DHI-TRANSMIT-001726 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c22dbc5-d5a7-4c57-8ff3-c20b66693754 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7305 | T16182-YQ01-P0ZEN-152314 | 2018-05-17 | DHI-TRANSMIT-001727 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20d3852d-e1e3-4687-a9f2-82a075113e9f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7306 | T16182-YB11-P0ZEN-152406 | 2018-05-17 | DHI-WTRAN-001327 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbf981a5-896a-48c6-8040-25f906e5bdc6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7307 | T16182-YQ01-P0ZEN-152306 | 2018-05-17 | DHI-WTRAN-001327 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d928984-b031-44c7-b839-1de0b03aa546 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7308 | T16182-YT10-P0ZEN-152208 | 2018-05-17 | DHI-WTRAN-001327 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51cabd14-5121-4ae6-8328-a1d04993dd73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7309 | T16182-XW03-P0SAD-134501 | 2018-05-17 | DHI-WTRAN-001328 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e57801ef-8900-4f90-bf80-4714a1b18695 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7310 | T16182-XG07-P0SAD-134502 | 2018-05-17 | DHI-WTRAN-001328 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b7a2f18-4d21-4851-84be-cb7a8e2eb663 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7311 | T16182-XW03-P0SAD-134503 | 2018-05-17 | DHI-WTRAN-001328 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5aaef381-6e70-4673-b7df-12688d090269 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7312 | T16182-XH02-P0SAD-134504 | 2018-05-17 | DHI-WTRAN-001328 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33477d27-1d26-4a18-8ae7-f3188f218e74 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7313 | T16182-XG02-P0SGA-139301 | 2018-05-17 | DHI-WTRAN-001329 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7897c347-df2a-4312-82b4-1c980fada658 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7314 | T16182-XH01-P0SGA-139311 | 2018-05-17 | DHI-WTRAN-001329 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=288479f3-ef8b-4fd4-b631-0992e5bd44c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7315 | T16182-YD00-P0CYE-139041 | 2018-05-17 | DHI-TRANSMIT-001728 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c65dfe0-b9b1-422d-9031-035405af995a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7316 | T16182-YU02-P0CYE-139042 | 2018-05-17 | DHI-TRANSMIT-001728 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae314d97-3cc0-4cc3-8817-8f5dbacdcc7c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7317 | T16182-YK09-P0SMQ-128024 | 2018-05-17 | DHI-TRANSMIT-001729 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f834cbf4-058b-4fdf-81bb-8d354bf234b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7318 | T16182-XJ00-P0LCA-140206 | 2018-05-17 | DHI-WTRAN-001330 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74642766-124c-4a9a-b86a-265abb15ff28 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7319 | T16182-UT01-P0GQB-173402 | 2018-05-17 | DHI-TRANSMIT-001730 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=512da6f4-5e0e-4c4b-97a6-452193598703 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7320 | T16182-UT01-P0GQB-173403 | 2018-05-17 | DHI-TRANSMIT-001730 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd80c08f-f163-414e-809d-c1dfc7e4ea42 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7321 | T16182-YD00-P0EKG-124009 | 2018-05-17 | DHI-WTRAN-001331 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=247b9a03-dd83-4b2b-b998-cfa0607a4de9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7322 | T16182-VE04-P0UZT-173001 | 2018-05-17 | DHI-TRANSMIT-001731 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60f03278-6c57-4ef0-8288-80fc267ad88a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7323 | T16182-VK02-P0UZT-173008 | 2018-05-17 | DHI-TRANSMIT-001731 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d310d04-9c8b-448b-822d-885b737e12a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7324 | T16182-XB02-P0UZT-173002 | 2018-05-17 | DHI-TRANSMIT-001731 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=766958df-c624-4e8f-bf8f-1245a97a0745 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7325 | T16182-XB02-P0UZT-173003 | 2018-05-17 | DHI-TRANSMIT-001731 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43dafebd-4b06-4e2b-9987-17ab1142c374 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7326 | T16182-YT01-P0MBA-121023 | 2018-05-18 | DHI-WTRAN-001332 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7327 | T16182-CA05-P0UGD-181986 | 2018-05-18 | DHI-TRANSMIT-001732 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92997769-96a5-42e1-a281-40c1b037c3e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7328 | T16182-YQ01-P0ZEN-152322 | 2018-05-18 | DHI-TRANSMIT-001733 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1503a1ce-0742-4dec-9a56-431b43cb141a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7329 | T16182-YQ01-P0ZEN-152332 | 2018-05-18 | DHI-TRANSMIT-001733 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8793b63b-2143-47e0-9ef2-cb6f875a69ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7330 | T16182-XB02-P0GUB-173302 | 2018-05-18 | DHI-TRANSMIT-001734 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7093a956-75bb-4cbc-a478-df6192a3185c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7331 | T16182-XB02-P0GUB-173303 | 2018-05-18 | DHI-TRANSMIT-001734 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e07f653d-9af7-415a-99cd-3a96e45a9490 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7332 | T16182-XH01-P0SGC-137011 | 2018-05-18 | DHI-TRANSMIT-001735 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79c2f040-ae51-4846-8d79-43061cf65b05 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7333 | T16182-XJ00-P0GHC-140113 | 2018-05-18 | DHI-TRANSMIT-001736 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bae14468-d346-4f9b-a8ce-c50e2e404ade | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7334 | T16182-XJ00-P0LBG-140204 | 2018-05-18 | DHI-TRANSMIT-001736 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c75ff94c-a184-4b1b-81c6-7601bf254cbf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7335 | T16182-XJ00-P0QJA-140223 | 2018-05-18 | DHI-TRANSMIT-001736 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a632bd85-9566-4101-ac0f-46ab4755a874 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7336 | T16182-XJ00-P0SCA-140210 | 2018-05-18 | DHI-TRANSMIT-001736 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffe49134-d802-4f93-9a0d-76bcba4d8ba9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7337 | T16182-CA06-P0UYF-183600 | 2018-05-18 | DHI-WTRAN-001333 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62d3bf53-4081-496c-bd92-203c62e8dfe3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7338 | T16182-CV03-P0CWQ-161135 | 2018-05-18 | DHI-TRANSMIT-001737 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60696091-e187-4cdd-a709-1d7330fce4d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7339 | T16182-VN03-P0LB-122015 | 2018-05-23 | DHI-TRANSMIT-001739 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3d5e391-db91-4061-beaf-4a1229962820 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7340 | T16182-YT10-P0MKY-290010 | 2018-05-23 | DHI-WTRAN-001334 | IFR | E | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31af2339-6687-4526-a049-a362d3d80d0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7341 | T16182-XJ00-P0GHC-140213 | 2018-05-23 | DHI-TRANSMIT-001740 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05828ef5-96f5-4419-9266-569e1521d71f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7342 | T16182-XJ00-P0GKB-140212 | 2018-05-23 | DHI-TRANSMIT-001740 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27f735ec-8fe6-40c4-a138-7eff56ac2428 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7343 | T16182-XL00-P0STG-130503 | 2018-05-24 | DHI-TRANSMIT-001741 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=558d4b5b-18fe-42ea-9623-c996aefd2f91 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7344 | T16182-XW01-P0STG-130501 | 2018-05-24 | DHI-WTRAN-001335 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9d9c2a5-fc67-41cf-9b9f-4ed478ed6ea0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7345 | T16182-YD02-P0ZEN-165518 | 2018-05-24 | DHI-TRANSMIT-001742 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6aa6cce-2778-405a-b340-a14292af2cf0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7346 | T16182-YK00-P0ZEN-165314 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4475c068-118c-49b7-b10d-4046bdb6e2f7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7347 | T16182-YK00-P0ZEN-165315 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4557a015-d7e0-47a3-9944-86cdca57e7f1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7348 | T16182-YK00-P0ZEN-165316 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81c262dd-cd78-440b-aabc-e0e8b0137e41 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7349 | T16182-YK00-P0ZEN-165317 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac8f5dac-69a0-4d74-a0a8-6dddc973680b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7350 | T16182-YK00-P0ZEN-165318 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9aae59e-2699-4ab6-a252-7a57d1137c0a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7351 | T16182-YK00-P0ZEN-165319 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd8e8b8b-fea1-45b4-903a-5b46bcd57903 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7352 | T16182-YK00-P0ZEN-165320 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7af5de1c-69b3-441e-b1dd-d060d46de137 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7353 | T16182-YK00-P0ZEN-165321 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daa09789-b731-41e3-a144-44141bedadb2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7354 | T16182-YK00-P0ZEN-165322 | 2018-05-24 | DHI-TRANSMIT-001743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8769dc41-567a-41c1-8c48-3df80fe9372c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7355 | T16182-YD00-P0CYE-137741 | 2018-05-25 | DHI-TRANSMIT-001745 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffaa1679-917f-466f-a9e6-dd77fb7a1282 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7356 | T16182-YF00-P0SAY-163405 | 2018-05-25 | DHI-WTRAN-001336 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c202d6b-c8b7-4316-98cd-f9a03df893c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7357 | T16182-VK02-P0UZJ-173209 | 2018-05-25 | DHI-TRANSMIT-001746 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0187aa15-3713-421e-ab24-daa266d3f25e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7358 | T16182-VK02-P0UZT-172713 | 2018-05-25 | DHI-TRANSMIT-001747 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3308e59a-a6d4-4ad1-9512-a87d3714a3a5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7359 | T16182-XB02-P0UZT-172716 | 2018-05-25 | DHI-TRANSMIT-001747 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bba90b1a-09df-4499-855b-d5483f457eaa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7360 | T16182-YD04-P0ZEN-152010 | 2018-05-25 | DHI-TRANSMIT-001748 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=119075dd-d235-456c-bd0b-b303d00e7809 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7361 | T16182-XB02-P0UEG-171502 | 2018-05-25 | DHI-TRANSMIT-001749 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=578c8f7e-e657-49e9-bcef-669fc06443fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7362 | T16182-XB02-P0UEG-171504 | 2018-05-25 | DHI-TRANSMIT-001749 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=429f239c-32f2-4b2c-b36d-5ccc15c03808 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7363 | T16182-YQ08-P0CY-154036 | 2018-05-25 | DHI-TRANSMIT-001750 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15b98d2c-ce6a-4adc-b67d-4a602246e568 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7364 | T16182-CM01-P6MAA-220205 | 2018-05-25 | DHI-WTRAN-001337 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=201d9cea-abdb-4247-9d76-c99d8bca8aca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7365 | T16182-CM01-P7MAA-220206 | 2018-05-25 | DHI-WTRAN-001337 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ba995a1-cd1f-407e-9aa4-4034673653a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7366 | T16182-XH01-P0LD-130213 | 2018-05-25 | DHI-TRANSMIT-001751 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acd98330-87e5-42f1-b765-3b448708b23e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7367 | T16182-XG07-P0SAE-134602 | 2018-05-25 | DHI-TRANSMIT-001752 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e131a349-132e-4747-9d6c-745041da0e37 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7368 | T16182-XH02-P0SAE-134604 | 2018-05-25 | DHI-TRANSMIT-001752 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ed3d6e7-e780-4a4d-a323-0478b4bbd150 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7369 | T16182-XW03-P0SAE-134601 | 2018-05-25 | DHI-TRANSMIT-001752 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a49a923-64bc-40ee-a121-596acded901d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7370 | T16182-XW03-P0SAE-134603 | 2018-05-25 | DHI-TRANSMIT-001752 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86eb861c-80d5-4aee-8b52-ad72a705ca6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7371 | T16182-CA06-P0UYF-183600 | 2018-05-25 | DHI-TRANSMIT-001753 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6641cb70-a2b7-4c23-94b6-b64d343a6846 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7372 | T16182-XJ00-P0EKC-140117 | 2018-05-25 | DHI-TRANSMIT-001754 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28075f43-9c1d-4e53-b0ee-35a5769219fa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7373 | T16182-XJ00-P0MBH-140116 | 2018-05-25 | DHI-TRANSMIT-001754 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ead7777a-c6ad-4947-9098-ef6b6dd239a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7374 | T16182-XJ00-P0PGB-140209 | 2018-05-25 | DHI-TRANSMIT-001754 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7931eb27-7ab4-4a2b-aba3-c1d8a1426e9c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7375 | T16182-XJ00-P0QFB-140211 | 2018-05-25 | DHI-TRANSMIT-001754 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c98f553-ab8f-4b6f-af5d-3392dc8b0205 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7376 | T16182-YD00-P0BF-150933 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bee08eb-4f26-4c80-bd8f-a534d20ac4c4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7377 | T16182-YD00-P0BF-150934 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa6e0545-59b4-43f5-bf88-10f431bbe55d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7378 | T16182-YD00-P0BF-150935 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfebf796-193b-4ac5-8b14-a5c67888a106 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7379 | T16182-YD00-P0BF-150936 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4543ae9d-2b45-415b-9b07-980a5fbaa4f6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7380 | T16182-YD00-P0BF-150937 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=197c5861-30a7-4995-b5af-6e59a76ce0a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7381 | T16182-YD00-P0BF-150938 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=798c3ac5-12d6-41b9-97ef-0cb4cb9f3b31 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7382 | T16182-YD00-P0BF-150931 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1921007a-90ec-472b-85dc-de35973416c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7383 | T16182-YD00-P0BF-150932 | 2018-05-25 | DHI-WTRAN-001338 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d73aa1f-fd47-42e8-96ca-8148b4e32861 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7384 | T16182-YU02-P0BFA-150911 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea72ebc6-7cd7-4fb6-9e09-2d365b2b29db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7385 | T16182-YU02-P0BFA-150912 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bacaa21f-9270-4299-b526-22515efc4fe2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7386 | T16182-YU02-P0BFA-150913 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c97e96f5-10fc-4087-be1b-d560af0f0387 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7387 | T16182-YU02-P0BFA-150914 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2de6da19-e0ca-4ec1-a21d-c8e5143a4dfa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7388 | T16182-YU02-P0BFA-150915 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b094c27-dd2f-47d7-99ee-aaa492d5bcbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7389 | T16182-YU02-P0BFA-150916 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e0b9815-bde3-485c-8bf7-ca5edff95ab4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7390 | T16182-YU02-P0BFA-150917 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=609d3ed9-65f9-4aba-a94a-d737cd7c80eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7391 | T16182-YU02-P0BFA-150918 | 2018-05-25 | DHI-WTRAN-001339 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3da0b33c-fd9f-47b4-9666-c081e20c3f55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7392 | T16182-YD00-P8ZEN-125728 | 2018-05-25 | DHI-WTRAN-001340 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80cabec8-340d-436d-bb1f-64c39b86e086 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7393 | T16182-YB11-P0ZEN-152422 | 2018-05-28 | DHI-TRANSMIT-001755 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2071a30-4e9f-49d5-a1cc-946d585836ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7394 | T16182-YB11-P0ZEN-152427 | 2018-05-28 | DHI-TRANSMIT-001755 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3df0c513-bbc8-4655-886c-9a075a1e93ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7395 | T16182-YQ01-P0ZEN-152327 | 2018-05-28 | DHI-TRANSMIT-001755 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bc97019-b7cb-468d-9540-f258081935e2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7396 | T16182-YD00-P0SMG-128030 | 2018-05-28 | DHI-TRANSMIT-001756 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fe78ceb-774f-44dc-a982-32c7ae210405 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7397 | T16182-YD00-P0SMG-128051 | 2018-05-28 | DHI-TRANSMIT-001756 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e1777aa-d324-4430-a2f2-7756fecc6e19 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7398 | T16182-YD00-P0SMU-128032 | 2018-05-28 | DHI-TRANSMIT-001756 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3110c93d-2b2f-4076-8717-bd1d86e07ce3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7399 | T16182-XB02-P0UNX-171402 | 2018-05-28 | DHI-TRANSMIT-001757 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=30c3bd7d-b25e-4893-8a97-e37600677ec1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7400 | T16182-XB02-P0UNX-171403 | 2018-05-28 | DHI-TRANSMIT-001757 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=137ff2d5-7202-4cb9-a45c-5301ca797210 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7401 | T16182-XB02-P0UNX-171410 | 2018-05-28 | DHI-TRANSMIT-001757 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3e18a1a-69e0-4e12-bc8d-d8a4c26e1972 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7402 | T16182-YF00-P0PCA-126522 | 2018-05-28 | DHI-WTRAN-001341 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebec19d9-0519-4765-b367-a547d1d71d39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7403 | T16182-VK02-P0UZA-172908 | 2018-05-28 | DHI-TRANSMIT-001758 | IFC | 4 | D | TRUE | FALSE | 2018-05-28_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67b07d08-44c9-4ee7-a94a-8ec024bf490d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7404 | T16182-YD00-P0EKG-124009 | 2018-05-28 | DHI-WTRAN-001342 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d176a6b-1bbc-4463-997b-13ebd1aa8cf7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7405 | T16182-YT01-P0SGX-136616 | 2018-05-28 | DHI-TRANSMIT-001759 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce0955fc-4609-4bc7-8f97-d28d75faf0e2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7406 | T16182-VK02-P0UGF-173107 | 2018-05-29 | DHI-TRANSMIT-001763 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d10f29a5-0b3e-4086-9d9f-8d6bb97ac560 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7407 | T16182-XB02-P0UGF-173101 | 2018-05-29 | DHI-TRANSMIT-001763 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41057463-e555-48b7-8bae-108a8ea75c82 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7408 | T16182-XB02-P0UGF-173102 | 2018-05-29 | DHI-TRANSMIT-001763 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=626c60d1-972b-41fc-93a8-44cf6bfe8343 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7409 | T16182-CC00-P8QHA-125101 | 2018-05-29 | DHI-TRANSMIT-001764 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1787761-a228-42ff-9aad-539610024bac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7410 | T16182-CV03-P8ZEN-125601 | 2018-05-29 | DHI-TRANSMIT-001765 | IFC | 1 | D | TRUE | FALSE | 2018-05-29_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6dc8a10-90a3-4fc9-817b-4ce38652918c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7411 | T16182-YL13-P6MAA-220143 | 2018-05-30 | DHI-WTRAN-001343 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7412 | T16182-YD02-P0ZEN-165510 | 2018-05-30 | DHI-WTRAN-001344 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab807850-c3a3-4a40-ba40-e0c7bc583ada | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7413 | T16182-XG02-P0LBA-110003 | 2018-05-30 | DHI-TRANSMIT-001766 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b8a8458-8594-4d84-b3f5-5665d6ebe140 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7414 | T16182-XH01-P0SGK-138712 | 2018-05-30 | DHI-TRANSMIT-001767 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba174fd4-3c28-4303-98fb-daedcb5d6b29 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7415 | T16182-XH01-P0LF-140405 | 2018-05-30 | DHI-TRANSMIT-001768 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b37be095-2201-41f3-9999-26c006011a73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7416 | T16182-YF02-P6CJJ-220275 | 2018-05-30 | DHI-WTRAN-001345 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0684406a-6df1-4612-b9b1-10585fa6b405 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7417 | T16182-YF02-P7CJJ-220276 | 2018-05-30 | DHI-WTRAN-001345 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4b6003c-02f3-4eb6-848d-6ee14ead49f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7418 | T16182-YV02-P6CJJ-220277 | 2018-05-30 | DHI-WTRAN-001345 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc0c606a-cce3-45ea-a3e8-bdb8b46391c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7419 | T16182-YV02-P7CJJ-220278 | 2018-05-30 | DHI-WTRAN-001345 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9a72b77-4b26-4611-8f28-f6a75f9e67f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7420 | T16182-CV03-P0LD-130219 | 2018-05-31 | DHI-WTRAN-001346 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c9e5c17-d38a-4737-96a3-3bd7f5a401b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7421 | T16182-YT01-P0LD-130214 | 2018-05-31 | DHI-WTRAN-001346 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b14b8385-0637-4756-8366-776ed1941ac6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7422 | T16182-XG02-P0LD-130204 | 2018-05-31 | DHI-TRANSMIT-001769 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cde66d8b-ca4a-4dc6-ab7d-c039c37b9c70 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7423 | T16182-YD00-P8ZEN-125728 | 2018-05-31 | DHI-TRANSMIT-001770 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc933b16-7c48-49cf-8529-9c73023518ab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7424 | T16182-CA00-P0UBA-181001 | 2018-05-31 | DHI-TRANSMIT-001771 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6794d940-feca-43b9-b54f-6378a33b8989 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7425 | T16182-CA00-P0UBA-181101 | 2018-05-31 | DHI-TRANSMIT-001771 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df6d5c93-05fc-4b0e-a546-8657f197d595 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7426 | T16182-YL01-P8ZEN-125703 | 2018-06-01 | DHI-WTRAN-001347 | IFI | 2 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7427 | T16182-CA03-P0HBD-189002 | 2018-06-01 | INT-IFC-180601-01 | INTERNAL IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f88dc96a-56e5-4b42-a7ed-ba2cb4cdb7de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7428 | T16182-VE04-P0UZT-173001 | 2018-06-01 | DHI-TRANSMIT-001775 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1bae0ec0-f472-4c87-b2a5-025df8a6d10a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7429 | T16182-XB02-P0UZT-173002 | 2018-06-01 | DHI-TRANSMIT-001775 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=720c747f-6a7c-4b7e-9118-88afbebb9f75 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7430 | T16182-XB02-P0UZT-173003 | 2018-06-01 | DHI-TRANSMIT-001775 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20a927d7-35b5-4e22-a9cc-fb1bb5e8b2bf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7431 | T16182-VK02-P0UZT-173008 | 2018-06-01 | DHI-TRANSMIT-001775 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d79acba0-3ecf-4b54-a401-91f1274ec1e5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7432 | T16182-YD00-P0SGZ-139131 | 2018-06-01 | DHI-TRANSMIT-001776 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1428266-8f57-4203-90b8-8f3f7dd3f56b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7433 | T16182-YD00-P0SGZ-139231 | 2018-06-01 | DHI-TRANSMIT-001776 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f6ca7b54-6f46-411d-b473-8016b33be60f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7434 | T16182-YD00-P0SGZ-139331 | 2018-06-01 | DHI-TRANSMIT-001776 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b250fa33-76ee-4782-8934-7e772dd123c7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7435 | T16182-XH01-P0SGK-138812 | 2018-06-01 | DHI-TRANSMIT-001777 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bccd3be-a711-486e-b435-2001c287aa94 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7436 | T16182-CV03-P8ZEN-125604 | 2018-06-01 | DHI-TRANSMIT-001778 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f778914-8268-4312-9a80-905e1a5ef37c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7437 | T16182-CV03-P8ZEN-125609 | 2018-06-01 | DHI-TRANSMIT-001778 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e59fa56-19c8-4de2-98f4-1c93956ae483 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7438 | T16182-XA00-P8QHL-125402 | 2018-06-01 | DHI-TRANSMIT-001778 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28aaeea4-5529-4410-a753-f87fb39a0785 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7439 | T16182-XH02-P8QHL-125400 | 2018-06-01 | DHI-TRANSMIT-001778 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74054283-3b21-4b18-9c58-312aa8875d0b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7440 | T16182-XK00-P8ZEN-125509 | 2018-06-01 | DHI-TRANSMIT-001778 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d48c5e66-d3ec-478a-8a80-e9673001c2dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7441 | T16182-XW03-P8ZEN-125014 | 2018-06-01 | DHI-TRANSMIT-001778 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b242831-53ce-41d3-8379-d9e3676c9c90 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7442 | T16182-CA03-P0UMY-185169 | 2018-06-01 | DHI-TRANSMIT-001779 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe62d570-bf77-4e51-88d9-7e463b5e8a3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7443 | T16182-CA03-P0UMY-185175 | 2018-06-01 | DHI-TRANSMIT-001779 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a1dd2c9-833d-4981-aeb9-b36f041a2765 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7444 | T16182-YT10-P0SGC-137021 | 2018-06-01 | DHI-TRANSMIT-001780 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ac5abab-d317-4a68-9168-769795a88f23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7445 | T16182-YT10-P0SGC-137121 | 2018-06-01 | DHI-TRANSMIT-001780 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=678e7e2c-0189-4b22-87d0-817731c6ec94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7446 | T16182-YU02-P0CYE-139142 | 2018-06-01 | DHI-WTRAN-001348 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea17f124-e27f-4f5b-a8b1-4be20d31ce4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7447 | T16182-YT10-P0CYE-139143 | 2018-06-01 | DHI-WTRAN-001348 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36010c96-efcb-4422-be58-b2fbe4c6bd94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7448 | T16182-YD00-P0CYE-139141 | 2018-06-01 | DHI-WTRAN-001348 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23804f2f-2429-4d62-92ca-256d98aeb893 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7449 | T16182-XG02-P0CYE-139144 | 2018-06-01 | DHI-WTRAN-001348 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c82db3fa-1048-4882-b7f7-b1ab7283f075 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7450 | T16182-VN01-P0MAG-123050 | 2018-06-01 | DHI-WTRAN-001349 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=771db95e-c6a3-4923-9a08-14bce3237192 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7451 | T16182-BP00-P0LBC-140012 | 2018-06-01 | DHI-WTRAN-001350 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3286a47-0318-4273-815e-c05fb21de0f8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7452 | T16182-BP00-P0LBG-140016 | 2018-06-01 | DHI-WTRAN-001350 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99c3506a-6b9b-402a-bbf3-b545623faf59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7453 | T16182-YF00-P8ZEN-125710 | 2018-06-01 | DHI-WTRAN-001351 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d268174-5cbd-4b2c-9d3e-8a20fc5790f3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7454 | T16182-YK10-P8QHA-125308 | 2018-06-01 | DHI-WTRAN-001352 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c10b103c-2669-436a-9909-35832d7faa39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7455 | T16182-XS00-P0MAG-123005 | 2018-06-01 | DHI-WTRAN-001353 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73af437c-9065-40bc-b927-e01346a39aac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7456 | T16182-YL00-P0MAG-123031 | 2018-06-01 | DHI-WTRAN-001353 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2db83ea-f046-4c8b-a6f7-ffa3a6d8d90d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7457 | T16182-YT01-P0MAG-123038 | 2018-06-01 | DHI-WTRAN-001354 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=033e4e13-6f2b-4b1a-b6cd-3b977af7089c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7458 | T16182-CV03-P8SGK-125650 | 2018-06-01 | DHI-WTRAN-001355 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46316129-4fe2-4482-b1fb-e5f9d5dbb3b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7459 | T16182-VN01-P0MAG-123045 | 2018-06-04 | INT-IFC-180604-01 | INTERNAL IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4d88ad2-05a2-4e27-afe8-6f13eb006efc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7460 | T16182-CA00-P0ULD-183902 | 2018-06-04 | DHI-TRANSMIT-001781 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71641fcb-a696-4d9c-ad7f-36a1a9d1978d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7461 | T16182-YK00-P0ZEN-165303 | 2018-06-04 | DHI-TRANSMIT-001782 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24307e49-ada8-446a-95ad-a73d4e74e3ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7462 | T16182-YK08-P0ZEN-020008 | 2018-06-04 | DHI-WTRAN-001356 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b88037fd-1498-4990-b83b-4b8af1c24816 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7463 | T16182-YL00-P0LB-122079 | 2018-06-04 | DHI-TRANSMIT-001783 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41831bfb-57af-482e-92ab-768c0c2ff947 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7464 | T16182-YL01-P0MAG-123034 | 2018-06-05 | DHI-WTRAN-001357 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7465 | T16182-XW03-P0SAM-135001 | 2018-06-05 | DHI-TRANSMIT-001784 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34dfa8a0-235c-46a3-952e-8734643a7b68 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7466 | T16182-XG07-P0SAM-135002 | 2018-06-05 | DHI-TRANSMIT-001784 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62216548-8bfe-4a08-8193-d2df924018f0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7467 | T16182-XW03-P0SAM-135003 | 2018-06-05 | DHI-TRANSMIT-001784 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0762e96d-563c-40d0-8d55-77c82134b4e9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7468 | T16182-XH02-P0SAM-135004 | 2018-06-05 | DHI-TRANSMIT-001784 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e42c384a-9aa7-4f6e-84e8-1c561aad4e7f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7469 | T16182-VK02-P0GUB-173313 | 2018-06-05 | DHI-TRANSMIT-001785 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61b6cba6-4cc7-49e6-855d-807ca3c4c422 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7470 | T16182-XJ00-P8ZEN-125520 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bc9d394-7777-47a4-b401-a27c7e0fa958 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7471 | T16182-XJ00-P8ZEN-125521 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06845ad9-8027-4101-adbc-ea2beba5fd8f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7472 | T16182-XJ00-P8ZEN-125522 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ed5f521-8383-49af-815b-38c079d2e7d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7473 | T16182-XJ00-P8ZEN-125523 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52f2e31b-0901-42ab-9102-66a55dcbf65b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7474 | T16182-XJ00-P8ZEN-125524 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54d492eb-f52f-4cd9-9eb1-af8cc8fd175d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7475 | T16182-XJ00-P8ZEN-125525 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0255cc91-c311-4a74-a768-53cc81bc1ab4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7476 | T16182-XJ00-P8ZEN-125526 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b22e7627-891d-41f6-b5a6-d3200f94b932 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7477 | T16182-XJ00-P8ZEN-125527 | 2018-06-05 | DHI-TRANSMIT-001786 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fce8ff5-911e-420c-9ece-be7d415c19f4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7478 | T16182-XJ00-P6MKA-260003 | 2018-06-05 | DHI-TRANSMIT-001787 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c5f6521-968d-45c1-b8fe-1b4cb5ca2944 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7479 | T16182-XJ00-P7MKA-260006 | 2018-06-05 | DHI-TRANSMIT-001787 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aea63bcc-951d-4df3-a9e7-df667177bae5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7480 | T16182-YD00-P0CYE-139341 | 2018-06-05 | DHI-TRANSMIT-001788 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8dc531b9-d40f-4ec3-b308-b94fb5936757 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7481 | T16182-YU02-P0CYE-139342 | 2018-06-05 | DHI-TRANSMIT-001788 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aeeb1c5f-40c8-4d0b-8a52-73b7d1bd296b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7482 | T16182-YD00-P0CYE-136641 | 2018-06-05 | DHI-TRANSMIT-001788 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd346f12-3f41-4ee6-b26d-01412c462fae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7483 | T16182-YU02-P0CYE-136642 | 2018-06-05 | DHI-TRANSMIT-001788 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e7b5541-fdb9-424a-a0e8-f15436f4c2b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7484 | T16182-YD00-P0CYE-139241 | 2018-06-05 | DHI-TRANSMIT-001788 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eccd4de8-c5da-4e82-bb75-1110bd902619 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7485 | T16182-YU02-P0CYE-139242 | 2018-06-05 | DHI-TRANSMIT-001788 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71aa96fb-1201-440a-816d-94ac43081e3b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7486 | T16182-YE03-P0BAU-152504 | 2018-06-05 | DHI-TRANSMIT-001789 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adbfb42b-b2d5-4d12-8766-5b7048117fc4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7487 | T16182-XB02-P0UZA-172904 | 2018-06-14 | DHI-TRANSMIT-001791 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68dc66a8-3f94-4a3f-a9b4-cfc8208b541c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7488 | T16182-XG11-P0MJ-110564 | 2018-06-14 | DHI-WTRAN-001358 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83126a15-583c-46ea-a06d-e5e3fe8e6274 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7489 | T16182-YM02-P0MJ-110561 | 2018-06-14 | DHI-WTRAN-001358 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cceeffdc-a1cc-4e00-b8af-772cbdab7712 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7490 | T16182-YT10-P0MJ-110568 | 2018-06-14 | DHI-WTRAN-001358 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a23db539-05fb-42eb-952e-d67ad8fe454e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7491 | T16182-BV02-P0CJN-290003 | 2018-06-14 | DHI-WTRAN-001359 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7492 | T16182-YD00-P0UBA-150504 | 2018-06-14 | DHI-TRANSMIT-001792 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e595cd7-74d1-4c1f-873e-b9c950e99522 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7493 | T16182-YD00-P0CYE-138241 | 2018-06-14 | DHI-TRANSMIT-001793 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d058f643-303f-4452-9f24-50c3fcc306bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7494 | T16182-YT10-P0SGK-138722 | 2018-06-14 | DHI-TRANSMIT-001793 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3caaac5e-085b-4e38-87ae-61082c278d0a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7495 | T16182-YT10-P0SGK-138822 | 2018-06-14 | DHI-TRANSMIT-001793 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d34640c3-646d-4362-9056-c9867dbe194b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7496 | T16182-XJ00-P0LBC-140202 | 2018-06-14 | DHI-WTRAN-001360 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=568d7e59-3566-48b7-a63b-9817075c94a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7497 | T16182-XJ00-P0LBG-140203 | 2018-06-14 | DHI-WTRAN-001360 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ab7eb0b-6aa4-4b9d-a57b-56926e89d407 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7498 | T16182-CV03-P8SGK-125650 | 2018-06-14 | DHI-WTRAN-001361 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d5a1ebc-c594-4d52-8ea0-b9384169ac28 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7499 | T16182-YD00-P0CYE-138341 | 2018-06-14 | DHI-TRANSMIT-001794 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b1aa782-a634-4843-8e30-89c5d0ab51a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7500 | T16182-XG07-P0SAL-134002 | 2018-06-14 | DHI-TRANSMIT-001795 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75b4b217-d7eb-4fcb-92cd-a6b913863e60 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7501 | T16182-XH02-P0SAL-134004 | 2018-06-14 | DHI-TRANSMIT-001795 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a086def-acc0-4624-92c6-44fb5d8df5b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7502 | T16182-XW03-P0SAL-134001 | 2018-06-14 | DHI-TRANSMIT-001795 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bee8382-e8b4-44c2-bf5f-112f38e0dc98 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7503 | T16182-XW03-P0SAL-134003 | 2018-06-14 | DHI-TRANSMIT-001795 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d398bee4-8131-4b56-b3b4-5408b68d7f4d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7504 | T16182-XG07-P0SAD-134502 | 2018-06-14 | DHI-TRANSMIT-001796 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1767379a-b92c-43ac-bf48-5e3a034b969d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7505 | T16182-XH02-P0SAD-134504 | 2018-06-14 | DHI-TRANSMIT-001796 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bf2704a-c5f3-4e5c-a90b-b09f7299c2ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7506 | T16182-XW03-P0SAD-134501 | 2018-06-14 | DHI-TRANSMIT-001796 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=617b2074-10ac-48d1-a057-8d0ff9ca583d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7507 | T16182-XW03-P0SAD-134503 | 2018-06-14 | DHI-TRANSMIT-001796 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=864cff26-20f2-4105-9611-53f9e0b5c99d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7508 | T16182-XB02-P0GCF-130042 | 2018-06-14 | DHI-TRANSMIT-001797 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=592246a2-65d8-42f1-a892-b0635ff3b13b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7509 | T16182-XG02-P0GCF-130004 | 2018-06-14 | DHI-TRANSMIT-001797 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c22b411-aec2-4e29-bc49-2c1abf6b272b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7510 | T16182-XG02-P0GNR-130103 | 2018-06-14 | DHI-TRANSMIT-001797 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8470361a-a5ca-46ae-85f3-52863cb05b8b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7511 | T16182-VK02-P0UGF-173107 | 2018-06-14 | DHI-TRANSMIT-001798 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bb54613a-f732-4c34-9b60-f38db763aa48 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7512 | T16182-XB02-P0UGF-173101 | 2018-06-14 | DHI-TRANSMIT-001798 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b89b1333-0e9d-431d-bc51-414379ebfbd7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7513 | T16182-XB02-P0UGF-173102 | 2018-06-14 | DHI-TRANSMIT-001798 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c6747b7-22ba-4444-a37b-21c2da89f78b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7514 | T16182-XG02-P0SGE-137303 | 2018-06-14 | DHI-TRANSMIT-001799 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce1832bf-1fb4-4918-b996-4e9a30dc618b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7515 | T16182-XH01-P0SGA-137711 | 2018-06-14 | DHI-TRANSMIT-001799 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e10a6bc9-54a7-4396-a124-f4e781bf5801 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7516 | T16182-XH01-P0SGA-138011 | 2018-06-14 | DHI-TRANSMIT-001799 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9b21d56-1b2f-4a26-92e3-192c2344daec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7517 | T16182-VK02-P0UAZ-172613 | 2018-06-14 | DHI-TRANSMIT-001800 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60a8e308-450f-40db-89e2-e01f8fac6d15 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7518 | T16182-YD00-P0BAA-150766 | 2018-06-14 | DHI-WTRAN-001362 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d75a7d12-3293-441b-9b3c-50e0c01d1be9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7519 | T16182-XG07-P0SAR-134202 | 2018-06-15 | DHI-TRANSMIT-001803 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5fff8a6-96da-4b8f-979c-30729c6964d0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7520 | T16182-XH02-P0SAR-134204 | 2018-06-15 | DHI-TRANSMIT-001803 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc6a32ea-6eb2-4918-b7e9-2507a2b11e09 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7521 | T16182-XW03-P0SAR-134203 | 2018-06-15 | DHI-TRANSMIT-001803 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a70cae51-240d-4e17-b1a6-de130c90db91 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7522 | T16182-XG02-P0SGA-139101 | 2018-06-15 | DHI-WTRAN-001363 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ba522a5-4c57-41ad-91ed-85f176d63403 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7523 | T16182-XG02-P0SGK-139103 | 2018-06-15 | DHI-WTRAN-001363 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52891b14-6a08-4d5a-bcdf-62871ba62e7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7524 | T16182-XH01-P0SGE-138612 | 2018-06-15 | DHI-TRANSMIT-001804 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4d3cdba-f64b-4524-ab42-e18b72891875 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7525 | T16182-YD02-P0SAC-163415 | 2018-06-15 | DHI-WTRAN-001364 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58d65e0c-2ea3-4333-ac69-6515a92b6cb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7526 | T16182-VK02-P0UZJ-173208 | 2018-06-15 | DHI-TRANSMIT-001805 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b7bbe0c-4529-4509-9241-e6f47c5ccc06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7527 | T16182-VK02-P0UZJ-173209 | 2018-06-15 | DHI-TRANSMIT-001805 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2b1d6a6-b368-4927-8a2a-dd4a5bb5cbfc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7528 | T16182-XB02-P0UBN-172202 | 2018-06-15 | DHI-TRANSMIT-001806 | IFC | 5 | D | TRUE | FALSE | 2018-06-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=826584e2-6aa2-462a-9899-47a6ce84efbe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7529 | T16182-YU02-P0CYE-138242 | 2018-06-15 | DHI-TRANSMIT-001807 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e1061aa-e068-4f65-a176-f77119eeebd4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7530 | T16182-YU02-P0CYE-138342 | 2018-06-15 | DHI-TRANSMIT-001807 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eecd491e-314d-49e7-a9eb-f2b3b51cca62 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7531 | T16182-YU03-P0BB-150831 | 2018-06-15 | DHI-WTRAN-001365 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b15f340-5859-4df6-80d1-bddd8eaacb56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7532 | T16182-YF00-P0BB-150402 | 2018-06-15 | DHI-TRANSMIT-001808 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d8e759b-5b80-4d5e-a596-0a2a12ea4a88 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7533 | T16182-XG07-P0SAB-134802 | 2018-06-15 | DHI-TRANSMIT-001809 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b9cc2d1-e8ff-4862-ad50-ec1575392ab1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7534 | T16182-XH02-P0SAB-134804 | 2018-06-15 | DHI-TRANSMIT-001809 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ed993fc-c302-4b3d-bb94-4cb48afd8df4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7535 | T16182-XB02-P0GKC-173602 | 2018-06-15 | DHI-TRANSMIT-001810 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d9b3c5e-7bf2-48e7-9ba0-2cb0ffc129ce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7536 | T16182-YQ01-P0ZEN-152330 | 2018-06-15 | DHI-TRANSMIT-001811 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc89ac1d-8e35-43cd-b8cd-3cd6f9d4ce30 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7537 | T16182-YQ01-P0ZEN-152331 | 2018-06-15 | DHI-TRANSMIT-001811 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0616fa8a-1e8b-4924-b833-4d1beeb76acd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7538 | T16182-YK08-P0ZEN-020008 | 2018-06-18 | DHI-TRANSMIT-001812 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2774bf2d-28ff-4de2-8c4b-e1fc5467306f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7539 | T16182-YD00-P0CWQ-161401 | 2018-06-18 | DHI-TRANSMIT-001813 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7de9eb8b-86e9-4a1f-943d-8b5c32ae1e60 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7540 | T16182-YD00-P0CWQ-161402 | 2018-06-18 | DHI-TRANSMIT-001813 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8f29c23-48a5-4876-b597-155f84f6bc69 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7541 | T16182-YD00-P0CWQ-161405 | 2018-06-18 | DHI-TRANSMIT-001813 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=455e2ecf-8602-4afd-86ec-9f4ea31a6c5d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7542 | T16182-YD00-P0CWQ-161406 | 2018-06-18 | DHI-TRANSMIT-001813 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=772d6251-df18-4cd7-907d-52ba78c62086 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7543 | T16182-YD00-P0CWQ-161407 | 2018-06-18 | DHI-TRANSMIT-001813 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4981c09-90cc-4e2f-9b8c-7477b31ea871 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7544 | T16182-YD00-P0CWQ-161408 | 2018-06-18 | DHI-TRANSMIT-001813 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c41dbef-13f9-457f-b6bf-bb14f8d7106b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7545 | T16182-YD00-P0CWQ-161409 | 2018-06-18 | DHI-TRANSMIT-001813 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45c841e3-a9ac-425d-9973-ff48e40d8513 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7546 | T16182-XJ00-P0EKC-140217 | 2018-06-18 | DHI-WTRAN-001366 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26c58ce5-b3e1-4368-ab26-cb33e9ae2c5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7547 | T16182-YD02-P0ZEN-165501 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d3cbb81-98b3-4776-a107-dce22f43b4fc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7548 | T16182-YD02-P0ZEN-165516 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f1f9355-0a7a-468a-95e8-fe024176b142 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7549 | T16182-YD02-P0ZEN-165525 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=091a1140-9f01-4b13-9d14-c081754e71e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7550 | T16182-YD02-P0ZEN-165526 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90ae9e61-67ca-4694-b843-7b2f9a52e95e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7551 | T16182-YD02-P0ZEN-165527 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12fcc4b4-2cf5-4b72-88f5-75eff5390189 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7552 | T16182-YD02-P0ZEN-165528 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=485bb0f9-b605-4622-b348-03e031255ca1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7553 | T16182-YD02-P0ZEN-165529 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1898aaff-8804-4efe-a8af-94a1c2bea679 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7554 | T16182-YD02-P0ZEN-165571 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63e381f7-bbcf-42b2-aac9-b2acea61c05c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7555 | T16182-YD02-P0ZEN-165572 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ef4d7c7-e9ed-49ef-a9be-de9886478885 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7556 | T16182-YD02-P0ZEN-165573 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bd9331e-5440-4ec7-9b3b-9d8f181bfcde | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7557 | T16182-YD02-P0ZEN-165575 | 2018-06-19 | DHI-TRANSMIT-001814 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef588a32-265b-4627-8669-eaf0212fcd8f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7558 | T16182-XW01-P0LB-122046 | 2018-06-19 | DHI-WTRAN-001367 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08677334-99f5-4872-915f-4bae89694f32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7559 | T16182-YT10-P0ZEN-150311 | 2018-06-20 | DHI-TRANSMIT-001815 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0826786d-6abc-4f2a-b46e-5c6290498872 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7560 | T16182-YT10-P0ZEN-150314 | 2018-06-20 | DHI-TRANSMIT-001815 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc7dee0d-fd6b-4171-bf67-50aa5b4cd18c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7561 | T16182-XH02-P0SAN-134404 | 2018-06-20 | DHI-TRANSMIT-001816 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd3a4d06-9dca-4bd5-bd20-74b4bea47b19 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7562 | T16182-CA03-P0ULA-182153 | 2018-06-20 | DHI-TRANSMIT-001817 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=393c426a-ec20-4714-9774-5edbb9fe2b4e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7563 | T16182-YE00-P0ZEN-152791 | 2018-06-20 | DHI-WTRAN-001368 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=356a9785-0658-4b5f-9649-2c938da857f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7564 | T16182-YE00-P0ZEN-152793 | 2018-06-20 | DHI-WTRAN-001368 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c2f3fe5-2888-4e53-8649-a1be9aac4dbc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7565 | T16182-XH02-P0SAF-134704 | 2018-06-20 | DHI-TRANSMIT-001818 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3e67957-9499-43bb-8833-4fbef6094061 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7566 | T16182-UT01-P0GQB-173413 | 2018-06-21 | DHI-TRANSMIT-001819 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36fca73a-33f8-4b38-99fb-44cfe5edf2a6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7567 | T16182-YT01-P0MAJ-123012 | 2018-06-21 | DHI-WTRAN-001369 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d2c6763-43f5-4262-9922-1c3b0b2a610e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7568 | T16182-XH01-P0SGK-139113 | 2018-06-21 | DHI-WTRAN-001370 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b43dac31-305e-4993-9602-e1a5999eef75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7569 | T16182-YT10-P0SGK-139123 | 2018-06-21 | DHI-WTRAN-001370 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f60edd9-cf55-4a48-b33a-72fe756d61f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7570 | T16182-XJ00-P0QUB-140219 | 2018-06-21 | DHI-WTRAN-001371 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3aa7c538-692e-4c83-b057-4e72a2d31ea5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7571 | T16182-YM02-P0MJ-110578 | 2018-06-21 | DHI-WTRAN-001372 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=672c3b17-b5b7-4c19-a7ae-b45e5040b0fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7572 | T16182-YU02-P0BFA-150911 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e2f9dec-94bc-40c3-9e52-25785f5e9394 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7573 | T16182-YU02-P0BFA-150912 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e31a9ce2-0a2b-483f-8c4c-de19eb067f87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7574 | T16182-YU02-P0BFA-150913 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6b5d49b-9815-4084-88c0-b670736752fc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7575 | T16182-YU02-P0BFA-150914 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=851b3ce5-1df8-431b-b85c-42051fec8682 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7576 | T16182-YU02-P0BFA-150915 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=207b00a2-f54a-4235-bea4-d45c19989e62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7577 | T16182-YU02-P0BFA-150916 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c12161a-c2b7-4423-9f3d-329d3c194e61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7578 | T16182-YU02-P0BFA-150917 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3adf77b-c7db-4143-bcf4-c0f1ce23349e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7579 | T16182-YU02-P0BFA-150918 | 2018-06-22 | DHI-WTRAN-001373 | IFI | 3 | DR | TRUE | TRUE | 2018-06-22_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a1a99a8d-0b6b-46e7-be4d-ca7da91069ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7580 | T16182-YD00-P0BF-150931 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0396e151-0b45-4388-a9d2-f3736f600621 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7581 | T16182-YD00-P0BF-150932 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b9eaacf-6afe-4d0d-9d08-bdec9e78805a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7582 | T16182-YD00-P0BF-150933 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efcedeab-ac92-437b-b6a9-e09614eb9cb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7583 | T16182-YD00-P0BF-150934 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef3c2ec1-1e2a-45c8-aaed-5b3bdb47da50 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7584 | T16182-YD00-P0BF-150935 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf2a4741-a292-43ed-872e-c68430c5ed68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7585 | T16182-YD00-P0BF-150936 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6edc245-8ff2-4488-ae17-e5b1766e6d89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7586 | T16182-YD00-P0BF-150937 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=614e5f48-0fb1-4017-8c64-d2dd86c488c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7587 | T16182-YD00-P0BF-150938 | 2018-06-22 | DHI-WTRAN-001374 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25f2e0ae-5437-4902-9023-68dab29af3a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7588 | T16182-YF00-P0BB-150403 | 2018-06-22 | DHI-TRANSMIT-001820 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=651a0485-ea73-4723-a495-2f4a5674b752 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7589 | T16182-YD00-P0LB-122049 | 2018-06-22 | DHI-TRANSMIT-001821 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e52a0e66-5870-468f-8cba-ce52f28eeda6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7590 | T16182-XB02-P0UHA-171815 | 2018-06-22 | DHI-TRANSMIT-001822 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17da0953-650c-4da4-a88f-9d1e46920a42 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7591 | T16182-XH02-P0SAQ-135204 | 2018-06-22 | DHI-TRANSMIT-001823 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe32f726-b042-4de8-84af-b7a20f3ef188 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7592 | T16182-XW03-P0SAQ-135203 | 2018-06-22 | DHI-TRANSMIT-001823 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7851355-26d8-40d7-b0ab-ed20756cd24c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7593 | T16182-XG02-P8ZEN-125586 | 2018-06-22 | DHI-TRANSMIT-001824 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0694ebe2-4347-45bf-97ad-d58936b1e662 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7594 | T16182-XG02-P8ZEN-125588 | 2018-06-22 | DHI-TRANSMIT-001824 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b5fe85b-6217-4433-b465-dc9c36613eaa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7595 | T16182-XG02-P8ZEN-125591 | 2018-06-22 | DHI-TRANSMIT-001824 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffca56bc-ce59-4c8c-892d-909ff6097901 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7596 | T16182-XG01-P0MJ-110509 | 2018-06-22 | DHI-TRANSMIT-001825 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17850637-821d-426d-94f3-ed2204c3c7a5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7597 | T16182-XG02-P0MJ-110505 | 2018-06-22 | DHI-TRANSMIT-001825 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc482151-626c-454e-9eef-d0b1c964e779 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7598 | T16182-XS00-P8QHA-125002 | 2018-06-22 | DHI-TRANSMIT-001826 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be4a4681-be13-4d70-a50d-3dadde104ecb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7599 | T16182-YT01-P0SAA-136004 | 2018-06-22 | DHI-WTRAN-001375 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62b9c438-6718-4869-b240-c38dbfd21434 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7600 | T16182-XW03-P0SAG-134901 | 2018-06-22 | DHI-TRANSMIT-001827 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f29c4f6-43e6-47cb-b9f5-9d89e2544b23 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7601 | T16182-XG07-P0SAG-134902 | 2018-06-22 | DHI-TRANSMIT-001827 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14e3b447-0877-42e0-bfe8-17ebdf94f2cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7602 | T16182-XW03-P0SAG-134903 | 2018-06-22 | DHI-TRANSMIT-001827 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04e30782-81fa-4d2d-a128-93124041124f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7603 | T16182-XH02-P0SAG-134904 | 2018-06-22 | DHI-TRANSMIT-001827 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4af06df6-4c41-4788-8b32-a7a4089106ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7604 | T16182-YD00-P0GCF-130006 | 2018-06-22 | DHI-TRANSMIT-001828 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b3d3e5d-1923-4fc8-9686-ba75ea8f7430 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7605 | T16182-YF02-P0ZEN-161031 | 2018-06-22 | DHI-TRANSMIT-001829 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b44c88ea-0a2b-4e03-ae8b-6209e4e91e79 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7606 | T16182-YD02-P0SAC-163416 | 2018-06-22 | DHI-WTRAN-001376 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d3fd835-d964-4abb-8b5d-ed25ac3b8ed6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7607 | T16182-YD02-P0SAC-163413 | 2018-06-22 | DHI-TRANSMIT-001830 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21082406-e2e1-4f0a-88ae-790e0a11b4e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7608 | T16182-YD02-P0SAC-163414 | 2018-06-22 | DHI-TRANSMIT-001830 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c135fa1d-a471-4b01-b36c-10e62333606c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7609 | T16182-YF02-P0SAY-163401 | 2018-06-22 | DHI-TRANSMIT-001831 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=beb3fcdd-eded-4f3a-ba4a-bf3bceb30cce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7610 | T16182-XB02-P0ULX-171602 | 2018-06-22 | DHI-TRANSMIT-001832 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=975f041e-22c4-40a0-ae1e-9ab8661e71d2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7611 | T16182-XB02-P0ULX-171603 | 2018-06-22 | DHI-TRANSMIT-001832 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a8034d7-2f50-4059-92f3-a3f08224c547 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7612 | T16182-VK02-P0ULX-171604 | 2018-06-22 | DHI-TRANSMIT-001832 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e6b2309-7cc9-42cd-b770-e5e374eacbef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7613 | T16182-YU03-P0BAT-150631 | 2018-06-25 | DHI-TRANSMIT-001834 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e36dd66d-6e3a-490b-b306-5b70af8cdd1e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7614 | T16182-YU03-P0BAT-150636 | 2018-06-25 | DHI-TRANSMIT-001834 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35365fe6-7b2a-4774-b076-16c0f1547819 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7615 | T16182-YU03-P0BBT-150681 | 2018-06-25 | DHI-TRANSMIT-001834 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abad6ab3-39b1-49ba-b339-4cbddc7f7395 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7616 | T16182-XB02-P0GHC-173802 | 2018-06-25 | DHI-TRANSMIT-001835 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d640704-6eba-4eb1-bccd-6d018f933946 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7617 | T16182-YR05-P0CWQ-161141 | 2018-06-25 | DHI-TRANSMIT-001836 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90970d45-2a1c-40df-936b-e119bd8a0998 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7618 | T16182-YR05-P0CWQ-161142 | 2018-06-25 | DHI-TRANSMIT-001836 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61743fdb-d178-4753-b21f-0032b9a93f71 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7619 | T16182-YR05-P0CWQ-161143 | 2018-06-25 | DHI-TRANSMIT-001836 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=932f01b0-4c46-4357-becd-011914b88d71 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7620 | T16182-YR05-P0CWQ-161147 | 2018-06-25 | DHI-TRANSMIT-001836 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9f399dd-0736-4b7a-91f2-c46bfae0fb0d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7621 | T16182-CV03-P0CWQ-161134 | 2018-06-26 | DHI-TRANSMIT-001838 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1d65605-7bca-4e22-b6f1-57f76baf13d4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7622 | T16182-YD02-P0ZEN-165515 | 2018-06-26 | DHI-TRANSMIT-001839 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7fd8b08-eeb2-49ac-beca-c6c18f90aa6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7623 | T16182-YD02-P0ZEN-165520 | 2018-06-26 | DHI-TRANSMIT-001839 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20343ab8-18e7-4e6a-9a7d-1139fd4586b0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7624 | T16182-DA01-P0ZEN-020002 | 2018-06-27 | DHI-WTRAN-001378 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38565e5f-e744-4c66-b945-f05d2c57892a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7625 | T16182-YU03-P0BFA-150951 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e34c208-18d3-45cc-b3d9-1edcfcb5fd1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7626 | T16182-YU03-P0BFA-150952 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b6b433c-7d15-47cf-8da5-acfca0ad36ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7627 | T16182-YU03-P0BFA-150953 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1927549-675a-41b3-a902-fb5566973bdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7628 | T16182-YU03-P0BFA-150954 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=086a0814-ff4a-4a53-884c-67f8942a717c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7629 | T16182-YU03-P0BFA-150955 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbc7da4d-f8a6-4272-98ce-976931b88721 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7630 | T16182-YU03-P0BFA-150956 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74696d8f-8686-43af-a7e9-0f46726cc05e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7631 | T16182-YU03-P0BFA-150957 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0de9bf46-0d49-4ecb-8ebe-0208a82f7f35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7632 | T16182-YU03-P0BFA-150958 | 2018-06-27 | DHI-WTRAN-001379 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64101a40-c25a-4dc0-9d39-e55fff678947 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7633 | T16182-YD00-P0SGZ-136631 | 2018-06-27 | DHI-WTRAN-001380 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5efe5520-c242-49df-a662-fda638d4915b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7634 | T16182-XB00-P0GM-128506 | 2018-06-27 | DHI-TRANSMIT-001840 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a93f2f78-6462-4cc5-a6c5-a4a801e4c146 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7635 | T16182-CV03-P8ZEN-125601 | 2018-06-27 | DHI-TRANSMIT-001841 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b0aa464-429f-4e74-a064-04dd691d70c1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7636 | T16182-CV03-P8ZEN-125604 | 2018-06-27 | DHI-TRANSMIT-001841 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae409849-bae6-4106-ae61-e1205ddfceda | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7637 | T16182-YK08-P0LCM-420030 | 2018-06-27 | DHI-TRANSMIT-001842 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95972d85-b08e-4b99-9043-678732253dd0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7638 | T16182-YK08-P0LCM-420040 | 2018-06-27 | DHI-TRANSMIT-001842 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f214270-c832-4168-a04e-9c9f916db573 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7639 | T16182-YK00-P0LB-122071 | 2018-06-27 | DHI-TRANSMIT-001843 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=653b65a3-bfa0-4484-9b94-2e66761ef06f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7640 | T16182-CA00-P0UYB-183501 | 2018-06-27 | DHI-TRANSMIT-001844 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=159aaa1e-35c1-48c7-9b38-01e8e44140d8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7641 | T16182-CA00-P0UYB-183502 | 2018-06-27 | DHI-TRANSMIT-001844 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2340d17-e83b-42ab-840b-89f90afbdd55 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7642 | T16182-CA01-P0UYB-183551 | 2018-06-27 | DHI-TRANSMIT-001844 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58066e4d-e153-47ac-afce-075bff6fe351 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7643 | T16182-CA01-P0UYB-183552 | 2018-06-27 | DHI-TRANSMIT-001844 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ae4c94a-9bec-46a0-99aa-7220b41f05a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7644 | T16182-CA02-P0UYB-183553 | 2018-06-27 | DHI-TRANSMIT-001844 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6e283b1-b783-49f8-b9f1-59b917590385 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7645 | T16182-CA02-P0UYB-183554 | 2018-06-27 | DHI-TRANSMIT-001844 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7a42f1d-94f6-4030-9535-4d5ca7b73659 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7646 | T16182-XJ00-P0SGA-136622 | 2018-06-28 | DHI-WTRAN-001381 | IFI | 0 | D | TRUE | FALSE | 2018-06-29_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=754a19a1-e955-4b68-85ae-e860e565c2b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7647 | T16182-XH01-P0SGA-136604 | 2018-06-28 | DHI-TRANSMIT-001845 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=074a01bc-fdce-4467-bde9-d3a80857f154 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7648 | T16182-XJ00-P0LAB-140208 | 2018-06-29 | DHI-TRANSMIT-001846 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6aa91a63-b523-4dba-9f8f-cbb72ddf10fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7649 | T16182-XB02-P0UEG-171502 | 2018-06-29 | DHI-TRANSMIT-001847 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faf1ca42-198f-47f1-920c-69c8a547f6f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7650 | T16182-XB02-P0UEG-171504 | 2018-06-29 | DHI-TRANSMIT-001847 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72336ce7-80a2-4e6c-8ab3-792573e1f82c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7651 | T16182-CV03-P0CWQ-161133 | 2018-06-29 | DHI-TRANSMIT-001848 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc1e851c-d898-423b-8004-76adeb426259 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7652 | T16182-CV03-P0CWQ-161135 | 2018-06-29 | DHI-TRANSMIT-001848 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=322a9d7b-71e3-425b-8791-90e367caee4a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7653 | T16182-YR05-P0CWQ-161146 | 2018-06-29 | DHI-TRANSMIT-001848 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5329dcc-4a8d-4fa0-9891-f4ef73fa918f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7654 | T16182-YF00-P0BA-150401 | 2018-06-29 | DHI-TRANSMIT-001849 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03bb9b8c-36bc-4692-bcad-0390df026089 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7655 | T16182-YU03-P0CFA-151181 | 2018-06-29 | DHI-WTRAN-001382 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98d1b5f1-8ecb-4429-bf90-be30417a1e66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7656 | T16182-YU03-P0CHB-151121 | 2018-06-29 | DHI-WTRAN-001382 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b964bdc-9d29-4097-9b10-127131501357 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7657 | T16182-YU03-P0CHB-151122 | 2018-06-29 | DHI-WTRAN-001382 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=418b543e-fc20-4e4d-a126-c60d5b9370ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7658 | T16182-YE00-P0ZEN-152792 | 2018-06-29 | DHI-WTRAN-001383 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0d0aaea-cc20-496e-a101-fe3fcb7a1f4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7659 | T16182-YE00-P0ZEN-152794 | 2018-06-29 | DHI-WTRAN-001383 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62ef7c97-08d1-4d3f-8019-ea871b1fe71c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7660 | T16182-YE00-P0ZEN-152795 | 2018-06-29 | DHI-WTRAN-001383 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e57b64c-4560-4545-b3f0-841993195d1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7661 | T16182-YQ08-P0CY-154036 | 2018-06-29 | DHI-TRANSMIT-001850 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee3dabc5-9106-4a92-bb64-6066bdfc3b9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7662 | T16182-YQ08-P0CY-154039 | 2018-06-29 | DHI-TRANSMIT-001850 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daea54f8-6a90-45a0-a930-7cae09737ae1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7663 | T16182-YQ08-P0CY-154040 | 2018-06-29 | DHI-TRANSMIT-001850 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f2fcf87-b494-4895-93d5-8978d37b06ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7664 | T16182-YQ08-P0CY-154041 | 2018-06-29 | DHI-TRANSMIT-001850 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ea68113-7c91-496b-a07d-9f05737724ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7665 | T16182-YQ08-P0CY-154042 | 2018-06-29 | DHI-TRANSMIT-001850 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9d7b532-53fd-4753-b922-5e77e6862858 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7666 | T16182-XW03-P0SAJ-133701 | 2018-06-29 | DHI-TRANSMIT-001851 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c654bdd-1999-44f0-a7c3-380d40d182b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7667 | T16182-XW03-P0SAJ-133703 | 2018-06-29 | DHI-TRANSMIT-001851 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=879ad012-47d0-40cf-8721-e08318cc3992 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7668 | T16182-XH02-P0SAJ-133704 | 2018-06-29 | DHI-TRANSMIT-001851 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27ad1f7a-234a-4391-a63c-f8cb5d404c3c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7669 | T16182-XG02-P0QC-130303 | 2018-06-29 | DHI-TRANSMIT-001852 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1e793d0-6f72-4f25-b628-fe6dec0c7bd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7670 | T16182-YD00-P0QC-130302 | 2018-06-29 | DHI-TRANSMIT-001852 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eed9e929-9e89-47ca-ad42-4832b0bb05a1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7671 | T16182-YT01-P0QC-130307 | 2018-06-29 | DHI-WTRAN-001384 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b10fcb18-a277-41b3-8697-0421e3b8a456 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7672 | T16182-YR05-P0QC-130306 | 2018-06-29 | DHI-WTRAN-001384 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83e15498-9e77-47e6-bb06-8604671b3a0e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7673 | T16182-YF00-P0QC-130309 | 2018-06-29 | DHI-WTRAN-001384 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f1fc755-1b10-468e-b7c1-65936ace15e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7674 | T16182-YU03-P0QC-130308 | 2018-06-29 | DHI-WTRAN-001384 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08539131-d2ef-4b6f-a178-4c3f5bb479cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7675 | T16182-XB02-P0UGF-173101 | 2018-06-29 | DHI-TRANSMIT-001853 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a651af5e-86ea-4e97-ab09-5a326aa27983 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7676 | T16182-XB02-P0UGF-173102 | 2018-06-29 | DHI-TRANSMIT-001853 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99ea887a-c256-4a2b-ba8d-bb46a97db475 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7677 | T16182-VK02-P0UGF-173107 | 2018-06-29 | DHI-TRANSMIT-001853 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=182b98ad-6120-4e1e-a5df-60e4b4309ddc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7678 | T16182-XB02-P0GUB-173302 | 2018-06-29 | DHI-TRANSMIT-001854 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9aafdadf-1ad9-4cbf-a17b-cfc0b3fcdfcb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7679 | T16182-XB02-P0GUB-173303 | 2018-06-29 | DHI-TRANSMIT-001854 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a263329b-99f0-49ca-af4d-e0446099af0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7680 | T16182-YU02-P0LD-130210 | 2018-06-29 | DHI-WTRAN-001385 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f06562e6-9f28-4e6f-8f3a-9a2c80c82a1b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7681 | T16182-YD00-P0LD-130206 | 2018-06-29 | DHI-WTRAN-001385 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7f72db1-9fa2-4b00-8e23-2c069c81aa6e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7682 | T16182-UT01-P0GQB-173402 | 2018-06-29 | DHI-TRANSMIT-001855 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83708d52-7fb9-4d52-a382-77978b3407ce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7683 | T16182-UT01-P0GQB-173403 | 2018-06-29 | DHI-TRANSMIT-001855 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df2fd949-1a59-4b3c-80a8-66a42658c480 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7684 | T16182-YD04-P0ZEN-152005 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d028184-9d53-4229-9a38-cb52ba6a0877 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7685 | T16182-YD04-P0ZEN-152006 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=731199ce-2ea3-4c67-b999-289ae0dff9cd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7686 | T16182-YE00-P0ZEN-152718 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fb5d57d-f6f9-4f3c-b009-39f9d8781ac7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7687 | T16182-YE00-P0ZEN-152715 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63d27b70-7590-46a0-bc7f-04effaac0f34 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7688 | T16182-YE00-P0ZEN-152726 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55efbcf2-476d-4a27-b0a1-d63024466c66 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7689 | T16182-YE00-P0ZEN-152727 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f7388b0-f3da-4e2f-95df-da4b507967fd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7690 | T16182-YE00-P0ZEN-152728 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71bf1044-171b-4a76-a6fc-900b241ce0a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7691 | T16182-YE00-P0ZEN-152729 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35d1fd44-171e-4fac-b983-2e2bd2583343 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7692 | T16182-YE00-P0ZEN-152730 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df665212-7519-4ca1-9dda-984dabcafada | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7693 | T16182-YE00-P0ZEN-152731 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b794b5d2-070c-48f4-8398-2b605c96d079 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7694 | T16182-YE00-P0ZEN-152732 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b6295836-1ac6-421f-af2f-e0b4a9963162 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7695 | T16182-YE00-P0ZEN-152733 | 2018-07-02 | DHI-TRANSMIT-001856 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c889188-2222-4464-87f7-c7c9a13fad6a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7696 | T16182-XB02-P0UHA-171815 | 2018-07-02 | DHI-TRANSMIT-001857 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ba07b55-7ad4-4518-b993-2ad0c2389291 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7697 | T16182-XB02-P0UHA-171816 | 2018-07-02 | DHI-TRANSMIT-001857 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac061983-9b76-4f1f-b8f9-e2d053508371 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7698 | T16182-XB02-P0UZJ-173202 | 2018-07-02 | DHI-TRANSMIT-001858 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=739fefbe-b007-4983-b809-4fa5c2f86348 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7699 | T16182-VK02-P0UZJ-173208 | 2018-07-02 | DHI-TRANSMIT-001858 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=063ee419-1e9d-442d-b9d9-4aa90f791942 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7700 | T16182-VK02-P0UZJ-173209 | 2018-07-02 | DHI-TRANSMIT-001858 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d5311de-7fe7-43de-881f-822c9751102a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7701 | T16182-YS01-P0MKY-290009 | 2018-07-02 | DHI-TRANSMIT-001859 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebb7fa55-904a-4f04-ad4a-a59750260065 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7702 | T16182-CV03-P0CWQ-161134 | 2018-07-03 | DHI-TRANSMIT-001860 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b5e9734-7c25-4742-a997-41e03e252c9a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7703 | T16182-XB02-P0GCF-130042 | 2018-07-03 | DHI-TRANSMIT-001861 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d6c4f12-9c7e-4bc6-ac5c-a3b6e1b8f7ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7704 | T16182-YD02-P0ZEN-165509 | 2018-07-03 | DHI-TRANSMIT-001862 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97e349ad-1d3e-4cf7-86fd-c07cdb79c7a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7705 | T16182-BP00-P0LBC-140012 | 2018-07-03 | DHI-TRANSMIT-001863 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffbdb2d5-68a7-4be3-b651-abd8f126dbe7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7706 | T16182-BP00-P0LBG-140016 | 2018-07-03 | DHI-TRANSMIT-001863 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d050a5ab-00d2-4fd8-b6fa-d7954bf6761a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7707 | T16182-YK08-P0ZEN-020008 | 2018-07-04 | DHI-TRANSMIT-001864 | IFC | 1 | DR | TRUE | TRUE | 2018-07-04_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff855094-1378-4e0a-b057-48cc28543454 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7708 | T16182-YR01-P0CRU-161150 | 2018-07-04 | DHI-WTRAN-001386 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a69b525-acbe-402b-8c62-32ba676e4714 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7709 | T16182-XJ00-P0LBA-140201 | 2018-07-04 | DHI-WTRAN-001387 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f86633a6-6ea9-48bb-829a-708864c5ed6b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7710 | T16182-YL01-P0CBA-161101 | 2018-07-04 | DHI-TRANSMIT-001865 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b443f269-dda7-43af-b515-1df2e3c440ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7711 | T16182-VK02-P0UZA-172908 | 2018-07-04 | DHI-TRANSMIT-001866 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=946a8332-c8fe-426d-996d-3450f82e15be | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7712 | T16182-XB02-P0UZT-172702 | 2018-07-04 | DHI-TRANSMIT-001867 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=485105f4-41be-411e-a07b-55e93ee73235 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7713 | T16182-XB02-P0UZT-172703 | 2018-07-04 | DHI-TRANSMIT-001867 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d290e2b-497c-4dc4-8214-aa5b62b4f43e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7714 | T16182-VK02-P0UZT-172713 | 2018-07-04 | DHI-TRANSMIT-001867 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f94a78c-1d8d-4ca8-a438-1747c98f5d16 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7715 | T16182-XB02-P0UZT-172716 | 2018-07-04 | DHI-TRANSMIT-001867 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2fd51051-8dcb-48f5-bac1-596fb6549d31 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7716 | T16182-XG02-P0PGB-110010 | 2018-07-04 | DHI-TRANSMIT-001868 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97892020-e869-4283-afb8-d1c9ac63ae61 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7717 | T16182-YK08-P0ZEN-020008 | 2018-07-05 | DHI-TRANSMIT-001869 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f2671c5-7da4-449b-8dab-53801c0b5426 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7718 | T16182-YK00-P0SCA-127522 | 2018-07-05 | DHI-TRANSMIT-001870 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c52c7a2-fe73-47f0-89e0-0433859475ff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7719 | T16182-BP00-P0LBA-140011 | 2018-07-06 | DHI-WTRAN-001388 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fea9b11-fe48-4f17-a92a-16f61d47cd4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7720 | T16182-YE01-P0BAU-152609 | 2018-07-06 | DHI-WTRAN-001389 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d30ac6e9-5839-4ca8-81a9-6a89e07f8084 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7721 | T16182-YE03-P0BAU-152513 | 2018-07-06 | DHI-TRANSMIT-001871 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c385a3d8-b315-41b2-a561-58176f7b0c5c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7722 | T16182-YE03-P0BAU-152514 | 2018-07-06 | DHI-TRANSMIT-001871 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfba5d46-8895-4b49-a317-dc5450f3f49d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7723 | T16182-YE03-P0BAU-152515 | 2018-07-06 | DHI-TRANSMIT-001871 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f88e358-262a-48b9-aa60-298db1ad51ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7724 | T16182-YE03-P0BAU-152516 | 2018-07-06 | DHI-TRANSMIT-001871 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b13a6a0-d437-4791-9856-295c6201a80d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7725 | T16182-YE03-P0BAU-152540 | 2018-07-06 | DHI-TRANSMIT-001871 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ed436a3-9115-46e4-8fac-a69f06f834fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7726 | T16182-CA00-P0UBA-181001 | 2018-07-06 | DHI-TRANSMIT-001872 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6048f1eb-dde0-429c-8094-dcc10745559b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7727 | T16182-CA00-P0UBA-181004 | 2018-07-06 | DHI-TRANSMIT-001872 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c509a65-e549-422b-ae76-b2318b2e7881 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7728 | T16182-CA01-P0UBA-181052 | 2018-07-06 | DHI-TRANSMIT-001872 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59157d24-3b69-4967-9ec8-3aaf6e44633e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7729 | T16182-CA01-P0UBA-181054 | 2018-07-06 | DHI-TRANSMIT-001872 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5be7bee-576a-4a17-92a1-a97793041bcc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7730 | T16182-CA00-P0UBA-181101 | 2018-07-06 | DHI-TRANSMIT-001872 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13bcdb80-341a-4681-a273-3cbae447e011 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7731 | T16182-CA00-P0UBA-181104 | 2018-07-06 | DHI-TRANSMIT-001872 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b004fb6-6b58-47ee-91b6-e0db6180b75c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7732 | T16182-CA01-P0UBA-181152 | 2018-07-06 | DHI-TRANSMIT-001872 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ee6a076-8c9c-4ffe-b3b3-918d802f4ada | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7733 | T16182-YD00-P0BBT-150671 | 2018-07-06 | DHI-WTRAN-001396 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78d202d3-b3aa-4d13-8d34-00ff3dd3986c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7734 | T16182-YD04-P0ZEN-152004 | 2018-07-06 | DHI-TRANSMIT-001873 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b14741fe-09ff-474b-b8be-f895ab3e5594 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7735 | T16182-YQ08-P0CY-154031 | 2018-07-06 | DHI-TRANSMIT-001874 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a22fb04-103f-40b0-aa95-e6911c430312 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7736 | T16182-YQ08-P0CY-154037 | 2018-07-06 | DHI-TRANSMIT-001874 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cd956ce-0b52-4508-985a-a3621bc64269 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7737 | T16182-BP00-P0LBS-140013 | 2018-07-06 | DHI-TRANSMIT-001875 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cc76cf6-4e80-4258-b0fa-3e845f330cbb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7738 | T16182-XJ00-P0LCM-140205 | 2018-07-06 | DHI-WTRAN-001397 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65e4ba08-7899-4949-9724-cd878752bf3a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7739 | T16182-XJ00-P0ZEN-140120 | 2018-07-06 | DHI-WTRAN-001397 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5aad3b81-c236-446b-96f2-fbff4a246598 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7740 | T16182-DN05-P0SG-136620 | 2018-07-06 | DHI-TRANSMIT-001876 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf53da99-a24f-44f3-886c-094796086556 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7741 | T16182-XG02-P0SGK-136803 | 2018-07-06 | DHI-TRANSMIT-001876 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0384f347-a9db-45fc-98e2-757894d0cdec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7742 | T16182-XH01-P0SGK-136813 | 2018-07-06 | DHI-TRANSMIT-001876 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1f5a3e9-5932-48dc-9652-423316b78eb6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7743 | T16182-VE04-P0GUC-172801 | 2018-07-06 | DHI-TRANSMIT-001877 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a654ce9d-1d3c-4b73-b0ac-4a323dfb25d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7744 | T16182-XB02-P0GUC-172802 | 2018-07-06 | DHI-TRANSMIT-001877 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a1c6a1a-4113-4e32-a6ed-3ce3f6de4b85 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7745 | T16182-XB02-P0GUC-172803 | 2018-07-06 | DHI-TRANSMIT-001877 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87acd991-84fb-4e6d-acb5-830dddfcc8df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7746 | T16182-VK02-P0GUC-172804 | 2018-07-06 | DHI-TRANSMIT-001877 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=947ebda0-4480-47d3-96ff-24e7a89b39ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7747 | T16182-VK02-P0UZA-172908 | 2018-07-09 | DHI-TRANSMIT-001878 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef5dc0fb-d815-4370-88b6-300acd044055 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7748 | T16182-XB02-P0UZA-172902 | 2018-07-09 | DHI-TRANSMIT-001878 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94ed95bb-57ab-42c3-b8ed-bebda63f7fc4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7749 | T16182-XB02-P0UZA-172903 | 2018-07-09 | DHI-TRANSMIT-001878 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b89ccfd-c612-4042-88c0-4b42da5f3433 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7750 | T16182-YD02-P0ZEN-165524 | 2018-07-09 | DHI-TRANSMIT-001879 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c7040f7-94bd-457f-a98f-efc048982cfb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7751 | T16182-CA03-P0UMY-185177 | 2018-07-09 | DHI-TRANSMIT-001880 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8ce14bd-9f21-47af-a733-94493c549466 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7752 | T16182-XJ00-P0LB-122027 | 2018-07-09 | DHI-TRANSMIT-001881 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e35b285e-9038-45d2-ad1e-2a646e6693e2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7753 | T16182-CA00-P0UYP-183201 | 2018-07-10 | DHI-TRANSMIT-001882 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fa2adaf-7cd3-45d4-be41-808bb7a4e897 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7754 | T16182-XH01-P0SGC-138111 | 2018-07-10 | DHI-TRANSMIT-001883 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5483713f-b598-44d3-aade-69d3372c6444 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7755 | T16182-YE00-P0ZEN-152710 | 2018-07-10 | DHI-TRANSMIT-001884 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23b913b5-2f54-469c-845d-85294c71a591 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7756 | T16182-YT02-P0PCA-126529 | 2018-07-10 | DHI-WTRAN-001398 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf836037-2970-40c1-8f63-c2350fd22b6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7757 | T16182-XB02-P0UZA-172904 | 2018-07-10 | DHI-TRANSMIT-001885 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31affb0f-66be-4609-bf63-66d5758f78e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7758 | T16182-YT10-P0MKY-290010 | 2018-07-11 | DHI-TRANSMIT-001886 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3be789d-41f0-44ac-b7ed-60121d57a9da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7759 | T16182-XG02-P0GHC-110011 | 2018-07-11 | DHI-TRANSMIT-001887 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=766cab88-a9ee-49b0-8e40-aac436884626 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7760 | T16182-VK02-P0UAG-172170 | 2018-07-11 | DHI-TRANSMIT-001888 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7173e0ca-4e89-41a9-aff2-c406e1a1d282 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7761 | T16182-XB02-P0UAG-172102 | 2018-07-11 | DHI-TRANSMIT-001888 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e69f0090-fd0c-4b00-b8a2-2290022c8fff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7762 | T16182-XB02-P0UAG-172162 | 2018-07-11 | DHI-TRANSMIT-001888 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c22e93b-8e7c-427e-8611-51ab5b370c35 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7763 | T16182-YE00-P0ZEN-152724 | 2018-07-11 | DHI-TRANSMIT-001889 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f02ddd82-52e1-4659-97ab-9f3d62febe09 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7764 | T16182-YE00-P0ZEN-152725 | 2018-07-11 | DHI-TRANSMIT-001889 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f5d209b-93fe-479e-a9df-317bceb023a2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7765 | T16182-YF00-P0CBA-161203 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e749c9b-58e3-4a5f-88eb-4eee480a9379 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7766 | T16182-YF00-P0CBA-161204 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e32305d-d57b-4dac-8dce-6580e076a311 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7767 | T16182-YF00-P0CBA-161205 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=114b8742-da5f-4cc1-be9b-f4fff93f9110 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7768 | T16182-YF00-P0CBA-161206 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d214fbf6-533f-4104-8bea-cb99593e550c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7769 | T16182-YF00-P0CBA-161207 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c47b07b-15e9-4ad6-b07b-96ab434a3fe6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7770 | T16182-YF00-P0CBA-161208 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc9c0203-10d9-4f7c-94d7-b65b12094c72 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7771 | T16182-YF00-P0CBA-161209 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c2048ab-7fe5-4aa8-8978-d0ab969427ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7772 | T16182-YF00-P0CBA-161210 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=612bed94-12d9-4630-9421-a6f1ab893fd9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7773 | T16182-YF00-P0CBA-161211 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e155346-ef8e-4ac5-8b98-81efdb9dd2e2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7774 | T16182-YF00-P0CBA-161212 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b476997-c839-4599-81ba-8a79f9e11333 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7775 | T16182-YF00-P0CBA-161213 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbdbab4e-289a-498f-b95f-9c6bfe708b0d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7776 | T16182-YF00-P0CBA-161214 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=091bc85f-fee1-4fa0-b8cf-16bed2f2616c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7777 | T16182-YF00-P0CBA-161220 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d84371b-67f4-4be6-b512-d485e8d29e9a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7778 | T16182-YF00-P0CBA-161221 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac26bae4-1b4a-459b-83bb-23cf1085c17d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7779 | T16182-YF00-P0CBA-161222 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36a2a4ec-9d6e-4d0b-bed8-9a31c5abe33d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7780 | T16182-YF00-P0CGA-161303 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=952ef61e-47f7-460d-a610-2e3c35e33c23 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7781 | T16182-YF00-P0CGA-161304 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a51c754e-5475-4c8a-b9f7-36c9a9b95dcc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7782 | T16182-YF00-P0CGA-161305 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a466a85-d0ff-4094-9228-73a87294fd65 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7783 | T16182-YF00-P0CGA-161306 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1c14e01-28e0-45ea-97cf-76a02f97121c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7784 | T16182-YF00-P0CGA-161307 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0920be6d-5a4b-45f9-84bb-8ba8e61d2ee7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7785 | T16182-YF00-P0CGA-161308 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55d03a44-f7ed-49fa-a833-b75af111b4e3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7786 | T16182-YF00-P0CGA-161309 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=031cff05-d865-4eda-9d45-c0565d5f4bb6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7787 | T16182-YF00-P0CGA-161310 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0967ff48-a21c-492f-b434-94341bdcfd51 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7788 | T16182-YF00-P0CGA-161311 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afb2a795-7205-4ca1-9291-08776a6f8b10 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7789 | T16182-YF00-P0CGA-161312 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34894640-22e1-4260-a89f-162792b3f44c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7790 | T16182-YF00-P0CGA-161313 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1dcb3c3-1941-4698-9613-4d29afbb17c5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7791 | T16182-YF00-P0CGA-161314 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29229bf0-06af-49ce-b1f5-4f38acbe6448 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7792 | T16182-YF00-P0CGA-161316 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47a177f8-d343-4294-ab69-b27c54349fb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7793 | T16182-YF00-P0CGA-161320 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a3f2c9a-0488-479d-a3bd-85a7c53b2232 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7794 | T16182-YF00-P0CGA-161321 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13ea20f4-1b93-4ae0-84ea-b53a5d0b5cba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7795 | T16182-YF00-P0CGA-161322 | 2018-07-11 | DHI-TRANSMIT-001890 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe1f0dbd-4c05-444a-98f6-db5e9182ac94 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7796 | T16182-CA00-P0UST-182001 | 2018-07-12 | DHI-TRANSMIT-001891 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8b0452c-fd6f-4841-bb66-5d71b645afd5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7797 | T16182-CA00-P0UST-182005 | 2018-07-12 | DHI-TRANSMIT-001891 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c45faa3-b002-40d0-934f-b2b56ba80547 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7798 | T16182-CA00-P0UST-182006 | 2018-07-12 | DHI-TRANSMIT-001891 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f330ce7-df0a-49c0-aa4a-591532a834b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7799 | T16182-CA01-P0UST-182053 | 2018-07-12 | DHI-TRANSMIT-001891 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bcb088c3-d77c-454b-ad96-50c1bd48f934 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7800 | T16182-CA00-P0UTF-182801 | 2018-07-12 | DHI-TRANSMIT-001892 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72d0a9ff-41b0-4ae8-8462-9f19c687c3fa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7801 | T16182-CA00-P0UTF-182803 | 2018-07-12 | DHI-TRANSMIT-001892 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55bbb4df-4bd0-41ef-9a77-3da117c69bd9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7802 | T16182-CA01-P0UTF-182853 | 2018-07-12 | DHI-TRANSMIT-001892 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90f81810-d3c7-402c-8e16-337b57df7653 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7803 | T16182-CA01-P0UTF-182855 | 2018-07-12 | DHI-TRANSMIT-001892 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0218553-284c-4e3d-8c6f-dbac02209c69 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7804 | T16182-YT01-P0SAA-136004 | 2018-07-12 | DHI-TRANSMIT-001893 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86692f11-8609-4767-966f-f7bc16c0ca82 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7805 | T16182-XB02-P0MPA-171106 | 2018-07-12 | DHI-TRANSMIT-001894 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c05b741-6e7e-4c07-87c3-c8d599de6466 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7806 | T16182-XB02-P0MPA-171113 | 2018-07-12 | DHI-TRANSMIT-001894 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=134ff356-8d32-4a86-a6f0-4720a74c03a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7807 | T16182-YD00-P0CYE-139141 | 2018-07-12 | DHI-TRANSMIT-001895 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=419050f6-16cf-4561-b056-ae4514f898a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7808 | T16182-YU02-P0CYE-139142 | 2018-07-12 | DHI-TRANSMIT-001895 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7a32e3f-dc7b-4d6d-a9ee-848010db3430 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7809 | T16182-XG02-P0CYE-139144 | 2018-07-12 | DHI-TRANSMIT-001895 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c53e454f-7c18-412e-a096-ac1d7375254b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7810 | T16182-UE00-P0LB-122008 | 2018-07-12 | DHI-TRANSMIT-001896 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5deb8156-f4a4-4686-94ca-3d5f5e9bb1c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7811 | T16182-YT01-P0LB-122103 | 2018-07-12 | DHI-TRANSMIT-001896 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65c2a9bd-d116-4e18-9727-e7ee29123558 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7812 | T16182-YB03-P0SAY-163407 | 2018-07-13 | DHI-TRANSMIT-001897 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c793badf-20d1-47c5-a623-e4501b21d97b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7813 | T16182-YR05-P0SAY-163423 | 2018-07-13 | DHI-WTRAN-001399 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa4dab7f-0d18-4a7e-ba1d-b838bd2aec9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7814 | T16182-YD00-P0SMU-128015 | 2018-07-13 | DHI-TRANSMIT-001898 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b5ef98a-5dfc-4ef2-8b69-99a29300327b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7815 | T16182-XH01-P0LB-122024 | 2018-07-14 | DHI-TRANSMIT-001899 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b29c390-ea04-4d94-a7e7-c473812b5df2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7816 | T16182-XH01-P0LB-122025 | 2018-07-14 | DHI-TRANSMIT-001899 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7be9710c-9f56-49ee-a328-f1ce7decb5c6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7817 | T16182-XJ00-P0LB-122027 | 2018-07-14 | DHI-TRANSMIT-001899 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ebdc762-be50-458f-98bd-c062b72e1041 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7818 | T16182-XJ00-P0LB-122028 | 2018-07-14 | DHI-TRANSMIT-001899 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6eb6bee-2631-4dc6-9b5b-713591ab216d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7819 | T16182-XB02-P8UTH-172007 | 2018-07-16 | DHI-TRANSMIT-001900 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98b4dc94-f026-4db7-ac00-a7778ffde031 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7820 | T16182-YQ01-P0ZEN-152306 | 2018-07-16 | DHI-TRANSMIT-001901 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4875d771-63b3-4b7e-a2b4-be0f0a866c93 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7821 | T16182-YQ01-P0ZEN-152324 | 2018-07-16 | DHI-TRANSMIT-001901 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7d5d278-e3b1-441c-a09a-7503e838ebbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7822 | T16182-YT01-P0LB-122093 | 2018-07-16 | DHI-TRANSMIT-001902 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1cf0021-aca1-40f1-9f74-9eb0b16d67b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7823 | T16182-XJ00-P0LCM-140105 | 2018-07-16 | DHI-TRANSMIT-001903 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7803ade5-adc0-4450-b34d-f1180ca04208 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7824 | T16182-XJ00-P0LAB-140108 | 2018-07-16 | DHI-TRANSMIT-001903 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b3ff7694-b7d7-41d6-be3a-309ee6ffe0d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7825 | T16182-YU03-P0QU-130406 | 2018-07-16 | DHI-WTRAN-001400 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=751a24c4-2e9c-4063-800f-a8f7257fa4ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7826 | T16182-YD00-P0QU-130402 | 2018-07-16 | DHI-TRANSMIT-001904 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23678d91-d3ce-439b-b081-0dba1335875c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7827 | T16182-YE00-P0ZEN-152791 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f9aaabd-79d5-4a06-b650-03ed1bdc354b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7828 | T16182-YE00-P0ZEN-152793 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=138ec416-ce55-4797-8179-a18b692b42d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7829 | T16182-YQ08-P0CY-154031 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55931391-9972-4b35-91de-8965be4ff122 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7830 | T16182-YQ08-P0CY-154033 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a9c851c-f52a-493c-bed6-10aa16cf203c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7831 | T16182-YQ08-P0CY-154040 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6050558-4938-426c-9253-e3b361bca543 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7832 | T16182-YQ08-P0CY-154042 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9dcee5a5-fae0-4fcf-921f-2d5795fe3a06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7833 | T16182-YQ08-P0CY-154044 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a960ce0e-64da-4722-afdc-778b8f0244cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7834 | T16182-YU02-P0CYA-154011 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4875d033-c459-4d04-bb94-b60b3f15ab0a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7835 | T16182-YU02-P0CYM-154013 | 2018-07-16 | DHI-TRANSMIT-001905 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a9a91b5-3c12-401c-a587-cd37eecdedd8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7836 | T16182-YD02-P0SAC-163409 | 2018-07-16 | DHI-TRANSMIT-001906 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d17f1311-85b4-4c26-9678-b603b00bdd20 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7837 | T16182-YK01-P0LAC-126006 | 2018-07-16 | DHI-WTRAN-001401 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18721fd2-3a17-4e44-8dd1-6ad4486e1e24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7838 | T16182-YK01-P0LAC-126056 | 2018-07-16 | DHI-TRANSMIT-001907 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac3e7eb7-9e44-4f3d-bd84-2a7511e64b6c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7839 | T16182-YT01-P0LAC-126009 | 2018-07-16 | DHI-TRANSMIT-001908 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3dfce4a-5cd3-4b9b-961d-f9d2b43688b4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7840 | T16182-YT01-P0LAC-126059 | 2018-07-16 | DHI-TRANSMIT-001908 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f41637cb-23bc-4e2f-90b5-a6f408a30d81 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7841 | T16182-YF00-P0GCF-130018 | 2018-07-16 | DHI-WTRAN-001402 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f6b6838-e4fc-40d0-acc3-59b0169538d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7842 | T16182-XG02-P0GNR-130103 | 2018-07-16 | DHI-TRANSMIT-001909 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=212754bc-144b-44c5-8d53-5a92d3624278 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7843 | T16182-YU03-P0GCF-130017 | 2018-07-16 | DHI-TRANSMIT-001909 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de178226-6c32-481c-b4af-8ece4318ae09 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7844 | T16182-CA03-P0UMY-185169 | 2018-07-16 | DHI-TRANSMIT-001910 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c736359-e274-4160-9f38-4e56e159749b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7845 | T16182-CA03-P0UMY-185170 | 2018-07-16 | DHI-TRANSMIT-001910 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82b6db20-d3cb-445c-a48c-b56c71362f7b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7846 | T16182-CA03-P0UMY-185175 | 2018-07-16 | DHI-TRANSMIT-001910 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=476f13ae-bbcb-4771-add7-010cd85a1440 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7847 | T16182-CA03-P0UMY-185177 | 2018-07-16 | DHI-TRANSMIT-001910 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0763be07-6199-4b43-9173-df815eb307dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7848 | T16182-YD02-P0ZEN-165506 | 2018-07-16 | DHI-TRANSMIT-001911 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84794c33-1534-4802-9542-5227e6d714de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7849 | T16182-YD02-P0ZEN-165523 | 2018-07-16 | DHI-TRANSMIT-001911 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7ff53ea-1fe3-4282-b2ec-71f0220f45d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7850 | T16182-YD00-P0BAT-150621 | 2018-07-16 | DHI-WTRAN-001403 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b772931-f059-4166-bd61-58ffa1fcf597 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7851 | T16182-YD00-P0BAT-150626 | 2018-07-16 | DHI-WTRAN-001403 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75d5f71d-b4c4-4d02-95b7-b8e78d37c358 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7852 | T16182-XH01-P0SGE-136712 | 2018-07-16 | DHI-TRANSMIT-001912 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=554544a0-c2cd-435a-b89a-95069361673b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7853 | T16182-XJ00-P0GHC-140213 | 2018-07-16 | DHI-TRANSMIT-001913 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbc06e06-cac6-47cf-ad7d-206151e6fb3f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7854 | T16182-XJ00-P0GM-140121 | 2018-07-16 | DHI-TRANSMIT-001913 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1eec45b2-a530-4934-848e-9fde805a3325 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7855 | T16182-VK02-P8UTH-172005 | 2018-07-17 | DHI-TRANSMIT-001914 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=341d31aa-2bd4-4a91-8a94-cbc2d6bb5618 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7856 | T16182-XB02-P8UTH-172003 | 2018-07-17 | DHI-TRANSMIT-001914 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=884abca6-b590-4867-957b-f56450d872db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7857 | T16182-XB02-P8UTH-172004 | 2018-07-17 | DHI-TRANSMIT-001914 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0da9fcac-2ed9-4941-b7d2-18950adf7d84 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7858 | T16182-DM01-P0LAC-126012 | 2018-07-17 | DHI-TRANSMIT-001919 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22dba813-5f79-4cab-bb3d-4345e0447e2f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7859 | T16182-UC02-P8QHA-125303 | 2018-07-17 | DHI-TRANSMIT-001920 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=495d903e-f270-4d03-834b-d7ed9ff8b6a0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7860 | T16182-CV03-P0LD-130219 | 2018-07-17 | DHI-WTRAN-001404 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79344fbc-e99e-4654-8ebd-4eac763847d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7861 | T16182-YE00-P0LD-130215 | 2018-07-17 | DHI-WTRAN-001404 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5bed05e8-32ec-438e-91f1-f5ffb6eaa722 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7862 | T16182-YR05-P0LD-130207 | 2018-07-17 | DHI-WTRAN-001404 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=deb5853a-7cab-4b95-a87d-f4ab2823ab72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7863 | T16182-XG02-P0LD-130204 | 2018-07-17 | DHI-TRANSMIT-001921 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ae95467-1b9b-4b2a-afad-e95116839840 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7864 | T16182-YD00-P0CYE-136741 | 2018-07-17 | DHI-TRANSMIT-001922 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b1a8bc8-d2b3-497e-bb76-cd3557aba856 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7865 | T16182-YU02-P0CYE-136742 | 2018-07-17 | DHI-TRANSMIT-001922 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eeef1a9a-4d60-4e1f-b8e9-04fb62de18fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7866 | T16182-XG02-P0LB-122022 | 2018-07-18 | DHI-TRANSMIT-001923 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edf73ac6-9400-40cf-9fa9-800d476bab05 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7867 | T16182-YK00-P0ZEN-165301 | 2018-07-18 | DHI-TRANSMIT-001925 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67d0117e-744d-479e-9319-2532ea68dfe5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7868 | T16182-VE04-P8UTH-172011 | 2018-07-18 | DHI-TRANSMIT-001926 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dabb3bc3-2036-40a0-8b65-a5f03fcb9407 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7869 | T16182-XB02-P8UTH-172013 | 2018-07-18 | DHI-TRANSMIT-001926 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0915ea23-ca25-4563-8687-e9f576f63649 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7870 | T16182-CA00-P0USG-182701 | 2018-07-18 | DHI-TRANSMIT-001927 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91a3c604-a7aa-4b81-9859-c02ed56abb3f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7871 | T16182-CA03-P1BAT-180512 | 2018-07-18 | DHI-TRANSMIT-001927 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11b9590d-0f7a-42fb-b562-76ef155e154e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7872 | T16182-XH01-P0GCF-130013 | 2018-07-19 | DHI-TRANSMIT-001929 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2ace195-c237-4fd1-ab91-76eacd2747df | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7873 | T16182-YE00-P0GCF-130015 | 2018-07-19 | DHI-TRANSMIT-001929 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b2571f8-526b-4ddb-abf4-a378a1c50bd6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7874 | T16182-YD00-P0BAA-150767 | 2018-07-19 | DHI-WTRAN-001405 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4ec235d-f92a-4318-8fd9-43fa246883c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7875 | T16182-YD00-P0BAA-150776 | 2018-07-19 | DHI-WTRAN-001405 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f3c333f-a3d8-490e-aeb0-9665113198fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7876 | T16182-YT01-P0BAA-150752 | 2018-07-19 | DHI-TRANSMIT-001930 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1db9b596-078f-47f0-821d-9a775ff77913 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7877 | T16182-YQ01-P0ZEN-152302 | 2018-07-19 | DHI-TRANSMIT-001931 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f91ff5cf-330d-4946-9757-f7b4ab27b913 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7878 | T16182-YQ01-P0ZEN-152321 | 2018-07-19 | DHI-TRANSMIT-001931 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9282afa-2581-48cc-845d-aea2f8462120 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7879 | T16182-YQ01-P0ZEN-152329 | 2018-07-19 | DHI-TRANSMIT-001931 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0fbdb538-8b21-4293-ab02-edaaa4468c90 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7880 | T16182-YQ01-P0ZEN-152316 | 2018-07-19 | DHI-TRANSMIT-001931 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f27f6e28-ac40-46a4-b8b8-e46fb2052a7a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7881 | T16182-CN00-P0ZEN-110701 | 2018-07-19 | DHI-TRANSMIT-001932 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad46ff3e-a1b0-40ed-be87-07551e2cd2b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7882 | T16182-DP00-P0ZEN-020009 | 2018-07-19 | DHI-WTRAN-001406 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9635de6d-b97c-46d3-8f1d-63c4436678df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7883 | T16182-YT10-P0MKY-290010 | 2018-07-20 | DHI-TRANSMIT-001933 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2db42627-259e-4e53-b994-6b13f4d640f9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7884 | T16182-YT01-P0ASS-155001 | 2018-07-20 | DHI-WTRAN-001407 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97e707fd-db9f-433b-b0ba-c5978f0a7751 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7885 | T16182-CA00-P0UCB-180614 | 2018-07-20 | DHI-TRANSMIT-001934 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35845be2-522c-45d2-9d10-38561c1d58f4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7886 | T16182-XG02-P0SGC-138201 | 2018-07-20 | DHI-TRANSMIT-001935 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de6df7e8-c4d0-4de8-a10b-b91f6f3e444c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7887 | T16182-YD00-P0CYE-137441 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c1ede7f-c3c6-4618-926e-7b051301e0fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7888 | T16182-YU02-P0CYE-137442 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf48f230-dd2a-4037-9172-34ef44b09743 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7889 | T16182-YD00-P0CYE-137941 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04e3e8a3-1bdf-4b02-b6f6-2db862c2d2bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7890 | T16182-YU02-P0CYE-137942 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5238767d-a832-478a-9dd7-ad653892f6da | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7891 | T16182-XG02-P0SGA-139301 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56bed711-9b6d-4378-9c88-344b5ec4e66f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7892 | T16182-XH01-P0SGA-139311 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ff55947-d9ef-47a9-b317-a854fb19e6a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7893 | T16182-XH01-P0SGC-138111 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60291e3b-e2c7-4aa6-829b-2dcf2c5537b8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7894 | T16182-YT10-P0SGC-138121 | 2018-07-20 | DHI-TRANSMIT-001936 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62dbf69b-be86-415a-a960-f52575ea5a7e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7895 | T16182-XK00-P8ZEN-125533 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e998dcf-303f-4058-9cf2-1b80b7d66c40 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7896 | T16182-XK00-P8ZEN-125535 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d925ecd-392d-4469-96bc-869d8d28fb14 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7897 | T16182-XJ00-P8ZEN-125520 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=788be13c-29a4-4134-b7d9-5dfc7bda4367 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7898 | T16182-XJ00-P8ZEN-125522 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4d24697-3afa-4293-96fd-b9ec03be8335 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7899 | T16182-XJ00-P8ZEN-125523 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d5ce8df-7f22-4a98-b88b-d18b872eaa0a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7900 | T16182-XJ00-P8ZEN-125525 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40116f62-a942-45da-bcbf-9a24efb184a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7901 | T16182-XJ00-P8ZEN-125542 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2380356-19c3-48a4-96d6-862038b0ec76 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7902 | T16182-XK00-P8ZEN-125531 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bac85b96-18e6-4628-b848-cce603883de0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7903 | T16182-XK00-P8ZEN-125532 | 2018-07-24 | DHI-TRANSMIT-001937 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11879473-9c1c-4ba7-a8ad-d740da01f740 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7904 | T16182-XH01-P0EKG-124002 | 2018-07-24 | DHI-TRANSMIT-001938 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a617e1a1-bc2e-443b-9c68-e27b4089e4c3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7905 | T16182-UB01-P0EKG-124075 | 2018-07-24 | DHI-TRANSMIT-001939 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c122801e-7644-403f-a180-eab1d9c9c4ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7906 | T16182-YM03-P8ZEN-125721 | 2018-07-25 | DHI-TRANSMIT-001940 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff6a1b68-eb4e-4b00-b6d4-d4ef2019ed2b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7907 | T16182-YT02-P0LAC-126011 | 2018-07-25 | DHI-WTRAN-001408 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fb78b95-5be4-421e-9a11-4845c1e9b23a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7908 | T16182-YT02-P0LAC-126061 | 2018-07-25 | DHI-WTRAN-001408 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=590d7479-6d15-4768-8677-a1e096f873c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7909 | T16182-XH01-P0LF-140415 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f10f013-aaaf-4f7b-971f-8cc03e63f337 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7910 | T16182-XH01-P0LF-140411 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6992e934-3439-4fc8-a9de-a669809ed69a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7911 | T16182-XH01-P0LF-140401 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d67d7594-e377-461b-8a72-82e7d2964fd2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7912 | T16182-XH01-P0LF-140402 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b0e3879-437b-4f44-b4f2-81d7d475d56a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7913 | T16182-XH01-P0LF-140403 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cb20127-dea1-4b04-ad2b-f2e25974f9c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7914 | T16182-XH01-P0LF-140404 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed451c29-895d-4790-89fc-45befd84fec0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7915 | T16182-XJ00-P0GM-140224 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8dcdbe44-0ffe-47f7-8a02-40b9971bf266 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7916 | T16182-XH01-P0LF-140408 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23717cef-e6f0-4704-ab30-36a4b7b0249b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7917 | T16182-XH01-P0LF-140406 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2abcc56-e236-452c-aa84-52f992024be0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7918 | T16182-XH01-P0LF-140412 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cca4e58-c94d-462e-825e-6c85f53d2f45 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7919 | T16182-XH01-P0LF-140407 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afbd47b4-bfa3-4b93-b5e0-d66c8786c58a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7920 | T16182-XH01-P0LF-140417 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92b3c254-43f4-4dfd-9361-29d37c057a53 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7921 | T16182-XH01-P0LF-140416 | 2018-07-25 | DHI-TRANSMIT-001941 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de7f426a-66ec-4987-87df-e66d3a578c75 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7922 | T16182-XB02-P0UZA-172904 | 2018-07-25 | DHI-TRANSMIT-001942 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83cc9f51-f32a-486e-9bc0-f527ebabc480 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7923 | T16182-XB02-P0GUC-172803 | 2018-07-25 | DHI-TRANSMIT-001943 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ecc8758-79e6-440a-b025-ec286a4915b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7924 | T16182-VK02-P0GUC-172804 | 2018-07-25 | DHI-TRANSMIT-001943 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7bf62a6-1da4-41d8-84cc-c9188bb7a256 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7925 | T16182-XB02-P0UZT-172702 | 2018-07-25 | DHI-TRANSMIT-001944 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66f9a69b-f83c-4f63-8f2f-fa7df41f4106 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7926 | T16182-XB02-P0UZT-172703 | 2018-07-25 | DHI-TRANSMIT-001944 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=befc7e0e-3926-494c-bb91-46ca1a248785 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7927 | T16182-VK02-P0UZT-172713 | 2018-07-25 | DHI-TRANSMIT-001944 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6484ef5b-3f06-4ae2-ad93-3b9bbc187e94 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7928 | T16182-VN02-P0LB-122090 | 2018-07-25 | DHI-WTRAN-001410 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf816784-2c49-4ada-9495-b080d89987e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7929 | T16182-YT10-P0SGA-136605 | 2018-07-25 | DHI-TRANSMIT-001945 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb122f2c-f635-4456-bc44-37ee25516b96 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7930 | T16182-YE03-P0BAU-152529 | 2018-07-25 | DHI-TRANSMIT-001946 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be2baa66-ad1c-43ab-9cfd-a6358e968211 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7931 | T16182-YE03-P0BAU-152530 | 2018-07-25 | DHI-TRANSMIT-001946 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7483b5f8-8654-4995-8064-144c99184b77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7932 | T16182-YE01-P0BAU-152609 | 2018-07-25 | DHI-TRANSMIT-001946 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=591be993-cd02-48b7-92a3-196e0979b972 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7933 | T16182-YD00-P0BBT-150671 | 2018-07-25 | DHI-WTRAN-001411 | IFI | 8 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef2831ae-c994-47a2-b7f4-94f6ad3f0eb8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7934 | T16182-CM01-P6MAA-220205 | 2018-07-25 | DHI-WTRAN-001412 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4d91943-3945-4cab-b1bd-3dc100605242 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7935 | T16182-XG01-P7MAA-220090 | 2018-07-25 | DHI-WTRAN-001412 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5beceb06-1a8d-4240-8bf0-24562e2721f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7936 | T16182-XH01-P0LB-122024 | 2018-07-25 | DHI-TRANSMIT-001947 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=550d6347-c2b1-4a18-b378-ea03f878b57b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7937 | T16182-XH01-P0LB-122025 | 2018-07-25 | DHI-TRANSMIT-001947 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e34e62e-e14f-4d0a-9c74-5ad4da574637 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7938 | T16182-XJ00-P0LB-122027 | 2018-07-25 | DHI-TRANSMIT-001947 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fedcb6e7-63eb-4c4b-add8-99ef657b1a45 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7939 | T16182-YT10-P0ASR-155011 | 2018-07-25 | DHI-WTRAN-001423 | IFR | A | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0bbf2e8-e2b9-4e4d-8c8f-e01c0c46fbd3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7940 | T16182-YD00-P0MKW-260001 | 2018-07-26 | DHI-TRANSMIT-001948 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a8297ec-9e1d-4672-ab96-440ea94a8e25 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7941 | T16182-YE00-P8ZEN-125751 | 2018-07-26 | DHI-TRANSMIT-001949 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bab4fec-b88e-4b4a-a1ce-5d37fa3c0b65 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7942 | T16182-YB11-P0ZEN-152402 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6152c98-0ed4-4efc-ab7d-935ce82fecc7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7943 | T16182-YB11-P0ZEN-152403 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d785385-fcce-41ed-8b52-3c74bae3fb98 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7944 | T16182-YB11-P0ZEN-152406 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc8f153d-2acc-4b77-aa40-813df8b5a667 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7945 | T16182-YB11-P0ZEN-152407 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37bffefa-d920-429c-8a3b-269b05aa2127 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7946 | T16182-YB11-P0ZEN-152418 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53c477ee-5a44-4e04-8e0c-b8743e41baf3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7947 | T16182-YB11-P0ZEN-152421 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2544f5a0-8b41-4d1b-9851-6f5ea6387c74 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7948 | T16182-YB11-P0ZEN-152422 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=94f90369-6f58-4cf9-8736-204bfaa96c0c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7949 | T16182-YB11-P0ZEN-152427 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9345752d-fabb-40ec-9aa9-fe407930b366 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7950 | T16182-YB11-P0ZEN-152428 | 2018-07-26 | DHI-TRANSMIT-001950 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d62ea603-561d-406d-9b56-2112a3d33b58 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7951 | T16182-YK09-P0SMS-128008 | 2018-07-26 | DHI-TRANSMIT-001951 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88367950-b14d-4da1-8c0b-724a1348eb2e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7952 | T16182-DM01-P0LAC-126062 | 2018-07-26 | DHI-TRANSMIT-001952 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f1282ce-25ff-4ea5-887d-3ff1e17a2453 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7953 | T16182-CQ02-P0MBA-121051 | 2018-07-27 | DHI-WTRAN-001424 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b110fbb7-920b-4236-a549-b38536a9ea1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7954 | T16182-CQ02-P0MBA-121073 | 2018-07-27 | DHI-WTRAN-001424 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b99d460a-2680-4598-a2cb-61edbcf5b3d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7955 | T16182-YT01-P0MBA-121677 | 2018-07-27 | DHI-WTRAN-001424 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdbf4341-8e28-46ed-91db-af303798580a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7956 | T16182-YT01-P0SAA-136005 | 2018-07-27 | DHI-WTRAN-001425 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47d0a7a9-ef1e-46ef-82d0-212d4a6d39dc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7957 | T16182-XJ00-P0ZEN-140119 | 2018-07-27 | DHI-TRANSMIT-001953 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=785083ee-19b9-41c1-9e56-ce7765aeb216 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7958 | T16182-XS00-P0GNR-130101 | 2018-07-27 | DHI-TRANSMIT-001954 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dca1a7c1-d807-4fba-8de7-736ba8fac30d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7959 | T16182-XG07-P0GNR-130102 | 2018-07-27 | DHI-TRANSMIT-001954 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3b2760ee-a35d-4941-8c81-da3bdf665130 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7960 | T16182-XG02-P0GNR-130103 | 2018-07-27 | DHI-TRANSMIT-001954 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65262958-4c33-44e5-a0da-94a0df538592 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7961 | T16182-XG02-P0GCF-130004 | 2018-07-27 | DHI-TRANSMIT-001954 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3439eb27-0a0e-4cc1-8212-e4476ca109bf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7962 | T16182-YQ08-P0CY-154053 | 2018-07-27 | DHI-WTRAN-001426 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f6b25e8-2609-4d6f-b0e6-f0df2590fe3e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7963 | T16182-YE00-P0ZEN-152792 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c0553d1-d3eb-4764-960e-8d89bf5e6192 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7964 | T16182-YE00-P0ZEN-152794 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83999b01-e51f-4fd5-b354-28fa61ee2b3d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7965 | T16182-YE00-P0ZEN-152795 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4f8fabc-088a-4147-a80c-6d9e8f594a2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7966 | T16182-DE00-P0CY-154001 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15e168a9-f6f1-4bb2-8d71-d6d3c7df0410 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7967 | T16182-YU02-P0CYA-154011 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ead124e-e78f-4439-bdcf-c6d835dbd498 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7968 | T16182-YU02-P0CYM-154013 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ade7891-fb88-463c-a82b-0d330eff4668 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7969 | T16182-YQ03-P0CY-154021 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec251958-3b36-4f5c-8448-078a952f315d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7970 | T16182-YQ08-P0CY-154031 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c0b1187-5181-496a-b687-e4a5019f79f1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7971 | T16182-YQ08-P0CY-154032 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68407291-e347-4de5-addc-ab63de377b2e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7972 | T16182-YQ08-P0CY-154033 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04469fdf-2c0b-4cc8-8511-edfa9b5ec674 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7973 | T16182-YQ08-P0CY-154034 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aefe02f5-ca23-4124-a600-4ecd3e0cf384 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7974 | T16182-YQ08-P0CY-154035 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=120df883-e6ef-41b6-814b-7f3c48cdcda0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7975 | T16182-YQ08-P0CY-154036 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57ea05d5-74a8-44a4-b686-040ce52e97db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7976 | T16182-YQ08-P0CY-154037 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6e39e73-610c-4d45-8749-82b204f432f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7977 | T16182-YQ08-P0CY-154038 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e717ebc-5a74-47c6-a6c4-19f52c07de2d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7978 | T16182-YQ08-P0CY-154039 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bcebcce-907d-4381-8e25-419a9c02f7ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7979 | T16182-YQ08-P0CY-154040 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f79da23-6823-4876-b7c8-d9846d524f79 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7980 | T16182-YQ08-P0CY-154041 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bba9458-6261-4a70-80e5-0bb1e119c425 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7981 | T16182-YQ08-P0CY-154042 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=269feae4-bd63-4d8a-9d01-4ad65b98941c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7982 | T16182-YQ08-P0CY-154044 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb32307b-2476-47f3-976f-5547011f866e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7983 | T16182-YQ08-P0CY-154045 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=710ae8b2-44fe-4735-a77e-3814d27b7971 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7984 | T16182-YQ08-P0CY-154049 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=550f4e58-7371-4c21-b6c3-6f1e5843587a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7985 | T16182-YQ08-P0CY-154051 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bc639a1-87ad-4390-957d-9cb276fc2af3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7986 | T16182-YQ08-P0CY-154052 | 2018-07-27 | DHI-TRANSMIT-001955 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ddb5d8f0-e785-409d-bc6d-ccec7be5a532 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7987 | T16182-XG02-P0SGA-139601 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 1 | D | TRUE | FALSE | 2018-07-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f2f62f9-f7b9-45bc-956a-79994c1d059d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7988 | T16182-XG02-P0SGE-139603 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 1 | D | TRUE | FALSE | 2018-07-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d4f4f7c-ba0c-4031-859d-dbe3032b41a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7989 | T16182-XH01-P0SGE-139613 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 2 | D | TRUE | FALSE | 2018-07-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c8c6794-b1ee-4f6b-9e47-cf9b716ffac1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7990 | T16182-XG02-P0SGA-139401 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58a3767c-b3a6-401c-9317-20e349bafe6f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7991 | T16182-XH01-P0SGA-139411 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46eb40b4-1ae0-4743-873f-47192f559f77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7992 | T16182-XG02-P0SGC-137401 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 2 | D | TRUE | FALSE | 2018-07-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae75b4ff-b82d-4619-ab98-d6b694632c67 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7993 | T16182-XG02-P0SGC-138101 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e529559-a609-478d-a289-b039a79ce42f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7994 | T16182-YD00-P0SGZ-137331 | 2018-07-27 | DHI-TRANSMIT-001956 | IFC | 4 | D | TRUE | FALSE | 2018-07-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c76aace-ac22-4360-8089-bbf2179e2b97 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7995 | T16182-UT01-P0GQB-173402 | 2018-07-27 | DHI-TRANSMIT-001957 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2943c031-9b63-4dd4-a662-aaf4dcf9d842 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7996 | T16182-UT01-P0GQB-173403 | 2018-07-27 | DHI-TRANSMIT-001957 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad2821a8-2c8f-47de-90b1-9d205d97bce3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7997 | T16182-UT01-P0GQB-173413 | 2018-07-27 | DHI-TRANSMIT-001957 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=143d53a3-32c7-4e1f-b18d-42b97ab4dea3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7998 | T16182-XH01-P0LF-140421 | 2018-07-27 | DHI-WTRAN-001427 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3262ed70-ae65-48ba-8034-696b60aa898a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
7999 | T16182-XH01-P0LF-140422 | 2018-07-27 | DHI-WTRAN-001427 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e952564-4346-4f24-aed1-0da4a126aecb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8000 | T16182-XH01-P0SGK-138512 | 2018-07-27 | DHI-TRANSMIT-001958 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a99c2ba-9f72-4798-a0cf-f46c58b9f8e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8001 | T16182-YT01-P0LBG-110251 | 2018-07-27 | DHI-WTRAN-001428 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26124252-d64b-46c8-bc3d-08a12c029f4f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8002 | T16182-YK08-P0LBG-110252 | 2018-07-27 | DHI-TRANSMIT-001959 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8844159-b779-484c-8513-b398ecff5a42 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8003 | T16182-YT01-P0MBA-121023 | 2018-07-27 | DHI-WTRAN-001429 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c1143f5-d515-4e51-8e63-87df5243bb2f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8004 | T16182-XB02-P0UHA-171815 | 2018-07-27 | DHI-TRANSMIT-001960 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67644d78-addb-4e9b-bf88-fe82a6a1b60b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8005 | T16182-XB02-P0UHA-171816 | 2018-07-27 | DHI-TRANSMIT-001960 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83c66148-b29c-4ecf-9ead-fb61887145a6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8006 | T16182-YQ03-P0CY-154021 | 2018-08-06 | DHI-TRANSMIT-001967 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=34b96c8e-6527-4c2b-9da3-d3689a4d0840 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8007 | T16182-DN05-P0SG-136623 | 2018-08-07 | DHI-WTRAN-001430 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65c4694e-2784-4537-94cb-33f468dc51d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8008 | T16182-XN00-P0LD-130208 | 2018-08-07 | DHI-WTRAN-001431 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61e3f346-86fd-495b-a807-a1f9ef28bc8f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8009 | T16182-YD00-P0LD-130202 | 2018-08-07 | DHI-TRANSMIT-001971 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4021f165-1522-457c-b84d-cb787e042c52 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8010 | T16182-XH01-P0SGE-139512 | 2018-08-07 | DHI-TRANSMIT-001972 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f64c198b-7da5-4de3-ac1a-b3481ae651f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8011 | T16182-XF00-P8ZEN-125729 | 2018-08-08 | DHI-TRANSMIT-001973 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca6f6346-2358-4ece-976a-73712c1636aa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8012 | T16182-YL01-P0MBA-121022 | 2018-08-08 | DHI-WTRAN-001432 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0925d3b-6fbd-43e3-9987-174c88636f91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8013 | T16182-CV03-P8ZEN-125606 | 2018-08-09 | DHI-TRANSMIT-001974 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d46340f7-53fd-4a4d-92c2-ddaeb724f62b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8014 | T16182-YS00-P0MBA-121678 | 2018-08-09 | DHI-WTRAN-001433 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff625d5a-211c-4008-93c0-c75858a287ae | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8015 | T16182-YD00-P0CYE-139641 | 2018-08-09 | DHI-TRANSMIT-001975 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93f87b28-71dc-4690-9487-e67b13cc835b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8016 | T16182-YU02-P0CYE-139642 | 2018-08-09 | DHI-TRANSMIT-001975 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccef0aa1-8edc-4bab-86d8-99aa464d0a00 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8017 | T16182-XH01-P0SGC-137211 | 2018-08-09 | DHI-TRANSMIT-001976 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4de03005-e448-469e-9b65-358324293e3e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8018 | T16182-XG02-P0QJA-110012 | 2018-08-09 | DHI-TRANSMIT-001977 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e57413a3-ef3a-4702-997e-c03f36bb3951 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8019 | T16182-VE04-P0UZT-173001 | 2018-08-10 | DHI-TRANSMIT-001978 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c062371-ca7d-4810-85f1-5d8641bfd02f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8020 | T16182-XB02-P0UZT-173002 | 2018-08-10 | DHI-TRANSMIT-001978 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebacde0e-cf9d-46f1-a5b5-cce16351fb6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8021 | T16182-XB02-P0UZT-173003 | 2018-08-10 | DHI-TRANSMIT-001978 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f816bc2-db44-4761-8865-db5f51e124ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8022 | T16182-VK02-P0UZT-173008 | 2018-08-10 | DHI-TRANSMIT-001978 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a96b1c80-3967-496f-8b2c-e04b4ca9429e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8023 | T16182-YT10-P0ZEN-152212 | 2018-08-10 | DHI-WTRAN-001434 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=958af8bc-609f-4d71-b0d6-9dbb53650f9c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8024 | T16182-UC07-P0ZEN-100001 | 2018-08-10 | DHI-TRANSMIT-001979 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3af6c383-eb15-42ed-bab0-b4461f302cb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8025 | T16182-UC07-P0ZEN-100002 | 2018-08-10 | DHI-TRANSMIT-001979 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23755abc-5197-4b3d-8dda-c4e02d2aef8e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8026 | T16182-UC07-P0ZEN-100003 | 2018-08-10 | DHI-TRANSMIT-001979 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b863ee47-89d0-4d86-966f-7b684cd93f0f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8027 | T16182-YK00-P0GCF-130016 | 2018-08-13 | DHI-WTRAN-001435 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76e7ae5d-1cbc-48ce-af0c-e3dc97e9e16a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8028 | T16182-YB03-P0EKG-124180 | 2018-08-13 | DHI-WTRAN-001436 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ab8e883-edb9-4622-8a98-c1e3aa4e9a53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8029 | T16182-CV03-P8SGK-125650 | 2018-08-13 | DHI-TRANSMIT-001981 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=561b83c7-c737-4aca-b69d-f87c473fd0af | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8030 | T16182-XH02-P8QHL-125400 | 2018-08-13 | DHI-TRANSMIT-001982 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9007a3e-5ce0-4ae7-b864-101ca7c947e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8031 | T16182-YD00-P0EKG-124009 | 2018-08-13 | DHI-WTRAN-001437 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d704f52-b043-4e74-a2eb-e8f079c95f21 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8032 | T16182-CA00-P0UST-182001 | 2018-08-14 | DHI-TRANSMIT-001984 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e84f2b3-b144-4cad-8282-7abc266db649 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8033 | T16182-CA00-P0UST-182005 | 2018-08-14 | DHI-TRANSMIT-001984 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=931241e4-4f69-4923-964e-ea03b70c92f9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8034 | T16182-YU03-P0BB-150836 | 2018-08-14 | DHI-WTRAN-001438 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d3eaf92-980b-416a-bea2-bee21ff9a373 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8035 | T16182-XG02-P0LAA-110009 | 2018-08-14 | DHI-TRANSMIT-001985 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac237680-5738-42e5-b072-76f42563d05b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8036 | T16182-XG02-P1EKC-110014 | 2018-08-14 | DHI-TRANSMIT-001985 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58c6b7a7-4782-4b74-9e5d-77e50b911a7c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8037 | T16182-XG02-P6LCA-110008 | 2018-08-14 | DHI-TRANSMIT-001985 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a71fc48-c238-4334-9739-b5574a6b2335 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8038 | T16182-YK10-P0LCP-410001 | 2018-08-14 | DHI-TRANSMIT-001986 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39920955-45dd-4d8c-8232-62f51aa0b61c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8040 | T16182-XG02-P0GKB-120001 | 2018-08-16 | DHI-TRANSMIT-001988 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc254363-4fea-4912-aff4-bccfff46065e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8041 | T16182-VK02-P0UZA-172908 | 2018-08-16 | DHI-TRANSMIT-001989 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea2320d9-3e85-4dd7-b9f1-7d3a47b12615 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8042 | T16182-YM01-P0GHC-129035 | 2018-08-16 | DHI-WTRAN-001439 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74f1ad41-8969-4a08-8114-136130f9763d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8043 | T16182-YU03-P0CHB-151121 | 2018-08-17 | DHI-WTRAN-001440 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb116735-0abf-4a8d-908b-cdb16cd4f728 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8044 | T16182-CA03-P0UMY-185169 | 2018-08-17 | DHI-TRANSMIT-001990 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7febe9b3-e095-4f9c-af99-c1e6c97b2a60 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8045 | T16182-CA03-P0UMY-185175 | 2018-08-17 | DHI-TRANSMIT-001990 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e866c04e-9d7f-4796-ae6d-0496b96f3725 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8046 | T16182-XG07-P0ZEN-120050 | 2018-08-17 | DHI-TRANSMIT-001991 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a2f0f87-305a-4ee8-9bf6-11c309f75e53 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8047 | T16182-YT10-P0ZEN-150312 | 2018-08-17 | DHI-TRANSMIT-001992 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cb0254a-449e-45cf-9746-9dd09f376187 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8048 | T16182-YL00-P0ZEN-163101 | 2018-08-17 | DHI-TRANSMIT-001993 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e0c7c6a-f72f-4442-a5d7-ea2bbe4074f4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8049 | T16182-CV03-P0ZEN-163103 | 2018-08-17 | DHI-TRANSMIT-001993 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d1883de-b934-4054-8a2c-e936cf5e1bf5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8050 | T16182-CV03-P0ZEN-163104 | 2018-08-17 | DHI-TRANSMIT-001993 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b82f520b-bfd2-40fc-ae49-26bfc4552352 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8051 | T16182-CV03-P0ZEN-163102 | 2018-08-17 | DHI-TRANSMIT-001993 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b19d7b9-f7bb-45a0-89aa-2fabd614867c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8052 | T16182-XB02-P0GUB-173302 | 2018-08-17 | DHI-TRANSMIT-001994 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53fdac10-614f-41b0-8a3c-24e56361e4be | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8053 | T16182-XB02-P0GUB-173303 | 2018-08-17 | DHI-TRANSMIT-001994 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=194516b9-3735-4f9c-a7bd-3e96336d6c06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8054 | T16182-VK02-P0GUB-173313 | 2018-08-17 | DHI-TRANSMIT-001994 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ce11c5d-7884-447f-aac5-077553c2c14f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8055 | T16182-YT01-P0LD-130214 | 2018-08-20 | DHI-WTRAN-001441 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be39dffe-0308-441e-b9a3-bdf80063f3e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8056 | T16182-YF00-P0PCA-126522 | 2018-08-20 | DHI-WTRAN-001442 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=630dd7cc-4afe-4fac-9fff-652d4cdf6e45 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8057 | T16182-YU03-P0BB-150831 | 2018-08-20 | DHI-WTRAN-001443 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63925933-c96f-45cc-956c-0f4d987689e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8058 | T16182-YU02-P0BB-150811 | 2018-08-20 | DHI-WTRAN-001443 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44ca6828-0845-4a3a-94fa-f3bcbc520e58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8059 | T16182-YU02-P0BB-150812 | 2018-08-20 | DHI-WTRAN-001443 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b678697-b97d-4e72-87bd-9e5ee73ee796 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8060 | T16182-YU02-P0BB-150813 | 2018-08-20 | DHI-WTRAN-001443 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73419130-46de-4929-8857-f188e03645cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8061 | T16182-YU02-P0BB-150814 | 2018-08-20 | DHI-WTRAN-001443 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b649f2cc-9493-40fd-a8b4-2b2550a4fb2a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8062 | T16182-YU02-P0BB-150815 | 2018-08-20 | DHI-WTRAN-001443 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3052ef33-656b-468e-8f25-94cdbcd56727 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8063 | T16182-YU02-P0BB-150816 | 2018-08-20 | DHI-WTRAN-001443 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0cecded-c890-4132-b7ab-4c59e2631696 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8064 | T16182-YT01-P0MBA-121023 | 2018-08-22 | DHI-WTRAN-001444 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8065 | T16182-XB02-P0UZA-172902 | 2018-08-22 | DHI-TRANSMIT-002000 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22826517-d091-4031-a07a-f58414ac452b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8066 | T16182-XB02-P0UZA-172903 | 2018-08-22 | DHI-TRANSMIT-002000 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d119cce-069e-473e-ada3-47b3e928b824 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8067 | T16182-CM01-P7MAA-220206 | 2018-08-22 | DHI-WTRAN-001445 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a4fbd2d-a885-4702-9cb5-4ab1636a3284 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8068 | T16182-YR00-P6MAA-220073 | 2018-08-22 | DHI-WTRAN-001445 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2b6c567-3e0c-42c3-bf81-06d9accbda66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8069 | T16182-YD00-P0EKG-124018 | 2018-08-22 | DHI-WTRAN-001446 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89842cd0-c601-45a7-8ea8-e028d4c0e9f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8070 | T16182-DM01-P0LAC-126012 | 2018-08-22 | DHI-TRANSMIT-002001 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80035460-1144-4e76-8e3b-2efcc101fc94 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8071 | T16182-DM01-P0LAC-126062 | 2018-08-22 | DHI-TRANSMIT-002001 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af5eed93-4acc-400d-bbca-8e4d6bd10f36 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8072 | T16182-VK02-P0GUB-173313 | 2018-08-22 | DHI-TRANSMIT-002002 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=942451d4-b40e-4971-b4f7-6b3561dd87cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8073 | T16182-UE00-P0MB-100004 | 2018-08-22 | DHI-TRANSMIT-002003 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39607744-0f0e-4004-8c7d-4453740ca6af | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8074 | T16182-UE00-P0MB-100005 | 2018-08-22 | DHI-TRANSMIT-002003 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=201e69bc-c739-4acf-b0d5-77de20bf7503 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8075 | T16182-UE00-P0MB-100006 | 2018-08-22 | DHI-TRANSMIT-002003 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7edaa692-913a-4185-a8e1-6adf06d723b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8076 | T16182-UE00-P0MB-100007 | 2018-08-22 | DHI-TRANSMIT-002003 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9977141c-a821-47ce-830d-727f2c159589 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8077 | T16182-UE00-P0UMA-100008 | 2018-08-22 | DHI-TRANSMIT-002003 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73554803-cb48-41c7-b68e-688435746a22 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8078 | T16182-UE00-P0UMA-100009 | 2018-08-22 | DHI-TRANSMIT-002003 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67901896-1e26-41fb-8e75-8e6d6408a69d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8079 | T16182-UE00-P0UMA-100010 | 2018-08-22 | DHI-TRANSMIT-002003 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8dcb6c95-495e-4b51-aed2-18242badf035 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8080 | T16182-YD04-P0ZEN-152004 | 2018-08-23 | DHI-TRANSMIT-002004 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cd76976-90d9-4af8-9c16-91b199104eca | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8081 | T16182-YS01-P0MKY-290008 | 2018-08-24 | DHI-TRANSMIT-002005 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=052cb7a0-58ae-4395-b8ad-59c4fe6dcb9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8082 | T16182-YS01-P0MKY-290009 | 2018-08-24 | DHI-TRANSMIT-002005 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aab82251-84e7-4f8f-a982-b7e704b2bf28 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8083 | T16182-YD02-P0SAC-163415 | 2018-08-24 | DHI-TRANSMIT-002006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab003b8f-b9be-466a-b6a4-e91fd348e5b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8084 | T16182-YD02-P0SAC-163416 | 2018-08-24 | DHI-TRANSMIT-002006 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e0cf001-119f-4cb4-b451-cd1e08ee9a1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8039 | T16182-XG02-P0LB-122022 | 2018-08-27 | DHI-TRANSMIT-002007 | IFC | 3 | D | TRUE | FALSE | 2018-08-27_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6e5c5b3-c987-4e98-9260-25a0960d1643 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8085 | T16182-YQ08-P0CY-154037 | 2018-08-27 | DHI-TRANSMIT-002008 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8179fc98-9cca-453a-a7ad-c8ead24ec56a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8086 | T16182-YD00-P0MAG-123051 | 2018-08-28 | INT-IFC-180828-01 | INTERNAL IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64111098-3bc2-4b7c-b50b-ccfc08fb7e49 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8087 | T16182-XW03-P0SAF-134701 | 2018-08-28 | DHI-TRANSMIT-002009 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53027fdd-b834-45db-b1cb-0b0770a2d80d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8088 | T16182-XG07-P0SAF-134702 | 2018-08-28 | DHI-TRANSMIT-002009 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7dae14c-7f8d-4df1-a1b7-cc0a5804a2f3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8089 | T16182-XH02-P0SAF-134704 | 2018-08-28 | DHI-TRANSMIT-002009 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2518025-e7b4-4aea-977a-dcb0cc286f77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8090 | T16182-XH02-P0SAQ-135204 | 2018-08-28 | DHI-TRANSMIT-002009 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebe7bb92-b096-47ed-8ebe-22edd5dcc7f5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8091 | T16182-XH02-P0SAM-135004 | 2018-08-28 | DHI-TRANSMIT-002009 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6903ee83-2613-4ff0-97be-ad27eeda653f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8092 | T16182-YD02-P0ZEN-165518 | 2018-08-28 | DHI-TRANSMIT-002010 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d143258-d4c0-4970-b4ad-ed2382c7fe87 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8093 | T16182-YR05-P0LD-130207 | 2018-08-28 | DHI-WTRAN-001447 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab3ff9eb-a7da-4954-9108-76c874c498e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8094 | T16182-YU03-P0LD-130217 | 2018-08-28 | DHI-WTRAN-001447 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84ce5737-6590-47c5-b5dd-2a7dcba56021 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8095 | T16182-XB02-P0UEG-171502 | 2018-08-28 | DHI-TRANSMIT-002011 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce992423-d413-4b38-8692-0719a5e359bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8096 | T16182-XB02-P0UEG-171504 | 2018-08-28 | DHI-TRANSMIT-002011 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=322832dc-bf08-4272-88b1-f1111219e4e2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8097 | T16182-YD00-P0CYE-137441 | 2018-08-28 | DHI-TRANSMIT-002012 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf40ad9b-b6ea-4a54-8538-d632f484f97f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8098 | T16182-XG07-P0SAH-133402 | 2018-08-30 | DHI-TRANSMIT-002014 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc74727e-3d63-4056-84ee-4bfa58918d74 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8099 | T16182-XH02-P0SAH-133404 | 2018-08-30 | DHI-TRANSMIT-002014 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29241731-c27c-46f5-9818-6e1f6c691fc0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8100 | T16182-XH02-P0SAB-134804 | 2018-09-03 | DHI-TRANSMIT-002016 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfaf2003-d4d6-4af7-ad6c-efcc13c2e386 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8101 | T16182-YR02-P0ZEN-150001 | 2018-09-03 | DHI-TRANSMIT-002017 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b98ce4ea-9031-4258-86e4-64401fbafa4a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8102 | T16182-YD02-P0SAC-163426 | 2018-09-03 | DHI-WTRAN-001452 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4984875-b574-48ee-b6f3-453ce163cc10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8103 | T16182-VK02-P0UZT-173008 | 2018-09-03 | DHI-TRANSMIT-002018 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7398718-c394-46c9-b506-59d92e053b42 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8104 | T16182-XB02-P0UZT-173002 | 2018-09-03 | DHI-TRANSMIT-002018 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=521a0d40-cea2-4318-a6a7-a6e34dc36b89 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8105 | T16182-XB02-P0UZT-173003 | 2018-09-03 | DHI-TRANSMIT-002018 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a37a608e-41ee-4f3f-8359-6b88e2441f26 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8106 | T16182-YQ01-P0ZEN-152201 | 2018-09-03 | DHI-TRANSMIT-002019 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69244db1-ec6b-4a6d-be50-aee6b63a25a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8107 | T16182-YQ01-P0ZEN-152306 | 2018-09-03 | DHI-TRANSMIT-002019 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be2fe5bb-0567-40ac-b912-99ab173e4310 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8108 | T16182-YQ01-P0ZEN-152316 | 2018-09-03 | DHI-TRANSMIT-002019 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52702edd-6dc2-42e5-9d88-0611012f2507 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8109 | T16182-XH01-P0LF-140423 | 2018-09-03 | DHI-WTRAN-001453 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bf70af3-2b80-407b-9fee-6c1e63954d6c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8110 | T16182-XJ00-P0SCA-140210 | 2018-09-03 | DHI-TRANSMIT-002020 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=655d6bbe-ef33-42cf-bcf3-5601a44c0be4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8111 | T16182-XW03-P0SAK-133601 | 2018-09-03 | DHI-TRANSMIT-002021 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=294f4843-3e93-4863-bb0e-8ff65fada9ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8112 | T16182-XG07-P0SAK-133602 | 2018-09-03 | DHI-TRANSMIT-002021 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8cb8188-667c-4f29-9851-3e517874a4b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8113 | T16182-XW03-P0SAK-133603 | 2018-09-03 | DHI-TRANSMIT-002021 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0ce92a5-f32b-49d3-92f5-59c94573d8b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8114 | T16182-XH02-P0SAK-133604 | 2018-09-03 | DHI-TRANSMIT-002021 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0842894-dae5-498e-a506-06af891c0252 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8115 | T16182-VK02-P0UZA-172908 | 2018-09-03 | DHI-TRANSMIT-002022 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e95158a-4619-414b-8c7b-e4a3e85460ab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8116 | T16182-XB02-P0UZA-172902 | 2018-09-03 | DHI-TRANSMIT-002022 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3e78848-3cb4-4617-9db2-e765830f128f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8117 | T16182-XB02-P0UZA-172903 | 2018-09-03 | DHI-TRANSMIT-002022 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c43792b7-7f66-415e-913c-73ec2e5a996d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8118 | T16182-YD00-P0CYE-139341 | 2018-09-03 | DHI-TRANSMIT-002023 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a97d0b94-603d-4392-b27a-50f166eeb192 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8119 | T16182-YU02-P0CYE-139342 | 2018-09-03 | DHI-TRANSMIT-002023 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=956b90f6-c4e7-4289-866d-36c50c863bc4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8120 | T16182-XH01-P0SGA-138911 | 2018-09-03 | DHI-TRANSMIT-002023 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bc1a38a-6836-4671-a4bb-13bfedc7a1b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8121 | T16182-XJ00-P0GHC-140213 | 2018-09-04 | DHI-TRANSMIT-002024 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24c9c67a-d297-42da-a8f0-6679b3203c7d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8122 | T16182-XJ00-P0QFB-140211 | 2018-09-04 | DHI-TRANSMIT-002024 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87b91367-c067-4edd-af22-3ac3341071dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8123 | T16182-VK02-P0GUC-172804 | 2018-09-04 | DHI-TRANSMIT-002025 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72cd56ca-3a3d-4b5a-9cbe-16d43ab3dab0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8124 | T16182-XB02-P0GUC-172803 | 2018-09-04 | DHI-TRANSMIT-002025 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15b5eca4-154e-46f0-b6d0-c3d7168c5d3d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8125 | T16182-XB02-P0GUC-172802 | 2018-09-04 | DHI-TRANSMIT-002025 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=617d4222-da94-4e10-a6f2-ba627c53334d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8126 | T16182-XH01-P0SGA-138411 | 2018-09-04 | DHI-TRANSMIT-002026 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0370e237-bdc1-423b-8ec7-312d7476854a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8127 | T16182-XG02-P0GNR-130103 | 2018-09-04 | DHI-TRANSMIT-002027 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0061c150-f1ff-4c24-8acc-e16a74f84ceb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8128 | T16182-CA03-P0ULA-182154 | 2018-09-04 | DHI-TRANSMIT-002028 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68d847c6-22c8-4b89-a97f-2382124e2a7e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8129 | T16182-YT01-P0LB-122099 | 2018-09-04 | DHI-WTRAN-001455 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bb292b7-8162-4ca8-b4cf-a20569793268 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8130 | T16182-DA01-P0ZEN-020002 | 2018-09-04 | DHI-WTRAN-001456 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6af25ce5-f2ea-4ce2-9186-263b318dba0a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8131 | T16182-XJ00-P0QCA-140221 | 2018-09-05 | DHI-TRANSMIT-002029 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a37c9f25-b747-4110-98e8-3438a0cc93e7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8132 | T16182-XJ00-P0QUB-140219 | 2018-09-05 | DHI-TRANSMIT-002029 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9998d0ba-a6c7-41fd-a8bb-447e9d2f0d26 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8133 | T16182-BP00-P0LBA-140011 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6486b58-02fb-46d2-b3d8-6508c1859380 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8134 | T16182-XJ00-P0LBA-140201 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4603ba07-afbc-43e6-84b4-e57dc7aecc24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8135 | T16182-XJ00-P0LBC-140202 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d5267d7-4e11-450e-8a40-c85d4f152aba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8136 | T16182-XJ00-P0LBG-140203 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ddf23d34-0a41-4bd9-992c-22a9a1bb40fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8137 | T16182-XJ00-P0GKB-140212 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d716bd1d-7d2e-4095-9d74-41994101b8e7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8138 | T16182-XJ00-P0MBH-140216 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b42fdaf5-ef9f-41e9-add7-f780f143dbf5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8139 | T16182-XJ00-P0EKC-140217 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fedbaf2-dc1d-4785-8ca5-33025ace97b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8140 | T16182-XJ00-P0QJA-140223 | 2018-09-06 | DHI-TRANSMIT-002030 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eaaee502-314d-4f7f-bf15-73190cf1e282 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8141 | T16182-YD00-P0SMS-128002 | 2018-09-07 | DHI-TRANSMIT-002031 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e0f8999-258f-4021-807f-f92fe625bb8c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8142 | T16182-YT02-P0PCA-126529 | 2018-09-07 | DHI-WTRAN-001457 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25f75661-74f9-42b2-bdfd-65a31be36aaa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8143 | T16182-XH02-P0SAR-134104 | 2018-09-07 | DHI-TRANSMIT-002032 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00538781-5863-406a-a834-00bcd5d2700d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8144 | T16182-XW03-P0SAR-134103 | 2018-09-07 | DHI-TRANSMIT-002032 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8f7614c-6dca-4bd5-a785-ceb9aa60101d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8145 | T16182-XH02-P0SAR-134204 | 2018-09-07 | DHI-TRANSMIT-002033 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2078b53-6668-41cb-8a76-ab6ccc6da467 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8146 | T16182-VK02-P0UZJ-173208 | 2018-09-07 | DHI-TRANSMIT-002034 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd300efa-20fc-49d5-8c10-3c7513b31bc7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8147 | T16182-XB02-P0UZJ-173202 | 2018-09-07 | DHI-TRANSMIT-002034 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0089e874-d494-49b9-8d63-67245b10d7bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8148 | T16182-YD00-P0CYE-136741 | 2018-09-07 | DHI-TRANSMIT-002035 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=181174c0-98ae-4df5-8d28-77029330fa1d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8149 | T16182-YU02-P0CYE-136742 | 2018-09-07 | DHI-TRANSMIT-002035 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d4518b3-92f7-41d9-8b77-f3b037a89e05 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8150 | T16182-YK08-P0ZEN-020008 | 2018-09-07 | DHI-TRANSMIT-002036 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4249aead-6b37-4c52-9ec0-89b928ad8dd1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8151 | T16182-YT10-P0ASR-155011 | 2018-09-07 | DHI-TRANSMIT-002037 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fcb3069f-5efd-4bc8-b313-8607069ece2e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8152 | T16182-YT01-P0MBA-121971 | 2018-09-10 | DHI-WTRAN-001458 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a38b28b-74a0-4e9b-a7fc-0b70f736e94c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8153 | T16182-YD02-P0SAC-163412 | 2018-09-10 | DHI-TRANSMIT-002038 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e0fa015-cdc7-46cd-8da4-65c5a6618dbc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8154 | T16182-YD02-P0SAC-163415 | 2018-09-10 | DHI-TRANSMIT-002038 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca058ed2-d268-44d2-b2eb-26c659c7a0f1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8155 | T16182-YD02-P0SAC-163418 | 2018-09-10 | DHI-TRANSMIT-002038 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b16168d1-0d94-4bc2-adbd-69c06bf9c912 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8156 | T16182-YR01-P8ZEN-125597 | 2018-09-10 | DHI-WTRAN-001459 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4486bf6a-1516-47cc-a519-862637731f90 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8157 | T16182-YD02-P0LB-122063 | 2018-09-10 | DHI-TRANSMIT-002039 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=598fe9d7-a72c-4236-a1e5-24373264f1b6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8158 | T16182-XG02-P0GM-120008 | 2018-09-11 | DHI-TRANSMIT-002041 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b8811af-7717-4602-97c1-a6c78cb26205 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8159 | T16182-YQ01-P0ZEN-152332 | 2018-09-11 | DHI-TRANSMIT-002042 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61a1392c-4b26-4e06-9645-7d31ee08f9a2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8160 | T16182-UT01-P0GQB-173413 | 2018-09-12 | DHI-TRANSMIT-002043 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e8b7f87-c489-4843-9cce-3f5144e166c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8161 | T16182-YD00-P0CYE-138141 | 2018-09-12 | DHI-TRANSMIT-002044 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b1dfd7a-d92e-4923-89ca-f381391f1d6a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8162 | T16182-XH01-P0EKG-124002 | 2018-09-13 | DHI-TRANSMIT-002045 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db6d034b-f399-4381-a0b9-34a0bf251d77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8163 | T16182-XJ00-P0LB-122028 | 2018-09-13 | DHI-TRANSMIT-002046 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71b18422-3935-4bbd-9a8e-38266dec3bdd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8164 | T16182-YT10-P0ZEN-150304 | 2018-09-13 | DHI-TRANSMIT-002047 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9313cd4d-d82d-48be-babf-2832bd7c986e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8165 | T16182-XJ00-P0LCA-140206 | 2018-09-14 | DHI-TRANSMIT-002048 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66d9bb51-ae53-4509-b5ba-3df6d2266448 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8166 | T16182-XG02-P0QU-130403 | 2018-09-14 | DHI-TRANSMIT-002049 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=148eeb88-056b-4896-8dfc-1fbda5b16a7d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8167 | T16182-YE03-P0BAU-152505 | 2018-09-14 | DHI-TRANSMIT-002050 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=914c98b9-068e-4361-83e7-4b760436f014 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8168 | T16182-YE03-P0BAU-152506 | 2018-09-14 | DHI-TRANSMIT-002050 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9e40923-70d9-4660-8763-3d36caf25779 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8169 | T16182-YE03-P0BAU-152532 | 2018-09-14 | DHI-TRANSMIT-002050 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dabc955d-6a75-4504-82d0-40ea657ae790 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8170 | T16182-YE03-P0BAU-152533 | 2018-09-14 | DHI-TRANSMIT-002050 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e339eda2-36d8-482f-8b4e-71cd8f3a9668 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8171 | T16182-XG02-P0SGC-137401 | 2018-09-14 | DHI-TRANSMIT-002051 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e32a300-4fb3-40a2-b817-c53ad714e774 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8172 | T16182-XH01-P0SGC-137411 | 2018-09-14 | DHI-TRANSMIT-002051 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc990792-84ca-4a00-9741-76915c784b93 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8173 | T16182-YD00-P0SGZ-136631 | 2018-09-18 | DHI-TRANSMIT-002054 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53863950-d3fa-419a-894e-bf67e7ee44b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8174 | T16182-BV02-P0ZEN-020040 | 2018-09-18 | DHI-WTRAN-001461 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=579ec724-da93-4959-9298-1c7d268f84b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8175 | T16182-XH01-P0SGE-139512 | 2018-09-18 | DHI-TRANSMIT-002055 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d26f0cc0-3342-4684-a3f0-174512c1a6b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8176 | T16182-YD00-P0UBA-150502 | 2018-09-18 | DHI-TRANSMIT-002056 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0500bcae-19b8-445a-a750-5ee3ac7f40df | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8177 | T16182-YD00-P0UCA-150501 | 2018-09-18 | DHI-TRANSMIT-002056 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66251342-4579-434c-a284-78732009904f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8178 | T16182-BV02-P0CJN-290003 | 2018-09-19 | DHI-WTRAN-001462 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dbc40f86-2de5-47a1-abc7-139d7b08e4cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8179 | T16182-YU02-P0ZEN-150202 | 2018-09-19 | DHI-TRANSMIT-002058 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91761d30-d821-47e6-ade1-d40775e63fae | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8180 | T16182-XW03-P0SAE-134601 | 2018-09-19 | DHI-TRANSMIT-002059 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05fb8195-7767-4171-886e-dd0c31c96933 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8181 | T16182-XG07-P0SAE-134602 | 2018-09-19 | DHI-TRANSMIT-002059 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78f52025-dacb-43f9-bfbb-44e8f6100c85 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8182 | T16182-XW03-P0SAE-134603 | 2018-09-19 | DHI-TRANSMIT-002059 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a824179-5ce8-41fe-8855-1e3be5dcfd89 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8183 | T16182-XH02-P0SAE-134604 | 2018-09-19 | DHI-TRANSMIT-002059 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=922dea7a-b117-4207-832c-6d2df96a9622 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8184 | T16182-YK08-P0ZEN-020008 | 2018-09-19 | DHI-TRANSMIT-002060 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dae28e16-dba7-4fad-b153-5e81952b7e61 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8185 | T16182-XB02-P0UZA-172902 | 2018-09-19 | DHI-TRANSMIT-002061 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0454b1a6-2069-4748-b514-c325635d2338 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8186 | T16182-XB02-P0UZA-172903 | 2018-09-19 | DHI-TRANSMIT-002061 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18c1ddcb-01fd-4c02-bb86-1b3c7bde4114 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8187 | T16182-VK02-P0UZA-172908 | 2018-09-19 | DHI-TRANSMIT-002061 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2698a268-5ad9-4479-8a31-5148d4559467 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8188 | T16182-XH01-P0LF-140421 | 2018-09-19 | DHI-TRANSMIT-002062 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2df7582f-7a9f-4c02-992a-544ae35cf914 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8189 | T16182-XH01-P0LF-140422 | 2018-09-19 | DHI-TRANSMIT-002062 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c3ac60a-c145-48e9-8499-d2c6bb04802d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8190 | T16182-VK02-P0UZT-173008 | 2018-09-19 | DHI-TRANSMIT-002063 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=734a69a7-00e3-4de1-9931-ead814e7131e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8191 | T16182-XB02-P0UBN-172202 | 2018-09-19 | DHI-TRANSMIT-002064 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b100cbb9-2a34-4195-893b-0c7ce0f5385d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8192 | T16182-VK02-P0UBN-172203 | 2018-09-19 | DHI-TRANSMIT-002064 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=115499d5-0a03-4f6d-91a3-5b39b3480c06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8193 | T16182-YT01-P0SAA-136005 | 2018-09-19 | DHI-TRANSMIT-002065 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84b511fa-3957-48ee-a29d-3929594ec102 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8194 | T16182-XW03-P0SAD-134501 | 2018-09-19 | DHI-TRANSMIT-002066 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70088e8f-bab2-4987-a2ae-087bd17669c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8195 | T16182-XG07-P0SAD-134502 | 2018-09-19 | DHI-TRANSMIT-002066 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e990c977-490e-46da-abd1-c7c28baec030 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8196 | T16182-XW03-P0SAD-134503 | 2018-09-19 | DHI-TRANSMIT-002066 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3096cb67-231a-4cbf-b2d5-5c169184bf2f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8197 | T16182-XH02-P0SAD-134504 | 2018-09-19 | DHI-TRANSMIT-002066 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=332ddd6d-bb4b-4444-841c-43d4be482eb0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8198 | T16182-YU03-P0BFA-150951 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=59c20162-b3f4-45d5-9283-78d13d6ca9d9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8199 | T16182-YU03-P0BFA-150952 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=caf0070c-53d3-498d-bb72-f1bbefa71ba5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8200 | T16182-YU03-P0BFA-150953 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc537fb3-9843-4fc0-b71b-c086bba92b91 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8201 | T16182-YU03-P0BFA-150954 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6bf37f7-d3a2-4231-9780-5e106291040f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8202 | T16182-YU03-P0BFA-150955 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2221c9de-69be-486d-a371-a0e1ceb05e2c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8203 | T16182-YU03-P0BFA-150956 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5966efbc-31c4-49b6-9653-e08c8294d6b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8204 | T16182-YU03-P0BFA-150957 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c81e647-4e8c-4525-b969-201df1503c71 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8205 | T16182-YU03-P0BFA-150958 | 2018-09-19 | DHI-WTRAN-001463 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a25a4b9c-0ae3-4714-9745-a37e12f5251e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8206 | T16182-YD00-P0CYE-139141 | 2018-09-19 | DHI-TRANSMIT-002067 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5862cbce-6dfb-4e98-858e-e48f78e0e5c5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8207 | T16182-YU02-P0CYE-139142 | 2018-09-19 | DHI-TRANSMIT-002067 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=75ae4a82-b1aa-440a-be4f-aa2d49d05aa1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8208 | T16182-YD00-P0CYE-137941 | 2018-09-19 | DHI-TRANSMIT-002067 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6be2575b-a603-4381-ace5-92d7c5abf071 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8209 | T16182-YU02-P0CYE-137942 | 2018-09-19 | DHI-TRANSMIT-002067 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2166f1d-2330-4caf-8709-d84dbe796c89 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8210 | T16182-XB02-P0GUB-173302 | 2018-09-19 | DHI-TRANSMIT-002068 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12d5ac64-047c-40e2-b885-a9f28e3abf9b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8211 | T16182-XB02-P0GUB-173303 | 2018-09-19 | DHI-TRANSMIT-002068 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07830c8a-6d95-4b67-af43-e907e8eba6fc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8212 | T16182-VK02-P0GUB-173313 | 2018-09-19 | DHI-TRANSMIT-002068 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16ec324d-d3a3-450d-8d05-954c9a2722b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8213 | T16182-VK02-P0UZJ-173208 | 2018-09-19 | DHI-TRANSMIT-002069 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11e58496-635f-43e9-a98c-db23c950a0cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8214 | T16182-XB02-P0UZJ-173202 | 2018-09-19 | DHI-TRANSMIT-002069 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5c51ef7-22c4-4be7-9e1e-dd1716ba4c23 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8215 | T16182-BV02-P0ZEN-020020 | 2018-09-25 | DHI-WTRAN-001464 | IFI | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8216 | T16182-BV02-P0ZEN-020030 | 2018-09-25 | DHI-WTRAN-001465 | IFI | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8217 | T16182-CV03-P0CWQ-161121 | 2018-10-01 | DHI-TRANSMIT-002076 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18f628b4-4eb3-4e9d-9efe-883b2eb9e642 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8218 | T16182-XJ00-P0QCA-140221 | 2018-10-01 | DHI-TRANSMIT-002077 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dafc8596-646a-40eb-8bbf-fee97d6fcde9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8219 | T16182-YL00-P0LB-122079 | 2018-10-01 | DHI-TRANSMIT-002078 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93753446-090e-4c6c-bb7b-cb159572ef82 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8220 | T16182-CA03-P0UMY-185172 | 2018-10-01 | DHI-TRANSMIT-002079 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e3b2af5-2b31-4118-b2a9-7a7e3488028e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8221 | T16182-XG02-P0LB-122022 | 2018-10-02 | DHI-TRANSMIT-002080 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c86f785-8045-4adc-a7b2-37ee2c18ff8f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8222 | T16182-XJ00-P0LCM-140205 | 2018-10-02 | DHI-WTRAN-001466 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e3600a3-d982-48b2-9c02-a800a8db5ec6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8223 | T16182-YD02-P0LB-122065 | 2018-10-02 | DHI-WTRAN-001467 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f85c5da-fc54-4466-8484-3947342feed6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8224 | T16182-YD00-P0CYE-137441 | 2018-10-02 | DHI-TRANSMIT-002081 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05ff4be5-9d7e-45b9-b9a4-74a3bd9e3735 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8225 | T16182-YU02-P0CYE-137442 | 2018-10-02 | DHI-TRANSMIT-002081 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04346233-9933-48c8-b095-fc29cd257a78 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8226 | T16182-YD00-P0CYE-139641 | 2018-10-02 | DHI-TRANSMIT-002081 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15d602c3-de2f-4d25-a686-47f8efb5f6e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8227 | T16182-YU02-P0CYE-139642 | 2018-10-02 | DHI-TRANSMIT-002081 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69bd73e1-09f3-4ed2-8e50-6e892d1eaca3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8228 | T16182-YD02-P0ZEN-165577 | 2018-10-02 | DHI-TRANSMIT-002082 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a693d07-0ce0-4205-a8a6-867a2d35aad6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8229 | T16182-YD02-P0ZEN-165575 | 2018-10-02 | DHI-TRANSMIT-002082 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0da0a953-9021-4521-93e4-06a7f0ba0de7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8230 | T16182-YD02-P0ZEN-165515 | 2018-10-02 | DHI-TRANSMIT-002082 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5b842ba-8f7b-4bc5-bdb1-c900cba7d992 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8231 | T16182-YD02-P0ZEN-165517 | 2018-10-02 | DHI-TRANSMIT-002082 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8ef62d0-e438-4293-8526-ed0f42befc84 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8232 | T16182-YK00-P0ZEN-165315 | 2018-10-02 | DHI-TRANSMIT-002082 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=568bb7c5-d78c-4372-bd0a-cc6dd6fe5626 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8233 | T16182-XJ00-P0EKC-140217 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=565310b1-6c5c-4f0e-9da7-ecab1171b813 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8234 | T16182-XJ00-P0GHC-140213 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4f5ba84-5586-4d02-bf0a-9d4a3190a36f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8235 | T16182-XJ00-P0LAB-140208 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68d14b1e-2456-4ff5-af84-a46ef417b832 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8236 | T16182-XJ00-P0LBA-140201 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=601f8f12-5924-433e-9cfb-6e8c040e2b63 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8237 | T16182-XJ00-P0LBC-140202 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=714a705e-84fe-40fa-98ca-51c21e126f3e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8238 | T16182-XJ00-P0LBG-140203 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e4ea8c6-6bb9-4811-a310-19282d7d34f2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8239 | T16182-XJ00-P0MBH-140216 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ffd0e564-125d-44ad-873d-6a6f01c80c13 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8240 | T16182-XJ00-P0PGB-140209 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc19acfc-e73e-4ced-a54f-4cee40b113f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8241 | T16182-XJ00-P0SCA-140210 | 2018-10-02 | DHI-TRANSMIT-002083 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4c31169-3847-45f0-881f-f2c304737f8b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8242 | T16182-YR01-P8ZEN-125597 | 2018-10-04 | DHI-WTRAN-001468 | IFR | B | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4237cab-67c0-4d5f-bf28-c2949eab6648 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8243 | T16182-XJ00-P0QFB-140211 | 2018-10-04 | DHI-TRANSMIT-002088 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=855a252e-8b4f-4468-9d58-5c2c0b13dbc3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8244 | T16182-XJ00-P0QJA-140223 | 2018-10-04 | DHI-TRANSMIT-002088 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44224ab3-6cd5-41bf-a2cb-50e3d5934b54 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8245 | T16182-XJ00-P0LBG-140204 | 2018-10-04 | DHI-TRANSMIT-002088 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12876049-ebec-413b-b412-99401fa07a2e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8246 | T16182-XJ00-P0GKB-140212 | 2018-10-04 | DHI-TRANSMIT-002088 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d57657b-72c4-4880-9a0e-b1764d93f968 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8247 | T16182-XJ00-P0GM-140224 | 2018-10-04 | DHI-TRANSMIT-002088 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37cc98a0-d499-4b99-b3a0-f38b4eaf2ab1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8248 | T16182-XJ00-P0QUB-140219 | 2018-10-04 | DHI-TRANSMIT-002088 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd03e442-673e-46ce-a070-34e73ec165ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8249 | T16182-XJ00-P0ZEN-140120 | 2018-10-04 | DHI-TRANSMIT-002088 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55fb15c2-d151-49fc-9be1-7122fe36be8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8250 | T16182-YD00-P0LD-130202 | 2018-10-04 | DHI-TRANSMIT-002089 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3c43308-d668-48c7-865e-39dbd7e34d17 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8251 | T16182-XG02-P0SGK-136903 | 2018-10-04 | DHI-TRANSMIT-002090 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=338a125f-7fca-43e9-b5c7-ac5385ceb016 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8252 | T16182-XH01-P0SGK-136913 | 2018-10-04 | DHI-TRANSMIT-002090 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f24732b-cf49-4d1a-a0e2-18a7a6142979 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8253 | T16182-YT10-P0SGK-136923 | 2018-10-04 | DHI-TRANSMIT-002090 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8fd93e65-8bb9-4dd6-8165-16122bffbd55 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8254 | T16182-YT01-P0BT-151011 | 2018-10-04 | DHI-TRANSMIT-002091 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad70eddd-75ed-4f71-833b-fc6744c2bd57 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8255 | T16182-XJ00-P0LCA-140206 | 2018-10-04 | DHI-TRANSMIT-002092 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=235882cb-9fc6-4825-9be6-25ce6b3d46d9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8256 | T16182-YD00-P0CYE-138741 | 2018-10-05 | DHI-TRANSMIT-002093 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b2d96cb-9401-4f76-bd43-081d032d831a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8257 | T16182-YU02-P0CYE-138742 | 2018-10-05 | DHI-TRANSMIT-002093 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8aae19fd-3ae6-4825-9c49-dda2e5afdf30 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8258 | T16182-UE00-P0LB-122009 | 2018-10-05 | DHI-TRANSMIT-002094 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f77d6e56-bb03-472d-ac94-ee74568edcb8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8259 | T16182-YD00-P0SGZ-136731 | 2018-10-05 | DHI-TRANSMIT-002095 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23573c93-d9b8-4810-a033-52e90dfdb33b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8260 | T16182-YD00-P0SGZ-136831 | 2018-10-05 | DHI-TRANSMIT-002095 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a0d8a3c-fa43-47a3-9cda-796df02cd99b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8261 | T16182-YD00-P0CYE-139541 | 2018-10-05 | DHI-TRANSMIT-002096 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1966094a-59ad-48c7-a8d3-8ad2c76f0ec8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8262 | T16182-YU02-P0CYE-139542 | 2018-10-05 | DHI-TRANSMIT-002096 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=367ffc34-f717-495d-8447-3bb3418411c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8263 | T16182-YF00-P0SCA-127518 | 2018-10-05 | DHI-WTRAN-001469 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92ddde0b-2546-4a58-b443-90d520fea6ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8264 | T16182-YF02-P0SCA-127514 | 2018-10-05 | DHI-WTRAN-001470 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c937156c-ab22-43d8-909b-fa2732d60cb3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8265 | T16182-YB03-P0LB-122047 | 2018-10-08 | DHI-WTRAN-001471 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37b437f8-26ec-4187-87fc-81c3fb731267 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8266 | T16182-YL16-P0LB-122078 | 2018-10-08 | DHI-WTRAN-001471 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b7a4d5d-01e5-4670-a8f8-36d8db2261e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8267 | T16182-YD02-P0ZEN-165516 | 2018-10-08 | DHI-TRANSMIT-002097 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26ce2401-794b-4fe8-9a67-678158d301a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8268 | T16182-XH01-P0LF-140418 | 2018-10-08 | DHI-WTRAN-001472 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9d26932-4d7e-4749-897c-bf5def5c23fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8269 | T16182-XH01-P0LF-140401 | 2018-10-08 | DHI-TRANSMIT-002098 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36a41335-cf24-4282-b2bb-4196cd9ffd32 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8270 | T16182-XH01-P0LF-140404 | 2018-10-08 | DHI-TRANSMIT-002098 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a2f2e29-6e3e-4e99-a24f-b66aa0a6892a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8271 | T16182-XH01-P0LF-140407 | 2018-10-08 | DHI-TRANSMIT-002098 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=984f86db-e763-47b6-8bb5-02fc961ffef4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8272 | T16182-XH01-P0LF-140420 | 2018-10-08 | DHI-TRANSMIT-002098 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07d6f682-ae43-4c1a-a885-495dd81ad336 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8273 | T16182-XH01-P0LF-140423 | 2018-10-08 | DHI-TRANSMIT-002098 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3dfc03a-5f27-4b29-9aff-681a07d4ff27 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8274 | T16182-YT10-P0ZEN-152229 | 2018-10-08 | DHI-WTRAN-001473 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23bdf101-8f29-42f8-aa2e-6f4e8b57c930 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8275 | T16182-YQ01-P0ZEN-152315 | 2018-10-08 | DHI-TRANSMIT-002099 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7134804c-4af0-40aa-99b2-b41bdc60d9d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8276 | T16182-YQ01-P0ZEN-152327 | 2018-10-08 | DHI-TRANSMIT-002099 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3a27bb2-9593-4248-8e4f-d8302cc8ddd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8277 | T16182-DE00-P0ZEN-152202 | 2018-10-08 | DHI-TRANSMIT-002100 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99258ad6-6ecc-4d89-9a75-80dad201021a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8278 | T16182-XB02-P8UTH-172003 | 2018-10-10 | DHI-TRANSMIT-002103 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32b1c929-065d-4664-a886-18ff5637b2e3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8279 | T16182-XB02-P8UTH-172004 | 2018-10-10 | DHI-TRANSMIT-002103 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c25f1492-c294-4cf9-8776-e4acc7aeb578 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8280 | T16182-YE04-P0BAU-152501 | 2018-10-10 | DHI-TRANSMIT-002104 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5070666-6220-45b3-9c59-81a88417ee85 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8281 | T16182-YU02-P0BT-151021 | 2018-10-11 | DHI-WTRAN-001474 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee127499-8e95-4189-9cfa-c75cc1342289 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8282 | T16182-YU02-P0BT-151026 | 2018-10-11 | DHI-WTRAN-001474 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32d92ef6-d869-4c83-a6eb-4bc89a2a2640 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8283 | T16182-YU02-P0BT-151031 | 2018-10-11 | DHI-WTRAN-001474 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=458d20bc-3c19-476a-828c-8902d1bc563a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8284 | T16182-YU03-P0BT-151061 | 2018-10-11 | DHI-WTRAN-001474 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c80c2a2-50da-4ea1-9ab5-2b396e2bcdf2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8285 | T16182-YU03-P0BT-151066 | 2018-10-11 | DHI-WTRAN-001474 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b1d2539-cf3a-49df-af01-d613cb00ba24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8286 | T16182-YU03-P0BT-151071 | 2018-10-11 | DHI-WTRAN-001474 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a27a7af-16ed-4ed3-ae3c-4faf806d192c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8287 | T16182-YD00-P0SGZ-137332 | 2018-10-11 | DHI-TRANSMIT-002105 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9eba0df5-3698-47fe-8e94-1a2eaefafce7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8288 | T16182-YD00-P0SGZ-137431 | 2018-10-11 | DHI-TRANSMIT-002105 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2772d40-1bba-43e2-be78-54f7c19e0471 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8289 | T16182-YD00-P0SGZ-138331 | 2018-10-11 | DHI-TRANSMIT-002105 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58652ac0-7a70-40bd-b1be-2297f38325c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8290 | T16182-YD00-P0SGZ-138431 | 2018-10-11 | DHI-TRANSMIT-002105 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8886777-56a7-4b17-808d-2ac05b65425d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8291 | T16182-YD00-P0CYE-138841 | 2018-10-11 | DHI-TRANSMIT-002106 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d15533fb-cb87-4123-b57c-f4740b59f2d8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8292 | T16182-YU02-P0CYE-138842 | 2018-10-11 | DHI-TRANSMIT-002106 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86b9f6e9-f0ae-4b9a-bc29-44c822e140ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8293 | T16182-XG02-P0LAA-110009 | 2018-10-12 | DHI-TRANSMIT-002107 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=950cb298-4ac2-4461-9233-878140dd14ad | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8294 | T16182-XS00-P0MAG-123010 | 2018-10-12 | DHI-WTRAN-001475 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35142b20-5d05-4f40-acdd-e70e82a6815f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8295 | T16182-YL00-P0LB-122075 | 2018-10-12 | DHI-WTRAN-001476 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8be7bc5-f131-4eb1-aa7f-b6cbe7d0a13b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8296 | T16182-YR01-P8ZEN-125597 | 2018-10-12 | DHI-TRANSMIT-002108 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0586804-1fa6-4a3d-94db-b0c6b551d57e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8297 | T16182-DP00-P0ZEN-020004 | 2018-10-15 | DHI-TRANSMIT-002109 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3fba7b0-164b-4b24-8c52-eb9e71188462 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8298 | T16182-XJ00-P0ZEN-140120 | 2018-10-15 | DHI-TRANSMIT-002110 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5660474-ad20-4086-a0f0-10d6f511ccc8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8299 | T16182-YD02-P0SAC-163414 | 2018-10-15 | DHI-TRANSMIT-002111 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7d9f64d-7947-4ac3-9981-dca83a330de2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8300 | T16182-YF00-P0BB-150403 | 2018-10-15 | DHI-TRANSMIT-002112 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea685b26-6e7f-41df-b421-0ed4722f5b5b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8301 | T16182-YK08-P0MJ-110506 | 2018-10-15 | DHI-TRANSMIT-002113 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=baa7cdf9-183b-4ef9-8767-95f4ca86716f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8302 | T16182-XB02-P0UGF-173101 | 2018-10-15 | DHI-TRANSMIT-002114 | IFC | 9 | D | TRUE | FALSE | 2018-10-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c834f33-1fc8-4264-877f-45de92e75996 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8303 | T16182-XB02-P0UGF-173102 | 2018-10-15 | DHI-TRANSMIT-002114 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c58d86a1-c588-4ddc-8235-62ef73fdca1f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8304 | T16182-VK02-P0UGF-173107 | 2018-10-15 | DHI-TRANSMIT-002114 | IFC | 8 | D | TRUE | FALSE | 2018-10-15_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=217a8126-2722-41e1-93e6-9a447f606fa4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8305 | T16182-XG02-P0SGK-139103 | 2018-10-15 | DHI-TRANSMIT-002115 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c59d275-e4bc-47b2-ae03-d00f8996204d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8306 | T16182-XH01-P0SGK-139113 | 2018-10-15 | DHI-TRANSMIT-002115 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=055861fe-86c6-4f0b-9144-160b21b5dc10 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8307 | T16182-YT10-P0SGK-139123 | 2018-10-15 | DHI-TRANSMIT-002115 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce113980-fdbb-42ef-b54a-6cb2300c4ee2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8308 | T16182-XH01-P0SGA-138611 | 2018-10-15 | DHI-TRANSMIT-002115 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8742605f-7884-4afc-b54d-2e05a0ba1970 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8309 | T16182-XH01-P0SGC-138614 | 2018-10-15 | DHI-TRANSMIT-002115 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cc18c46-6968-4cb1-88f9-ef290e942264 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8310 | T16182-XJ00-P0QUB-140219 | 2018-10-16 | DHI-TRANSMIT-002116 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f2315d1-e0d5-4729-8964-bad3156b7baa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8311 | T16182-XJ00-P0LBG-140204 | 2018-10-16 | DHI-TRANSMIT-002116 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79ac1efd-6aee-4c6b-9af4-0d360aca5e53 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8312 | T16182-YD02-P0ZEN-165503 | 2018-10-16 | DHI-TRANSMIT-002117 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab901aaf-fad2-4dca-92ef-20e7e0616d80 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8313 | T16182-YK00-P0ZEN-165318 | 2018-10-16 | DHI-TRANSMIT-002117 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=250c453d-dcee-4157-94ac-56d95a779be9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8314 | T16182-YK00-P0GM-128509 | 2018-10-16 | DHI-TRANSMIT-002118 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0223a24a-de56-45b4-8ceb-a45c5e6e597d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8315 | T16182-YK00-P0LB-122072 | 2018-10-16 | DHI-TRANSMIT-002119 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b055eefd-5135-48c0-a274-c84f6f00f191 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8316 | T16182-YM03-P0LB-122069 | 2018-10-16 | DHI-TRANSMIT-002119 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db55798f-c8ab-4361-8a5d-0000fecb1cdd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8317 | T16182-YD00-P0SGZ-137631 | 2018-10-17 | DHI-TRANSMIT-002120 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1f1bfc1-fe8f-46f1-8128-7b726ac5de7d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8318 | T16182-YD00-P0SGZ-137931 | 2018-10-17 | DHI-TRANSMIT-002120 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b1e99f8-fe43-4e27-a00c-0cb8064932ad | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8319 | T16182-YF00-P0MJ-110511 | 2018-10-17 | DHI-TRANSMIT-002121 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04ef9eeb-a616-47c9-9335-1d065046ec16 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8320 | T16182-YD00-P0BT-151041 | 2018-10-18 | DHI-WTRAN-001477 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35e3d7a4-d754-4d8b-96d1-b101e9dada5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8321 | T16182-YD00-P0BT-151046 | 2018-10-18 | DHI-WTRAN-001477 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=779a7826-70bf-4d84-b176-2773c7183cbe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8322 | T16182-YD00-P0BT-151051 | 2018-10-18 | DHI-WTRAN-001477 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d907f7dc-e82c-4b1a-aa4f-a898ecbee36c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8323 | T16182-YQ01-P0ZEN-123052 | 2018-10-18 | DHI-WTRAN-001478 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fc72800-40d5-4a04-88d2-c08a37b484d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8324 | T16182-YD02-P0ZEN-165518 | 2018-10-18 | DHI-TRANSMIT-002124 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bcc73491-e71e-4116-90d8-eeed83505052 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8325 | T16182-YK00-P0ZEN-165316 | 2018-10-18 | DHI-TRANSMIT-002124 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b65ae3f5-de13-41dc-af7c-93b3ee4a76ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8326 | T16182-YK00-P0ZEN-165319 | 2018-10-18 | DHI-TRANSMIT-002124 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0003f97-7501-4b39-8e43-29947af64afd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8327 | T16182-XS00-P0SG-136601 | 2018-10-18 | DHI-TRANSMIT-002125 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0b0154d-99c9-4952-8c84-775d6b0cdcc5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8328 | T16182-XJ00-P0LCA-140206 | 2018-10-18 | DHI-TRANSMIT-002126 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=41d590a3-de7b-486f-a188-01c3731e7fe6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8329 | T16182-VK02-P0UEM-171711 | 2018-10-19 | DHI-TRANSMIT-002127 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5758e011-a9e8-4c5a-81f0-c2021e5ffdf1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8330 | T16182-XB02-P0UEM-171702 | 2018-10-19 | DHI-TRANSMIT-002127 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=518b9496-eaa7-4a73-a297-dcde10bb575f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8331 | T16182-XB02-P0UEM-171708 | 2018-10-19 | DHI-TRANSMIT-002127 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=705b583f-6f12-4abf-a0f0-2bb015a19946 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8332 | T16182-YE04-P0BAU-152501 | 2018-10-19 | DHI-TRANSMIT-002128 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a1e22bd-a746-4fd2-9563-b932bd533cc5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8333 | T16182-DE00-P0BAU-152502 | 2018-10-19 | DHI-TRANSMIT-002128 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=140dead6-9595-4065-ae76-d716337798a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8334 | T16182-YE03-P0BAU-152504 | 2018-10-19 | DHI-TRANSMIT-002128 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f04162c3-685b-458b-a873-ec95e46a85dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8335 | T16182-YE03-P0BAU-152511 | 2018-10-19 | DHI-TRANSMIT-002128 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5d127c4-9045-4ce7-9e03-12c7cf2ee16f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8336 | T16182-YE03-P0BAU-152524 | 2018-10-19 | DHI-TRANSMIT-002128 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e875a91-08e2-4b14-8622-142e56141c81 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8337 | T16182-YE03-P0BAU-152536 | 2018-10-19 | DHI-TRANSMIT-002128 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8442024d-a7b0-4a8b-b9a8-31c61174df0f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8338 | T16182-YE01-P0BAU-152601 | 2018-10-19 | DHI-TRANSMIT-002128 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cdd95f8-c659-4e03-b023-22ce1662a5e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8339 | T16182-XG02-P0SGA-137701 | 2018-10-19 | DHI-TRANSMIT-002129 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=597ef579-0891-4581-af32-64cbeb698b2b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8340 | T16182-XH01-P0SGA-137711 | 2018-10-19 | DHI-TRANSMIT-002129 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d37a6e0-4fc7-4c1a-9e27-5ac975cd636e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8341 | T16182-XG02-P0GKC-120002 | 2018-10-19 | DHI-TRANSMIT-002130 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f68175f5-25e7-4d34-bee6-e4b33c09a027 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8342 | T16182-XG02-P6LCA-110008 | 2018-10-22 | DHI-TRANSMIT-002131 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3cee7607-ea80-4823-a49c-93d76e3cea4f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8343 | T16182-XG02-P0PGB-110010 | 2018-10-22 | DHI-TRANSMIT-002131 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35407d80-6e1a-4446-b1d9-35418ee2750b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8344 | T16182-XG02-P0GHC-110011 | 2018-10-22 | DHI-TRANSMIT-002131 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f756ff1-d736-422d-b2d8-cafb314e6ade | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8345 | T16182-XB02-P8UTH-172007 | 2018-10-22 | DHI-TRANSMIT-002132 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8cfb9e9b-65d0-4053-be81-5bc6574a8853 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8346 | T16182-UE00-P0LB-122111 | 2018-10-22 | DHI-WTRAN-001479 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c95eade5-f5f2-4472-bf6f-0a897c8727c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8347 | T16182-YD00-P0CYE-137741 | 2018-10-23 | DHI-TRANSMIT-002133 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4e45c03-6e16-4e43-a2dc-a4f0fa675466 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8348 | T16182-YU02-P0CYE-137742 | 2018-10-23 | DHI-TRANSMIT-002133 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d8481d9-251b-4dd1-bd1a-d81fc44ca56f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8349 | T16182-YU02-P0BFA-150911 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=211443ec-336d-42d1-8015-aac2673fc8e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8350 | T16182-YU02-P0BFA-150912 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1ad54deb-d981-4e07-83d8-59e1a44d4fd4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8351 | T16182-YU02-P0BFA-150913 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=232a5aca-670f-46d4-a1a7-303baa13890c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8352 | T16182-YU02-P0BFA-150914 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20dada2f-0f33-497f-8e7a-0c473b0610a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8353 | T16182-YU02-P0BFA-150915 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5579fad-26a0-468f-b077-ac3d74848b87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8354 | T16182-YU02-P0BFA-150916 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=98786bf5-b5e3-449d-b7fd-224114412c69 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8355 | T16182-YU02-P0BFA-150917 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1633414d-43d5-4546-beea-5b159b29e1d0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8356 | T16182-YU02-P0BFA-150918 | 2018-10-23 | DHI-WTRAN-001480 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77382c23-2bc2-4d31-853e-f42fce6fa28d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8357 | T16182-YD00-P0BF-150931 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2657030-2acf-4cab-a551-10f48ac3404d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8358 | T16182-YD00-P0BF-150932 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3bb90e3-3034-4e2c-9fd5-c5ffcaf7191a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8359 | T16182-YD00-P0BF-150933 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62e42f9a-68d1-4978-81bf-45f6cf39c0b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8360 | T16182-YD00-P0BF-150934 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2eb3e3d-413b-4397-ad48-1d4810cf247a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8361 | T16182-YD00-P0BF-150935 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01501153-bcb0-4952-a440-7468c9accb86 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8362 | T16182-YD00-P0BF-150936 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52fba59f-3e3b-4d04-9e11-b2c5e23fd74f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8363 | T16182-YD00-P0BF-150937 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa21aa1e-fd39-473a-ba92-d0fa76d9431e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8364 | T16182-YD00-P0BF-150938 | 2018-10-23 | DHI-WTRAN-001481 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3bc36e1-6bac-4f7f-9657-63a26105b0cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8365 | T16182-XJ00-P0PGB-140209 | 2018-10-24 | DHI-TRANSMIT-002134 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ac2bcd0-ee32-49e3-b7d0-446770d0695a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8366 | T16182-XJ00-P0GHC-140213 | 2018-10-24 | DHI-TRANSMIT-002134 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd96c929-ec1d-4dfa-ad43-c985b69fd106 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8367 | T16182-XJ00-P0QFB-140211 | 2018-10-24 | DHI-TRANSMIT-002134 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=150a0719-da1f-4716-bf09-933d6a92275f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8368 | T16182-XJ00-P0GKB-140212 | 2018-10-24 | DHI-TRANSMIT-002134 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95748347-f7e9-4e08-aa05-846b9221ab06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8369 | T16182-XJ00-P0LBG-140204 | 2018-10-24 | DHI-TRANSMIT-002134 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a02d0613-a5ff-4f08-b624-60a81b9a6747 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8370 | T16182-XJ00-P0LCM-140205 | 2018-10-24 | DHI-TRANSMIT-002134 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=973b5732-5f08-40cf-aec6-55e02f49dda1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8371 | T16182-XJ00-P0ZEN-140120 | 2018-10-24 | DHI-TRANSMIT-002134 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=769b179e-7563-4d81-93d6-08c62cda49b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8372 | T16182-YR05-P0GM-128511 | 2018-10-24 | DHI-WTRAN-001482 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62d3ee3e-99ac-4ccf-be88-e4148f553412 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8373 | T16182-XG02-P0GM-122112 | 2018-10-24 | DHI-WTRAN-001483 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d0b4018-a8e4-4342-b524-d12c266f0061 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8374 | T16182-XG02-P8ZEN-125582 | 2018-10-24 | DHI-TRANSMIT-002135 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e00007d6-e9a3-4b41-8bc4-4280e13d9631 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8375 | T16182-XG02-P8ZEN-125584 | 2018-10-24 | DHI-TRANSMIT-002135 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b33b602-e3cd-464c-a602-d775e25a4749 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8376 | T16182-XG02-P8ZEN-125585 | 2018-10-24 | DHI-TRANSMIT-002135 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b53fca2-f239-4d43-8833-73e344939261 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8377 | T16182-YT10-P0ZEN-150313 | 2018-10-24 | DHI-TRANSMIT-002136 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b740bd54-2c7a-4caf-b4a9-35406db8ff30 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8378 | T16182-YQ01-P0ZEN-152312 | 2018-10-24 | DHI-TRANSMIT-002137 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f14b7232-9ffa-4f42-be98-0e96fc55fcbc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8379 | T16182-YQ01-P0ZEN-152310 | 2018-10-24 | DHI-TRANSMIT-002137 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=594ad206-6f87-43df-97cd-3bf8030aa142 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8380 | T16182-YQ01-P0ZEN-152311 | 2018-10-24 | DHI-TRANSMIT-002137 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d2bdeb1-dbc4-4dd8-bc95-0416eb0dbc7e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8381 | T16182-YQ01-P0ZEN-152309 | 2018-10-24 | DHI-TRANSMIT-002137 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16e9a0d1-668d-483f-a911-1373a94c42fd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8382 | T16182-YQ01-P0ZEN-152313 | 2018-10-24 | DHI-TRANSMIT-002137 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f995540a-e122-4b76-a6fd-67d9e6432c75 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8383 | T16182-YT10-P0ZEN-152211 | 2018-10-24 | DHI-WTRAN-001484 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca8d1f9e-10f2-4645-8779-e35cd0ad310e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8384 | T16182-YT10-P0ZEN-152215 | 2018-10-24 | DHI-WTRAN-001484 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f120caee-0b57-486f-a860-8fef97b97618 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8385 | T16182-YT10-P0ZEN-152214 | 2018-10-24 | DHI-WTRAN-001484 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=473051d2-5a58-4c9e-9c36-0b22e581a685 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8386 | T16182-YT10-P0ZEN-152213 | 2018-10-24 | DHI-WTRAN-001484 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26f1e9e3-683a-4b9f-aa25-a0e2270af12f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8387 | T16182-XH01-P0SGA-138011 | 2018-10-24 | DHI-TRANSMIT-002138 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c40e8e04-5241-4710-b095-8b4538cc8e6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8388 | T16182-XG02-P0SGA-138601 | 2018-10-24 | DHI-TRANSMIT-002138 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08d79faa-03e4-4a2d-a87a-45eab97b3dfc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8389 | T16182-XH01-P0SGA-138611 | 2018-10-24 | DHI-TRANSMIT-002138 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0464913-3316-4b0d-81dc-1d1ad883bdb8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8390 | T16182-YT01-P0SGE-136612 | 2018-10-24 | DHI-TRANSMIT-002138 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c0eaa65-3a83-4633-8ae9-bdce098f995c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8391 | T16182-YT01-P0SGC-136613 | 2018-10-24 | DHI-TRANSMIT-002138 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=796d5f3b-3f4a-4360-88f8-555d30fb988c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8392 | T16182-XJ00-P0LB-122028 | 2018-10-25 | DHI-TRANSMIT-002139 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cab0ca21-a181-463d-94a4-73ca8283e39a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8393 | T16182-XG02-P0SCA-120006 | 2018-10-25 | DHI-TRANSMIT-002140 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d940210-a252-493e-a1ac-87de913961c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8394 | T16182-XG02-P0LD-130204 | 2018-10-25 | DHI-TRANSMIT-002141 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26337c39-e54a-4218-8e0d-8f8fdea7da6e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8395 | T16182-XN00-P0LD-130208 | 2018-10-25 | DHI-WTRAN-001485 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad847324-1352-444d-abaf-6c181eca192d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8396 | T16182-YD00-P0MAG-123051 | 2018-10-25 | DHI-WTRAN-001486 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55b46e1b-ad2b-466f-a64a-3ab28a096a7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8397 | T16182-XB02-P0UNX-171402 | 2018-10-26 | DHI-TRANSMIT-002142 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=607acb1d-9ceb-4502-a4de-270c2fca713e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8398 | T16182-XB02-P0UNX-171403 | 2018-10-26 | DHI-TRANSMIT-002142 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ae888dc-2a7a-4107-9f3b-0f7c5f5c0595 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8399 | T16182-XB02-P0UNX-171410 | 2018-10-26 | DHI-TRANSMIT-002142 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccfdb926-b030-457b-8bfe-6f6a4265aa51 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8400 | T16182-XG02-P0SCA-120005 | 2018-10-26 | DHI-TRANSMIT-002143 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4ed6805-0ab8-4a08-98a3-e2f3a7a75061 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8401 | T16182-YD00-P0CYE-136741 | 2018-10-26 | DHI-TRANSMIT-002144 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6df4c3b3-5e47-4630-bd40-a8e724b911c9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8402 | T16182-XG02-P0SGA-137301 | 2018-10-26 | DHI-TRANSMIT-002145 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37ad1f8d-6b0e-423e-ba13-c6ba6b5e8c1d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8403 | T16182-XH01-P0SGA-137311 | 2018-10-26 | DHI-TRANSMIT-002145 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c720ffba-541c-4256-b889-279002b316ae | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8404 | T16182-XG02-P0GM-120008 | 2018-10-26 | DHI-TRANSMIT-002146 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=54d6b914-0ea4-4b29-a315-66a96124dacc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8405 | T16182-YQ01-P0ZEN-152301 | 2018-10-26 | DHI-TRANSMIT-002147 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=371610fc-d2a0-40df-b671-d5aa02edaa68 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8406 | T16182-XJ00-P6MAA-220383 | 2018-10-26 | DHI-WTRAN-001487 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3265554c-b75c-4f41-9b6a-b563594e28d5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8407 | T16182-XJ00-P7MAA-220384 | 2018-10-26 | DHI-WTRAN-001487 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aceb3970-b7c3-415e-b3b6-1627f798228f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8408 | T16182-XW03-P8ZEN-125014 | 2018-10-26 | DHI-TRANSMIT-002148 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fa9d1f8-467a-4a3a-bd9e-083fb0127423 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8409 | T16182-VK02-P0UZJ-173208 | 2018-10-26 | DHI-TRANSMIT-002149 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ede4448b-29d8-47b1-8f13-e3b1ee6568bc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8410 | T16182-XB02-P0UZJ-173202 | 2018-10-26 | DHI-TRANSMIT-002149 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fdce258-e701-405d-94e1-2c1d6242bafb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8411 | T16182-XB02-P0UZA-172902 | 2018-10-29 | DHI-TRANSMIT-002150 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=21972ae3-7ed6-4da3-ad4a-9e69b0be2d6a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8412 | T16182-XB02-P0UZA-172903 | 2018-10-29 | DHI-TRANSMIT-002150 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c0f0eeb-c1c4-4425-a745-10221b0e65bb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8413 | T16182-VK02-P0UZA-172908 | 2018-10-29 | DHI-TRANSMIT-002150 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f5a0bc3-e7d9-4e0c-8a1d-d61921f9907a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8414 | T16182-YQ08-P0CY-154051 | 2018-10-29 | DHI-TRANSMIT-002151 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b699b908-9d27-444f-9bb4-6827856c23b0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8415 | T16182-XG02-P0SCA-120004 | 2018-10-29 | DHI-TRANSMIT-002152 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b61c1db2-a15a-4f4b-8607-9739a2b40a07 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8416 | T16182-YT01-P0MBA-121023 | 2018-10-29 | DHI-WTRAN-001488 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6928ec0e-6a8b-461f-88d6-12b49cfb49d3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8417 | T16182-XB02-P0UGF-173101 | 2018-10-29 | DHI-TRANSMIT-002153 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a8e0ac1-5c48-421e-af7c-1cf7e50cf3fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8418 | T16182-XB02-P0UGF-173102 | 2018-10-29 | DHI-TRANSMIT-002153 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71f4396e-8e8b-4088-9d19-9c8636d2eabb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8419 | T16182-XH01-P0SGA-136711 | 2018-10-30 | DHI-TRANSMIT-002154 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f4e2483-1708-402f-ab97-df0d03b8dc0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8420 | T16182-XH01-P0SGA-137911 | 2018-10-30 | DHI-TRANSMIT-002154 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1837df0d-873e-413c-9d18-418b3287a732 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8421 | T16182-UT01-P0GQB-173413 | 2018-10-30 | DHI-TRANSMIT-002155 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58117430-f10d-4b31-9c8e-59da7be3abe9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8422 | T16182-YD00-P0CWQ-161401 | 2018-10-30 | DHI-TRANSMIT-002156 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8fb7769-7a04-45dd-9675-6dd3fc8d5796 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8423 | T16182-YD00-P0CWQ-161402 | 2018-10-30 | DHI-TRANSMIT-002156 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a07de070-a46a-41b4-8548-b0ed4dcfe70f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8424 | T16182-YD00-P0CWQ-161405 | 2018-10-30 | DHI-TRANSMIT-002156 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb2fdedc-61c3-4fc1-b29d-e36a9501301d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8425 | T16182-YD00-P0CWQ-161407 | 2018-10-30 | DHI-TRANSMIT-002156 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d12bc15-da2d-4166-a132-84aab4127ff7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8426 | T16182-YD00-P0CWQ-161408 | 2018-10-30 | DHI-TRANSMIT-002156 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=225be670-fc11-470d-80f0-ee1e84a956ff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8427 | T16182-YD00-P0CWQ-161409 | 2018-10-30 | DHI-TRANSMIT-002156 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=157f34c7-121b-4b83-86d3-c823e9de90ab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8428 | T16182-VK02-P0GUB-173313 | 2018-10-30 | DHI-TRANSMIT-002157 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd0d443c-c1ed-420a-97e1-c182a24d8af9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8429 | T16182-XG02-P0PCA-126502 | 2018-10-30 | DHI-TRANSMIT-002158 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4073409-8d6c-42ae-bf61-9c039f0e46c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8430 | T16182-XH01-P0SGA-138411 | 2018-10-30 | DHI-TRANSMIT-002159 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72045d9e-e014-421f-bcc1-e0757e64eb6c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8431 | T16182-XB02-P0UZT-173002 | 2018-10-30 | DHI-TRANSMIT-002160 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b44afcd0-55ec-4919-81df-d1dcce2264fa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8432 | T16182-XB02-P0UZT-173003 | 2018-10-30 | DHI-TRANSMIT-002160 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a2881e53-5ec7-4d7d-b162-e209a58db3b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8433 | T16182-VK02-P0UZT-173008 | 2018-10-30 | DHI-TRANSMIT-002160 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88d084cb-16bc-4f44-99dc-5718db090397 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8434 | T16182-YE00-P0ZEN-152725 | 2018-10-31 | DHI-TRANSMIT-002164 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f33245e6-0691-43ce-8933-a69f9c3927c6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8435 | T16182-YQ03-P8ZEN-125769 | 2018-11-01 | DHI-TRANSMIT-002166 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25576a88-93a1-455f-88f8-e03889802ba0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8436 | T16182-XG02-P6LCA-110008 | 2018-11-01 | DHI-TRANSMIT-002167 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55f90f32-5067-4956-8bce-05754c5765ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8437 | T16182-YD02-P0LB-122063 | 2018-11-02 | DHI-TRANSMIT-002168 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cc4113f-7866-440e-9874-b62f5c613715 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8438 | T16182-YQ01-P0ZEN-152301 | 2018-11-02 | DHI-TRANSMIT-002169 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebdd4986-7279-4dbe-a4bd-b71eef057b93 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8439 | T16182-YK09-P0PCA-126540 | 2018-11-02 | DHI-WTRAN-001489 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=706c2740-a566-47ca-af41-cff7887c4b9c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8440 | T16182-XH01-P0SGC-138616 | 2018-11-05 | DHI-TRANSMIT-002170 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04e48cda-f892-4775-984b-1c06c8deec47 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8441 | T16182-YD00-P0CYE-139041 | 2018-11-05 | DHI-TRANSMIT-002170 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c86a47e-3cee-4557-b53e-6384615d7ab5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8442 | T16182-YU02-P0CYE-139042 | 2018-11-05 | DHI-TRANSMIT-002170 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=937068a2-e712-4636-a2ab-e96b3e0e175a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8443 | T16182-YD00-P0CYE-139441 | 2018-11-05 | DHI-TRANSMIT-002170 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c7b61d0-a28a-4d67-a892-82f90a592092 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8444 | T16182-YU02-P0CYE-139442 | 2018-11-05 | DHI-TRANSMIT-002170 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c974c573-ba6e-425b-bfe7-9d5cd00d985e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8445 | T16182-YD02-P0SAC-163408 | 2018-11-05 | DHI-TRANSMIT-002171 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4994b29-a67c-4822-a58e-dbbb83cd4cba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8446 | T16182-YD00-P0SGZ-137331 | 2018-11-06 | DHI-TRANSMIT-002173 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=171a71bb-7318-466e-b437-db1e7f62498a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8447 | T16182-YD00-P0QU-130402 | 2018-11-06 | DHI-TRANSMIT-002174 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cad53cc-edf0-47ad-bc91-6f1d6cc76fc4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8448 | T16182-XJ00-P0LBG-140204 | 2018-11-06 | DHI-TRANSMIT-002175 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07ee4e5e-620e-4704-9f42-9d2cf42d2e99 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8449 | T16182-XJ00-P0QJA-140223 | 2018-11-06 | DHI-TRANSMIT-002175 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2697029-81e0-448d-a202-b9fbc2c2e789 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8450 | T16182-YM03-P0LB-122069 | 2018-11-06 | DHI-TRANSMIT-002176 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd58fee0-e7d8-43cf-bc23-50778dd7e2c1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8451 | T16182-XH01-P0SGA-139111 | 2018-11-08 | DHI-WTRAN-001492 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9cb058d-c2d2-4e59-b696-d04e3e112802 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8452 | T16182-DE00-P0PCA-126519 | 2018-11-08 | DHI-WTRAN-001493 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=860fadd3-373f-4271-beb3-2497a2b406af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8453 | T16182-YT10-P0ZEN-150312 | 2018-11-08 | DHI-TRANSMIT-002177 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aabfd8cf-e696-4a4f-8853-8c3c834520f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8454 | T16182-XG02-P0SGA-138401 | 2018-11-08 | DHI-TRANSMIT-002178 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff82fa49-e9f2-44ee-b5d2-499ab822fcb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8455 | T16182-XH01-P0SGA-136911 | 2018-11-08 | DHI-TRANSMIT-002178 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=378ff802-0709-478d-b4b8-bb5a85c01769 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8456 | T16182-XG02-P0SGA-139101 | 2018-11-08 | DHI-TRANSMIT-002179 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7202524e-ebdf-4f56-8419-dcf6928f07a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8457 | T16182-YT02-P8ZEN-125725 | 2018-11-08 | DHI-TRANSMIT-002180 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5b55afe-381b-4ff4-8125-4f16fbdeac8f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8458 | T16182-YQ01-P8ZEN-125765 | 2018-11-08 | DHI-TRANSMIT-002181 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b2cc9df-011e-4b48-887f-553cd674c533 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8459 | T16182-YT01-P0BF-150902 | 2018-11-08 | DHI-TRANSMIT-002182 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd514ee5-f1cf-4647-88a9-c8a8bb06d00b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8460 | T16182-XB02-P0LD-130220 | 2018-11-09 | DHI-WTRAN-001494 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e7762d3f-d71a-4b2f-938f-665779c99b0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8461 | T16182-YD02-P0ZEN-165506 | 2018-11-09 | DHI-TRANSMIT-002185 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8d0762e-a648-482b-992a-6d2118186b99 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8462 | T16182-XG02-P0LBS-110006 | 2018-11-09 | DHI-TRANSMIT-002186 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3c5dfaf4-12ad-448e-adec-2929d73e920c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8463 | T16182-XG02-P6LCM-110007 | 2018-11-09 | DHI-TRANSMIT-002186 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5b24602-0d8c-4027-9c7b-44a693ce9651 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8464 | T16182-YQ01-P0ZEN-152301 | 2018-11-09 | DHI-TRANSMIT-002187 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8151119e-1262-4181-89cd-daae039df052 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8465 | T16182-YQ01-P0ZEN-152315 | 2018-11-09 | DHI-TRANSMIT-002187 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5dfe1aa2-fd2c-4e11-8184-5da7dccd46eb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8466 | T16182-YE00-P0ZEN-152721 | 2018-11-09 | DHI-TRANSMIT-002188 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11653ad9-312c-40a0-9a60-a5db3853274e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8467 | T16182-XG02-P0GNR-130103 | 2018-11-09 | DHI-TRANSMIT-002189 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08ad25b4-4196-4105-b6ee-853a38b926a0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8468 | T16182-YD00-P0CYE-138541 | 2018-11-09 | DHI-TRANSMIT-002190 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e80ccaa3-389d-41bf-9615-9eaed9bd95e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8469 | T16182-YU02-P0CYE-138542 | 2018-11-09 | DHI-TRANSMIT-002190 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13dcbb69-300d-4f43-bce7-7433c7ce795a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8470 | T16182-YD00-P0CYE-139341 | 2018-11-09 | DHI-TRANSMIT-002190 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0573ceea-ebe0-406b-9f26-ffadcc75869b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8471 | T16182-YU02-P0CYE-139342 | 2018-11-09 | DHI-TRANSMIT-002190 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e50b973d-53d0-4630-a141-a57d8039a9ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8472 | T16182-XG02-P0MAG-123002 | 2018-11-12 | DHI-TRANSMIT-002192 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=416dfaea-ad17-4ea0-98b9-2963e7c9a051 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8473 | T16182-YD00-P0MAG-123051 | 2018-11-12 | DHI-TRANSMIT-002193 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01f4e72e-7ad0-4bf4-9058-367798fc47a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8474 | T16182-VK02-P0UZT-173008 | 2018-11-12 | DHI-TRANSMIT-002194 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5088176c-11ad-4d1b-af61-f3e822773abb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8475 | T16182-XB02-P0UZT-173002 | 2018-11-12 | DHI-TRANSMIT-002194 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6661b8d8-1dd9-41ad-a39e-f08076d01660 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8476 | T16182-XB02-P0UZT-173003 | 2018-11-12 | DHI-TRANSMIT-002194 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db11b28c-0565-44c8-b2f0-61204c9cfd8d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8477 | T16182-XG02-P0SGC-138902 | 2018-11-13 | DHI-WTRAN-001495 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e1d91ec-b970-48b5-9403-ff5bbcb03c23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8478 | T16182-XH01-P0SGC-138912 | 2018-11-13 | DHI-WTRAN-001495 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69b71673-fb48-430e-8b32-027bb672cdcd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8479 | T16182-DS00-P0MAG-123053 | 2018-11-13 | DHI-WTRAN-001496 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8669e054-5a1d-4b32-9311-0bb6506db673 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8480 | T16182-XH01-P0LF-140403 | 2018-11-13 | DHI-TRANSMIT-002195 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10f57088-28dc-48cd-ba3f-0f3aa98d9b7e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8481 | T16182-XH01-P0LF-140418 | 2018-11-13 | DHI-TRANSMIT-002195 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed7984d3-4171-4f92-a126-24292d7ac091 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8482 | T16182-XH01-P0LF-140408 | 2018-11-13 | DHI-TRANSMIT-002195 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3cbf8940-d1ef-420a-bbe1-19d96721b6ab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8483 | T16182-XH01-P0LF-140411 | 2018-11-13 | DHI-TRANSMIT-002195 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26f50749-b10f-4035-bb4e-5ab45ba9556c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8484 | T16182-XH01-P0LF-140422 | 2018-11-13 | DHI-TRANSMIT-002195 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6ebe4fec-77a7-4b16-bf00-49614f6412b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8485 | T16182-XN00-P0LD-130208 | 2018-11-14 | DHI-WTRAN-001497 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f864e1d2-78d3-4931-90d5-6b5bc5abb12d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8486 | T16182-YT01-P0LB-122095 | 2018-11-14 | DHI-WTRAN-001498 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db86225d-bc49-4249-bd3e-5d08cebe7db1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8487 | T16182-YT02-P0LB-122094 | 2018-11-14 | DHI-WTRAN-001498 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf47a5d2-60f5-453a-96e9-9ab4a49cd7ce | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8488 | T16182-XH01-P0LD-130213 | 2018-11-14 | DHI-TRANSMIT-002196 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73e9d23b-78ea-4dda-bd53-62eee5ac14f2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8489 | T16182-YE00-P0LD-130215 | 2018-11-14 | DHI-TRANSMIT-002196 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1da2ce8a-d418-49d2-963b-97c6e38d0431 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8490 | T16182-YQ01-P0ZEN-152331 | 2018-11-14 | DHI-TRANSMIT-002197 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e7ff512-04ec-4480-9377-a94d64453391 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8491 | T16182-YQ01-P0ZEN-152329 | 2018-11-14 | DHI-TRANSMIT-002197 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebc88f73-b2f4-4ecb-bf8c-2307eaf934d0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8492 | T16182-YQ01-P0ZEN-152330 | 2018-11-14 | DHI-TRANSMIT-002197 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df01f1ec-e5f1-482e-b1e7-818d924d8fde | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8493 | T16182-YT10-P0SGC-138922 | 2018-11-15 | DHI-WTRAN-001499 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f3197ae-df7b-4db8-8ce6-eaaa46ec63cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8494 | T16182-XG02-P0LB-122022 | 2018-11-16 | DHI-TRANSMIT-002200 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=adceecfd-90a2-41c3-9581-b2105210460e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8495 | T16182-XH01-P0LF-140401 | 2018-11-16 | DHI-TRANSMIT-002201 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0fc4974f-3702-45aa-b7e7-35f6cbf5ff4d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8496 | T16182-XH01-P0LF-140406 | 2018-11-16 | DHI-TRANSMIT-002201 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef2c6fea-62fd-49d7-b1ca-b8bcbbfc901a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8497 | T16182-XH01-P0LF-140412 | 2018-11-16 | DHI-TRANSMIT-002201 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=415bf133-6b51-43fa-95b1-28b35a1c4b5f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8498 | T16182-XH01-P0LF-140417 | 2018-11-16 | DHI-TRANSMIT-002201 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1603cf29-927f-450a-8c3a-2d2d69c5fd74 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8499 | T16182-YQ01-P0ZEN-152321 | 2018-11-16 | DHI-TRANSMIT-002202 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a738c582-24ab-4682-be5a-1707b3009f98 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8500 | T16182-YS01-P0GK-130602 | 2018-11-19 | DHI-WTRAN-001500 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a9a83b9-f06e-4e59-b0d3-0858cc5c51e2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8501 | T16182-YD00-P0LD-130206 | 2018-11-19 | DHI-TRANSMIT-002205 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40e7521b-b83e-4809-9a93-73acb1f203a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8502 | T16182-YQ08-P0CY-154032 | 2018-11-19 | DHI-TRANSMIT-002206 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6b5576e-0b81-4ad1-b4be-bcf4bebe831b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8503 | T16182-YQ08-P0CY-154033 | 2018-11-19 | DHI-TRANSMIT-002206 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b953ceff-4622-469d-ac0e-462cb1f29a5c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8504 | T16182-YQ08-P0CY-154039 | 2018-11-19 | DHI-TRANSMIT-002206 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f118d419-dd06-4361-a576-6ec3b023c4ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8505 | T16182-YQ08-P0CY-154053 | 2018-11-19 | DHI-TRANSMIT-002206 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb0168d9-21c2-4841-be40-49dabcd6b705 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8506 | T16182-XG02-P1MBH-110013 | 2018-11-19 | DHI-TRANSMIT-002207 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c1490ab-fc20-4157-b1c3-d44ed12b96fc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8507 | T16182-XW03-P0SAL-134001 | 2018-11-19 | DHI-TRANSMIT-002208 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=307505d0-a426-4b0e-b78d-5a1cdb732f7d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8508 | T16182-XG07-P0SAL-134002 | 2018-11-19 | DHI-TRANSMIT-002208 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfb6c601-b62d-46ac-a476-1e3263bdd317 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8509 | T16182-XW03-P0SAL-134003 | 2018-11-19 | DHI-TRANSMIT-002208 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2074533f-b6ed-4716-aba4-876b782003b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8510 | T16182-XH02-P0SAL-134004 | 2018-11-19 | DHI-TRANSMIT-002208 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e274892-de0b-48e2-ae4a-badc9f0a666c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8511 | T16182-YD02-P0LB-122064 | 2018-11-19 | DHI-TRANSMIT-002209 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a87d3d1-0f84-4e50-9359-e6224594f601 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8512 | T16182-XJ00-P6MAA-220383 | 2018-11-20 | DHI-WTRAN-001501 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b49fd0f2-7278-4498-bbee-5ad8dbf11e66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8513 | T16182-XJ00-P7MAA-220384 | 2018-11-20 | DHI-WTRAN-001501 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d72306ad-82a3-476a-9c1c-178b858f6834 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8514 | T16182-XH01-P0SGA-136711 | 2018-11-20 | DHI-TRANSMIT-002210 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbeb1fdd-b465-47cc-8bee-1124aaa3e9fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8515 | T16182-XH01-P0SGA-139511 | 2018-11-20 | DHI-TRANSMIT-002210 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55f05624-58d9-4192-89ad-bc715d26c131 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8516 | T16182-YD00-P0SGZ-137231 | 2018-11-20 | DHI-TRANSMIT-002210 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=568e2c74-9207-4350-ba36-152bc8d354b0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8517 | T16182-YD00-P0SGZ-139931 | 2018-11-20 | DHI-TRANSMIT-002210 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7768aa8b-c03e-4718-88df-8730b2cc68b6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8518 | T16182-XG02-P0SGA-136701 | 2018-11-20 | DHI-TRANSMIT-002211 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ad7a6eb-bb7e-41b4-aa19-a13e04b0bb46 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8519 | T16182-XH01-P0SGE-139512 | 2018-11-20 | DHI-TRANSMIT-002211 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=188e6cc8-0fa2-4aac-a7e0-3a03ee167afe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8520 | T16182-XW03-P0SAE-134601 | 2018-11-20 | DHI-TRANSMIT-002212 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a6ce0bf-26dd-45b8-b722-0ddbc2d43755 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8521 | T16182-XG07-P0SAE-134602 | 2018-11-20 | DHI-TRANSMIT-002212 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b5bc995-0610-4248-b19a-77a02180fde2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8522 | T16182-XW03-P0SAE-134603 | 2018-11-20 | DHI-TRANSMIT-002212 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec1a1bec-509e-4c2f-8b9d-6a3c55ca632e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8523 | T16182-XH02-P0SAE-134604 | 2018-11-20 | DHI-TRANSMIT-002212 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c13b8fa2-4a16-417a-8487-157ce7b4ebf5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8524 | T16182-XJ00-P0SCA-140110 | 2018-11-22 | DHI-WTRAN-001502 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c289f369-a81f-4bd8-bc56-2e6e7bd30f59 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8525 | T16182-XH01-P0LD-130213 | 2018-11-22 | DHI-TRANSMIT-002213 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed0e34cb-b820-464d-96ab-ececa189848b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8526 | T16182-XB02-P0UHA-171815 | 2018-11-22 | DHI-TRANSMIT-002214 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f1d8646-fba2-42a8-90d8-9ac4b4435a56 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8527 | T16182-YE03-P0BAU-152504 | 2018-11-22 | DHI-TRANSMIT-002215 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=315bd670-2e9a-461b-a231-0a18b9fb883b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8528 | T16182-YE03-P0BAU-152513 | 2018-11-22 | DHI-TRANSMIT-002215 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1d41133-74f1-415c-a0ea-307347eb9ece | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8529 | T16182-YE03-P0BAU-152531 | 2018-11-22 | DHI-TRANSMIT-002215 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca7f1051-3dc3-4549-b3d5-beeb287be492 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8530 | T16182-YE03-P0BAU-152535 | 2018-11-22 | DHI-TRANSMIT-002215 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d573e84a-bf0d-4610-87ff-63dc6cb8db0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8531 | T16182-YE01-P0BAU-152606 | 2018-11-22 | DHI-TRANSMIT-002215 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f67389b3-2227-4493-9236-aefccad88f77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8532 | T16182-YR05-P0LD-130207 | 2018-11-22 | DHI-TRANSMIT-002216 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=705d5f12-3349-49ca-b123-9441750d4010 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8533 | T16182-YE00-P0ZEN-152750 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0049f43f-6ac3-4234-96da-2ff98601933c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8534 | T16182-YE00-P0ZEN-152751 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=569a32be-64b5-45e3-b052-29bee8e08d4c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8535 | T16182-YE00-P0ZEN-152752 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2865857c-58b7-4cdc-b017-9a00458b90a5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8536 | T16182-YE00-P0ZEN-152753 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8f71ab50-152d-439b-a559-84ea5f526adb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8537 | T16182-YE00-P0ZEN-152754 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a222f57-0a33-4888-8fed-c5b0fcd65e14 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8538 | T16182-YE00-P0ZEN-152755 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b83fd0db-c84c-43b6-90d9-f4369a8e096a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8539 | T16182-YE00-P0ZEN-152756 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce2bbe55-3bc8-48ca-9760-8a58c17fc91d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8540 | T16182-YE00-P0ZEN-152757 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2cdc5f4-72a8-4707-8fad-aec901d2bfcb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8541 | T16182-YE00-P0ZEN-152758 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=122e44bd-28d0-4e38-b0c2-4185c9857b0b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8542 | T16182-YE00-P0ZEN-152759 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe40532a-8d70-48ef-a25a-24a62e51705f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8543 | T16182-YE00-P0ZEN-152760 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02250827-8b8d-411c-9f16-e3b9df5bcae3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8544 | T16182-YE00-P0ZEN-152761 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0048c465-28e3-4d0f-b0fd-fec81791976a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8545 | T16182-YE00-P0ZEN-152762 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fee9edb-240f-42ca-9b2a-fe6b9e663e12 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8546 | T16182-YE00-P0ZEN-152763 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a23303f-4a50-41e3-a91a-ac23af8775c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8547 | T16182-YE00-P0ZEN-152764 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bc7ee21-078a-44fd-a2db-a72100c69158 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8548 | T16182-YE00-P0ZEN-152765 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=008aa300-2ae7-48ed-82eb-0af3bcd4093d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8549 | T16182-YE00-P0ZEN-152766 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae3d12f8-2c17-40f7-8f4e-37426b081126 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8550 | T16182-YE00-P0ZEN-152767 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91e4dfd4-7a60-4d56-b1c7-fb90d174fafb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8551 | T16182-YE00-P0ZEN-152768 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c6820ef1-aca7-4ac9-bdfe-f0d7582106cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8552 | T16182-YE00-P0ZEN-152769 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=66a3e78d-a0da-4ab4-a4ed-9583ad3b7cb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8553 | T16182-YE00-P0ZEN-152770 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d509c081-cad7-43dc-a8b8-d6b83e7c6269 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8554 | T16182-YE00-P0ZEN-152771 | 2018-11-22 | DHI-TRANSMIT-002217 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff7bc641-0c42-4c1c-8af8-8a4d033eb273 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8555 | T16182-VK02-P0UZJ-173208 | 2018-11-23 | DHI-TRANSMIT-002218 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf887165-2270-45c4-acb5-a432621172f0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8556 | T16182-XB02-P0UZJ-173202 | 2018-11-23 | DHI-TRANSMIT-002218 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07849be7-1931-4fbe-80ce-44938c945d9e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8557 | T16182-YD00-P0CYE-137341 | 2018-11-23 | DHI-TRANSMIT-002219 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a34cc97c-d244-4033-aac9-38368a44a233 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8558 | T16182-YU02-P0CYE-137342 | 2018-11-23 | DHI-TRANSMIT-002219 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86b9dc65-64a4-41ea-9de5-4bc286c57233 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8559 | T16182-XG02-P0SGA-138901 | 2018-11-23 | DHI-TRANSMIT-002220 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35118ea3-30d8-4374-b808-15c53337deef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8560 | T16182-XG02-P0SGC-138902 | 2018-11-23 | DHI-TRANSMIT-002220 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46eeb495-7bd7-41c6-a84e-2e61c319b7c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8561 | T16182-XH01-P0SGC-138912 | 2018-11-23 | DHI-TRANSMIT-002220 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=add3556d-0fd1-460f-8642-ff1a103f8fc2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8562 | T16182-XS00-P0LB-122035 | 2018-11-23 | DHI-TRANSMIT-002221 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e987cc12-0bf9-4668-9602-9bb5cb897beb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8563 | T16182-XB02-P0UZA-172902 | 2018-11-26 | DHI-TRANSMIT-002223 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f19d383-3273-4971-ace8-be8cc29bb90e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8564 | T16182-XB02-P0UZA-172903 | 2018-11-26 | DHI-TRANSMIT-002223 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5362fc8a-0c69-4e46-a350-53f2e2af962c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8565 | T16182-VK02-P0UZA-172908 | 2018-11-26 | DHI-TRANSMIT-002223 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a29b802-ba93-4696-94de-0c3c1ad8fb00 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8566 | T16182-XB02-P0ULC-172502 | 2018-11-26 | DHI-TRANSMIT-002224 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7db55fe5-bbb0-424b-9aa9-834d7120dd2d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8567 | T16182-XB02-P0UGF-172522 | 2018-11-26 | DHI-TRANSMIT-002224 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cb77c0b-aea4-422f-9034-a08be87470ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8568 | T16182-XB02-P0UGD-172542 | 2018-11-26 | DHI-TRANSMIT-002224 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b7cd9f6-7feb-4f9c-81b4-7d337ba6a11f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8569 | T16182-XB02-P0UGG-172562 | 2018-11-26 | DHI-TRANSMIT-002224 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d455e418-1cdd-46ed-a694-4eaf6c9eaa96 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8570 | T16182-XB02-P0LD-130220 | 2018-11-26 | DHI-TRANSMIT-002225 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc96eca8-a3a2-4ee7-901d-9d8875727236 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8571 | T16182-XB02-P0ULX-172582 | 2018-11-26 | DHI-TRANSMIT-002226 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1d89f3d-22d3-4f47-b54e-b40d32ad94db | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8572 | T16182-XB02-P0ULX-172585 | 2018-11-26 | DHI-TRANSMIT-002226 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c2db7a6-d9ed-450d-9515-dd89bdca8090 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8573 | T16182-XJ00-P0ZEN-140120 | 2018-11-27 | DHI-TRANSMIT-002230 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd4de427-92b0-42cb-951c-b8e7046157d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8574 | T16182-YT02-P0PCA-126529 | 2018-11-27 | DHI-TRANSMIT-002231 | IFC | 0 | D | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0208a52b-1318-4391-a54f-fc408e9d3d06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8575 | T16182-XG02-P0EK-120007 | 2018-11-27 | DHI-TRANSMIT-002232 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=034be6f3-4516-4d80-8c2f-730c26a22927 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8576 | T16182-YK00-P0ZEN-165322 | 2018-11-27 | DHI-TRANSMIT-002233 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af33a7ae-e457-4aa1-b1dd-f1329e350672 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8577 | T16182-YT10-P0ASR-155012 | 2018-11-28 | DHI-WTRAN-001503 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ace32007-935d-4985-bce3-e026a7d75539 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8578 | T16182-XG01-P6MAA-220089 | 2018-11-28 | DHI-WTRAN-001504 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67e521c2-747a-42e7-9966-e52d4d39d771 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8579 | T16182-XG01-P7MAA-220090 | 2018-11-28 | DHI-WTRAN-001504 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7815fc1b-8c1e-4142-b7ab-0253302a6d94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8580 | T16182-XB02-P0UEM-171702 | 2018-11-28 | DHI-TRANSMIT-002234 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48e55ec2-590c-41c4-801e-73dd404b85dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8581 | T16182-YD00-P0SGZ-139831 | 2018-11-28 | DHI-TRANSMIT-002235 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49cb9167-4c76-49b7-8a92-911ea720d980 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8582 | T16182-XH01-P0SGA-139611 | 2018-11-28 | DHI-TRANSMIT-002235 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36aae467-d67a-40d3-88e6-f730ef0be879 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8583 | T16182-XH01-P0SGA-139011 | 2018-11-28 | DHI-TRANSMIT-002235 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c975448a-e58b-4693-87cd-cfc2ec6abfa8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8584 | T16182-XG02-P0SGA-139501 | 2018-11-28 | DHI-TRANSMIT-002235 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36b18ce2-03ea-4963-8f95-026b893d84e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8585 | T16182-YD00-P0SGZ-138231 | 2018-11-28 | DHI-TRANSMIT-002235 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e4b42f0-664a-422e-8866-09bfe69fe69a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8586 | T16182-XH01-P0SGA-139411 | 2018-11-28 | DHI-TRANSMIT-002235 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eaa57b10-da63-428c-ae0b-582823416b8d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8587 | T16182-BV02-P0CJN-290003 | 2018-11-29 | DHI-WTRAN-001505 | IFR | C | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8588 | T16182-CA03-P0UMY-185171 | 2018-11-29 | DHI-TRANSMIT-002236 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d69c20dc-aab0-4a90-babb-5a2b782b0680 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8589 | T16182-CA03-P0UMY-185172 | 2018-11-29 | DHI-TRANSMIT-002236 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=509ad139-a7d9-4fe9-8bec-ee9c2017c994 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8590 | T16182-YT01-P0MBA-121023 | 2018-11-29 | DHI-WTRAN-001506 | IFI | 3 | DR | TRUE | TRUE | 2018-12-03_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd0e534e-25f2-497f-8459-3514d3557c73 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8591 | T16182-YL16-P0ZEN-152850 | 2018-11-30 | DHI-WTRAN-001507 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6968c856-05a4-4a52-b95a-5be69c23d5dd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8592 | T16182-XJ00-P0QUB-140219 | 2018-11-30 | DHI-TRANSMIT-002237 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd954b6e-cd78-4701-b0c7-a014bb39bb64 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8593 | T16182-XH01-P0SGE-139512 | 2018-11-30 | DHI-TRANSMIT-002238 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac2aab01-e2bf-451f-9c97-e9edb7a5e5a6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8594 | T16182-XK00-P0PCA-126538 | 2018-11-30 | DHI-TRANSMIT-002239 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99a20393-ffeb-4e3e-9b40-3c7940f206c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8595 | T16182-YQ01-P0ZEN-152327 | 2018-11-30 | DHI-TRANSMIT-002240 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fca91554-66be-49b6-8874-b47eaffae28d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8596 | T16182-XG02-P0GM-121100 | 2018-12-03 | DHI-WTRAN-001508 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b926b31-3853-4b30-a9d7-a83dd26471b6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8597 | T16182-YR05-P0CJN-290004 | 2018-12-03 | DHI-TRANSMIT-002241 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53015fb1-cf95-45ee-b17d-f37ce11bef36 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8598 | T16182-YD00-P0CYE-138441 | 2018-12-03 | DHI-TRANSMIT-002242 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad8c96fc-6393-4498-bf69-92e0ea5c976d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8599 | T16182-YU02-P0CYE-138442 | 2018-12-03 | DHI-TRANSMIT-002242 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e191681-5f22-417d-b3f7-906864eb5745 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8600 | T16182-XG02-P0CYE-137944 | 2018-12-03 | DHI-TRANSMIT-002242 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0fdd13e-2b8c-47c5-b1a5-d145dd064839 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8601 | T16182-XH01-P0GCF-130013 | 2018-12-04 | DHI-TRANSMIT-002243 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23b9a4a0-0f29-45a3-9d2d-673495629124 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8602 | T16182-YQ03-P0CY-121036 | 2018-12-04 | DHI-WTRAN-001509 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba9d3b63-9763-4672-92da-f92a65505d57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8603 | T16182-XB02-P0ULC-171302 | 2018-12-04 | DHI-TRANSMIT-002244 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81f2bf36-c1af-462a-9510-63ddbb97ffac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8604 | T16182-XB02-P0ULC-171303 | 2018-12-04 | DHI-TRANSMIT-002244 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63113cb2-f94a-41b8-9325-ab63ddde32f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8605 | T16182-VK02-P0ULC-171308 | 2018-12-04 | DHI-TRANSMIT-002244 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c37381d9-4a69-4376-b278-321e6d8e4737 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8606 | T16182-YD00-P0CYE-138941 | 2018-12-04 | DHI-TRANSMIT-002245 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87b2d9ac-7aa0-4055-9f41-2034137a9924 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8607 | T16182-YU02-P0CYE-138942 | 2018-12-04 | DHI-TRANSMIT-002245 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9da1d2a0-8f7d-407c-9feb-0daf23b352ce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8608 | T16182-XJ00-P0LCM-140205 | 2018-12-05 | DHI-TRANSMIT-002246 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df0ffa5f-7053-4146-b059-a91320fce5b8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8609 | T16182-XS00-P0LA-110042 | 2018-12-05 | DHI-TRANSMIT-002247 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91eef515-8bbc-420c-87bc-c58e3393acf6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8610 | T16182-XS00-P0LC-110041 | 2018-12-05 | DHI-TRANSMIT-002247 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0b09e1f-027e-4648-bf1b-fb520a12980b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8611 | T16182-XG07-P0SAD-134502 | 2018-12-05 | DHI-TRANSMIT-002248 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d7fefc3-fa2e-447e-93a9-33d6a81be77a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8612 | T16182-XH02-P0SAD-134504 | 2018-12-05 | DHI-TRANSMIT-002248 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d355671c-ee65-4831-9b05-83a0219aefd5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8613 | T16182-XG02-P0GNR-130103 | 2018-12-06 | DHI-TRANSMIT-002250 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad17b024-0bf0-41c0-ba1d-38e000825d7a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8614 | T16182-YD00-P0GCF-130002 | 2018-12-06 | DHI-TRANSMIT-002250 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62674f27-8d99-4ba6-874a-dfa114e68cd9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8615 | T16182-YK00-P8ZEN-125720 | 2018-12-06 | DHI-WTRAN-001510 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afc4e9de-8681-4f3c-96ef-f57dd9d86e8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8616 | T16182-XG02-P8ZEN-125591 | 2018-12-06 | DHI-TRANSMIT-002251 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ff9843b-41c1-45a0-854a-5c3eef37a684 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8617 | T16182-XJ00-P8ZEN-125548 | 2018-12-06 | DHI-TRANSMIT-002251 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd0911c3-dabc-4d22-befd-559cee706d6e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8618 | T16182-XH01-P0SGC-138211 | 2018-12-06 | DHI-TRANSMIT-002252 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08d0c5bc-2a14-4a03-8253-3d93099cd266 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8619 | T16182-YT01-P0MAN-110153 | 2018-12-06 | DHI-WTRAN-001511 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f616dec-e784-4767-94ab-60d057940623 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8620 | T16182-YK08-P0MAN-110154 | 2018-12-06 | DHI-TRANSMIT-002253 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c5a4dc95-9146-463f-bf29-10b7abb72d40 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8621 | T16182-XJ00-P0GKB-140215 | 2018-12-07 | DHI-TRANSMIT-002254 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05958e15-c04a-42cb-8455-44d9257bfba3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8622 | T16182-CA05-P0UYA-183181 | 2018-12-07 | DHI-TRANSMIT-002255 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd398a02-49a5-48da-ad08-edb69e12e30c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8623 | T16182-CA05-P0UYA-183182 | 2018-12-07 | DHI-TRANSMIT-002255 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e86bd47-e02e-4f41-814e-c6a1aba1db8e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8624 | T16182-CA05-P0UYA-183183 | 2018-12-07 | DHI-TRANSMIT-002255 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15a777f5-97ce-4f3f-afd6-0c06813d96a6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8625 | T16182-XJ00-P0LB-122027 | 2018-12-07 | DHI-TRANSMIT-002256 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c94af566-488a-459f-a46f-0cad480e5cbb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8626 | T16182-XS01-P0MBA-121026 | 2018-12-10 | DHI-WTRAN-001512 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=427791bd-839f-4fc2-8b65-06cdbe7ae2a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8627 | T16182-XS01-P0MBA-121027 | 2018-12-10 | DHI-WTRAN-001512 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48e028ab-e11d-4eb7-8825-314311f56af6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8628 | T16182-XH01-P0SGA-139111 | 2018-12-10 | DHI-TRANSMIT-002258 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44186d0a-1917-4719-98a3-b652a59d32d4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8629 | T16182-XJ00-P0LB-122028 | 2018-12-10 | DHI-TRANSMIT-002259 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db0f5c17-874b-497c-808f-6b3cbdcd3d36 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8630 | T16182-XJ00-P0ZEN-140122 | 2018-12-11 | INT-IFC-181211-01 | INTERNAL IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3be6cc64-6110-4f20-b9b8-8cdf8b9fa066 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8631 | T16182-YD05-P0MBA-121032 | 2018-12-12 | DHI-WTRAN-001513 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=750f2cc4-159a-46b4-bf06-88c713cc1531 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8632 | T16182-CV03-P0SAY-163403 | 2018-12-12 | DHI-WTRAN-001514 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11e8fb09-73a5-4143-a14d-e384b4267cff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8633 | T16182-YL01-P0SAY-163402 | 2018-12-12 | DHI-WTRAN-001515 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b72e5f1b-fdd2-4fbf-a88b-e5d2fbd7692e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8634 | T16182-YF00-P0LD-130218 | 2018-12-12 | DHI-WTRAN-001516 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=929845e7-fa17-4b4a-860a-bc2e119205c0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8635 | T16182-XJ00-P0LAB-140208 | 2018-12-12 | DHI-TRANSMIT-002260 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fa111a0-1ea7-49e1-921c-09afb9f3d11a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8636 | T16182-XB02-P0UZT-173002 | 2018-12-12 | DHI-TRANSMIT-002261 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a03086b2-85e9-4c8c-a8c7-b75baef1260f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8637 | T16182-XB02-P0UZT-173003 | 2018-12-12 | DHI-TRANSMIT-002261 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c205823-adfd-4170-ab1d-fa30f80f36fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8638 | T16182-VK02-P0UZT-173008 | 2018-12-12 | DHI-TRANSMIT-002261 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b34cf127-c33a-496f-8842-fb2c368d1150 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8639 | T16182-XB02-P0UBN-172202 | 2018-12-12 | DHI-TRANSMIT-002262 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bf49086-d223-4a03-b2aa-132f6ab0fba7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8640 | T16182-XN00-P0GCF-130008 | 2018-12-12 | DHI-TRANSMIT-002263 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=606071c8-baf9-46da-a713-d2dca65f92ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8641 | T16182-XN00-P0GNR-130105 | 2018-12-12 | DHI-TRANSMIT-002263 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c78b7ce9-e54e-4890-beef-abb095460e7a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8642 | T16182-YD00-P0UBA-150503 | 2018-12-12 | DHI-TRANSMIT-002264 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=79bd64be-90eb-422e-a790-e94315fc3026 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8643 | T16182-XH01-P0SGK-136913 | 2018-12-13 | DHI-TRANSMIT-002265 | IFC | 3 | D | TRUE | FALSE | 2018-12-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da797b47-458d-4713-adef-103ae1613506 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8644 | T16182-YD00-P0SGZ-138131 | 2018-12-13 | DHI-TRANSMIT-002265 | IFC | 1 | D | TRUE | FALSE | 2018-12-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd751fc7-5b95-47ac-af2f-432b37de8c76 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8645 | T16182-XH01-P0SGE-138613 | 2018-12-13 | DHI-TRANSMIT-002265 | IFC | 1 | D | TRUE | FALSE | 2018-12-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=466267c6-ac46-4f33-8ecb-e7bc45a5e99a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8646 | T16182-XH01-P0SGA-138411 | 2018-12-13 | DHI-TRANSMIT-002265 | IFC | 3 | D | TRUE | FALSE | 2018-12-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=306d24e6-4648-4927-bc4c-3a560efce7e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8647 | T16182-YD00-P0SGZ-139031 | 2018-12-13 | DHI-TRANSMIT-002265 | IFC | 1 | D | TRUE | FALSE | 2018-12-13_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e1ecaba-4206-4cbf-8d07-2cda27fbb866 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8648 | T16182-YT10-P0ASR-155011 | 2018-12-14 | DHI-TRANSMIT-002266 | IFC | 1 | D | TRUE | TRUE | 2018-12-14_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01dedeb3-5891-466b-a345-6c33dd69e367 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8649 | T16182-YT10-P0ASR-155012 | 2018-12-14 | DHI-TRANSMIT-002266 | IFC | 0 | D | TRUE | TRUE | 2018-12-14_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2238d511-4b47-4738-ad81-e5bb63e17d5a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8650 | T16182-YR05-P0QC-130306 | 2018-12-14 | DHI-WTRAN-001517 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b67d88d1-04a3-4990-bb78-68fc00e5a8f7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8651 | T16182-YU03-P0QC-130308 | 2018-12-14 | DHI-WTRAN-001517 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf0c9c65-039a-47a2-b81b-45bfd8240702 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8652 | T16182-XJ00-P0SCA-140210 | 2018-12-17 | DHI-TRANSMIT-002269 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f52a87bb-68c2-4729-a1b2-1ab575b8231a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8653 | T16182-XJ00-P0QJA-140223 | 2018-12-17 | DHI-TRANSMIT-002269 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e53bfa5-d9f5-4d4c-9bfb-1ba9b2895b7a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8654 | T16182-XJ00-P0GHC-140213 | 2018-12-17 | DHI-TRANSMIT-002269 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=61a2defa-3d29-4b26-954e-fad908b140b6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8655 | T16182-XJ00-P0GKB-140212 | 2018-12-17 | DHI-TRANSMIT-002269 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=647b8bdc-25cd-4a09-94e5-731bdc158f32 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8656 | T16182-XJ00-P0QFB-140211 | 2018-12-17 | DHI-TRANSMIT-002269 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cc3804ea-f55b-4d0f-a039-ecfc854b6b85 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8657 | T16182-YV02-P0SCA-127511 | 2018-12-17 | DHI-WTRAN-001518 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d4beabf-ecf6-474f-996a-12a66a6b98b1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8658 | T16182-YD00-P0LCB-127555 | 2018-12-17 | DHI-WTRAN-001519 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4737f87b-70b4-4257-a8fd-39d4bd734155 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8659 | T16182-XW01-P0SCA-127556 | 2018-12-17 | DHI-WTRAN-001519 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3efad1b0-dc9b-42a4-8d9b-443ed9597ba3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8660 | T16182-XG02-P0SCA-127557 | 2018-12-17 | DHI-WTRAN-001519 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0e4a03d-0850-4ac2-a7a6-7e1e8517211c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8661 | T16182-XN00-P0LB-122032 | 2018-12-18 | DHI-WTRAN-001520 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b20a535-b19f-4241-9afd-e44dcb5931c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8662 | T16182-XN00-P0LB-122033 | 2018-12-18 | DHI-WTRAN-001520 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6dcd968-b71a-4ed1-b721-1630b5a91686 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8663 | T16182-XV00-P0LB-122038 | 2018-12-18 | DHI-WTRAN-001520 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35ebd490-19b7-43ab-8485-8206f46312ee | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8664 | T16182-YE00-P0LD-130215 | 2018-12-18 | DHI-TRANSMIT-002272 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3899ac9c-dd6b-4495-9792-b093ed2ab810 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8665 | T16182-XJ00-P0GKB-140215 | 2018-12-18 | DHI-TRANSMIT-002273 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22b7b099-e0cd-42b1-8379-d8c29d399b6a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8666 | T16182-XJ00-P0MBH-140216 | 2018-12-18 | DHI-TRANSMIT-002273 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a41cdc5-cb98-4712-a210-e2bc05f142b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8667 | T16182-XJ00-P0EKC-140217 | 2018-12-18 | DHI-TRANSMIT-002273 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ef7fc885-d359-431c-a69a-b83419639dec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8668 | T16182-XG02-P0LB-122022 | 2018-12-20 | DHI-TRANSMIT-002275 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dd9cc3b8-4eec-40a6-8fc1-bb6c618d91c2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8669 | T16182-YD00-P0LD-130202 | 2018-12-20 | DHI-TRANSMIT-002276 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f02a43dc-c168-44ad-91a4-542ecd01a299 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8670 | T16182-YE00-P0GCF-130015 | 2018-12-20 | DHI-TRANSMIT-002277 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=395eb823-3187-43f4-942e-4553f2cd28eb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8672 | T16182-YT01-P0BAT-150611 | 2018-12-20 | DHI-TRANSMIT-002279 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=928d0add-ae77-46e1-859b-1aed4a47fd61 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8673 | T16182-XW01-P0LB-122045 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3a346c5-711c-4333-b783-0d3c4129ac24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8674 | T16182-XW01-P0LB-122046 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=178cb0e6-04ab-4f97-89c9-b226059f7efc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8675 | T16182-YD00-P0LB-122056 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a4d4dd2-b54b-4f48-864d-cd260070515c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8676 | T16182-YD00-P0LB-122058 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2166e057-ae8e-4f80-95e4-a6a5db1e892d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8677 | T16182-YD02-P0LB-122065 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fc09db8-80ee-4758-829d-25244b5ed119 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8678 | T16182-YL00-P0LB-122076 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4acffddf-705b-4119-917c-9979a23e2876 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8679 | T16182-YR05-P0LB-122084 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf4c7821-2d5e-4d44-9045-f0f64443a73c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8680 | T16182-YQ01-P0LB-122085 | 2018-12-20 | DHI-WTRAN-001521 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ced3f516-09d8-4916-a72e-052e63556db3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8671 | T16182-XG02-P0LD-130204 | 2018-12-21 | DHI-TRANSMIT-002283 | IFC | 5 | D | TRUE | FALSE | 2018-12-21_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82b29163-6c8c-45b9-9238-a501303f6aba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8681 | T16182-YT10-P0ASR-155014 | 2018-12-21 | DHI-TRANSMIT-002284 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6bea35d6-acb9-4fdc-82c3-8bfc0917c90c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8682 | T16182-DP00-P8ZEN-125766 | 2018-12-21 | DHI-TRANSMIT-002285 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1a1dd6a-d148-4885-b64d-7fd24f57acda | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8683 | T16182-YT10-P0ZEN-150304 | 2018-12-21 | DHI-TRANSMIT-002286 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b68ae215-949b-41e5-987d-5141bae168cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8684 | T16182-YT01-P0MBA-121971 | 2019-01-02 | DHI-WTRAN-001522 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b0d3c24-4f46-426c-8c29-8194ba57b90c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8685 | T16182-XH01-P0SGC-137011 | 2019-01-02 | DHI-TRANSMIT-002295 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=38a08384-8cb5-47c2-98ab-3744d3804498 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8686 | T16182-XG02-P0SGC-138101 | 2019-01-02 | DHI-TRANSMIT-002295 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37b76aea-4f0a-4f14-94ca-28a3f50eadce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8687 | T16182-XH01-P0SGE-138612 | 2019-01-02 | DHI-TRANSMIT-002295 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7775b2db-cc8a-4c3c-90b4-68f69c89e578 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8688 | T16182-YT10-P0SGC-138922 | 2019-01-02 | DHI-TRANSMIT-002295 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5de2f2d3-39a9-475f-83be-f97239b065b2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8689 | T16182-XG02-P0SGA-137301 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09f5b955-39cd-48be-a08e-277f48b947aa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8690 | T16182-XG02-P0SGE-137302 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7d29a2b-0b1e-46f6-a58c-2c446cf91aae | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8691 | T16182-XH01-P0SGA-137311 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=319f0569-3b8d-4f12-bcab-ced2b38ac226 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8692 | T16182-XH01-P0SGE-137312 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a737186d-13f5-4719-a39b-fcb05b21ae77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8693 | T16182-XG02-P0SGA-137901 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78d16fb9-39fa-4225-b54d-44750fd637bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8694 | T16182-XG02-P0SGE-137903 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1ba494a-ea8c-4bcd-803f-2459567df514 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8695 | T16182-XH01-P0SGA-137911 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab758f14-e9be-49ec-9eda-500a01c07cb0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8696 | T16182-XH01-P0SGE-137913 | 2019-01-02 | DHI-TRANSMIT-002296 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8438e3e0-15d6-4d21-8d65-4c541cbeb08a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8697 | T16182-YK00-P0ZEN-165318 | 2019-01-02 | DHI-TRANSMIT-002297 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=765e21f7-1c84-4bb1-9dcc-4645e3e29c5e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8698 | T16182-YD00-P0CYE-136624 | 2019-01-03 | DHI-WTRAN-001523 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c05c035-239b-40ab-949c-3a3017dc7d2d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8699 | T16182-YE00-P0CJN-290005 | 2019-01-03 | DHI-TRANSMIT-002298 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2dbcaf44-3785-402f-b3a0-8816e33039fa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8700 | T16182-VK02-P8UTH-172008 | 2019-01-03 | DHI-TRANSMIT-002299 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f801bbc0-b312-4391-9f3c-936a05c9bc3f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8701 | T16182-XJ00-P0QJA-140223 | 2019-01-03 | DHI-TRANSMIT-002300 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7e7dbe0-b528-4955-9c32-2072c935274f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8702 | T16182-XJ00-P0GM-140224 | 2019-01-03 | DHI-TRANSMIT-002300 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90428128-0cf6-4960-90be-81714c40ae17 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8703 | T16182-XJ00-P0LAB-140208 | 2019-01-03 | DHI-TRANSMIT-002300 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=724e5cc0-ae29-4c53-b3e9-c625b776048a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8704 | T16182-YD00-P0CYE-138143 | 2019-01-04 | DHI-WTRAN-001524 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f4c5576-1936-470f-9ab6-1668985b7a68 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8705 | T16182-YU02-P0CYE-138144 | 2019-01-04 | DHI-WTRAN-001524 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3aafce8-906a-4236-b8e3-f0a123b9f0ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8706 | T16182-YD00-P0SGZ-137331 | 2019-01-04 | DHI-TRANSMIT-002302 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b252f6f9-0577-4bb1-8525-4d6b3e485407 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8707 | T16182-XJ00-P0GKB-140215 | 2019-01-04 | DHI-TRANSMIT-002303 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a6d8420-8293-4592-94d5-1641b2a3e246 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8708 | T16182-XJ00-P0EKC-140217 | 2019-01-04 | DHI-TRANSMIT-002303 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d51e952-3421-4849-9ae8-a0378c896226 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8709 | T16182-XG02-P0SGC-138102 | 2019-01-07 | DHI-WTRAN-001525 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3120a72a-4a86-43b5-9bd0-5c9f70aa6418 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8710 | T16182-XG02-P0SGA-137801 | 2019-01-07 | DHI-TRANSMIT-002304 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4bd4cec-3701-4e5a-b7b2-793edd00e25f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8711 | T16182-XG02-P0SGC-137001 | 2019-01-07 | DHI-TRANSMIT-002304 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acf1a08e-5d36-4beb-b869-3005e91103d4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8712 | T16182-XW01-P0SAA-133301 | 2019-01-07 | DHI-TRANSMIT-002305 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc6cdb09-92a3-43ac-98f6-c0a7f644f654 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8713 | T16182-XG02-P0SGA-137701 | 2019-01-07 | DHI-TRANSMIT-002306 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=891e00fd-2b14-4c0d-b86f-4eb77621d6e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8714 | T16182-XG02-P0SGC-138201 | 2019-01-07 | DHI-TRANSMIT-002306 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2e64292a-53d7-4c0e-8d05-41626f5aa41b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8715 | T16182-XG02-P0SGC-138301 | 2019-01-07 | DHI-TRANSMIT-002306 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f9f6507-d331-4dc0-a808-c589b377d5ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8716 | T16182-XH01-P0SGA-137711 | 2019-01-07 | DHI-TRANSMIT-002306 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71914fbb-6f51-4b13-8093-e1813fefa0c3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8717 | T16182-XH01-P0SGC-138211 | 2019-01-07 | DHI-TRANSMIT-002306 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c425bab-e8d0-41da-8e11-52bf66f6df71 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8718 | T16182-XH01-P0SGC-138311 | 2019-01-07 | DHI-TRANSMIT-002306 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46dc50d6-738d-4935-bc87-f875f7dab755 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8719 | T16182-XG02-P0SGE-136702 | 2019-01-08 | DHI-TRANSMIT-002308 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4adc3ea0-26c7-4078-811f-efab6498532e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8720 | T16182-XH01-P0SGE-136712 | 2019-01-08 | DHI-TRANSMIT-002308 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b106890-c937-4388-b5d3-0ce59bc1ca1a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8721 | T16182-XG02-P0SGA-136701 | 2019-01-08 | DHI-TRANSMIT-002308 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4224432-0d94-4fcd-9346-23f40d3fb3b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8722 | T16182-XH01-P0SGA-136711 | 2019-01-08 | DHI-TRANSMIT-002308 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97994b61-78a7-499b-987a-d8cbd5e3f3ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8723 | T16182-YT01-P0GCF-130014 | 2019-01-08 | DHI-TRANSMIT-002307 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db569215-cc54-4fd5-a034-92ca98a3c725 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8724 | T16182-YT01-P0GNR-130108 | 2019-01-08 | DHI-TRANSMIT-002307 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88281378-6610-4c0e-b54b-aaaf7af8e562 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8725 | T16182-XJ00-P0ZEN-140122 | 2019-01-09 | INT-IFC-190109-01 | INTERNAL IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a735a03-331b-4491-97ed-d6f084dd0da9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8726 | T16182-YD02-P0ZEN-165510 | 2019-01-09 | DHI-TRANSMIT-002309 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9427148-99a3-4890-a8af-fb638060c819 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8727 | T16182-YD02-P0ZEN-165576 | 2019-01-09 | DHI-TRANSMIT-002309 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=970d16ae-b56d-4265-b36a-253aa81b532d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8728 | T16182-XH01-P0SGE-136812 | 2019-01-09 | DHI-TRANSMIT-002310 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b720a2c3-e79c-417b-b94e-88815cb22882 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8729 | T16182-XG02-P0SGE-136802 | 2019-01-09 | DHI-TRANSMIT-002310 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6583add0-2f27-425b-9a30-7c82d3f98318 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8730 | T16182-XG02-P0SGA-136801 | 2019-01-09 | DHI-TRANSMIT-002310 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39437e74-486e-488f-838c-fbaf757c0c01 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8731 | T16182-XH01-P0SGA-136811 | 2019-01-09 | DHI-TRANSMIT-002310 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10fc5282-ab8b-4aa9-bb5f-af251d29bb70 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8732 | T16182-XJ00-P0LBA-140201 | 2019-01-09 | DHI-TRANSMIT-002311 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5654b096-46ef-4e57-aa62-795363c5741f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8733 | T16182-XJ00-P0QUB-140219 | 2019-01-09 | DHI-TRANSMIT-002311 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92e78ee4-4a40-4318-ae5f-0bd4d43cb2c1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8734 | T16182-XJ00-P0ZEN-140120 | 2019-01-09 | DHI-TRANSMIT-002311 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=483fb4a3-395e-4749-840e-2dd5d0e0017a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8735 | T16182-YD02-P0ZEN-165515 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90ac8656-f402-4988-8956-a11f3005fd2d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8736 | T16182-YD02-P0ZEN-165522 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65dde48d-57e0-4c9e-b9ee-ec5ba976de12 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8737 | T16182-YD02-P0ZEN-165525 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c04985e-fe20-42d2-bee0-a308e42bbf40 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8738 | T16182-YD02-P0ZEN-165526 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=785b207a-f9b5-4bd5-98fd-ddbf5e0bb8e1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8739 | T16182-YD02-P0ZEN-165527 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d4c0019-abda-4506-99c4-56e06b21cb97 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8740 | T16182-YD02-P0ZEN-165528 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=930c8a25-e0a5-4297-a171-b88ecba4de65 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8741 | T16182-YD02-P0ZEN-165529 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c9d98b8-890d-4524-9364-99cdeaa224d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8742 | T16182-YK00-P0ZEN-165315 | 2019-01-11 | DHI-TRANSMIT-002312 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbcb2b5e-d2a3-4dc7-9cdf-fb3e9a27194b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8743 | T16182-YD00-P0MAG-123054 | 2019-01-14 | DHI-WTRAN-001526 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e060ccd-be11-4ec9-97b0-59c1882dcfbd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8744 | T16182-YD00-P0LCB-127001 | 2019-01-14 | DHI-TRANSMIT-002313 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c0eb2f4-57cc-40ce-9c63-1343015392be | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8745 | T16182-XJ00-P0LB-122028 | 2019-01-14 | DHI-TRANSMIT-002314 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6173e28-95ae-4767-aa26-34dadf4ca8bb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8746 | T16182-YR01-P0CRU-161150 | 2019-01-15 | DHI-TRANSMIT-002315 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=814dbeeb-a43d-4602-957b-292692021502 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8747 | T16182-YD00-P0CYE-137941 | 2019-01-15 | DHI-TRANSMIT-002316 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0a16202-c828-4e71-8c24-7a13dfab6bff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8748 | T16182-YU02-P0CYE-137942 | 2019-01-15 | DHI-TRANSMIT-002316 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58e6c363-5012-4351-a96f-e5aab182ad88 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8749 | T16182-YD00-P0CYE-136841 | 2019-01-15 | DHI-TRANSMIT-002316 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87520a42-8772-4bb3-934b-304262f47dd6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8750 | T16182-YU02-P0CYE-136842 | 2019-01-15 | DHI-TRANSMIT-002316 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1439868-e0a0-472b-b4d2-1ca5938624b4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8751 | T16182-YT01-P0CYE-136617 | 2019-01-15 | DHI-TRANSMIT-002316 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19c07a92-23b8-472b-904d-17372fb4f8af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8752 | T16182-YD00-P0SGZ-138531 | 2019-01-15 | DHI-TRANSMIT-002316 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03bb734d-686d-4a02-a120-0f40bf3d44e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8753 | T16182-XJ00-P0ZEN-140120 | 2019-01-15 | DHI-TRANSMIT-002317 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e79bd96-9b81-483a-b35d-a09cdd2f0912 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8754 | T16182-YB03-P0LB-122047 | 2019-01-16 | DHI-WTRAN-001527 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=561e4cc3-4053-487f-b24b-f989d11cdf40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8755 | T16182-YL16-P0LB-122078 | 2019-01-16 | DHI-WTRAN-001527 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b17ecfd2-8965-4401-a330-d02961fe2224 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8756 | T16182-YT01-P0LB-122051 | 2019-01-16 | DHI-TRANSMIT-002318 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f47d0f12-7a25-4816-902f-0804a0ec8367 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8757 | T16182-YE04-P0BAU-152501 | 2019-01-16 | DHI-TRANSMIT-002319 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f97b51b3-ac28-44b9-a164-a4e059e6eb21 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8758 | T16182-XW01-P0MBA-121037 | 2019-01-16 | DHI-WTRAN-001528 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5889a679-64fc-4a2f-9f97-42a82954b3c2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8759 | T16182-YQ01-P0ZEN-123052 | 2019-01-16 | DHI-WTRAN-001529 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0645f7b-9af5-412a-a675-b18af1bbe7b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8760 | T16182-YT02-P0LB-122094 | 2019-01-17 | DHI-WTRAN-001530 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=39595285-2f33-4537-963d-340c4685916d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8761 | T16182-XW01-P0MBA-121037 | 2019-01-17 | DHI-WTRAN-001531 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6379bd39-deb0-4ca4-856e-8708e690c7db | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8762 | T16182-YK00-P0LB-122072 | 2019-01-17 | DHI-TRANSMIT-002320 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1f7d1fb-2dcf-49f6-87ea-d7ede75e32cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8763 | T16182-XG02-P0GKB-120001 | 2019-01-17 | DHI-TRANSMIT-002321 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3691a70c-af6e-4b31-b785-adddc4e42ce1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8764 | T16182-XG02-P0GKC-120002 | 2019-01-17 | DHI-TRANSMIT-002321 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7375f5d-0d55-4cb8-af63-0e22f34293c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8765 | T16182-BV02-P0CJN-290003 | 2019-01-18 | DHI-WTRAN-001532 | IFR | D | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49a826ab-c22c-4bda-b91e-065850c48c51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8766 | T16182-XJ00-P0LBA-140201 | 2019-01-18 | DHI-TRANSMIT-002322 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=101fea59-0954-49b3-9596-9bac1cd75cc2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8767 | T16182-XJ00-P0GKB-140212 | 2019-01-18 | DHI-TRANSMIT-002322 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b216784-5b12-4c4a-96d8-5a1a272f5403 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8768 | T16182-XJ00-P0GHC-140213 | 2019-01-18 | DHI-TRANSMIT-002322 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e985e800-79ac-4588-b92a-573db798856e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8769 | T16182-XH01-P0SGC-138112 | 2019-01-21 | DHI-WTRAN-001537 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96ae8daf-52bc-4fd7-bc20-60e21bddad39 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8770 | T16182-YT10-P0SGC-138122 | 2019-01-21 | DHI-WTRAN-001537 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9dfdc7a4-1e21-4442-9aa6-f7beb2234f06 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8771 | T16182-YD02-P0ZEN-165506 | 2019-01-21 | DHI-TRANSMIT-002323 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=255d0028-9a9e-4423-8388-82c4e6a43e51 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8772 | T16182-XN00-P0LD-130208 | 2019-01-22 | DHI-WTRAN-001539 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be9f113e-828b-4ad5-82ac-b68afe613022 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8773 | T16182-XJ00-P0LBG-140204 | 2019-01-22 | DHI-TRANSMIT-002324 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fce1c1b-6bfd-4330-805e-957602b70412 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8774 | T16182-XJ00-P0LCM-140205 | 2019-01-22 | DHI-TRANSMIT-002324 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29437a45-c6f2-4c7b-925b-b4700185c9ca | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8775 | T16182-YE03-P8ZEN-125767 | 2019-01-24 | DHI-TRANSMIT-002327 | IFC | 1 | D | TRUE | FALSE | 2019-01-24_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7271a276-8860-4844-8691-4a32faba868c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8776 | T16182-YT10-P0MJ-110568 | 2019-01-24 | DHI-WTRAN-001540 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0aeda6d-2db1-4c60-93ed-c160b2e49a87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8777 | T16182-YQ01-P8ZEN-125765 | 2019-01-24 | DHI-TRANSMIT-002328 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f30e508-3994-4ae6-a880-28b7a7e284ed | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8778 | T16182-XB02-P0UEM-171702 | 2019-01-24 | DHI-TRANSMIT-002329 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f5145672-249b-43fe-9d9f-3ef66fe00012 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8779 | T16182-VK02-P0UAZ-172613 | 2019-01-24 | DHI-TRANSMIT-002330 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d35224e-25c7-495a-a217-7f7e28cea35c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8780 | T16182-YK00-P0LB-122072 | 2019-01-24 | DHI-TRANSMIT-002331 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=362724d7-bd70-4c1c-b59b-be62803276d7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8781 | T16182-XJ00-P0LBA-140201 | 2019-01-24 | DHI-TRANSMIT-002332 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6e8a7cb-e595-4b1b-84ae-6e1e51ec75ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8782 | T16182-XJ00-P0SCA-140210 | 2019-01-24 | DHI-TRANSMIT-002332 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cd1353e3-eb19-4d78-b96b-29aae8e0badc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8783 | T16182-XJ00-P0QFB-140211 | 2019-01-24 | DHI-TRANSMIT-002332 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f99726ec-f55c-4288-b19f-58916e3d27c0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8784 | T16182-YS01-P0MKY-290012 | 2019-01-24 | DHI-TRANSMIT-002333 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab5613c9-d7b9-4609-ab8e-663fa2fb4d8e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8785 | T16182-XG02-P0LD-130204 | 2019-01-24 | DHI-TRANSMIT-002334 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0373402-58c6-47fb-9a9e-ccbc8659ff0c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8786 | T16182-YD00-P0CYE-137441 | 2019-01-28 | DHI-TRANSMIT-002335 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b006363d-3107-4271-bfd1-34f2a2db1b24 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8787 | T16182-YT10-P0MKY-290010 | 2019-01-28 | DHI-TRANSMIT-002336 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c37bf8a-bd78-4a44-9a2b-a83821fb332a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8788 | T16182-YD00-P0CYE-138641 | 2019-01-28 | DHI-TRANSMIT-002337 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=956592d3-8cd4-453d-a4a6-7a1e30996ad9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8789 | T16182-YU02-P0CYE-138642 | 2019-01-28 | DHI-TRANSMIT-002337 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6cab8676-ddf2-463e-abb5-3ef8c7bf0c79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8790 | T16182-YD00-P0CYE-136624 | 2019-01-28 | DHI-TRANSMIT-002337 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db6797ca-a261-42b0-a6f6-09c4cc6c03c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8791 | T16182-YT10-P0ASR-155014 | 2019-01-30 | DHI-TRANSMIT-002340 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=145af928-0a42-4e58-9ef7-4506526134f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8792 | T16182-XJ00-P0LB-122027 | 2019-01-30 | DHI-TRANSMIT-002341 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdefa7b4-3a2a-45db-a850-3a47d349bdf0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8793 | T16182-XJ00-P0LAB-140208 | 2019-01-30 | DHI-TRANSMIT-002342 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4e5ca57c-0420-4e18-9ab8-ec2bf417d59f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8794 | T16182-YT01-P0LAC-126009 | 2019-01-30 | DHI-TRANSMIT-002343 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bde52b8e-90dc-48d4-8bad-1f9f4b342ef0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8795 | T16182-YT01-P0LAC-126059 | 2019-01-30 | DHI-TRANSMIT-002343 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78969e06-1b4a-486c-99c2-769b0c73b5d2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8796 | T16182-XJ00-P0LB-122028 | 2019-01-30 | DHI-TRANSMIT-002344 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19992f9b-acdf-4e69-a49e-1577f00f65c6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8797 | T16182-XG02-P0GM-120008 | 2019-01-31 | DHI-TRANSMIT-002345 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6def88b7-0a53-4315-884c-5ed864a69bf9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8798 | T16182-XB02-P0UGF-173101 | 2019-01-31 | DHI-TRANSMIT-002346 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff7e51a2-c1db-48f2-98d0-9e59c1148e1a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8799 | T16182-XB02-P0UGF-173102 | 2019-01-31 | DHI-TRANSMIT-002346 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efcf94c2-cd72-42c4-8a34-ae3e7c1dfb8b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8800 | T16182-VK02-P0UGF-173107 | 2019-01-31 | DHI-TRANSMIT-002346 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abb41f16-c9ab-4c1c-8916-a6eb894315dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8801 | T16182-VN03-P0LB-122015 | 2019-01-31 | DHI-TRANSMIT-002347 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=750bd415-b5c9-4f45-b416-db4dfdc9520b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8802 | T16182-DE00-P0ZEN-152202 | 2019-01-31 | DHI-TRANSMIT-002348 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce35b4c3-a3dd-4ab9-9e83-a07e5cb32131 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8803 | T16182-XG11-P0MJ-110564 | 2019-01-31 | DHI-WTRAN-001541 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d0cfa146-de36-41bb-9add-ae703ec5c020 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8804 | T16182-YM02-P0MJ-110561 | 2019-01-31 | DHI-WTRAN-001541 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=613c57ae-1379-4607-bb12-be6e745d6b72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8805 | T16182-YU02-P0MJ-110507 | 2019-01-31 | DHI-WTRAN-001541 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d58a702-a377-4ab8-b039-47d87928fb6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8806 | T16182-YR01-P0ZEN-110201 | 2019-01-31 | DHI-TRANSMIT-002349 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a0aa2bc-b698-46db-85fc-f230816fbf62 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8807 | T16182-YU03-P0BB-150831 | 2019-02-01 | DHI-WTRAN-001542 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d120ac4-cbb1-453d-8af9-f70a7fc39cd8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8808 | T16182-YU02-P0ZEN-150212 | 2019-02-01 | DHI-TRANSMIT-002350 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0315026-03fe-432f-9aed-e6d6cd572248 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8809 | T16182-YD00-P0CYE-139541 | 2019-02-01 | DHI-TRANSMIT-002351 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc92d248-0b34-4596-9e02-0f81a9618cab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8810 | T16182-YU02-P0CYE-139542 | 2019-02-01 | DHI-TRANSMIT-002351 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c27d4c2-9070-4714-bc78-85d209bfa805 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8811 | T16182-YQ01-P0ZEN-152303 | 2019-02-01 | DHI-TRANSMIT-002352 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a6aa1b7-3729-4c87-8689-aeeb10d0617a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8812 | T16182-YQ01-P0ZEN-152327 | 2019-02-01 | DHI-TRANSMIT-002352 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3f445bc-0b25-4648-afbd-504ea6fdae91 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8813 | T16182-XJ00-P0QCA-140221 | 2019-02-01 | DHI-TRANSMIT-002353 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65888690-f136-4a48-bf85-a19fb5b4ef04 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8814 | T16182-YD00-P0BAT-150621 | 2019-02-11 | DHI-WTRAN-001543 | IFI | 8 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c7b5dbe-45e7-48ca-b79a-a7816eefd88f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8815 | T16182-YD00-P0BAT-150626 | 2019-02-11 | DHI-WTRAN-001543 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec2a4d55-a79d-4b74-935d-a0da3bf1a95d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8816 | T16182-YD00-P0BBT-150671 | 2019-02-11 | DHI-WTRAN-001543 | IFI | 9 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6aa7cddc-fc03-47c9-8053-1c7a3d78ce19 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8817 | T16182-XJ00-P0GM-140224 | 2019-02-11 | DHI-TRANSMIT-002359 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7a6a682-ffbd-40ed-8fdc-bc7dc16f0e9c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8818 | T16182-XJ00-P0ZEN-140120 | 2019-02-11 | DHI-TRANSMIT-002359 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d2284aad-34a3-4967-a47f-58590487148c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8819 | T16182-XH01-P0SGK-136713 | 2019-02-11 | DHI-TRANSMIT-002360 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50ba654b-aba0-499f-ba75-36d67c3d52ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8820 | T16182-YB03-P0SAY-163407 | 2019-02-12 | DHI-TRANSMIT-002361 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=09b2770e-cedc-4658-b56e-fffa776d3d6b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8821 | T16182-YD02-P0SAC-163426 | 2019-02-12 | DHI-TRANSMIT-002362 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdaab495-710f-4e1c-ac05-d0d5e55c6a93 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8822 | T16182-XJ00-P0LCM-140205 | 2019-02-12 | DHI-TRANSMIT-002363 | IFC | 3 | DR | TRUE | TRUE | 2019-02-12_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca7de366-b6fb-41ce-be5c-c72fa47918bf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8823 | T16182-XJ00-P0EKC-140217 | 2019-02-12 | DHI-TRANSMIT-002364 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=83ccd729-e289-4d69-bbc7-217d3228d67b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8824 | T16182-XJ00-P0MBH-140216 | 2019-02-12 | DHI-TRANSMIT-002364 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bba2d08-dc53-4240-a264-ea0e637bdb7a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8825 | T16182-YT10-P0MKY-290010 | 2019-02-13 | DHI-TRANSMIT-002365 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a575e89-dbb2-4a00-9931-29cd7bb37d94 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8826 | T16182-YV02-P0SCA-127548 | 2019-02-14 | DHI-WTRAN-001544 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=232f14bf-2cc1-4fe6-bd34-4a3bbbd6134d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8827 | T16182-YD04-P0ZEN-152015 | 2019-02-14 | DHI-TRANSMIT-002366 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c9c20cb9-116e-43c3-a91e-30392464c9c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8828 | T16182-XJ00-P0LBA-140201 | 2019-02-14 | DHI-TRANSMIT-002367 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fe7acfd-1098-45b1-974c-664396fd6af9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8829 | T16182-YK00-P0ZEN-165321 | 2019-02-14 | DHI-TRANSMIT-002368 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4ef0aef-fe6a-4b57-9803-7cfec33cb654 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8830 | T16182-YU02-P0ZEN-150212 | 2019-02-15 | DHI-TRANSMIT-002369 | IFC | 3 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8831 | T16182-XJ00-P0QUB-140219 | 2019-02-15 | DHI-TRANSMIT-002373 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46ae0c82-2079-44a7-a60a-118112239d70 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8832 | T16182-XJ00-P0PGB-140209 | 2019-02-15 | DHI-TRANSMIT-002373 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=46b6f533-ced5-450e-b89f-06fc83f353de | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8833 | T16182-YD04-P0ZEN-152007 | 2019-02-15 | DHI-TRANSMIT-002374 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fe38306-9af0-4316-ac90-d40512e32c62 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8834 | T16182-XH01-P0SGE-138613 | 2019-02-15 | DHI-TRANSMIT-002375 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c60148dc-1c39-4e65-8638-29735bc41e7d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8835 | T16182-XJ00-P0SCA-140110 | 2019-02-18 | DHI-TRANSMIT-002378 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35335d3a-0f5a-43e7-a638-1dc6dbbfad89 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8836 | T16182-DM02-P0MBA-121010 | 2019-02-18 | DHI-WTRAN-001545 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d8e05d30-51ac-4f79-8b04-b14858035d55 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8837 | T16182-DM02-P0MBA-121038 | 2019-02-18 | DHI-WTRAN-001545 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccf00596-eace-4b5a-82b2-98904fb70a36 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8838 | T16182-XG02-P0SGC-138102 | 2019-02-19 | DHI-TRANSMIT-002379 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=446ee0c0-27ee-4dbd-82de-178c6d9acc12 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8839 | T16182-XH01-P0SGC-138112 | 2019-02-19 | DHI-TRANSMIT-002379 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f84ab29f-de63-49e4-a8ea-d9c1ac9db510 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8840 | T16182-YD02-P0ZEN-165504 | 2019-02-19 | DHI-TRANSMIT-002380 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be2bac0e-750e-4fdf-a96e-0dae8ada3761 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8841 | T16182-YD02-P0ZEN-165508 | 2019-02-19 | DHI-TRANSMIT-002380 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cbaa69c2-a6fc-474a-a3a5-dbcf5903225e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8842 | T16182-XJ00-P0ZEN-140120 | 2019-02-19 | DHI-TRANSMIT-002381 | IFC | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c69bbe5e-7ce5-4afb-b689-951056888ced | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8843 | T16182-YD00-P0CYE-138641 | 2019-02-19 | DHI-TRANSMIT-002382 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8674e8da-d7c4-4a0d-a014-49157aeca7f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8844 | T16182-YD00-P0CYE-139741 | 2019-02-19 | DHI-TRANSMIT-002382 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a51eac95-97de-4f1b-baf1-688e8109a9b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8845 | T16182-XN00-P0GCF-130008 | 2019-02-20 | DHI-TRANSMIT-002383 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b0a3453-19c3-47fc-ac93-702799cc091b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8846 | T16182-XG02-P0GNR-130103 | 2019-02-20 | DHI-TRANSMIT-002383 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44618d0f-0128-4080-81e2-53e366172022 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8847 | T16182-YT01-P0GNR-130108 | 2019-02-20 | DHI-TRANSMIT-002383 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d9e79da-4998-4002-8947-cbd184f8274c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8848 | T16182-XG02-P0GCF-130004 | 2019-02-20 | DHI-TRANSMIT-002383 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8967cfb5-ba8f-4075-8037-a85ded04797d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8849 | T16182-YT01-P0GCF-130014 | 2019-02-20 | DHI-TRANSMIT-002383 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87c86dc2-d67a-4735-afc0-8c9a62842045 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8850 | T16182-XB02-P0UZA-172902 | 2019-02-21 | DHI-TRANSMIT-002386 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e05036d3-b604-4ee3-9bce-1dbfac3c71e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8851 | T16182-XB02-P0UZA-172903 | 2019-02-21 | DHI-TRANSMIT-002386 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=23742876-102d-42c7-b86d-442e2d3035cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8852 | T16182-VK02-P0UZA-172908 | 2019-02-21 | DHI-TRANSMIT-002386 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9b3cfc47-8579-4b6d-b8f2-ea0ecfaa5f56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8853 | T16182-YB03-P0ZEN-165532 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e643d38b-e2de-41fe-b118-a2b8a241636f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8854 | T16182-YB03-P0ZEN-165533 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b4a3d4f-fa3e-4231-95b8-e8c3a21edd5e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8855 | T16182-YB03-P0ZEN-165534 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=949d263a-f288-4cc9-8c16-34bc42ebf8c3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8856 | T16182-YB03-P0ZEN-165535 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb58f01c-61e4-4364-bb4e-d3195d34ac35 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8857 | T16182-YB03-P0ZEN-165536 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0753d3fa-98be-4827-a43b-7108559e95e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8858 | T16182-YB03-P0ZEN-165537 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0f6eb177-47be-41ad-afae-65489ab68611 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8859 | T16182-YB03-P0ZEN-165538 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfde8911-b55b-469d-9f1a-1add20fcc03c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8860 | T16182-YB03-P0ZEN-165539 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69975aba-b810-4cfe-a089-d6ddf80c915f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8861 | T16182-YB03-P0ZEN-165540 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04bc68ab-fba4-432a-8895-da3f7af96d8a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8862 | T16182-YB03-P0ZEN-165541 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a880aa06-2a5f-4395-894e-bfe478865cb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8863 | T16182-YB03-P0ZEN-165542 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c73ae2b0-bc6c-4ee1-92d0-12bdafc9d710 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8864 | T16182-YB03-P0ZEN-165543 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c058044d-25a3-4ea9-b3dd-4d82dd5ff234 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8865 | T16182-YB03-P0ZEN-165544 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f56e7d91-58d1-4270-b869-58903f6feccd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8866 | T16182-YB03-P0ZEN-165545 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae488ff0-7714-43f7-92e7-902dd88338c9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8867 | T16182-YB03-P0ZEN-165546 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89cf29e0-ca02-4efa-9894-00f26e5b309e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8868 | T16182-YB03-P0ZEN-165547 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a5d9f75-1b27-4f01-a817-c4f8a5fae979 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8869 | T16182-YB03-P0ZEN-165548 | 2019-02-21 | DHI-TRANSMIT-002387 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6eccd5a0-c9ca-4026-9aad-2f73deb4b7c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8870 | T16182-YD04-P0ZEN-152020 | 2019-02-21 | DHI-WTRAN-001546 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b18a400e-b374-4263-9b7e-cd09892d97de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8871 | T16182-XJ00-P0SCA-140210 | 2019-02-21 | DHI-TRANSMIT-002388 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e1951ab-1485-4ead-9214-c4a312d78706 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8872 | T16182-XJ00-P0ZEN-140120 | 2019-02-21 | DHI-TRANSMIT-002388 | IFC | 8 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa68c99e-f3a6-43e5-9381-abd528ea2ca2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8873 | T16182-YB03-P0ZEN-152052 | 2019-02-25 | DHI-WTRAN-001547 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3771cf29-6f0d-418d-8347-a54c48ba46b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8874 | T16182-YU03-P0BFA-150956 | 2019-02-25 | DHI-WTRAN-001548 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cdee9411-3b8d-4fd1-a9dc-c97a15407314 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8875 | T16182-YU03-P0BFA-150957 | 2019-02-25 | DHI-WTRAN-001548 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d68e550f-54e8-4bcd-9144-c1dce4888322 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8876 | T16182-YD00-P0CYE-138143 | 2019-02-25 | DHI-TRANSMIT-002389 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca9c4191-e47b-4c80-abbb-98e19bb5e225 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8877 | T16182-YU02-P0CYE-138144 | 2019-02-25 | DHI-TRANSMIT-002389 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4550d859-8119-41db-8b64-1820fc41f81a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8878 | T16182-XH01-P0SGC-137211 | 2019-02-25 | DHI-TRANSMIT-002390 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7c75e3c-f5a4-4814-8f0d-955c3d82285f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8879 | T16182-YS01-P0MKY-290011 | 2019-02-25 | DHI-TRANSMIT-002391 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c81e96f-36c4-4f2f-99db-9e783daefcbd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8880 | T16182-XJ00-P0GM-140224 | 2019-02-25 | DHI-TRANSMIT-002392 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1fdda7d-8c6b-412b-9108-298eb8ba32ff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8881 | T16182-XJ00-P0GHC-140213 | 2019-02-25 | DHI-TRANSMIT-002392 | IFC | 8 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7664d23f-a469-43bd-bbfd-6021ea2474d9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8882 | T16182-YD00-P0CWQ-161401 | 2019-02-25 | DHI-TRANSMIT-002393 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa7efa93-4a13-4d91-972a-73ef41709f1b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8883 | T16182-YD00-P0CWQ-161402 | 2019-02-25 | DHI-TRANSMIT-002393 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b670760a-c18a-420b-8539-3f50b5c502f2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8884 | T16182-YD00-P0CWQ-161407 | 2019-02-25 | DHI-TRANSMIT-002393 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d40849ea-b056-4ef1-9cdb-03f2065b994e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8885 | T16182-YD00-P0CWQ-161408 | 2019-02-25 | DHI-TRANSMIT-002393 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6250674c-1f92-47a4-b0de-96c2ff3e8d82 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8886 | T16182-YL16-P0ZEN-165552 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9137dc3d-06b2-4395-9e47-f51a3b6a3f1b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8887 | T16182-YL16-P0ZEN-165553 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d9017db-2600-49a1-8b25-386deed66250 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8888 | T16182-YL16-P0ZEN-165554 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d401523-aae0-4ade-a2c5-efa3e9157427 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8889 | T16182-YL16-P0ZEN-165555 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e873ada-e29c-4628-ab65-53c193d7bfe6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8890 | T16182-YL16-P0ZEN-165556 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=64ac98da-ad15-4a07-a726-0d2b246e169d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8891 | T16182-YL16-P0ZEN-165557 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a037886a-ede9-4e2a-961b-dda6712d956b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8892 | T16182-YL16-P0ZEN-165558 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a5ccacc-e335-4754-8cb4-82aab24c8fa2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8893 | T16182-YL16-P0ZEN-165559 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc4181ec-820c-417e-8695-b10fbf9cf165 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8894 | T16182-YL16-P0ZEN-165560 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70aaaaa0-4031-4e02-994f-9d7d5e005264 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8895 | T16182-YL16-P0ZEN-165561 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c73729ba-7b0a-4563-97da-0e62fbeee4b4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8896 | T16182-YL16-P0ZEN-165562 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bbea82b-592c-469c-855b-127bc70a8ba1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8897 | T16182-YL16-P0ZEN-165563 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3a7ae19-bed6-4333-a58f-01ea502fac25 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8898 | T16182-YL16-P0ZEN-165564 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f5558a1-9271-4133-929d-77bf07264e97 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8899 | T16182-YL16-P0ZEN-165565 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b8d5802-d98b-40d1-b941-3c90c936f93c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8900 | T16182-YL16-P0ZEN-165566 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7325c2a0-802f-481a-a8a9-d116de20f51a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8901 | T16182-YL16-P0ZEN-165567 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a34c2072-8af9-4237-8da2-9838ab00be04 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8902 | T16182-YL16-P0ZEN-165568 | 2019-02-25 | DHI-TRANSMIT-002394 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5f717ee-e1b5-4522-9afb-c34bcf94d744 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8903 | T16182-YQ01-P0ZEN-152201 | 2019-02-25 | DHI-TRANSMIT-002395 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3bf8046b-7d9d-43aa-a3b9-179dd814ff11 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8904 | T16182-YQ01-P0ZEN-152314 | 2019-02-25 | DHI-TRANSMIT-002395 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e46568da-76db-4eaf-9f27-5bbf74cadf58 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8905 | T16182-YD00-P0CYE-136841 | 2019-02-25 | DHI-TRANSMIT-002396 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7a11583-3360-45b4-b1b3-bed2dfb97473 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8906 | T16182-YU02-P0CYE-136842 | 2019-02-25 | DHI-TRANSMIT-002396 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ceb3cbf-4bc3-4b4c-bb08-4eabf7591c67 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8907 | T16182-XW03-P0SAL-134001 | 2019-02-25 | DHI-TRANSMIT-002397 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbec002c-546c-46bf-b24d-b2c2db717f95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8908 | T16182-XG07-P0SAL-134002 | 2019-02-25 | DHI-TRANSMIT-002397 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bfd8c2c-b708-4329-aa61-7a9c4a6a76e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8909 | T16182-XW03-P0SAL-134003 | 2019-02-25 | DHI-TRANSMIT-002397 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ad71792-03a8-4359-951a-bee8888d9c65 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8910 | T16182-XH02-P0SAL-134004 | 2019-02-25 | DHI-TRANSMIT-002397 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33ca81f6-a7f5-4c51-b665-603896ba8301 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8911 | T16182-XG02-P0GKC-120002 | 2019-02-27 | DHI-TRANSMIT-002398 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4d438313-02fe-46ab-9329-659c04eec873 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8912 | T16182-YT10-P0SGC-138122 | 2019-02-27 | DHI-TRANSMIT-002399 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=747ae0eb-6d29-4ece-ba4d-1eb8002c4b52 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8913 | T16182-YD02-P0ZEN-165507 | 2019-02-27 | DHI-TRANSMIT-002400 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b380b20f-0f9f-4035-80bc-21ea73b5a80d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8914 | T16182-XJ00-P0GKB-140212 | 2019-02-28 | DHI-TRANSMIT-002401 | IFC | 8 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e19fad2-c3d8-447e-ad80-ac7ecf3194bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8915 | T16182-XJ00-P0LAB-140208 | 2019-02-28 | DHI-TRANSMIT-002401 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fa74549-5e02-4e61-bb23-8f0672d6ed3a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8916 | T16182-XJ00-P0LBA-140201 | 2019-02-28 | DHI-TRANSMIT-002401 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f44117c-b80f-493c-96d1-571d395b13a1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8917 | T16182-XJ00-P0PGB-140209 | 2019-02-28 | DHI-TRANSMIT-002401 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=17bdc864-40d6-464c-92f9-362bf90d416e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8918 | T16182-YK00-P0ZEN-165322 | 2019-02-28 | DHI-TRANSMIT-002402 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a54271c-ea46-4576-adea-aab7aac70009 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8919 | T16182-YD00-P0UCA-150501 | 2019-03-04 | DHI-TRANSMIT-002403 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da5b6ecc-be50-43fc-a124-012c3396c889 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8920 | T16182-YD00-P0CYE-139441 | 2019-03-05 | DHI-TRANSMIT-002404 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7825713-79de-4084-92a5-cf1b61388597 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8921 | T16182-YU02-P0CYE-139442 | 2019-03-05 | DHI-TRANSMIT-002404 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d648100-b6ef-4ad2-b84d-627db8643310 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8922 | T16182-XG02-P0QJA-110012 | 2019-03-06 | DHI-TRANSMIT-002405 | IFC | 3 | D | TRUE | FALSE | 2019-03-06_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc869648-12d6-4080-a63d-c091bb277f74 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8923 | T16182-XJ00-P0LCM-140205 | 2019-03-06 | DHI-TRANSMIT-002406 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3271884b-4296-4b45-9335-ac92352c50c5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8924 | T16182-XJ00-P0MBH-140216 | 2019-03-06 | DHI-TRANSMIT-002406 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6c011326-0d65-4892-9268-86ba4b9fd273 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8925 | T16182-YE00-P0GCF-130015 | 2019-03-06 | DHI-TRANSMIT-002407 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36392bd8-60ba-43c6-94bc-b870425acc21 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8926 | T16182-YU03-P0GCF-130017 | 2019-03-06 | DHI-TRANSMIT-002407 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a139d3be-4838-454b-b0b4-856a30ee5380 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8927 | T16182-YF02-P0GCF-130011 | 2019-03-06 | DHI-WTRAN-001550 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=942106ba-be2d-4fe4-95e5-8e2550f674e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8928 | T16182-YS01-P0MKY-290009 | 2019-03-06 | DHI-TRANSMIT-002408 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c000b3a3-23b7-4869-b0a3-772b01b59c80 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8929 | T16182-YM03-P0LD-130221 | 2019-03-07 | DHI-WTRAN-001551 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=935e4785-3733-4e04-b036-f983dc8a861a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8930 | T16182-YE00-P0LD-130215 | 2019-03-07 | DHI-TRANSMIT-002411 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7eb85f6d-7cca-4c9f-8dd9-b252c835b371 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8931 | T16182-YU03-P0CYE-136606 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d352d01f-ce7d-4b0a-bf1b-5a24701cd1a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8932 | T16182-YU02-P0CYE-136607 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9318fbc9-0bd6-45bb-aa18-24ab1f2bc4c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8933 | T16182-YD00-P0CYE-137441 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24993c72-36f0-4aae-a2e7-8c9fd0f68f89 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8934 | T16182-YU02-P0CYE-137442 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a9e57b6-3b30-405d-8cb6-0964537b5696 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8935 | T16182-YD00-P0CYE-138341 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d521b42-30d8-4074-b354-42c338198507 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8936 | T16182-YU02-P0CYE-138342 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a501435-c038-4471-98fd-b7025193670a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8937 | T16182-YD00-P0CYE-138241 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fc83061-e993-4670-9243-baa8b3b67ba7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8938 | T16182-YU02-P0CYE-138242 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=027c04cb-8c66-4ee2-bcc9-458a38314689 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8939 | T16182-YD00-P0CYE-137041 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5e2e392-92e5-40c3-a17a-6b8a1d823f6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8940 | T16182-YU02-P0CYE-137042 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02c7bae3-2327-4aea-a15a-45a2792c2530 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8941 | T16182-YD00-P0CYE-137141 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=046a7d17-a91e-4167-87df-703b83b6eb2e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8942 | T16182-YU02-P0CYE-137142 | 2019-03-07 | DHI-TRANSMIT-002412 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc84aca6-cd72-4894-b8b4-3df10d09d9b0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8943 | T16182-YT10-P0ASR-155013 | 2019-03-11 | DHI-TRANSMIT-002414 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b334d92b-58a9-4c96-9c10-4175e128cf3f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8944 | T16182-XJ00-P0LCA-140206 | 2019-03-11 | DHI-TRANSMIT-002415 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ae74e1a-3248-4873-a59b-a112e9fb1634 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8945 | T16182-XJ00-P0QFB-140211 | 2019-03-11 | DHI-TRANSMIT-002415 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9e18ae6-e9c2-4ad4-a284-e1254d6b0a89 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8946 | T16182-XJ00-P0SCA-140210 | 2019-03-11 | DHI-TRANSMIT-002415 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c76567d-ecf8-43a1-a031-44c25b5f8761 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8947 | T16182-XJ00-P0QJA-140223 | 2019-03-11 | DHI-TRANSMIT-002415 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50bcffe1-3cba-410e-b820-cf776cb44ca6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8948 | T16182-XJ00-P0GKB-140212 | 2019-03-11 | DHI-TRANSMIT-002415 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b1a3621-45e3-445e-a659-f42b04c78da1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8949 | T16182-XW01-P0SCA-127556 | 2019-03-12 | DHI-WTRAN-001553 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33053c44-9a69-4415-b3fe-9603f7ea78e1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8950 | T16182-YB03-P0LB-122047 | 2019-03-12 | DHI-WTRAN-001554 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9f32e50b-8fdb-4124-89f8-f1cff0fb6245 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8951 | T16182-YL16-P0LB-122078 | 2019-03-12 | DHI-WTRAN-001554 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f00bca37-1f34-451b-abeb-4cdf2e24cf6f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8952 | T16182-YB11-P0ZEN-152401 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b853fd67-7980-4793-bf51-ead6d80bafad | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8953 | T16182-YB11-P0ZEN-152402 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df9f2213-9fbe-49ed-ab22-740f2b92ed33 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8954 | T16182-YB11-P0ZEN-152403 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=813c734f-2a38-4d88-9367-ff8407774151 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8955 | T16182-YB11-P0ZEN-152404 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c3fc0ca8-d314-46d3-8ad3-fae96ba61831 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8956 | T16182-YB11-P0ZEN-152405 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f341c24-ec52-4f15-830d-60e2a90b62dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8957 | T16182-YB11-P0ZEN-152406 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65ffc5ab-9b40-4649-90df-fcc0602e8689 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8958 | T16182-YB11-P0ZEN-152407 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4aa7eb6-d6ae-46cc-a6f4-fab67a2deba0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8959 | T16182-YB11-P0ZEN-152408 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60ab6eaf-1cc5-48e6-b715-7acb64a48d13 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8960 | T16182-YB11-P0ZEN-152409 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9bb693cc-3608-4f29-8b9e-123dd6c32ef5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8961 | T16182-YB11-P0ZEN-152411 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b7eaa72-5127-44d9-9270-fff0b2eee10f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8962 | T16182-YB11-P0ZEN-152415 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51c99408-5cce-4ad3-9b0c-cc8916d6ac04 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8963 | T16182-YB11-P0ZEN-152418 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a413aa66-3427-4011-ab11-f32c0e9f2d66 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8964 | T16182-YB11-P0ZEN-152419 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b83e6808-d661-4bf5-b567-f78b1e7b7263 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8965 | T16182-YB11-P0ZEN-152421 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aff2a764-892e-4fcc-9a97-a4cb9f65b415 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8966 | T16182-YB11-P0ZEN-152427 | 2019-03-12 | DHI-TRANSMIT-002417 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da8ce27c-990a-459d-a853-4af11a38e0af | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8967 | T16182-YD00-P0CYE-136941 | 2019-03-12 | DHI-TRANSMIT-002418 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=530dd130-c7cd-4bd8-8da8-c0463ac59ca1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8968 | T16182-YU02-P0CYE-136942 | 2019-03-12 | DHI-TRANSMIT-002418 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0043b0d9-6490-4ac5-a1e0-c4c7e0a1376e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8969 | T16182-DP00-P8ZEN-125766 | 2019-03-12 | DHI-TRANSMIT-002419 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0230642c-c741-4d52-94ce-dba01c7c3187 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8970 | T16182-YT01-P0SGA-136609 | 2019-03-12 | DHI-TRANSMIT-002420 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fabef02-343e-4325-b7c9-44caff678c28 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8971 | T16182-YS01-P0MKY-290012 | 2019-03-13 | DHI-TRANSMIT-002421 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9488691-9713-49b2-a3ff-589c53463d18 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8972 | T16182-YS01-P0MKY-290013 | 2019-03-13 | DHI-TRANSMIT-002421 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80d2d3b7-5cbc-4236-9300-c8b0df97e61e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8973 | T16182-YS01-P0MKY-290009 | 2019-03-13 | DHI-TRANSMIT-002422 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33ed735b-7833-4ad8-970a-d5af29b1d8e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8974 | T16182-YE00-P0ZEN-152707 | 2019-03-14 | DHI-TRANSMIT-002423 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=31b461a1-0a5e-4692-8ac8-3c1e2cd02f08 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8975 | T16182-XJ00-P0GKB-140215 | 2019-03-14 | DHI-TRANSMIT-002424 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6361dfaf-1ca1-45fa-ad97-6bd755aabeea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8976 | T16182-XB02-P0UAZ-172608 | 2019-03-15 | DHI-TRANSMIT-002425 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf337d6f-5188-4a83-a22e-4a5bd38e9cf1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8977 | T16182-XJ00-P0ZEN-140120 | 2019-03-18 | DHI-TRANSMIT-002427 | IFC | 9 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a060fe6a-53a0-4b60-a103-0d244a09f57b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8978 | T16182-YU02-P0ZEN-150212 | 2019-03-18 | DHI-TRANSMIT-002428 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=995b1a05-5de3-4641-aed0-993e8dc0995d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8979 | T16182-VK02-P0UGF-173107 | 2019-03-18 | DHI-TRANSMIT-002429 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a550925-4a92-4f33-b792-03973676eda9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8980 | T16182-YS00-P0CJN-290001 | 2019-03-19 | DHI-TRANSMIT-002432 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77529ed7-3b3c-43c1-a14e-24c3e563cfdf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8981 | T16182-YK09-P0LD-130212 | 2019-03-19 | DHI-TRANSMIT-002433 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d04cf71c-67a9-48a0-ab20-58c65881264c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8982 | T16182-XG07-P0SCA-120014 | 2019-03-22 | DHI-TRANSMIT-002434 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=030384af-7387-49a9-8580-893114eabed8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8983 | T16182-XJ00-P0GM-140224 | 2019-03-22 | DHI-TRANSMIT-002435 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b5b86a2-4341-492f-9e48-206a4bcc14dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8984 | T16182-YD00-P0LCB-127555 | 2019-03-25 | DHI-WTRAN-001557 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e9a78295-ad81-42cb-9a2e-c33c33d6df57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8985 | T16182-XG02-P0SCA-127557 | 2019-03-26 | DHI-WTRAN-001561 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa7f63e4-5cd4-4c44-8086-15da28ed38b5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8986 | T16182-DN05-P0SG-136623 | 2019-03-26 | DHI-TRANSMIT-002436 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a050357-3f6c-4dbc-9192-2266155a31cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8987 | T16182-XW03-P0MJ-110053 | 2019-03-26 | DHI-TRANSMIT-002437 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bb55310-b226-4c2c-bfbd-a606c997a185 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8988 | T16182-CA00-P0UTG-184901 | 2019-03-26 | DHI-TRANSMIT-002438 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=761d2928-41c3-4769-92cf-aaa71d06db3a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8989 | T16182-CA01-P0UTG-184952 | 2019-03-26 | DHI-TRANSMIT-002438 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c7cefd2b-83fd-48b6-abcc-0acb86a256fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8990 | T16182-XW01-P0SCA-127556 | 2019-03-28 | DHI-WTRAN-001562 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8991 | T16182-XW03-P0LB-122110 | 2019-03-29 | DHI-WTRAN-001563 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f367358c-2c16-4c90-a30e-86c3f866bc51 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8992 | T16182-XJ00-P0LBG-140204 | 2019-03-29 | DHI-TRANSMIT-002439 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b94bcc03-fef8-4853-bce2-3e259e0f0976 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8993 | T16182-XJ00-P0ZEN-140120 | 2019-03-29 | DHI-TRANSMIT-002439 | IFC | 10 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a089ccae-4175-4179-acda-39bb5c783130 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8994 | T16182-XG02-P0GCF-130004 | 2019-03-29 | DHI-TRANSMIT-002440 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b36322eb-054c-443c-964e-d2db6cc09557 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8995 | T16182-XG02-P0GM-122112 | 2019-04-01 | DHI-TRANSMIT-002442 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eaab9501-cf1f-4ab2-aebe-1f04cdaa97c3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8996 | T16182-XJ00-P0GHC-140213 | 2019-04-01 | DHI-TRANSMIT-002443 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25bde67d-0975-41e7-bc6a-472cf569cd12 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8997 | T16182-XJ00-P0SGA-136622 | 2019-04-01 | DHI-TRANSMIT-002444 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b9ffea2c-7d51-4a8f-8b2e-1579c3b00cc0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8998 | T16182-VK02-P0UZK-173502 | 2019-04-03 | DHI-WTRAN-001564 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5cb3503-ce04-4401-a2c9-add4f5f8f734 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
8999 | T16182-XB02-P0UZK-173501 | 2019-04-03 | DHI-WTRAN-001564 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=da4903cd-0f0f-46d2-9399-17e00aa1523a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9000 | T16182-YT10-P0ASR-155013 | 2019-04-04 | DHI-TRANSMIT-002445 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8bf9b0bb-c092-41a6-85b6-03c758852c99 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9001 | T16182-XJ00-P0ZEN-140120 | 2019-04-04 | DHI-TRANSMIT-002446 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b45977d8-09e9-4d58-ba82-22b3545d0cc4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9002 | T16182-XJ00-P0LBA-140201 | 2019-04-04 | DHI-TRANSMIT-002446 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d017b34a-409c-4d5f-ac3c-56cda28c9b96 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9003 | T16182-XJ00-P0LBC-140202 | 2019-04-04 | DHI-TRANSMIT-002446 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71a1c4ab-387a-45bb-86ce-0541161a3803 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9004 | T16182-XJ00-P0LBG-140203 | 2019-04-04 | DHI-TRANSMIT-002446 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3994252c-f558-499a-8959-b4000389023e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9005 | T16182-XJ00-P0SCA-140210 | 2019-04-04 | DHI-TRANSMIT-002446 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=424df2cb-9583-4660-b156-939094fa2920 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9006 | T16182-XJ00-P0GKB-140212 | 2019-04-04 | DHI-TRANSMIT-002446 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c14d98e-b4dd-4286-9748-8f537d2454a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9007 | T16182-XJ00-P0QJA-140223 | 2019-04-04 | DHI-TRANSMIT-002446 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9a8dc8b-5987-493f-afee-ed28aaaef08f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9008 | T16182-XG02-P0SCA-127557 | 2019-04-08 | DHI-WTRAN-001565 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9009 | T16182-YD00-P0LCB-127555 | 2019-04-08 | DHI-WTRAN-001566 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9010 | T16182-UC02-P0MKA-250010 | 2019-04-08 | DHI-WTRAN-001567 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93eb9124-340b-4360-8371-a74f3cd84312 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9011 | T16182-YK00-P8ZEN-125720 | 2019-04-08 | DHI-WTRAN-001568 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44faaada-86ce-4701-b817-089f2cbfc4b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9012 | T16182-VN01-P0MAG-123055 | 2019-04-08 | DHI-WTRAN-001569 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12c10a30-7396-45dd-9001-7d3b1bb8b2bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9013 | T16182-BV02-P0CJN-290003 | 2019-04-09 | DHI-WTRAN-001570 | IFR | E | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bebe625-34b2-4c10-8459-e9a630354e94 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9014 | T16182-YB03-P8ZEN-125732 | 2019-04-09 | DHI-TRANSMIT-002449 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9fbfd85-e1b4-4bdc-b897-279da83ecb9d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9015 | T16182-YB03-P8ZEN-125761 | 2019-04-09 | DHI-TRANSMIT-002449 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecb2e17f-4ef7-42fa-b430-08b592b57a9e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9016 | T16182-YL16-P8ZEN-125731 | 2019-04-09 | DHI-TRANSMIT-002449 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d882005-4dcb-4754-812f-53dc561c1a39 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9017 | T16182-YL16-P8ZEN-125760 | 2019-04-09 | DHI-TRANSMIT-002449 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8372fb27-7260-4659-8299-5d1c2b681e2e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9018 | T16182-YM03-P8ZEN-125721 | 2019-04-09 | DHI-TRANSMIT-002449 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=700467cd-e93a-427d-bec8-257a440b65aa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9019 | T16182-VK02-P0UZJ-173208 | 2019-04-10 | DHI-TRANSMIT-002450 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d74973fd-9e82-4838-90ac-7e32c6cb7459 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9020 | T16182-XB02-P0UZJ-173202 | 2019-04-10 | DHI-TRANSMIT-002450 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2cf4dbae-978c-4214-8384-e8a491c53558 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9021 | T16182-YL01-P0SCA-127517 | 2019-04-11 | DHI-WTRAN-001571 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=953988dd-f58b-4e37-b441-243f80d65532 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9022 | T16182-YD16-P0SCA-127546 | 2019-04-11 | DHI-WTRAN-001571 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db63305f-3da7-430f-9504-8653b55378c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9023 | T16182-YL01-P0SCA-127516 | 2019-04-11 | DHI-WTRAN-001571 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89a61688-92de-4035-841e-eda0334f603d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9024 | T16182-YF02-P0SCA-127514 | 2019-04-11 | DHI-WTRAN-001571 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cfad3fd-cfaf-4387-ab24-b59271ef69ba | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9025 | T16182-YR05-P0SCA-127523 | 2019-04-11 | DHI-WTRAN-001571 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=363f09e6-230a-461d-ae46-1d91ced53a15 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9026 | T16182-YU02-P0ZEN-150202 | 2019-04-11 | DHI-TRANSMIT-002461 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e13136f-eb09-4f2d-8f83-33aaf6e7422f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9027 | T16182-YT01-P0LD-130214 | 2019-04-15 | DHI-WTRAN-001572 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a3f6814-ff1f-4154-a63c-9ca09a80bd44 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9028 | T16182-YD00-P0UBA-150502 | 2019-04-15 | DHI-TRANSMIT-002462 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e654c43-65be-48c5-bb60-33f66c808a54 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9029 | T16182-YD04-P0ZEN-152020 | 2019-04-16 | DHI-TRANSMIT-002463 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a3bad0c-de72-4844-afa9-2df0e80ee511 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9030 | T16182-UE00-P0LB-122111 | 2019-04-16 | DHI-TRANSMIT-002464 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac88426d-9683-4806-8422-403f319196a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9031 | T16182-XW03-P0LB-122110 | 2019-04-16 | DHI-TRANSMIT-002464 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe41e00c-f20f-4070-9254-0138cc89c0e4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9032 | T16182-XB02-P0UZA-172911 | 2019-04-17 | DHI-WTRAN-001573 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d611b67f-ae77-4cee-a72f-240e10997ea0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9033 | T16182-VK02-P0UZA-172912 | 2019-04-17 | DHI-WTRAN-001573 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87c4ce3c-d223-402f-87c9-33afa8d7ebb0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9034 | T16182-YL06-P0ZEN-150101 | 2019-04-17 | DHI-TRANSMIT-002465 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45e90fb1-5735-4c78-8c5a-3591bedd965e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9035 | T16182-XB02-P0UAZ-172608 | 2019-04-17 | DHI-TRANSMIT-002466 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8acc50e4-afb8-493b-929a-e832800a8778 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9036 | T16182-DE00-P0ZEN-152823 | 2019-04-17 | DHI-TRANSMIT-002467 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b93b96d-913a-48b4-bee1-108f879701b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9037 | T16182-XG02-P0GKB-120001 | 2019-04-18 | DHI-TRANSMIT-002470 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f044f56-e92a-4139-b3c5-b3db7652ca26 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9038 | T16182-YL00-P0QU-130404 | 2019-04-19 | DHI-WTRAN-001575 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92b4ae2b-e212-40a5-bbd7-afe826ac1f9e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9039 | T16182-XB02-P0UNX-171402 | 2019-04-19 | DHI-TRANSMIT-002474 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fb0dc0b-57a6-4568-9c83-0577503f1efa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9040 | T16182-XB02-P0UNX-171403 | 2019-04-19 | DHI-TRANSMIT-002474 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac0a3237-8c51-4f5d-9f73-3daac2e43056 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9041 | T16182-XB02-P0UNX-171410 | 2019-04-19 | DHI-TRANSMIT-002474 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccd9a872-26c7-4de1-b5fb-b61f2d281caa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9042 | T16182-XH01-P0LF-140410 | 2019-04-22 | DHI-WTRAN-001576 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9cfa111e-0b2b-46e6-820b-3d41ad340a32 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9043 | T16182-YT01-P0MBA-121023 | 2019-04-22 | DHI-WTRAN-001577 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4944550f-64f4-4dc2-92fa-3b789bc2b9c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9044 | T16182-YQ08-P0CY-154038 | 2019-04-22 | DHI-TRANSMIT-002475 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2f644bb-0db9-4726-9158-424e0229b535 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9045 | T16182-XG02-P0MBA-121003 | 2019-04-22 | DHI-TRANSMIT-002476 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d9e1319-03c1-406c-a66c-8abd77fcb9c8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9046 | T16182-XJ00-P0GKB-140212 | 2019-04-23 | DHI-TRANSMIT-002477 | IFC | 11 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d85f7877-89eb-4de3-bcb5-0a6bdbfe9e25 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9047 | T16182-XJ00-P0GM-140224 | 2019-04-23 | DHI-TRANSMIT-002477 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62517da5-59fb-4aca-8e58-2abef7e9d6ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9048 | T16182-XJ00-P0LAB-140208 | 2019-04-23 | DHI-TRANSMIT-002477 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d757d0f2-12a8-4a06-a4a9-7f8f668b58e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9049 | T16182-XJ00-P0ZEN-140120 | 2019-04-23 | DHI-TRANSMIT-002477 | IFC | 12 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afb0982c-da29-4eb7-b3dc-0a567eec1017 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9050 | T16182-YD00-P0BF-150931 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdc46207-0a72-4027-aad7-99cf49c24a83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9051 | T16182-YD00-P0BF-150932 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d5d307b5-b35e-4758-b440-3e197712f0fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9052 | T16182-YD00-P0BF-150933 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ed3fcf30-33c7-4a43-8e6e-1aea40507e4c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9053 | T16182-YD00-P0BF-150934 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9089321-d330-4964-bc60-23a4e1a2ad0f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9054 | T16182-YD00-P0BF-150935 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47a6a33f-7193-4fac-8ccc-15f6fd502d75 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9055 | T16182-YD00-P0BF-150936 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35149380-41c0-4cae-aac5-7c01bb9cf120 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9056 | T16182-YD00-P0BF-150937 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44640088-7813-4f48-9081-c64918550915 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9057 | T16182-YD00-P0BF-150938 | 2019-04-24 | DHI-WTRAN-001578 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18b89ac8-5c4f-48a9-b4b6-1f7df966e5a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9058 | T16182-YU02-P0BFA-150911 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea20d0f9-a139-4a98-8b55-7e3fc7bbf751 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9059 | T16182-YU02-P0BFA-150912 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=885c8b71-2abb-4612-821f-74f3aeee57d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9060 | T16182-YU02-P0BFA-150913 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=370ffe95-4776-4d3b-80d2-735bac4b47e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9061 | T16182-YU02-P0BFA-150914 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1152811-bf8d-45ab-b9b1-989f67d8c139 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9062 | T16182-YU02-P0BFA-150915 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e8236f5-ed83-4280-ae73-59f0cccb73fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9063 | T16182-YU02-P0BFA-150916 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3841bf1e-bd30-4ba8-b357-4245a26b2ae7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9064 | T16182-YU02-P0BFA-150917 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96d5ea93-ae2f-40b1-93ea-5002e9038acc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9065 | T16182-YU02-P0BFA-150918 | 2019-04-24 | DHI-WTRAN-001579 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1711f988-190d-4b94-83a1-68da85787342 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9066 | T16182-CA00-P0UBA-181001 | 2019-04-26 | DHI-TRANSMIT-002478 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c92ab59b-de21-44f4-b850-52c4871309a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9067 | T16182-CA00-P0UBA-181005 | 2019-04-26 | DHI-TRANSMIT-002478 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b0a7ad6-f08e-4700-ab12-0a0d7f68f8cb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9068 | T16182-CA00-P0UBA-181101 | 2019-04-26 | DHI-TRANSMIT-002478 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=58576bb2-f608-4ccd-ad5f-8216c1d7c9e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9069 | T16182-CA00-P0UBA-181105 | 2019-04-26 | DHI-TRANSMIT-002478 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ac7d0cd-8cab-43b5-b659-3fbac4afbe72 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9070 | T16182-CA00-P0UBA-186101 | 2019-04-26 | DHI-TRANSMIT-002478 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df7e64a7-6edc-43e8-8f44-d8960e64873a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9071 | T16182-XB02-P0UGF-173101 | 2019-04-26 | DHI-TRANSMIT-002479 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8050606-04bd-4896-81a2-f655f5420cab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9072 | T16182-XB02-P0UGF-173102 | 2019-04-26 | DHI-TRANSMIT-002479 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a184fd3-2f21-4a65-b5ae-0f9a803326e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9073 | T16182-YK09-P0LCB-127004 | 2019-04-26 | DHI-TRANSMIT-002480 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf24acbe-cb2b-4e7c-a7af-46c4fea23258 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9074 | T16182-XB02-P0UZJ-173902 | 2019-04-30 | DHI-WTRAN-001581 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1c555c3-301e-4d43-bd03-5c249496bd54 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9075 | T16182-VK02-P0UZJ-173903 | 2019-04-30 | DHI-WTRAN-001581 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7384d8f5-884f-4f18-8b65-79a865fff74a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9076 | T16182-CA00-P0UYC-182908 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd7bf4b4-515e-4df5-8852-f0f0d19c71ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9077 | T16182-CA01-P0UYC-182952 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efd9f694-c11c-4bb1-a5cb-92997fcadbb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9078 | T16182-CA01-P0UYC-182953 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2bcd87f-6b9e-4b82-b081-a9fcd4863127 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9079 | T16182-CA02-P0UYC-182958 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e880a45f-e793-4e97-9c05-beb9f1680dc6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9080 | T16182-CA05-P0UYC-182981 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=62e122d1-945e-4977-bc68-db53aa5ce8c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9081 | T16182-CA05-P0UYC-182983 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e309b94-6389-460f-8cc8-7005c91cd419 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9082 | T16182-CA05-P0UYC-182985 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48727207-ef97-44b9-8ac8-9408c97da339 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9083 | T16182-CA00-P0UYC-182901 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=120aa54a-a59b-4635-86ca-a9d8dd1b81fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9084 | T16182-CA00-P0UYC-182902 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=937dc0b6-b45d-435e-9853-a2153819ab51 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9085 | T16182-CA00-P0UYC-182903 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=18ed6a82-46df-4831-8283-660540c35a19 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9086 | T16182-CA00-P0UYC-182904 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=267288ca-1a2d-4bf1-b79c-4206b439a36c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9087 | T16182-CA00-P0UYC-182905 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20e4c509-d8ff-4cc4-af30-07c2c87bbadb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9088 | T16182-CA00-P0UYC-182906 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=377cdb44-7753-45cc-92a2-de414ef30e06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9089 | T16182-CA00-P0UYC-182907 | 2019-04-30 | DHI-TRANSMIT-002494 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cfd12fa8-e342-4e42-a418-333dc437dc30 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9090 | T16182-YD00-P0BAA-150782 | 2019-05-02 | DHI-WTRAN-001582 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c7b5f35-d4e7-4c60-a732-c293c2339f5c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9091 | T16182-CA00-P0UBA-181202 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b12ce32f-9b07-425e-b587-1b2da990f872 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9092 | T16182-CA00-P0UBA-181203 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3a396435-3f5a-4c2b-acdc-2da747938c0f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9093 | T16182-CA00-P0UBA-181206 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f67fb3b6-8889-423f-a771-caacd122b1a8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9094 | T16182-CA00-P0UBA-181207 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e92dc6d3-6b7f-49ed-9b10-6ba8cc967925 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9095 | T16182-CA00-P0UBA-181208 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5490f4d5-cb35-4b2f-8dcc-1db1cde35f5a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9096 | T16182-CA00-P0UBA-181302 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec7cdca4-2276-4c5d-b02b-18c14c705686 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9097 | T16182-CA00-P0UBA-181303 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fb731e1-80e6-4277-a6d3-3dd2a7710aac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9098 | T16182-CA00-P0UBA-181306 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b4e15b3-595c-4fab-8ec3-ef7e14159632 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9099 | T16182-CA00-P0UBA-181307 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65bf3a03-4283-49bd-926b-e719c3122cc2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9100 | T16182-CA00-P0UYB-183501 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b68fa76d-372e-4fb1-a4d1-208da843d3d9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9101 | T16182-CA01-P0UBA-181252 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=abdc3246-a9d0-4fd2-b271-6bcb61ef9094 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9102 | T16182-CA01-P0UBA-181253 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f525964-266e-420a-aff6-66c194aebae5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9103 | T16182-CA01-P0UBA-181352 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b588582-4cb0-4dfc-a846-06a1db68dccc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9104 | T16182-CA01-P0UBA-181353 | 2019-05-02 | DHI-TRANSMIT-002495 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=035a8cf5-8547-4cce-9ec8-337f9f597166 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9105 | T16182-XJ00-P0LAB-140208 | 2019-05-02 | DHI-TRANSMIT-002496 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74bbe4a0-2aa3-4eaa-9898-5cb435414d39 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9106 | T16182-XJ00-P0ZEN-140120 | 2019-05-02 | DHI-TRANSMIT-002496 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fb6b7a0-8158-4f79-89d6-2c991610fbe3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9107 | T16182-YU03-P0BB-150831 | 2019-05-03 | DHI-WTRAN-001583 | IFI | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4abf2f2-33a9-4025-91a4-402bf325d699 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9108 | T16182-YU03-P0BB-150836 | 2019-05-03 | DHI-WTRAN-001583 | IFI | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e24b8bc5-2684-427c-9de1-996d856a6428 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9109 | T16182-YF00-P0BB-150402 | 2019-05-03 | DHI-TRANSMIT-002499 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87915d4f-8497-4bc9-b2ae-2e80d374de81 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9110 | T16182-XG02-P0CYE-137644 | 2019-05-07 | DHI-TRANSMIT-002500 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5253379-562e-47a6-b7be-0bd964d69aad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9111 | T16182-XG02-P0SGA-136603 | 2019-05-09 | DHI-TRANSMIT-002501 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7e4ff205-e6e9-48fc-a10f-d43459542388 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9112 | T16182-YT01-P0GHC-129032 | 2019-05-09 | DHI-WTRAN-001584 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82e38cdb-8000-46a6-9daa-c107585306fd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9113 | T16182-YD00-P0GHC-129031 | 2019-05-09 | DHI-TRANSMIT-002502 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c27fe683-da6c-4ac4-a434-2937d44fc022 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9114 | T16182-YK09-P0GHC-129033 | 2019-05-09 | DHI-TRANSMIT-002502 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e2853690-01ed-4c1a-a7fa-d8c5d72e270e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9115 | T16182-YU03-P0BB-150831 | 2019-05-09 | DHI-WTRAN-001585 | IFI | 6 | D | TRUE | FALSE |  | http:// http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=26cac97e-28df-4e42-8519-362c397750fe http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=26cac97e-28df-4e42-8519-362c397750fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9116 | T16182-YU03-P0BB-150836 | 2019-05-09 | DHI-WTRAN-001585 | IFI | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/sso/fileDown_nsso.jsp?r_object_id=bdef3d55-ed63-4ca1-9600-ab95f3454d27 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9117 | T16182-YQ01-P0ZEN-152306 | 2019-05-09 | DHI-TRANSMIT-002503 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ce4d2965-a88c-4c95-b5fa-98860fded4a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9118 | T16182-YQ01-P0ZEN-152318 | 2019-05-09 | DHI-TRANSMIT-002503 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47eb521d-c7e1-4e7e-b01f-a5fb9644f4a5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9119 | T16182-YQ01-P0ZEN-152319 | 2019-05-09 | DHI-TRANSMIT-002503 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ed4a3b8-bc1e-44a4-8aaa-a13994804fec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9120 | T16182-YD02-P0ZEN-165573 | 2019-05-09 | DHI-TRANSMIT-002504 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afcee813-42c5-4b9f-b4b0-a5b728c4313c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9121 | T16182-XW01-P0SCA-127556 | 2019-05-09 | DHI-WTRAN-001586 | IFR | B | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9122 | T16182-XJ00-P0LCA-140206 | 2019-05-10 | DHI-TRANSMIT-002505 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5f220a9-d1ec-40ef-9841-fbf1c11a375c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9123 | T16182-XJ00-P0QJA-140223 | 2019-05-10 | DHI-TRANSMIT-002505 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50e56b2a-4e1f-4c67-aa29-d00983db1ae2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9124 | T16182-YT10-P0ZEN-150312 | 2019-05-13 | DHI-TRANSMIT-002506 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e65d719f-d20a-4eae-9a21-88e5ed6b575e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9125 | T16182-YD02-P0ZEN-165516 | 2019-05-13 | DHI-TRANSMIT-002507 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff83d964-46d3-4616-b4b0-0c7e0c011f45 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9126 | T16182-VK02-P0UZA-172908 | 2019-05-14 | DHI-TRANSMIT-002508 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba5ace0e-7a40-40c5-83f4-d9cdbbbef2a0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9127 | T16182-XB02-P0UZA-172902 | 2019-05-14 | DHI-TRANSMIT-002508 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a52859d5-68e1-4103-84df-e7a45d8aa15a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9128 | T16182-XB02-P0UZA-172903 | 2019-05-14 | DHI-TRANSMIT-002508 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbf10881-34d4-4700-8fab-e16b0ef7bb53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9129 | T16182-XG02-P0SCA-120006 | 2019-05-14 | DHI-TRANSMIT-002509 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d15f46ee-3af6-4aca-a305-65e311800433 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9130 | T16182-XG02-P0SCA-120004 | 2019-05-14 | DHI-TRANSMIT-002509 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=caa2a2be-086b-4dba-92ae-9cf6070d4adb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9131 | T16182-YU02-P0BB-150811 | 2019-05-14 | DHI-WTRAN-001587 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85992be4-c8fd-46fd-8263-f850b658aa0f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9132 | T16182-YU02-P0BB-150812 | 2019-05-14 | DHI-WTRAN-001587 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=997c3365-d6a3-435a-b21a-55480243a7a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9133 | T16182-YU02-P0BB-150813 | 2019-05-14 | DHI-WTRAN-001587 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f475cf00-0569-4497-bce6-a2ae3a529eca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9134 | T16182-YU02-P0BB-150814 | 2019-05-14 | DHI-WTRAN-001587 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ddb043f-4f74-4f37-9559-f683eb1cf92c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9135 | T16182-YU02-P0BB-150815 | 2019-05-14 | DHI-WTRAN-001587 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7b0c94fb-9a81-4a4a-8be0-6460817aeafb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9136 | T16182-YU02-P0BB-150816 | 2019-05-14 | DHI-WTRAN-001587 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=52a2fae6-4790-4696-a094-b87a1fcae404 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9137 | T16182-YT10-P0ZEN-150314 | 2019-05-14 | DHI-TRANSMIT-002510 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbd61595-0e54-422f-a745-6f7e944e2d76 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9138 | T16182-YU02-P0ZEN-150212 | 2019-05-14 | DHI-TRANSMIT-002510 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ff8fea8-1519-4ef3-a9ac-5523a91af5d2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9139 | T16182-YQ08-P0CY-154036 | 2019-05-14 | DHI-TRANSMIT-002511 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c22879f8-ca42-4193-9a44-184e612b84e8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9140 | T16182-YQ08-P0CY-154044 | 2019-05-14 | DHI-TRANSMIT-002511 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=421000a1-61ba-4446-9614-8a5e0f1d1236 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9141 | T16182-BP00-P0EKG-140015 | 2019-05-16 | DHI-TRANSMIT-002512 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20ffebf6-5f7e-45fb-9d71-97de5846ad40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9142 | T16182-BP00-P0LBS-140013 | 2019-05-16 | DHI-TRANSMIT-002512 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0205869c-8d00-415c-9f2a-ca7b9fc6daaf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9143 | T16182-YL00-P0LB-122079 | 2019-05-17 | DHI-TRANSMIT-002513 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7077c90f-7fff-41dc-804f-a62e542539be | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9144 | T16182-YD00-P8ZEN-125728 | 2019-05-17 | DHI-TRANSMIT-002514 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=459ae775-bccb-46ca-984c-d72391aca3b4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9145 | T16182-YL16-P0ZEN-165568 | 2019-05-17 | DHI-TRANSMIT-002515 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99c94276-dc1a-4b10-a935-4712162134ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9146 | T16182-YS00-P0CJN-290001 | 2019-05-17 | DHI-TRANSMIT-002516 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73bb1126-5e8f-47c9-8f1e-316d56e0389b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9147 | T16182-XG02-P0GHC-110011 | 2019-05-20 | DHI-TRANSMIT-002520 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=182354b5-d0d2-4233-bf17-c69d8a8e28b7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9148 | T16182-XG02-P6LCA-110008 | 2019-05-20 | DHI-TRANSMIT-002520 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05068084-7d5d-4edb-91c9-63a73f1e9c33 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9149 | T16182-XB02-P0ULX-171202 | 2019-05-20 | DHI-TRANSMIT-002521 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c89048f8-1dc7-4e92-9841-202812b573ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9150 | T16182-XB02-P0ULX-171203 | 2019-05-20 | DHI-TRANSMIT-002521 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=994d67b7-3574-4ce5-a639-04c56cfad6c1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9151 | T16182-XB02-P0UBN-172202 | 2019-05-20 | DHI-TRANSMIT-002522 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a54a4b81-4244-410d-9bbc-cd6c678e8c04 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9152 | T16182-BP00-P0LBA-140011 | 2019-05-20 | DHI-TRANSMIT-002523 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b5ece2e2-bddf-4ab2-afc9-98f974a12ab1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9153 | T16182-BP00-P0LBC-140012 | 2019-05-20 | DHI-TRANSMIT-002523 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48e61dcb-1e99-46d2-b2fd-79510977bef5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9154 | T16182-BP00-P0LBG-140016 | 2019-05-20 | DHI-TRANSMIT-002523 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5e596fe4-656c-4bab-b76b-f0cb16e9c8b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9155 | T16182-XJ00-P0PGB-140209 | 2019-05-21 | DHI-TRANSMIT-002524 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dc5cace6-b8d1-4a9b-9e72-ff515046cade | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9156 | T16182-XJ00-P0QFB-140211 | 2019-05-21 | DHI-TRANSMIT-002524 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc7c6458-c003-4ee8-8643-401762b9c5ff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9157 | T16182-XJ00-P0SCA-140210 | 2019-05-21 | DHI-TRANSMIT-002524 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69dd7572-81b2-4ba3-9779-b00f53282093 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9158 | T16182-XJ00-P0ZEN-140120 | 2019-05-21 | DHI-TRANSMIT-002524 | IFC | 14 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d68f5959-1b13-4bc0-ae75-ba7de71f1a2b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9159 | T16182-BP00-P0LAB-140014 | 2019-05-21 | DHI-TRANSMIT-002525 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8c8acd58-e251-43db-82c6-148054157038 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9160 | T16182-BV02-P0CJN-290003 | 2019-05-22 | DHI-WTRAN-001588 | IFR | F | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2d5addca-c19c-454f-9a8f-cb4cba3edadd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9161 | T16182-YS01-P0MKY-290009 | 2019-05-22 | DHI-TRANSMIT-002529 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24f787c7-588f-419e-aaf1-6cb2079f3baa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9162 | T16182-YM01-P0GHC-129035 | 2019-05-23 | DHI-WTRAN-001589 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5e37ae9-e3df-4cdf-8c47-ff3ee35769fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9163 | T16182-YL00-P0GHC-129036 | 2019-05-23 | DHI-WTRAN-001589 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70528cb6-bcf8-4a15-844d-64f513ee22ca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9164 | T16182-YL22-P0GHC-129038 | 2019-05-23 | DHI-WTRAN-001589 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=073c5978-fa80-411e-99f6-7bfc897643da | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9165 | T16182-YT01-P0GHC-129034 | 2019-05-23 | DHI-WTRAN-001590 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b2d20401-7a85-4917-9119-e398d966b4b7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9166 | T16182-YF00-P0SCA-127518 | 2019-05-23 | DHI-WTRAN-001591 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3022691f-bf0e-4651-a604-f51d0ecad785 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9167 | T16182-XB02-P0GKC-173602 | 2019-05-23 | DHI-TRANSMIT-002530 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19b95b2f-f250-4e8d-901a-4165eafa9660 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9168 | T16182-YQ08-P0CY-154036 | 2019-05-23 | DHI-TRANSMIT-002531 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6d5fb62-3be3-4416-8797-c9c09351d8b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9169 | T16182-YQ08-P0CY-154040 | 2019-05-23 | DHI-TRANSMIT-002531 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50ebfd60-63fc-4dde-9988-80dc92440783 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9170 | T16182-YQ08-P0CY-154041 | 2019-05-23 | DHI-TRANSMIT-002531 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1532a38f-7434-4cca-878d-e4af91a5ce8c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9171 | T16182-XB02-P0ULX-171222 | 2019-05-24 | DHI-TRANSMIT-002532 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=106a18f4-e6fa-4ace-b60d-5dbee998a811 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9172 | T16182-XB02-P0ULX-171223 | 2019-05-24 | DHI-TRANSMIT-002532 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bba0b8db-8fcb-4084-93db-09d7938f1bde | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9173 | T16182-YD00-P0CYE-138941 | 2019-05-24 | DHI-TRANSMIT-002533 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ddc9595-0e81-4ac9-bd09-8fc06966c8e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9174 | T16182-YU02-P0CYE-138942 | 2019-05-24 | DHI-TRANSMIT-002533 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73788b40-cd1b-4836-85c6-74fb2b0f325a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9175 | T16182-YD00-P0CYE-139441 | 2019-05-24 | DHI-TRANSMIT-002533 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=210717b3-2cab-4989-a97d-d3544682df44 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9176 | T16182-YU02-P0CYE-139442 | 2019-05-24 | DHI-TRANSMIT-002533 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=71f4a047-2c54-42be-aa68-fcca00a75c4b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9177 | T16182-YD00-P0CYE-139141 | 2019-05-24 | DHI-TRANSMIT-002533 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f7ca8e4-fd6c-4a3a-8e22-2108c6d54cf8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9178 | T16182-YU02-P0CYE-139142 | 2019-05-24 | DHI-TRANSMIT-002533 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=985c2654-a412-476d-af10-0b9f505c0474 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9179 | T16182-YK08-P0PCA-126515 | 2019-05-24 | DHI-TRANSMIT-002534 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49bd886f-4f4c-4191-a24b-84159b004378 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9180 | T16182-YK08-P0PCA-126514 | 2019-05-24 | DHI-TRANSMIT-002535 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25e70836-0ab9-486d-a33a-773c8996b7d6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9181 | T16182-XB02-P0UZT-173003 | 2019-05-27 | DHI-TRANSMIT-002536 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=139db1b5-66c5-431b-8251-00131bb5ac99 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9182 | T16182-VK02-P8UTH-172005 | 2019-05-28 | DHI-TRANSMIT-002537 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ec365dd-e54e-4d6d-81c3-9409ad909a2f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9183 | T16182-XB02-P8UTH-172003 | 2019-05-28 | DHI-TRANSMIT-002537 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4fd94930-efbb-47e1-a238-4deb4557e12a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9184 | T16182-XB02-P8UTH-172004 | 2019-05-28 | DHI-TRANSMIT-002537 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4c76fd24-af22-41e8-859b-bdf8e556a563 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9185 | T16182-YQ01-P0ZEN-152308 | 2019-05-28 | DHI-TRANSMIT-002538 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35c6bec8-1a20-426d-9fb4-018eec1cf3a9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9186 | T16182-YQ01-P0ZEN-152315 | 2019-05-28 | DHI-TRANSMIT-002538 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35511dd2-8ae3-4648-b720-0176990747e4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9187 | T16182-YD02-P0ZEN-165515 | 2019-05-28 | DHI-TRANSMIT-002539 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06d53702-7125-47be-9cef-5fed98f7ed05 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9188 | T16182-YD02-P0ZEN-165518 | 2019-05-28 | DHI-TRANSMIT-002539 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02553aae-7485-4c44-91e4-cab31f0973cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9189 | T16182-VK02-P0UZK-173502 | 2019-05-28 | DHI-TRANSMIT-002540 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d6730449-55ad-4fe6-a81d-52db3e809dcf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9190 | T16182-VK02-P0UZK-173503 | 2019-05-28 | DHI-TRANSMIT-002540 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01799cf8-5c7c-479a-b783-9a6deea38364 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9191 | T16182-VK02-P0UZK-173504 | 2019-05-28 | DHI-TRANSMIT-002540 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=378974eb-5895-47ec-8bb7-878e7285a897 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9192 | T16182-VK02-P0UZK-173505 | 2019-05-28 | DHI-TRANSMIT-002540 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=67972306-d182-40c6-a198-e29075b72486 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9193 | T16182-XB02-P0UZK-173501 | 2019-05-28 | DHI-TRANSMIT-002540 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a3ad8242-41e1-4611-a74f-9519a399babc | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9194 | T16182-VK02-P0UZJ-173208 | 2019-05-29 | DHI-TRANSMIT-002541 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=701f3649-594c-4bb2-bd6e-ed71472d0670 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9195 | T16182-XB02-P0UZJ-173202 | 2019-05-29 | DHI-TRANSMIT-002541 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16bca63a-92fd-4179-b421-39b12770e740 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9196 | T16182-YV02-P0SCA-127548 | 2019-06-04 | DHI-WTRAN-001592 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8a731647-699b-4262-b29a-eae963df1819 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9197 | T16182-XH01-P0SGE-138612 | 2019-06-04 | DHI-TRANSMIT-002542 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6e1fa9b6-b418-4d57-963b-95d9967d53a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9198 | T16182-YT10-P0SGE-138622 | 2019-06-04 | DHI-TRANSMIT-002542 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45c5a675-3e4a-4c07-b195-fa931890ec09 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9199 | T16182-XW01-P0SCA-127556 | 2019-06-04 | DHI-TRANSMIT-002543 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51aae694-8cd1-45f6-a59b-ff123dd45245 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9200 | T16182-CV03-P0ZEN-163102 | 2019-06-04 | DHI-TRANSMIT-002544 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=989d68a3-8fda-46af-9a33-9d3d046637ba | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9201 | T16182-YL00-P0ZEN-163101 | 2019-06-04 | DHI-TRANSMIT-002544 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a42ae1f-f6dc-423e-a2a8-bf23308bc151 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9202 | T16182-XH01-P0LF-140410 | 2019-06-04 | DHI-TRANSMIT-002545 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8153f92e-fdf5-4cf3-b4d7-f3e523cb02c9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9203 | T16182-XJ00-P0LAB-140108 | 2019-06-04 | DHI-TRANSMIT-002545 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2db3ec89-2147-45d5-93a9-cec47bb7c82b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9204 | T16182-XJ00-P0LBA-140101 | 2019-06-04 | DHI-TRANSMIT-002545 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b85f834-2267-471f-96aa-d6670542b1cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9205 | T16182-XJ00-P0LBC-140102 | 2019-06-04 | DHI-TRANSMIT-002545 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d573cdd3-1a74-4a9e-9df4-38efff4a6d9b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9206 | T16182-XJ00-P0LBG-140103 | 2019-06-04 | DHI-TRANSMIT-002545 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b8471ef5-7a13-4c43-9c2a-38602d245672 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9207 | T16182-YF02-P8ZEN-125701 | 2019-06-04 | DHI-TRANSMIT-002546 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19287c15-364f-4659-a298-8e4d12c7f9ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9208 | T16182-YT02-P8ZEN-125727 | 2019-06-04 | DHI-TRANSMIT-002546 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4144f8d9-cbda-45ef-a37b-d4e4fc040d9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9209 | T16182-XB02-P0UZT-173003 | 2019-06-05 | DHI-TRANSMIT-002547 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d2bb387-9d6b-498c-8075-fcf81a1a6e59 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9210 | T16182-YD00-P0LCB-127555 | 2019-06-05 | DHI-TRANSMIT-002548 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78b2748e-c375-48e7-9299-f409413c99b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9211 | T16182-YD02-P0ZEN-165506 | 2019-06-05 | DHI-TRANSMIT-002549 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96847422-f116-4189-9ec4-22bc116e4032 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9212 | T16182-YD02-P0ZEN-165507 | 2019-06-05 | DHI-TRANSMIT-002549 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8de6b6b-4def-422c-824d-570c5dd1a336 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9213 | T16182-YD02-P0ZEN-165508 | 2019-06-05 | DHI-TRANSMIT-002549 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15645cc1-aee9-49b2-bb32-2f9c0cd1135b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9214 | T16182-YD02-P0ZEN-165509 | 2019-06-05 | DHI-TRANSMIT-002549 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43e5577e-cbea-4f24-8d12-660e8d8cae5a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9215 | T16182-YD02-P0ZEN-165522 | 2019-06-05 | DHI-TRANSMIT-002549 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=70a9178a-7a0f-46b9-ae10-051f00f7ee94 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9216 | T16182-YD02-P0ZEN-165577 | 2019-06-05 | DHI-TRANSMIT-002549 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e08894e6-d33d-4b05-b09c-c6e45951704b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9217 | T16182-XG02-P0LD-130204 | 2019-06-10 | DHI-TRANSMIT-002550 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=532e3b2e-a796-4bd7-a662-252d2ec2dc66 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9218 | T16182-YD00-P0CYE-139041 | 2019-06-10 | DHI-TRANSMIT-002551 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04539702-acf2-4b52-afaa-484b84c6579e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9219 | T16182-XB02-P0UGF-173101 | 2019-06-10 | DHI-TRANSMIT-002552 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bcebb20-712a-45ff-9f58-70ec966f61e0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9220 | T16182-XB02-P0UGF-173102 | 2019-06-10 | DHI-TRANSMIT-002552 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a783ff40-693d-4b0d-93b6-8d2b07a8686e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9221 | T16182-XJ00-P0GKB-140215 | 2019-06-10 | DHI-TRANSMIT-002553 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f65c864-d1dd-45ef-8c3c-9a563acff952 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9222 | T16182-XJ00-P0LAB-140208 | 2019-06-10 | DHI-TRANSMIT-002553 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0aca5485-39c0-4da9-b7d3-9aa47945ddff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9223 | T16182-XJ00-P0LBG-140104 | 2019-06-10 | DHI-TRANSMIT-002553 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4729a5ab-77ba-490a-b15c-527ae13d19dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9224 | T16182-XJ00-P0LBG-140204 | 2019-06-10 | DHI-TRANSMIT-002553 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91f37003-93dc-4492-8e87-fd920acb38b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9225 | T16182-XJ00-P0PGB-140109 | 2019-06-10 | DHI-TRANSMIT-002553 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=de760943-2e92-4baa-9d1c-0b17390e068f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9226 | T16182-BP00-P0LCA-140017 | 2019-06-10 | DHI-WTRAN-001593 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aa91e8b7-7f8a-4759-af1c-cb584f898cb4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9227 | T16182-YT01-P0LD-130214 | 2019-06-12 | DHI-WTRAN-001594 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1aaddaf-36f5-4333-82e4-b67ed4055ab7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9228 | T16182-DP00-P8ZEN-125766 | 2019-06-12 | DHI-TRANSMIT-002554 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d3ee4063-f14f-4e93-8485-b4a43d657a57 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9229 | T16182-XJ00-P0GHC-140113 | 2019-06-12 | DHI-TRANSMIT-002555 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d14a711a-4bb2-481f-8103-9c875cd71e25 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9230 | T16182-XJ00-P0GKB-140112 | 2019-06-12 | DHI-TRANSMIT-002555 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aebe41ad-435f-4be9-abfb-05b17e899080 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9231 | T16182-XJ00-P0LCM-140105 | 2019-06-12 | DHI-TRANSMIT-002555 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a14647e7-99cc-41ef-8285-ff12b8688575 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9232 | T16182-XB02-P0UZT-173003 | 2019-06-12 | DHI-TRANSMIT-002556 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=92b51520-fa03-4f01-9490-7e1a5058ac9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9233 | T16182-YQ08-P0CY-154039 | 2019-06-12 | DHI-TRANSMIT-002557 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e25c44d-c847-4b92-ae4b-78c28f4900da | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9234 | T16182-XJ00-P0GM-140121 | 2019-06-12 | DHI-TRANSMIT-002558 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b016f36-01e6-4ca9-b0bd-6efda0c8de7f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9235 | T16182-XJ00-P0LCA-140106 | 2019-06-12 | DHI-TRANSMIT-002558 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee880fb8-bf0a-445f-9ecf-344fd52a93e5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9236 | T16182-XJ00-P0MBH-140116 | 2019-06-12 | DHI-TRANSMIT-002558 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4267c2cc-3bd5-4387-bc48-6ac9259c7b3c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9237 | T16182-XJ00-P0PDA-140114 | 2019-06-12 | DHI-TRANSMIT-002558 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1fde7a92-f1f1-4609-afbe-b00ed931ea6d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9238 | T16182-VK02-P0GUB-173313 | 2019-06-13 | DHI-TRANSMIT-002559 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d75f04a3-8246-4ffc-8692-eb58ce3cfe24 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9239 | T16182-XB02-P0GUB-173302 | 2019-06-13 | DHI-TRANSMIT-002559 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f04c8e4e-97df-4fa1-8295-bdbc49e2e993 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9240 | T16182-XB02-P0GUB-173303 | 2019-06-13 | DHI-TRANSMIT-002559 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf761330-c7f9-4a3f-9e0c-b77f668738fb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9241 | T16182-VK02-P0ULC-172503 | 2019-06-13 | DHI-TRANSMIT-002560 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e5d8c70-6e14-4c39-b8bd-c2cbea5e3f86 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9242 | T16182-YT01-P0GNR-130108 | 2019-06-14 | DHI-TRANSMIT-002561 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=155fce25-68fa-4861-a154-5aed9f9ca15e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9243 | T16182-XJ00-P0EKC-140117 | 2019-06-14 | DHI-TRANSMIT-002562 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c49d6e55-599f-4a4e-ab10-d737eedf9fc7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9244 | T16182-XJ00-P0EKG-140118 | 2019-06-14 | DHI-TRANSMIT-002562 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=93d94653-d162-4897-95ef-291c6942fca7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9245 | T16182-XJ00-P0ZEN-140119 | 2019-06-14 | DHI-TRANSMIT-002562 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6fb598a4-c55a-48ff-9a95-f889f547de61 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9246 | T16182-XH01-P0LF-140401 | 2019-06-14 | DHI-TRANSMIT-002563 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a74f7ba-2821-4474-9123-a3a095c3df80 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9247 | T16182-XH01-P0LF-140402 | 2019-06-14 | DHI-TRANSMIT-002563 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec6f24b1-62b1-43e1-90b4-c4a5ad089c0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9248 | T16182-XH01-P0LF-140403 | 2019-06-14 | DHI-TRANSMIT-002563 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bbf268e3-b347-4db5-bf62-4db28880fbce | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9249 | T16182-XG02-P0LB-122022 | 2019-06-14 | DHI-TRANSMIT-002564 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=205c69c0-69e9-4c46-964e-b4f71d67de1d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9250 | T16182-XW01-P0MBA-121037 | 2019-06-17 | DHI-WTRAN-001595 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ee42dd9d-e23e-4f32-b8b4-333a4d409bf3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9251 | T16182-VK02-P0UZJ-173903 | 2019-06-19 | DHI-WTRAN-001596 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e6db5a2-fac7-4873-806e-85534e20d7d2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9252 | T16182-XB02-P0UZJ-173902 | 2019-06-19 | DHI-WTRAN-001596 | IFR | B | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c2e2009-51e3-4237-9dee-d7f7c7b00ccb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9253 | T16182-XB02-P0UGF-173101 | 2019-06-19 | DHI-TRANSMIT-002565 | IFC | 14 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=29c28b56-33cc-4b77-a716-6593f58f3dbe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9254 | T16182-XB02-P0UGF-173102 | 2019-06-19 | DHI-TRANSMIT-002565 | IFC | 14 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c55578a7-c4ca-4dc0-9136-a8710710185f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9255 | T16182-XB02-P0UBN-172202 | 2019-06-19 | DHI-TRANSMIT-002566 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6493ccc0-b023-4419-8bc5-9a822ed8fd8f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9256 | T16182-XJ00-P0GM-140224 | 2019-06-19 | DHI-TRANSMIT-002567 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b63c48a-bbe2-4260-b9ea-c674cb955537 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9257 | T16182-XJ00-P0LCA-140206 | 2019-06-19 | DHI-TRANSMIT-002567 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=191fb732-1e0d-4e94-aa5d-cc692ce74c79 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9258 | T16182-XJ00-P0ZEN-140120 | 2019-06-19 | DHI-TRANSMIT-002567 | IFC | 15 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ebd377d-9da7-42c9-ac30-7806f5efccd1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9259 | T16182-XG02-P0SCA-127557 | 2019-06-21 | DHI-TRANSMIT-002568 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65f99b36-2ce4-459b-8399-9e89a57fef25 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9260 | T16182-YM01-P0LCB-127010 | 2019-06-21 | DHI-WTRAN-001597 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7a520529-429e-4797-b5e2-a15722da009c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9261 | T16182-YF00-P8ZEN-125709 | 2019-06-24 | DHI-WTRAN-001598 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c027737-b1c6-4b26-b4a7-ee5a04dfde92 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9262 | T16182-YF00-P8ZEN-125710 | 2019-06-24 | DHI-WTRAN-001598 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec1be3d3-0072-446f-b462-7755a0fb6f40 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9263 | T16182-YE00-P0ZEN-152725 | 2019-06-24 | DHI-TRANSMIT-002569 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8b2120db-1a0c-46c4-aae5-761b67dec1f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9264 | T16182-CA00-P0QJA-184801 | 2019-06-24 | DHI-TRANSMIT-002570 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b3b5052-af22-4026-8626-606d151a4e3a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9265 | T16182-CA01-P0QJA-184852 | 2019-06-24 | DHI-TRANSMIT-002570 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90cb9dfc-fc0a-4ab0-8ae6-42e29589c159 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9266 | T16182-CA00-P0GEN-185701 | 2019-06-24 | DHI-TRANSMIT-002571 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=966c4412-2d01-40ec-a395-04ba43a283c7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9267 | T16182-CA01-P0GEN-185751 | 2019-06-24 | DHI-TRANSMIT-002571 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01ed14bb-1f68-4db8-b57a-f70e8b75773f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9268 | T16182-CA01-P0GEN-185852 | 2019-06-24 | DHI-TRANSMIT-002572 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b329e93-5b97-4c04-a178-54f14e4d43cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9269 | T16182-CA01-P0GEN-185853 | 2019-06-24 | DHI-TRANSMIT-002572 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a4956c3-b8ce-457a-87e2-e95219d487a5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9270 | T16182-CA02-P0GEN-185854 | 2019-06-24 | DHI-TRANSMIT-002572 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0962a0d-ac21-4a78-9c8d-5a4ecc0199f1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9271 | T16182-CA00-P0USG-182701 | 2019-06-24 | DHI-TRANSMIT-002573 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6244db3-aa43-4bce-b4d1-15e3661d9031 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9272 | T16182-CA00-P0USG-182704 | 2019-06-24 | DHI-TRANSMIT-002573 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42f1a7b7-1c3c-4ed9-8941-ec20cc75d04f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9273 | T16182-CA01-P0USG-182752 | 2019-06-24 | DHI-TRANSMIT-002573 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88cd9843-e655-48d6-9db3-7f519aeeead9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9274 | T16182-CA00-P0UGD-186601 | 2019-06-24 | DHI-TRANSMIT-002574 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d71b51c-44cc-4ff1-b07a-1832deab4249 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9275 | T16182-CA01-P0UGD-186651 | 2019-06-24 | DHI-TRANSMIT-002574 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d04ba1e9-2035-45ea-af58-5693fbf04b9d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9276 | T16182-CA01-P0UGD-186652 | 2019-06-24 | DHI-TRANSMIT-002574 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9a0c2d73-298b-4fd2-93eb-34ea77a6b5b4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9277 | T16182-XH01-P0LF-140404 | 2019-06-24 | DHI-TRANSMIT-002575 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49642b7d-a1ba-4d48-895c-01230d953e3f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9278 | T16182-XH01-P0LF-140406 | 2019-06-24 | DHI-TRANSMIT-002575 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=011a508f-6689-4bb7-ac1f-ac1b97b1d650 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9279 | T16182-XH01-P0LF-140407 | 2019-06-24 | DHI-TRANSMIT-002575 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6092edbc-9c25-47b5-b451-5db77cb997ec | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9280 | T16182-XH01-P0LF-140408 | 2019-06-24 | DHI-TRANSMIT-002575 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=466bb04d-76ee-4a06-af90-24ad4ffa871f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9281 | T16182-XH01-P0LF-140411 | 2019-06-24 | DHI-TRANSMIT-002575 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2859831a-22a1-4ba7-b36b-65813b084b9a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9282 | T16182-XH01-P0LF-140412 | 2019-06-24 | DHI-TRANSMIT-002575 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=013db7e2-42ff-4bec-b0e1-84f8dbdde990 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9283 | T16182-CQ02-P0MBA-121077 | 2019-06-26 | DHI-WTRAN-001599 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0aec059-d98b-4782-817d-10fc1f43f07a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9284 | T16182-XN00-P0LD-130208 | 2019-06-27 | DHI-WTRAN-001600 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b44bf128-c7cb-4bf7-acc4-8cc12f7c47e9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9285 | T16182-YM03-P0LD-130221 | 2019-06-27 | DHI-WTRAN-001600 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e836680f-68d5-42b0-915c-74e84de46321 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9286 | T16182-YU03-P0LD-130217 | 2019-06-27 | DHI-WTRAN-001600 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a78c54e5-3f23-48b1-ba47-32d981a59157 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9287 | T16182-YF00-P0ZEN-167001 | 2019-06-27 | DHI-WTRAN-001601 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6dc1bfa9-76c0-4d13-bb51-800478e51732 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9288 | T16182-YD02-P0SAC-163426 | 2019-06-27 | DHI-TRANSMIT-002578 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89a48d19-b9d9-445b-9ec1-993b8adc076d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9289 | T16182-XB02-P0UZK-173501 | 2019-06-27 | DHI-TRANSMIT-002579 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4066fadf-9ca9-463f-878a-f6d38aa2ad29 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9290 | T16182-VK02-P0UZK-173502 | 2019-06-27 | DHI-TRANSMIT-002579 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2df7c2d3-8cb8-486a-86f7-060a062923ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9291 | T16182-VK02-P0UZK-173504 | 2019-06-27 | DHI-TRANSMIT-002579 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=db91cba6-8c7d-42ef-bed3-d40290d9938b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9292 | T16182-VK02-P0UZK-173505 | 2019-06-27 | DHI-TRANSMIT-002579 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=90047381-91a5-4f95-8d88-5439a15e8d11 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9293 | T16182-XJ00-P0ZEN-140120 | 2019-06-27 | DHI-TRANSMIT-002580 | IFC | 16 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d400983-0ce0-475d-a4d5-0b5e9ce70a0c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9294 | T16182-XJ00-P0QJA-140223 | 2019-06-27 | DHI-TRANSMIT-002580 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5effdc29-8f71-4536-920a-443be9f6d33a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9295 | T16182-XH01-P0LF-140420 | 2019-06-27 | DHI-TRANSMIT-002580 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cf2912c-a669-4f1d-b667-178867e28ad1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9296 | T16182-XB02-P0UZA-172911 | 2019-06-27 | DHI-TRANSMIT-002581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=191edf1d-10ec-4bcc-a7a4-6c57fc39d814 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9297 | T16182-VK02-P0UZA-172912 | 2019-06-27 | DHI-TRANSMIT-002581 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e3fd299-16b9-40a1-bf57-5bcb1f8e061d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9298 | T16182-DE00-P0ZEN-152823 | 2019-06-27 | DHI-TRANSMIT-002582 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9982fc28-8997-4af2-8eb9-f885d9d68683 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9299 | T16182-YU02-P0BT-151021 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1017d1f9-23ab-4c2f-a4d5-d33eca673b05 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9300 | T16182-YU02-P0BT-151026 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=00777b9d-120c-48c8-8ddb-e06967d59a23 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9301 | T16182-YU02-P0BT-151031 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2f447e31-4eb1-4117-838b-5ca6260350af | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9302 | T16182-YD00-P0BT-151041 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f61b6377-1f98-4315-b20c-df8b202332f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9303 | T16182-YD00-P0BT-151046 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2caa9037-09d6-4f7c-9e5d-858380f7f470 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9304 | T16182-YD00-P0BT-151051 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f9929130-7f64-4785-b183-6a53f5fadd83 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9305 | T16182-YU03-P0BT-151061 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=010cc5b1-3eb6-412a-bfbd-220f64f4b4d6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9306 | T16182-YU03-P0BT-151066 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=65155d7f-693f-43da-a798-c79e2b6dff6c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9307 | T16182-YU03-P0BT-151071 | 2019-07-01 | DHI-WTRAN-001602 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=093d42bd-9bff-407c-908b-2bc027113fbf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9308 | T16182-YK00-P0LD-130216 | 2019-07-01 | DHI-WTRAN-001603 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4a88111-2c39-4f03-8df2-23ac60855305 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9309 | T16182-YE00-P0LD-130215 | 2019-07-01 | DHI-TRANSMIT-002583 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16894467-f48f-4105-81c8-ed3689f0c2a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9310 | T16182-YR05-P0LD-130207 | 2019-07-01 | DHI-TRANSMIT-002584 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afeda606-9f81-41ff-b2e1-e5a6163a1519 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9311 | T16182-XH01-P0LF-140406 | 2019-07-01 | DHI-TRANSMIT-002585 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac911351-cab8-482c-8997-0fbd3a16faf8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9312 | T16182-XH01-P0LF-140407 | 2019-07-01 | DHI-TRANSMIT-002585 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0cabfd75-d911-4098-b5f4-025eed103b78 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9313 | T16182-XH01-P0LF-140423 | 2019-07-01 | DHI-TRANSMIT-002585 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f28a540-dae8-451e-a32f-7c9b1edd574e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9314 | T16182-YE03-P0BAU-152525 | 2019-07-01 | DHI-TRANSMIT-002586 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=941a1885-d4f4-4560-8ff5-894d018aa189 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9315 | T16182-YT01-P0GNR-130108 | 2019-07-02 | DHI-TRANSMIT-002587 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74817fe1-f207-44d5-baa9-9791b3b35413 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9316 | T16182-YT01-P0LAC-126054 | 2019-07-02 | DHI-TRANSMIT-002588 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=76d8180a-3a6a-43f4-87de-0c181974899a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9317 | T16182-CA00-P0UCB-180601 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccbd10a4-d4d2-40c0-90b7-d5a3dc478b72 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9318 | T16182-CA00-P0UCB-180603 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3739d52c-897a-40b4-a55d-26553fa42e6d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9319 | T16182-CA00-P0UCB-180605 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a7842fe2-858c-4971-a39b-6fc19acbefe4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9320 | T16182-CA00-P0UCB-180606 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=305e4170-dded-40bc-afa5-bf865040b719 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9321 | T16182-CA00-P0UCB-180607 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57954440-b2a3-498b-80c2-750ee3b97a92 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9322 | T16182-CA00-P0UCB-180608 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4a43484-e2f5-4575-98dd-9a4e267d05f5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9323 | T16182-CA00-P0UCB-180609 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b62df7e-b0c6-4fa1-be6b-270346ca7ca9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9324 | T16182-CA00-P0UCB-180610 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d58d30a6-009b-4470-b4da-92e963cefa07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9325 | T16182-CA00-P0UCB-180611 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=666c1819-db74-4907-b65d-fca2c75e9a46 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9326 | T16182-CA00-P0UCB-180612 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4a174a7-0d19-4199-bae0-dae37ca097de | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9327 | T16182-CA00-P0UCB-180613 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e8fc466-1f1c-426e-9db6-6e5df7d1e564 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9328 | T16182-CA00-P0UCB-180614 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2022b48d-7991-447f-b1eb-e3d0baec7581 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9329 | T16182-CA01-P0UCB-180651 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2257e18-2fc0-49f5-898a-ffe091c0dbeb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9330 | T16182-CA01-P0UCB-180654 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c164b188-c788-449d-a11f-ce0aa0233459 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9331 | T16182-CA01-P0UCB-180657 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e753c9dc-1c89-447e-9bf6-2624755bd031 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9332 | T16182-CA01-P0UCB-180658 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24014e61-a251-4ed9-a53e-f3b4a07d5c48 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9333 | T16182-CA02-P0UCB-180668 | 2019-07-02 | DHI-TRANSMIT-002589 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf44d844-5d05-4a74-b14d-4b6591522ba3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9334 | T16182-XH01-P0SGA-136604 | 2019-07-03 | DHI-TRANSMIT-002590 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d673c5fa-6f92-4dab-b812-a3a4f482189c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9335 | T16182-YD02-P0ZEN-165504 | 2019-07-03 | DHI-TRANSMIT-002591 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fef1518a-2d0e-4af3-b5f1-fea61171059a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9336 | T16182-YE03-P0BAU-152510 | 2019-07-03 | DHI-TRANSMIT-002592 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae7258ec-f42c-48a5-8e88-0e60adedde39 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9337 | T16182-YE03-P0BAU-152512 | 2019-07-03 | DHI-TRANSMIT-002592 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e6052d20-45cd-46a0-9d5a-8b0015d594a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9338 | T16182-YL00-P0LD-130209 | 2019-07-03 | DHI-WTRAN-001604 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12d43806-0c39-46e5-9d2b-7ea96e8bf9fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9339 | T16182-XS00-P0GHC-110044 | 2019-07-03 | DHI-TRANSMIT-002593 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=543c1037-199f-44c4-ba06-ebeb12c7764d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9340 | T16182-YE00-P8ZEN-125751 | 2019-07-03 | DHI-TRANSMIT-002594 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=026f23dc-1be9-4145-8f32-c0de4ae4158c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9341 | T16182-YU03-P0QU-130406 | 2019-07-04 | DHI-WTRAN-001605 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=14d75b35-3c64-44e3-a4e4-88dcbf00d887 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9342 | T16182-XG02-P0LBA-110003 | 2019-07-04 | DHI-TRANSMIT-002595 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d04efdea-5fd1-4970-aaa3-84cb1b044016 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9343 | T16182-XG02-P0LBC-110004 | 2019-07-04 | DHI-TRANSMIT-002595 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ba033bd1-ce81-4f31-a961-a03e0c6008ea | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9344 | T16182-XG02-P0LBG-110005 | 2019-07-04 | DHI-TRANSMIT-002595 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=36474064-9f4d-4b8a-9ba9-6cec23c14059 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9345 | T16182-XG02-P0LBS-110006 | 2019-07-04 | DHI-TRANSMIT-002595 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08dfd9ea-96ac-4e4f-a5f8-514e4b5e231b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9346 | T16182-XG02-P6LCM-110007 | 2019-07-04 | DHI-TRANSMIT-002595 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88f25a00-4023-4cd3-bb3f-586497755353 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9347 | T16182-XG02-P0QJA-110012 | 2019-07-04 | DHI-TRANSMIT-002595 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12f09557-b7d2-4ca7-a1aa-92361e8dc282 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9348 | T16182-XB02-P0UNX-171402 | 2019-07-05 | DHI-TRANSMIT-002596 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45e36170-8ca4-42eb-986f-4325a492c5ac | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9349 | T16182-XB02-P0UNX-171403 | 2019-07-05 | DHI-TRANSMIT-002596 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e67ceb7-76eb-4a8b-b33f-99fbe2c4ace6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9350 | T16182-XB02-P0UNX-171410 | 2019-07-05 | DHI-TRANSMIT-002596 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1dc1bd7-15ca-40fd-beed-21a53566e251 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9351 | T16182-XG02-P0SCA-120005 | 2019-07-05 | DHI-TRANSMIT-002597 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88694f05-1f76-4b1c-b3a4-4b02ced4481b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9352 | T16182-XG02-P0SCA-120006 | 2019-07-05 | DHI-TRANSMIT-002597 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=866e1535-627a-433d-a390-18992bc83552 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9353 | T16182-BP00-P0LCA-140017 | 2019-07-05 | DHI-TRANSMIT-002598 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8656a502-1a39-4775-a021-ae6966ce7475 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9354 | T16182-XH01-P0LF-140404 | 2019-07-05 | DHI-TRANSMIT-002598 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=56387b38-a120-4b2e-bf4c-296589775f2b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9355 | T16182-XH01-P0LF-140406 | 2019-07-05 | DHI-TRANSMIT-002598 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=524ec9af-7bcf-4225-921a-202afb7c0ee3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9356 | T16182-VK02-P0UGF-173107 | 2019-07-05 | DHI-TRANSMIT-002599 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f856d7d0-cdac-4620-a6e2-4034d33e9bb1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9357 | T16182-XB02-P0UGF-173101 | 2019-07-05 | DHI-TRANSMIT-002599 | IFC | 15 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af9c17f6-c7e4-4d60-9f87-5636f7042ffc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9358 | T16182-XB02-P0UGF-173102 | 2019-07-05 | DHI-TRANSMIT-002599 | IFC | 15 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e22e8f01-f784-45d1-89ad-a718c39cd7a0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9359 | T16182-YM03-P8ZEN-125721 | 2019-07-09 | DHI-TRANSMIT-002600 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ccf7686b-46c0-4897-b57f-25daf2142c45 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9360 | T16182-VK02-P0GUC-172804 | 2019-07-09 | DHI-TRANSMIT-002601 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d0b8427-2e43-4003-abd0-0c41d361b6a9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9361 | T16182-YQ01-P0ZEN-152312 | 2019-07-09 | DHI-TRANSMIT-002602 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9e67454e-a93f-4a2d-8b78-3def84460ab4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9362 | T16182-YQ08-P0CY-154033 | 2019-07-09 | DHI-TRANSMIT-002602 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a25a6485-b11b-48a7-bf66-304c84937d51 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9363 | T16182-VK02-P0UZJ-173903 | 2019-07-10 | DHI-TRANSMIT-002603 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47781477-1db5-4fed-b466-f82ca2ae3327 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9364 | T16182-XB02-P0UZJ-173902 | 2019-07-10 | DHI-TRANSMIT-002603 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2bb7236-df34-4d82-939a-93ae17a876df | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9365 | T16182-YE01-P0BAU-152606 | 2019-07-10 | DHI-TRANSMIT-002604 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9c7547bc-8ffd-447e-9598-895322fe8a40 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9366 | T16182-VK02-P0UZJ-173208 | 2019-07-15 | DHI-TRANSMIT-002609 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cb72c609-4745-4ca7-bfa0-7ce2acdcca90 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9367 | T16182-XB02-P0UZJ-173202 | 2019-07-15 | DHI-TRANSMIT-002609 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4392a981-c2a5-4a04-aabe-9682adb50881 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9368 | T16182-XN00-P0LD-130208 | 2019-07-15 | DHI-WTRAN-001606 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7d7035f1-b53c-4cd9-84fc-4174a90ab946 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9369 | T16182-CC05-P0ZEN-180044 | 2019-07-15 | DHI-WTRAN-001607 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=60f9679c-f1d5-49b0-a26b-44d7345c56e7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9370 | T16182-XW01-P0MBA-121037 | 2019-07-15 | DHI-WTRAN-001608 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=10f7db7e-9bda-44dd-a07d-817d671b1b58 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9371 | T16182-XG02-P0GCF-130004 | 2019-07-15 | DHI-TRANSMIT-002610 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0900a14-9752-439c-a520-c113cda498b3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9372 | T16182-XH01-P0LD-130213 | 2019-07-15 | DHI-TRANSMIT-002610 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1342274c-dcb1-440f-bd37-a8e3301ab814 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9373 | T16182-YD04-P0ZEN-152010 | 2019-07-15 | DHI-TRANSMIT-002611 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eba26e73-3301-42c0-b6f1-cfbfb9311160 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9374 | T16182-XJ00-P0GKB-140212 | 2019-07-15 | DHI-TRANSMIT-002612 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=42f92a18-948d-480f-ba76-acb12e448f7c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9375 | T16182-XJ00-P0LBG-140204 | 2019-07-15 | DHI-TRANSMIT-002612 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=13da0149-0f6d-4701-bd6f-faaa70dfa7b9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9376 | T16182-CV03-P0PUR-411001 | 2019-07-15 | DHI-TRANSMIT-002613 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb1f637f-cd17-4f3b-83b2-e3e989bff0f4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9377 | T16182-CV03-P0PUR-411011 | 2019-07-15 | DHI-TRANSMIT-002613 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8d091dc-3823-4bb2-a914-801331610997 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9378 | T16182-CV03-P0PUR-411021 | 2019-07-15 | DHI-TRANSMIT-002613 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=368608a8-af7d-4181-9d0d-64c09ce601cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9379 | T16182-CV03-P0PUR-411031 | 2019-07-15 | DHI-TRANSMIT-002613 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7435f9a6-94fb-448b-9f87-2b4a221231d3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9380 | T16182-XB02-P0UZA-172902 | 2019-07-15 | DHI-TRANSMIT-002614 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f8683024-2115-4598-a935-5dcb65bfee03 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9381 | T16182-XB02-P0UZA-172903 | 2019-07-15 | DHI-TRANSMIT-002614 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=19c9e915-e86e-4f87-8ec9-bbe8ce3bc787 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9382 | T16182-VK02-P0UZA-172908 | 2019-07-15 | DHI-TRANSMIT-002614 | IFC | 14 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bd067efa-6dba-4fab-9f81-ba04b042e986 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9383 | T16182-YL00-P0LB-122075 | 2019-07-17 | DHI-WTRAN-001609 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eff0e71c-f3c9-446c-bce7-21f7f91e4cde | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9384 | T16182-YU03-P0BB-150831 | 2019-07-17 | DHI-WTRAN-001610 | IFI | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9419c2c-4a0e-4fdc-8904-aeea7aa33cea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9385 | T16182-YT10-P0ZEN-150312 | 2019-07-17 | DHI-TRANSMIT-002617 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebb5618e-b847-4575-9d9c-59ca92156874 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9386 | T16182-YL00-P0LB-122079 | 2019-07-17 | DHI-TRANSMIT-002618 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91e0f00c-9130-4ad9-b4b9-dd2059b0d515 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9387 | T16182-XB02-P0UZT-172702 | 2019-07-17 | DHI-TRANSMIT-002619 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63df30d4-a8d4-4bc3-a56d-711d93b76d77 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9388 | T16182-XB02-P0UZT-172703 | 2019-07-17 | DHI-TRANSMIT-002619 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f55326c-68d6-4daf-bf1b-4831c3a50351 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9389 | T16182-XB02-P0UZT-172716 | 2019-07-17 | DHI-TRANSMIT-002619 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d1507521-36d7-44f1-8ed6-9c16660820b1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9390 | T16182-XB02-P0GUB-173302 | 2019-07-17 | DHI-TRANSMIT-002620 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=48e14603-d6d5-4dc9-99ff-e2dc889cce9b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9391 | T16182-XB02-P0GUB-173303 | 2019-07-17 | DHI-TRANSMIT-002620 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=efb13440-f2c1-4cab-b5d3-e48ce0e763c0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9392 | T16182-YU03-P0BFA-150958 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2ab5a673-ab86-4083-97cb-33c74723841f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9393 | T16182-YU03-P0BFA-150951 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=deabd2f5-659f-4e99-9a3b-b869d7fdfc70 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9394 | T16182-YU03-P0BFA-150952 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ea2428fd-387b-4284-bab3-a96bc3e29e7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9395 | T16182-YU03-P0BFA-150953 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a8131a91-c759-463c-abb2-9f1aebf71ed9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9396 | T16182-YU03-P0BFA-150954 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3e420011-cd54-4bbe-a69b-6376bfcaee5f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9397 | T16182-YU03-P0BFA-150955 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c7c92fb-19a5-4c61-b409-d02c604586a4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9398 | T16182-YU03-P0BFA-150956 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6aa4e1c4-ce90-4366-ae98-3bcf0e15efa9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9399 | T16182-YU03-P0BFA-150957 | 2019-07-19 | DHI-WTRAN-001611 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4632bab-3f89-4048-b32f-798a6ade22c1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9400 | T16182-XG02-P8ZEN-125592 | 2019-07-19 | DHI-TRANSMIT-002621 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=410d7b19-1454-4774-9b23-c3db37071bd4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9401 | T16182-XG02-P8ZEN-125593 | 2019-07-19 | DHI-TRANSMIT-002621 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fc22e3f7-3193-46fb-bb1e-120697637ce0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9402 | T16182-YQ01-P0ZEN-152302 | 2019-07-23 | DHI-TRANSMIT-002622 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=332d4e9a-567c-4158-93e8-d46d05689fab | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9403 | T16182-YQ01-P0ZEN-152303 | 2019-07-23 | DHI-TRANSMIT-002622 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac8851c7-a5a2-4f0c-88cb-d1fe23b96041 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9404 | T16182-YQ01-P0ZEN-152310 | 2019-07-23 | DHI-TRANSMIT-002622 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b17042b-31d5-465d-8962-2669dd05deff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9405 | T16182-YQ01-P0ZEN-152332 | 2019-07-23 | DHI-TRANSMIT-002622 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a532ff9f-77a1-4b65-9930-ca3a1f0dd14e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9406 | T16182-VK02-P0UZA-172912 | 2019-07-23 | DHI-TRANSMIT-002623 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=55880cc8-17c4-4afb-a418-c6e1aa57758d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9407 | T16182-XB02-P0UZA-172911 | 2019-07-23 | DHI-TRANSMIT-002623 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d797bc1a-e0a6-40b1-8d07-52e8c0d6bac3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9408 | T16182-VE04-P0UNX-171401 | 2019-07-25 | DHI-TRANSMIT-002624 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3d941dc-550f-46db-a6ce-f8fdb0539df2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9409 | T16182-YQ01-P0ZEN-152301 | 2019-07-25 | DHI-TRANSMIT-002625 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e0f7bb3-9b0b-44ba-9a1f-47836ccd6650 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9410 | T16182-XB02-P0UZT-173003 | 2019-07-26 | DHI-TRANSMIT-002626 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a48bec3-4421-4d2c-856a-289781f9c410 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9411 | T16182-CA07-P0ZEN-020010 | 2019-07-26 | DHI-TRANSMIT-002627 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c404156f-0c3e-415d-adf1-455e712897f1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9412 | T16182-XB02-P0UZA-172904 | 2019-07-26 | DHI-TRANSMIT-002628 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35ed5f28-3fed-4823-945b-b41a94edbfe1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9413 | T16182-YQ01-P0ZEN-152310 | 2019-08-07 | DHI-TRANSMIT-002632 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=083b4f18-6805-410f-95d5-138405c9e4a9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9414 | T16182-YQ01-P0ZEN-152327 | 2019-08-07 | DHI-TRANSMIT-002632 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ced5e8f7-b19f-40cf-93e2-c689f8d378fe | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9415 | T16182-XG02-P8ZEN-125589 | 2019-08-07 | DHI-TRANSMIT-002633 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1844c5f9-8dc0-4f21-af86-ae7724982f6c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9416 | T16182-XH01-P0LF-140404 | 2019-08-09 | DHI-TRANSMIT-002638 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=103848fe-c13a-4cdc-a06e-ef501f63b145 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9417 | T16182-XJ00-P0QFB-140211 | 2019-08-09 | DHI-TRANSMIT-002638 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=06b2f955-d223-487a-9b6a-f12dc2f31f72 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9418 | T16182-XJ00-P0SCA-140210 | 2019-08-09 | DHI-TRANSMIT-002638 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77ba9222-4bea-44b5-9137-c0dfc69e3b59 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9419 | T16182-XJ00-P0ZEN-140120 | 2019-08-09 | DHI-TRANSMIT-002638 | IFC | 17 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=15cca614-c245-4ca6-bfd2-32efaa4b2776 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9420 | T16182-XB02-P0UZA-172904 | 2019-08-14 | DHI-TRANSMIT-002641 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cb5e538-42b9-4ee8-a04f-2b456875ba44 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9421 | T16182-YU03-P0QC-130308 | 2019-08-14 | DHI-WTRAN-001613 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=834b7a7e-aae4-499f-84cf-41eab29c063e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9422 | T16182-XB02-P0GUB-173302 | 2019-08-19 | DHI-TRANSMIT-002642 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=69b818d1-54e5-4e3b-b497-62d722fc69bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9423 | T16182-XB02-P0GUB-173303 | 2019-08-19 | DHI-TRANSMIT-002642 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8edc3f50-5016-4944-af4c-7f57926709de | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9424 | T16182-CA07-P0ZEN-020010 | 2019-08-19 | DHI-TRANSMIT-002643 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d69f81a-19ad-4cce-bb18-4b8e9adcc199 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9425 | T16182-VK02-P0UZJ-173208 | 2019-08-19 | DHI-TRANSMIT-002644 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d629c257-7870-4255-b00e-de3506b0cc27 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9426 | T16182-XB02-P0UZJ-173202 | 2019-08-19 | DHI-TRANSMIT-002644 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebba147d-7dd9-4e36-aa9a-15b1f0717259 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9427 | T16182-YU03-P0BB-150831 | 2019-08-20 | DHI-WTRAN-001614 | IFI | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d1a54bf-e792-47ee-9001-6b8401291ee0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9428 | T16182-YQ01-P0ZEN-152313 | 2019-08-20 | DHI-TRANSMIT-002645 | IFC | 1 | D | TRUE | FALSE | 2019-08-23_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=189e1ade-f568-4eec-bd6d-3918bd586df6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9429 | T16182-YR01-P0LB-122082 | 2019-08-22 | DHI-WTRAN-001615 | IFI | 1 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9430 | T16182-XS00-P0LB-122035 | 2019-08-22 | DHI-TRANSMIT-002646 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26fec431-6b40-4ea0-8e16-9038b65d7ab6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9431 | T16182-XG07-P0SAB-134802 | 2019-08-22 | DHI-TRANSMIT-002647 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0388728f-70d9-4ddc-be15-e642760a6683 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9432 | T16182-XW03-P0SAB-134801 | 2019-08-22 | DHI-TRANSMIT-002647 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=230e8647-4c41-46f9-9edd-b0d1bf4afc80 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9433 | T16182-XW03-P0SAB-134803 | 2019-08-22 | DHI-TRANSMIT-002647 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=915af22c-281e-40e9-913c-49741b77ad68 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9434 | T16182-XB02-P0UZA-172902 | 2019-08-22 | DHI-TRANSMIT-002648 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ded119d-7f59-4abc-8e47-b0e1ce21fc29 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9435 | T16182-XB02-P0UZA-172903 | 2019-08-22 | DHI-TRANSMIT-002648 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fd3f8cbe-a4b9-47ae-a749-44de974c034a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9436 | T16182-XJ00-P0EKG-140118 | 2019-08-22 | DHI-TRANSMIT-002649 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d5a8e95-32b5-4130-8e8f-40a5625feb2a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9437 | T16182-XJ00-P0LCM-140105 | 2019-08-22 | DHI-TRANSMIT-002649 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e520641-03d9-4cf0-9783-a0f77c69c657 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9438 | T16182-XJ00-P0LBA-140101 | 2019-08-22 | DHI-TRANSMIT-002649 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3dcfb2f6-eede-47c1-8acd-e1b9743597ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9439 | T16182-XJ00-P0PGB-140209 | 2019-08-22 | DHI-TRANSMIT-002649 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f8d6cb3-4f0a-4add-9445-925936689713 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9440 | T16182-XJ00-P0LAB-140108 | 2019-08-22 | DHI-TRANSMIT-002649 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dfc183b9-e24e-431c-86d1-15cc78ad9354 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9441 | T16182-XJ00-P0LBG-140204 | 2019-08-22 | DHI-TRANSMIT-002649 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c55d888-2c44-49a8-9248-0cf3cebc0472 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9442 | T16182-XJ00-P0ZEN-140119 | 2019-08-22 | DHI-TRANSMIT-002649 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5647df7c-53f3-4970-8e8f-0c73509f70e5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9443 | T16182-VK02-P0UZJ-173208 | 2019-08-23 | DHI-TRANSMIT-002651 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe3147e9-e28e-473f-a759-09a76f22916c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9444 | T16182-XJ00-P0GKB-140215 | 2019-08-23 | DHI-TRANSMIT-002652 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7a64872-18d3-4bdf-97d8-b4b8cb96cd07 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9445 | T16182-YQ01-P0ZEN-152309 | 2019-08-23 | DHI-TRANSMIT-002653 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cec9ba41-2d9e-4996-8d8d-64cc3a2c0c8d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9446 | T16182-XG02-P0GKC-120002 | 2019-08-23 | DHI-TRANSMIT-002654 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e3baa2b-1cef-458e-85fe-372bff8aafed | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9447 | T16182-XB02-P0UNX-171402 | 2019-08-27 | DHI-TRANSMIT-002655 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b489385d-4678-40e1-a1e1-37c8c1713ab6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9448 | T16182-XB02-P0UNX-171403 | 2019-08-27 | DHI-TRANSMIT-002655 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f673b5e4-08b6-43b5-8fac-ee3c03fda543 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9449 | T16182-XB02-P0UNX-171410 | 2019-08-27 | DHI-TRANSMIT-002655 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50673b60-0f9b-483b-b3f5-43a567194cff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9450 | T16182-YT01-P0LB-122042 | 2019-08-27 | DHI-TRANSMIT-002656 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0dd519e-6f49-4ed8-8fac-f5f75fe24e99 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9451 | T16182-XG02-P0LBS-110006 | 2019-08-27 | DHI-TRANSMIT-002657 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4f266629-0717-450a-836a-a0b9c1bbef9b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9452 | T16182-XG02-P6LCM-110007 | 2019-08-27 | DHI-TRANSMIT-002657 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=902690a2-16ae-4240-a79e-d7ab30ec440c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9453 | T16182-YS01-P0MKY-290009 | 2019-08-29 | DHI-TRANSMIT-002658 | IFC | 9 | D | TRUE | FALSE | 2019-08-29_Changed by jisoo1.chung | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4a7717c-64cf-454f-86e0-44075f9f4cd5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9454 | T16182-XJ00-P0LBA-140201 | 2019-08-29 | DHI-TRANSMIT-002659 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b6ab298-0274-40ab-8eea-80c41a468b5f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9455 | T16182-CQ02-P0LB-122001 | 2019-09-02 | DHI-WTRAN-001616 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b88c36fb-c89d-46ff-a07b-587f6afa70ad | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9456 | T16182-YD00-P8ZEN-125750 | 2019-09-04 | DHI-TRANSMIT-002661 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=835da53c-a9cf-462e-8796-5f69199c2105 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9457 | T16182-YE03-P0LB-122067 | 2019-09-06 | DHI-WTRAN-001617 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d27faee5-8de9-4a09-8df3-c8f7562606cf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9458 | T16182-YF00-P0LB-122066 | 2019-09-06 | DHI-WTRAN-001617 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bcb6022a-d857-44b8-8bcc-ac33562ae161 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9459 | T16182-XG02-P0LBA-110003 | 2019-09-09 | DHI-TRANSMIT-002663 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9d768f30-663a-431e-9443-4b21f6214d0b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9460 | T16182-XS00-P0LB-110040 | 2019-09-09 | DHI-TRANSMIT-002663 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae16dbc2-89da-4d40-8c3e-368359874c97 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9461 | T16182-XW01-P0LB-110035 | 2019-09-09 | DHI-TRANSMIT-002663 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb44b03b-01fc-4dd0-824f-c40a6850fe9d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9462 | T16182-XJ00-P0LAB-140108 | 2019-09-17 | DHI-TRANSMIT-002664 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=97a0106d-2cc5-4945-984c-f03174f8c7be | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9463 | T16182-XJ00-P0LBG-140104 | 2019-09-17 | DHI-TRANSMIT-002664 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f315c759-d662-4437-8001-930364ca7949 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9464 | T16182-XJ00-P0LBG-140204 | 2019-09-17 | DHI-TRANSMIT-002664 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b7a19584-cc03-4d96-92d9-66065b946b0e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9465 | T16182-XJ00-P0SCA-140110 | 2019-09-17 | DHI-TRANSMIT-002664 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4bccb566-ac9e-49da-bc77-4f038730a89c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9466 | T16182-XJ00-P0ZEN-140120 | 2019-09-17 | DHI-TRANSMIT-002664 | IFC | 18 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2afd435d-eeac-43e9-9d12-377ed9d33ba3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9467 | T16182-YD02-P0ZEN-165514 | 2019-09-18 | DHI-TRANSMIT-002665 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=694ce9ac-10fb-4cf6-afc2-f9afdbbab416 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9468 | T16182-YB03-P8ZEN-125732 | 2019-09-18 | DHI-TRANSMIT-002666 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=44cc26c0-bd30-4bea-b0aa-d72e6a16db01 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9469 | T16182-YL16-P8ZEN-125731 | 2019-09-18 | DHI-TRANSMIT-002666 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a63fd90-701e-448b-9f2c-c9ab8fef5c9f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9470 | T16182-XB02-P0UZA-172902 | 2019-09-19 | DHI-TRANSMIT-002667 | IFC | 14 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=316933fd-ad3e-46be-ad72-69f5932852fe | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9471 | T16182-XB02-P0UZA-172903 | 2019-09-19 | DHI-TRANSMIT-002667 | IFC | 14 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2bf56943-409c-4948-b094-a699c572a18b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9472 | T16182-YS01-P0MKY-290011 | 2019-09-23 | DHI-TRANSMIT-002668 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3526f57b-a77a-43c7-9581-8811ff888a76 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9473 | T16182-XG07-P0ZEN-120050 | 2019-09-23 | DHI-TRANSMIT-002669 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c390051-d05d-4e66-a18d-b81068a1a5fa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9474 | T16182-VK02-P0UGF-173107 | 2019-09-24 | DHI-TRANSMIT-002670 | IFC | 12 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f23919ef-6f5a-47c1-94ee-7c642f5205bd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9475 | T16182-YB03-P0LB-122047 | 2019-09-25 | DHI-WTRAN-001618 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df167859-a276-4f65-82ce-55d406a4f932 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9476 | T16182-YL16-P0LB-122078 | 2019-09-25 | DHI-WTRAN-001618 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=515b6d70-f570-4845-8494-7c6a8b804a4a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9477 | T16182-YB03-P0ZEN-165548 | 2019-09-25 | DHI-TRANSMIT-002671 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d845d15-04aa-462e-9075-7f99896ae3a3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9478 | T16182-XB02-P0GUB-173302 | 2019-09-25 | DHI-TRANSMIT-002672 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e38bdf71-4b69-445d-bebb-e54245c1ca57 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9479 | T16182-XB02-P0GUB-173303 | 2019-09-25 | DHI-TRANSMIT-002672 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63c7ca60-325d-4a5c-81ef-38d793fd6d64 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9480 | T16182-YQ01-P8ZEN-125765 | 2019-09-25 | DHI-TRANSMIT-002673 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99d20151-63d2-4359-aeaf-5199f91e12b2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9481 | T16182-VN01-P0MAG-123050 | 2019-09-26 | DHI-TRANSMIT-002674 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0483862e-c819-4cc8-873b-f6ac65824c7a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9482 | T16182-UT01-P0GQB-173402 | 2019-09-26 | DHI-TRANSMIT-002675 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c4ba59a0-5490-4520-abf3-3b64bfb1d803 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9483 | T16182-UT01-P0GQB-173403 | 2019-09-26 | DHI-TRANSMIT-002675 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a354eb92-7e26-482d-999b-bf8a8602e8fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9484 | T16182-YU03-P0BBT-150681 | 2019-09-27 | DHI-TRANSMIT-002676 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04807e30-ae85-42f0-97f0-08fcc4a30092 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9485 | T16182-XB00-P0MAG-123023 | 2019-09-30 | DHI-WTRAN-001619 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45b0d1bf-657e-402f-89d7-e0b7350dbe7b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9486 | T16182-XS00-P0MAG-123005 | 2019-09-30 | DHI-WTRAN-001619 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f06e8bd7-f7b0-47ed-ab66-ee7760de5f57 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9487 | T16182-XB02-P0UZA-172902 | 2019-09-30 | DHI-TRANSMIT-002677 | IFC | 15 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1451d856-0cbc-44e3-b16b-fa9f9377230b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9488 | T16182-XB02-P0UZA-172903 | 2019-09-30 | DHI-TRANSMIT-002677 | IFC | 15 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02624f47-9cf0-4182-8bbc-b23d304fb7f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9489 | T16182-CV03-P0PUR-411001 | 2019-10-02 | DHI-TRANSMIT-002678 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=11c9ea96-f67a-49a9-895d-d8cafa2390c4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9490 | T16182-CV03-P0PUR-411011 | 2019-10-02 | DHI-TRANSMIT-002678 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4f9d109-b008-4a51-861b-1cce32f75b1b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9491 | T16182-CV03-P0PUR-411021 | 2019-10-02 | DHI-TRANSMIT-002678 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7c70e264-99f8-48dd-b967-d2d2a52b5b56 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9492 | T16182-CV03-P0PUR-411031 | 2019-10-02 | DHI-TRANSMIT-002678 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa35f3c8-48d8-4fbe-8e47-e26c9b076877 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9493 | T16182-XG02-P0SCA-120004 | 2019-10-02 | DHI-TRANSMIT-002679 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e019c5a4-10c4-49bc-b1ad-38f081deacfa | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9494 | T16182-VK02-P0UGF-173107 | 2019-10-02 | DHI-TRANSMIT-002680 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ecfd2f13-348b-4000-a9bf-b90316e748a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9495 | T16182-YQ03-P0CY-121036 | 2019-10-07 | DHI-WTRAN-001620 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bdf5b6f7-f1a8-4934-a12d-17264e2d4034 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9496 | T16182-YT01-P0EKG-124040 | 2019-10-07 | DHI-WTRAN-001621 | IFR | A | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b619084-4c60-426a-bc37-6b71ff4c91fa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9497 | T16182-YD02-P0LB-122065 | 2019-10-14 | DHI-WTRAN-001622 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9aa0f75-5c79-489c-b000-c6958ee503ab | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9498 | T16182-YS01-P0MKY-290011 | 2019-10-14 | DHI-TRANSMIT-002683 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c0acfb0-33bc-4374-8174-35898b5f61e0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9499 | T16182-XJ00-P0EKG-140118 | 2019-10-15 | DHI-TRANSMIT-002684 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3819f993-49e1-4372-a97f-677a097ed185 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9500 | T16182-XJ00-P0LBA-140101 | 2019-10-15 | DHI-TRANSMIT-002684 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b93a1635-c87e-46ce-840a-f36fe52b9258 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9501 | T16182-XJ00-P0QFB-140211 | 2019-10-15 | DHI-TRANSMIT-002684 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c42763a2-77ee-4c57-9980-90b4cfc9eb07 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9502 | T16182-XJ00-P0SCA-140110 | 2019-10-15 | DHI-TRANSMIT-002684 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d35e08f0-2dba-43b5-9c1f-0e07cf063e9e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9503 | T16182-XJ00-P0ZEN-140120 | 2019-10-15 | DHI-TRANSMIT-002684 | IFC | 19 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=410f7a7a-470e-4fae-826c-d6fa54474757 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9504 | T16182-YT01-P0LD-130214 | 2019-10-16 | DHI-WTRAN-001623 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0eab4b43-f188-43a9-8be0-0216266fc8a1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9505 | T16182-YR05-P0LD-130207 | 2019-10-16 | DHI-TRANSMIT-002689 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9397758f-7690-4148-afb5-77ff7032baff | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9506 | T16182-YD00-P0BF-150940 | 2019-10-17 | DHI-WTRAN-001624 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3681baad-4176-42ac-875c-431e2fe9f6c6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9507 | T16182-YT01-P0BF-150903 | 2019-10-17 | DHI-TRANSMIT-002690 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a5a61e9c-ca6e-400f-9820-523fce318f89 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9508 | T16182-YQ01-P0ZEN-152305 | 2019-10-17 | DHI-TRANSMIT-002691 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=250cfb47-fb9a-4100-879d-bcdbd0c31ccd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9509 | T16182-YQ01-P0ZEN-152306 | 2019-10-17 | DHI-TRANSMIT-002691 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=167801e1-42e1-4dc6-b61a-139fec5bd003 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9510 | T16182-YQ01-P0ZEN-152321 | 2019-10-17 | DHI-TRANSMIT-002691 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bcc1cca7-cfaa-4304-b7f8-582ca14abf58 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9511 | T16182-YT01-P0LAC-126004 | 2019-10-17 | DHI-TRANSMIT-002692 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4b7ad5fa-415c-4492-96b7-c2cf6b5d8440 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9512 | T16182-YT01-P0LAC-126054 | 2019-10-17 | DHI-TRANSMIT-002692 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74ca06af-e013-4ac9-9e27-40768a7ab633 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9513 | T16182-YD00-P0BAT-150621 | 2019-10-18 | DHI-WTRAN-001625 | IFI | 9 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ff6aacb9-ca00-4e66-8077-af3f9fa167a6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9514 | T16182-YD00-P0BAT-150626 | 2019-10-18 | DHI-WTRAN-001625 | IFI | 8 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b46bfc74-5a4e-4620-a85e-1254b61167ac | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9515 | T16182-YD00-P0CHB-151131 | 2019-10-18 | DHI-WTRAN-001626 | IFI | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8ab9a050-b7ea-4e4a-a9ce-543a2f35f8cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9516 | T16182-YD00-P0BT-151041 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12ee9d1a-3c3d-4c4b-969c-fe69ff456533 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9517 | T16182-YD00-P0BT-151046 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=859c9489-13f4-4f4e-b24a-bdcec16e409a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9518 | T16182-YD00-P0BT-151051 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0a4c91b2-8fa0-415e-b1c5-9094c612e47f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9519 | T16182-YU02-P0BT-151021 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f213e8e6-2d3d-4354-ae8c-81f9ca552cb4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9520 | T16182-YU02-P0BT-151026 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=661fa6fd-dba9-4b6d-b849-88eabd1f0e34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9521 | T16182-YU02-P0BT-151031 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=799fa6d3-3c60-4c6a-802b-aa2f5de6c6bb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9522 | T16182-YU03-P0BT-151061 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84f8082c-51ee-4487-8e59-52a7723b0da8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9523 | T16182-YU03-P0BT-151066 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e4f3588e-8e3e-4f3d-8a99-14c373504755 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9524 | T16182-YU03-P0BT-151071 | 2019-10-18 | DHI-WTRAN-001627 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=995b1e11-582a-4e90-a136-9956eb290b79 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9525 | T16182-YD00-P0BF-150931 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0d02918d-6ab6-40c2-8bca-532f56d02f0c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9526 | T16182-YD00-P0BF-150932 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2fa5af82-51e3-4f88-bec0-d9cf2b5e2bb5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9527 | T16182-YD00-P0BF-150933 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f253cddd-9211-49a5-973e-e92dd8291254 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9528 | T16182-YD00-P0BF-150934 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0df3df5a-b377-4b57-b2e2-dfd040f92fdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9529 | T16182-YD00-P0BF-150935 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d55222d-0477-4db0-91cc-7896a72d8c5e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9530 | T16182-YD00-P0BF-150936 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40accefa-1f76-408c-9a59-84904c67237a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9531 | T16182-YD00-P0BF-150937 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28fe2d51-2348-4d78-a3cd-422836e08162 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9532 | T16182-YD00-P0BF-150938 | 2019-10-18 | DHI-WTRAN-001628 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae022355-8fcd-4f9c-b614-36d62e5d9043 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9533 | T16182-YU02-P0BFA-150911 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=27d4de76-725f-4c12-ab16-68108f0757e8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9534 | T16182-YU02-P0BFA-150912 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=950236e4-1925-4962-9b85-b3b1be46cf95 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9535 | T16182-YU02-P0BFA-150913 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96c87616-269e-4768-8548-cf739680e01f | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9536 | T16182-YU02-P0BFA-150914 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3662265c-8621-4c25-8a0b-ff2d5fdacd8c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9537 | T16182-YU02-P0BFA-150915 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0af0119a-4ca3-4966-a2f5-f8753caafd53 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9538 | T16182-YU02-P0BFA-150916 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=74acfca7-ffb0-486f-8a57-13145d8497b9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9539 | T16182-YU02-P0BFA-150917 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f1462b6-4a4e-4f60-a19b-c62102b0b909 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9540 | T16182-YU02-P0BFA-150918 | 2019-10-18 | DHI-WTRAN-001629 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c024e696-a36a-4f1d-957f-ff57c14ff7f2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9541 | T16182-XH01-P0LF-140407 | 2019-10-22 | DHI-TRANSMIT-002693 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b57d01cf-acb4-43ea-93f5-8ff36464c0f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9542 | T16182-XH01-P0LF-140417 | 2019-10-22 | DHI-TRANSMIT-002693 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1c77a709-cf7e-49c5-839d-fd90890dbce1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9543 | T16182-XJ00-P0EKG-140118 | 2019-10-22 | DHI-TRANSMIT-002693 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8e6e571-0b4c-428a-8b7e-74bda066d84a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9544 | T16182-XJ00-P0LAB-140108 | 2019-10-22 | DHI-TRANSMIT-002693 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d21b389e-e804-42c9-8bdc-1fab0ff230cc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9545 | T16182-XJ00-P0LBA-140201 | 2019-10-22 | DHI-TRANSMIT-002693 | IFC | 9 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ec4335dd-03be-453d-aa86-a9b3b3fdc420 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9546 | T16182-YL16-P0CRN-161115 | 2019-10-24 | DHI-TRANSMIT-002696 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43c47632-0e96-4838-b1de-46a23a98567e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9547 | T16182-XG02-P0EK-120007 | 2019-10-28 | DHI-TRANSMIT-002698 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26c5bf6f-1111-4729-b729-8044dd6701f9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9548 | T16182-XG02-P0QJA-110012 | 2019-10-28 | DHI-TRANSMIT-002699 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6488a433-1cd9-453d-89de-f4f895eb54da | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9549 | T16182-YD02-P0ZEN-165515 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84430cdd-96fa-4c1f-8666-9f11ec88623f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9550 | T16182-YD02-P0ZEN-165520 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b87d08e-a768-433b-bdd5-6d2d566cbedc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9551 | T16182-YD02-P0ZEN-165525 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a912f0f7-3383-47fe-8b93-ed9c9320d394 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9552 | T16182-YD02-P0ZEN-165526 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=96635bf9-8659-4495-afc8-404800a1789d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9553 | T16182-YD02-P0ZEN-165527 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d9208ed-9601-4409-96eb-3161e69a92a2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9554 | T16182-YD02-P0ZEN-165528 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d98ed932-690b-4b97-ac5f-a061ce210657 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9555 | T16182-YD02-P0ZEN-165529 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35c50999-e04c-410e-9c76-94fad5cd407e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9556 | T16182-YD02-P0ZEN-165571 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=81f84cd8-4d19-4e6f-bacc-d7173d6393ee | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9557 | T16182-YD02-P0ZEN-165572 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=902cf386-337c-457c-a0fb-7cd761a1698f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9558 | T16182-YD02-P0ZEN-165573 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=370df494-e76e-4fd4-bdfa-9a495f12d4f4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9559 | T16182-YD02-P0ZEN-165576 | 2019-10-28 | DHI-TRANSMIT-002700 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5b03d2dc-f045-4a86-b8a8-2193ddc92b6f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9560 | T16182-YE03-P0BAU-152510 | 2019-10-28 | DHI-TRANSMIT-002701 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d7878eea-c6d7-48e9-95b2-b17f2484aa64 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9561 | T16182-YE03-P0BAU-152514 | 2019-10-28 | DHI-TRANSMIT-002701 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=95e97faa-7cb8-4a39-93cc-dcd174b40deb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9562 | T16182-YE03-P0BAU-152516 | 2019-10-28 | DHI-TRANSMIT-002701 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4a7f1eb-ca7d-43d4-9d00-d76b312c5604 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9563 | T16182-YE03-P0BAU-152518 | 2019-10-28 | DHI-TRANSMIT-002701 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c288683f-23fa-4430-9b06-744965533940 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9564 | T16182-YE03-P0BAU-152527 | 2019-10-28 | DHI-TRANSMIT-002701 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae74eb41-a7cb-4261-9957-2b16df227a02 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9565 | T16182-XJ00-P0LBA-140201 | 2019-10-28 | DHI-TRANSMIT-002702 | IFC | 10 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e401daf9-7a65-41b8-b97c-99a12253de19 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9566 | T16182-XJ00-P0EKG-140118 | 2019-10-28 | DHI-TRANSMIT-002702 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2f080ba-883a-4835-9e05-c10682f41664 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9567 | T16182-XJ00-P0LAB-140108 | 2019-10-28 | DHI-TRANSMIT-002702 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12f2f7f2-cbc9-4232-85e1-3f5e8bee552b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9568 | T16182-YT01-P0EKG-124040 | 2019-10-29 | DHI-TRANSMIT-002703 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=013c2137-cc13-4407-8c0d-151bd20bbcd3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9569 | T16182-YB03-P0ZEN-165546 | 2019-10-29 | DHI-TRANSMIT-002704 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a9f00104-7910-4b61-b7b4-57951f4e3a06 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9570 | T16182-YB03-P0ZEN-165548 | 2019-10-29 | DHI-TRANSMIT-002704 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0bec89df-9ddc-4ea7-b472-206243c32632 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9571 | T16182-YL16-P0ZEN-165568 | 2019-10-29 | DHI-TRANSMIT-002704 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=566240a3-6b74-4e5f-ae1d-5da8a567ad32 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9572 | T16182-YE00-P0ZEN-152726 | 2019-10-31 | DHI-TRANSMIT-002705 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab6689f2-a897-445c-b78a-905751df6555 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9573 | T16182-YE00-P0ZEN-152727 | 2019-10-31 | DHI-TRANSMIT-002705 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=68c2403a-6eb6-414c-a174-b39c32bee7f0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9574 | T16182-YE00-P0ZEN-152728 | 2019-10-31 | DHI-TRANSMIT-002705 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3ec8fcdf-5ba4-4837-aba0-6e9cbbc5a593 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9575 | T16182-YE00-P0ZEN-152729 | 2019-10-31 | DHI-TRANSMIT-002705 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=86893a63-19ef-4ac3-9297-ab105f9ce641 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9576 | T16182-YE00-P0ZEN-152730 | 2019-10-31 | DHI-TRANSMIT-002705 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6d1fbbe2-0cdf-4380-9068-1f91ba256110 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9577 | T16182-YD00-P0UBA-150502 | 2019-10-31 | DHI-TRANSMIT-002706 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6420fd77-def4-452d-8494-b2483f1db4b5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9578 | T16182-XG02-P0QU-130403 | 2019-10-31 | DHI-TRANSMIT-002707 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=20c2a080-2e36-4e43-8be5-c26e7163b595 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9579 | T16182-YT01-P0CYE-136617 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=37cc1715-ae85-4b38-bb75-64bf6f86fa5f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9580 | T16182-YD00-P0CYE-137341 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a08dbb44-75ec-4cba-bb49-124951f895a9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9581 | T16182-YU02-P0CYE-137342 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51589fc8-e7b9-43d0-9002-0b7f543e84b0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9582 | T16182-YD00-P0CYE-137841 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f4fa042-5a07-4d42-9c3d-97cd389f1b39 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9583 | T16182-YU02-P0CYE-137842 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d4b4684d-ebc4-4932-a6db-980f47b28956 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9584 | T16182-YD00-P0CYE-137941 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=be664248-3a54-40a0-b043-6085f2320188 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9585 | T16182-YU02-P0CYE-137942 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fe7c625-545d-4f38-8f2c-de4550544acf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9586 | T16182-YD00-P0CYE-138741 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aaed2d01-f999-4899-b5ac-fbfc1af96b76 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9587 | T16182-YU02-P0CYE-138742 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5934767d-3c3d-423c-8676-3e22c1444811 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9588 | T16182-YD00-P0CYE-138841 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5fba1de6-3421-4dc7-969e-58b5ba4093fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9589 | T16182-YU02-P0CYE-138842 | 2019-10-31 | DHI-TRANSMIT-002708 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf2fdf7b-8499-4e49-ab7c-1a7c3d7e8921 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9590 | T16182-XG02-P0QC-130303 | 2019-11-01 | DHI-TRANSMIT-002709 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=924f5b9f-f3e0-4bbb-a3ec-d382cc7d8546 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9591 | T16182-XG02-P6LCM-110007 | 2019-11-04 | DHI-TRANSMIT-002710 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=741a3497-e72c-4038-bf59-72a778e5ccd6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9592 | T16182-XG02-P0LBA-110003 | 2019-11-04 | DHI-TRANSMIT-002710 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9ed1ccb-81ac-483e-9c8e-67a81e08fc92 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9593 | T16182-XG02-P0PGB-110010 | 2019-11-06 | DHI-TRANSMIT-002711 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=810d93e5-8338-44c1-9793-56776e7b7a43 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9594 | T16182-XG02-P1EKC-110014 | 2019-11-06 | DHI-TRANSMIT-002711 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=57fe4817-5153-46aa-b2dc-a47307598b4e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9595 | T16182-YF00-P6MAA-220097 | 2019-11-07 | DHI-WTRAN-001630 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=faa41595-7d89-4fd6-9e61-c853258ef6d7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9596 | T16182-YL08-P6MAA-220207 | 2019-11-07 | DHI-WTRAN-001630 | IFI | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73fb1928-bd7a-4ee8-aef4-a4085e2606c5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9597 | T16182-XH01-P0LF-140404 | 2019-11-08 | DHI-TRANSMIT-002712 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4cc33159-ef6f-4c68-8dfb-9e8b27bf0c31 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9598 | T16182-XJ00-P0LBG-140104 | 2019-11-08 | DHI-TRANSMIT-002712 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5c56ee8c-9651-4253-8219-669996079d2c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9599 | T16182-XJ00-P0QJA-140223 | 2019-11-08 | DHI-TRANSMIT-002712 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b59e7435-92bf-4e21-8db7-5661a2867a51 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9600 | T16182-YD00-P0CYE-139241 | 2019-11-08 | DHI-TRANSMIT-002713 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7cea12be-5918-45ac-b20c-d0a1efeac2f2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9601 | T16182-YU02-P0CYE-139242 | 2019-11-08 | DHI-TRANSMIT-002713 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0991d90-31e1-480b-a9c7-8da1978817d1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9602 | T16182-YD00-P0CYE-139341 | 2019-11-08 | DHI-TRANSMIT-002713 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=af8ae597-0633-4b4d-9d6b-811e4f079733 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9603 | T16182-YU02-P0CYE-139342 | 2019-11-08 | DHI-TRANSMIT-002713 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ebf17c6-799c-4e76-9880-adba399de093 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9604 | T16182-YD00-P0CYE-136641 | 2019-11-08 | DHI-TRANSMIT-002713 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a2d1276-f932-412f-8a2e-e545b3744ec6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9605 | T16182-YU02-P0CYE-136642 | 2019-11-08 | DHI-TRANSMIT-002713 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fe5e956a-66cc-4918-b25e-ff5eaa2dce16 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9606 | T16182-XG02-P0LB-122022 | 2019-11-12 | DHI-TRANSMIT-002715 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c02f02e2-d659-4978-bc77-76260d40e919 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9607 | T16182-YF02-P0ZEN-161031 | 2019-11-12 | DHI-TRANSMIT-002716 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edb4a535-8c57-4ec9-b990-bd5bc45528f6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9608 | T16182-VK02-P0UZA-172912 | 2019-11-12 | DHI-TRANSMIT-002717 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e096dee2-aedc-4f72-bf66-1e279eddd900 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9609 | T16182-XB02-P0UZA-172911 | 2019-11-12 | DHI-TRANSMIT-002717 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a161487f-c949-414e-83d6-ba38ad01aac7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9610 | T16182-YU03-P0BB-150836 | 2019-11-12 | DHI-WTRAN-001631 | IFI | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=163e42bc-29ec-4b91-93c8-813985beaa13 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9611 | T16182-YT01-P0EKG-124079 | 2019-11-13 | DHI-WTRAN-001632 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f85c73f-f710-4ff2-8d0c-9d43c0eaa247 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9612 | T16182-XG02-P0SGE-137303 | 2019-11-13 | DHI-TRANSMIT-002719 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b066f41f-bd10-4c8e-9d58-2f90e4be0227 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9613 | T16182-XK00-P0MAG-123027 | 2019-11-14 | DHI-WTRAN-001633 | IFR | C | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7f640caa-9179-4138-b32e-2dfb1bbfdabf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9614 | T16182-XG02-P0PCA-126502 | 2019-11-14 | DHI-TRANSMIT-002720 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63077468-af66-4242-b72b-7176db2940da | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9615 | T16182-YL30-P0EKG-124078 | 2019-11-18 | DHI-WTRAN-001634 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=89bfa37c-e031-472d-97c1-d9864c401457 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9616 | T16182-XB02-P0UZA-172902 | 2019-11-19 | DHI-TRANSMIT-002722 | IFC | 16 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b78091c0-1d39-4938-9dcd-a407afe920f3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9617 | T16182-XB02-P0UZA-172903 | 2019-11-19 | DHI-TRANSMIT-002722 | IFC | 16 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df6319b9-0136-4cd9-b63d-bbe7ad72fa5b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9618 | T16182-XG02-P0SCA-120005 | 2019-11-19 | DHI-TRANSMIT-002723 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f7a93bd-5dcf-49b1-96e2-87377a845486 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9619 | T16182-YQ01-P0ZEN-152301 | 2019-11-19 | DHI-TRANSMIT-002724 | IFC | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=50cdbf42-af1e-42a6-9e61-c945a7776132 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9620 | T16182-YQ01-P0ZEN-152302 | 2019-11-19 | DHI-TRANSMIT-002724 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47fb5e25-9c76-40b6-866b-c32714c77d27 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9621 | T16182-YQ01-P0ZEN-152303 | 2019-11-19 | DHI-TRANSMIT-002724 | IFC | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0df10d41-d63f-4ae5-9bef-a08af473fdb5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9622 | T16182-YQ01-P0ZEN-152315 | 2019-11-19 | DHI-TRANSMIT-002724 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7bcb596d-b903-4269-b954-ae42ad2cdf35 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9623 | T16182-YQ01-P0ZEN-152319 | 2019-11-19 | DHI-TRANSMIT-002724 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=dec8e3e6-54b3-4f99-b7f5-95c1a89fdf12 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9624 | T16182-YU02-P0CYA-154011 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43221022-360a-4fb5-9e35-0707faea4e39 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9625 | T16182-YU02-P0CYM-154013 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=03f0b89e-8d6e-4caf-960f-93d803a3495a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9626 | T16182-YQ08-P0CY-154031 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 9 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0b4c5494-3bdb-4cb3-9026-b21400d7842f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9627 | T16182-YQ08-P0CY-154038 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3d2ce0db-9f98-4fed-bf79-c5f6d39db26d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9628 | T16182-YQ08-P0CY-154039 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d37ac7a9-d78b-4089-8131-b8c56126199f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9629 | T16182-YQ08-P0CY-154040 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=22dcf27b-8f0f-4abb-b300-1fb814053c48 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9630 | T16182-YQ08-P0CY-154041 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=53ed284a-cd2a-4093-b3f1-d43727bd61fb | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9631 | T16182-YQ08-P0CY-154042 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47000a6c-1f4e-4203-9484-ba69968653d7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9632 | T16182-YQ08-P0CY-154044 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1b586df8-9274-48d4-9b04-06bc17e9c9a1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9633 | T16182-YQ08-P0CY-154045 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4907864e-9934-4d7d-8992-8d7c4e2c6511 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9634 | T16182-YQ08-P0CY-154051 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e0a94e1c-ed11-48be-8713-e03dcc8feca1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9635 | T16182-YQ08-P0CY-154052 | 2019-11-19 | DHI-TRANSMIT-002725 | IFC | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bc418e67-745a-417a-8204-61ea8c179196 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9636 | T16182-YB03-P8ZEN-125732 | 2019-11-19 | DHI-TRANSMIT-002726 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e19e7201-8afc-4675-9be8-5172ffd9e13d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9637 | T16182-YL16-P8ZEN-125731 | 2019-11-19 | DHI-TRANSMIT-002726 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3edcbb9d-acc7-40f6-8b80-18c34d2db3ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9638 | T16182-XG02-P0QU-130403 | 2019-11-19 | DHI-TRANSMIT-002727 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ad6109a4-ce36-4e09-bf51-0f081508c205 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9639 | T16182-YD00-P0CYE-136624 | 2019-11-20 | DHI-TRANSMIT-002728 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=99f83ed4-e213-4df8-9431-ce0cc384a616 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9640 | T16182-YD00-P0MAG-123051 | 2019-11-20 | DHI-TRANSMIT-002729 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ac001c46-a79a-48f9-88c4-f333f705c8de | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9641 | T16182-XG02-P0SGE-137303 | 2019-11-20 | DHI-TRANSMIT-002730 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3331207-51a6-49c2-8140-e0d6574b2963 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9642 | T16182-YT10-P0ZEN-150313 | 2019-11-20 | DHI-TRANSMIT-002731 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=133a096e-6eb1-4786-8dac-371c1efda58a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9643 | T16182-CV03-P0EKU-163202 | 2019-11-21 | DHI-TRANSMIT-002732 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6058ca49-f9c3-44af-8b65-d0879b62d634 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9644 | T16182-YE01-P0BAU-152606 | 2019-11-21 | DHI-TRANSMIT-002733 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8e67c0ac-0c76-4e87-9cce-72bb3c6ebf01 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9645 | T16182-YE03-P0BAU-152504 | 2019-11-21 | DHI-TRANSMIT-002733 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3d665c2-9a3d-45cc-a8de-b9e1200c66cf | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9646 | T16182-YE03-P0BAU-152510 | 2019-11-21 | DHI-TRANSMIT-002733 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=28659169-2394-49d2-b5fb-3c81ba00269c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9647 | T16182-YE03-P0BAU-152514 | 2019-11-21 | DHI-TRANSMIT-002733 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=12dbbc07-6937-4a27-b752-e111b9be61d9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9648 | T16182-YE03-P0BAU-152516 | 2019-11-21 | DHI-TRANSMIT-002733 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=26557efe-f28f-46cb-bb6d-75d867ccf9f8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9649 | T16182-YE03-P0BAU-152527 | 2019-11-21 | DHI-TRANSMIT-002733 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=eb30e15b-b405-4bb2-8075-425d3324c1ef | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9650 | T16182-YL16-P0ZEN-152850 | 2019-11-22 | DHI-WTRAN-001635 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1a053198-523c-471e-98b2-cb6a548ad32b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9651 | T16182-YF00-P0ZEN-167001 | 2019-11-26 | DHI-WTRAN-001637 | IFI | 0 | R | FALSE | TRUE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9652 | T16182-XB02-P0UEM-171702 | 2019-11-26 | DHI-TRANSMIT-002736 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80c516ba-8e67-4426-ae88-8926c0e837f0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9653 | T16182-XN00-P0LD-130208 | 2019-12-02 | DHI-WTRAN-001638 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=01c1e533-8d16-4bfa-afdd-701851be2a16 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9654 | T16182-XG02-P0LD-130204 | 2019-12-02 | DHI-TRANSMIT-002738 | IFC | 8 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bae58433-cb49-43b7-a15b-eb325ff9b72c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9655 | T16182-YR05-P0LD-130207 | 2019-12-02 | DHI-TRANSMIT-002739 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=212067ac-56f9-429b-b4d3-0cb49c6f1c50 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9656 | T16182-XG02-P0SGA-136603 | 2019-12-02 | DHI-TRANSMIT-002740 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2a0d5b0b-c9ed-46fa-8372-1c6479913686 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9657 | T16182-YQ01-P0ZEN-152311 | 2019-12-03 | DHI-TRANSMIT-002742 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f8b4532-0d15-4984-b8b8-2843b41f5ee0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9658 | T16182-YF00-P8ZEN-125710 | 2019-12-05 | DHI-WTRAN-001639 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c2ec7ed3-819a-440b-bb30-09e07b169fef | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9659 | T16182-YD00-P0SGZ-136931 | 2019-12-06 | DHI-TRANSMIT-002743 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=84b745c9-8ece-4c52-8131-9216551d9a34 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9660 | T16182-YD00-P0SGZ-137431 | 2019-12-06 | DHI-TRANSMIT-002743 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d5b3619-8481-4c12-bf73-d7f0cca87ae6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9661 | T16182-XG02-P0SGE-137303 | 2019-12-06 | DHI-TRANSMIT-002744 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=544f362a-03a1-49e1-9df9-9da9487499e5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9662 | T16182-YQ01-P0ZEN-152305 | 2019-12-06 | DHI-TRANSMIT-002745 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6f1f8241-e8a9-45e4-a491-888b21080703 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9663 | T16182-YQ01-P0ZEN-152317 | 2019-12-06 | DHI-TRANSMIT-002745 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ab9746a0-400a-4a4d-a20e-37eb069a4e26 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9664 | T16182-YQ01-P0ZEN-152321 | 2019-12-06 | DHI-TRANSMIT-002745 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0ffe99b-d988-48f4-9587-310538518395 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9665 | T16182-XJ00-P0ZEN-140120 | 2019-12-10 | DHI-TRANSMIT-002746 | IFC | 20 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b4bba6f9-1913-4868-be63-9968bf7429dd | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9666 | T16182-XG02-P8ZEN-125583 | 2019-12-10 | DHI-TRANSMIT-002747 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1f024a0c-3aa9-4c07-8367-57e4d0b7cbf1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9667 | T16182-XG02-P8ZEN-125585 | 2019-12-10 | DHI-TRANSMIT-002747 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e1b7138d-3932-4a80-b376-7845fb981dc0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9668 | T16182-XG02-P8ZEN-125587 | 2019-12-10 | DHI-TRANSMIT-002747 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2b72486a-06a3-4517-9265-d386012d087a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9669 | T16182-VK02-P0UZJ-173208 | 2019-12-11 | DHI-TRANSMIT-002748 | IFC | 13 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f53835a0-e3f6-4a55-99d2-28328d8d8bb1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9670 | T16182-VK02-P0UZJ-173209 | 2019-12-11 | DHI-TRANSMIT-002748 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5af884bc-9ae3-4535-be48-c7e248007e75 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9671 | T16182-XB02-P0UZA-172902 | 2019-12-11 | DHI-TRANSMIT-002749 | IFC | 17 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f0d11572-c9cb-454d-abc1-53214ea846c2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9672 | T16182-XB02-P0UZA-172903 | 2019-12-11 | DHI-TRANSMIT-002749 | IFC | 17 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1cd1cb49-4849-4d53-8761-c3b0b3d43c5f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9673 | T16182-YQ01-P0ZEN-123052 | 2019-12-12 | DHI-WTRAN-001640 | IFI | 2 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0324bf68-c857-4694-9253-71d93babb079 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9674 | T16182-CV03-P0EKU-163202 | 2019-12-12 | DHI-TRANSMIT-002750 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=78d14d49-78d0-4698-93c0-83c251eb037e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9675 | T16182-CV03-P8ZEN-125607 | 2019-12-12 | DHI-TRANSMIT-002751 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4ed1d449-8462-412f-8454-60e440623a71 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9676 | T16182-YD00-P0MAG-123051 | 2019-12-12 | DHI-TRANSMIT-002752 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7fbbaef2-1131-4882-bff9-f975ede17373 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9677 | T16182-YR05-P0GM-128511 | 2019-12-16 | DHI-WTRAN-001641 | IFI | 6 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=40dabdf8-44d2-477e-9842-c03f0040c7eb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9678 | T16182-YL00-P0LB-122075 | 2019-12-17 | DHI-WTRAN-001642 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=450de35e-9f24-43fc-bf31-f87e2d9067cd | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9679 | T16182-YT02-P0LB-122094 | 2019-12-17 | DHI-WTRAN-001642 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5a117a9f-d9a2-48af-b4dc-e50b567f6485 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9680 | T16182-YK00-P0LB-122072 | 2019-12-17 | DHI-TRANSMIT-002754 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d519c410-497e-44ed-be03-76f35eccb430 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9681 | T16182-UE00-P0UMA-100008 | 2019-12-19 | DHI-TRANSMIT-002755 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1e3f1a17-da3d-49b4-8811-43cfc2a42c7d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9682 | T16182-YE03-P0BAU-152514 | 2019-12-19 | DHI-TRANSMIT-002756 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3f450b43-ed0d-4ae1-baea-984027d7416c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9683 | T16182-YE03-P0BAU-152518 | 2019-12-19 | DHI-TRANSMIT-002756 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3c33907-3952-4d61-b2e2-b997dac1d44e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9684 | T16182-YE03-P0BAU-152540 | 2019-12-19 | DHI-TRANSMIT-002756 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a0279e0f-71b1-4b7c-a392-76c7c3d1648d | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9685 | T16182-YT10-P0ZEN-152216 | 2019-12-20 | DHI-WTRAN-001644 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f7f1bc56-0db4-4ea5-8856-7b089baa9c56 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9686 | T16182-YQ01-P0ZEN-152314 | 2019-12-20 | DHI-TRANSMIT-002758 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25dc520a-b826-4ad3-a9ab-d8d96b57bc5f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9687 | T16182-YQ01-P0ZEN-152327 | 2019-12-20 | DHI-TRANSMIT-002758 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fdc353f2-f661-40a4-9ab6-2cc1a27a2b08 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9688 | T16182-BV02-P0CJN-290003 | 2019-12-20 | DHI-TRANSMIT-002759 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e7df560-a961-46af-8775-11e6d0fc86d1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9689 | T16182-XG07-P0SCA-120014 | 2020-01-03 | DHI-TRANSMIT-002764 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b78da232-875b-49b7-a30b-d1d6d2debb2a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9690 | T16182-XW03-P0SCA-120017 | 2020-01-03 | DHI-TRANSMIT-002764 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c10cf77d-7033-4b3e-a9a2-9851e9e01c37 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9691 | T16182-XW01-P0STG-130501 | 2020-01-03 | DHI-WTRAN-001647 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c0de4011-4d80-445a-a5f9-c1003f05a262 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9692 | T16182-XL00-P0STG-130503 | 2020-01-03 | DHI-TRANSMIT-002765 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9240af81-0978-4104-ac98-30267e5c03d5 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9693 | T16182-YD00-P0STG-130502 | 2020-01-03 | DHI-TRANSMIT-002765 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5f3476ab-0280-477f-a8c1-8cf9f0cf9e1f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9694 | T16182-XG02-P0LBA-110003 | 2020-01-03 | DHI-TRANSMIT-002766 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8f030f3-8eed-489d-9399-31596f26411c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9695 | T16182-XG02-P0LBG-110005 | 2020-01-03 | DHI-TRANSMIT-002766 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6917ee13-afcd-449c-818e-136df0bd140f | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9696 | T16182-XG02-P0LBS-110006 | 2020-01-03 | DHI-TRANSMIT-002766 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=24451cb7-a30d-437e-9d13-a98bf35ee99b | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9697 | T16182-XG02-P6LCM-110007 | 2020-01-03 | DHI-TRANSMIT-002766 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e8e96485-4e4b-4aff-befe-5bc0dfb3efe4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9698 | T16182-XK00-P0MAG-123008 | 2020-01-03 | DHI-WTRAN-001648 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=557f2806-8914-4122-8d3f-4673eb670dfa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9699 | T16182-YU02-P0MJ-110507 | 2020-01-03 | DHI-WTRAN-001649 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fbc4cf10-3653-484e-ade5-7803b70eeaf3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9700 | T16182-XG02-P0SGE-137303 | 2020-01-03 | DHI-TRANSMIT-002767 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=05e8491d-03ab-41f3-bef7-fff42909d127 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9701 | T16182-BV02-P0CJN-290003 | 2020-01-03 | DHI-TRANSMIT-002768 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0ade9a88-24b9-429b-9f44-3c82119834e0 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9702 | T16182-XG02-P0PCA-126502 | 2020-01-03 | DHI-TRANSMIT-002769 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f3b50285-64ed-4f40-b918-627b0835f1e6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9703 | T16182-YQ01-P0ZEN-152333 | 2020-01-03 | DHI-WTRAN-001650 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=626c3ad3-fc87-4d2d-9000-8a2d7a5a689b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9704 | T16182-YL06-P0ZEN-150101 | 2020-01-07 | DHI-TRANSMIT-002772 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63c9f8f4-0688-4566-8329-eb8f7041c783 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9705 | T16182-YF00-P8ZEN-125709 | 2020-01-07 | DHI-WTRAN-001651 | IFI | 4 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=aaed1d0a-7d5e-4c6c-b501-ca9a2b992b87 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9706 | T16182-YF02-P0SCA-127514 | 2020-01-07 | DHI-WTRAN-001652 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5068d554-dd28-44d1-8ae0-24d99cb7600b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9707 | T16182-YF00-P0LB-122066 | 2020-01-07 | DHI-WTRAN-001653 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4efbcfb0-4f9a-4687-a267-f12451bb92e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9708 | T16182-YE03-P0LB-122067 | 2020-01-07 | DHI-WTRAN-001653 | IFI | 3 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f1b14fd7-32bb-41c3-8d5f-5cc5776fb08a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9709 | T16182-YM02-P0MAG-123029 | 2020-01-07 | DHI-WTRAN-001654 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f96284c1-a62d-47e7-89fa-c0ca8d906ab5 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9710 | T16182-YQ08-P0CY-154039 | 2020-01-09 | DHI-TRANSMIT-002774 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f4c3609d-d029-4424-94e5-5327d77f1cd3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9711 | T16182-BV02-P0CJN-290003 | 2020-01-09 | DHI-TRANSMIT-002775 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f2c91c0b-9ce6-4f0b-b471-383c5b6efde6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9712 | T16182-YE00-P0EKG-124014 | 2020-01-09 | DHI-WTRAN-001655 | IFI | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fb7993f3-a944-42e2-9705-e8f86a0d7667 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9713 | T16182-YD00-P0SMU-128070 | 2020-01-09 | DHI-WTRAN-001656 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=635cdac3-50a1-4ccd-b6de-a85c5e7d3199 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9714 | T16182-YD00-P0SMS-128060 | 2020-01-09 | DHI-WTRAN-001656 | IFI | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa9a5927-1fa3-4f40-8e93-5fbf17f5a2a3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9715 | T16182-XG02-P0SCA-127502 | 2020-01-09 | DHI-TRANSMIT-002776 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=33aec1ee-3084-4cfc-962c-18cd55cb8b58 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9716 | T16182-YD00-P8ZEN-125728 | 2020-01-09 | DHI-TRANSMIT-002777 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a73f7f45-8716-441a-98f5-cf1977c93b84 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9717 | T16182-YD00-P8ZEN-125750 | 2020-01-09 | DHI-TRANSMIT-002777 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=80182e0b-4d5e-4b57-a7f5-99a2637b566e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9718 | T16182-XH01-P0LF-140405 | 2020-01-09 | DHI-TRANSMIT-002778 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a6254f31-f8fd-4df5-a707-f318faf3a017 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9719 | T16182-XH01-P0LF-140422 | 2020-01-09 | DHI-TRANSMIT-002778 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=4a365aab-5feb-47da-a793-6a6b934bbea6 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9720 | T16182-XJ00-P0LCM-140105 | 2020-01-09 | DHI-TRANSMIT-002778 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=a4d0dc10-3501-43b5-b6b0-2bdf6a5859a7 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9721 | T16182-YF00-P0CBA-161210 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=25f35717-ef26-43f5-9d4d-7f00ccff9731 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9722 | T16182-YF00-P0CBA-161216 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=940fd929-8547-4970-bc6d-35bbd58ea8c8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9723 | T16182-YF00-P0CBA-161208 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6a0df7fc-03c0-44f4-830e-480e49fa2ad6 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9724 | T16182-YF00-P0CBA-161211 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=16fe4994-19ac-4ab5-b3cf-b44d836287a9 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9725 | T16182-YF00-P0CBA-161220 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6db751fb-550c-466f-98e8-ef64d87bf3ea | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9726 | T16182-YF00-P0CBA-161209 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0e8c8d9d-8979-466d-9136-3e421dab9791 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9727 | T16182-YF00-P0CBA-161213 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73814d83-8a99-42f4-861e-a1a464e5159e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9728 | T16182-YF00-P0CBA-161212 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5d914707-9d18-4656-8d51-2a8c13e8433e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9729 | T16182-YF00-P0CBA-161203 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=45a82ece-caf2-47e6-82c8-fb630def1934 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9730 | T16182-YF00-P0CBA-161221 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=129acb66-79d3-4209-b335-e0f5eead62ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9731 | T16182-YF00-P0CBA-161204 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=388564da-ceee-4f62-871f-036a98ef0912 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9732 | T16182-YF00-P0CBA-161205 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=87565303-eaf4-48de-af61-52321e2e02b0 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9733 | T16182-YF00-P0CBA-161222 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=afcb2699-5e9a-4358-a5fd-d5c26624922d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9734 | T16182-YF00-P0CBA-161214 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=edd002ec-5873-4176-9631-0968616d6772 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9735 | T16182-YF00-P0CBA-161206 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b0288be3-b03c-4d2e-956d-fdb838eebad3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9736 | T16182-YF00-P0CBA-161207 | 2020-01-10 | DHI-TRANSMIT-002780 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ae8d2d5e-7264-4088-8ae8-1dac2a123d85 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9737 | T16182-YF00-P0CGA-161310 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=7ee2be29-a7d8-44f4-acd2-8698236e0a0b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9738 | T16182-YF00-P0CGA-161316 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=72ea62a8-fd65-4ee5-9516-4a2849043fb1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9739 | T16182-YF00-P0CGA-161308 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=df2dd05b-0d2d-4a10-a802-22151e1f9052 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9740 | T16182-YF00-P0CGA-161311 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3fae827f-87cb-4e70-8126-c6605adcc4a2 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9741 | T16182-YF00-P0CGA-161320 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6b1e5e30-155a-47e3-9951-edaa32d82e7a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9742 | T16182-YF00-P0CGA-161309 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c285818c-83c1-4d02-953f-76bd84e73af1 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9743 | T16182-YF00-P0CGA-161313 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c8e1f54d-451b-4210-920f-cbdf166be5ed | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9744 | T16182-YF00-P0CGA-161312 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04ab3ea2-5349-44b9-93bd-706fee7152a8 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9745 | T16182-YF00-P0CGA-161303 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=77b3fe68-b623-42d3-845b-f8a8f0cb5837 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9746 | T16182-YF00-P0CGA-161321 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=135ceeda-6824-4106-9be1-417fd5634a34 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9747 | T16182-YF00-P0CGA-161304 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=5ce97905-c4a7-4fdf-81e2-7e3e823f24f4 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9748 | T16182-YF00-P0CGA-161305 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=82b8651f-4d79-421d-9b5b-191e3f5bfe7e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9749 | T16182-YF00-P0CGA-161322 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ebcfeb3f-1434-42d6-9f2b-33bc94b44003 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9750 | T16182-YF00-P0CGA-161314 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf8be20d-5428-4e8a-aea7-415c99b3641d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9751 | T16182-YF00-P0CGA-161306 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=daaa3d9d-783b-4c6b-9fd5-afb1827d8269 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9752 | T16182-YF00-P0CGA-161307 | 2020-01-10 | DHI-TRANSMIT-002781 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=d9956671-42fd-4821-ab34-7df5425a26ff | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9753 | T16182-YF00-P0CJA-161041 | 2020-01-10 | DHI-TRANSMIT-002782 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85f3f071-6de0-41a0-82c9-8b655f2901a7 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9754 | T16182-YF00-P0CJD-161025 | 2020-01-10 | DHI-TRANSMIT-002782 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1d4c2cfa-f11e-499c-926e-72bce636d2cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9755 | T16182-YF00-P0CJD-161022 | 2020-01-10 | DHI-TRANSMIT-002782 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=582088c3-f569-45a2-ad0c-2c72131a107c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9756 | T16182-XG02-P0LAA-110009 | 2020-01-14 | DHI-TRANSMIT-002785 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3aa08952-3ca4-42e8-930d-be871b2cecc3 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9757 | T16182-XG02-P6LCA-110008 | 2020-01-14 | DHI-TRANSMIT-002785 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=567eba4a-8d3f-48f7-8ee7-9a9d21f0dce2 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9758 | T16182-YV02-P0SCA-127511 | 2020-01-14 | DHI-WTRAN-001657 | IFI | 5 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=919e6649-0389-45a8-8179-1752a8592b1d | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9759 | T16182-XG02-P0QJA-110012 | 2020-01-16 | DHI-TRANSMIT-002787 | IFC | 6 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=51021715-8749-4fbd-b098-a2334c9258dc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9760 | T16182-XW03-P0QJA-110052 | 2020-01-16 | DHI-TRANSMIT-002787 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=9ec25f2e-91cc-4485-bae0-3470ea982b84 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9761 | T16182-YQ08-P0CY-154042 | 2020-01-16 | DHI-TRANSMIT-002788 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=49fafd89-08a8-4c78-b3f8-b581a63f04d8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9762 | T16182-XJ00-P0GHC-140113 | 2020-01-17 | DHI-TRANSMIT-002789 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=6889703c-b6e4-49f9-a428-e4ae4e93c11e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9763 | T16182-XJ00-P0GKB-140215 | 2020-01-17 | DHI-TRANSMIT-002789 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=acc346a6-0393-43c2-b2b0-cd8456ec4525 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9764 | T16182-XJ00-P0LBG-140104 | 2020-01-17 | DHI-TRANSMIT-002789 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=2c47149b-b32c-46f1-ba4c-f0ccad937f4c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9765 | T16182-XJ00-P0LCA-140106 | 2020-01-17 | DHI-TRANSMIT-002789 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=cf677e8b-2d03-468f-a682-c081ef0fe325 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9766 | T16182-XJ00-P0LCM-140205 | 2020-01-17 | DHI-TRANSMIT-002789 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=c1f0578b-6db5-4a8f-a57b-6d390b02a74c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9767 | T16182-XJ00-P0QFB-140211 | 2020-01-17 | DHI-TRANSMIT-002789 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=73fdebaa-8b92-421c-ab42-364809757215 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9768 | T16182-XJ00-P0SCA-140210 | 2020-01-17 | DHI-TRANSMIT-002789 | IFC | 11 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=63a4ac13-b570-46f2-9196-17de048ddea9 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9769 | T16182-XG02-P0LBA-110003 | 2020-01-17 | DHI-TRANSMIT-002790 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=47052c82-0e6d-4481-b58c-56e1d4e83dcc | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9770 | T16182-XG02-P0LBC-110004 | 2020-01-17 | DHI-TRANSMIT-002790 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=32707305-252a-4098-9180-7a287b52bb0c | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9771 | T16182-XG02-P0LBG-110005 | 2020-01-17 | DHI-TRANSMIT-002790 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0c27dd7a-1339-4e39-aa4f-b6df3c7c6e34 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9772 | T16182-XG02-P0LBS-110006 | 2020-01-17 | DHI-TRANSMIT-002790 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=02d7aacf-ebda-4d20-9fbe-f6ff0aeefe25 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9773 | T16182-XG02-P6LCM-110007 | 2020-01-17 | DHI-TRANSMIT-002790 | IFC | 7 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8007f676-676a-42c9-b532-a27c6024b538 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9774 | T16182-XG02-P0PGB-110010 | 2020-01-23 | DHI-TRANSMIT-002791 | IFC | 5 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=265e6881-51d7-4268-bfb5-4a04494c4cc1 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9775 | T16182-YK08-P0MAN-110154 | 2020-02-03 | DHI-TRANSMIT-002793 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=91250c8b-2d48-4146-ad9d-016e95100d1e | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9776 | T16182-YT01-P0MAN-110153 | 2020-02-03 | DHI-WTRAN-001659 | IFI | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=913417ee-36e8-4371-ba8e-29cc333a283b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9777 | T16182-YF00-P0ZEN-167001 | 2020-02-03 | DHI-WTRAN-001660 | IFI | 1 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=88dfd85c-71be-44af-a3d8-089d5f1b9b1c | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9778 | T16182-XG02-P0MAG-123002 | 2020-02-03 | DHI-TRANSMIT-002794 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bebc9d79-01f7-40eb-adf8-8413bcdb27a4 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9779 | T16182-YR05-P0GM-128511 | 2020-02-03 | DHI-WTRAN-001661 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=1252ad90-a20e-4ada-a8a4-e6bb92fd38cb | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9780 | T16182-YU02-P0BFA-150911 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=f16ac52f-3418-42f2-bec6-81da1befa48e | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9781 | T16182-YU02-P0BFA-150912 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=04491395-8b02-4d55-98b3-1dba226037bf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9782 | T16182-YU02-P0BFA-150913 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=8d033fdf-c2b0-4746-839f-d54694a8a022 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9783 | T16182-YU02-P0BFA-150914 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bf9bcbb7-4dd8-4286-a823-7e9cecfbce07 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9784 | T16182-YU02-P0BFA-150915 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=43252c24-0e58-42b7-a9fe-43f2c8880bfa | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9785 | T16182-YU02-P0BFA-150916 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=ca3dc83b-dd9c-47ff-b5c8-7791de14cc35 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9786 | T16182-YU02-P0BFA-150917 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=bfe7ae3f-35fe-4f8b-baef-226f543cfcca | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9787 | T16182-YU02-P0BFA-150918 | 2020-02-04 | DHI-WTRAN-001662 | IFI | 7 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=e3341063-cbda-4876-af75-08376ef4b4e3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9788 | T16182-YT01-P0SGZ-136615 | 2020-02-05 | DHI-TRANSMIT-002796 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=08d1ea80-523f-4454-b62a-4fc462b4586a | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9789 | T16182-YD00-P0CUQ-161119 | 2020-02-06 | DHI-TRANSMIT-002797 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=07948b2f-7723-4d17-abb7-3b4f8882bd57 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9790 | T16182-YF02-P0CRV-161102 | 2020-02-06 | DHI-TRANSMIT-002797 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=526ec58e-4d48-40d2-b1d3-1c7d438dfb03 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9791 | T16182-YR05-P0CWQ-161148 | 2020-02-06 | DHI-TRANSMIT-002797 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=fa512c0d-5a4c-411d-a8c9-a38717915753 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9792 | T16182-YB03-P0CRN-161114 | 2020-02-06 | DHI-TRANSMIT-002797 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=679d7404-d071-4636-beb7-3fc201982483 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9793 | T16182-YD00-P0CRN-161113 | 2020-02-06 | DHI-TRANSMIT-002797 | IFC | 2 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=0eb38cae-19cc-41b8-b51d-3c7ba26d04ed | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9794 | T16182-YD00-P0CUQ-161112 | 2020-02-06 | DHI-TRANSMIT-002797 | IFC | 1 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=35b3fde8-dfb4-4982-9de1-7dbf8dd65c22 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9795 | T16182-DA01-P0ZEN-020001 | 2020-02-10 | DHI-ASBUILT-000001 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20a | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9796 | T16182-BV02-P0ZEN-020020 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9797 | T16182-BV02-P0ZEN-020030 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9798 | T16182-BV02-P0ZEN-020040 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9799 | T16182-BV02-P0ZEN-050001 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9800 | T16182-DA01-P0ZEN-020002 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9801 | T16182-DP00-P0ZEN-020004 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9802 | T16182-DP00-P0ZEN-020006 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9803 | T16182-DP00-P0ZEN-020007 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9804 | T16182-UC07-P0ZEN-100001 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9805 | T16182-UC07-P0ZEN-100002 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9806 | T16182-UC07-P0ZEN-100003 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9807 | T16182-UE00-P0MB-100004 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9808 | T16182-UE00-P0MB-100005 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9809 | T16182-UE00-P0MB-100006 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9810 | T16182-UE00-P0MB-100007 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9811 | T16182-UE00-P0UMA-100008 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9812 | T16182-UE00-P0UMA-100009 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9813 | T16182-UE00-P0UMA-100010 | 2020-02-10 | DHI-ASBUILT-000002 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10000 | T16182-YB03-P0ZEN-165537 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10001 | T16182-YB03-P0ZEN-165538 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10002 | T16182-YB03-P0ZEN-165539 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10003 | T16182-YB03-P0ZEN-165540 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10004 | T16182-YB03-P0ZEN-165541 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10005 | T16182-YB03-P0ZEN-165542 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10006 | T16182-YB03-P0ZEN-165543 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10007 | T16182-YB03-P0ZEN-165544 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10008 | T16182-YB03-P0ZEN-165545 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10009 | T16182-YB03-P0ZEN-165546 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10010 | T16182-YB03-P0ZEN-165547 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10011 | T16182-YB03-P0ZEN-165548 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10012 | T16182-YL16-P0ZEN-165551 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10013 | T16182-YL16-P0ZEN-165552 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10014 | T16182-YL16-P0ZEN-165553 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10015 | T16182-YL16-P0ZEN-165554 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10016 | T16182-YL16-P0ZEN-165555 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10017 | T16182-YL16-P0ZEN-165556 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10018 | T16182-YL16-P0ZEN-165557 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10019 | T16182-YL16-P0ZEN-165558 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10020 | T16182-YL16-P0ZEN-165559 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10021 | T16182-YL16-P0ZEN-165560 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10022 | T16182-YL16-P0ZEN-165561 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10023 | T16182-YL16-P0ZEN-165562 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10024 | T16182-YL16-P0ZEN-165563 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10025 | T16182-YL16-P0ZEN-165564 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10026 | T16182-YL16-P0ZEN-165565 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10027 | T16182-YL16-P0ZEN-165566 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10028 | T16182-YL16-P0ZEN-165567 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10029 | T16182-YL16-P0ZEN-165568 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10030 | T16182-YD02-P0ZEN-165571 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10031 | T16182-YD02-P0ZEN-165572 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10032 | T16182-YD02-P0ZEN-165573 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10033 | T16182-YD02-P0ZEN-165575 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10034 | T16182-YD02-P0ZEN-165576 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10035 | T16182-CV03-P0ZEN-165701 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10036 | T16182-CV03-P0ZEN-165711 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10037 | T16182-CV03-P0ZEN-165731 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10038 | T16182-YR02-P0ZEN-165900 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10039 | T16182-YR05-P0SAY-163425 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10040 | T16182-YD02-P0ZEN-165577 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10041 | T16182-YR01-P0CRU-161150 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10042 | T16182-YD02-P0SAC-163426 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10043 | T16182-XW01-P0SAA-133301 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10044 | T16182-YK09-P0SAA-133302 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10045 | T16182-XW03-P0SAH-133401 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10046 | T16182-XG07-P0SAH-133402 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10047 | T16182-XW03-P0SAH-133403 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10048 | T16182-XH02-P0SAH-133404 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10049 | T16182-XW03-P0SAC-133501 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10050 | T16182-XG07-P0SAC-133502 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10051 | T16182-XW03-P0SAC-133503 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10052 | T16182-XH02-P0SAC-133504 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10053 | T16182-XW03-P0SAK-133601 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10054 | T16182-XG07-P0SAK-133602 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10055 | T16182-XW03-P0SAK-133603 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10056 | T16182-XH02-P0SAK-133604 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10057 | T16182-XW03-P0SAJ-133701 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10058 | T16182-XG07-P0SAJ-133702 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10059 | T16182-XW03-P0SAJ-133703 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10060 | T16182-XH02-P0SAJ-133704 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10061 | T16182-XW03-P0SAI-133801 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10062 | T16182-XG07-P0SAI-133802 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10063 | T16182-XW03-P0SAI-133803 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10064 | T16182-XH02-P0SAI-133804 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10065 | T16182-XW03-P0SAI-133901 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10066 | T16182-XG07-P0SAI-133902 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10067 | T16182-XW03-P0SAI-133903 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10068 | T16182-XH02-P0SAI-133904 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10069 | T16182-XW03-P0SAL-134001 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10070 | T16182-XG07-P0SAL-134002 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10071 | T16182-XW03-P0SAL-134003 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10072 | T16182-XH02-P0SAL-134004 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10073 | T16182-XW03-P0SAR-134101 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10074 | T16182-XG07-P0SAR-134102 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10075 | T16182-XW03-P0SAR-134103 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10076 | T16182-XH02-P0SAR-134104 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10077 | T16182-XW03-P0SAR-134201 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10078 | T16182-XG07-P0SAR-134202 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10079 | T16182-XW03-P0SAR-134203 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10080 | T16182-XH02-P0SAR-134204 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10081 | T16182-XW03-P0SAE-134301 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10082 | T16182-XG07-P0SAE-134302 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10083 | T16182-XW03-P0SAE-134303 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10084 | T16182-XH02-P0SAE-134304 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10085 | T16182-XW03-P0SAN-134401 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10086 | T16182-XG07-P0SAN-134402 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10087 | T16182-XW03-P0SAN-134403 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10088 | T16182-XH02-P0SAN-134404 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10089 | T16182-XW03-P0SAD-134501 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10090 | T16182-XG07-P0SAD-134502 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10091 | T16182-XW03-P0SAD-134503 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10092 | T16182-XH02-P0SAD-134504 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10093 | T16182-XW03-P0SAE-134601 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10094 | T16182-XG07-P0SAE-134602 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10095 | T16182-XW03-P0SAE-134603 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10096 | T16182-XH02-P0SAE-134604 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10097 | T16182-XW03-P0SAF-134701 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10098 | T16182-XG07-P0SAF-134702 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10099 | T16182-XW03-P0SAF-134703 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10100 | T16182-XH02-P0SAF-134704 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10101 | T16182-XW03-P0SAB-134801 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10102 | T16182-XG07-P0SAB-134802 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10103 | T16182-XW03-P0SAB-134803 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10104 | T16182-XH02-P0SAB-134804 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10105 | T16182-XW03-P0SAG-134901 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10106 | T16182-XG07-P0SAG-134902 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10107 | T16182-XW03-P0SAG-134903 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10108 | T16182-XH02-P0SAG-134904 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10109 | T16182-XW03-P0SAM-135001 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10110 | T16182-XG07-P0SAM-135002 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10111 | T16182-XW03-P0SAM-135003 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10112 | T16182-XH02-P0SAM-135004 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10113 | T16182-XW03-P0SAV-135101 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10114 | T16182-XG07-P0SAV-135102 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10115 | T16182-XW03-P0SAV-135103 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10116 | T16182-XH02-P0SAV-135104 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10117 | T16182-YT01-P0SAA-136001 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10118 | T16182-XW03-P0SAQ-135201 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10119 | T16182-XG07-P0SAQ-135202 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10120 | T16182-XW03-P0SAQ-135203 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10121 | T16182-XH02-P0SAQ-135204 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10122 | T16182-YT01-P0SAA-136002 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10123 | T16182-YT01-P0SAA-136003 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10124 | T16182-YT01-P0SAA-136004 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10125 | T16182-YT01-P0SAA-136005 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10126 | T16182-XW03-P0SAE-135301 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10127 | T16182-XG07-P0SAE-135302 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10128 | T16182-XW03-P0SAE-135303 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10129 | T16182-XH02-P0SAE-135304 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10130 | T16182-XW03-P0SAE-135401 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10131 | T16182-XG07-P0SAE-135402 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10132 | T16182-XW03-P0SAE-135403 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10133 | T16182-XH02-P0SAE-135404 | 2020-02-11 | DHI-ASBUILT-000004 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10134 | T16182-XB00-P6MKA-250001 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10135 | T16182-XB00-P7MKA-250002 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10136 | T16182-UF00-P6MKA-250003 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10137 | T16182-YD00-P0MKA-250004 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10138 | T16182-YD00-P0MKA-250005 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10139 | T16182-YD00-P0MKA-250006 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10140 | T16182-YK10-P0MKA-250007 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10141 | T16182-YD00-P6MKA-250008 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10142 | T16182-YT01-P0MKA-250009 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10143 | T16182-UC02-P0MKA-250010 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10144 | T16182-UC02-P6MKA-250011 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10145 | T16182-UC02-P7MKA-250012 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10146 | T16182-UC02-P0MKA-250013 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10147 | T16182-UC02-P0MKA-250014 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10148 | T16182-UC02-P0MKA-250015 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10149 | T16182-YD00-P0MKA-250016 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10150 | T16182-YD00-P0MKA-250017 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10151 | T16182-YD00-P0MKA-250018 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10152 | T16182-DM02-P0MKA-250019 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10153 | T16182-YD00-P0MKA-250020 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10154 | T16182-DM02-P0MKA-250021 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10155 | T16182-UC02-P0MKA-250022 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10156 | T16182-YS00-P0CJN-290001 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10157 | T16182-YR05-P0CJN-290002 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10158 | T16182-BV02-P0CJN-290003 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10159 | T16182-YR05-P0CJN-290004 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10160 | T16182-YE00-P0CJN-290005 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10161 | T16182-YU02-P0MKY-290006 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10162 | T16182-YF00-P0MKY-290007 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10163 | T16182-YS01-P0MKY-290008 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10164 | T16182-YS01-P0MKY-290009 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10165 | T16182-YT10-P0MKY-290010 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10166 | T16182-YS01-P0MKY-290011 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10167 | T16182-YS01-P0MKY-290012 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10168 | T16182-YS01-P0MKY-290013 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10169 | T16182-YR02-P0CJN-290014 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10170 | T16182-YD00-P0MKA-250023 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10171 | T16182-YD00-P0MKA-250024 | 2020-02-11 | DHI-ASBUILT-000005 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9814 | T16182-XW01-P0ZEN-161001 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9815 | T16182-YR05-P0ZEN-161011 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9816 | T16182-YF00-P0CJD-161021 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9817 | T16182-YF00-P0CJD-161022 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9818 | T16182-YF00-P0CJD-161025 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9819 | T16182-YF02-P0ZEN-161031 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9820 | T16182-YF00-P0CJA-161041 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9821 | T16182-YF01-P0BYA-161051 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9822 | T16182-YL01-P0CBA-161101 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9823 | T16182-YF02-P0CRV-161102 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9824 | T16182-CV03-P0CRN-161103 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9825 | T16182-CV03-P0CRN-161104 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9826 | T16182-CV03-P0CRN-161105 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9827 | T16182-YR04-P0CUQ-161111 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9828 | T16182-YD00-P0CUQ-161112 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9829 | T16182-YD00-P0CRN-161113 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9830 | T16182-YB03-P0CRN-161114 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9831 | T16182-YL16-P0CRN-161115 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9832 | T16182-YD05-P0CRN-161116 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9833 | T16182-YL01-P0CRN-161117 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9834 | T16182-YR04-P0CUQ-161118 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9835 | T16182-YD00-P0CUQ-161119 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9836 | T16182-CV03-P0CWQ-161121 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9837 | T16182-CV03-P0CWQ-161122 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9838 | T16182-CV03-P0CWQ-161123 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9839 | T16182-CV03-P0CWQ-161132 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9840 | T16182-CV03-P0CWQ-161133 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9841 | T16182-CV03-P0CWQ-161134 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9842 | T16182-CV03-P0CWQ-161135 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9843 | T16182-YR05-P0CWQ-161141 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9844 | T16182-YR05-P0CWQ-161142 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9845 | T16182-YR05-P0CWQ-161143 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9846 | T16182-YR05-P0CWQ-161146 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9847 | T16182-YR05-P0CWQ-161147 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9848 | T16182-YR05-P0CWQ-161148 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9849 | T16182-CV03-P0CRT-161149 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9850 | T16182-YF00-P0CBA-161201 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9851 | T16182-YF00-P0CBA-161202 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9852 | T16182-YF00-P0CBA-161203 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9853 | T16182-YF00-P0CBA-161204 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9854 | T16182-YF00-P0CBA-161205 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9855 | T16182-YF00-P0CBA-161206 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9856 | T16182-YF00-P0CBA-161207 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9857 | T16182-YF00-P0CBA-161208 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9858 | T16182-YF00-P0CBA-161209 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9859 | T16182-YF00-P0CBA-161210 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9860 | T16182-YF00-P0CBA-161211 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9861 | T16182-YF00-P0CBA-161212 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9862 | T16182-YF00-P0CBA-161213 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9863 | T16182-YF00-P0CBA-161214 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9864 | T16182-YF00-P0CBA-161216 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9865 | T16182-YF00-P0CBA-161220 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9866 | T16182-YF00-P0CBA-161221 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9867 | T16182-YF00-P0CBA-161222 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9868 | T16182-YF00-P0CGA-161301 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9869 | T16182-YF00-P0CGA-161302 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9870 | T16182-YF00-P0CGA-161303 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9871 | T16182-YF00-P0CGA-161304 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9872 | T16182-YF00-P0CGA-161305 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9873 | T16182-YF00-P0CGA-161306 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9874 | T16182-YF00-P0CGA-161307 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9875 | T16182-YF00-P0CGA-161308 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9876 | T16182-YF00-P0CGA-161309 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9877 | T16182-YF00-P0CGA-161310 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9878 | T16182-YF00-P0CGA-161311 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9879 | T16182-YF00-P0CGA-161312 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9880 | T16182-YF00-P0CGA-161313 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9881 | T16182-YF00-P0CGA-161314 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9882 | T16182-YF00-P0CGA-161316 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9883 | T16182-YF00-P0CGA-161320 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9884 | T16182-YF00-P0CGA-161321 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9885 | T16182-YF00-P0CGA-161322 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9886 | T16182-YD00-P0CWQ-161401 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9887 | T16182-YD00-P0CWQ-161402 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9888 | T16182-YD00-P0CWQ-161403 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9889 | T16182-YD00-P0CWQ-161404 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9890 | T16182-YD00-P0CWQ-161405 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9891 | T16182-YD00-P0CWQ-161406 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9892 | T16182-YD00-P0CWQ-161407 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9893 | T16182-YD00-P0CWQ-161408 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9894 | T16182-YD00-P0CWQ-161409 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9895 | T16182-YL00-P0ZEN-163101 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9896 | T16182-CV03-P0ZEN-163102 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9897 | T16182-CV03-P0ZEN-163103 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9898 | T16182-CV03-P0ZEN-163104 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9899 | T16182-CV03-P0ZEN-163201 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9900 | T16182-CV03-P0EKU-163202 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9901 | T16182-CV03-P0UCL-163203 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9902 | T16182-CV03-P0ZEN-163204 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9903 | T16182-YS00-P0ZEN-163301 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9904 | T16182-YS00-P0ZEN-163302 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9905 | T16182-YS00-P0ZEN-163303 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9906 | T16182-YS00-P0ZEN-163304 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9907 | T16182-YS00-P0ZEN-163305 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9908 | T16182-YS00-P0ZEN-163306 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9909 | T16182-YS00-P0ZEN-163307 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9910 | T16182-YS00-P0ZEN-163308 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9911 | T16182-YS00-P0ZEN-163309 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9912 | T16182-YS00-P0ZEN-163310 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9913 | T16182-YS00-P0ZEN-163311 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9914 | T16182-YS00-P0ZEN-163312 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9915 | T16182-YS00-P0ZEN-163313 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9916 | T16182-YS00-P0ZEN-163314 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9917 | T16182-YS00-P0ZEN-163315 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9918 | T16182-YS00-P0ZEN-163316 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9919 | T16182-YS00-P0ZEN-163317 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9920 | T16182-YS00-P0ZEN-163318 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9921 | T16182-YS00-P0ZEN-163319 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9922 | T16182-YS00-P0ZEN-163320 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9923 | T16182-YS00-P0ZEN-163321 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9924 | T16182-CV03-P0ZEN-163331 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9925 | T16182-YF02-P0SAY-163401 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9926 | T16182-YL01-P0SAY-163402 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9927 | T16182-CV03-P0SAY-163403 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9928 | T16182-YK00-P0SAY-163404 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9929 | T16182-YF00-P0SAY-163405 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9930 | T16182-YL16-P0SAY-163406 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9931 | T16182-YB03-P0SAY-163407 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9932 | T16182-YD02-P0SAC-163408 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9933 | T16182-YD02-P0SAC-163409 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9934 | T16182-YD02-P0SAC-163411 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9935 | T16182-YD02-P0SAC-163412 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9936 | T16182-YD02-P0SAC-163413 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9937 | T16182-YD02-P0SAC-163414 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9938 | T16182-YD02-P0SAC-163415 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9939 | T16182-YD02-P0SAC-163416 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9940 | T16182-YD02-P0SAC-163417 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9941 | T16182-YD02-P0SAC-163418 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9942 | T16182-YD02-P0SAC-163419 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9943 | T16182-YD02-P0SAC-163420 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9944 | T16182-YD02-P0SAC-163421 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9945 | T16182-YD02-P0SAC-163422 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9946 | T16182-YR05-P0SAY-163423 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9947 | T16182-YD05-P0SAY-163424 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9948 | T16182-XW01-P0ZEN-165001 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9949 | T16182-YL02-P0ZEN-165011 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9950 | T16182-YK00-P0ZEN-165301 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9951 | T16182-YK00-P0ZEN-165302 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9952 | T16182-YK00-P0ZEN-165303 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9953 | T16182-YK00-P0ZEN-165304 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9954 | T16182-YK00-P0ZEN-165305 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9955 | T16182-YK00-P0ZEN-165311 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9956 | T16182-YK00-P0ZEN-165312 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9957 | T16182-YK00-P0ZEN-165313 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9958 | T16182-YK00-P0ZEN-165314 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9959 | T16182-YK00-P0ZEN-165315 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9960 | T16182-YK00-P0ZEN-165316 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9961 | T16182-YK00-P0ZEN-165317 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9962 | T16182-YK00-P0ZEN-165318 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9963 | T16182-YK00-P0ZEN-165319 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9964 | T16182-YK00-P0ZEN-165320 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9965 | T16182-YK00-P0ZEN-165321 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9966 | T16182-YK00-P0ZEN-165322 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9967 | T16182-YK00-P0ZEN-165323 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9968 | T16182-YD02-P0ZEN-165501 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9969 | T16182-YD02-P0ZEN-165502 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9970 | T16182-YD02-P0ZEN-165503 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9971 | T16182-YD02-P0ZEN-165504 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9972 | T16182-YD02-P0ZEN-165505 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9973 | T16182-YD02-P0ZEN-165506 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9974 | T16182-YD02-P0ZEN-165507 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9975 | T16182-YD02-P0ZEN-165508 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9976 | T16182-YD02-P0ZEN-165509 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9977 | T16182-YD02-P0ZEN-165510 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9978 | T16182-YD02-P0ZEN-165514 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9979 | T16182-YD02-P0ZEN-165515 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9980 | T16182-YD02-P0ZEN-165516 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9981 | T16182-YD02-P0ZEN-165517 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9982 | T16182-YD02-P0ZEN-165518 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9983 | T16182-YD02-P0ZEN-165519 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9984 | T16182-YD02-P0ZEN-165520 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9985 | T16182-YD02-P0ZEN-165521 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9986 | T16182-YD02-P0ZEN-165522 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9987 | T16182-YD02-P0ZEN-165523 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9988 | T16182-YD02-P0ZEN-165524 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9989 | T16182-YD02-P0ZEN-165525 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9990 | T16182-YD02-P0ZEN-165526 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9991 | T16182-YD02-P0ZEN-165527 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9992 | T16182-YD02-P0ZEN-165528 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9993 | T16182-YD02-P0ZEN-165529 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9994 | T16182-YB03-P0ZEN-165531 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9995 | T16182-YB03-P0ZEN-165532 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9996 | T16182-YB03-P0ZEN-165533 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9997 | T16182-YB03-P0ZEN-165534 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9998 | T16182-YB03-P0ZEN-165535 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
9999 | T16182-YB03-P0ZEN-165536 | 2020-02-11 | DHI-ASBUILT-000003 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10172 | T16182-XS00-P0SG-136601 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10173 | T16182-XS00-P0SG-136602 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10174 | T16182-XG02-P0SGA-136603 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10175 | T16182-XH01-P0SGA-136604 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10176 | T16182-YT10-P0SGA-136605 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10177 | T16182-YU03-P0CYE-136606 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10178 | T16182-YU02-P0CYE-136607 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10179 | T16182-YT01-P0SGA-136609 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10180 | T16182-YT01-P0SGA-136610 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10181 | T16182-YT01-P0SGA-136611 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10182 | T16182-YT01-P0SGE-136612 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10183 | T16182-YT01-P0SGC-136613 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10184 | T16182-YT01-P0SGK-136614 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10185 | T16182-YT01-P0SGZ-136615 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10186 | T16182-YT01-P0SGX-136616 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10187 | T16182-YT01-P0CYE-136617 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10188 | T16182-YT01-P0CYE-136618 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10189 | T16182-XG02-P0SGA-136701 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10190 | T16182-XG02-P0SGE-136702 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10191 | T16182-XG02-P0SGK-136703 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10192 | T16182-XH01-P0SGA-136711 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10193 | T16182-XH01-P0SGE-136712 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10194 | T16182-XH01-P0SGK-136713 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10195 | T16182-YT10-P0SGE-136722 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10196 | T16182-YT10-P0SGK-136723 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10197 | T16182-YD00-P0SGZ-136731 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10198 | T16182-YD00-P0CYE-136741 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10199 | T16182-YU02-P0CYE-136742 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10200 | T16182-YT10-P0CYE-136743 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10201 | T16182-XG02-P0CYE-136744 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10202 | T16182-XG02-P0SGA-136801 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10203 | T16182-XG02-P0SGE-136802 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10204 | T16182-XG02-P0SGK-136803 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10205 | T16182-XH01-P0SGA-136811 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10206 | T16182-XH01-P0SGE-136812 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10207 | T16182-XH01-P0SGK-136813 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10208 | T16182-YT10-P0SGE-136822 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10209 | T16182-YT10-P0SGK-136823 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10210 | T16182-YD00-P0SGZ-136831 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10211 | T16182-YD00-P0CYE-136841 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10212 | T16182-YU02-P0CYE-136842 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10213 | T16182-YT10-P0CYE-136843 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10214 | T16182-XG02-P0CYE-136844 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10215 | T16182-XG02-P0SGA-136901 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10216 | T16182-XG02-P0SGE-136902 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10217 | T16182-XG02-P0SGK-136903 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10218 | T16182-XH01-P0SGA-136911 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10219 | T16182-XH01-P0SGE-136912 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10220 | T16182-XH01-P0SGK-136913 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10221 | T16182-YT10-P0SGE-136922 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10222 | T16182-YT10-P0SGK-136923 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10223 | T16182-YD00-P0SGZ-136931 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10224 | T16182-YD00-P0CYE-136941 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10225 | T16182-YU02-P0CYE-136942 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10226 | T16182-YT10-P0CYE-136943 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10227 | T16182-XG02-P0CYE-136944 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10228 | T16182-XG02-P0SGC-137001 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10229 | T16182-XH01-P0SGC-137011 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10230 | T16182-YT10-P0SGC-137021 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10231 | T16182-YD00-P0SGZ-137031 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10232 | T16182-YD00-P0CYE-137041 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10233 | T16182-YU02-P0CYE-137042 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10234 | T16182-XG02-P0SGC-137101 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10235 | T16182-XH01-P0SGC-137111 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10236 | T16182-YT10-P0SGC-137121 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10237 | T16182-YD00-P0SGZ-137131 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10238 | T16182-YD00-P0CYE-137141 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10239 | T16182-YU02-P0CYE-137142 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10240 | T16182-XG02-P0SGC-137201 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10241 | T16182-XH01-P0SGC-137211 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10242 | T16182-YT10-P0SGC-137221 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10243 | T16182-YD00-P0SGZ-137231 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10244 | T16182-YD00-P0CYE-137241 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10245 | T16182-YU02-P0CYE-137242 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10246 | T16182-XG02-P0SGA-137301 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10247 | T16182-XG02-P0SGE-137302 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10248 | T16182-XG02-P0SGE-137303 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10249 | T16182-XH01-P0SGA-137311 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10250 | T16182-XH01-P0SGE-137312 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10251 | T16182-YT10-P0SGE-137322 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10252 | T16182-YD00-P0SGZ-137331 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10253 | T16182-YD00-P0SGZ-137332 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10254 | T16182-YD00-P0CYE-137341 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10255 | T16182-YU02-P0CYE-137342 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10256 | T16182-XG02-P0SGC-137401 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10257 | T16182-XH01-P0SGC-137411 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10258 | T16182-YT10-P0SGC-137421 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10259 | T16182-YD00-P0SGZ-137431 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10260 | T16182-YD00-P0CYE-137441 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10261 | T16182-YU02-P0CYE-137442 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10262 | T16182-XG02-P0SGK-137603 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10263 | T16182-XH01-P0SGK-137613 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10264 | T16182-YT10-P0SGK-137623 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10265 | T16182-YT10-P0CYE-137643 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10266 | T16182-XG02-P0CYE-137644 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10267 | T16182-YD00-P0SGZ-137631 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10268 | T16182-YD00-P0CYE-137641 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10269 | T16182-YU02-P0CYE-137642 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10270 | T16182-XG02-P0SGA-137701 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10271 | T16182-XH01-P0SGA-137711 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10272 | T16182-YD00-P0SGZ-137731 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10273 | T16182-YD00-P0CYE-137741 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10274 | T16182-YU02-P0CYE-137742 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10275 | T16182-XG02-P0SGA-137801 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10276 | T16182-XH01-P0SGA-137811 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10277 | T16182-YD00-P0SGZ-137831 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10278 | T16182-YD00-P0CYE-137841 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10279 | T16182-YU02-P0CYE-137842 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10280 | T16182-XG02-P0SGA-137901 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10281 | T16182-XG02-P0SGK-137902 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10282 | T16182-XG02-P0SGE-137903 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10283 | T16182-XH01-P0SGA-137911 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10284 | T16182-XH01-P0SGK-137912 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10285 | T16182-XH01-P0SGE-137913 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10286 | T16182-YT10-P0SGK-137922 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10287 | T16182-YT10-P0SGE-137923 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10288 | T16182-YD00-P0SGZ-137931 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10289 | T16182-YD00-P0CYE-137941 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10290 | T16182-YU02-P0CYE-137942 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10291 | T16182-YT10-P0CYE-137943 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10292 | T16182-XG02-P0CYE-137944 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10293 | T16182-XG02-P0SGA-138001 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10294 | T16182-XH01-P0SGA-138011 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10295 | T16182-YD00-P0SGZ-138031 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10296 | T16182-YD00-P0CYE-138041 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10297 | T16182-YU02-P0CYE-138042 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10298 | T16182-XG02-P0SGC-138101 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10299 | T16182-XH01-P0SGC-138111 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10300 | T16182-YT10-P0SGC-138121 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10301 | T16182-YD00-P0SGZ-138131 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10302 | T16182-YD00-P0CYE-138141 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10303 | T16182-YU02-P0CYE-138142 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10304 | T16182-XG02-P0SGC-138201 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10305 | T16182-XH01-P0SGC-138211 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10306 | T16182-YT10-P0SGC-138221 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10307 | T16182-YD00-P0SGZ-138231 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10308 | T16182-YD00-P0CYE-138241 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10309 | T16182-YU02-P0CYE-138242 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10310 | T16182-XG02-P0SGC-138301 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10311 | T16182-XH01-P0SGC-138311 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10312 | T16182-YT10-P0SGC-138321 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10313 | T16182-YD00-P0SGZ-138331 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10314 | T16182-YD00-P0CYE-138341 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10315 | T16182-YU02-P0CYE-138342 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10316 | T16182-YD00-P0SGZ-138431 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10317 | T16182-YD00-P0CYE-138441 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10318 | T16182-YU02-P0CYE-138442 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10319 | T16182-XG02-P0SGA-138601 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10320 | T16182-XG02-P0SGE-138602 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10321 | T16182-XG02-P0SGE-138603 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10322 | T16182-XG02-P0SGC-138604 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10323 | T16182-XG02-P0SGC-138606 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10324 | T16182-XH01-P0SGA-138611 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10325 | T16182-XH01-P0SGE-138612 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10326 | T16182-XH01-P0SGE-138613 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10327 | T16182-XH01-P0SGC-138614 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10328 | T16182-XH01-P0SGC-138616 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10329 | T16182-YT10-P0SGE-138622 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10330 | T16182-YT10-P0SGE-138623 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10331 | T16182-YT10-P0SGC-138624 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10332 | T16182-YT10-P0SGC-138626 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10333 | T16182-YD00-P0SGZ-138631 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10334 | T16182-YD00-P0CYE-138641 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10335 | T16182-YU02-P0CYE-138642 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10336 | T16182-YT10-P0CYE-138643 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10337 | T16182-XG02-P0CYE-138644 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10338 | T16182-XG02-P0SGK-138702 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10339 | T16182-XH01-P0SGK-138712 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10340 | T16182-YT10-P0SGK-138722 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10341 | T16182-YD00-P0SGZ-138731 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10342 | T16182-YD00-P0CYE-138741 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10343 | T16182-YU02-P0CYE-138742 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10344 | T16182-YT10-P0CYE-138743 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10345 | T16182-XG02-P0CYE-138744 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10346 | T16182-XG02-P0SGK-138802 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10347 | T16182-XH01-P0SGK-138812 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10348 | T16182-YT10-P0SGK-138822 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10349 | T16182-YD00-P0SGZ-138831 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10350 | T16182-YD00-P0CYE-138841 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10351 | T16182-YU02-P0CYE-138842 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10352 | T16182-YT10-P0CYE-138843 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10353 | T16182-XG02-P0CYE-138844 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10354 | T16182-XG02-P0SGA-138901 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10355 | T16182-XH01-P0SGA-138911 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10356 | T16182-YD00-P0SGZ-138931 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10357 | T16182-YD00-P0CYE-138941 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10358 | T16182-YU02-P0CYE-138942 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10359 | T16182-XG02-P0SGA-139001 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10360 | T16182-XH01-P0SGA-139011 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10361 | T16182-YD00-P0SGZ-139031 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10362 | T16182-YD00-P0CYE-139041 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10363 | T16182-YU02-P0CYE-139042 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10364 | T16182-YT10-P0CYE-139043 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10365 | T16182-XG02-P0CYE-139044 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10366 | T16182-XG02-P0SGA-139101 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10367 | T16182-XG02-P0SGK-139103 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10368 | T16182-XH01-P0SGA-139111 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10369 | T16182-XH01-P0SGK-139113 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10370 | T16182-YT10-P0SGK-139123 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10371 | T16182-YD00-P0SGZ-139131 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10372 | T16182-YD00-P0CYE-139141 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10373 | T16182-YU02-P0CYE-139142 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10374 | T16182-YT10-P0CYE-139143 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10375 | T16182-XG02-P0CYE-139144 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10376 | T16182-YD00-P0SGZ-139231 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10377 | T16182-YD00-P0CYE-139241 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10378 | T16182-YU02-P0CYE-139242 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10379 | T16182-XG02-P0SGA-139301 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10380 | T16182-XH01-P0SGA-139311 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10381 | T16182-YD00-P0SGZ-139331 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10382 | T16182-YD00-P0CYE-139341 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10383 | T16182-YU02-P0CYE-139342 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10384 | T16182-XG02-P0SGA-139401 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10385 | T16182-XH01-P0SGA-139411 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10386 | T16182-YD00-P0SGZ-139431 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10387 | T16182-YD00-P0CYE-139441 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10388 | T16182-YU02-P0CYE-139442 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10389 | T16182-YT10-P0CYE-139443 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10390 | T16182-XG02-P0CYE-139444 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10391 | T16182-XG02-P0SGA-139501 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10392 | T16182-XG02-P0SGE-139502 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10393 | T16182-XH01-P0SGA-139511 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10394 | T16182-XH01-P0SGE-139512 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10395 | T16182-YT10-P0SGE-139522 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10396 | T16182-YD00-P0SGZ-139531 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10397 | T16182-YD00-P0CYE-139541 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10398 | T16182-YU02-P0CYE-139542 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10399 | T16182-YT10-P0CYE-139543 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10400 | T16182-XG02-P0CYE-139544 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10401 | T16182-XG02-P0SGA-139601 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10402 | T16182-XG02-P0SGK-139602 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10403 | T16182-XG02-P0SGE-139603 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10404 | T16182-XH01-P0SGA-139611 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10405 | T16182-XH01-P0SGK-139612 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10406 | T16182-XH01-P0SGE-139613 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10407 | T16182-YT10-P0SGE-139623 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10408 | T16182-YT10-P0SGK-139622 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10409 | T16182-YD00-P0SGZ-139631 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10410 | T16182-YD00-P0CYE-139641 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10411 | T16182-YU02-P0CYE-139642 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10412 | T16182-YD00-P0SGZ-139731 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10413 | T16182-YD00-P0CYE-139741 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10414 | T16182-YU02-P0CYE-139742 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10415 | T16182-YD00-P0SGZ-139831 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10416 | T16182-YD00-P0CYE-139841 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10417 | T16182-YU02-P0CYE-139842 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10418 | T16182-XG02-P0SGC-139901 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10419 | T16182-XH01-P0SGC-139911 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10420 | T16182-YT10-P0SGC-139921 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10421 | T16182-YD00-P0SGZ-139931 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10422 | T16182-YD00-P0CYE-139941 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10423 | T16182-YU02-P0CYE-139942 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10424 | T16182-DN05-P0SG-136620 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10425 | T16182-CV03-P0SG-136621 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10426 | T16182-XG02-P0SGK-138608 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10427 | T16182-XH01-P0SGK-138618 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10428 | T16182-YT10-P0SGK-138628 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10429 | T16182-XG02-P0SGK-139002 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10430 | T16182-XH01-P0SGK-139012 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10431 | T16182-YT10-P0SGK-139023 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10432 | T16182-XG02-P0SGA-138401 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10433 | T16182-XH01-P0SGA-138411 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10434 | T16182-XG02-P0SGK-138502 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10435 | T16182-XH01-P0SGK-138512 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10436 | T16182-YT10-P0SGK-138522 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10437 | T16182-YD00-P0CYE-138541 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10438 | T16182-YU02-P0CYE-138542 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10439 | T16182-YD00-P0SGZ-138531 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10440 | T16182-DN05-P0SG-136623 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10441 | T16182-XJ00-P0SGA-136622 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10442 | T16182-YD00-P0SGZ-136631 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10443 | T16182-YD00-P0CYE-136641 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10444 | T16182-YU02-P0CYE-136642 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10445 | T16182-XG02-P0SGC-138902 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10446 | T16182-XH01-P0SGC-138912 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10447 | T16182-YT10-P0SGC-138922 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10448 | T16182-YD00-P0CYE-136624 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10449 | T16182-XG02-P0SGC-138102 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10450 | T16182-XH01-P0SGC-138112 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10451 | T16182-YT10-P0SGC-138122 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10452 | T16182-YD00-P0CYE-138143 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10453 | T16182-YU02-P0CYE-138144 | 2020-02-12 | DHI-ASBUILT-000006 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10454 | T16182-YK10-P0LCP-410001 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10455 | T16182-YK10-P0GHC-410011 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10456 | T16182-YK10-P0GKB-410021 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10457 | T16182-YK10-P0GKB-410031 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10458 | T16182-YT10-P0LCP-410002 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10459 | T16182-YT10-P0GHC-410012 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10460 | T16182-YT10-P0GKB-410022 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10461 | T16182-YT10-P0GKB-410032 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10462 | T16182-CV03-P0PUR-411001 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10463 | T16182-CV03-P0PUR-411011 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10464 | T16182-CV03-P0PUR-411021 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10465 | T16182-CV03-P0PUR-411031 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10466 | T16182-YK08-P0PGB-420010 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10467 | T16182-YK08-P0PGB-420020 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10468 | T16182-YK08-P0LCM-420030 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10469 | T16182-YK08-P0LCM-420040 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10470 | T16182-YK08-P0GKC-420050 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10471 | T16182-YK08-P0GKC-420051 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10472 | T16182-DD09-P0ZEN-755001 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10473 | T16182-DD09-P0ZEN-755002 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10474 | T16182-DD09-P0ZEN-755003 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10475 | T16182-DD09-P0ZEN-755004 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10476 | T16182-DD09-P0ZEN-755005 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10477 | T16182-DD09-P0ZEN-755006 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10478 | T16182-DD09-P0ZEN-755007 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10479 | T16182-DD09-P0ZEN-755008 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10480 | T16182-DD09-P0ZEN-755009 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10481 | T16182-DD09-P0ZEN-755010 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10482 | T16182-DD09-P0ZEN-755011 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10483 | T16182-DD09-P0ZEN-755012 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10484 | T16182-DD09-P0ZEN-755013 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10485 | T16182-DD09-P0ZEN-755014 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10486 | T16182-DD09-P0ZEN-755015 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10487 | T16182-DD09-P0ZEN-755016 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10488 | T16182-DD09-P0ZEN-755017 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10489 | T16182-DD09-P0ZEN-755019 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10490 | T16182-DD09-P0ZEN-755020 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10491 | T16182-DD09-P0ZEN-755021 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10492 | T16182-DD09-P0ZEN-755022 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10493 | T16182-DD09-P0ZEN-755023 | 2020-02-12 | DHI-ASBUILT-000007 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10494 | T16182-XW01-P0MBA-121037 | 2020-02-17 | DHI-TRANSMIT-002807 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=889fca06-2e19-42f9-a86c-bb9cf5e2e5b3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10495 | T16182-CV03-P0ZEN-140001 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10496 | T16182-CV03-P0ZEN-140002 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10497 | T16182-XN00-P0ZEN-140003 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10498 | T16182-XL00-P0ZEN-140004 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10499 | T16182-XL00-P0ZEN-140005 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10500 | T16182-XL00-P0ZEN-140006 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10501 | T16182-BP00-P0LBA-140011 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10502 | T16182-BP00-P0LBC-140012 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10503 | T16182-BP00-P0LBS-140013 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10504 | T16182-BP00-P0LAB-140014 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10505 | T16182-BP00-P0EKG-140015 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10506 | T16182-BP00-P0LBG-140016 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10507 | T16182-XH01-P6UMA-140021 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10508 | T16182-XH01-P6UMA-140022 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10509 | T16182-XH01-P7UMA-140023 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10510 | T16182-XH01-P7UMA-140024 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10511 | T16182-XH01-P6UMA-140025 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10512 | T16182-XH01-P7UMA-140026 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10513 | T16182-XH01-P0ULY-140027 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10514 | T16182-XH01-P0ULY-140028 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10515 | T16182-XH01-P0ULY-140029 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10516 | T16182-XH01-P0ULY-140030 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10517 | T16182-XH01-P0ZEN-140031 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10518 | T16182-XH01-P1UHA-140032 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10519 | T16182-XH01-P1UHA-140034 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10520 | T16182-XH01-P1UHA-140036 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10521 | T16182-XH01-P2UHA-140037 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10522 | T16182-XH01-P2UHA-140038 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10523 | T16182-XH01-P2UHA-140039 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10524 | T16182-XH01-P3UHA-140040 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10525 | T16182-XH01-P3UHA-140041 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10526 | T16182-XH01-P3UHA-140042 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10527 | T16182-XH01-P4UHA-140043 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10528 | T16182-XH01-P4UHA-140044 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10529 | T16182-XH01-P4UHA-140045 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10530 | T16182-XH01-P5UHA-140046 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10531 | T16182-XH01-P5UHA-140047 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10532 | T16182-XH01-P5UHA-140048 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10533 | T16182-XH01-P1MBA-140049 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10534 | T16182-XH01-P2MBA-140050 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10535 | T16182-XH01-P3MBA-140051 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10536 | T16182-XH01-P4MBA-140052 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10537 | T16182-XH01-P5MBA-140053 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10538 | T16182-XH01-P0ULA-140054 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10539 | T16182-XH01-P0ULA-140055 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10540 | T16182-XH01-P0ULA-140056 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10541 | T16182-XH01-P0ULA-140057 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10542 | T16182-XH01-P0ULY-140058 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10543 | T16182-XH01-P0ULY-140059 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10544 | T16182-XH01-P0ULY-140060 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10545 | T16182-XH01-P0ULY-140061 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10546 | T16182-XH01-P0ZEN-140062 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10547 | T16182-XH01-P0UTF-140063 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10548 | T16182-XH01-P0GRK-140064 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10549 | T16182-XH01-P0UGD-140065 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10550 | T16182-XH01-P0UGA-140066 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10551 | T16182-XH01-P0UGA-140067 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10552 | T16182-XH01-P0UCB-140068 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10553 | T16182-XH01-P0LCA-140069 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10554 | T16182-XH01-P0LCA-140070 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10555 | T16182-XH01-P0LDK-140071 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10556 | T16182-XH01-P0LDK-140072 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10557 | T16182-XH01-P0EKG-140073 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10558 | T16182-XH01-P0UYE-140074 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10559 | T16182-XH01-P0UYF-140075 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10560 | T16182-XH01-P0UYC-140076 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10561 | T16182-XH01-P0UST-140077 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10562 | T16182-XH01-P0UYP-140078 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10563 | T16182-XH01-P7UBA-140079 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10564 | T16182-XH01-P6UBA-140080 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10565 | T16182-XH01-P0ZEN-140081 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10566 | T16182-XH01-P0ZEN-140082 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10567 | T16182-XH01-P0ZEN-140083 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10568 | T16182-XJ00-P0LBA-140101 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10569 | T16182-XJ00-P0LBC-140102 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10570 | T16182-XJ00-P0LBG-140103 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10571 | T16182-XJ00-P0LBG-140104 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10572 | T16182-XJ00-P0LCM-140105 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10573 | T16182-XJ00-P0LCA-140106 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10574 | T16182-XJ00-P0LAB-140108 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10575 | T16182-XJ00-P0PGB-140109 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10576 | T16182-XJ00-P0GKB-140112 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10577 | T16182-XJ00-P0GHC-140113 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10578 | T16182-XJ00-P0PDA-140114 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10579 | T16182-XJ00-P0MBH-140116 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10580 | T16182-XJ00-P0EKC-140117 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10581 | T16182-XJ00-P0EKG-140118 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10582 | T16182-XJ00-P0ZEN-140119 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10583 | T16182-XJ00-P0ZEN-140120 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10584 | T16182-XJ00-P0LBA-140201 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10585 | T16182-XJ00-P0LBC-140202 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10586 | T16182-XJ00-P0LBG-140203 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10587 | T16182-XJ00-P0LBG-140204 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10588 | T16182-XJ00-P0LCM-140205 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10589 | T16182-XJ00-P0LCA-140206 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10590 | T16182-XJ00-P0LAB-140208 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10591 | T16182-XJ00-P0PGB-140209 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10592 | T16182-XJ00-P0SCA-140210 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10593 | T16182-XJ00-P0QFB-140211 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10594 | T16182-XJ00-P0GKB-140212 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10595 | T16182-XJ00-P0GHC-140213 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10596 | T16182-XJ00-P0MBH-140216 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10597 | T16182-XJ00-P0EKC-140217 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10598 | T16182-XJ00-P0QUB-140219 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10599 | T16182-XJ00-P0QCA-140221 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10600 | T16182-XJ00-P0QJA-140223 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10601 | T16182-YK10-P0LF-140301 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10602 | T16182-YK10-P0LF-140302 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10603 | T16182-YK10-P0LF-140303 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10604 | T16182-YK10-P0LF-140304 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10605 | T16182-XH01-P0ZEN-140020 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10606 | T16182-XJ00-P0ZEN-140100 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10607 | T16182-XH01-P0LF-140401 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10608 | T16182-XH01-P0LF-140402 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10609 | T16182-XH01-P0LF-140403 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10610 | T16182-XH01-P0LF-140404 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10611 | T16182-XH01-P0LF-140405 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10612 | T16182-XH01-P0LF-140406 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10613 | T16182-XH01-P0LF-140407 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10614 | T16182-XH01-P0LF-140408 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10615 | T16182-XH01-P0LF-140411 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10616 | T16182-XH01-P0LF-140412 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10617 | T16182-XH01-P0LF-140415 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10618 | T16182-XH01-P0LF-140416 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10619 | T16182-XH01-P0LF-140417 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10620 | T16182-XH01-P0LF-140419 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10621 | T16182-XH01-P0LF-140420 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10622 | T16182-XJ00-P0GKB-140215 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10623 | T16182-XJ00-P0GM-140121 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10624 | T16182-XJ00-P0GM-140224 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10625 | T16182-XH01-P0LF-140421 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10626 | T16182-XH01-P0LF-140422 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10627 | T16182-XH01-P0LF-140423 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10628 | T16182-XH01-P0LF-140418 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10629 | T16182-XJ00-P0SCA-140110 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10630 | T16182-XH01-P0LF-140410 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10631 | T16182-BP00-P0LCA-140017 | 2020-02-18 | DHI-ASBUILT-000008 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10632 | T16182-XG05-P0ZEN-110001 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10633 | T16182-XG02-P0ZEN-110002 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10634 | T16182-XG02-P0LBA-110003 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10635 | T16182-XG02-P0LBC-110004 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10636 | T16182-XG02-P0LBG-110005 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10637 | T16182-XG02-P0LBS-110006 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10638 | T16182-XG02-P6LCM-110007 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10639 | T16182-XG02-P6LCA-110008 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10640 | T16182-XG02-P0LAA-110009 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10641 | T16182-XG02-P0PGB-110010 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10642 | T16182-XG02-P0GHC-110011 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10643 | T16182-XG02-P0QJA-110012 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10644 | T16182-XG02-P1EKC-110014 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10645 | T16182-XG07-P0LA-110031 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10646 | T16182-XG07-P0PG-110032 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10647 | T16182-XG07-P0GHC-110033 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10648 | T16182-XW01-P0LB-110035 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10649 | T16182-XW01-P0LC-110036 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10650 | T16182-XW01-P0LA-110037 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10651 | T16182-XW01-P0PGB-110038 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10652 | T16182-XW01-P0GHC-110039 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10653 | T16182-XS00-P0LB-110040 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10654 | T16182-XS00-P0LC-110041 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10655 | T16182-XS00-P0LA-110042 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10656 | T16182-XS00-P0PGB-110043 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10657 | T16182-XS00-P0GHC-110044 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10658 | T16182-XW03-P0LB-110045 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10659 | T16182-XW03-P0LC-110046 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10660 | T16182-XW03-P0LC-110047 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10661 | T16182-XW03-P0LA-110048 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10662 | T16182-XW03-P0LA-110049 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10663 | T16182-XW03-P0PGB-110050 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10664 | T16182-XW03-P0GHC-110051 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10665 | T16182-XW03-P0QJA-110052 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10666 | T16182-YT01-P0LF-110101 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10667 | T16182-YK08-P0LF-110102 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10668 | T16182-YT01-P0MAN-110153 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10669 | T16182-YK08-P0MAN-110154 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10670 | T16182-YT01-P0LBG-110251 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10671 | T16182-YK08-P0LBG-110252 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10672 | T16182-YT01-P0LCP-110301 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10673 | T16182-YD00-P0LCP-110302 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10674 | T16182-YD00-P0PGB-110401 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10675 | T16182-YL22-P0PGB-110402 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10676 | T16182-YT01-P0PGB-110403 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10677 | T16182-YD00-P0PGB-110404 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10678 | T16182-YD00-P0PGB-110405 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10679 | T16182-YL22-P0PGB-110406 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10680 | T16182-YT01-P0PGB-110407 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10681 | T16182-XS00-P0QJA-110500 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10682 | T16182-YK08-P0QJA-110501 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10683 | T16182-YD00-P0QJA-110502 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10684 | T16182-YT01-P0QJA-110503 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10685 | T16182-XW03-P0MJ-110053 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10686 | T16182-YD00-P0MJ-110504 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10687 | T16182-XG02-P0MJ-110505 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10688 | T16182-YK08-P0MJ-110506 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10689 | T16182-YU02-P0MJ-110507 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10690 | T16182-YT01-P0MJ-110508 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10691 | T16182-XG01-P0MJ-110509 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10692 | T16182-XS00-P0MJ-110510 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10693 | T16182-YT01-P0LF-110601 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10694 | T16182-YK10-P0LF-110602 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10695 | T16182-YT01-P0LF-110603 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10696 | T16182-YK10-P0LF-110604 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10697 | T16182-CN00-P0ZEN-110701 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10698 | T16182-CN00-P0ZEN-110702 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10699 | T16182-CN00-P0ZEN-110703 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10700 | T16182-CN00-P0ZEN-110704 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10701 | T16182-CN00-P0ZEN-110705 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10702 | T16182-CN00-P0ZEN-110706 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10703 | T16182-YF00-P0MJ-110511 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10704 | T16182-YE00-P0MJ-110512 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10705 | T16182-XW03-P0LA-110061 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10706 | T16182-YT10-P0MJ-110568 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10707 | T16182-XG11-P0MJ-110564 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10708 | T16182-YM02-P0MJ-110561 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10709 | T16182-YM02-P0MJ-110578 | 2020-02-20 | DHI-ASBUILT-000009 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10710 | T16182-XW03-P0MJ-110053 | 2020-02-21 | DHI-TRANSMIT-002813 | IFC | 4 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=3775818d-fbd2-493f-86b3-2f8861f3ccb8 | TRUE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10711 | T16182-XW01-P0MBA-121037 | 2020-02-26 | DHI-TRANSMIT-002821 | IFC | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10712 | T16182-BF05-P0ZEN-170101 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10713 | T16182-BF05-P0ZEN-170102 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10714 | T16182-VE04-P0ZEN-170103 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10715 | T16182-VK02-P0ZEN-170104 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10716 | T16182-BF05-P0ZEN-170105 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10717 | T16182-VE04-P0UMX-171001 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10718 | T16182-XB02-P0UMX-171002 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10719 | T16182-VE04-P0UMX-171004 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10720 | T16182-XB02-P0UMX-171005 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10721 | T16182-XB02-P0UMX-171006 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10722 | T16182-XB02-P0UMX-171007 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10723 | T16182-XB02-P0UMX-171008 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10724 | T16182-XB02-P0UMX-171009 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10725 | T16182-XB02-P0UMX-171010 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10726 | T16182-XB02-P0UMX-171011 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10727 | T16182-VK02-P0UMX-171012 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10728 | T16182-VK02-P0UMX-171013 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10729 | T16182-VK02-P0UMX-171014 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10730 | T16182-VK02-P0UMX-171015 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10731 | T16182-VK02-P0UMX-171016 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10732 | T16182-VK02-P0UMX-171017 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10733 | T16182-VK02-P0UMX-171018 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10734 | T16182-VK02-P0UMX-171019 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10735 | T16182-VK02-P0UMX-171020 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10736 | T16182-VK02-P0UMX-171021 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10737 | T16182-VK02-P0UMX-171022 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10738 | T16182-VK02-P0UMX-171023 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10739 | T16182-VK02-P0UMX-171024 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10740 | T16182-VE04-P0UMX-171051 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10741 | T16182-XB02-P0UMX-171052 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10742 | T16182-XB02-P0UMX-171053 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10743 | T16182-XB02-P0UMX-171054 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10744 | T16182-XB02-P0UMX-171055 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10745 | T16182-XB02-P0UMX-171056 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10746 | T16182-XB02-P0UMX-171057 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10747 | T16182-XB02-P0UMX-171058 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10748 | T16182-VE04-P0MPA-171101 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10749 | T16182-VE04-P0MPA-171102 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10750 | T16182-VE04-P0MPA-171103 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10751 | T16182-XB02-P0MPA-171104 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10752 | T16182-XB02-P0MPA-171105 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10753 | T16182-XB02-P0MPA-171106 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10754 | T16182-XB02-P0MPA-171113 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10755 | T16182-VK02-P0MPA-171117 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10756 | T16182-VE04-P0ULX-171201 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10757 | T16182-XB02-P0ULX-171202 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10758 | T16182-XB02-P0ULX-171203 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10759 | T16182-VE04-P0ULX-171221 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10760 | T16182-XB02-P0ULX-171222 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10761 | T16182-XB02-P0ULX-171223 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10762 | T16182-VE04-P0ULC-171301 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10763 | T16182-XB02-P0ULC-171302 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10764 | T16182-XB02-P0ULC-171303 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10765 | T16182-VK02-P0ULC-171308 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10766 | T16182-VK02-P0ULC-171309 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10767 | T16182-VE04-P0UNX-171401 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10768 | T16182-XB02-P0UNX-171402 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10769 | T16182-XB02-P0UNX-171410 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10770 | T16182-VE04-P0UEG-171501 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10771 | T16182-XB02-P0UEG-171502 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10772 | T16182-XB02-P0UEG-171504 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10773 | T16182-VE04-P0ULX-171601 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10774 | T16182-XB02-P0ULX-171602 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10775 | T16182-XB02-P0ULX-171603 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10776 | T16182-VK02-P0ULX-171604 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10777 | T16182-VE04-P0UEM-171701 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10778 | T16182-XB02-P0UEM-171702 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10779 | T16182-XB02-P0UEM-171708 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10780 | T16182-VK02-P0UEM-171711 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10781 | T16182-VE04-P0UHA-171801 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10782 | T16182-VE04-P0UHA-171802 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10783 | T16182-XB02-P0UHA-171803 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10784 | T16182-XB02-P0UHA-171804 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10785 | T16182-XB02-P0UHA-171805 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10786 | T16182-XB02-P0UHA-171806 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10787 | T16182-XB02-P0UHA-171807 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10788 | T16182-XB02-P0UHA-171815 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10789 | T16182-XB02-P0UHA-171816 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10790 | T16182-VE04-P0UHA-171819 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10791 | T16182-VE04-P8UTH-172001 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10792 | T16182-XB02-P8UTH-172003 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10793 | T16182-XB02-P8UTH-172004 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10794 | T16182-VK02-P8UTH-172005 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10795 | T16182-XB02-P8UTH-172007 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10796 | T16182-VK02-P8UTH-172008 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10797 | T16182-VE04-P8UTH-172011 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10798 | T16182-XB02-P8UTH-172012 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10799 | T16182-XB02-P8UTH-172013 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10800 | T16182-XB02-P0UAG-172100 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10801 | T16182-VE04-P0UAG-172101 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10802 | T16182-XB02-P0UAG-172102 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10803 | T16182-XB02-P0UAG-172108 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10804 | T16182-VK02-P0UAG-172109 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10805 | T16182-VE04-P0UAG-172151 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10806 | T16182-XB02-P0UAG-172162 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10807 | T16182-XB02-P0UAG-172168 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10808 | T16182-VK02-P0UAG-172170 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10809 | T16182-VE04-P0UBN-172201 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10810 | T16182-XB02-P0UBN-172202 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10811 | T16182-VK02-P0UBN-172203 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10812 | T16182-VE04-P0BAA-172401 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10813 | T16182-XB02-P0BAA-172402 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10814 | T16182-VK02-P0BAA-172403 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10815 | T16182-VE04-P0ULC-172501 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10816 | T16182-XB02-P0ULC-172502 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10817 | T16182-VK02-P0ULC-172503 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10818 | T16182-VE04-P0UGF-172521 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10819 | T16182-XB02-P0UGF-172522 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10820 | T16182-VK02-P0UGF-172523 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10821 | T16182-VE04-P0UGD-172541 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10822 | T16182-XB02-P0UGD-172542 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10823 | T16182-VK02-P0UGD-172543 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10824 | T16182-VE04-P0UGG-172561 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10825 | T16182-XB02-P0UGG-172562 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10826 | T16182-VK02-P0UGG-172563 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10827 | T16182-VE04-P0UAZ-172601 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10828 | T16182-XB02-P0UAZ-172602 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10829 | T16182-XB02-P0UAZ-172603 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10830 | T16182-XB02-P0UAZ-172608 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10831 | T16182-VK02-P0UAZ-172613 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10832 | T16182-VE04-P0UZT-172701 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10833 | T16182-XB02-P0UZT-172702 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10834 | T16182-XB02-P0UZT-172703 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10835 | T16182-VK02-P0UZT-172704 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10836 | T16182-VK02-P0UZT-172713 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10837 | T16182-XB02-P0UZT-172716 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10838 | T16182-VE04-P0GUC-172801 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10839 | T16182-XB02-P0GUC-172802 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10840 | T16182-VK02-P0GUC-172804 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10841 | T16182-VE04-P0UZA-172901 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10842 | T16182-XB02-P0UZA-172902 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10843 | T16182-XB02-P0UZA-172903 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10844 | T16182-VK02-P0UZA-172908 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10845 | T16182-VE04-P0UZT-173001 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10846 | T16182-XB02-P0UZT-173002 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10847 | T16182-XB02-P0UZT-173003 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10848 | T16182-VK02-P0UZT-173008 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10849 | T16182-XB02-P0UGF-173101 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10850 | T16182-XB02-P0UGF-173102 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10851 | T16182-VK02-P0UGF-173107 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10852 | T16182-XB02-P0UZJ-173202 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10853 | T16182-VK02-P0UZJ-173208 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10854 | T16182-VE04-P0GUB-173301 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10855 | T16182-XB02-P0GUB-173302 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10856 | T16182-XB02-P0GUB-173303 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10857 | T16182-VK02-P0GUB-173313 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10858 | T16182-VE04-P0GQB-173401 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10859 | T16182-UT01-P0GQB-173402 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10860 | T16182-UT01-P0GQB-173403 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10861 | T16182-UT01-P0GQB-173413 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10862 | T16182-VK02-P0GQB-173417 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10863 | T16182-XB02-P0UZK-173501 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10864 | T16182-VK02-P0UZK-173502 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10865 | T16182-VK02-P0UZK-173504 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10866 | T16182-XB02-P0UNX-171403 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10867 | T16182-XB02-P0GUC-172803 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10868 | T16182-VK02-P0UMX-171059 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10869 | T16182-VK02-P0UMX-171060 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10870 | T16182-VE04-P0ULX-172581 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10871 | T16182-XB02-P0ULX-172582 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10872 | T16182-XB02-P0ULX-172583 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10873 | T16182-XB02-P0ULX-172584 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10874 | T16182-XB02-P0ULX-172585 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10875 | T16182-XB02-P0UMX-171061 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10876 | T16182-XB02-P0UMX-171062 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10877 | T16182-XB02-P0UMX-171063 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10878 | T16182-VE04-P0GKC-173601 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10879 | T16182-XB02-P0GKC-173602 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10880 | T16182-XB02-P0GKC-173702 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10881 | T16182-VE04-P0GHC-173801 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10882 | T16182-XB02-P0GHC-173802 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10883 | T16182-VK02-P0UZJ-173209 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10884 | T16182-XB02-P0UZA-172904 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10885 | T16182-XB02-P0UZA-172911 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10886 | T16182-VK02-P0UZA-172912 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10887 | T16182-XB02-P0UZJ-173902 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10888 | T16182-VK02-P0UZJ-173903 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10889 | T16182-VK02-P0UZK-173503 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10890 | T16182-VK02-P0UZK-173505 | 2020-02-26 | DHI-ASBUILT-000010 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10891 | T16182-XG02-P0MKG-260034 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10892 | T16182-CY03-P0MKG-260032 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10893 | T16182-CY03-P0MKW-260031 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10894 | T16182-XG02-P0MKW-260033 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10895 | T16182-XH01-P6MKA-260004 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10896 | T16182-XH01-P7MKA-260007 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10897 | T16182-XJ00-P6MKA-260003 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10898 | T16182-XJ00-P7MKA-260006 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10899 | T16182-XK00-P6MKA-260005 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10900 | T16182-XK00-P7MKA-260008 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10901 | T16182-XL00-P0MKA-260035 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10902 | T16182-XN00-P0MKA-260036 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10903 | T16182-YD00-P0MKG-260014 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10904 | T16182-YD00-P0MKG-260015 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10905 | T16182-YD00-P0MKG-260016 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10906 | T16182-YD00-P0MKG-260017 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10907 | T16182-YD00-P0MKG-260018 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10908 | T16182-YD00-P0MKW-260001 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10909 | T16182-YD00-P0MKW-260002 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10910 | T16182-YD00-P0MKW-260011 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10911 | T16182-YD00-P0MKW-260012 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10912 | T16182-YD00-P0MKW-260013 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10913 | T16182-YT01-P0MKA-260019 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10914 | T16182-YT01-P0MKA-260020 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10915 | T16182-YV02-P0MKG-260022 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10916 | T16182-YV02-P0MKW-260021 | 2020-02-26 | DHI-ASBUILT-000011 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10917 | T16182-DA01-P0ZEN-020002 | 2020-02-26 | DHI-ASBUILT-000012 | AB | 0 | D | TRUE | FALSE | 2021-02-08_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/PDF/T16182-DA01-P0ZEN-020002_AB_0_NEW.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10918 | T16182-YF00-P0ZEN-167001 | 2020-02-26 | DHI-ASBUILT-000012 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10919 | T16182-XW03-P0MJ-110053 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10920 | T16182-XJ00-P0LBA-140101 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10921 | T16182-XJ00-P0LCM-140105 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10922 | T16182-XJ00-P0LBA-140201 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10923 | T16182-CC05-P0ZEN-180001 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10924 | T16182-CC05-P0ZEN-180002 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10925 | T16182-CC05-P0ZEN-180006 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10926 | T16182-CC05-P0ZEN-180008 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10927 | T16182-CC05-P0ZEN-180019 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10928 | T16182-CC05-P0ZEN-180020 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10929 | T16182-CC05-P0ZEN-180024 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10930 | T16182-CC05-P0ZEN-180025 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10931 | T16182-CC05-P0ZEN-180030 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10932 | T16182-CC05-P0ZEN-180033 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10933 | T16182-CC05-P0ZEN-180034 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10934 | T16182-CC05-P0ZEN-180035 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10935 | T16182-CC05-P0ZEN-180036 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10936 | T16182-CC05-P0ZEN-180037 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10937 | T16182-CC05-P0ZEN-180038 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10938 | T16182-CC05-P0ZEN-180039 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10939 | T16182-CC05-P0ZEN-180040 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10940 | T16182-CC05-P0ZEN-180041 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10941 | T16182-CC05-P0ZEN-180042 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10942 | T16182-CC05-P0ZEN-180043 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10943 | T16182-CC05-P0ZEN-180044 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10944 | T16182-CA00-P0UMA-180401 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10945 | T16182-CA00-P0UMA-180402 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10946 | T16182-CA00-P0UMA-180403 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10947 | T16182-CA00-P0UMA-180404 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10948 | T16182-CA00-P0UMA-180405 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10949 | T16182-CA00-P0UMA-180406 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10950 | T16182-CA00-P0UMA-180408 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10951 | T16182-CA01-P0UMA-180451 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10952 | T16182-CA01-P0UMA-180452 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10953 | T16182-CA01-P0UMA-180454 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10954 | T16182-CA03-P0UMA-180458 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10955 | T16182-CA03-P0UMA-180459 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10956 | T16182-CA03-P0UMA-180460 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10957 | T16182-CA03-P0UMA-180462 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10958 | T16182-CA03-P0UMA-180463 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10959 | T16182-CA03-P0UMA-180464 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10960 | T16182-CA03-P0UMA-180465 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10961 | T16182-CA03-P0UMA-180466 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10962 | T16182-CA03-P0UMA-180467 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10963 | T16182-CA03-P0UMA-180468 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10964 | T16182-CA03-P0UMA-180469 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10965 | T16182-CA05-P0UMA-180481 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10966 | T16182-CA05-P0UMA-180482 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10967 | T16182-CA06-P0UMA-180490 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10968 | T16182-CA06-P0UMA-180491 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10969 | T16182-CA06-P0UMA-180492 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10970 | T16182-CA06-P0BAT-180500 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10971 | T16182-CA00-P1BAT-180511 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10972 | T16182-CA03-P1BAT-180512 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10973 | T16182-CA03-P1BAT-180513 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10974 | T16182-CA06-P0UCB-180600 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10975 | T16182-CA00-P0UCB-180601 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10976 | T16182-CA00-P0UCB-180602 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10977 | T16182-CA00-P0UCB-180603 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10978 | T16182-CA00-P0UCB-180604 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10979 | T16182-CA00-P0UCB-180605 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10980 | T16182-CA00-P0UCB-180606 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10981 | T16182-CA00-P0UCB-180607 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10982 | T16182-CA00-P0UCB-180608 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10983 | T16182-CA00-P0UCB-180609 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10984 | T16182-CA00-P0UCB-180610 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10985 | T16182-CA00-P0UCB-180611 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10986 | T16182-CA00-P0UCB-180612 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10987 | T16182-CA00-P0UCB-180613 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10988 | T16182-CA00-P0UCB-180614 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10989 | T16182-CA01-P0UCB-180651 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10990 | T16182-CA01-P0UCB-180652 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10991 | T16182-CA01-P0UCB-180653 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10992 | T16182-CA01-P0UCB-180654 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10993 | T16182-CA01-P0UCB-180655 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10994 | T16182-CA01-P0UCB-180656 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10995 | T16182-CA01-P0UCB-180657 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10996 | T16182-CA01-P0UCB-180658 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10997 | T16182-CA01-P0UCB-180659 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10998 | T16182-CA01-P0UCB-180660 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
10999 | T16182-CA01-P0UCB-180661 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11000 | T16182-CA02-P0UCB-180664 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11001 | T16182-CA02-P0UCB-180665 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11002 | T16182-CA02-P0UCB-180666 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11003 | T16182-CA02-P0UCB-180667 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11004 | T16182-CA02-P0UCB-180668 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11005 | T16182-CA05-P0UCB-180681 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11006 | T16182-CA05-P0UCB-180682 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11007 | T16182-CA05-P0UCB-180683 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11008 | T16182-CA05-P0UCB-180684 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11009 | T16182-CA05-P0UCB-180685 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11010 | T16182-CA05-P0UCB-180686 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11011 | T16182-CA05-P0UCB-180687 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11012 | T16182-CA06-P0UBA-181000 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11013 | T16182-CA00-P0UBA-181001 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11014 | T16182-CA00-P0UBA-181002 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11015 | T16182-CA00-P0UBA-181003 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11016 | T16182-CA00-P0UBA-181004 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11017 | T16182-CA00-P0UBA-181005 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11018 | T16182-CA01-P0UBA-181051 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11019 | T16182-CA01-P0UBA-181052 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11020 | T16182-CA01-P0UBA-181053 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11021 | T16182-CA01-P0UBA-181054 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11022 | T16182-CA02-P0UBA-181055 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11023 | T16182-CA02-P0UBA-181056 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11024 | T16182-CA06-P0UBA-181100 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11025 | T16182-CA00-P0UBA-181101 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11026 | T16182-CA00-P0UBA-181102 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11027 | T16182-CA00-P0UBA-181103 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11028 | T16182-CA00-P0UBA-181104 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11029 | T16182-CA00-P0UBA-181105 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11030 | T16182-CA01-P0UBA-181151 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11031 | T16182-CA01-P0UBA-181152 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11032 | T16182-CA01-P0UBA-181153 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11033 | T16182-CA01-P0UBA-181154 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11034 | T16182-CA02-P0UBA-181155 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11035 | T16182-CA02-P0UBA-181156 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11036 | T16182-CA06-P0UBA-181200 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11037 | T16182-CA00-P0UBA-181201 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11038 | T16182-CA00-P0UBA-181202 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11039 | T16182-CA00-P0UBA-181203 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11040 | T16182-CA00-P0UBA-181204 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11041 | T16182-CA00-P0UBA-181205 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11042 | T16182-CA00-P0UBA-181206 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11043 | T16182-CA00-P0UBA-181207 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11044 | T16182-CA00-P0UBA-181208 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11045 | T16182-CA01-P0UBA-181251 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11046 | T16182-CA01-P0UBA-181252 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11047 | T16182-CA01-P0UBA-181253 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11048 | T16182-CA01-P0UBA-181254 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11049 | T16182-CA01-P0UBA-181255 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11050 | T16182-CA01-P0UBA-181256 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11051 | T16182-CA02-P0UBA-181257 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11052 | T16182-CA02-P0UBA-181258 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11053 | T16182-CA02-P0UBA-181259 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11054 | T16182-CA02-P0UBA-181260 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11055 | T16182-CA05-P0UBA-181281 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11056 | T16182-CA05-P0UBA-181282 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11057 | T16182-CA05-P0UBA-181284 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11058 | T16182-CA06-P0UBA-181300 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11059 | T16182-CA00-P0UBA-181301 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11060 | T16182-CA00-P0UBA-181302 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11061 | T16182-CA00-P0UBA-181303 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11062 | T16182-CA00-P0UBA-181304 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11063 | T16182-CA00-P0UBA-181305 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11064 | T16182-CA00-P0UBA-181306 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11065 | T16182-CA00-P0UBA-181307 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11066 | T16182-CA01-P0UBA-181351 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11067 | T16182-CA01-P0UBA-181352 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11068 | T16182-CA01-P0UBA-181353 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11069 | T16182-CA01-P0UBA-181354 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11070 | T16182-CA01-P0UBA-181355 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11071 | T16182-CA01-P0UBA-181356 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11072 | T16182-CA02-P0UBA-181357 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11073 | T16182-CA02-P0UBA-181358 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11074 | T16182-CA02-P0UBA-181359 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11075 | T16182-CA02-P0UBA-181360 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11076 | T16182-CA05-P0UBA-181381 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11077 | T16182-CA05-P0UBA-181382 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11078 | T16182-CA05-P0UBA-181384 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11079 | T16182-CA06-P0BAT-181800 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11080 | T16182-CA00-P6BAT-181811 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11081 | T16182-CA03-P6BAT-181812 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11082 | T16182-CA03-P6BAT-181813 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11083 | T16182-CA06-P0UGD-181900 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11084 | T16182-CA00-P0UGD-181901 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11085 | T16182-CA00-P0UGD-181902 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11086 | T16182-CA00-P0UGD-181903 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11087 | T16182-CA00-P0UGD-181904 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11088 | T16182-CA00-P0UGD-181905 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11089 | T16182-CA00-P0UGD-181906 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11090 | T16182-CA00-P0UGD-181908 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11091 | T16182-CA00-P0UGD-181909 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11092 | T16182-CA00-P0UGD-181910 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11093 | T16182-CA00-P0UGD-181911 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11094 | T16182-CA00-P0UGD-181912 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11095 | T16182-CA00-P0UGD-181913 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11096 | T16182-CA00-P0UGD-181914 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11097 | T16182-CA01-P0UGD-181951 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11098 | T16182-CA01-P0UGD-181952 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11099 | T16182-CA01-P0UGD-181953 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11100 | T16182-CA01-P0UGD-181954 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11101 | T16182-CA01-P0UGD-181955 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11102 | T16182-CA01-P0UGD-181956 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11103 | T16182-CA01-P0UGD-181957 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11104 | T16182-CA02-P0UGD-181958 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11105 | T16182-CA02-P0UGD-181959 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11106 | T16182-CA02-P0UGD-181960 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11107 | T16182-CA02-P0UGD-181961 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11108 | T16182-CA02-P0UGD-181962 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11109 | T16182-CA02-P0UGD-181963 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11110 | T16182-CA02-P0UGD-181964 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11111 | T16182-CA03-P0UGD-181965 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11112 | T16182-CA03-P0UGD-181966 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11113 | T16182-CA03-P0UGD-181967 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11114 | T16182-CA03-P0UGD-181968 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11115 | T16182-CA05-P0UGD-181981 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11116 | T16182-CA05-P0UGD-181982 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11117 | T16182-CA05-P0UGD-181983 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11118 | T16182-CA05-P0UGD-181984 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11119 | T16182-CA05-P0UGD-181985 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11120 | T16182-CA05-P0UGD-181986 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11121 | T16182-CA06-P0UST-182000 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11122 | T16182-CA00-P0UST-182001 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11123 | T16182-CA00-P0UST-182002 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11124 | T16182-CA00-P0UST-182003 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11125 | T16182-CA00-P0UST-182004 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11126 | T16182-CA00-P0UST-182005 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11127 | T16182-CA00-P0UST-182006 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11128 | T16182-CA01-P0UST-182051 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11129 | T16182-CA01-P0UST-182052 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11130 | T16182-CA01-P0UST-182053 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11131 | T16182-CA03-P0UST-182054 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11132 | T16182-CA03-P0UST-182055 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11133 | T16182-CA03-P0UST-182056 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11134 | T16182-CA02-P0UST-182058 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11135 | T16182-CA02-P0UST-182059 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11136 | T16182-CA02-P0UST-182060 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11137 | T16182-CA02-P0UST-182061 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11138 | T16182-CA03-P0UST-182062 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11139 | T16182-CA03-P0UST-182063 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11140 | T16182-CA05-P0UST-182081 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11141 | T16182-CA05-P0UST-182082 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11142 | T16182-CA05-P0UST-182083 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11143 | T16182-CA05-P0UST-182084 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11144 | T16182-CA05-P0UST-182085 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11145 | T16182-CA01-P0ULA-182151 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11146 | T16182-CA03-P0ULA-182152 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11147 | T16182-CA03-P0ULA-182153 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11148 | T16182-CA03-P0ULA-182154 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11149 | T16182-CA03-P0ULA-182155 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11150 | T16182-CA03-P0ULA-182157 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11151 | T16182-CA03-P0ULA-182160 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11152 | T16182-CA06-P0ULA-182190 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11153 | T16182-CA06-P0ULA-182191 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11154 | T16182-CA06-P0USG-182700 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11155 | T16182-CA00-P0USG-182701 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11156 | T16182-CA00-P0USG-182702 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11157 | T16182-CA00-P0USG-182703 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11158 | T16182-CA00-P0USG-182704 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11159 | T16182-CA01-P0USG-182751 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11160 | T16182-CA01-P0USG-182752 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11161 | T16182-CA01-P0USG-182753 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11162 | T16182-CA02-P0USG-182754 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11163 | T16182-CA02-P0USG-182755 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11164 | T16182-CA06-P0UTF-182800 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11165 | T16182-CA00-P0UTF-182801 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11166 | T16182-CA00-P0UTF-182802 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11167 | T16182-CA00-P0UTF-182803 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11168 | T16182-CA00-P0UTF-182804 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11169 | T16182-CA01-P0UTF-182851 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11170 | T16182-CA01-P0UTF-182852 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11171 | T16182-CA01-P0UTF-182853 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11172 | T16182-CA01-P0UTF-182854 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11173 | T16182-CA01-P0UTF-182855 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11174 | T16182-CA01-P0UTF-182856 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11175 | T16182-CA02-P0UTF-182857 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11176 | T16182-CA06-P0UYC-182900 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11177 | T16182-CA00-P0UYC-182901 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11178 | T16182-CA00-P0UYC-182902 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11179 | T16182-CA00-P0UYC-182903 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11180 | T16182-CA00-P0UYC-182904 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11181 | T16182-CA00-P0UYC-182905 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11182 | T16182-CA00-P0UYC-182906 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11183 | T16182-CA00-P0UYC-182907 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11184 | T16182-CA00-P0UYC-182908 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11185 | T16182-CA01-P0UYC-182951 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11186 | T16182-CA01-P0UYC-182952 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11187 | T16182-CA01-P0UYC-182953 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11188 | T16182-CA01-P0UYC-182954 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11189 | T16182-CA01-P0UYC-182955 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11190 | T16182-CA01-P0UYC-182956 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11191 | T16182-CA02-P0UYC-182957 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11192 | T16182-CA02-P0UYC-182958 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11193 | T16182-CA05-P0UYC-182981 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11194 | T16182-CA05-P0UYC-182982 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11195 | T16182-CA05-P0UYC-182983 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11196 | T16182-CA05-P0UYC-182984 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11197 | T16182-CA05-P0UYC-182985 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11198 | T16182-CA06-P0UYA-183100 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11199 | T16182-CA00-P0UYA-183101 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11200 | T16182-CA00-P0UYA-183102 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11201 | T16182-CA00-P0UYA-183103 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11202 | T16182-CA00-P0UYA-183104 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11203 | T16182-CA00-P0UYA-183105 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11204 | T16182-CA01-P0UYA-183151 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11205 | T16182-CA01-P0UYA-183152 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11206 | T16182-CA01-P0UYA-183153 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11207 | T16182-CA01-P0UYA-183154 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11208 | T16182-CA02-P0UYA-183155 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11209 | T16182-CA05-P0UYA-183181 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11210 | T16182-CA05-P0UYA-183182 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11211 | T16182-CA05-P0UYA-183183 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11212 | T16182-CA06-P0UYP-183200 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11213 | T16182-CA00-P0UYP-183201 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11214 | T16182-CA00-P0UYP-183202 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11215 | T16182-CA00-P0UYP-183203 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11216 | T16182-CA00-P0UYP-183204 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11217 | T16182-CA00-P0UYP-183205 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11218 | T16182-CA01-P0UYP-183251 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11219 | T16182-CA01-P0UYP-183252 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11220 | T16182-CA01-P0UYP-183253 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11221 | T16182-CA01-P0UYP-183254 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11222 | T16182-CA01-P0UYP-183255 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11223 | T16182-CA02-P0UYP-183256 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11224 | T16182-CA02-P0UYP-183257 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11225 | T16182-CA05-P0UYP-183281 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11226 | T16182-CA05-P0UYP-183282 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11227 | T16182-CA05-P0UYP-183283 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11228 | T16182-CA05-P0UYP-183284 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11229 | T16182-CA05-P0UYP-183285 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11230 | T16182-CA06-P0UYE-183300 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11231 | T16182-CA00-P0UYE-183301 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11232 | T16182-CA00-P0UYE-183302 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11233 | T16182-CA00-P0UYE-183303 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11234 | T16182-CA01-P0UYE-183351 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11235 | T16182-CA01-P0UYE-183352 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11236 | T16182-CA01-P0UYE-183353 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11237 | T16182-CA02-P0UYE-183354 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11238 | T16182-CA02-P0UYE-183355 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11239 | T16182-CA00-P0UTX-183361 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11240 | T16182-CA03-P0UTX-183371 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11241 | T16182-CA03-P0UTX-183372 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11242 | T16182-CA03-P0UTX-183373 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11243 | T16182-CA03-P0UTX-183375 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11244 | T16182-CA02-P0UTX-183377 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11245 | T16182-CA06-P0UTX-183390 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11246 | T16182-CA06-P0UYB-183500 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11247 | T16182-CA00-P0UYB-183501 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11248 | T16182-CA00-P0UYB-183502 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11249 | T16182-CA01-P0UYB-183551 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11250 | T16182-CA01-P0UYB-183552 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11251 | T16182-CA02-P0UYB-183553 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11252 | T16182-CA02-P0UYB-183554 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11253 | T16182-CA05-P0UYB-183581 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11254 | T16182-CA05-P0UYB-183582 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11255 | T16182-CA06-P0UYF-183600 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11256 | T16182-CA00-P0UYF-183601 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11257 | T16182-CA00-P0UYF-183602 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11258 | T16182-CA00-P0UYF-183603 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11259 | T16182-CA01-P0UYF-183651 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11260 | T16182-CA01-P0UYF-183652 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11261 | T16182-CA01-P0UYF-183653 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11262 | T16182-CA06-P0ULD-183900 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11263 | T16182-CA00-P0ULD-183902 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11264 | T16182-CA00-P0ULD-183903 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11265 | T16182-CA00-P0ULD-183904 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11266 | T16182-CA00-P0ULD-183905 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11267 | T16182-CA00-P0ULD-183906 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11268 | T16182-CA00-P0ULD-183908 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11269 | T16182-CA00-P0ULD-183909 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11270 | T16182-CA00-P0ULD-183910 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11271 | T16182-CA01-P0ULD-183951 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11272 | T16182-CA01-P0ULD-183952 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11273 | T16182-CA01-P0ULD-183953 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11274 | T16182-CA01-P0ULD-183954 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11275 | T16182-CA02-P0ULD-183955 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11276 | T16182-CA02-P0ULD-183956 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11277 | T16182-CA02-P0ULD-183957 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11278 | T16182-CA02-P0ULD-183958 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11279 | T16182-CA02-P0ULD-183959 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11280 | T16182-CA02-P0ULD-183960 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11281 | T16182-CA02-P0ULD-183961 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11282 | T16182-CA03-P0ULD-183962 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11283 | T16182-CA03-P0ULD-183963 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11284 | T16182-CA03-P0ULD-183964 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11285 | T16182-CA03-P0ULD-183965 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11286 | T16182-CA06-P0USR-184700 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11287 | T16182-CA00-P0USR-184701 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11288 | T16182-CA00-P0USR-184702 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11289 | T16182-CA03-P0USR-184751 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11290 | T16182-CA03-P0USR-184752 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11291 | T16182-CA06-P0QJA-184800 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11292 | T16182-CA00-P0QJA-184801 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11293 | T16182-CA00-P0QJA-184802 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11294 | T16182-CA00-P0QJA-184803 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11295 | T16182-CA01-P0QJA-184851 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11296 | T16182-CA01-P0QJA-184852 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11297 | T16182-CA01-P0QJA-184853 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11298 | T16182-CA02-P0QJA-184854 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11299 | T16182-CA06-P0UTG-184900 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11300 | T16182-CA00-P0UTG-184901 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11301 | T16182-CA00-P0UTG-184902 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11302 | T16182-CA00-P0UTG-184903 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11303 | T16182-CA01-P0UTG-184951 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11304 | T16182-CA01-P0UTG-184952 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11305 | T16182-CA01-P0UTG-184953 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11306 | T16182-CA02-P0UTG-184954 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11307 | T16182-CA03-P0UMY-185151 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11308 | T16182-CA03-P0UMY-185152 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11309 | T16182-CA03-P0UMY-185153 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11310 | T16182-CA03-P0UMY-185154 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11311 | T16182-CA03-P0UMY-185155 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11312 | T16182-CA03-P0UMY-185160 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11313 | T16182-CA03-P0UMY-185161 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11314 | T16182-CA03-P0UMY-185162 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11315 | T16182-CA03-P0UMY-185163 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11316 | T16182-CA03-P0UMY-185164 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11317 | T16182-CA03-P0UMY-185165 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11318 | T16182-CA03-P0UMY-185166 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11319 | T16182-CA03-P0UMY-185167 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11320 | T16182-CA03-P0UMY-185168 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11321 | T16182-CA03-P0UMY-185169 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11322 | T16182-CA03-P0UMY-185170 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11323 | T16182-CA03-P0UMY-185171 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11324 | T16182-CA03-P0UMY-185172 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11325 | T16182-CA03-P0UMY-185173 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11326 | T16182-CA03-P0UMY-185174 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11327 | T16182-CA03-P0UMY-185175 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11328 | T16182-CA03-P0UMY-185176 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11329 | T16182-CA03-P0UMY-185177 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11330 | T16182-CA03-P0UMY-185178 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11331 | T16182-CA06-P0UMY-185190 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11332 | T16182-CA06-P0UMY-185191 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11333 | T16182-CA06-P0UMY-185192 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11334 | T16182-CA00-P0GEN-185701 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11335 | T16182-CA01-P0GEN-185751 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11336 | T16182-CA06-P0GEN-185800 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11337 | T16182-CA00-P0GEN-185801 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11338 | T16182-CA00-P0GEN-185802 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11339 | T16182-CA00-P0GEN-185803 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11340 | T16182-CA01-P0GEN-185851 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11341 | T16182-CA01-P0GEN-185852 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11342 | T16182-CA01-P0GEN-185853 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11343 | T16182-CA02-P0GEN-185854 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11344 | T16182-CA06-P0UBA-186100 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11345 | T16182-CA00-P0UBA-186101 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11346 | T16182-CA00-P0UBA-186103 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11347 | T16182-CA00-P0UBA-186104 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11348 | T16182-CA01-P0UBA-186151 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11349 | T16182-CA01-P0UBA-186152 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11350 | T16182-CA01-P0UBA-186154 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11351 | T16182-CA02-P0UBA-186155 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11352 | T16182-CA02-P0UBA-186156 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11353 | T16182-CA07-P0ZEN-189000 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11354 | T16182-CA03-P0UMA-180471 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11355 | T16182-CA06-P0UGD-186600 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11356 | T16182-CA00-P0UGD-186601 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11357 | T16182-CA00-P0UGD-186602 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11358 | T16182-CA01-P0UGD-186651 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11359 | T16182-CA01-P0UGD-186652 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11360 | T16182-CA06-P0UBA-186800 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11361 | T16182-CA00-P0UBA-186801 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11362 | T16182-CA00-P0UBA-186802 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11363 | T16182-CA00-P0UBA-186803 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11364 | T16182-CA01-P0UBA-186851 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11365 | T16182-CA01-P0UBA-186852 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11366 | T16182-CA01-P0UBA-186853 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11367 | T16182-CA02-P0UBA-186854 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11368 | T16182-CA02-P0UBA-186855 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11369 | T16182-CA05-P0UYF-183681 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11370 | T16182-CA05-P0UYF-183682 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11371 | T16182-CA00-P0UYF-183604 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11372 | T16182-CA02-P0UYF-183654 | 2020-02-27 | DHI-ASBUILT-000013 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11373 | T16182-XS00-P0GCF-130001 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11374 | T16182-YD00-P0GCF-130002 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11375 | T16182-XG07-P0GCF-130003 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11376 | T16182-XG02-P0GCF-130004 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11377 | T16182-XW03-P0GCF-130005 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11378 | T16182-YD00-P0GCF-130006 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11379 | T16182-YR05-P0GCF-130007 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11380 | T16182-XN00-P0GCF-130008 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11381 | T16182-YL00-P0GCF-130009 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11382 | T16182-YU02-P0GCF-130010 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11383 | T16182-YF02-P0GCF-130011 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11384 | T16182-YK09-P0GCF-130012 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11385 | T16182-XH01-P0GCF-130013 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11386 | T16182-YT01-P0GCF-130014 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11387 | T16182-YE00-P0GCF-130015 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11388 | T16182-YK00-P0GCF-130016 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11389 | T16182-YU03-P0GCF-130017 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11390 | T16182-YF00-P0GCF-130018 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11391 | T16182-YD00-P0GCF-130019 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11392 | T16182-YL01-P0GCF-130035 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11393 | T16182-XB02-P0GCF-130042 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11394 | T16182-CV03-P0GCF-130055 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11395 | T16182-XS00-P0GNR-130101 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11396 | T16182-XG07-P0GNR-130102 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11397 | T16182-XG02-P0GNR-130103 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11398 | T16182-XW03-P0GNR-130104 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11399 | T16182-XN00-P0GNR-130105 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11400 | T16182-YL00-P0GNR-130106 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11401 | T16182-XN00-P0GNR-130107 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11402 | T16182-YT01-P0GNR-130108 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11403 | T16182-XS00-P0LD-130201 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11404 | T16182-YD00-P0LD-130202 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11405 | T16182-XG07-P0LD-130203 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11406 | T16182-XG02-P0LD-130204 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11407 | T16182-XW03-P0LD-130205 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11408 | T16182-YD00-P0LD-130206 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11409 | T16182-YR05-P0LD-130207 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11410 | T16182-XN00-P0LD-130208 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11411 | T16182-YL00-P0LD-130209 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11412 | T16182-YU02-P0LD-130210 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11413 | T16182-YF02-P0LD-130211 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11414 | T16182-YK09-P0LD-130212 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11415 | T16182-XH01-P0LD-130213 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11416 | T16182-YT01-P0LD-130214 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11417 | T16182-YE00-P0LD-130215 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11418 | T16182-YK00-P0LD-130216 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11419 | T16182-YU03-P0LD-130217 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11420 | T16182-YF00-P0LD-130218 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11421 | T16182-XS00-P0QC-130301 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11422 | T16182-YD00-P0QC-130302 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11423 | T16182-XG02-P0QC-130303 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11424 | T16182-XW03-P0QC-130304 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11425 | T16182-YL00-P0QC-130305 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11426 | T16182-YR05-P0QC-130306 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11427 | T16182-YT01-P0QC-130307 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11428 | T16182-YU03-P0QC-130308 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11429 | T16182-YF00-P0QC-130309 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11430 | T16182-XS00-P0QU-130401 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11431 | T16182-YD00-P0QU-130402 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11432 | T16182-XG02-P0QU-130403 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11433 | T16182-YL00-P0QU-130404 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11434 | T16182-YT01-P0QU-130405 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11435 | T16182-YU03-P0QU-130406 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11436 | T16182-YF00-P0QU-130407 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11437 | T16182-XW01-P0STG-130501 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11438 | T16182-YD00-P0STG-130502 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11439 | T16182-XL00-P0STG-130503 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11440 | T16182-YT10-P0MKY-290010 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11441 | T16182-YD00-P0GK-130601 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11442 | T16182-YS01-P0GK-130602 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11443 | T16182-CV03-P0LD-130219 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11444 | T16182-XB02-P0LD-130220 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11445 | T16182-YM03-P0LD-130221 | 2020-03-03 | DHI-ASBUILT-000014 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11446 | T16182-XK00-P0MAG-123027 | 2020-03-03 | DHI-TRANSMIT-002833 | IFC | 0 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=032497b7-0d3c-4c4a-a9e5-db0d3fde871b | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11447 | T16182-YE00-P0ZEN-152766 | 2020-03-06 | DHI-TRANSMIT-002847 | IFC | 3 | D | TRUE | FALSE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=b1113ec3-bd81-4b24-820b-2fdca751cff3 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11448 | T16182-YQ01-P0ZEN-152333 | 2020-03-06 | DHI-TRANSMIT-002847 | IFC | 0 | DR | TRUE | TRUE |  | http://dheim.doosanheavy.com/EDMSOpenPopup.jsp?r_object_id=85b66b6d-5fe8-42b3-8d8f-0747f917b678 | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11449 | T16182-YR02-P0ZEN-150001 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11450 | T16182-YL06-P0ZEN-150101 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11451 | T16182-YU02-P0ZEN-150201 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11452 | T16182-YU02-P0ZEN-150202 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11453 | T16182-YU02-P0ZEN-150211 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11454 | T16182-YU02-P0ZEN-150212 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11455 | T16182-YU05-P0ZEN-150221 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11456 | T16182-YT10-P0ZEN-150301 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11457 | T16182-YT10-P0ZEN-150302 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11458 | T16182-YT10-P0ZEN-150303 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11459 | T16182-YT10-P0ZEN-150304 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11460 | T16182-YT10-P0ZEN-150305 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11461 | T16182-YT10-P0ZEN-150306 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11462 | T16182-YT10-P0ZEN-150311 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11463 | T16182-YT10-P0ZEN-150312 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11464 | T16182-YT10-P0ZEN-150313 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11465 | T16182-YT10-P0ZEN-150314 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11466 | T16182-YF00-P0BA-150401 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11467 | T16182-YF00-P0BB-150402 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11468 | T16182-YF00-P0BB-150403 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11469 | T16182-YF00-P0BA-150404 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11470 | T16182-YD00-P0UCA-150501 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11471 | T16182-YD00-P0UBA-150502 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11472 | T16182-YD00-P0UBA-150503 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11473 | T16182-YD00-P0UBA-150504 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11474 | T16182-YD00-P0UBA-150505 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11475 | T16182-YD00-P0UBA-150506 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11476 | T16182-YD00-P0UBA-150508 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11477 | T16182-YT10-P0BAT-150601 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11478 | T16182-YT01-P0BAT-150611 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11479 | T16182-YD00-P0BAT-150621 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11480 | T16182-YU03-P0BAT-150631 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11481 | T16182-YT10-P0BBT-150651 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11482 | T16182-YT01-P0BBT-150661 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11483 | T16182-YD00-P0BBT-150671 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11484 | T16182-YU03-P0BBT-150681 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11485 | T16182-YT10-P0BAA-150701 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11486 | T16182-YT01-P0BAC-150711 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11487 | T16182-YD00-P0BAC-150721 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11488 | T16182-YU03-P0BAC-150731 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11489 | T16182-YT01-P0BAA-150751 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11490 | T16182-YT01-P0BAA-150752 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11491 | T16182-YD00-P0BAA-150761 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11492 | T16182-YD00-P0BAA-150762 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11493 | T16182-YD00-P0BAA-150766 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11494 | T16182-YD00-P0BAA-150767 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11495 | T16182-YD00-P0BAA-150771 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11496 | T16182-YD00-P0BAA-150772 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11497 | T16182-YD00-P0BAA-150776 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11498 | T16182-YD00-P0BAA-150777 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11499 | T16182-YD00-P0BAA-150781 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11500 | T16182-YD00-P0BAA-150782 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11501 | T16182-YT01-P0BB-150801 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11502 | T16182-YU02-P0BB-150811 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11503 | T16182-YD00-P0BB-150821 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11504 | T16182-YU03-P0BB-150831 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11505 | T16182-YU03-P0BB-150836 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11506 | T16182-YT01-P0BF-150901 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11507 | T16182-YT01-P0BF-150902 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11508 | T16182-YT01-P0BF-150903 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11509 | T16182-YU02-P0BFA-150911 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11510 | T16182-YU02-P0BFA-150912 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11511 | T16182-YU02-P0BFA-150913 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11512 | T16182-YU02-P0BFA-150914 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11513 | T16182-YU02-P0BFA-150915 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11514 | T16182-YU02-P0BFA-150916 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11515 | T16182-YU02-P0BFA-150917 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11516 | T16182-YU02-P0BFA-150918 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11517 | T16182-YD00-P0BF-150931 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11518 | T16182-YD00-P0BF-150932 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11519 | T16182-YD00-P0BF-150933 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11520 | T16182-YD00-P0BF-150934 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11521 | T16182-YD00-P0BF-150935 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11522 | T16182-YD00-P0BF-150936 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11523 | T16182-YD00-P0BF-150937 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11524 | T16182-YD00-P0BF-150938 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11525 | T16182-YD00-P0BF-150939 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11526 | T16182-YD00-P0BF-150940 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11527 | T16182-YU03-P0BFA-150951 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11528 | T16182-YU03-P0BFA-150952 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11529 | T16182-YU03-P0BFA-150953 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11530 | T16182-YU03-P0BFA-150954 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11531 | T16182-YU03-P0BFA-150955 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11532 | T16182-YU03-P0BFA-150956 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11533 | T16182-YU03-P0BFA-150957 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11534 | T16182-YU03-P0BFA-150958 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11535 | T16182-YT10-P0BT-151001 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11536 | T16182-YT01-P0BT-151011 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11537 | T16182-YU02-P0BT-151021 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11538 | T16182-YU02-P0BT-151026 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11539 | T16182-YU02-P0BT-151031 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11540 | T16182-YD00-P0BT-151041 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11541 | T16182-YD00-P0BT-151046 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11542 | T16182-YD00-P0BT-151051 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11543 | T16182-YU03-P0BT-151061 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11544 | T16182-YU03-P0BT-151066 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11545 | T16182-YU03-P0BT-151071 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11546 | T16182-YT01-P0CHB-151101 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11547 | T16182-YD00-P0CHB-151111 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11548 | T16182-YD00-P0CHB-151112 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11549 | T16182-YU03-P0CHB-151121 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11550 | T16182-YU03-P0CHB-151122 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11551 | T16182-YD00-P0CHB-151131 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11552 | T16182-YT01-P0CFA-151161 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11553 | T16182-YD00-P0CFA-151171 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11554 | T16182-YU03-P0CFA-151181 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11555 | T16182-YQ02-P0ZEN-152001 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11556 | T16182-DE00-P0ZEN-152002 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11557 | T16182-YD16-P0ZEN-152003 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11558 | T16182-YD04-P0ZEN-152004 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11559 | T16182-YD04-P0ZEN-152005 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11560 | T16182-YD04-P0ZEN-152006 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11561 | T16182-YD04-P0ZEN-152007 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11562 | T16182-YD04-P0ZEN-152008 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11563 | T16182-YD04-P0ZEN-152009 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11564 | T16182-YD04-P0ZEN-152010 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11565 | T16182-YD04-P0ZEN-152011 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11566 | T16182-YD04-P0ZEN-152012 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11567 | T16182-YD04-P0ZEN-152013 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11568 | T16182-YD04-P0ZEN-152014 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11569 | T16182-YD04-P0ZEN-152015 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11570 | T16182-YB03-P0ZEN-152052 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11571 | T16182-YQ01-P0ZEN-152201 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11572 | T16182-DE00-P0ZEN-152202 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11573 | T16182-YT10-P0ZEN-152203 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11574 | T16182-YT10-P0ZEN-152204 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11575 | T16182-YT10-P0ZEN-152205 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11576 | T16182-YT10-P0ZEN-152206 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11577 | T16182-YT10-P0ZEN-152207 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11578 | T16182-YT10-P0ZEN-152208 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11579 | T16182-YT10-P0ZEN-152209 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11580 | T16182-YT10-P0ZEN-152210 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11581 | T16182-YT10-P0ZEN-152211 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11582 | T16182-YT10-P0ZEN-152212 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11583 | T16182-YT10-P0ZEN-152213 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11584 | T16182-YT10-P0ZEN-152214 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11585 | T16182-YT10-P0ZEN-152215 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11586 | T16182-YT10-P0ZEN-152216 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11587 | T16182-YT10-P0ZEN-152217 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11588 | T16182-YT10-P0ZEN-152218 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11589 | T16182-YT10-P0ZEN-152219 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11590 | T16182-YT10-P0ZEN-152220 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11591 | T16182-YT10-P0ZEN-152221 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11592 | T16182-YT10-P0ZEN-152222 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11593 | T16182-YT10-P0ZEN-152223 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11594 | T16182-YT10-P0ZEN-152224 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11595 | T16182-YT10-P0ZEN-152225 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11596 | T16182-YT10-P0ZEN-152226 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11597 | T16182-YT10-P0ZEN-152229 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11598 | T16182-YQ01-P0ZEN-152301 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11599 | T16182-YQ01-P0ZEN-152302 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11600 | T16182-YQ01-P0ZEN-152303 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11601 | T16182-YQ01-P0ZEN-152304 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11602 | T16182-YQ01-P0ZEN-152305 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11603 | T16182-YQ01-P0ZEN-152306 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11604 | T16182-YQ01-P0ZEN-152307 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11605 | T16182-YQ01-P0ZEN-152308 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11606 | T16182-YQ01-P0ZEN-152309 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11607 | T16182-YQ01-P0ZEN-152310 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11608 | T16182-YQ01-P0ZEN-152311 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11609 | T16182-YQ01-P0ZEN-152312 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11610 | T16182-YQ01-P0ZEN-152313 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11611 | T16182-YQ01-P0ZEN-152314 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11612 | T16182-YQ01-P0ZEN-152315 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11613 | T16182-YQ01-P0ZEN-152316 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11614 | T16182-YQ01-P0ZEN-152317 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11615 | T16182-YQ01-P0ZEN-152318 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11616 | T16182-YQ01-P0ZEN-152319 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11617 | T16182-YQ01-P0ZEN-152320 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11618 | T16182-YQ01-P0ZEN-152321 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11619 | T16182-YQ01-P0ZEN-152322 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11620 | T16182-YQ01-P0ZEN-152323 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11621 | T16182-YQ01-P0ZEN-152324 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11622 | T16182-YQ01-P0ZEN-152327 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11623 | T16182-YB11-P0ZEN-152401 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11624 | T16182-YB11-P0ZEN-152402 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11625 | T16182-YB11-P0ZEN-152403 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11626 | T16182-YB11-P0ZEN-152404 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11627 | T16182-YB11-P0ZEN-152405 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11628 | T16182-YB11-P0ZEN-152406 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11629 | T16182-YB11-P0ZEN-152407 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11630 | T16182-YB11-P0ZEN-152408 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11631 | T16182-YB11-P0ZEN-152409 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11632 | T16182-YB11-P0ZEN-152411 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11633 | T16182-YB11-P0ZEN-152414 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11634 | T16182-YB11-P0ZEN-152415 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11635 | T16182-YB11-P0ZEN-152418 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11636 | T16182-YB11-P0ZEN-152419 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11637 | T16182-YB11-P0ZEN-152421 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11638 | T16182-YB11-P0ZEN-152422 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11639 | T16182-YB11-P0ZEN-152427 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11640 | T16182-YE04-P0BAU-152501 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11641 | T16182-DE00-P0BAU-152502 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11642 | T16182-YT10-P0BAU-152503 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11643 | T16182-YE03-P0BAU-152504 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11644 | T16182-YE03-P0BAU-152505 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11645 | T16182-YE03-P0BAU-152506 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11646 | T16182-YE03-P0BAU-152507 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11647 | T16182-YE03-P6BAU-152508 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11648 | T16182-YE03-P7BAU-152509 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11649 | T16182-YE03-P0BAU-152510 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11650 | T16182-YE03-P0BAU-152511 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11651 | T16182-YE03-P0BAU-152512 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11652 | T16182-YE03-P0BAU-152513 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11653 | T16182-YE03-P0BAU-152514 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11654 | T16182-YE03-P0BAU-152515 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11655 | T16182-YE03-P0BAU-152516 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11656 | T16182-YE03-P0BAU-152517 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11657 | T16182-YE03-P0BAU-152518 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11658 | T16182-YE03-P0BAU-152519 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11659 | T16182-YE03-P0BAU-152520 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11660 | T16182-YE03-P0BAU-152521 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11661 | T16182-YE03-P0BAU-152522 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11662 | T16182-YE03-P0BAU-152523 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11663 | T16182-YE03-P0BAU-152524 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11664 | T16182-YE03-P0BAU-152525 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11665 | T16182-YE03-P0BAU-152526 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11666 | T16182-YE03-P0BAU-152528 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11667 | T16182-YE03-P0BAU-152529 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11668 | T16182-YE03-P0BAU-152530 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11669 | T16182-YE03-P0BAU-152531 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11670 | T16182-YE03-P0BAU-152532 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11671 | T16182-YE03-P0BAU-152533 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11672 | T16182-YE03-P0BAU-152534 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11673 | T16182-YE03-P0BAU-152535 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11674 | T16182-YE01-P0BAU-152600 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11675 | T16182-YE01-P0BAU-152601 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11676 | T16182-YE01-P0BAU-152602 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11677 | T16182-YE01-P0BAU-152603 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11678 | T16182-YE01-P0BAU-152608 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11679 | T16182-YE01-P0BAU-152609 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11680 | T16182-YE01-P0BAU-152614 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11681 | T16182-YE01-P0BAU-152620 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11682 | T16182-YE01-P0BAU-152621 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11683 | T16182-DE00-P0ZEN-152701 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11684 | T16182-DE00-P0ZEN-152702 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11685 | T16182-YE00-P0ZEN-152705 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11686 | T16182-YE00-P0ZEN-152706 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11687 | T16182-YE00-P0ZEN-152707 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11688 | T16182-YE00-P0ZEN-152708 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11689 | T16182-YE00-P0ZEN-152709 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11690 | T16182-YE00-P0ZEN-152710 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11691 | T16182-YE00-P0ZEN-152711 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11692 | T16182-YE00-P0ZEN-152715 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11693 | T16182-YE00-P0ZEN-152716 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11694 | T16182-YE00-P0ZEN-152717 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11695 | T16182-YE00-P0ZEN-152718 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11696 | T16182-YE00-P0ZEN-152719 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11697 | T16182-YE00-P0ZEN-152720 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11698 | T16182-YE00-P0ZEN-152721 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11699 | T16182-YE00-P0ZEN-152722 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11700 | T16182-YE00-P0ZEN-152724 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11701 | T16182-YE00-P0ZEN-152725 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11702 | T16182-YE00-P0ZEN-152726 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11703 | T16182-YE00-P0ZEN-152727 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11704 | T16182-YE00-P0ZEN-152728 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11705 | T16182-YE00-P0ZEN-152729 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11706 | T16182-YE00-P0ZEN-152730 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11707 | T16182-YE00-P0ZEN-152731 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11708 | T16182-YE00-P0ZEN-152732 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11709 | T16182-YE00-P0ZEN-152733 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11710 | T16182-YE00-P0ZEN-152735 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11711 | T16182-YE00-P0ZEN-152736 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11712 | T16182-YE00-P0ZEN-152750 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11713 | T16182-YE00-P0ZEN-152751 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11714 | T16182-YE00-P0ZEN-152752 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11715 | T16182-YE00-P0ZEN-152753 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11716 | T16182-YE00-P0ZEN-152754 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11717 | T16182-YE00-P0ZEN-152755 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11718 | T16182-YE00-P0ZEN-152756 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11719 | T16182-YE00-P0ZEN-152757 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11720 | T16182-YE00-P0ZEN-152758 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11721 | T16182-YE00-P0ZEN-152759 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11722 | T16182-YE00-P0ZEN-152760 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11723 | T16182-YE00-P0ZEN-152761 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11724 | T16182-YE00-P0ZEN-152762 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11725 | T16182-YE00-P0ZEN-152763 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11726 | T16182-YE00-P0ZEN-152764 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11727 | T16182-YE00-P0ZEN-152765 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11728 | T16182-YE00-P0ZEN-152766 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11729 | T16182-YE00-P0ZEN-152767 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11730 | T16182-YE00-P0ZEN-152768 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11731 | T16182-YE00-P0ZEN-152769 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11732 | T16182-YE00-P0ZEN-152770 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11733 | T16182-YE00-P0ZEN-152771 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11734 | T16182-YR02-P0ZEN-152801 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11735 | T16182-YT10-P0ZEN-152810 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11736 | T16182-DE00-P0ZEN-152820 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11737 | T16182-YD00-P0ZEN-152822 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11738 | T16182-DE00-P0ZEN-152830 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11739 | T16182-DE00-P0ZEN-152840 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11740 | T16182-YL16-P0ZEN-152850 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11741 | T16182-YL16-P0ZEN-152860 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11742 | T16182-DE00-P0ZEN-152870 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11743 | T16182-DE00-P0CY-154001 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11744 | T16182-YU02-P0CYA-154011 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11745 | T16182-YU02-P0CYM-154013 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11746 | T16182-YQ03-P0CY-154021 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11747 | T16182-YQ08-P0CY-154031 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11748 | T16182-YQ08-P0CY-154032 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11749 | T16182-YQ08-P0CY-154033 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11750 | T16182-YQ08-P0CY-154034 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11751 | T16182-YQ08-P0CY-154035 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11752 | T16182-YQ08-P0CY-154036 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11753 | T16182-YQ08-P0CY-154037 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11754 | T16182-YQ08-P0CY-154038 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11755 | T16182-YQ08-P0CY-154039 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11756 | T16182-YQ08-P0CY-154040 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11757 | T16182-YQ08-P0CY-154041 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11758 | T16182-YQ08-P0CY-154042 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11759 | T16182-YQ08-P0CY-154044 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11760 | T16182-YQ08-P0CY-154045 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11761 | T16182-YQ08-P0CY-154049 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11762 | T16182-YQ08-P0CY-154051 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11763 | T16182-YQ08-P0CY-154052 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11764 | T16182-YD00-P0BAT-150626 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11765 | T16182-YU03-P0BAT-150636 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11766 | T16182-YU02-P0BB-150812 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11767 | T16182-YU02-P0BB-150813 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11768 | T16182-YU02-P0BB-150814 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11769 | T16182-YU02-P0BB-150815 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11770 | T16182-YU02-P0BB-150816 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11771 | T16182-YE03-P0BAU-152536 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11772 | T16182-YE03-P0BAU-152537 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11773 | T16182-YE03-P0BAU-152538 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11774 | T16182-DE00-P0ZEN-152823 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11775 | T16182-YE03-P0BAU-152539 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11776 | T16182-YE03-P0BAU-152527 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11777 | T16182-YE01-P0BAU-152606 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11778 | T16182-YD04-P0ZEN-152016 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11779 | T16182-YD04-P0ZEN-152017 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11780 | T16182-YD04-P0ZEN-152018 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11781 | T16182-YD04-P0ZEN-152019 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11782 | T16182-YT10-P0ZEN-152230 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11783 | T16182-YQ01-P0ZEN-152328 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11784 | T16182-YB11-P0ZEN-152428 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11785 | T16182-YT10-P0ZEN-152231 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11786 | T16182-YQ01-P0ZEN-152329 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11787 | T16182-YT10-P0ZEN-152232 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11788 | T16182-YT10-P0ZEN-152233 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11789 | T16182-YQ01-P0ZEN-152330 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11790 | T16182-YQ01-P0ZEN-152331 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11791 | T16182-YT10-P0ZEN-152234 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11792 | T16182-YQ01-P0ZEN-152332 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11793 | T16182-YE03-P0BAU-152540 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11794 | T16182-YE00-P0ZEN-152791 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11795 | T16182-YE00-P0ZEN-152792 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11796 | T16182-YE00-P0ZEN-152793 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11797 | T16182-YE00-P0ZEN-152794 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11798 | T16182-YE00-P0ZEN-152795 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11799 | T16182-YQ08-P0CY-154053 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11800 | T16182-YT01-P0ASS-155001 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11801 | T16182-YT10-P0ASR-155011 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11802 | T16182-YT10-P0ASR-155012 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11803 | T16182-YT10-P0ASR-155014 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11804 | T16182-YD04-P0ZEN-152020 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11805 | T16182-YT10-P0ASR-155013 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11806 | T16182-YQ01-P0ZEN-152333 | 2020-03-06 | DHI-ASBUILT-000015 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11807 | T16182-XG02-P0LAA-110009 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11808 | T16182-YT01-P0QJA-110503 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11809 | T16182-YD00-P0QJA-110502 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11810 | T16182-XS00-P0QJA-110500 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11811 | T16182-XG02-P0QJA-110012 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11812 | T16182-YD00-P0STG-130502 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11813 | T16182-XW01-P0STG-130501 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11814 | T16182-XL00-P0STG-130503 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11815 | T16182-XB02-P0ULX-172583 | 2020-03-06 | DHI-ASBUILT-000016 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11816 | T16182-XG02-P0GKB-120001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11817 | T16182-XG02-P0GKC-120002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11818 | T16182-XG02-P0SCA-120004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11819 | T16182-XG02-P0SCA-120005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11820 | T16182-XG02-P0SCA-120006 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11821 | T16182-XG02-P0EK-120007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11822 | T16182-XG02-P0GM-120008 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11823 | T16182-XS00-P0GKS-120012 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11824 | T16182-XW03-P0GKS-120013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11825 | T16182-XG07-P0SCA-120014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11826 | T16182-XS00-P0SCA-120015 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11827 | T16182-XS00-P0SCA-120016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11828 | T16182-XW03-P0SCA-120017 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11829 | T16182-XG07-P0EKG-120018 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11830 | T16182-XS00-P0EKG-120019 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11831 | T16182-XS00-P0EKG-120020 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11832 | T16182-XW03-P0EKG-120021 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11833 | T16182-XS00-P0GM-120022 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11834 | T16182-XS00-P0GM-120023 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11835 | T16182-XG07-P0ZEN-120050 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11836 | T16182-XS00-P0GKS-120051 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11837 | T16182-YD00-P0MBA-121001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11838 | T16182-YL25-P0MBA-121002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11839 | T16182-XG02-P0MBA-121003 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11840 | T16182-XG02-P1MBH-110013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11841 | T16182-XW01-P0MBA-121004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11842 | T16182-XW01-P0MBA-121005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11843 | T16182-XW01-P0MBA-121006 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11844 | T16182-XB00-P0MBA-121007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11845 | T16182-XJ00-P0MBA-121008 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11846 | T16182-YK08-P0MBA-121009 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11847 | T16182-DM02-P0MBA-121010 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11848 | T16182-XS00-P0MBA-121011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11849 | T16182-YU02-P0MBA-121012 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11850 | T16182-YT01-P0MBA-121013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11851 | T16182-YL25-P0MBA-121014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11852 | T16182-XW01-P0MBA-121015 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11853 | T16182-YL06-P0MBA-121016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11854 | T16182-YU05-P0MBA-121017 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11855 | T16182-YU02-P0MBA-121018 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11856 | T16182-YB03-P0MBA-121019 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11857 | T16182-YS00-P0MBA-121020 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11858 | T16182-YD02-P0MBA-121021 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11859 | T16182-YL01-P0MBA-121022 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11860 | T16182-YT01-P0MBA-121023 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11861 | T16182-YL25-P0MBA-121024 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11862 | T16182-YL01-P0MBA-121025 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11863 | T16182-XS01-P0MBA-121026 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11864 | T16182-XS01-P0MBA-121027 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11865 | T16182-YL01-P0MBA-121028 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11866 | T16182-YS00-P0MBA-121029 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11867 | T16182-YT01-P0MBA-121030 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11868 | T16182-YR05-P0MBA-121031 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11869 | T16182-YD05-P0MBA-121032 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11870 | T16182-XS01-P0MBA-121033 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11871 | T16182-XS01-P0MBA-121034 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11872 | T16182-XS01-P0MBA-121035 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11873 | T16182-VN01-P0MBA-121044 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11874 | T16182-CQ02-P0LB-122001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11875 | T16182-DF04-P0LB-122003 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11876 | T16182-DF04-P0LB-122004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11877 | T16182-DF04-P0LB-122005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11878 | T16182-UE00-P0LB-122007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11879 | T16182-UE00-P0LB-122008 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11880 | T16182-UE00-P0LB-122009 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11881 | T16182-UE00-P0LB-122010 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11882 | T16182-UE00-P0LB-122011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11883 | T16182-UE00-P0LB-122012 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11884 | T16182-UE00-P0LB-122013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11885 | T16182-UE00-P0LB-122014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11886 | T16182-VN03-P0LB-122015 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11887 | T16182-XB02-P0LB-122016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11888 | T16182-XB02-P0LB-122017 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11889 | T16182-XB02-P0LB-122018 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11890 | T16182-XB02-P0LB-122019 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11891 | T16182-XB02-P0LB-122020 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11892 | T16182-XG01-P0LB-122021 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11893 | T16182-XG02-P0LB-122022 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11894 | T16182-XG02-P0LB-122023 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11895 | T16182-XH01-P0LB-122024 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11896 | T16182-XH01-P0LB-122025 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11897 | T16182-XH01-P0LB-122026 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11898 | T16182-XJ00-P0LB-122027 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11899 | T16182-XJ00-P0LB-122028 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11900 | T16182-XJ00-P0LB-122029 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11901 | T16182-XL00-P0LB-122030 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11902 | T16182-XL00-P0LB-122031 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11903 | T16182-XN00-P0LB-122032 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11904 | T16182-XN00-P0LB-122033 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11905 | T16182-XN00-P0LB-122034 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11906 | T16182-XS00-P0LB-122035 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11907 | T16182-XS00-P0LB-122037 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11908 | T16182-XV00-P0LB-122038 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11909 | T16182-XV00-P0LB-122039 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11910 | T16182-CN00-P0LB-122040 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11911 | T16182-XW01-P0LB-122041 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11912 | T16182-YT01-P0LB-122042 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11913 | T16182-YD00-P0LB-122044 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11914 | T16182-XW01-P0LB-122045 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11915 | T16182-XW01-P0LB-122046 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11916 | T16182-YB03-P0LB-122047 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11917 | T16182-YB03-P0LB-122048 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11918 | T16182-YD00-P0LB-122049 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11919 | T16182-YD00-P0LB-122050 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11920 | T16182-YT01-P0LB-122051 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11921 | T16182-YD00-P0LB-122052 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11922 | T16182-YD00-P0LB-122053 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11923 | T16182-YD00-P0LB-122054 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11924 | T16182-YD00-P0LB-122055 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11925 | T16182-YD00-P0LB-122056 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11926 | T16182-YD00-P0LB-122057 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11927 | T16182-YD00-P0LB-122058 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11928 | T16182-YD05-P0LB-122059 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11929 | T16182-YT01-P0LB-122060 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11930 | T16182-XW01-P0LB-122061 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11931 | T16182-UE00-P0LB-122062 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11932 | T16182-YD02-P0LB-122063 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11933 | T16182-YD02-P0LB-122064 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11934 | T16182-YD02-P0LB-122065 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11935 | T16182-YF00-P0LB-122066 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11936 | T16182-YE03-P0LB-122067 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11937 | T16182-YM03-P0LB-122069 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11938 | T16182-YF00-P0LB-122070 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11939 | T16182-YK00-P0LB-122071 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11940 | T16182-YK00-P0LB-122072 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11941 | T16182-YK00-P0LB-122073 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11942 | T16182-YK01-P0LB-122074 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11943 | T16182-YL00-P0LB-122075 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11944 | T16182-YL00-P0LB-122076 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11945 | T16182-YK10-P0LB-122077 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11946 | T16182-YL16-P0LB-122078 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11947 | T16182-YL00-P0LB-122079 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11948 | T16182-YL01-P0LB-122080 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11949 | T16182-US02-P0LB-122081 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11950 | T16182-YR01-P0LB-122082 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11951 | T16182-YL08-P0LB-122083 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11952 | T16182-YQ01-P0LB-122085 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11953 | T16182-YQ03-P0LB-122086 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11954 | T16182-YQ03-P0LB-122087 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11955 | T16182-YQ03-P0LB-122088 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11956 | T16182-VN02-P0LB-122089 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11957 | T16182-VN02-P0LB-122090 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11958 | T16182-YS00-P0LB-122091 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11959 | T16182-YS00-P0LB-122092 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11960 | T16182-YT01-P0LB-122093 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11961 | T16182-YT02-P0LB-122094 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11962 | T16182-YT01-P0LB-122095 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11963 | T16182-YT01-P0LB-122096 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11964 | T16182-YT01-P0LB-122097 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11965 | T16182-YT01-P0LB-122098 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11966 | T16182-YT01-P0LB-122099 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11967 | T16182-YT01-P0LB-122100 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11968 | T16182-YT01-P0LB-122101 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11969 | T16182-YT01-P0LB-122102 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11970 | T16182-YT01-P0LB-122103 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11971 | T16182-YT02-P0LB-122104 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11972 | T16182-YT01-P0LB-122105 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11973 | T16182-YT01-P0LB-122106 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11974 | T16182-YQ01-P0LB-122107 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11975 | T16182-YT01-P0LB-122108 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11976 | T16182-YD00-P0LB-122109 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11977 | T16182-YD00-P0MAG-123001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11978 | T16182-XG02-P0MAG-123002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11979 | T16182-XS00-P0MAG-123004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11980 | T16182-XS00-P0MAG-123005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11981 | T16182-VN02-P0MAG-123006 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11982 | T16182-XW01-P0MAG-123007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11983 | T16182-XK00-P0MAG-123008 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11984 | T16182-XK00-P0MAG-123009 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11985 | T16182-XS00-P0MAG-123010 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11986 | T16182-DH02-P0MAG-123011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11987 | T16182-YT01-P0MAJ-123012 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11988 | T16182-XR00-P0MAG-123013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11989 | T16182-YT01-P0MAG-123014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11990 | T16182-XH02-P0MAG-123015 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11991 | T16182-XH01-P0MAG-123016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11992 | T16182-YK08-P0MAG-123017 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11993 | T16182-XJ00-P0MAG-123019 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11994 | T16182-DE00-P0MAG-123020 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11995 | T16182-XL00-P0MAG-123021 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11996 | T16182-VN02-P0MAG-123022 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11997 | T16182-XB00-P0MAG-123023 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11998 | T16182-YM01-P0MAG-123025 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
11999 | T16182-YU02-P0MAG-123026 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12000 | T16182-XK00-P0MAG-123027 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12001 | T16182-YM02-P0MAG-123029 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12002 | T16182-YR04-P0MAG-123030 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12003 | T16182-YL00-P0MAG-123031 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12004 | T16182-YF00-P0MAG-123032 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12005 | T16182-YV02-P0MAG-123033 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12006 | T16182-YL01-P0MAG-123034 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12007 | T16182-YT02-P0MAG-123035 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12008 | T16182-YT01-P0MAG-123036 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12009 | T16182-YK00-P0MAG-123037 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12010 | T16182-YT01-P0MAG-123038 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12011 | T16182-YD00-P0MAG-123039 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12012 | T16182-XG01-P0EKG-124001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12013 | T16182-XH01-P0EKG-124002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12014 | T16182-XG07-P0EKG-124003 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12015 | T16182-YD00-P0EKG-124004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12016 | T16182-YK10-P0EKG-124005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12017 | T16182-YK10-P0EKG-124006 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12018 | T16182-YK10-P0EKG-124007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12019 | T16182-YK10-P0EKG-124008 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12020 | T16182-YD00-P0EKG-124009 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12021 | T16182-YK10-P0EKG-124010 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12022 | T16182-YD00-P0EKG-124011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12023 | T16182-YD00-P0EKG-124012 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12024 | T16182-YK10-P0EKG-124013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12025 | T16182-YE00-P0EKG-124014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12026 | T16182-XB02-P0EKG-124015 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12027 | T16182-YF00-P0EKG-124016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12028 | T16182-YB03-P0EKG-124017 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12029 | T16182-YD00-P0EKG-124018 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12030 | T16182-BX03-P0EKG-124020 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12031 | T16182-XS00-P0EKG-124021 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12032 | T16182-YV02-P0EKG-124022 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12033 | T16182-XN00-P0EKG-124023 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12034 | T16182-YT01-P0EKG-124024 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12035 | T16182-YD00-P0EKG-124025 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12036 | T16182-YD00-P0EKG-124026 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12037 | T16182-YT01-P0EKG-124027 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12038 | T16182-YT01-P0EKG-124028 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12039 | T16182-YT01-P0EKG-124029 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12040 | T16182-YT01-P0EKG-124030 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12041 | T16182-YT01-P0EKG-124031 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12042 | T16182-YT01-P0EKG-124032 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12043 | T16182-YT01-P0EKG-124033 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12044 | T16182-XV00-P8ZEN-125001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12045 | T16182-XS00-P8QHA-125002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12046 | T16182-XW03-P8ZEN-125012 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12047 | T16182-XW03-P8ZEN-125014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12048 | T16182-CC00-P8QHA-125101 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12049 | T16182-CC08-P8QHB-125151 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12050 | T16182-XT00-P8QHB-125152 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12051 | T16182-XT00-P8QHB-125153 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12052 | T16182-CC05-P8QHB-125161 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12053 | T16182-CC05-P8QHB-125162 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12054 | T16182-CC02-P8QHB-125164 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12055 | T16182-CC02-P8QHB-125172 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12056 | T16182-YD07-P8QHA-125201 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12057 | T16182-YK10-P8QHA-125202 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12058 | T16182-CC08-P8QHA-125300 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12059 | T16182-UC02-P8QHA-125303 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12060 | T16182-UC02-P8QHA-125304 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12061 | T16182-YK10-P8QHA-125308 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12062 | T16182-DP00-P8ZEN-125310 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12063 | T16182-XH02-P8QHL-125400 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12064 | T16182-XA00-P8QHL-125401 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12065 | T16182-XA00-P8QHL-125402 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12066 | T16182-YK08-P8QHL-125403 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12067 | T16182-DE00-P8ZEN-125502 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12068 | T16182-XN00-P8ZEN-125503 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12069 | T16182-XN00-P8ZEN-125504 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12070 | T16182-XV00-P8ZEN-125505 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12071 | T16182-DP00-P8ZEN-125506 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12072 | T16182-YD00-P8ZEN-125507 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12073 | T16182-XK00-P8ZEN-125509 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12074 | T16182-YL30-P8ZEN-125514 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12075 | T16182-XG05-P8ZEN-125571 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12076 | T16182-XG02-P8ZEN-125582 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12077 | T16182-XG02-P8ZEN-125583 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12078 | T16182-XG02-P8ZEN-125584 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12079 | T16182-XG02-P8ZEN-125585 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12080 | T16182-XG02-P8ZEN-125586 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12081 | T16182-XG02-P8ZEN-125587 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12082 | T16182-XG02-P8ZEN-125588 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12083 | T16182-XG02-P8ZEN-125589 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12084 | T16182-XG02-P8ZEN-125590 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12085 | T16182-XG02-P8ZEN-125591 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12086 | T16182-XG02-P8ZEN-125592 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12087 | T16182-XG02-P8ZEN-125593 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12088 | T16182-CV03-P8ZEN-125601 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12089 | T16182-CV03-P8ZEN-125602 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12090 | T16182-CV03-P8ZEN-125604 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12091 | T16182-CV03-P8ZEN-125605 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12092 | T16182-CV03-P8ZEN-125606 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12093 | T16182-CV03-P8ZEN-125607 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12094 | T16182-CV03-P8ZEN-125608 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12095 | T16182-CV03-P8ZEN-125609 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12096 | T16182-CV03-P8ZEN-125610 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12097 | T16182-CV03-P8ZEN-125611 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12098 | T16182-CV03-P8ZEN-125612 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12099 | T16182-CC08-P8ZEN-125614 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12100 | T16182-CC08-P8ZEN-125615 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12101 | T16182-CC08-P8ZEN-125616 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12102 | T16182-CC08-P8ZEN-125617 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12103 | T16182-CC08-P8ZEN-125618 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12104 | T16182-CC08-P8ZEN-125619 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12105 | T16182-CC08-P8ZEN-125620 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12106 | T16182-XS01-P8ZEN-125700 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12107 | T16182-YF02-P8ZEN-125701 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12108 | T16182-DP00-P8ZEN-125702 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12109 | T16182-YL01-P8ZEN-125703 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12110 | T16182-YL01-P8ZEN-125704 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12111 | T16182-YL01-P8ZEN-125705 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12112 | T16182-YL01-P8ZEN-125706 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12113 | T16182-YL00-P8ZEN-125707 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12114 | T16182-YL00-P8ZEN-125708 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12115 | T16182-YF00-P8ZEN-125709 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12116 | T16182-YF00-P8ZEN-125710 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12117 | T16182-YF00-P8ZEN-125711 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12118 | T16182-YT02-P8ZEN-125713 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12119 | T16182-YT02-P8ZEN-125714 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12120 | T16182-YT02-P8ZEN-125715 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12121 | T16182-YT02-P8ZEN-125716 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12122 | T16182-YT02-P8ZEN-125717 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12123 | T16182-YT02-P8ZEN-125718 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12124 | T16182-YT02-P8ZEN-125719 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12125 | T16182-YK00-P8ZEN-125720 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12126 | T16182-YM03-P8ZEN-125721 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12127 | T16182-YT10-P8ZEN-125722 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12128 | T16182-YT10-P8ZEN-125723 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12129 | T16182-YF00-P8ZEN-125724 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12130 | T16182-YT02-P8ZEN-125725 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12131 | T16182-YT02-P8ZEN-125726 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12132 | T16182-YT02-P8ZEN-125727 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12133 | T16182-YD00-P8ZEN-125728 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12134 | T16182-XF00-P8ZEN-125729 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12135 | T16182-YL16-P8ZEN-125731 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12136 | T16182-YB03-P8ZEN-125732 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12137 | T16182-DP00-P8ZEN-125734 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12138 | T16182-YD00-P8ZEN-125735 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12139 | T16182-DP00-P8ZEN-125749 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12140 | T16182-YD00-P8ZEN-125750 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12141 | T16182-YE00-P8ZEN-125751 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12142 | T16182-YE00-P8ZEN-125752 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12143 | T16182-DP00-P8ZEN-125754 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12144 | T16182-YU02-P8ZEN-125755 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12145 | T16182-YU03-P8ZEN-125756 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12146 | T16182-DP00-P8ZEN-125757 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12147 | T16182-DP00-P8ZEN-125758 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12148 | T16182-DP00-P8ZEN-125759 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12149 | T16182-YL16-P8ZEN-125760 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12150 | T16182-YB03-P8ZEN-125761 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12151 | T16182-YD02-P8ZEN-125762 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12152 | T16182-DP00-P8ZEN-125763 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12153 | T16182-YT10-P8ZEN-125764 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12154 | T16182-YQ01-P8ZEN-125765 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12155 | T16182-DP00-P8ZEN-125766 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12156 | T16182-YE03-P8ZEN-125767 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12157 | T16182-YE01-P8ZEN-125768 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12158 | T16182-YQ03-P8ZEN-125769 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12159 | T16182-YD00-P0LAC-126001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12160 | T16182-XG02-P0LAC-126003 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12161 | T16182-YT01-P0LAC-126004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12162 | T16182-YT01-P0LAC-126005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12163 | T16182-YK01-P0LAC-126006 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12164 | T16182-YD00-P0LAC-126007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12165 | T16182-YT01-P0LAC-126009 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12166 | T16182-YD00-P0LAC-126010 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12167 | T16182-YT02-P0LAC-126011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12168 | T16182-DM01-P0LAC-126012 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12169 | T16182-YT01-P0LAC-126016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12170 | T16182-YD00-P0LAC-126019 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12171 | T16182-YD00-P0LAC-126051 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12172 | T16182-XG02-P0LAC-126053 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12173 | T16182-YT01-P0LAC-126054 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12174 | T16182-YT01-P0LAC-126055 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12175 | T16182-YK01-P0LAC-126056 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12176 | T16182-YD00-P0LAC-126057 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12177 | T16182-YT01-P0LAC-126059 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12178 | T16182-YD00-P0LAC-126060 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12179 | T16182-YT02-P0LAC-126061 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12180 | T16182-DM01-P0LAC-126062 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12181 | T16182-YT01-P0LAC-126066 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12182 | T16182-YD00-P0LAC-126069 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12183 | T16182-XS00-P0PCA-126501 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12184 | T16182-XG02-P0PCA-126502 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12185 | T16182-YD00-P0PCA-126503 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12186 | T16182-XS00-P0PCA-126504 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12187 | T16182-YL25-P0PCA-126505 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12188 | T16182-XV00-P0PCA-126506 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12189 | T16182-XN00-P0PCA-126507 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12190 | T16182-XK00-P0PCA-126508 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12191 | T16182-XS00-P0PCA-126509 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12192 | T16182-YK08-P0PCA-126512 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12193 | T16182-YK08-P0PCA-126513 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12194 | T16182-YK08-P0PCA-126514 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12195 | T16182-YK08-P0PCA-126515 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12196 | T16182-YK08-P0PCA-126516 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12197 | T16182-XH01-P0PCA-126517 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12198 | T16182-DE00-P0PCA-126519 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12199 | T16182-YF00-P0PCA-126522 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12200 | T16182-YL00-P0PCA-126523 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12201 | T16182-YL01-P0PCA-126524 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12202 | T16182-YK00-P0PCA-126525 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12203 | T16182-YL01-P0PCA-126526 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12204 | T16182-YL01-P0PCA-126527 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12205 | T16182-YT02-P0PCA-126529 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12206 | T16182-YD00-P0PCA-126530 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12207 | T16182-YB03-P0PCA-126533 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12208 | T16182-XK00-P0PCA-126538 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12209 | T16182-XK00-P0PCA-126539 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12210 | T16182-YD00-P0LCB-127001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12211 | T16182-XG02-P0LCB-127002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12212 | T16182-YT01-P0LCB-127003 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12213 | T16182-YK09-P0LCB-127004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12214 | T16182-YT01-P0LCB-127005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12215 | T16182-YT01-P0LCB-127006 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12216 | T16182-YT01-P0LCB-127007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12217 | T16182-YD00-P0LCB-127009 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12218 | T16182-YM01-P0LCB-127010 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12219 | T16182-YK09-P0LCB-127011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12220 | T16182-YL00-P0LCB-127013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12221 | T16182-YK00-P0LCB-127015 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12222 | T16182-YT01-P0LCB-127016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12223 | T16182-YL22-P0LCB-127018 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12224 | T16182-YD00-P0LCB-127031 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12225 | T16182-XG02-P0LCB-127032 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12226 | T16182-YT01-P0LCB-127033 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12227 | T16182-YK09-P0LCB-127034 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12228 | T16182-YT01-P0LCB-127035 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12229 | T16182-YT01-P0LCB-127036 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12230 | T16182-YT01-P0LCB-127037 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12231 | T16182-YD00-P0LCB-127038 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12232 | T16182-YM01-P0LCB-127039 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12233 | T16182-YL00-P0LCB-127040 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12234 | T16182-YK00-P0LCB-127041 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12235 | T16182-YL22-P0LCB-127042 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12236 | T16182-YD00-P0LCB-127501 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12237 | T16182-XG02-P0SCA-127502 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12238 | T16182-XW01-P0SCA-127503 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12239 | T16182-XW01-P0SCA-127504 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12240 | T16182-XW01-P0SCA-127505 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12241 | T16182-XW01-P0SCA-127506 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12242 | T16182-XB00-P0SCA-127509 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12243 | T16182-YU02-P0SCA-127510 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12244 | T16182-YV02-P0SCA-127511 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12245 | T16182-YF02-P0SCA-127514 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12246 | T16182-YD05-P0SCA-127515 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12247 | T16182-YL01-P0SCA-127516 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12248 | T16182-YL01-P0SCA-127517 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12249 | T16182-YF00-P0SCA-127518 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12250 | T16182-YL00-P0SCA-127520 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12251 | T16182-CV03-P0SCA-127521 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12252 | T16182-YK00-P0SCA-127522 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12253 | T16182-YR05-P0SCA-127523 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12254 | T16182-XF00-P0SCA-127524 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12255 | T16182-XN00-P0SCA-127525 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12256 | T16182-YT01-P0SCA-127526 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12257 | T16182-YD00-P0SMM-128001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12258 | T16182-YD00-P0SMS-128002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12259 | T16182-YT01-P0SMM-128004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12260 | T16182-YT01-P0SMS-128005 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12261 | T16182-YK09-P0SMM-128007 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12262 | T16182-YK09-P0SMS-128008 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12263 | T16182-YS18-P0SMM-128010 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12264 | T16182-YS18-P0SMS-128011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12265 | T16182-YD00-P0SML-128013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12266 | T16182-YD00-P0SMQ-128014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12267 | T16182-YD00-P0SMU-128015 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12268 | T16182-YD00-P0SMG-128016 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12269 | T16182-YD00-P0SMU-128017 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12270 | T16182-YT01-P0SML-128018 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12271 | T16182-YT01-P0SMQ-128019 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12272 | T16182-YT01-P0SMU-128020 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12273 | T16182-YT01-P0SMG-128021 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12274 | T16182-YT01-P0SMU-128022 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12275 | T16182-YK09-P0SML-128023 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12276 | T16182-YK09-P0SMQ-128024 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12277 | T16182-YK09-P0SMU-128025 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12278 | T16182-YK09-P0SMG-128026 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12279 | T16182-YS18-P0SML-128027 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12280 | T16182-YD00-P0GM-128501 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12281 | T16182-YT01-P0GM-128502 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12282 | T16182-YD00-P0GM-128503 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12283 | T16182-XK00-P0GM-128504 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12284 | T16182-XK00-P0GM-128505 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12285 | T16182-XB00-P0GM-128506 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12286 | T16182-XW01-P0GM-128507 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12287 | T16182-CV03-P0GM-128508 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12288 | T16182-YK00-P0GM-128509 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12289 | T16182-XF00-P0GM-128510 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12290 | T16182-YR05-P0GM-128511 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12291 | T16182-YL00-P0GM-128512 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12292 | T16182-YD00-P0GHC-129001 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12293 | T16182-YT01-P0GHC-129002 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12294 | T16182-YK09-P0GHC-129003 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12295 | T16182-YT01-P0GHC-129004 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12296 | T16182-YM01-P0GHC-129008 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12297 | T16182-YL00-P0GHC-129011 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12298 | T16182-YK00-P0GHC-129013 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12299 | T16182-YL22-P0GHC-129014 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12300 | T16182-YD00-P0GHC-129031 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12301 | T16182-YT01-P0GHC-129032 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12302 | T16182-YK09-P0GHC-129033 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12303 | T16182-YT01-P0GHC-129034 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12304 | T16182-YM01-P0GHC-129035 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12305 | T16182-YL00-P0GHC-129036 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12306 | T16182-YK00-P0GHC-129037 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12307 | T16182-YL22-P0GHC-129038 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12308 | T16182-YK10-P8QHA-125207 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12309 | T16182-YD16-P0SCA-127546 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12310 | T16182-YK08-P0LAC-126027 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12311 | T16182-YK08-P0LAC-126077 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12312 | T16182-XJ00-P8ZEN-125520 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12313 | T16182-XJ00-P8ZEN-125521 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12314 | T16182-XJ00-P8ZEN-125522 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12315 | T16182-XJ00-P8ZEN-125523 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12316 | T16182-XJ00-P8ZEN-125524 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12317 | T16182-XJ00-P8ZEN-125525 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12318 | T16182-XJ00-P8ZEN-125526 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12319 | T16182-XJ00-P8ZEN-125527 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12320 | T16182-XK00-P8ZEN-125530 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12321 | T16182-XK00-P8ZEN-125531 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12322 | T16182-XK00-P8ZEN-125532 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12323 | T16182-XK00-P8ZEN-125533 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12324 | T16182-XK00-P8ZEN-125534 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12325 | T16182-XK00-P8ZEN-125535 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12326 | T16182-XK00-P8ZEN-125536 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12327 | T16182-XK00-P8ZEN-125537 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12328 | T16182-XJ00-P8ZEN-125540 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12329 | T16182-XJ00-P8ZEN-125541 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12330 | T16182-XJ00-P8ZEN-125542 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12331 | T16182-XJ00-P8ZEN-125543 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12332 | T16182-XJ00-P8ZEN-125544 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12333 | T16182-XJ00-P8ZEN-125545 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12334 | T16182-XJ00-P8ZEN-125546 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12335 | T16182-XJ00-P8ZEN-125547 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12336 | T16182-XJ00-P8ZEN-125548 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12337 | T16182-XJ00-P8ZEN-125549 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12338 | T16182-XJ00-P8ZEN-125550 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12339 | T16182-YT01-P0MBA-121555 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12340 | T16182-YD00-P0SMM-128101 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12341 | T16182-YD00-P0SMS-128102 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12342 | T16182-YD00-P0SML-128103 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12343 | T16182-YT01-P0GHC-129050 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12344 | T16182-YD00-P0GHC-129051 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12345 | T16182-YK09-P0GHC-129053 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12346 | T16182-YT01-P0GHC-129055 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12347 | T16182-YL22-P0GHC-129056 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12348 | T16182-YM01-P0GHC-129060 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12349 | T16182-YL00-P0GHC-129063 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12350 | T16182-YK00-P0GHC-129064 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12351 | T16182-DP00-P8ZEN-125737 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12352 | T16182-UB01-P0EKG-124075 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12353 | T16182-YB11-P0LAC-126301 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12354 | T16182-YB11-P0LAC-126351 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12355 | T16182-YD00-P0SMC-128028 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12356 | T16182-YD00-P0SMS-128029 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12357 | T16182-YD00-P0SMG-128030 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12358 | T16182-YD00-P0SMM-128031 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12359 | T16182-YD00-P0SMU-128032 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12360 | T16182-YT01-P0SMC-128033 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12361 | T16182-YT01-P0SMS-128034 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12362 | T16182-YT01-P0SMG-128035 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12363 | T16182-YT01-P0SMM-128036 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12364 | T16182-YT01-P0SMU-128037 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12365 | T16182-YK09-P0SMC-128038 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12366 | T16182-YK09-P0SMS-128039 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12367 | T16182-YK09-P0SMG-128040 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12368 | T16182-YK09-P0SMM-128041 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12369 | T16182-YK09-P0SMU-128042 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12370 | T16182-YS18-P0SMC-128043 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12371 | T16182-YS18-P0SMS-128044 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12372 | T16182-YS18-P0SMQ-128045 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12373 | T16182-YS18-P0SMU-128046 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12374 | T16182-YS18-P0SMG-128047 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12375 | T16182-YS18-P0SMG-128048 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12376 | T16182-YS18-P0SMM-128049 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12377 | T16182-YS02-P0LAC-126302 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12378 | T16182-YS02-P0LAC-126352 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12379 | T16182-YD00-P0LB-122006 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12380 | T16182-XJ00-P8ZEN-125570 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12381 | T16182-YD00-P0SMG-128051 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12382 | T16182-YD00-P0SMG-128052 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12383 | T16182-YD00-P0SMG-128053 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12384 | T16182-CQ02-P0MBA-121076 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12385 | T16182-XA00-P0MAG-123048 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12386 | T16182-XA00-P0MAG-123049 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12387 | T16182-YT01-P0MBA-121824 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12388 | T16182-CV03-P8SGK-125650 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12389 | T16182-VN01-P0MAG-123050 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12390 | T16182-XW03-P0LB-122110 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12391 | T16182-CQ02-P0MBA-121073 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12392 | T16182-YT01-P0MBA-121677 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12393 | T16182-CQ02-P0MBA-121051 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12394 | T16182-YS00-P0MBA-121678 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12395 | T16182-YB03-P0EKG-124180 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12396 | T16182-YD00-P0MAG-123051 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12397 | T16182-YT01-P0MBA-121971 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12398 | T16182-YR01-P8ZEN-125597 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12399 | T16182-YQ01-P0ZEN-123052 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12400 | T16182-UE00-P0LB-122111 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12401 | T16182-XG02-P0GM-122112 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12402 | T16182-YK09-P0PCA-126540 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12403 | T16182-DS00-P0MAG-123053 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12404 | T16182-XG02-P0GM-121100 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12405 | T16182-YQ03-P0CY-121036 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Bu | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12406 | T16182-YD00-P0LCB-127555 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12407 | T16182-XW01-P0SCA-127556 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12408 | T16182-XG02-P0SCA-127557 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12409 | T16182-YD00-P0MAG-123054 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12410 | T16182-XW01-P0MBA-121037 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12411 | T16182-YV02-P0SCA-127548 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12412 | T16182-DM02-P0MBA-121038 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12413 | T16182-VN01-P0MAG-123055 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12414 | T16182-CQ02-P0MBA-121077 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12415 | T16182-YT01-P0EKG-124040 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12416 | T16182-YL30-P0EKG-124078 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12417 | T16182-YD00-P0SMU-128070 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12418 | T16182-YD00-P0SMS-128060 | 2020-03-06 | DHI-ASBUILT-000017 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12419 | T16182-YD00-P0GHC-129031 | 2020-03-12 | DHI-ASBUILT-000018 | AB | 0 | D | TRUE | FALSE | 2020-03-17_Changed by jisoo1.chung | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12420 | T16182-VL00-P0MPA-220001 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12421 | T16182-VL00-P7MPA-220002 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12422 | T16182-UF00-P0MAA-220003 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12423 | T16182-XM00-P0MAA-220015 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12424 | T16182-CA07-P0MPA-220023 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12425 | T16182-XG02-P6MAA-220025 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12426 | T16182-XG02-P7MAA-220026 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12427 | T16182-XG02-P6MAA-220027 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12428 | T16182-XG02-P7MAA-220028 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12429 | T16182-XG02-P6MAA-220029 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12430 | T16182-XG02-P7MAA-220030 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12431 | T16182-VE01-P6MAA-220047 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12432 | T16182-YR00-P6MAA-220073 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12433 | T16182-XG01-P6MAA-220089 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12434 | T16182-XG01-P7MAA-220090 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12435 | T16182-XS01-P6MAA-220093 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12436 | T16182-YL13-P6MAA-220095 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12437 | T16182-YF00-P6MAA-220097 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12438 | T16182-CM01-P6MAA-220205 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12439 | T16182-CM01-P7MAA-220206 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12440 | T16182-YL08-P6MAA-220207 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12441 | T16182-YF02-P6CJJ-220275 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12442 | T16182-YF02-P7CJJ-220276 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12443 | T16182-YV02-P6CJJ-220277 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12444 | T16182-YV02-P7CJJ-220278 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12445 | T16182-YT02-P6CJJ-220293 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12446 | T16182-YT02-P7CJJ-220294 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12447 | T16182-XJ00-P6MAA-220383 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12448 | T16182-XJ00-P7MAA-220384 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12449 | T16182-YD00-P0MAA-220801 | 2020-04-02 | DHI-ASBUILT-000019 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As B | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12450 | T16182-XG02-P0EK-120007 | 2020-04-03 | DHI-ASBUILT-000020 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20an | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12451 | T16182-YE03-P0BAU-152507 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 0 | D | TRUE | FALSE |  |  | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12452 | T16182-YK08-P0MJ-110506 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12453 | T16182-YF00-P0MJ-110511 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12454 | T16182-YT10-P0MJ-110568 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12455 | T16182-YD02-P0LB-122065 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12456 | T16182-DS00-P0MAG-123053 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12457 | T16182-YU02-P0SCA-127510 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12458 | T16182-YU02-P0LD-130210 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12459 | T16182-YU03-P0QC-130308 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12460 | T16182-YD00-P0BBT-150671 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12461 | T16182-YQ01-P0ZEN-152306 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12462 | T16182-YQ01-P0ZEN-152332 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12463 | T16182-YE03-P0BAU-152536 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12464 | T16182-YD02-P0ZEN-165502 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12465 | T16182-YR02-P0ZEN-150001 | 2020-06-12 | DHI-ASBUILT-000021 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12466 | T16182-YF00-P0CBA-161210 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12467 | T16182-YF00-P0CBA-161213 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12468 | T16182-YF00-P0CBA-161220 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12469 | T16182-YF00-P0CBA-161221 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12470 | T16182-YF00-P0CGA-161303 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12471 | T16182-YF00-P0CGA-161304 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12472 | T16182-YF00-P0CGA-161305 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12473 | T16182-YF00-P0CGA-161306 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12474 | T16182-YF00-P0CGA-161307 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12475 | T16182-YF00-P0CGA-161308 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12476 | T16182-YF00-P0CGA-161309 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12477 | T16182-YF00-P0CGA-161313 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12478 | T16182-YF00-P0CBA-161203 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12479 | T16182-YF00-P0CBA-161204 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12480 | T16182-YF00-P0CBA-161205 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12481 | T16182-YF00-P0CBA-161206 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12482 | T16182-YF00-P0CBA-161207 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12483 | T16182-YF00-P0CBA-161208 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12484 | T16182-YF00-P0CBA-161209 | 2020-06-16 | DHI-ASBUILT-000022 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12485 | T16182-YU03-P0BFA-150956 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12486 | T16182-YU03-P0BFA-150957 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12487 | T16182-YU03-P0BFA-150958 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12488 | T16182-YQ01-P0ZEN-152319 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12489 | T16182-YQ01-P0ZEN-152322 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12490 | T16182-YB11-P0ZEN-152406 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12491 | T16182-YE03-P0BAU-152529 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12492 | T16182-YE03-P0BAU-152530 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12493 | T16182-YE01-P0BAU-152606 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12494 | T16182-YT01-P0MKA-250009 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12495 | T16182-YE01-P8ZEN-125768 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12496 | T16182-YU03-P0LD-130217 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12497 | T16182-YU03-P0BB-150836 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12498 | T16182-YU03-P0BFA-150951 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12499 | T16182-YU03-P0BFA-150952 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12500 | T16182-YU03-P0BFA-150953 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12501 | T16182-YU03-P0BFA-150954 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12502 | T16182-YU03-P0BFA-150955 | 2020-06-17 | DHI-ASBUILT-000023 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12503 | T16182-YD00-P0GCF-130006 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12504 | T16182-YF00-P0LD-130218 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12505 | T16182-YF00-P0CJD-161025 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12506 | T16182-YF02-P0ZEN-161031 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12507 | T16182-YL01-P0CBA-161101 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12508 | T16182-YL01-P0CRN-161117 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12509 | T16182-YD00-P0CWQ-161401 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12510 | T16182-YB03-P0ZEN-165548 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12511 | T16182-YF00-P0BB-150402 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12512 | T16182-XS00-P0LB-122036 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12513 | T16182-YF00-P0LB-122068 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12514 | T16182-YR05-P0LB-122084 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12515 | T16182-XS00-P0LB-110040 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12516 | T16182-XS00-P0LA-110042 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12517 | T16182-CN00-P0ZEN-110702 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12518 | T16182-XW01-P0MBA-121006 | 2020-06-18 | DHI-ASBUILT-000024 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12519 | T16182-YU02-P0BB-150811 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12520 | T16182-YU02-P0BB-150816 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12521 | T16182-YU03-P0BAT-150636 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/s | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12522 | T16182-YU03-P0BB-150831 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12523 | T16182-YU03-P0BBT-150681 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12524 | T16182-CA00-P0UYC-182905 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12525 | T16182-CA01-P0UYC-182951 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12526 | T16182-CA01-P0UYC-182956 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12527 | T16182-CA06-P0UYC-182900 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12528 | T16182-XG02-P8ZEN-125587 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12529 | T16182-YB11-P0ZEN-152401 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12530 | T16182-YD00-P0LAC-126010 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12531 | T16182-YD00-P0LAC-126060 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12532 | T16182-YD00-P0UBA-150508 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12533 | T16182-YK10-P0LF-140301 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12534 | T16182-YK10-P0LF-140302 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12535 | T16182-YK10-P0LF-140303 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12536 | T16182-YK10-P0LF-140304 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12537 | T16182-YT01-P0MBA-121555 | 2020-06-22 | DHI-ASBUILT-000025 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12538 | T16182-XG01-P6MAA-220089 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12539 | T16182-XG01-P7MAA-220090 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12540 | T16182-XG02-P0LBS-110006 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12541 | T16182-XG02-P0SCA-120005 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12542 | T16182-XG02-P6LCM-110007 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12543 | T16182-YD05-P0MBA-121032 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12544 | T16182-YL00-P8ZEN-125707 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12545 | T16182-YL08-P6MAA-220207 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12546 | T16182-YQ03-P0CY-154021 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12547 | T16182-YS00-P0CJN-290001 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12548 | T16182-YT02-P8ZEN-125714 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12549 | T16182-YT10-P0ZEN-150312 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12550 | T16182-YT10-P0ZEN-150313 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12551 | T16182-YU02-P0BB-150813 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12552 | T16182-YU02-P0BB-150815 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12553 | T16182-YU02-P0BFA-150914 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12554 | T16182-YU03-P0BAT-150631 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/s | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12555 | T16182-CN00-P0ZEN-110701 | 2020-06-25 | DHI-ASBUILT-000026 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12556 | T16182-CA00-P0UGD-181904 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12557 | T16182-CA01-P0QJA-184851 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12558 | T16182-CA01-P0UCB-180652 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12559 | T16182-CA01-P0UMA-180451 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12560 | T16182-CA02-P0UBA-181055 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12561 | T16182-CA02-P0UBA-181258 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12562 | T16182-CA02-P0UST-182061 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12563 | T16182-CA03-P0UMA-180458 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12564 | T16182-CA03-P0UMA-180459 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12565 | T16182-CA03-P0UMA-180462 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12566 | T16182-CA03-P0UMA-180463 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12567 | T16182-CA05-P0UBA-181281 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12568 | T16182-CA05-P0UYP-183283 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12569 | T16182-CA05-P0UYP-183285 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12570 | T16182-CV03-P8SGK-125650 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12571 | T16182-XJ00-P0LB-122027 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12572 | T16182-XS01-P8ZEN-125700 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12573 | T16182-YM03-P0LB-122069 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12574 | T16182-YQ01-P0LB-122085 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12575 | T16182-YT01-P0EKG-124079 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12576 | T16182-YU02-P8ZEN-125755 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12577 | T16182-YU03-P8ZEN-125756 | 2020-06-26 | DHI-ASBUILT-000027 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12578 | T16182-CA00-P0UBA-181003 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12579 | T16182-CA00-P0UBA-181103 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12580 | T16182-CA00-P0UGD-181908 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12581 | T16182-CA00-P0UGD-181910 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12582 | T16182-CA00-P0UGD-181912 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12583 | T16182-CA00-P0UGD-181913 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12584 | T16182-CA00-P0UTF-182801 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12585 | T16182-CA01-P0UTF-182853 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12586 | T16182-CA02-P0UBA-181360 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12587 | T16182-CA02-P0ULD-183960 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12588 | T16182-CA02-P0UTF-182857 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12589 | T16182-CA03-P0ULA-182155 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12590 | T16182-CA03-P0UMY-185161 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12591 | T16182-CA03-P1BAT-180512 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12592 | T16182-CA05-P0UCB-180684 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12593 | T16182-CA05-P0UYP-183281 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12594 | T16182-CA05-P0UYP-183282 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12595 | T16182-CA06-P0UMY-185191 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12596 | T16182-CA06-P0UMY-185192 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12597 | T16182-CC05-P0ZEN-180008 | 2020-07-01 | DHI-ASBUILT-000028 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12598 | T16182-CA00-P0UBA-181305 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12599 | T16182-CA00-P0UBA-186801 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12600 | T16182-CA00-P0UGD-181901 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12601 | T16182-CA00-P0ULD-183902 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12602 | T16182-CA00-P0UMA-180401 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12603 | T16182-CA00-P0UYA-183101 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12604 | T16182-CA00-P0UYE-183301 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12605 | T16182-CA00-P0UYF-183601 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12606 | T16182-CA00-P0UYP-183201 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12607 | T16182-CA00-P0UYP-183203 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12608 | T16182-CA01-P0UBA-186152 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12609 | T16182-CA01-P0ULD-183951 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12610 | T16182-CA01-P0ULD-183952 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12611 | T16182-CA02-P0ULD-183956 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12612 | T16182-CA02-P0ULD-183957 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12613 | T16182-CA03-P0ULA-182154 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12614 | T16182-CA03-P0UST-182055 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12615 | T16182-YD00-P0BAA-150762 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12616 | T16182-YE00-P0ZEN-152716 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12617 | T16182-YS01-P0MKY-290009 | 2020-07-02 | DHI-ASBUILT-000029 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12618 | T16182-CA00-P0UBA-181205 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12619 | T16182-CA00-P0UBA-186103 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12620 | T16182-XB00-P0GM-128506 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12621 | T16182-XG02-P0PCA-126502 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12622 | T16182-XG02-P8ZEN-125584 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12623 | T16182-XN00-P0EKG-124023 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12624 | T16182-YD00-P0GHC-129031 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12625 | T16182-YK09-P0GHC-129033 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12626 | T16182-YT01-P0GHC-129032 | 2020-07-03 | DHI-ASBUILT-000030 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. D | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12627 | T16182-CV03-P0CWQ-161122 | 2020-07-09 | DHI-ASBUILT-000031 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/s | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12628 | T16182-XS00-P0MJ-110510 | 2020-07-09 | DHI-ASBUILT-000031 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/si | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12629 | T16182-YS01-P0MKY-290011 | 2020-07-09 | DHI-ASBUILT-000031 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/s | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12630 | T16182-YS01-P0MKY-290012 | 2020-07-09 | DHI-ASBUILT-000031 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/s | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12631 | T16182-YU02-P0MBA-121018 | 2020-07-09 | DHI-ASBUILT-000031 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/s | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12632 | T16182-YU02-P0MKY-290006 | 2020-07-09 | DHI-ASBUILT-000031 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/s | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12633 | T16182-XH01-P0LF-140423 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12634 | T16182-XS00-P0LB-122035 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12635 | T16182-YE03-P0LB-122067 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12636 | T16182-YF00-P0LB-122066 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12637 | T16182-YT01-P0BT-151011 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12638 | T16182-YU02-P0BT-151021 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12639 | T16182-YU02-P0BT-151026 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12640 | T16182-YU02-P0BT-151031 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12641 | T16182-YU03-P0BT-151061 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12642 | T16182-YU03-P0BT-151066 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12643 | T16182-YU03-P0BT-151071 | 2020-07-10 | DHI-ASBUILT-000032 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Do | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12644 | T16182-DN05-P0ZEN-860001 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860001_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12645 | T16182-DN05-P0ZEN-860002 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860002_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12646 | T16182-DN05-P0ZEN-860003 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860003_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12647 | T16182-DN05-P0ZEN-860004 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860004_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12648 | T16182-DN05-P0ZEN-860006 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860006_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12649 | T16182-DN05-P0ZEN-860007 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860007_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12650 | T16182-DN05-P0ZEN-860008 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860008_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12651 | T16182-DN05-P0ZEN-860009 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860009_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12652 | T16182-DN05-P0ZEN-860010 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860010_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12653 | T16182-DN05-P0ZEN-860011 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860011_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12654 | T16182-DN05-P0ZEN-860012 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860012_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12655 | T16182-DN05-P0ZEN-860013 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860013_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12656 | T16182-DN05-P0ZEN-860014 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860014_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12657 | T16182-DN05-P0ZEN-860015 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860015_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12658 | T16182-DN05-P0ZEN-860016 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860016_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12659 | T16182-DN05-P0ZEN-860017 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860017_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12660 | T16182-DN05-P0ZEN-860018 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860018_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12661 | T16182-DN05-P0ZEN-860019 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860019_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12662 | T16182-DN05-P0ZEN-860020 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860020_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12663 | T16182-DN05-P0ZEN-860021 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860021_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12664 | T16182-DN05-P0ZEN-860022 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860022_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12665 | T16182-DN05-P0ZEN-860027 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860027_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12666 | T16182-DN05-P0ZEN-860028 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860028_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12667 | T16182-DN05-P0ZEN-860029 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860029_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12668 | T16182-DN05-P0ZEN-860030 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P0ZEN-860030_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12669 | T16182-DN05-P8MB-810006 | 2020-07-15 | DHI-ASBUILT-000033 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000033/T16182-DN05-P8MB-810006_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12670 | T16182-YU03-P0CHB-151121 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-YU03-P0CHB-151121_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12671 | T16182-YU03-P0CHB-151122 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-YU03-P0CHB-151122_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12672 | T16182-UB01-P0EKG-124075 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-UB01-P0EKG-124075_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12673 | T16182-XH01-P0EKG-124002 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-XH01-P0EKG-124002_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12674 | T16182-XS00-P0EKG-120019 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-XS00-P0EKG-120019_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12675 | T16182-YE00-P0EKG-124014 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-YE00-P0EKG-124014_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12676 | T16182-YM02-P0MJ-110578 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-YM02-P0MJ-110578_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12677 | T16182-YU02-P0MJ-110507 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-YU02-P0MJ-110507_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12678 | T16182-YU03-P0CFA-151181 | 2020-07-16 | DHI-ASBUILT-000034 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000034/T16182-YU03-P0CFA-151181_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12679 | T16182-XH01-P0LF-140401 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-XH01-P0LF-140401_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12680 | T16182-XH01-P0LF-140402 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-XH01-P0LF-140402_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12681 | T16182-XH01-P0LF-140403 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-XH01-P0LF-140403_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12682 | T16182-XH01-P0LF-140404 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-XH01-P0LF-140404_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12683 | T16182-XH01-P0LF-140406 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-XH01-P0LF-140406_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12684 | T16182-XH01-P0LF-140407 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-XH01-P0LF-140407_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12685 | T16182-XH01-P0LF-140417 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-XH01-P0LF-140417_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12686 | T16182-YQ01-P0ZEN-152301 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YQ01-P0ZEN-152301_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12687 | T16182-YQ01-P0ZEN-152302 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YQ01-P0ZEN-152302_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12688 | T16182-YQ01-P0ZEN-152303 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YQ01-P0ZEN-152303_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12689 | T16182-YQ01-P0ZEN-152304 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YQ01-P0ZEN-152304_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12690 | T16182-YQ01-P0ZEN-152308 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YQ01-P0ZEN-152308_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12691 | T16182-YQ01-P0ZEN-152315 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YQ01-P0ZEN-152315_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12692 | T16182-YQ01-P0ZEN-152321 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YQ01-P0ZEN-152321_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12693 | T16182-YT01-P0MAN-110153 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YT01-P0MAN-110153_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12694 | T16182-YU05-P0MBA-121017 | 2020-07-20 | DHI-ASBUILT-000035 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000035/T16182-YU05-P0MBA-121017_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12695 | T16182-YQ01-P0ZEN-152305 | 2020-07-21 | DHI-ASBUILT-000036 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000036/T16182-YQ01-P0ZEN-152305_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12696 | T16182-XG02-P0LBA-110003 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-XG02-P0LBA-110003_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12697 | T16182-XJ00-P0LAB-140108 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-XJ00-P0LAB-140108_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12698 | T16182-XJ00-P0LBA-140101 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-XJ00-P0LBA-140101_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12699 | T16182-XJ00-P0LBG-140104 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-XJ00-P0LBG-140104_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12700 | T16182-XJ00-P0LBG-140204 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-XJ00-P0LBG-140204_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12701 | T16182-XJ00-P0LCM-140105 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-XJ00-P0LCM-140105_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12702 | T16182-XN00-P0ZEN-140003 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-XN00-P0ZEN-140003_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12703 | T16182-YF00-P0CJA-161041 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-YF00-P0CJA-161041_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12704 | T16182-YL01-P0MBA-121025 | 2020-07-27 | DHI-ASBUILT-000037 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000037/T16182-YL01-P0MBA-121025_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12705 | T16182-DN05-P0GC-830007 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0GC-830007_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12706 | T16182-DN05-P0GHC-830002 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0GHC-830002_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12707 | T16182-DN05-P0GHD-830001 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0GHD-830001_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12708 | T16182-DN05-P0GN-830009 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0GN-830009_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12709 | T16182-DN05-P0HA-800001 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0HA-800001_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12710 | T16182-DN05-P0HA-800003 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0HA-800003_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12711 | T16182-DN05-P0LA-830006 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0LA-830006_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12712 | T16182-DN05-P0LB-800004 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0LB-800004_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12713 | T16182-DN05-P0LC-830016 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0LC-830016_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12714 | T16182-DN05-P0LD-830024 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0LD-830024_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12715 | T16182-DN05-P0MA-810005 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0MA-810005_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12716 | T16182-DN05-P0MAG-830020 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0MAG-830020_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12717 | T16182-DN05-P0MAG-830046 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0MAG-830046_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12718 | T16182-DN05-P0MBP-830005 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0MBP-830005_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12719 | T16182-DN05-P0MBP-830017 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0MBP-830017_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12720 | T16182-DN05-P0MJ-830021 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0MJ-830021_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12721 | T16182-DN05-P0PG-830003 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0PG-830003_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12722 | T16182-DN05-P0QC-830015 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0QC-830015_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12723 | T16182-DN05-P0QJA-830023 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0QJA-830023_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12724 | T16182-DN05-P0QU-830014 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0QU-830014_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12725 | T16182-DN05-P0SC-830004 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0SC-830004_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12726 | T16182-DN05-P0ZEN-830045 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-830045_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12727 | T16182-DN05-P0ZEN-840201 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840201_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12728 | T16182-DN05-P0ZEN-840202 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840202_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12729 | T16182-DN05-P0ZEN-840203 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840203_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12730 | T16182-DN05-P0ZEN-840204 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840204_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12731 | T16182-DN05-P0ZEN-840205 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840205_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12732 | T16182-DN05-P0ZEN-840209 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840209_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12733 | T16182-DN05-P0ZEN-840210 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840210_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12734 | T16182-DN05-P0ZEN-840211 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840211_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12735 | T16182-DN05-P0ZEN-840213 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840213_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12736 | T16182-DN05-P0ZEN-840215 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-840215_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12737 | T16182-DN05-P0ZEN-860023 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-860023_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12738 | T16182-DN05-P0ZEN-860024 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-860024_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12739 | T16182-DN05-P0ZEN-860025 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-860025_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12740 | T16182-DN05-P0ZEN-860026 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P0ZEN-860026_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12741 | T16182-DN05-P1HNY-830013 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P1HNY-830013_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12742 | T16182-DN05-P1HNY-830018 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P1HNY-830018_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12743 | T16182-DN05-P1LB-830012 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P1LB-830012_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12744 | T16182-DN05-P8MB-810002 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P8MB-810002_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12745 | T16182-DN05-P8QH-830008 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P8QH-830008_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12746 | T16182-DN05-P8QH-830010 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P8QH-830010_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12747 | T16182-DN05-P8QH-830011 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P8QH-830011_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12748 | T16182-DN05-P8QH-830019 | 2020-08-18 | DHI-ASBUILT-000038 | AB | 0 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000038/T16182-DN05-P8QH-830019_AB_0.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12749 | T16182-YF00-P0SCA-127518 | 2020-08-26 | DHI-ASBUILT-000039 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000039/T16182-YF00-P0SCA-127518_AB_1.pdf?csf=1&web=1&e=meTazU | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12750 | T16182-YL01-P0SCA-127517 | 2020-08-26 | DHI-ASBUILT-000039 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/:b:/r/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000039/T16182-YL01-P0SCA-127517_AB_1.pdf?csf=1&web=1&e=b49Q7K | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12751 | T16182-UB01-P0EKG-124075 | 2020-10-07 | DHI-ASBUILT-000041 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000041/T16182-UB01-P0EKG-124075_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12752 | T16182-XH01-P0EKG-124002 | 2020-10-07 | DHI-ASBUILT-000041 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000041/T16182-XH01-P0EKG-124002_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12753 | T16182-YE00-P0EKG-124014 | 2020-10-07 | DHI-ASBUILT-000041 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000041/T16182-YE00-P0EKG-124014_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12754 | T16182-YD00-P8ZEN-125750 | 2020-10-29 | DHI-ASBUILT-000042 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000042/T16182-YD00-P8ZEN-125750_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12755 | T16182-YM03-P8ZEN-125721 | 2020-10-29 | DHI-ASBUILT-000042 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000042/T16182-YM03-P8ZEN-125721_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12756 | T16182-YQ01-P8ZEN-125765 | 2020-10-29 | DHI-ASBUILT-000042 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000042/T16182-YQ01-P8ZEN-125765_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12757 | T16182-YU03-P0BFA-150956 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150956_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12758 | T16182-YU03-P0BFA-150957 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150957_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12759 | T16182-YU03-P0BFA-150958 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150958_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12760 | T16182-YF00-P0BB-150403 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YF00-P0BB-150403_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12761 | T16182-YU03-P0BFA-150951 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150951_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12762 | T16182-YU03-P0BFA-150952 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150952_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12763 | T16182-YU03-P0BFA-150953 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150953_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12764 | T16182-YU03-P0BFA-150954 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150954_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12765 | T16182-YU03-P0BFA-150955 | 2020-11-09 | DHI-ASBUILT-000043 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared Documents/1. Document and Drawing/3. As Built/Revised/AB1/DHI-ASBUILT-000043/T16182-YU03-P0BFA-150955_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12766 | T16182-XG02-P0MJ-110505 | 2021-02-01 | DHI-ASBUILT-000044 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000044/T16182-XG02-P0MJ-110505_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12767 | T16182-XG02-P8ZEN-125587 | 2021-02-01 | DHI-ASBUILT-000044 | AB | 2 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000044/T16182-XG02-P8ZEN-125587_AB_2.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12768 | T16182-XW01-P0SCA-127504 | 2021-03-05 | DHI-ASBUILT-000045 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000045/T16182-XW01-P0SCA-127504_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST
12769 | T16182-XG02-P0MBA-121003 | 2021-03-05 | DHI-ASBUILT-000045 | AB | 1 | D | TRUE | FALSE |  | https://doosankor.sharepoint.com/sites/0900.REQTEAMS.2383/Shared%20Documents/1.%20Document%20and%20Drawing/3.%20As%20Built/Revised/AB1/DHI-ASBUILT-000045/T16182-XG02-P0MBA-121003_AB_1.pdf | FALSE | 항목 | sites/0900.REQTEAMS.2383/Lists/DT_LIST