## Generated Schedule
source_file | document_no | title | deliverable | equipment | system | building | itb_sources | rule_query | matched_rule | matched_rule_keyword | matched_rule_priority | matched_rule_validation_time | matched_rule_date_formula | rule_match_query_source | rule_match_query_family | rule_match_rule_family | rule_match_query_subtype | rule_match_rule_subtype | rule_match_query_scope | rule_match_rule_scope | rule_match_rule_scope_type | rule_match_family_status | rule_match_subtype_status | rule_match_scope_status | rule_match_guard_status | rule_match_guard_reason | rule_match_token_score | rule_match_semantic_score | rule_match_hybrid_score | rule_match_final_score | submission_type | matched_activity_id | matched_activity_name | matched_activity_wbs_path | matched_activity_start_date | matched_activity_finish_date | activity_match_query_phase | activity_match_activity_phase | activity_match_phase_status | activity_match_query_scope | activity_match_rule_scope | activity_match_effective_scope | activity_match_scope_source | activity_match_activity_scope | activity_match_scope_status | activity_match_generic_activity | activity_match_bm25_rank | activity_match_semantic_rank | activity_match_bm25_score | activity_match_semantic_score | activity_match_rrf_score | activity_match_adjusted_score | activity_match_resolver_mode | activity_match_resolution_reason | activity_match_structured_scope | activity_match_structured_allowed_phases | activity_match_structured_cell_size | fa_earliest | fa_recommended | fa_latest | fc_earliest | fc_recommended | fc_latest | date_range_status | date_range_confidence | schedule_confidence | schedule_quality_status | schedule_quality_reasons | date_range_notes | ntp_shift_days
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION | [7 empty] | DOCUMENT IDENTIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | document_identification | document_identification |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | 27 | 60 |  | 0.3299 | 0.0198 | 0.0112 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | [7 empty] | EQUIPMENT AND SYSTEM IDENTIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | equipment_and_system_identification | equipment_and_system_identification |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 2CF1660W86A13 | (HRSG #21 I&C Vendor Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | 2008-10-20 | 2009-02-11 |  | procurement | query_unknown |  |  |  |  | hrsg | query_unscoped | false | 52 | 5 | 5.1562 | 0.4964 | 0.0243 | 0.0137 | hybrid | structured_no_system |  |  |  | 2025-06-08 | 2025-06-23 | 2025-07-08 | 2025-07-23 | 2025-08-22 | 2025-09-21 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VA08-P0ZEN-020003 | CONTRACTORS ADMIN PLAN | PLAN |  |  |  |  | Plan |  | CONTRACTORS ADMIN PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 6 | 6.7010 | 0.4445 | 0.0294 | 0.0166 | hybrid | structured_no_system |  |  |  | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020004 | PAINTING SPECIFICATION | SPECIFICATION |  |  |  |  | Painting Specification | [5 empty] | rule_query | specification | specification | painting_specification | specification |  |  | scoped | match | mismatch | query_unscoped | rejected | blocked_deliverable_family | 0.6667 | 0.8723 | 0.7283 | 0.7283 |  | 0EF6040W70A01 | (Lighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System |  | 2007-05-30 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 9 | 6 | 8.0179 | 0.4036 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | procurement | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:blocked_deliverable_family |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020005 | PACKING SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 9 | 28 | 8.9176 | 0.4951 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | procurement |  | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020006 | NAME AND TAG PLATE | [7 empty] | NAME AND TAG PLATE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | name_and_tag_plate | name_and_tag_plate |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0PF6500W70A03.6T | (Electrical Protection Panel) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-03-11 | 2008-04-24 |  | delivery | query_unknown |  |  |  |  | electrical | query_unscoped | false | 841 | 2 |  | 0.3642 | 0.0172 | 0.0097 | hybrid | structured_no_system |  |  |  | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2025-01-11 | 2025-02-10 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020007 | ABBREVIATION LIST | LIST |  |  |  |  | LIST | [5 empty] | rule_query | other | list | list | io_list |  |  | generic | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.5843 | 0.4086 | 0.4086 |  | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | 1 | 2 | 22.6729 | 0.3418 | 0.0325 | 0.0183 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0ZEN-020008 | LABELING LAYOUT FOR WATER STORAGE TANKS | LAYOUT | WATER STORAGE TANKS |  |  |  | Layout Drawing for Tank | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6051 | 0.5315 | 0.5315 | SKIP | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 3 | 1 | 32.2001 | 0.5972 | 0.0323 | 0.0181 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020009 | TYPICAL DANGER SIGN DRAWING | DRAWING |  |  |  |  | DRAWING |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6332 | 0.6566 | 0.4596 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 27 | 28 |  | 0.3466 | 0.0229 | 0.0103 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0ZEN-020010 | UNDERGROUND PIPE MARKER DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | UNDERGROUND PIPE MARKER DETAIL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 16 | 4 | 8.0439 | 0.4468 | 0.0288 | 0.0162 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020020 | MAINTAINABILITY STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 |  | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 |  | design_criteria | query_unknown | [5 empty] | query_unscoped | true | 23 | 4 |  | 0.3709 | 0.0277 | 0.0125 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020030 | CORROSION AND MATERIAL STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 |  | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 |  | procurement | query_unknown |  |  |  |  | electrical | query_unscoped | false | 6 | 28 | 5.8171 | 0.3708 | 0.0265 | 0.0149 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020040 | FIRE STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 |  | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 6 | 4 | 6.8830 | 0.4439 | 0.0308 | 0.0173 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-050001 | BUILDING RISK ASSESSMENT | ASSESSMENT |  |  |  |  | ASSESSMENT | [5 empty] | rule_query | other | other | assessment | building_risk_assessment |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.5163 | 0.3882 | 0.2718 |  | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 33 | 17 | 4.1610 | 0.4121 | 0.0237 | 0.0134 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100001 | SITE PLAN | PLAN |  |  |  |  | Plan |  | SITE PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 2 | 33.3450 | 0.5174 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100002 | OVERALL PLOT PLAN WITH ESF AREA | PLAN |  |  |  |  | Plan |  | PipeRack Area FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  | piperack | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.4612 | 0.4883 | 0.4883 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match |  |  |  |  | stg | query_unscoped | false | 8 | 16 | 7.2689 | 0.4011 | 0.0279 | 0.0209 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100003 | OVERALL PLOT PLAN | PLAN |  |  |  |  | Plan |  | Lab FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.4978 | 0.3827 | 0.3827 | FA | 0EF3040W16A01 | (Lab) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-06-30 | civil_design | civil_design | match |  | lab | lab | rule | lab | match | false | 1 | 1 |  | 0.2804 | 0.0328 | 0.0328 | hybrid | structured_preferred | lab | civil_design | 2 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100004 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 1&2 (PLAN VIEW) | GENERAL ARRANGEMENT | GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7857 | 0.9357 | 0.9357 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | false | 1 | 1 | 33.4315 | 0.6866 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg¦hrsg | system_design | 9 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100005 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 3&4&5 (PLAN VIEW) | GENERAL ARRANGEMENT | GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7857 | 0.9357 | 0.9357 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | false | 3 | 1 | 31.6734 | 0.6797 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg¦hrsg | system_design | 9 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100006 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION A - A) | GENERAL ARRANGEMENT | GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7857 | 0.9357 | 0.9357 | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | false | 9 | 13 | 29.8421 | 0.6614 | 0.0282 | 0.0282 | hybrid | structured_preferred | gtg¦hrsg | civil_design | 10 | 2024-09-15 | 2024-10-15 | 2024-11-14 | 2024-11-29 | 2024-12-14 | 2024-12-29 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100007 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION B - B) | GENERAL ARRANGEMENT | GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for GTG & HRSG ¦ Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7857 | 0.9357 | 0.9357 | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | false | 9 | 14 | 29.8421 | 0.6649 | 0.0280 | 0.0280 | hybrid | structured_preferred | gtg¦hrsg | civil_design | 10 | 2024-09-15 | 2024-10-15 | 2024-11-14 | 2024-11-29 | 2024-12-14 | 2024-12-29 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100008 | PLANT GENERAL ARRANGEMENT FOR STG AREA (PLAN VIEW) | GENERAL ARRANGEMENT | STG ¦ Steam Turbine Generator |  |  |  | General Arrangement Drawing for STG ¦ Steam Turbine Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6881 | 0.9064 | 0.9064 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 5.6716 | 0.6201 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100009 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION A - A) | GENERAL ARRANGEMENT | STG ¦ Steam Turbine Generator |  |  |  | General Arrangement Drawing for STG ¦ Steam Turbine Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6881 | 0.9064 | 0.9064 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 4 | 31.3994 | 0.6763 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100010 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION B - B) | GENERAL ARRANGEMENT | STG ¦ Steam Turbine Generator |  |  |  | General Arrangement Drawing for STG ¦ Steam Turbine Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6881 | 0.9064 | 0.9064 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 4 | 31.3994 | 0.6729 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG05-P0ZEN-110001 | HEAT BALANCE DIAGRAMS | DIAGRAMS |  |  |  |  | DIAGRAMS |  | HEAT BALANCE DIAGRAMS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible |  |  |  |  | hrsg | query_unscoped | false | 110 | 10 | 3.1626 | 0.4934 | 0.0202 | 0.0113 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0ZEN-110002 | P&I DIAGRAM FOR SYMBOL AND LEGEND | P&I DIAGRAM |  |  |  |  | P&ID |  | GT - P&I DIAGRAM LEGEND | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | title | diagram | diagram | p_id | p_id |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7813 | 0.7594 | 0.7594 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match |  | gtg | gtg | rule |  | activity_unscoped | true | 1 | 1 | 21.8815 | 0.6844 | 0.0328 | 0.0098 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-07-22 | 2024-08-21 | 2024-09-20 | 2024-10-05 | 2024-10-20 | 2024-11-04 | generated | 0.90 | 0.23 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=activity_unscoped;activity_rule_scope_unmatched;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBA-110003 | P&I DIAGRAM FOR HP STEAM SYSTEM | P&I DIAGRAM |  | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | P&ID for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7201 | 0.5660 | 0.5660 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | false | 1 | 1 | 27.0892 | 0.7569 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBC-110004 | P&I DIAGRAM FOR IP STEAM SYSTEM | P&I DIAGRAM |  | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | P&ID for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7335 | 0.5700 | 0.5700 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | false | 1 | 2 | 27.0892 | 0.7739 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBG-110005 | P&I DIAGRAM FOR LP STEAM SYSTEM | P&I DIAGRAM |  | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | P&ID for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7047 | 0.5614 | 0.5614 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | false | 1 | 1 | 27.0892 | 0.7566 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBS-110006 | P&I DIAGRAM FOR PROCESS STEAM SYSTEM | P&I DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | P&ID for PROCESS STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7273 | 0.5682 | 0.5682 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | false | 4 | 4 | 23.7046 | 0.8064 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6LCM-110007 | P&I DIAGRAM FOR STEAM DRAIN SYSTEM | P&I DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | P&ID for STEAM DRAIN SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7033 | 0.5610 | 0.5610 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | false | 1 | 4 | 23.7046 | 0.7779 | 0.0320 | 0.0320 | hybrid | structured_preferred | steam | system_design¦procurement | 10 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6LCA-110008 | P&I DIAGRAM FOR CONDENSATE SYSTEM | P&I DIAGRAM |  | CONDENSATE SYSTEM |  |  | P&ID for CONDENSATE SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | condensate |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7209 | 0.5663 | 0.5663 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate | h2 | condensate | query | condensate | match | false | 1 | 1 | 29.6320 | 0.7999 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAA-110009 | P&I DIAGRAM FOR FEEDWATER SYSTEM | P&I DIAGRAM |  | FEEDWATER SYSTEM |  |  | P&ID for FEEDWATER SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7098 | 0.5629 | 0.5629 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater | h2 | feedwater | query | feedwater | match | false | 1 | 4 | 17.3813 | 0.7930 | 0.0320 | 0.0320 | hybrid | structured_preferred | feedwater | system_design¦procurement | 10 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0PGB-110010 | P&I DIAGRAM FOR CLOSED COOLING WATER SYSTEM | P&I DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | P&ID for CLOSED COOLING WATER SYSTEM | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7404 | 0.5721 | 0.5721 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | 29 | 18 | 31.9057 | 0.6546 | 0.0241 | 0.0144 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GHC-110011 | P&I DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | P&I DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | P&ID for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6876 | 0.5563 | 0.5563 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | h2 | wts | query | wts | match | false | 1 | 1 | 30.7530 | 0.6894 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦procurement | 10 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QJA-110012 | P&I DIAGRAM FOR NITROGEN GAS SYSTEM | P&I DIAGRAM |  | NITROGEN GAS SYSTEM |  |  | P&ID for NITROGEN GAS SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7583 | 0.5775 | 0.5775 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 | h2 | n2 | query | n2 | match | false | 1 | 1 | 34.2050 | 0.8328 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P1MBH-110013 | GTG - P&I DIAGRAM FOR GT ROTOR COOLING AIR COOLER SYSTEM | P&I DIAGRAM | GTG ¦ Gas Turbine Generator | GT ROTOR COOLING AIR COOLER SYSTEM ¦ Gas Turbine ROTOR COOLING AIR COOLER SYSTEM |  |  | P&ID for GT ROTOR COOLING AIR COOLER SYSTEM ¦ Gas Turbine ROTOR COOLING AIR COOLER SYSTEM |  | GT - GT FUEL GAS HEATER & GT COOLING AIR COOLER SYSTEM P&I DIAGRAM | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | rule_query | diagram | diagram | p_id | p_id | air¦cooler¦cooling¦gas¦generator¦gtg¦rotor¦turbine | fgp¦gt¦gtg | scoped | match | match | match | passed |  | 0.6000 | 0.7627 | 0.6488 | 0.6488 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | fgp¦gtg | gtg | query | ccw¦gtg | match | false | 608 | 32 | 18.2839 | 0.6734 | 0.0124 | 0.0124 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 | 0.77 | usable | default_fc_window;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P1EKC-110014 | P&I DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | P&I DIAGRAM |  | GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | P&ID for GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM |  | GT - FUEL GAS SYSTEM P&I DIAGRAM | 1 | start+86D<=FA<=start+86D+2M | FA ∈ [start+86d, start+146d] | rule_query | diagram | diagram | p_id | p_id | gas¦gtg¦heater¦performance¦turbine | fgp¦gt¦gtg | scoped | match | match | match | passed |  | 0.5000 | 0.7131 | 0.5639 | 0.5639 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | gtg | fgp¦gtg | gtg | query | fgp | mismatch | false | 75 | 47 | 19.8427 | 0.6116 | 0.0168 | 0.0042 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0LA-110031 | PROCESS FLOW DIAGRAM FOR STEAM/CONDENSATE/FW SYSTEM | PROCESS FLOW DIAGRAM |  | STEAM/CONDENSATE/FW SYSTEM ¦ STEAM/CONDENSATE/Feed Water SYSTEM |  |  | PROCESS FLOW DIAGRAM for STEAM/CONDENSATE/FW SYSTEM ¦ STEAM/CONDENSATE/Feed Water SYSTEM | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | rule_query | diagram | diagram | diagram | diagram | condensate¦feed¦steam¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5944 | 0.5283 | 0.5283 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | condensate¦feedwater |  | condensate¦feedwater | query | feedwater | match | false | 2 | 1 | 23.7707 | 0.7020 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate¦feedwater | system_design¦engineering | 2 | 2024-04-16 | 2024-05-21 | 2024-06-25 | 2024-06-11 | 2024-07-16 | 2024-08-20 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0PG-110032 | PROCESS FLOW DIAGRAM FOR CCW SYSTEM | PROCESS FLOW DIAGRAM |  | CCW SYSTEM ¦ Closed Cooling Water SYSTEM |  |  | PROCESS FLOW DIAGRAM for CCW SYSTEM ¦ Closed Cooling Water SYSTEM | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | title | diagram | diagram | diagram | diagram | ccw¦closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6105 | 0.5332 | 0.5332 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 31.7142 | 0.4802 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-03-15 | 2024-04-19 | 2024-05-24 | 2024-05-10 | 2024-06-14 | 2024-07-19 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GHC-110033 | PROCESS FLOW DIAGRAM FOR DM WATER SYSTEM | PROCESS FLOW DIAGRAM |  | DM WATER SYSTEM ¦ Demineralized WATER SYSTEM |  |  | PROCESS FLOW DIAGRAM for DM WATER SYSTEM ¦ Demineralized WATER SYSTEM | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | title | diagram | diagram | diagram | diagram | demineralized¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5549 | 0.5165 | 0.5165 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 25.2640 | 0.5991 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦engineering | 5 | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-110035 | DESIGN CRITERIA FOR STEAM AND BYPASS SYSTEM | DESIGN CRITERIA |  | STEAM AND BYPASS SYSTEM |  |  | DESIGN CRITERIA for STEAM AND BYPASS SYSTEM | Intake Screening System | Design Criteria | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | criteria | criteria | design_criteria | design_criteria | bypass¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5394 | 0.5818 | 0.5818 | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | [5 empty] | query_unscoped | true | 1 | 4 | 62.3058 | 0.6070 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | design_criteria¦system_design¦civil_design |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LC-110036 | DESIGN CRITERIA FOR CONDENSATE SYSTEM | DESIGN CRITERIA |  | CONDENSATE SYSTEM |  |  | DESIGN CRITERIA for CONDENSATE SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | condensate |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6209 | 0.6063 | 0.6063 | FA | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | design_criteria | civil_design | compatible | condensate | wts | condensate | query | condensate | match | false | 7 | 4 | 23.3948 | 0.6677 | 0.0306 | 0.0229 | hybrid | structured_cell_found_text_preferred | condensate | design_criteria¦system_design¦civil_design |  | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LA-110037 | DESIGN CRITERIA FOR FEEDWATER SYSTEM | DESIGN CRITERIA |  | FEEDWATER SYSTEM |  |  | DESIGN CRITERIA for FEEDWATER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6526 | 0.6158 | 0.6158 | FA | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | design_criteria | civil_design | compatible | feedwater | wts | feedwater | query | feedwater | match | false | 1 | 1 | 10.6433 | 0.6337 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater | design_criteria¦system_design¦civil_design | 10 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0PGB-110038 | DESIGN CRITERIA FOR CLOSED COOLING WATER SYSTEM | DESIGN CRITERIA |  | CLOSED COOLING WATER SYSTEM |  |  | DESIGN CRITERIA for CLOSED COOLING WATER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6211 | 0.6063 | 0.6063 | FA | 2EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | 2007-09-03 | 2008-01-30 | design_criteria | civil_design | compatible | ccw | wts | ccw | query | ccw | match | false | 3 | 2 | 38.1569 | 0.5971 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | ccw | design_criteria¦system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0GHC-110039 | DESIGN CRITERIA FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | DESIGN CRITERIA |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | DESIGN CRITERIA for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6451 | 0.6135 | 0.6135 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | design_criteria | civil_design | compatible | wts | wts | wts | query | wts | match | false | 3 | 1 | 54.7606 | 0.6092 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | wts | design_criteria¦system_design¦civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-110040 | SYSTEM DESCRIPTION FOR STEAM AND BYPASS SYSTEM | SYSTEM DESCRIPTION |  | STEAM AND BYPASS SYSTEM |  |  | System Description for STEAM AND BYPASS SYSTEM | Sampling System | System Description for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | bypass¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.6771 | 0.6406 | 0.6406 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match |  | sampling | sampling | rule | sampling | match | false | 1 | 1 | 15.1307 | 0.5730 | 0.0328 | 0.0328 | hybrid | structured_preferred | sampling | system_design¦procurement | 5 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LC-110041 | SYSTEM DESCRIPTION FOR CONDENSATE SYSTEM | SYSTEM DESCRIPTION |  | CONDENSATE SYSTEM |  |  | System Description for CONDENSATE SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | condensate |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6085 | 0.6492 | 0.5518 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 22.4052 | 0.8082 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦procurement |  | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LA-110042 | SYSTEM DESCRIPTION FOR FEEDWATER SYSTEM | SYSTEM DESCRIPTION |  | FEEDWATER SYSTEM |  |  | System Description for FEEDWATER SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | feedwater |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5742 | 0.6389 | 0.5431 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | false | 1 | 1 | 10.0830 | 0.7584 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design¦procurement | 10 | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PGB-110043 | SYSTEM DESCRIPTION FOR CLOSED COOLING WATER SYSTEM | SYSTEM DESCRIPTION |  | CLOSED COOLING WATER SYSTEM |  |  | System Description for CLOSED COOLING WATER SYSTEM | Cooling ToWer | COOLING TOWER _System Descriptions | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | description | description | system_description | system_description | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7068 | 0.5620 | 0.5620 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | 233 | 1 | 17.9791 | 0.6611 | 0.0198 | 0.0119 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GHC-110044 | SYSTEM DESCRIPTION FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | SYSTEM DESCRIPTION |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | System Description for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Sampling System | System Description for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.5732 | 0.6095 | 0.6095 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | sampling | wts | query | wts | match | false | 1 | 1 | 23.0179 | 0.6478 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦procurement | 10 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LB-110045 | PRESSURE LOSS CALCULATIONS FOR MAIN STEAM SYSTEM | CALCULATIONS |  | MAIN STEAM SYSTEM |  |  | CALCULATIONS for MAIN STEAM SYSTEM | Sampling System | Calculation Sheet for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | main¦steam |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6950 | 0.4418 | 0.4418 | FI | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | civil_design | civil_design | match | steam | sampling | steam | query | hrsg | mismatch | false | 25 | 953 | 16.7068 | 0.4379 | 0.0128 | 0.0032 | hybrid | structured_phase_gap | steam | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LC-110046 | SIZING CALCULATION FOR CONDENSATE EXTRACTION PUMP | SIZING CALCULATION | CONDENSATE EXTRACTION PUMP |  |  |  | Calculation sheet for CONDENSATE EXTRACTION PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4871 | 0.4961 | 0.4961 | SKIP | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 2 | 39.5705 | 0.5966 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LC-110047 | SIZING CALCULATION FOR FGP CONDENSATE PUMP | SIZING CALCULATION | FGP CONDENSATE PUMP ¦ Fuel Gas Package CONDENSATE PUMP |  |  |  | Calculation sheet for FGP CONDENSATE PUMP ¦ Fuel Gas Package CONDENSATE PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | condensate¦fgp¦fuel¦gas¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4720 | 0.4916 | 0.4916 | SKIP | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate¦fgp |  | condensate¦fgp | query | condensate¦fgp | match | false | 1 | 1 | 36.2630 | 0.6501 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fgp | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110048 | SIZING CALCULATION FOR HRSG FEEDWATER PUMP | SIZING CALCULATION | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | Calculation sheet for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4870 | 0.4961 | 0.4961 | SKIP | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | false | 9 | 28 | 16.0954 | 0.5338 | 0.0259 | 0.0259 | hybrid | structured_preferred | feedwater¦hrsg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110049 | SIZING CALCULATION FOR FGP FEEDWATER PUMP | SIZING CALCULATION | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | Calculation sheet for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | feedwater¦fgp¦fuel¦gas¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4688 | 0.4906 | 0.4906 | SKIP | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | civil_design | civil_design | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | false | 15 | 3 | 8.5502 | 0.6443 | 0.0292 | 0.0292 | hybrid | structured_preferred | feedwater¦fgp | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0PGB-110050 | SIZING CALCULATION FOR CLOSED COOLING WATER SYSTEM | SIZING CALCULATION |  | CLOSED COOLING WATER SYSTEM |  |  | Calculation sheet for CLOSED COOLING WATER SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5643 | 0.5193 | 0.5193 | SKIP | 1EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-01-30 | civil_design | civil_design | match | ccw | dc_ups | ccw | query | ccw | match | false | 1 | 9 | 28.9307 | 0.5496 | 0.0309 | 0.0309 | hybrid | structured_preferred | ccw | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GHC-110051 | SIZING CALCULATION FOR CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP | SIZING CALCULATION | CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP ¦ CYCLE MAKEUP WATER PUMP AND Demineralized WATER SUPPLY PUMP |  |  |  | Calculation sheet for CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP ¦ CYCLE MAKEUP WATER PUMP AND Demineralized WATER SUPPLY PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | cycle¦demineralized¦makeup¦pump¦supply¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4680 | 0.4904 | 0.4904 | SKIP | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 1 | 2 | 37.5260 | 0.5564 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0QJA-110052 | SIZING CALCULATION FOR NITROGEN GAS SYSTEM | SIZING CALCULATION |  | NITROGEN GAS SYSTEM |  |  | Calculation sheet for NITROGEN GAS SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5561 | 0.5168 | 0.5168 | SKIP | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 | dc_ups | n2 | query | n2 | match | false | 1 | 5 | 18.3083 | 0.5675 | 0.0318 | 0.0318 | hybrid | structured_preferred | n2 | civil_design | 9 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0MJ-110053 | BSEDG - CALCULATION | CALCULATION | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | Calculation sheet for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | HVAC Calculation | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | calculation | calculation | calculation | calculation | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7483 | 0.6912 | 0.6912 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg¦hvac | bsedg | query | bsedg | match | false | 1 | 2 | 7.2736 | 0.6598 | 0.0325 | 0.0325 | hybrid | structured_preferred | bsedg | civil_design | 6 | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110061 | HRSG/FGP FEEDWATER PUMP NPSH TRANSIENT ANALYSIS | ANALYSIS | HRSG/FGP FEEDWATER PUMP ¦ Heat Recovery Steam Generator/Fuel Gas Package FEEDWATER PUMP |  |  |  | ANALYSIS for HRSG/FGP FEEDWATER PUMP ¦ Heat Recovery Steam Generator/Fuel Gas Package FEEDWATER PUMP | [5 empty] | rule_query | other | drawing | analysis | drawing | feedwater¦fgp¦fuel¦gas¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg¦pump | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.7049 | 0.5615 | 0.5615 |  | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | feedwater¦fgp¦hrsg |  | feedwater¦fgp¦hrsg | query | hrsg | match | false | 37 | 24 | 16.7507 | 0.5854 | 0.0222 | 0.0167 | hybrid | structured_no_phase | feedwater¦fgp¦hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110101 | DATA SHEET FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | DATA SHEET | SAFETY RELIEF VALVE AND RUPTURE DISC | BOP SYSTEMS ¦ Balance of Plant SYSTEMS |  |  | Data Sheet for SAFETY RELIEF VALVE AND RUPTURE DISC | BYPASS VALVE & PRDS | Data Sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | datasheet | datasheet | data_sheet | data_sheet | bop¦disc¦relief¦rupture¦safety¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7348 | 0.6404 | 0.6404 | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match | bop |  | bop | query | bop | match | false | 1 | 1 | 75.5297 | 0.7006 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop | procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LF-110102 | OUTLINE DRAWING FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | OUTLINE DRAWING | SAFETY RELIEF VALVE AND RUPTURE DISC | BOP SYSTEMS ¦ Balance of Plant SYSTEMS |  |  | Outline Drawing for SAFETY RELIEF VALVE AND RUPTURE DISC | BYPASS VALVE & PRDS | Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | bop¦disc¦relief¦rupture¦safety¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7412 | 0.6424 | 0.6424 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | bop |  | bop | query |  | activity_unscoped | true | 768 | 21 | 6.9073 | 0.5323 | 0.0136 | 0.0081 | hybrid | structured_phase_gap | bop | system_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAN-110153 | DATA SHEET FOR BYPASS AND PRDS | DATA SHEET | BYPASS AND PRDS ¦ BYPASS AND Pressure Reducing and Desuperheating Station |  |  |  | Data Sheet for BYPASS AND PRDS ¦ BYPASS AND Pressure Reducing and Desuperheating Station | BYPASS VALVE & PRDS | Data Sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | bypass¦desuperheating¦prds¦pressure¦reducing¦station |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FA | 3PF1625W42A06P | (HRSG #31 Bypass Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | 2007-07-03 | 2008-04-01 | procurement | procurement | match |  |  |  |  | hrsg | query_unscoped | false | 19 | 8 | 26.9120 | 0.6160 | 0.0274 | 0.0205 | hybrid | structured_no_system |  | procurement |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MAN-110154 | OUTLINE DRAWING FOR BYPASS AND PRDS | OUTLINE DRAWING | BYPASS AND PRDS ¦ BYPASS AND Pressure Reducing and Desuperheating Station |  |  |  | Outline Drawing for BYPASS AND PRDS ¦ BYPASS AND Pressure Reducing and Desuperheating Station | BYPASS VALVE & PRDS | Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | bypass¦desuperheating¦prds¦pressure¦reducing¦station |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7924 | 0.7977 | 0.7977 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | [5 empty] | query_unscoped | true | 3 | 2 | 31.5610 | 0.6629 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | system_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0ZEN-110201 | STEAM BLOWING - OUT PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | STEAM BLOWING - OUT PROCEDURE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | procedure | procedure |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Compressed Air System (BOP) | 2008-09-02 | 2008-12-31 |  |  | query_unknown |  |  |  |  | bop¦compressed_air | query_unscoped | false | 6 | 31 | 7.7635 | 0.5223 | 0.0261 | 0.0147 | hybrid | structured_no_system |  |  |  | 2025-04-21 | 2025-05-06 | 2025-05-21 | 2025-06-05 | 2025-07-05 | 2025-08-04 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LBG-110251 | DATA SHEET FOR SILENCER | DATA SHEET | SILENCER |  |  |  | Data Sheet for SILENCER | Silencer | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | silencer |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8574 | 0.7822 | 0.7822 | FA | 1PF2510W42A04P | (Silencer) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-15 | 2008-07-15 | procurement | procurement | match |  |  |  |  | steam | query_unscoped | false | 2 | 2 | 21.2416 | 0.7137 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LBG-110252 | OUTLINE DRAWING FOR SILENCER | OUTLINE DRAWING | SILENCER |  |  |  | Outline Drawing for SILENCER |  | OUTLINE DRAWING FOR SILENCER | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | outline_drawing | outline_drawing | silencer |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match |  |  |  |  | n2 | query_unscoped | false | 1175 | 72 |  | 0.3534 | 0.0084 | 0.0063 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCP-110301 | DATA SHEET FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | DATA SHEET | CONDENSATE PLATE TYPE HEAT EXCHANGER |  |  |  | Data Sheet for CONDENSATE PLATE TYPE HEAT EXCHANGER |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | condensate¦exchanger¦heat¦plate¦type |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5777 | 0.6400 | 0.6400 | FA | 2PF3020W42A20P | (COND) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-29 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 8 | 1 | 20.4134 | 0.6561 | 0.0311 | 0.0311 | hybrid | structured_preferred | condensate | procurement | 10 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCP-110302 | OUTLINE DRAWING FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | OUTLINE DRAWING | CONDENSATE PLATE TYPE HEAT EXCHANGER |  |  |  | Outline Drawing for CONDENSATE PLATE TYPE HEAT EXCHANGER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | condensate¦exchanger¦heat¦plate¦type |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5325 | 0.6264 | 0.6264 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 14.3810 | 0.5857 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110401 | GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | GENERAL ARRANGEMENT DRAWING | CLOSED COOLING WATER PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for CLOSED COOLING WATER PUMP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | closed¦cooling¦pump¦water |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6420 | 0.8926 | 0.8926 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 14.0432 | 0.4099 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0PGB-110402 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | DRAWING | CLOSED COOLING WATER PUMP |  |  |  | DRAWING for CLOSED COOLING WATER PUMP | Cooling ToWer | COOLING TOWER_DATA & DRAWING FOR ACTUATOR | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | closed¦cooling¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6941 | 0.5582 | 0.5582 | FA | 1EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-01-30 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw | match | false | 1 | 8 | 33.3425 | 0.6114 | 0.0311 | 0.0233 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0PGB-110403 | DATA SHEET FOR CLOSED COOLING WATER PUMP | DATA SHEET | CLOSED COOLING WATER PUMP |  |  |  | Data Sheet for CLOSED COOLING WATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | closed¦cooling¦pump¦water | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6906 | 0.7322 | 0.7322 | FA | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match | ccw |  | ccw | query | ccw | match | false | 1 | 4 | 42.3791 | 0.7184 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-06-07 | 2024-07-12 | 2024-08-16 | 2024-08-02 | 2024-09-06 | 2024-10-11 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110404 | OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | OUTLINE DRAWING | CLOSED COOLING WATER PUMP MOTOR |  |  |  | Outline Drawing for CLOSED COOLING WATER PUMP MOTOR |  | Pump Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | closed¦cooling¦motor¦pump¦water | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7034 | 0.9110 | 0.9110 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 14.0432 | 0.3711 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110405 | MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | DRAWING | CLOSED COOLING WATER PUMP MOTOR |  |  |  | DRAWING for CLOSED COOLING WATER PUMP MOTOR |  | Name Plate DraWing for Pump and Motor | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | closed¦cooling¦motor¦pump¦water | pump | scoped | match | match | match | passed |  | 0.5714 | 0.6774 | 0.6032 | 0.6032 | FI | 1EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | false | 7 | 3 | 29.4028 | 0.5871 | 0.0308 | 0.0231 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0PGB-110406 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | DRAWING | CLOSED COOLING WATER PUMP MOTOR |  |  |  | DRAWING for CLOSED COOLING WATER PUMP MOTOR |  | Name Plate DraWing for Pump and Motor | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | closed¦cooling¦motor¦pump¦water | pump | scoped | match | match | match | passed |  | 0.5714 | 0.6774 | 0.6032 | 0.6032 | FI | 1EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-01-30 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw | match | false | 1 | 8 | 33.3425 | 0.5904 | 0.0311 | 0.0233 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0PGB-110407 | DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | DATA SHEET | CLOSED COOLING WATER PUMP MOTOR |  |  |  | Data Sheet for CLOSED COOLING WATER PUMP MOTOR | Cooling ToWer | COOLING TOWER _MOTOR DATA SHEET | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | closed¦cooling¦motor¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7635 | 0.7891 | 0.7891 | FA | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match | ccw |  | ccw | query | ccw | match | false | 1 | 1 | 42.3791 | 0.6830 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QJA-110500 | SYSTEM DESCRIPTION FOR NITROGEN GAS SYSTEM | SYSTEM DESCRIPTION |  | NITROGEN GAS SYSTEM |  |  | System Description for NITROGEN GAS SYSTEM | N2 Gas System | System Description | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | description | description | system_description | system_description | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8613 | 0.7834 | 0.7834 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 | n2 | n2 | query | n2 | match | false | 1 | 1 | 27.1069 | 0.8229 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | system_design¦procurement |  | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0QJA-110501 | EQUIPMENT ASSEMBLY AND DETAIL DRAWING FOR NITROGEN GAS SYSTEM | EQUIPMENT ASSEMBLY AND DETAIL DRAWING |  | NITROGEN GAS SYSTEM |  |  | EQUIPMENT ASSEMBLY AND DETAIL DRAWING for NITROGEN GAS SYSTEM | N2 Gas System | Equipment Assembly and Detail DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.8509 | 0.8678 | 0.8678 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | design_drawing | system_design | compatible | n2 | n2 | n2 | query | n2 | match | false | 1 | 1 | 25.0974 | 0.7188 | 0.0328 | 0.0246 | hybrid | structured_preferred | n2 | system_design¦civil_design | 10 | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QJA-110502 | GENERAL ARRANGEMENT DRAWING FOR NITROGEN GAS SYSTEM | GENERAL ARRANGEMENT DRAWING |  | NITROGEN GAS SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for NITROGEN GAS SYSTEM |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦nitrogen |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6557 | 0.8967 | 0.8967 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 |  | n2 | query | n2 | match | false | 1 | 1 | 20.4399 | 0.7390 | 0.0328 | 0.0328 | hybrid | structured_preferred | n2 | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QJA-110503 | DATA SHEET FOR NITROGEN GAS SYSTEM | DATA SHEET |  | NITROGEN GAS SYSTEM |  |  | Data Sheet for NITROGEN GAS SYSTEM | N2 Gas System | Instrument Data Sheet | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8225 | 0.7134 | 0.7134 | FA | 1EF3515W00A02 | (N2 Gas System) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-27 | 2007-07-31 | procurement | procurement | match | n2 | n2 | n2 | query | n2 | match | false | 1 | 1 | 28.1299 | 0.7496 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | procurement |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MJ-110504 | BSEDG - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | GENERAL ARRANGEMENT DRAWING for BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | black¦diesel¦emergency¦generator¦start |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6636 | 0.8991 | 0.8991 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg |  | bsedg | query |  | activity_unscoped | true | 111 | 307 | 13.4438 | 0.5191 | 0.0086 | 0.0051 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MJ-110505 | BSEDG - P&I DIAGRAM | P&I DIAGRAM | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | P&ID for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8412 | 0.8124 | 0.8124 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | 8 | 34 | 19.0877 | 0.6201 | 0.0253 | 0.0152 | hybrid | structured_blocked_procurement_conflict | bsedg | system_design¦procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MJ-110506 | BSEDG - OUTLINE DRAWING | OUTLINE DRAWING | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | Outline Drawing for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Equipment Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8436 | 0.7531 | 0.7531 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | 605 | 358 | 2.5734 | 0.4860 | 0.0039 | 0.0023 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MJ-110507 | BSEDG - SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | Single Line Diagram for BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7057 | 0.9117 | 0.9117 | SKIP | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg |  | bsedg | query |  | activity_unscoped | true | 27 | 278 | 13.8746 | 0.5099 | 0.0145 | 0.0087 | hybrid | structured_phase_gap | bsedg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MJ-110508 | BSEDG - DATA SHEET | DATA SHEET | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | Data Sheet for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Equipment Data Sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8546 | 0.7564 | 0.7564 | FA | 0EF3530W00A01 | (BSDG) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-03-01 | 2007-04-30 | procurement | procurement | match | bsedg | bsedg | bsedg | query | bsedg | match | false | 1 | 2 | 17.3361 | 0.7190 | 0.0325 | 0.0325 | hybrid | structured_preferred | bsedg | procurement | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0MJ-110509 | BSEDG - PIPING ISOMETRIC DRAWING | PIPING ISOMETRIC DRAWING | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | PIPING ISOMETRIC DRAWING for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Pipe Isometric DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8447 | 0.7534 | 0.7534 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | 216 | 44 | 8.5049 | 0.5914 | 0.0132 | 0.0079 | hybrid | structured_phase_gap | bsedg | system_design |  | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MJ-110510 | BSEDG - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | System Description for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | System description including Operation Philosophy | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | description | description | system_description | system_description | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.5556 | 0.8102 | 0.6320 | 0.6320 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | 119 | 104 | 8.9278 | 0.5586 | 0.0117 | 0.0070 | hybrid | structured_blocked_procurement_conflict | bsedg | system_design¦procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MJ-110511 | BSEDG - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | Control Logic Diagram for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6259 | 0.7128 | 0.7128 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg |  | bsedg | query |  | activity_unscoped | true | 35 | 373 | 13.8746 | 0.4865 | 0.0128 | 0.0077 | hybrid | structured_phase_gap | bsedg | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0MJ-110512 | BSEDG - EMBEDDED CONDUIT LAYOUT | EMBEDDED CONDUIT LAYOUT | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8758 | 0.9628 | 0.6739 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg |  | bsedg | query | bsedg | match | false | 1 | 4 | 7.2736 | 0.6952 | 0.0320 | 0.0320 | hybrid | structured_preferred | bsedg | civil_design | 6 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MJ-110561 | BSEDG - CONTROL PANEL OUTLINE DRAWING | OUTLINE DRAWING | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | Outline Drawing for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Equipment Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8436 | 0.7531 | 0.7531 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | 864 | 216 | 2.5734 | 0.5007 | 0.0047 | 0.0028 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XG11-P0MJ-110564 | BSEDG - SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | SCHEMATIC DIAGRAM for BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | schematic_diagram | schematic_diagram | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6489 | 0.6613 | 0.6613 | SKIP | 0EF3530W32A16.1 | (Common EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Common Emergency Diesel Generator | 2007-07-27 | 2007-11-27 | design_drawing | civil_design | compatible | bsedg |  | bsedg | query |  | activity_unscoped | true | 31 | 88 | 13.5569 | 0.5782 | 0.0177 | 0.0080 | hybrid | structured_phase_gap | bsedg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0MJ-110568 | BSEDG - PROTECTION RELAY SETTING REPORT | REPORT | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | REPORT for BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  | PROTECTION RELAY SETTING REPORT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8747 | 0.9624 | 0.6737 | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bsedg |  | bsedg | query | ccw¦gtg | mismatch | false | 370 | 748 | 1.0037 | 0.4365 | 0.0036 | 0.0009 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MJ-110578 | BSEDG – MV SWGR DRAWING | DRAWING | BSEDG ¦ BLACK START EMERGENCY Diesel Generator |  |  |  | DRAWING for BSEDG ¦ BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Piping Arrangement DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7660 | 0.6298 | 0.6298 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | design_drawing | civil_design | compatible | bsedg | bsedg | bsedg | query | bsedg | match | false | 1 | 2 | 7.2736 | 0.6556 | 0.0325 | 0.0244 | hybrid | structured_preferred | bsedg | system_design¦civil_design | 6 | 2025-05-01 | 2025-05-31 | 2025-06-30 | 2025-07-15 | 2025-07-30 | 2025-08-14 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110601 | VALVE LIST & DATA SHEET FOR MOV (G&G) | VALVE LIST & DATA SHEET | MOV ¦ Motor Operated Valve |  |  |  | Valve List for MOV ¦ Motor Operated Valve |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | motor¦mov¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6973 | 0.6759 | 0.6759 | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 1 | 79.7603 | 0.7233 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-110602 | OUTLINE DRAWING FOR MOV (G&G) | OUTLINE DRAWING | MOV ¦ Motor Operated Valve |  |  |  | Outline Drawing for MOV ¦ Motor Operated Valve |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | motor¦mov¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6350 | 0.8905 | 0.8905 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | 556 | 195 | 5.3193 | 0.4454 | 0.0055 | 0.0033 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110603 | VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | VALVE LIST & DATA SHEET | MOV ¦ Motor Operated Valve |  |  |  | Valve List for MOV ¦ Motor Operated Valve |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | motor¦mov¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6973 | 0.6759 | 0.6759 | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 1 | 79.7603 | 0.7342 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-110604 | OUTLINE DRAWING FOR MOV (BUTTERFLY) | OUTLINE DRAWING | MOV ¦ Motor Operated Valve |  |  |  | Outline Drawing for MOV ¦ Motor Operated Valve |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | motor¦mov¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6350 | 0.8905 | 0.8905 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | 505 | 78 | 5.3193 | 0.4470 | 0.0090 | 0.0054 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110701 | OPERATION PHILOSOPHY OF OVERALL PLANT | OPERATION PHILOSOPHY |  |  |  |  | OPERATION PHILOSOPHY |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.2500 | 0.4212 | 0.3013 | 0.3013 | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | 6 | 9 | 15.6495 | 0.4584 | 0.0296 | 0.0167 | hybrid | structured_no_system | [9 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110702 | PLANT START-UP AND SHUT-DOWN PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | PLANT start - UP AND SHUT - DOWN PROCEDURE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | procedure | procedure |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9355 | 0.9807 | 0.6865 | FA | 0SF7000W62A08 | (DCS) Start up | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-02 | 2008-07-11 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | 1 | 4 | 15.9027 | 0.5304 | 0.0320 | 0.0180 | hybrid | structured_no_system |  |  |  | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-04-04 | 2025-05-04 | 2025-06-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110703 | HAZARD AND OPERABILITY STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 |  | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 1 | 1412 | 4.2192 | 0.2942 | 0.0171 | 0.0128 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110704 | SAFETY INTEGRITY LEVEL STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 |  | 0PF6050W86A04.1T | (Safety Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2008-05-24 | 2008-07-08 |  | delivery | query_unknown |  |  |  |  | bop | query_unscoped | false | 4 | 25 | 11.5474 | 0.3922 | 0.0274 | 0.0154 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110705 | HAZARDOUS AREA CLASSIFICATION REPORT | REPORT |  |  |  |  | Hazardous Area Classification |  | GT - HAZARDOUS AREA CLASSIFICATION | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | classification | classification | hazardous_area_classification | hazardous_area_classification |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8089 | 0.7677 | 0.7677 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  | gtg | gtg | rule | ccw¦gtg | match | false | 1 | 1 |  | 0.3454 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110706 | HAZOP AND SIL STUDY PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.4221 | 0.4766 | 0.4766 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 28 | 3058 | 4.2192 | 0.3344 | 0.0117 | 0.0088 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GKB-120001 | P&I DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | P&I DIAGRAM |  | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | P&ID for POTABLE WATER STORAGE AND SUPPLY SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | potable¦storage¦supply¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6937 | 0.6748 | 0.6748 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts | h2 | wts | query | wts | match | false | 1 | 1 | 53.6325 | 0.7591 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GKC-120002 | P&I DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | P&I DIAGRAM |  | POTABLE WATER DISTRIBUTION SYSTEM |  |  | P&ID for POTABLE WATER DISTRIBUTION SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | distribution¦potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6436 | 0.5431 | 0.5431 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts | h2 | wts | query | wts | match | false | 1 | 1 | 43.8375 | 0.7558 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120004 | P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | P&I DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | P&ID for COMPRESSED AIR SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7275 | 0.5683 | 0.5683 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | h2 | compressed_air | query | compressed_air | match | false | 1 | 1 | 42.1472 | 0.7797 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120005 | P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | P&I DIAGRAM |  | INSTRUMENT AIR SYSTEM |  |  | P&ID for INSTRUMENT AIR SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦instrument |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7293 | 0.5688 | 0.5688 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | h2 | compressed_air | query | compressed_air | match | false | 5 | 1 | 25.8024 | 0.7249 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120006 | P&I DIAGRAM FOR SERVICE AIR SYSTEM | P&I DIAGRAM |  | SERVICE AIR SYSTEM |  |  | P&ID for SERVICE AIR SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦service |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6992 | 0.5598 | 0.5598 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | h2 | compressed_air | query | compressed_air | match | false | 5 | 1 | 25.8024 | 0.7159 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0EK-120007 | P&I DIAGRAM FOR FUEL GAS SYSTEM | P&I DIAGRAM |  | FUEL GAS SYSTEM |  |  | P&ID for FUEL GAS SYSTEM | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8032 | 0.7660 | 0.7660 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 27.2811 | 0.7746 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-120008 | P&I DIAGRAM FOR WASTE WATER TRANSFER SYSTEM | P&I DIAGRAM |  | WASTE WATER TRANSFER SYSTEM |  |  | P&ID for WASTE WATER TRANSFER SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | transfer¦waste¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6807 | 0.5542 | 0.5542 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | h2 | wts | query | wts | match | false | 1 | 1 | 40.9993 | 0.7320 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GKS-120012 | DESIGN CRITERIA FOR POTABLE WATER SYSTEM | DESIGN CRITERIA |  | POTABLE WATER SYSTEM |  |  | DESIGN CRITERIA for POTABLE WATER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6420 | 0.6126 | 0.6126 | FA | 0EF3035W16A14 | (PWT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-11-02 | 2008-03-04 | design_criteria | civil_design | compatible | wts | wts | wts | query | wts | match | false | 3 | 2 | 35.0193 | 0.5962 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | wts | design_criteria¦system_design¦civil_design |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GKS-120013 | SIZING CALCULATION - POTABLE WATER DISTRIBUTION PUMP | SIZING CALCULATION | POTABLE WATER DISTRIBUTION PUMP |  |  |  | Calculation sheet for POTABLE WATER DISTRIBUTION PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | distribution¦potable¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5154 | 0.5046 | 0.5046 | SKIP | 0EF3035W16A14 | (PWT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-11-02 | 2008-03-04 | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 1 | 2 | 23.5163 | 0.5418 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SCA-120014 | PROCESS FLOW DIAGRAM FOR COMPRESSED AIR SYSTEM | PROCESS FLOW DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | PROCESS FLOW DIAGRAM for COMPRESSED AIR SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6337 | 0.8901 | 0.6231 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 35.3482 | 0.6720 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SCA-120015 | SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | SYSTEM DESCRIPTION |  | COMPRESSED AIR SYSTEM |  |  | System Description for COMPRESSED AIR SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | title | description | description | system_description | system_description | air¦compressed |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6218 | 0.6532 | 0.5552 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 34.7443 | 0.7578 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | generated | 0.60 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SCA-120016 | DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | DESIGN CRITERIA |  | COMPRESSED AIR SYSTEM |  |  | DESIGN CRITERIA for COMPRESSED AIR SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5608 | 0.5882 | 0.5882 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_criteria | system_design | compatible | compressed_air | wts | compressed_air | query | compressed_air | match | false | 2 | 3 | 35.0666 | 0.5859 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | compressed_air | design_criteria¦system_design¦civil_design |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SCA-120017 | SIZING CALCULATION - COMPRESSED AIR SYSTEM | SIZING CALCULATION |  | COMPRESSED AIR SYSTEM |  |  | Calculation sheet for COMPRESSED AIR SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6166 | 0.5350 | 0.5350 | SKIP | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | civil_design | civil_design | match | compressed_air | dc_ups | compressed_air | query | compressed_air | match | false | 2 | 1 | 23.9477 | 0.5954 | 0.0325 | 0.0325 | hybrid | structured_preferred | compressed_air | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0EKG-120018 | PROCESS FLOW DIAGRAM FOR FUEL GAS SYSTEM | PROCESS FLOW DIAGRAM |  | FUEL GAS SYSTEM |  |  | PROCESS FLOW DIAGRAM for FUEL GAS SYSTEM | Fuel Gas System | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | rule_query | diagram | diagram | diagram | diagram | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8183 | 0.7705 | 0.7705 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 22.7650 | 0.7007 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design¦engineering | 2 | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-120019 | SYSTEM DESCRIPTION FOR FUEL GAS SYSTEM | SYSTEM DESCRIPTION |  | FUEL GAS SYSTEM |  |  | System Description for FUEL GAS SYSTEM | Fuel Gas System | System description | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | rule_query | description | description | system_description | system_description | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 1.0000 | 0.9117 | 0.9735 | 0.9735 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 19.7835 | 0.7313 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-120020 | DESIGN CRITERIA FOR FUEL GAS SYSTEM | DESIGN CRITERIA |  | FUEL GAS SYSTEM |  |  | DESIGN CRITERIA for FUEL GAS SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | criteria | criteria | design_criteria | design_criteria | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5649 | 0.5895 | 0.5895 | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | design_criteria | civil_design | compatible | fgp | wts | fgp | query | fgp¦gtg | match | false | 1 | 2 | 20.9022 | 0.6434 | 0.0325 | 0.0244 | hybrid | structured_preferred | fgp | design_criteria¦system_design¦civil_design | 10 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0EKG-120021 | SIZING CALCULATION - FUEL GAS SYSTEM | SIZING CALCULATION |  | FUEL GAS SYSTEM |  |  | Calculation sheet for FUEL GAS SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5952 | 0.5286 | 0.5286 | SKIP | 0EF3520W16A01 | (Gas Buffer) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-08-02 | 2007-12-04 | civil_design | civil_design | match | fgp | dc_ups | fgp | query | fgp | match | false | 5 | 31 | 10.4590 | 0.5620 | 0.0264 | 0.0264 | hybrid | structured_preferred | fgp | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GM-120022 | SYSTEM DESCRIPTION FOR WASTE WATER TRANSFER SYSTEM | SYSTEM DESCRIPTION |  | WASTE WATER TRANSFER SYSTEM |  |  | System Description for WASTE WATER TRANSFER SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | transfer¦waste¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5377 | 0.6280 | 0.5338 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 33.6246 | 0.6912 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GM-120023 | DESIGN CRITERIA FOR WASTE WATER TRANSFER SYSTEM | DESIGN CRITERIA |  | WASTE WATER TRANSFER SYSTEM |  |  | DESIGN CRITERIA for WASTE WATER TRANSFER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | transfer¦waste¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6499 | 0.6150 | 0.6150 | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | design_criteria | civil_design | compatible | wts | wts | wts | query | wts | match | false | 7 | 2 | 34.2095 | 0.5748 | 0.0311 | 0.0233 | hybrid | structured_cell_found_text_preferred | wts | design_criteria¦system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0ZEN-120050 | WATER BALANCE DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | GT - GENERATOR COOLING WATER DIAGRAM | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | title | diagram | diagram | diagram | diagram |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.5718 | 0.4515 | 0.4515 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible |  | gtg | gtg | rule | ccw¦gtg | match | false | 1 | 2 | 1.7129 | 0.3681 | 0.0325 | 0.0244 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GKS-120051 | SYSTEM DESCRIPTION FOR POTABLE WATER SYSTEM | SYSTEM DESCRIPTION |  | POTABLE WATER SYSTEM |  |  | System Description for POTABLE WATER SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | potable¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5764 | 0.6396 | 0.5436 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 36.1024 | 0.7404 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | generated | 0.60 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MBA-121001 | GTG - EQUIPMENT ARRANGEMENT | ARRANGEMENT | GTG ¦ Gas Turbine Generator |  |  |  | ARRANGEMENT for GTG ¦ Gas Turbine Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | title | other | other | arrangement | arrangement | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5028 | 0.3842 | 0.3265 | FA | 2EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | false | 2 | 2 | 14.3007 | 0.6679 | 0.0323 | 0.0242 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121002 | GTG - GT EXHAUST MECHANICAL INTERFACE REQUIREMENTS | REQUIREMENTS | GTG ¦ Gas Turbine Generator | GT EXHAUST SYSTEM ¦ Gas Turbine EXHAUST SYSTEM |  |  | REQUIREMENTS for GTG ¦ Gas Turbine Generator |  | Gas Turbine EXHAUST MECHANICAL INTERFACE REQUIREMENTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | requirements | requirements | design_requirements | design_requirements | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.5000 | 0.6223 | 0.5367 | 0.3757 | FA | 1PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | 2008-02-01 | 2008-03-17 |  | delivery | query_unknown | gtg | gtg | gtg | query | gtg | match | false | 1 | 4 | 32.1142 | 0.6737 | 0.0320 | 0.0240 | hybrid | structured_no_phase | gtg |  |  | 2024-09-19 | 2024-10-04 | 2024-10-19 | 2024-11-03 | 2024-12-03 | 2025-01-02 | generated | 0.30 | 0.64 | usable | rule_score_medium;activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MBA-121003 | GTG - P&I DIAGRAM | P&I DIAGRAM | GTG ¦ Gas Turbine Generator |  |  |  | P&ID for GTG ¦ Gas Turbine Generator |  | GT - P&I DIAGRAM LEGEND | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | title | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.5000 | 0.8113 | 0.5934 | 0.5934 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | gtg | gtg | query | ccw¦gtg | match | false | 634 | 29 | 7.5809 | 0.6878 | 0.0127 | 0.0127 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 | 0.77 | usable | default_fc_window;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121004 | GTG - ROTOR COOLING AIR SYSTEM REQUIREMENTS | REQUIREMENTS | GTG ¦ Gas Turbine Generator | ROTOR COOLING AIR SYSTEM |  |  | REQUIREMENTS for GTG ¦ Gas Turbine Generator |  | Gas Turbine EXHAUST MECHANICAL INTERFACE REQUIREMENTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | requirements | requirements | design_requirements | design_requirements | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.5000 | 0.6223 | 0.5367 | 0.3757 | FA | 2PF1265W42A14T | (TCA Cooler) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | 2008-04-01 | 2008-05-15 |  | delivery | query_unknown | gtg | gtg | gtg | query | fgp¦gtg | match | false | 3 | 1 | 16.9491 | 0.6611 | 0.0323 | 0.0242 | hybrid | structured_no_phase | gtg |  |  | 2024-11-18 | 2024-12-03 | 2024-12-18 | 2025-01-02 | 2025-02-01 | 2025-03-03 | generated | 0.30 | 0.64 | usable | rule_score_medium;activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121005 | GTG - GOVERNOR AND TURBINE MODEL | MODEL | GTG ¦ Gas Turbine Generator |  |  |  | MODEL for GTG ¦ Gas Turbine Generator |  | GOVERNOR AND TURBINE MODEL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | model | model | model | model | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8314 | 0.9494 | 0.6646 | FA | 2SF9012W62A04 | (GTG #21) TBN & GEN Protection Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | 2008-10-05 | 2008-10-06 |  | commissioning | query_unknown | gtg |  | gtg | query | gtg | match | false | 134 | 2 | 9.4750 | 0.6809 | 0.0213 | 0.0160 | hybrid | structured_no_phase | gtg |  |  | 2025-05-24 | 2025-06-08 | 2025-06-23 | 2025-07-08 | 2025-08-07 | 2025-09-06 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121006 | GTG - GENERATOR, EXCITATION SYSTEM, AND POWER SYSTEM STABILIZER MODEL | MODEL | GTG ¦ Gas Turbine Generator | EXCITATION SYSTEM |  |  | MODEL for GTG ¦ Gas Turbine Generator |  | GOVERNOR AND TURBINE MODEL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | model | model | model | model | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6312 | 0.5394 | 0.3776 | FA | 2CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | 2008-06-02 | 2008-06-14 |  | installation | query_unknown | gtg |  | gtg | query | gtg | match | false | 5 | 109 | 13.3449 | 0.6365 | 0.0213 | 0.0160 | hybrid | structured_no_phase | gtg |  |  | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-04-04 | 2025-05-04 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0MBA-121007 | GTG - AUXILIARY EQUIPMENT FOUNDATION INTERFACE DRAWINGS | DRAWINGS | GTG ¦ Gas Turbine Generator |  |  |  | DRAWINGS for GTG ¦ Gas Turbine Generator |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.7454 | 0.7836 | 0.7836 | FA | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | false | 13 | 1 | 10.6670 | 0.7023 | 0.0301 | 0.0301 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-09-10 | 2024-10-10 | 2024-11-09 | 2024-11-24 | 2024-12-09 | 2024-12-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBA-121008 | GTG - CUSTOMER PIPING CONNECTIONS PHYSICAL AND PROCESS DATA | DATA | GTG ¦ Gas Turbine Generator | PIPING |  |  | DATA for GTG ¦ Gas Turbine Generator | Process Metering | Heat Loss Data | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | data | data | data | data | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.4266 | 0.4080 | 0.4080 | FI | 2PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | 2007-03-30 | 2008-02-29 | procurement | procurement | match | gtg |  | gtg | query | gtg | match | false | 5 | 14 | 16.6255 | 0.6525 | 0.0289 | 0.0289 | hybrid | structured_preferred | gtg | procurement | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MBA-121009 | GTG - INLET FILTER AND DUCT SUPPLIER DRAWINGS | DRAWINGS | GTG ¦ Gas Turbine Generator |  |  |  | DRAWINGS for GTG ¦ Gas Turbine Generator |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.7454 | 0.7836 | 0.7836 | FA | 1EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2007-08-31 | design_drawing | civil_design | compatible | gtg | gtg | gtg | query | fgp¦gtg | match | false | 1 | 11 | 12.0943 | 0.6011 | 0.0305 | 0.0229 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MBA-121010 | GTG_STG-PAC INSTRUCTION BOOK VOLUME I (GAS TURBINE AND AUXILIARIES | INSTRUCTION BOOK | GTG STG-PAC ¦ Gas Turbine Generator Steam Turbine Generator-PAC |  |  |  | INSTRUCTION BOOK for GTG STG-PAC ¦ Gas Turbine Generator Steam Turbine Generator-PAC | [5 empty] | rule_query | other | other | instruction_book | gt_generator_outline | gas¦generator¦gtg¦pac¦steam¦stg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6280 | 0.6551 | 0.6551 |  | 1CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | 2008-05-03 | 2008-05-16 |  | installation | query_unknown | gtg¦stg |  | gtg¦stg | query | gtg | match | false | 71 | 5 | 18.9455 | 0.6334 | 0.0230 | 0.0173 | hybrid | structured_no_phase | gtg¦stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MBA-121011 | GTG - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | GTG ¦ Gas Turbine Generator |  |  |  | System Description for GTG ¦ Gas Turbine Generator |  | GT - SYSTEM DESCRIPTION | 1 | start+158D<=FA<=start+158D+2M | FA ∈ [start+158d, start+218d] | rule_query | description | description | system_description | system_description | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 0.6585 | 0.8976 | 0.8976 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | gtg | gtg | query | ccw¦gtg | match | false | 1194 | 30 | 7.5809 | 0.6615 | 0.0119 | 0.0119 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-08-06 | 2024-09-05 | 2024-10-05 | 2024-10-20 | 2024-11-04 | 2024-11-19 | generated | 0.90 | 0.77 | usable | default_fc_window;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MBA-121012 | GTG - GENERATOR/MEDIUM VOLTAGE SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | GTG ¦ Gas Turbine Generator |  |  |  | Single Line Diagram for GTG ¦ Gas Turbine Generator |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7353 | 0.9206 | 0.9206 | SKIP | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 1 | 8.5847 | 0.6568 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121013 | GTG - GENERATOR CAPABILITY CURVES AND DATA | DATA | GTG ¦ Gas Turbine Generator |  |  |  | Generator Capability Curves and Data for GTG ¦ Gas Turbine Generator |  | GENERATOR CAPABILITY CURVES AND DATA | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | curve | curve | generator_capability_curve | generator_capability_curve | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8630 | 0.9589 | 0.6712 | FA | 1EF1225W00A02.1 | (CCWP) Key data for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | 2007-03-01 | 2007-05-01 | procurement | procurement | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 4 | 16.3026 | 0.6035 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | installation¦erection¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121014 | GTG - GENERATOR ISOPHASE BUS INTERFACE | INTERFACE | GTG ¦ Gas Turbine Generator |  |  |  | INTERFACE for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | interface | gt_generator_outline | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.7214 | 0.6831 | 0.6831 |  | 1CF1213W52A11 | (GTG #11) Insulation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2008-06-16 | 2008-06-30 |  |  | query_unknown | gtg |  | gtg | query | gtg | match | false | 5 | 21 | 8.7584 | 0.6670 | 0.0277 | 0.0208 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121015 | GTG - DESIGN REQUIREMENTS FOR VT & SURGE, BAB36 | DESIGN REQUIREMENTS | GTG ¦ Gas Turbine Generator |  |  |  | DESIGN REQUIREMENTS for GTG ¦ Gas Turbine Generator |  | DESIGN REQUIREMENTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | requirements | requirements | design_requirements | design_requirements | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6253 | 0.6542 | 0.4580 | FA | 3EF1210W20A09 | (GTG Common BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-08-31 |  | civil_design | query_unknown | gtg |  | gtg | query | gtg | match | false | 6 | 1 | 13.5741 | 0.6485 | 0.0315 | 0.0237 | hybrid | structured_no_phase | gtg |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL06-P0MBA-121016 | GTG - ELECTRICAL LOAD LIST | LIST | GTG ¦ Gas Turbine Generator |  |  |  | LIST for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | list | list | valve_list | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7143 | 0.7509 | 0.7253 | 0.7253 |  | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2007-03-30 | 2008-04-29 | procurement | procurement | match | gtg |  | gtg | query | electrical¦gtg | match | false | 2 | 1 | 10.7034 | 0.6930 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | procurement | 10 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU05-P0MBA-121017 | GTG - THREE - LINE SCHEMATICS | THREE - LINE SCHEMATICS | GTG ¦ Gas Turbine Generator |  |  |  | THREE - LINE SCHEMATICS for GTG ¦ Gas Turbine Generator |  | Single line /Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | schematic_diagram | schematic_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.2500 | 0.6235 | 0.3620 | 0.3620 | SKIP | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2007-04-30 | 2008-05-28 | procurement | procurement | match | gtg |  | gtg | query | electrical¦gtg | match | false | 11 | 4 | 14.7571 | 0.7270 | 0.0297 | 0.0297 | hybrid | structured_cell_found_text_preferred | gtg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MBA-121018 | GTG - MCC & 125VDC SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | GTG ¦ Gas Turbine Generator |  |  |  | Single Line Diagram for GTG ¦ Gas Turbine Generator |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7353 | 0.9206 | 0.9206 | SKIP | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 1 | 7.5809 | 0.6523 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0MBA-121019 | GTG - CUSTOMER ELECTRICAL CONNECTIONS |  | GTG ¦ Gas Turbine Generator |  |  |  | for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | gtg_customer_electrical_connections | gt_generator_outline | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6961 | 0.6755 | 0.6755 |  | 1CF1255W70A03 | (GTG#11 Electrical) Installation- PCC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-01 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | false | 10 | 7 | 10.7767 | 0.6893 | 0.0292 | 0.0219 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121020 | GTG - ELECTRICAL SCHEMATICS | SCHEMATICS | GTG ¦ Gas Turbine Generator |  |  |  | SCHEMATICS for GTG ¦ Gas Turbine Generator | GENERATOR CIRCUIT BREAKER | Schematic diagram | 1 | start+8M<=FA<=start+8M+2M | FA ∈ [start+240d, start+300d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.2000 | 0.6183 | 0.3255 | 0.3255 | FA | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2007-03-30 | 2008-04-29 | procurement | procurement | match | gtg |  | gtg | query | electrical¦gtg | match | false | 2 | 1 | 17.8879 | 0.7736 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gtg | system_design¦engineering |  | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 0.61 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_score_medium;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0MBA-121021 | GTG - ABOVE - GRADE FIELD CONDUIT PLAN | PLAN | GTG ¦ Gas Turbine Generator |  |  |  | Plan for GTG |  | GTG LEB FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.5000 | 0.6383 | 0.5415 | 0.5415 | FA | 1SF9012W62A04 | (GTG #11) TBN & GEN Protection Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-10-22 | 2008-10-23 |  | commissioning | query_unknown | gtg | gtg | gtg | query | gtg | match | false | 3 | 133 | 7.7356 | 0.6005 | 0.0211 | 0.0158 | hybrid | structured_no_phase | gtg |  |  | 2025-06-10 | 2025-06-25 | 2025-07-10 | 2025-07-25 | 2025-08-24 | 2025-09-23 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121022 | GTG - CABLE AND CONDUIT LIST | LIST | GTG ¦ Gas Turbine Generator |  |  |  | LIST for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | list | list | valve_list | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7143 | 0.7509 | 0.7253 | 0.7253 |  | 2CF1255W74A09 | (GTG#21 Electrical) Cable work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2008-08-01 | 2008-09-15 |  |  | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | false | 4 | 2 | 14.0908 | 0.6952 | 0.0318 | 0.0238 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121023 | GTG_ELECTRICAL PROTECTION AND OPERATION SETTINGS |  | GTG ¦ Gas Turbine Generator |  |  |  | for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | settings | gt_generator_outline | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6961 | 0.6755 | 0.6755 |  | 1CF1255W70A05 | (GTG#11 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-01 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | false | 1 | 2 | 17.7450 | 0.7218 | 0.0325 | 0.0244 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121024 | GTG - DCS SIGNAL INTERFACE INFORMATION |  | GTG ¦ Gas Turbine Generator |  |  |  | for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | gtg_dcs_signal_interface_information | gt_generator_outline | dcs¦gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6961 | 0.6755 | 0.6755 |  | 2PF1255W70A02T | (GTG#21 Electrical) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2008-04-30 | 2008-06-13 |  | delivery | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | false | 32 | 11 | 7.6777 | 0.6656 | 0.0250 | 0.0187 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121025 | GTG - INSTRUMENT, VALVE AND CONTROL SETTINGS LIST | LIST | GTG ¦ Gas Turbine Generator |  |  |  | LIST for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | list | list | valve_list | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7143 | 0.7509 | 0.7253 | 0.7253 |  | 2EF1200W00A02 | (GTG #21/#22) Instrument, Service Air, Aux steam Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-29 |  |  | query_unknown | gtg |  | gtg | query | compressed_air¦gtg¦steam | match | false | 14 | 1 | 14.1872 | 0.7151 | 0.0299 | 0.0224 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121026 | GTG - CONTROL PHILOSOPHY | PHILOSOPHY | GTG ¦ Gas Turbine Generator | CONTROL |  |  | PHILOSOPHY for CONTROL | Air Compressor | Control Philosophy | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | description | description | control_description | control_description | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5164 | 0.5049 | 0.5049 | FA | 2PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | 2007-03-30 | 2008-02-29 | procurement | procurement | match | gtg | compressed_air | gtg | query | gtg | match | false | 3 | 10 | 21.0836 | 0.6707 | 0.0302 | 0.0302 | hybrid | structured_cell_found_text_preferred | gtg | procurement |  | 2024-06-22 | 2024-07-22 | 2024-08-21 | 2024-09-05 | 2024-09-20 | 2024-10-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121027 | GTG - CONTROL SYSTEM DESCRIPTION | DESCRIPTION | GTG ¦ Gas Turbine Generator | CONTROL SYSTEM |  |  | DESCRIPTION for CONTROL SYSTEM |  | GT - SYSTEM DESCRIPTION | 1 | start+158D<=FA<=start+158D+2M | FA ∈ [start+158d, start+218d] | title | description | description | system_description | system_description | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7788 | 0.7003 | 0.7003 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | gtg | gtg | query | ccw¦gtg | match | false | 1423 | 57 | 7.5809 | 0.6598 | 0.0092 | 0.0092 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121028 | GTG - CONTROL SYSTEM INPUT/OUTPUT DATABASE (I/O DATABASE) | DATABASE | GTG ¦ Gas Turbine Generator | CONTROL SYSTEM |  |  | DATABASE for GTG ¦ Gas Turbine Generator |  | INPUT/OUTPUT DATABASE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6805 | 0.9042 | 0.6329 | FA | 2CF1255W86A06 | (GTG#21 Electrical) Installation- GT control Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2008-08-04 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | false | 15 | 4 | 15.2845 | 0.6622 | 0.0290 | 0.0217 | hybrid | structured_no_phase | gtg |  |  | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-06-06 | 2025-07-06 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121029 | GTG - POWER SUPPLY DISTRIBUTION DRAWING | DRAWING | GTG ¦ Gas Turbine Generator |  |  |  | DRAWING for GTG ¦ Gas Turbine Generator |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6000 | 0.6850 | 0.6255 | 0.6255 | FA | 2CF1265W16A12 | (TCA Cooler) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | 2007-10-31 | 2007-12-31 | design_drawing | civil_design | compatible | gtg | gtg | gtg | query | fgp¦gtg | match | false | 2 | 55 | 9.2360 | 0.6050 | 0.0248 | 0.0186 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2025-02-10 | 2025-03-12 | 2025-04-11 | 2025-04-26 | 2025-05-11 | 2025-05-26 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121030 | GTG - DATA SHEETS FOR I&C EQUIPMENT | DATA SHEETS | GTG ¦ Gas Turbine Generator | I&C ¦ Instrumentation and Control |  |  | DATA SHEETS for GTG ¦ Gas Turbine Generator |  | GT - SPECIFICATION OF GAS DETECTOR | 1 | start+172D<=FA<=start+172D+2M | FA ∈ [start+172d, start+232d] | rule_query | datasheet | specification | data_sheet | gas_detector_specification | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | compatible | not_applicable | match | passed |  | 0.4000 | 0.5805 | 0.4541 | 0.4541 | FA | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2007-03-30 | 2008-04-29 | procurement | procurement | match | gtg | gtg | gtg | query | electrical¦gtg | match | false | 34 | 1 | 14.7571 | 0.6844 | 0.0270 | 0.0270 | hybrid | structured_preferred | gtg | procurement | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_family_uncertain:compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0MBA-121031 | GTG - CABINET / PANEL TERMINAL BLOCK DETAILS |  | GTG ¦ Gas Turbine Generator |  |  |  | for GTG |  | GTG LEB FOUNDATION REINF. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5341 | 0.3002 | 0.3002 | FA | 3CF1255W70A03 | (GTG#31 Electrical) Installation- PCC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-01 | 2008-09-15 |  | installation | query_unknown | gtg | gtg | gtg | query | electrical¦gtg | match | false | 60 | 4 | 7.8969 | 0.6501 | 0.0240 | 0.0180 | hybrid | structured_no_phase | gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0MBA-121032 | GTG - HMI GRAPHIC | GRAPHIC | GTG ¦ Gas Turbine Generator |  |  |  | GRAPHIC for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | graphic | gt_generator_outline | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.7422 | 0.6893 | 0.6893 |  | 2PF1255W70A02T | (GTG#21 Electrical) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2008-04-30 | 2008-06-13 |  | delivery | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | false | 22 | 4 | 7.6777 | 0.6662 | 0.0278 | 0.0209 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121033 | GTG - CONTROL SYSTEM OVERVIEW | OVERVIEW | GTG ¦ Gas Turbine Generator | CONTROL SYSTEM |  |  | OVERVIEW for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | overview | gt_generator_outline | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.7450 | 0.6902 | 0.6902 |  | 2CF1255W86A06 | (GTG#21 Electrical) Installation- GT control Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2008-08-04 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | false | 8 | 1 | 15.7943 | 0.6942 | 0.0311 | 0.0233 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121034 | GTG - FOUNDATION DESIGN BASIS DOCUMENT | DOCUMENT | GTG ¦ Gas Turbine Generator |  |  |  | DOCUMENT for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | document | gt_generator_outline | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.7272 | 0.6848 | 0.6848 |  | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-08-01 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | false | 2 | 4 | 12.4898 | 0.7422 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121035 | GTG - POWER BLOCK FOUNDATION GENERAL NOTES |  | GTG ¦ Gas Turbine Generator |  |  |  | for GTG ¦ Gas Turbine Generator |  | GENERAL NOTES FORMWORK | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | notes | notes | general_notes | general_notes | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5855 | 0.6423 | 0.4496 | FA | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-08-01 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | false | 22 | 4 | 9.5819 | 0.7473 | 0.0278 | 0.0278 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0CY-121036 | GTG – ELECTRICAL PACKAGE COMMUNICATION LAYOUT DRAWING | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator | Communication System & Security System |  |  | Layout Drawing for GTG |  | ELECTRICAL PACKAGE COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8600 | 0.9580 | 0.6706 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | false | 11 | 4 | 9.0570 | 0.6685 | 0.0297 | 0.0223 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121037 | GTG - PSS STUDY REPORT_DRAFT | REPORT | GTG ¦ Gas Turbine Generator |  |  |  | REPORT for GTG ¦ Gas Turbine Generator |  | PSS STUDY REPORT_DRAFT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | study_report | study_report | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8104 | 0.9431 | 0.6602 | FA | 2SF9013W62A11 | (GTG #21) Reliability Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | 2008-12-05 | 2008-12-19 |  | commissioning | query_unknown | gtg |  | gtg | query | gtg | match | false | 8 | 2 | 7.7314 | 0.6825 | 0.0308 | 0.0231 | hybrid | structured_no_phase | gtg |  |  | 2025-07-24 | 2025-08-08 | 2025-08-23 | 2025-09-07 | 2025-10-07 | 2025-11-06 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MBA-121038 | GTG_STG-PAC INSTRUCTION BOOK VOLUME II (GENERATOR AND AUXILIARIES) | INSTRUCTION BOOK VOLUME II | GTG STG ¦ Gas Turbine Generator Steam Turbine Generator |  |  |  | INSTRUCTION BOOK VOLUME II for GTG STG ¦ Gas Turbine Generator Steam Turbine Generator | [5 empty] | rule_query | other | other | instruction_book_volume_ii | gt_generator_outline | gas¦generator¦gtg¦steam¦stg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6250 | 0.6542 | 0.6542 |  | 1CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | 2008-05-03 | 2008-05-16 |  | installation | query_unknown | gtg¦stg |  | gtg¦stg | query | gtg | match | false | 110 | 4 | 13.9195 | 0.6336 | 0.0215 | 0.0161 | hybrid | structured_no_phase | gtg¦stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MBA-121044 | GTG - ACCESS PLATFORM LAYOUT | LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | ACCESS PLATFORM LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7204 | 0.9161 | 0.6413 | FA | 2EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | false | 5 | 2 | 10.6049 | 0.7088 | 0.0315 | 0.0236 | hybrid | structured_cell_found_text_preferred | gtg | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121051 | GTG_GAS TURBINE AND AUXILIARIES INSTALLATION MANUAL | INSTALLATION MANUAL | GTG ¦ Gas Turbine Generator |  |  |  | INSTALLATION MANUAL for GTG ¦ Gas Turbine Generator |  | Installation and Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5875 | 0.7013 | 0.7013 | FI | 1CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | 2008-05-03 | 2008-05-16 | manual | installation | compatible | gtg |  | gtg | query | gtg | match | false | 13 | 29 | 17.4316 | 0.6393 | 0.0249 | 0.0187 | hybrid | structured_cell_found_text_preferred | gtg | delivery¦procurement¦installation |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121073 | GTG_GAS TURBINE AND AUXILIARIES COMMISSIOINING MANUAL | COMMISSIOINING MANUAL | GTG ¦ Gas Turbine Generator |  |  |  | COMMISSIOINING MANUAL for GTG ¦ Gas Turbine Generator | N2 Gas System | Commissioning Manual for N2 Gas System | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6837 | 0.5551 | 0.5551 | FI | 1PF1255W70A02T | (GTG#11 Electrical) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-04-01 | 2008-05-15 | manual | delivery | match | gtg | n2 | gtg | query | electrical¦gtg | match | false | 7 | 1 | 13.9550 | 0.6782 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | delivery¦procurement¦installation | 10 | 2024-12-23 | 2025-01-22 | 2025-02-21 | 2025-03-08 | 2025-03-23 | 2025-04-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121076 | GTG_INSTALLATION MANUAL | INSTALLATION MANUAL | GTG ¦ Gas Turbine Generator |  |  |  | INSTALLATION MANUAL for GTG ¦ Gas Turbine Generator |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6360 | 0.6575 | 0.6575 | FI | 2CF1255W70A03 | (GTG#21 Electrical) Installation- PCC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2008-08-01 | 2008-09-15 | manual | installation | compatible | gtg |  | gtg | query | electrical¦gtg | match | false | 2 | 35 | 11.6552 | 0.6280 | 0.0267 | 0.0200 | hybrid | structured_preferred | gtg | delivery¦procurement¦installation | 10 | 2025-04-25 | 2025-05-25 | 2025-06-24 | 2025-07-09 | 2025-07-24 | 2025-08-08 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121077 | GTG_GENERATOR REMOVAL PROCEDURE | PROCEDURE | GTG ¦ Gas Turbine Generator |  |  |  | PROCEDURE for GTG ¦ Gas Turbine Generator |  | GT - PAINTING PROCEDURE FOR GTG | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | rule_query | procedure | procedure | procedure | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.6338 | 0.7501 | 0.7501 | FA | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2007-03-30 | 2008-04-29 | procurement | procurement | match | gtg | gtg | gtg | query | electrical¦gtg | match | false | 2 | 4 | 15.7666 | 0.7211 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | gtg | procurement |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121099 | GTG ERECTION DRAWING PACKAGE | ERECTION DRAWING PACKAGE | GTG ¦ Gas Turbine Generator |  |  |  | ERECTION DRAWING PACKAGE for GTG ¦ Gas Turbine Generator |  | ERECTION DRAWING PACKAGE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8826 | 0.9648 | 0.6753 | FA | 1EF1210W20A09 | (GTG Common BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-31 | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | false | 5 | 20 | 7.1833 | 0.6389 | 0.0279 | 0.0209 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-121100 | GTG – DRAIN INTERFACE FLOW DIAGRAM | FLOW DIAGRAM | GTG ¦ Gas Turbine Generator | Drain System |  |  | FLOW DIAGRAM for Drain System |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | drain¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6520 | 0.6623 | 0.4636 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 3 | 7.5809 | 0.6557 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | needs_review | rule_scope_status=rule_generic;rule_score_medium;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121555 | GTG_CONDUIT LAYOUT DRAWING | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | CONDUIT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8690 | 0.9607 | 0.6725 | FA | 2EF1210W20A09 | (GTG Common BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-08-31 | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | false | 8 | 11 | 7.1833 | 0.6573 | 0.0288 | 0.0216 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121677 | GTG_GAS TURBINE GENERATOR COMMISSIOINING MANUAL | COMMISSIOINING MANUAL | GTG ¦ Gas Turbine Generator |  |  |  | COMMISSIOINING MANUAL for GTG ¦ Gas Turbine Generator | N2 Gas System | Commissioning Manual for N2 Gas System | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6837 | 0.5551 | 0.5551 | FI | 1PF1255W70A02T | (GTG#11 Electrical) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-04-01 | 2008-05-15 | manual | delivery | match | gtg | n2 | gtg | query | electrical¦gtg | match | false | 1 | 1 | 14.9761 | 0.6834 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | delivery¦procurement¦installation | 10 | 2024-12-23 | 2025-01-22 | 2025-02-21 | 2025-03-08 | 2025-03-23 | 2025-04-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121678 | GTG_I&C SCHEMATICS | SCHEMATICS | GTG ¦ Gas Turbine Generator | I&C ¦ Instrumentation and Control |  |  | SCHEMATICS for I&C ¦ Instrumentation and Control |  | I&C SCHEMATICS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | andc¦gas¦generator¦gtg¦instrumentation¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8565 | 0.7236 | 0.5065 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 2 | 7.5809 | 0.6521 | 0.0325 | 0.0244 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121824 | GTG_FIRE PROTECTION SYSTEM DRAWING | DRAWING | GTG ¦ Gas Turbine Generator | FIRE PROTECTION SYSTEM |  |  | DRAWING for GTG ¦ Gas Turbine Generator |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6000 | 0.6850 | 0.6255 | 0.6255 | FA | 2CF1265W16A11 | (Control Oil) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | 2007-10-31 | 2007-12-31 | design_drawing | civil_design | compatible | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query | gtg | match | false | 12 | 77 | 8.0218 | 0.5897 | 0.0212 | 0.0159 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | 2025-02-10 | 2025-03-12 | 2025-04-11 | 2025-04-26 | 2025-05-11 | 2025-05-26 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121971 | GTG – SFC / SEE CIRCUIT DIAGRAM | CIRCUIT DIAGRAM | GTG ¦ Gas Turbine Generator |  |  |  | CIRCUIT DIAGRAM for GTG ¦ Gas Turbine Generator |  | GT - GAS TURBINE GENERAL LOGIC DIAGRAM | 1 | start+165D<=FA<=start+165D+2M | FA ∈ [start+165d, start+225d] | rule_query | diagram | diagram | diagram | diagram | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7907 | 0.7039 | 0.7039 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | gtg | gtg | gtg | query | ccw¦gtg | match | false | 2 | 1 | 7.5809 | 0.6725 | 0.0325 | 0.0244 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-08-13 | 2024-09-12 | 2024-10-12 | 2024-10-27 | 2024-11-11 | 2024-11-26 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0LB-122001 | HRSG - INSTALLATION AND INSTRUCTION MANUAL | INSTALLATION AND INSTRUCTION MANUAL | HRSG ¦ Heat Recovery Steam Generator |  |  |  | INSTALLATION AND INSTRUCTION MANUAL for HRSG ¦ Heat Recovery Steam Generator |  | Installation and Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6065 | 0.7069 | 0.7069 | FI | 3PF1655W86A12T | (HRSG #31 I&C Vendor Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | 2008-10-04 | 2008-11-18 | manual | delivery | match | hrsg |  | hrsg | query | hrsg | match | false | 9 | 28 | 22.9297 | 0.6269 | 0.0259 | 0.0259 | hybrid | structured_preferred | hrsg | delivery¦procurement¦installation | 10 | 2025-06-28 | 2025-07-28 | 2025-08-27 | 2025-09-11 | 2025-09-26 | 2025-10-11 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122003 | HRSG - STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | ISOMETRIC DRAWING | HRSG ¦ Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Erection Isometric DraWing for PIPNG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7867 | 0.7027 | 0.7027 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 22.2617 | 0.6835 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122004 | HRSG - CFD REPORT FOR INLET DUCT | REPORT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | CFD Report for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - HRSG CFD Report | 1 | start+149D<=FA<=start+149D+2M | FA ∈ [start+149d, start+209d] | rule_query | report | report | cfd_report | cfd_report | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8956 | 0.9687 | 0.9687 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 4 | 17.4274 | 0.6161 | 0.0320 | 0.0320 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122005 | HRSG - CFD REPORT FOR DUCT BURNER SYSTEM | REPORT | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | CFD Report for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - HRSG CFD Report | 1 | start+149D<=FA<=start+149D+2M | FA ∈ [start+149d, start+209d] | rule_query | report | report | cfd_report | cfd_report | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8956 | 0.9687 | 0.9687 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 5 | 18.3209 | 0.6209 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122006 | HRSG - SPEC. & DRAWING FOR HOIST |  | HRSG ¦ Heat Recovery Steam Generator |  |  |  | for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.3333 | 0.6766 | 0.4363 | 0.4363 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 5 | 17.4274 | 0.6499 | 0.0318 | 0.0238 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.57 | usable | default_fc_window;rule_score_medium;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122007 | HRSG - GENERAL ARRANGEMENT | GENERAL ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8456 | 0.9537 | 0.9537 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 2 | 30.7117 | 0.7190 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122008 | HRSG - ARRANGEMENT OF CASING & FIELD ERECTION | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 2 | 1 | 24.1423 | 0.6731 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122009 | HRSG - ARRANGEMENT OF INLET DUCT | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 2 | 3 | 27.9268 | 0.6658 | 0.0320 | 0.0240 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122010 | HRSG - ARRANGEMENT OF MAIN STACK& FIELD ERECTION | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 3 | 2 | 33.6229 | 0.7263 | 0.0320 | 0.0240 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122011 | HRSG - GENERAL ARRANGEMENT FOR DUCT BURNER SYSTEM | GENERAL ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8456 | 0.9537 | 0.9537 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 30.7117 | 0.7079 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122012 | HRSG - DETAIL ARRANGEMENT FOR DUCT BURNER SYSTEM | DETAIL ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DETAIL ARRANGEMENT for HRSG |  | HRSG FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6534 | 0.5460 | 0.5460 | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 27.9268 | 0.6907 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122013 | HRSG - FUEL GAS SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | fgp¦generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 8 | 1 | 24.1423 | 0.6746 | 0.0311 | 0.0233 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122014 | HRSG - COOLING AIR SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 8 | 1 | 24.1423 | 0.6684 | 0.0311 | 0.0233 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-VN03-P0LB-122015 | HRSG - ARRANGEMENT FOR PLATFORM STRUCTURE | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg |  | hrsg | query | hrsg | match | false | 2 | 4 | 22.8843 | 0.6238 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122016 | HRSG - COLUMN LOCATION FOR STEEL STRUCTURE AND STACK |  | HRSG ¦ Heat Recovery Steam Generator |  |  |  | for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | diagram | hrsg_column_location_for_steel_structure_and_stack | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6763 | 0.5529 | 0.5529 |  | 3CF1610W20A05 | (HRSG #31 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  | installation | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 3 | 21 | 28.3118 | 0.7049 | 0.0282 | 0.0212 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122017 | HRSG - FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | TABLE | HRSG ¦ Heat Recovery Steam Generator |  |  |  | TABLE for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | diagram | table | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6316 | 0.5395 | 0.5395 |  | 2EF1625W00A02 | (HRSG #21 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2007-07-05 |  | civil_design | civil_design | match | hrsg |  | hrsg | query | hrsg | match | false | 4 | 8 | 25.3681 | 0.7244 | 0.0303 | 0.0303 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122018 | HRSG - BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | DETAIL | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Detail Drawing for HRSG |  | HRSG - Base Plate anD Anchor Bolts Detail for HRSG (Steel Structure) | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | title | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9475 | 0.9842 | 0.9842 | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 9 | 4 | 16.0954 | 0.6420 | 0.0301 | 0.0301 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-10-16 | 2024-11-15 | 2024-12-15 | 2024-12-30 | 2025-01-14 | 2025-01-29 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122019 | HRSG - ANCHOR BOLT & TEMPLATE DETAIL FOR STACK | DETAIL | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Detail Drawing for HRSG |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5841 | 0.6419 | 0.6419 | FI | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 4 | 17 | 21.6412 | 0.6593 | 0.0286 | 0.0215 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122020 | HRSG - FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7663 | 0.5799 | 0.5799 | FA | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 22 | 2 | 17.4581 | 0.6648 | 0.0283 | 0.0283 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0LB-122021 | HRSG - LARGE BORE PIPING ARRANGEMENT | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator | Piping |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 2 | 4 | 24.1423 | 0.6589 | 0.0318 | 0.0238 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LB-122022 | HRSG - P&I DIAGRAM | P&I DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | P&ID for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9799 | 0.9940 | 0.9940 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 30.8870 | 0.7441 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦procurement |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LB-122023 | HRSG - P&I DIAGRAM FOR HRSG DUCT BURNER SYSTEM | P&I DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | P&ID for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8536 | 0.9561 | 0.9561 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 13 | 1 | 34.3658 | 0.7560 | 0.0301 | 0.0301 | hybrid | structured_blocked_procurement_conflict | hrsg | system_design¦procurement |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122024 | HRSG - PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | DRAWING | HRSG ¦ Heat Recovery Steam Generator | Piping |  |  | DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7663 | 0.5799 | 0.5799 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 22.2617 | 0.6647 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122025 | HRSG - TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | DRAWING | HRSG ¦ Heat Recovery Steam Generator | Piping |  |  | DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7663 | 0.5799 | 0.5799 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 3 | 22.2617 | 0.6737 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122026 | HRSG - PIPE SUPPORT DRAWINGS | DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - PoWer Distribution Panel DraWings | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7406 | 0.5022 | 0.5022 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 3 | 17.4274 | 0.6536 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122027 | HRSG - LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | ISOMETRIC DRAWING | HRSG ¦ Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Erection Isometric DraWing for PIPNG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7867 | 0.7027 | 0.7027 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 22.2617 | 0.6746 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122028 | HRSG - SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | ISOMETRIC DRAWING | HRSG ¦ Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Erection Isometric DraWing for PIPNG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7867 | 0.7027 | 0.7027 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 22.2617 | 0.6728 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122029 | HRSG - VENT & DRAIN LINE (MODULE /FIELD WELD) |  | HRSG ¦ Heat Recovery Steam Generator |  |  |  | for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Vent & Drain Line (MoDule /FielD WelD) | 1 | start+286D<=FA<=start+286D+2M | FA ∈ [start+286d, start+346d] | title | other | other | hrsg_vent_and_drain_line_module_field_weld | hrsg_vent_and_drain_line_module_field_weld | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9457 | 0.9837 | 0.9837 | FA | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | 2007-07-03 | 2008-05-02 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 3 | 2 | 30.5701 | 0.7426 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-04-15 | 2025-05-15 | 2025-06-14 | 2025-06-29 | 2025-07-14 | 2025-07-29 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0LB-122030 | HRSG - LINE LIST | LINE LIST | HRSG ¦ Heat Recovery Steam Generator |  |  |  | LINE LIST for HRSG ¦ Heat Recovery Steam Generator | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5917 | 0.5275 | 0.5275 | FI | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | compressed_air | hrsg | query | hrsg | match | false | 13 | 6 | 23.1098 | 0.7088 | 0.0289 | 0.0289 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0LB-122031 | HRSG - LINE LIST FOR DUCT BURNER SYSTEM | LINE LIST | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LINE LIST for HRSG ¦ Heat Recovery Steam Generator | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5917 | 0.5275 | 0.5275 | FI | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | compressed_air | hrsg | query | hrsg | match | false | 2 | 1 | 34.4847 | 0.7498 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122032 | HRSG - MANUAL VALVE LIST | LIST | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Valve List for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Valve List for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | list | list | valve_list | valve_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8116 | 0.8035 | 0.8035 | FA | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-13 | 2008-02-29 | manual | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 12 | 11 | 23.1098 | 0.6939 | 0.0280 | 0.0280 | hybrid | structured_cell_found_text_preferred | hrsg | delivery¦procurement¦installation |  | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122033 | HRSG - MOV & CV LIST | LIST | HRSG ¦ Heat Recovery Steam Generator |  |  |  | LIST for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | list | list | io_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.6422 | 0.7177 | 0.7177 |  | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 5 | 3 | 16.7507 | 0.6430 | 0.0313 | 0.0234 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122034 | HRSG - VALVE LIST FOR DUCT BURNER SYSTEM | LIST | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Valve List for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Valve List for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | list | list | valve_list | valve_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8116 | 0.8035 | 0.8035 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 34.4847 | 0.7514 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122035 | HRSG - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | System Description for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - System Description | 1 | start+103D<=FA<=start+103D+2M | FA ∈ [start+103d, start+163d] | rule_query | description | description | system_description | system_description | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8074 | 0.9422 | 0.9422 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 23.4269 | 0.7143 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦procurement |  | 2024-06-30 | 2024-07-30 | 2024-08-29 | 2024-09-13 | 2024-09-28 | 2024-10-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122036 | HRSG - SYSTEM DESCRIPTION FOR HRSG DUCT BURNER SYSTEM | SYSTEM DESCRIPTION | HRSG ¦ Heat Recovery Steam Generator | HRSG DUCT BURNER SYSTEM ¦ Heat Recovery Steam Generator DUCT BURNER SYSTEM |  |  | System Description for HRSG DUCT BURNER SYSTEM ¦ Heat Recovery Steam Generator DUCT BURNER SYSTEM |  | HRSG - System Description for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | description | description | system_description | system_description | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8867 | 0.9660 | 0.9660 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 121 | 1 | 40.0971 | 0.6872 | 0.0219 | 0.0219 | hybrid | structured_blocked_procurement_conflict | hrsg | system_design¦procurement |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122037 | HRSG - BLOWDOWN SYSTEM SUMMARY | SUMMARY | HRSG ¦ Heat Recovery Steam Generator |  |  |  | SUMMARY for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | other | summary | hrsg_hrsg_blowdown_system_summary | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.5000 | 0.7796 | 0.5839 | 0.5839 |  | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 2 | 1 | 16.7507 | 0.6300 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0LB-122038 | HRSG - BMS PANEL PART LIST FOR DUCT BURNER SYSTEM | LIST | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LIST for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | list | list | io_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.6422 | 0.7177 | 0.7177 |  | 2EF1615W64A04 | (HRSG #21 Duct) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-17 | 2007-11-19 |  |  | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 9 | 6 | 27.3886 | 0.6923 | 0.0296 | 0.0222 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0LB-122039 | HRSG - EQUIPMENT LIST | LIST | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Equipment List for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment List | 1 | start+134D<=FA<=start+134D+2M | FA ∈ [start+134d, start+194d] | rule_query | list | list | equipment_list | equipment_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8501 | 0.9550 | 0.9550 | FA | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 3 | 24.8685 | 0.7176 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0LB-122040 | HRSG - HAZARDOUS AREA CLASSIFICATION SPECIFICATION & DRAWING FOR DUCT BURNER SYSTEM | SPECIFICATION & DRAWING | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Hazardous Area Classification for DUCT BURNER SYSTEM |  | HRSG - HazarDous Area Classification Specification & DraWing for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | classification | classification | hazardous_area_classification | hazardous_area_classification | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7640 | 0.6959 | 0.6959 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 18.3209 | 0.6418 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122041 | HRSG - TECHNICAL SPECIFICATION FOR AC & DC DISTRIBUTION BOARD | TECHNICAL SPECIFICATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Technical Specification for HRSG ¦ Heat Recovery Steam Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Technical specification for Panel /SWGR | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4444 | 0.5588 | 0.4788 | 0.4788 | FA | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-09-15 | 2008-08-23 | procurement | procurement | match | hrsg | bsedg | hrsg | query | hrsg | match | false | 3 | 9 | 23.3676 | 0.6305 | 0.0304 | 0.0304 | hybrid | structured_cell_found_text_preferred | hrsg | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122042 | HRSG - COOLING AIR FAN & MOTOR DATASHEET FOR DUCT BURNER SYSTEM | DATASHEET | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Data Sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7100 | 0.7380 | 0.7380 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 34.4847 | 0.6892 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122044 | HRSG - BMS SHELTER LAYOUT FOR DUCT BURNER SYSTEM | LAYOUT | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 4 | 1 | 29.8650 | 0.7213 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122045 | HRSG - TECHNICAL SPECIFICATION FOR EARTHING & LIGHTNING PROTECTION SYSTEM | TECHNICAL SPECIFICATION | HRSG ¦ Heat Recovery Steam Generator | EARTHING & LIGHTNING PROTECTION SYSTEM |  |  | Technical Specification for HRSG ¦ Heat Recovery Steam Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Technical specification for Panel /SWGR | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4444 | 0.5588 | 0.4788 | 0.4788 | FA | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-09-15 | 2008-08-23 | procurement | procurement | match | electrical¦hrsg | bsedg | electrical¦hrsg | query | hrsg | match | false | 9 | 4 | 23.3676 | 0.6056 | 0.0301 | 0.0301 | hybrid | structured_cell_found_text_preferred | electrical¦hrsg | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122046 | HRSG - TECHNICAL SPECIFICATION FOR COMMUNICATION SYSTEM | TECHNICAL SPECIFICATION | HRSG ¦ Heat Recovery Steam Generator | COMMUNICATION SYSTEM |  |  | Technical Specification for HRSG ¦ Heat Recovery Steam Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Technical specification for Panel /SWGR | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4444 | 0.5588 | 0.4788 | 0.4788 | FA | 2PF1665W42A02P | (HRSG #21 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | 2007-09-10 | 2008-09-02 | procurement | procurement | match | hrsg | bsedg | hrsg | query | hrsg | match | false | 6 | 13 | 23.3190 | 0.6277 | 0.0289 | 0.0289 | hybrid | structured_cell_found_text_preferred | hrsg | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0LB-122047 | HRSG - CABLE CONNECTION DIAGRAM | CABLE CONNECTION DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | CABLE CONNECTION DIAGRAM for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - PoWer Cable Connection Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8462 | 0.8139 | 0.8139 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 26.6382 | 0.6522 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0LB-122048 | HRSG - PRESSURE PART ARRANGEMENT | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 2 | 1 | 24.1423 | 0.6846 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122049 | HRSG - SPEC. & DRAWING FOR STEAM DRUM | SPEC. & DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7982 | 0.7995 | 0.7995 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 5 | 19.8869 | 0.6374 | 0.0318 | 0.0238 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122050 | HRSG - SPEC. & DRAWING FOR BLOWDOWN PUMP | SPEC. & DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7982 | 0.7995 | 0.7995 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 17.4274 | 0.6444 | 0.0328 | 0.0246 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122051 | HRSG - SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | SPEC. & DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7982 | 0.7995 | 0.7995 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 3 | 2 | 17.4274 | 0.6503 | 0.0320 | 0.0240 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122052 | HRSG - SPEC. & DRAWING FOR STACK DAMPER | SPEC. & DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7982 | 0.7995 | 0.7995 | FA | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 4 | 21 | 21.6412 | 0.6363 | 0.0280 | 0.0210 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122053 | HRSG - SPEC. & DRAWING FOR VENT SILENCER | SPEC. & DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7982 | 0.7995 | 0.7995 | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 6 | 1 | 16.7507 | 0.6340 | 0.0315 | 0.0237 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122054 | HRSG - SPEC. & DRAWING FOR DEAERATOR & STORAGE TANK | SPEC. & DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7982 | 0.7995 | 0.7995 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 3 | 17.4274 | 0.6344 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122055 | HRSG - EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | EQUIPMENT OUTLINE DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | EQUIPMENT OUTLINE DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment Outline DraWing for BloWDoWn Tank | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg¦tank | scoped | match | match | match | passed |  | 0.7143 | 0.8093 | 0.7428 | 0.7428 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 17.4274 | 0.6582 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122056 | HRSG - POWER DISTRIBUTION PANEL DRAWINGS | DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - PoWer Distribution Panel DraWings | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7406 | 0.5022 | 0.5022 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 17.4276 | 0.6781 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122057 | HRSG - HEADER AND SUPPORT DRAWING FOR DUCT BURNER SYSTEM | DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7663 | 0.5799 | 0.5799 | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 15 | 1 | 20.6957 | 0.6942 | 0.0297 | 0.0223 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-03-11 | 2025-04-10 | 2025-05-10 | 2025-05-25 | 2025-06-09 | 2025-06-24 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122058 | HRSG - BMS PANEL LAYOUT FOR DUCT BURNER SYSTEM | LAYOUT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 5 | 4 | 24.3112 | 0.6853 | 0.0310 | 0.0233 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦civil_design |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0LB-122059 | HRSG - HMI SCREEN LAYOUT FOR DUCT BURNER SYSTEM | LAYOUT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 5 | 1 | 24.3112 | 0.6925 | 0.0318 | 0.0238 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦civil_design |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122060 | HRSG - JUNCTION BOX DATASHEET FOR DUCT BURNER SYSTEM | DATASHEET | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Data Sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7100 | 0.7380 | 0.7380 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 7 | 28.7972 | 0.6916 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122061 | HRSG - FLAME SCANNER & IGNITION BURNER SPECIFICATION FOR DUCT BURNER SYSTEM | SPECIFICATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Technical Specification for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | title | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.8574 | 0.8406 | 0.8406 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 28.7972 | 0.6954 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-12-10 | 2025-01-09 | 2025-02-08 | 2025-02-23 | 2025-03-10 | 2025-03-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122062 | HRSG - ARRANGEMENT OF STACK SILENCER | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 6 | 1 | 27.9247 | 0.6717 | 0.0315 | 0.0237 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122063 | HRSG - CONDUIT LAYOUT DRAWING | LAYOUT DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 17.4274 | 0.6744 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122064 | HRSG - CABLE TRAY & RACEWAY LAYOUT DIAGRAM | LAYOUT DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | LAYOUT DIAGRAM for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Cable Tray & RaceWay Layout Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6940 | 0.5582 | 0.5582 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 26.6382 | 0.6525 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122065 | HRSG - GROUNDING AND LIGHTNING PLAN DIAGRAMS | PLAN DIAGRAMS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | PLAN DIAGRAMS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Lighting Plan Diagrams | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7095 | 0.7379 | 0.7379 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 19.7045 | 0.6585 | 0.0328 | 0.0246 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122066 | HRSG - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Control Logic Diagram for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Control Logic Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8622 | 0.9587 | 0.9587 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 26.6382 | 0.6927 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0LB-122067 | HRSG - CONTROL LOOP DIAGRAM | CONTROL LOOP DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Control Loop Diagram for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Control Loop Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8753 | 0.9626 | 0.9626 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 3 | 26.6382 | 0.6963 | 0.0323 | 0.0323 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122068 | HRSG - LOGIC DIAGRAM FOR DUCT BURNER SYSTEM | LOGIC DIAGRAM | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LOGIC DIAGRAM for DUCT BURNER SYSTEM |  | HRSG - Cable Interconnection Diagram for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | title | diagram | diagram | diagram | diagram | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7143 | 0.7681 | 0.7304 | 0.7304 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 27.5316 | 0.6715 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YM03-P0LB-122069 | HRSG - INSTRUMENT LOCATION | LOCATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | LOCATION for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | other | location | hrsg_instrument_location_for_scr | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6000 | 0.7110 | 0.6333 | 0.6333 |  | 1EF1600W00A03 | (HRSG #11/#12) Instrument, Service Air Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-29 |  |  | query_unknown | hrsg |  | hrsg | query | compressed_air¦hrsg | match | false | 1 | 3 | 22.9548 | 0.6613 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122070 | HRSG - BMS SYSTEM CONFIGURATION FOR DUCT BURNER SYSTEM |  | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | diagram | hrsg_bms_system_configuration_for_duct_burner_system | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6763 | 0.5529 | 0.5529 |  | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 2 | 4 | 16.7507 | 0.6274 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | system_design | 6 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122071 | HRSG - LINK ASSEMBLY DRAWING | ASSEMBLY DRAWING | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ASSEMBLY DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Link Assembly DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7970 | 0.7641 | 0.7641 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 4 | 17.4274 | 0.6587 | 0.0320 | 0.0240 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-12-31 | 2025-01-30 | 2025-03-01 | 2025-03-16 | 2025-03-31 | 2025-04-15 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122072 | HRSG - INSTRUMENT INSTALLATION DETAIL DRAWINGS | DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG |  | HRSG - Instrument Installation Detail DraWings | 1 | start+134D<=FA<=start+134D+2M | FA ∈ [start+134d, start+194d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7876 | 0.5163 | 0.5163 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 17.4274 | 0.6938 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122073 | HRSG - SPECIALTY DRAWING FOR EXTERNAL PIPING | DRAWING | HRSG ¦ Heat Recovery Steam Generator | PIPING |  |  | DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7663 | 0.5799 | 0.5799 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 22.2617 | 0.6989 | 0.0328 | 0.0246 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LB-122074 | HRSG - MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | DRAWING | HRSG ¦ Heat Recovery Steam Generator | PIPING |  |  | DRAWING for HRSG ¦ Heat Recovery Steam Generator |  | Shop Quality Manual for HRSG | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | manual | manual | manual | manual | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.5891 | 0.4567 | 0.3197 | FA | 3CF1650W52A04 | (HRSG #31 Insulation) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | 2009-03-19 | 2009-04-22 | manual | installation | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 6 | 18 | 22.8863 | 0.6306 | 0.0280 | 0.0210 | hybrid | structured_preferred | hrsg | delivery¦procurement¦installation | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122075 | HRSG - INSTRUMENT LIST | INSTRUMENT LIST | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Instrument List for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Instrument List | 1 | start+133D<=FA<=start+133D+2M | FA ∈ [start+133d, start+193d] | rule_query | list | list | instrument_list | instrument_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8155 | 0.9446 | 0.9446 | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 26 | 13 | 23.0781 | 0.7143 | 0.0253 | 0.0253 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-01-26 | 2025-02-25 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-11 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122076 | HRSG - INSTRUMENT LIST FOR DUCT BURNER SYSTEM | INSTRUMENT LIST | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Instrument List for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Instrument List | 1 | start+133D<=FA<=start+133D+2M | FA ∈ [start+133d, start+193d] | rule_query | list | list | instrument_list | instrument_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8155 | 0.9446 | 0.9446 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 34.4847 | 0.7437 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LB-122077 | HRSG - ALARM AND TRIP SETTING LIST FOR DUCT BURNER SYSTEM | LIST | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LIST for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | list | list | io_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.6422 | 0.7177 | 0.7177 |  | 2CF1615W64A08 | (HRSG #21 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2008-10-18 | 2009-01-17 |  | installation | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 2 | 2 | 28.2748 | 0.6508 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0LB-122078 | HRSG - CABLE SCHEDULE | CABLE SCHEDULE | HRSG ¦ Heat Recovery Steam Generator |  |  |  | CABLE SCHEDULE for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - PoWer Cable ScheDule | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | list | list | cable_schedule | cable_schedule | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7678 | 0.7553 | 0.7553 | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 28 | 1 | 22.8804 | 0.6747 | 0.0278 | 0.0278 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-07-22 | 2025-08-21 | 2025-09-20 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122079 | HRSG - LIGHTING PLAN DIAGRAMS | PLAN DIAGRAMS | HRSG ¦ Heat Recovery Steam Generator | Lighting & Small Power System |  |  | PLAN DIAGRAMS for Lighting & Small Power System |  | HRSG - Lighting Plan Diagrams | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦lighting¦power¦recovery¦small¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7036 | 0.7361 | 0.7361 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | electrical¦hrsg | hrsg | electrical¦hrsg | query | hrsg | match | false | 1 | 2 | 17.8744 | 0.6670 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical¦hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0LB-122080 | HRSG - COMMUNICATION BLOCK DIAGRAM | BLOCK DIAGRAM | HRSG ¦ Heat Recovery Steam Generator | Communication System & Security System |  |  | BLOCK DIAGRAM for Communication System & Security System |  | HRSG - Cable Block Diagram for HRSG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | diagram | diagram | diagram | diagram | communication¦generator¦heat¦hrsg¦recovery¦security¦steam | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.8163 | 0.6649 | 0.6649 | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 28.0788 | 0.6637 | 0.0325 | 0.0244 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦engineering |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-US02-P0LB-122081 | HRSG - COMMUNICATION LAYOUT DRAWING | LAYOUT DRAWING | HRSG ¦ Heat Recovery Steam Generator | Communication System & Security System |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 18.3209 | 0.6774 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0LB-122082 | HRSG - CHEMICAL CLEANING PROCEDURE | PROCEDURE | HRSG ¦ Heat Recovery Steam Generator |  |  |  | PROCEDURE for HRSG ¦ Heat Recovery Steam Generator |  | CHEMICAL CLEANING PROCEDURE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | procedure | procedure | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7717 | 0.9315 | 0.6520 | FA | 2CF1640W60A07 | (HRSG #21) Acid Cleaning | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Piping Work | 2009-02-27 | 2009-03-21 |  |  | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 2 | 1 | 23.6588 | 0.7192 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hrsg |  |  | 2025-10-16 | 2025-10-31 | 2025-11-15 | 2025-11-30 | 2025-12-30 | 2026-01-29 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL08-P0LB-122083 | HRSG - PRESERVATION AND STORAGE PROCEDURE | PROCEDURE | HRSG ¦ Heat Recovery Steam Generator |  |  |  | PROCEDURE for HRSG ¦ Heat Recovery Steam Generator |  | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6450 | 0.7185 | 0.7185 | FI | 1PF1650W52A03T | (HRSG #11 Insulation) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-10-01 | 2008-11-14 | delivery | delivery | match | hrsg |  | hrsg | query | hrsg | match | false | 19 | 3 | 18.9833 | 0.6586 | 0.0285 | 0.0285 | hybrid | structured_cell_found_text_preferred | hrsg | delivery¦procurement |  | 2025-06-24 | 2025-07-24 | 2025-08-23 | 2025-09-07 | 2025-09-22 | 2025-10-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0LB-122084 | HRSG - PANEL ELECTRIC SCHEME FOR DUCT BURNER SYSTEM |  | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | diagram | hrsg_panel_electric_scheme_for_duct_burner_system | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6763 | 0.5529 | 0.5529 |  | 1CF1615W64A08 | (HRSG #11 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2008-09-16 | 2008-12-16 |  | installation | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 1 | 8 | 28.2748 | 0.6922 | 0.0311 | 0.0233 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0LB-122085 | HRSG - WIRING & SCHEMATIC DIAGRAM | WIRING & SCHEMATIC DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | WIRING & SCHEMATIC DIAGRAM for HRSG ¦ Heat Recovery Steam Generator |  | WIRING & SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7315 | 0.9194 | 0.6436 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 1 | 24.5408 | 0.6704 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122086 | HRSG - DATA & BOM OF INSULATION FOR BLOWDOWN TANK | DATA & BOM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATA & BOM for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Data & BOM of Insulation for Piping | 1 | start+317D<=FA<=start+317D+2M | FA ∈ [start+317d, start+377d] | rule_query | data | data | data | data | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg | scoped | match | match | match | passed |  | 0.5714 | 0.7699 | 0.6310 | 0.6310 | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 29.4859 | 0.7234 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-11-22 | 2025-12-22 | 2026-01-21 | 2026-02-05 | 2026-02-20 | 2026-03-07 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122087 | HRSG - DATA & BOM OF INSULATION FOR INTERNAL PIPING | DATA & BOM | HRSG ¦ Heat Recovery Steam Generator | PIPING |  |  | DATA & BOM for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Data & BOM of Insulation for Piping | 1 | start+317D<=FA<=start+317D+2M | FA ∈ [start+317d, start+377d] | rule_query | data | data | data | data | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5714 | 0.7699 | 0.6310 | 0.6310 | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 36.4979 | 0.7649 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-11-22 | 2025-12-22 | 2026-01-21 | 2026-02-05 | 2026-02-20 | 2026-03-07 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122088 | HRSG - PERFORMANCE AND OPERATIONAL DATA | DATA | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATA for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | data | data | operational_data | data | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.4970 | 0.6158 | 0.6158 |  | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 1 | 4 | 25.6913 | 0.6796 | 0.0320 | 0.0240 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0LB-122089 | HRSG - MOV DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 12 | 1 | 23.1098 | 0.6831 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0LB-122090 | HRSG - CV DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 12 | 1 | 23.1098 | 0.6974 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0LB-122091 | HRSG - DESH. DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 12 | 1 | 23.1098 | 0.6825 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0LB-122092 | HRSG - AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | DATASHEET & LAYOUT DIAGRAM | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & LAYOUT DIAGRAM for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Aircraft Warning Light Data sheet / layout Diagram | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.9510 | 0.8103 | 0.8103 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 17 | 3 | 23.1098 | 0.6464 | 0.0289 | 0.0289 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122093 | HRSG - CEMS DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cems¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 2PF1660W86A04P | (CEMS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | 2007-08-29 | 2008-04-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | cems¦hrsg | match | false | 2 | 2 | 27.5776 | 0.7354 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-05-11 | 2025-06-10 | 2025-07-10 | 2025-07-25 | 2025-08-09 | 2025-08-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LB-122094 | HRSG - LOCAL INSTRUMENT DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 3PF1600W90A10P | (HRSG #31 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-09-15 | 2008-08-23 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 9 | 4 | 27.5542 | 0.6821 | 0.0301 | 0.0301 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-05-28 | 2025-06-27 | 2025-07-27 | 2025-08-11 | 2025-08-26 | 2025-09-10 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122095 | HRSG - TRANSMITTER DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 12 | 1 | 23.1098 | 0.7030 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122096 | HRSG - DRUM LEVEL GAUGE DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 3PF1645W42A03P | (HRSG #31 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Drum | 2007-06-13 | 2008-07-01 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 3 | 1 | 32.3078 | 0.7137 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-23 | 2025-03-25 | 2025-04-24 | 2025-05-09 | 2025-05-24 | 2025-06-08 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122097 | HRSG - FLOW ELEMENT DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 12 | 1 | 23.1098 | 0.7095 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122098 | HRSG - REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6977 | 0.5593 | 0.5593 | FA | 3PF1645W42A03P | (HRSG #31 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Drum | 2007-06-13 | 2008-07-01 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 3 | 1 | 32.3078 | 0.6913 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-23 | 2025-03-25 | 2025-04-24 | 2025-05-09 | 2025-05-24 | 2025-06-08 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122099 | HRSG - TECHNICAL SPECIFICATION FOR LIGHTING & SMALL POWER SYSTEM | TECHNICAL SPECIFICATION | HRSG ¦ Heat Recovery Steam Generator | LIGHTING & SMALL POWER SYSTEM |  |  | Technical Specification for HRSG ¦ Heat Recovery Steam Generator |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4732 | 0.4920 | 0.4920 | FA | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-09-15 | 2008-08-23 | procurement | procurement | match | electrical¦hrsg |  | electrical¦hrsg | query | hrsg | match | false | 7 | 7 | 23.3680 | 0.6372 | 0.0299 | 0.0299 | hybrid | structured_cell_found_text_preferred | electrical¦hrsg | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122100 | HRSG - ELECTRICAL SINGLE LINE DIAGRAMS | SINGLE LINE DIAGRAMS | HRSG ¦ Heat Recovery Steam Generator | Electrical System |  |  | SINGLE LINE DIAGRAMS for Electrical System |  | HRSG - Electrical Single Line Diagrams | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | electrical¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7286 | 0.7786 | 0.7786 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | electrical¦hrsg | electrical¦hrsg | electrical¦hrsg | query | hrsg | match | false | 1 | 2 | 17.8742 | 0.6873 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦hrsg | system_design¦engineering | 6 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122101 | HRSG - ILLUMINATION CALCULATION | CALCULATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7930 | 0.7046 | 0.7046 | FA | 1EF1600W00A01 | (HRSG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 7 | 2 | 16.0954 | 0.6101 | 0.0311 | 0.0311 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-12-01 | 2024-12-31 | 2025-01-30 | 2025-02-14 | 2025-03-01 | 2025-03-16 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122102 | HRSG - I/O LIST FOR BMS AND CEMS | LIST | HRSG ¦ Heat Recovery Steam Generator |  |  |  | I/O List for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - DCS I/O List | 1 | start+134D<=FA<=start+134D+2M | FA ∈ [start+134d, start+194d] | rule_query | list | list | io_list | io_list | cems¦generator¦heat¦hrsg¦recovery¦steam | dcs¦hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7492 | 0.6914 | 0.6914 | FA | 2PF1660W86A04P | (CEMS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | 2007-08-29 | 2008-04-30 | procurement | procurement | match | hrsg | dcs¦hrsg | hrsg | query | cems¦hrsg | match | false | 3 | 2 | 29.8308 | 0.7400 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-01-10 | 2025-02-09 | 2025-03-11 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122103 | HRSG - ARRANGEMENT OF PARTITION PLATE & GAS BAFFLE | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 2 | 1 | 24.1423 | 0.6620 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LB-122104 | HRSG - PIPING MATERIAL CLASSIFICATION | CLASSIFICATION | HRSG ¦ Heat Recovery Steam Generator | Piping |  |  | CLASSIFICATION for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | other | classification | hrsg_piping_material_classification_for_hrsg | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6000 | 0.7429 | 0.6429 | 0.6429 |  | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 1 | 20.1643 | 0.6520 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122105 | HRSG - INSTRUMENT SPECIFICATION & DATASHEET FOR DUCT BURNER SYSTEM | SPECIFICATION & DATASHEET | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | SPECIFICATION & DATASHEET for HRSG ¦ Heat Recovery Steam Generator |  | INSTRUMENT SPECIFICATION & DATASHEET | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | specification | specification | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6593 | 0.8978 | 0.6284 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg |  | hrsg | query | hrsg | match | false | 8 | 1 | 26.9630 | 0.6559 | 0.0311 | 0.0311 | hybrid | structured_preferred | hrsg | procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | 2024-05-15 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122106 | HRSG - SHUT OFF AND CONTROL VALVE DATASHEET FOR DUCT BURNER SYSTEM | DATASHEET | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Data Sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7100 | 0.7380 | 0.7380 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 4 | 34.4847 | 0.7060 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0LB-122107 | HRSG - INTERCONNECTION WIRING DIAGRAM FOR DUCT BURNER SYSTEM | WIRING DIAGRAM | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | WIRING DIAGRAM for DUCT BURNER SYSTEM |  | HRSG - Wiring Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.6474 | 0.6609 | 0.6609 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 27.5316 | 0.6697 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122108 | HRSG - BMS SPECIFICATION FOR DUCT BURNER SYSTEM | SPECIFICATION | HRSG ¦ Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Technical Specification for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | title | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.9007 | 0.8535 | 0.8535 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 2 | 1 | 34.4847 | 0.7259 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-12-10 | 2025-01-09 | 2025-02-08 | 2025-02-23 | 2025-03-10 | 2025-03-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122109 | HRSG - UNDERGROUND EARTHING CABLE LAYOUT DRAWING | LAYOUT DRAWING | HRSG ¦ Heat Recovery Steam Generator | EARTHING & Lightning Protection System |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | design_drawing | civil_design | compatible | electrical¦hrsg | hrsg | electrical¦hrsg | query | hrsg | match | false | 14 | 3 | 16.0954 | 0.6318 | 0.0294 | 0.0220 | hybrid | structured_preferred | electrical¦hrsg | system_design¦civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LB-122110 | HRSG - STRENGTH CALCULATION REPORT FOR STEEL STRUCTURE | CALCULATION REPORT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | CALCULATION REPORT for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Strength Calculation Report for HRSG Stack | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | report | report | report | report | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.8414 | 0.8357 | 0.8357 | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 9 | 11 | 16.0954 | 0.6177 | 0.0286 | 0.0286 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122111 | HRSG – PERPENDICULAR BAFFLE AND TIE PLATE ASSY DRAWINGS | DRAWINGS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - PoWer Distribution Panel DraWings | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7406 | 0.5022 | 0.5022 | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 6 | 1 | 16.7507 | 0.6524 | 0.0315 | 0.0237 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-09-11 | 2024-10-11 | 2024-11-10 | 2024-11-25 | 2024-12-10 | 2024-12-25 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-122112 | HRSG – DRAIN FLOW DIAGRAM | FLOW DIAGRAM | HRSG ¦ Heat Recovery Steam Generator | Drain System |  |  | FLOW DIAGRAM for Drain System |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | drain¦generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6520 | 0.6623 | 0.4636 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 1 | 24.9875 | 0.6663 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123001 | ACC - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | GENERAL ARRANGEMENT DRAWING for ACC ¦ Air Cooled Condenser |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | acc¦air¦condenser¦cooled |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7067 | 0.9120 | 0.9120 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc |  | acc | query |  | activity_unscoped | true | 1115 | 33 | 2.1289 | 0.5670 | 0.0116 | 0.0070 | hybrid | structured_phase_gap | acc | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MAG-123002 | ACC - P&I DIAGRAM | P&I DIAGRAM | ACC ¦ Air Cooled Condenser |  |  |  | P&ID for ACC ¦ Air Cooled Condenser |  | ACC - P&I Diagram_Steam & ConDensate System | 1 | start+79D<=FA<=start+79D+2M | FA ∈ [start+79d, start+139d] | title | diagram | diagram | p_id | p_id | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.7846 | 0.5854 | 0.5854 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | acc | acc¦condensate | acc | query |  | activity_unscoped | true | 1 | 63 | 22.0712 | 0.5659 | 0.0245 | 0.0147 | hybrid | structured_blocked_procurement_conflict | acc | system_design¦procurement |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-15 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123004 | ACC - PERFORMANCE CURVE | PERFORMANCE CURVE | ACC ¦ Air Cooled Condenser |  |  |  | Performance Curve for ACC ¦ Air Cooled Condenser |  | ACC - Performance Curve | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | rule_query | curve | curve | performance_curve | performance_curve | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7526 | 0.9258 | 0.9258 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6336 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123005 | ACC - EQUIPMENT LIST | EQUIPMENT LIST | ACC ¦ Air Cooled Condenser |  |  |  | Equipment List for ACC ¦ Air Cooled Condenser |  | ACC - Equipment List | 1 | start+99D<=FA<=start+99D+2M | FA ∈ [start+99d, start+159d] | rule_query | list | list | equipment_list | equipment_list | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7219 | 0.9166 | 0.9166 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 3 | 2 | 21.1047 | 0.7092 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-10 | 2025-02-09 | 2025-03-11 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0MAG-123006 | ACC - FAN SPECIFICATION | SPECIFICATION | ACC ¦ Air Cooled Condenser |  |  |  | Fan Specification for ACC ¦ Air Cooled Condenser |  | FAN SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | fan_specification | fan_specification | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8330 | 0.7166 | 0.5016 | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | false | 1 | 1 | 15.3123 | 0.4968 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc | procurement | 4 | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MAG-123007 | ACC - CONDENSATE COLLECTING TANK OUTLINE DRAWING | OUTLINE DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | Outline Drawing for ACC ¦ Air Cooled Condenser |  | ACC - Fan Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | acc¦air¦condenser¦cooled¦tank | acc | scoped | match | match | match | passed |  | 0.7500 | 0.6870 | 0.7311 | 0.7311 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc | acc | acc | query |  | activity_unscoped | true | 1108 | 27 | 2.1289 | 0.5693 | 0.0124 | 0.0074 | hybrid | structured_phase_gap | acc | system_design |  | 2024-10-18 | 2024-11-17 | 2024-12-17 | 2025-01-01 | 2025-01-16 | 2025-01-31 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123008 | ACC - GEARBOX DATASHEET | DATASHEET | ACC ¦ Air Cooled Condenser |  |  |  | Data Sheet for ACC ¦ Air Cooled Condenser |  | ACC - Gearbox Datasheet | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9688 | 0.9906 | 0.9906 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6069 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123009 | ACC - FAN MOTOR DATA SHEET | DATA SHEET | ACC ¦ Air Cooled Condenser |  |  |  | Data Sheet for ACC ¦ Air Cooled Condenser |  | ACC - Fan Motor Datasheet | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.9362 | 0.8059 | 0.8059 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 6 | 2 | 15.9757 | 0.5951 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123010 | ACC - CONDENSATE DRAIN PUMP SPECIFICATION | SPECIFICATION | ACC ¦ Air Cooled Condenser |  |  |  | Drain Pump Specification for ACC ¦ Air Cooled Condenser |  | CONDENSATE DRAIN PUMP SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | drain_pump_specification | drain_pump_specification | acc¦air¦condenser¦cooled¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.7912 | 0.7623 | 0.5336 | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc | condensate | acc | query | acc¦condensate | match | false | 1 | 1 | 21.4138 | 0.5778 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc | procurement | 4 | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DH02-P0MAG-123011 | ACC - SJAE DATASHEET | DATASHEET | ACC ¦ Air Cooled Condenser |  |  |  | Data Sheet for ACC ¦ Air Cooled Condenser |  | ACC - Datasheet | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.6667 | 0.8221 | 0.7133 | 0.7133 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6258 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAJ-123012 | ACC - CLEANING WATER PUMP DATASHEET | DATASHEET | ACC ¦ Air Cooled Condenser |  |  |  | Data Sheet for ACC ¦ Air Cooled Condenser |  | ACC - Cleaning Water Pump Datasheet | 1 | start+269D<=FA<=start+269D+2M | FA ∈ [start+269d, start+329d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled¦pump | acc¦pump | scoped | match | match | match | passed |  | 1.0000 | 0.9668 | 0.9900 | 0.9900 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6224 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2025-06-29 | 2025-07-29 | 2025-08-28 | 2025-09-12 | 2025-09-27 | 2025-10-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XR00-P0MAG-123013 | ACC - ELECTRICAL LIFTING HOIST DATASHEET | DATASHEET | ACC ¦ Air Cooled Condenser |  |  |  | Data Sheet for ACC ¦ Air Cooled Condenser |  | ACC - Electrical Lifting Hoist Datasheet | 1 | start+269D<=FA<=start+269D+2M | FA ∈ [start+269d, start+329d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9658 | 0.9897 | 0.9897 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc¦crane_hoist¦electrical | acc | query | acc¦condensate | match | false | 2 | 2 | 15.9757 | 0.6003 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-06-29 | 2025-07-29 | 2025-08-28 | 2025-09-12 | 2025-09-27 | 2025-10-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123014 | ACC - MANUAL VALVE LIST | LIST | ACC ¦ Air Cooled Condenser |  |  |  | Valve List for ACC ¦ Air Cooled Condenser |  | ACC - Valve List | 1 | start+137D<=FA<=start+137D+2M | FA ∈ [start+137d, start+197d] | rule_query | list | list | valve_list | valve_list | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7881 | 0.9364 | 0.9364 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | manual | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6299 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | delivery¦procurement¦installation | 10 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0MAG-123015 | ACC - MANUAL VALVE OUTLINE DRAWING | OUTLINE DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | Outline Drawing for ACC ¦ Air Cooled Condenser |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8454 | 0.9536 | 0.6675 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc |  | acc | query |  | activity_unscoped | true | 1416 | 1 |  | 0.5462 | 0.0171 | 0.0102 | hybrid | structured_phase_gap | acc | system_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0MAG-123016 | ACC - PIPING ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | ACC ¦ Air Cooled Condenser | Piping |  |  | General Arrangement Drawing for ACC ¦ Air Cooled Condenser |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | acc¦air¦condenser¦cooled |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7181 | 0.9154 | 0.9154 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc |  | acc | query |  | activity_unscoped | true | 681 | 7 | 7.0358 | 0.6120 | 0.0163 | 0.0098 | hybrid | structured_phase_gap | acc | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MAG-123017 | ACC - PIPING ISOMETRIC DRAWING | ISOMETRIC DRAWING | ACC ¦ Air Cooled Condenser | Piping |  |  | Isometric Drawing for ACC ¦ Air Cooled Condenser | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7052 | 0.6315 | 0.6315 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | acc | compressed_air | acc | query |  | activity_unscoped | true | 48 | 89 | 13.1146 | 0.5316 | 0.0160 | 0.0096 | hybrid | structured_phase_gap | acc | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MAG-123019 | ACC - LINE LIST | LINE LIST | ACC ¦ Air Cooled Condenser |  |  |  | LINE LIST for ACC ¦ Air Cooled Condenser | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6809 | 0.7293 | 0.7293 | FI | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | compressed_air | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6529 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0MAG-123020 | ACC - STEEL STRUCTURE SPECIFICATION | SPECIFICATION | ACC ¦ Air Cooled Condenser |  |  |  | Technical Specification for ACC ¦ Air Cooled Condenser |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | acc¦air¦condenser¦cooled |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5319 | 0.6262 | 0.4384 | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | false | 1 | 1 | 15.3123 | 0.5213 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc | procurement | 4 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0MAG-123021 | ACC - FOUNDATION DRAWINGS / CIVIL LOADING DATA | DRAWINGS | ACC ¦ Air Cooled Condenser |  |  |  | DRAWINGS for ACC ¦ Air Cooled Condenser | H2, CO2 Supply System | Foundation DraWings/Civil Loading Data | 1 | start+1M-2M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.5556 | 0.6360 | 0.5797 | 0.5797 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | h2 | acc | query | acc¦condensate | match | false | 1 | 3 | 10.5740 | 0.5741 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc | civil_design | 6 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0MAG-123022 | ACC - EMBEDDED MATERIAL SPECIFICATION | SPECIFICATION | ACC ¦ Air Cooled Condenser |  |  |  | Technical Specification for ACC ¦ Air Cooled Condenser |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | acc¦air¦condenser¦cooled |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5319 | 0.6262 | 0.4384 | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | false | 1 | 1 | 18.6280 | 0.5891 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | acc | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0MAG-123023 | ACC - ELECTRICAL LOAD LIST | LOAD LIST | ACC ¦ Air Cooled Condenser | ELECTRICAL |  |  | LOAD LIST for ACC ¦ Air Cooled Condenser | [5 empty] | rule_query | other | other | load_list | acc_elec_load_list | acc¦air¦condenser¦cooled | acc | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.7500 | 0.6949 | 0.7335 | 0.7335 |  | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc¦electrical |  | acc¦electrical | query | acc¦condensate | match | false | 2 | 2 | 8.4032 | 0.4968 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc¦electrical | procurement | 10 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0MAG-123025 | ACC - MOTOR THERMAL LIMIT CURVE | CURVE | ACC ¦ Air Cooled Condenser |  |  |  | Performance Curve for ACC ¦ Air Cooled Condenser |  | ACC - Performance Curve | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | rule_query | curve | curve | performance_curve | performance_curve | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7526 | 0.9258 | 0.9258 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 2 | 1 | 15.9757 | 0.5849 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MAG-123026 | ACC - SPEED - TORQUE & CURRENT CURVE | CURVE | ACC ¦ Air Cooled Condenser |  |  |  | Performance Curve for ACC ¦ Air Cooled Condenser |  | ACC - Performance Curve | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | rule_query | curve | curve | performance_curve | performance_curve | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7526 | 0.9258 | 0.9258 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 2 | 2 | 15.9757 | 0.5615 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123027 | ACC - FUNCTIONAL DESCRIPTION | FUNCTIONAL DESCRIPTION | ACC ¦ Air Cooled Condenser |  |  |  | FUNCTIONAL DESCRIPTION for ACC ¦ Air Cooled Condenser |  | Functional Description | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | functional_description | functional_description | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6052 | 0.6482 | 0.4538 | FA | 1CF3020W42A08 | (COND Air EXT Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-09-27 | 2008-11-10 |  | installation | query_unknown | acc |  | acc | query | acc¦condensate | match | false | 26 | 5 | 8.5906 | 0.5447 | 0.0270 | 0.0203 | hybrid | structured_no_phase | acc |  |  | 2025-05-16 | 2025-05-31 | 2025-06-15 | 2025-06-30 | 2025-07-30 | 2025-08-29 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MAG-123029 | ACC - CONTROL LOGIC & LOOP DIAGRAM | CONTROL LOGIC & LOOP DIAGRAM | ACC ¦ Air Cooled Condenser |  |  |  | CONTROL LOGIC & LOOP DIAGRAM for ACC ¦ Air Cooled Condenser |  | Logic & Loop Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | diagram | diagram | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6766 | 0.9030 | 0.9030 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc |  | acc | query |  | activity_unscoped | true | 92 | 18 | 11.4781 | 0.5550 | 0.0194 | 0.0116 | hybrid | structured_phase_gap | acc | system_design¦engineering |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0MAG-123030 | ACC - I&C WIRING DIAGRAMS | WIRING DIAGRAMS | ACC ¦ Air Cooled Condenser | I&C ¦ Instrumentation and Control |  |  | WIRING DIAGRAMS for I&C ¦ Instrumentation and Control |  | ACC - Wiring Diagram | 1 | start+289D<=FA<=start+289D+2M | FA ∈ [start+289d, start+349d] | title | diagram | diagram | wiring_diagram | wiring_diagram | acc¦air¦andc¦condenser¦cooled¦instrumentation | acc | scoped | match | match | match | passed |  | 0.6667 | 0.8129 | 0.7105 | 0.7105 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc | acc | acc | query |  | activity_unscoped | true | 576 | 1 | 7.1447 | 0.6159 | 0.0180 | 0.0108 | hybrid | structured_phase_gap | acc | system_design¦engineering |  | 2025-01-16 | 2025-02-15 | 2025-03-17 | 2025-04-01 | 2025-04-16 | 2025-05-01 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0MAG-123031 | ACC - INSTRUMENT LIST | LIST | ACC ¦ Air Cooled Condenser | INSTRUMENT |  |  | Instrument List for ACC ¦ Air Cooled Condenser |  | ACC - Instrument List | 1 | start+137D<=FA<=start+137D+2M | FA ∈ [start+137d, start+197d] | rule_query | list | list | instrument_list | instrument_list | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.6843 | 0.9053 | 0.9053 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6401 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MAG-123032 | ACC - INSTRUMENT DATASHEET | DATASHEET | ACC ¦ Air Cooled Condenser | INSTRUMENT |  |  | Data Sheet for ACC ¦ Air Cooled Condenser |  | ACC - Instrument Datasheet | 1 | start+151D<=FA<=start+151D+2M | FA ∈ [start+151d, start+211d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9430 | 0.9829 | 0.9829 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 2 | 15.9757 | 0.6207 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2025-03-03 | 2025-04-02 | 2025-05-02 | 2025-05-17 | 2025-06-01 | 2025-06-16 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MAG-123033 | ACC - INSTRUMENT DRAWING | DRAWING | ACC ¦ Air Cooled Condenser | INSTRUMENT |  |  | DRAWING for ACC ¦ Air Cooled Condenser |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7078 | 0.6790 | 0.6790 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc |  | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.5037 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-04-27 | 2025-05-27 | 2025-06-26 | 2025-07-11 | 2025-07-26 | 2025-08-10 | generated | 0.90 | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MAG-123034 | ACC - INSTRUMENT CALIBRATION SHEET | CALIBRATION SHEET | ACC ¦ Air Cooled Condenser | INSTRUMENT |  |  | CALIBRATION SHEET for ACC ¦ Air Cooled Condenser | [5 empty] | rule_query | other | other | calibration_sheet | instrument_calibration_sheet | acc¦air¦condenser¦cooled |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.7096 | 0.6796 | 0.6796 |  | 1EF1600W00A03 | (HRSG #11/#12) Instrument, Service Air Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-29 |  |  | query_unknown | acc |  | acc | query | compressed_air¦hrsg | mismatch | false | 11 | 15 | 17.4936 | 0.5399 | 0.0274 | 0.0051 | hybrid | structured_no_phase | acc | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0MAG-123035 | ACC - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | ACC ¦ Air Cooled Condenser | INSTRUMENTATION |  |  | HOOK - UP DRAWING for ACC ¦ Air Cooled Condenser |  | ACC - Instrument Hook-up DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.8000 | 0.7673 | 0.7902 | 0.7902 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.4666 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-09-17 | 2025-10-17 | 2025-11-16 | 2025-12-01 | 2025-12-16 | 2025-12-31 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123036 | ACC-MOTORISED VALVE SPECIFICATION | SPECIFICATION | ACC ¦ Air Cooled Condenser |  |  |  | Technical Specification for ACC ¦ Air Cooled Condenser |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | acc¦air¦condenser¦cooled |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5319 | 0.6262 | 0.4384 | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | false | 3 | 2 | 15.3123 | 0.5162 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | acc | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0MAG-123037 | ACC - I&C JB OUTLINE AND LAYOUT DRAWING | DRAWING | ACC ¦ Air Cooled Condenser | I&C ¦ Instrumentation and Control |  |  | DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.5371 | 0.5111 | 0.5111 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.4868 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123038 | ACC - TERMINAL POINT LIST | LIST | ACC ¦ Air Cooled Condenser |  |  |  | LIST for ACC ¦ Air Cooled Condenser | [5 empty] | rule_query | other | list | list | equipment_list | acc¦air¦condenser¦cooled | acc | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6701 | 0.6677 | 0.6677 |  | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | false | 2 | 2 | 8.4032 | 0.5347 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc | procurement | 4 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123039 | ACC - UTILITY CONSUMPTION LIST | LIST | ACC ¦ Air Cooled Condenser |  |  |  | LIST for ACC ¦ Air Cooled Condenser | [5 empty] | rule_query | other | list | list | equipment_list | acc¦air¦condenser¦cooled | acc | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6701 | 0.6677 | 0.6677 |  | 1PF3020W42A07T | (COND Air EXT Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-08-13 | 2008-09-26 |  | delivery | query_unknown | acc |  | acc | query | acc¦condensate | match | false | 13 | 17 | 8.5906 | 0.5291 | 0.0267 | 0.0200 | hybrid | structured_no_phase | acc | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123045 | ACC ERECTION DRAWING | DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | DRAWING for ACC ¦ Air Cooled Condenser |  | ACC - Steel Structure DraWing (Erection DraWing) | 1 | start+169D<=FA<=start+169D+2M | FA ∈ [start+169d, start+229d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.6000 | 0.7903 | 0.6571 | 0.6571 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.5258 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-08-18 | 2025-09-17 | 2025-10-17 | 2025-11-01 | 2025-11-16 | 2025-12-01 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123046 | ACC REFERENCE DRAWING | DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | DRAWING for ACC ¦ Air Cooled Condenser |  | REFERENCE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7006 | 0.6768 | 0.4738 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc |  | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.5486 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123047 | ACC ERECTION MANUAL | MANUAL | ACC ¦ Air Cooled Condenser |  |  |  | MANUAL for ACC ¦ Air Cooled Condenser |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6898 | 0.6736 | 0.6736 | FI | 2PF3020W42A07T | (COND Air EXT Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-09-12 | 2008-10-27 | manual | delivery | match | acc |  | acc | query | acc¦condensate | match | false | 2 | 1 | 11.9081 | 0.5609 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | delivery¦procurement¦installation | 10 | 2025-06-06 | 2025-07-06 | 2025-08-05 | 2025-08-20 | 2025-09-04 | 2025-09-19 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XA00-P0MAG-123048 | ACC - HOLDING EJECTOR DRAWING | DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | DRAWING for ACC ¦ Air Cooled Condenser |  | HOLDING EJECTOR DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9072 | 0.9721 | 0.6805 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc |  | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.5730 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XA00-P0MAG-123049 | ACC - HOGGING EJECTOR DRAWING | DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | DRAWING for ACC ¦ Air Cooled Condenser |  | HOLDING EJECTOR DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7877 | 0.7030 | 0.4921 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc |  | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.5800 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123050 | ACC - WINDWALL DRAWING | DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | DRAWING for ACC ¦ Air Cooled Condenser |  | WINDWALL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8662 | 0.7265 | 0.5086 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc |  | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.5190 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123051 | ACC CABLE TRAY LAYOUT DRAWING | DRAWING | ACC ¦ Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.5371 | 0.5111 | 0.5111 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | false | 1 | 3 | 8.4959 | 0.5027 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-123052 | ACC_LIGHTING & SMALL POWER LAYOUT DRAWING | LAYOUT DRAWING | ACC ¦ Air Cooled Condenser | LIGHTING & SMALL POWER |  |  | Layout Drawing for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.6746 | 0.7274 | 0.7274 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc¦electrical | acc¦electrical | acc¦electrical | query | acc¦condensate | match | false | 1 | 14 | 8.4964 | 0.4682 | 0.0299 | 0.0224 | hybrid | structured_preferred | acc¦electrical | system_design¦civil_design | 10 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-DS00-P0MAG-123053 | ACC – CLEANING PROCEDURE | PROCEDURE | ACC ¦ Air Cooled Condenser |  |  |  | PROCEDURE for ACC ¦ Air Cooled Condenser |  | Cleaning & Painting Procedure | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | procedure | procedure | procedure | procedure | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6248 | 0.6541 | 0.6541 | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | false | 4 | 5 | 15.9757 | 0.6383 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-23 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123054 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COOLED CONDENSER | DRAWING | AIR COOLED CONDENSER |  |  |  | DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦bop¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.5371 | 0.5111 | 0.5111 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | false | 1 | 3 | 16.9918 | 0.5768 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123055 | WINDWALL LOGO FOR AIR COOLED CONDENSER |  | AIR COOLED CONDENSER |  |  |  | for AIR COOLED CONDENSER | [5 empty] | rule_query | other | drawing | windwall_logo_for_air_cooled_condenser | detail_drawing | acc¦air¦condenser¦cooled | acc | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.7376 | 0.6413 | 0.6413 |  | 1CF3020W42A08 | (COND Air EXT Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-09-27 | 2008-11-10 |  | installation | query_unknown | acc |  | acc | query | acc¦condensate | match | false | 2 | 7 | 17.1813 | 0.5126 | 0.0311 | 0.0233 | hybrid | structured_no_phase | acc | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0EKG-124001 | FGS - FUEL GAS SYSTEM GENERAL LAYOUT DRAWING | LAYOUT DRAWING |  | FGS - FUEL GAS SYSTEM ¦ Fuel Gas System - FUEL GAS SYSTEM |  |  | Layout Drawing for FGS - FUEL GAS SYSTEM ¦ Fuel Gas System - FUEL GAS SYSTEM | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 1 | 2 | 35.5215 | 0.7299 | 0.0325 | 0.0244 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0EKG-124002 | FGS - P&I DIAGRAM | P&I DIAGRAM |  | FGS ¦ Fuel Gas System |  |  | P&ID for FGS ¦ Fuel Gas System | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.7797 | 0.7589 | 0.7589 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 21.9084 | 0.8237 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0EKG-124003 | FGS - GAS FILTER & SEPARATOR ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | FGS - GAS FILTER & SEPARATOR ¦ Fuel Gas System - GAS FILTER & SEPARATOR |  |  | ASSEMBLY DRAWING for FGS - GAS FILTER & SEPARATOR ¦ Fuel Gas System - GAS FILTER & SEPARATOR | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦filter¦fuel¦gas¦separator | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7122 | 0.6803 | 0.6803 | FA | 1EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2007-08-31 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp¦gtg | match | false | 10 | 6 | 24.3369 | 0.6282 | 0.0294 | 0.0221 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-06-21 | 2024-08-02 | 2024-09-13 | 2024-08-23 | 2024-10-04 | 2024-11-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124004 | FGS - GAS HEATER ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | FGS - GAS HEATER ¦ Fuel Gas System - GAS HEATER |  |  | ASSEMBLY DRAWING for FGS - GAS HEATER ¦ Fuel Gas System - GAS HEATER | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦fuel¦gas¦heater | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7193 | 0.6825 | 0.6825 | FA | 1EF3520W16A01.2 | (Gas HTR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2007-10-01 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 2 | 1 | 31.9187 | 0.7097 | 0.0325 | 0.0244 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-10-23 | 2024-12-04 | 2025-01-15 | 2024-12-25 | 2025-02-05 | 2025-03-19 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124005 | FGS - MAIN GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | FGS ¦ Fuel Gas System |  |  | ASSEMBLY DRAWING for FGS ¦ Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7791 | 0.7004 | 0.7004 | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp¦gtg | match | false | 4 | 2 | 17.8543 | 0.7029 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-03 | 2025-02-14 | 2025-01-24 | 2025-03-07 | 2025-04-18 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124006 | FGS - 2ND GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | FGS ¦ Fuel Gas System |  |  | ASSEMBLY DRAWING for FGS ¦ Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7791 | 0.7004 | 0.7004 | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp¦gtg | match | false | 4 | 3 | 17.8543 | 0.7036 | 0.0315 | 0.0236 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-03 | 2025-02-14 | 2025-01-24 | 2025-03-07 | 2025-04-18 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124007 | FGS - COLD VENT STACK ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | FGS ¦ Fuel Gas System |  |  | ASSEMBLY DRAWING for FGS ¦ Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7791 | 0.7004 | 0.7004 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 5 | 1 | 7.6021 | 0.6741 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-07-05 | 2024-08-16 | 2024-09-27 | 2024-09-06 | 2024-10-18 | 2024-11-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124008 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP ASSEMBLY DRAWING | ASSEMBLY DRAWING | Tank | FGS ¦ Fuel Gas System |  |  | ASSEMBLY DRAWING for Tank |  | Tank DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | fgp¦pump¦tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7244 | 0.6840 | 0.4788 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | design_drawing | civil_design | compatible | fgp |  | fgp | query | condensate¦fgp | match | false | 1 | 1 | 31.8927 | 0.7118 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | 2024-04-02 | 2024-05-02 | generated | 0.30 | 0.64 | usable | rule_score_medium;activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124009 | FGS - PANEL LAYOUT FOR LOCAL ELECTRICAL ROOM FOR FUEL GAS SUPPLY SYSTEM | LAYOUT |  | FUEL GAS SUPPLY SYSTEM | LOCAL ELECTRICAL ROOM |  | Layout Drawing for LOCAL ELECTRICAL ROOM | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦local¦room | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8036 | 0.8244 | 0.8244 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 3 | 1 | 32.4605 | 0.7485 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124010 | FGS - GAS CHROMATOGRAPH OUTLINE DRAWING | OUTLINE DRAWING |  | FGS ¦ Fuel Gas System |  |  | Outline Drawing for FGS ¦ Fuel Gas System |  | GAS CHROMATOGRAPH OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | outline_drawing | outline_drawing | fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8764 | 0.9629 | 0.6740 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 6.8233 | 0.7226 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124011 | FGS - ESD VALVE ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | FGS ¦ Fuel Gas System |  |  | ASSEMBLY DRAWING for FGS ¦ Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7791 | 0.7004 | 0.7004 | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 1 | 3 | 17.0083 | 0.6046 | 0.0323 | 0.0242 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-09-04 | 2024-10-16 | 2024-11-27 | 2024-11-06 | 2024-12-18 | 2025-01-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124012 | FGS - CABLE ROUTE LAYOUT FOR FUEL GAS SUPPLY SYSTEM | CABLE ROUTE LAYOUT |  | FGS ¦ Fuel Gas System |  |  | CABLE ROUTE LAYOUT for FGS ¦ Fuel Gas System | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7967 | 0.8223 | 0.8223 | FA | 0EF3520W32A04.1 | (FGS LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 2 | 4 | 25.6500 | 0.6682 | 0.0318 | 0.0238 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124013 | FGS - FOUDATION & LOADS FOR FUEL GAS SUPPLY SYSTEM |  |  | FGS ¦ Fuel Gas System |  |  | for FGS ¦ Fuel Gas System | [5 empty] | rule_query | other | description | fgs_foudation_and_loads_for_fuel_gas_supply_system | system_description | fgp¦fgs¦fuel¦gas | fgp | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.7463 | 0.7489 | 0.7489 |  | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 |  | civil_design | query_unknown | fgp |  | fgp | query | fgp | match | false | 1 | 2 | 25.6500 | 0.7443 | 0.0325 | 0.0244 | hybrid | structured_no_phase | fgp | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0EKG-124014 | FGS - CONTROL LOOP, LOGIC DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | LOGIC DIAGRAM |  | FGS ¦ Fuel Gas System |  |  | Control Loop Diagram for FGS ¦ Fuel Gas System | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7592 | 0.7528 | 0.7528 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | 2 | 1 | 25.8316 | 0.7430 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0EKG-124015 | FGS - CABLE BLOCK DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | BLOCK DIAGRAM |  | FGS ¦ Fuel Gas System |  |  | BLOCK DIAGRAM for FGS ¦ Fuel Gas System | Cathodic | Block Diagram | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | diagram | diagram | diagram | diagram | fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5229 | 0.6235 | 0.6235 | SKIP | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 25.8316 | 0.7310 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0EKG-124016 | FGS - TERMINAL BOX DRAWING FOR FUEL GAS SUPPLY SYSTEM | DRAWING |  | FGS ¦ Fuel Gas System |  |  | DRAWING for FGS ¦ Fuel Gas System | Fuel Gas System | Embedded Material DraWing | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7430 | 0.6896 | 0.6896 | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 1 | 3 | 25.6500 | 0.6696 | 0.0323 | 0.0242 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-10-02 | 2024-10-30 | 2024-11-27 | 2024-11-20 | 2024-12-18 | 2025-01-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0EKG-124017 | FGS - SINGLE LINE DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | SINGLE LINE DIAGRAM |  | FGS ¦ Fuel Gas System |  |  | Single Line Diagram for FGS ¦ Fuel Gas System | Fuel Gas System | Single Line Diagram | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 1.0000 | 0.9181 | 0.9754 | 0.9754 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | 3 | 1 | 25.8316 | 0.7817 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering |  | 2024-05-10 | 2024-06-21 | 2024-08-02 | 2024-07-12 | 2024-08-23 | 2024-10-04 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124018 | FGS - MEASUREMENT LIST FOR FUEL GAS SUPPLY SYSTEM | LIST |  | FGS ¦ Fuel Gas System |  |  | LIST for FGS ¦ Fuel Gas System | [5 empty] | rule_query | other | list | list | instrument_list | fgp¦fgs¦fuel¦gas | fgp | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.8000 | 0.8031 | 0.8009 | 0.8009 |  | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 |  | procurement | query_unknown | fgp |  | fgp | query | fgp | match | false | 35 | 1 | 14.2585 | 0.7110 | 0.0269 | 0.0202 | hybrid | structured_no_phase | fgp | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BX03-P0EKG-124020 | FGS - WIRING DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | WIRING DIAGRAM |  | FGS ¦ Fuel Gas System |  |  | WIRING DIAGRAM for FGS ¦ Fuel Gas System | Fuel Gas System | Interconnection Wiring Diagram | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7845 | 0.8187 | 0.8187 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 25.8316 | 0.7686 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering |  | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-124021 | FGS - VALVE LIST | LIST |  | FGS ¦ Fuel Gas System |  |  | Valve List for FGS ¦ Fuel Gas System |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | valve_list | valve_list | fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7385 | 0.6882 | 0.6882 | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | 7 | 5 | 12.2775 | 0.6383 | 0.0303 | 0.0303 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-08-24 | 2024-09-23 | 2024-10-23 | 2024-11-07 | 2024-11-22 | 2024-12-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0EKG-124022 | FGS - VALVE DATA SHEET | DATA SHEET |  | FGS ¦ Fuel Gas System |  |  | Data Sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 14.9235 | 0.6970 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0EKG-124023 | FGS - BUFFER TANK OUTLINE DRAWING | OUTLINE DRAWING |  | FGS ¦ Fuel Gas System |  |  | Outline Drawing for FGS ¦ Fuel Gas System |  | BUFFER TANK OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | outline_drawing | outline_drawing | fgp¦fgs¦fuel¦gas¦tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.8537 | 0.9561 | 0.6693 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 5.3727 | 0.6758 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124024 | FGS - BOOSTER COMPRESSOR OUTLINE DRAWING | OUTLINE DRAWING |  | FGS ¦ Fuel Gas System |  |  | Outline Drawing for FGS ¦ Fuel Gas System | Substation | Outline DraWing (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5844 | 0.6420 | 0.6420 | SKIP | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | dc_ups | fgp | query | fgp | match | false | 1 | 1 | 7.6021 | 0.6940 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124025 | FGS - GAS HEATER DATA SHEET | DATA SHEET |  | FGS ¦ Fuel Gas System |  |  | Data Sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 2 | 1 | 20.8124 | 0.7321 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-09-11 | 2024-10-30 | 2024-12-18 | 2024-11-20 | 2025-01-08 | 2025-02-26 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124026 | FGS - MAIN GAS PRESSURE REDUCING STATION DATA SHEET | DATA SHEET |  | FGS ¦ Fuel Gas System |  |  | Data Sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-04-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp¦gtg | match | false | 2 | 2 | 24.7216 | 0.7074 | 0.0323 | 0.0323 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124027 | FGS - 2ND GAS PRESSURE REDUCING STATION DATA SHEET | DATA SHEET |  | FGS ¦ Fuel Gas System |  |  | Data Sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-04-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp¦gtg | match | false | 2 | 4 | 24.7216 | 0.6799 | 0.0318 | 0.0318 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124028 | FGS - COLD VENT STACK DATA SHEET | DATA SHEET |  | FGS ¦ Fuel Gas System |  |  | Data Sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 14.9235 | 0.6744 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124029 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP DATA SHEET | DATA SHEET |  | FGS ¦ Fuel Gas System |  |  | Data Sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fgs¦fuel¦gas¦pump¦tank | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | procurement | procurement | match | fgp | fgp | fgp | query | condensate¦fgp | match | false | 1 | 1 | 31.1873 | 0.7242 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124030 | FGS - GAS CHROMATOGRAPH DATA SHEET | DATA SHEET |  | FGS ¦ Fuel Gas System |  |  | Data Sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8387 | 0.8349 | 0.8349 | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 16.4325 | 0.7231 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124031 | FGS - ESD VALVE DATA SHEET | DATA SHEET | ESD VALVE | FGS ¦ Fuel Gas System |  |  | Data Sheet for ESD VALVE |  | Valve Data Sheet | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | esd¦fgp¦valve |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7540 | 0.9262 | 0.6483 | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 14.9235 | 0.6122 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124032 | FGS - BOOSTER COMPRESSOR DATA SHEET | DATA SHEET | BOOSTER COMPRESSOR | FGS ¦ Fuel Gas System |  |  | Data Sheet for BOOSTER COMPRESSOR | Air Compressor | Data Sheet for Valves | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | booster¦compressor¦fgp |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7470 | 0.6908 | 0.6908 | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | procurement | procurement | match | fgp | compressed_air | fgp | query | fgp | match | false | 1 | 2 | 38.8465 | 0.6837 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124033 | FGS - BUFFER TANK DATA SHEET | DATA SHEET | BUFFER TANK | FGS ¦ Fuel Gas System |  |  | Data Sheet for BUFFER TANK |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | buffer¦fgp¦tank |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5984 | 0.6462 | 0.6462 | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 33.9800 | 0.7463 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-CH01-P0EKG-124039 | INSTALLATION & ERECTION MANUAL | INSTALLATION & ERECTION MANUAL |  |  |  |  | INSTALLATION & ERECTION MANUAL |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9423 | 0.9827 | 0.9827 | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | manual | delivery | match |  |  |  |  | bop | query_unscoped | false | 1 | 5 | 29.1386 | 0.4819 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | delivery¦procurement¦installation |  | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124040 | FGS_DATASHEET AND OUTLINE DRAWING FOR GTG INLET STRAINERS | DATASHEET AND OUTLINE DRAWING | GTG INLET STRAINERS ¦ Gas Turbine Generator INLET STRAINERS | FGS ¦ Fuel Gas System |  |  | DATASHEET AND OUTLINE DRAWING for GTG INLET STRAINERS ¦ Gas Turbine Generator INLET STRAINERS |  | Valve datasheet & draWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | datasheet | datasheet | data_sheet | data_sheet | fgp¦gas¦generator¦gtg¦inlet¦strainers¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5919 | 0.6442 | 0.6442 | FA | 2PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | 2007-03-30 | 2008-02-29 | procurement | procurement | match | fgp¦gtg |  | fgp¦gtg | query | gtg | match | false | 2 | 10 | 35.0374 | 0.6199 | 0.0304 | 0.0304 | hybrid | structured_cell_found_text_preferred | fgp¦gtg | procurement |  | 2024-06-22 | 2024-07-22 | 2024-08-21 | 2024-09-05 | 2024-09-20 | 2024-10-05 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0EKG-124048 | CABLE CONNECTION DIAGRAM | CABLE CONNECTION DIAGRAM |  |  |  |  | CABLE CONNECTION DIAGRAM | Substation | Cable Connection Diagram | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7653 | 0.7546 | 0.7546 | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 18 | 111 | 16.9020 | 0.4439 | 0.0187 | 0.0105 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-UB01-P0EKG-124075 | FGS - FUNCTIONAL DESCRIPTION | FUNCTIONAL DESCRIPTION |  | FGS ¦ Fuel Gas System |  |  | FUNCTIONAL DESCRIPTION for FGS ¦ Fuel Gas System | Fuel Gas System | Functional description | 1 | start+10W<=FA<=FC<=start+18W | FA ∈ [start+70d, start+126d] ¦ FC ∈ [start+70d, start+126d] | rule_query | other | other | functional_description | functional_description | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 1.0000 | 0.8544 | 0.9563 | 0.9563 | FA | 0PF3520W42A04.3P | (FOFP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 | 2008-03-28 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 4 | 6 | 12.4076 | 0.6441 | 0.0308 | 0.0308 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-09-10 | 2024-10-08 | 2024-11-05 | 2024-10-29 | 2024-11-26 | 2024-12-24 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKG-124077 | FGS – ISO DRAWING | ISO DRAWING |  | FGS ¦ Fuel Gas System |  |  | ISO DRAWING for FGS ¦ Fuel Gas System | Fuel Gas System | Piping ISO DraWing | 1 | start+20W<=FA<=FC<=start+36W | FA ∈ [start+140d, start+252d] ¦ FC ∈ [start+140d, start+252d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7308 | 0.8026 | 0.8026 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 5 | 1 | 7.6021 | 0.7177 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-08-02 | 2024-09-27 | 2024-11-22 | 2024-10-18 | 2024-12-13 | 2025-02-07 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL30-P0EKG-124078 | FGS – SALES GAS CONTROL VALVE STATION DOCUMENT & DRAWING | DOCUMENT & DRAWING | SALES GAS CONTROL VALVE STATION | FGS ¦ Fuel Gas System |  |  | DOCUMENT & DRAWING for SALES GAS CONTROL VALVE STATION |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | fgp¦gas¦sales¦station¦valve |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5002 | 0.5001 | 0.5001 | FI | 0EF3520W00A10.3 | (FO FWD Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 |  | design_drawing | civil_design | compatible | fgp |  | fgp | query | fgp | match | false | 13 | 2 | 19.6206 | 0.6082 | 0.0298 | 0.0224 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-19 | 2024-12-19 | 2025-01-18 | 2025-02-02 | 2025-02-17 | 2025-03-04 | generated | 0.90 | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124079 | FGS – DUPLEX STRAINER INSTRUMENT DATA & DRAWING | DATA & DRAWING | DUPLEX STRAINER | FGS ¦ Fuel Gas System |  |  | DATA & DRAWING for DUPLEX STRAINER |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | duplex¦fgp¦strainer |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5643 | 0.6359 | 0.6359 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp |  | fgp | query | fgp | match | false | 1 | 7 | 24.6020 | 0.5555 | 0.0313 | 0.0235 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-07-10 | 2024-08-09 | 2024-09-08 | 2024-09-23 | 2024-10-08 | 2024-10-23 | generated | 0.90 | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-DN04-P0EKG-124161 | INSULATION PROCEDURE FOR FGSS AREA AND HEATER SKIDS | PROCEDURE | HEATER SKIDS | FGSS ¦ Fuel Gas Supply System |  |  | PROCEDURE for HEATER SKIDS |  | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | fgp¦heater¦skids |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4185 | 0.4755 | 0.4755 | FI | 1PF3520W42A08.2T | (Gas HTR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2008-04-02 | 2008-05-16 | delivery | delivery | match | fgp |  | fgp | query | fgp | match | false | 1 | 5 | 25.4495 | 0.6167 | 0.0318 | 0.0318 | hybrid | structured_preferred | fgp | delivery¦procurement | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0EKG-124180 | FGS - 120V TR PANEL FOR GAS CHROMATOGRAPH |  | 120V TR PANEL ¦ 120V Transformer PANEL | FGS ¦ Fuel Gas System |  |  | for 120V TR PANEL ¦ 120V Transformer PANEL | [5 empty] | rule_query | other | other | fgs_120v_tr_panel_for_gas_chromatograph | rating_plate | 120v¦fgp¦panel¦transformer |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.3333 | 0.5652 | 0.4029 | 0.4029 |  | 1CF6500W70A06 | (GTG TR) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-05-31 | 2008-07-16 |  | installation | query_unknown | fgp¦gsut_uat |  | fgp¦gsut_uat | query | electrical¦gsut_uat¦gtg | match | false | 18 | 2 | 16.7468 | 0.6271 | 0.0289 | 0.0217 | hybrid | structured_no_phase | fgp¦gsut_uat | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P8ZEN-125001 | RESERVE BOILER - SUPPLY/EQUIPMENT LIST | LIST | RESERVE BOILER |  |  |  | Equipment List for RESERVE BOILER |  | Equipment list | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | equipment_list | equipment_list | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6505 | 0.6618 | 0.6618 | FI | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 52 | 2 | 9.6644 | 0.5951 | 0.0251 | 0.0063 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P8QHA-125002 | RESERVE BOILER - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | RESERVE BOILER |  |  |  | System Description for RESERVE BOILER |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5362 | 0.6275 | 0.5334 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 2 | 21 | 9.5174 | 0.5345 | 0.0285 | 0.0171 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.60 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P8ZEN-125012 | RESERVE BOILER - BOILER PREDICTED PERFORMANCE DATA & CURVE | DATA & CURVE | RESERVE BOILER |  |  |  | Performance Curve for RESERVE BOILER |  | Boiler Predicted Performance Data & Curve | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | curve | curve | performance_curve | performance_curve | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8565 | 0.9569 | 0.6699 | FA | 0EF3530W00A01.1 | (Common EDG) Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Common Emergency Diesel Generator | 2007-03-01 | 2007-04-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 6 | 145 | 9.7142 | 0.4188 | 0.0200 | 0.0120 | hybrid | structured_system_absent | reserve_boiler | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P8ZEN-125014 | RESERVE BOILER - BOILER START - UP CURVE | CURVE | RESERVE BOILER |  |  |  | Performance Curve for RESERVE BOILER | FinFan Cooler | Performance Curve | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | curve | curve | performance_curve | performance_curve | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6100 | 0.5330 | 0.5330 | FI | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 22 | 11 | 8.5035 | 0.5031 | 0.0263 | 0.0066 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P8ZEN-125019 | RESERVE BOILER_ERECTION MANUAL | ERECTION MANUAL | RESERVE BOILER |  |  |  | ERECTION MANUAL for RESERVE BOILER |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6179 | 0.6520 | 0.6520 | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | manual | delivery | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 1 | 1 | 29.1386 | 0.5699 | 0.0328 | 0.0082 | hybrid | structured_system_absent | reserve_boiler | delivery¦procurement¦installation | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC00-P8QHA-125101 | RESERVE BOILER - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | GENERAL ARRANGEMENT DRAWING for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6751 | 0.9025 | 0.9025 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 49 | 458 | 13.4438 | 0.4833 | 0.0111 | 0.0067 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8QHB-125151 | RESERVE BOILER - FOUNDATION LOADING DATA FOR STEEL STRUCTURE & STACK |  | RESERVE BOILER |  |  |  | for RESERVE BOILER |  | FOUNDATION AND LOADING DATA | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5484 | 0.6895 | 0.4827 | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 39 | 2 | 10.3089 | 0.6501 | 0.0262 | 0.0066 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XT00-P8QHB-125152 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STEEL STRUCTURE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | FinFan Cooler | Fin Fan Cooler Steel structure assembly draWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3750 | 0.5536 | 0.4286 | 0.4286 | FA | 3EF1625W00A02.1 | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | 2007-08-01 |  | civil_design | civil_design | match | reserve_boiler | ccw | reserve_boiler | query | hrsg | mismatch | false | 776 | 38 | 3.4651 | 0.5265 | 0.0114 | 0.0029 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XT00-P8QHB-125153 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STACK | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Arrangement DraWing for Stack | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5540 | 0.8662 | 0.6064 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 177 | 218 | 3.6958 | 0.4701 | 0.0078 | 0.0020 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P8QHB-125161 | RESERVE BOILER - DESIGN CRITERIA FOR STEEL STRUCTURE | DESIGN CRITERIA | RESERVE BOILER |  |  |  | DESIGN CRITERIA for RESERVE BOILER |  | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | criteria | criteria | design_criteria | design_criteria | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.5964 | 0.4789 | 0.4789 | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 1 | 1 | 62.3058 | 0.6051 | 0.0328 | 0.0197 | hybrid | structured_system_absent | reserve_boiler | design_criteria¦system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P8QHB-125162 | RESERVE BOILER - CONNECTION DETAIL DRAWING FOR STEEL STRUCTURE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5634 | 0.6357 | 0.6357 | FI | 3EF1625W00A02.2 | (HRSG #32 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | 2007-08-06 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3955 | 37 |  | 0.5236 | 0.0106 | 0.0026 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC02-P8QHB-125164 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STEEL STRUCTURE | ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 134 | 7 | 10.1506 | 0.5725 | 0.0201 | 0.0050 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC02-P8QHB-125172 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STACK | ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 82 | 106 | 10.6763 | 0.5372 | 0.0131 | 0.0033 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD07-P8QHA-125201 | RESERVE BOILER - PRESSURE PART ARRANGEMENT OF BOILER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | Cooling ToWer | COOLING TOWER _MECHANICAL PART ASSEMBLY DRAWING | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5521 | 0.3990 | 0.3990 | FA | 1EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | fgp¦gtg¦hrsg | mismatch | false | 19 | 414 | 8.9279 | 0.4737 | 0.0148 | 0.0028 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125202 | RESERVE BOILER - DESUPERHEATER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Desuperheater DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7904 | 0.7038 | 0.4927 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3792 | 1 |  | 0.5642 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125207 | RESERVE BOILER - ECONOMIZER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Economizer - DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6967 | 0.6757 | 0.4730 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3792 | 3 |  | 0.5259 | 0.0161 | 0.0030 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8QHA-125300 | RESERVE BOILER - FOUNDATION LOADING DATA FOR BOILER PROPER | DATA | RESERVE BOILER |  |  |  | DATA for RESERVE BOILER |  | FOUNDATION AND LOADING DATA | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5985 | 0.7046 | 0.4932 | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | 87 | 6 | 8.9406 | 0.5649 | 0.0220 | 0.0055 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P8QHA-125303 | RESERVE BOILER - REFRACTORY LINING PROCEDURE FOR BOILER PROPER | PROCEDURE | RESERVE BOILER |  |  |  | PROCEDURE for RESERVE BOILER | FireFighting | Rubber Lining Procedure (if applicable) | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | title | procedure | procedure | procedure | procedure | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5651 | 0.4029 | 0.4029 | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 7 | 2 | 11.9765 | 0.5724 | 0.0311 | 0.0078 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P8QHA-125304 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR BOILER PROPER | SPECIFICATION & DRAWING | RESERVE BOILER |  |  |  | Insulation Specification for RESERVE BOILER | FireFighting | Insulation Specification | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | specification | specification | insulation_specification | insulation_specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6906 | 0.6738 | 0.6738 | FA | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-10-01 | 2008-04-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 5 | 1 | 19.4219 | 0.5985 | 0.0318 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125308 | RESERVE BOILER - NAME PLATE DRAWING OF BOILER PROPER | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6275 | 0.8882 | 0.8882 | FI | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 581 | 82 | 2.0974 | 0.5123 | 0.0086 | 0.0016 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125310 | RESERVE BOILER - NAME PLATE DRAWING OF VALVE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5845 | 0.8754 | 0.8754 | FI | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 604 | 60 | 2.0974 | 0.5132 | 0.0098 | 0.0018 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P8QHL-125400 | RESERVE BOILER - GAS & AIR DUCT ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 131 | 69 | 10.6763 | 0.5631 | 0.0130 | 0.0032 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XA00-P8QHL-125401 | RESERVE BOILER - DAMPER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3831 | 40 |  | 0.5442 | 0.0103 | 0.0019 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XA00-P8QHL-125402 | RESERVE BOILER - EXPANSION JOINT DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Expansion Joint Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7411 | 0.9223 | 0.6456 | FA | 1EF3030W16A01 | (EXP Head Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | ccw | mismatch | false | 47 | 28 | 4.3847 | 0.5000 | 0.0207 | 0.0039 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P8QHL-125403 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR DUCT | SPECIFICATION & DRAWING | RESERVE BOILER |  |  |  | Insulation Specification for RESERVE BOILER | FireFighting | Insulation Specification | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | specification | specification | insulation_specification | insulation_specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6906 | 0.6738 | 0.6738 | FA | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-10-01 | 2008-04-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 4 | 1 | 19.4219 | 0.5867 | 0.0320 | 0.0080 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P8ZEN-125502 | RESERVE BOILER - PMS (PIPE MATERIAL SPECIFICATION) | PMS (PIPE MATERIAL SPECIFICATION) | RESERVE BOILER |  |  |  | PMS (PIPE MATERIAL SPECIFICATION) for RESERVE BOILER | FinFan Cooler | Pipe Material Specification | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | specification | specification | specification | specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6314 | 0.6094 | 0.6094 | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 11 | 1 | 21.2319 | 0.6904 | 0.0305 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P8ZEN-125503 | RESERVE BOILER - LINE LIST | LINE LIST | RESERVE BOILER |  |  |  | LINE LIST for RESERVE BOILER | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5878 | 0.5263 | 0.5263 | FI | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | procurement | procurement | match | reserve_boiler | compressed_air | reserve_boiler | query | bop | mismatch | false | 21 | 11 | 8.5035 | 0.5778 | 0.0264 | 0.0066 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P8ZEN-125504 | RESERVE BOILER - VALVE LIST | VALVE LIST | RESERVE BOILER |  |  |  | Valve List for RESERVE BOILER |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7560 | 0.6935 | 0.6935 | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 6 | 4 | 22.3249 | 0.5992 | 0.0308 | 0.0185 | hybrid | structured_system_absent | reserve_boiler | procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P8ZEN-125505 | RESERVE BOILER - PIPING SPECIALITY DRAWING & LIST | DRAWING & LIST | RESERVE BOILER | PIPING |  |  | DRAWING & LIST for RESERVE BOILER |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6711 | 0.5513 | 0.5513 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 49 | 328 | 10.3393 | 0.4831 | 0.0118 | 0.0053 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125506 | RESERVE BOILER - MANUAL VALVE DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | MANUAL VALVE ASSEMBLY DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7880 | 0.7614 | 0.5330 | FA | 0PF7000W86A03T | (Control Valve) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2008-08-16 | 2008-09-30 | manual | delivery | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 14 | 58 | 7.5359 | 0.4712 | 0.0220 | 0.0099 | hybrid | structured_system_absent | reserve_boiler | delivery¦procurement¦installation |  | 2025-04-04 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-18 | 2025-07-18 | generated | 0.30 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125507 | RESERVE BOILER - PIPING & PIPING SUPPORT PLAN DRAWING | DRAWING | RESERVE BOILER | PIPING |  |  | DRAWING for RESERVE BOILER | FireFighting | Piping Support DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6250 | 0.7125 | 0.7125 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 104 | 180 | 12.8493 | 0.5145 | 0.0103 | 0.0046 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125509 | RESERVE BOILER - PIPING SUPPORT DETAIL DRAWING FOR SMALL BORE PIPING. | DRAWING | RESERVE BOILER | PIPING |  |  | DRAWING for PIPING |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | piping¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6485 | 0.8946 | 0.6262 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | 325 | 5 | 7.8939 | 0.5152 | 0.0180 | 0.0034 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL30-P8ZEN-125514 | RESERVE BOILER - CONTROL VALVE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5196 | 0.5059 | 0.5059 | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 479 | 569 | 5.3193 | 0.4647 | 0.0034 | 0.0016 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125520 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6063 | 0.6019 | 0.6019 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 92 | 73 | 11.6136 | 0.5181 | 0.0141 | 0.0085 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125521 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦pump¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6016 | 0.6005 | 0.6005 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater¦reserve_boiler | compressed_air | feedwater¦reserve_boiler | query | feedwater | match | false | 1 | 1 | 8.4247 | 0.6315 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater¦reserve_boiler | system_design | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125522 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5968 | 0.5990 | 0.5990 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 32 | 38 | 18.6136 | 0.5438 | 0.0211 | 0.0126 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125523 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5957 | 0.5987 | 0.5987 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦steam | compressed_air | reserve_boiler¦steam | query | steam | match | false | 1 | 1 | 14.3151 | 0.6358 | 0.0328 | 0.0328 | hybrid | structured_preferred | reserve_boiler¦steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125524 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5935 | 0.5981 | 0.5981 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 92 | 263 | 11.6136 | 0.4990 | 0.0097 | 0.0058 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125525 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5874 | 0.5962 | 0.5962 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 321 | 25 | 8.4723 | 0.5410 | 0.0144 | 0.0086 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125526 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.6955 | 0.7086 | 0.7086 | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | ccw¦reserve_boiler¦service_water |  | ccw¦reserve_boiler¦service_water | query | service_water | match | false | 1 | 1 | 38.8077 | 0.6284 | 0.0328 | 0.0328 | hybrid | structured_preferred | ccw¦reserve_boiler¦service_water | system_design | 4 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125527 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6385 | 0.7515 | 0.7515 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler | compressed_air | compressed_air¦reserve_boiler | query | compressed_air | match | false | 1 | 1 | 24.3472 | 0.5604 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125530 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for DEAERATOR SYSTEM |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | deaerator¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7256 | 0.6377 | 0.6377 | FI | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | 327 | 1 | 6.4487 | 0.5631 | 0.0190 | 0.0036 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125531 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for Pump | FireFighting | Equipment (incl. pump) Detail DraWing | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump¦reserve_boiler | pump | scoped | match | match | match | passed |  | 0.3333 | 0.5981 | 0.4128 | 0.4128 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | feedwater¦reserve_boiler |  | feedwater¦reserve_boiler | query | feedwater | match | false | 1 | 1 | 8.4247 | 0.6253 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater¦reserve_boiler | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125532 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for BOILER WATER SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve_boiler¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5304 | 0.6258 | 0.6258 | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 34 | 45 | 18.6136 | 0.5349 | 0.0202 | 0.0091 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125533 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for BOILER STEAM SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve_boiler¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5272 | 0.6248 | 0.6248 | FI | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler¦steam |  | reserve_boiler¦steam | query | steam | match | false | 1 | 1 | 14.3151 | 0.6221 | 0.0328 | 0.0246 | hybrid | structured_preferred | reserve_boiler¦steam | system_design¦civil_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125534 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for BURNER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | burner¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6308 | 0.8892 | 0.6225 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | 327 | 1 | 6.4487 | 0.5565 | 0.0190 | 0.0036 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125535 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for BLOWDOWN SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | blowdown¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5294 | 0.6255 | 0.6255 | FI | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 325 | 24 | 8.4723 | 0.5367 | 0.0145 | 0.0065 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125536 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for CLOSED COOLING WATER & SERVICE WATER SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | closed¦cooling¦reserve_boiler¦service¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5312 | 0.6260 | 0.6260 | FI | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | ccw¦reserve_boiler¦service_water |  | ccw¦reserve_boiler¦service_water | query | service_water | match | false | 1 | 1 | 38.8077 | 0.6128 | 0.0328 | 0.0246 | hybrid | structured_preferred | ccw¦reserve_boiler¦service_water | system_design¦civil_design | 10 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125537 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for SERVICE AIR & SEALING AIR SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦reserve_boiler¦sealing¦service |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.6275 | FI | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible | compressed_air¦reserve_boiler |  | compressed_air¦reserve_boiler | query | compressed_air | match | false | 1 | 1 | 24.3472 | 0.5478 | 0.0328 | 0.0246 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design¦civil_design | 10 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125540 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6156 | 0.6047 | 0.6047 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 92 | 58 | 11.6136 | 0.5264 | 0.0151 | 0.0090 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125541 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦pump¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6105 | 0.6031 | 0.6031 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater¦reserve_boiler | compressed_air | feedwater¦reserve_boiler | query | feedwater | match | false | 1 | 1 | 8.4247 | 0.6419 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater¦reserve_boiler | system_design | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125542 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6092 | 0.6028 | 0.6028 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 32 | 39 | 18.6136 | 0.5488 | 0.0210 | 0.0126 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125543 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6079 | 0.6024 | 0.6024 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦steam | compressed_air | reserve_boiler¦steam | query | steam | match | false | 1 | 1 | 14.3151 | 0.6463 | 0.0328 | 0.0328 | hybrid | structured_preferred | reserve_boiler¦steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125544 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(COMBUSTION AIR & FLUE GAS SYSTEM) | DRAWING | RESERVE BOILER | COMBUSTION AIR & FLUE GAS SYSTEM ¦ COMBUSTION Air and Flue Gas System |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6327 | 0.7498 | 0.7498 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 89 | 110 | 20.9360 | 0.5248 | 0.0126 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125545 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6085 | 0.6026 | 0.6026 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 92 | 225 | 11.6136 | 0.5015 | 0.0101 | 0.0061 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125546 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6003 | 0.6001 | 0.6001 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 321 | 18 | 8.4723 | 0.5468 | 0.0154 | 0.0093 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125547 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CHEMICAL DOSING SYSTEM) | DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6044 | 0.6013 | 0.6013 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦wts | compressed_air | reserve_boiler¦wts | query | wts | match | false | 1 | 1 | 38.6097 | 0.6565 | 0.0328 | 0.0328 | hybrid | structured_preferred | reserve_boiler¦wts | system_design | 5 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125548 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.6998 | 0.7099 | 0.7099 | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | ccw¦reserve_boiler¦service_water |  | ccw¦reserve_boiler¦service_water | query | service_water | match | false | 1 | 1 | 38.8077 | 0.6281 | 0.0328 | 0.0328 | hybrid | structured_preferred | ccw¦reserve_boiler¦service_water | system_design | 4 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125549 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(INSTRUMENT AIR SYSTEM) | DRAWING | RESERVE BOILER | INSTRUMENT AIR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6597 | 0.7579 | 0.7579 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler | compressed_air | compressed_air¦reserve_boiler | query | compressed_air | match | false | 1 | 1 | 16.5618 | 0.5889 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125550 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6513 | 0.7554 | 0.7554 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler | compressed_air | compressed_air¦reserve_boiler | query | compressed_air | match | false | 1 | 1 | 24.3472 | 0.5611 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125570 | RESERVE BOILER_ FUEL SKID DETAIL DRAWING | DETAIL DRAWING | RESERVE BOILER |  |  |  | Detail Drawing for RESERVE BOILER |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5311 | 0.6260 | 0.6260 | FI | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | 479 | 8 | 5.4788 | 0.5536 | 0.0166 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG05-P8ZEN-125571 | RESERVE BOILER - HEAT & MASS BLANCE DIAGRAM | DIAGRAM | RESERVE BOILER |  |  |  | Diagram for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5980 | 0.4127 | 0.2889 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query | hrsg | mismatch | false | 4 | 5 | 12.1052 | 0.5357 | 0.0310 | 0.0058 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125582 | RESERVE BOILER - P&ID OF DEAERATOR SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | DEAERATOR SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for DEAERATOR SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | deaerator¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7337 | 0.9201 | 0.6441 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 3 | 6 | 29.5500 | 0.6034 | 0.0310 | 0.0186 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125583 | RESERVE BOILER - P&ID OF FEEDWATER PUMP SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for FEEDWATER PUMP SYSTEM | Boiler Feed Pump | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | p_id | p_id | feedwater¦pump¦reserve_boiler | pump | scoped | match | match | match | passed |  | 0.7500 | 0.7649 | 0.7545 | 0.7545 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater¦reserve_boiler | feedwater | feedwater¦reserve_boiler | query | feedwater | match | false | 1 | 1 | 29.8610 | 0.7004 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater¦reserve_boiler | system_design¦procurement | 10 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125584 | RESERVE BOILER - P&ID OF BOILER WATER SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | BOILER WATER SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for BOILER WATER SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | boiler¦reserve_boiler¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7450 | 0.9235 | 0.6464 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 7 | 11 | 35.0262 | 0.6022 | 0.0290 | 0.0174 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125585 | RESERVE BOILER - P&ID OF BOILER STEAM SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for BOILER STEAM SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | boiler¦reserve_boiler¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7484 | 0.9245 | 0.6472 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦steam |  | reserve_boiler¦steam | query | steam | match | false | 1 | 1 | 34.5041 | 0.7434 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦steam | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125586 | RESERVE BOILER - P&ID OF COMBUSTION AIR & FLUE GAS SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | COMBUSTION AIR & FLUE GAS SYSTEM ¦ COMBUSTION Air and Flue Gas System |  |  | P&ID ¦ Piping and Instrumentation Diagram for COMBUSTION AIR & FLUE GAS SYSTEM ¦ COMBUSTION Air and Flue Gas System |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | air¦combustion¦flue¦gas¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7134 | 0.9140 | 0.6398 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 51 | 13 | 41.4556 | 0.5906 | 0.0227 | 0.0136 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125587 | RESERVE BOILER - P&ID OF BURNER & FUEL GAS SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | FUEL GAS SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for FUEL GAS SYSTEM | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fgp¦fuel¦gas¦reserve_boiler | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.7812 | 0.7594 | 0.7594 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp¦reserve_boiler | fgp | fgp¦reserve_boiler | query | fgp | match | false | 1 | 2 | 40.0552 | 0.6942 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp¦reserve_boiler | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125588 | RESERVE BOILER - P&ID OF BLOWDOWN SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for BLOWDOWN SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | blowdown¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7167 | 0.9150 | 0.6405 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 3 | 15 | 29.5500 | 0.5660 | 0.0292 | 0.0175 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125589 | RESERVE BOILER - P&ID OF SAMPLING SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | SAMPLING SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for SAMPLING SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | reserve_boiler¦sampling |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7411 | 0.9223 | 0.6456 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | reserve_boiler¦sampling |  | reserve_boiler¦sampling | query | sampling | match | false | 1 | 1 | 45.3567 | 0.6987 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦sampling | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125590 | RESERVE BOILER - P&ID OF CHEMICAL DOSING SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for CHEMICAL DOSING SYSTEM | Chemical Dosing System | P&ID | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | p_id | p_id | chemical¦dosing¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8903 | 0.9671 | 0.9671 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦wts | wts | reserve_boiler¦wts | query | wts | match | false | 1 | 1 | 59.7216 | 0.7258 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125591 | RESERVE BOILER - P&ID OF CLOSED COOLING WATER & SERVICE WATER SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for CLOSED COOLING WATER & SERVICE WATER SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | closed¦cooling¦reserve_boiler¦service¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6834 | 0.9050 | 0.6335 | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | ccw¦reserve_boiler¦service_water |  | ccw¦reserve_boiler¦service_water | query | service_water | match | false | 1 | 1 | 58.9967 | 0.6698 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | ccw¦reserve_boiler¦service_water | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125592 | RESERVE BOILER - P&ID OF INSTRUMENT AIR SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | INSTRUMENT AIR SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for INSTRUMENT AIR SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | air¦instrument¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7665 | 0.9299 | 0.6510 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler |  | compressed_air¦reserve_boiler | query | compressed_air | match | false | 1 | 4 | 36.4307 | 0.6665 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air¦reserve_boiler | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125593 | RESERVE BOILER - P&ID OF SERVICE AIR & SEALING AIR SYSTEM | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for SERVICE AIR & SEALING AIR SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | air¦reserve_boiler¦sealing¦service |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7142 | 0.9142 | 0.6400 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler |  | compressed_air¦reserve_boiler | query | compressed_air | match | false | 2 | 5 | 44.2161 | 0.6403 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | compressed_air¦reserve_boiler | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR01-P8ZEN-125597 | METHODS STATEMENTS OF STEAM FLUSHING FOR RESERVE BOILER |  | RESERVE BOILER |  |  |  | for RESERVE BOILER | [5 empty] | rule_query | other | diagram | methods_statements_of_steam_flushing_for_reserve_boiler | p_id | boiler¦reserve¦reserve_boiler | pump | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.2500 | 0.5144 | 0.3293 | 0.3293 |  | 2CF1615W62A19 | (HRSG #21) Diverter Damper Control Unit Flushing | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2008-07-08 | 2008-07-24 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 11 | 1 | 8.6797 | 0.5553 | 0.0305 | 0.0057 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125601 | RESERVE BOILER - F.D FAN DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER | Cooling ToWer | COOLING TOWER _FAN STACK DRAWING | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5775 | 0.4533 | 0.4533 | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | 577 | 143 | 2.1949 | 0.5299 | 0.0065 | 0.0012 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125602 | RESERVE BOILER - BURNER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Burner Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5555 | 0.8666 | 0.6067 | FA | 3EF1625W00A02.1 | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | 2007-08-01 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3928 | 2 |  | 0.5335 | 0.0164 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125604 | RESERVE BOILER - BFP DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | 990 | 4 |  | 0.5325 | 0.0166 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125605 | RESERVE BOILER - DEAERATOR WITH STORAGE TANK DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Tank DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler¦tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.5124 | 0.6204 | 0.4343 | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | wts | mismatch | false | 9 | 15 | 16.4358 | 0.5122 | 0.0278 | 0.0052 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125606 | RESERVE BOILER - SILENCER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Silencer Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6205 | 0.8862 | 0.6203 | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3826 | 46 |  | 0.5189 | 0.0097 | 0.0018 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125607 | RESERVE BOILER - SAMPLING SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | SAMPLING SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Sampling System Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6786 | 0.9036 | 0.6325 | FA | 1EF3040W16A02 | (Sampling Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2008-01-01 | 2008-04-02 | design_drawing | civil_design | compatible | reserve_boiler¦sampling | sampling | reserve_boiler¦sampling | query | sampling | match | false | 1 | 3 | 18.5328 | 0.4693 | 0.0323 | 0.0242 | hybrid | structured_preferred | reserve_boiler¦sampling | system_design¦civil_design | 7 | 2024-08-19 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-11-02 | 2024-12-02 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125608 | RESERVE BOILER - CHEMICAL DOSING SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER | Chemical Dosing System | Piping Arrangement DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7101 | 0.6797 | 0.6797 | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler¦wts | wts | reserve_boiler¦wts | query | wts | match | false | 4 | 4 | 33.6657 | 0.6539 | 0.0312 | 0.0234 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦wts | system_design¦civil_design |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125609 | RESERVE BOILER - MONORAIL HOIST DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Monorail Hoist Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7286 | 0.9186 | 0.6430 | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler | crane_hoist | reserve_boiler | query | hrsg | mismatch | false | 3814 | 1 |  | 0.5184 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125610 | RESERVE BOILER - SRV DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3792 | 1 |  | 0.5456 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125611 | RESERVE BOILER - BLOWDOWN TANK DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | HRSG - Spec. & DraWing for BloWDoWn Tank Pump | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler¦tank | hrsg¦pump¦tank | scoped | match | match | match | passed |  | 0.4286 | 0.7259 | 0.5178 | 0.5178 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler | hrsg | reserve_boiler | query | hrsg | mismatch | false | 634 | 143 | 2.0974 | 0.5212 | 0.0064 | 0.0012 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125612 | RESERVE BOILER - LEVEL GAUGE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | LEVEL REINFORCEMENT DRAWING BASEMAT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4512 | 0.4853 | 0.3397 | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3849 | 1 |  | 0.5304 | 0.0166 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125614 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR F.D FAN |  | RESERVE BOILER |  |  |  | for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5337 | 0.6268 | 0.6268 | SKIP | 3EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | 686 | 1 | 4.4703 | 0.6011 | 0.0177 | 0.0044 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125615 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BOILER FEED WATER PUMP |  | RESERVE BOILER |  |  |  | for RESERVE BOILER | Boiler Feed Pump | Aux. piping arrangement draWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | boiler¦pump¦reserve¦reserve_boiler | pump | scoped | match | match | match | passed |  | 0.1429 | 0.5095 | 0.2528 | 0.2528 | FI | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | civil_design | civil_design | match | reserve_boiler | feedwater | reserve_boiler | query |  | activity_unscoped | true | 68 | 20 | 12.2665 | 0.5619 | 0.0203 | 0.0122 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125616 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR FUEL SKID | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5383 | 0.6282 | 0.6282 | SKIP | 0EF3520W00A10.3 | (FO FWD Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | 196 | 4 | 7.6594 | 0.5848 | 0.0195 | 0.0049 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125617 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR SAMPLING SYSTEM | DRAWING | RESERVE BOILER | SAMPLING SYSTEM |  |  | DRAWING for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5295 | 0.6255 | 0.6255 | SKIP | 1EF3040W16A02 | (Sampling Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2008-01-01 | 2008-04-02 | civil_design | civil_design | match | reserve_boiler¦sampling |  | reserve_boiler¦sampling | query | sampling | match | false | 1 | 3 | 20.7130 | 0.5173 | 0.0323 | 0.0323 | hybrid | structured_preferred | reserve_boiler¦sampling | civil_design | 6 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125618 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR CHEMICAL DOSING SYSTEM | DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DRAWING for RESERVE BOILER | Chemical Dosing System | Piping Arrangement DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7111 | 0.6800 | 0.6800 | FI | 2EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | 2007-09-26 |  | civil_design | civil_design | match | reserve_boiler¦wts | wts | reserve_boiler¦wts | query | wts | match | false | 5 | 1 | 35.3086 | 0.6594 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦wts | civil_design |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125619 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BLOW DOWN TANK | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | HRSG - FounDation LoaDing & Location DraWing for BloWDoWn Tank | 1 | start+103D<=FA<=start+103D+2M | FA ∈ [start+103d, start+163d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler¦tank | hrsg¦tank | scoped | match | match | match | passed |  | 0.6250 | 0.7972 | 0.6767 | 0.6767 | FA | 3EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | reserve_boiler | hrsg | reserve_boiler | query | feedwater | mismatch | false | 714 | 1 | 4.4703 | 0.5779 | 0.0177 | 0.0044 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125620 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR ELECTRICAL & CONTROL ROOM | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦ccr¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5851 | 0.6422 | 0.6422 | SKIP | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 123 | 31 | 8.9442 | 0.5552 | 0.0165 | 0.0099 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8SGK-125650 | RESERVE BOILER_ FM GAS SYSTEM CALCULATION & DOCUMENT | CALCULATION & DOCUMENT | RESERVE BOILER | FM GAS SYSTEM |  |  | CALCULATION & DOCUMENT for RESERVE BOILER |  | Gas HTR Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5486 | 0.5146 | 0.5146 | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | fgp¦gtg | mismatch | false | 63 | 8 | 4.1061 | 0.5687 | 0.0228 | 0.0057 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P8ZEN-125700 | RESERVE BOILER - OPERATION PHILOSOPHY | PHILOSOPHY | RESERVE BOILER |  |  |  | PHILOSOPHY for RESERVE BOILER | [5 empty] | rule_query | other | other | philosophy | gt_design_philosophy_for_emergency_air_system | boiler¦reserve¦reserve_boiler | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.2857 | 0.4734 | 0.3420 | 0.3420 |  | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 1 | 9 | 25.1097 | 0.4704 | 0.0309 | 0.0139 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P8ZEN-125701 | RESERVE BOILER - CONTROL SYSTEM CONFIGURATION |  | RESERVE BOILER | CONTROL SYSTEM |  |  | for RESERVE BOILER | [5 empty] | rule_query | other | diagram | reserve_boiler_control_system_configuration | p_id | boiler¦reserve¦reserve_boiler | pump | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.2500 | 0.5144 | 0.3293 | 0.3293 |  | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | 662 | 5 | 1.1861 | 0.5397 | 0.0168 | 0.0042 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125702 | RESERVE BOILER - BMS SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | 1 | 10 | 16.3955 | 0.4832 | 0.0307 | 0.0077 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125703 | RESERVE BOILER - BMS I/O LIST | I/O LIST ¦ Input / Output LIST | RESERVE BOILER |  |  |  | I/O List for RESERVE BOILER | [5 empty] | rule_query | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | match | match | mismatch | rejected | scope_mismatch | 0.5000 | 0.6729 | 0.5519 | 0.5519 |  | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 11 | 6 | 9.2496 | 0.4989 | 0.0292 | 0.0073 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125704 | RESERVE BOILER - BCS I/O LIST | I/O LIST ¦ Input / Output LIST | RESERVE BOILER |  |  |  | I/O List for RESERVE BOILER | [5 empty] | rule_query | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | match | match | mismatch | rejected | scope_mismatch | 0.5000 | 0.6729 | 0.5519 | 0.5519 |  | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 11 | 7 | 9.2496 | 0.4947 | 0.0290 | 0.0073 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125705 | RESERVE BOILER - VMS I/O LIST | I/O LIST ¦ Input / Output LIST | RESERVE BOILER | VMS ¦ Vibration Monitoring System |  |  | I/O List for RESERVE BOILER | [5 empty] | rule_query | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | match | match | mismatch | rejected | scope_mismatch | 0.5000 | 0.6729 | 0.5519 | 0.5519 |  | 3PF1260W86A02.1P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-07-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | gtg | mismatch | false | 8 | 2 | 33.6224 | 0.5782 | 0.0308 | 0.0077 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125706 | RESERVE BOILER - DATALINK I/O LIST | I/O LIST ¦ Input / Output LIST | RESERVE BOILER |  |  |  | I/O List for RESERVE BOILER | Air Compressor | Datalink interface IO List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6409 | 0.4256 | 0.4256 | FI | 3PF1655W86A11P | (HRSG #31 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | 2007-10-02 | 2008-10-03 | procurement | procurement | match | reserve_boiler | compressed_air | reserve_boiler | query | hrsg | mismatch | false | 6 | 6 | 16.6734 | 0.5365 | 0.0303 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P8ZEN-125707 | RESERVE BOILER - INSTRUMENT LIST | LIST | RESERVE BOILER |  |  |  | Instrument List for RESERVE BOILER | FireFighting | Instrument List | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | list | list | instrument_list | instrument_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6778 | 0.6700 | 0.6700 | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 5 | 45 | 15.9566 | 0.5591 | 0.0249 | 0.0149 | hybrid | structured_system_absent | reserve_boiler | procurement |  | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P8ZEN-125708 | RESERVE BOILER - ALARM AND TRIP SETTING LIST | LIST | RESERVE BOILER |  |  |  | LIST for RESERVE BOILER | [5 empty] | rule_query | other | list | list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.5000 | 0.5269 | 0.5081 | 0.5081 |  | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 2 | 5 | 22.6729 | 0.4745 | 0.0315 | 0.0059 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125709 | RESERVE BOILER - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | RESERVE BOILER |  |  |  | Control Logic Diagram for RESERVE BOILER | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6985 | 0.7345 | 0.7345 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 8 | 301 | 14.8839 | 0.4823 | 0.0175 | 0.0105 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125710 | RESERVE BOILER - CONTROL LOOP DIAGRAM | CONTROL LOOP DIAGRAM | RESERVE BOILER |  |  |  | Control Loop Diagram for RESERVE BOILER | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7519 | 0.7506 | 0.7506 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 15 | 228 | 14.8839 | 0.5010 | 0.0168 | 0.0101 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125711 | RESERVE BOILER - BMS LOGIC DIAGRAM | LOGIC DIAGRAM | RESERVE BOILER |  |  |  | LOGIC DIAGRAM for RESERVE BOILER |  | Logic & Loop Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6023 | 0.6474 | 0.6474 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 4 | 305 | 14.8839 | 0.4848 | 0.0184 | 0.0110 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125713 | RESERVE BOILER - MOV DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3814 | 5 |  | 0.5033 | 0.0156 | 0.0029 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125714 | RESERVE BOILER - TRANSMITTER SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | FA | 0EF7000W86A01 | (Control Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves |  | 2007-06-28 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 8 | 131 | 7.8774 | 0.4503 | 0.0199 | 0.0120 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125715 | RESERVE BOILER - LOCAL GAUGE SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | FA | 1EF1600W74A05.1 | (HRSG #12 LEB) MPS Issue - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB |  | 2007-06-15 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3 | 52 | 10.7369 | 0.4552 | 0.0248 | 0.0062 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125716 | RESERVE BOILER - TEMP. ELEMENT SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | FA | 1EF3030W42A01 | (Temp. Cooling Tower) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower |  | 2007-10-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | ccw | mismatch | false | 2 | 1 | 13.9920 | 0.4746 | 0.0325 | 0.0081 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125717 | RESERVE BOILER - FLOW ELEMENT SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER | FloW element | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6483 | 0.4945 | 0.4945 | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 9 | 2 | 10.1928 | 0.5666 | 0.0306 | 0.0077 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125718 | RESERVE BOILER - REMOTE DRUM LEVEL INDICATOR SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | FA | 1EF1645W42A02 | (HRSG #11 Drum) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | 2007-05-15 |  | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 2 | 8 | 16.0544 | 0.4435 | 0.0308 | 0.0077 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125719 | RESERVE BOILER - AIR OPERATED VALVE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER | Air Compressor | Instrument Installation DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5791 | 0.4537 | 0.4537 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | 88 | 517 | 8.0946 | 0.4666 | 0.0085 | 0.0038 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P8ZEN-125720 | RESERVE BOILER - INSTRUMENT INSTALLATION DETAIL DRAWING | DRAWING | RESERVE BOILER | INSTRUMENT INSTALLATION MATERIAL |  |  | DRAWING for INSTRUMENT INSTALLATION MATERIAL | FinFan Cooler | Instrument Installation Detail DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | detail_drawing | detail_drawing | installation¦instrument¦material¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6540 | 0.6629 | 0.6629 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 488 | 329 | 5.3193 | 0.5040 | 0.0044 | 0.0020 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YM03-P8ZEN-125721 | RESERVE BOILER - INSTRUMENT LOCATION DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6060 | 0.6485 | 0.6485 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 520 | 21 | 2.0974 | 0.5547 | 0.0141 | 0.0026 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125722 | RESERVE BOILER - TRANSMITTER CALIBRATION SHEET | SHEET | RESERVE BOILER |  |  |  | SHEET for RESERVE BOILER | [5 empty] | rule_query | other | calculation | sheet | calculation | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.3333 | 0.5893 | 0.4101 | 0.4101 |  | 1SF3520W62A14 | (FGSS #12) Metering System Calibration with supplier | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2008-09-24 | 2008-09-28 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | electrical¦fgp | mismatch | false | 2 | 6 | 9.0842 | 0.5144 | 0.0313 | 0.0059 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125723 | RESERVE BOILER - FLOW ELEMENT CALIBRATION SHEET | SHEET | RESERVE BOILER |  |  |  | SHEET for RESERVE BOILER | [5 empty] | rule_query | other | calculation | sheet | calculation | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.3333 | 0.5893 | 0.4101 | 0.4101 |  | 0EF1000W00A01 | Heat Balance Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-07-02 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 27 | 77 |  | 0.4564 | 0.0188 | 0.0085 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125724 | RESERVE BOILER - MONITOR SCREEN DIAGRAM | MONITOR SCREEN DIAGRAM | RESERVE BOILER |  |  |  | MONITOR SCREEN DIAGRAM for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5545 | 0.3997 | 0.2798 | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query |  | activity_unscoped | true | 15 | 42 | 9.8679 | 0.4558 | 0.0231 | 0.0104 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125725 | RESERVE BOILER - GAS LEAK DETECTION SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | GAS LEAK DETECTION SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | 46 | 8 | 4.1389 | 0.5458 | 0.0241 | 0.0045 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125726 | RESERVE BOILER - O2 ANALYZER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 3792 | 1 |  | 0.5345 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125727 | RESERVE BOILER - CEMS DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | CEMS ¦ Continuous Emissions Monitoring System |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | HRSG - SPEC. & DraWing for CEMS | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | drawing | drawing | drawing | drawing | boiler¦cems¦reserve¦reserve_boiler | cems¦hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7203 | 0.4961 | 0.4961 | FA | 1EF1660W16A01 | (CEMS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | 2007-10-30 | 2008-01-25 | design_drawing | civil_design | compatible | cems¦reserve_boiler | cems¦hrsg | cems¦reserve_boiler | query | cems¦hrsg | match | false | 1 | 4 | 32.8548 | 0.6266 | 0.0320 | 0.0240 | hybrid | structured_preferred | cems¦reserve_boiler | system_design¦civil_design | 10 | 2025-07-12 | 2025-08-11 | 2025-09-10 | 2025-09-25 | 2025-10-10 | 2025-10-25 | generated | 0.90 | 0.57 | usable | default_fc_window;rule_score_medium;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125728 | RESERVE BOILER - CONTROL ROOM & ELECTRICAL ROOM ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦ccr¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 1345 | 5 | 2.0974 | 0.5699 | 0.0161 | 0.0040 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XF00-P8ZEN-125729 | RESERVE BOILER - JUNCTION BOX DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Motor Terminal box draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6025 | 0.5308 | 0.5308 | FA | 1EF3020W16A09 | (COND Flash Box) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-01-02 | 2008-03-31 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | condensate | mismatch | false | 36 | 609 | 8.1584 | 0.4536 | 0.0119 | 0.0022 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P8ZEN-125731 | RESERVE BOILER - I&C CABLE SCHEDULE | SCHEDULE | RESERVE BOILER |  |  |  | Schedule for RESERVE BOILER | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6143 | 0.6510 | 0.6510 | SKIP | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-10-02 | 2008-08-04 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 7 | 1 | 12.4890 | 0.5881 | 0.0313 | 0.0078 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P8ZEN-125732 | RESERVE BOILER - I&C CABLE CONNECTION DIAGRAM | DIAGRAM | RESERVE BOILER |  |  |  | Diagram for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5980 | 0.4127 | 0.2889 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query |  | activity_unscoped | true | 12 | 80 | 10.1910 | 0.4703 | 0.0210 | 0.0095 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125734 | RESERVE BOILER - BCS SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | 1 | 11 | 16.3955 | 0.4605 | 0.0305 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125735 | RESERVE BOILER - HAZARDOUS AREA CLASSFICATION | CLASSFICATION | RESERVE BOILER |  |  |  | CLASSFICATION for RESERVE BOILER | [5 empty] | rule_query | other | drawing | classfication | drawing | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.2500 | 0.5243 | 0.3323 | 0.3323 |  | 0EF1600W14A10 | HRSG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-06-15 |  | civil_design | query_unknown | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 4 | 293 | 7.2263 | 0.4085 | 0.0185 | 0.0035 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125737 | RESERVE BOILER _ VMS SPECIFICATION | SPECIFICATION | RESERVE BOILER | VMS ¦ Vibration Monitoring System |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | FA | 1EF1260W86A01.1 | (VMS) MPS Issue for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) |  | 2007-05-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | gtg | mismatch | false | 2 | 4 | 35.7476 | 0.6053 | 0.0318 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125749 | RESERVE BOILER - MOTOR LIST | LIST | RESERVE BOILER |  |  |  | LIST for RESERVE BOILER | [5 empty] | rule_query | other | list | list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.5000 | 0.5269 | 0.5081 | 0.5081 |  | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 2 | 4 | 22.6729 | 0.4813 | 0.0318 | 0.0060 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125750 | RESERVE BOILER - POWER DISTRIBUTION PANEL DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | POWER SUPPLY DISTRIBUTION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7332 | 0.7450 | 0.5215 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 2011 | 1 | 0.0002 | 0.5658 | 0.0169 | 0.0032 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P8ZEN-125751 | RESERVE BOILER - RACEWAY PLAN DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6005 | 0.8802 | 0.8802 | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 9 | 3155 | 12.0304 | 0.3415 | 0.0148 | 0.0067 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P8ZEN-125752 | RESERVE BOILER - RACEWAY DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5448 | 0.6301 | 0.6301 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | 504 | 138 | 2.0974 | 0.5113 | 0.0068 | 0.0013 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125754 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR MCC | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5533 | 0.6327 | 0.4429 | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 11 | 1 | 10.4900 | 0.5037 | 0.0305 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P8ZEN-125755 | RESERVE BOILER - MCC SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | RESERVE BOILER |  |  |  | Single Line Diagram for RESERVE BOILER |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7137 | 0.9141 | 0.9141 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 11 | 177 | 14.8839 | 0.4972 | 0.0183 | 0.0110 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P8ZEN-125756 | RESERVE BOILER - MCC SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM | RESERVE BOILER |  |  |  | SCHEMATIC DIAGRAM for RESERVE BOILER |  | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6055 | 0.6483 | 0.6483 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 4 | 89 | 14.8839 | 0.5205 | 0.0223 | 0.0101 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125757 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLE | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5819 | 0.6412 | 0.4489 | FA | 1EF6040W74A05 | (EHV Cable) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable |  | 2007-05-01 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | electrical | mismatch | false | 2 | 5 | 15.0390 | 0.4462 | 0.0315 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125758 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5742 | 0.6389 | 0.4472 | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | 10 | 2 | 10.4900 | 0.4768 | 0.0304 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125759 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR FIRE STOP MATERIALS | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5338 | 0.6268 | 0.4388 | FA | 0EF4500W38A02 | (Fire Fighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | fire_fighting¦hvac | mismatch | false | 4 | 3 | 13.8924 | 0.4713 | 0.0315 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P8ZEN-125760 | RESERVE BOILER - POWER CABLE SCHEDULE | SCHEDULE | RESERVE BOILER |  |  |  | Schedule for RESERVE BOILER | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6270 | 0.6548 | 0.6548 | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | electrical | mismatch | false | 5 | 18 | 15.3884 | 0.5399 | 0.0282 | 0.0071 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P8ZEN-125761 | RESERVE BOILER - POWER CABLE CONNECTION DIAGRAM | DIAGRAM | RESERVE BOILER |  |  |  | Diagram for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5980 | 0.4127 | 0.2889 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query | steam | mismatch | false | 14 | 10 | 10.0271 | 0.4742 | 0.0278 | 0.0052 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P8ZEN-125762 | RESERVE BOILER - EMBEDDED CONDUIT LAYOUT DRAWING | LAYOUT DRAWING | RESERVE BOILER |  |  |  | Layout Drawing for RESERVE BOILER |  | EMBEDDED CONDUIT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7644 | 0.9293 | 0.6505 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 2 | 1803 | 24.0608 | 0.3676 | 0.0167 | 0.0100 | hybrid | structured_system_absent | reserve_boiler | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125763 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR LIGHTING SYSTEM | TECHNICAL SPECIFICATION | RESERVE BOILER | LIGHTING SYSTEM |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5738 | 0.6388 | 0.4472 | FA | 0EF6040W70A01 | (Lighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System |  | 2007-05-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | electrical | mismatch | false | 1 | 1 | 35.8808 | 0.5113 | 0.0328 | 0.0082 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125764 | RESERVE BOILER - ILLUMINATION CALCULATION | CALCULATION | RESERVE BOILER |  |  |  | Calculation sheet for RESERVE BOILER | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5375 | 0.5112 | 0.5112 | FA | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 678 | 96 |  | 0.4533 | 0.0078 | 0.0047 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P8ZEN-125765 | RESERVE BOILER - LIGHTING LAYOUT DRAWING | LAYOUT DRAWING | RESERVE BOILER | LIGHTING |  |  | Layout Drawing for LIGHTING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7105 | 0.7382 | 0.7382 | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 6 | 2220 | 24.0608 | 0.3695 | 0.0156 | 0.0070 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125766 | RESERVE BOILER - AIRCRAFT WARNING LIGHT DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Aircraft Warning Light DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7190 | 0.9157 | 0.6410 | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | compressed_air | mismatch | false | 411 | 1 |  | 0.4850 | 0.0185 | 0.0035 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P8ZEN-125767 | RESERVE BOILER - EARTHING DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | EARTHING |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Earthing Concept – DraWing Document | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6049 | 0.7065 | 0.4945 | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | design_drawing | civil_design | compatible | electrical¦reserve_boiler | electrical | electrical¦reserve_boiler | query | electrical | discipline_only | false | 29 | 1 |  | 0.5117 | 0.0276 | 0.0104 | hybrid | structured_preferred | electrical¦reserve_boiler | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 0.26 | needs_review | rule_score_medium;activity_phase_status=compatible;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE01-P8ZEN-125768 | RESERVE BOILER - LIGHTNING PROTECTION DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | LIGHTNING PROTECTION |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Lightning Protection Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7393 | 0.9218 | 0.6452 | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical¦reserve_boiler | electrical | electrical¦reserve_boiler | query | electrical | discipline_only | false | 1 | 21 |  | 0.4464 | 0.0287 | 0.0108 | hybrid | structured_preferred | electrical¦reserve_boiler | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.30 | needs_review | activity_phase_status=compatible;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P8ZEN-125769 | RESERVE BOILER - COMMUNICATION SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | COMMUNICATION SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Communication System Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6501 | 0.8950 | 0.6265 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 6 | 240 | 1.3610 | 0.4533 | 0.0185 | 0.0083 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.33 | needs_review | activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126001 | HRSG FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7425 | 0.9227 | 0.9227 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 2 | 1 | 30.7117 | 0.6464 | 0.0325 | 0.0325 | hybrid | structured_preferred | feedwater¦hrsg | system_design | 7 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAC-126003 | HRSG FEEDWATER PUMP - P&I DIAGRAM | P&I DIAGRAM | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | P&ID for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8182 | 0.9455 | 0.9455 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 1 | 7 | 30.8870 | 0.6896 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | feedwater¦hrsg | system_design¦procurement |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126004 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | DATA SHEET AND CHARACTERISTIC CURVE | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7393 | 0.9218 | 0.9218 | FA | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | 2007-07-03 | 2008-05-02 | procurement | procurement | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | false | 29 | 13 | 23.1098 | 0.5803 | 0.0249 | 0.0249 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126005 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | DATA SHEET AND CHARACTERISTIC CURVE | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7393 | 0.9218 | 0.9218 | FA | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | 2007-07-03 | 2008-05-02 | procurement | procurement | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | false | 29 | 12 | 23.1098 | 0.5630 | 0.0251 | 0.0251 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LAC-126006 | HRSG FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | SECTIONAL DRAWING | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | SECTIONAL DRAWING for HRSG |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦heat¦hrsg¦pump¦recovery¦steam | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6399 | 0.6586 | 0.6586 | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | false | 9 | 4 | 16.0954 | 0.5795 | 0.0301 | 0.0301 | hybrid | structured_preferred | feedwater¦hrsg | civil_design | 10 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126007 | HRSG FEEDWATER PUMP - NAME PLATE DRAWING | DRAWING | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DRAWING for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7031 | 0.5609 | 0.5609 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 1 | 3 | 17.4274 | 0.6197 | 0.0323 | 0.0242 | hybrid | structured_preferred | feedwater¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126009 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | OUTLINE DRAWING AND DATA SHEET | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Elevator Data Sheet anD DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.6826 | 0.7881 | 0.7881 | FA | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-14 | 2008-04-02 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 28 | 7 | 23.1098 | 0.6020 | 0.0263 | 0.0263 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126010 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | OUTLINE DRAWING AND DATA SHEET | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Elevator Data Sheet anD DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.6826 | 0.7881 | 0.7881 | FA | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | 2007-07-03 | 2008-05-02 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 29 | 14 | 23.1098 | 0.5830 | 0.0247 | 0.0247 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-04-16 | 2025-05-16 | 2025-06-15 | 2025-06-30 | 2025-07-15 | 2025-07-30 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LAC-126011 | HRSG FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | LIST AND DATA SHEET | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | Instrument List for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Instrument List | 1 | start+133D<=FA<=start+133D+2M | FA ∈ [start+133d, start+193d] | rule_query | list | list | instrument_list | instrument_list | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7196 | 0.9159 | 0.9159 | FA | 1PF1660W86A07.1P | (HRSG #12 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | 2007-10-02 | 2008-08-04 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 10 | 20 | 26.2336 | 0.6065 | 0.0268 | 0.0268 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-02-12 | 2025-03-14 | 2025-04-13 | 2025-04-28 | 2025-05-13 | 2025-05-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-DM01-P0LAC-126012 | HRSG FEEDWATER PUMP - INSTALLATION MANUAL | INSTALLATION MANUAL | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | INSTALLATION MANUAL for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5803 | 0.6408 | 0.6408 | FI | 3PF1615W64A11T | (HRSG #31(HRSG #11 Damper) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2008-05-02 | 2008-06-16 | manual | delivery | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | false | 10 | 24 | 19.9835 | 0.5893 | 0.0262 | 0.0262 | hybrid | structured_preferred | feedwater¦hrsg | delivery¦procurement¦installation | 10 | 2025-01-24 | 2025-02-23 | 2025-03-25 | 2025-04-09 | 2025-04-24 | 2025-05-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126016 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | OUTLINE DRAWING AND DATA SHEET | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Elevator Data Sheet anD DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.6826 | 0.7881 | 0.7881 | FA | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | 2007-07-03 | 2008-05-02 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 29 | 14 | 23.1098 | 0.5870 | 0.0247 | 0.0247 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-04-16 | 2025-05-16 | 2025-06-15 | 2025-06-30 | 2025-07-15 | 2025-07-30 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126019 | HRSG FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DRAWING for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7031 | 0.5609 | 0.5609 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 1 | 1 | 17.4274 | 0.6190 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LAC-126027 | HRSG FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | DATA SHEET & DRAWING | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DATA SHEET & DRAWING for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.6750 | 0.7275 | 0.7275 | FA | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-13 | 2008-02-29 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 7 | 20 | 23.1098 | 0.5805 | 0.0274 | 0.0274 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-03-03 | 2025-04-02 | 2025-05-02 | 2025-05-17 | 2025-06-01 | 2025-06-16 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126051 | FGP FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | feedwater¦fgp¦fuel¦gas¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6537 | 0.8961 | 0.8961 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | false | 1 | 2 | 6.9833 | 0.6375 | 0.0325 | 0.0325 | hybrid | structured_preferred | feedwater¦fgp | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAC-126053 | FGP FEEDWATER PUMP - P&I DIAGRAM | P&I DIAGRAM | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | P&ID for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.7533 | 0.7510 | 0.7510 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | feedwater¦fgp | fgp | feedwater¦fgp | query | fgp | match | false | 26 | 5 | 21.2897 | 0.7227 | 0.0270 | 0.0270 | hybrid | structured_blocked_procurement_conflict | feedwater¦fgp | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126054 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | DATA SHEET AND CHARACTERISTIC CURVE | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7408 | 0.9222 | 0.9222 | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | false | 8 | 5 | 20.3301 | 0.6730 | 0.0301 | 0.0301 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126055 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | DATA SHEET AND CHARACTERISTIC CURVE | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7408 | 0.9222 | 0.9222 | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | false | 9 | 1 | 16.6251 | 0.6762 | 0.0309 | 0.0309 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LAC-126056 | FGP FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | SECTIONAL DRAWING | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | SECTIONAL DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8877 | 0.9663 | 0.9663 | FA | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | civil_design | civil_design | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | false | 15 | 3 | 11.4002 | 0.6602 | 0.0292 | 0.0292 | hybrid | structured_preferred | feedwater¦fgp | civil_design | 10 | 2024-12-26 | 2025-01-25 | 2025-02-24 | 2025-03-11 | 2025-03-26 | 2025-04-10 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126057 | FGP FEEDWATER PUMP - NAME PLATE DRAWING | DRAWING | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | DRAWING for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6715 | 0.5514 | 0.5514 | FA | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | design_drawing | civil_design | compatible | feedwater¦fgp | fgp | feedwater¦fgp | query | feedwater | match | false | 15 | 3 | 8.5502 | 0.6609 | 0.0292 | 0.0219 | hybrid | structured_preferred | feedwater¦fgp | system_design¦civil_design | 10 | 2025-02-20 | 2025-04-17 | 2025-06-12 | 2025-05-08 | 2025-07-03 | 2025-08-28 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126059 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | OUTLINE DRAWING AND DATA SHEET | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6224 | 0.7117 | 0.7117 | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | false | 7 | 4 | 17.5690 | 0.6543 | 0.0306 | 0.0306 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-07-09 | 2024-08-13 | 2024-09-17 | 2024-09-03 | 2024-10-08 | 2024-11-12 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126060 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | OUTLINE DRAWING AND DATA SHEET | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6224 | 0.7117 | 0.7117 | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | false | 7 | 5 | 17.5690 | 0.6576 | 0.0303 | 0.0303 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-07-09 | 2024-08-13 | 2024-09-17 | 2024-09-03 | 2024-10-08 | 2024-11-12 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LAC-126061 | FGP FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | LIST AND DATA SHEET | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | Instrument List for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Instrument List | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | list | list | instrument_list | instrument_list | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.7226 | 0.7768 | 0.7768 | FI | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | feedwater¦fgp | fgp | feedwater¦fgp | query | feedwater | match | false | 7 | 5 | 17.5690 | 0.6867 | 0.0303 | 0.0303 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-06-25 | 2024-08-06 | 2024-09-17 | 2024-08-27 | 2024-10-08 | 2024-11-19 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-DM01-P0LAC-126062 | FGP FEEDWATER PUMP - INSTALLATION MANUAL | INSTALLATION MANUAL | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | INSTALLATION MANUAL for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Fuel Gas Compressor | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7155 | 0.6813 | 0.6813 | FI | 1PF3015W42A07T | (FWP) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2008-08-30 | 2008-10-14 | manual | delivery | match | feedwater¦fgp | fgp | feedwater¦fgp | query | feedwater | match | false | 28 | 4 | 12.0833 | 0.6573 | 0.0270 | 0.0270 | hybrid | structured_preferred | feedwater¦fgp | delivery¦procurement¦installation | 10 | 2025-05-24 | 2025-06-23 | 2025-07-23 | 2025-08-07 | 2025-08-22 | 2025-09-06 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126066 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | OUTLINE DRAWING AND DATA SHEET | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6224 | 0.7117 | 0.7117 | FA | 0EF3520W00A01.2 | (FOSS) FO Forwarding Pump, FO Unloading Pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-04-02 | 2007-04-30 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | false | 1 | 17 | 31.4257 | 0.6265 | 0.0294 | 0.0294 | hybrid | structured_cell_found_text_preferred | feedwater¦fgp | procurement |  | 2024-07-09 | 2024-08-13 | 2024-09-17 | 2024-09-03 | 2024-10-08 | 2024-11-12 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126069 | FGP FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | DRAWING for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6715 | 0.5514 | 0.5514 | FA | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | design_drawing | civil_design | compatible | feedwater¦fgp | fgp | feedwater¦fgp | query | feedwater | match | false | 15 | 3 | 8.5502 | 0.6599 | 0.0292 | 0.0219 | hybrid | structured_preferred | feedwater¦fgp | system_design¦civil_design | 10 | 2025-02-20 | 2025-04-17 | 2025-06-12 | 2025-05-08 | 2025-07-03 | 2025-08-28 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LAC-126077 | FGP FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | DATA SHEET & DRAWING | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | DATA SHEET & DRAWING for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6488 | 0.7197 | 0.7197 | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | false | 7 | 5 | 17.5690 | 0.6393 | 0.0303 | 0.0303 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-07-09 | 2024-08-13 | 2024-09-17 | 2024-09-03 | 2024-10-08 | 2024-11-12 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0LAC-126301 | HRSG FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | DRAWING | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP | I&C ¦ Instrumentation and Control |  |  | DRAWING for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7031 | 0.5609 | 0.5609 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 1 | 1 | 22.3690 | 0.6685 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0LAC-126302 | HRSG FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | WIRING DIAGRAM for HRSG FEEDWATER PUMP ¦ Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Wiring Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7616 | 0.9285 | 0.9285 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | false | 1 | 1 | 26.6382 | 0.6380 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater¦hrsg | system_design¦engineering | 7 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0LAC-126351 | FGP FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | DRAWING | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | I&C ¦ Instrumentation and Control |  |  | DRAWING for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6715 | 0.5514 | 0.5514 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | feedwater¦fgp | fgp | feedwater¦fgp | query | fgp | match | false | 15 | 5 | 12.2357 | 0.6236 | 0.0287 | 0.0215 | hybrid | structured_preferred | feedwater¦fgp | system_design¦civil_design | 10 | 2024-07-05 | 2024-08-30 | 2024-10-25 | 2024-09-20 | 2024-11-15 | 2025-01-10 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0LAC-126352 | FGP FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP |  |  |  | WIRING DIAGRAM for FGP FEEDWATER PUMP ¦ Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Interconnection Wiring Diagram | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6778 | 0.6700 | 0.6700 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | feedwater¦fgp | fgp | feedwater¦fgp | query | fgp | match | false | 1 | 1 | 16.7736 | 0.6581 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater¦fgp | system_design¦engineering | 3 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126501 | FIN FAN COOLER - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | FIN FAN COOLER |  |  |  | System Description for FIN FAN COOLER | FinFan Cooler | System Description | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9241 | 0.8022 | 0.8022 | FI | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | 110 | 51 | 8.6823 | 0.5283 | 0.0149 | 0.0089 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0PCA-126502 | FIN FAN COOLER - P&I DIAGRAM | P&I DIAGRAM | FIN FAN COOLER |  |  |  | P&ID for FIN FAN COOLER | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8616 | 0.7835 | 0.7835 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | 46 | 78 | 19.0877 | 0.5415 | 0.0167 | 0.0100 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PCA-126503 | FIN FAN COOLER - GENERAL ARRANGEMENT & PLOT PLAN DRAWING | GENERAL ARRANGEMENT & PLOT PLAN DRAWING | FIN FAN COOLER |  |  |  | GENERAL ARRANGEMENT & PLOT PLAN DRAWING for FIN FAN COOLER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cooler¦fan¦fin |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6520 | 0.8956 | 0.8956 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 3 | 1 | 35.7395 | 0.5944 | 0.0323 | 0.0323 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126504 | FIN FAN COOLER - PERFORMANCE CURVE | PERFORMANCE CURVE | FIN FAN COOLER |  |  |  | Performance Curve for FIN FAN COOLER | FinFan Cooler | Performance Curve | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | curve | curve | performance_curve | performance_curve | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9465 | 0.8089 | 0.8089 | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 2 | 1 | 42.1378 | 0.6284 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0PCA-126505 | FIN FAN COOLER - TERMINAL POINT LIST & DRAWING | LIST & DRAWING | FIN FAN COOLER |  |  |  | LIST & DRAWING for FIN FAN COOLER | FinFan Cooler | RaceWay draWing | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | drawing | drawing | drawing | drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7798 | 0.5839 | 0.5839 | FA | 3PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 3 | 1 | 42.1378 | 0.6311 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0PCA-126506 | FIN FAN COOLER - EQUIPMENT LIST | EQUIPMENT LIST | FIN FAN COOLER |  |  |  | Equipment List for FIN FAN COOLER | FinFan Cooler | Equipment List | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | list | list | equipment_list | equipment_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9493 | 0.8098 | 0.8098 | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 2 | 1 | 42.1378 | 0.6688 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0PCA-126507 | FIN FAN COOLER - VALVE LIST | VALVE LIST | FIN FAN COOLER |  |  |  | Valve List for FIN FAN COOLER |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7297 | 0.6856 | 0.6856 | FA | 3PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 3 | 1 | 42.1378 | 0.6355 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126508 | FIN FAN COOLER - BELT PULLEY DATA SHEET | DATA SHEET | FIN FAN COOLER |  |  |  | Data Sheet for FIN FAN COOLER | FinFan Cooler | Fan Data Sheet & Outline DraWing | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.8302 | 0.6491 | 0.6491 | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 2 | 1 | 42.1378 | 0.6061 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126509 | FIN FAN COOLER - FAN MOTOR DATA SHEET | DATA SHEET | FIN FAN COOLER |  |  |  | Data Sheet for FIN FAN COOLER | FireFighting | Motor Data Sheet | 1 | start+20W<=FA<=FC<=start+30W | FA ∈ [start+140d, start+210d] ¦ FC ∈ [start+140d, start+210d] | title | datasheet | datasheet | data_sheet | data_sheet | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5475 | 0.6893 | 0.6893 | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 2 | 1 | 48.2855 | 0.6022 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-11-20 | 2024-12-25 | 2025-01-29 | 2025-01-15 | 2025-02-19 | 2025-03-26 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126512 | FIN FAN COOLER - FAN OUTLINE DRAWING (WITH MOTOR) | OUTLINE DRAWING (WITH MOTOR) | FIN FAN COOLER |  |  |  | OUTLINE DRAWING (WITH MOTOR) for FIN FAN COOLER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6963 | 0.9089 | 0.9089 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 |  | 0.3921 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126513 | FIN FAN COOLER - VALVE OUTLINE DRAWING | OUTLINE DRAWING | FIN FAN COOLER |  |  |  | Outline Drawing for FIN FAN COOLER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5971 | 0.6458 | 0.6458 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 |  | 0.3858 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126514 | FIN FAN COOLER - PIPING ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | FIN FAN COOLER | PIPING |  |  | General Arrangement Drawing for FIN FAN COOLER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cooler¦fan¦fin |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7129 | 0.9139 | 0.9139 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 |  | 0.4382 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126515 | FIN FAN COOLER - PIPING ISOMETRIC DRAWRING | ISOMETRIC DRAWRING | FIN FAN COOLER | PIPING |  |  | ISOMETRIC DRAWRING for FIN FAN COOLER | H2, CO2 Supply System | Piping Isometric DraWring | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | isometric_drawing | isometric_drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6364 | 0.4909 | 0.4909 | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw | h2 | ccw | query | ccw¦gtg | match | false | 2 | 4 | 42.1378 | 0.6198 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126516 | FIN FAN COOLER - PIPE MATERIAL SPECIFICATION | MATERIAL SPECIFICATION | FIN FAN COOLER | PIPE |  |  | MATERIAL SPECIFICATION for FIN FAN COOLER | FinFan Cooler | Pipe Material Specification | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | specification | specification | specification | specification | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8616 | 0.8185 | 0.8185 | FA | 1EF1225W42A17.1 | (CCW H/EX) MPS Issue_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System |  | 2007-05-01 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 2 | 6 | 46.7736 | 0.5901 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-07-30 | 2024-08-29 | 2024-09-28 | 2024-10-13 | 2024-10-28 | 2024-11-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0PCA-126517 | FIN FAN COOLER - PIPE LINE LIST | LINE LIST | FIN FAN COOLER | PIPE |  |  | LINE LIST for FIN FAN COOLER | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6395 | 0.5419 | 0.5419 | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw | compressed_air | ccw | query | ccw¦gtg | match | false | 2 | 1 | 42.1378 | 0.6385 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0PCA-126519 | FIN FAN COOLER - CONTROL DESCRIPTION (PHILOSOPHY) | CONTROL DESCRIPTION (PHILOSOPHY) | FIN FAN COOLER |  |  |  | CONTROL DESCRIPTION (PHILOSOPHY) for FIN FAN COOLER | FinFan Cooler | Control Description (Philosophy) including Control Steps | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | description | description | control_description | control_description | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.8322 | 0.6496 | 0.6496 | FA | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 42.1378 | 0.5851 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0PCA-126522 | FIN FAN COOLER - LOGIC / FUNCTIONAL LOOP DIAGRAMS | LOGIC / FUNCTIONAL LOOP DIAGRAMS | FIN FAN COOLER |  |  |  | LOGIC / FUNCTIONAL LOOP DIAGRAMS for FIN FAN COOLER |  | FUNCTIONAL LOOP DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | functional_loop_diagram | functional_loop_diagram | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7208 | 0.6829 | 0.4780 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 |  | 0.4354 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0PCA-126523 | FIN FAN COOLER - INSTRUMENT LIST | LIST | FIN FAN COOLER | INSTRUMENT |  |  | Instrument List for FIN FAN COOLER | FinFan Cooler | Instrument list | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | list | list | instrument_list | instrument_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9365 | 0.8059 | 0.8059 | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 2 | 1 | 42.1378 | 0.6532 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126524 | FIN FAN COOLER - INSTRUMENT CATALOG | CATALOG | FIN FAN COOLER | INSTRUMENT |  |  | CATALOG for FIN FAN COOLER | [5 empty] | rule_query | other | other | catalog | instrument_catalog | cooler¦fan¦fin |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.5000 | 0.8240 | 0.5972 | 0.5972 |  | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2008-06-16 | 2008-07-30 |  | installation | query_unknown | ccw |  | ccw | query | ccw¦gtg | match | false | 4 | 7 | 36.1017 | 0.5248 | 0.0306 | 0.0229 | hybrid | structured_no_phase | ccw | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0PCA-126525 | FIN FAN COOLER - INSTRUMENT INSTALLATION DETAIL DRAWING | DRAWING | FIN FAN COOLER | INSTRUMENT INSTALLATION MATERIAL |  |  | DRAWING for INSTRUMENT INSTALLATION MATERIAL | FinFan Cooler | Instrument Installation Detail DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | detail_drawing | detail_drawing | installation¦instrument¦material |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8215 | 0.8298 | 0.8298 | FA | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 5 | 35.7395 | 0.5175 | 0.0318 | 0.0238 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126526 | FIN FAN COOLER - INSTRUMENT DATA SHEET | DATA SHEET | FIN FAN COOLER | INSTRUMENT |  |  | Data Sheet for FIN FAN COOLER | FireFighting | Instrument Data Sheet | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | title | datasheet | datasheet | data_sheet | data_sheet | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6163 | 0.7099 | 0.7099 | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | false | 2 | 1 | 42.1378 | 0.6024 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-11-20 | 2024-12-05 | 2024-12-20 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126527 | FIN FAN COOLER - DRIVE LIST (MOVS, MOTORS, CONTROL VALVES, SOLENOID VALVES, ETC..) | LIST | FIN FAN COOLER |  |  |  | LIST for FIN FAN COOLER | [5 empty] | rule_query | other | list | list | instrument_list | cooler¦fan¦fin |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.8244 | 0.5973 | 0.5973 |  | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2008-06-16 | 2008-07-30 |  | installation | query_unknown | ccw |  | ccw | query | ccw¦gtg | match | false | 4 | 7 | 36.1017 | 0.5492 | 0.0306 | 0.0229 | hybrid | structured_no_phase | ccw | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0PCA-126529 | FIN FAN COOLER - RACEWAY DRAWING | DRAWING | FIN FAN COOLER |  |  |  | DRAWING for FIN FAN COOLER | FinFan Cooler | RaceWay draWing | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | drawing | drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8134 | 0.7690 | 0.7690 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | false | 3 | 3 | 35.7395 | 0.5367 | 0.0317 | 0.0238 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PCA-126530 | JUNCTION BOX OUTLINE AND LAYOUT DRAWING | OUTLINE AND LAYOUT DRAWING | JUNCTION BOX |  |  |  | OUTLINE AND LAYOUT DRAWING for JUNCTION BOX |  | I&C junction box outline and layout draWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | box¦junction |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.8108 | 0.8432 | 0.8432 | FI | 1EF3020W16A09 | (COND Flash Box) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-01-02 | 2008-03-31 | design_drawing | civil_design | compatible |  |  |  |  | condensate | query_unscoped | false | 13 | 203 | 16.3168 | 0.3892 | 0.0175 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2025-03-27 | 2025-04-26 | 2025-05-26 | 2025-06-10 | 2025-06-25 | 2025-07-10 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0PCA-126533 | FIN FAN COOLER - WIRING DIAGRAMS FOR JUNCTION BOXES | WIRING DIAGRAMS | FIN FAN COOLER |  |  |  | WIRING DIAGRAMS for FIN FAN COOLER | FinFan Cooler | Wiring diagrams | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9332 | 0.8050 | 0.8050 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 |  | 0.3722 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126538 | FIN FAN COOLER - FOUNDATION DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING (INCLUDE AUXILIARY EQUIPMENT) | DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING | FIN FAN COOLER |  |  |  | DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING for FIN FAN COOLER | FinFan Cooler | Foundation DraWings / Civil Loading Data (With Embedded Material DraWing (include Auxiliary equipment)) | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.6429 | 0.8913 | 0.7174 | 0.7174 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 3 | 8 | 37.5617 | 0.5701 | 0.0306 | 0.0306 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126539 | FIN FAN COOLER - STEEL STRUCTURE CALCULATION | CALCULATION | FIN FAN COOLER |  |  |  | Calculation sheet for FIN FAN COOLER | FinFan Cooler | Steel Structure Calculation | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | calculation | calculation | calculation | calculation | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8587 | 0.8176 | 0.8176 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 3 | 1 | 35.7395 | 0.5323 | 0.0323 | 0.0323 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0PCA-126540 | FIN FAN COOLER – DETAIL DRAWING FOR CLEANING COMPRESSOR | DETAIL DRAWING | FIN FAN COOLER |  |  |  | Detail Drawing for FIN FAN COOLER |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5543 | 0.6330 | 0.6330 | FI | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | false | 3 | 3 | 35.7395 | 0.5528 | 0.0317 | 0.0238 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127001 | FGP COP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | FGP COP ¦ Fuel Gas Package COP |  |  |  | GENERAL ARRANGEMENT DRAWING for FGP COP ¦ Fuel Gas Package COP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6606 | 0.8982 | 0.8982 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 6.9833 | 0.6470 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LCB-127002 | FGP COP - P&I DIAGRAM | P&I DIAGRAM | FGP COP ¦ Fuel Gas Package COP |  |  |  | P&ID for FGP COP ¦ Fuel Gas Package COP | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.7885 | 0.7615 | 0.7615 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 21.2897 | 0.7240 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127003 | FGP COP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | FGP COP ¦ Fuel Gas Package COP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for FGP COP ¦ Fuel Gas Package COP | Fuel Gas Compressor | Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8571 | 0.7678 | 0.8303 | 0.8303 | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 16.6251 | 0.7038 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127004 | FGP COP - PUMP SECTIONAL DRAWING | DRAWING | FGP COP ¦ Fuel Gas Package COP |  |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match | fgp |  | fgp | query | fgp | match | false | 11 | 2 | 7.8224 | 0.6592 | 0.0302 | 0.0302 | hybrid | structured_preferred | fgp | civil_design | 10 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127005 | FGP COP - MECHANICAL SEAL SPECIFICATION | SPECIFICATION | FGP COP ¦ Fuel Gas Package COP |  |  |  | Technical Specification for FGP COP ¦ Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5087 | 0.6193 | 0.4335 | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | 1 | 2 | 14.3363 | 0.5634 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | procurement | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127006 | FGP COP - COUPLING SPECIFICATION | SPECIFICATION | FGP COP ¦ Fuel Gas Package COP |  |  |  | Technical Specification for FGP COP ¦ Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5087 | 0.6193 | 0.4335 | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | 1 | 5 | 14.3363 | 0.5961 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | fgp | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127007 | FGP COP - SUCTION STRAINER SPECIFICATION | SPECIFICATION | FGP COP ¦ Fuel Gas Package COP |  |  |  | Technical Specification for FGP COP ¦ Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5087 | 0.6193 | 0.4335 | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | 1 | 6 | 14.3363 | 0.5821 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | fgp | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127009 | FGP COP - FOUNDATION DRAWINGS | DRAWINGS | FGP COP ¦ Fuel Gas Package COP |  |  |  | DRAWINGS for FGP COP ¦ Fuel Gas Package COP | Fuel Gas System | Control System Configuration DraWings | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6638 | 0.5491 | 0.5491 | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 2 | 9.8076 | 0.6679 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | civil_design | 10 | 2024-10-25 | 2024-12-06 | 2025-01-17 | 2024-12-27 | 2025-02-07 | 2025-03-21 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0LCB-127010 | FGP COP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | FGP COP ¦ Fuel Gas Package COP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for FGP COP ¦ Fuel Gas Package COP | Fuel Gas Compressor | Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8571 | 0.7678 | 0.8303 | 0.8303 | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 3 | 1 | 16.6251 | 0.7008 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127011 | FGP COP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | FGP COP ¦ Fuel Gas Package COP |  |  |  | DRAWING for FGP COP ¦ Fuel Gas Package COP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6460 | 0.5438 | 0.5438 | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 1 | 2 | 7.8224 | 0.6293 | 0.0325 | 0.0244 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-17 | 2025-03-14 | 2025-02-07 | 2025-04-04 | 2025-05-30 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LCB-127013 | FGP COP - INSTRUMENT LIST AND DATA SHEET | LIST AND DATA SHEET | FGP COP ¦ Fuel Gas Package COP |  |  |  | Instrument List for FGP COP ¦ Fuel Gas Package COP | Fuel Gas System | Instrument List | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | list | list | instrument_list | instrument_list | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.7878 | 0.7964 | 0.7964 | FI | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 16.6251 | 0.6963 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-05-24 | 2024-07-05 | 2024-08-16 | 2024-07-26 | 2024-09-06 | 2024-10-18 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LCB-127015 | FGP COP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | FGP COP ¦ Fuel Gas Package COP |  |  |  | HOOK - UP DRAWING for FGP COP ¦ Fuel Gas Package COP |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6670 | 0.7251 | 0.7251 | FI | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 9.8154 | 0.6305 | 0.0328 | 0.0246 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127016 | FGP COP - VMS SPECIFICATION | SPECIFICATION | FGP COP ¦ Fuel Gas Package COP | VMS ¦ Vibration Monitoring System |  |  | Technical Specification for FGP COP ¦ Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5087 | 0.6193 | 0.4335 | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | 1 | 2 | 14.7807 | 0.5882 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | procurement | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0LCB-127018 | FGP COP - NAME PLATE DRAWING | DRAWING | FGP COP ¦ Fuel Gas Package COP |  |  |  | DRAWING for FGP COP ¦ Fuel Gas Package COP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6460 | 0.5438 | 0.5438 | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 1 | 3 | 7.8224 | 0.6262 | 0.0323 | 0.0242 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-17 | 2025-03-14 | 2025-02-07 | 2025-04-04 | 2025-05-30 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127031 | CEP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | CEP ¦ Condensate Extraction Pump |  |  |  | GENERAL ARRANGEMENT DRAWING for CEP ¦ Condensate Extraction Pump |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | condensate¦extraction¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6485 | 0.8946 | 0.8946 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 8.2795 | 0.5613 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LCB-127032 | CEP - P&I DIAGRAM | P&I DIAGRAM | CEP ¦ Condensate Extraction Pump |  |  |  | P&ID for CEP ¦ Condensate Extraction Pump | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5816 | 0.5245 | 0.5245 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 21 | 20 | 22.2561 | 0.6666 | 0.0248 | 0.0248 | hybrid | structured_blocked_procurement_conflict | condensate | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127033 | CEP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | CEP ¦ Condensate Extraction Pump |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for CEP ¦ Condensate Extraction Pump |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | condensate¦extraction¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7269 | 0.9181 | 0.9181 | FA | 2PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-09-08 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 2 | 1 | 38.4515 | 0.7894 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127034 | CEP - PUMP SECTIONAL DRAWING | DRAWING | CEP ¦ Condensate Extraction Pump |  |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 2 | 35.7289 | 0.7257 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-12-04 | 2025-01-03 | 2025-02-02 | 2025-02-17 | 2025-03-04 | 2025-03-19 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127035 | CEP - MECHANICAL SEAL SPECIFICATION | SPECIFICATION | CEP ¦ Condensate Extraction Pump |  |  |  | Technical Specification for CEP ¦ Condensate Extraction Pump |  | TECHNICAL SPECIFICATION & DATASHEET | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5353 | 0.6272 | 0.4391 | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 37.7881 | 0.6779 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127036 | CEP - COUPLING SPECIFICATION | SPECIFICATION | CEP ¦ Condensate Extraction Pump |  |  |  | Technical Specification for CEP ¦ Condensate Extraction Pump |  | TECHNICAL SPECIFICATION & DATASHEET | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5353 | 0.6272 | 0.4391 | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 1 | 4 | 37.7881 | 0.6962 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127037 | CEP - SUCTION STRAINER SPECIFICATION | SPECIFICATION | CEP ¦ Condensate Extraction Pump |  |  |  | Technical Specification for CEP ¦ Condensate Extraction Pump |  | TECHNICAL SPECIFICATION & DATASHEET | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5353 | 0.6272 | 0.4391 | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 1 | 4 | 37.7881 | 0.6944 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127038 | CEP - FOUNDATION DRAWINGS | DRAWINGS | CEP ¦ Condensate Extraction Pump |  |  |  | DRAWINGS for CEP ¦ Condensate Extraction Pump |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦extraction¦pump | pump | scoped | match | match | match | passed |  | 0.3333 | 0.6560 | 0.4301 | 0.3011 | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 2 | 33.2814 | 0.7480 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | condensate | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.30 | 0.85 | usable | rule_score_medium | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0LCB-127039 | CEP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | CEP ¦ Condensate Extraction Pump |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for CEP ¦ Condensate Extraction Pump |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | condensate¦extraction¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7269 | 0.9181 | 0.9181 | FA | 2PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-09-08 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 2 | 1 | 38.4515 | 0.7637 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LCB-127040 | CEP - INSTRUMENT LIST AND DATA SHEET | LIST AND DATA SHEET | CEP ¦ Condensate Extraction Pump |  |  |  | Instrument List for CEP ¦ Condensate Extraction Pump |  | INSTRUMENT LIST & DATA SHEET | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | list | list | instrument_list | instrument_list | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8479 | 0.9544 | 0.6681 | FA | 2PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-09-08 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 3 | 1 | 30.8791 | 0.7331 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | procurement | 10 | 2024-04-25 | 2024-05-10 | 2024-05-25 | 2024-06-09 | 2024-07-09 | 2024-08-08 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LCB-127041 | CEP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | CEP ¦ Condensate Extraction Pump |  |  |  | HOOK - UP DRAWING for CEP ¦ Condensate Extraction Pump |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6381 | 0.7164 | 0.7164 | FI | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | design_drawing | civil_design | compatible | condensate |  | condensate | query | condensate | match | false | 1 | 2 | 31.2033 | 0.6603 | 0.0325 | 0.0244 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0LCB-127042 | CEP - NAME PLATE DRAWING | DRAWING | CEP ¦ Condensate Extraction Pump |  |  |  | DRAWING for CEP ¦ Condensate Extraction Pump |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦extraction¦pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6361 | 0.6575 | 0.4602 | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | design_drawing | civil_design | compatible | condensate |  | condensate | query | condensate | match | false | 1 | 2 | 31.2033 | 0.7137 | 0.0325 | 0.0244 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.30 | 0.64 | usable | rule_score_medium;activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127501 | AIR COMPRESSOR - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | AIR COMPRESSOR |  |  |  | GENERAL ARRANGEMENT DRAWING for AIR COMPRESSOR |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | air¦compressor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7104 | 0.9131 | 0.9131 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 10.0325 | 0.6003 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-127502 | AIR COMPRESSOR - P&I DIAGRAM | P&I DIAGRAM | AIR COMPRESSOR |  |  |  | P&ID for AIR COMPRESSOR | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6790 | 0.5537 | 0.5537 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 3 | 1 | 24.4523 | 0.7193 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127503 | AIR COMPRESSOR - AIR COMPRESSOR SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5670 | 0.6368 | 0.4457 | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 5 | 31.0917 | 0.5299 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127504 | AIR COMPRESSOR - AIR DRYER SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5670 | 0.6368 | 0.4457 | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 27.1757 | 0.5340 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | procurement | 9 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127505 | AIR COMPRESSOR - AIR RECEIVER SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5670 | 0.6368 | 0.4457 | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 27.1757 | 0.5090 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | procurement | 9 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127506 | AIR COMPRESSOR - AIR FILTER SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5670 | 0.6368 | 0.4457 | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 2 | 27.1757 | 0.5069 | 0.0325 | 0.0325 | hybrid | structured_preferred | compressed_air | procurement | 9 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0SCA-127509 | AIR COMPRESSOR - FOUNDATION DRAWINGS | DRAWINGS | AIR COMPRESSOR |  |  |  | DRAWINGS for AIR COMPRESSOR | Air Compressor | Control System Configuration DraWings | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7560 | 0.5768 | 0.5768 | FA | 0EF3510W16A03 | (COMP Air PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-12-03 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 2 | 1 | 18.1662 | 0.6156 | 0.0325 | 0.0325 | hybrid | structured_preferred | compressed_air | civil_design | 10 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0SCA-127510 | AIR COMPRESSOR - SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | AIR COMPRESSOR |  |  |  | Single Line Diagram for AIR COMPRESSOR | Air Compressor | Single Line Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9626 | 0.9888 | 0.9888 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 19.9004 | 0.6218 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design¦engineering | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0SCA-127511 | AIR COMPRESSOR - SCHEMATIC & WIRING DIAGRAM | SCHEMATIC & WIRING DIAGRAM | AIR COMPRESSOR |  |  |  | SCHEMATIC & WIRING DIAGRAM for AIR COMPRESSOR | Air Compressor | Interconnection Wiring Diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7734 | 0.7920 | 0.7920 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 19.9004 | 0.5575 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design¦engineering | 1 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0SCA-127514 | AIR COMPRESSOR - CONTROL DESCRIPTION (PHILOSOPHY) |  | AIR COMPRESSOR |  |  |  | for AIR COMPRESSOR | Air Compressor | Control Philosophy | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | description | description | control_description | control_description | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7480 | 0.9244 | 0.9244 | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 23.8609 | 0.6314 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0SCA-127515 | AIR COMPRESSOR - PLC HMI GRAPHICS | HMI GRAPHICS ¦ Human Machine Interface GRAPHICS | AIR COMPRESSOR |  |  |  | HMI GRAPHICS ¦ Human Machine Interface GRAPHICS for AIR COMPRESSOR | [5 empty] | rule_query | other | other | hmi_graphics_human_machine_interface_graphics | hmi_graphics | air¦compressor |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6833 | 0.6716 | 0.6716 |  | 0CF3510W42A08 | (COMP Air PKG) Installation_Compressor, Dryer | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2008-06-16 | 2008-08-16 |  | installation | query_unknown | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 24 | 20.3673 | 0.4752 | 0.0283 | 0.0212 | hybrid | structured_no_phase | compressed_air | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SCA-127516 | AIR COMPRESSOR - PLC HARDWIRED IO LIST | LIST | AIR COMPRESSOR |  |  |  | I/O List for AIR COMPRESSOR | Air Compressor | Datalink interface IO List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | io_list | io_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7048 | 0.6781 | 0.6781 | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 2 | 1 | 23.8609 | 0.5908 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SCA-127517 | AIR COMPRESSOR - DATALINK INTERFACE IO LIST | LIST | AIR COMPRESSOR |  |  |  | I/O List for AIR COMPRESSOR | Air Compressor | Datalink interface IO List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | io_list | io_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8822 | 0.9647 | 0.9647 | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 2 | 1 | 23.8609 | 0.5677 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0SCA-127518 | AIR COMPRESSOR - CONTROL LOGIC & LOOP DIAGRAM | & LOOP DIAGRAM | AIR COMPRESSOR |  |  |  | & LOOP DIAGRAM for AIR COMPRESSOR | Air Compressor | Control Logic & Loop Diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | diagram | diagram | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8704 | 0.7278 | 0.7278 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 19.9004 | 0.6184 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design¦engineering | 1 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0SCA-127520 | AIR COMPRESSOR - INSTRUMENT LIST | INSTRUMENT LIST | AIR COMPRESSOR |  |  |  | Instrument List for AIR COMPRESSOR | Air Compressor | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9514 | 0.9854 | 0.9854 | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 23.8609 | 0.6016 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | procurement | 9 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SCA-127521 | AIR COMPRESSOR - INSTRUMENT SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5670 | 0.6368 | 0.4457 | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 6 | 23.2225 | 0.5533 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0SCA-127522 | AIR COMPRESSOR - INSTRUMENTATION HOOK - UP DRAWING | DRAWING | AIR COMPRESSOR |  |  |  | DRAWING for AIR COMPRESSOR |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8077 | 0.9423 | 0.9423 | FI | 0EF3510W16A03 | (COMP Air PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-12-03 | design_drawing | civil_design | compatible | compressed_air |  | compressed_air | query | compressed_air | match | false | 3 | 3 | 15.9122 | 0.5295 | 0.0317 | 0.0238 | hybrid | structured_preferred | compressed_air | system_design¦civil_design | 10 | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SCA-127523 | AIR COMPRESSOR - PLC PANEL DRAWING | DRAWING | AIR COMPRESSOR |  |  |  | DRAWING for AIR COMPRESSOR |  | PLC PANEL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8356 | 0.9507 | 0.6655 | FA | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | design_drawing | civil_design | compatible | compressed_air |  | compressed_air | query | compressed_air | match | false | 2 | 3 | 15.9122 | 0.5701 | 0.0320 | 0.0240 | hybrid | structured_preferred | compressed_air | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XF00-P0SCA-127524 | AIR COMPRESSOR - NAME PLATE DRAWING | DRAWING | AIR COMPRESSOR |  |  |  | DRAWING for AIR COMPRESSOR | Air Compressor | Name Plate draWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8608 | 0.9582 | 0.9582 | FA | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | design_drawing | civil_design | compatible | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 2 | 4 | 15.9122 | 0.5577 | 0.0318 | 0.0238 | hybrid | structured_preferred | compressed_air | system_design¦civil_design | 10 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0SCA-127525 | AIR COMPRESSOR - VALVE LIST | VALVE LIST | AIR COMPRESSOR |  |  |  | Valve List for AIR COMPRESSOR | Air Compressor | Valve List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | list | list | valve_list | valve_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9464 | 0.9839 | 0.9839 | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 23.8609 | 0.5685 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | procurement | 9 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SCA-127526 | AIR COMPRESSOR - VALVE SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5670 | 0.6368 | 0.4457 | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 7 | 23.2225 | 0.5005 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD16-P0SCA-127546 | AIR COMPRESSOR - EMBEDDED CONDUIT LAYOUT FOR CONTROL CABLES (FROM MCP TO EQUIPMENT) | LAYOUT | AIR COMPRESSOR |  |  |  | Layout Drawing for AIR COMPRESSOR |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7172 | 0.9151 | 0.6406 | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 4 | 1 | 24.5878 | 0.5621 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0SCA-127548 | AIR COMPRESSOR – I&C CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | AIR COMPRESSOR |  |  |  | WIRING DIAGRAM for AIR COMPRESSOR | Air Compressor | Interconnection Wiring Diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8030 | 0.8009 | 0.8009 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 19.9004 | 0.5584 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design¦engineering | 1 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127555 | AIR COMPRESSOR - AIR CHILLER - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | AIR COMPRESSOR - AIR CHILLER |  |  |  | GENERAL ARRANGEMENT DRAWING for AIR COMPRESSOR - AIR CHILLER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | air¦chiller¦compressor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6506 | 0.8952 | 0.8952 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 17.8179 | 0.5901 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127556 | AIR COMPRESSOR - AIR CHILLER - DATA SHEET | DATA SHEET | AIR COMPRESSOR - AIR CHILLER |  |  |  | Data Sheet for AIR COMPRESSOR - AIR CHILLER | Air Compressor | Data Sheet for Valves | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | air¦chiller¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7510 | 0.8086 | 0.8086 | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 2 | 4 | 31.7673 | 0.5888 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-127557 | AIR COMPRESSOR - AIR CHILLER - P&I DIAGRAM | P&I DIAGRAM | AIR COMPRESSOR - AIR CHILLER |  |  |  | P&ID for AIR COMPRESSOR - AIR CHILLER | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦chiller¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6760 | 0.5528 | 0.5528 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 2 | 1 | 32.2377 | 0.6828 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128001 | CRANE - GA DRAWING FOR STEAM TURBINE BUILDING CRANE | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | CRANE |  | STEAM TURBINE BUILDING |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane¦stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7363 | 0.9209 | 0.9209 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist¦stg |  | crane_hoist¦stg | query | stg | match | false | 1 | 2 | 22.8299 | 0.6209 | 0.0325 | 0.0325 | hybrid | structured_preferred | crane_hoist¦stg | civil_design | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128002 | CRANE - GA DRAWING FOR WORKSHOP CRANE | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | CRANE |  | WORKSHOP |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7363 | 0.9209 | 0.9209 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 201 | 207 | 8.0086 | 0.4642 | 0.0076 | 0.0045 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMM-128004 | CRANE - DATA SHEETS FOR STEAM TURBINE BUILDING CRANE | DATA SHEETS | CRANE |  | STEAM TURBINE BUILDING |  | DATA SHEETS for CRANE | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | crane¦stg |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7509 | 0.5053 | 0.5053 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist¦stg | crane_hoist | crane_hoist¦stg | query | crane_hoist | match | false | 1 | 1 | 40.5637 | 0.6137 | 0.0328 | 0.0328 | hybrid | structured_preferred | crane_hoist¦stg | procurement | 10 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMS-128005 | CRANE - DATA SHEETS FOR WORKSHOP CRANE | DATA SHEETS | CRANE |  | WORKSHOP |  | DATA SHEETS for CRANE | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | crane |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7509 | 0.5053 | 0.5053 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | false | 1 | 1 | 40.5637 | 0.6455 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMM-128007 | CRANE - MECHNICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | DETAIL | CRANE |  | STEAM TURBINE BUILDING |  | Detail Drawing for STEAM TURBINE BUILDING |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5487 | 0.6313 | 0.6313 | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist¦stg |  | crane_hoist¦stg | query | stg | match | false | 4 | 2 | 8.1992 | 0.5274 | 0.0318 | 0.0318 | hybrid | structured_preferred | crane_hoist¦stg | civil_design | 10 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMS-128008 | CRANE - MECHNICAL DETAIL FOR WORKSHOP CRANE | DETAIL | CRANE |  | WORKSHOP |  | Detail Drawing for WORKSHOP |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | workshop |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5857 | 0.6424 | 0.6424 | FI | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 1308 | 65 |  | 0.4597 | 0.0087 | 0.0039 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMM-128010 | CRANE - ELECTRICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | DETAIL | CRANE |  | STEAM TURBINE BUILDING |  | Detail Drawing for STEAM TURBINE BUILDING |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5487 | 0.6313 | 0.6313 | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist¦stg |  | crane_hoist¦stg | query | stg | match | false | 4 | 2 | 8.1992 | 0.5491 | 0.0318 | 0.0318 | hybrid | structured_preferred | crane_hoist¦stg | civil_design | 10 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMS-128011 | CRANE - ELECTRICAL DETAIL FOR WORKSHOP CRANE | DETAIL | CRANE |  | WORKSHOP |  | Detail Drawing for WORKSHOP |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | workshop |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5857 | 0.6424 | 0.6424 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | electrical | mismatch | false | 43 | 15 | 12.8430 | 0.5155 | 0.0230 | 0.0043 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SML-128013 | CRANE - GA DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | CRANE |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7363 | 0.9209 | 0.9209 | FA | 0EF5550W00A01 | (Pipe Rack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 27 | 23 | 16.0798 | 0.5588 | 0.0235 | 0.0141 | hybrid | structured_phase_gap | crane_hoist | civil_design |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMQ-128014 | HOIST - GA DRAWING FOR FF PUMP HOUSE HOIST | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  | FF PUMP HOUSE ¦ Fire Fighting PUMP HOUSE |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | crane_hoist¦fire_fighting |  | crane_hoist¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 2.2120 | 0.4388 | 0.0328 | 0.0328 | hybrid | structured_preferred | crane_hoist¦fire_fighting | system_design | 2 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128015 | HOIST - GA DRAWING FOR AIR COMPRSSOR HOUSE HOIST | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | crane_hoist |  | crane_hoist | query | hrsg | mismatch | false | 49 | 204 | 14.4142 | 0.4912 | 0.0130 | 0.0032 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128016 | HOIST - GA DRAWING FOR DM WATER TREATMENT HOIST | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | crane_hoist |  | crane_hoist | query | hrsg | mismatch | false | 49 | 112 | 14.4142 | 0.4881 | 0.0150 | 0.0037 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128017 | HOIST - GA DRAWING FOR CHAIN BLOCK | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 209 | 516 | 8.0086 | 0.4083 | 0.0055 | 0.0033 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SML-128018 | CRANE - DATA SHEETS FOR DEAERATOR SUPPORT STRUCTURE CRANE | DATA SHEETS | CRANE |  |  |  | DATA SHEETS for CRANE | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | crane |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7509 | 0.5053 | 0.5053 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | false | 1 | 2 | 40.5637 | 0.6101 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMQ-128019 | HOIST - DATA SHEETS FOR FF PUMP HOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist¦pump | pump | scoped | match | match | match | passed |  | 0.5000 | 0.6443 | 0.5433 | 0.5433 | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist |  | crane_hoist | query | crane_hoist | match | false | 1 | 1 | 42.1824 | 0.5736 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-11-07 | 2024-12-12 | 2025-01-16 | 2025-01-02 | 2025-02-06 | 2025-03-13 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128020 | HOIST - DATA SHEETS FOR AIR COMPRSSOR HOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Air Compressor | Data Sheet for Valves | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6084 | 0.5325 | 0.5325 | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | compressed_air | crane_hoist | query | crane_hoist | match | false | 1 | 2 | 42.1824 | 0.5744 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMG-128021 | HOIST - DATA SHEETS FOR DM WATER TREATMENT HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Water Treatment System | Motor Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6703 | 0.6011 | 0.6011 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | wts | crane_hoist | query | crane_hoist | match | false | 1 | 1 | 42.1824 | 0.5496 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128022 | HOIST - DATA SHEETS FOR CHAIN BLOCK | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | false | 1 | 1 | 30.9529 | 0.5957 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SML-128023 | CRANE - MECHNICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | MECHNICAL DETAIL | CRANE |  |  |  | MECHNICAL DETAIL for CRANE |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | crane |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7571 | 0.7871 | 0.7871 | FI | 0CF3530W42A09 | (Crane & Hoist) Crane Erection for BSDG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-03-08 | 2008-04-08 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | bsedg¦crane_hoist | match | false | 2 | 1 | 37.7358 | 0.5706 | 0.0325 | 0.0244 | hybrid | structured_no_phase | crane_hoist | [5 empty] | 2024-12-09 | 2025-01-08 | 2025-02-07 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMQ-128024 | HOIST - MECHANICAL DETAIL FOR FF PUMP HOUSE HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for Pump |  | Pump Pit Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7122 | 0.6803 | 0.5783 | FA | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-04-16 | 2008-05-16 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | compressed_air¦crane_hoist | match | false | 3 | 1 | 36.5994 | 0.5247 | 0.0323 | 0.0242 | hybrid | structured_no_phase | crane_hoist |  |  | 2024-12-03 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.60 | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMU-128025 | HOIST - MECHANICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for HOIST |  | MECHANICAL DETAIL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7646 | 0.6961 | 0.4872 | FA | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-04-16 | 2008-05-16 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | compressed_air¦crane_hoist | match | false | 1 | 1 | 39.5348 | 0.6193 | 0.0328 | 0.0246 | hybrid | structured_no_phase | crane_hoist |  |  | 2024-12-03 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMG-128026 | HOIST - MECHANICAL DETAIL FOR DM WATER TREATMENT HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for HOIST | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.6000 | 0.5745 | 0.5924 | 0.5924 | FA | 0CF3530W42A09 | (Crane & Hoist) Crane Erection for BSDG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-03-08 | 2008-04-08 |  | installation | query_unknown | crane_hoist | wts | crane_hoist | query | bsedg¦crane_hoist | match | false | 2 | 4 | 36.5994 | 0.4991 | 0.0318 | 0.0238 | hybrid | structured_no_phase | crane_hoist |  |  | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | 2025-01-08 | 2025-02-07 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SML-128027 | CRANE - ELECTRICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | ELECTRICAL DETAIL | CRANE |  |  |  | ELECTRICAL DETAIL for CRANE |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | crane |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7400 | 0.7820 | 0.7820 | FI | 0CF3530W42A09 | (Crane & Hoist) Crane Erection for BSDG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-03-08 | 2008-04-08 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | bsedg¦crane_hoist | match | false | 2 | 3 | 37.7358 | 0.5764 | 0.0320 | 0.0240 | hybrid | structured_no_phase | crane_hoist | [5 empty] | 2024-12-09 | 2025-01-08 | 2025-02-07 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMC-128028 | HOIST - GA DRAWING FOR CENTRAL CONTROL BUILDING HOIST | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  | CENTRAL CONTROL BUILDING |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | ccr¦central¦hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 14 | 2 | 33.3586 | 0.5875 | 0.0296 | 0.0178 | hybrid | structured_phase_gap | crane_hoist | civil_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128029 | HOIST - GA DRAWING FOR WAREHOUSE HOIST | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 185 | 526 | 8.0086 | 0.4123 | 0.0058 | 0.0035 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128030 | HOIST - GA DRAWING FOR WASTE WATER TREATMENT HOIST | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | crane_hoist |  | crane_hoist | query | wts | mismatch | false | 22 | 348 | 20.0784 | 0.4559 | 0.0146 | 0.0037 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128031 | HOIST - GA DRAWING FOR CPP HOIST | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | crane_hoist |  | crane_hoist | query | hrsg | mismatch | false | 41 | 119 | 14.4142 | 0.4977 | 0.0155 | 0.0039 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128032 | JIB CRANE - GA DRAWING FOR AIR COOLED CONDENSER JIB CRANE | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | JIB CRANE |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for JIB CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | acc¦air¦condenser¦cooled¦crane¦jib |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7041 | 0.9112 | 0.9112 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 247 | 304 | 8.0086 | 0.4574 | 0.0060 | 0.0036 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMC-128033 | HOIST - DATA SHEETS FOR CENTRAL CONTROL BUILDING HOIST | DATA SHEETS | HOIST |  | CENTRAL CONTROL BUILDING |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | ccr¦central¦hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | false | 1 | 2 | 42.1824 | 0.5898 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMS-128034 | HOIST - DATA SHEETS FOR WAREHOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | false | 1 | 1 | 42.1824 | 0.6114 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMG-128035 | HOIST - DATA SHEETS FOR WASTE WATER TREATMENT HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Water Treatment System | Pump Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist¦wts | pump¦wts | scoped | match | match | match | passed |  | 0.5714 | 0.6075 | 0.5823 | 0.5823 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | wts | crane_hoist | query | crane_hoist | match | false | 1 | 1 | 42.1824 | 0.5577 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMM-128036 | HOIST - DATA SHEETS FOR CPP HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | false | 1 | 1 | 42.1824 | 0.6211 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128037 | JIB CRANE - DATA SHEETS FOR AIR COOLED CONDENSER JIB CRANE | DATA SHEETS | JIB CRANE |  |  |  | DATA SHEETS for JIB CRANE | Cooling ToWer | COOLING TOWER _JIB CRANE DATASHEET | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled¦crane¦jib |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.8270 | 0.5281 | 0.5281 | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | false | 2 | 2 | 40.5637 | 0.5804 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMC-128038 | HOIST - MECHANICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | DETAIL | HOIST |  | CENTRAL CONTROL BUILDING |  | Detail Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8173 | 0.8052 | 0.8052 | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 24 | 3 | 17.6674 | 0.5518 | 0.0278 | 0.0167 | hybrid | structured_phase_gap | crane_hoist | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMS-128039 | HOIST - MECHANICAL DETAIL FOR WAREHOUSE HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | FI | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 37 | 13 | 11.4430 | 0.5063 | 0.0240 | 0.0108 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMG-128040 | HOIST - MECHANICAL DETAIL FOR WASTE WATER TREATMENT HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.6731 | 0.7619 | 0.7619 | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | design_drawing | civil_design | compatible | crane_hoist | wts | crane_hoist | query | wts | mismatch | false | 30 | 2 | 19.2922 | 0.4878 | 0.0272 | 0.0051 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMM-128041 | HOIST - MECHANICAL DETAIL FOR CPP HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | FI | 0EF5560W16A02 | (M&E WORKSHOP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 | 2008-04-09 | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | electrical | mismatch | false | 79 | 2441 | 8.2543 | 0.3240 | 0.0076 | 0.0014 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMU-128042 | JIB CRANE - MECHANICAL DETAIL FOR AIR COOLED CONDENSER JIB CRANE | DETAIL | JIB CRANE |  |  |  | Detail Drawing for ACC | CONDENSER | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.8000 | 0.6664 | 0.7599 | 0.7599 | FA | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | crane_hoist | acc | crane_hoist | query | acc¦condensate | mismatch | false | 30 | 4 | 8.4959 | 0.5172 | 0.0267 | 0.0050 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMC-128043 | HOIST - ELECTRICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | DETAIL | HOIST |  | CENTRAL CONTROL BUILDING |  | Detail Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8173 | 0.8052 | 0.8052 | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 28 | 2 | 17.6674 | 0.5501 | 0.0275 | 0.0165 | hybrid | structured_phase_gap | crane_hoist | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMS-128044 | HOIST - ELECTRICAL DETAIL FOR WAREHOUSE HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | FI | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 40 | 26 | 11.4430 | 0.4985 | 0.0216 | 0.0097 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMQ-128045 | HOIST - ELECTRICAL DETAIL FOR FF PUMP HOUSE HOIST | DETAIL | HOIST |  | FF PUMP HOUSE ¦ Fire Fighting PUMP HOUSE |  | Detail Drawing for FF PUMP HOUSE ¦ Fire Fighting PUMP HOUSE |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | fighting¦fire¦house¦pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5299 | 0.6256 | 0.6256 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | crane_hoist¦fire_fighting |  | crane_hoist¦fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 1 | 4.6749 | 0.5103 | 0.0320 | 0.0240 | hybrid | structured_preferred | crane_hoist¦fire_fighting | system_design¦civil_design | 10 | 2024-06-12 | 2024-07-12 | 2024-08-11 | 2024-08-26 | 2024-09-10 | 2024-09-25 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMU-128046 | HOIST - ELECTRICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | FI | 2EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-02 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | fgp | mismatch | false | 474 | 2 | 6.7600 | 0.5724 | 0.0180 | 0.0034 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMG-128047 | HOIST - ELECTRICAL DETAIL FOR DM WATER TREATMENT HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | FI | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 760 | 30 | 3.6346 | 0.4823 | 0.0123 | 0.0055 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 0.29 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMG-128048 | HOIST - ELECTRICAL DETAIL FOR WASTE WATER TREATMENT HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.6598 | 0.7579 | 0.7579 | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | design_drawing | civil_design | compatible | crane_hoist | wts | crane_hoist | query | wts | mismatch | false | 23 | 1 | 21.6660 | 0.4981 | 0.0284 | 0.0053 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMM-128049 | HOIST - ELECTRICAL DETAIL FOR CPP HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | FI | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-06-20 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | hrsg | mismatch | false | 1247 | 122 | 2.3034 | 0.4729 | 0.0063 | 0.0012 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128051 | JIB CRANE - GA DRAWING FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | JIB CRANE |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for JIB CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane¦jib¦pump¦tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7041 | 0.9112 | 0.9112 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 294 | 267 | 8.0086 | 0.4361 | 0.0059 | 0.0035 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128052 | JIB CRANE - DATA SHEETS FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | DATA SHEETS | JIB CRANE |  |  |  | DATA SHEETS for JIB CRANE |  | ACC - Drain Pump Datasheet | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | title | datasheet | datasheet | data_sheet | data_sheet | crane¦jib¦pump¦tank | acc¦pump | scoped | match | match | match | passed |  | 0.5000 | 0.5764 | 0.5229 | 0.5229 | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | acc | crane_hoist | query | crane_hoist | match | false | 1 | 2 | 40.5637 | 0.5573 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2025-03-18 | 2025-04-17 | 2025-05-17 | 2025-06-01 | 2025-06-16 | 2025-07-01 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128053 | JIB CRANE - MECHANICAL DETAIL FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | DETAIL | JIB CRANE |  |  |  | Detail Drawing for Tank |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump¦tank |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6199 | 0.6526 | 0.6526 | FI | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | 721 | 33 | 4.9357 | 0.4579 | 0.0120 | 0.0054 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2024-05-29 | 2024-06-28 | 2024-07-28 | 2024-08-12 | 2024-08-27 | 2024-09-11 | generated | 0.90 | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128060 | PORTABLE GANTRY - GA DRAWING | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | PORTABLE GANTRY |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for PORTABLE GANTRY |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gantry¦portable |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6985 | 0.9096 | 0.9096 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 33 | 268 | 14.4142 | 0.4539 | 0.0138 | 0.0104 | hybrid | structured_no_system |  | system_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128070 | HOIST - GA DRAWING FOR ST GSUT | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GA DRAWING ¦ GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist¦stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7271 | 0.9181 | 0.9181 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | crane_hoist |  | crane_hoist | query | hrsg | mismatch | false | 41 | 161 | 14.4142 | 0.4720 | 0.0144 | 0.0036 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128101 | CRANE - NAME PLATE DRAWING FOR STEAM TURBINE BUILDING CRANE | DRAWING | CRANE |  |  |  | DRAWING for CRANE |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | crane¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6508 | 0.8952 | 0.8952 | FI | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query | stg | mismatch | false | 369 | 219 | 8.1992 | 0.5234 | 0.0059 | 0.0015 | hybrid | structured_phase_gap | crane_hoist | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128102 | CRANE - NAME PLATE DRAWING FOR WORKSHOP CRANE | DRAWING | CRANE |  |  |  | DRAWING for CRANE |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | crane |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6723 | 0.9017 | 0.9017 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | electrical | mismatch | false | 85 | 66 | 9.7017 | 0.4854 | 0.0148 | 0.0028 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SML-128103 | CRANE - NAME PLATE DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | DRAWING | CRANE |  |  |  | DRAWING for CRANE |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | crane |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6570 | 0.8971 | 0.8971 | FI | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query | bop | mismatch | false | 99 | 643 | 8.2027 | 0.4417 | 0.0077 | 0.0019 | hybrid | structured_phase_gap | crane_hoist | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GM-128501 | SUMP PUMP - PUMP OUTLINE DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for SUMP PUMP |  | Pump Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | pump¦sump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7869 | 0.9361 | 0.9361 | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | [5 empty] | query_unscoped | true | 81 | 52 | 14.0842 | 0.5014 | 0.0160 | 0.0096 | hybrid | structured_no_system |  | system_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GM-128502 | SUMP PUMP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | SUMP PUMP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for SUMP PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | pump¦sump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8104 | 0.9431 | 0.9431 | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | false | 5 | 4 | 17.2807 | 0.5292 | 0.0310 | 0.0233 | hybrid | structured_no_system |  | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GM-128503 | SUMP PUMP - PUMP SECTIONAL DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | FA | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 40 | 41 | 14.8071 | 0.5144 | 0.0199 | 0.0119 | hybrid | structured_no_system |  | civil_design |  | 2024-05-29 | 2024-06-28 | 2024-07-28 | 2024-08-12 | 2024-08-27 | 2024-09-11 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0GM-128504 | SUMP PUMP - MECHANICAL SEAL SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | 2 | 2 | 15.8838 | 0.5019 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0GM-128505 | SUMP PUMP - COUPLING SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | 2 | 2 | 15.8838 | 0.4781 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0GM-128506 | SUMP PUMP - FOUNDATION DRAWINGS | DRAWINGS | SUMP PUMP |  |  |  | DRAWINGS for SUMP PUMP |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pump¦sump | pump | scoped | match | match | match | passed |  | 0.3333 | 0.6794 | 0.4372 | 0.3060 | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | 10 | 14 | 11.1294 | 0.5068 | 0.0278 | 0.0208 | hybrid | structured_no_system |  | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.30 | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0GM-128507 | SUMP PUMP - MOTOR SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | 3 | 2 | 15.8838 | 0.4590 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0GM-128508 | SUMP PUMP - INSTRUMENT SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | 3 | 2 | 15.8838 | 0.5059 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GM-128509 | SUMP PUMP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | SUMP PUMP |  |  |  | HOOK - UP DRAWING for SUMP PUMP | FireFighting | Hook Up DraWing | 1 | start+4W<=FA<=FC<=start+10W | FA ∈ [start+28d, start+70d] ¦ FC ∈ [start+28d, start+70d] | rule_query | drawing | drawing | drawing | drawing | pump¦sump |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6441 | 0.7182 | 0.7182 | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 19 | 24 | 23.1671 | 0.5261 | 0.0246 | 0.0111 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-12 | 2024-05-03 | 2024-05-24 | 2024-05-24 | 2024-06-14 | 2024-07-05 | generated | 0.90 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XF00-P0GM-128510 | SUMP PUMP - NAME PLATE DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for SUMP PUMP |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pump¦sump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6652 | 0.6662 | 0.4664 | FA | 0EF3025W16A12 | (Intake Pump Station) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-06-04 | 2007-10-03 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 5 | 6 | 10.1912 | 0.4818 | 0.0305 | 0.0137 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-06 | 2024-04-05 | 2024-05-05 | generated | 0.30 | 0.41 | needs_review | rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0GM-128511 | SUMP PUMP - SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING FOR WASTE WATER TRANSFER SYSTEM | DRAWING | SUMP PUMP | WASTE WATER TRANSFER SYSTEM |  |  | DRAWING for WASTE WATER TRANSFER SYSTEM |  | SCHEMATIC AND WIRING DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | wiring_diagram | wiring_diagram | pump¦transfer¦waste¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6143 | 0.8843 | 0.6190 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 3 | 31.7790 | 0.5242 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GM-128512 | SUMP PUMP - INSTRUMENT LIST | LIST | SUMP PUMP |  |  |  | Instrument List for SUMP PUMP |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | instrument_list | instrument_list | pump¦sump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6310 | 0.6560 | 0.6560 | FI | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | 4 | 9 | 16.5472 | 0.5514 | 0.0301 | 0.0226 | hybrid | structured_no_system |  | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129001 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  |  |  | GENERAL ARRANGEMENT DRAWING for PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | distribution¦internal¦plant¦pumps¦water |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6184 | 0.8855 | 0.8855 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 380 | 21 | 9.4882 | 0.5932 | 0.0146 | 0.0110 | hybrid | structured_no_system |  | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129002 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  | DATA SHEET & CHARACTERISTIC CURVE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | distribution¦internal¦plant¦pumps¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6569 | 0.8971 | 0.6279 | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | false | 5 | 4 | 16.9363 | 0.5789 | 0.0310 | 0.0233 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-28 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129003 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - PUMP SECTIONAL DRAWING | DRAWING | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | FA | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 119 | 19 | 11.9444 | 0.5848 | 0.0182 | 0.0109 | hybrid | structured_no_system |  | civil_design |  | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129004 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MECHANICAL SEAL SPECIFICATION | SPECIFICATION | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  |  |  | Technical Specification for PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | distribution¦internal¦plant¦pumps¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.4924 | 0.6144 | 0.4301 | FA | 0EF3010W42A04 | (WTS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System |  | 2007-05-30 | procurement | procurement | match |  |  |  |  | wts | query_unscoped | false | 2 | 17 | 14.8649 | 0.5539 | 0.0291 | 0.0218 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129008 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) | FireFighting | Motor Data Sheet | 1 | start+20W<=FA<=FC<=start+30W | FA ∈ [start+140d, start+210d] ¦ FC ∈ [start+140d, start+210d] | title | datasheet | datasheet | data_sheet | data_sheet | distribution¦internal¦plant¦pumps¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.4994 | 0.6748 | 0.6748 | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | false | 13 | 2 | 16.9363 | 0.5955 | 0.0298 | 0.0224 | hybrid | structured_no_system |  | procurement |  | 2024-09-14 | 2024-10-19 | 2024-11-23 | 2024-11-09 | 2024-12-14 | 2025-01-18 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129011 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | PUMPS |  |  |  | Instrument List for PUMPS |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | pumps |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7164 | 0.6816 | 0.6816 | FI | 3PF3015W58A14P | (FW PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | 2007-11-02 | 2008-08-29 | procurement | procurement | match |  |  |  |  | feedwater | query_unscoped | false | 50 | 9 | 13.1532 | 0.5848 | 0.0236 | 0.0177 | hybrid | structured_no_system |  | procurement |  | 2025-01-25 | 2025-02-24 | 2025-03-26 | 2025-04-10 | 2025-04-25 | 2025-05-10 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129013 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING | PUMPS |  |  |  | INSTRUMENTATION HOOK - UP DRAWING for PUMPS |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | pumps |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8231 | 0.9469 | 0.9469 | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 1 | 1 | 29.4341 | 0.6251 | 0.0328 | 0.0148 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129014 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - NAME PLATE DRAWING | DRAWING |  |  |  |  | DRAWING |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.5508 | 0.8652 | 0.8652 | FI | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 975 | 2 | 2.6624 | 0.5995 | 0.0171 | 0.0077 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-08-21 | 2024-09-20 | 2024-10-20 | 2024-11-04 | 2024-11-19 | 2024-12-04 | generated | 0.90 | 0.29 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129031 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | PUMPS |  |  |  | GENERAL ARRANGEMENT DRAWING for PUMPS |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fgp¦pumps |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7413 | 0.9224 | 0.9224 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 4 | 273 | 18.4064 | 0.5545 | 0.0186 | 0.0140 | hybrid | structured_no_system |  | system_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129032 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE |  |  |  |  | DATA SHEET & CHARACTERISTIC CURVE |  | DATA SHEET & CHARACTERISTIC CURVE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0EF3520W00A01.2 | (FOSS) FO Forwarding Pump, FO Unloading Pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-04-02 | 2007-04-30 | procurement | procurement | match |  |  |  |  | fgp | query_unscoped | false | 9 | 50 | 13.5652 | 0.4962 | 0.0236 | 0.0177 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.64 | needs_review | rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129033 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - PUMP SECTIONAL DRAWING | PUMP SECTIONAL DRAWING | PUMPS |  |  |  | PUMP SECTIONAL DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.9013 | 0.9704 | 0.9704 | FA | 0CF3520W16A04 | (Transfer Pump) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > DFO Tank & Pump | 2007-10-31 | 2007-12-27 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | false | 63 | 55 | 12.7354 | 0.5949 | 0.0168 | 0.0126 | hybrid | structured_no_system |  | civil_design |  | 2024-12-26 | 2025-01-25 | 2025-02-24 | 2025-03-11 | 2025-03-26 | 2025-04-10 | generated | 0.90 | 0.61 | usable | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129034 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MECHANICAL SEAL SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | fgp |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | FA | 2PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | 2007-03-30 | 2008-02-28 | procurement | procurement | match |  |  |  |  | gtg | query_unscoped | false | 4 | 22 | 15.7901 | 0.5642 | 0.0278 | 0.0209 | hybrid | structured_no_system |  | procurement |  | 2024-04-13 | 2024-05-13 | 2024-06-12 | 2024-06-27 | 2024-07-12 | 2024-07-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129035 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE |  |  |  |  | DATA SHEET & CHARACTERISTIC CURVE |  | DATA SHEET & CHARACTERISTIC CURVE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0EF3520W00A01.2 | (FOSS) FO Forwarding Pump, FO Unloading Pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-04-02 | 2007-04-30 | procurement | procurement | match |  |  |  |  | fgp | query_unscoped | false | 10 | 35 | 13.5652 | 0.5015 | 0.0248 | 0.0186 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.64 | needs_review | rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129036 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | PUMPS |  |  |  | Instrument List for PUMPS |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | fgp¦pumps |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7164 | 0.6816 | 0.6816 | FI | 2PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-10-01 | 2008-06-02 | procurement | procurement | match |  |  |  |  | steam | query_unscoped | false | 77 | 2 | 13.0184 | 0.6200 | 0.0234 | 0.0176 | hybrid | structured_no_system |  | procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129037 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING | PUMPS |  |  |  | INSTRUMENTATION HOOK - UP DRAWING for PUMPS |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | fgp¦pumps |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8231 | 0.9469 | 0.9469 | FI | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 93 | 6 | 13.2098 | 0.6257 | 0.0217 | 0.0122 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.43 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129038 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - NAME PLATE DRAWING | DRAWING |  |  |  |  | DRAWING |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5955 | 0.8786 | 0.8786 | FI | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 393 | 55 | 7.4088 | 0.5847 | 0.0109 | 0.0061 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129050 | CHILLED WATER DISTRIBUTION PUMP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | PUMP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8856 | 0.9657 | 0.9657 | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | false | 3 | 18 | 21.0540 | 0.5535 | 0.0287 | 0.0215 | hybrid | structured_no_system |  | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129051 | CHILLED WATER DISTRIBUTION PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for PUMP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7387 | 0.9216 | 0.9216 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 69 | 708 | 13.9610 | 0.4652 | 0.0091 | 0.0068 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129053 | CHILLED WATER DISTRIBUTION PUMP - PUMP SECTIONAL DRAWING | PUMP SECTIONAL DRAWING | PUMP |  |  |  | PUMP SECTIONAL DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.9013 | 0.9704 | 0.9704 | FA | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 47 | 36 | 22.3341 | 0.5777 | 0.0198 | 0.0119 | hybrid | structured_no_system |  | civil_design |  | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129055 | CHILLED WATER DISTRIBUTION PUMP - MECHANICAL SEAL SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification for Pump |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4967 | 0.4990 | 0.4990 | FA | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 25 | 1 | 12.9248 | 0.6023 | 0.0282 | 0.0211 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129056 | CHILLED WATER DISTRIBUTION PUMP - NAME PLATE DRAWING | DRAWING |  |  |  |  | DRAWING for Pump |  | HRSG - Spec. & DraWing for Recirculation Pump | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | pump | hrsg¦pump | scoped | match | match | match | passed |  | 0.5000 | 0.5158 | 0.5047 | 0.5047 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible |  | hrsg | hrsg | rule | hrsg | match | false | 1 | 2 | 2.0974 | 0.4828 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129060 | CHILLED WATER DISTRIBUTION PUMP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE |  |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for Pump |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8909 | 0.9673 | 0.9673 | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | false | 2 | 17 | 17.1083 | 0.5426 | 0.0291 | 0.0218 | hybrid | structured_no_system |  | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129063 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | PUMP |  |  |  | Instrument List for PUMP |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7420 | 0.6893 | 0.6893 | FI | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 35 | 13 | 17.3579 | 0.5503 | 0.0242 | 0.0182 | hybrid | structured_no_system |  | procurement |  | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129064 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING | PUMP |  |  |  | INSTRUMENTATION HOOK - UP DRAWING for PUMP |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | pump |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8256 | 0.9477 | 0.9477 | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 14 | 9 | 29.4339 | 0.5765 | 0.0280 | 0.0126 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GCF-130001 | SYSTEM DESCRIPTION FOR WATER TREATMENT PLANT |  | Water Treatment Plant |  |  |  | for Water Treatment Plant | Water Treatment System | System Description for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | plant¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6000 | 0.6800 | 0.6240 | 0.6240 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 11 | 11 | 22.9842 | 0.6690 | 0.0282 | 0.0282 | hybrid | structured_blocked_procurement_conflict | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130002 | GENERAL ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | GENERAL ARRANGEMENT DRAWING | WATER TREATMENT PLANT |  |  |  | GENERAL ARRANGEMENT DRAWING for WATER TREATMENT PLANT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | plant¦treatment¦water¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6710 | 0.9013 | 0.9013 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 22.3170 | 0.6628 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GCF-130003 | PROCESS FLOW DIAGRAM FOR WATER TREATMENT PLANT | PROCESS FLOW DIAGRAM | WATER TREATMENT PLANT |  |  |  | PROCESS FLOW DIAGRAM for WATER TREATMENT PLANT | Water Treatment System | Process FloW Diagram & Mass Balance for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | plant¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7744 | 0.6990 | 0.6990 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 5 | 32.5080 | 0.6501 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GCF-130004 | PIPING & INSTRUMENT DIAGRAM FOR WATER TREATMENT PLANT | PIPING & INSTRUMENT DIAGRAM | WATER TREATMENT PLANT |  |  |  | PIPING & INSTRUMENT DIAGRAM for WATER TREATMENT PLANT |  | Piping & Instrument Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | plant¦treatment¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7592 | 0.9278 | 0.6494 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | wts |  | wts | query | wts | match | false | 1 | 1 | 35.5361 | 0.7717 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GCF-130005 | CALCULATION SHEET FOR WATER TREATMENT PLANT | CALCULATION SHEET | WATER TREATMENT PLANT |  |  |  | CALCULATION SHEET for WATER TREATMENT PLANT | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | plant¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8813 | 0.8477 | 0.8477 | FA | 0EF3010W16A01 | (WTS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-01-09 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 5 | 1 | 20.4729 | 0.5983 | 0.0318 | 0.0318 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130006 | MCC ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | ARRANGEMENT DRAWING | MCC ¦ Motor Control Center |  |  |  | General Arrangement Drawing for MCC ¦ Motor Control Center |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | center¦mcc¦motor¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6500 | 0.8950 | 0.8950 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 110 | 9 | 14.6840 | 0.5472 | 0.0204 | 0.0122 | hybrid | structured_phase_gap | mv_lv | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.46 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0GCF-130007 | CONTROL PANEL ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | ARRANGEMENT DRAWING |  |  |  |  | General Arrangement Drawing |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.9450 | 0.9835 | 0.9835 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 7 | 10 | 26.0298 | 0.5875 | 0.0292 | 0.0219 | hybrid | structured_no_system |  | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GCF-130008 | VALVE LIST FOR WATER TREATMENT PLANT | LIST | VALVE |  |  |  | Valve List for VALVE |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | valve¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.9375 | 0.7479 | 0.7479 | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 2 | 4 | 29.3466 | 0.6012 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | procurement |  | 2024-12-17 | 2025-01-16 | 2025-02-15 | 2025-03-02 | 2025-03-17 | 2025-04-01 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GCF-130009 | INSTRUMENT LIST FOR WATER TREATMENT PLANT | LIST | INSTRUMENT |  |  |  | Instrument List for INSTRUMENT |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | instrument¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8087 | 0.7093 | 0.7093 | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match |  |  |  |  | wts | query_unscoped | false | 10 | 1 | 18.3982 | 0.6618 | 0.0307 | 0.0230 | hybrid | structured_no_system |  | procurement |  | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0GCF-130010 | SINGLE LINE DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 4 | 2 | 28.6128 | 0.6524 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0GCF-130011 | CONTROL CONFIGURATION DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | DIAGRAM |  |  |  |  | Diagram | Water Treatment System | Control Configuration Diagram for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | diagram | diagram | wts | wts | scoped | match | match | match | passed |  | 0.8571 | 0.8322 | 0.8496 | 0.8496 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 3 | 1 | 28.6128 | 0.6540 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.90 | usable | default_fc_window;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GCF-130012 | EQUIPMENT ASSEMBLY DRAWING FOR WATER TREATMENT PLANT | ASSEMBLY DRAWING |  |  |  |  | ASSEMBLY DRAWING |  | EQUIPMENT ASSEMBLY DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7855 | 0.9357 | 0.6550 | FA | 0EF3010W16A01 | (WTS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-01-09 | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 27 | 2 | 10.2365 | 0.6018 | 0.0276 | 0.0155 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0GCF-130013 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | ARRANGEMENT DRAWING |  | PIPING |  |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 48 | 1 | 17.6675 | 0.6974 | 0.0257 | 0.0192 | hybrid | structured_no_system |  | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GCF-130014 | TEHCNICAL DATA SHEET FOR WATER TREATMENT PLANT | TEHCNICAL DATA SHEET |  |  |  |  | TEHCNICAL DATA SHEET | Water Treatment System | Pump Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | datasheet | datasheet | data_sheet | data_sheet | wts | pump¦wts | scoped | match | match | match | passed |  | 0.7143 | 0.7406 | 0.7222 | 0.7222 | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match |  | wts | wts | rule | wts | match | false | 3 | 1 | 18.3982 | 0.6711 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.90 | usable | default_fc_window;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0GCF-130015 | CABLE TRAY LAYOUT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | LAYOUT DRAWING | CABLE TRAY |  |  |  | Layout Drawing for CABLE TRAY | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | drawing | drawing | layout_drawing | layout_drawing | cable¦tray¦wts | wts | scoped | match | match | match | passed |  | 0.8750 | 0.8645 | 0.8718 | 0.8718 | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible |  | wts | wts | rule | wts | match | false | 3 | 9 | 26.0298 | 0.5598 | 0.0304 | 0.0228 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GCF-130016 | HOOK - UP DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | HOOK - UP DRAWING |  |  |  |  | HOOK - UP DRAWING |  | Instruments Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | wts |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7626 | 0.7538 | 0.7538 | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible |  |  |  |  | wts | query_unscoped | false | 8 | 5 | 26.0298 | 0.6025 | 0.0301 | 0.0169 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.43 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0GCF-130017 | SCHEMATIC AND WIRING DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | SCHEMATIC AND WIRING DIAGRAM |  |  |  |  | SCHEMATIC AND WIRING DIAGRAM | Water Treatment System | Interconnection Wiring Diagram for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | diagram | diagram | wiring_diagram | wiring_diagram | wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.7417 | 0.7225 | 0.7225 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 2 | 1 | 33.6515 | 0.6558 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 0.90 | usable | default_fc_window;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0GCF-130018 | CONTROL LOOP & LOGIC DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | DIAGRAM |  |  |  |  | Control Loop Diagram | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | wts |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8073 | 0.7672 | 0.7672 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 3 | 1 | 28.6128 | 0.6015 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130019 | SLEEVE AND WALL OPENING FOR WATER AND WASTE WATER TREATMENT PLANT | [6 empty] | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL OPENING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | title | plan | plan | plan | plan | wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7382 | 0.6881 | 0.6881 | FI | 2CF4035W58A01 | (WWTS) Piping Work(Block #2) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Waste Water Treatment System (BOP) | 2008-10-17 | 2009-01-15 |  |  | query_unknown |  | wts | wts | rule | bop¦wts | match | false | 15 | 8 | 22.9536 | 0.5516 | 0.0280 | 0.0210 | hybrid | structured_no_phase | wts | [5 empty] | 2026-01-16 | 2026-02-15 | 2026-03-17 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0GCF-130035 | PLC IO LIST FOR WATER AND WASTE WATER TREATMENT PLANT | LIST |  |  |  |  | I/O List | Water Treatment System | PLC I/O List for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | list | list | io_list | io_list | wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8963 | 0.8522 | 0.8522 | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match |  | wts | wts | rule | wts | match | false | 1 | 2 | 29.6627 | 0.6469 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 | 0.90 | usable | default_fc_window;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GCF-130042 | FOUNDATION AND LOADING DATA FOR WATER AND WASTE WATER TREATMENT PLANT | DATA |  |  |  |  | DATA | FireFighting | Foundation Plan and Loading Data | 1 | start+16W<=FA<=FC<=start+24W | FA ∈ [start+112d, start+168d] ¦ FC ∈ [start+112d, start+168d] | title | plan | plan | plan | plan | wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6455 | 0.6603 | 0.6603 | FA | 0EF5535W00A15.1 | (WWT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 2 | 6 | 30.1915 | 0.5994 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  | 2024-12-24 | 2025-01-21 | 2025-02-18 | 2025-02-11 | 2025-03-11 | 2025-04-08 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0GCF-130055 | PIPING MATERIAL CLASSIFICATION FOR WATER AND WASTE WATER TREATMENT PLANT |  |  | WATER AND WASTE WATER TREATMENT PLANT |  |  | for WATER AND WASTE WATER TREATMENT PLANT |  | Water Treatment Plant | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7589 | 0.9277 | 0.6494 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 3 | 3 | 50.1701 | 0.6424 | 0.0317 | 0.0317 | hybrid | structured_cell_found_text_preferred | wts | system_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GNR-130101 | SYSTEM DESCRIPTION FOR WASTE WATER TREATMENT PLANT | SYSTEM DESCRIPTION |  | WASTE WATER TREATMENT PLANT |  |  | System Description for WASTE WATER TREATMENT PLANT | Water Treatment System | System Description for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7934 | 0.9380 | 0.9380 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 44.8597 | 0.7226 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GNR-130102 | PROCESS FLOW DIAGRAM FOR WASTE WATER TREATMENT PLANT | PROCESS FLOW DIAGRAM |  | WASTE WATER TREATMENT PLANT |  |  | PROCESS FLOW DIAGRAM for WASTE WATER TREATMENT PLANT | Water Treatment System | Process FloW Diagram & Mass Balance for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7310 | 0.6860 | 0.6860 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 4 | 47.7182 | 0.6434 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GNR-130103 | PIPING & INSTRUMENT DIAGRAM FOR WASTE WATER TREATMENT PLANT | PIPING & INSTRUMENT DIAGRAM |  | WASTE WATER TREATMENT PLANT |  |  | PIPING & INSTRUMENT DIAGRAM for WASTE WATER TREATMENT PLANT |  | Piping & Instrument Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | plant¦treatment¦waste¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7424 | 0.9227 | 0.6459 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts |  | wts | query | wts | match | false | 1 | 1 | 50.6272 | 0.7676 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GNR-130104 | CALCULATION SHEET FOR WASTE WATER TREATMENT PLANT | CALCULATION SHEET |  | WASTE WATER TREATMENT PLANT |  |  | CALCULATION SHEET for WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT PLANT | CALCULATION OF WASTE WATER TREATMENT PLANT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8768 | 0.8464 | 0.8464 | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 8 | 1 | 35.9876 | 0.5790 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GNR-130105 | VALVE LIST FOR WASTE WATER TREATMENT PLANT | VALVE LIST |  | WASTE WATER TREATMENT PLANT |  |  | Valve List for WASTE WATER TREATMENT PLANT |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | plant¦treatment¦waste¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7069 | 0.6787 | 0.6787 | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts |  | wts | query | wts | match | false | 1 | 1 | 44.2306 | 0.6628 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-11-26 | 2024-12-26 | 2025-01-25 | 2025-02-09 | 2025-02-24 | 2025-03-11 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GNR-130106 | INSTRUMENT LIST FOR WASTE WATER TREATMENT PLANT | INSTRUMENT LIST |  | WASTE WATER TREATMENT PLANT |  |  | Instrument List for WASTE WATER TREATMENT PLANT | Water Treatment System | Instrument List & Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | list | list | instrument_list | instrument_list | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6250 | 0.7702 | 0.6685 | 0.6685 | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 44.2306 | 0.6822 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GNR-130107 | EQUIPMENT ASSEMBLY DRAWING FOR WASTE WATER TREATMENT PLANT | ASSEMBLY DRAWING |  | WASTE WATER TREATMENT PLANT |  |  | ASSEMBLY DRAWING for WASTE WATER TREATMENT PLANT | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.7104 | 0.6131 | 0.6131 | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | false | 5 | 2 | 37.9279 | 0.6432 | 0.0315 | 0.0236 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GNR-130108 | TEHCNICAL DATA SHEET FOR WASTE WATER TREATMENT PLANT | TEHCNICAL DATA SHEET |  | WASTE WATER TREATMENT PLANT |  |  | TEHCNICAL DATA SHEET for WASTE WATER TREATMENT PLANT | Water Treatment System | Pump Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | plant¦treatment¦waste¦water¦wts | pump¦wts | scoped | match | match | match | passed |  | 0.7143 | 0.6924 | 0.7077 | 0.7077 | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | false | 3 | 1 | 44.2306 | 0.6946 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LD-130201 | SYSTEM DESCRIPTION FOR CONDENSATE POLISHING PLANT | SYSTEM DESCRIPTION |  | CONDENSATE POLISHING PLANT |  |  | System Description for CONDENSATE POLISHING PLANT |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | title | description | description | system_description | system_description | condensate¦plant¦polishing |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5207 | 0.6229 | 0.5294 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 21.1313 | 0.6932 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦procurement |  | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LD-130202 | GENERAL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | GENERAL ARRANGEMENT DRAWING |  | CONDENSATE POLISHING PLANT |  |  | GENERAL ARRANGEMENT DRAWING for CONDENSATE POLISHING PLANT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | condensate¦plant¦polishing |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6365 | 0.8910 | 0.8910 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 14.3814 | 0.5840 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0LD-130203 | PROCESS FLOW DIAGRAM FOR CONDENSATE POLISHING PLANT | PROCESS FLOW DIAGRAM |  | CONDENSATE POLISHING PLANT |  |  | PROCESS FLOW DIAGRAM for CONDENSATE POLISHING PLANT | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | rule_query | diagram | diagram | diagram | diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5430 | 0.5129 | 0.5129 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 23.9460 | 0.6078 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design¦engineering | 1 | 2024-04-16 | 2024-05-21 | 2024-06-25 | 2024-06-11 | 2024-07-16 | 2024-08-20 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LD-130204 | PIPING & INSTRUMENT DIAGRAM FOR CONDENSATE POLISHING PLANT | PIPING & INSTRUMENT DIAGRAM |  | CONDENSATE POLISHING PLANT |  |  | PIPING & INSTRUMENT DIAGRAM for CONDENSATE POLISHING PLANT |  | Piping & Instrument Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7279 | 0.9184 | 0.6429 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 26.7880 | 0.6903 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LD-130205 | CALCULATION SHEET FOR CONDENSATE POLISHING PLANT | CALCULATION SHEET |  | CONDENSATE POLISHING PLANT |  |  | CALCULATION SHEET for CONDENSATE POLISHING PLANT |  | Chlorination Plant Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5518 | 0.5156 | 0.5156 | FA | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 11 | 1 | 12.6306 | 0.5021 | 0.0305 | 0.0305 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LD-130206 | MCC ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | ARRANGEMENT DRAWING | MCC ¦ Motor Control Center | CONDENSATE POLISHING PLANT |  |  | General Arrangement Drawing for MCC ¦ Motor Control Center |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | center¦mcc¦motor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6500 | 0.8950 | 0.8950 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate¦mv_lv |  | condensate¦mv_lv | query | condensate | match | false | 1 | 1 | 14.3814 | 0.5289 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦mv_lv | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0LD-130207 | CONTROL PANEL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | ARRANGEMENT DRAWING |  | CONDENSATE POLISHING PLANT |  |  | General Arrangement Drawing for CONDENSATE POLISHING PLANT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | condensate¦plant¦polishing |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6658 | 0.8998 | 0.8998 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 14.3814 | 0.5941 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LD-130208 | VALVE LIST FOR CONDENSATE POLISHING PLANT | VALVE LIST |  | CONDENSATE POLISHING PLANT |  |  | Valve List for CONDENSATE POLISHING PLANT |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6922 | 0.6743 | 0.6743 | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 1 | 5 | 21.6012 | 0.6095 | 0.0318 | 0.0318 | hybrid | structured_preferred | condensate | procurement | 10 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LD-130209 | INSTRUMENT LIST FOR CONDENSATE POLISHING PLANT | INSTRUMENT LIST |  | CONDENSATE POLISHING PLANT |  |  | Instrument List for CONDENSATE POLISHING PLANT |  | Instrument List | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | list | list | instrument_list | instrument_list | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5988 | 0.6463 | 0.6463 | FA | 2PF3020W42A20P | (COND) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-29 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | false | 12 | 1 | 20.4139 | 0.6468 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0LD-130210 | SINGLE LINE DIAGRAM FOR CONDENSATE POLISHING PLANT | SINGLE LINE DIAGRAM |  | CONDENSATE POLISHING PLANT |  |  | Single Line Diagram for CONDENSATE POLISHING PLANT |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6848 | 0.9054 | 0.9054 | SKIP | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 2 | 5 | 23.9460 | 0.6279 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0LD-130211 | CONTROL CONFIGURATION DIAGRAM FOR CONDENSATE POLISHING PLANT | CONTROL CONFIGURATION DIAGRAM |  | CONDENSATE POLISHING PLANT |  |  | CONTROL CONFIGURATION DIAGRAM for CONDENSATE POLISHING PLANT |  | CONTROL CONFIGURATION DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6780 | 0.9034 | 0.6324 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 21.7680 | 0.6001 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LD-130212 | EQUIPMENT ASSEMBLY DRAWING FOR CONDENSATE POLISHING PLANT | EQUIPMENT ASSEMBLY DRAWING |  |  |  |  | EQUIPMENT ASSEMBLY DRAWING |  | EQUIPMENT ASSEMBLY DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible |  |  |  |  | acc¦condensate | query_unscoped | false | 9 | 11 | 11.3628 | 0.5630 | 0.0286 | 0.0161 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LD-130213 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | ARRANGEMENT DRAWING |  | PIPING |  |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match |  |  |  |  | condensate | query_unscoped | false | 69 | 8 | 13.2997 | 0.6336 | 0.0225 | 0.0168 | hybrid | structured_no_system |  | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LD-130214 | TECHNICAL DATA SHEET FOR CONDENSATE POLISHING PLANT | TECHNICAL DATA SHEET |  |  |  |  | TECHNICAL DATA SHEET |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | specification | technical_data_sheet | technical_specification |  |  | scoped | compatible | not_applicable | query_unscoped | passed |  | 0.6000 | 0.6577 | 0.6173 | 0.6173 | FA | 2PF3020W42A20P | (COND) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-29 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | 14 | 1 | 14.1534 | 0.6404 | 0.0299 | 0.0224 | hybrid | structured_no_system |  | procurement |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 0.43 | needs_review | default_fc_window;rule_family_status=compatible;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0LD-130215 | CABLE TRAY LAYOUT DRAWING FOR CONDENSATE POLISHING PLANT | LAYOUT DRAWING | CABLE TRAY |  |  |  | Layout Drawing for CABLE TRAY | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | cable¦tray |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7577 | 0.6940 | 0.6940 | SKIP | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible |  |  |  |  | condensate | query_unscoped | false | 117 | 6 | 8.2797 | 0.5527 | 0.0208 | 0.0117 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LD-130216 | HOOK - UP DRAWING FOR CONDENSATE POLISHING PLANT | HOOK - UP DRAWING |  |  |  |  | HOOK - UP DRAWING |  | Instruments Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7626 | 0.7538 | 0.7538 | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 3 | 19 | 20.4005 | 0.5479 | 0.0285 | 0.0128 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 0.35 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0LD-130217 | SCHEMATIC & WIRING DIAGRAM FOR CONDENSATE POLISHING PLANT | SCHEMATIC & WIRING DIAGRAM |  |  |  |  | SCHEMATIC & WIRING DIAGRAM |  | ACC - Wiring Diagram | 1 | start+289D<=FA<=start+289D+2M | FA ∈ [start+289d, start+349d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram |  | acc | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6455 | 0.6603 | 0.6603 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | 4 | 26 | 14.8841 | 0.5605 | 0.0273 | 0.0082 | hybrid | structured_phase_gap | acc | system_design¦engineering |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.23 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=activity_unscoped;activity_rule_scope_unmatched;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LD-130218 | CONTROL LOOP & LOGIC DIAGRAM FOR CONDENSATE POLISHING PLANT | CONTROL LOOP & LOGIC DIAGRAM |  |  |  |  | Control Loop Diagram | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8073 | 0.7672 | 0.7672 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match |  |  |  |  | condensate | query_unscoped | false | 5 | 4 | 17.8443 | 0.5922 | 0.0310 | 0.0233 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0LD-130219 | PIPING MATERIAL SPECIFICATION FOR CONDENSATE POLISHING PLANT | MATERIAL SPECIFICATION |  | PIPING |  |  | MATERIAL SPECIFICATION for PIPING | FireFighting | Piping Material Specification | 1 | start+4W<=FA<=FC<=start+12W | FA ∈ [start+28d, start+84d] ¦ FC ∈ [start+28d, start+84d] | rule_query | specification | specification | specification | specification | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7302 | 0.7441 | 0.7441 | FA | 0EF6020W58A01 | (Piping) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 1 | 36.0206 | 0.7001 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-08-27 | 2024-09-24 | 2024-10-22 | 2024-10-15 | 2024-11-12 | 2024-12-10 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LD-130220 | FOUNDATION AND LOADING DATA FOR CONDENSATE POLISHING PLANT | DATA |  |  |  |  | DATA | FireFighting | Foundation Plan and Loading Data | 1 | start+16W<=FA<=FC<=start+24W | FA ∈ [start+112d, start+168d] ¦ FC ∈ [start+112d, start+168d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.5665 | 0.6366 | 0.6366 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 31 | 320 | 12.4837 | 0.4837 | 0.0136 | 0.0102 | hybrid | structured_no_system |  | civil_design |  | 2024-07-20 | 2024-08-17 | 2024-09-14 | 2024-09-07 | 2024-10-05 | 2024-11-02 | generated | 0.90 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YM03-P0LD-130221 | INSTRUMENT LOCATION DRAWING FOR CONDENSATE POLISHING PLANT | LOCATION DRAWING |  | INSTRUMENT |  |  | LOCATION DRAWING for INSTRUMENT |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | instrument |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6713 | 0.6681 | 0.6681 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible |  |  |  |  | condensate | query_unscoped | false | 96 | 4 | 8.2797 | 0.5998 | 0.0220 | 0.0124 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.43 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QC-130301 | SYSTEM DESCRIPTION FOR CHEMICAL DOSING SYSTEM | SYSTEM DESCRIPTION |  | CHEMICAL DOSING SYSTEM |  |  | System Description for CHEMICAL DOSING SYSTEM | Chemical Dosing System | System Description | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9489 | 0.9847 | 0.9847 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 40.3327 | 0.8290 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QC-130302 | GENERAL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | GENERAL ARRANGEMENT DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for CHEMICAL DOSING SYSTEM | Chemical Dosing System | General Arrangement DraWing | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9342 | 0.9803 | 0.9803 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 33.6657 | 0.7599 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QC-130303 | PIPING & INSTRUMENT DIAGRAM FOR CHEMICAL DOSING SYSTEM | PIPING & INSTRUMENT DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | PIPING & INSTRUMENT DIAGRAM for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Control Configuration Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7569 | 0.6937 | 0.6937 | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | false | 1 | 1 | 48.0296 | 0.8466 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0QC-130304 | CALCULATION SHEET FOR CHEMICAL DOSING SYSTEM | CALCULATION SHEET |  | CHEMICAL DOSING SYSTEM |  |  | CALCULATION SHEET for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Calculation Sheet | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9523 | 0.9857 | 0.9857 | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 2 | 1 | 31.8262 | 0.6463 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0QC-130305 | INSTRUMENT LIST FOR CHEMICAL DOSING SYSTEM | INSTRUMENT LIST |  | CHEMICAL DOSING SYSTEM |  |  | Instrument List for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Instrument List and Data Sheet | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | list | list | instrument_list | instrument_list | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.8763 | 0.7004 | 0.7004 | FI | 2PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-08-25 | procurement | procurement | match | wts | wts | wts | query | wts | match | false | 2 | 1 | 39.2774 | 0.7887 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0QC-130306 | CONTROL PANEL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | ARRANGEMENT DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | General Arrangement Drawing for CHEMICAL DOSING SYSTEM | Chemical Dosing System | General Arrangement DraWing | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9436 | 0.9831 | 0.9831 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 33.6657 | 0.7582 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QC-130307 | TECHNICAL DATA SHEET FOR CHEMICAL DOSING SYSTEM | TECHNICAL DATA SHEET |  | CHEMICAL DOSING SYSTEM |  |  | TECHNICAL DATA SHEET for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Technical Data Sheet | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | datasheet | datasheet | technical_data_sheet | technical_data_sheet | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9253 | 0.9776 | 0.9776 | FA | 2PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-08-25 | procurement | procurement | match | wts | wts | wts | query | wts | match | false | 5 | 1 | 39.2774 | 0.7775 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0QC-130308 | SCHEMATIC & WIRING DIAGRAM FOR CHEMICAL DOSING SYSTEM | SCHEMATIC & WIRING DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | SCHEMATIC & WIRING DIAGRAM for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Interconnection Wiring Diagram | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8379 | 0.8347 | 0.8347 | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 43.0856 | 0.7730 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0QC-130309 | CONTROL LOOP & LOGIC DIAGRAM FOR CHEMICAL DOSING SYSTEM | CONTROL LOOP & LOGIC DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | Control Loop Diagram for CHEMICAL DOSING SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7293 | 0.7438 | 0.7438 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 4 | 43.0856 | 0.7331 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QU-130401 | SYSTEM DESCRIPTION FOR SAMPLING SYSTEM | SYSTEM DESCRIPTION |  | SAMPLING SYSTEM |  |  | System Description for SAMPLING SYSTEM | Sampling System | System Description for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | description | description | system_description | system_description | sampling |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7375 | 0.5712 | 0.5712 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling | sampling | sampling | query | sampling | match | false | 1 | 1 | 27.5345 | 0.8105 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QU-130402 | GENERAL ARRANGEMENT DRAWING FOR SAMPLING SYSTEM | GENERAL ARRANGEMENT DRAWING |  | SAMPLING SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for SAMPLING SYSTEM |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | sampling |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7090 | 0.9127 | 0.9127 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | false | 6 | 1 | 20.6995 | 0.7191 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | sampling | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QU-130403 | PIPING & INSTRUMENT DIAGRAM FOR SAMPLING SYSTEM | PIPING & INSTRUMENT DIAGRAM |  | SAMPLING SYSTEM |  |  | PIPING & INSTRUMENT DIAGRAM for SAMPLING SYSTEM |  | Piping & Instrument Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | sampling |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7544 | 0.9263 | 0.6484 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | design_drawing | system_design | compatible | sampling |  | sampling | query | sampling | match | false | 1 | 1 | 33.2997 | 0.8257 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0QU-130404 | INSTRUMENT LIST FOR SAMPLING SYSTEM | LIST |  | SAMPLING SYSTEM |  |  | Instrument List for SAMPLING SYSTEM |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | sampling |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7034 | 0.6777 | 0.6777 | FI | 3PF3040W42A05P | (Sampling Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | 2007-10-01 | 2008-09-30 | procurement | procurement | match | sampling |  | sampling | query | sampling | match | false | 4 | 1 | 26.2910 | 0.7264 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | sampling | procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QU-130405 | TECHNICAL DATA SHEET FOR SAMPLING SYSTEM | TECHNICAL DATA SHEET |  | SAMPLING SYSTEM |  |  | TECHNICAL DATA SHEET for SAMPLING SYSTEM | Intake Screening System | Technical Data Sheet | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | datasheet | datasheet | technical_data_sheet | technical_data_sheet | sampling |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6685 | 0.6672 | 0.6672 | FA | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-10-01 | 2008-07-30 | procurement | procurement | match | sampling |  | sampling | query | sampling | match | false | 1 | 3 | 26.2910 | 0.7138 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | sampling | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0QU-130406 | SCHEMATIC & WIRING DIAGRAM FOR SAMPLING SYSTEM | SCHEMATIC & WIRING DIAGRAM |  | SAMPLING SYSTEM |  |  | SCHEMATIC & WIRING DIAGRAM for SAMPLING SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | sampling |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5692 | 0.6374 | 0.6374 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | false | 1 | 1 | 30.4134 | 0.7184 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0QU-130407 | CONTROL LOOP & LOGIC DIAGRAM FOR SAMPLING SYSTEM | CONTROL LOOP & LOGIC DIAGRAM |  | SAMPLING SYSTEM |  |  | Control Loop Diagram for SAMPLING SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | sampling |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7233 | 0.7420 | 0.7420 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | false | 1 | 1 | 30.4134 | 0.6533 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0STG-130501 | EQUIPMENT SPECIFICATION FOR CHEMICAL LABORATORY | EQUIPMENT SPECIFICATION | CHEMICAL LABORATORY |  |  |  | EQUIPMENT SPECIFICATION for CHEMICAL LABORATORY | Chemical Dosing System | Piping Material Specification | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | title | specification | specification | specification | specification | chemical¦laboratory |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5168 | 0.3884 | 0.3884 | FI | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | procurement | procurement | match | lab | wts | lab | query | lab | match | false | 1 | 4 | 37.8834 | 0.6092 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | lab | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0STG-130502 | ARRANGEMENT DRAWING FOR CHEMICAL LABORATORY EQUIPMENT | ARRANGEMENT DRAWING | CHEMICAL LABORATORY EQUIPMENT |  |  |  | General Arrangement Drawing for CHEMICAL LABORATORY EQUIPMENT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chemical¦laboratory |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6765 | 0.9029 | 0.9029 | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | lab |  | lab | query |  | activity_unscoped | true | 1230 | 21 | 2.3206 | 0.4997 | 0.0131 | 0.0079 | hybrid | structured_phase_gap | lab | system_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0STG-130503 | EQUIPMENT LIST FOR CHEMICAL LABORATORY | EQUIPMENT LIST | CHEMICAL LABORATORY |  |  |  | Equipment List for CHEMICAL LABORATORY | Chemical Laboratory Equipment | Equipment List & Specification for Chemical Laboratory Equipment | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | list | list | equipment_list | equipment_list | chemical¦laboratory |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8158 | 0.8281 | 0.8281 | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | procurement | procurement | match | lab | lab | lab | query | lab | match | false | 1 | 4 | 37.8834 | 0.6060 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | lab | procurement |  | 2025-05-01 | 2025-05-31 | 2025-06-30 | 2025-07-15 | 2025-07-30 | 2025-08-14 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GK-130601 | GENERAL ARRANGEMENT DRAWING FOR POTABLE WATER CHILLER | GENERAL ARRANGEMENT DRAWING | POTABLE WATER CHILLER |  |  |  | GENERAL ARRANGEMENT DRAWING for POTABLE WATER CHILLER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chiller¦potable¦water |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6462 | 0.8939 | 0.8939 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 3 | 4 | 27.6111 | 0.5781 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | wts | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0GK-130602 | ELECTRICAL DRAWING FOR POTABLE WATER CHILLER | DRAWING | POTABLE WATER CHILLER |  |  |  | DRAWING for POTABLE WATER CHILLER |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | chiller¦potable¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5408 | 0.8622 | 0.6036 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | wts | electrical | wts | query | wts | match | false | 1 | 1 | 25.2904 | 0.5337 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SAA-133301 | DESIGN CRITERIA FOR HVAC SYSTEM | DESIGN CRITERIA |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  |  | DESIGN CRITERIA for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | Intake Screening System | Design Criteria | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | criteria | criteria | design_criteria | design_criteria | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5274 | 0.5782 | 0.5782 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_criteria | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 2 | 2 | 51.5486 | 0.5884 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | hvac | design_criteria¦system_design¦civil_design |  | 2024-04-13 | 2024-05-13 | 2024-06-12 | 2024-06-27 | 2024-07-12 | 2024-07-27 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SAA-133302 | STANDARD DRAIWNG FOR HVAC SYSTEM | STANDARD DRAIWNG |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  |  | STANDARD DRAIWNG for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | [5 empty] | rule_query | other | model | standard_draiwng | model | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.4939 | 0.4982 | 0.4982 |  | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 4 | 1 | 42.2730 | 0.6755 | 0.0320 | 0.0240 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAH-133401 | LOAD CALCULATION OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | STEAM TURBINE BUILDING |  | Calculation sheet for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦stg¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6125 | 0.6504 | 0.6504 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | hvac¦stg |  | hvac¦stg | query | stg | match | false | 10 | 4 | 12.8861 | 0.5387 | 0.0299 | 0.0299 | hybrid | structured_preferred | hvac¦stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAH-133402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | STEAM TURBINE BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦stg¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac¦stg |  | hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 23 | 4 | 33.9935 | 0.5821 | 0.0277 | 0.0138 | hybrid | structured_cell_found_text_preferred | hvac¦stg | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAH-133403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR STEAM TURBINE BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | STEAM TURBINE BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦stg¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6400 | 0.6120 | 0.6120 | FI | 1CF2010W36A10 | (STG #10 BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-10-13 | 2008-12-08 |  | commissioning | query_unknown | hvac¦stg |  | hvac¦stg | query | hvac¦stg | match | false | 16 | 5 | 32.6850 | 0.5997 | 0.0285 | 0.0214 | hybrid | structured_no_phase | hvac¦stg | [5 empty] | 2025-07-16 | 2025-08-15 | 2025-09-14 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAH-133404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSEM FOR STEAM TURBINE BUILDING | PLAN |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | STEAM TURBINE BUILDING |  | Plan for STEAM TURBINE BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5959 | 0.5288 | 0.5288 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac¦stg | stg | hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 1 | 1 | 42.7435 | 0.6762 | 0.0328 | 0.0123 | hybrid | structured_no_phase | hvac¦stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAC-133501 | LOAD CALCULATION OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CENTRAL CONTROL BUILDING |  | Calculation sheet for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦ccr¦central¦conditioning¦heating¦hvac¦ventilating | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.7933 | 0.9380 | 0.9380 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 32.8497 | 0.6107 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAC-133502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CENTRAL CONTROL BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦ccr¦central¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 20 | 3 | 33.9935 | 0.6097 | 0.0284 | 0.0284 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAC-133503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CENTRAL CONTROL BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | CENTRAL CONTROL BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦ccr¦central¦conditioning¦heating¦hvac¦sysem¦ventilating | ccr | scoped | match | match | match | passed |  | 0.8333 | 0.7829 | 0.8182 | 0.8182 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | false | 1 | 1 | 53.3027 | 0.6510 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAC-133504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | false | 1 | 2 | 45.8997 | 0.6394 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAK-133601 | LOAD CALCULATION OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WATER TREATMENT BUILDING |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7738 | 0.9321 | 0.9321 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | hvac¦wts | wts | hvac¦wts | query | wts | match | false | 10 | 2 | 26.4445 | 0.5759 | 0.0304 | 0.0304 | hybrid | structured_preferred | hvac¦wts | civil_design | 10 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAK-133602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WATER TREATMENT BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | Water Treatment System | Control Configuration Diagram for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.6331 | 0.6899 | 0.6899 | FI | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac¦wts | wts | hvac¦wts | query | fire_fighting¦hvac | discipline_only | false | 26 | 10 | 33.9935 | 0.6094 | 0.0259 | 0.0130 | hybrid | structured_cell_found_text_preferred | hvac¦wts | system_design¦engineering |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | 2024-11-20 | 2024-12-05 | 2024-12-20 | generated | 0.90 | 0.45 | needs_review | default_fc_window;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAK-133603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WATER TREATMENT BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | WATER TREATMENT BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8262 | 0.8312 | 0.8312 | FI | 0CF5534W36A07 | (DWP BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-15 |  | commissioning | query_unknown | hvac¦wts | wts | hvac¦wts | query | hvac¦wts | match | false | 9 | 4 | 38.2100 | 0.6460 | 0.0301 | 0.0226 | hybrid | structured_no_phase | hvac¦wts | [5 empty] | 2025-04-03 | 2025-05-03 | 2025-06-02 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAK-133604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0CF5534W36A07 | (DWP BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-15 |  | commissioning | query_unknown | hvac¦wts | wts | hvac¦wts | query | hvac¦wts | match | false | 7 | 2 | 39.9400 | 0.6782 | 0.0311 | 0.0233 | hybrid | structured_no_phase | hvac¦wts | [5 empty] | 2025-09-30 | 2025-10-30 | 2025-11-29 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAJ-133701 | LOAD CALCULATION OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦fgp¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7715 | 0.9315 | 0.9315 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp¦hvac | electrical | electrical¦fgp¦hvac | query | fgp | match | false | 9 | 6 | 21.2880 | 0.5297 | 0.0296 | 0.0296 | hybrid | structured_preferred | electrical¦fgp¦hvac | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAJ-133702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦fgp¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fgp¦hvac |  | electrical¦fgp¦hvac | query | fire_fighting¦hvac | discipline_only | false | 21 | 2 | 33.9935 | 0.6345 | 0.0285 | 0.0142 | hybrid | structured_cell_found_text_preferred | electrical¦fgp¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAJ-133703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FGS ELECTRICAL BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦fgp¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6433 | 0.6130 | 0.6130 | FI | 0CF3520W36A07.1 | (FGS LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-15 | 2008-07-11 |  | commissioning | query_unknown | electrical¦fgp¦hvac |  | electrical¦fgp¦hvac | query | fgp¦hvac | match | false | 16 | 18 | 33.0336 | 0.5864 | 0.0260 | 0.0195 | hybrid | structured_no_phase | electrical¦fgp¦hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAJ-133704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Plan for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7435 | 0.9230 | 0.6461 | FA | 0CF3520W36A07.1 | (FGS LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-15 | 2008-07-11 |  | commissioning | query_unknown | electrical¦fgp¦hvac |  | electrical¦fgp¦hvac | query | fgp¦hvac | match | false | 8 | 14 | 34.8011 | 0.6026 | 0.0282 | 0.0212 | hybrid | structured_no_phase | electrical¦fgp¦hvac |  |  | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133801 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #1/2 LEB | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | GTG #1/2 LEB ¦ Gas Turbine Generator #1/2 Local Electrical Building |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦gtg¦heating¦hvac¦leb¦local¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.6932 | 0.9080 | 0.9080 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg¦hvac | gtg | electrical¦gtg¦hvac | query | gtg | match | false | 9 | 1 | 17.6643 | 0.6031 | 0.0309 | 0.0309 | hybrid | structured_preferred | electrical¦gtg¦hvac | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAI-133802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #1/2 LEB | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | GTG #1/2 LEB ¦ Gas Turbine Generator #1/2 Local Electrical Building |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦gtg¦heating¦hvac¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | gtg | match | false | 684 | 61 | 8.7678 | 0.5521 | 0.0096 | 0.0096 | hybrid | structured_cell_found_text_preferred | electrical¦gtg¦hvac | system_design¦engineering | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #1/2 LEB | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | GTG #1/2 LEB ¦ Gas Turbine Generator #1/2 Local Electrical Building |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦gtg¦heating¦hvac¦leb¦local¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.8000 | 0.7222 | 0.7767 | 0.7767 | FI | 2CF1200W36A07 | (GTG #21 LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-15 | 2008-06-30 |  | commissioning | query_unknown | electrical¦gtg¦hvac | gtg | electrical¦gtg¦hvac | query | gtg¦hvac | match | false | 19 | 1 | 30.7733 | 0.6595 | 0.0291 | 0.0218 | hybrid | structured_no_phase | electrical¦gtg¦hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAI-133804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #1/2 LEB | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | GTG #1/2 LEB ¦ Gas Turbine Generator #1/2 Local Electrical Building |  | Plan for GTG #1/2 LEB ¦ Gas Turbine Generator #1/2 Local Electrical Building |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7564 | 0.9269 | 0.6489 | FA | 2CF1200W36A07 | (GTG #21 LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-15 | 2008-06-30 |  | commissioning | query_unknown | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | gtg¦hvac | match | false | 8 | 3 | 30.7730 | 0.6212 | 0.0306 | 0.0229 | hybrid | structured_no_phase | electrical¦gtg¦hvac |  |  | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133901 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #3/4/5 LEB | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | GTG #3/4/5 LEB ¦ Gas Turbine Generator #3/4/5 Local Electrical Building |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦gtg¦heating¦hvac¦leb¦local¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.6878 | 0.9063 | 0.9063 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg¦hvac | gtg | electrical¦gtg¦hvac | query | gtg | match | false | 9 | 3 | 16.5143 | 0.5600 | 0.0304 | 0.0304 | hybrid | structured_preferred | electrical¦gtg¦hvac | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAI-133902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #3/4/5 LEB | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | GTG #3/4/5 LEB ¦ Gas Turbine Generator #3/4/5 Local Electrical Building |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦gtg¦heating¦hvac¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | fire_fighting¦hvac | discipline_only | false | 48 | 23 | 30.0435 | 0.5745 | 0.0213 | 0.0107 | hybrid | structured_cell_found_text_preferred | electrical¦gtg¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #3/4/5 LEB | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | GTG #3/4/5 LEB ¦ Gas Turbine Generator #3/4/5 Local Electrical Building |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦gtg¦heating¦hvac¦leb¦local¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.8000 | 0.6716 | 0.7615 | 0.7615 | FI | 3CF1200W36A07 | (GTG #31 LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-15 | 2008-06-30 |  | commissioning | query_unknown | electrical¦gtg¦hvac | gtg | electrical¦gtg¦hvac | query | gtg¦hvac | match | false | 20 | 1 | 30.7962 | 0.6398 | 0.0289 | 0.0217 | hybrid | structured_no_phase | electrical¦gtg¦hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAI-133904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #3/4/5 LEB | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | GTG #3/4/5 LEB ¦ Gas Turbine Generator #3/4/5 Local Electrical Building |  | Plan for GTG #3/4/5 LEB ¦ Gas Turbine Generator #3/4/5 Local Electrical Building |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7482 | 0.9244 | 0.6471 | FA | 3CF1200W36A07 | (GTG #31 LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-15 | 2008-06-30 |  | commissioning | query_unknown | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | gtg¦hvac | match | false | 9 | 2 | 30.7959 | 0.6089 | 0.0306 | 0.0230 | hybrid | structured_no_phase | electrical¦gtg¦hvac |  |  | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAL-134001 | LOAD CALCULATION OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ADMIN & SOCIAL BUILDING ¦ Administration & SOCIAL BUILDING |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5995 | 0.6465 | 0.6465 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 37.3904 | 0.5748 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAL-134002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ADMIN & SOCIAL BUILDING ¦ Administration & SOCIAL BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 20 | 4 | 33.9935 | 0.5979 | 0.0281 | 0.0281 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAL-134003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ADMIN & SOCIAL BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | ADMIN & SOCIAL BUILDING ¦ Administration & SOCIAL BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7587 | 0.6943 | 0.6943 | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 2 | 47.9654 | 0.6398 | 0.0320 | 0.0240 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-05-17 | 2024-06-16 | 2024-07-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAL-134004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  |  | Plan for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7284 | 0.9185 | 0.6430 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6580 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134101 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #1 LEB | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦stg¦ventilating | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.6757 | 0.9027 | 0.9027 | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦hvac¦stg | stg | electrical¦hvac¦stg | query | stg | match | false | 15 | 8 | 10.6091 | 0.4592 | 0.0280 | 0.0280 | hybrid | structured_preferred | electrical¦hvac¦stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAR-134102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #1 LEB | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦stg¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac¦stg |  | electrical¦hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 28 | 7 | 31.2989 | 0.5917 | 0.0263 | 0.0131 | hybrid | structured_cell_found_text_preferred | electrical¦hvac¦stg | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#1 LEB | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦stg¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6448 | 0.6134 | 0.6134 | FI | 0PF5000W36A05T | (HVAC Equipment) 1st Delivery on site_Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System |  | 2008-05-14 |  | delivery | query_unknown | electrical¦hvac¦stg | gtg | electrical¦hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 4 | 1 | 47.1257 | 0.6440 | 0.0320 | 0.0120 | hybrid | structured_no_phase | electrical¦hvac¦stg | [5 empty] | 2025-02-14 | 2025-03-16 | 2025-04-15 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAR-134104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #1 LEB | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | Plan for ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.5738 | 0.6971 | 0.6971 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac¦stg | stg | electrical¦hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 1 | 1 | 44.7446 | 0.6364 | 0.0328 | 0.0123 | hybrid | structured_no_phase | electrical¦hvac¦stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134201 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #2 LEB | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | ST #2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦stg¦ventilating | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.6852 | 0.9056 | 0.9056 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦hvac¦stg | stg | electrical¦hvac¦stg | query | stg | match | false | 15 | 6 | 11.1508 | 0.4753 | 0.0285 | 0.0285 | hybrid | structured_preferred | electrical¦hvac¦stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAR-134202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #2 LEB | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦stg¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac¦stg |  | electrical¦hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 45 | 9 | 30.0435 | 0.5964 | 0.0240 | 0.0120 | hybrid | structured_cell_found_text_preferred | electrical¦hvac¦stg | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#2 LEB | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦stg¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6451 | 0.6135 | 0.6135 | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | electrical¦hvac¦stg | gtg | electrical¦hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 1 | 6 | 48.8359 | 0.6133 | 0.0315 | 0.0118 | hybrid | structured_no_phase | electrical¦hvac¦stg | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAR-134204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #2 LEB | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Plan for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.5796 | 0.6989 | 0.6989 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac¦stg | stg | electrical¦hvac¦stg | query | fire_fighting¦hvac | discipline_only | false | 1 | 1 | 44.7446 | 0.6372 | 0.0328 | 0.0123 | hybrid | structured_no_phase | electrical¦hvac¦stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134301 | LOAD CALCULATION OF HVAC SYSTEM FOR MAIN GATE HOUSE | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE HOUSE |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7184 | 0.9155 | 0.9155 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 33.5852 | 0.5799 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-134302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR MAIN GATE HOUSE | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE HOUSE |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 58.0917 | 0.6287 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR MAIN GATE HOUSE | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | MAIN GATE HOUSE |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | PLUMBING EQUIPMENT SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6969 | 0.6757 | 0.4730 | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | false | 1 | 1 | 51.2575 | 0.6592 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-134304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR MAIN GATE HOUSE | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE HOUSE |  | Plan for MAIN GATE HOUSE |  | Gate House FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6664 | 0.7249 | 0.7249 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6576 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAN-134401 | LOAD CALCULATION OF HVAC SYSTEM FOR SUPPORT BUILDING | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7227 | 0.9168 | 0.9168 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 7 | 1 | 37.3904 | 0.6120 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | hvac | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAN-134402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SUPPORT BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 20 | 2 | 33.9935 | 0.6222 | 0.0286 | 0.0286 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAN-134403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SUPPORT BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SUPPORT BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7385 | 0.6216 | 0.6216 | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 47.9654 | 0.6532 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-07-16 | 2024-08-15 | 2024-09-14 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAN-134404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SUPPORT BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING |  | Plan for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING PLAN | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | rule_query | plan | plan | plan | plan | support |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7074 | 0.7372 | 0.7372 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6705 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-30 | 2024-04-29 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAD-134501 | LOAD CALCULATION OF HVAC SYSTEM FOR SECURITY BUILDING | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SECURITY BUILDING |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7123 | 0.9137 | 0.9137 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 7 | 1 | 37.3904 | 0.6267 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | hvac | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAD-134502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SECURITY BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SECURITY BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 20 | 1 | 33.9935 | 0.6342 | 0.0289 | 0.0289 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAD-134503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SECURITY BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7616 | 0.7885 | 0.7885 | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 47.9654 | 0.6490 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-05-17 | 2024-06-16 | 2024-07-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAD-134504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SECURITY BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SECURITY BUILDING |  | Plan for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7534 | 0.7510 | 0.7510 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6666 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134601 | LOAD CALCULATION OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SEARCH FACILITY & VISITORS CENTRE |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.7093 | 0.7128 | 0.7128 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 33.5852 | 0.5578 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-134602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SEARCH FACILITY & VISITORS CENTRE |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 58.0917 | 0.5903 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SEARCH FACILITY & VISITORS CENTRE | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SEARCH FACILITY & VISITORS CENTRE |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.5455 | 0.6811 | 0.5862 | 0.5862 | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 47.9654 | 0.6327 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-05-17 | 2024-06-16 | 2024-07-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-134604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.7896 | 0.6744 | 0.6744 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6304 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAF-134701 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE BRIGADE | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7604 | 0.9281 | 0.9281 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 40.3471 | 0.6786 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAF-134702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE BRIGADE | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 2 | 62.7574 | 0.6658 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAF-134703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE BRIGADE | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | FIRE BRIGADE |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8000 | 0.8000 | 0.8000 | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 53.7119 | 0.6862 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAF-134704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE BRIGADE | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 49.4102 | 0.7025 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAB-134801 | LOAD CALCULATION OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WORKSHOP & STORAGE BUILDING |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7538 | 0.9261 | 0.9261 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 7 | 1 | 37.3904 | 0.5665 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | hvac | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAB-134802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WORKSHOP & STORAGE BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 22 | 4 | 33.9935 | 0.5822 | 0.0278 | 0.0278 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAB-134803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WORKSHOP & STORAGE BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | WORKSHOP & STORAGE BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7876 | 0.8196 | 0.8196 | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 47.9654 | 0.6577 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-05-17 | 2024-06-16 | 2024-07-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAB-134804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6456 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAG-134901 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FIRE WATER PUMP HOUSE |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | Fire Water Pump House | FIRE WATER PUMP HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦pump¦ventilating | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7970 | 0.9391 | 0.9391 | FI | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦hvac | fire_fighting | fire_fighting¦hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 45.8018 | 0.6713 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting¦hvac | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAG-134902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FIRE WATER PUMP HOUSE |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦pump¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦hvac |  | fire_fighting¦hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 62.7574 | 0.6927 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAG-134903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE WATER PUMP HOUSE | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | FIRE WATER PUMP HOUSE |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦pump¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7052 | 0.6316 | 0.6316 | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | fire_fighting¦hvac |  | fire_fighting¦hvac | query | fire_fighting¦hvac | match | false | 1 | 2 | 53.7119 | 0.6737 | 0.0325 | 0.0244 | hybrid | structured_no_phase | fire_fighting¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAG-134904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | FIRE WATER PUMP HOUSE |  | Plan for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.8333 | 0.8449 | 0.8368 | 0.8368 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | fire_fighting¦hvac | fire_fighting | fire_fighting¦hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 49.4102 | 0.7139 | 0.0328 | 0.0246 | hybrid | structured_no_phase | fire_fighting¦hvac | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAM-135001 | LOAD CALCULATION OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CPP Regeneration Building | CPP & CPP REGEN BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7996 | 0.7999 | 0.7999 | FI | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate¦hvac |  | condensate¦hvac | query | acc¦condensate | match | false | 11 | 8 | 4.1978 | 0.4702 | 0.0288 | 0.0288 | hybrid | structured_preferred | condensate¦hvac | civil_design | 10 |  |  |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAM-135002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | condensate¦hvac |  | condensate¦hvac | query | fire_fighting¦hvac | discipline_only | false | 20 | 7 | 33.9935 | 0.5872 | 0.0274 | 0.0137 | hybrid | structured_cell_found_text_preferred | condensate¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAM-135003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CPP & CPP REGEN BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6006 | 0.6002 | 0.6002 | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | condensate¦hvac |  | condensate¦hvac | query | fire_fighting¦hvac | discipline_only | false | 1 | 2 | 48.8359 | 0.6537 | 0.0325 | 0.0122 | hybrid | structured_no_phase | condensate¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 | 0.30 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAM-135004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7415 | 0.9225 | 0.6457 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | condensate¦hvac |  | condensate¦hvac | query | fire_fighting¦hvac | discipline_only | false | 1 | 1 | 44.7446 | 0.6777 | 0.0328 | 0.0123 | hybrid | structured_no_phase | condensate¦hvac |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.30 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAV-135101 | LOAD CALCULATION OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | WASTE WATER TREATMENT PLANT | CALCULATION OF WASTE WATER TREATMENT PLANT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.6626 | 0.7821 | 0.7821 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | hvac | wts | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 41.6465 | 0.6169 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAV-135102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | Water Treatment System | Control Configuration Diagram for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.5483 | 0.6645 | 0.6645 | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | hvac | wts | hvac | query | fire_fighting¦hvac | match | false | 18 | 3 | 38.9978 | 0.6292 | 0.0287 | 0.0287 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-05-31 | 2024-06-30 | 2024-07-30 | 2024-08-14 | 2024-08-29 | 2024-09-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAV-135103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7216 | 0.6831 | 0.6831 | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | hvac | wts | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 48.8359 | 0.6538 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAV-135104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  |  | Plan for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | air¦conditioning¦heating¦hvac¦ventilating¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7287 | 0.9186 | 0.6430 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 2 | 1 | 44.7446 | 0.6565 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAQ-135201 | LOAD CALCULATION OF HVAC SYSTEM FOR AUX. LEB | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | AUX. LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦ventilating | leb | scoped | match | match | match | passed |  | 1.0000 | 0.7531 | 0.9259 | 0.9259 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 33.5852 | 0.5460 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAQ-135202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR AUX. LEB | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | false | 41 | 12 | 30.0435 | 0.5646 | 0.0238 | 0.0238 | hybrid | structured_cell_found_text_preferred | electrical¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAQ-135203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR AUX. LEB | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6033 | 0.6010 | 0.6010 | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 48.8359 | 0.6363 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAQ-135204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR AUX. LEB | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Plan for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 0.5000 | 0.7080 | 0.5624 | 0.5624 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6491 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135301 | LOAD CALCULATION OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | PLANT ACCESS GATE HOUSE |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6553 | 0.7216 | 0.7216 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 33.5854 | 0.5730 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-135302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | PLANT ACCESS GATE HOUSE |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 58.0919 | 0.6433 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PLANT ACCESS GATE HOUSE | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | PLANT ACCESS GATE HOUSE |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | PLUMBING EQUIPMENT SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6969 | 0.6757 | 0.4730 | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | false | 1 | 1 | 51.2577 | 0.6655 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-135304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | PLANT ACCESS GATE HOUSE |  | Plan for PLANT ACCESS GATE HOUSE |  | Gate House FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | access¦gate¦house¦plant |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6017 | 0.7055 | 0.7055 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7448 | 0.6601 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135401 | LOAD CALCULATION OF HVAC SYSTEM FOR PIC GATE HOUSE | LOAD CALCULATION |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | PIC GATE HOUSE |  | LOAD CALCULATION for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6417 | 0.7175 | 0.7175 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 33.5852 | 0.5592 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-135402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PIC GATE HOUSE | AIR FLOW DIAGRAM |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | PIC GATE HOUSE |  | AIR FLOW DIAGRAM for HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7085 | 0.9126 | 0.6388 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 58.0917 | 0.6420 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PIC GATE HOUSE | EQUIPMENT SCHEDULE |  | HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM | PIC GATE HOUSE |  | EQUIPMENT SCHEDULE for HVAC SYSEM ¦ Heating Ventilating and Air Conditioning SYSEM |  | PLUMBING EQUIPMENT SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦hvac¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6969 | 0.6757 | 0.4730 | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | false | 1 | 1 | 51.2575 | 0.6590 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.30 | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-135404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PIC GATE HOUSE | PLAN |  | HVAC SYSTEM ¦ Heating Ventilating and Air Conditioning SYSTEM | PIC GATE HOUSE |  | Plan for PIC GATE HOUSE |  | Gate House FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | gate¦house¦pic |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6163 | 0.7099 | 0.7099 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 44.7446 | 0.6681 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136001 | VENDOR PRINT FOR HVAC EQUIPMENT-1 | VENDOR PRINT | HVAC EQUIPMENT-1 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-1 |  |  |  | VENDOR PRINT for HVAC EQUIPMENT-1 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-1 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6002 | 0.6467 | 0.4527 |  | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 51.6460 | 0.6636 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136002 | VENDOR PRINT FOR HVAC EQUIPMENT-2 | VENDOR PRINT | HVAC EQUIPMENT-2 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-2 |  |  |  | VENDOR PRINT for HVAC EQUIPMENT-2 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-2 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6116 | 0.6502 | 0.4551 |  | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 51.6460 | 0.6675 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136003 | VENDOR PRINT FOR HVAC EQUIPMENT-3 | VENDOR PRINT | HVAC EQUIPMENT-3 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-3 |  |  |  | VENDOR PRINT for HVAC EQUIPMENT-3 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-3 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6110 | 0.6500 | 0.4550 |  | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 51.6460 | 0.6513 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136004 | VENDOR PRINT FOR HVAC EQUIPMENT-4 | VENDOR PRINT | HVAC EQUIPMENT-4 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-4 |  |  |  | VENDOR PRINT for HVAC EQUIPMENT-4 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-4 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6008 | 0.6469 | 0.4528 |  | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 51.6460 | 0.6493 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136005 | VENDOR PRINT FOR HVAC EQUIPMENT-5 | VENDOR PRINT | HVAC EQUIPMENT-5 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-5 |  |  |  | VENDOR PRINT for HVAC EQUIPMENT-5 ¦ Heating Ventilating and Air Conditioning EQUIPMENT-5 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6017 | 0.6472 | 0.4530 |  | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 3 | 1 | 51.6460 | 0.6502 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SG-136601 | FIRE FIGHTING SYSTEM CONCEPTUAL DESIGN | DESIGN |  | FIRE FIGHTING SYSTEM |  |  | DESIGN for FIRE FIGHTING SYSTEM | [5 empty] | rule_query | other | other | design | fire_fighting_system | fighting¦fire |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 1.0000 | 0.7606 | 0.9282 | 0.6497 |  | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 34.9449 | 0.6981 | 0.0328 | 0.0246 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SG-136602 | FIRE RISK EVALUATION | EVALUATION |  |  |  |  | EVALUATION | [5 empty] | rule_query | other | other | evaluation | technical_bid_evaluation |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.4798 | 0.3773 | 0.2641 |  | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 6 | 9 | 6.8830 | 0.4210 | 0.0296 | 0.0167 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136603 | FIRE SERVICE RING MAIN SYSTEM - P&ID | P&ID ¦ Piping and Instrumentation Diagram |  | FIRE SERVICE RING MAIN SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for FIRE SERVICE RING MAIN SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6941 | 0.9082 | 0.6358 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 3 | 2 | 42.3703 | 0.6595 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136604 | FIRE SERVICE RING MAIN SYSTEM - PIPE LAYOUT AND DETAIL DRAWING | LAYOUT AND DETAIL DRAWING |  | FIRE SERVICE RING MAIN SYSTEM |  |  | LAYOUT AND DETAIL DRAWING for FIRE SERVICE RING MAIN SYSTEM |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7303 | 0.9191 | 0.6434 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 21.2965 | 0.5294 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGA-136605 | FIRE SERVICE RING MAIN SYSTEM - HYDRAULIC CALCULATION | HYDRAULIC CALCULATION |  | FIRE SERVICE RING MAIN SYSTEM |  |  | HYDRAULIC CALCULATION for FIRE SERVICE RING MAIN SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6739 | 0.6689 | 0.6689 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 14.9275 | 0.4779 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CYE-136606 | FIRE DETECTION AND ALARM SYSTEM - BLOCK DIAGRAM | BLOCK DIAGRAM |  | FIRE DETECTION AND ALARM SYSTEM |  |  | BLOCK DIAGRAM for FIRE DETECTION AND ALARM SYSTEM | Cathodic | Block Diagram | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | diagram | diagram | diagram | diagram | alarm¦detection¦fire |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4697 | 0.6076 | 0.6076 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 33.2223 | 0.5510 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136607 | FIRE DETECTION AND ALARM SYSTEM - NETWORK SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Single Line Diagram for FIRE DETECTION AND ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦detection¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6995 | 0.9099 | 0.9099 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 5 | 33.2223 | 0.5638 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136609 | FIRE FIGHTING PUMP SYSTEM - DATASHEET | DATASHEET |  | FIRE FIGHTING PUMP SYSTEM |  |  | Data Sheet for FIRE FIGHTING PUMP SYSTEM | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fighting¦fire¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.8726 | 0.7868 | 0.7868 | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 35.6767 | 0.6790 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-11-07 | 2024-12-12 | 2025-01-16 | 2025-01-02 | 2025-02-06 | 2025-03-13 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136610 | OUTDOOR HYDRANT SYSTEM - DATASHEET | DATASHEET |  | OUTDOOR HYDRANT SYSTEM |  |  | Data Sheet for OUTDOOR HYDRANT SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hydrant¦outdoor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5768 | 0.6397 | 0.6397 | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 1 | 9.0704 | 0.5505 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136611 | STAND PIPE SYSTEM - DATASHEET | DATASHEET |  | STAND PIPE SYSTEM |  |  | Data Sheet for STAND PIPE SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | pipe¦stand |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5920 | 0.6443 | 0.6443 | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 1 | 9.0704 | 0.5736 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGE-136612 | SPRINKLER SYSTEM - DATASHEET | DATASHEET |  | SPRINKLER SYSTEM |  |  | Data Sheet for SPRINKLER SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | sprinkler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6035 | 0.6477 | 0.6477 | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 1 | 9.0704 | 0.5428 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGC-136613 | WATER SPRAY SYSTEM - DATASHEET | DATASHEET |  | WATER SPRAY SYSTEM |  |  | Data Sheet for WATER SPRAY SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | spray¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5937 | 0.6448 | 0.6448 | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 1 | 9.0704 | 0.5350 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGK-136614 | CLEAN AGENT SYSTEM - DATASHEET | DATASHEET |  | CLEAN AGENT SYSTEM |  |  | Data Sheet for CLEAN AGENT SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | agent¦clean |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5721 | 0.6383 | 0.6383 | FA | 3PF1265W38A04P | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2007-04-30 | 2008-05-13 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦gtg | match | false | 3 | 4 | 30.3054 | 0.6102 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | fire_fighting | procurement |  | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGZ-136615 | FIRE EXTINGUISHER SYSTEM - DATASHEET | DATASHEET |  | FIRE EXTINGUISHER SYSTEM |  |  | Data Sheet for FIRE EXTINGUISHER SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | extinguisher¦fire |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6167 | 0.6517 | 0.6517 | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | procurement | procurement | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 1 | 1 | 22.3779 | 0.6048 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGX-136616 | PIPE AND BULK MATERIAL - DATASHEET | DATASHEET |  |  |  |  | Data Sheet |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet |  |  | generic | match | match | query_unscoped | passed |  | 0.6667 | 0.7755 | 0.6993 | 0.6993 | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 2 | 15.8120 | 0.6399 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | 2024-11-20 | 2024-12-05 | 2024-12-20 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CYE-136617 | FIRE DETECTION AND ALARM SYSTEM - DATASHEET | DATASHEET |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Data Sheet for FIRE DETECTION AND ALARM SYSTEM |  | Data Sheet for Fire Alarm System | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | alarm¦detection¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9375 | 0.9813 | 0.6869 | FA | 0EF4500W38A08 | (Fire Fighting System) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 19.5504 | 0.4648 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CYE-136618 | CABLE AND BULK MATERIAL - DATASHEET | DATASHEET |  |  |  |  | Data Sheet |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet |  |  | generic | match | match | query_unscoped | passed |  | 0.6667 | 0.7755 | 0.6993 | 0.6993 | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 1 | 2 | 15.7092 | 0.5632 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0SG-136620 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR ESOD | PROCEDURE |  | FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  |  | PROCEDURE for FIRE FIGHTING, DETECTION AND ALARM SYSTEM | Chemical Dosing System | Commissioning Procedure | 1 | start-2M-2M<=FA<=start-2M | FA ∈ [start-120d, start-60d] | title | procedure | procedure | procedure | procedure | alarm¦detection¦fighting¦fire |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5430 | 0.5829 | 0.5829 | FI | 0CF4500W90A08 | (Fire WTR Pump Shelter) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-06 | 2008-07-02 | commissioning | commissioning | match | fire_fighting | wts | fire_fighting | query | fire_fighting¦hvac | match | false | 9 | 6 | 36.3490 | 0.5776 | 0.0296 | 0.0296 | hybrid | structured_preferred | fire_fighting | commissioning | 10 | 2025-03-05 | 2025-04-04 | 2025-05-04 | 2025-05-19 | 2025-06-03 | 2025-06-18 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SG-136621 | PIPING MATERIAL SPECIFICATION FOR FIRE FIGHTING SYSTEM | SPECIFICATION |  | FIRE FIGHTING SYSTEM |  |  | Technical Specification for FIRE FIGHTING SYSTEM |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | fighting¦fire |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5606 | 0.6348 | 0.4444 | FA | 0EF4500W38A08 | (Fire Fighting System) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 38.6106 | 0.6776 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SGA-136622 | ISOMETRIC DRAWING FOR FIRE SERVICE RING MAIN SYSTEM | ISOMETRIC DRAWING |  | FIRE SERVICE RING MAIN SYSTEM |  |  | Isometric Drawing for FIRE SERVICE RING MAIN SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.5717 | 0.4715 | 0.4715 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 16.7207 | 0.5272 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design | 2 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0SG-136623 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR NON ESOD | PROCEDURE |  | FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  |  | PROCEDURE for FIRE FIGHTING, DETECTION AND ALARM SYSTEM | Chemical Dosing System | Commissioning Procedure | 1 | start-2M-2M<=FA<=start-2M | FA ∈ [start-120d, start-60d] | title | procedure | procedure | procedure | procedure | alarm¦detection¦fighting¦fire |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5346 | 0.5804 | 0.5804 | FI | 0CF4500W90A09 | (Fire Fighting BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-02-02 | 2008-03-31 | commissioning | commissioning | match | fire_fighting | wts | fire_fighting | query | fire_fighting¦hvac | match | false | 7 | 8 | 37.4743 | 0.5800 | 0.0296 | 0.0296 | hybrid | structured_preferred | fire_fighting | commissioning | 10 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136624 | FIRE DETECTION AND ALARM SYSTEM LAYOUT FOR YARD AREA | LAYOUT |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Layout Drawing for FIRE DETECTION AND ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦detection¦fire |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6255 | 0.5376 | 0.5376 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 22.6631 | 0.5377 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SUPPORT BUILDING | ARRANGEMENT |  |  | SUPPORT BUILDING |  | ARRANGEMENT for SUPPORT BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | support |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5479 | 0.3977 | 0.3380 | FA | 0EF3520W00A01.3 | (Foam Station BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Foam Station Building | 2007-05-01 |  | civil_design | civil_design | match |  |  |  |  | fgp¦fire_fighting | query_unscoped | false | 29 | 113 | 10.9843 | 0.4795 | 0.0170 | 0.0128 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136641 | FIRE ALARM SYSTEM LAYOUT FOR SUPPORT BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | SUPPORT BUILDING |  | Layout Drawing for SUPPORT BUILDING | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6311 | 0.5393 | 0.5393 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 22.0451 | 0.6042 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SUPPORT BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | SUPPORT BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 27 | 12 | 18.8774 | 0.5385 | 0.0254 | 0.0254 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136701 | P&ID OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM | CENTRAL CONTROL BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | ccr¦central¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6074 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136702 | P&ID OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for SPRINKLER SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | ccr¦central¦sprinkler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7371 | 0.9211 | 0.6448 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6182 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136703 | P&ID OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for CLEAN AGENT SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | agent¦ccr¦central¦clean |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7155 | 0.9146 | 0.6403 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6122 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL for CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7752 | 0.7926 | 0.5548 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 4 | 9.8406 | 0.5013 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136712 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL for CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7752 | 0.7926 | 0.5548 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 9.8406 | 0.4864 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136713 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL for CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7752 | 0.7926 | 0.5548 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 1 | 9.3549 | 0.5264 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136722 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | CALCULATION |  | SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING |  | Calculation sheet for SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | ccr¦central¦sprinkler | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.7082 | 0.9124 | 0.9124 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 5.1115 | 0.5098 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136723 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | CALCULATION |  | CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING |  | Calculation sheet for CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦ccr¦central¦clean | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.6795 | 0.9039 | 0.9039 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 5.1115 | 0.5183 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CENTRAL CONTROL BUILDING | ARRANGEMENT |  |  | CENTRAL CONTROL BUILDING |  | ARRANGEMENT for CENTRAL CONTROL BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | ccr¦central |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4909 | 0.3806 | 0.3235 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 3 | 25.7139 | 0.5492 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136741 | FIRE ALARM SYSTEM LAYOUT FOR CENTRAL CONTROL BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6558 | 0.5467 | 0.5467 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 22.0451 | 0.5694 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦ccr¦central¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 30 | 19 | 18.8774 | 0.5153 | 0.0238 | 0.0238 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | CALCULATION |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | Calculation sheet for FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦ccr¦central¦fire | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.6526 | 0.8958 | 0.8958 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 3 | 18.8774 | 0.4854 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦ccr¦central¦fire |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 |  | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting | match | false | 1 | 1 | 31.1845 | 0.5515 | 0.0328 | 0.0246 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136801 | P&ID OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | P&ID ¦ Piping and Instrumentation Diagram | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6792 | 0.9037 | 0.6326 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | electrical¦gtg |  | electrical¦gtg | query |  | activity_unscoped | true | 1 | 1032 | 37.7165 | 0.5495 | 0.0173 | 0.0104 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.44 | needs_review | rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136802 | P&ID OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | P&ID ¦ Piping and Instrumentation Diagram | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6792 | 0.9037 | 0.6326 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | electrical¦gtg |  | electrical¦gtg | query |  | activity_unscoped | true | 1 | 1026 | 37.7165 | 0.5383 | 0.0173 | 0.0104 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.44 | needs_review | rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136803 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | P&ID ¦ Piping and Instrumentation Diagram | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6792 | 0.9037 | 0.6326 | FA | 2EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match | electrical¦gtg |  | electrical¦gtg | query |  | activity_unscoped | true | 1 | 778 | 42.7061 | 0.5662 | 0.0176 | 0.0106 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.44 | needs_review | rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL for LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7441 | 0.7832 | 0.5483 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7166 | 0.7215 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136812 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL for LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7439 | 0.7832 | 0.5482 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7166 | 0.7063 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136813 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL for LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7439 | 0.7832 | 0.5482 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7166 | 0.7122 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136822 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | CALCULATION | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Calculation sheet for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6297 | 0.6556 | 0.6556 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7166 | 0.6602 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136823 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | CALCULATION | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Calculation sheet for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6297 | 0.6556 | 0.6556 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7166 | 0.6537 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #1,2 LEB | ARRANGEMENT | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | ARRANGEMENT for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4669 | 0.3734 | 0.3174 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 3 | 26.6952 | 0.6812 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136841 | FIRE ALARM SYSTEM LAYOUT FOR GTG #1,2 LEB | LAYOUT | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6956 | 0.5587 | 0.5587 | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 1 | 23.2059 | 0.7583 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | SINGLE LINE DIAGRAM | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Single Line Diagram for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7103 | 0.9131 | 0.9131 | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 61 | 7 | 19.7166 | 0.6864 | 0.0232 | 0.0232 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | BATTERY CALCULATION | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | BATTERY CALCULATION for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5791 | 0.6404 | 0.6404 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7166 | 0.6508 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | CAUSE & EFFECT MATRIX | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | CAUSE & EFFECT MATRIX for GTG #1,2 ¦ Gas Turbine Generator #1,2 | [5 empty] | rule_query | other | other | cause_and_effect_matrix | gt_generator_outline | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5760 | 0.6395 | 0.6395 |  | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-31 | 2008-07-04 |  | commissioning | query_unknown | electrical¦gtg |  | electrical¦gtg | query | fire_fighting¦gtg | match | false | 11 | 3 | 21.4116 | 0.6676 | 0.0300 | 0.0225 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136901 | P&ID OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | P&ID ¦ Piping and Instrumentation Diagram | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6862 | 0.9059 | 0.6341 | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | electrical¦gtg |  | electrical¦gtg | query | ccw¦gtg | match | false | 75 | 1 | 12.7867 | 0.6478 | 0.0238 | 0.0238 | hybrid | structured_preferred | electrical¦gtg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136902 | P&ID OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | P&ID ¦ Piping and Instrumentation Diagram | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6862 | 0.9059 | 0.6341 | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | electrical¦gtg |  | electrical¦gtg | query | ccw¦gtg | match | false | 75 | 1 | 12.7867 | 0.6389 | 0.0238 | 0.0238 | hybrid | structured_preferred | electrical¦gtg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136903 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | P&ID ¦ Piping and Instrumentation Diagram | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6862 | 0.9059 | 0.6341 | FA | 3EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match | electrical¦gtg |  | electrical¦gtg | query |  | activity_unscoped | true | 1 | 622 | 39.1097 | 0.5727 | 0.0179 | 0.0107 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.44 | needs_review | rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL for LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7439 | 0.7832 | 0.5482 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 12 | 1 | 16.2666 | 0.6929 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136912 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL for LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7442 | 0.7833 | 0.5483 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 12 | 2 | 16.2666 | 0.6679 | 0.0300 | 0.0300 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136913 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL for LEB ¦ Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7439 | 0.7832 | 0.5482 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 12 | 1 | 16.2666 | 0.6904 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136922 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | CALCULATION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Calculation sheet for GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6344 | 0.6570 | 0.6570 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 12 | 1 | 16.2666 | 0.6161 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136923 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | CALCULATION | GTG ¦ Gas Turbine Generator | CLEAN AGENT SYSTEM | LEB ¦ Local Electrical Building |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg | gtg | electrical¦fire_fighting¦gtg | query | gtg | match | false | 12 | 1 | 12.8492 | 0.5953 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #3,4,5 LEB | ARRANGEMENT | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | ARRANGEMENT for GTG ¦ Gas Turbine Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4801 | 0.3774 | 0.3208 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 5 | 19.8277 | 0.6369 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136941 | FIRE ALARM SYSTEM LAYOUT FOR GTG #3,4,5 LEB | LAYOUT | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6956 | 0.5587 | 0.5587 | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg |  | electrical¦fire_fighting¦gtg | query | gtg | match | false | 4 | 2 | 16.3384 | 0.6975 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦fire_fighting¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | SINGLE LINE DIAGRAM | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM | LEB ¦ Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg |  | electrical¦fire_fighting¦gtg | query | gtg | match | false | 406 | 35 | 12.8492 | 0.6454 | 0.0127 | 0.0127 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting¦gtg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | CALCULATION | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM | LEB ¦ Local Electrical Building |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg | gtg | electrical¦fire_fighting¦gtg | query | gtg | match | false | 20 | 2 | 12.8492 | 0.6111 | 0.0286 | 0.0286 | hybrid | structured_preferred | electrical¦fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | CAUSE & EFFECT MATRIX | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM | LEB ¦ Local Electrical Building |  | CAUSE & EFFECT MATRIX for GTG ¦ Gas Turbine Generator | [5 empty] | rule_query | other | other | cause_and_effect_matrix | gt_generator_outline | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6337 | 0.6568 | 0.6568 |  | 3SF1265W62A09.00 | (F/F GTG#31) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2008-08-14 | 2008-08-23 |  | commissioning | query_unknown | electrical¦fire_fighting¦gtg |  | electrical¦fire_fighting¦gtg | query | fire_fighting¦gtg | match | false | 1 | 1 | 37.0116 | 0.6516 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦fire_fighting¦gtg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137001 | P&ID OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | P&ID ¦ Piping and Instrumentation Diagram | GTG ¦ Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦spray¦turbine¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦gtg |  | fire_fighting¦gtg | query | wts | mismatch | false | 1 | 6 | 36.6905 | 0.6339 | 0.0315 | 0.0079 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦gtg | system_design¦procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137011 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | PIPE LAYOUT AND DETAIL | GTG ¦ Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6115 | 0.8834 | 0.6184 | FA | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | fire_fighting¦gtg | fire_fighting | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 44 | 1 | 11.2906 | 0.6393 | 0.0260 | 0.0195 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137021 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | CALCULATION | GTG ¦ Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 2EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query | ccw¦gtg | match | false | 3 | 16 | 13.6494 | 0.5556 | 0.0290 | 0.0290 | hybrid | structured_preferred | fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG GSU TRANSFORMER | ARRANGEMENT | GTG ¦ Gas Turbine Generator |  |  |  | ARRANGEMENT for GTG ¦ Gas Turbine Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4801 | 0.3774 | 0.3208 | FA | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 11 | 4 | 10.3627 | 0.6518 | 0.0297 | 0.0223 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137041 | FIRE ALARM SYSTEM LAYOUT FOR GTG GSU TRANSFORMER | LAYOUT | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for GTG | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5650 | 0.5195 | 0.5195 | SKIP | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | fire_fighting¦gtg |  | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 14 | 1 | 11.2906 | 0.6903 | 0.0299 | 0.0224 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG GSU TRANSFORMER | SINGLE LINE DIAGRAM | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦gtg |  | fire_fighting¦gtg | query | fire_fighting¦hvac | match | false | 1 | 4 | 26.4345 | 0.4925 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦engineering | 5 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137101 | P&ID OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | P&ID ¦ Piping and Instrumentation Diagram | GTG ¦ Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦spray¦turbine¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦gtg |  | fire_fighting¦gtg | query | wts | mismatch | false | 1 | 4 | 36.6905 | 0.6353 | 0.0320 | 0.0080 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦gtg | system_design¦procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | PIPE LAYOUT AND DETAIL | GTG ¦ Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6177 | 0.8853 | 0.6197 | FA | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 | design_drawing | civil_design | compatible | fire_fighting¦gtg | fire_fighting | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 8 | 1 | 14.7603 | 0.6458 | 0.0311 | 0.0233 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | CALCULATION | GTG ¦ Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 1 | 5 | 14.9409 | 0.5828 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG UNIT AUX. TRANSFORMER | ARRANGEMENT | GTG ¦ Gas Turbine Generator |  |  |  | ARRANGEMENT for GTG ¦ Gas Turbine Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4801 | 0.3774 | 0.3208 | FA | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 14 | 2 | 13.8621 | 0.6735 | 0.0296 | 0.0222 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137141 | FIRE ALARM SYSTEM LAYOUT FOR GTG UNIT AUX. TRANSFORMER | LAYOUT | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for GTG | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5650 | 0.5195 | 0.5195 | SKIP | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | design_drawing | civil_design | compatible | fire_fighting¦gtg |  | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 4 | 4 | 17.4913 | 0.7003 | 0.0312 | 0.0234 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG UNIT AUX. TRANSFORMER | SINGLE LINE DIAGRAM | GTG ¦ Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦gtg |  | fire_fighting¦gtg | query | fire_fighting¦hvac | match | false | 1 | 4 | 26.4345 | 0.4871 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦engineering | 5 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137201 | P&ID OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | P&ID ¦ Piping and Instrumentation Diagram | STG ¦ Steam Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | generator¦spray¦steam¦stg¦turbine¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | wts | mismatch | false | 1 | 8 | 36.6905 | 0.6226 | 0.0311 | 0.0078 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | PIPE LAYOUT AND DETAIL | STG ¦ Steam Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7359 | 0.7808 | 0.7808 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | fire_fighting¦stg | stg | fire_fighting¦stg | query | gsut_uat¦stg | match | false | 1 | 9 | 22.2070 | 0.6052 | 0.0309 | 0.0232 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | CALCULATION | STG GSU TRANSFORMER ¦ Steam Turbine Generator GSU TRANSFORMER | WATER SPRAY SYSTEM |  |  | Calculation sheet for STG GSU TRANSFORMER ¦ Steam Turbine Generator GSU TRANSFORMER |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦gsu¦steam¦stg¦transformer¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5840 | 0.5952 | 0.5952 | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | gsut_uat¦stg | match | false | 1 | 10 | 33.3985 | 0.5597 | 0.0307 | 0.0307 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | civil_design | 10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG GSU TRANSFORMER | ARRANGEMENT | STG GSU TRANSFORMER ¦ Steam Turbine Generator GSU TRANSFORMER |  |  |  | ARRANGEMENT for STG GSU TRANSFORMER ¦ Steam Turbine Generator GSU TRANSFORMER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦gsu¦steam¦stg¦transformer¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4334 | 0.3634 | 0.3089 | FA | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | gsut_uat¦stg |  | gsut_uat¦stg | query | gsut_uat¦stg | match | false | 2 | 1 | 37.9302 | 0.6632 | 0.0325 | 0.0244 | hybrid | structured_preferred | gsut_uat¦stg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137241 | FIRE ALARM SYSTEM LAYOUT FOR STG GSU TRANSFORMER | LAYOUT | STG GSU TRANSFORMER ¦ Steam Turbine Generator GSU TRANSFORMER | FIRE ALARM SYSTEM |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | gsut_uat¦stg | match | false | 1 | 4 | 34.4651 | 0.6589 | 0.0320 | 0.0240 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG GSU TRANSFORMER | SINGLE LINE DIAGRAM | STG GSU TRANSFORMER ¦ Steam Turbine Generator GSU TRANSFORMER | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦gsut_uat¦stg |  | fire_fighting¦gsut_uat¦stg | query | fire_fighting¦hvac | match | false | 1 | 4 | 26.4345 | 0.4464 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦engineering | 5 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137301 | P&ID OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM | FIRE WATER PUMP HOUSE |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pipe¦pump¦stand |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 35.7883 | 0.6674 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137302 | P&ID OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | P&ID ¦ Piping and Instrumentation Diagram |  | SPRINKLER SYSTEM | FIRE WATER PUMP HOUSE |  | P&ID ¦ Piping and Instrumentation Diagram for SPRINKLER SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pump¦sprinkler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7371 | 0.9211 | 0.6448 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 35.7883 | 0.6749 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137303 | P&ID OF FIRE WATER PUMP FOR FIRE WATER PUMP HOUSE | P&ID ¦ Piping and Instrumentation Diagram | FIRE WATER PUMP |  | FIRE WATER PUMP HOUSE |  | P&ID ¦ Piping and Instrumentation Diagram for FIRE WATER PUMP |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | fire¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7338 | 0.9201 | 0.6441 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 47.6075 | 0.6861 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | FIRE WATER PUMP HOUSE |  | PIPE LAYOUT AND DETAIL for FIRE WATER PUMP HOUSE | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.6727 | 0.6018 | 0.6018 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 1 | 18.4726 | 0.5625 | 0.0320 | 0.0240 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-137312 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | FIRE WATER PUMP HOUSE |  | PIPE LAYOUT AND DETAIL for FIRE WATER PUMP HOUSE | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7075 | 0.6122 | 0.6122 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 1 | 18.4726 | 0.5680 | 0.0320 | 0.0240 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-137322 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | CALCULATION |  | SPRINKLER SYSTEM | FIRE WATER PUMP HOUSE |  | Calculation sheet for SPRINKLER SYSTEM | Fire Water Pump House | FIRE WATER PUMP HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | pump¦sprinkler | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8124 | 0.9437 | 0.9437 | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 6 | 2 | 14.6770 | 0.5488 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137331 | FIRE WATER PUMP ARRANGEMENT FOR FIRE WATER PUMP HOUSE | ARRANGEMENT | FIRE WATER PUMP |  | FIRE WATER PUMP HOUSE |  | ARRANGEMENT for FIRE WATER PUMP |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | fire¦pump¦water |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4432 | 0.3663 | 0.3114 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 7 | 46.1626 | 0.6084 | 0.0313 | 0.0235 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137332 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE WATER PUMP HOUSE | ARRANGEMENT |  |  | FIRE WATER PUMP HOUSE |  | ARRANGEMENT for FIRE WATER PUMP HOUSE |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | fire¦house¦pump¦water |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4175 | 0.3586 | 0.3048 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 20.0399 | 0.5595 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137341 | FIRE ALARM SYSTEM LAYOUT FOR FIRE WATER PUMP HOUSE | LAYOUT |  | FIRE ALARM SYSTEM | FIRE WATER PUMP HOUSE |  | Layout Drawing for FIRE WATER PUMP HOUSE | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7021 | 0.6106 | 0.6106 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 31.0811 | 0.6482 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE WATER PUMP HOUSE | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | FIRE WATER PUMP HOUSE |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦pump |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 33.0165 | 0.5914 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137401 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | P&ID ¦ Piping and Instrumentation Diagram | RESERVE BOILER | WATER SPRAY SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | reserve_boiler¦spray¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5486 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137411 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | PIPE LAYOUT AND DETAIL | RESERVE BOILER | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for WATER SPRAY SYSTEM |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | reserve_boiler¦spray¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7060 | 0.9118 | 0.6383 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting¦reserve_boiler | fire_fighting | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | false | 1 | 6 | 9.7725 | 0.4261 | 0.0315 | 0.0237 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137421 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | CALCULATION | RESERVE BOILER | WATER SPRAY SYSTEM |  |  | Calculation sheet for RESERVE BOILER |  | Water injection System Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6276 | 0.6083 | 0.6083 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | false | 4 | 1 | 4.4658 | 0.4633 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR RESERVE BOILER | ARRANGEMENT | RESERVE BOILER |  |  |  | ARRANGEMENT for RESERVE BOILER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4671 | 0.3735 | 0.3174 | FA | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | 56 | 3339 | 8.5272 | 0.3435 | 0.0089 | 0.0040 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137441 | FIRE ALARM SYSTEM LAYOUT FOR RESERVE BOILER | LAYOUT | RESERVE BOILER | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦fire¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6352 | 0.5405 | 0.5405 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | design_drawing | civil_design | compatible | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | false | 1 | 1 | 18.2399 | 0.5436 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR RESERVE BOILER | SINGLE LINE DIAGRAM | RESERVE BOILER | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | false | 1 | 1 | 26.4345 | 0.5276 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦engineering | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-137603 | P&ID OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.6943 | 0.7333 | 0.7333 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 1 | 1 | 29.9286 | 0.7035 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fgp | system_design¦procurement | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-137613 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | Layout |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7389 | 0.8050 | 0.8050 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 1 | 1 | 14.7948 | 0.6067 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-137623 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | CALCULATION |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8172 | 0.9452 | 0.9452 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 4 | 2 | 11.4004 | 0.5205 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FGS ELECTRICAL BUILDING | ARRANGEMENT |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | ARRANGEMENT for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦fgp¦fgs¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.3990 | 0.3530 | 0.3001 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp |  | electrical¦fgp | query | fgp | match | false | 1 | 1 | 17.6048 | 0.5461 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137641 | FIRE ALARM SYSTEM LAYOUT FOR FGS ELECTRICAL BUILDING | LAYOUT |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7389 | 0.8050 | 0.8050 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 1 | 1 | 14.7948 | 0.5854 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | SINGLE LINE DIAGRAM |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Single Line Diagram for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Single Line Diagram | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 1.0000 | 0.8098 | 0.9429 | 0.9429 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 118 | 5 | 11.4004 | 0.5518 | 0.0210 | 0.0210 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | system_design¦engineering |  | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-137643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | CALCULATION |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8172 | 0.9452 | 0.9452 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 4 | 5 | 11.4004 | 0.4838 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-137644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | CAUSE & EFFECT MATRIX |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | CAUSE & EFFECT MATRIX for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | [5 empty] | rule_query | other | calculation | cause_and_effect_matrix | calculation | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.7500 | 0.6217 | 0.7115 | 0.7115 |  | 1CF3530W38A18 | (Block #1 EDG BLDG) Installation - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2008-04-02 | 2008-05-17 |  | installation | query_unknown | electrical¦fgp |  | electrical¦fgp | query | electrical¦fire_fighting | discipline_only | false | 47 | 1 | 9.7258 | 0.5194 | 0.0257 | 0.0097 | hybrid | structured_no_phase | electrical¦fgp | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137701 | P&ID OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | P&ID ¦ Piping and Instrumentation Diagram |  |  | AIR COMPRESSOR SHELTER |  | P&ID ¦ Piping and Instrumentation Diagram for AIR COMPRESSOR SHELTER |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7114 | 0.9134 | 0.6394 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 31.8629 | 0.7402 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | Layout |  |  | AIR COMPRESSOR SHELTER |  | Layout Drawing for AIR COMPRESSOR SHELTER |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7008 | 0.9102 | 0.6372 | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 16.0156 | 0.6499 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AIR COMPRESSOR SHELTER | ARRANGEMENT |  |  | AIR COMPRESSOR SHELTER |  | ARRANGEMENT for AIR COMPRESSOR SHELTER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | air¦compressor¦shelter |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4077 | 0.3556 | 0.3023 | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 5 | 19.1404 | 0.5649 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137741 | FIRE ALARM SYSTEM LAYOUT FOR AIR COMPRESSOR SHELTER | LAYOUT |  |  | AIR COMPRESSOR SHELTER |  | Layout Drawing for AIR COMPRESSOR SHELTER |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7008 | 0.9102 | 0.6372 | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 5 | 1 | 16.0156 | 0.6387 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AIR COMPRESSOR SHELTER | SINGLE LINE DIAGRAM |  |  | AIR COMPRESSOR SHELTER |  | Single Line Diagram for AIR COMPRESSOR SHELTER | Air Compressor | Single Line Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8457 | 0.9537 | 0.9537 | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 64 | 5 | 12.8973 | 0.5562 | 0.0234 | 0.0234 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137801 | P&ID OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | P&ID ¦ Piping and Instrumentation Diagram |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | P&ID ¦ Piping and Instrumentation Diagram for Tank | Chemical Dosing System | P&ID | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | tank¦wts |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6507 | 0.7202 | 0.7202 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 2 | 1 | 31.1768 | 0.7020 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | system_design¦procurement | 10 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | Layout |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5437 | 0.6298 | 0.6298 | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 4 | 1 | 31.7839 | 0.6577 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | ARRANGEMENT |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | ARRANGEMENT for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.3434 | 0.3363 | 0.2859 | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 34.6729 | 0.5971 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137841 | FIRE ALARM SYSTEM LAYOUT FORSHELTER FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5437 | 0.6298 | 0.6298 | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 3 | 2 | 31.7839 | 0.6417 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | SINGLE LINE DIAGRAM |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Single Line Diagram for Tank |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | tank¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8141 | 0.9442 | 0.9442 | SKIP | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 9 | 5 | 28.3427 | 0.5464 | 0.0299 | 0.0299 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137901 | P&ID OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  |  | WATER TREATMENT BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for WATER TREATMENT BUILDING | Water Treatment System | P&ID for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | p_id | p_id | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.8256 | 0.8077 | 0.8077 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 41.1747 | 0.7601 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-137902 | P&ID OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  |  | WATER TREATMENT BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for WATER TREATMENT BUILDING | Water Treatment System | P&ID for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | p_id | p_id | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.8256 | 0.8077 | 0.8077 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 41.1747 | 0.7370 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137903 | P&ID OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | SPRINKLER SYSTEM | WATER TREATMENT BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for SPRINKLER SYSTEM | Water Treatment System | P&ID for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | sprinkler¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7640 | 0.9292 | 0.9292 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦wts | wts | fire_fighting¦wts | query | wts | match | false | 1 | 1 | 41.8420 | 0.7036 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  |  | WATER TREATMENT BUILDING |  | PIPE LAYOUT AND DETAIL for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6101 | 0.6497 | 0.6497 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 10 | 1 | 12.0076 | 0.6292 | 0.0307 | 0.0307 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-137912 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  |  | WATER TREATMENT BUILDING |  | PIPE LAYOUT AND DETAIL for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6052 | 0.6482 | 0.6482 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 8 | 1 | 13.3267 | 0.6034 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-137913 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | WATER TREATMENT BUILDING |  | PIPE LAYOUT AND DETAIL for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6142 | 0.6509 | 0.6509 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match | fire_fighting¦wts | electrical¦wts | fire_fighting¦wts | query | wts | match | false | 10 | 1 | 12.6263 | 0.5752 | 0.0307 | 0.0307 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-137922 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | FLOW CALCULATION |  |  | WATER TREATMENT BUILDING |  | FLOW CALCULATION for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8749 | 0.9625 | 0.9625 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 5 | 8 | 13.8294 | 0.5228 | 0.0301 | 0.0301 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-137923 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | WATER TREATMENT BUILDING |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | sprinkler¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.5478 | 0.5144 | 0.5144 | FA | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | fire_fighting¦wts | wts | fire_fighting¦wts | query | wts | match | false | 6 | 2 | 14.4183 | 0.5220 | 0.0313 | 0.0313 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WATER TREATMENT BUILDING | ARRANGEMENT |  |  | WATER TREATMENT BUILDING |  | ARRANGEMENT for WATER TREATMENT BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | treatment¦water¦wts |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4647 | 0.3727 | 0.3168 | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 2 | 4 | 20.1473 | 0.5573 | 0.0318 | 0.0318 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137941 | FIRE ALARM SYSTEM LAYOUT FOR WATER TREATMENT BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | Layout Drawing for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6911 | 0.6740 | 0.6740 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting¦wts | electrical¦wts | fire_fighting¦wts | query | fire_fighting¦hvac | match | false | 1 | 3 | 22.0451 | 0.5922 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2024-12-05 | 2025-01-04 | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-03-20 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦wts |  | fire_fighting¦wts | query | fire_fighting¦hvac | match | false | 41 | 71 | 18.8774 | 0.5196 | 0.0175 | 0.0175 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-137943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦fire¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.6179 | 0.8854 | 0.8854 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting¦wts | wts | fire_fighting¦wts | query | fire_fighting¦hvac | match | false | 4 | 1 | 18.4555 | 0.4907 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-137944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | MATRIX |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | matrix | data_sheet | alarm¦fire¦wts |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6852 | 0.6722 | 0.4706 |  | 0CF5534W38A06 | (DWP BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-08-27 |  | commissioning | query_unknown | fire_fighting¦wts |  | fire_fighting¦wts | query | fire_fighting¦wts | match | false | 8 | 1 | 23.4638 | 0.5379 | 0.0311 | 0.0233 | hybrid | structured_no_phase | fire_fighting¦wts | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138001 | P&ID OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | P&ID ¦ Piping and Instrumentation Diagram |  |  | N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | P&ID ¦ Piping and Instrumentation Diagram for N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | gas¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7020 | 0.9106 | 0.6374 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 |  | n2 | query | n2 | match | false | 1 | 1 | 35.2033 | 0.7610 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138011 | PIPE LAYOUT AND DETAIL OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | PIPE LAYOUT AND DETAIL |  |  | N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | PIPE LAYOUT AND DETAIL for N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7206 | 0.7762 | 0.5433 | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | false | 1 | 5 | 14.9955 | 0.6406 | 0.0318 | 0.0318 | hybrid | structured_preferred | n2 | civil_design | 9 | 2024-07-21 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR N2 GAS STORAGE SHELTER | ARRANGEMENT |  |  | N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | ARRANGEMENT for N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | gas¦nitrogen¦shelter¦storage |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4030 | 0.3542 | 0.3011 | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | false | 4 | 1 | 14.5315 | 0.6602 | 0.0320 | 0.0320 | hybrid | structured_preferred | n2 | civil_design | 9 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138041 | FIRE ALARM SYSTEM LAYOUT FOR N2 GAS STORAGE SHELTER | LAYOUT |  | FIRE ALARM SYSTEM | N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | Layout Drawing for N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6679 | 0.9004 | 0.6303 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦n2 |  | fire_fighting¦n2 | query | fire_fighting¦hvac | match | false | 1 | 7 | 23.5717 | 0.6058 | 0.0313 | 0.0313 | hybrid | structured_preferred | fire_fighting¦n2 | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR N2 GAS STORAGE SHELTER | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | N2 GAS STORAGE SHELTER ¦ Nitrogen GAS STORAGE SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 3EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | fire_fighting¦n2 |  | fire_fighting¦n2 | query | n2 | match | false | 69 | 11 | 15.4594 | 0.5586 | 0.0218 | 0.0218 | hybrid | structured_cell_found_text_preferred | fire_fighting¦n2 | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138101 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | P&ID ¦ Piping and Instrumentation Diagram | HRSG ¦ Heat Recovery Steam Generator |  |  |  | P&ID ¦ Piping and Instrumentation Diagram for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - P&ID for Duct Burner | 1 | start+271D<=FA<=start+271D+2M | FA ∈ [start+271d, start+331d] | title | diagram | diagram | p_id | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7530 | 0.7859 | 0.7859 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 1 | 43.3517 | 0.7362 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦procurement |  | 2024-12-15 | 2025-01-14 | 2025-02-13 | 2025-02-28 | 2025-03-15 | 2025-03-30 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138102 | P&ID OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | P&ID ¦ Piping and Instrumentation Diagram | GTG ¦ Gas Turbine Generator | LUBE OIL SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for LUBE OIL SYSTEM |  | GT - LUBE OIL SYSTEM P&I DIAGRAM | 1 | start+86D<=FA<=start+86D+2M | FA ∈ [start+86d, start+146d] | rule_query | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦lube¦oil¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7823 | 0.7014 | 0.7014 | FA | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | 2007-04-02 | 2007-10-31 | system_design | system_design | match | gtg | gtg | gtg | query |  | activity_unscoped | true | 25 | 196 | 35.3105 | 0.6277 | 0.0157 | 0.0094 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | PIPE LAYOUT AND DETAIL | HRSG ¦ Heat Recovery Steam Generator |  |  |  | PIPE LAYOUT AND DETAIL for HRSG |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7193 | 0.6825 | 0.6825 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 20.3308 | 0.6580 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138112 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | PIPE LAYOUT AND DETAIL | GTG ¦ Gas Turbine Generator | LUBE OIL SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6350 | 0.8905 | 0.6233 | FA | 2CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | 2007-10-31 | 2007-12-31 | design_drawing | civil_design | compatible | gtg | fire_fighting | gtg | query | gtg | match | false | 6 | 3 | 27.9262 | 0.6282 | 0.0310 | 0.0233 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | CALCULATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7930 | 0.7046 | 0.7046 | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 9 | 18 | 16.0954 | 0.5655 | 0.0273 | 0.0273 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-12-01 | 2024-12-31 | 2025-01-30 | 2025-02-14 | 2025-03-01 | 2025-03-16 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138122 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | CALCULATION | GTG ¦ Gas Turbine Generator | LUBE OIL SYSTEM |  |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 2CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | 2007-10-31 | 2007-12-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 5 | 5 | 27.9262 | 0.5974 | 0.0308 | 0.0308 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR HRSG | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | false | 2 | 1 | 24.1423 | 0.6624 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138141 | FIRE ALARM SYSTEM LAYOUT FOR HRSG | LAYOUT | HRSG ¦ Heat Recovery Steam Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | design_drawing | civil_design | compatible | fire_fighting¦hrsg | hrsg | fire_fighting¦hrsg | query | hrsg | match | false | 5 | 4 | 19.4899 | 0.6637 | 0.0310 | 0.0233 | hybrid | structured_preferred | fire_fighting¦hrsg | system_design¦civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR HRSG | SINGLE LINE DIAGRAM | HRSG ¦ Heat Recovery Steam Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | fire_fighting¦hrsg |  | fire_fighting¦hrsg | query | hrsg | match | false | 1 | 3 | 27.5316 | 0.6674 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦hrsg | system_design¦engineering | 8 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138143 | FIRE ALARM SYSTEM LAYOUT FOR GTG LUBE OIL UNIT | LAYOUT | GTG ¦ Gas Turbine Generator | LUBE OIL SYSTEM |  |  | Layout Drawing for GTG | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6028 | 0.5308 | 0.5308 | FA | 2CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | 2007-10-31 | 2007-12-31 | design_drawing | civil_design | compatible | gtg | fire_fighting | gtg | query | gtg | match | false | 4 | 14 | 27.9262 | 0.6283 | 0.0291 | 0.0219 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138144 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG LUBE OIL UNIT | SINGLE LINE DIAGRAM | GTG ¦ Gas Turbine Generator | LUBE OIL SYSTEM |  |  | Single Line Diagram for LUBE OIL SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦lube¦oil¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7480 | 0.9244 | 0.9244 | SKIP | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 3 | 11.1065 | 0.5916 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138201 | P&ID OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | P&ID ¦ Piping and Instrumentation Diagram | BSDG ¦ Blackstart Diesel Generator |  |  |  | P&ID ¦ Piping and Instrumentation Diagram for BSDG ¦ Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | blackstart¦bsdg¦diesel¦generator¦tank |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7662 | 0.7899 | 0.7899 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | 3 | 43 | 35.9127 | 0.5718 | 0.0256 | 0.0153 | hybrid | structured_blocked_procurement_conflict | bsedg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | PIPE LAYOUT AND DETAIL | BSDG ¦ Blackstart Diesel Generator |  |  |  | PIPE LAYOUT AND DETAIL for Tank |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6009 | 0.8803 | 0.6162 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | design_drawing | civil_design | compatible | bsedg | fire_fighting | bsedg | query | bsedg | match | false | 1 | 2 | 34.8894 | 0.6370 | 0.0325 | 0.0244 | hybrid | structured_preferred | bsedg | system_design¦civil_design | 6 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | CALCULATION | BSDG ¦ Blackstart Diesel Generator |  |  |  | Calculation sheet for BSDG ¦ Blackstart Diesel Generator |  | CALCULATION OF BSDG FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | blackstart¦bsdg¦diesel¦generator¦tank |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5917 | 0.7025 | 0.7025 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg | bsedg | query | bsedg | match | false | 5 | 2 | 34.8894 | 0.6011 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | bsedg | civil_design |  | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR BSDG DIESEL OIL DAY TANK | ARRANGEMENT | BSDG ¦ Blackstart Diesel Generator |  |  |  | ARRANGEMENT for BSDG ¦ Blackstart Diesel Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | blackstart¦bsdg¦diesel¦generator¦tank |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4462 | 0.3672 | 0.3121 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | design_drawing | civil_design | compatible | bsedg |  | bsedg | query | bsedg | match | false | 7 | 2 | 34.8894 | 0.6989 | 0.0311 | 0.0233 | hybrid | structured_cell_found_text_preferred | bsedg | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138241 | FIRE ALARM SYSTEM LAYOUT FOR BSDG DIESEL OIL DAY TANK | LAYOUT | BSDG ¦ Blackstart Diesel Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for Tank | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6058 | 0.5317 | 0.5317 | FA | 0EF3530W00A13 | (BSDG BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-05-01 |  | design_drawing | civil_design | compatible | bsedg¦fire_fighting | fire_fighting | bsedg¦fire_fighting | query | bsedg | match | false | 2 | 1 | 36.7387 | 0.7198 | 0.0325 | 0.0244 | hybrid | structured_cell_found_text_preferred | bsedg¦fire_fighting | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR BSDG DIESEL OIL DAY TANK | SINGLE LINE DIAGRAM | BSDG ¦ Blackstart Diesel Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | bsedg¦fire_fighting |  | bsedg¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 26.4345 | 0.4970 | 0.0328 | 0.0328 | hybrid | structured_preferred | bsedg¦fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138301 | P&ID OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | P&ID ¦ Piping and Instrumentation Diagram | GAS COMPRESSOR |  |  |  | P&ID ¦ Piping and Instrumentation Diagram for GAS COMPRESSOR |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | compressor¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7247 | 0.9174 | 0.6422 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 1 | 4 | 32.4397 | 0.6233 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138311 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | PIPE LAYOUT AND DETAIL | GAS COMPRESSOR |  |  |  | PIPE LAYOUT AND DETAIL for GAS COMPRESSOR |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | compressor¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6268 | 0.8880 | 0.6216 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible |  | fire_fighting | fire_fighting | rule | fire_fighting¦hvac | match | false | 1 | 4 | 9.1055 | 0.4520 | 0.0320 | 0.0240 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138321 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | CALCULATION | GAS COMPRESSOR |  |  |  | Calculation sheet for GAS COMPRESSOR | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | compressor¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7077 | 0.6323 | 0.6323 | FI | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | civil_design | civil_design | match |  | compressed_air | compressed_air | rule | compressed_air | match | false | 2 | 3 | 11.3725 | 0.5184 | 0.0320 | 0.0320 | hybrid | structured_preferred | compressed_air | civil_design | 10 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GPRS AREA | ARRANGEMENT |  |  |  |  | ARRANGEMENT |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement |  |  | generic | match | match | query_unscoped | passed |  | 0.3333 | 0.8688 | 0.4940 | 0.4199 | FA | 3EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | design_drawing | civil_design | compatible |  |  |  |  | fgp¦gtg¦hrsg | query_unscoped | false | 65 | 34 | 9.6939 | 0.5183 | 0.0186 | 0.0105 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | generated | 0.60 | 0.31 | needs_review | default_fc_window;rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138341 | FIRE ALARM SYSTEM LAYOUT FOR GPRS AREA | LAYOUT |  | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6352 | 0.5405 | 0.5405 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 18.2399 | 0.5364 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GPRS AREA | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 26.4345 | 0.5198 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138401 | P&ID of Standpipe system for H2, CO2 Gas Storage Shelter | P&ID ¦ Piping and Instrumentation Diagram |  |  | H2, CO2 Gas Storage Shelter ¦ Hydrogen, Carbon Dioxide Gas Storage Shelter |  | P&ID ¦ Piping and Instrumentation Diagram for H2, CO2 Gas Storage Shelter ¦ Hydrogen, Carbon Dioxide Gas Storage Shelter |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | carbon¦co2¦dioxide¦gas¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6747 | 0.9024 | 0.6317 | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 |  | h2 | query | h2 | match | false | 1 | 1 | 38.2706 | 0.6922 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | h2 | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138411 | Pipe layout and detail of Standpipe system for H2, CO2 Gas Storage Shelter | Pipe layout and detail |  |  | H2, CO2 Gas Storage Shelter ¦ Hydrogen, Carbon Dioxide Gas Storage Shelter |  | Pipe layout and detail for H2, CO2 Gas Storage Shelter ¦ Hydrogen, Carbon Dioxide Gas Storage Shelter | H2, CO2 Supply System | Panel/shelter/JB outline and layout draWings | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | layout_drawing | layout_drawing | carbon¦co2¦dioxide¦gas¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.5455 | 0.6935 | 0.5899 | 0.5899 | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | false | 1 | 1 | 8.8427 | 0.4675 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR H2, CO2 GAS STORAGE SHELTER | ARRANGEMENT |  |  | H2, CO2 GAS STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | ARRANGEMENT for H2, CO2 GAS STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | carbon¦co2¦dioxide¦gas¦hydrogen¦shelter¦storage |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.3645 | 0.3427 | 0.2913 | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 |  | h2 | query | h2 | match | false | 1 | 1 | 8.8427 | 0.4445 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138441 | FIRE ALARM SYSTEM LAYOUT FOR H2, CO2 GAS STORAGE SHELTER | LAYOUT |  | FIRE ALARM SYSTEM | H2, CO2 GAS STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | Layout Drawing for H2, CO2 GAS STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | carbon¦co2¦dioxide¦gas¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6462 | 0.8939 | 0.6257 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦h2 |  | fire_fighting¦h2 | query | fire_fighting¦hvac | match | false | 1 | 1 | 23.5717 | 0.6374 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting¦h2 | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR H2, CO2 GAS STORAGE SHELTER | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | H2, CO2 GAS STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦h2 |  | fire_fighting¦h2 | query | fire_fighting¦hvac | match | false | 39 | 3 | 20.0824 | 0.5800 | 0.0260 | 0.0260 | hybrid | structured_cell_found_text_preferred | fire_fighting¦h2 | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138502 | P&ID OF CLEAN AGENT SYSTEM FOR AUX. LEB | P&ID ¦ Piping and Instrumentation Diagram |  | CLEAN AGENT SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for CLEAN AGENT SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7155 | 0.9146 | 0.6403 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5883 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138512 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR AUX. LEB | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | PIPE LAYOUT AND DETAIL for AUX. LEB ¦ Auxiliary Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | aux¦auxiliary¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7177 | 0.7753 | 0.5427 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | false | 10 | 3 | 5.8906 | 0.4871 | 0.0302 | 0.0302 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138522 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR AUX. LEB | CALCULATION |  | CLEAN AGENT SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Calculation sheet for CLEAN AGENT SYSTEM |  | AUX. LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦clean¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 0.6479 | 0.8944 | 0.8944 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | false | 5 | 4 | 1.1615 | 0.4402 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AUX. LEB | ARRANGEMENT |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | ARRANGEMENT for AUX. LEB ¦ Auxiliary Local Electrical Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | aux¦auxiliary¦electrical¦leb¦local |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4252 | 0.3609 | 0.3068 | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 4 | 1 | 7.0774 | 0.4177 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138541 | FIRE ALARM SYSTEM LAYOUT FOR AUX. LEB | LAYOUT |  | FIRE ALARM SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Layout Drawing for AUX. LEB ¦ Auxiliary Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | aux¦auxiliary¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6600 | 0.5480 | 0.5480 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 18.2399 | 0.5421 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AUX. LEB | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | false | 49 | 63 | 14.9275 | 0.4896 | 0.0173 | 0.0173 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138601 | P&ID OF STAND PIPE SYSTEM FOR ST BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pipe¦stand¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6127 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-138602 | P&ID OF SPRINKLER SYSTEM FOR ST BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | SPRINKLER SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for SPRINKLER SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | sprinkler¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7371 | 0.9211 | 0.6448 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6101 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-138603 | P&ID OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | PRE - ACTION SPRINKLER SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for PRE - ACTION SPRINKLER SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | action¦pre¦sprinkler¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7236 | 0.9171 | 0.6420 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5932 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138604 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | WATER SPRAY SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | spray¦stg¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5948 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138606 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | WATER SPRAY SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | spray¦stg¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6153 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138608 | P&ID of Clean agent system for Excitation Panel Room for ST Building | P&ID ¦ Piping and Instrumentation Diagram |  | Clean agent system | ST Building ¦ Steam Turbine Building |  | P&ID ¦ Piping and Instrumentation Diagram for Clean agent system |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7145 | 0.9143 | 0.6400 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5938 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ST BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | PIPE LAYOUT AND DETAIL for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6661 | 0.6198 | 0.6198 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 3 | 9.8406 | 0.5183 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-138612 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR ST BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | PIPE LAYOUT AND DETAIL for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6661 | 0.6198 | 0.6198 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 9.8406 | 0.5177 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-138613 | PIPE LAYOUT AND DETAIL OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | PIPE LAYOUT AND DETAIL |  | PRE - ACTION SPRINKLER SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | PIPE LAYOUT AND DETAIL for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6661 | 0.6198 | 0.6198 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 4 | 2 | 9.8406 | 0.5237 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138614 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | PIPE LAYOUT AND DETAIL |  | WATER SPRAY SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | PIPE LAYOUT AND DETAIL for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6661 | 0.6198 | 0.6198 | FA | 2EF2030W16A01 | (Lube Oil Sys.) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | 2007-10-23 | 2008-01-22 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | stg | match | false | 3 | 1 | 11.6960 | 0.5771 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-06-10 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-24 | 2024-09-23 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138616 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | PIPE LAYOUT AND DETAIL |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | PIPE LAYOUT AND DETAIL for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6661 | 0.6198 | 0.6198 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 12 | 1 | 4.8686 | 0.5263 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138618 | Pipe Layout and detail of Clean agent system for Excitation Panel Room for ST Building | Pipe Layout and detail |  |  | ST Building ¦ Steam Turbine Building |  | Pipe Layout and detail for ST Building ¦ Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6024 | 0.6007 | 0.6007 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 12 | 1 | 3.9005 | 0.4999 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-138622 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR ST BUILDING | HYDRAULIC CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | HYDRAULIC CALCULATION for ST BUILDING ¦ Steam Turbine BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6734 | 0.6687 | 0.6687 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 11 | 1 | 3.9005 | 0.4399 | 0.0305 | 0.0305 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-138623 | HYDRAULIC CALCULATION OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | HYDRAULIC CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | HYDRAULIC CALCULATION for ST BUILDING ¦ Steam Turbine BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6734 | 0.6687 | 0.6687 | FI | 0CF6010W12A04 | Pre-Excavation(GTG, HRSG,STG Area) Block #1 | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-05-15 | 2007-06-30 | civil_design | civil_design | match | stg |  | stg | query | gtg¦hrsg¦stg | match | false | 1 | 8 | 9.3831 | 0.3809 | 0.0311 | 0.0311 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138624 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL FOR ST BUILDING | HYDRAULIC CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | HYDRAULIC CALCULATION for ST BUILDING ¦ Steam Turbine BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6734 | 0.6687 | 0.6687 | FI | 1EF2030W16A01 | (Lube Oil Sys.) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2007-10-23 | 2008-01-22 | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 3 | 11.1438 | 0.5484 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-07-25 | 2024-08-24 | 2024-09-23 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138626 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | HYDRAULIC CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | HYDRAULIC CALCULATION for ST BUILDING ¦ Steam Turbine BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6734 | 0.6687 | 0.6687 | FI | 1EF2030W16A01 | (Lube Oil Sys.) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2007-10-23 | 2008-01-22 | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 13 | 3 | 4.8677 | 0.4857 | 0.0296 | 0.0296 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-07-25 | 2024-08-24 | 2024-09-23 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138628 | Flow calculation of Clean Agent system for Excitation Panel Room for ST Building | Flow calculation |  |  | ST Building ¦ Steam Turbine Building |  | Flow calculation for ST Building ¦ Steam Turbine Building | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5640 | 0.6359 | 0.6359 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 11 | 1 | 3.9005 | 0.4542 | 0.0305 | 0.0305 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST BUILDING | ARRANGEMENT |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | ARRANGEMENT for ST BUILDING ¦ Steam Turbine BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4603 | 0.3714 | 0.3157 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 3 | 11.4031 | 0.4100 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138641 | FIRE ALARM SYSTEM LAYOUT FOR ST BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | Layout Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6639 | 0.6192 | 0.6192 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 1 | 22.0451 | 0.6004 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 24 | 12 | 18.8774 | 0.5287 | 0.0258 | 0.0258 | hybrid | structured_cell_found_text_preferred | fire_fighting¦stg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦fire¦stg |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5703 | 0.6377 | 0.6377 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 3 | 18.8774 | 0.4659 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | ST BUILDING ¦ Steam Turbine BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦fire¦stg |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 |  | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 9 | 11 | 18.8774 | 0.4721 | 0.0286 | 0.0214 | hybrid | structured_no_phase | fire_fighting¦stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138702 | P&ID OF CLEAN AGENT SYSTEM FOR ST#1 LEB | P&ID ¦ Piping and Instrumentation Diagram |  | CLEAN AGENT SYSTEM | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for CLEAN AGENT SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7155 | 0.9146 | 0.6403 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | electrical¦fire_fighting¦stg |  | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5818 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138712 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#1 LEB | PIPE LAYOUT AND DETAIL |  |  | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6389 | 0.6117 | 0.6117 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 48 | 7 | 1.2352 | 0.4804 | 0.0242 | 0.0242 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138722 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#1 LEB | FLOW CALCULATION |  |  | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | FLOW CALCULATION for ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.5840 | 0.8752 | 0.8752 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 1 | 18 | 5.7347 | 0.3851 | 0.0292 | 0.0292 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#1 LEB | ARRANGEMENT |  |  | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | ARRANGEMENT for ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦leb¦local¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4086 | 0.3559 | 0.3025 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | gsut_uat¦stg | match | false | 6 | 12 | 8.0965 | 0.3766 | 0.0290 | 0.0290 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138741 | FIRE ALARM SYSTEM LAYOUT FOR ST#1 LEB | LAYOUT |  | FIRE ALARM SYSTEM | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | Layout Drawing for ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6203 | 0.6061 | 0.6061 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting¦stg | stg | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 1 | 19.4366 | 0.5453 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#1 LEB | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting¦stg |  | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 42 | 61 | 15.8470 | 0.4897 | 0.0181 | 0.0181 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting¦stg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#1 LEB | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | BATTERY CALCULATION for FIRE ALARM SYSTEM |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦electrical¦fire¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.5150 | 0.8545 | 0.8545 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting¦stg | stg | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 4 | 1 | 15.8470 | 0.4415 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#1 LEB | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | ST#1 LEB ¦ Steam Turbine#1 Local Electrical Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦electrical¦fire¦leb¦local¦stg |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 |  | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2008-11-01 | 2008-12-15 |  | commissioning | query_unknown | electrical¦fire_fighting¦stg |  | electrical¦fire_fighting¦stg | query | fire_fighting¦hrsg | match | false | 16 | 5 | 15.1475 | 0.5126 | 0.0285 | 0.0214 | hybrid | structured_no_phase | electrical¦fire_fighting¦stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138802 | P&ID OF CLEAN AGENT SYSTEM FOR ST#2 LEB | P&ID ¦ Piping and Instrumentation Diagram |  | CLEAN AGENT SYSTEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | P&ID ¦ Piping and Instrumentation Diagram for CLEAN AGENT SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7155 | 0.9146 | 0.6403 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | electrical¦fire_fighting¦stg |  | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5884 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138812 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#2 LEB | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6324 | 0.6097 | 0.6097 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦fire_fighting¦stg | stg | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 12 | 5 | 5.8906 | 0.4826 | 0.0293 | 0.0293 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138822 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#2 LEB | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | FLOW CALCULATION for CLEAN AGENT SYSTEM |  | ST #2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦clean¦electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.5975 | 0.8793 | 0.8793 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦fire_fighting¦stg | stg | electrical¦fire_fighting¦stg | query | stg | match | false | 3 | 38 | 4.3991 | 0.3627 | 0.0261 | 0.0261 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#2 LEB | ARRANGEMENT |  |  | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | ARRANGEMENT for ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦leb¦local¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4002 | 0.3534 | 0.3004 | FA | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | gsut_uat¦stg | match | false | 6 | 7 | 8.6080 | 0.3967 | 0.0301 | 0.0301 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138841 | FIRE ALARM SYSTEM LAYOUT FOR ST#2 LEB | LAYOUT |  | FIRE ALARM SYSTEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | Layout Drawing for ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6106 | 0.6032 | 0.6032 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting¦stg | stg | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 1 | 18.2399 | 0.5517 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#2 LEB | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting¦stg |  | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 54 | 78 | 14.9275 | 0.4881 | 0.0160 | 0.0160 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting¦stg | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#2 LEB | CALCULATION |  | FIRE ALARM SYSTEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | Calculation sheet for FIRE ALARM SYSTEM |  | ST #2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦electrical¦fire¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.5130 | 0.8539 | 0.8539 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting¦stg | stg | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 7 | 1 | 14.6503 | 0.4818 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#2 LEB | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | ST#2 LEB ¦ Steam Turbine#2 Local Electrical Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦electrical¦fire¦leb¦local¦stg |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 |  | 2CF1600W38A13 | (HRSG #21 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2008-11-01 | 2008-12-15 |  | commissioning | query_unknown | electrical¦fire_fighting¦stg |  | electrical¦fire_fighting¦stg | query | fire_fighting¦hrsg | match | false | 8 | 2 | 15.4601 | 0.5336 | 0.0308 | 0.0231 | hybrid | structured_no_phase | electrical¦fire_fighting¦stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138901 | P&ID OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5939 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138902 | P&ID OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | P&ID ¦ Piping and Instrumentation Diagram |  | WATER SPRAY SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | spray¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5846 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM |  |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8189 | 0.8057 | 0.5640 | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 4 | 10.2173 | 0.4581 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138912 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | PIPE LAYOUT AND DETAIL |  | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for WATER SPRAY SYSTEM |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | spray¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7060 | 0.9118 | 0.6383 | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 13.8506 | 0.4843 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138922 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | CALCULATION |  | WATER SPRAY SYSTEM |  |  | Calculation sheet for WATER SPRAY SYSTEM |  | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | spray¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7476 | 0.7843 | 0.7843 | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 9.1931 | 0.4942 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR DEAERATOR SUPPORT STRUCTURE | ARRANGEMENT |  |  |  |  | ARRANGEMENT |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement |  |  | generic | match | match | query_unscoped | passed |  | 0.3333 | 0.8688 | 0.4940 | 0.4199 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 34 | 756 | 10.9575 | 0.4533 | 0.0119 | 0.0089 | hybrid | structured_no_system |  | civil_design |  | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.60 | 0.42 | needs_review | default_fc_window;rule_scope_status=query_unscoped;rule_score_medium;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138941 | FIRE ALARM SYSTEM LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | LAYOUT |  | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6352 | 0.5405 | 0.5405 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 3 | 1 | 18.2399 | 0.5702 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 21 | 91 | 19.3818 | 0.4913 | 0.0190 | 0.0190 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139001 | P&ID OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6029 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139002 | P&ID of Clean Agent system for Administration & Social Building | P&ID ¦ Piping and Instrumentation Diagram |  | Clean Agent system | Administration & Social Building |  | P&ID ¦ Piping and Instrumentation Diagram for Clean Agent system |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7167 | 0.9150 | 0.6405 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6213 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139011 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | PIPE LAYOUT AND DETAIL for ADMINISTRATION & SOCIAL BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7572 | 0.7872 | 0.5510 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 3 | 9.8406 | 0.5192 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139012 | Pipe Layout and detail of Clean Agent system for Administration & Social Building | Pipe Layout and detail |  | Clean Agent system | Administration & Social Building |  | Pipe Layout and detail for Administration & Social Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6961 | 0.7688 | 0.5382 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 4 | 9.8406 | 0.5431 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139023 | Flow calculation of Clean Agent system for Administration & Social Building | Flow calculation |  |  | Administration & Social Building |  | Flow calculation for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7560 | 0.7868 | 0.7868 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 332 | 7 | 4.3685 | 0.5326 | 0.0175 | 0.0131 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ADMINISTRATION & SOCIAL BUILDING | ARRANGEMENT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | ARRANGEMENT for ADMINISTRATION & SOCIAL BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | administration¦social |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5159 | 0.3881 | 0.3299 | FA | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 42 | 22.7898 | 0.4916 | 0.0262 | 0.0157 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139041 | FIRE ALARM SYSTEM LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5763 | 0.5229 | 0.5229 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 22.0451 | 0.5869 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 25 | 14 | 18.8774 | 0.5183 | 0.0253 | 0.0253 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139043 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.5975 | 0.7392 | 0.7392 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 3 | 18.8774 | 0.4671 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139044 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦fire |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 |  | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting | match | false | 7 | 1 | 25.5441 | 0.5662 | 0.0313 | 0.0235 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139101 | P&ID OF STAND PIPE SYSTEM FOR SECURITY BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM | SECURITY BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6102 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139103 | P&ID OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  |  | SECURITY BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for SECURITY BUILDING |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7139 | 0.9142 | 0.6399 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 13 | 4 | 28.5340 | 0.6718 | 0.0293 | 0.0220 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139111 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR SECURITY BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | SECURITY BUILDING |  | PIPE LAYOUT AND DETAIL for SECURITY BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7915 | 0.7974 | 0.5582 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 9.8406 | 0.5102 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139113 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | PIPE LAYOUT AND DETAIL |  |  | SECURITY BUILDING |  | PIPE LAYOUT AND DETAIL for SECURITY BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7915 | 0.7974 | 0.5582 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 29 | 21 | 22.5014 | 0.5176 | 0.0236 | 0.0177 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139123 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | FLOW CALCULATION |  |  | SECURITY BUILDING |  | FLOW CALCULATION for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7988 | 0.9396 | 0.9396 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 324 | 10 | 4.3685 | 0.5119 | 0.0169 | 0.0127 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SECURITY BUILDING | ARRANGEMENT |  |  | SECURITY BUILDING |  | ARRANGEMENT for SECURITY BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | security |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5698 | 0.4043 | 0.3436 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 28 | 211 | 10.9843 | 0.4621 | 0.0151 | 0.0113 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139141 | FIRE ALARM SYSTEM LAYOUT FOR SECURITY BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING | Substation | Security Configuration & Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6386 | 0.6116 | 0.6116 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 22.0451 | 0.5870 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | SECURITY BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 24 | 12 | 18.8774 | 0.5239 | 0.0258 | 0.0258 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139143 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | SECURITY BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6078 | 0.8824 | 0.8824 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 3 | 18.8774 | 0.4743 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139144 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | SECURITY BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦fire |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 |  | 0CF4500W90A09 | (Fire Fighting BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-02-02 | 2008-03-31 |  | commissioning | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 14 | 2 | 18.7344 | 0.4737 | 0.0296 | 0.0222 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR MAIN GATE HOUSE | ARRANGEMENT |  |  | MAIN GATE HOUSE |  | ARRANGEMENT for MAIN GATE HOUSE |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | gate¦house¦main |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5329 | 0.3932 | 0.3342 | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 13 | 17.1992 | 0.5104 | 0.0298 | 0.0134 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139241 | FIRE ALARM SYSTEM LAYOUT FOR MAIN GATE HOUSE | LAYOUT |  | FIRE ALARM SYSTEM | MAIN GATE HOUSE |  | Layout Drawing for MAIN GATE HOUSE | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6086 | 0.5326 | 0.5326 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | design_drawing | civil_design | compatible | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 18.2399 | 0.5447 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR MAIN GATE HOUSE | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | MAIN GATE HOUSE |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 26.4345 | 0.5303 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139301 | P&ID OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM | X-RAY SEARCHING ROOM |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.5735 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | PIPE LAYOUT AND DETAIL |  |  | X-RAY SEARCHING ROOM |  | PIPE LAYOUT AND DETAIL for X-RAY SEARCHING ROOM |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7071 | 0.7721 | 0.5405 | FA | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 9 | 3 | 31.5903 | 0.5218 | 0.0304 | 0.0171 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR X-RAY SEARCHING ROOM | ARRANGEMENT |  |  | X-RAY SEARCHING ROOM |  | ARRANGEMENT for X-RAY SEARCHING ROOM |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | ray¦room¦searching |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4991 | 0.3831 | 0.3256 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 18 | 702 | 10.9575 | 0.3812 | 0.0141 | 0.0079 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139341 | FIRE ALARM SYSTEM LAYOUT FOR X-RAY SEARCHING ROOM | LAYOUT |  | FIRE ALARM SYSTEM | X-RAY SEARCHING ROOM |  | Layout Drawing for X-RAY SEARCHING ROOM | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5456 | 0.5137 | 0.5137 | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 18.2399 | 0.4997 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR X-RAY SEARCHING ROOM | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | X-RAY SEARCHING ROOM |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 26.4345 | 0.5130 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139401 | P&ID OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  |  | FIRE BRIGADE BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for FIRE BRIGADE BUILDING |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7120 | 0.9136 | 0.6395 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 1 | 1 | 35.1160 | 0.7059 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139411 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | PIPE LAYOUT AND DETAIL |  |  | FIRE BRIGADE BUILDING |  | PIPE LAYOUT AND DETAIL for FIRE BRIGADE BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7945 | 0.7984 | 0.5588 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 10 | 4 | 31.5903 | 0.5440 | 0.0299 | 0.0224 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE BRIGADE BUILDING | ARRANGEMENT |  |  | FIRE BRIGADE BUILDING |  | ARRANGEMENT for FIRE BRIGADE BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | brigade¦fire |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4760 | 0.3761 | 0.3197 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 1 | 46 | 17.7462 | 0.4977 | 0.0258 | 0.0194 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139441 | FIRE ALARM SYSTEM LAYOUT FOR FIRE BRIGADE BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | Layout Drawing for FIRE BRIGADE BUILDING | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6847 | 0.5554 | 0.5554 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 28.8069 | 0.6324 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 17 | 8 | 25.7604 | 0.5515 | 0.0277 | 0.0277 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139443 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6757 | 0.9027 | 0.9027 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 25.7604 | 0.5023 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139444 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦fire |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 |  | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 9 | 3 | 25.7604 | 0.5092 | 0.0304 | 0.0228 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139501 | P&ID OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  |  | WORKSHOP & STORAGE BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for WORKSHOP & STORAGE BUILDING |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7338 | 0.9201 | 0.6441 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 6 | 2 | 28.8561 | 0.6933 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-139502 | P&ID OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  |  | WORKSHOP & STORAGE BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for WORKSHOP & STORAGE BUILDING |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7338 | 0.9201 | 0.6441 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 6 | 3 | 28.8561 | 0.6682 | 0.0310 | 0.0233 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139511 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | PIPE LAYOUT AND DETAIL |  |  | WORKSHOP & STORAGE BUILDING |  | PIPE LAYOUT AND DETAIL for WORKSHOP & STORAGE BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7869 | 0.7961 | 0.5572 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 10 | 13 | 31.5903 | 0.5476 | 0.0280 | 0.0210 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-139512 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | PIPE LAYOUT AND DETAIL |  |  | WORKSHOP & STORAGE BUILDING |  | PIPE LAYOUT AND DETAIL for WORKSHOP & STORAGE BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7869 | 0.7961 | 0.5572 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 14 | 24 | 23.5464 | 0.4916 | 0.0254 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-139522 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | CALCULATION |  |  | WORKSHOP & STORAGE BUILDING |  | Calculation sheet for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8451 | 0.9535 | 0.9535 | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 10 | 26 | 11.3127 | 0.4657 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WORKSHOP & STORAGE BUILDING | ARRANGEMENT |  |  | WORKSHOP & STORAGE BUILDING |  | ARRANGEMENT for WORKSHOP & STORAGE BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | storage¦workshop |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5006 | 0.3835 | 0.3260 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 3 | 120 | 16.9855 | 0.4881 | 0.0214 | 0.0161 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139541 | FIRE ALARM SYSTEM LAYOUT FOR MAINTENANCE AND WORKSHOP & STORAGE BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | MAINTENANCE AND WORKSHOP & STORAGE BUILDING |  | Layout Drawing for MAINTENANCE AND WORKSHOP & STORAGE BUILDING | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | maintenance¦storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6134 | 0.5340 | 0.5340 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 24.2567 | 0.6045 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | WORKSHOP & STORAGE BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 28 | 11 | 18.8774 | 0.5390 | 0.0254 | 0.0254 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139543 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | WORKSHOP & STORAGE BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6514 | 0.8954 | 0.8954 | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 1 | 18.4555 | 0.4715 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139544 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | MATRIX |  | FIRE ALARM SYSTEM | WORKSHOP & STORAGE BUILDING |  | MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | matrix | data_sheet | alarm¦fire |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.6852 | 0.6722 | 0.4706 |  | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 |  | civil_design | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 13 | 4 | 18.8774 | 0.5067 | 0.0293 | 0.0220 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139601 | P&ID OF STAND PIPE SYSTEM FOR CPP BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | STAND PIPE SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for STAND PIPE SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7575 | 0.9273 | 0.6491 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 1 | 29.2064 | 0.6361 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate¦fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139602 | P&ID OF CLEAN AGENT SYSTEM FOR CPP BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | CLEAN AGENT SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for CLEAN AGENT SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7155 | 0.9146 | 0.6403 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 1 | 29.2064 | 0.6396 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate¦fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-139603 | P&ID OF SPRINKLER SYSTEM FOR CPP BUILDING | P&ID ¦ Piping and Instrumentation Diagram |  | SPRINKLER SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | P&ID ¦ Piping and Instrumentation Diagram for SPRINKLER SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | sprinkler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7371 | 0.9211 | 0.6448 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 29.2804 | 0.6314 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate¦fire_fighting | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL for CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7761 | 0.7928 | 0.5550 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 4 | 9.8406 | 0.4948 | 0.0320 | 0.0320 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139612 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL for CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7761 | 0.7928 | 0.5550 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 4 | 9.8406 | 0.5173 | 0.0320 | 0.0320 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-139613 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL for CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7761 | 0.7928 | 0.5550 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 3 | 9.8406 | 0.4861 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139622 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CPP BUILDING | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦clean |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5477 | 0.6310 | 0.6310 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 5.1115 | 0.4973 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-139623 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CPP BUILDING | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | sprinkler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5603 | 0.6348 | 0.6348 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 5.1115 | 0.4995 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CPP BUILDING | ARRANGEMENT |  |  | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | ARRANGEMENT for CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | condensate¦cpp¦plant¦polising |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4023 | 0.3540 | 0.3009 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | 6 | 2 |  | 0.3836 | 0.0313 | 0.0313 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139641 | FIRE ALARM SYSTEM LAYOUT FOR CPP BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | Layout Drawing for CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5904 | 0.5271 | 0.5271 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | condensate¦fire_fighting | fire_fighting | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 1 | 22.0451 | 0.5690 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CPP BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | false | 24 | 17 | 18.8774 | 0.5076 | 0.0249 | 0.0249 | hybrid | structured_cell_found_text_preferred | condensate¦fire_fighting | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | ARRANGEMENT | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  | CHEMICAL DOSING SHELTER |  | ARRANGEMENT for STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4440 | 0.3665 | 0.3115 | FA | 3EF6500W00A01 | (STG #30 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | hrsg¦stg¦wts |  | hrsg¦stg¦wts | query | gsut_uat¦stg | match | false | 3 | 9 | 29.1432 | 0.6187 | 0.0304 | 0.0304 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139741 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | LAYOUT | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Layout Drawing for CHEMICAL DOSING SHELTER |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.5845 | 0.6420 | 0.6420 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦stg¦wts | hrsg | fire_fighting¦hrsg¦stg¦wts | query | gsut_uat¦stg | match | false | 1 | 4 | 25.6782 | 0.6324 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦hrsg¦stg¦wts | civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | SINGLE LINE DIAGRAM | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦generator¦heat¦hrsg¦recovery¦steam¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 1EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦stg¦wts |  | fire_fighting¦hrsg¦stg¦wts | query | fgp¦gtg¦hrsg | match | false | 904 | 1 | 15.7078 | 0.6354 | 0.0174 | 0.0174 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hrsg¦stg¦wts | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR HRSG | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  | CHEMICAL DOSING SHELTER |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 3EF1600W00A01.1 | (HRSG #32 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg¦wts |  | hrsg¦wts | query | hrsg | match | false | 6 | 9 | 22.6890 | 0.6081 | 0.0296 | 0.0296 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139841 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | LAYOUT | HRSG ¦ Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Layout Drawing for CHEMICAL DOSING SHELTER |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.5943 | 0.6450 | 0.6450 | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦wts | hrsg | fire_fighting¦hrsg¦wts | query | hrsg | match | false | 10 | 5 | 19.4899 | 0.6316 | 0.0297 | 0.0297 | hybrid | structured_preferred | fire_fighting¦hrsg¦wts | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-07 | 2024-03-22 | 2024-04-21 | 2024-05-21 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR HRSG | SINGLE LINE DIAGRAM | HRSG ¦ Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 2EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦wts |  | fire_fighting¦hrsg¦wts | query | fgp¦gtg¦hrsg | match | false | 870 | 4 | 13.2071 | 0.6209 | 0.0167 | 0.0167 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hrsg¦wts | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-139901 | P&ID OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | P&ID ¦ Piping and Instrumentation Diagram | STG ¦ Steam Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for WATER SPRAY SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | generator¦spray¦steam¦stg¦turbine¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7054 | 0.9116 | 0.6381 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | false | 1 | 31 | 29.2804 | 0.5054 | 0.0274 | 0.0274 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦procurement | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-139911 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | PIPE LAYOUT AND DETAIL | STG ¦ Steam Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7359 | 0.7808 | 0.7808 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | fire_fighting¦stg | stg | fire_fighting¦stg | query | gsut_uat¦stg | match | false | 1 | 7 | 22.2070 | 0.5660 | 0.0313 | 0.0235 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-139921 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | HYDRAULIC CALCULATION | STG EXCITATION TRANSFORMER ¦ Steam Turbine Generator EXCITATION TRANSFORMER | WATER SPRAY SYSTEM |  |  | HYDRAULIC CALCULATION for STG EXCITATION TRANSFORMER ¦ Steam Turbine Generator EXCITATION TRANSFORMER |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | excitation¦generator¦steam¦stg¦transformer¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5071 | 0.5721 | 0.5721 | FI | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | false | 13 | 1 | 28.8436 | 0.5874 | 0.0301 | 0.0301 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | civil_design | 10 |  |  |  | 2024-11-08 | 2024-12-08 | 2025-01-07 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG EXCITATION TRANSFORMER | ARRANGEMENT | STG EXCITATION TRANSFORMER ¦ Steam Turbine Generator EXCITATION TRANSFORMER |  |  |  | ARRANGEMENT for STG EXCITATION TRANSFORMER ¦ Steam Turbine Generator EXCITATION TRANSFORMER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | excitation¦generator¦steam¦stg¦transformer¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4398 | 0.3653 | 0.3105 | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | gsut_uat¦stg |  | gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | false | 13 | 1 | 27.9157 | 0.6703 | 0.0301 | 0.0226 | hybrid | structured_preferred | gsut_uat¦stg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139941 | FIRE ALARM SYSTEM LAYOUT FOR STG EXCITATION TRANSFORMER | LAYOUT | STG EXCITATION TRANSFORMER ¦ Steam Turbine Generator EXCITATION TRANSFORMER | FIRE ALARM SYSTEM |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | false | 13 | 1 | 28.8436 | 0.6606 | 0.0301 | 0.0226 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG EXCITATION TRANSFORMER | SINGLE LINE DIAGRAM | STG EXCITATION TRANSFORMER ¦ Steam Turbine Generator EXCITATION TRANSFORMER | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | fire_fighting¦gsut_uat¦stg |  | fire_fighting¦gsut_uat¦stg | query | stg | match | false | 3 | 1 | 5.6714 | 0.5137 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦engineering | 5 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-140001 | PIPING MATERIAL SPECIFICATION | SPECIFICATION |  | PIPING |  |  | Technical Specification for PIPING |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | piping |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5672 | 0.6368 | 0.4458 | FA | 0EF6020W58A01 | (Piping) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 2 | 4 | 23.3500 | 0.6855 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-140002 | PIPING INSULATION SPECIFICATION | SPECIFICATION |  | PIPING |  |  | Insulation Specification for PIPING |  | Piping Insulation Specification | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | insulation_specification | insulation_specification | piping |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9448 | 0.9834 | 0.6884 | FA | 0EF6020W58A10 | (Piping Insulation) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 2 | 2 | 24.4809 | 0.6648 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-03-17 | 2024-04-01 | 2024-04-16 | 2024-05-01 | 2024-05-31 | 2024-06-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0ZEN-140003 | MANUAL VALVE LIST | LIST |  |  |  |  | Valve List |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.7667 | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | manual | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 1 | 30.3466 | 0.7074 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | delivery¦procurement¦installation |  | 2024-12-17 | 2025-01-16 | 2025-02-15 | 2025-03-02 | 2025-03-17 | 2025-04-01 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140004 | PIPING SPECIALTY LIST | LIST |  | PIPING |  |  | LIST for PIPING | [5 empty] | rule_query | other | other | list | st_line_list_for_stg_piping | piping | st¦stg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.5000 | 0.7375 | 0.5713 | 0.5713 |  | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | 1 | 4 | 32.0146 | 0.5642 | 0.0320 | 0.0180 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140005 | PIPING LINE LIST | LIST |  | PIPING |  |  | LIST for PIPING | [5 empty] | rule_query | other | other | list | st_line_list_for_stg_piping | piping | st¦stg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.5000 | 0.7375 | 0.5713 | 0.5713 |  | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | 1 | 10 | 32.0146 | 0.4955 | 0.0307 | 0.0173 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140006 | PIPING TERMINAL POINT LIST BETWEEN FCHPP AND FGP | LIST | FCHPP AND FGP ¦ Fuel Conditioning & Heating Preparation Package AND Fuel Gas Package | PIPING |  |  | LIST for FCHPP AND FGP ¦ Fuel Conditioning & Heating Preparation Package AND Fuel Gas Package | [5 empty] | rule_query | other | list | list | instrument_list | conditioning¦fchpp¦fgp¦fuel¦gas¦heating¦preparation | fgp | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6609 | 0.6183 | 0.6183 |  | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp¦hvac |  | fgp¦hvac | query | fgp | match | false | 7 | 2 | 13.9919 | 0.6102 | 0.0311 | 0.0311 | hybrid | structured_preferred | fgp¦hvac | procurement | 10 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBA-140011 | STRESS ANALYSIS REPORT FOR HP STEAM SYSTEM | REPORT |  | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | REPORT for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7451 | 0.9235 | 0.6465 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 10.1539 | 0.5681 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBC-140012 | STRESS ANALYSIS REPORT FOR IP STEAM SYSTEM | REPORT |  | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | REPORT for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7482 | 0.9245 | 0.6471 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 10.1539 | 0.6187 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBS-140013 | STRESS ANALYSIS REPORT FOR PROCESS STEAM SYSTEM | REPORT |  | PROCESS STEAM SYSTEM |  |  | REPORT for PROCESS STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7683 | 0.9305 | 0.6513 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 6.7693 | 0.6095 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LAB-140014 | STRESS ANALYSIS REPORT FOR FEED WATER SYSTEM | REPORT |  | FEED WATER SYSTEM |  |  | REPORT for FEED WATER SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | feed¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7648 | 0.9295 | 0.6506 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | false | 1 | 1 | 21.6028 | 0.6223 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design | 1 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0EKG-140015 | STRESS ANALYSIS REPORT FOR FUEL SYSTEM | REPORT |  | FUEL SYSTEM |  |  | REPORT for FUEL SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | fuel |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7684 | 0.9305 | 0.6514 | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 135 | 212 | 7.7981 | 0.4650 | 0.0088 | 0.0066 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBG-140016 | STRESS ANALYSIS REPORT FOR LP STEAM SYSTEM | REPORT |  | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | REPORT for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7422 | 0.9227 | 0.6459 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 10.1539 | 0.5775 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LCA-140017 | STRESS ANALYSIS REPORT FOR CONDENSATE SYSTEM | REPORT |  | CONDENSATE SYSTEM |  |  | REPORT for CONDENSATE SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7640 | 0.9292 | 0.6504 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 13.4774 | 0.5982 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140020 | KEY PLAN DRAWING | PLAN DRAWING |  |  |  |  | PLAN DRAWING |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6060 | 0.6485 | 0.6485 | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 327 | 24.0608 | 0.4477 | 0.0187 | 0.0084 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.29 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140021 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 GROUND FLOOR | ARRANGEMENT DRAWING |  | PIPING | ST BLDG #1 ¦ Steam Turbine Building #1 |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping¦stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 3 | 14.8695 | 0.5530 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140022 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 OPERATING FLOOR | ARRANGEMENT DRAWING |  | PIPING | ST BLDG #1 ¦ Steam Turbine Building #1 |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping¦stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 3 | 14.8695 | 0.5592 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140023 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 GROUND FLOOR | PIPING ARRANGEMENT DRAWING |  | Piping | ST BLDG #2 ¦ Steam Turbine Building #2 |  | PIPING ARRANGEMENT DRAWING for Piping |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | piping¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8446 | 0.7784 | 0.7784 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 12.0772 | 0.5591 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140024 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 OPERATING FLOOR | PIPING ARRANGEMENT DRAWING |  | Piping | ST BLDG #2 ¦ Steam Turbine Building #2 |  | PIPING ARRANGEMENT DRAWING for Piping |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | piping¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8446 | 0.7784 | 0.7784 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 12.0772 | 0.5585 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140025 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #1 AREA | PIPING ARRANGEMENT DRAWING | AIR COOLED CONDENSER #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for AIR COOLED CONDENSER #1 |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7544 | 0.9263 | 0.9263 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc | acc | acc | query |  | activity_unscoped | true | 366 | 19 | 12.6343 | 0.5820 | 0.0150 | 0.0090 | hybrid | structured_phase_gap | acc | system_design |  | 2024-11-17 | 2024-12-17 | 2025-01-16 | 2025-01-31 | 2025-02-15 | 2025-03-02 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140026 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #2 & H2 CO2 N2 STORAGE SHELTER AREA | PIPING ARRANGEMENT DRAWING | AIR COOLED CONDENSER #2 | Piping | H2 CO2 N2 STORAGE SHELTER ¦ Hydrogen Carbon Dioxide Nitrogen STORAGE SHELTER |  | PIPING ARRANGEMENT DRAWING for AIR COOLED CONDENSER #2 |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7458 | 0.9237 | 0.9237 | FA | 2EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 |  | civil_design | civil_design | match | acc¦h2¦n2 | acc | acc¦h2¦n2 | query | n2 | match | false | 1 | 1 | 23.1354 | 0.5798 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc¦h2¦n2 | civil_design | 10 | 2025-07-20 | 2025-08-19 | 2025-09-18 | 2025-10-03 | 2025-10-18 | 2025-11-02 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140027 | PIPING ARRANGEMENT DRAWING FOR ST BLDG PIPE RACK AREA | PIPING ARRANGEMENT DRAWING |  | Piping | ST BLDG ¦ Steam Turbine Building |  | PIPING ARRANGEMENT DRAWING for ST BLDG ¦ Steam Turbine Building |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | bldg¦pipe¦piperack¦rack¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7305 | 0.7442 | 0.7442 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 3 | 10.3003 | 0.5007 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140028 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #1 MAIN PIPE RACK AREA | PIPING ARRANGEMENT DRAWING |  | Piping | ST BLDG #1 ¦ Steam Turbine Building #1 |  | PIPING ARRANGEMENT DRAWING for ST BLDG #1 ¦ Steam Turbine Building #1 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | bldg¦pipe¦piperack¦rack¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7336 | 0.7451 | 0.7451 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 3 | 16.8515 | 0.5118 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140029 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #2 MAIN PIPE RACK AREA | PIPING ARRANGEMENT DRAWING |  | Piping | ST BLDG #2 ¦ Steam Turbine Building #2 |  | PIPING ARRANGEMENT DRAWING for ST BLDG #2 ¦ Steam Turbine Building #2 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | bldg¦pipe¦piperack¦rack¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7322 | 0.7447 | 0.7447 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 17.3933 | 0.5193 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140030 | PIPING ARRANGEMENT DRAWING FOR TO MAIN FCP GATE HOUSE AREA | PIPING ARRANGEMENT DRAWING |  | Piping | GATE HOUSE |  | PIPING ARRANGEMENT DRAWING for Piping |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8446 | 0.7784 | 0.7784 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 299 | 7 | 11.4706 | 0.5891 | 0.0177 | 0.0106 | hybrid | structured_no_system |  | system_design |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140031 | PIPING ARRANGEMENT DRAWING FOR TO ESF AREA | PIPING ARRANGEMENT DRAWING |  | Piping |  |  | PIPING ARRANGEMENT DRAWING for Piping |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8446 | 0.7784 | 0.7784 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 262 | 13 | 11.4706 | 0.5776 | 0.0168 | 0.0101 | hybrid | structured_no_system |  | system_design |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140032 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +0 | PIPING ARRANGEMENT DRAWING | HRSG #1 ¦ Heat Recovery Steam Generator #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #1 ¦ Heat Recovery Steam Generator #1 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7507 | 0.7502 | 0.7502 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 4 | 2 | 34.3262 | 0.7153 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140034 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | HRSG #1 ¦ Heat Recovery Steam Generator #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #1 ¦ Heat Recovery Steam Generator #1 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7507 | 0.7502 | 0.7502 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 2 | 28.3451 | 0.7096 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140036 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +108,000 & ABOVE | PIPING ARRANGEMENT DRAWING | HRSG #1 ¦ Heat Recovery Steam Generator #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #1 ¦ Heat Recovery Steam Generator #1 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7507 | 0.7502 | 0.7502 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 2 | 28.3451 | 0.7165 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140037 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +0 | PIPING ARRANGEMENT DRAWING | HRSG #2 ¦ Heat Recovery Steam Generator #2 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #2 ¦ Heat Recovery Steam Generator #2 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7513 | 0.7504 | 0.7504 | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 4 | 1 | 35.9341 | 0.7252 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140038 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | HRSG #2 ¦ Heat Recovery Steam Generator #2 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #2 ¦ Heat Recovery Steam Generator #2 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7513 | 0.7504 | 0.7504 | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 1 | 29.9530 | 0.7177 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140039 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +108,000 & ABOVE | PIPING ARRANGEMENT DRAWING | HRSG #2 ¦ Heat Recovery Steam Generator #2 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #2 ¦ Heat Recovery Steam Generator #2 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7513 | 0.7504 | 0.7504 | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 1 | 29.9530 | 0.7225 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140040 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +0 | PIPING ARRANGEMENT DRAWING | HRSG #3 ¦ Heat Recovery Steam Generator #3 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #3 ¦ Heat Recovery Steam Generator #3 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7522 | 0.7507 | 0.7507 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 4 | 3 | 36.0038 | 0.6944 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140041 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | HRSG #3 ¦ Heat Recovery Steam Generator #3 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #3 ¦ Heat Recovery Steam Generator #3 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7522 | 0.7507 | 0.7507 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 3 | 30.0228 | 0.6937 | 0.0323 | 0.0323 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140042 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +108,000 & ABOVE | PIPING ARRANGEMENT DRAWING | HRSG #3 ¦ Heat Recovery Steam Generator #3 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #3 ¦ Heat Recovery Steam Generator #3 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7522 | 0.7507 | 0.7507 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 3 | 30.0228 | 0.6970 | 0.0323 | 0.0323 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140043 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +0 | PIPING ARRANGEMENT DRAWING | HRSG #4 ¦ Heat Recovery Steam Generator #4 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #4 ¦ Heat Recovery Steam Generator #4 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7424 | 0.7477 | 0.7477 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 2 | 30.6599 | 0.6998 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140044 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | HRSG #4 ¦ Heat Recovery Steam Generator #4 | Piping |  |  | PIPING ARRANGEMENT DRAWING for HRSG #4 ¦ Heat Recovery Steam Generator #4 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7424 | 0.7477 | 0.7477 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | false | 1 | 2 | 24.6788 | 0.6953 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140045 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +108,000 & ABOVE | ARRANGEMENT DRAWING | HRSG #4 ¦ Heat Recovery Steam Generator #4 | PIPING |  |  | General Arrangement Drawing for HRSG #4 ¦ Heat Recovery Steam Generator #4 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7933 | 0.9380 | 0.9380 | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 5 | 27.4270 | 0.6849 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140046 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +0 | ARRANGEMENT DRAWING | HRSG #5 ¦ Heat Recovery Steam Generator #5 | PIPING |  |  | General Arrangement Drawing for HRSG #5 ¦ Heat Recovery Steam Generator #5 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7977 | 0.9393 | 0.9393 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 2 | 28.2428 | 0.7017 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140047 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +106,000 | ARRANGEMENT DRAWING | HRSG #5 ¦ Heat Recovery Steam Generator #5 | PIPING |  |  | General Arrangement Drawing for HRSG #5 ¦ Heat Recovery Steam Generator #5 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7977 | 0.9393 | 0.9393 | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 5 | 27.4270 | 0.6724 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140048 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +108,000 & ABOVE | ARRANGEMENT DRAWING | HRSG #5 ¦ Heat Recovery Steam Generator #5 | PIPING |  |  | General Arrangement Drawing for HRSG #5 ¦ Heat Recovery Steam Generator #5 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7977 | 0.9393 | 0.9393 | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 1 | 5 | 27.4270 | 0.6806 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1MBA-140049 | PIPING ARRANGEMENT DRAWING FOR GT #1 AREA | ARRANGEMENT DRAWING | GT #1 ¦ Gas Turbine #1 | PIPING |  |  | General Arrangement Drawing for GT #1 ¦ Gas Turbine #1 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6957 | 0.9087 | 0.9087 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 1 | 3.1086 | 0.5783 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2MBA-140050 | PIPING ARRANGEMENT DRAWING FOR GT #2 AREA | ARRANGEMENT DRAWING | GT #2 ¦ Gas Turbine #2 | PIPING |  |  | General Arrangement Drawing for GT #2 ¦ Gas Turbine #2 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7006 | 0.9102 | 0.9102 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 1 | 8.2464 | 0.5928 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3MBA-140051 | PIPING ARRANGEMENT DRAWING FOR GT #3 AREA | ARRANGEMENT DRAWING | GT #3 ¦ Gas Turbine #3 | PIPING |  |  | General Arrangement Drawing for GT #3 ¦ Gas Turbine #3 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6915 | 0.9075 | 0.9075 | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 1 | 8.3144 | 0.5789 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4MBA-140052 | PIPING ARRANGEMENT DRAWING FOR GT #4 AREA | ARRANGEMENT DRAWING | GT #4 ¦ Gas Turbine #4 | PIPING |  |  | General Arrangement Drawing for GT #4 ¦ Gas Turbine #4 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6885 | 0.9065 | 0.9065 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 1 | 3.1086 | 0.5777 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5MBA-140053 | PIPING ARRANGEMENT DRAWING FOR GT #5 AREA | ARRANGEMENT DRAWING | GT #5 ¦ Gas Turbine #5 | PIPING |  |  | General Arrangement Drawing for GT #5 ¦ Gas Turbine #5 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6783 | 0.9035 | 0.9035 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 1 | 3.1086 | 0.5703 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140054 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +0 | ARRANGEMENT DRAWING | BFP ¦ Boiler Feed Pump | PIPING |  |  | General Arrangement Drawing for BFP ¦ Boiler Feed Pump |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦feed¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6965 | 0.9089 | 0.9089 | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | feedwater |  | feedwater | query | feedwater | match | false | 4 | 2 | 24.7520 | 0.6793 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | feedwater | civil_design |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140055 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +111,500 | ARRANGEMENT DRAWING | BFP ¦ Boiler Feed Pump | PIPING |  |  | General Arrangement Drawing for BFP ¦ Boiler Feed Pump |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦feed¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6965 | 0.9089 | 0.9089 | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | feedwater |  | feedwater | query | feedwater | match | false | 3 | 2 | 24.7520 | 0.6834 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | feedwater | civil_design |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140056 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +114,500 | ARRANGEMENT DRAWING | BFP ¦ Boiler Feed Pump | PIPING |  |  | General Arrangement Drawing for BFP ¦ Boiler Feed Pump |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦feed¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6965 | 0.9089 | 0.9089 | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | feedwater |  | feedwater | query | feedwater | match | false | 3 | 2 | 24.7520 | 0.6860 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | feedwater | civil_design |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140057 | PIPING ARRANGEMENT DRAWING FOR DEAERATOR AREA | ARRANGEMENT DRAWING |  | PIPING |  |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 63 | 11 | 13.9400 | 0.5864 | 0.0222 | 0.0133 | hybrid | structured_no_system |  | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140058 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 1 | ARRANGEMENT DRAWING |  | PIPING | MAIN PIPE RACK |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 1 | 5 | 38.8580 | 0.6651 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140059 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 2 | ARRANGEMENT DRAWING |  | PIPING | MAIN PIPE RACK |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 1 | 6 | 39.5500 | 0.6613 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140060 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 3 | ARRANGEMENT DRAWING |  | PIPING | MAIN PIPE RACK |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 1 | 6 | 39.5800 | 0.6639 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140061 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 4 | ARRANGEMENT DRAWING |  | PIPING | MAIN PIPE RACK |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 2 | 5 | 37.2801 | 0.6604 | 0.0315 | 0.0236 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140062 | PIPING ARRANGEMENT DRAWING FOR CCW FIN FAN COOLER AREA | ARRANGEMENT DRAWING | FIN FAN COOLER | PIPING |  |  | General Arrangement Drawing for FIN FAN COOLER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cooler¦fan¦fin |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7129 | 0.9139 | 0.9139 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 3 | 4.0191 | 0.4584 | 0.0323 | 0.0323 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UTF-140063 | PIPING ARRANGEMENT DRAWING FOR AIR COMPRESSOR AREA | ARRANGEMENT DRAWING | AIR COMPRESSOR | PIPING |  |  | General Arrangement Drawing for AIR COMPRESSOR |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | air¦compressor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7382 | 0.9215 | 0.9215 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 15.2116 | 0.6582 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0GRK-140064 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT BLDG AREA | ARRANGEMENT DRAWING |  | PIPING | WATER TREATMENT BLDG ¦ WATER TREATMENT Building |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 6 | 2 | 22.3201 | 0.6597 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-10-12 | 2024-11-11 | 2024-12-11 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGD-140065 | PIPING ARRANGEMENT DRAWING FOR DEMI & POTABLE WATER TANK AREA | ARRANGEMENT DRAWING | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 30 | 13 | 20.3146 | 0.5670 | 0.0248 | 0.0186 | hybrid | structured_no_system |  | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGA-140066 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK A/B AREA | ARRANGEMENT DRAWING | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 24 | 9 | 20.3146 | 0.5719 | 0.0264 | 0.0198 | hybrid | structured_no_system |  | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGA-140067 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK C AREA | ARRANGEMENT DRAWING | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 24 | 9 | 20.3146 | 0.5722 | 0.0264 | 0.0198 | hybrid | structured_no_system |  | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UCB-140068 | PIPING ARRANGEMENT DRAWING FOR CCB AREA | ARRANGEMENT DRAWING |  | Piping | CCB ¦ Central Control Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | ccr¦piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 6 | 9 | 21.3666 | 0.5871 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LCA-140069 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK C AREA | ARRANGEMENT DRAWING | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match |  |  |  |  | condensate | query_unscoped | false | 122 | 2 | 13.2995 | 0.6040 | 0.0216 | 0.0162 | hybrid | structured_no_system |  | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LCA-140070 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A/B AREA | ARRANGEMENT DRAWING | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match |  |  |  |  | condensate | query_unscoped | false | 121 | 2 | 13.2995 | 0.6007 | 0.0217 | 0.0162 | hybrid | structured_no_system |  | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LDK-140071 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 1 | ARRANGEMENT DRAWING |  | Piping | CPP BLDG ¦ CONDENSATE POLISING PLANT Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 7 | 3 | 1.5999 | 0.4155 | 0.0308 | 0.0308 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-11-20 | 2024-12-20 | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LDK-140072 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 2 | ARRANGEMENT DRAWING |  | Piping | CPP BLDG ¦ CONDENSATE POLISING PLANT Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | 5 | 3 | 2.3015 | 0.4167 | 0.0313 | 0.0313 | hybrid | structured_preferred | condensate | civil_design | 10 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0EKG-140073 | PIPING ARRANGEMENT DRAWING FOR GPRS AREA | ARRANGEMENT DRAWING |  | Piping |  |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 63 | 31 | 13.9400 | 0.5811 | 0.0191 | 0.0115 | hybrid | structured_no_system |  | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYE-140074 | PIPING ARRANGEMENT DRAWING FOR MAIN GATE HOUSE AREA | ARRANGEMENT DRAWING |  | Piping | GATE HOUSE |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 81 | 6 | 13.9400 | 0.5997 | 0.0222 | 0.0133 | hybrid | structured_no_system |  | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYF-140075 | PIPING ARRANGEMENT DRAWING FOR SECURITY BUILDING AREA | ARRANGEMENT DRAWING |  | Piping | SECURITY BUILDING |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 6 | 4 | 21.3666 | 0.6000 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYC-140076 | PIPING ARRANGEMENT DRAWING FOR MAIN ADMIN BUILDING AREA | ARRANGEMENT DRAWING |  | Piping | ADMIN BUILDING ¦ Administration BUILDING |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 7 | 8 | 21.3666 | 0.6029 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UST-140077 | PIPING ARRANGEMENT DRAWING FOR MAINTENANCE & WORKSHOP BUILDING AREA | ARRANGEMENT DRAWING |  | Piping | WORKSHOP BUILDING |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 7 | 5 | 21.3666 | 0.6082 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYP-140078 | PIPING ARRANGEMENT DRAWING FOR FIRE BRIGATE AREA | ARRANGEMENT DRAWING |  | Piping |  |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 68 | 11 | 13.8923 | 0.5867 | 0.0219 | 0.0164 | hybrid | structured_no_system |  | system_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UBA-140079 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #2 AREA | ARRANGEMENT DRAWING | STG ¦ Steam Turbine Generator | Piping | ELECTRICAL BUILDING |  | General Arrangement Drawing for STG ¦ Steam Turbine Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6881 | 0.9064 | 0.9064 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 2 | 2 | 31.6696 | 0.7070 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UBA-140080 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #1 & SWAS CONTAINER AREA | ARRANGEMENT DRAWING | STG ¦ Steam Turbine Generator | Piping | ELECTRICAL BUILDING |  | General Arrangement Drawing for STG ¦ Steam Turbine Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6881 | 0.9064 | 0.9064 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 4 | 1 | 29.8927 | 0.7024 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140081 | PIPING ARRANGEMENT DRAWING FOR FGP TP AREA | ARRANGEMENT DRAWING | FGP ¦ Fuel Gas Package | Piping |  |  | General Arrangement Drawing for FGP ¦ Fuel Gas Package |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6824 | 0.9047 | 0.9047 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 12.1217 | 0.7042 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140082 | PIPING ARRANGEMENT DRAWING FOR YARD AREA TO FGP TP | ARRANGEMENT DRAWING | FGP ¦ Fuel Gas Package | Piping |  |  | General Arrangement Drawing for FGP ¦ Fuel Gas Package |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6824 | 0.9047 | 0.9047 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 12.1217 | 0.6989 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140083 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A & YARD AREA | ARRANGEMENT DRAWING | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match |  |  |  |  | condensate | query_unscoped | false | 121 | 6 | 13.2995 | 0.6017 | 0.0207 | 0.0155 | hybrid | structured_no_system |  | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140100 | FABRICATION STANDARD DRAWING | DRAWING |  |  |  |  | DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8031 | 0.7076 | 0.4953 | FA | 0EF3040W16A01 | (Lab) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-06-30 | design_drawing | civil_design | compatible |  |  |  |  | lab | query_unscoped | false | 15 | 123 | 0.0002 | 0.3967 | 0.0188 | 0.0106 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-11-17 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-31 | 2025-03-02 | generated | 0.30 | 0.35 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBA-140101 | FABRICATION ISOMETRIC DRAWING FOR HP STEAM SYSTEM | ISOMETRIC DRAWING |  | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6444 | 0.4933 | 0.4933 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 12.4371 | 0.6631 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBC-140102 | FABRICATION ISOMETRIC DRAWING FOR IP STEAM SYSTEM | ISOMETRIC DRAWING |  | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | Isometric Drawing for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6633 | 0.4990 | 0.4990 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 12.4371 | 0.6955 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140103 | FABRICATION ISOMETRIC DRAWING FOR LP STEAM SYSTEM | ISOMETRIC DRAWING |  | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6419 | 0.4926 | 0.4926 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 12.4371 | 0.6672 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140104 | FABRICATION ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6284 | 0.6552 | 0.6552 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 2.9879 | 0.5179 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCM-140105 | FABRICATION ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM | ISOMETRIC DRAWING |  | STEAM DRAIN SYSTEM |  |  | Isometric Drawing for STEAM DRAIN SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6397 | 0.4919 | 0.4919 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 9.0525 | 0.6713 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design | 3 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCA-140106 | FABRICATION ISOMETRIC DRAWING FOR CONDENSATE SYSTEM | ISOMETRIC DRAWING |  | CONDENSATE SYSTEM |  |  | Isometric Drawing for CONDENSATE SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6829 | 0.5049 | 0.5049 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 15.6554 | 0.6746 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LAB-140108 | FABRICATION ISOMETRIC DRAWING FOR FEED WATER SYSTEM | ISOMETRIC DRAWING |  | FEED WATER SYSTEM |  |  | Isometric Drawing for FEED WATER SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | feed¦water |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6585 | 0.4975 | 0.4975 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | false | 1 | 1 | 23.7808 | 0.6842 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design | 1 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PGB-140109 | FABRICATION ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM | ISOMETRIC DRAWING |  | CLOSED COOLING WATER SYSTEM |  |  | Isometric Drawing for CLOSED COOLING WATER SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7513 | 0.6254 | 0.6254 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 14.0432 | 0.3498 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-08-16 | 2024-09-15 | 2024-10-15 | 2024-10-30 | 2024-11-14 | 2024-11-29 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SCA-140110 | FABRICATION ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM | ISOMETRIC DRAWING |  | SERVICE AIR SYSTEM |  |  | Isometric Drawing for SERVICE AIR SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | air¦service |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7366 | 0.6410 | 0.6410 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 11.3826 | 0.6183 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140112 | FABRICATION ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM | ISOMETRIC DRAWING |  | POTABLE WATER SYSTEM |  |  | Isometric Drawing for POTABLE WATER SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6381 | 0.4914 | 0.4914 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 4 | 1 | 28.9455 | 0.6492 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | system_design |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GHC-140113 | FABRICATION ISOMETRIC DRAWING FOR DEMI WATER SYSTEM | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.8333 | 0.7006 | 0.7935 | 0.7935 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 6.5714 | 0.5517 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PDA-140114 | FABRICATION ISOMETRIC DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6642 | 0.6659 | 0.6659 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 5.5073 | 0.5525 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBH-140116 | FABRICATION ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | ISOMETRIC DRAWING | GT ¦ Gas Turbine |  |  |  | Isometric Drawing for GT ¦ Gas Turbine | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6204 | 0.6061 | 0.6061 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | compressed_air | gtg | query | ccw¦gtg | match | false | 1 | 3 | 8.1715 | 0.5363 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKC-140117 | FABRICATION ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM | ISOMETRIC DRAWING | GT ¦ Gas Turbine |  |  |  | Isometric Drawing for GT ¦ Gas Turbine | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | gas¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6402 | 0.4721 | 0.4721 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | compressed_air | gtg | query | ccw¦gtg | match | false | 1 | 3 | 3.1086 | 0.5372 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKG-140118 | FABRICATION ISOMETRIC DRAWING FOR FUEL GAS SYSTEM | ISOMETRIC DRAWING |  | FUEL GAS SYSTEM |  |  | Isometric Drawing for FUEL GAS SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6231 | 0.4869 | 0.4869 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | 1 | 1 | 12.9747 | 0.6515 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140119 | FABRICATION ISOMETRIC DRAWING FOR TG MISCELLANEOUS SYSTEM | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.5800 | 0.6407 | 0.6407 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 2.9879 | 0.4550 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140120 | ISOMETRIC DRAWING FOR TG MISCELLANEOUS SMALL BORE SYSTEM | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6013 | 0.6470 | 0.6470 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 2.9879 | 0.4674 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GM-140121 | FABRICATION ISOMETRIC DRAWING FOR WASTE WATER SYSTEM | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.8333 | 0.7052 | 0.7949 | 0.7949 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 2 | 1 | 6.5714 | 0.5711 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBA-140201 | ISOMETRIC DRAWING FOR HP STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7612 | 0.7884 | 0.5519 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 10.1539 | 0.6574 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBC-140202 | ISOMETRIC DRAWING FOR IP STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | Isometric Drawing for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7691 | 0.7907 | 0.5535 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 10.1539 | 0.6914 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140203 | ISOMETRIC DRAWING FOR LP STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7617 | 0.7885 | 0.5520 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 10.1539 | 0.6587 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140204 | ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6409 | 0.6590 | 0.6590 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 2.9879 | 0.5460 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCM-140205 | ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | STEAM DRAIN SYSTEM |  |  | Isometric Drawing for STEAM DRAIN SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7886 | 0.7966 | 0.5576 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 1 | 6.7693 | 0.6743 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCA-140206 | ISOMETRIC DRAWING FOR CONDENSATE SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | CONDENSATE SYSTEM |  |  | Isometric Drawing for CONDENSATE SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7858 | 0.7957 | 0.5570 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 13.4774 | 0.6658 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LAB-140208 | ISOMETRIC DRAWING FOR FEED WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | FEED WATER SYSTEM |  |  | Isometric Drawing for FEED WATER SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | feed¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7963 | 0.7989 | 0.5592 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | false | 1 | 1 | 21.6028 | 0.6591 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design | 1 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PGB-140209 | ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | CLOSED COOLING WATER SYSTEM |  |  | Isometric Drawing for CLOSED COOLING WATER SYSTEM | Cooling ToWer | COOLING TOWER _ISOMETRIC DRAWING FOR VACUUM PIPING | 1 | start+24W<=FA<=start+24W+2M | FA ∈ [start+168d, start+228d] | title | drawing | drawing | isometric_drawing | isometric_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7576 | 0.6273 | 0.6273 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 14.0432 | 0.3606 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-08-16 | 2024-09-15 | 2024-10-15 | 2024-10-30 | 2024-11-14 | 2024-11-29 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SCA-140210 | ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | SERVICE AIR SYSTEM |  |  | Isometric Drawing for SERVICE AIR SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | air¦service |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7366 | 0.6410 | 0.6410 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 11.3826 | 0.6139 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QFB-140211 | ISOMETRIC DRAWING FOR INSTRUMENT AIR SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | INSTRUMENT AIR SYSTEM |  |  | Isometric Drawing for INSTRUMENT AIR SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | air¦instrument |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7311 | 0.6393 | 0.6393 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 1 | 11.3826 | 0.6460 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140212 | ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | POTABLE WATER SYSTEM |  |  | Isometric Drawing for POTABLE WATER SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7671 | 0.7901 | 0.5531 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 26.6249 | 0.6445 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GHC-140213 | ISOMETRIC DRAWING FOR DEMI WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.8333 | 0.7332 | 0.8033 | 0.8033 | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 6.5714 | 0.5733 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140215 | ISOMETRIC DRAWING FOR UNDERGROUND PIPING SYSTEM | ISOMETRIC DRAWING |  | PIPING |  |  | Isometric Drawing for PIPING | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7662 | 0.6499 | 0.6499 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  | compressed_air | compressed_air | rule | compressed_air | match | false | 1 | 1 | 8.1013 | 0.5589 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBH-140216 | ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM SMALL BORE | ISOMETRIC DRAWING | GT ¦ Gas Turbine | COOLING SYSTEM |  |  | Isometric Drawing for GT ¦ Gas Turbine | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6510 | 0.6153 | 0.6153 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | compressed_air | gtg | query | ccw¦gtg | match | false | 1 | 3 | 10.7030 | 0.5199 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKC-140217 | ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM SMALL BORE | ISOMETRIC DRAWING | GT ¦ Gas Turbine |  |  |  | Isometric Drawing for GT ¦ Gas Turbine |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7196 | 0.7759 | 0.5431 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 3 | 3.1086 | 0.5152 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QUB-140219 | ISOMETRIC DRAWING FOR SAMPLING SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | SAMPLING SYSTEM |  |  | Isometric Drawing for SAMPLING SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | sampling |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7897 | 0.7969 | 0.5578 | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | false | 1 | 1 | 18.4875 | 0.6614 | 0.0328 | 0.0328 | hybrid | structured_preferred | sampling | system_design | 1 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QCA-140221 | ISOMETRIC DRAWING FOR CHEMICAL DOSING SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | Isometric Drawing for CHEMICAL DOSING SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7580 | 0.7874 | 0.5512 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 31.5207 | 0.7257 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QJA-140223 | ISOMETRIC DRAWING FOR N2 GAS SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | N2 GAS SYSTEM ¦ Nitrogen GAS SYSTEM |  |  | Isometric Drawing for N2 GAS SYSTEM ¦ Nitrogen GAS SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7576 | 0.7873 | 0.5511 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 |  | n2 | query | n2 | match | false | 1 | 1 | 27.4423 | 0.7384 | 0.0328 | 0.0328 | hybrid | structured_preferred | n2 | system_design | 1 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GM-140224 | ISOMETRIC DRAWING FOR WASTE WATER SYSTEM SMALL BORE | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS | CONTROL VALVE | Valve Assembly/ Outline draWings | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.5495 | 0.4449 | 0.4449 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 8 | 3 | 14.4611 | 0.5799 | 0.0306 | 0.0229 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140301 | MANUAL BUTTERFLY VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS | MANUAL BUTTERFLY VALVE |  |  |  | OUTLINE DRAWINGS for MANUAL BUTTERFLY VALVE |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual | butterfly¦valve |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8725 | 0.7868 | 0.5507 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 65 | 112 |  | 0.3152 | 0.0138 | 0.0083 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.44 | needs_review | activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140302 | MANUAL LOW PRESSURE CASTING VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8247 | 0.7724 | 0.5407 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | 1182 | 29 |  | 0.3804 | 0.0120 | 0.0090 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140303 | MANUAL HIGH PRESSURE CASTING VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8372 | 0.7762 | 0.5433 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | 1200 | 27 |  | 0.3884 | 0.0123 | 0.0092 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140304 | MANUAL FORGING VALVE OUTLINE DRAWINGS | DRAWINGS |  |  |  |  | DRAWINGS |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8738 | 0.7871 | 0.5510 | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 130 | 17 |  | 0.4338 | 0.0183 | 0.0137 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140401 | PIPING SUPPORT DETAIL DRAWING FOR HP STEAM SYSTEM | DRAWING |  | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | DRAWING for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6437 | 0.8931 | 0.6252 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | false | 2 | 1 | 12.7852 | 0.6736 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140402 | PIPING SUPPORT DETAIL DRAWING FOR IP STEAM SYSTEM | DRAWING |  | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | DRAWING for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6583 | 0.8975 | 0.6283 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | false | 2 | 1 | 12.7852 | 0.7071 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140403 | PIPING SUPPORT DETAIL DRAWING FOR LP STEAM SYSTEM | DRAWING |  | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | DRAWING for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6662 | 0.8999 | 0.6299 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | false | 2 | 1 | 12.7852 | 0.6654 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140404 | PIPING SUPPORT DETAIL DRAWING FOR PROCESS STEAM SYSTEM | DRAWING |  | PROCESS STEAM SYSTEM |  |  | DRAWING for PROCESS STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6819 | 0.9046 | 0.6332 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | false | 1 | 1 | 9.4005 | 0.7327 | 0.0328 | 0.0246 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140405 | PIPING SUPPORT DETAIL DRAWING FOR STEAM DRAIN SYSTEM | DRAWING |  | STEAM DRAIN SYSTEM |  |  | DRAWING for STEAM DRAIN SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6695 | 0.9008 | 0.6306 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | false | 2 | 1 | 9.4005 | 0.6679 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140406 | PIPING SUPPORT DETAIL DRAWING FOR CONDENSATE SYSTEM | DRAWING |  | CONDENSATE SYSTEM |  |  | DRAWING for CONDENSATE SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6849 | 0.9055 | 0.6338 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 15.9873 | 0.6892 | 0.0328 | 0.0246 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140407 | PIPING SUPPORT DETAIL DRAWING FOR FEEDWATER SYSTEM | DRAWING |  | FEEDWATER SYSTEM |  |  | DRAWING for FEEDWATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | feedwater |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6717 | 0.9015 | 0.6311 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | feedwater |  | feedwater | query | feedwater | match | false | 1 | 1 | 3.7367 | 0.6870 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140408 | PIPING SUPPORT DETAIL DRAWING FOR CLOSED COOLING WATER SYSTEM | DRAWING |  | CLOSED COOLING WATER SYSTEM |  |  | DRAWING for CLOSED COOLING WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6507 | 0.8952 | 0.6267 | FA | 1EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-01-30 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw | match | false | 1 | 6 | 28.9307 | 0.5880 | 0.0315 | 0.0237 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140410 | PIPING SUPPORT DETAIL DRAWING FOR SERVICE AIR SYSTEM | DRAWING |  | SERVICE AIR SYSTEM |  |  | DRAWING for SERVICE AIR SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦service |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6965 | 0.9089 | 0.6363 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 11.7251 | 0.6358 | 0.0328 | 0.0246 | hybrid | structured_preferred | compressed_air | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140411 | PIPING SUPPORT DETAIL DRAWING FOR POTABLE WATER SYSTEM | DRAWING |  | POTABLE WATER SYSTEM |  |  | DRAWING for POTABLE WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | potable¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6645 | 0.8993 | 0.6295 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | wts |  | wts | query | wts | match | false | 1 | 1 | 29.2993 | 0.6488 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140412 | PIPING SUPPORT DETAIL DRAWING FOR DEMI. WATER SYSTEM | DRAWING |  | DEMI. WATER SYSTEM ¦ Demineralized WATER SYSTEM |  |  | DRAWING for DEMI. WATER SYSTEM ¦ Demineralized WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | demi¦demineralized¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6572 | 0.8971 | 0.6280 | FA | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | design_drawing | civil_design | compatible | wts |  | wts | query | wts | match | false | 2 | 1 | 32.1385 | 0.6714 | 0.0325 | 0.0244 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140415 | PIPING SUPPORT DETAIL DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6304 | 0.8891 | 0.6224 | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | design_drawing | civil_design | compatible | gtg |  | gtg | query | fgp¦gtg | match | false | 1 | 25 | 12.1281 | 0.5817 | 0.0282 | 0.0211 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140416 | PIPING SUPPORT DETAIL DRAWING FOR GT PERFORMANCE HEATER SYSTEM | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.6786 | 0.7636 | 0.7636 | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | design_drawing | civil_design | compatible | gtg | gtg | gtg | query | fgp¦gtg | match | false | 1 | 8 | 12.1281 | 0.5972 | 0.0311 | 0.0233 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140417 | PIPING SUPPORT DETAIL DRAWING FOR FUEL GAS SYSTEM | DRAWING |  | FUEL GAS SYSTEM |  |  | DRAWING for FUEL GAS SYSTEM | Fuel Gas System | Equipment (incl. pump) Detail DraWing | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | fgp¦fuel¦gas | fgp¦pump | scoped | match | match | match | passed |  | 0.5000 | 0.7621 | 0.5786 | 0.5786 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 1 | 1 | 15.5439 | 0.6897 | 0.0328 | 0.0246 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-08-02 | 2024-08-30 | 2024-09-27 | 2024-09-20 | 2024-10-18 | 2024-11-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140418 | PIPING SUPPORT DETAIL DRAWING FOR STEAM BLOWING | DRAWING |  |  |  |  | DRAWING |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.6690 | 0.9007 | 0.6305 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 219 | 4 | 5.4229 | 0.6259 | 0.0192 | 0.0108 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140419 | PIPING SUPPORT DETAIL DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | DRAWING |  |  |  |  | DRAWING |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.6049 | 0.8815 | 0.6170 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible |  |  |  |  | wts | query_unscoped | false | 134 | 1 | 5.8610 | 0.5965 | 0.0215 | 0.0121 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140420 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING ESOD AREA | DRAWING |  |  |  |  | DRAWING | FireFighting | Piping Support DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6666 | 0.7250 | 0.7250 | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 25 | 133 | 17.3706 | 0.5110 | 0.0169 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-12-22 | 2025-02-16 | 2025-04-13 | 2025-03-09 | 2025-05-04 | 2025-06-29 | generated | 0.90 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140421 | PIPING SUPPORT DETAIL DRAWING FOR WASTE WATER SYSTEM | DRAWING |  | WASTE WATER SYSTEM |  |  | DRAWING for WASTE WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | waste¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6667 | 0.9000 | 0.6300 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts |  | wts | query | wts | match | false | 1 | 1 | 27.0327 | 0.6384 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140422 | PIPING SUPPORT DETAIL DRAWING FOR TG MISCELLANEOUS SYSTEM | DRAWING |  |  |  |  | DRAWING |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.6989 | 0.9097 | 0.6368 | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 115 | 4 | 6.9231 | 0.5641 | 0.0213 | 0.0120 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140423 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING NON ESOD AREA | DRAWING |  | SB PIPING |  |  | DRAWING for SB PIPING | FireFighting | Piping Support DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | title | drawing | drawing | drawing | drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6668 | 0.7250 | 0.7250 | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 33 | 103 | 20.9535 | 0.5091 | 0.0169 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-12-22 | 2025-02-16 | 2025-04-13 | 2025-03-09 | 2025-05-04 | 2025-06-29 | generated | 0.90 | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-150001 | DESIGN CRITERIA FOR ELECTRICAL SYSTEM | DESIGN CRITERIA |  | ELECTRICAL SYSTEM |  |  | DESIGN CRITERIA for ELECTRICAL SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | criteria | criteria | design_criteria | design_criteria | electrical |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5023 | 0.5707 | 0.5707 | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_criteria | civil_design | compatible | electrical | wts | electrical | query | electrical¦gsut_uat¦gtg | match | false | 7 | 4 | 15.5488 | 0.4792 | 0.0306 | 0.0229 | hybrid | structured_preferred | electrical | design_criteria¦system_design¦civil_design | 10 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL06-P0ZEN-150101 | ELECTRICAL LOAD LIST | LOAD LIST |  | ELECTRICAL |  |  | LOAD LIST for ELECTRICAL | [5 empty] | rule_query | other | other | load_list | electrical_load_list | electrical |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8329 | 0.9499 | 0.9499 |  | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | false | 4 | 2 | 7.2798 | 0.4438 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | procurement | 10 | [6 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150201 | SYMBOL & LEGEND FOR ELECTRICAL SYSTEM | SYMBOL & LEGEND |  | ELECTRICAL SYSTEM |  |  | SYMBOL & LEGEND for ELECTRICAL SYSTEM | [5 empty] | rule_query | other | diagram | symbol_and_legend | diagram | electrical | gt¦gtg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.4286 | 0.5688 | 0.4706 | 0.4706 |  | 0CF6500W70A04.6 | (Electrical Protection Panel) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-04-25 | 2008-05-26 |  | installation | query_unknown | electrical |  | electrical | query | electrical | match | false | 18 | 1 | 8.3620 | 0.5143 | 0.0292 | 0.0219 | hybrid | structured_no_phase | electrical | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150202 | KEY SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | 19 | 127 | 12.3101 | 0.5019 | 0.0180 | 0.0135 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150211 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR GTG UNIT | SINGLE LINE DIAGRAM | GTG UNIT ¦ Gas Turbine Generator UNIT | PROTECTION AND METERING |  |  | Single Line Diagram for PROTECTION AND METERING |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦metering¦protection¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7277 | 0.9183 | 0.9183 | SKIP | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 1 | 7.5809 | 0.6055 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150212 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR STG UNIT | SINGLE LINE DIAGRAM | STG UNIT ¦ Steam Turbine Generator UNIT | PROTECTION AND METERING |  |  | Single Line Diagram for PROTECTION AND METERING |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | generator¦metering¦protection¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7277 | 0.9183 | 0.9183 | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 5.6714 | 0.5962 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU05-P0ZEN-150221 | PHASING DIAGRAM | PHASING DIAGRAM |  |  |  |  | PHASING DIAGRAM |  | System Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram |  |  | generic | match | match | query_unscoped | passed |  | 0.3333 | 0.5362 | 0.3942 | 0.2759 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 11 | 2 | 10.0268 | 0.4219 | 0.0302 | 0.0170 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150301 | SHORT CIRCUIT STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 |  | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 85 | 3092 |  | 0.2245 | 0.0072 | 0.0054 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150302 | LOAD FLOW & LARGE MOTOR STARTING STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 |  | 3EF2020W00A01 | (ST #30) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  |  |  |  | stg | query_unscoped | false | 3992 | 217 |  | 0.3953 | 0.0039 | 0.0029 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150303 | CT PT CALCULATION STUDY REPORT FOR HV EQUIPMENT | REPORT | HV EQUIPMENT ¦ HIGH VOLTAGE EQUIPMENT |  |  |  | REPORT for HV EQUIPMENT ¦ HIGH VOLTAGE EQUIPMENT |  | STUDY REPORT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | study_report | study_report | high¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5602 | 0.6347 | 0.4443 | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | 1307 | 4 |  | 0.5226 | 0.0164 | 0.0123 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150304 | HARMONIC STUDY REPORT | REPORT |  |  |  |  | REPORT |  | GT - HAZOP STUDY REPORT | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | title | report | report | study_report | study_report |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5847 | 0.5254 | 0.5254 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  | gtg | gtg | rule | ccw¦gtg | match | false | 1 | 2 |  | 0.3670 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150305 | INSULATION STUDY REPORT | REPORT |  |  |  |  | REPORT |  | GT - SIL STUDY REPORT | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | title | report | report | study_report | study_report |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5367 | 0.5110 | 0.5110 | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | procurement | procurement | match |  | gtg | gtg | rule | electrical¦gsut_uat¦gtg | match | false | 1 | 4 | 7.5725 | 0.4786 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | procurement | 10 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150306 | TAP RATIO STUDY REPORT | REPORT |  |  |  |  | REPORT |  | GT - SIL STUDY REPORT | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | title | report | report | study_report | study_report |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5917 | 0.5275 | 0.5275 | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | procurement | procurement | match |  | gtg | gtg | rule | electrical¦gsut_uat¦gtg | match | false | 1 | 4 | 7.5725 | 0.4619 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | procurement | 10 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150311 | PROTECTION RELAY COORDINATION STUDY - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | STUDY | GSUT / UAT ¦ Generator Step-Up Transformer / Unit Auxiliary Transformer |  |  |  | STUDY for GSUT / UAT ¦ Generator Step-Up Transformer / Unit Auxiliary Transformer | [5 empty] | rule_query | other | calculation | study | calculation | auxiliary¦gas¦generator¦gsut¦gtg¦step¦transformer¦turbine¦uat¦unit | gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4444 | 0.6718 | 0.5127 | 0.5127 |  | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | 188 | 3398 | 7.5405 | 0.3218 | 0.0043 | 0.0026 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150312 | PROTECTION RELAY COORDINATION STUDY - MV SWITCHGEAR | STUDY | MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  |  |  | STUDY for MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR | [5 empty] | rule_query | other | drawing | study | drawing | medium¦switchgear¦voltage |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.7500 | 0.7155 | 0.7396 | 0.5178 |  | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 111 | 1280 |  | 0.3431 | 0.0066 | 0.0040 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150313 | PROTECTION RELAY COORDINATION STUDY - LV SWITCHGEAR | STUDY | LV SWITCHGEAR ¦ Low Voltage SWITCHGEAR |  |  |  | STUDY for LV SWITCHGEAR ¦ Low Voltage SWITCHGEAR | [5 empty] | rule_query | other | drawing | study | drawing | low¦switchgear¦voltage |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.6873 | 0.5562 | 0.3893 |  | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 111 | 912 |  | 0.3485 | 0.0069 | 0.0041 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150314 | PROTECTION RELAY COORDINATION STUDY - GSUT / OVERALL PROTECTION FOR STG UNIT | STUDY | GSUT ¦ Generator Step-Up Transformer |  |  |  | STUDY for GSUT ¦ Generator Step-Up Transformer | [5 empty] | rule_query | other | drawing | study | sectional_drawing | generator¦gsut¦steam¦step¦stg¦transformer¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.3750 | 0.6432 | 0.4555 | 0.4555 |  | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | 154 | 3455 | 7.5405 | 0.3119 | 0.0050 | 0.0030 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BA-150401 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | LOGIC DIAGRAM | GSUT / UAT ¦ Generator Step-Up Transformer / Unit Auxiliary Transformer |  |  |  | Control Logic Diagram for GSUT / UAT ¦ Generator Step-Up Transformer / Unit Auxiliary Transformer | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | title | diagram | diagram | control_logic_diagram | control_logic_diagram | auxiliary¦gas¦generator¦gsut¦gtg¦step¦transformer¦turbine¦uat¦unit |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5697 | 0.6959 | 0.6959 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | 75 | 2111 | 22.4244 | 0.4273 | 0.0079 | 0.0047 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BB-150402 | ELECTRICAL CONTROL LOGIC DIAGRAM - MV SWITCHGEAR | LOGIC DIAGRAM | MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  |  |  | Control Logic Diagram for MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | medium¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6367 | 0.7160 | 0.7160 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 42 | 313 | 14.8839 | 0.4464 | 0.0125 | 0.0075 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BB-150403 | ELECTRICAL CONTROL LOGIC DIAGRAM - LV SWITCHGEAR | LOGIC DIAGRAM | LV SWITCHGEAR ¦ Low Voltage SWITCHGEAR |  |  |  | Control Logic Diagram for LV SWITCHGEAR ¦ Low Voltage SWITCHGEAR | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | low¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6623 | 0.7237 | 0.7237 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 43 | 618 | 13.8746 | 0.4068 | 0.0112 | 0.0067 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BA-150404 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / OVERALL PROTECTION FOR STG UNIT | LOGIC DIAGRAM | GSUT ¦ Generator Step-Up Transformer |  |  |  | Control Logic Diagram for GSUT ¦ Generator Step-Up Transformer | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | title | diagram | diagram | control_logic_diagram | control_logic_diagram | generator¦gsut¦steam¦step¦stg¦transformer¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5700 | 0.6960 | 0.6960 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | 26 | 2588 | 22.4244 | 0.3977 | 0.0120 | 0.0072 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UCA-150501 | ELECTRICAL ROOM LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  |  | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING | Substation | Electrical Room Layout DraWing_Control BLDG | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8384 | 0.7515 | 0.7515 | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  | electrical | electrical | rule | electrical | match | false | 7 | 8 | 5.4929 | 0.5223 | 0.0296 | 0.0296 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150502 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8693 | 0.9608 | 0.6726 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 4 | 1 | 22.0905 | 0.7816 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150503 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8577 | 0.9573 | 0.6701 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 12 | 1 | 18.6405 | 0.7549 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150504 | ELECTRICAL ROOM LAYOUT DRAWING - STG #1 LEB | LAYOUT DRAWING | STG #1 ¦ Steam Turbine Generator #1 |  | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8769 | 0.9631 | 0.6742 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 4 | 1 | 18.8612 | 0.6635 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150505 | ELECTRICAL ROOM LAYOUT DRAWING - STG #2 LEB | LAYOUT DRAWING | STG #2 ¦ Steam Turbine Generator #2 |  | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8681 | 0.9604 | 0.6723 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 5 | 1 | 20.4863 | 0.6634 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150506 | ELECTRICAL ROOM LAYOUT DRAWING - WATER TREATMENT PLANT BUILDING | LAYOUT DRAWING |  |  | WATER TREATMENT PLANT BUILDING |  | Layout Drawing for WATER TREATMENT PLANT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | plant¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6778 | 0.6700 | 0.6700 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 1 | 7 | 16.6819 | 0.5741 | 0.0313 | 0.0313 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150508 | ELECTRICAL ROOM LAYOUT DRAWING –AUX. LEB | LAYOUT DRAWING |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Layout Drawing for AUX. LEB ¦ Auxiliary Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | aux¦auxiliary¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8659 | 0.9598 | 0.6718 | FA | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 4 | 15 | 6.3319 | 0.5155 | 0.0290 | 0.0290 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | 2024-10-06 | 2024-11-05 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAT-150601 | SIZING CALCULATION - GENERATOR STEP - UP TRANSFORMER | SIZING CALCULATION | GENERATOR STEP - UP TRANSFORMER |  |  |  | Calculation sheet for GENERATOR STEP - UP TRANSFORMER | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6310 | 0.5393 | 0.5393 | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat |  | gsut_uat | query | electrical¦gsut_uat¦gtg | match | false | 13 | 1 | 12.9176 | 0.5651 | 0.0301 | 0.0301 | hybrid | structured_preferred | gsut_uat | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAT-150611 | TECHNICAL SPECIFICATION - GENERATOR STEP - UP TRANSFORMER | TECHNICAL SPECIFICATION | GENERATOR STEP - UP TRANSFORMER |  |  |  | Technical Specification for GENERATOR STEP - UP TRANSFORMER | Transformer | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7088 | 0.5626 | 0.5626 | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | procurement | procurement | match | gsut_uat | gsut_uat | gsut_uat | query | gsut_uat¦stg | match | false | 1 | 13 | 50.7844 | 0.6184 | 0.0301 | 0.0301 | hybrid | structured_cell_found_text_preferred | gsut_uat | procurement |  | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAT-150621 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (GTG) | OUTLINE DRAWING | GENERATOR STEP - UP TRANSFORMER (GTG) ¦ GENERATOR STEP - UP TRANSFORMER (Gas Turbine Generator) |  |  |  | Outline Drawing for GENERATOR STEP - UP TRANSFORMER (GTG) ¦ GENERATOR STEP - UP TRANSFORMER (Gas Turbine Generator) |  | GT - OUTLINE DRAWING OF VALVES FOR GAS TURBINE PART | 1 | start+345D<=FA<=start+345D+2M | FA ∈ [start+345d, start+405d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | gas¦generator¦gtg¦step¦transformer¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.6995 | 0.6765 | 0.6765 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gsut_uat¦gtg | gtg | gsut_uat¦gtg | query | ccw¦gtg | match | false | 1 | 2 | 10.5921 | 0.5630 | 0.0325 | 0.0325 | hybrid | structured_preferred | gsut_uat¦gtg | system_design | 3 | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAT-150626 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (STG) | OUTLINE DRAWING | GENERATOR STEP - UP TRANSFORMER (STG) ¦ GENERATOR STEP - UP TRANSFORMER (Steam Turbine Generator) |  |  |  | Outline Drawing for GENERATOR STEP - UP TRANSFORMER (STG) ¦ GENERATOR STEP - UP TRANSFORMER (Steam Turbine Generator) |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | generator¦steam¦step¦stg¦transformer¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5806 | 0.6408 | 0.6408 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gsut_uat¦stg |  | gsut_uat¦stg | query | stg | match | false | 1 | 2 | 8.0958 | 0.6060 | 0.0325 | 0.0325 | hybrid | structured_preferred | gsut_uat¦stg | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAT-150631 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER | SCHEMATIC DIAGRAM | GENERATOR STEP - UP TRANSFORMER |  |  |  | SCHEMATIC DIAGRAM for GENERATOR STEP - UP TRANSFORMER | Transformer | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7417 | 0.9225 | 0.9225 | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | gsut_uat | gsut_uat | gsut_uat | query | gsut_uat¦stg | match | false | 11 | 64 | 43.6949 | 0.5626 | 0.0221 | 0.0166 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering |  | 2025-01-23 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAT-150636 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER (STG) | SCHEMATIC DIAGRAM | GENERATOR STEP - UP TRANSFORMER (STG) ¦ GENERATOR STEP - UP TRANSFORMER (Steam Turbine Generator) |  |  |  | SCHEMATIC DIAGRAM for GENERATOR STEP - UP TRANSFORMER (STG) ¦ GENERATOR STEP - UP TRANSFORMER (Steam Turbine Generator) | Transformer | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦step¦stg¦transformer¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6265 | 0.8880 | 0.8880 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | gsut_uat¦stg | gsut_uat | gsut_uat¦stg | query | stg | match | false | 1 | 1 | 8.0958 | 0.6156 | 0.0328 | 0.0246 | hybrid | structured_preferred | gsut_uat¦stg | system_design¦engineering | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BBT-150651 | SIZING CALCULATION - UNIT AUXILIARY TRANSFORMER | SIZING CALCULATION | UNIT AUXILIARY TRANSFORMER |  |  |  | Calculation sheet for UNIT AUXILIARY TRANSFORMER | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6349 | 0.5405 | 0.5405 | SKIP | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gsut_uat |  | gsut_uat | query | electrical¦gsut_uat¦gtg | match | false | 1 | 2 | 28.0819 | 0.6079 | 0.0325 | 0.0325 | hybrid | structured_preferred | gsut_uat | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BBT-150661 | TECHNICAL SPECIFICATION - UNIT AUXILIARY TRANSFORMER | TECHNICAL SPECIFICATION | UNIT AUXILIARY TRANSFORMER |  |  |  | Technical Specification for UNIT AUXILIARY TRANSFORMER | Transformer | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7178 | 0.5654 | 0.5654 | FA | 2PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-04-16 | procurement | procurement | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | false | 2 | 1 | 35.1702 | 0.6843 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gsut_uat | procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BBT-150671 | OUTLINE DRAWING - UNIT AUXILIARY TRANSFORMER | OUTLINE DRAWING | UNIT AUXILIARY TRANSFORMER |  |  |  | Outline Drawing for UNIT AUXILIARY TRANSFORMER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5652 | 0.6362 | 0.6362 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | 169 | 178 | 10.7524 | 0.4523 | 0.0086 | 0.0051 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BBT-150681 | SCHEMATIC DIAGRAM - UNIT AUXILIARY TRANSFORMER | SCHEMATIC DIAGRAM | UNIT AUXILIARY TRANSFORMER |  |  |  | SCHEMATIC DIAGRAM for UNIT AUXILIARY TRANSFORMER | Transformer | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7293 | 0.9188 | 0.9188 | FA | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | design_drawing | civil_design | compatible | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | false | 13 | 8 | 28.0819 | 0.6295 | 0.0284 | 0.0213 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAA-150701 | SIZING CALCULATION - GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | SIZING CALCULATION | GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT |  |  |  | Calculation sheet for GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | breaker¦busduct¦circuit¦generator¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6534 | 0.5460 | 0.5460 | SKIP | 1EF3530W16A02 | (Block #1 EDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-10-29 | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 1 | 13 | 1.7821 | 0.4766 | 0.0301 | 0.0301 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAC-150711 | TECHNICAL SPECIFICATION - GENERATOR CIRCUIT BREAKER | TECHNICAL SPECIFICATION | GENERATOR CIRCUIT BREAKER |  |  |  | Technical Specification for GENERATOR CIRCUIT BREAKER | GENERATOR CIRCUIT BREAKER | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | breaker¦circuit¦generator |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.8684 | 0.6980 | 0.6980 | FA | 1PF6500W86A02P | (GT GCB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2007-05-31 | 2008-03-31 | procurement | procurement | match |  |  |  |  | electrical¦gtg | query_unscoped | false | 1 | 1 | 43.7256 | 0.7168 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAC-150721 | OUTLINE DRAWING - GENERATOR CIRCUIT BREAKER | OUTLINE DRAWING | GENERATOR CIRCUIT BREAKER |  |  |  | Outline Drawing for GENERATOR CIRCUIT BREAKER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | breaker¦circuit¦generator |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5975 | 0.6459 | 0.6459 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 475 | 1135 | 3.8574 | 0.4038 | 0.0027 | 0.0020 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAC-150731 | SCHEMATIC DIAGRAM - GENERATOR CIRCUIT BREAKER | SCHEMATIC DIAGRAM | GENERATOR CIRCUIT BREAKER |  |  |  | SCHEMATIC DIAGRAM for GENERATOR CIRCUIT BREAKER | GENERATOR CIRCUIT BREAKER | Schematic diagram | 1 | start+8M<=FA<=start+8M+2M | FA ∈ [start+240d, start+300d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | breaker¦circuit¦generator |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9701 | 0.9910 | 0.9910 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible |  |  |  |  | hrsg | query_unscoped | false | 39 | 912 | 13.0682 | 0.4248 | 0.0111 | 0.0063 | hybrid | structured_no_system |  | system_design¦engineering |  | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAA-150751 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR GTG UNIT | TECHNICAL SPECIFICATION | ISOLATED PHASE BUSDUCT |  |  |  | Technical Specification for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8742 | 0.6123 | 0.6123 | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | false | 1 | 2 | 67.1464 | 0.6936 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAA-150752 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR STG UNIT | TECHNICAL SPECIFICATION | ISOLATED PHASE BUSDUCT |  |  |  | Technical Specification for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8742 | 0.6123 | 0.6123 | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | false | 1 | 2 | 67.1464 | 0.6958 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150761 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | GENERAL ARRANGEMENT DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | GENERAL ARRANGEMENT DRAWING for ISOLATED PHASE BUSDUCT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6165 | 0.8850 | 0.8850 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | 78 | 776 | 13.4438 | 0.4898 | 0.0084 | 0.0051 | hybrid | structured_phase_gap | electrical | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150762 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | GENERAL ARRANGEMENT DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | GENERAL ARRANGEMENT DRAWING for ISOLATED PHASE BUSDUCT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6165 | 0.8850 | 0.8850 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | 84 | 548 | 13.4438 | 0.4839 | 0.0086 | 0.0052 | hybrid | structured_phase_gap | electrical | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150766 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | CONNECTION DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | CONNECTION DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8683 | 0.8205 | 0.8205 | FA | 2EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-01 | 2007-08-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 2 | 7 | 4.9828 | 0.5237 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-10-28 | 2024-11-27 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-10 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150767 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | CONNECTION DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | CONNECTION DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8683 | 0.8205 | 0.8205 | FA | 2EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-01 | 2007-08-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 2 | 8 | 3.9042 | 0.4873 | 0.0308 | 0.0231 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-10-28 | 2024-11-27 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-10 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150771 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | PRESSURIZATION PANEL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | PRESSURIZATION PANEL DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7627 | 0.6488 | 0.6488 | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 5 | 2 | 4.9085 | 0.5337 | 0.0315 | 0.0236 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150772 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | PRESSURIZATION PANEL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | PRESSURIZATION PANEL DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7627 | 0.6488 | 0.6488 | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 5 | 2 | 3.8460 | 0.4856 | 0.0315 | 0.0236 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150776 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | DETAIL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | Detail Drawing for GTG | Isolated Phase Bus | Foundation detail draWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7482 | 0.6911 | 0.6911 | FA | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 1 | 11 | 4.9828 | 0.5248 | 0.0305 | 0.0229 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150777 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | DETAIL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | Detail Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7167 | 0.7750 | 0.7750 | FA | 2EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-01 | 2007-08-30 | design_drawing | civil_design | compatible | electrical | stg | electrical | query | electrical¦gsut_uat¦gtg | match | false | 2 | 7 | 3.9042 | 0.5077 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150781 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | STEEL SUPPORT STRUCTURE DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | STEEL SUPPORT STRUCTURE DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Support DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7793 | 0.7938 | 0.7938 | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 1 | 3 | 13.6270 | 0.5572 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150782 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | STEEL SUPPORT STRUCTURE DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | STEEL SUPPORT STRUCTURE DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Support DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7793 | 0.7938 | 0.7938 | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 1 | 6 | 12.5645 | 0.5129 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BB-150801 | TECHNICAL SPECIFICATION - MV SWITCHGEAR | TECHNICAL SPECIFICATION | MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  |  |  | Technical Specification for MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | medium¦switchgear¦voltage |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6677 | 0.6670 | 0.4669 | FA | 0EF6500W70A01.2 | (MV SWGR) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries |  | 2007-03-30 | procurement | procurement | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | false | 1 | 1 | 60.1661 | 0.6541 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150811 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #1 | SINGLE LINE DIAGRAM | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 29 | 2441 | 14.8839 | 0.4163 | 0.0116 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150812 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #2 | SINGLE LINE DIAGRAM | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 29 | 2378 | 14.8839 | 0.4184 | 0.0116 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150813 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #3 | SINGLE LINE DIAGRAM | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 29 | 2247 | 14.8839 | 0.4174 | 0.0117 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150814 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #4 | SINGLE LINE DIAGRAM | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 29 | 2338 | 14.8839 | 0.4187 | 0.0117 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150815 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #5 | SINGLE LINE DIAGRAM | GTG ¦ Gas Turbine Generator |  |  |  | Single Line Diagram for GTG ¦ Gas Turbine Generator |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7353 | 0.9206 | 0.9206 | SKIP | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 1 | 7.5809 | 0.6321 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150816 | SINGLE LINE DIAGRAM – 13.8kV COMMON SWITCHGEAR | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | service_water | query_unscoped | false | 21 | 227 | 13.3885 | 0.4733 | 0.0158 | 0.0119 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BB-150821 | OUTLINE DRAWING - MV SWITCHGEAR | OUTLINE DRAWING | MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  |  |  | Outline Drawing for MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | medium¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5824 | 0.6414 | 0.6414 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 500 | 390 | 5.3193 | 0.4416 | 0.0040 | 0.0024 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BB-150831 | WIRING DIAGRAM - MV SWITCHGEAR | WIRING DIAGRAM | MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  |  |  | WIRING DIAGRAM for MV SWITCHGEAR ¦ Medium Voltage SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | medium¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6073 | 0.6488 | 0.6488 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 36 | 239 | 14.8839 | 0.4658 | 0.0138 | 0.0083 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BB-150836 | DRAWINGS - HTS | DRAWINGS |  |  |  |  | DRAWINGS | [5 empty] | rule_query | drawing |  | drawing | [6 empty] | query_unscoped | no_match | [6 empty] | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible |  |  |  |  | hrsg | query_unscoped | false | 3792 | 1 |  | 0.4343 | 0.0167 | 0.0094 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150901 | TECHNICAL SPECIFICATION - LV SWITCHGEAR | TECHNICAL SPECIFICATION | LV SWITCHGEAR ¦ Low Voltage SWITCHGEAR |  |  |  | Technical Specification for LV SWITCHGEAR ¦ Low Voltage SWITCHGEAR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | low¦switchgear¦voltage |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6637 | 0.6658 | 0.4660 | FA | 0EF6500W70A01.3 | (LV SWGR) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries |  | 2007-03-30 | procurement | procurement | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | false | 1 | 1 | 58.5849 | 0.6204 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150902 | TECHNICAL SPECIFICATION - 13.8/0.48kV MOLD TRANSFORMER | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification | Transformer | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6326 | 0.5398 | 0.5398 | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | procurement | procurement | match |  | gsut_uat | gsut_uat | rule | electrical¦gsut_uat¦gtg | match | false | 2 | 1 | 13.4284 | 0.5819 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gsut_uat | procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150903 | TECHNICAL SPECIFICATION - 480V NON SEGREGATED PHASE BUS DUCT | TECHNICAL SPECIFICATION | NSPB ¦ NON SEGREGATED PHASE BUS |  |  |  | Technical Specification for NSPB ¦ NON SEGREGATED PHASE BUS | Isolated Phase Bus | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | bus¦non¦nspb¦phase¦segregated |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8121 | 0.5936 | 0.5936 | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 1 | 2 | 27.2976 | 0.6321 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150911 | SINGLE LINE DIAGRAM - 480V GTG/HRSG SWITCHGEAR | SINGLE LINE DIAGRAM | GTG/HRSG ¦ Gas Turbine Generator/Heat Recovery Steam Generator |  |  |  | Single Line Diagram for GTG/HRSG ¦ Gas Turbine Generator/Heat Recovery Steam Generator |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7164 | 0.9149 | 0.9149 | SKIP | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | system_design | system_design | match | gtg¦hrsg |  | gtg¦hrsg | query | hrsg | match | false | 2 | 1 | 27.5182 | 0.6185 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg¦hrsg | system_design¦engineering | 9 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150912 | SINGLE LINE DIAGRAM - 480V STG/ACC SWITCHGEAR | SINGLE LINE DIAGRAM | STG/ACC ¦ Steam Turbine Generator/Air Cooled Condenser |  |  |  | Single Line Diagram for STG/ACC ¦ Steam Turbine Generator/Air Cooled Condenser |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | acc¦air¦condenser¦cooled¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6863 | 0.9059 | 0.9059 | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | acc¦stg |  | acc¦stg | query | stg | match | false | 1 | 2 | 5.6714 | 0.5881 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc¦stg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150913 | SINGLE LINE DIAGRAM - 480V COMMON SWITCHGEAR | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | service_water | query_unscoped | false | 21 | 149 | 13.3885 | 0.4931 | 0.0171 | 0.0128 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150914 | SINGLE LINE DIAGRAM - 480V WT SWITCHGEAR | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 15 | 597 | 12.5116 | 0.4602 | 0.0149 | 0.0111 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150915 | SINGLE LINE DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 2 | 188 | 18.5078 | 0.4937 | 0.0202 | 0.0151 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150916 | SINGLE LINE DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | 12 | 553 | 14.3287 | 0.4740 | 0.0155 | 0.0116 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150917 | SINGLE LINE DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | 11 | 589 | 15.0403 | 0.4768 | 0.0156 | 0.0117 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150918 | SINGLE LINE DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | SKIP | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | service_water | query_unscoped | false | 21 | 166 | 13.3885 | 0.4991 | 0.0168 | 0.0126 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150931 | OUTLINE DRAWING - 480V GTG/HRSG SWITCHGEAR | OUTLINE DRAWING | GTG/HRSG ¦ Gas Turbine Generator/Heat Recovery Steam Generator |  |  |  | Outline Drawing for GTG/HRSG ¦ Gas Turbine Generator/Heat Recovery Steam Generator |  | GT - OUTLINE DRAWING OF VALVES FOR GAS TURBINE PART | 1 | start+345D<=FA<=start+345D+2M | FA ∈ [start+345d, start+405d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7394 | 0.6885 | 0.6885 | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg¦hrsg | gtg | gtg¦hrsg | query | hrsg | match | false | 5 | 1 | 17.7122 | 0.6325 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg¦hrsg | system_design | 9 | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150932 | OUTLINE DRAWING - 480V STG/ACC SWITCHGEAR | OUTLINE DRAWING | STG/ACC ¦ Steam Turbine Generator/Air Cooled Condenser |  |  |  | Outline Drawing for STG/ACC ¦ Steam Turbine Generator/Air Cooled Condenser |  | ACC - Steam Jet Air Ejector Outline DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | acc¦air¦condenser¦cooled¦generator¦steam¦stg¦turbine | acc | scoped | match | match | match | passed |  | 0.7143 | 0.7110 | 0.7133 | 0.7133 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | acc¦stg | acc | acc¦stg | query | stg | match | false | 1 | 2 | 5.6714 | 0.5758 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc¦stg | system_design | 3 | 2024-10-16 | 2024-11-15 | 2024-12-15 | 2024-12-30 | 2025-01-14 | 2025-01-29 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150933 | OUTLINE DRAWING - 480V COMMON SWITCHGEAR | OUTLINE DRAWING |  |  |  |  | Outline Drawing |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6885 | 0.6732 | 0.6732 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 528 | 122 | 3.1128 | 0.4655 | 0.0072 | 0.0054 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150934 | OUTLINE DRAWING - 480V WT SWITCHGEAR | OUTLINE DRAWING |  |  |  |  | Outline Drawing |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6885 | 0.6732 | 0.6732 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 530 | 464 | 2.0974 | 0.4442 | 0.0036 | 0.0027 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150935 | OUTLINE DRAWING - 480V FIRE BRIGADE SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | mv_lv |  | mv_lv | query | fire_fighting¦hvac | mismatch | false | 54 | 159 | 8.7940 | 0.4752 | 0.0133 | 0.0033 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150936 | OUTLINE DRAWING - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 526 | 519 | 2.2471 | 0.4450 | 0.0034 | 0.0021 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150937 | OUTLINE DRAWING - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 480 | 1015 | 4.8538 | 0.4151 | 0.0028 | 0.0017 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150938 | OUTLINE DRAWING - 480V COMMON ESSENTIAL SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 507 | 360 | 3.3134 | 0.4483 | 0.0041 | 0.0025 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150939 | OUTLINE DRAWING - 13.8/0.48kV MOLD TRANSFORMER | OUTLINE DRAWING | TRANSFORMER |  |  |  | Outline Drawing for TRANSFORMER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | transformer |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6166 | 0.6516 | 0.6516 | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | 128 | 1011 | 8.5282 | 0.3570 | 0.0063 | 0.0038 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150940 | OUTLINE DRAWING - 480V NON SEGREGATED PHASE BUS DUCT | OUTLINE DRAWING | NON SEGREGATED PHASE BUS DUCT |  |  |  | Outline Drawing for NON SEGREGATED PHASE BUS DUCT |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | bus¦duct¦non¦phase¦segregated |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5134 | 0.6207 | 0.6207 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 655 | 188 | 2.0974 | 0.4291 | 0.0054 | 0.0041 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150951 | WIRING DIAGRAM - 480V GTG/HRSG SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | HRSG - Wiring Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | title | diagram | diagram | wiring_diagram | wiring_diagram | generator¦gtg¦heat¦hrsg¦recovery¦steam¦switchgear | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7507 | 0.9252 | 0.9252 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv | hrsg | mv_lv | query |  | activity_unscoped | true | 22 | 2268 | 14.8839 | 0.4540 | 0.0126 | 0.0076 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150952 | WIRING DIAGRAM - 480V STG/ACC SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | ACC - Wiring Diagram | 1 | start+289D<=FA<=start+289D+2M | FA ∈ [start+289d, start+349d] | title | diagram | diagram | wiring_diagram | wiring_diagram | acc¦air¦condenser¦cooled¦stg¦switchgear | acc | scoped | match | match | match | passed |  | 1.0000 | 0.6387 | 0.8916 | 0.8916 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv | acc | mv_lv | query |  | activity_unscoped | true | 22 | 1080 | 14.8839 | 0.4334 | 0.0131 | 0.0078 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150953 | WIRING DIAGRAM - 480V COMMON SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 20 | 453 | 15.9270 | 0.4610 | 0.0144 | 0.0087 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150954 | WIRING DIAGRAM - 480V WT SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 22 | 519 | 14.8839 | 0.4544 | 0.0139 | 0.0084 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150955 | WIRING DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 24 | 805 | 14.8839 | 0.4330 | 0.0131 | 0.0078 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150956 | WIRING DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 22 | 1059 | 14.8839 | 0.4386 | 0.0131 | 0.0079 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150957 | WIRING DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 23 | 1076 | 14.8839 | 0.4378 | 0.0129 | 0.0078 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150958 | WIRING DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | 20 | 647 | 15.9270 | 0.4449 | 0.0139 | 0.0083 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BT-151001 | SIZING CALCULATION - DC & AC UPS SYSTEM | SIZING CALCULATION |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Calculation sheet for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8623 | 0.8420 | 0.8420 | SKIP | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | civil_design | civil_design | match | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | 553 | 25 | 4.4223 | 0.4722 | 0.0134 | 0.0080 | hybrid | structured_phase_gap | dc_ups | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BT-151011 | TECHNICAL SPECIFICATION - DC & AC UPS SYSTEM | TECHNICAL SPECIFICATION |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Technical Specification for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4998 | 0.4999 | 0.4999 | FA | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | procurement | procurement | match | dc_ups |  | dc_ups | query | dc_ups¦electrical | match | false | 1 | 1 | 73.5665 | 0.7535 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dc_ups | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151021 | SINGLE LINE DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | SINGLE LINE DIAGRAM |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Single Line Diagram for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6793 | 0.9038 | 0.9038 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups |  | dc_ups | query |  | activity_unscoped | true | 16 | 85 | 19.9534 | 0.4897 | 0.0201 | 0.0120 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151026 | SINGLE LINE DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | SINGLE LINE DIAGRAM |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Single Line Diagram for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6793 | 0.9038 | 0.9038 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups |  | dc_ups | query |  | activity_unscoped | true | 16 | 98 | 19.9534 | 0.4906 | 0.0195 | 0.0117 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151031 | SINGLE LINE DIAGRAM - COMMON DC & UPS SYSTEM | SINGLE LINE DIAGRAM |  | DC & UPS SYSTEM ¦ Direct Current and Uninterruptible Power Supply SYSTEM |  |  | Single Line Diagram for DC & UPS SYSTEM ¦ Direct Current and Uninterruptible Power Supply SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7098 | 0.9129 | 0.9129 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups |  | dc_ups | query |  | activity_unscoped | true | 14 | 52 | 23.3610 | 0.5108 | 0.0224 | 0.0135 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151041 | OUTLINE DRAWING - BLOCK #1 DC & AC UPS SYSTEM | OUTLINE DRAWING |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Outline DraWing (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6962 | 0.7922 | 0.7922 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | 106 | 104 | 10.3888 | 0.4736 | 0.0121 | 0.0073 | hybrid | structured_phase_gap | dc_ups | system_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151046 | OUTLINE DRAWING - BLOCK #2 DC & AC UPS SYSTEM | OUTLINE DRAWING |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Outline DraWing (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6962 | 0.7922 | 0.7922 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | 126 | 117 | 10.3888 | 0.4708 | 0.0110 | 0.0066 | hybrid | structured_phase_gap | dc_ups | system_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151051 | OUTLINE DRAWING - COMMON DC & AC UPS SYSTEM | OUTLINE DRAWING |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Outline DraWing (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6962 | 0.7922 | 0.7922 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | 52 | 60 | 11.4319 | 0.4805 | 0.0173 | 0.0104 | hybrid | structured_phase_gap | dc_ups | system_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151061 | SCHEMATIC DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Schematic Diagram (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6645 | 0.7827 | 0.7827 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | 12 | 97 | 19.9534 | 0.4663 | 0.0203 | 0.0091 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151066 | SCHEMATIC DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Schematic Diagram (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6645 | 0.7827 | 0.7827 | SKIP | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | design_drawing | system_design | compatible | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | 24 | 66 | 16.3302 | 0.4849 | 0.0198 | 0.0089 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151071 | SCHEMATIC DIAGRAM - COMMON DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for DC & AC UPS SYSTEM ¦ DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Schematic Diagram (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | current¦direct¦power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6645 | 0.7827 | 0.7827 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | 12 | 51 | 20.9965 | 0.4760 | 0.0229 | 0.0103 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CHB-151101 | TECHNICAL SPECIFICATION - PROTECTION RELAY PANEL | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 1 | 1 | 30.2650 | 0.6876 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151111 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | OUTLINE DRAWING | GTG ¦ Gas Turbine Generator | FMS ¦ FAULT MONITORING SYSTEM |  |  | Outline Drawing for GTG ¦ Gas Turbine Generator |  | GT - OUTLINE DRAWING OF VALVES FOR GAS TURBINE PART | 1 | start+345D<=FA<=start+345D+2M | FA ∈ [start+345d, start+405d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7578 | 0.6940 | 0.6940 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | gtg | gtg | query | ccw¦gtg | match | false | 2 | 1 | 7.5809 | 0.6295 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151112 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR STG UNIT | OUTLINE DRAWING | STG ¦ Steam Turbine Generator | FMS ¦ FAULT MONITORING SYSTEM |  |  | Outline Drawing for STG ¦ Steam Turbine Generator |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6034 | 0.6477 | 0.6477 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 5.6714 | 0.5753 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CHB-151121 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | WIRING DIAGRAM | GTG ¦ Gas Turbine Generator | FMS ¦ FAULT MONITORING SYSTEM |  |  | WIRING DIAGRAM for FMS ¦ FAULT MONITORING SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | fault¦fms¦gas¦generator¦gtg¦monitoring¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5944 | 0.6450 | 0.6450 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 2 | 1 | 7.5809 | 0.6533 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CHB-151122 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR STG UNIT | WIRING DIAGRAM | STG ¦ Steam Turbine Generator | FMS ¦ FAULT MONITORING SYSTEM |  |  | WIRING DIAGRAM for FMS ¦ FAULT MONITORING SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | fault¦fms¦generator¦monitoring¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5944 | 0.6450 | 0.6450 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | false | 1 | 3 | 5.6714 | 0.5848 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151131 | CONFIGURATION DIAGRM - FAULT MONITORING SYSTEM | CONFIGURATION DIAGRM |  | FAULT MONITORING SYSTEM |  |  | CONFIGURATION DIAGRM for FAULT MONITORING SYSTEM | [5 empty] | rule_query | other | other | configuration_diagrm | vms_system_configuration | fault¦monitoring |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.4397 | 0.5986 | 0.5986 |  | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | feedwater | query_unscoped | false | 266 | 8 | 1.2267 | 0.4333 | 0.0178 | 0.0133 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CFA-151161 | TECHNICAL SPECIFICATION - METERING PANEL | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 1 | 3 | 20.5628 | 0.6117 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CFA-151171 | OUTLINE DRAWING - METERING PANEL | OUTLINE DRAWING |  |  |  |  | Outline Drawing |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6885 | 0.6732 | 0.6732 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 547 | 85 | 2.5734 | 0.4628 | 0.0085 | 0.0051 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CFA-151181 | WIRING DIAGRAM - METERING PANEL | WIRING DIAGRAM |  |  |  |  | WIRING DIAGRAM |  | ACC - Wiring Diagram | 1 | start+289D<=FA<=start+289D+2M | FA ∈ [start+289d, start+349d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram |  | acc | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6629 | 0.6655 | 0.6655 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | 6 | 312 | 14.8839 | 0.4633 | 0.0178 | 0.0054 | hybrid | structured_phase_gap | acc | system_design¦engineering | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YQ02-P0ZEN-152001 | TYPICAL INSTALLATION DRAWING - RACEWAY | TYPICAL INSTALLATION DRAWING |  |  |  |  | TYPICAL INSTALLATION DRAWING |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 3537 | 7 |  | 0.4680 | 0.0152 | 0.0086 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152002 | TECHNICAL SPECIFICATION - CABLE TRAY AND ACCESSORIES | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 4 | 1 | 15.3878 | 0.5457 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD16-P0ZEN-152003 | MAIN CABLE ROUTE PLAN | PLAN |  |  |  |  | Plan |  | MAIN CABLE ROUTE PLAN OVERALL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.9548 | 0.8464 | 0.5925 | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 3 | 2 | 9.2252 | 0.5276 | 0.0320 | 0.0180 | hybrid | structured_no_system |  |  |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152004 | 380KV CABLE ROUTE PLAN | PLAN |  |  |  |  | Plan |  | Cable Conduit Plan | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6495 | 0.6615 | 0.4631 | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 3 | 1 | 9.2252 | 0.6073 | 0.0323 | 0.0181 | hybrid | structured_no_system |  |  |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152005 | CABLE TRAY LAYOUT FOR CENTRAL CONTROL BUILDING | CABLE TRAY LAYOUT |  |  | CENTRAL CONTROL BUILDING |  | CABLE TRAY LAYOUT for CENTRAL CONTROL BUILDING | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7506 | 0.5752 | 0.5752 | SKIP | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 20 | 4 | 18.3850 | 0.5885 | 0.0281 | 0.0169 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152006 | CABLE TRAY LAYOUT FOR GTG #1,2 LEB | CABLE TRAY LAYOUT | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | CABLE TRAY LAYOUT for LEB ¦ Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7176 | 0.5653 | 0.5653 | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 7 | 1 | 13.9992 | 0.6861 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152007 | CABLE TRAY LAYOUT FOR GTG #3,4,5 LEB | CABLE TRAY LAYOUT | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | CABLE TRAY LAYOUT for LEB ¦ Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7176 | 0.5653 | 0.5653 | SKIP | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 12 | 5 | 17.1502 | 0.6780 | 0.0293 | 0.0293 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152008 | CABLE TRAY LAYOUT FOR ST #1 LEB | CABLE TRAY LAYOUT | ST #1 ¦ Steam Turbine #1 |  | LEB ¦ Local Electrical Building |  | CABLE TRAY LAYOUT for LEB ¦ Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7176 | 0.5653 | 0.5653 | SKIP | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 3 | 15 | 17.5437 | 0.5498 | 0.0292 | 0.0292 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152009 | CABLE TRAY LAYOUT FOR ST #2 LEB | CABLE TRAY LAYOUT | ST #2 ¦ Steam Turbine #2 |  | LEB ¦ Local Electrical Building |  | CABLE TRAY LAYOUT for LEB ¦ Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7176 | 0.5653 | 0.5653 | SKIP | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 3 | 20 | 19.3008 | 0.5377 | 0.0284 | 0.0284 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152010 | CABLE TRAY LAYOUT FOR ST BUILDING | CABLE TRAY LAYOUT |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | CABLE TRAY LAYOUT for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6193 | 0.6058 | 0.6058 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 11 | 1 | 3.9005 | 0.4796 | 0.0305 | 0.0305 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152011 | CABLE TRAY LAYOUT FOR WATER TREATMENT BUILDING | CABLE TRAY LAYOUT |  |  | WATER TREATMENT BUILDING |  | CABLE TRAY LAYOUT for WATER TREATMENT BUILDING | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7500 | 0.8423 | 0.7777 | 0.7777 | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 4 | 6 | 13.6713 | 0.5440 | 0.0308 | 0.0308 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152012 | CABLE TRAY LAYOUT FOR FGS ELECTRICAL BUILDING | CABLE TRAY LAYOUT |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | CABLE TRAY LAYOUT for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.6904 | 0.7905 | 0.7905 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 10 | 4 | 10.8160 | 0.5320 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152013 | CABLE TRAY LAYOUT FOR WORKSHOP & STORAGE BUILDING | CABLE TRAY LAYOUT |  |  | WORKSHOP & STORAGE BUILDING |  | CABLE TRAY LAYOUT for WORKSHOP & STORAGE BUILDING | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6856 | 0.5557 | 0.5557 | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 18 | 34 | 16.9020 | 0.4878 | 0.0235 | 0.0176 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152014 | CABLE TRAY LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | CABLE TRAY LAYOUT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | CABLE TRAY LAYOUT for ADMINISTRATION & SOCIAL BUILDING | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6836 | 0.5551 | 0.5551 | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 17 | 17 | 16.9020 | 0.4958 | 0.0260 | 0.0195 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152015 | CABLE TRAY LAYOUT FOR PIPE RACK | CABLE TRAY LAYOUT |  |  | PIPE RACK |  | CABLE TRAY LAYOUT for PIPE RACK | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7206 | 0.5662 | 0.5662 | SKIP | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 22 | 5 | 20.1089 | 0.6334 | 0.0276 | 0.0207 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152016 | CABLE TRAY LAYOUT FOR AUX LEB | CABLE TRAY LAYOUT |  |  | AUX LEB ¦ Auxiliary Local Electrical Building |  | CABLE TRAY LAYOUT for AUX LEB ¦ Auxiliary Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | aux¦auxiliary¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6942 | 0.5583 | 0.5583 | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 2 | 4 | 16.9020 | 0.5008 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152017 | CABLE TRAY LAYOUT FOR GTG PCC #1,2,3,4,5 | CABLE TRAY LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | CABLE TRAY LAYOUT for GTG | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7399 | 0.5720 | 0.5720 | SKIP | 2CF1265W16A12.4 | (TCA Cooler) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | 2007-10-30 | 2007-12-29 | design_drawing | civil_design | compatible | gtg |  | gtg | query | fgp¦gtg | match | false | 3 | 58 | 14.7441 | 0.5886 | 0.0243 | 0.0183 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152018 | CABLE TRAY LAYOUT FOR TANK SLEEPER AREA | CABLE TRAY LAYOUT | TANK |  |  |  | CABLE TRAY LAYOUT for Tank | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7368 | 0.5710 | 0.5710 | SKIP | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | design_drawing | civil_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | 118 | 16 | 10.7403 | 0.5033 | 0.0188 | 0.0106 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152019 | CABLE TRAY LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | CABLE TRAY LAYOUT |  |  |  |  | CABLE TRAY LAYOUT | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.7578 | 0.5773 | 0.5773 | SKIP | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 125 | 7 | 8.2027 | 0.5441 | 0.0203 | 0.0152 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152020 | CABLE TRAY LAYOUT FOR SECURITY BUILDING | CABLE TRAY LAYOUT |  |  | SECURITY BUILDING |  | CABLE TRAY LAYOUT for SECURITY BUILDING | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7071 | 0.5621 | 0.5621 | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 17 | 10 | 16.9020 | 0.5007 | 0.0273 | 0.0205 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-152052 | CONTROL CABLE CONNECTION DIAGRAM | DIAGRAM |  |  |  |  | Diagram | Substation | Cable Connection Diagram | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7178 | 0.7403 | 0.7403 | SKIP | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible |  |  |  |  | h2 | query_unscoped | false | 13 | 1833 | 12.9352 | 0.3277 | 0.0142 | 0.0080 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152201 | TYPICAL INSTALLATION DRAWING - LIGHTING AND SMALL POWER | DRAWING |  | LIGHTING AND SMALL POWER |  |  | DRAWING for LIGHTING AND SMALL POWER |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8144 | 0.9443 | 0.6610 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical | match | false | 7 | 9 | 7.5816 | 0.4445 | 0.0294 | 0.0221 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152202 | TECHNICAL SPECIFICATION - LIGHTING AND SMALL POWER | TECHNICAL SPECIFICATION |  | LIGHTING AND SMALL POWER |  |  | Technical Specification for LIGHTING AND SMALL POWER |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5711 | 0.6380 | 0.6380 | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | false | 1 | 1 | 35.2503 | 0.6816 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152203 | ILLUMINATION CALCULATION - CENTRAL CONTROL BUILDING | ILLUMINATION CALCULATION |  |  | CENTRAL CONTROL BUILDING |  | ILLUMINATION CALCULATION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | ccr¦central | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.8035 | 0.9410 | 0.9410 | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 3 | 4 | 18.3850 | 0.5500 | 0.0315 | 0.0189 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152204 | ILLUMINATION CALCULATION - GTG #1,2 LEB | ILLUMINATION CALCULATION | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | ILLUMINATION CALCULATION for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5927 | 0.6445 | 0.6445 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7166 | 0.6827 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152205 | ILLUMINATION CALCULATION - GTG #3,4,5 LEB | ILLUMINATION CALCULATION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | ILLUMINATION CALCULATION for GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5914 | 0.6441 | 0.6441 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 12 | 1 | 16.2666 | 0.6471 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152206 | ILLUMINATION CALCULATION - ST #1 LEB | CALCULATION |  |  | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | Calculation sheet for ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.6424 | 0.8927 | 0.8927 | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 3 | 36 | 4.3991 | 0.3290 | 0.0263 | 0.0263 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152207 | ILLUMINATION CALCULATION - ST #2 LEB | CALCULATION |  |  | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Calculation sheet for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | ST #2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.6403 | 0.8921 | 0.8921 | FI | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | gsut_uat¦stg | match | false | 44 | 1 | 1.6779 | 0.4001 | 0.0260 | 0.0260 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152208 | ILLUMINATION CALCULATION - ST BUILDING | CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Calculation sheet for ST BUILDING ¦ Steam Turbine BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7082 | 0.6791 | 0.6791 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 11 | 1 | 3.9005 | 0.4558 | 0.0305 | 0.0305 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152209 | ILLUMINATION CALCULATION - FGS ELECTRICAL BUILDING | CALCULATION |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8172 | 0.9452 | 0.9452 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 4 | 3 | 10.8160 | 0.4643 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152210 | ILLUMINATION CALCULATION - ADMINISTRATION | CALCULATION |  |  | ADMINISTRATION |  | Calculation sheet for ADMINISTRATION | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | administration |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7488 | 0.6446 | 0.6446 | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 3 | 10.8677 | 0.4394 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152211 | ILLUMINATION CALCULATION - SECURITY BUILDING | CALCULATION |  |  | SECURITY BUILDING |  | Calculation sheet for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8272 | 0.9482 | 0.9482 | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 7 | 18 | 4.2752 | 0.4014 | 0.0277 | 0.0166 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152212 | ILLUMINATION CALCULATION - MAIN GATE HOUSE | CALCULATION |  |  | MAIN GATE HOUSE |  | Calculation sheet for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8554 | 0.9566 | 0.9566 | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 1 | 17.1992 | 0.4918 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152213 | ILLUMINATION CALCULATION - SUPPORT BUILDING | CALCULATION |  |  | SUPPORT BUILDING |  | Calculation sheet for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8578 | 0.9573 | 0.9573 | FI | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 44 | 2 | 4.1062 | 0.4477 | 0.0257 | 0.0154 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152214 | ILLUMINATION CALCULATION - X-RAY SEARCHING ROOM | CALCULATION |  |  | X-RAY SEARCHING ROOM |  | Calculation sheet for X-RAY SEARCHING ROOM | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4786 | 0.4936 | 0.4936 | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match |  |  |  |  | feedwater | query_unscoped | false | 1378 | 10 |  | 0.4074 | 0.0150 | 0.0112 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152215 | ILLUMINATION CALCULATION - MAIN GATE HOUSE SUNSHADE | CALCULATION |  |  | MAIN GATE HOUSE SUNSHADE |  | Calculation sheet for MAIN GATE HOUSE SUNSHADE | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gate¦house¦main¦sunshade |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8848 | 0.9654 | 0.9654 | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 4 | 17.1992 | 0.4389 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152216 | ILLUMINATION CALCULATION - FIRE BRIGADE & AUX. LEB | CALCULATION |  |  | FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building |  | Calculation sheet for FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | aux¦auxiliary¦brigade¦electrical¦fire¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7242 | 0.9173 | 0.9173 | FI | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 4 | 4 | 3.1906 | 0.3977 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152217 | ILLUMINATION CALCULATION - WORKSHOP & STORAGE BUILDING | CALCULATION |  |  | WORKSHOP & STORAGE BUILDING |  | Calculation sheet for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8451 | 0.9535 | 0.9535 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 31 | 3 | 9.7017 | 0.4597 | 0.0269 | 0.0201 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152218 | ILLUMINATION CALCULATION - H2, CO2, N2 STORAGE SHELTER | CALCULATION |  |  | H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | Calculation sheet for H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | carbon¦co2¦dioxide¦hydrogen¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8405 | 0.8355 | 0.8355 | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | h2¦n2 | h2 | h2¦n2 | query | n2 | match | false | 1 | 4 | 13.1604 | 0.5526 | 0.0320 | 0.0320 | hybrid | structured_preferred | h2¦n2 | civil_design | 10 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152219 | ILLUMINATION CALCULATION - AIR COMPRESSOR SHELTER | CALCULATION |  |  | AIR COMPRESSOR SHELTER |  | Calculation sheet for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9085 | 0.9726 | 0.9726 | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 2 | 3 | 12.3084 | 0.5178 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152220 | ILLUMINATION CALCULATION - DEAERATOR SUPPORT STRUCTURE | CALCULATION |  |  |  |  | Calculation sheet |  | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7787 | 0.7936 | 0.7936 | FI | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match |  |  |  |  | feedwater | query_unscoped | false | 1096 | 2 |  | 0.5149 | 0.0170 | 0.0127 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | fi_complete | 0.90 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152221 | ILLUMINATION CALCULATION - FIRE WATER PUMP HOUSE | CALCULATION |  |  | FIRE WATER PUMP HOUSE |  | Calculation sheet for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8736 | 0.9621 | 0.9621 | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 3 | 7 | 13.5235 | 0.5202 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152222 | ILLUMINATION CALCULATION - WWT & BULK CHEMICAL STORAGE TANK SHELTER | CALCULATION |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Calculation sheet for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | tank | scoped | match | match | match | passed |  | 1.0000 | 0.8863 | 0.9659 | 0.9659 | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 2 | 2 | 28.7086 | 0.5488 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152223 | ILLUMINATION CALCULATION - WATER TREATMENT BUILDING | CALCULATION |  |  | WATER TREATMENT BUILDING |  | Calculation sheet for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8605 | 0.9581 | 0.9581 | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 6 | 2 | 13.2405 | 0.5095 | 0.0313 | 0.0313 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152224 | ILLUMINATION CALCULATION - CPP & CPP REGENERATION BUILDING | CALCULATION |  |  | CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Calculation sheet for CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | condensate¦cpp¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7826 | 0.7948 | 0.7948 | FI | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | 6 | 2 |  | 0.3580 | 0.0313 | 0.0313 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152225 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR STG & HRSG | CALCULATION | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator | CHEMICAL DOSING |  |  | Calculation sheet for STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7495 | 0.6915 | 0.6915 | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match | hrsg¦stg¦wts | hrsg | hrsg¦stg¦wts | query | wts | match | false | 2 | 7 | 30.8879 | 0.5819 | 0.0311 | 0.0311 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152226 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR HRSG | CALCULATION | HRSG ¦ Heat Recovery Steam Generator |  | CHEMICAL DOSING SHELTER |  | Calculation sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7930 | 0.7046 | 0.7046 | FA | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg¦wts | hrsg | hrsg¦wts | query | hrsg | match | false | 11 | 3 | 15.9912 | 0.5834 | 0.0300 | 0.0300 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | 2024-12-01 | 2024-12-31 | 2025-01-30 | 2025-02-14 | 2025-03-01 | 2025-03-16 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152229 | ILLUMINATION CALCULATION - YARD | CALCULATION |  |  |  |  | Calculation sheet | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6392 | 0.5418 | 0.5418 | FA | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | civil_design | civil_design | match |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | 3250 | 7 |  | 0.4149 | 0.0152 | 0.0114 | hybrid | structured_no_system |  | civil_design |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.49 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152230 | ILLUMINATION CALCULATION – TANK AREA | CALCULATION |  |  |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 500 | 9 | 5.6753 | 0.4692 | 0.0163 | 0.0122 | hybrid | structured_no_system |  | civil_design |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 0.61 | usable | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152231 | ILLUMINATION CALCULATION – GTG #1, 2 TRANSFORMER AREA | CALCULATION | GTG ¦ Gas Turbine Generator |  |  |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | false | 7 | 1 | 12.6642 | 0.6493 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152232 | ILLUMINATION CALCULATION – GTG #3, 4, 5 TRANSFORMER AREA | CALCULATION | GTG ¦ Gas Turbine Generator |  |  |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | false | 11 | 3 | 12.6946 | 0.6454 | 0.0300 | 0.0300 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152233 | ILLUMINATION CALCULATION – STG #1, 2 TRANSFORMER AREA | CALCULATION | STG ¦ Steam Turbine Generator |  |  |  | Calculation sheet for STG ¦ Steam Turbine Generator |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5739 | 0.5922 | 0.5922 | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | false | 1 | 10 | 23.9108 | 0.5996 | 0.0307 | 0.0307 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152234 | ILLUMINATION CALCULATION – FUEL GAS SYSTEM AREA | CALCULATION |  | FUEL GAS SYSTEM |  |  | Calculation sheet for FUEL GAS SYSTEM | Fuel Gas System | Calculation Sheets | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | calculation | calculation | calculation | calculation | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.9435 | 0.8430 | 0.8430 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | fgp | fgp | fgp | query | fgp | match | false | 4 | 1 | 10.8719 | 0.5587 | 0.0320 | 0.0320 | hybrid | structured_preferred | fgp | civil_design | 10 | 2024-10-02 | 2024-10-30 | 2024-11-27 | 2024-11-20 | 2024-12-18 | 2025-01-15 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152301 | LIGHTING & SMALL POWER LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7422 | 0.7477 | 0.7477 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 12 | 1 | 2.3394 | 0.5346 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152302 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator | LIGHTING & SMALL POWER | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7395 | 0.7468 | 0.7468 | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 1 | 13.9996 | 0.7409 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152303 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator | LIGHTING & SMALL POWER | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7383 | 0.7465 | 0.7465 | SKIP | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 4 | 4 | 13.5303 | 0.6847 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152304 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #1 LEB | LAYOUT DRAWING | ST ¦ Steam Turbine | LIGHTING & SMALL POWER | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7358 | 0.7457 | 0.7457 | SKIP | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | gsut_uat¦stg | match | false | 14 | 1 | 5.3098 | 0.6239 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152305 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #2 LEB | LAYOUT DRAWING | ST ¦ Steam Turbine | LIGHTING & SMALL POWER | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7365 | 0.7459 | 0.7459 | SKIP | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 11 | 2 | 6.0760 | 0.6209 | 0.0302 | 0.0302 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152306 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | ST BUILDING ¦ Steam Turbine BUILDING |  | Layout Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6639 | 0.6192 | 0.6192 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 11 | 1 | 3.9009 | 0.5463 | 0.0305 | 0.0305 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152307 | LIGHTING & SMALL POWER LAYOUT DRAWING - FGS ELECTRICAL BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7389 | 0.8050 | 0.8050 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 4 | 1 | 10.8162 | 0.5558 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152308 | LIGHTING & SMALL POWER LAYOUT DRAWING - ADMINISTRATION | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | ADMINISTRATION |  | Layout Drawing for ADMINISTRATION | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | administration |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7152 | 0.7396 | 0.7396 | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 1 | 30 | 0.0005 | 0.4068 | 0.0275 | 0.0206 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152309 | LIGHTING & SMALL POWER LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7241 | 0.7422 | 0.7422 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 4 | 1 | 2.3394 | 0.5228 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152310 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | MAIN GATE HOUSE |  | Layout Drawing for MAIN GATE HOUSE | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7158 | 0.7397 | 0.7397 | SKIP | 1CF6500W16A02 | (GTG TR) FDN & Firewall Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-12-01 | 2008-04-01 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 7 | 18 | 0.0005 | 0.4633 | 0.0277 | 0.0208 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152311 | LIGHTING & SMALL POWER LAYOUT DRAWING - SUPPORT BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | SUPPORT BUILDING |  | Layout Drawing for SUPPORT BUILDING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7348 | 0.7454 | 0.7454 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 4 | 1 | 2.3394 | 0.5336 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152312 | LIGHTING & SMALL POWER LAYOUT DRAWING - X-RAY SEARCHING ROOM | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | X-RAY SEARCHING ROOM |  | Layout Drawing for X-RAY SEARCHING ROOM | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6763 | 0.7279 | 0.7279 | SKIP | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦stg | match | false | 2 | 33 | 0.0005 | 0.3897 | 0.0269 | 0.0202 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152313 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE SUNSHADE | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | MAIN GATE HOUSE |  | Layout Drawing for MAIN GATE HOUSE | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6893 | 0.7318 | 0.7318 | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 1 | 25 | 0.0005 | 0.4410 | 0.0282 | 0.0211 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152314 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building |  | Layout Drawing for FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | aux¦auxiliary¦brigade¦electrical¦fire¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6956 | 0.7337 | 0.7337 | SKIP | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 4 | 8 | 3.1908 | 0.4991 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152315 | LIGHTING & SMALL POWER LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for WORKSHOP & STORAGE BUILDING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6998 | 0.7349 | 0.7349 | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 7 | 1 | 9.7019 | 0.5831 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152316 | LIGHTING & SMALL POWER LAYOUT DRAWING - H2, CO2, N2 STORAGE SHELTER | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | Layout Drawing for H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | carbon¦co2¦dioxide¦hydrogen¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6707 | 0.7262 | 0.7262 | SKIP | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | electrical¦h2¦n2 |  | electrical¦h2¦n2 | query | n2 | match | false | 1 | 5 | 13.1609 | 0.5792 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦h2¦n2 | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152317 | LIGHTING & SMALL POWER LAYOUT DRAWING - AIR COMPRESSOR SHELTER | LAYOUT DRAWING | AIR COMPRESSOR | LIGHTING & SMALL POWER | AIR COMPRESSOR SHELTER |  | Layout Drawing for AIR COMPRESSOR SHELTER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6693 | 0.7258 | 0.7258 | SKIP | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air¦electrical |  | compressed_air¦electrical | query | compressed_air | match | false | 2 | 2 | 19.9312 | 0.5878 | 0.0323 | 0.0323 | hybrid | structured_preferred | compressed_air¦electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152318 | LIGHTING & SMALL POWER LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | LAYOUT DRAWING |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7511 | 0.7503 | 0.7503 | SKIP | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 5 | 4 | 4.3597 | 0.5451 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152319 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE WATER PUMP HOUSE | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | FIRE WATER PUMP HOUSE |  | Layout Drawing for FIRE WATER PUMP HOUSE | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7108 | 0.7382 | 0.7382 | SKIP | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | design_drawing | civil_design | compatible | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 13.5237 | 0.5560 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical¦fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152320 | LIGHTING & SMALL POWER LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT DRAWING | TANK | LIGHTING & SMALL POWER | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5437 | 0.6298 | 0.6298 | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | false | 4 | 2 | 34.5568 | 0.6046 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦wts | civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152321 | LIGHTING & SMALL POWER LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | WATER TREATMENT BUILDING |  | Layout Drawing for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6911 | 0.6740 | 0.6740 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | false | 1 | 5 | 14.1673 | 0.5813 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152322 | LIGHTING & SMALL POWER LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Layout Drawing for CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7050 | 0.7365 | 0.7365 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | condensate¦electrical |  | condensate¦electrical | query | electrical | discipline_only | false | 4 | 1 | 2.3394 | 0.5305 | 0.0320 | 0.0160 | hybrid | structured_preferred | condensate¦electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152323 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR STG & HRSG | LAYOUT DRAWING | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator | LIGHTING & SMALL POWER | CHEMICAL DOSING SHELTER |  | Layout Drawing for CHEMICAL DOSING SHELTER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6968 | 0.7340 | 0.7340 | SKIP | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | electrical¦hrsg¦stg¦wts |  | electrical¦hrsg¦stg¦wts | query | gsut_uat¦stg | match | false | 1 | 7 | 24.7342 | 0.6357 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦hrsg¦stg¦wts | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152324 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR HRSG | LAYOUT DRAWING | HRSG ¦ Heat Recovery Steam Generator | LIGHTING & SMALL POWER | CHEMICAL DOSING SHELTER |  | Layout Drawing for CHEMICAL DOSING SHELTER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6904 | 0.7321 | 0.7321 | SKIP | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | electrical¦hrsg¦wts |  | electrical¦hrsg¦wts | query | hrsg | match | false | 9 | 5 | 16.0958 | 0.6579 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical¦hrsg¦wts | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152327 | LIGHTING & SMALL POWER LAYOUT DRAWING - YARD | LAYOUT DRAWING |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7511 | 0.7503 | 0.7503 | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 1 | 26 | 0.0005 | 0.4397 | 0.0280 | 0.0210 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152328 | LIGHTING & SMALL POWER LAYOUT DRAWING – TANK AREA | LAYOUT DRAWING |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for Tank | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7201 | 0.7410 | 0.7410 | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 1 | 17 | 0.0005 | 0.4646 | 0.0294 | 0.0220 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152329 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #1, 2 TRANSFORMER AREA | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for GTG | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7368 | 0.7460 | 0.7460 | SKIP | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 | design_drawing | civil_design | compatible | electrical¦gtg |  | electrical¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 10 | 4 | 12.2710 | 0.7065 | 0.0299 | 0.0224 | hybrid | structured_preferred | electrical¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152330 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #3, 4, 5 TRANSFORMER AREA | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for GTG | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7248 | 0.7424 | 0.7424 | SKIP | 3EF6500W32A12 | (GTG #31 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 | design_drawing | civil_design | compatible | electrical¦gtg |  | electrical¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 15 | 1 | 12.3008 | 0.7049 | 0.0297 | 0.0223 | hybrid | structured_preferred | electrical¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152331 | LIGHTING & SMALL POWER LAYOUT DRAWING – STG #1, 2 TRANSFORMER AREA | LAYOUT DRAWING | STG ¦ Steam Turbine Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | electrical¦stg | stg | electrical¦stg | query | gsut_uat¦stg | match | false | 8 | 1 | 21.1092 | 0.6659 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical¦stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152332 | LIGHTING & SMALL POWER LAYOUT DRAWING – FUEL GAS SYSTEM AREA | LAYOUT DRAWING |  | Fuel Gas System |  |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7646 | 0.6960 | 0.6960 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 4 | 1 | 10.8720 | 0.6634 | 0.0320 | 0.0240 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152333 | LIGHTING & SMALL POWER LAYOUT DRAWING – WELDING SHED AND CONTAINER AT OPEN STORAGE AREA | LAYOUT DRAWING |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7511 | 0.7503 | 0.7503 | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical | match | false | 7 | 1 | 3.7909 | 0.5197 | 0.0313 | 0.0235 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152401 | LIGHTING PANEL BOARD SCHEDULE - CENTRAL CONTROL BUILDING | SCHEDULE |  | LIGHTING | CENTRAL CONTROL BUILDING |  | Schedule for LIGHTING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - DOOR & WINDOW SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | schedule | schedule | schedule | schedule | ccr¦central¦lighting | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7533 | 0.6927 | 0.6927 | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 |  | delivery | query_unknown |  |  |  |  | electrical | query_unscoped | false | 1 | 8 | 27.0226 | 0.5300 | 0.0311 | 0.0175 | hybrid | structured_no_system |  |  |  | 2025-07-28 | 2025-08-27 | 2025-09-26 | 2025-10-11 | 2025-10-26 | 2025-11-10 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152402 | LIGHTING PANEL BOARD SCHEDULE - GTG #1,2 LEB | SCHEDULE |  | LIGHTING | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Schedule for LIGHTING |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦gtg¦leb¦lighting¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8706 | 0.9612 | 0.6728 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 11 | 2 | 8.7681 | 0.5655 | 0.0302 | 0.0227 | hybrid | structured_no_phase | electrical¦gtg |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152403 | LIGHTING PANEL BOARD SCHEDULE - GTG #3,4,5 LEB | SCHEDULE |  |  | GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building |  | Schedule for GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.5904 | 0.5971 | 0.5971 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 55 | 1 | 7.6181 | 0.5925 | 0.0251 | 0.0188 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152404 | LIGHTING PANEL BOARD SCHEDULE - ST #1 LEB | SCHEDULE |  |  | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | Schedule for ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.5952 | 0.7036 | 0.7036 | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 |  | delivery | query_unknown | electrical¦stg | stg | electrical¦stg | query | electrical | discipline_only | false | 1 | 2 | 13.5115 | 0.5357 | 0.0325 | 0.0122 | hybrid | structured_no_phase | electrical¦stg |  |  | 2025-07-28 | 2025-08-27 | 2025-09-26 | 2025-10-11 | 2025-10-26 | 2025-11-10 | generated | 0.90 | 0.34 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152405 | LIGHTING PANEL BOARD SCHEDULE - ST #2 LEB | SCHEDULE |  |  | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Schedule for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6060 | 0.7068 | 0.7068 | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 |  | delivery | query_unknown | electrical¦stg | stg | electrical¦stg | query | electrical | discipline_only | false | 1 | 2 | 13.5115 | 0.5326 | 0.0325 | 0.0122 | hybrid | structured_no_phase | electrical¦stg |  |  | 2025-07-28 | 2025-08-27 | 2025-09-26 | 2025-10-11 | 2025-10-26 | 2025-11-10 | generated | 0.90 | 0.34 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152406 | LIGHTING PANEL BOARD SCHEDULE - ST BUILDING | SCHEDULE |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Schedule for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6881 | 0.7314 | 0.7314 | FI | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  |  | civil_design | query_unknown | stg | stg | stg | query |  | activity_unscoped | true | 113 | 6 | 4.1065 | 0.5056 | 0.0209 | 0.0094 | hybrid | structured_no_phase | stg |  |  | 2024-08-27 | 2024-09-26 | 2024-10-26 | 2024-11-10 | 2024-11-25 | 2024-12-10 | generated | 0.90 | 0.43 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152407 | LIGHTING PANEL BOARD SCHEDULE - FGS ELECTRICAL BUILDING | SCHEDULE |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Schedule for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8822 | 0.9647 | 0.6753 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  |  | civil_design | query_unknown | electrical¦fgp |  | electrical¦fgp | query | fgp | match | false | 20 | 8 | 10.8163 | 0.5283 | 0.0272 | 0.0204 | hybrid | structured_no_phase | electrical¦fgp |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152408 | LIGHTING PANEL BOARD SCHEDULE - ADMINISTRATION | SCHEDULE |  |  |  |  | Schedule |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9003 | 0.9701 | 0.6791 | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 2 | 13.5115 | 0.5350 | 0.0323 | 0.0181 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152409 | LIGHTING PANEL BOARD SCHEDULE - SECURITY BUILDING | SCHEDULE |  |  | SECURITY BUILDING |  | Schedule for SECURITY BUILDING |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8720 | 0.9616 | 0.6731 | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 1 | 13.5115 | 0.5507 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152411 | LIGHTING PANEL BOARD SCHEDULE - SUPPORT BUILDING | SCHEDULE |  |  | SUPPORT BUILDING |  | Schedule for SUPPORT BUILDING |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8824 | 0.9647 | 0.6753 | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 1 | 13.5115 | 0.5691 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152414 | LIGHTING PANEL BOARD SCHEDULE - FIRE BRIGADE & AUX. LEB | SCHEDULE |  |  | FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building |  | Schedule for FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | aux¦auxiliary¦brigade¦electrical¦fire¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8088 | 0.9426 | 0.6599 | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown | electrical |  | electrical | query | electrical | match | false | 2 | 5 | 13.5115 | 0.5527 | 0.0315 | 0.0236 | hybrid | structured_no_phase | electrical |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152415 | LIGHTING PANEL BOARD SCHEDULE - WORKSHOP & STORAGE BUILDING | SCHEDULE |  |  | WORKSHOP & STORAGE BUILDING |  | Schedule for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7425 | 0.6894 | 0.6894 | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 2 | 13.5115 | 0.5362 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2025-01-15 | 2025-02-14 | 2025-03-16 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152418 | LIGHTING PANEL BOARD SCHEDULE - DEAERATOR SUPPORT STRUCTURE | SCHEDULE |  |  |  |  | Schedule |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8201 | 0.9460 | 0.6622 | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 |  | procurement | query_unknown |  |  |  |  | electrical | query_unscoped | false | 4 | 43 | 13.3126 | 0.5076 | 0.0253 | 0.0143 | hybrid | structured_no_system |  |  |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152419 | LIGHTING PANEL BOARD SCHEDULE - FIRE WATER PUMP HOUSE | SCHEDULE |  |  | FIRE WATER PUMP HOUSE |  | Schedule for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - FOUNDATION REBAR SCHEDULE, SLAB REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.5556 | 0.7277 | 0.6072 | 0.6072 | FI | 0CF4500W74A07 | (Fire WTR Pump Shelter) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-06 | 2008-07-02 |  | commissioning | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 13 | 2 | 13.4366 | 0.5496 | 0.0298 | 0.0224 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2025-02-06 | 2025-03-08 | 2025-04-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152421 | LIGHTING PANEL BOARD SCHEDULE - WATER TREATMENT BUILDING | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7905 | 0.7038 | 0.7038 | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 11 | 7 | 13.6716 | 0.5405 | 0.0290 | 0.0218 | hybrid | structured_no_phase | wts | [5 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152422 | LIGHTING PANEL BOARD SCHEDULE - CPP & CPP REGENERATION BUILDING | SCHEDULE |  |  |  |  | Schedule |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8309 | 0.9493 | 0.6645 | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 3 | 13.5115 | 0.5432 | 0.0320 | 0.0180 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152427 | LIGHTING PANEL BOARD SCHEDULE - YARD | SCHEDULE |  |  |  |  | Schedule |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8955 | 0.9686 | 0.6780 | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 1 | 13.5115 | 0.5435 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152428 | LIGHTING PANEL BOARD SCHEDULE – TANK AREA | SCHEDULE |  |  |  |  | Schedule for Tank |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8731 | 0.9619 | 0.6733 | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 1 | 13.5115 | 0.5179 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE04-P0BAU-152501 | TYPICAL INSTALLATION DRAWING - EARTHING AND LIGHTNING PROTECTION | DRAWING |  | EARTHING AND LIGHTNING PROTECTION |  |  | DRAWING for EARTHING AND LIGHTNING PROTECTION |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | earthing¦lightning¦protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7825 | 0.9348 | 0.6543 | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical | match | false | 9 | 1 |  | 0.4626 | 0.0309 | 0.0232 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0BAU-152502 | TECHNICAL SPECIFICATION - EARTHING AND LIGHTNING PROTECTION SYSTEM | TECHNICAL SPECIFICATION |  | EARTHING AND LIGHTNING PROTECTION SYSTEM |  |  | Technical Specification for EARTHING AND LIGHTNING PROTECTION SYSTEM |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | earthing¦lightning¦protection |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6981 | 0.6761 | 0.4733 | FA | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | false | 1 | 3 | 61.2120 | 0.6683 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAU-152503 | MAIN EARTHING GRID CALCULATION | CALCULATION |  |  |  |  | Calculation sheet | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6392 | 0.5418 | 0.5418 | FA | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | civil_design | civil_design | match |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | 3288 | 18 |  | 0.4975 | 0.0131 | 0.0098 | hybrid | structured_no_system |  | civil_design |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.49 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152504 | EARTHING LAYOUT DRAWING - MAIN GRID | DRAWING |  |  |  |  | DRAWING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7883 | 0.7615 | 0.7615 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 1 | 1 |  | 0.5319 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152505 | EARTHING LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  | EARTHING | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7854 | 0.7606 | 0.7606 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 12 | 1 | 2.3392 | 0.5347 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152506 | EARTHING LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING |  | EARTHING | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Layout Drawing for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7571 | 0.7521 | 0.7521 | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 1 | 1 | 8.7678 | 0.6191 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152507 | EARTHING LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING |  | EARTHING | GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building |  | Layout Drawing for GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7439 | 0.7482 | 0.7482 | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 6 | 1 | 7.6178 | 0.6024 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P6BAU-152508 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #1 LEB | LAYOUT DRAWING | ST ¦ Steam Turbine | EARTHING & LIGHTNING PROTECTION | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | Layout Drawing for ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6094 | 0.6028 | 0.6028 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | gsut_uat¦stg | match | false | 14 | 1 | 5.3094 | 0.6046 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE03-P7BAU-152509 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #2 LEB | LAYOUT DRAWING | ST ¦ Steam Turbine | EARTHING & LIGHTNING PROTECTION | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Layout Drawing for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6027 | 0.6008 | 0.6008 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 11 | 4 | 6.0756 | 0.5900 | 0.0297 | 0.0297 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152510 | EARTHING LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING |  | EARTHING | ST BUILDING ¦ Steam Turbine BUILDING |  | Layout Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6639 | 0.6192 | 0.6192 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 12 | 2 | 3.9005 | 0.5444 | 0.0300 | 0.0300 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152511 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7389 | 0.8050 | 0.8050 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 4 | 5 | 10.8160 | 0.5151 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152512 | EARTHING LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | LAYOUT DRAWING |  | EARTHING | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7268 | 0.7430 | 0.7430 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 4 | 1 | 2.3392 | 0.5427 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152513 | EARTHING LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | EARTHING | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7446 | 0.7484 | 0.7484 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 4 | 1 | 2.3392 | 0.5272 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152514 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GATE HOUSE | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | GATE HOUSE |  | Layout Drawing for GATE HOUSE | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gate¦house |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7606 | 0.7882 | 0.7882 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | false | 1 | 1 |  | 0.5427 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152515 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SUPPORT BUILDING | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | SUPPORT BUILDING |  | Layout Drawing for SUPPORT BUILDING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7592 | 0.7878 | 0.7878 | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 2 | 2 | 2.5087 | 0.5105 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152516 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SEARCH FACILITY AND VISITORS CENTRE | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | SEARCH FACILITY AND VISITORS CENTRE |  | Layout Drawing for SEARCH FACILITY AND VISITORS CENTRE | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6545 | 0.7564 | 0.7564 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | false | 9 | 1 |  | 0.5036 | 0.0309 | 0.0232 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152517 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE BRIGADE | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | FIRE BRIGADE |  | Layout Drawing for FIRE BRIGADE | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7502 | 0.7851 | 0.7851 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | false | 1 | 1 |  | 0.5153 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152518 | EARTHING LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | EARTHING | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for WORKSHOP & STORAGE BUILDING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7366 | 0.7460 | 0.7460 | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 7 | 1 | 9.7017 | 0.5715 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152519 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - N2 STORAGE SHELTER | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | Layout Drawing for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7257 | 0.7777 | 0.7777 | SKIP | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | electrical¦n2 | electrical | electrical¦n2 | query | n2 | match | false | 1 | 6 | 13.1604 | 0.5832 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦n2 | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152520 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COMPRESSOR SHELTER | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | AIR COMPRESSOR SHELTER |  | Layout Drawing for AIR COMPRESSOR SHELTER | Air Compressor | Earthing point layout | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7398 | 0.7819 | 0.7819 | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air¦electrical | compressed_air¦electrical | compressed_air¦electrical | query | compressed_air | match | false | 1 | 3 | 12.3084 | 0.5709 | 0.0323 | 0.0323 | hybrid | structured_preferred | compressed_air¦electrical | civil_design | 10 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152521 | EARTHING LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | LAYOUT DRAWING |  | EARTHING |  |  | Layout Drawing for EARTHING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | earthing |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7641 | 0.7542 | 0.7542 | SKIP | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 5 | 4 | 4.3592 | 0.5340 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152522 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | FIRE WATER PUMP HOUSE |  | Layout Drawing for FIRE WATER PUMP HOUSE | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7465 | 0.7839 | 0.7839 | SKIP | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | design_drawing | civil_design | compatible | electrical¦fire_fighting | electrical | electrical¦fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 13.5235 | 0.5459 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical¦fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152523 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5437 | 0.6298 | 0.6298 | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | false | 1 | 3 | 28.7086 | 0.5705 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152524 | EARTHING LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | EARTHING | WATER TREATMENT BUILDING |  | Layout Drawing for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6911 | 0.6740 | 0.6740 | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | false | 4 | 3 | 13.6713 | 0.5857 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152525 | EARTHING LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | EARTHING LAYOUT DRAWING |  |  | CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | EARTHING LAYOUT DRAWING for CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6946 | 0.7334 | 0.7334 | SKIP | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate | electrical | condensate | query | acc¦condensate | match | false | 6 | 3 |  | 0.3923 | 0.0310 | 0.0310 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152526 | EARTHING LAYOUT DRAWING - PIPE RACK FOR HRSG | EARTHING LAYOUT DRAWING | HRSG ¦ Heat Recovery Steam Generator |  | PIPE RACK |  | EARTHING LAYOUT DRAWING for PIPE RACK | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | hrsg¦pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7321 | 0.7446 | 0.7446 | SKIP | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | electrical | hrsg | query | hrsg | match | false | 9 | 3 | 16.0954 | 0.6594 | 0.0304 | 0.0304 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152527 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AUX. LEB | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for AUX. LEB ¦ Auxiliary Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | aux¦auxiliary¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7235 | 0.7770 | 0.7770 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 5 | 1 |  | 0.5279 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152528 | EARTHING LAYOUT DRAWING - TANK AREA | EARTHING LAYOUT DRAWING |  |  |  |  | EARTHING LAYOUT DRAWING for Tank | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7782 | 0.7585 | 0.7585 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 1 | 12 |  | 0.4644 | 0.0303 | 0.0227 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152529 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #1,2 AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | GTG ¦ Gas Turbine Generator |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for GTG | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7761 | 0.7928 | 0.7928 | SKIP | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | electrical¦gsut_uat¦gtg | match | false | 8 | 9 | 11.0686 | 0.6755 | 0.0292 | 0.0219 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152530 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #3,4,5 AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | GTG ¦ Gas Turbine Generator |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for GTG | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7761 | 0.7928 | 0.7928 | SKIP | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | electrical¦gsut_uat¦gtg | match | false | 16 | 6 | 11.0990 | 0.6716 | 0.0283 | 0.0212 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152531 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - STG TR AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | STG ¦ Steam Turbine Generator |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Steam Turbine Generator | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7647 | 0.7894 | 0.7894 | SKIP | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | design_drawing | civil_design | compatible | stg | electrical | stg | query | stg | match | false | 1 | 16 | 18.5204 | 0.6099 | 0.0296 | 0.0222 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152532 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-1 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | AIR COOLED CONDENSER-1 |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8244 | 0.9473 | 0.9473 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | false | 1 | 3 | 20.1915 | 0.5506 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152533 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-2 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | AIR COOLED CONDENSER-2 |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8244 | 0.9473 | 0.9473 | FA | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | false | 1 | 1 | 21.5947 | 0.5523 | 0.0328 | 0.0246 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152534 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIN FAN COOLER & CCW PUMP AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | FIN FAN COOLER & CCW PUMP ¦ FIN FAN COOLER & Closed Cooling Water PUMP |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Pump | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | pump |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7511 | 0.7853 | 0.7853 | SKIP | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw | electrical | ccw | query | ccw¦gtg | match | false | 3 | 3 | 73.0070 | 0.5919 | 0.0317 | 0.0238 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152535 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  | FGS ¦ Fuel Gas System |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for FGS ¦ Fuel Gas System | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7884 | 0.8199 | 0.8199 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp | electrical¦fgp | fgp | query | fgp | match | false | 4 | 1 | 16.1968 | 0.6603 | 0.0320 | 0.0240 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152536 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - BLACK START DIESEL GENERATOR AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | BLACK START DIESEL GENERATOR |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for BLACK START DIESEL GENERATOR | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | black¦diesel¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7408 | 0.7822 | 0.7822 | SKIP | 1EF3530W16A02 | (Block #1 EDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-10-29 | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 1 | 8 | 13.4496 | 0.5365 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152537 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - H2, CO2 STORAGE SHELTER | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6853 | 0.7656 | 0.7656 | SKIP | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | electrical | h2 | query | h2 | match | false | 1 | 1 | 8.8427 | 0.4256 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152538 | EARTHING LAYOUT DRAWING - 380kV EHV CABLE INSULATION JOINT AREA | EARTHING LAYOUT DRAWING |  |  |  |  | EARTHING LAYOUT DRAWING |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing |  | acc | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8322 | 0.7747 | 0.7747 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  | acc¦electrical | acc¦electrical | rule | electrical | discipline_only | false | 2 | 2 | 8.4510 | 0.5449 | 0.0323 | 0.0060 | hybrid | structured_preferred | acc¦electrical | system_design¦civil_design | 10 | [6 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152539 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - CHEMICAL DOSING SYSTEM | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for CHEMICAL DOSING SYSTEM | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7174 | 0.7752 | 0.7752 | SKIP | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | wts | electrical | wts | query | wts | match | false | 1 | 1 | 33.6657 | 0.6704 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152540 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - PRELIMINARY INSPECTION CHECK POINT (PIC) | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7951 | 0.7985 | 0.7985 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 1 | 1 |  | 0.5175 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152600 | LIGHTNING PROTECTION LAYOUT DRAWING - OVERALL AREA | LIGHTNING PROTECTION LAYOUT DRAWING |  |  |  |  | LIGHTNING PROTECTION LAYOUT DRAWING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.8340 | 0.8102 | 0.8102 | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 1 | 1 |  | 0.4786 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152601 | LIGHTNING PROTECTION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LIGHTNING PROTECTION LAYOUT DRAWING |  |  | CENTRAL CONTROL BUILDING |  | LIGHTNING PROTECTION LAYOUT DRAWING for CENTRAL CONTROL BUILDING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8020 | 0.8006 | 0.8006 | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match |  | electrical | electrical | rule | electrical | match | false | 8 | 2 | 2.5087 | 0.4938 | 0.0308 | 0.0308 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152602 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #1,2 LEB | LIGHTNING PROTECTION LAYOUT DRAWING | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | LIGHTNING PROTECTION LAYOUT DRAWING for LEB ¦ Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7824 | 0.7947 | 0.7947 | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 1 | 1 | 13.9992 | 0.7037 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152603 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #3,4,5 LEB | LIGHTNING PROTECTION LAYOUT DRAWING | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | LIGHTNING PROTECTION LAYOUT DRAWING for LEB ¦ Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7824 | 0.7947 | 0.7947 | SKIP | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 4 | 5 | 13.5299 | 0.6636 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152606 | LIGHTNING PROTECTION LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING |  | LIGHTNING PROTECTION | ST BUILDING ¦ Steam Turbine BUILDING |  | Layout Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6639 | 0.6192 | 0.6192 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 11 | 2 | 3.9005 | 0.5096 | 0.0302 | 0.0302 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152608 | LIGHTNING PROTECTION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | LAYOUT DRAWING |  | LIGHTNING PROTECTION | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7462 | 0.7839 | 0.7839 | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 2 | 2 | 2.5087 | 0.4929 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152609 | LIGHTNING PROTECTION LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | LIGHTNING PROTECTION | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7690 | 0.7907 | 0.7907 | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 2 | 2 | 2.5087 | 0.4882 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152614 | LIGHTNING PROTECTION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | LIGHTNING PROTECTION | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for WORKSHOP & STORAGE BUILDING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7586 | 0.7876 | 0.7876 | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 7 | 2 | 9.7017 | 0.5110 | 0.0311 | 0.0311 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152620 | LIGHTNING PROTECTION LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | LIGHTNING PROTECTION | WATER TREATMENT BUILDING |  | Layout Drawing for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6911 | 0.6740 | 0.6740 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | false | 1 | 4 | 14.1670 | 0.5388 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152621 | LIGHTNING PROTECTION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | LAYOUT DRAWING |  | LIGHTNING PROTECTION | CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Layout Drawing for CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7601 | 0.7880 | 0.7880 | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | condensate¦electrical | electrical | condensate¦electrical | query | electrical | discipline_only | false | 2 | 2 | 2.5087 | 0.4905 | 0.0323 | 0.0161 | hybrid | structured_preferred | condensate¦electrical | civil_design | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152701 | TECHNICAL SPECIFICATION - PVC CONDUIT AND ACCESSORIES | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7963 | 0.9389 | 0.9389 | FA | 0EF6020W58A01 | (Piping) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 5 | 15 | 10.8065 | 0.4730 | 0.0287 | 0.0215 | hybrid | structured_no_system |  | procurement |  | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152702 | TECHNICAL SPECIFICATION - STEEL CONDUIT AND ACCESSORIES | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8202 | 0.9461 | 0.9461 | FA | 0EF6020W46A07 | (Hanger & Support & Fitting) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 29 | 9 | 10.4905 | 0.5033 | 0.0257 | 0.0193 | hybrid | structured_no_system |  | procurement |  | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152705 | EMBEDDED CONDUIT LAYOUT FOR ST #1 LEB | LAYOUT |  |  | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | Layout Drawing for ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6094 | 0.6028 | 0.6028 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | gsut_uat¦stg | match | false | 8 | 5 | 4.6314 | 0.4945 | 0.0301 | 0.0301 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152706 | EMBEDDED CONDUIT LAYOUT FOR ST #2 LEB | LAYOUT |  |  | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Layout Drawing for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6027 | 0.6008 | 0.6008 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 6 | 9 | 5.5282 | 0.4834 | 0.0296 | 0.0296 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152707 | EMBEDDED CONDUIT LAYOUT FOR ST BUILDING | LAYOUT |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Layout Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6639 | 0.6192 | 0.6192 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 2 | 1 | 7.6518 | 0.5227 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152708 | EMBEDDED CONDUIT LAYOUT FOR FGS ELECTRICAL BUILDING | LAYOUT |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7389 | 0.8050 | 0.8050 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 4 | 3 | 14.2104 | 0.5788 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152709 | EMBEDDED CONDUIT LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | LAYOUT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8169 | 0.9451 | 0.6616 | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 22 | 13 | 7.5640 | 0.5103 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152710 | EMBEDDED CONDUIT LAYOUT FOR SECURITY BUILDING | LAYOUT |  |  | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8706 | 0.9612 | 0.6728 | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 13 | 38 | 7.5640 | 0.4695 | 0.0239 | 0.0179 | hybrid | structured_no_system |  | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152711 | EMBEDDED CONDUIT LAYOUT FOR MAIN GATE HOUSE AREA | LAYOUT |  |  |  |  | Layout Drawing |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8581 | 0.9574 | 0.6702 | FA | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 4 | 1 | 17.1992 | 0.5455 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152715 | EMBEDDED CONDUIT LAYOUT FOR FIRE BRIGADE | LAYOUT |  |  | FIRE BRIGADE |  | Layout Drawing for FIRE BRIGADE |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8749 | 0.9625 | 0.6737 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 4 | 4 | 10.3514 | 0.5273 | 0.0312 | 0.0234 | hybrid | structured_no_system |  | civil_design |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152716 | EMBEDDED CONDUIT LAYOUT FOR WORKSHOP & STORAGE BUILDING | LAYOUT |  |  | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for WORKSHOP & STORAGE BUILDING |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8342 | 0.9502 | 0.6652 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 7 | 1 | 13.3436 | 0.5593 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152717 | EMBEDDED CONDUIT LAYOUT FOR H2, CO2, N2 STORAGE SHELTER | LAYOUT |  |  | H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | Layout Drawing for H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | carbon¦co2¦dioxide¦hydrogen¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7329 | 0.9199 | 0.6439 | FA | 1EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 |  | civil_design | civil_design | match | h2¦n2 |  | h2¦n2 | query | n2 | match | false | 1 | 2 | 15.0302 | 0.6256 | 0.0325 | 0.0325 | hybrid | structured_preferred | h2¦n2 | civil_design | 10 | 2024-07-21 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152718 | EMBEDDED CONDUIT LAYOUT FOR AIR COMPRESSOR SHELTER | LAYOUT | AIR COMPRESSOR |  | AIR COMPRESSOR SHELTER |  | Layout Drawing for AIR COMPRESSOR SHELTER |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7982 | 0.9395 | 0.6576 | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 4 | 1 | 22.7315 | 0.6432 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152719 | EMBEDDED CONDUIT LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | LAYOUT |  |  |  |  | Layout Drawing |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8158 | 0.9447 | 0.6613 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 18 | 34 | 7.1778 | 0.5148 | 0.0235 | 0.0176 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152720 | EMBEDDED CONDUIT LAYOUT FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER(CPP) | EMBEDDED CONDUIT LAYOUT | Fire water pump |  | Fire Water Pump House |  | EMBEDDED CONDUIT LAYOUT for Fire Water Pump House | CPP FIN FAN COOLER | CPP FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6715 | 0.7848 | 0.7848 | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | ccw | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 1 | 27.0469 | 0.6009 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152721 | EMBEDDED CONDUIT LAYOUT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | EMBEDDED CONDUIT LAYOUT | BULK CHEMICAL STORAGE TANK |  | WWT ¦ Waste Water Treatment |  | EMBEDDED CONDUIT LAYOUT for WWT ¦ Waste Water Treatment |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank¦treatment¦waste¦water¦wts¦wwt |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7993 | 0.9398 | 0.6578 | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 2 | 3 | 52.9788 | 0.6042 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152722 | EMBEDDED CONDUIT LAYOUT FOR WATER TREATMENT BUILDING | EMBEDDED CONDUIT LAYOUT |  |  | WATER TREATMENT BUILDING |  | EMBEDDED CONDUIT LAYOUT for WATER TREATMENT BUILDING |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8417 | 0.9525 | 0.6667 | FA | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 1 | 6 | 14.1670 | 0.5739 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152724 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | EMBEDDED CONDUIT LAYOUT | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator | CHEMICAL DOSING |  |  | EMBEDDED CONDUIT LAYOUT for HRSG |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7156 | 0.6813 | 0.6813 | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match | hrsg¦stg¦wts | hrsg | hrsg¦stg¦wts | query | wts | match | false | 2 | 1 | 30.8879 | 0.6196 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2024-05-14 | 2024-05-29 | 2024-06-13 | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152725 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | EMBEDDED CONDUIT LAYOUT | HRSG ¦ Heat Recovery Steam Generator | CHEMICAL DOSING |  |  | EMBEDDED CONDUIT LAYOUT for HRSG |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7156 | 0.6813 | 0.6813 | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match | hrsg¦wts | hrsg | hrsg¦wts | query | wts | match | false | 2 | 1 | 30.8879 | 0.6251 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | 2024-05-14 | 2024-05-29 | 2024-06-13 | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152726 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | EMBEDDED CONDUIT LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 4 | 2 | 11.9626 | 0.7076 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152727 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | EMBEDDED CONDUIT LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | FA | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 3 | 1 | 12.6642 | 0.7014 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152728 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | EMBEDDED CONDUIT LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | FA | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 3 | 3 | 12.6946 | 0.7032 | 0.0317 | 0.0317 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152729 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | EMBEDDED CONDUIT LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | FA | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 15 | 1 | 10.3627 | 0.7008 | 0.0297 | 0.0297 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152730 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | EMBEDDED CONDUIT LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 10 | 1 | 10.3627 | 0.6979 | 0.0307 | 0.0307 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152731 | EMBEDDED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | EMBEDDED CONDUIT LAYOUT | POTABLE STORAGE WATER TANK & FIRE WATER TANK |  |  |  | EMBEDDED CONDUIT LAYOUT for Tank |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8735 | 0.9620 | 0.6734 | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 2 | 2 | 20.9779 | 0.4828 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152732 | EMBEDDED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | EMBEDDED CONDUIT LAYOUT |  |  |  |  | EMBEDDED CONDUIT LAYOUT for Tank |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8735 | 0.9620 | 0.6734 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 2 | 2 | 25.7879 | 0.5788 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152733 | EMBEDDED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | EMBEDDED CONDUIT LAYOUT |  |  |  |  | EMBEDDED CONDUIT LAYOUT for Tank |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8735 | 0.9620 | 0.6734 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match |  |  |  |  | condensate¦fgp | query_unscoped | false | 15 | 18 | 11.4563 | 0.5615 | 0.0262 | 0.0196 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | 2024-04-02 | 2024-05-02 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152735 | EMBEDDED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | EMBEDDED CONDUIT LAYOUT | Fin Fan Cooler(CCW) & CCW PUMP ¦ Fin Fan Cooler(Closed Cooling Water) & Closed Cooling Water PUMP |  |  |  | EMBEDDED CONDUIT LAYOUT for Pump | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | pump |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7635 | 0.8124 | 0.8124 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | false | 3 | 3 | 92.4047 | 0.6614 | 0.0317 | 0.0317 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152736 | EMBEDDED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | EMBEDDED CONDUIT LAYOUT | STG ¦ Steam Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7058 | 0.7717 | 0.7717 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | false | 3 | 9 | 23.9108 | 0.6602 | 0.0304 | 0.0304 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152750 | ELECTRICAL DUCT BANK LAYOUT DRAWING CENTRAL CONTROL BUILDING AREA | LAYOUT DRAWING |  |  | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8588 | 0.9576 | 0.9576 | FA | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match |  | electrical | electrical | rule | electrical | match | false | 14 | 3 | 4.8096 | 0.5354 | 0.0294 | 0.0294 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.80 | usable | activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152751 | ELECTRICAL DUCT BANK LAYOUT GTG #1 AREA | ELECTRICAL DUCT BANK LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | FA | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | false | 1 | 2 | 13.2693 | 0.6858 | 0.0325 | 0.0244 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152752 | ELECTRICAL DUCT BANK LAYOUT GTG #2 AREA | ELECTRICAL DUCT BANK LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | FA | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | false | 1 | 7 | 13.8139 | 0.6832 | 0.0313 | 0.0235 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152753 | ELECTRICAL DUCT BANK LAYOUT GTG #3,#4 AREA | ELECTRICAL DUCT BANK LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | FA | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | false | 1 | 12 | 13.8376 | 0.6680 | 0.0303 | 0.0227 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152754 | ELECTRICAL DUCT BANK LAYOUT GTG #5 AREA | ELECTRICAL DUCT BANK LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | FA | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | false | 4 | 1 | 12.0274 | 0.6821 | 0.0320 | 0.0240 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152755 | ELECTRICAL DUCT BANK LAYOUT HRSG #1 AREA | LAYOUT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 1EF1615W00A01 | (HRSG #11 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-04-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 4 | 9 | 25.5142 | 0.6952 | 0.0301 | 0.0226 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦civil_design |  | 2025-01-10 | 2025-02-09 | 2025-03-11 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152756 | ELECTRICAL DUCT BANK LAYOUT HRSG #2 AREA | LAYOUT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 3 | 7 | 26.0417 | 0.7016 | 0.0308 | 0.0231 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦civil_design |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152757 | ELECTRICAL DUCT BANK LAYOUT HRSG #3,#4 AREA | LAYOUT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 3 | 7 | 26.0646 | 0.6945 | 0.0308 | 0.0231 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦civil_design |  | 2025-03-11 | 2025-04-10 | 2025-05-10 | 2025-05-25 | 2025-06-09 | 2025-06-24 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152758 | ELECTRICAL DUCT BANK LAYOUT HRSG #5 AREA | LAYOUT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | false | 4 | 7 | 24.3112 | 0.6814 | 0.0306 | 0.0229 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦civil_design |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152759 | ELECTRICAL DUCT BANK LAYOUT AIR COMPRESSOR & ACC AREA | LAYOUT | AIR COMPRESSOR & ACC ¦ AIR COMPRESSOR & Air Cooled Condenser |  |  |  | Layout Drawing for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.6746 | 0.7274 | 0.7274 | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  | design_drawing | civil_design | compatible | acc¦compressed_air | acc¦electrical | acc¦compressed_air | query | compressed_air | match | false | 1 | 1 | 30.5609 | 0.6415 | 0.0328 | 0.0246 | hybrid | structured_preferred | acc¦compressed_air | system_design¦civil_design | 10 | 2025-03-18 | 2025-04-17 | 2025-05-17 | 2025-06-01 | 2025-06-16 | 2025-07-01 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152760 | ELECTRICAL DUCT BANK LAYOUT ST #1 LEB | LAYOUT | ST ¦ Steam Turbine |  | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8813 | 0.9644 | 0.9644 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | gsut_uat¦stg | match | false | 9 | 1 | 8.7745 | 0.6359 | 0.0309 | 0.0309 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152761 | ELECTRICAL DUCT BANK LAYOUT ST #2 LEB | LAYOUT | ST ¦ Steam Turbine |  | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8730 | 0.9619 | 0.9619 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 8 | 3 | 9.8269 | 0.6267 | 0.0306 | 0.0306 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152762 | ELECTRICAL DUCT BANK LAYOUT TANK AREA | LAYOUT | TANK |  |  |  | Layout Drawing for Tank |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9305 | 0.9791 | 0.9791 | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 4 | 4 | 5.9370 | 0.5167 | 0.0312 | 0.0234 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152763 | ELECTRICAL DUCT BANK LAYOUT WATER TREATMENT BUILDING AREA | LAYOUT |  |  | WATER TREATMENT BUILDING |  | Layout Drawing for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6911 | 0.6740 | 0.6740 | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 4 | 3 | 19.5344 | 0.6097 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152764 | ELECTRICAL DUCT BANK LAYOUT CPP REGEN BUILDING AREA | LAYOUT |  |  |  |  | Layout Drawing |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8508 | 0.9552 | 0.9552 | FA | 2EF3530W00A01 | (Block #2 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | civil_design | civil_design | match |  | electrical | electrical | rule | electrical | match | false | 5 | 1 | 5.9370 | 0.5512 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.80 | needs_review | rule_scope_status=query_unscoped;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152765 | ELECTRICAL DUCT BANK LAYOUT FGS & RESERVE BOILER AREA | LAYOUT | RESERVE BOILER | FGS ¦ Fuel Gas System |  |  | Layout Drawing for FGS ¦ Fuel Gas System | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fgs¦fuel¦gas¦reserve_boiler | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8361 | 0.8342 | 0.8342 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp¦reserve_boiler | fgp | fgp¦reserve_boiler | query | fgp | match | false | 4 | 1 | 21.9177 | 0.6505 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | fgp¦reserve_boiler | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152766 | ELECTRICAL DUCT BANK LAYOUT ADMINISTRATION & SOCIAL BUILDING AREA | LAYOUT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8395 | 0.9519 | 0.9519 | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match |  | electrical | electrical | rule | electrical | match | false | 1 | 3 | 8.5917 | 0.5247 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.80 | usable | activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152767 | ELECTRICAL DUCT BANK LAYOUT SECURITY BUILDING AREA | LAYOUT |  |  | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8811 | 0.9643 | 0.9643 | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | civil_design | civil_design | match |  | electrical | electrical | rule | electrical | match | false | 4 | 1 | 5.9370 | 0.5365 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.80 | usable | activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152768 | ELECTRICAL DUCT BANK LAYOUT MAIN GATE HOUSE AREA | LAYOUT |  |  | MAIN GATE HOUSE |  | Layout Drawing for MAIN GATE HOUSE |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8816 | 0.9645 | 0.9645 | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 4 | 1 | 5.9370 | 0.5405 | 0.0320 | 0.0240 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152769 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 1 | LAYOUT | EHV CABLE ¦ Extra High Voltage CABLE |  |  |  | Layout Drawing for EHV CABLE ¦ Extra High Voltage CABLE |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | cable¦ehv¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8644 | 0.9593 | 0.9593 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 2 | 2 | 48.7220 | 0.6263 | 0.0323 | 0.0242 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152770 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 2 | LAYOUT | EHV CABLE ¦ Extra High Voltage CABLE |  |  |  | Layout Drawing for EHV CABLE ¦ Extra High Voltage CABLE |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | cable¦ehv¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8635 | 0.9591 | 0.9591 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 4 | 1 | 47.1332 | 0.6299 | 0.0320 | 0.0240 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152771 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 3 | LAYOUT | EHV CABLE ¦ Extra High Voltage CABLE |  |  |  | Layout Drawing for EHV CABLE ¦ Extra High Voltage CABLE |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | cable¦ehv¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8639 | 0.9592 | 0.9592 | FA | 3CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 2 | 2 | 49.4490 | 0.6265 | 0.0323 | 0.0242 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152791 | RACEWAY DRAWING FOR HCIS – MAIN GATE HOUSE | RACEWAY DRAWING |  |  | MAIN GATE HOUSE |  | RACEWAY DRAWING for MAIN GATE HOUSE |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6778 | 0.6700 | 0.6700 | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 9 | 7 | 17.1992 | 0.5072 | 0.0294 | 0.0132 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152792 | RACEWAY DRAWING FOR HCIS – PLANT ACCESS GATE HOUSE | RACEWAY DRAWING |  |  | PLANT ACCESS GATE HOUSE |  | RACEWAY DRAWING for PLANT ACCESS GATE HOUSE |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | access¦gate¦house¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6921 | 0.6743 | 0.6743 | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 9 | 7 | 17.1995 | 0.5316 | 0.0294 | 0.0132 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152793 | RACEWAY DRAWING FOR HCIS – SEARCH FACILITY & VISITOR CENTRE | RACEWAY DRAWING |  |  | SEARCH FACILITY & VISITOR CENTRE |  | RACEWAY DRAWING for SEARCH FACILITY & VISITOR CENTRE |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | centre¦facility¦search¦visitor |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6538 | 0.6628 | 0.6628 | FA | 0EF5570W32A03.1 | (Convered Parking Place shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-15 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 1336 | 13 |  | 0.4367 | 0.0144 | 0.0065 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-12-27 | 2025-01-26 | 2025-02-25 | 2025-03-12 | 2025-03-27 | 2025-04-11 | generated | 0.90 | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152794 | RACEWAY DRAWING FOR HCIS – SUPPORT BUILDING | RACEWAY DRAWING |  |  | SUPPORT BUILDING |  | RACEWAY DRAWING for SUPPORT BUILDING |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7066 | 0.6786 | 0.6786 | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 1072 | 71 | 2.4495 | 0.4382 | 0.0085 | 0.0064 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152795 | RACEWAY DRAWING FOR HCIS – PRELIMINARY INSPECTION CHECKPOINT | RACEWAY DRAWING |  |  |  |  | RACEWAY DRAWING |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7881 | 0.7031 | 0.7031 | FA | 1CF3030W16A18 | (CCWP) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-01-31 | 2008-03-28 | design_drawing | civil_design | compatible |  |  |  |  | ccw | query_unscoped | false | 550 | 211 | 3.3799 | 0.4149 | 0.0053 | 0.0030 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-152801 | SIZING CALCULATION - MV/LV POWER CABLES | SIZING CALCULATION | MV/LV POWER CABLES ¦ Medium Voltage/Low Voltage POWER CABLES |  |  |  | Calculation sheet for MV/LV POWER CABLES ¦ Medium Voltage/Low Voltage POWER CABLES | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | cables¦low¦medium¦power¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7350 | 0.5705 | 0.5705 | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 48 | 16 | 12.4418 | 0.4881 | 0.0224 | 0.0168 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152810 | SIZING CALCULATION - 380KV EHV CABLE AND ACCESSOIRES | SIZING CALCULATION | 380KV EHV CABLE AND ACCESSOIRES ¦ 380KV Extra High Voltage CABLE AND ACCESSOIRES |  |  |  | Calculation sheet for 380KV EHV CABLE AND ACCESSOIRES ¦ 380KV Extra High Voltage CABLE AND ACCESSOIRES | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | 380kv¦accessoires¦cable¦ehv¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6928 | 0.7329 | 0.7329 | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 21 | 8 | 44.5911 | 0.5819 | 0.0271 | 0.0203 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152820 | TECHNICAL SPECIFICATION - 380KV EHV CABLE AND ACCESSORIES | TECHNICAL SPECIFICATION | 380KV EHV CABLE AND ACCESSORIES ¦ 380KV Extra High Voltage CABLE AND ACCESSORIES |  |  |  | Technical Specification for 380KV EHV CABLE AND ACCESSORIES ¦ 380KV Extra High Voltage CABLE AND ACCESSORIES |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | 380kv¦accessories¦cable¦ehv¦extra¦high¦voltage |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6540 | 0.6629 | 0.4640 | FA | 2PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-04-01 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 12 | 1 | 57.9103 | 0.6536 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | procurement |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0ZEN-152822 | OUTLINE & SCHEMATIC DRAWING - 380KV EHV CABLE AND ACCESSOIRES | OUTLINE & SCHEMATIC DRAWING | 380KV EHV CABLE AND ACCESSOIRES ¦ 380KV Extra High Voltage CABLE AND ACCESSOIRES |  |  |  | OUTLINE & SCHEMATIC DRAWING for 380KV EHV CABLE AND ACCESSOIRES ¦ 380KV Extra High Voltage CABLE AND ACCESSOIRES |  | OUTLINE & SCHEMATIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | 380kv¦accessoires¦cable¦ehv¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7234 | 0.9170 | 0.6419 | FA | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 22 | 16 | 44.5911 | 0.5875 | 0.0254 | 0.0143 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152823 | INSTALLATION DRAWING - 380KV EHV CABLE AND ACCESSOIRES | INSTALLATION DRAWING | 380KV EHV CABLE AND ACCESSOIRES ¦ 380KV Extra High Voltage CABLE AND ACCESSOIRES |  |  |  | INSTALLATION DRAWING for 380KV EHV CABLE AND ACCESSOIRES ¦ 380KV Extra High Voltage CABLE AND ACCESSOIRES |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | 380kv¦accessoires¦cable¦ehv¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5984 | 0.6462 | 0.6462 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 21 | 11 | 44.5911 | 0.5933 | 0.0264 | 0.0149 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-12-28 | 2025-01-27 | 2025-02-26 | 2025-03-13 | 2025-03-28 | 2025-04-12 | generated | 0.90 | 0.43 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152830 | TECHNICAL SPECIFICATION - POWER & CONTROL & F/O CABLE | TECHNICAL SPECIFICATION | POWER & CONTROL & F/O CABLE |  |  |  | Technical Specification for POWER & CONTROL & F/O CABLE |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | cable¦power |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7686 | 0.6973 | 0.6973 | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 1 | 1 | 35.0262 | 0.6846 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152840 | TECHNICAL SPECIFICATION - CABLING ACCESSORIES | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 15 | 9 | 8.6256 | 0.5057 | 0.0278 | 0.0209 | hybrid | structured_no_system |  | procurement |  | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-152850 | POWER CABLE SCHEDULE | SCHEDULE | POWER CABLE |  |  |  | Schedule for POWER CABLE |  | POWER CABLE SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | list | list | cable_schedule | cable_schedule | cable¦power |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 1 | 8 | 18.4512 | 0.4723 | 0.0311 | 0.0175 | hybrid | structured_no_system |  |  |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-152860 | CONTROL CABLE SCHEDULE | SCHEDULE | CONTROL CABLE |  |  |  | Schedule for CONTROL CABLE |  | CONTROL CABLE SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | list | list | cable_schedule | cable_schedule | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0CF6040W74A05.1 | (Electrical Cable) Cable Pulling for CCB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2008-05-10 | 2008-05-20 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 1 | 2 | 24.8983 | 0.5334 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-03-12 | 2025-04-11 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152870 | TECHNICAL SPECIFICATION - FIRE STOP MATERIAL | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | FA | 0EF4500W38A02 | (Fire Fighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 2 | 1 | 17.3684 | 0.5334 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-05-15 | 2024-06-14 | 2024-07-14 | 2024-07-29 | 2024-08-13 | 2024-08-28 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0CY-154001 | TECHNICAL SPECIFICATION - COMMUNICATION SYSTEM | TECHNICAL SPECIFICATION |  | COMMUNICATION SYSTEM |  |  | Technical Specification for COMMUNICATION SYSTEM |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | communication |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.7527 | 0.6925 | 0.4847 | FA | 0EF6040W74A01 | (Raceway) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System |  | 2007-07-02 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 3 | 11 | 9.4111 | 0.4157 | 0.0300 | 0.0225 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYA-154011 | CONFIGURATION DIAGRAM - OFFICE TELEPHONE & LAN SYSTEM | CONFIGURATION DIAGRAM |  |  |  |  | CONFIGURATION DIAGRAM |  | DCS - LAN Configuration Diagram | 1 | start+121D<=FA<=start+121D+2M | FA ∈ [start+121d, start+181d] | title | diagram | diagram | diagram | diagram |  | dcs | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6103 | 0.7081 | 0.7081 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | dcs | dcs | rule |  | activity_unscoped | true | 1 | 209 | 15.5211 | 0.4132 | 0.0201 | 0.0060 | hybrid | structured_phase_gap | dcs | system_design¦engineering | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYM-154013 | CONFIGURATION DIAGRAM - PUBLIC ADDRESS SYSTEM (SIREN SYSTEM) | CONFIGURATION DIAGRAM |  |  |  |  | CONFIGURATION DIAGRAM |  | HRSG - System Configuration Diagram | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | title | diagram | diagram | diagram | diagram |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.5000 | 0.6750 | 0.6750 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match |  | hrsg | hrsg | rule | hrsg | match | false | 1 | 2 | 12.2016 | 0.4149 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0CY-154021 | TYPICAL INSTALLATION DRAWING - COMMUNICATION SYSTEM | TYPICAL INSTALLATION DRAWING |  | COMMUNICATION SYSTEM |  |  | TYPICAL INSTALLATION DRAWING for COMMUNICATION SYSTEM |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | communication |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8205 | 0.9461 | 0.6623 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | 970 | 39 | 1.3501 | 0.4580 | 0.0111 | 0.0062 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154031 | COMMUNICATION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  | COMMUNICATION | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8491 | 0.9547 | 0.6683 | FA | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 6 | 2 | 18.3850 | 0.6302 | 0.0313 | 0.0188 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154032 | COMMUNICATION LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING |  | COMMUNICATION | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Layout Drawing for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8346 | 0.9504 | 0.6653 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 4 | 1 | 8.7678 | 0.5914 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154033 | COMMUNICATION LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING |  | COMMUNICATION | GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building |  | Layout Drawing for GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8277 | 0.9483 | 0.6638 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 6 | 2 | 7.6178 | 0.5655 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154034 | COMMUNICATION LAYOUT DRAWING - ST #1 LEB | LAYOUT DRAWING |  | COMMUNICATION | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | Layout Drawing for ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6094 | 0.6028 | 0.6028 | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 3 | 38 | 4.3991 | 0.3722 | 0.0261 | 0.0261 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154035 | COMMUNICATION LAYOUT DRAWING - ST #2 LEB | LAYOUT DRAWING | ST #2 ¦ Steam Turbine #2 | COMMUNICATION | LEB ¦ Local Electrical Building |  | Layout Drawing for LEB ¦ Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8435 | 0.9530 | 0.6671 | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 1 | 7 | 19.3008 | 0.5660 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154036 | COMMUNICATION LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING | ST ¦ Steam Turbine | COMMUNICATION | ST BUILDING ¦ Steam Turbine BUILDING |  | Layout Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6639 | 0.6192 | 0.6192 | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 3 | 7 | 13.5371 | 0.5821 | 0.0308 | 0.0308 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154037 | COMMUNICATION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | LAYOUT DRAWING |  | COMMUNICATION | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7389 | 0.8050 | 0.8050 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 4 | 1 | 10.8160 | 0.5267 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154038 | COMMUNICATION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | LAYOUT DRAWING |  | COMMUNICATION | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7931 | 0.9379 | 0.6566 | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 6 | 2 | 15.1429 | 0.5983 | 0.0313 | 0.0188 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154039 | COMMUNICATION LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | COMMUNICATION | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8361 | 0.9508 | 0.6656 | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 10 | 8 | 4.2752 | 0.4907 | 0.0290 | 0.0174 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154040 | COMMUNICATION LAYOUT DRAWING – MAIN GATE & PLANT ACCESS GATE HOUSE | LAYOUT DRAWING |  | COMMUNICATION | MAIN GATE & PLANT ACCESS GATE HOUSE |  | Layout Drawing for MAIN GATE & PLANT ACCESS GATE HOUSE |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | access¦gate¦house¦main¦plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7788 | 0.9337 | 0.6536 | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 1 | 26.3714 | 0.5709 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154041 | COMMUNICATION LAYOUT DRAWING - SUPPORT BUILDING | LAYOUT DRAWING |  | COMMUNICATION | SUPPORT BUILDING |  | Layout Drawing for SUPPORT BUILDING |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8587 | 0.9576 | 0.6703 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 23 | 24.0608 | 0.4679 | 0.0282 | 0.0169 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154042 | COMMUNICATION LAYOUT DRAWING - X-RAY SEARCHING ROOM | LAYOUT DRAWING |  | COMMUNICATION | X-RAY SEARCHING ROOM |  | Layout Drawing for X-RAY SEARCHING ROOM |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7759 | 0.9328 | 0.6529 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 96 | 24.0608 | 0.3633 | 0.0225 | 0.0101 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154044 | COMMUNICATION LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | LAYOUT DRAWING |  | COMMUNICATION | FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building |  | Layout Drawing for FIRE BRIGADE & AUX. LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | aux¦auxiliary¦brigade¦electrical¦fire¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7598 | 0.9279 | 0.6495 | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 5 | 1 |  | 0.4469 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154045 | COMMUNICATION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | COMMUNICATION | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for WORKSHOP & STORAGE BUILDING |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8191 | 0.9457 | 0.6620 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 34 | 1 | 9.7017 | 0.5535 | 0.0270 | 0.0203 | hybrid | structured_no_system |  | civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154049 | COMMUNICATION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | LAYOUT DRAWING |  | COMMUNICATION | FIRE WATER PUMP HOUSE |  | Layout Drawing for FIRE WATER PUMP HOUSE |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7991 | 0.9397 | 0.6578 | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 1 | 2 | 13.5235 | 0.5220 | 0.0325 | 0.0244 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154051 | COMMUNICATION LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | COMMUNICATION | WATER TREATMENT BUILDING |  | Layout Drawing for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6911 | 0.6740 | 0.6740 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 8 | 1 | 12.7557 | 0.5940 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154052 | COMMUNICATION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | LAYOUT DRAWING |  | COMMUNICATION | CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Layout Drawing for CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate¦cpp¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8097 | 0.9429 | 0.6600 | FA | 1EF3020W16A09 | (COND Flash Box) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-01-02 | 2008-03-31 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 4 | 3 |  | 0.3785 | 0.0315 | 0.0315 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-10-04 | 2024-11-03 | 2024-12-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154053 | COMMUNICATION LAYOUT DRAWING – PIPE RACK | LAYOUT DRAWING |  | COMMUNICATION | PIPE RACK |  | Layout Drawing for PIPE RACK |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8414 | 0.9524 | 0.6667 | FA | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 15 | 3 | 16.5373 | 0.6441 | 0.0292 | 0.0219 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0ASS-155001 | RELAY SETTING CALCULATION OF 380kV SYNCHRONIZING SYSTEM | CALCULATION |  | SYNCHRONIZING SYSTEM |  |  | Calculation sheet for SYNCHRONIZING SYSTEM | Chemical Dosing System | Calculation Sheet | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | synchronizing |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6051 | 0.6015 | 0.6015 | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | 6 | 4 | 1.2375 | 0.3663 | 0.0308 | 0.0308 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155011 | RELAY SETTING CALCULATION FOR GTG1 & GTG2 CABLE PROTECTION | CALCULATION | GTG1 & GTG2 |  |  |  | Calculation sheet for GTG1 & GTG2 | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation | gtg1¦gtg2 |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5442 | 0.5133 | 0.5133 | FA | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | civil_design | civil_design | match |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | 2487 | 6 |  | 0.5601 | 0.0155 | 0.0117 | hybrid | structured_no_system |  | civil_design |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155012 | RELAY SETTING CALCULATION FOR GTG #3, 4, 5 CABLE PROTECTION | CALCULATION | GTG #3, 4, 5 ¦ Gas Turbine Generator #3, 4, 5 |  |  |  | Calculation sheet for GTG #3, 4, 5 ¦ Gas Turbine Generator #3, 4, 5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6365 | 0.6576 | 0.6576 | FI | 3EF1210W20A09 | (GTG Common BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-08-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 11 | 24 | 12.7953 | 0.5520 | 0.0260 | 0.0260 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155013 | RELAY SETTING CALCULATION FOR STG #1, 2 CABLE PROTECTION | CALCULATION | STG #1, 2 ¦ Steam Turbine Generator #1, 2 |  |  |  | Calculation sheet for STG #1, 2 ¦ Steam Turbine Generator #1, 2 |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5381 | 0.5814 | 0.5814 | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | false | 1 | 4 | 21.7225 | 0.5728 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155014 | RELAY SETTING CALCULATION FOR 13.8kV CABLE PROTECTION – COGEN TO ESF | CALCULATION |  |  |  |  | Calculation sheet | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6392 | 0.5418 | 0.5418 | FA | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 77 | 15 | 8.4510 | 0.4746 | 0.0206 | 0.0155 | hybrid | structured_no_system |  | civil_design |  | 2024-08-16 | 2024-09-15 | 2024-10-15 | 2024-10-30 | 2024-11-14 | 2024-11-29 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0ZEN-161001 | DESIGN CRITERIA FOR GENERAL I&C SYSTEM | DESIGN CRITERIA |  | GENERAL I&C SYSTEM ¦ GENERAL Instrumentation and Control SYSTEM |  |  | DESIGN CRITERIA for GENERAL I&C SYSTEM ¦ GENERAL Instrumentation and Control SYSTEM | Intake Screening System | Design Criteria | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | criteria | criteria | design_criteria | design_criteria | andc¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5466 | 0.5840 | 0.5840 | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | [5 empty] | query_unscoped | true | 1 | 1 | 78.6113 | 0.6682 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | design_criteria¦system_design¦civil_design |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0ZEN-161011 | MASTER CLOCK CONCEPT DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | MASTER CONTROL DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6714 | 0.6681 | 0.4677 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | 15 | 57 | 9.8679 | 0.3012 | 0.0219 | 0.0123 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161021 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM – SYMBOL & LEGEND | DIAGRAM |  |  |  |  | Diagram |  | Plant start-up & ShutdoWn Sequence Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8459 | 0.9538 | 0.6676 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 15 | 3 | 10.0270 | 0.5373 | 0.0292 | 0.0164 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161022 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR START - UP | DIAGRAM |  |  |  |  | Diagram |  | Plant start-up & ShutdoWn Sequence Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8887 | 0.9666 | 0.6766 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 86 | 14 | 10.0270 | 0.4841 | 0.0204 | 0.0115 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161025 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR SHUTDOWN | DIAGRAM |  |  |  |  | Diagram |  | Plant start-up & ShutdoWn Sequence Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8662 | 0.9599 | 0.6719 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 28 | 12 | 10.0270 | 0.4794 | 0.0253 | 0.0142 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0ZEN-161031 | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | DIAGRAM |  | PLANT CONTROL SYSTEM |  |  | Diagram for PLANT CONTROL SYSTEM |  | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  |  |  |  | compressed_air | query_unscoped | false | 11 | 5 | 11.2184 | 0.5440 | 0.0295 | 0.0221 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJA-161041 | PLANT MASTER CONTROL DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | Plant Master Control Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8924 | 0.9677 | 0.6774 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | 15 | 16 | 9.8681 | 0.4877 | 0.0265 | 0.0149 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF01-P0BYA-161051 | PLANT PROTECTION & INTERLOCK DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | PLANT PROTECTION & INTERLOCK DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9992 | 0.9998 | 0.6998 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible |  |  |  |  | wts | query_unscoped | false | 10 | 46 | 10.1912 | 0.4608 | 0.0237 | 0.0133 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0CBA-161101 | DCS I/O DATABASE | DATABASE | DCS ¦ Distributed Control System |  |  |  | DATABASE for DCS ¦ Distributed Control System | Cooling ToWer | COOLING TOWER_Input/Output database (I/O Database) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | data | data | data | data | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.2000 | 0.5945 | 0.3184 | 0.3184 | FI | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | false | 2 | 1 | 42.5556 | 0.7593 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0CRV-161102 | DCS - LAN CONFIGURATION DIAGRAM | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | DCS - LAN Configuration Diagram | 1 | start+121D<=FA<=start+121D+2M | FA ∈ [start+121d, start+181d] | title | diagram | diagram | diagram | diagram | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.9764 | 0.9929 | 0.9929 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs | dcs | dcs | query |  | activity_unscoped | true | 20 | 29 | 13.1789 | 0.4869 | 0.0237 | 0.0142 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-07-14 | 2024-08-13 | 2024-09-12 | 2024-09-27 | 2024-10-12 | 2024-10-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161103 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HARDWARE | FUNCTIONAL DESIGN SPECIFICATION | DCS ¦ Distributed Control System |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for DCS ¦ Distributed Control System |  | DCS - Functional Design Specification for SoftWare | 1 | start+107D<=FA<=start+107D+2M | FA ∈ [start+107d, start+167d] | rule_query | specification | specification | specification | specification | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.8333 | 0.8030 | 0.8242 | 0.8242 | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs | dcs | dcs | query | dcs | match | false | 2 | 1 | 43.7468 | 0.7030 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161104 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR SOFTWARE | FUNCTIONAL DESIGN SPECIFICATION | DCS ¦ Distributed Control System |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for DCS ¦ Distributed Control System |  | DCS - Functional Design Specification for SoftWare | 1 | start+107D<=FA<=start+107D+2M | FA ∈ [start+107d, start+167d] | rule_query | specification | specification | specification | specification | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.8333 | 0.8030 | 0.8242 | 0.8242 | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs | dcs | dcs | query | dcs | match | false | 2 | 1 | 43.7468 | 0.7187 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161105 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HMI GRAPHIC | FUNCTIONAL DESIGN SPECIFICATION | DCS ¦ Distributed Control System |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for DCS ¦ Distributed Control System |  | DCS - Functional Design Specification for SoftWare | 1 | start+107D<=FA<=start+107D+2M | FA ∈ [start+107d, start+167d] | rule_query | specification | specification | specification | specification | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.8333 | 0.8030 | 0.8242 | 0.8242 | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs | dcs | dcs | query | dcs | match | false | 2 | 1 | 43.7468 | 0.7045 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0CUQ-161111 | DCS POWER DISTRIBUTION CONCEPT DIAGRAM | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | PoWer Distribution Concept Diagram | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | diagram | diagram | power_distribution_diagram | power_distribution_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7536 | 0.9261 | 0.9261 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | 20 | 42 | 13.1790 | 0.5105 | 0.0223 | 0.0100 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.35 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CUQ-161112 | DCS - POWER DISTRIBUTION DRAWING | DRAWING | DCS ¦ Distributed Control System |  |  |  | DRAWING for DCS ¦ Distributed Control System |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7029 | 0.7359 | 0.7359 | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | 477 | 51 | 4.1968 | 0.5247 | 0.0109 | 0.0049 | hybrid | structured_phase_gap | dcs | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CRN-161113 | DCS - IO & MODULE ALLOCATION | ALLOCATION | DCS ¦ Distributed Control System |  |  |  | ALLOCATION for DCS ¦ Distributed Control System | [5 empty] | rule_query | other | other | allocation | distributed_control_system | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.6915 | 0.9075 | 0.6352 |  | 0CF7000W86A04 | (DCS) Installation for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-02 | 2008-06-16 |  | installation | query_unknown | dcs |  | dcs | query | dcs | match | false | 4 | 2 | 33.2253 | 0.6350 | 0.0318 | 0.0238 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0CRN-161114 | DCS - INTERNAL CABLE CONNECTION DIAGRAM | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System | FireFighting | Cable Connection Diagram | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | title | diagram | diagram | diagram | diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6613 | 0.7234 | 0.7234 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | 27 | 25 | 13.1789 | 0.5050 | 0.0233 | 0.0105 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-08-02 | 2024-08-30 | 2024-09-27 | 2024-09-20 | 2024-10-18 | 2024-11-15 | generated | 0.90 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0CRN-161115 | DCS - CABLE LIST | LIST | DCS ¦ Distributed Control System |  |  |  | LIST for DCS ¦ Distributed Control System | [5 empty] | rule_query | other | other | list | dcs_cable_list | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6686 | 0.6673 | 0.6673 |  | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | false | 4 | 4 | 33.2253 | 0.5858 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | dcs | procurement | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0CRN-161116 | DCS - HMI GRAPHIC DISPLAY DIAGRAM | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | HMI GRAPHIC DISPLAY DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8742 | 0.9623 | 0.6736 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | 19 | 14 | 10.8582 | 0.4829 | 0.0262 | 0.0118 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0CRN-161117 | 3RD PARTY DATA - LINK INTERFACE SIGNAL DATABASE | DATABASE |  |  |  |  | DATABASE |  | LINK INTERFACE SIGNAL DATABASE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8030 | 0.9409 | 0.6586 | FA | 0SF6500W62A01 | (Power Receiving) Interface signal Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-08-01 | 2008-08-02 |  | commissioning | query_unknown |  |  |  |  | electrical | query_unscoped | false | 1 | 1 | 24.5916 | 0.4312 | 0.0328 | 0.0184 | hybrid | structured_no_system |  |  |  | 2025-03-20 | 2025-04-04 | 2025-04-19 | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0CUQ-161118 | I&C GROUNDING CONCEPT DIAGRAM | DIAGRAM |  | I&C ¦ Instrumentation and Control |  |  | Diagram for I&C ¦ Instrumentation and Control |  | I&C GROUNDING CONCEPT DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | andc¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0EF5560W32A04 | (M&E WORKSHOP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 | 2008-04-09 | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 13 | 342 | 21.0627 | 0.4360 | 0.0162 | 0.0121 | hybrid | structured_phase_gap | electrical | system_design¦engineering |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 | 0.51 | needs_review | activity_phase_status=compatible;activity_scope_source=rule;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CUQ-161119 | DCS - GROUNDING DRAWING | DRAWING | DCS ¦ Distributed Control System | GROUNDING |  |  | DRAWING for DCS ¦ Distributed Control System |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7029 | 0.7359 | 0.7359 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible | dcs¦electrical |  | dcs¦electrical | query | electrical | discipline_only | false | 7 | 17 | 2.3516 | 0.4703 | 0.0279 | 0.0105 | hybrid | structured_preferred | dcs¦electrical | system_design¦civil_design | 10 | 2025-04-18 | 2025-05-18 | 2025-06-17 | 2025-07-02 | 2025-07-17 | 2025-08-01 | generated | 0.90 | 0.27 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161121 | DCS - PERFORMANCE MONITORING SYSTEM |  | DCS ¦ Distributed Control System | PERFORMANCE MONITORING SYSTEM |  |  | for DCS ¦ Distributed Control System | [5 empty] | rule_query | other | other | dcs_performance_monitoring_system | distributed_control_system | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8299 | 0.9490 | 0.6643 |  | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 |  | procurement | query_unknown | dcs |  | dcs | query | dcs | match | false | 3 | 1 | 34.2190 | 0.6618 | 0.0323 | 0.0242 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161122 | DCS - PLANT INFORMATION HISTORIAN |  | DCS ¦ Distributed Control System | PLANT INFORMATION HISTORIAN |  |  | for Distributed Control System |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.2500 | 0.3363 | 0.2759 | 0.2759 | FA | 0CF7000W86A04 | (DCS) Installation for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-02 | 2008-06-16 |  | installation | query_unknown | dcs |  | dcs | query | dcs | match | false | 4 | 1 | 33.2257 | 0.6789 | 0.0320 | 0.0240 | hybrid | structured_no_phase | dcs | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161123 | DCS - FIELD INSTRUMENT MONITORING SYSTEM |  | DCS ¦ Distributed Control System | FIELD INSTRUMENT MONITORING SYSTEM |  |  | for DCS ¦ Distributed Control System | [5 empty] | rule_query | other | other | dcs_field_instrument_monitoring_system | distributed_control_system | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8299 | 0.9490 | 0.6643 |  | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 |  |  | query_unknown | dcs |  | dcs | query | dcs | match | false | 1 | 3 | 51.4287 | 0.6828 | 0.0323 | 0.0242 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161132 | DCS - TECHNICAL SPECIFICATION FOR TIME SYNCHRONIZATION | TECHNICAL SPECIFICATION | DCS ¦ Distributed Control System |  |  |  | Technical Specification for DCS ¦ Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5061 | 0.5018 | 0.5018 | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | false | 1 | 1 | 44.2556 | 0.6699 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161133 | DCS - TECHNICAL SPECIFICATION FOR EMERGENCY PUSH BUTTON | TECHNICAL SPECIFICATION | DCS ¦ Distributed Control System |  |  |  | Technical Specification for DCS ¦ Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5061 | 0.5018 | 0.5018 | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | false | 2 | 1 | 43.7468 | 0.6627 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161134 | TECHNICAL SPECIFICATION & DATA SHEET FOR SETTLEMENT SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | SETTLEMENT SYSTEM |  |  | TECHNICAL SPECIFICATION & DATA SHEET for SETTLEMENT SYSTEM |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | settlement |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.5774 | 0.7332 | 0.7332 | FA | 1PF3030W68A04P | (EXP Head Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-30 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 35 | 10 | 11.4927 | 0.4759 | 0.0248 | 0.0186 | hybrid | structured_no_system |  | procurement |  | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161135 | DCS - TECHNICAL SPECIFICATION FOR LARGE SCREEN DISPLAY | TECHNICAL SPECIFICATION | DCS ¦ Distributed Control System |  |  |  | Technical Specification for DCS ¦ Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5061 | 0.5018 | 0.5018 | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | false | 1 | 1 | 44.2556 | 0.6979 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161141 | DCS - OUTLINE & DETAIL DRAWING FOR DCS SYSTEM CABINET | OUTLINE & DETAIL DRAWING | DCS ¦ Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for Provision Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.8571 | 0.8683 | 0.8605 | 0.8605 | FA | 3EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | design_drawing | system_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | 952 | 20 | 3.3747 | 0.5059 | 0.0135 | 0.0061 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161142 | DCS - OUTLINE & DETAIL DRAWING FOR LAN/SERVER CABINET | OUTLINE & DETAIL DRAWING | DCS ¦ Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for LAN/Server Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.9420 | 0.9826 | 0.9826 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | 506 | 18 | 4.1967 | 0.4971 | 0.0146 | 0.0066 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161143 | DCS - OUTLINE & DETAIL DRAWING FOR MARSHALLING CABINET | OUTLINE & DETAIL DRAWING | DCS ¦ Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for Relay Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.8571 | 0.8573 | 0.8572 | 0.8572 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | 506 | 18 | 4.1967 | 0.4928 | 0.0146 | 0.0066 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161146 | DCS - OUTLINE & DETAIL DRAWING FOR DCS CONSOLE & DESK | OUTLINE & DETAIL DRAWING | DCS ¦ Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for Provision Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.7143 | 0.8084 | 0.7425 | 0.7425 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | 506 | 18 | 4.1967 | 0.4991 | 0.0146 | 0.0066 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161147 | DCS - OUTLINE & DETAIL DRAWING FOR DCS POWER DISTRIBUTION CABINET | OUTLINE & DETAIL DRAWING | DCS ¦ Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for PoWer Distribution Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.9249 | 0.9775 | 0.9775 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | 506 | 22 | 4.1968 | 0.5073 | 0.0140 | 0.0063 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161148 | DCS - OUTLINE & DETAIL DRAWING FOR DCS GROUNDING BOX | OUTLINE & DETAIL DRAWING | DCS ¦ Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - GrounDing Detail DraWing | 1 | start+230D<=FA<=start+230D+2M | FA ∈ [start+230d, start+290d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.7817 | 0.9345 | 0.9345 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs¦electrical | dcs | query |  | activity_unscoped | true | 519 | 22 | 4.1967 | 0.5191 | 0.0139 | 0.0063 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-11-18 | 2024-12-18 | 2025-01-17 | 2025-02-01 | 2025-02-16 | 2025-03-03 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRT-161149 | DCS - TECHNICAL SPECIFICATION FOR FIELDBUS MOV | TECHNICAL SPECIFICATION | DCS ¦ Distributed Control System |  |  |  | Technical Specification for DCS ¦ Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5061 | 0.5018 | 0.5018 | FA | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | false | 3 | 1 | 40.9671 | 0.6657 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0CRU-161150 | INTEGRATED SAT(SITE ACCEPTANCE TEST) PROCEDURE FOR DCS | PROCEDURE | DCS ¦ Distributed Control System |  |  |  | PROCEDURE for DCS ¦ Distributed Control System |  | Site Acceptance Test Procedure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | test_procedure | test_procedure | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7121 | 0.9136 | 0.6395 | FA | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 | commissioning | commissioning | match | dcs |  | dcs | query | dcs¦electrical | match | false | 1 | 1 | 38.6599 | 0.7025 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dcs | commissioning |  | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-26 | 2025-06-25 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161201 | CONTROL LOGIC DIAGRAM - SYMBOL & LEGEND | CONTROL LOGIC DIAGRAM |  |  |  |  | Control Logic Diagram |  | ACC - Control Logic Diagram | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram |  | acc | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7929 | 0.7629 | 0.7629 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | 7 | 158 | 14.8839 | 0.4693 | 0.0195 | 0.0059 | hybrid | structured_phase_gap | acc | system_design¦engineering | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161202 | CONTROL LOGIC DIAGRAM - TYPICAL FUNCTION | CONTROL LOGIC DIAGRAM |  |  |  |  | Control Logic Diagram |  | ACC - Control Logic Diagram | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram |  | acc | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7929 | 0.7629 | 0.7629 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | 7 | 329 | 14.8839 | 0.4429 | 0.0175 | 0.0052 | hybrid | structured_phase_gap | acc | system_design¦engineering | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161203 | CONTROL LOGIC DIAGRAM FOR HP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | Control Logic Diagram for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6815 | 0.7294 | 0.7294 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 4 | 22.4640 | 0.6701 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | steam | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161204 | CONTROL LOGIC DIAGRAM FOR IP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | Control Logic Diagram for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6663 | 0.7249 | 0.7249 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 4 | 22.4640 | 0.6994 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | steam | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161205 | CONTROL LOGIC DIAGRAM FOR LP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | Control Logic Diagram for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6879 | 0.7314 | 0.7314 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 2 | 4 | 22.4640 | 0.6682 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | steam | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161206 | CONTROL LOGIC DIAGRAM FOR PROCESS STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | Control Logic Diagram for PROCESS STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7134 | 0.7390 | 0.7390 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 19.0793 | 0.6915 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161207 | CONTROL LOGIC DIAGRAM FOR STEAM DRAIN SYSTEM | CONTROL LOGIC DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | Control Logic Diagram for STEAM DRAIN SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7034 | 0.7360 | 0.7360 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 19.0793 | 0.6690 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161208 | CONTROL LOGIC DIAGRAM FOR CONDENSATE SYSTEM | CONTROL LOGIC DIAGRAM |  | CONDENSATE SYSTEM |  |  | Control Logic Diagram for CONDENSATE SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | condensate |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7134 | 0.7390 | 0.7390 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 4 | 25.2200 | 0.6791 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161209 | CONTROL LOGIC DIAGRAM FOR FEEDWATER SYSTEM | CONTROL LOGIC DIAGRAM |  | FEEDWATER SYSTEM |  |  | Control Logic Diagram for FEEDWATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7428 | 0.7478 | 0.7478 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | false | 1 | 1 | 12.9693 | 0.6778 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design¦engineering | 1 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161210 | CONTROL LOGIC DIAGRAM FOR CLOSED COOLING WATER SYSTEM | CONTROL LOGIC DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | Control Logic Diagram for CLOSED COOLING WATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6871 | 0.7311 | 0.7311 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 14.0432 | 0.4349 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161211 | CONTROL LOGIC DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | CONTROL LOGIC DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | Control Logic Diagram for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6377 | 0.7163 | 0.7163 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 26.0520 | 0.5846 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦engineering | 5 | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161212 | CONTROL LOGIC DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOGIC DIAGRAM |  | GT ROTOR COOLING AIR SYSTEM ¦ Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | Control Logic Diagram for GT ROTOR COOLING AIR SYSTEM ¦ Gas Turbine ROTOR COOLING AIR SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | air¦cooling¦gas¦gtg¦rotor¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6530 | 0.7209 | 0.7209 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 2 | 10.7030 | 0.5621 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161213 | CONTROL LOGIC DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | CONTROL LOGIC DIAGRAM |  | GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | Control Logic Diagram for GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | gas¦gtg¦heater¦performance¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6549 | 0.7215 | 0.7215 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 2 | 3.1086 | 0.5536 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161214 | CONTROL LOGIC DIAGRAM FOR POTABLE WATER SYSTEM | CONTROL LOGIC DIAGRAM |  | POTABLE WATER SYSTEM |  |  | Control Logic Diagram for POTABLE WATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7179 | 0.7404 | 0.7404 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 39.1365 | 0.6469 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161216 | CONTROL LOGIC DIAGRAM FOR COMPRESSED AIR SYSTEM | CONTROL LOGIC DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | Control Logic Diagram for COMPRESSED AIR SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6947 | 0.7334 | 0.7334 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 37.5953 | 0.6523 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161220 | CONTROL LOGIC DIAGRAM FOR ELECTRICAL SYSTEM | CONTROL LOGIC DIAGRAM |  | ELECTRICAL SYSTEM |  |  | Control Logic Diagram for ELECTRICAL SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | electrical |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7332 | 0.7450 | 0.7450 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | 13 | 472 | 16.1582 | 0.4562 | 0.0156 | 0.0093 | hybrid | structured_phase_gap | electrical | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161221 | CONTROL LOGIC DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | CONTROL LOGIC DIAGRAM |  | OTHER CONTROL SYSTEM |  |  | Control Logic Diagram for OTHER CONTROL SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | other |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7151 | 0.7395 | 0.7395 | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 164 | 34 | 13.0638 | 0.4711 | 0.0151 | 0.0113 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161222 | CONTROL LOGIC DIAGRAM FOR MISCELLANEOUS SYSTEM | CONTROL LOGIC DIAGRAM |  | MISCELLANEOUS SYSTEM |  |  | Control Logic Diagram for MISCELLANEOUS SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | miscellaneous |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7013 | 0.7354 | 0.7354 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | 6 | 35 | 16.1582 | 0.4950 | 0.0257 | 0.0154 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161301 | CONTROL LOOP DIAGRAM - SYMBOL & LEGEND | CONTROL LOOP DIAGRAM |  |  |  |  | Control Loop Diagram | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8073 | 0.7672 | 0.7672 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | 31 | 17 | 12.3101 | 0.5665 | 0.0240 | 0.0180 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161302 | CONTROL LOOP DIAGRAM - TYPICAL FUNCTION | CONTROL LOOP DIAGRAM |  |  |  |  | Control Loop Diagram | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8073 | 0.7672 | 0.7672 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | 14 | 60 | 14.8839 | 0.5353 | 0.0218 | 0.0131 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161303 | CONTROL LOOP DIAGRAM FOR HP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | Control Loop Diagram for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7157 | 0.7397 | 0.7397 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 22.4640 | 0.6813 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161304 | CONTROL LOOP DIAGRAM FOR IP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | Control Loop Diagram for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7054 | 0.7366 | 0.7366 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 22.4640 | 0.7065 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161305 | CONTROL LOOP DIAGRAM FOR LP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | Control Loop Diagram for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7034 | 0.7360 | 0.7360 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 22.4640 | 0.6783 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161306 | CONTROL LOOP DIAGRAM FOR PROCESS STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | Control Loop Diagram for PROCESS STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7494 | 0.7498 | 0.7498 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 19.0793 | 0.7071 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161307 | CONTROL LOOP DIAGRAM FOR STEAM DRAIN SYSTEM | CONTROL LOOP DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | Control Loop Diagram for STEAM DRAIN SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7397 | 0.7469 | 0.7469 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | false | 1 | 1 | 19.0793 | 0.6900 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161308 | CONTROL LOOP DIAGRAM FOR CONDENSATE SYSTEM | CONTROL LOOP DIAGRAM |  | CONDENSATE SYSTEM |  |  | Control Loop Diagram for CONDENSATE SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | condensate |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7417 | 0.7475 | 0.7475 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 4 | 25.2200 | 0.7033 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161309 | CONTROL LOOP DIAGRAM FOR FEEDWATER SYSTEM | CONTROL LOOP DIAGRAM |  | FEEDWATER SYSTEM |  |  | Control Loop Diagram for FEEDWATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7870 | 0.7611 | 0.7611 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | false | 1 | 1 | 12.9693 | 0.6897 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design¦engineering | 1 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161310 | CONTROL LOOP DIAGRAM FOR CLOSED COOLING WATER SYSTEM | CONTROL LOOP DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | Control Loop Diagram for CLOSED COOLING WATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7406 | 0.7472 | 0.7472 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | false | 1 | 2 | 14.0432 | 0.4106 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161311 | CONTROL LOOP DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | CONTROL LOOP DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | Control Loop Diagram for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6727 | 0.7268 | 0.7268 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 26.0520 | 0.6034 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦engineering | 5 | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161312 | CONTROL LOOP DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOOP DIAGRAM | GT ¦ Gas Turbine | GT ROTOR COOLING AIR SYSTEM ¦ Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | Control Loop Diagram for GT ROTOR COOLING AIR SYSTEM ¦ Gas Turbine ROTOR COOLING AIR SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | air¦cooling¦gas¦gtg¦rotor¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6859 | 0.7308 | 0.7308 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 2 | 13.8116 | 0.5887 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161313 | CONTROL LOOP DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | CONTROL LOOP DIAGRAM | GT ¦ Gas Turbine | GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | Control Loop Diagram for GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | gas¦gtg¦heater¦performance¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6820 | 0.7296 | 0.7296 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | false | 1 | 3 | 6.2173 | 0.5911 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161314 | CONTROL LOOP DIAGRAM FOR POTABLE WATER SYSTEM | CONTROL LOOP DIAGRAM |  | POTABLE WATER SYSTEM |  |  | Control Loop Diagram for POTABLE WATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7422 | 0.7477 | 0.7477 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 39.1365 | 0.6649 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161316 | CONTROL LOOP DIAGRAM FOR COMPRESSED AIR SYSTEM | CONTROL LOOP DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | Control Loop Diagram for COMPRESSED AIR SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7151 | 0.7395 | 0.7395 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | false | 1 | 1 | 37.5953 | 0.6591 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161320 | CONTROL LOOP DIAGRAM FOR ELECTRICAL SYSTEM | CONTROL LOOP DIAGRAM |  | ELECTRICAL SYSTEM |  |  | Control Loop Diagram for ELECTRICAL SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | electrical |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7590 | 0.7527 | 0.7527 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | 20 | 195 | 16.1582 | 0.4937 | 0.0164 | 0.0099 | hybrid | structured_phase_gap | electrical | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161321 | CONTROL LOOP DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | CONTROL LOOP DIAGRAM |  | INTERFACE WITH OTHER CONTROL SYSTEM |  |  | Control Loop Diagram for INTERFACE WITH OTHER CONTROL SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | interface¦other¦with |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7362 | 0.7459 | 0.7459 | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 180 | 35 | 13.0638 | 0.4988 | 0.0147 | 0.0110 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161322 | CONTROL LOOP DIAGRAM FOR MISCELLANEOUS SYSTEM | CONTROL LOOP DIAGRAM |  | MISCELLANEOUS SYSTEM |  |  | Control Loop Diagram for MISCELLANEOUS SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | miscellaneous |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7309 | 0.7443 | 0.7443 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | 13 | 9 | 16.1582 | 0.5505 | 0.0282 | 0.0169 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161401 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL CONTROL ROOM | LAYOUT DRAWING |  |  | CENTRAL CONTROL ROOM |  | Layout Drawing for CENTRAL CONTROL ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9107 | 0.9732 | 0.6812 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 14 | 1 | 17.3786 | 0.6476 | 0.0299 | 0.0135 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161402 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL ELECTRONIC ROOM | LAYOUT DRAWING |  |  | CENTRAL ELECTRONIC ROOM |  | Layout Drawing for CENTRAL ELECTRONIC ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | central¦electronic¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8956 | 0.9687 | 0.6781 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 14 | 1 | 13.1819 | 0.6025 | 0.0299 | 0.0135 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161403 | I&C EQUIPMENT LAYOUT DRAWING FOR COMPUTER ROOM | LAYOUT DRAWING |  |  | COMPUTER ROOM |  | Layout Drawing for COMPUTER ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | computer¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8878 | 0.9663 | 0.6764 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 33 | 15 | 9.0197 | 0.5041 | 0.0241 | 0.0135 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161404 | I&C EQUIPMENT LAYOUT DRAWING FOR IT & COMMUNICATION ROOM | LAYOUT DRAWING |  |  | IT & COMMUNICATION ROOM |  | Layout Drawing for IT & COMMUNICATION ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | communication¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8450 | 0.9535 | 0.6674 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 33 | 12 | 9.0197 | 0.4973 | 0.0246 | 0.0139 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161405 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #1,2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator |  | LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦electronic¦gtg¦leb¦local¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8258 | 0.9477 | 0.6634 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 1 | 1 | 20.8947 | 0.7711 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161406 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #3,4,5 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | GTG ¦ Gas Turbine Generator |  | LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦electronic¦gtg¦leb¦local¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8203 | 0.9461 | 0.6623 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | false | 4 | 1 | 19.7447 | 0.7558 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161407 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #1 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | ST ¦ Steam Turbine |  | LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦electronic¦leb¦local¦room¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8425 | 0.9528 | 0.6669 | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 7 | 12 | 13.5371 | 0.5777 | 0.0288 | 0.0288 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161408 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | ST ¦ Steam Turbine |  | LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for LEB LOCAL ELECTRICAL & ELECTRONIC ROOM ¦ Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦electronic¦leb¦local¦room¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8353 | 0.9506 | 0.6654 | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | false | 4 | 12 | 15.4583 | 0.5809 | 0.0295 | 0.0295 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161409 | I&C EQUIPMENT LAYOUT DRAWING FOR FGS ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM | LAYOUT DRAWING |  | I&C ¦ Instrumentation and Control | FGS ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM ¦ Fuel Gas System ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM |  | Layout Drawing for FGS ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM ¦ Fuel Gas System ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦electronic¦fgp¦fgs¦fuel¦gas¦local¦room | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.6875 | 0.7896 | 0.7896 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 12 | 1 | 15.2475 | 0.5764 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0ZEN-163101 | FIELD INSTRUMENT LIST FOR BOP | LIST |  |  |  |  | Instrument List |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | bop |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.7667 | FI | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 6 | 1 | 16.5654 | 0.6274 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | procurement |  | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163102 | TECHNICAL SPECIFICATION & DATA SHEET FOR LOCAL INSTRUMENT - BOP | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | bop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7990 | 0.7997 | 0.7997 | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 2 | 19.9360 | 0.5740 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163103 | TECHNICAL SPECIFICATION & DATA SHEET FOR PROCESS TRANSMITTER - BOP | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | bop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7990 | 0.7997 | 0.7997 | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 3 | 19.9360 | 0.5353 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163104 | TECHNICAL SPECIFICATION & DATA SHEET FOR FLOW ELEMENT - BOP | TECHNICAL SPECIFICATION & DATA SHEET | FLOW ELEMENT |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET for FLOW ELEMENT | FloW element | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | bop¦element¦flow |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.8883 | 0.8665 | 0.8665 | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 1 | 19.9360 | 0.5682 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163201 | TECHNICAL SPECIFICATION & DATA SHEET FOR CONTROL VALVE - BOP | TECHNICAL SPECIFICATION & DATA SHEET | CONTROL VALVE |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET for CONTROL VALVE | CONTROL VALVE | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | bop¦valve |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9180 | 0.8754 | 0.8754 | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 1 | 1 | 37.1676 | 0.6664 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0EKU-163202 | TECHNICAL SPECIFICATION & DATA SHEET FOR GAS METERING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | GAS METERING SYSTEM |  |  | TECHNICAL SPECIFICATION & DATA SHEET for GAS METERING SYSTEM |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | gas¦metering |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6096 | 0.7429 | 0.7429 | FA | 1PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | 2007-07-03 | 2008-04-01 | procurement | procurement | match | electrical |  | electrical | query | electrical¦fgp | match | false | 6 | 2 | 24.2092 | 0.6748 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-07-17 | 2024-08-16 | 2024-09-15 | 2024-09-30 | 2024-10-15 | 2024-10-30 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0UCL-163203 | TECHNICAL SPECIFICATION & DATA SHEET FOR STEAM/WATER METERING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7990 | 0.7997 | 0.7997 | FA | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 1 | 9 | 16.1671 | 0.5627 | 0.0309 | 0.0232 | hybrid | structured_no_system |  | procurement |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163204 | TECHNICAL SPECIFICATION & DATA SHEET FOR WEATHER STATION | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7990 | 0.7997 | 0.7997 | FA | 1PF3030W42A02P | (Temp. Cooling Tower) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower | 2008-02-21 | 2008-06-19 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 68 | 4 | 10.2297 | 0.4553 | 0.0234 | 0.0176 | hybrid | structured_no_system |  | procurement |  | 2025-03-21 | 2025-04-20 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-07-04 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163301 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM - INDEX | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7351 | 0.9205 | 0.9205 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 20 | 19 | 13.1789 | 0.5220 | 0.0252 | 0.0151 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163302 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR INCOMER | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6412 | 0.8924 | 0.8924 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 18 | 204 | 15.5211 | 0.4752 | 0.0166 | 0.0100 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163303 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR MOTOR FEEDER | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6380 | 0.8914 | 0.8914 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 21 | 223 | 15.5211 | 0.4620 | 0.0159 | 0.0095 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163304 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR TR FEEDER | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6538 | 0.8962 | 0.8962 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 18 | 240 | 15.5211 | 0.4649 | 0.0162 | 0.0097 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163305 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR BUS TIE | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6286 | 0.8886 | 0.8886 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 18 | 174 | 15.5211 | 0.4766 | 0.0171 | 0.0103 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163306 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR UNIT/COMMON TIE | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6319 | 0.8896 | 0.8896 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 18 | 111 | 16.5642 | 0.4984 | 0.0187 | 0.0112 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163307 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PT PANEL | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7320 | 0.9196 | 0.9196 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 23 | 45 | 13.1789 | 0.5181 | 0.0216 | 0.0129 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163308 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR INCOMER | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6576 | 0.8973 | 0.8973 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 27 | 191 | 13.1789 | 0.4736 | 0.0155 | 0.0093 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163309 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (ACB) | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6219 | 0.8866 | 0.8866 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 56 | 67 | 12.0861 | 0.4826 | 0.0165 | 0.0099 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163310 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (MCCB) | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6211 | 0.8863 | 0.8863 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 20 | 292 | 15.5211 | 0.4462 | 0.0153 | 0.0092 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163311 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (ACB) | DIAGRAM | DCS ¦ Distributed Control System |  |  |  | Diagram for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6322 | 0.8897 | 0.8897 | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 56 | 87 | 12.0861 | 0.4834 | 0.0154 | 0.0093 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163312 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (MCCB EHS) | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6188 | 0.8856 | 0.8856 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 31 | 187 | 13.1789 | 0.4485 | 0.0150 | 0.0090 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163313 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR BUS TIE | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6465 | 0.8940 | 0.8940 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 27 | 238 | 13.1789 | 0.4583 | 0.0148 | 0.0089 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163314 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG INPUT | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6810 | 0.9043 | 0.9043 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 22 | 20 | 13.1789 | 0.4959 | 0.0247 | 0.0148 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163315 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG OUTPUT | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6774 | 0.9032 | 0.9032 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 22 | 23 | 13.1789 | 0.4894 | 0.0242 | 0.0145 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163316 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY INPUT | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6673 | 0.9002 | 0.9002 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 22 | 42 | 13.1789 | 0.4678 | 0.0220 | 0.0132 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163317 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY OUTPUT | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6762 | 0.9029 | 0.9029 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 22 | 34 | 13.1789 | 0.4659 | 0.0228 | 0.0137 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163318 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC CONTROL VALVE - MODULATING | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6075 | 0.8823 | 0.8823 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 22 | 36 | 15.5211 | 0.4873 | 0.0226 | 0.0136 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163319 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC SHUT - OFF VALVE (SOLENOID VALVE) | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6059 | 0.8818 | 0.8818 | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 60 | 16 | 13.1789 | 0.4938 | 0.0215 | 0.0129 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163320 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - INTERNAL MCC | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6317 | 0.8895 | 0.8895 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 22 | 53 | 15.5211 | 0.4662 | 0.0210 | 0.0126 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163321 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - FIELDBUS | WIRING DIAGRAM | DCS ¦ Distributed Control System |  |  |  | WIRING DIAGRAM for DCS ¦ Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5959 | 0.8788 | 0.8788 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | 21 | 64 | 15.5211 | 0.4430 | 0.0204 | 0.0122 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163331 | TECHNICAL SPECIFICATION & DATA SHEET FOR VIBRATION MONITORING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | VIBRATION MONITORING SYSTEM |  |  | TECHNICAL SPECIFICATION & DATA SHEET for VIBRATION MONITORING SYSTEM |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | monitoring¦vibration |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6318 | 0.7495 | 0.7495 | FA | 1PF1260W86A02P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-05-01 | procurement | procurement | match |  |  |  |  | gtg | query_unscoped | false | 1 | 2 | 42.8426 | 0.5959 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0SAY-163401 | CONTROL SYSTEM CONFIGURATION DIAGRAM FOR HVAC | DIAGRAM |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | Diagram for HVAC ¦ Heating Ventilating and Air Conditioning |  | CONTROL SYSTEM CONFIGURATION DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8398 | 0.9519 | 0.6664 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 50.3584 | 0.6506 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SAY-163402 | I/O LIST FOR HVAC | I/O LIST ¦ Input / Output LIST |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | I/O List for HVAC ¦ Heating Ventilating and Air Conditioning | Air Compressor | HardWire Input /Output List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | io_list | io_list | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6023 | 0.4140 | 0.4140 | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac | compressed_air | hvac | query | fire_fighting¦hvac | match | false | 2 | 1 | 52.8561 | 0.6538 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hvac | procurement |  | 2024-11-07 | 2024-12-07 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-02-20 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SAY-163403 | TECHNICAL SPECIFICATION & DATA SHEET FOR FIELD INSTRUMENT - HVAC | TECHNICAL SPECIFICATION & DATA SHEET |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | TECHNICAL SPECIFICATION & DATA SHEET for HVAC ¦ Heating Ventilating and Air Conditioning |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6439 | 0.7532 | 0.7532 | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 48.2795 | 0.6735 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | procurement |  | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0SAY-163404 | INSTRUMENT INSTALLATION DETAIL DRAWING FOR HVAC | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | DRAWING for HVAC ¦ Heating Ventilating and Air Conditioning | FinFan Cooler | Instrument Installation Detail DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7100 | 0.6797 | 0.6797 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 2 | 2 | 42.4165 | 0.6465 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦civil_design |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0SAY-163405 | CONTROL LOGIC & LOOP DIAGRAM FOR HVAC | DIAGRAM |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | Diagram for HVAC ¦ Heating Ventilating and Air Conditioning |  | Logic & Loop Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6791 | 0.9037 | 0.9037 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 2 | 51.8364 | 0.6541 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0SAY-163406 | I&C CABLE SCHEDULE FOR HVAC | SCHEDULE |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | Schedule for HVAC ¦ Heating Ventilating and Air Conditioning | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.8159 | 0.6648 | 0.6648 | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 48.2798 | 0.6441 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | procurement |  | 2024-11-13 | 2024-12-13 | 2025-01-12 | 2025-01-27 | 2025-02-11 | 2025-02-26 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0SAY-163407 | I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HVAC | WIRING DIAGRAM |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | WIRING DIAGRAM for HVAC ¦ Heating Ventilating and Air Conditioning |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6844 | 0.9053 | 0.9053 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 2 | 51.8364 | 0.6247 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163408 | HVAC I&C CABLE RACEWAY DRAWING FOR CCB | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | CCB ¦ Central Control Building |  | DRAWING for HVAC ¦ Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦ccr¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8124 | 0.9437 | 0.6606 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 3 | 24.3915 | 0.5115 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163409 | HVAC I&C CABLE RACEWAY DRAWING FOR STEAM TURBINE BUILDING | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | STEAM TURBINE BUILDING |  | DRAWING for STEAM TURBINE BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7660 | 0.9298 | 0.6509 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | hvac¦stg |  | hvac¦stg | query | stg | match | false | 13 | 4 | 8.1992 | 0.5409 | 0.0293 | 0.0293 | hybrid | structured_preferred | hvac¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163411 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #1 | DRAWING | STG ¦ Steam Turbine Generator | HVAC ¦ Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7540 | 0.9262 | 0.6483 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦hvac¦stg |  | electrical¦hvac¦stg | query | stg | match | false | 10 | 2 | 20.2913 | 0.6440 | 0.0304 | 0.0304 | hybrid | structured_preferred | electrical¦hvac¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163412 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #2 | DRAWING | STG ¦ Steam Turbine Generator | HVAC ¦ Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7436 | 0.9231 | 0.6462 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦hvac¦stg |  | electrical¦hvac¦stg | query | stg | match | false | 10 | 1 | 20.8330 | 0.6591 | 0.0307 | 0.0307 | hybrid | structured_preferred | electrical¦hvac¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163413 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #1,2 | DRAWING | GTG ¦ Gas Turbine Generator | HVAC ¦ Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7481 | 0.9244 | 0.6471 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | gtg | match | false | 9 | 8 | 15.0882 | 0.6797 | 0.0292 | 0.0292 | hybrid | structured_preferred | electrical¦gtg¦hvac | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163414 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #3, 4, 5 | DRAWING | GTG ¦ Gas Turbine Generator | HVAC ¦ Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7462 | 0.9239 | 0.6467 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | gtg | match | false | 15 | 9 | 13.9382 | 0.6537 | 0.0278 | 0.0278 | hybrid | structured_preferred | electrical¦gtg¦hvac | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163415 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING |  | DRAWING for MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | administration¦facilities¦main¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6958 | 0.9088 | 0.6361 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 3 | 32.2913 | 0.5835 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163416 | HVAC I&C CABLE RACEWAY DRAWING FOR SECURITY BUILDING | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | SECURITY BUILDING |  | DRAWING for SECURITY BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7731 | 0.9319 | 0.6524 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 3 | 28.3414 | 0.5764 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163417 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE BRIGADE & AUX LEB | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | FIRE BRIGADE & AUX LEB ¦ FIRE BRIGADE & Auxiliary Local Electrical Building |  | DRAWING for HVAC ¦ Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦conditioning¦electrical¦heating¦hvac¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7490 | 0.9247 | 0.6473 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | false | 1 | 3 | 31.2744 | 0.6252 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163418 | HVAC I&C CABLE RACEWAY DRAWING FOR MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE |  | DRAWING for MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | maintenance¦warehouse¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7351 | 0.9205 | 0.6444 | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 2 | 2 | 30.7059 | 0.5622 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163419 | HVAC I&C CABLE RACEWAY DRAWING FOR FGS ELECTRICAL BUILDING | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | DRAWING for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6494 | 0.6615 | 0.6615 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp¦hvac | fgp | electrical¦fgp¦hvac | query | fgp | match | false | 26 | 6 | 10.8160 | 0.5456 | 0.0268 | 0.0268 | hybrid | structured_preferred | electrical¦fgp¦hvac | civil_design | 10 | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163420 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE WATER PUMP HOUSE | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | FIRE WATER PUMP HOUSE |  | DRAWING for HVAC ¦ Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦conditioning¦heating¦hvac¦pump¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7756 | 0.9327 | 0.6529 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting¦hvac |  | fire_fighting¦hvac | query | fire_fighting¦hvac | match | false | 5 | 1 | 44.9371 | 0.6565 | 0.0318 | 0.0238 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hvac | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163421 | HVAC I&C CABLE RACEWAY DRAWING FOR WATER TREATMENT BUILDING /W MAIN LABORATORY | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | WATER TREATMENT BUILDING /W MAIN LABORATORY |  | DRAWING for WATER TREATMENT BUILDING /W MAIN LABORATORY | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | laboratory¦main¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6516 | 0.5955 | 0.5955 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | hvac¦lab¦wts | wts | hvac¦lab¦wts | query | wts | match | false | 16 | 2 | 15.4574 | 0.5789 | 0.0293 | 0.0293 | hybrid | structured_preferred | hvac¦lab¦wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163422 | HVAC I&C CABLE RACEWAY DRAWING FOR CPP BUILDING | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | DRAWING for CPP BUILDING ¦ CONDENSATE POLISING PLANT BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | condensate¦cpp¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7571 | 0.9271 | 0.6490 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate¦hvac |  | condensate¦hvac | query | acc¦condensate | match | false | 9 | 11 | 2.8059 | 0.4796 | 0.0286 | 0.0286 | hybrid | structured_preferred | condensate¦hvac | civil_design | 10 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SAY-163423 | CONTROL PANEL OUTLINE & DETAIL DRAWING FOR HVAC | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | DRAWING for HVAC ¦ Heating Ventilating and Air Conditioning |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4965 | 0.6156 | 0.6156 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 2 | 2 | 42.4165 | 0.6331 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦civil_design |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0SAY-163424 | HMI GRAPHIC DISPLAY DIAGRAM FOR HVAC | DIAGRAM | HMI ¦ Human Machine Interface | HVAC ¦ Heating Ventilating and Air Conditioning |  |  | Diagram for HVAC ¦ Heating Ventilating and Air Conditioning |  | HMI GRAPHIC DISPLAY DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8910 | 0.9673 | 0.6771 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 49.6914 | 0.6057 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SAY-163425 | TECHNICAL SPECIFICATION - HVAC CONTROL SYSTEM | TECHNICAL SPECIFICATION |  | HVAC CONTROL SYSTEM ¦ Heating Ventilating and Air Conditioning CONTROL SYSTEM |  |  | Technical Specification for HVAC CONTROL SYSTEM ¦ Heating Ventilating and Air Conditioning CONTROL SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4718 | 0.6082 | 0.6082 | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 1 | 1 | 50.0339 | 0.6992 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | procurement |  | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163426 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN GATE HOUSE AREA | DRAWING |  | HVAC ¦ Heating Ventilating and Air Conditioning | MAIN GATE HOUSE AREA |  | DRAWING for HVAC ¦ Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦conditioning¦heating¦hvac¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7806 | 0.9342 | 0.6539 | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | false | 5 | 2 | 40.2715 | 0.5862 | 0.0315 | 0.0236 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0ZEN-165001 | DESIGN CRITERIA FOR I&C CABLE | DESIGN CRITERIA | I&C CABLE ¦ Instrumentation and Control CABLE |  |  |  | DESIGN CRITERIA for I&C CABLE ¦ Instrumentation and Control CABLE |  | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | rule_query | criteria | criteria | design_criteria | design_criteria | andc¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.4892 | 0.5468 | 0.5468 | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | [5 empty] | query_unscoped | true | 1 | 1 | 62.3058 | 0.5750 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | design_criteria¦system_design¦civil_design |  | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL02-P0ZEN-165011 | I&C CABLE PRINCIPLE DIAGRAM | PRINCIPLE DIAGRAM | I&C CABLE ¦ Instrumentation and Control CABLE |  |  |  | PRINCIPLE DIAGRAM for I&C CABLE ¦ Instrumentation and Control CABLE |  | Cable Principle Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | andc¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7299 | 0.9190 | 0.6433 | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 13 | 108 | 25.3530 | 0.4437 | 0.0197 | 0.0111 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165301 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONTROL VALVE | DRAWINGS | CONTROL VALVE |  |  |  | DRAWINGS for CONTROL VALVE |  | TYPICAL I&C CABLE INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | valve |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8678 | 0.8203 | 0.5742 | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 338 | 158 | 8.3933 | 0.4368 | 0.0071 | 0.0032 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165302 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - MOV | DRAWINGS | MOV ¦ Motor Operated Valve |  |  |  | DRAWINGS for MOV ¦ Motor Operated Valve |  | TYPICAL I&C CABLE INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | motor¦mov¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8233 | 0.8070 | 0.5649 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 35 | 249 | 8.4510 | 0.4109 | 0.0138 | 0.0077 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165303 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - INSTRUMENT RACK AND JUNCTION BOX | INSTALLATION DRAWINGS |  | I&C Cable ¦ Instrumentation and Control Cable |  |  | INSTALLATION DRAWINGS for I&C Cable ¦ Instrumentation and Control Cable |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | andc¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6134 | 0.6507 | 0.6507 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 109 | 431 | 25.3530 | 0.4213 | 0.0080 | 0.0045 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165304 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - FIELD INSTRUMENT | INSTALLATION DRAWINGS |  | I&C Cable ¦ Instrumentation and Control Cable |  |  | INSTALLATION DRAWINGS for I&C Cable ¦ Instrumentation and Control Cable |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | andc¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6760 | 0.6695 | 0.6695 | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 25 | 521 | 25.3530 | 0.4233 | 0.0135 | 0.0076 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165305 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONDUIT SUPPORT | INSTALLATION DRAWINGS |  | I&C Cable ¦ Instrumentation and Control Cable |  |  | INSTALLATION DRAWINGS for I&C Cable ¦ Instrumentation and Control Cable |  | TYPICAL I&C CABLE INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | andc¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8739 | 0.8222 | 0.5755 | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 20 | 78 | 25.3530 | 0.4721 | 0.0197 | 0.0111 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165311 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - GENERAL NOTE | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 1 | 1 | 17.9223 | 0.4779 | 0.0328 | 0.0246 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165312 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - SYMBOL & LEGEND | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 7 | 15.6273 | 0.4026 | 0.0308 | 0.0231 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165313 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - MATERIAL LISTS | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 5 | 15.6273 | 0.4122 | 0.0313 | 0.0234 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165314 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR FLOW TRANSMITTER | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 7 | 19.1989 | 0.4142 | 0.0308 | 0.0231 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165315 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR LEVEL TRANSMITTER | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 2 | 4 | 19.1989 | 0.3931 | 0.0318 | 0.0238 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165316 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE TRANSMITTER | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 6 | 19.1989 | 0.3892 | 0.0310 | 0.0233 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165317 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR DIFF. PRESSURE TRANSMITTER | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 4 | 19.1989 | 0.3834 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165318 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE GAUGE | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 4 | 19.1989 | 0.4049 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165319 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE TRANSMITTER (RTD/TC) | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 4 | 19.1989 | 0.3866 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165320 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE GAUGE | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 4 | 19.1989 | 0.3889 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165321 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEST WELL | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 1CF3035W62A02 | (SWS) Hydro Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Service Water System (BOP) | 2008-12-17 | 2009-01-01 | commissioning | commissioning | match | bop |  | bop | query | bop¦service_water | match | false | 1 | 4 | 26.8166 | 0.5294 | 0.0320 | 0.0320 | hybrid | structured_preferred | bop | commissioning | 10 | 2025-08-05 | 2025-08-20 | 2025-09-04 | 2025-09-19 | 2025-10-19 | 2025-11-18 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165322 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PNEUMATIC CONTROL VALVES | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 3 | 4 | 19.1989 | 0.3905 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165323 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR STANCHION & RACK | DETAIL DRAWINGS | BOP ¦ Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | FA | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 1 | 7 | 27.6923 | 0.4807 | 0.0313 | 0.0235 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165501 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CENTRAL CONTROL BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | BOP ¦ Balance of Plant |  | CENTRAL CONTROL BUILDING |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for CENTRAL CONTROL BUILDING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦ccr¦central | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9183 | 0.9755 | 0.6828 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match | bop | bop | bop | query | bop | match | false | 3 | 7 | 19.1989 | 0.4215 | 0.0308 | 0.0308 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165502 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #1,2 LEB | LAYOUT AND INSTRUMENT LOCATION DRAWING | BOP ¦ Balance of Plant |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦gas¦generator¦gtg¦leb¦local¦turbine | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9031 | 0.9709 | 0.6796 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | bop¦electrical¦gtg | bop | bop¦electrical¦gtg | query | gtg | match | false | 17 | 1 | 8.7680 | 0.6236 | 0.0294 | 0.0294 | hybrid | structured_preferred | bop¦electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165503 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #3,4,5 LEB | LAYOUT AND INSTRUMENT LOCATION DRAWING | BOP ¦ Balance of Plant |  | GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for GTG #3,4,5 LEB ¦ Gas Turbine Generator #3,4,5 Local Electrical Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦gas¦generator¦gtg¦leb¦local¦turbine | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9017 | 0.9705 | 0.6794 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | bop¦electrical¦gtg | bop | bop¦electrical¦gtg | query | gtg | match | false | 25 | 1 | 7.6180 | 0.5988 | 0.0282 | 0.0282 | hybrid | structured_preferred | bop¦electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165504 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #1 LEB | LAYOUT AND INSTRUMENT LOCATION DRAWING | BOP ¦ Balance of Plant |  | ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for ST #1 LEB ¦ Steam Turbine #1 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6232 | 0.6069 | 0.6069 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match | bop¦electrical¦stg | stg | bop¦electrical¦stg | query | bop | match | false | 6 | 18 | 19.5392 | 0.4738 | 0.0280 | 0.0280 | hybrid | structured_preferred | bop¦electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165505 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #2 LEB | DRAWING |  |  | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | DRAWING for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.4000 | 0.5731 | 0.4519 | 0.4519 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 44 | 4 | 1.7769 | 0.4933 | 0.0252 | 0.0252 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165506 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST BUILDING | DRAWING |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | DRAWING for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.4000 | 0.6131 | 0.4639 | 0.4639 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 12 | 1 | 3.9005 | 0.5349 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.85 | usable | rule_score_medium | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165507 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FGS ELECTRICAL BUILDING | DRAWING |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | DRAWING for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6837 | 0.6718 | 0.6718 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 4 | 1 | 10.8160 | 0.5706 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165508 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ADMINISTRATION & SOCIAL BUILDING | DRAWING |  |  | ADMINISTRATION & SOCIAL BUILDING |  | DRAWING for ADMINISTRATION & SOCIAL BUILDING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦bop¦social | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8912 | 0.9674 | 0.6772 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  | bop | bop | rule | bop | match | false | 3 | 7 | 7.4883 | 0.4186 | 0.0308 | 0.0308 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165509 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR SECURITY BUILDING | DRAWING |  |  | SECURITY BUILDING |  | DRAWING for SECURITY BUILDING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦security | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9168 | 0.9751 | 0.6825 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  | bop | bop | rule | bop | match | false | 3 | 7 | 7.4883 | 0.4203 | 0.0308 | 0.0308 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165510 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR MAIN GATE HOUSE AREA | DRAWING |  |  |  |  | DRAWING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9140 | 0.9742 | 0.6819 | FA | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible |  | bop | bop | rule | bop | match | false | 1 | 6 | 13.9396 | 0.4726 | 0.0315 | 0.0237 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 | 0.75 | usable | activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165514 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE BRIGADE | DRAWING |  |  | FIRE BRIGADE |  | DRAWING for FIRE BRIGADE |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦brigade¦fire | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9136 | 0.9741 | 0.6819 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  | bop | bop | rule | bop | match | false | 3 | 4 | 7.4883 | 0.4591 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.75 | usable | activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165515 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WORKSHOP & STORAGE BUILDING | DRAWING |  |  | WORKSHOP & STORAGE BUILDING |  | DRAWING for WORKSHOP & STORAGE BUILDING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦storage¦workshop | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9079 | 0.9724 | 0.6807 | FA | 3CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | civil_design | civil_design | match |  | bop | bop | rule | bop | match | false | 9 | 1 | 7.1888 | 0.4750 | 0.0309 | 0.0309 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165516 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR H2, CO2, N2 STORAGE SHELTER | DRAWING |  |  | H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | DRAWING for H2, CO2, N2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦carbon¦co2¦dioxide¦hydrogen¦nitrogen¦shelter¦storage | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8618 | 0.9585 | 0.6710 | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | h2¦n2 | bop | h2¦n2 | query | n2 | match | false | 1 | 5 | 13.1604 | 0.5453 | 0.0318 | 0.0318 | hybrid | structured_preferred | h2¦n2 | civil_design | 10 | 2024-07-21 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165517 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COMPRESSOR SHELTER | DRAWING | AIR COMPRESSOR |  |  |  | DRAWING for AIR COMPRESSOR |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦bop¦compressor | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8739 | 0.9622 | 0.6735 | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | bop | compressed_air | query | compressed_air | match | false | 4 | 4 | 19.9309 | 0.5956 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165518 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR DEAERATOR SUPPORT STRUCTURE | DRAWING |  |  |  |  | DRAWING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8844 | 0.9653 | 0.6757 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  | bop | bop | rule | bop | match | false | 5 | 1 | 7.4883 | 0.5056 | 0.0318 | 0.0318 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165519 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER (CPP) | DRAWING | Fin Fan Cooler |  | Fire Pump House |  | DRAWING for Fire Pump House | CPP FIN FAN COOLER | CPP FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦fire¦house¦pump |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6428 | 0.7762 | 0.7762 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw | ccw | ccw | query | ccw¦gtg | match | false | 3 | 1 | 38.5912 | 0.6189 | 0.0323 | 0.0242 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165520 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | DRAWING | Tank |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | DRAWING for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | wts | scoped | match | match | match | passed |  | 0.5000 | 0.5778 | 0.5233 | 0.5233 | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 4 | 2 | 34.5566 | 0.6028 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165521 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WATER TREATMENT BUILDING | DRAWING |  |  | WATER TREATMENT BUILDING |  | DRAWING for WATER TREATMENT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.6342 | 0.5403 | 0.5403 | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | false | 4 | 3 | 13.6713 | 0.5590 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165522 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CPP & CPP REGENERATION BUILDING | DRAWING |  |  | CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | DRAWING for CPP & CPP REGENERATION BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦condensate¦cpp¦plant¦polising¦regeneration | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9000 | 0.9700 | 0.6790 | FA | 1EF3020W16A09 | (COND Flash Box) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-01-02 | 2008-03-31 | civil_design | civil_design | match | condensate | bop | condensate | query | condensate | match | false | 4 | 3 |  | 0.4300 | 0.0315 | 0.0315 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-10-04 | 2024-11-03 | 2024-12-03 | generated | 0.30 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165523 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | DRAWING | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator | CHEMICAL DOSING |  |  | DRAWING for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦generator¦heat¦hrsg¦recovery¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7419 | 0.5726 | 0.5726 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | hrsg¦stg¦wts | hrsg | hrsg¦stg¦wts | query | gsut_uat¦stg | match | false | 13 | 11 | 24.7338 | 0.6213 | 0.0278 | 0.0278 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2025-08-10 | 2025-09-09 | 2025-10-09 | 2025-10-24 | 2025-11-08 | 2025-11-23 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165524 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR HRSG | DRAWING | HRSG ¦ Heat Recovery Steam Generator | CHEMICAL DOSING |  |  | DRAWING for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7419 | 0.5726 | 0.5726 | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg¦wts | hrsg | hrsg¦wts | query | hrsg | match | false | 25 | 3 | 16.0954 | 0.6444 | 0.0276 | 0.0276 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165525 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7636 | 0.9291 | 0.6504 | FA | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 3 | 10 | 13.0300 | 0.6910 | 0.0302 | 0.0226 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165526 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7613 | 0.9284 | 0.6499 | FA | 2EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | false | 9 | 2 | 12.3630 | 0.7120 | 0.0306 | 0.0230 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165527 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7585 | 0.9275 | 0.6493 | FA | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 1 | 11 | 15.2464 | 0.6861 | 0.0305 | 0.0229 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165528 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7536 | 0.9261 | 0.6482 | FA | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 4 | 12 | 13.0300 | 0.6872 | 0.0295 | 0.0221 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165529 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | LAYOUT | GTG ¦ Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7580 | 0.9274 | 0.6492 | FA | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | false | 4 | 10 | 13.0300 | 0.6812 | 0.0299 | 0.0224 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165531 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM - GENERAL INFORMATION | WIRING DIAGRAM | BOP ¦ Balance of Plant | I&C Cable ¦ Instrumentation and Control Cable |  |  | WIRING DIAGRAM for I&C Cable ¦ Instrumentation and Control Cable |  | Cable Interconnection Wiring Diagram | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | andc¦bop¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6810 | 0.7293 | 0.7293 | FI | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bop |  | bop | query |  | activity_unscoped | true | 19 | 37 | 25.3730 | 0.5528 | 0.0230 | 0.0138 | hybrid | structured_phase_gap | bop | system_design¦engineering |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165532 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HP STEAM SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | WIRING DIAGRAM for HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6361 | 0.8908 | 0.8908 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | false | 2 | 1 | 22.4642 | 0.6185 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165533 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR IP STEAM SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | WIRING DIAGRAM for IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6449 | 0.8935 | 0.8935 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | false | 1 | 1 | 22.4642 | 0.6467 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165534 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR LP STEAM SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | WIRING DIAGRAM for LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6307 | 0.8892 | 0.8892 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | false | 2 | 1 | 22.4642 | 0.6332 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165535 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR PROCESS STEAM SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | PROCESS STEAM SYSTEM |  |  | WIRING DIAGRAM for PROCESS STEAM SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6221 | 0.8866 | 0.8866 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | false | 1 | 1 | 19.0796 | 0.6201 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165536 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR STEAM DRAIN SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | STEAM DRAIN SYSTEM |  |  | WIRING DIAGRAM for STEAM DRAIN SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦drain¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6204 | 0.8861 | 0.8861 | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | false | 2 | 1 | 19.0796 | 0.6190 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165537 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CONDENSATE SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | CONDENSATE SYSTEM |  |  | WIRING DIAGRAM for CONDENSATE SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6348 | 0.8904 | 0.8904 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | bop¦condensate |  | bop¦condensate | query | condensate | match | false | 1 | 1 | 25.2202 | 0.6665 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦condensate | system_design¦engineering | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165538 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FEEDWATER SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | FEEDWATER SYSTEM |  |  | WIRING DIAGRAM for FEEDWATER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦feedwater |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6389 | 0.8917 | 0.8917 | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦feedwater |  | bop¦feedwater | query | feedwater | match | false | 1 | 1 | 12.9695 | 0.6679 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦feedwater | system_design¦engineering | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165539 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CLOSED COOLING WATER SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | CLOSED COOLING WATER SYSTEM |  |  | WIRING DIAGRAM for CLOSED COOLING WATER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6257 | 0.8877 | 0.8877 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bop¦ccw |  | bop¦ccw | query | ccw¦gtg | match | false | 1 | 2 | 14.0434 | 0.4426 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦ccw | system_design¦engineering | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165540 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | WIRING DIAGRAM for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6080 | 0.8824 | 0.8824 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | bop¦wts |  | bop¦wts | query | wts | match | false | 1 | 1 | 26.0522 | 0.6112 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | system_design¦engineering | 5 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165541 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | GT ROTOR COOLING AIR SYSTEM ¦ Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | WIRING DIAGRAM for GT ROTOR COOLING AIR SYSTEM ¦ Gas Turbine ROTOR COOLING AIR SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦bop¦cooling¦gas¦gtg¦rotor¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6156 | 0.8847 | 0.8847 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bop¦gtg |  | bop¦gtg | query | ccw¦gtg | match | false | 1 | 3 | 10.7032 | 0.5397 | 0.0323 | 0.0323 | hybrid | structured_preferred | bop¦gtg | system_design¦engineering | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165542 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | WIRING DIAGRAM for GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦gas¦gtg¦heater¦performance¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6078 | 0.8823 | 0.8823 | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bop¦gtg |  | bop¦gtg | query | ccw¦gtg | match | false | 2 | 1 | 3.1088 | 0.5307 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦gtg | system_design¦engineering | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165543 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | WIRING DIAGRAM for POTABLE WATER STORAGE AND SUPPLY SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦potable¦storage¦supply¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6098 | 0.8829 | 0.8829 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | bop¦wts |  | bop¦wts | query | wts | match | false | 1 | 1 | 48.9317 | 0.6654 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | system_design¦engineering | 5 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165544 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | POTABLE WATER DISTRIBUTION SYSTEM |  |  | WIRING DIAGRAM for POTABLE WATER DISTRIBUTION SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦distribution¦potable¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6210 | 0.8863 | 0.8863 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | bop¦wts |  | bop¦wts | query | wts | match | false | 1 | 1 | 39.1368 | 0.6593 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | system_design¦engineering | 5 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165545 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR COMPRESSED AIR SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | COMPRESSED AIR SYSTEM |  |  | WIRING DIAGRAM for COMPRESSED AIR SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦bop¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6367 | 0.8910 | 0.8910 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | bop¦compressed_air |  | bop¦compressed_air | query | compressed_air | match | false | 1 | 1 | 37.5955 | 0.6533 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦compressed_air | system_design¦engineering | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165546 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FUEL GAS SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | FUEL GAS SYSTEM |  |  | WIRING DIAGRAM for FUEL GAS SYSTEM | Fuel Gas System | Interconnection Wiring Diagram | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | bop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8270 | 0.8314 | 0.8314 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | bop¦fgp | fgp | bop¦fgp | query | fgp | match | false | 1 | 1 | 22.7652 | 0.6510 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦fgp | system_design¦engineering | 2 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165547 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR ELECTRICAL SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | ELECTRICAL SYSTEM |  |  | WIRING DIAGRAM for ELECTRICAL SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6879 | 0.9064 | 0.9064 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bop¦electrical |  | bop¦electrical | query |  | activity_unscoped | true | 173 | 95 | 13.8749 | 0.5436 | 0.0107 | 0.0064 | hybrid | structured_phase_gap | bop¦electrical | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165548 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | WIRING DIAGRAM | BOP ¦ Balance of Plant | INTERFACE WITH OTHER CONTROL SYSTEM |  |  | WIRING DIAGRAM for INTERFACE WITH OTHER CONTROL SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦interface¦other¦with |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6667 | 0.9000 | 0.9000 | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | bop |  | bop | query |  | activity_unscoped | true | 203 | 72 | 13.0172 | 0.5364 | 0.0114 | 0.0068 | hybrid | structured_phase_gap | bop | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165551 | BOP - I&C CABLE SCHEDULE - GENERAL INFORMATION | SCHEDULE | BOP ¦ Balance of Plant |  |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6334 | 0.6567 | 0.6567 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop |  | bop | query | bop | match | false | 1 | 1 | 24.9354 | 0.6879 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165552 | BOP - I&C CABLE SCHEDULE FOR HP STEAM SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | HP STEAM SYSTEM ¦ HIGH PRESSURE STEAM SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5764 | 0.6396 | 0.6396 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | false | 1 | 1 | 28.5688 | 0.6675 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165553 | BOP - I&C CABLE SCHEDULE FOR IP STEAM SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | IP STEAM SYSTEM ¦ Intermediate Pressure STEAM SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5848 | 0.6421 | 0.6421 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | false | 1 | 1 | 28.5688 | 0.6883 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165554 | BOP - I&C CABLE SCHEDULE FOR LP STEAM SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | LP STEAM SYSTEM ¦ LOW PRESSURE STEAM SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5868 | 0.6427 | 0.6427 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | false | 1 | 1 | 28.5688 | 0.6761 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165555 | BOP - I&C CABLE SCHEDULE FOR PROCESS STEAM SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | PROCESS STEAM SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5751 | 0.6392 | 0.6392 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | false | 1 | 1 | 28.5688 | 0.6910 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165556 | BOP - I&C CABLE SCHEDULE FOR STEAM DRAIN SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | STEAM DRAIN SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5714 | 0.6381 | 0.6381 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | false | 1 | 1 | 28.5688 | 0.6685 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165557 | BOP - I&C CABLE SCHEDULE FOR CONDENSATE SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | CONDENSATE SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7541 | 0.6462 | 0.6462 | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦condensate |  | bop¦condensate | query | bop | match | false | 1 | 1 | 28.5688 | 0.6728 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦condensate | procurement |  | 2024-12-13 | 2025-01-12 | 2025-02-11 | 2025-02-26 | 2025-03-13 | 2025-03-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165558 | BOP - I&C CABLE SCHEDULE FOR FEEDWATER SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | FEEDWATER SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5763 | 0.6396 | 0.6396 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦feedwater |  | bop¦feedwater | query | bop | match | false | 1 | 7 | 28.5688 | 0.6636 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | bop¦feedwater | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165559 | BOP - I&C CABLE SCHEDULE FOR CLOSED COOLING WATER SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | CLOSED COOLING WATER SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7679 | 0.6504 | 0.6504 | FA | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | procurement | procurement | match | bop¦ccw |  | bop¦ccw | query | ccw | match | false | 1 | 1 | 36.0068 | 0.6546 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦ccw | procurement |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165560 | BOP - I&C CABLE SCHEDULE FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5595 | 0.6345 | 0.6345 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦wts |  | bop¦wts | query | bop | match | false | 1 | 1 | 28.5688 | 0.6656 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | procurement | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165561 | BOP - I&C CABLE SCHEDULE FOR GT ROTOR COOLING AIR SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | GT ROTOR COOLING AIR SYSTEM ¦ Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦gtg¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7627 | 0.6488 | 0.6488 | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦gtg |  | bop¦gtg | query | bop | match | false | 10 | 2 | 28.5688 | 0.6361 | 0.0304 | 0.0304 | hybrid | structured_cell_found_text_preferred | bop¦gtg | procurement |  | 2024-12-13 | 2025-01-12 | 2025-02-11 | 2025-02-26 | 2025-03-13 | 2025-03-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165562 | BOP - I&C CABLE SCHEDULE FOR GT PERFORMANCE HEATER SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | GT PERFORMANCE HEATER SYSTEM ¦ Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦gtg¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7178 | 0.6353 | 0.6353 | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦gtg |  | bop¦gtg | query | bop | match | false | 7 | 1 | 28.5688 | 0.6349 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | bop¦gtg | procurement |  | 2024-12-13 | 2025-01-12 | 2025-02-11 | 2025-02-26 | 2025-03-13 | 2025-03-28 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165563 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | H2, CO2 Supply System | Cable schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5962 | 0.6455 | 0.6455 | FA | 0PF3035W42A06P | (PWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | bop¦wts | h2 | bop¦wts | query | wts | match | false | 1 | 1 | 37.7825 | 0.6812 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | procurement | 10 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165564 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER DISTRIBUTION SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | POTABLE WATER DISTRIBUTION SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5597 | 0.6346 | 0.6346 | SKIP | 0PF3035W42A06P | (PWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | bop¦wts |  | bop¦wts | query | wts | match | false | 1 | 1 | 32.8578 | 0.6607 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | procurement | 10 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165565 | BOP - I&C CABLE SCHEDULE FOR COMPRESSED AIR SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | COMPRESSED AIR SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5568 | 0.6337 | 0.6337 | SKIP | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | bop¦compressed_air |  | bop¦compressed_air | query | compressed_air | match | false | 4 | 5 | 31.8503 | 0.6653 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | bop¦compressed_air | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165566 | BOP - I&C CABLE SCHEDULE FOR FUEL GAS SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | FUEL GAS SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Fuel Gas System | Cable schedule & Sizing | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦fgp¦plant | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7085 | 0.7959 | 0.7959 | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦fgp | fgp | bop¦fgp | query | bop | match | false | 1 | 1 | 28.5688 | 0.6512 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦fgp | procurement |  | 2024-12-07 | 2025-01-18 | 2025-03-01 | 2025-02-08 | 2025-03-22 | 2025-05-03 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165567 | BOP - I&C CABLE SCHEDULE FOR ELECTRICAL SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | ELECTRICAL SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6342 | 0.6569 | 0.6569 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦electrical |  | bop¦electrical | query | bop | match | false | 1 | 1 | 28.5688 | 0.6672 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦electrical | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165568 | BOP - I&C CABLE SCHEDULE FOR INTERFACE WITH OTHER CONTROL SYSTEM | SCHEDULE | BOP ¦ Balance of Plant | OTHER CONTROL SYSTEM |  |  | Schedule for BOP ¦ Balance of Plant | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5931 | 0.6446 | 0.6446 | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop |  | bop | query | bop | match | false | 1 | 1 | 28.5688 | 0.6787 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop | procurement | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165571 | BOP EXPOSED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | EXPOSED CONDUIT LAYOUT | BOP ¦ Balance of Plant |  |  |  | EXPOSED CONDUIT LAYOUT for Tank |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8615 | 0.9584 | 0.6709 | FA | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 1 | 3 | 25.1061 | 0.5060 | 0.0323 | 0.0242 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165572 | BOP EXPOSED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | EXPOSED CONDUIT LAYOUT | BOP ¦ Balance of Plant |  |  |  | EXPOSED CONDUIT LAYOUT for Tank |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8615 | 0.9584 | 0.6709 | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | false | 2 | 1 | 25.1061 | 0.5098 | 0.0325 | 0.0244 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165573 | BOP EXPOSED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | LAYOUT | Tank |  |  |  | Layout Drawing for Tank |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7389 | 0.9217 | 0.6452 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | design_drawing | civil_design | compatible |  |  |  |  | condensate¦fgp | query_unscoped | false | 16 | 4 | 16.2248 | 0.5506 | 0.0288 | 0.0162 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | 2024-04-02 | 2024-05-02 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165575 | BOP EXPOSED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | LAYOUT | Fin Fan Cooler |  |  |  | Layout Drawing for Pump | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦pump |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7421 | 0.8060 | 0.8060 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw | ccw | ccw | query | ccw¦gtg | match | false | 3 | 1 | 43.4477 | 0.6302 | 0.0323 | 0.0242 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165576 | BOP EXPOSED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | LAYOUT | STG ¦ Steam Turbine Generator |  |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | stg | stg | stg | query | gsut_uat¦stg | match | false | 5 | 4 | 24.5739 | 0.6728 | 0.0310 | 0.0233 | hybrid | structured_cell_found_text_preferred | stg | system_design¦civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165577 | BOP EXPOSED CONDUIT LAYOUT FOR PIPE RACK AREA | LAYOUT |  |  | PIPE RACK |  | Layout Drawing for PIPE RACK |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7878 | 0.9363 | 0.6554 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 10 | 4 | 26.7413 | 0.6103 | 0.0299 | 0.0224 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165701 | TECHNICAL SPECIFICATION FOR I&C CABLE | TECHNICAL SPECIFICATION | I&C Cable ¦ Instrumentation and Control Cable |  |  |  | Technical Specification for I&C Cable ¦ Instrumentation and Control Cable |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | andc¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6792 | 0.6704 | 0.6704 | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 1 | 1 | 33.4427 | 0.6281 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165711 | TECHNICAL SPECIFICATION FOR JUNCTION BOX & RACK | TECHNICAL SPECIFICATION | Junction Box |  |  |  | Technical Specification for Junction Box | LOCAL BOX | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | box¦junction |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6596 | 0.4979 | 0.4979 | FA | 2PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-06-28 | 2008-02-01 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | 6 | 1 | 19.7891 | 0.5383 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | procurement |  | 2024-07-12 | 2024-08-11 | 2024-09-10 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165731 | TECHNICAL SPECIFICATION FOR INSTRUMENT INSTALLATION MATERIALS | TECHNICAL SPECIFICATION |  | INSTRUMENT INSTALLATION MATERIALS |  |  | Technical Specification for INSTRUMENT INSTALLATION MATERIALS | INSTRUMENT INSTALLATION MATERIA | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | installation¦instrument¦materials |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8404 | 0.6021 | 0.6021 | FA | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | 2 | 5 | 29.1037 | 0.5548 | 0.0315 | 0.0236 | hybrid | structured_no_system |  | procurement |  | 2024-06-13 | 2024-07-13 | 2024-08-12 | 2024-08-27 | 2024-09-11 | 2024-09-26 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-165900 | DESCRIPTION OF SETTLEMENT SYSTEM | DESCRIPTION |  | SETTLEMENT SYSTEM |  |  | DESCRIPTION for SETTLEMENT SYSTEM | [5 empty] | rule_query | other | description | description | system_description | settlement | gt¦gtg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.6667 | 0.4512 | 0.6020 | 0.6020 |  | 2CF3035W58A01 | (SWS) Piping Work(Block #2) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Service Water System (BOP) | 2008-10-17 | 2008-12-16 |  |  | query_unknown |  |  |  |  | bop¦service_water | query_unscoped | false | 13 | 72 | 6.1593 | 0.3252 | 0.0213 | 0.0120 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0ZEN-167001 | CYBER SECURITY PLAN | PLAN |  |  |  |  | Plan |  | CYBER SECURITY PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 2 | 15 | 24.0608 | 0.3306 | 0.0295 | 0.0133 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170101 | SOIL INVESTIGATION REPORT | REPORT |  |  |  |  | REPORT |  | SOIL INVESTIGATION REPORT | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | report | report | report | report |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 |  | civil_design | query_unknown |  |  |  |  | stg | query_unscoped | false | 5 | 9 | 8.3777 | 0.4075 | 0.0299 | 0.0168 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | 0.43 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170102 | TOPOGRAPHIC SURVEY REPORT | REPORT |  |  |  |  | REPORT |  | TOPOGRAPHIC SURVEY REPORT | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | report | report | report | report |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 30 | 1 |  | 0.4617 | 0.0275 | 0.0124 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-15 | 2024-04-30 | 2024-05-15 | generated | 0.90 | 0.35 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ZEN-170103 | PILE CAPACITY CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | PILE CAPACITY CALCULATION | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match |  |  |  |  | stg | query_unscoped | false | 1 | 12 | 11.0757 | 0.4423 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | civil_design |  | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ZEN-170104 | WORKING PILE DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | WORKING PILE DETAIL | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | design_drawing | civil_design | compatible |  |  |  |  | stg | query_unscoped | false | 3 | 5 | 11.0757 | 0.4827 | 0.0313 | 0.0176 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 0.43 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170105 | REPORT FOR PILE LOAD TEST OF BORED CAST - IN - PLACE PILE | REPORT |  |  |  |  | REPORT |  | REPORT FOR PILE LOAD TEST OF BORED CAST - IN - PLACE PILE | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | report | report | test_report | test_report |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 2CF3035W62A02.1 | (PWS) Hydro Test(Block #2) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Potable Water System (BOP) | 2009-01-03 | 2009-01-19 | commissioning | commissioning | match |  |  |  |  | bop¦wts | query_unscoped | false | 15 | 107 | 10.6956 | 0.3746 | 0.0193 | 0.0145 | hybrid | structured_no_system |  | commissioning |  | 2025-12-05 | 2026-01-04 | 2026-02-03 | 2026-02-18 | 2026-03-05 | 2026-03-20 | generated | 0.90 | 0.49 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171001 | GTG FOUNDATION - PILE CALCULATION SHEET | CALCULATION SHEET | GTG ¦ Gas Turbine Generator |  |  |  | CALCULATION SHEET for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6034 | 0.6477 | 0.6477 | FI | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 1 | 1 | 15.9929 | 0.7028 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171002 | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | GTG ¦ Gas Turbine Generator |  |  |  | General Arrangement Drawing for GTG ¦ Gas Turbine Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7068 | 0.9120 | 0.9120 | FA | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | false | 2 | 1 | 22.4323 | 0.7399 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171004 | GTG FOUNDATION - DESIGN REPORT | DESIGN REPORT | GTG ¦ Gas Turbine Generator |  |  |  | Design Report for GTG ¦ Gas Turbine Generator |  | GTG FOUNDATION - DESIGN REPORT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | report | report | design_report | design_report | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.7500 | 0.6326 | 0.7148 | 0.7148 | FA | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 1 | 5 | 15.6852 | 0.7059 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171005 | GT FDN GENERAL NOTES FORMWORK DWG | DWG ¦ Drawing | GT ¦ Gas Turbine |  |  |  | DWG ¦ Drawing for GT ¦ Gas Turbine |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.4000 | 0.6657 | 0.4797 | 0.4797 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 5 | 11.4109 | 0.6348 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-07-10 | 2024-08-09 | 2024-09-08 | 2024-09-23 | 2024-10-08 | 2024-10-23 | generated | 0.90 | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171006 | GT FDN TOP PLAN VIEW INSERT PLATE ARRANGEMENT AND DETAILS FORMWORK DWG, PART 1/6 | DWG ¦ Drawing | GT ¦ Gas Turbine |  |  |  | DWG ¦ Drawing for GT ¦ Gas Turbine |  | GT FDN TOP PLAN VIEW INSERT PLATE ARRANGEMENT AND DETAILS FORMWORK DWG, PART 1/6 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF1213W16A01.1 | (GT #12) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | 2007-03-01 | 2007-07-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 2 | 3 | 12.8321 | 0.6347 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171007 | GT FDN TOP PLAN VIEW ANCHOR BOLT ARRANGEMENT AND DETAILS FORMWORK DRAWING, PART 2/6 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT FDN TOP PLAN VIEW ANCHOR BOLT ARRANGEMENT AND DETAILS FORMWORK DRAWING, PART 2/6 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 2 | 13.1879 | 0.6668 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171008 | GT FDN TOP PLAN VIEW EXPANSION BOLT ARRGMNT AND DETAIL FORMWORK DWG, 3/6 | DWG ¦ Drawing | GT ¦ Gas Turbine |  |  |  | DWG ¦ Drawing for GT ¦ Gas Turbine |  | GT FDN TOP PLAN VIEW EXPANSION BOLT ARRGMNT AND DETAIL FORMWORK DWG, 3/6 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 2 | 11 | 13.2114 | 0.6216 | 0.0302 | 0.0302 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171009 | GT FDN VIEWS & SECTIONS FORMWORK DWG, PART 4/6 | DWG ¦ Drawing | GT ¦ Gas Turbine |  |  |  | DWG ¦ Drawing for GT ¦ Gas Turbine |  | GT - GT FUEL GAS HEATER SECTIONAL ASSEMBLY | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦gtg¦turbine | fgp¦gt¦gtg | scoped | match | match | match | passed |  | 0.3333 | 0.6081 | 0.4158 | 0.4158 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | fgp¦gtg | gtg | query | gtg | match | false | 3 | 4 | 11.4109 | 0.6175 | 0.0315 | 0.0315 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171010 | GT FDN ANCHOR BOLT DETAILS FORMWORK DWG, PART 5/6 | DWG ¦ Drawing | GT ¦ Gas Turbine |  |  |  | DWG ¦ Drawing for GT ¦ Gas Turbine |  | GT FDN ANCHOR BOLT DETAILS FORMWORK DWG, PART 5/6 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 6 | 1 | 11.4109 | 0.6266 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171011 | GT FDN TOP PLAN VIEW SCHEDULE OF EMBEDDED PARTS FORMWORK DRAWING, PART 6/6 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT FDN TOP PLAN VIEW SCHEDULE OF EMBEDDED PARTS FORMWORK DRAWING, PART 6/6 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 9 | 2 | 11.4111 | 0.6507 | 0.0306 | 0.0306 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171012 | GT FDN BOTTOM LONGITUDINAL & LATERAL REINFORCEMENT REINFORCEMENT DRAWING BASEMAT, PART 1/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.4000 | 0.6480 | 0.4744 | 0.4744 | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 1 | 12.6462 | 0.6417 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171013 | GT FDN TOP LOGITUDINAL & LATERAL REINFORCEMENT DWG BASEMAT, PART 2/9 | DWG ¦ Drawing | GT ¦ Gas Turbine |  |  |  | DWG ¦ Drawing for GT ¦ Gas Turbine |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.4000 | 0.6657 | 0.4797 | 0.4797 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 1 | 1 | 13.1879 | 0.6517 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-07-10 | 2024-08-09 | 2024-09-08 | 2024-09-23 | 2024-10-08 | 2024-10-23 | generated | 0.90 | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171014 | GT FDN BOTTOM & TOP (3rd + 4th LAYER) LATERAL & LONGITUDINAL REINFORCEMENT, PART 3/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.4000 | 0.6480 | 0.4744 | 0.4744 | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 1 | 1 | 13.2114 | 0.6555 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171015 | GT FDN CONNECTION AND SIDE FACE REINFORCEMENT PLAN AT +0.152M & 1.099M LEVEL REINFORCEMENT DRAWING BASEMAT, PART 4/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.4000 | 0.6480 | 0.4744 | 0.4744 | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 2 | 12.6462 | 0.6368 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171016 | GT FDN SPACER REBARS AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 5/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT FDN SPACER REBARS AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 5/9 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 9 | 1 | 11.4109 | 0.6302 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171017 | GT FDN SECTION 1-1 AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 6/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT FDN SECTION 1-1 AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 6/9 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF1213W16A01.1 | (GT #12) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | 2007-03-01 | 2007-07-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 2 | 3 | 14.3940 | 0.6495 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171018 | GT FDN REINFORCEMENT SECTION 2-2 AND 3-3 REINFORCEMENT DRAWING BASEMAT, PART 7/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT - GT FUEL GAS HEATER SECTIONAL ASSEMBLY | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦gtg¦turbine | fgp¦gt¦gtg | scoped | match | match | match | passed |  | 0.3333 | 0.5887 | 0.4099 | 0.4099 | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | civil_design | civil_design | match | gtg | fgp¦gtg | gtg | query | gtg | match | false | 1 | 4 | 15.0118 | 0.6217 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171019 | GT FDN REINFORCEMENT DETAILS SECTION 4-4 AND 5-5 REINFORCEMENT DRAWING BASEMAT, PART 8/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT FDN SECTION 1-1 AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 6/9 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 0.9195 | 0.9759 | 0.9759 | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 13 | 1 | 11.4109 | 0.6177 | 0.0301 | 0.0301 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171020 | GT FDN REINFORCEMENT PLAN & SECTIONS FOR COMPRESSION SUPPORT, TURNING GEAR PEDESTAL AND MOUNTING PAD PEDESTAL REINFORCEMENT DRAWING BASEMAT, PART 9/9 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT - GT FUEL GAS HEATER SECTIONAL ASSEMBLY | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦gtg¦turbine | fgp¦gt¦gtg | scoped | match | match | match | passed |  | 0.3333 | 0.5887 | 0.4099 | 0.4099 | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | fgp¦gtg | gtg | query | gtg | match | false | 7 | 1 | 11.4109 | 0.6382 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171021 | GT FDN REINFORCEMENT PLAN AT +1.099M LEVEL AND SPACER & SIDE FACE REBARS GENERATOR DECK REINFORCEMENT, PART 1/2 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.4000 | 0.6480 | 0.4744 | 0.4744 | FA | 2EF1213W16A01.1 | (GT #22) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | 2007-03-30 | 2007-08-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 1 | 5 | 16.4340 | 0.6606 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-07-10 | 2024-08-09 | 2024-09-08 | 2024-09-23 | 2024-10-08 | 2024-10-23 | generated | 0.90 | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171022 | GT FDN SECTIONS & DETAILS GENERATOR DECK REINFORCEMENT, PART 2/2 | DRAWING | GT ¦ Gas Turbine |  |  |  | DRAWING for GT ¦ Gas Turbine |  | GT FDN SECTIONS & DETAILS GENERATOR DECK REINFORCEMENT, PART 2/2 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | FA | 2EF1213W16A01.1 | (GT #22) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | 2007-03-30 | 2007-08-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 1 | 15.7479 | 0.6942 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171023 | GTG FOUNDATION BAR BENDING SCHEDULE | SCHEDULE | GTG ¦ Gas Turbine Generator |  |  |  | Schedule for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5337 | 0.4401 | 0.4401 | FI | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-08-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 6 | 9.2947 | 0.6345 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171024 | GT FDN BENDING SCHEDULES - GENERATOR DECK | SCHEDULES | GT ¦ Gas Turbine |  |  |  | SCHEDULES for GT ¦ Gas Turbine |  | GT FDN BENDING SCHEDULES - GENERATOR DECK | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | gas¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.3333 | 0.6153 | 0.4179 | 0.4179 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 |  | civil_design | query_unknown | gtg | gtg | gtg | query | gtg | match | false | 3 | 5 | 12.3791 | 0.6210 | 0.0313 | 0.0234 | hybrid | structured_no_phase | gtg |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.64 | usable | rule_score_medium;activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171051 | GTG AUXILIARY FOUNDATION - DESIGN REPORT | DESIGN REPORT | GTG ¦ Gas Turbine Generator |  |  |  | Design Report for GTG ¦ Gas Turbine Generator |  | GTG FOUNDATION - DESIGN REPORT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | report | report | design_report | design_report | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.7500 | 0.6326 | 0.7148 | 0.7148 | FA | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | false | 1 | 5 | 16.8510 | 0.7459 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171052 | GTG AUXILIARY FOUNDATION - GENERAL ARRANGEMENT | GENERAL ARRANGEMENT | GTG ¦ Gas Turbine Generator |  |  |  | General Arrangement Drawing for GTG ¦ Gas Turbine Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7068 | 0.9120 | 0.9120 | FA | 1EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 |  | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | false | 5 | 1 | 20.8701 | 0.7192 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171053 | FOUNDATION FOR SFC & SEE TRANSFORMER PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING | SFC ¦ Static Frequency Converter |  |  |  | DRAWING for SFC ¦ Static Frequency Converter |  | TRANSFORMER PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | converter¦frequency¦sfc¦static |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8551 | 0.9565 | 0.6696 | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match |  | gsut_uat | gsut_uat | rule | electrical¦gsut_uat¦stg | match | false | 2 | 3 | 7.9841 | 0.5622 | 0.0320 | 0.0320 | hybrid | structured_preferred | gsut_uat | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 | 0.80 | usable | activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171054 | FOUNDATION FOR EXHAUST TRANSITION DUCT & COMPRESSOR BLEED PIPE SUPPORT PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DUCT |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for DUCT |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | duct |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8720 | 0.9616 | 0.6731 | FA | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-08-02 | 2007-12-13 | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | false | 33 | 1 | 13.5157 | 0.6195 | 0.0271 | 0.0204 | hybrid | structured_no_system |  | civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171055 | FOUNDATION FOR WOBBE METER CABINET, GT ENCLOSURE RIGHT SIDE EXHAUST END EXTERIOR PLATFORM & AIR COMPRESSOR SKID(DAIS) PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | GT ¦ Gas Turbine |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for GT ¦ Gas Turbine |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8003 | 0.9401 | 0.6581 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | false | 9 | 10 | 11.4109 | 0.6514 | 0.0288 | 0.0288 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171056 | FOUNDATION FOR SEE/ SFC PACKAGE FOUNDATION INTERFACE-SEE ONLY PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | SFC PACKAGE ¦ Static Frequency Converter PACKAGE |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for SFC PACKAGE ¦ Static Frequency Converter PACKAGE |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | converter¦frequency¦sfc¦static |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6467 | 0.6607 | 0.6607 | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | 15 | 3 | 17.9487 | 0.5180 | 0.0292 | 0.0219 | hybrid | structured_no_system |  | civil_design |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | 2025-03-31 | 2025-04-15 | 2025-04-30 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171057 | FOUNDATION FOR SEE/ SFC PACKAGE SEE WITH SFC NORMAL START PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | SFC PACKAGE ¦ Static Frequency Converter PACKAGE |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for SFC PACKAGE ¦ Static Frequency Converter PACKAGE |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | converter¦frequency¦sfc¦static |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6174 | 0.6519 | 0.6519 | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | 17 | 3 | 15.6947 | 0.5145 | 0.0289 | 0.0216 | hybrid | structured_no_system |  | civil_design |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | 2025-03-31 | 2025-04-15 | 2025-04-30 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171058 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS FORMWORK DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK DRAWING |  |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK DRAWING |  | PLAN, SECTIONS AND DETAILS FORMWORK DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | 23 | 24 | 23.1444 | 0.5641 | 0.0240 | 0.0180 | hybrid | structured_no_system |  | civil_design |  | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-10-05 | 2024-11-04 | generated | 0.30 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171059 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING |  |  |  |  | PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.5639 | 0.6358 | 0.6358 | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | 24 | 52 | 23.1444 | 0.5452 | 0.0208 | 0.0156 | hybrid | structured_no_system |  | civil_design |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | 2025-03-31 | 2025-04-15 | 2025-04-30 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171060 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM BAR BENDING SCHEDULE | BAR BENDING SCHEDULE |  |  |  |  | BAR BENDING SCHEDULE |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  | gtg | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.6346 | 0.7504 | 0.7504 | FA | 3CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | 2007-10-31 | 2008-01-25 | civil_design | civil_design | match |  | gtg | gtg | rule | fgp¦gtg | match | false | 6 | 4 | 18.1314 | 0.5541 | 0.0308 | 0.0308 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.90 | 0.80 | needs_review | rule_scope_status=query_unscoped;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171061 | FOUNDATION FOR ROTOR AIR COOLER(KETTLE BOILER) & ROTOR COOLING AIR PIPE SUPPORTS PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING |  |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 47 | 4 | 13.7780 | 0.5436 | 0.0250 | 0.0187 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171062 | FOUNDATION FOR SFC CROSSOVER SWITCH & FIRE PROTECTION SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | SFC ¦ Static Frequency Converter | Fire Fighting |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for Fire Fighting |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | fighting¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8615 | 0.9585 | 0.6709 | FA | 0CF4500W16A03 | (Fire WTR Pump Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-08-31 | 2007-10-27 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 2 | 26.9000 | 0.5635 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171063 | FOUNDATION FOR PULSE AIR COMPRESSIOR SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | Compressor |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for Compressor |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8090 | 0.9427 | 0.6599 | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | 65 | 7 | 10.2101 | 0.5876 | 0.0229 | 0.0172 | hybrid | structured_no_system |  | civil_design |  | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-10-05 | 2024-11-04 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171101 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION PILE DESIGN | CALCULATION | Steam Turbine Generator |  |  |  | Calculation sheet for Steam Turbine Generator |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.4935 | 0.5680 | 0.5680 | FI | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 4 | 21.0973 | 0.6519 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171102 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION DYNAMIC ANALYSIS | CALCULATION | Steam Turbine Generator |  |  |  | Calculation sheet for Steam Turbine Generator |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.4935 | 0.5680 | 0.5680 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 1 | 13.3572 | 0.6719 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171103 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION R.C DESIGN | CALCULATION | Steam Turbine Generator |  |  |  | Calculation sheet for Steam Turbine Generator |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.4935 | 0.5680 | 0.5680 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 1 | 16.6824 | 0.6878 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171104 | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | FOUNDATION LAYOUT | Steam Turbine Generator |  |  |  | FOUNDATION LAYOUT for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 1.0000 | 0.8796 | 0.9639 | 0.9639 | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 3 | 1 | 15.5923 | 0.7346 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171105 | STEAM TURBINE GENERATOR FOUNDATION PILE ARRANGEMENT | FOUNDATION PILE ARRANGEMENT | Steam Turbine Generator |  |  |  | FOUNDATION PILE ARRANGEMENT for Steam Turbine Generator | [5 empty] | rule_query | other | other | foundation_pile_arrangement | steam_turbine_generator_foundation_pile_arrangement | generator¦steam¦stg¦turbine | stg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8814 | 0.9644 | 0.9644 |  | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 1 | 4 | 28.7888 | 0.6783 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | stg | civil_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171106 | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Steam Turbine Generator |  |  |  | PLAN AND SECTION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8571 | 0.8361 | 0.8508 | 0.8508 | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 2 | 13.3572 | 0.7094 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171113 | STEAM TURBINE GENERATOR FOUNDATION ANCHOR BOLTS AND EMBEDMENT |  | Steam Turbine Generator |  |  |  | for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION ANCHOR BOLTS AND EMBEDMENT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | steam_turbine_generator_foundation_anchor_bolts_and_embedment | steam_turbine_generator_foundation_anchor_bolts_and_embedment | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.3750 | 0.6271 | 0.4506 | 0.4506 | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 1 | 13.3572 | 0.6989 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.85 | usable | rule_score_medium | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0MPA-171117 | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | FOUNDATION R.C DETAIL | Steam Turbine Generator |  |  |  | FOUNDATION R.C DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 1.0000 | 0.8664 | 0.9599 | 0.9599 | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 1 | 15.5923 | 0.7118 | 0.0328 | 0.0328 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171201 | CALCULATION OF CCW FIN FAN COOLER FOUNDATION | CALCULATION | Fin Fan Cooler | CCW ¦ Closed Cooling Water |  |  | Calculation sheet for Fin Fan Cooler | CCW FIN FAN COOLER | CALCULATION OF CCW FIN FAN COOLER FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9617 | 0.9885 | 0.9885 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | false | 3 | 7 | 56.9594 | 0.6979 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | ccw | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171202 | CCW FIN FAN COOLER FOUNDATION LAYOUT | FOUNDATION LAYOUT | Fin Fan Cooler | CCW ¦ Closed Cooling Water |  |  | FOUNDATION LAYOUT for CCW ¦ Closed Cooling Water | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccw¦closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9568 | 0.9871 | 0.9871 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | false | 3 | 4 | 58.7817 | 0.7493 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | ccw | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171203 | CCW FIN FAN COOLER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | CCW FIN FAN COOLER ¦ Closed Cooling Water FIN FAN COOLER |  |  |  | PLAN AND SECTION for CCW FIN FAN COOLER ¦ Closed Cooling Water FIN FAN COOLER | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | ccw¦closed¦cooler¦cooling¦fan¦fin¦water |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.8621 | 0.8711 | 0.8711 | FA | 3EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | false | 5 | 1 | 74.8292 | 0.7285 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | ccw | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171221 | CALCULATION OF CPP FIN FAN COOLER FOUNDATION | CALCULATION | CPP FIN FAN COOLER ¦ CONDENSATE POLISING PLANT FIN FAN COOLER |  |  |  | Calculation sheet for CPP FIN FAN COOLER ¦ CONDENSATE POLISING PLANT FIN FAN COOLER | CPP FIN FAN COOLER | CALCULATION OF CPP FIN FAN COOLER FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | condensate¦cooler¦cpp¦fan¦fin¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8251 | 0.7475 | 0.7475 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw¦condensate | ccw | ccw¦condensate | query | ccw¦gtg | match | false | 3 | 19 | 55.4317 | 0.5842 | 0.0285 | 0.0285 | hybrid | structured_cell_found_text_preferred | ccw¦condensate | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171222 | CPP FIN FAN COOLER FOUNDATION LAYOUT | LAYOUT | CPP FIN FAN COOLER ¦ CONDENSATE POLISING PLANT FIN FAN COOLER |  |  |  | Layout Drawing for CPP FIN FAN COOLER ¦ CONDENSATE POLISING PLANT FIN FAN COOLER | CPP FIN FAN COOLER | CPP FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦cooler¦cpp¦fan¦fin¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7819 | 0.8179 | 0.8179 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw¦condensate | ccw | ccw¦condensate | query | ccw¦gtg | match | false | 3 | 4 | 55.4317 | 0.6204 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | ccw¦condensate | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171223 | CPP FIN FAN COOLER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | CPP FIN FAN COOLER ¦ CONDENSATE POLISING PLANT FIN FAN COOLER |  |  |  | PLAN AND SECTION for CPP FIN FAN COOLER ¦ CONDENSATE POLISING PLANT FIN FAN COOLER | CPP FIN FAN COOLER | CPP FIN FAN COOLER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | condensate¦cooler¦cpp¦fan¦fin¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.8668 | 0.8725 | 0.8725 | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw¦condensate | ccw | ccw¦condensate | query | ccw¦gtg | match | false | 3 | 8 | 55.4317 | 0.6104 | 0.0306 | 0.0306 | hybrid | structured_cell_found_text_preferred | ccw¦condensate | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULC-171301 | CALCULATION OF AIR COOLED CONDENSER FOUNDATION | CALCULATION | AIR COOLED CONDENSER |  |  |  | Calculation sheet for AIR COOLED CONDENSER | CONDENSER | CALCULATION OF AIR COOLED CONDENSER FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.6667 | 0.7901 | 0.7037 | 0.7037 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc | acc | query | acc¦condensate | match | false | 1 | 5 | 19.0699 | 0.6674 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | acc | civil_design |  | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-171302 | AIR COOLED CONDENSER FOUNDATION LAYOUT | LAYOUT | AIR COOLED CONDENSER |  |  |  | Layout Drawing for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.6746 | 0.7274 | 0.7274 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc¦electrical | acc | query | acc¦condensate | match | false | 4 | 2 | 19.0699 | 0.6672 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | acc | civil_design |  | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-171303 | AIR COOLED CONDENSER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | AIR COOLED CONDENSER |  |  |  | PLAN AND SECTION for ACC | CONDENSER | AIR COOLED CONDENSER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9706 | 0.9912 | 0.9912 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc | acc | query | acc¦condensate | match | false | 3 | 5 | 19.0699 | 0.6527 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | acc | civil_design |  | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-171308 | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | DETAIL | AIR COOLED CONDENSER |  |  |  | Detail Drawing for ACC | CONDENSER | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9794 | 0.9938 | 0.9938 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc | acc | query | acc¦condensate | match | false | 2 | 6 | 19.0699 | 0.6538 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | acc | civil_design |  | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-171309 | AIR COOLED CONDENSER DRAIN WATER PUMP PIT DETAIL | DETAIL | AIR COOLED CONDENSER |  |  |  | Detail Drawing for ACC | CONDENSER | AIR COOLED CONDENSER DRAIN WATER PUMP PIT DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | acc¦air¦condenser¦cooled¦pump | acc¦pump | scoped | match | match | match | passed |  | 1.0000 | 0.9753 | 0.9926 | 0.9926 | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | false | 1 | 3 | 16.9918 | 0.6112 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UNX-171401 | CALCULATION OF PIPE SLEEPER FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF PIPE SLEEPER FOUNDATION | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 1 | 1 | 14.0934 | 0.5014 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | civil_design |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171402 | PIPE SLEEPER FOUNDATION OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | PIPE SLEEPER FOUNDATION OVERALL LAYOUT | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9990 | 0.9997 | 0.9997 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 11 | 1 | 10.2065 | 0.5723 | 0.0305 | 0.0229 | hybrid | structured_no_system |  | civil_design |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171403 | PIPE SLEEPER FOUNDATION LAYOUT | LAYOUT |  |  |  |  | Layout Drawing |  | PIPE SLEEPER FOUNDATION LAYOUT | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 6 | 4 | 11.5202 | 0.5929 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  | 2025-02-08 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-24 | 2025-05-24 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171410 | PIPE SLEEPER FOUNDATION PLAN AND SECTION | PLAN AND SECTION |  |  |  |  | PLAN AND SECTION |  | PIPE SLEEPER FOUNDATION PLAN AND SECTION | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | sectional_drawing | sectional_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 7 | 1 | 10.2065 | 0.5531 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UEG-171501 | FGS AREA FOUNDATION CALCULATION | CALCULATION |  | FGS ¦ Fuel Gas System |  |  | Calculation sheet for FGS ¦ Fuel Gas System | Fuel Gas System | Calculation Sheets | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | calculation | calculation | calculation | calculation | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.9031 | 0.8309 | 0.8309 | FA | 0CF3520W16A03.1 | (FGS LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-09-14 | 2007-11-10 | civil_design | civil_design | match | fgp | fgp | fgp | query | fgp | match | false | 2 | 14 | 18.9360 | 0.6305 | 0.0296 | 0.0296 | hybrid | structured_cell_found_text_preferred | fgp | civil_design |  | 2025-02-01 | 2025-03-01 | 2025-03-29 | 2025-03-22 | 2025-04-19 | 2025-05-17 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEG-171502 | FGS AREA LAYOUT | LAYOUT |  | FGS ¦ Fuel Gas System |  |  | Layout Drawing for FGS ¦ Fuel Gas System | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8361 | 0.8342 | 0.8342 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | 4 | 1 | 19.5912 | 0.7376 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEG-171504 | FGS AREA PLAN AND SECTION | PLAN AND SECTION |  | FGS ¦ Fuel Gas System |  |  | PLAN AND SECTION for FGS ¦ Fuel Gas System | Fuel Gas System | FGS AREA PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8750 | 0.9015 | 0.8830 | 0.8830 | FA | 0EF3520W32A04.1 | (FGS LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 |  | civil_design | query_unknown | fgp | fgp | fgp | query | fgp | match | false | 6 | 4 | 17.0083 | 0.6706 | 0.0308 | 0.0231 | hybrid | structured_no_phase | fgp |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171601 | CALCULATION OF GT PERFORMANCE HEATER FOUNDATION | CALCULATION | GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  |  |  | Calculation sheet for GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  | CALCULATION OF GT PERFORMANCE HEATER FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7596 | 0.6945 | 0.6945 | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 1 | 6 | 11.4109 | 0.5634 | 0.0315 | 0.0315 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171602 | GT PERFORMANCE HEATER FOUNDATION LAYOUT | LAYOUT | GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  |  |  | Layout Drawing for GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  | GT PERFORMANCE HEATER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.7056 | 0.7717 | 0.7717 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 4 | 11.4109 | 0.5995 | 0.0315 | 0.0315 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171603 | GT PERFORMANCE HEATER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  |  |  | PLAN AND SECTION for GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  | GT PERFORMANCE HEATER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8571 | 0.7525 | 0.8258 | 0.8258 | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 1 | 3 | 11.4109 | 0.5768 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULX-171604 | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | DETAIL | GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  |  |  | Detail Drawing for GT PERFORMANCE HEATER ¦ Gas Turbine PERFORMANCE HEATER |  | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.6294 | 0.7488 | 0.7488 | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | false | 3 | 7 | 11.4109 | 0.5580 | 0.0308 | 0.0308 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UEM-171701 | CALCULATION OF WASTE WATER TREATMENT PLANT | CALCULATION | WASTE WATER TREATMENT PLANT |  |  |  | Calculation sheet for WASTE WATER TREATMENT PLANT | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8603 | 0.8414 | 0.8414 | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 8 | 1 | 35.9876 | 0.6223 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEM-171702 | WASTE WATER TREATMENT PLANT PLAN AND SECTION | PLAN AND SECTION | WASTE WATER TREATMENT PLANT |  |  |  | PLAN AND SECTION for WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT PLANT PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9316 | 0.9795 | 0.9795 | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 |  | system_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 3 | 40.5392 | 0.6229 | 0.0315 | 0.0236 | hybrid | structured_no_phase | wts |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEM-171708 | WASTE WATER TREATMENT PLANT EMBEDMENT DETAIL | DETAIL | WASTE WATER TREATMENT PLANT |  |  |  | Detail Drawing for WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8227 | 0.9468 | 0.9468 | FA | 0EF4035W16A02.2 | (WWT LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | design_drawing | civil_design | compatible | wts | wts | wts | query | wts | match | false | 4 | 4 | 39.5414 | 0.5745 | 0.0312 | 0.0234 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UEM-171711 | WASTE WATER TREATMENT R.C DETAIL | DETAIL |  |  |  |  | Detail Drawing | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.9515 | 0.8455 | 0.8455 | FA | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | design_drawing | civil_design | compatible |  | wts | wts | rule | wts | match | false | 4 | 6 | 19.8801 | 0.5740 | 0.0308 | 0.0231 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171801 | CALCULATION OF HRSG FOUNDATION PILING | CALCULATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7930 | 0.7046 | 0.7046 | FA | 0EF1600W14A10 | HRSG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-06-15 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 4 | 1 | 19.0338 | 0.7068 | 0.0320 | 0.0320 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171802 | CALCULATION OF HRSG FOUNDATION | CALCULATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7930 | 0.7046 | 0.7046 | FA | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-08-02 | 2007-12-13 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 7 | 10 | 17.7825 | 0.6411 | 0.0292 | 0.0292 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171803 | HRSG FOUNDATION ARRANGEMENT | ARRANGEMENT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG ¦ Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4713 | 0.3747 | 0.3185 | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg |  | hrsg | query | hrsg | match | false | 2 | 22 | 22.8843 | 0.6449 | 0.0283 | 0.0283 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171804 | HRSG FOUNDATION PILE ARRANGEMENT PLAN | ARRANGEMENT PLAN | HRSG ¦ Heat Recovery Steam Generator |  |  |  | ARRANGEMENT PLAN for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7211 | 0.6830 | 0.6830 | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 3 | 19 | 22.8843 | 0.6563 | 0.0285 | 0.0285 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-12-31 | 2025-01-30 | 2025-03-01 | 2025-03-16 | 2025-03-31 | 2025-04-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171805 | HRSG FOUNDATION LAYOUT | LAYOUT | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 8 | 1 | 19.4899 | 0.6822 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171806 | HRSG FOUNDATION PLAN SECTION & DETAIL | PLAN SECTION & DETAIL | HRSG ¦ Heat Recovery Steam Generator |  |  |  | PLAN SECTION & DETAIL for HRSG |  | HRSG FOUNDATION PLAN SECTION & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8222 | 0.8066 | 0.8066 | FA | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-08-02 | 2007-12-13 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 10 | 10 | 17.7825 | 0.6710 | 0.0286 | 0.0286 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171807 | HRSG FOUNDATION REBAR DETAIL | REBAR DETAIL | HRSG ¦ Heat Recovery Steam Generator |  |  |  | REBAR DETAIL for HRSG |  | HRSG FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.8521 | 0.7806 | 0.7806 | FA | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-09-03 | 2008-01-14 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 10 | 7 | 17.7825 | 0.6521 | 0.0292 | 0.0292 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171815 | HRSG MISC. FOUNDATION PLAN | PLAN | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7622 | 0.6953 | 0.6953 | FA | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-08-02 | 2007-12-13 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 7 | 12 | 17.7825 | 0.6673 | 0.0288 | 0.0288 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-02-12 | 2025-03-14 | 2025-04-13 | 2025-04-28 | 2025-05-13 | 2025-05-28 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171816 | HRSG MISC. FOUNDATION DETAILS | DETAILS | HRSG ¦ Heat Recovery Steam Generator |  |  |  | DETAILS for HRSG |  | HRSG MISC. FOUNDATION DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6971 | 0.5591 | 0.5591 | FA | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-09-03 | 2008-01-14 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 9 | 7 | 17.7825 | 0.6767 | 0.0294 | 0.0294 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171819 | CALCULATION OF HRSG MISC. FOUNDATION | CALCULATION | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG ¦ Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7930 | 0.7046 | 0.7046 | FA | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-09-03 | 2008-01-14 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 9 | 8 | 17.7825 | 0.6489 | 0.0292 | 0.0292 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-02-14 | 2025-03-16 | 2025-04-15 | 2025-04-30 | 2025-05-15 | 2025-05-30 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P8UTH-172001 | CALCULATION OF RESERVE BOILER FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF IPB FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6845 | 0.7303 | 0.7303 | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match |  | electrical | electrical | rule | electrical¦gsut_uat¦stg | match | false | 8 | 6 | 2.0781 | 0.4527 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.90 | 0.80 | usable | activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172003 | RESERVE BOILER FOUNDATION LAYOUT | LAYOUT |  |  |  |  | Layout Drawing |  | PIPE SLEEPER FOUNDATION LAYOUT | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | layout_drawing | layout_drawing | reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6655 | 0.5496 | 0.5496 | FA | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | false | 93 | 1 | 3.3489 | 0.5574 | 0.0229 | 0.0172 | hybrid | structured_no_system |  | civil_design |  | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | 2025-07-15 | 2025-08-14 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172004 | RESERVE BOILER FOUNDATION SECTION & DETAIL | SECTION & DETAIL |  |  |  |  | SECTION & DETAIL |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5970 | 0.6458 | 0.6458 | FA | 3EF1625W16A03.2 | (HRSG #32 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | 2007-11-08 | 2008-03-18 | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | false | 875 | 67 | 1.9705 | 0.5534 | 0.0089 | 0.0067 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P8UTH-172005 | RESERVE BOILER FOUNDATION REBAR DETAIL | REBAR DETAIL |  |  |  |  | REBAR DETAIL |  | Foundation Rebar Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7481 | 0.9244 | 0.7858 | FA | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | 67 | 5 | 2.1802 | 0.5049 | 0.0233 | 0.0174 | hybrid | structured_no_system |  | civil_design |  | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.60 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172007 | RESERVE BOILER GRADE SLAB PLAN & SECTION | PLAN & SECTION |  |  |  |  | PLAN & SECTION |  | Plan & Section | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.9372 | 0.7478 | 0.6356 | FA | 3CF2020W16A08 | (ST #30) Pedestal & Top Slab Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2008-04-16 | 2008-10-11 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 5 | 51 | 10.2570 | 0.4746 | 0.0244 | 0.0137 | hybrid | structured_no_system |  |  |  | 2024-12-03 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.60 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P8UTH-172008 | RESERVE BOILER GRADE SLAB REBAR DETAIL | REBAR DETAIL |  |  |  |  | REBAR DETAIL |  | Rebar Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.9065 | 0.7386 | 0.6278 | FA | 1CF2020W16A08 | (ST #10) Pedestal & Top Slab Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2008-03-04 | 2008-08-29 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 2 | 113 | 10.2570 | 0.4092 | 0.0219 | 0.0123 | hybrid | structured_no_system |  |  |  | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | 2025-01-04 | 2025-02-03 | generated | 0.60 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P8UTH-172011 | CALCULATION OF FD FAN AND MISC. FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF HRSG MISC. FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7454 | 0.7836 | 0.7836 | FA | 1CF1615W16A03 | (HRSG #11 Duct) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-12-14 | 2008-03-15 | civil_design | civil_design | match |  | hrsg | hrsg | rule | hrsg | match | false | 8 | 5 | 2.0621 | 0.4790 | 0.0301 | 0.0301 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-15 | 2024-10-15 | 2024-11-14 | generated | 0.90 | 0.80 | needs_review | rule_scope_status=query_unscoped;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172012 | RESERVE BOILER FD FAN FOUNDATION | FOUNDATION |  |  |  |  | FOUNDATION |  | Foundation | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | foundation | foundation | reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.9008 | 0.5036 | 0.4280 | FA | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match |  |  |  |  | ccw¦gtg | query_unscoped | false | 1 | 71 | 9.8537 | 0.5665 | 0.0240 | 0.0180 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.60 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172013 | RESERVE BOILER MISC. FOUNDATION | FOUNDATION |  |  |  |  | FOUNDATION |  | Foundation | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | foundation | foundation | reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.9008 | 0.5036 | 0.4280 | FA | 1CF3520W16A01 | (FGSS #11) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | false | 1 | 11 | 13.1819 | 0.5670 | 0.0305 | 0.0229 | hybrid | structured_no_system |  | civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.60 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172100 | TRANSFORMER FOUNDATION ARRANGEMENT PLAN | ARRANGEMENT PLAN | TRANSFORMER |  |  |  | ARRANGEMENT PLAN for TRANSFORMER |  | TRANSFORMER FOUNDATION ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | transformer |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8398 | 0.7769 | 0.7769 | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | false | 9 | 2 | 13.8900 | 0.6372 | 0.0306 | 0.0306 | hybrid | structured_cell_found_text_preferred | gsut_uat | civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAG-172101 | CALCULATION OF STG STEP - UP AND EXCITATION TRANSFORMER FOUNDATION | CALCULATION | STG ¦ Steam Turbine Generator |  |  |  | Calculation sheet for STG ¦ Steam Turbine Generator |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5739 | 0.5922 | 0.5922 | FI | 1EF6500W16A02 | (STG #10 & UST Shelter) FDN & Firewall Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | false | 4 | 16 | 37.5330 | 0.6338 | 0.0288 | 0.0288 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172102 | STG STEP UP AND EXCITATION TRANSFORMER PLAN & SECTION | PLAN & SECTION | STG ¦ Steam Turbine Generator |  |  |  | PLAN & SECTION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.7143 | 0.8341 | 0.7502 | 0.7502 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  | civil_design | query_unknown | stg | stg | stg | query | gsut_uat¦stg | match | false | 1 | 15 | 36.9909 | 0.6535 | 0.0297 | 0.0223 | hybrid | structured_no_phase | stg |  |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172108 | STG STEP UP AND EXCITATION TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | ARRANGEMENT PLAN & SECTION | STG ¦ Steam Turbine Generator |  |  |  | ARRANGEMENT PLAN & SECTION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.7143 | 0.7711 | 0.7313 | 0.7313 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | false | 1 | 1 | 41.4795 | 0.6984 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAG-172109 | STG STEP UP AND EXCITATION TRANSFORMER RE-BAR DETAIL | RE-BAR DETAIL | STG ¦ Steam Turbine Generator |  |  |  | RE-BAR DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7561 | 0.7868 | 0.7868 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  | civil_design | query_unknown | stg | stg | stg | query | gsut_uat¦stg | match | false | 1 | 7 | 36.9909 | 0.6580 | 0.0313 | 0.0235 | hybrid | structured_no_phase | stg |  |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAG-172151 | CALCULATION OF GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION | CALCULATION | GTG ¦ Gas Turbine Generator |  |  |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | false | 1 | 5 | 16.0483 | 0.7338 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172162 | GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION PLAN & SECTION | PLAN & SECTION | GTG ¦ Gas Turbine Generator |  |  |  | PLAN & SECTION for GTG |  | GTG #1,2 LEB - STAIR PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.7576 | 0.6473 | 0.6473 | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | false | 1 | 4 | 16.0483 | 0.7504 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172168 | GTG STEP UP & UNIT AUX. TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | ARRANGEMENT PLAN & SECTION | GTG ¦ Gas Turbine Generator |  |  |  | ARRANGEMENT PLAN & SECTION for GTG |  | GTG STEP UP & UNIT AUX. TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 |  | civil_design | civil_design | match | gtg | gsut_uat¦gtg | gtg | query | gtg | match | false | 4 | 1 | 14.3007 | 0.7013 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAG-172170 | GTG STEP UP & UNIT AUX. TRANSFORMER RE-BAR DETAIL | RE-BAR DETAIL | GTG ¦ Gas Turbine Generator |  |  |  | RE-BAR DETAIL for GTG |  | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.7849 | 0.7021 | 0.7021 | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 |  | civil_design | query_unknown | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | false | 33 | 4 | 14.0330 | 0.6975 | 0.0264 | 0.0198 | hybrid | structured_no_phase | gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UBN-172201 | CALCULATION OF BSDG FOUNDATION | CALCULATION | BSDG ¦ Blackstart Diesel Generator |  |  |  | Calculation sheet for BSDG ¦ Blackstart Diesel Generator |  | CALCULATION OF BSDG FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | blackstart¦bsdg¦diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg | bsedg | query | bsedg | match | false | 1 | 1 | 30.9125 | 0.7246 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bsedg | civil_design |  | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UBN-172202 | BSDG FOUNDATION PLAN & SECTION | PLAN & SECTION | BSDG ¦ Blackstart Diesel Generator |  |  |  | PLAN & SECTION for BSDG ¦ Blackstart Diesel Generator |  | BSDG FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | blackstart¦bsdg¦diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6845 | 0.7303 | 0.7303 | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg | bsedg | query | bsedg | match | false | 1 | 3 | 30.9125 | 0.7462 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | bsedg | civil_design |  | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UBN-172203 | BSDG FOUNDATION R.C DETAIL | R.C DETAIL | BSDG ¦ Blackstart Diesel Generator |  |  |  | R.C DETAIL for BSDG ¦ Blackstart Diesel Generator |  | BSDG FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | blackstart¦bsdg¦diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | FA | 0EF3530W16A14 | (BSDG BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-07-09 | 2007-10-08 | civil_design | civil_design | match | bsedg | bsedg | bsedg | query | bsedg | match | false | 5 | 1 | 30.5168 | 0.7569 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | bsedg | civil_design |  | 2024-03-01 | 2024-03-11 | 2024-03-26 | 2024-04-10 | 2024-05-10 | 2024-06-09 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0BAA-172401 | CALCULATION OF IPB FOUNDATION | CALCULATION | IPB ¦ Isolated Phase Busduct |  |  |  | Calculation sheet for IPB ¦ Isolated Phase Busduct |  | CALCULATION OF IPB FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | busduct¦ipb¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical¦gsut_uat¦gtg | match | false | 7 | 1 | 2.0781 | 0.4937 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0BAA-172402 | IPB FOUNDATION PLAN & SECTION | PLAN & SECTION | IPB ¦ Isolated Phase Busduct |  |  |  | PLAN & SECTION for IPB ¦ Isolated Phase Busduct |  | IPB FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | busduct¦ipb¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6503 | 0.7201 | 0.7201 | FA | 0CF5544W16A10 | (GIS BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-06-30 | 2007-08-27 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 2 | 1 | 2.1451 | 0.4916 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-02 | 2024-03-17 | 2024-04-01 | 2024-05-01 | 2024-05-31 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0BAA-172403 | IPB FOUNDATION R.C DETAIL | R.C DETAIL | IPB ¦ Isolated Phase Busduct |  |  |  | R.C DETAIL for IPB ¦ Isolated Phase Busduct |  | IPB FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | busduct¦ipb¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0CF5544W16A10 | (GIS BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-06-30 | 2007-08-27 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 10 | 4 | 2.1451 | 0.4734 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-02 | 2024-03-17 | 2024-04-01 | 2024-05-01 | 2024-05-31 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULC-172501 | CALCULATION OF CONDENSATE WATER TANK FOUNDATION | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match |  |  |  |  | condensate¦fgp | query_unscoped | false | 11 | 5 | 18.3030 | 0.5797 | 0.0295 | 0.0221 | hybrid | structured_no_system |  | civil_design |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-172502 | CONDENSATE WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank |  |  |  | PLAN & SECTION for Tank | Condensate | CONDENSATE WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.9338 | 0.9801 | 0.9801 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match |  | condensate | condensate | rule | condensate¦fgp | match | false | 3 | 7 | 18.3030 | 0.6312 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | condensate | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | 2024-04-02 | 2024-05-02 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-172503 | CONDENSATE WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank |  |  |  | Detail Drawing for Tank | Condensate | CONDENSATE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.9297 | 0.9789 | 0.9789 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match |  | condensate | condensate | rule | condensate¦fgp | match | false | 2 | 7 | 18.3030 | 0.5950 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | condensate | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | 2024-04-02 | 2024-05-02 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGF-172521 | CALCULATION OF POTABLE & FIRE FIGHTING WATER TANK FOUNDATION | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 26 | 19 | 17.3424 | 0.5260 | 0.0243 | 0.0182 | hybrid | structured_no_system |  | civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-172522 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank |  |  |  | PLAN & SECTION for Tank |  | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match |  | fire_fighting | fire_fighting | rule | fire_fighting¦hvac | match | false | 1 | 1 | 17.2034 | 0.5782 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGF-172523 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank |  |  |  | Detail Drawing for Tank |  | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match |  | fire_fighting | fire_fighting | rule | fire_fighting¦hvac | match | false | 1 | 1 | 17.2034 | 0.5277 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGD-172541 | CALCULATION OF DEMINERALIZED WATER TANK FOUNDATION | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 1 | 1 | 24.8353 | 0.6177 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGD-172542 | DEMINERALIZED WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank |  |  |  | PLAN & SECTION for Tank |  | DEMINERALIZED WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 24.8353 | 0.6500 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGD-172543 | DEMINERALIZED WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank |  |  |  | Detail Drawing for Tank |  | DEMINERALIZED WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | 2 | 1 | 24.8353 | 0.6172 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGG-172561 | CALCULATION OF POTABLE WATER TANK FOUNDATION | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 12 | 14 | 17.3424 | 0.5337 | 0.0274 | 0.0206 | hybrid | structured_no_system |  | civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGG-172562 | POTABLE WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank |  |  |  | PLAN & SECTION for Tank |  | POTABLE WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | 1 | 5 | 17.3424 | 0.5593 | 0.0318 | 0.0318 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGG-172563 | POTABLE WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank |  |  |  | Detail Drawing for Tank |  | POTABLE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | 1 | 4 | 17.3424 | 0.5141 | 0.0320 | 0.0320 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-172581 | CALCULATION OF GENERAL SERVICE PUMP FOUNDATION | CALCULATION | Pump |  |  |  | Calculation sheet for Pump |  | Transfer Pump Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pump | pump | scoped | match | match | match | passed |  | 0.5000 | 0.6749 | 0.5525 | 0.5525 | FA | 0CF3520W16A04 | (Transfer Pump) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > DFO Tank & Pump | 2007-10-31 | 2007-12-27 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | false | 14 | 34 | 11.9153 | 0.4976 | 0.0242 | 0.0181 | hybrid | structured_no_system |  | civil_design |  | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.90 | 0.80 | usable | activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172582 | GENERAL SERVICE PUMP FOUNDATIONS LAYOUT | LAYOUT | Pump |  |  |  | Layout Drawing for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.9217 | 0.9765 | 0.9765 | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match |  |  |  |  | feedwater | query_unscoped | false | 10 | 20 | 12.2167 | 0.5046 | 0.0268 | 0.0201 | hybrid | structured_no_system |  | civil_design |  | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.90 | 0.80 | usable | activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172583 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (1) | DETAILS (1) | Pump |  |  |  | DETAILS (1) for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (1) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.4000 | 0.6852 | 0.4855 | 0.4855 | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | 8 | 34 | 12.2510 | 0.5110 | 0.0253 | 0.0190 | hybrid | structured_no_system |  | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.90 | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172584 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (2) | DETAILS (2) | Pump |  |  |  | DETAILS (2) for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (2) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.4000 | 0.6882 | 0.4865 | 0.4865 | FA | 2EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | 2007-09-03 | 2008-01-30 | civil_design | civil_design | match |  |  |  |  | ccw | query_unscoped | false | 51 | 1 | 10.2923 | 0.5892 | 0.0254 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172585 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (3) | DETAILS (3) | Pump |  |  |  | DETAILS (3) for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (3) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.4000 | 0.7016 | 0.4905 | 0.4905 | FA | 3EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | 5 | 35 | 13.7151 | 0.4934 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.90 | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAZ-172601 | CALCULATION OF EHV CABLE TRENCH & DIRECT BURIED CABLE | CALCULATION | Cable |  |  |  | Calculation sheet for Cable |  | CALCULATION OF EHV CABLE TRENCH & DIRECT BURIED CABLE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 21 | 4 | 25.3530 | 0.6135 | 0.0280 | 0.0210 | hybrid | structured_no_system |  | civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172602 | EHV CABLE TRENCH & DIRECT BURIED CABLE OVERALL LAYOUT | OVERALL LAYOUT | Cable |  |  |  | OVERALL LAYOUT for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 21 | 4 | 25.3530 | 0.6553 | 0.0280 | 0.0157 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172603 | EHV CABLE TRENCH & DIRECT BURIED CABLE LAYOUT | LAYOUT | Cable |  |  |  | Layout Drawing for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 24 | 4 | 25.3530 | 0.6151 | 0.0275 | 0.0155 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172608 | EHV CABLE TRENCH & DIRECT BURIED CABLE PLAN & SECTION | PLAN & SECTION | Cable |  |  |  | PLAN & SECTION for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 2CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-05-17 | 2008-08-01 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 13 | 32.9909 | 0.5641 | 0.0298 | 0.0168 | hybrid | structured_no_system |  |  |  | 2025-01-03 | 2025-01-18 | 2025-02-02 | 2025-02-17 | 2025-03-19 | 2025-04-18 | generated | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAZ-172613 | EHV CABLE TRENCH & DIRECT BURIED CABLE DETAIL | DETAIL | Cable |  |  |  | Detail Drawing for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 22 | 4 | 25.3530 | 0.6390 | 0.0278 | 0.0156 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZT-172701 | CALCULATION OF ELECTRICAL DUCT BANK MANHOLE | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF ELECTRICAL DUCT BANK MANHOLE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9988 | 0.9996 | 0.9996 | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match |  | electrical | electrical | rule | electrical | match | false | 18 | 3 | 2.5421 | 0.4849 | 0.0287 | 0.0287 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 0.80 | needs_review | rule_scope_status=query_unscoped;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172702 | ELECTRICAL DUCT BANK OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | ELECTRICAL DUCT BANK OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 18 | 11 | 2.5421 | 0.5008 | 0.0269 | 0.0202 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172703 | ELECTRICAL DUCT BANK LAYOUT | LAYOUT |  |  |  |  | Layout Drawing |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9997 | 0.9999 | 0.9999 | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | design_drawing | civil_design | compatible |  | electrical | electrical | rule | electrical | match | false | 4 | 1 | 5.9370 | 0.5378 | 0.0320 | 0.0240 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-172704 | ELECTRICAL DUCT BANK TYPICAL SECTION & R.C DETAILS | [7 empty] | ELECTRICAL DUCT BANK TYPICAL SECTION & R.C DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-08-02 | 2007-12-13 |  | civil_design | query_unknown |  | electrical | electrical | rule | hrsg | mismatch | false | 38 | 3 | 5.7268 | 0.4793 | 0.0261 | 0.0024 | hybrid | structured_no_phase | electrical | [8 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-172713 | ELECTRICAL DUCT BANK MANHOLE SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | ELECTRICAL DUCT BANK MANHOLE SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 3CF1615W64A08 | (HRSG #31 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2008-11-18 | 2009-02-17 |  | installation | query_unknown |  | electrical | electrical | rule | hrsg | mismatch | false | 3 | 7 | 6.2775 | 0.4776 | 0.0308 | 0.0029 | hybrid | structured_no_phase | electrical | [8 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch;activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172716 | ELECTRICAL DUCT BANK MANHOLE PLAN, SECTION & R.C DETAILS | [7 empty] | ELECTRICAL DUCT BANK MANHOLE PLAN, SECTION & R.C DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown |  | electrical | electrical | rule |  | activity_unscoped | true | 4 | 74 | 12.0304 | 0.4451 | 0.0231 | 0.0052 | hybrid | structured_no_phase | electrical | [8 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GUC-172801 | CALCULATION OF STORMWATER POND | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF STORMWATER POND | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF5535W00A15.1 | (WWT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 363 | 1 |  | 0.4244 | 0.0188 | 0.0141 | hybrid | structured_no_system |  | civil_design |  | 2025-02-15 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-05-01 | 2025-05-31 | generated | 0.90 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUC-172802 | CLEAN STORM WATER PONDS OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | CLEAN STORM WATER PONDS OVERALL LAYOUT | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 1 | 24.0608 | 0.5140 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-27 | 2024-11-26 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUC-172803 | CLEAN STORM WATER PONDS PLAN AND SECTION | [7 empty] | CLEAN STORM WATER PONDS PLAN AND SECTION | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | sectional_drawing | sectional_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 |  | system_design | query_unknown | [5 empty] | query_unscoped | true | 6 | 9 | 8.2526 | 0.4960 | 0.0296 | 0.0133 | hybrid | structured_no_system |  |  |  | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GUC-172804 | STORMWATER POND DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | STORMWATER POND DETAIL | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 287 | 1 |  | 0.4881 | 0.0193 | 0.0108 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2025-04-16 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-30 | 2025-07-30 | generated | 0.90 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZA-172901 | CALCULATION OF ROAD AND PAVING | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF ROAD AND PAVING | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 2 | 12.1336 | 0.4913 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172902 | ROAD AND PAVING OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | ROAD AND PAVING OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 1 | 24.0608 | 0.6057 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172903 | ROAD AND PAVING LAYOUT | LAYOUT |  |  |  |  | Layout Drawing |  | ROAD AND PAVING LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 1 | 36.0912 | 0.5549 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172904 | ROAD AND PAVING - GRAVEL PAVEMENT PLAN & SECTION | [7 empty] | ROAD AND PAVING - GRAVEL PAVEMENT PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9998 | 0.9999 | 0.9999 | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 1 | 2 | 12.1336 | 0.5128 | 0.0325 | 0.0146 | hybrid | structured_no_system |  |  |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZA-172908 | ROAD AND PAVING DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | ROAD AND PAVING DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 1 | 12.1336 | 0.5360 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172911 | ROAD MARKING AND SIGN BOARD LAYOUT | LAYOUT |  |  |  |  | Layout Drawing |  | ROAD MARKING AND SIGN BOARD LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 1 | 36.0912 | 0.4991 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZA-172912 | ROAD MARKING AND SIGN BOARD DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | ROAD MARKING AND SIGN BOARD DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 2 | 2 | 12.1336 | 0.4477 | 0.0323 | 0.0145 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZT-173001 | CALCULATION OF LIGHTING POLE FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF LIGHTING POLE FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 5 | 4 | 6.0495 | 0.4546 | 0.0310 | 0.0233 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-173002 | LIGHTING POLE FOUNDATION OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | LIGHTING POLE FOUNDATION OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 1 | 24.0608 | 0.5321 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-173003 | LIGHTING POLE FOUNDATION LAYOUT | LAYOUT |  |  |  |  | Layout Drawing |  | LIGHTING POLE FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 21 | 11 | 3.7797 | 0.4899 | 0.0264 | 0.0198 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-173008 | LIGHTING POLE FOUNDATION PLAN & DETAIL | PLAN & DETAIL |  | Lighting |  |  | PLAN & DETAIL for Lighting |  | LIGHTING POLE FOUNDATION PLAN & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | lighting |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF3040W16A01 | (Lab) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-06-30 | civil_design | civil_design | match |  |  |  |  | lab | query_unscoped | false | 10 | 74 | 2.4624 | 0.4066 | 0.0217 | 0.0163 | hybrid | structured_no_system |  | civil_design |  | 2024-11-17 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-31 | 2025-03-02 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-173101 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS OVERALL LAYOUT | OVERALL LAYOUT |  | Fire Fighting |  |  | OVERALL LAYOUT for Fire Fighting |  | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fighting¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting | wts | fire_fighting | query | fire_fighting¦hvac | match | false | 6 | 3 | 19.5197 | 0.6467 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-173102 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS LAYOUT | LAYOUT |  | Fire Fighting |  |  | Layout Drawing for Fire Fighting |  | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fighting¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting | wts | fire_fighting | query | fire_fighting¦hvac | match | false | 5 | 1 | 22.0055 | 0.6504 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGF-173107 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS |  |  | Fire Fighting |  |  | for Fire Fighting |  | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | firefighting_and_potable_water_pipe_civil_works | firefighting_and_potable_water_pipe_civil_works | fighting¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0CF4500W32A05 | (Fire WTR Pump Shelter) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-10-29 | 2008-02-27 |  |  | query_unknown | fire_fighting | wts | fire_fighting | query | fire_fighting¦hvac | match | false | 10 | 3 | 15.1882 | 0.6254 | 0.0302 | 0.0226 | hybrid | structured_no_phase | fire_fighting |  |  | 2024-06-16 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-30 | 2024-09-29 | generated | 0.90 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZJ-173202 | FENCE AND GATE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FENCE AND GATE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0EF5570W16A10 | (Fence & Gate) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-12-12 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 7 | 2 | 20.4841 | 0.5854 | 0.0311 | 0.0140 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173208 | FENCE AND GATE PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL |  | FENCE AND GATE PLAN AND DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 3 | 14 | 25.6351 | 0.4341 | 0.0294 | 0.0165 | hybrid | structured_no_system |  |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.90 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173209 | INTERNAL FENCE AND GATE PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL |  | INTERNAL FENCE AND GATE PLAN AND DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 3 | 12 | 25.6351 | 0.4394 | 0.0298 | 0.0167 | hybrid | structured_no_system |  |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.90 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GUB-173301 | CALCULATION OF STORMWATER DRAINAGE | CALCULATION |  |  |  |  | Calculation sheet |  | CALCULATION OF STORMWATER POND | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8106 | 0.7682 | 0.7682 | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 95 | 12 | 3.6223 | 0.4085 | 0.0203 | 0.0153 | hybrid | structured_no_system |  | civil_design |  | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-25 | 2024-12-25 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUB-173302 | STORMWATER DRAINAGE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT | Fire Fighting System | STORMWATER DRAINAGE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5714 | 0.8345 | 0.6503 | 0.6503 | FA | 0EF3520W00A01.3 | (Foam Station BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Foam Station Building | 2007-05-01 |  | design_drawing | civil_design | compatible |  | fire_fighting | fire_fighting | rule | fgp¦fire_fighting | match | false | 1 | 1 |  | 0.4324 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUB-173303 | STORMWATER DRAINAGE LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.8168 | 0.5951 | 0.5951 | FA | 0EF3520W00A01.3 | (Foam Station BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Foam Station Building | 2007-05-01 |  | design_drawing | civil_design | compatible |  | fire_fighting | fire_fighting | rule | fgp¦fire_fighting | match | false | 1 | 2 | 3.5896 | 0.4315 | 0.0325 | 0.0244 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GUB-173313 | STORMWATER DRAINAGE STRUCTURAL DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | STORMWATER POND DETAIL | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8110 | 0.7100 | 0.7100 | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 287 | 4 |  | 0.5134 | 0.0185 | 0.0104 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2025-04-16 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-30 | 2025-07-30 | generated | 0.90 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GQB-173401 | CALCULATION OF WASTE WATER DRAINAGE OVERALL LAYOUT | CALCULATION OF OVERALL LAYOUT |  |  |  |  | CALCULATION OF OVERALL LAYOUT | Fire Fighting System | CALCULATION OF WASTE WATER DRAINAGE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.7000 | 0.8575 | 0.7473 | 0.7473 | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match |  | fire_fighting¦wts | fire_fighting¦wts | rule | wts | match | false | 4 | 1 | 12.4279 | 0.5205 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.80 | needs_review | rule_scope_status=query_unscoped;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173402 | WASTE WATER DRAINAGE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT | Fire Fighting System | WASTE WATER DRAINAGE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6250 | 0.8369 | 0.6886 | 0.6886 | FA | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | design_drawing | civil_design | compatible |  | fire_fighting¦wts | fire_fighting¦wts | rule | wts | match | false | 1 | 3 | 12.7969 | 0.5670 | 0.0323 | 0.0242 | hybrid | structured_preferred | fire_fighting¦wts | system_design¦civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173403 | WASTE WATER DRAINAGE LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5714 | 0.8165 | 0.6449 | 0.6449 | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | design_drawing | civil_design | compatible |  | fire_fighting¦wts | fire_fighting¦wts | rule | wts | match | false | 4 | 1 | 15.9172 | 0.6393 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173413 | WASTE WATER DRAINAGE MANHOLE SCHEDULE | SCHEDULE |  |  |  |  | Schedule | Fire Fighting System | WASTE WATER DRAINAGE MANHOLE SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 0.6250 | 0.8542 | 0.6938 | 0.6938 | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  | civil_design | query_unknown |  | fire_fighting¦wts | fire_fighting¦wts | rule | wts | match | false | 10 | 4 | 12.4283 | 0.4997 | 0.0299 | 0.0224 | hybrid | structured_no_phase | fire_fighting¦wts |  |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.60 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GQB-173417 | WASTE WATER DRAINAGE STRUCTURE MANHOLE RE-BAR DETAIL | DETAIL |  |  |  |  | Detail Drawing | Fire Fighting System | WASTE WATER DRAINAGE STRUCTURE MANHOLE RE-BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.7273 | 0.8324 | 0.7588 | 0.7588 | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match |  | fire_fighting¦wts | fire_fighting¦wts | rule | wts | match | false | 5 | 2 | 12.4279 | 0.4667 | 0.0315 | 0.0315 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 0.80 | needs_review | rule_scope_status=query_unscoped;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZK-173501 | LANDSCAPE LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6252 | 0.5376 | 0.5376 | SKIP | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 17 | 7 | 3.7797 | 0.4337 | 0.0279 | 0.0157 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173502 | LANDSCAPING CROSS SECTION & DETAIL | & DETAIL |  |  |  |  | & DETAIL |  | Arrangement Section & Detail | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | generic | match | match | query_unscoped | passed |  | 0.6667 | 0.5582 | 0.6341 | 0.4439 | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 |  | installation | query_unknown | [5 empty] | query_unscoped | true | 1 | 5 | 25.7245 | 0.4175 | 0.0318 | 0.0143 | hybrid | structured_no_system | [9 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173503 | WATER TANK SECTION & DETAIL | SECTION & DETAIL |  |  |  |  | SECTION & DETAIL for Tank |  | POTABLE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.6601 | 0.5480 | 0.5480 | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown |  | wts | wts | rule | wts | match | false | 2 | 6 | 9.5384 | 0.5003 | 0.0313 | 0.0235 | hybrid | structured_no_phase | wts |  |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173504 | PAVILION PLAN & DETAIL | PLAN & DETAIL |  |  |  |  | PLAN & DETAIL |  | FENCE AND GATE PLAN AND DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.6382 | 0.4715 | 0.4715 | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | 2 | 2 | 24.0608 | 0.4649 | 0.0323 | 0.0145 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173505 | PUMP ROOM PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL for Pump |  | Pump Pit Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7546 | 0.6930 | 0.5891 | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 10 | 8 | 9.5086 | 0.5058 | 0.0290 | 0.0163 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.60 | 0.60 | usable | activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GKC-173601 | CALCULATION OF CHILLED WATER STORAGE TANK FOUNDATION | CALCULATION | CHILLED WATER STORAGE TANK |  |  |  | Calculation sheet for CHILLED WATER STORAGE TANK | Condensate | CALCULATION OF CONDENSATE WATER TANK FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | chilled¦storage¦tank¦water | tank | scoped | match | match | match | passed |  | 0.5000 | 0.6598 | 0.5479 | 0.5479 | FA | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match |  | condensate | condensate | rule | condensate | match | false | 5 | 1 | 2.1802 | 0.5166 | 0.0318 | 0.0318 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GKC-173602 | CHILLED WATER STORAGE TANK FOUNDATION DETAIL | DETAIL | CHILLED WATER STORAGE TANK |  |  |  | Detail Drawing for Tank |  | POTABLE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7611 | 0.6950 | 0.6950 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | 1 | 1 | 43.2088 | 0.5449 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GKC-173702 | POTABLE WATER CHILLER FOUNDATION DETAIL | DETAIL | POTABLE WATER CHILLER |  |  |  | Detail Drawing for POTABLE WATER CHILLER |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | chiller¦potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5643 | 0.6360 | 0.6360 | FA | 0EF3035W16A14 | (PWT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-11-02 | 2008-03-04 | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 4 | 1 | 25.8493 | 0.5883 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GHC-173801 | CALCULATION OF ATM FLASH TANK & DRAIN PUMP PIT | CALCULATION | FLASH TANK, Pump |  |  |  | Calculation sheet for FLASH TANK, Pump |  | Flash tank calculation | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | flash¦pump¦tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.6847 | 0.9054 | 0.6338 | FA | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-02-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 11 | 2 | 20.1740 | 0.5713 | 0.0302 | 0.0181 | hybrid | structured_no_system |  | civil_design |  | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GHC-173802 | ATM FLASH TANK & DRAIN PUMP PIT DETAIL | DETAIL | FLASH TANK, Pump |  |  |  | Detail Drawing for Tank |  | Pump Pit Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | pump¦tank | pump | scoped | match | match | match | passed |  | 1.0000 | 0.6761 | 0.9028 | 0.7674 | FA | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-02-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 12 | 3 | 20.1740 | 0.5816 | 0.0298 | 0.0134 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.60 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZJ-173902 | POWER PLANT DIESEL GENERATOR FOUNDATION PLAN | PLAN | DIESEL GENERATOR |  |  |  | Plan for DIESEL GENERATOR |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6940 | 0.7332 | 0.7332 | FA | 1EF3530W16A02 | (Block #1 EDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-10-29 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 11 | 1 | 15.4653 | 0.6124 | 0.0305 | 0.0229 | hybrid | structured_no_system |  | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173903 | POWER PLANT DIESEL GENERATOR FOUNDATION REINF. DETAIL | DETAIL | DIESEL GENERATOR |  |  |  | Detail Drawing for DIESEL GENERATOR |  | Chlorination Plant FOUNDATION REINF. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7080 | 0.7724 | 0.7724 | FA | 1EF3530W16A02 | (Block #1 EDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-10-29 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 10 | 3 | 15.4653 | 0.6156 | 0.0302 | 0.0226 | hybrid | structured_no_system |  | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180001 | STANDARD DRAWING - GENERAL NOTES, ABBREVIATION, LEGEND & SIMBOLS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 58 | 2 | 3.4917 | 0.4700 | 0.0246 | 0.0138 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180002 | STANDARD DRAWING - INTERIOR FINISH DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | INTERIOR finish DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7798 | 0.9339 | 0.9339 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 975 | 2 | 0.0004 | 0.4534 | 0.0171 | 0.0096 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180006 | STANDARD DRAWING - CLADDING JOINT DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | CLADDING JOINT DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8762 | 0.9629 | 0.9629 | FI | 1EF1615W00A01 | (HRSG #11 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-04-30 |  | design_drawing | civil_design | compatible |  |  |  |  | hrsg | query_unscoped | false | 2797 | 6 | 0.0003 | 0.3903 | 0.0155 | 0.0087 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180008 | STANDARD DRAWING - MISC. ARCHITECTURAL DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | MISC. ARCHITECTURAL DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8136 | 0.9441 | 0.9441 | FI | 1CF3520W16A01 | (FGSS #11) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | false | 2 | 356 | 9.1821 | 0.3573 | 0.0185 | 0.0139 | hybrid | structured_no_system |  | civil_design |  | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 | 0.49 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180019 | STANDARD DRAWING - DOOR SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | DOOR SCHEDULE | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8450 | 0.7202 | 0.7202 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 945 | 1 | 0.0005 | 0.4172 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180020 | STANDARD DRAWING - DOOR DETAILS | DETAILS |  |  |  |  | DETAILS |  | DOOR DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7779 | 0.7000 | 0.7000 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 945 | 1 | 0.0002 | 0.3907 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180024 | STANDARD DRAWING - WINDOW SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | WINDOW SCHEDULE | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8000 | 0.7067 | 0.7067 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 945 | 1 | 0.0005 | 0.4272 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180025 | STANDARD DRAWING - WINDOW DETAILS | DETAILS |  |  |  |  | DETAILS |  | WINDOW DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6694 | 0.6675 | 0.6675 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 945 | 1 | 0.0002 | 0.4099 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180030 | STANDARD DRAWING - RE - BAR STANDARD | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | FA | 0EF3040W16A01 | (Lab) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-06-30 | design_drawing | civil_design | compatible |  |  |  |  | lab | query_unscoped | false | 15 | 172 | 0.0006 | 0.3666 | 0.0176 | 0.0099 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-11-17 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-31 | 2025-03-02 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180033 | STANDARD DRAWING - GENERAL NOTES, MATERIALS, CONNECTIONS & MEMBER SIZE DESIGNATION | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 69 | 1 | 3.3596 | 0.5123 | 0.0241 | 0.0136 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180034 | STANDARD DRAWING - ABBREVIATIONS & WELDING | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 23 | 24 | 0.0004 | 0.4189 | 0.0240 | 0.0108 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180035 | STANDARD DRAWING - MOMENT CONNECTION DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | MOMENT CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8474 | 0.9542 | 0.9542 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 582 | 4 | 0.0004 | 0.4109 | 0.0172 | 0.0097 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180036 | STANDARD DRAWING - SHEAR CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | SHEAR CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8745 | 0.9624 | 0.9624 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 582 | 4 | 0.0002 | 0.4412 | 0.0172 | 0.0097 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180037 | STANDARD DRAWING - TYPICAL VERTICAL & HORIZONTAL BRACING CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL VERTICAL & HORIZONTAL BRACING CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9244 | 0.9773 | 0.9773 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 582 | 4 | 0.0002 | 0.4587 | 0.0172 | 0.0097 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180038 | STANDARD DRAWING - TYPICAL STAIR & HANDRAIL DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL STAIR & HANDRAIL DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9183 | 0.9755 | 0.9755 | FI | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 1667 | 1 | 0.0002 | 0.4407 | 0.0170 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180039 | STANDARD DRAWING - TYPICAL STAIR STRINGER CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL STAIR STRINGER CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9084 | 0.9725 | 0.9725 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 582 | 1 | 0.0002 | 0.4129 | 0.0180 | 0.0101 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180040 | STANDARD DRAWING - GIRTH & PURLIN CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | GIRTH & PURLIN CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8707 | 0.9612 | 0.9612 | FI | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 1759 | 1 | 0.0002 | 0.4874 | 0.0169 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180041 | STANDARD DRAWING - TYPICAL GRATING AND CHK'D PLATE DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL GRATING AND CHK'D PLATE DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9039 | 0.9712 | 0.9712 | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 2 | 473 | 4.2194 | 0.3388 | 0.0180 | 0.0101 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180042 | STANDARD DRAWING - LADDER DETAILS | DRAWING |  |  |  |  | DRAWING |  | LADDER DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7976 | 0.7059 | 0.7059 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | 576 | 5 | 0.0002 | 0.4532 | 0.0170 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180043 | STANDARD DRAWING - PLUMBING STANDARD SYMBOL & ABBREVIATION | DRAWING |  |  |  |  | DRAWING |  | PLUMBING ISO DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7911 | 0.7040 | 0.4928 | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 23 | 15 | 0.0004 | 0.4761 | 0.0254 | 0.0114 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180044 | STANDARD DRAWING - PLUMBING STANDARD GENERAL DETAILS | DRAWING |  |  |  |  | DRAWING |  | PLUMBING STANDARD GENERAL DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9316 | 0.9795 | 0.9795 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 58 | 1 | 3.4917 | 0.5458 | 0.0249 | 0.0140 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 0.43 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180401 | ST BUILDING - GROUND FLOOR PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  |  | civil_design | query_unknown | stg | stg | stg | query | stg | match | false | 186 | 6 | 3.9005 | 0.5052 | 0.0192 | 0.0144 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.64 | fi_complete | activity_phase_status=query_unknown;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180402 | ST BUILDING - ROOF PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | stg | stg | stg | query | stg | match | false | 4 | 1 | 13.7004 | 0.5453 | 0.0320 | 0.0240 | hybrid | structured_no_phase | stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180403 | ST BUILDING - ELEVATION | ELEVATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Elevation Drawing for ST BUILDING ¦ Steam Turbine BUILDING |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6143 | 0.6509 | 0.4557 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 12 | 1 | 3.9005 | 0.5386 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180404 | ST BUILDING - SECTION | SECTION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | SECTION for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.7832 | 0.9349 | 0.9349 | FI | 3EF2010W20A02 | (STG #30 BLDG) Buliding Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 | 2007-09-18 |  |  | query_unknown | stg | stg | stg | query | stg | match | false | 119 | 2 | 4.0527 | 0.5199 | 0.0217 | 0.0163 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180405 | ST BUILDING - INTERIOR FINISH SCHEDULE | SCHEDULE |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Schedule for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6881 | 0.7314 | 0.7314 | FI | 0CF5566W24A10 | (ADMIN BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-04-30 | 2008-07-29 |  |  | query_unknown | stg | stg | stg | query |  | activity_unscoped | true | 1 | 2 | 11.9072 | 0.5008 | 0.0325 | 0.0146 | hybrid | structured_no_phase | stg |  |  | 2025-09-28 | 2025-10-28 | 2025-11-27 | 2025-12-12 | 2025-12-27 | 2026-01-11 | generated | 0.90 | 0.43 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180406 | ST BUILDING - DOOR SCHEDULE | SCHEDULE |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Schedule for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6881 | 0.7314 | 0.7314 | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  |  | civil_design | query_unknown | stg | stg | stg | query | stg | match | false | 177 | 2 | 3.9008 | 0.4758 | 0.0203 | 0.0153 | hybrid | structured_no_phase | stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180408 | ST BUILDING - WALL SECTION | SECTION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | SECTION for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.7832 | 0.9349 | 0.9349 | FI | 3CF2010W20A07 | (STG #30 BLDG) Cladding Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-06-25 | 2008-11-11 |  |  | query_unknown | stg | stg | stg | query | stg | match | false | 122 | 2 | 4.0527 | 0.4794 | 0.0216 | 0.0162 | hybrid | structured_no_phase | stg | [5 empty] | 2025-03-28 | 2025-04-27 | 2025-05-27 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180451 | ST BUILDING - PILE ARRANGEMENT | ARRANGEMENT |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | ARRANGEMENT for ST BUILDING ¦ Steam Turbine BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4603 | 0.3714 | 0.3157 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 4 | 3 | 11.0757 | 0.5671 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180452 | ST BUILDING - FOUNDATION LOCATION PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 4 | 6.6342 | 0.4886 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180454 | ST BUILDING - PILE CAP & FOUNDATION REINFORCEMENT DETAIL | DETAIL |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Detail Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6758 | 0.6227 | 0.6227 | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 3 | 1 | 11.0757 | 0.5457 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180458 | ST BUILDING - COLUMN LOCATION PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  |  | civil_design | query_unknown | stg | stg | stg | query | stg | match | false | 180 | 4 | 3.9005 | 0.5164 | 0.0198 | 0.0148 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.64 | fi_complete | activity_phase_status=query_unknown;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180459 | ST BUILDING - BASE PLATE DETAIL | DETAIL |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Detail Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6758 | 0.6227 | 0.6227 | FA | 1CF2010W16A03 | (STG #10 BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-11-02 | 2008-03-03 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 7 | 5 | 4.0527 | 0.4658 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180460 | ST BUILDING - CRANE GIRDER FRAMING PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 |  | installation | query_unknown | stg | stg | stg | query | crane_hoist¦stg | match | false | 6 | 1 | 14.9608 | 0.5918 | 0.0315 | 0.0237 | hybrid | structured_no_phase | stg | [5 empty] | 2025-04-19 | 2025-05-19 | 2025-06-18 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180462 | ST BUILDING - ROOF FRAMING PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | stg | stg | stg | query | stg | match | false | 4 | 1 | 13.7004 | 0.4897 | 0.0320 | 0.0240 | hybrid | structured_no_phase | stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180463 | ST BUILDING - FRAMING ELEVATION | ELEVATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Elevation Drawing for ST BUILDING ¦ Steam Turbine BUILDING |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6143 | 0.6509 | 0.4557 | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 11 | 1 | 3.9005 | 0.5139 | 0.0305 | 0.0305 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180464 | ST BUILDING - GIRT NORTH - SOUTH ELEVATION | ELEVATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Elevation Drawing for ST BUILDING ¦ Steam Turbine BUILDING |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6143 | 0.6509 | 0.4557 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 12 | 1 | 3.9005 | 0.5299 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180465 | ST BUILDING - GIRT EAST - WEST ELEVATION | ELEVATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Elevation Drawing for ST BUILDING ¦ Steam Turbine BUILDING |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6143 | 0.6509 | 0.4557 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | false | 12 | 1 | 3.9005 | 0.5282 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180466 | ST BUILDING - MISC. PLATFORM PLAN & SECTION | PLAN & SECTION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | PLAN & SECTION for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.7174 | 0.9152 | 0.9152 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  |  | civil_design | query_unknown | stg | stg | stg | query | stg | match | false | 186 | 3 | 3.9005 | 0.5117 | 0.0199 | 0.0150 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.64 | fi_complete | activity_phase_status=query_unknown;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180467 | ST BUILDING - STAIR PLAN, ELEVATION & DETAIL | PLAN, ELEVATION & DETAIL |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | PLAN, ELEVATION & DETAIL for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - STAIR PLAN, ELEVATION & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.8333 | 0.7656 | 0.8130 | 0.8130 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  |  | civil_design | query_unknown | stg | stg | stg | query | stg | match | false | 181 | 2 | 3.9005 | 0.4641 | 0.0203 | 0.0152 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180468 | ST BUILDING – MAIN TRUSS DETAIL | DETAIL |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Detail Drawing for ST BUILDING ¦ Steam Turbine BUILDING | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6758 | 0.6227 | 0.6227 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 12 | 1 | 3.9005 | 0.4918 | 0.0303 | 0.0303 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180469 | ST BUILDING - ROOF WALKWAY FRAMING PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | stg | stg | stg | query | stg | match | false | 4 | 1 | 13.7004 | 0.5094 | 0.0320 | 0.0240 | hybrid | structured_no_phase | stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180471 | ST BUILDING - ROOF PURLIN PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown | stg | stg | stg | query | stg | match | false | 5 | 5 | 13.7004 | 0.4772 | 0.0308 | 0.0231 | hybrid | structured_no_phase | stg | [5 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UMA-180481 | ST BUILDING - EQUIPMENT DRAIN PLAN | PLAN |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Plan for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6996 | 0.7349 | 0.7349 | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  | civil_design | query_unknown | stg | stg | stg | query |  | activity_unscoped | true | 5 | 58 | 8.3123 | 0.5016 | 0.0239 | 0.0107 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UMA-180482 | ST BUILDING - EQUIPMENT DRAIN PLAN (ISO) | PLAN (ISO) |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | PLAN (ISO) for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.6903 | 0.7321 | 0.7321 | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | stg | stg | stg | query |  | activity_unscoped | true | 1 | 97 | 24.0608 | 0.4831 | 0.0228 | 0.0102 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180490 | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Calculation sheet for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | design_calculation | design_calculation | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.6811 | 0.6710 | 0.6710 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 5 | 9.9595 | 0.5018 | 0.0318 | 0.0318 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180491 | ST BUILDING - DESIGN CALCULATION FOR BASE PLATE, COLUMN, BEAM & ROOF TRUSS | CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Calculation sheet for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | design_calculation | design_calculation | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.6811 | 0.6710 | 0.6710 | FI | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 6 | 1 | 6.9759 | 0.5168 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180492 | ST BUILDING - DESIGN CALCULATION FOR CRANE GIRDER, PURLIN & SIDE GIRT | CALCULATION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | Calculation sheet for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | design_calculation | design_calculation | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.6811 | 0.6710 | 0.6710 | FI | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 6 | 1 | 6.9759 | 0.5387 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0BAT-180500 | ROOF FOR GTG TR - CALCULATION | CALCULATION | GTG TR ¦ Gas Turbine Generator Transformer |  |  |  | Calculation sheet for GTG TR ¦ Gas Turbine Generator Transformer |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦transformer¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5783 | 0.6402 | 0.6402 | FI | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat¦gtg | gtg | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 7 | 2 | 18.9833 | 0.7198 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | gsut_uat¦gtg | civil_design |  |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180500 | ST BUILDING_MISC. PLATFORM PLAN & SECTION | PLAN & SECTION |  |  | ST BUILDING ¦ Steam Turbine BUILDING |  | PLAN & SECTION for ST BUILDING ¦ Steam Turbine BUILDING | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.7174 | 0.9152 | 0.9152 | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  |  | civil_design | query_unknown | stg | stg | stg | query | stg | match | false | 186 | 6 | 3.9005 | 0.4789 | 0.0192 | 0.0144 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.64 | fi_complete | activity_phase_status=query_unknown;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P1BAT-180511 | ROOF FOR GTG #1 TR - PLAN, SECTION, ELEVATION | PLAN, SECTION, ELEVATION | GTG #1 TR ¦ Gas Turbine Generator #1 Transformer |  |  |  | PLAN, SECTION, ELEVATION for GTG |  | PLAN, SECTION, ELEVATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7867 | 0.9360 | 0.6552 | FA | 1CF6500W70A06 | (GTG TR) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-05-31 | 2008-07-16 |  | installation | query_unknown | gsut_uat¦gtg |  | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 2 | 1 | 24.0745 | 0.7397 | 0.0325 | 0.0244 | hybrid | structured_no_phase | gsut_uat¦gtg |  |  | 2025-01-17 | 2025-02-01 | 2025-02-16 | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.30 | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P1BAT-180512 | ROOF FOR GTG #1 TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | PLAN, BASEPLATE DETAILS | GTG #1 TR ¦ Gas Turbine Generator #1 Transformer |  |  |  | PLAN, BASEPLATE DETAILS for GTG | SUPPORT BUILDING | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4444 | 0.6523 | 0.5068 | 0.5068 | FI | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 |  | civil_design | query_unknown | gsut_uat¦gtg |  | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 9 | 3 | 23.7828 | 0.7343 | 0.0304 | 0.0228 | hybrid | structured_no_phase | gsut_uat¦gtg | [5 empty] | 2024-05-04 | 2024-06-03 | 2024-07-03 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P1BAT-180513 | ROOF FOR GTG #1 TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | Drawing | GTG #1 TR ¦ Gas Turbine Generator #1 Transformer |  |  |  | Drawing for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5044 | 0.2913 | 0.2913 | FI | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat¦gtg | gtg | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | false | 1 | 2 | 23.7828 | 0.7262 | 0.0325 | 0.0325 | hybrid | structured_preferred | gsut_uat¦gtg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UCB-180600 | CENTRAL CONTROL BUILDING - CALCULATION | CALCULATION |  |  | CENTRAL CONTROL BUILDING |  | Calculation sheet for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | ccr¦central | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.8628 | 0.9588 | 0.9588 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 3 | 18.3850 | 0.6093 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180601 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 10 | 17.4405 | 0.6164 | 0.0280 | 0.0157 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180602 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 10 | 17.4405 | 0.6154 | 0.0280 | 0.0157 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180603 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 8 | 17.4405 | 0.6124 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180604 | CENTRAL CONTROL BUILDING - ROOF PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 12 | 8 | 17.4405 | 0.5971 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180605 | CENTRAL CONTROL BUILDING - SIDE WALL ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5077 | 0.5023 | 0.5023 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 4 | 18.3850 | 0.5955 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180606 | CENTRAL CONTROL BUILDING - MAIN SECTION | SECTION |  |  | CENTRAL CONTROL BUILDING |  | SECTION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8679 | 0.8204 | 0.8204 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 11 | 9 | 17.4405 | 0.6223 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180607 | CENTRAL CONTROL BUILDING - INTERIOR FINISH SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7724 | 0.6984 | 0.6984 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 8 | 17.4408 | 0.5762 | 0.0290 | 0.0163 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180608 | CENTRAL CONTROL BUILDING - DOOR & WINDOW SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7724 | 0.6984 | 0.6984 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 8 | 17.4408 | 0.5255 | 0.0290 | 0.0163 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180609 | CENTRAL CONTROL BUILDING - STAIRCASE#1 ENLARGED PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 8 | 17.4405 | 0.5229 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180610 | CENTRAL CONTROL BUILDING - STAIRCASE#2 ENLARGED PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 8 | 17.4405 | 0.5281 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180611 | CENTRAL CONTROL BUILDING - ENLARGED TOILET PLAN & ELEVATION | PLAN & ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | PLAN & ELEVATION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8467 | 0.8140 | 0.8140 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 12 | 10 | 17.4405 | 0.5184 | 0.0282 | 0.0158 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180612 | CENTRAL CONTROL BUILDING - WALL OPENING ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5077 | 0.5023 | 0.5023 | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 3 | 3 | 18.3850 | 0.5855 | 0.0317 | 0.0190 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180613 | CENTRAL CONTROL BUILDING - CEILING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 12 | 8 | 17.4405 | 0.5894 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180614 | CENTRAL CONTROL BUILDING - MISC. DETAIL | DETAIL |  |  | CENTRAL CONTROL BUILDING |  | Detail Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8173 | 0.8052 | 0.8052 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 3 | 4 | 18.3850 | 0.6304 | 0.0315 | 0.0189 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180651 | CENTRAL CONTROL BUILDING - FDN & COLUMN ARRANGEMENT PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 4 | 1 | 20.6978 | 0.7055 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180652 | CENTRAL CONTROL BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 10 | 17.4405 | 0.5732 | 0.0280 | 0.0157 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180653 | CENTRAL CONTROL BUILDING - 1ST FLOOR FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 9 | 17.4405 | 0.5629 | 0.0282 | 0.0159 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180654 | CENTRAL CONTROL BUILDING - 2ND FLOOR FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 8 | 17.4405 | 0.5610 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180655 | CENTRAL CONTROL BUILDING - ROOF FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 12 | 9 | 17.4405 | 0.5349 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180656 | CENTRAL CONTROL BUILDING - LINE FRAMING ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5077 | 0.5023 | 0.5023 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 4 | 18.3850 | 0.6142 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180657 | CENTRAL CONTROL BUILDING - ROW FRAMING ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5077 | 0.5023 | 0.5023 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 4 | 18.3850 | 0.5947 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180658 | CENTRAL CONTROL BUILDING - STAIRCASE#1 FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | PLAN & ELEVATION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8467 | 0.8140 | 0.8140 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 11 | 17.4405 | 0.4941 | 0.0278 | 0.0156 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180659 | CENTRAL CONTROL BUILDING - STAIRCASE#2 FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | PLAN & ELEVATION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8467 | 0.8140 | 0.8140 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 13 | 17.4405 | 0.4947 | 0.0274 | 0.0154 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180660 | CENTRAL CONTROL BUILDING - 1ST FLOOR OPENING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 8 | 17.4405 | 0.5904 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180661 | CENTRAL CONTROL BUILDING - 2ND FLOOR OPENING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 8 | 17.4405 | 0.5835 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180664 | CENTRAL CONTROL BUILDING - FOUNDATION RE - BAR DETAIL |  |  |  | CENTRAL CONTROL BUILDING |  | for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6000 | 0.8201 | 0.6660 | 0.6660 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 1 | 20.6978 | 0.6586 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180665 | CENTRAL CONTROL BUILDING - COLUMN RE - BAR SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7724 | 0.6984 | 0.6984 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 9 | 17.4408 | 0.5707 | 0.0288 | 0.0162 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180666 | CENTRAL CONTROL BUILDING - BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7724 | 0.6984 | 0.6984 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 10 | 17.4408 | 0.5210 | 0.0286 | 0.0161 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180667 | CENTRAL CONTROL BUILDING - SLAB & MISC. RE - BAR SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7724 | 0.6984 | 0.6984 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 11 | 17.4408 | 0.5191 | 0.0284 | 0.0160 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180668 | CENTRAL CONTROL BUILDING - STRUCTURAL MISC. DETAIL | DETAIL |  |  | CENTRAL CONTROL BUILDING |  | Detail Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8173 | 0.8052 | 0.8052 | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 4 | 1 | 18.3850 | 0.6323 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180681 | CENTRAL CONTROL BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7724 | 0.6984 | 0.6984 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 1 | 21.1421 | 0.5843 | 0.0307 | 0.0173 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180682 | CENTRAL CONTROL BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | CENTRAL CONTROL BUILDING |  | Diagram for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7681 | 0.6971 | 0.6971 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 1 | 18.3850 | 0.5973 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | system_design¦engineering |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180683 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 7 | 17.4405 | 0.6012 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180684 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 6 | 17.4405 | 0.5924 | 0.0289 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180685 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 13 | 6 | 17.4405 | 0.5884 | 0.0289 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180686 | CENTRAL CONTROL BUILDING - ROOF PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 12 | 6 | 17.4405 | 0.5798 | 0.0290 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180687 | CENTRAL CONTROL BUILDING - ENLARGED TOILET & SHOWER PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8309 | 0.8093 | 0.8093 | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 12 | 8 | 17.4405 | 0.5454 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181000 | ST #1 LEB - CALCULATION | CALCULATION | ST #1 ¦ Steam Turbine #1 |  | LEB ¦ Local Electrical Building |  | Calculation sheet for ST #1 ¦ Steam Turbine #1 |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.5755 | 0.6393 | 0.6393 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 1 | 2 | 17.5437 | 0.5953 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181001 | ST #1 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) ¦ PLAN & INTERIOR FINISH SCHEDULE(Including DOOR & WINDOW) | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) ¦ PLAN & INTERIOR FINISH SCHEDULE(Including DOOR & WINDOW) for ST ¦ Steam Turbine | ST BUILDING | ST BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.8000 | 0.7099 | 0.7730 | 0.7730 | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 57 | 19 | 18.1332 | 0.5825 | 0.0212 | 0.0159 | hybrid | structured_no_phase | electrical¦stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181002 | ST #1 LEB - ROOF PLAN | PLAN | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Plan for #1 LEB ¦ #1 Local Electrical Building |  | ST #1 LEB - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 9 | 2 | 15.3806 | 0.6545 | 0.0306 | 0.0230 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181003 | ST #1 LEB - SIDE WALL ELEVATION | ELEVATION | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Elevation Drawing for #1 LEB ¦ #1 Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5348 | 0.8604 | 0.6023 | FA | 3EF2020W16A06 | (ST #30) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 5 | 2 | 13.5371 | 0.6085 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181004 | ST #1 LEB - MAIN SECTION | MAIN SECTION | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | MAIN SECTION for #1 LEB ¦ #1 Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6681 | 0.7604 | 0.7604 | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 1 | 6 | 18.1326 | 0.6498 | 0.0315 | 0.0237 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181005 | ST #1 LEB - ARCHITECTURAL MISC. DETAIL | DETAIL | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Detail Drawing for #1 LEB ¦ #1 Local Electrical Building |  | ST #1 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 1 | 9 | 14.8726 | 0.5950 | 0.0309 | 0.0309 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181051 | ST #1 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Plan for #1 LEB ¦ #1 Local Electrical Building |  | ST #1 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 5 | 1 | 17.1077 | 0.7072 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181052 | ST #1 LEB - GROUND FLOOR FRAMING PLAN | PLAN | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Plan for #1 LEB ¦ #1 Local Electrical Building |  | ST #1 LEB - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  | civil_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 11 | 5 | 14.8726 | 0.6426 | 0.0295 | 0.0221 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181053 | ST #1 LEB - ROOF FLOOR FRAMING PLAN | PLAN | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Plan for #1 LEB ¦ #1 Local Electrical Building |  | ST #1 LEB - ROOF FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 9 | 2 | 15.3806 | 0.6399 | 0.0306 | 0.0230 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181054 | ST #1 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Elevation Drawing for #1 LEB ¦ #1 Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5348 | 0.8604 | 0.6023 | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 1 | 9 | 14.8726 | 0.6099 | 0.0309 | 0.0309 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181055 | ST #1 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Detail Drawing for #1 LEB ¦ #1 Local Electrical Building |  | ST #1 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 7 | 1 | 17.1077 | 0.6598 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181056 | ST #1 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE | ST ¦ Steam Turbine |  | #1 LEB ¦ #1 Local Electrical Building |  | Schedule for ST ¦ Steam Turbine | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5434 | 0.5130 | 0.5130 | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 1 | 7 | 18.1330 | 0.6117 | 0.0313 | 0.0235 | hybrid | structured_no_phase | electrical¦stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181100 | ST #2 LEB - CALCULATION | CALCULATION | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | Calculation sheet for ST ¦ Steam Turbine |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.5423 | 0.6294 | 0.6294 | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 1 | 3 | 15.4583 | 0.5753 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181101 | ST #2 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) ¦ PLAN & INTERIOR FINISH SCHEDULE(Including DOOR & WINDOW) | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) ¦ PLAN & INTERIOR FINISH SCHEDULE(Including DOOR & WINDOW) for ST ¦ Steam Turbine | ST BUILDING | ST BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.8000 | 0.7099 | 0.7730 | 0.7730 | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 59 | 18 | 16.8205 | 0.5810 | 0.0212 | 0.0159 | hybrid | structured_no_phase | electrical¦stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181102 | ST #2 LEB - ROOF PLAN | PLAN | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | Plan for #2 LEB ¦ #2 Local Electrical Building |  | ST #2 LEB - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 9 | 3 | 15.9498 | 0.6461 | 0.0304 | 0.0228 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181103 | ST #2 LEB - SIDE WALL ELEVATION | ELEVATION | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | Elevation Drawing for #2 LEB ¦ #2 Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5128 | 0.8538 | 0.5977 | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 1 | 8 | 15.4583 | 0.5943 | 0.0311 | 0.0311 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181104 | ST #2 LEB - MAIN SECTION | MAIN SECTION | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | MAIN SECTION for #2 LEB ¦ #2 Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6915 | 0.7674 | 0.7674 | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 3 | 3 | 16.8199 | 0.6414 | 0.0317 | 0.0238 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181105 | ST #2 LEB - ARCHITECTURAL MISC. DETAIL | DETAIL | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | Detail Drawing for #2 LEB ¦ #2 Local Electrical Building |  | ST #2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 1 | 7 | 15.4583 | 0.5997 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181151 | ST #2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | Plan for #2 LEB ¦ #2 Local Electrical Building |  | ST #2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 5 | 1 | 17.6935 | 0.7059 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181152 | ST #2 LEB - GROUND FLOOR FRAMING PLAN | PLAN | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | Plan for #2 LEB ¦ #2 Local Electrical Building |  | ST #2 LEB - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 |  | civil_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 11 | 4 | 15.4583 | 0.6470 | 0.0297 | 0.0223 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181153 | ST #2 LEB - ROOF FLOOR FRAMING PLAN | PLAN | ST ¦ Steam Turbine |  | #2 LEB ¦ #2 Local Electrical Building |  | Plan for #2 LEB ¦ #2 Local Electrical Building |  | ST #2 LEB - ROOF FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 9 | 1 | 15.9498 | 0.6400 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181154 | ST #2 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION | ST ¦ Steam Turbine |  | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Elevation Drawing for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5016 | 0.8505 | 0.5953 | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | false | 1 | 8 | 15.4583 | 0.6073 | 0.0311 | 0.0311 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181155 | ST #2 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL | ST ¦ Steam Turbine |  | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Detail Drawing for ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | ST #2 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 7 | 3 | 17.6935 | 0.6528 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181156 | ST #2 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE | ST ¦ Steam Turbine |  | ST #2 LEB ¦ Steam Turbine #2 Local Electrical Building |  | Schedule for ST ¦ Steam Turbine | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5434 | 0.5130 | 0.5130 | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | false | 3 | 15 | 16.8203 | 0.6009 | 0.0292 | 0.0219 | hybrid | structured_no_phase | electrical¦stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181200 | GTG #1,2 LEB - CALCULATION | CALCULATION | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Calculation sheet for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5813 | 0.6410 | 0.6410 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 13.9992 | 0.7002 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181201 | GTG #1,2 LEB - BASEMENT FLOOR PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - BASEMENT FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 9 | 1 | 13.9992 | 0.7516 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181202 | GTG #1,2 LEB - GROUND FLOOR PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 9 | 1 | 13.9992 | 0.7529 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181203 | GTG #1,2 LEB - ROOF PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 7 | 1 | 13.9992 | 0.7555 | 0.0313 | 0.0235 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181204 | GTG #1,2 LEB - SIDE WALL ELEVATION | ELEVATION | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Elevation Drawing for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6000 | 0.6427 | 0.6128 | 0.6128 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 13.9992 | 0.7316 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-09-10 | 2024-10-10 | 2024-11-09 | 2024-11-24 | 2024-12-09 | 2024-12-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181205 | GTG #1,2 LEB - MAIN SECTION | SECTION | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | SECTION for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.7500 | 0.6396 | 0.7169 | 0.7169 | FI | 2EF1200W32A04 | (GTG #21 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 18 | 3 | 13.5063 | 0.7408 | 0.0287 | 0.0215 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181206 | GTG #1,2 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | SCHEDULE | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Schedule for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5337 | 0.4401 | 0.4401 | FI | 2CF1200W24A10 | (GTG #21 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-27 | 2008-08-04 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.8535 | 0.6899 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181207 | GTG #1,2 LEB - STAIR PLAN & SECTION | PLAN & SECTION | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | PLAN & SECTION for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - STAIR PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.8000 | 0.6965 | 0.7689 | 0.7689 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 3 | 1 | 13.9992 | 0.7482 | 0.0323 | 0.0242 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181208 | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | DETAIL | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Detail Drawing for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6650 | 0.6195 | 0.6195 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 2 | 1 | 13.9992 | 0.7447 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181251 | GTG #1,2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 3 | 3 | 17.4884 | 0.7529 | 0.0317 | 0.0317 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181252 | GTG #1,2 LEB - GROUND FLOOR FRAMING PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 9 | 1 | 13.9992 | 0.7562 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181253 | GTG #1,2 LEB - ROOF FRAMING PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 7 | 1 | 13.9992 | 0.7406 | 0.0313 | 0.0235 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181254 | GTG #1,2 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Elevation Drawing for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GT - TURBINE & GENERATOR FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6000 | 0.6427 | 0.6128 | 0.6128 | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 13.9992 | 0.7430 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-09-10 | 2024-10-10 | 2024-11-09 | 2024-11-24 | 2024-12-09 | 2024-12-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181255 | GTG #1,2 LEB - STAIR FRAMING PLAN & ELEVATION | PLAN & ELEVATION | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | PLAN & ELEVATION for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - STAIR FRAMING PLAN & ELEVATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6797 | 0.6706 | 0.6706 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 3 | 1 | 13.9992 | 0.7486 | 0.0323 | 0.0242 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181256 | GTG #1,2 LEB - GROUND FLOOR OPENING PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR OPENING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 9 | 1 | 13.9992 | 0.7407 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181257 | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | DETAIL | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Detail Drawing for GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6650 | 0.6195 | 0.6195 | FI | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 2 | 1 | 15.5215 | 0.7313 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181258 | GTG #1,2 LEB - COLUMN RE - BAR SCHEDULE | SCHEDULE | GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB ¦ Gas Turbine Generator #1,2 Local Electrical Building |  | Schedule for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5337 | 0.4401 | 0.4401 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 13.9995 | 0.7163 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181259 | GTG #1,2 LEB - BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Schedule for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5816 | 0.4545 | 0.4545 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 1 | 19.7170 | 0.7179 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181260 | GTG #1,2 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Detail Drawing for LEB ¦ Local Electrical Building |  | GTG #1,2 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 2 | 1 | 19.7166 | 0.7512 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181281 | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Schedule for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5816 | 0.4545 | 0.4545 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 1 | 5 | 19.7170 | 0.6854 | 0.0318 | 0.0238 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181282 | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Diagram for GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 3 | 2 | 19.7166 | 0.7142 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | system_design¦engineering |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181284 | GTG #1,2 LEB - GROUND FLOOR PLUMBING PLAN | PLAN | GTG #1,2 ¦ Gas Turbine Generator #1,2 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR PLUMBING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 5 | 1 | 19.7166 | 0.7373 | 0.0318 | 0.0238 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181300 | GTG #3,4,5 LEB - CALCULATION | CALCULATION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Calculation sheet for GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6344 | 0.6570 | 0.6570 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 12 | 1 | 16.2666 | 0.6913 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181301 | GTG #3,4,5 LEB - BASEMENT FLOOR PLAN | PLAN | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - BASEMENT FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 83 | 1 | 17.1502 | 0.7317 | 0.0234 | 0.0175 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181302 | GTG #3,4,5 LEB - GROUND FLOOR PLAN | PLAN | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - GROUND FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 83 | 2 | 17.1502 | 0.7140 | 0.0231 | 0.0173 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181303 | GTG #3,4,5 LEB - ROOF PLAN | PLAN | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 84 | 4 | 17.1502 | 0.7160 | 0.0226 | 0.0169 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181304 | GTG #3,4,5 LEB - SIDE WALL ELEVATION | ELEVATION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Elevation Drawing for LEB ¦ Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5718 | 0.8715 | 0.6101 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 12 | 1 | 16.2666 | 0.7198 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181305 | GTG #3,4,5 LEB - MAIN SECTION | SECTION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | SECTION for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-01-25 | 2008-04-26 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 90 | 1 | 17.1502 | 0.7403 | 0.0231 | 0.0173 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-10-27 | 2024-11-26 | 2024-12-26 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181306 | GTG #3,4,5 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | SCHEDULE | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Schedule for GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | GTG#3,4,5LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5791 | 0.4537 | 0.4537 | FI | 3CF1200W24A10 | (GTG #31 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-27 | 2008-08-04 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 56 | 1 | 23.4974 | 0.6831 | 0.0250 | 0.0188 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181307 | GTG #3,4,5 LEB - STAIR PLAN & SECTION | PLAN & SECTION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | PLAN & SECTION for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - STAIR PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9994 | 0.9998 | 0.9998 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 90 | 2 | 16.2666 | 0.7158 | 0.0228 | 0.0171 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181351 | GTG #3,4,5 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 10 | 3 | 19.1654 | 0.7448 | 0.0302 | 0.0302 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181352 | GTG #3,4,5 LEB - GROUND FLOOR FRAMING PLAN | PLAN | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9998 | 0.9999 | 0.9999 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 92 | 4 | 16.2666 | 0.7132 | 0.0222 | 0.0167 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181353 | GTG #3,4,5 LEB - ROOF FRAMING PLAN | PLAN | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 84 | 4 | 17.1502 | 0.7110 | 0.0226 | 0.0169 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181354 | GTG #3,4,5 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Elevation Drawing for LEB ¦ Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5718 | 0.8715 | 0.6101 | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | false | 12 | 2 | 16.2666 | 0.7254 | 0.0300 | 0.0300 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181355 | GTG #3,4,5 LEB - STAIR FRAMING PLAN & ELEVATION | PLAN & ELEVATION | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | PLAN & ELEVATION for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - STAIR FRAMING PLAN & ELEVATION | 1 | start+2M<=FC<=start+2M+2M | FC ∈ [start+60d, start+120d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 82 | 4 | 17.1502 | 0.6933 | 0.0227 | 0.0170 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-09-30 | 2024-10-30 | 2024-11-29 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181356 | GTG #3,4,5 LEB - GROUND FLOOR OPENING PLAN | PLAN | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - GROUND FLOOR OPENING PLAN | 1 | start+2M<=FC<=start+2M+2M | FC ∈ [start+60d, start+120d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9994 | 0.9998 | 0.9998 | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 92 | 2 | 16.2666 | 0.6952 | 0.0227 | 0.0170 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-07-30 | 2024-08-29 | 2024-09-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181357 | GTG #3,4,5 LEB - FOUNDATION RE - BAR DETAIL | DETAIL | GTG #3,4,5 ¦ Gas Turbine Generator #3,4,5 |  | LEB ¦ Local Electrical Building |  | Detail Drawing for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - FOUNDATION RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9998 | 1.0000 | 1.0000 | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 9 | 3 | 19.1654 | 0.7317 | 0.0304 | 0.0304 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181358 | GTG #3,4,5 LEB - COLUMN RE - BAR SCHEDULE | SCHEDULE | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | Schedule for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5337 | 0.4401 | 0.4401 | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 21 | 5 | 13.5302 | 0.6912 | 0.0277 | 0.0208 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181359 | GTG #3,4,5 LEB - BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | Schedule for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5337 | 0.4401 | 0.4401 | FI | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-01-25 | 2008-04-26 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 23 | 4 | 13.5302 | 0.6933 | 0.0277 | 0.0208 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181360 | GTG #3,4,5 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | Detail Drawing for LEB ¦ Local Electrical Building |  | GTG #3,4,5 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 4 | 4 | 13.5299 | 0.7003 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181381 | GTG#3,4,5LEB - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | Schedule for GTG ¦ Gas Turbine Generator |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | gas¦generator¦gtg¦leb¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5337 | 0.4401 | 0.4401 | FI | 3SF9013W62A12 | (GTG #31) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | 2009-01-18 | 2009-02-01 |  | commissioning | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | fgp¦gtg | match | false | 46 | 14 | 9.3625 | 0.6414 | 0.0229 | 0.0172 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181382 | GTG#3,4,5LEB - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | Diagram for GTG ¦ Gas Turbine Generator |  | GTG#3,4,5LEB - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | gas¦generator¦gtg¦leb¦turbine | gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 176 | 9 | 8.8082 | 0.6559 | 0.0187 | 0.0187 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | system_design¦engineering |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.85 | fi_complete | activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181384 | GTG#3,4,5LEB - GROUND FLOOR PLUMBING PLAN | PLAN | GTG ¦ Gas Turbine Generator |  | LEB ¦ Local Electrical Building |  | Plan for LEB ¦ Local Electrical Building |  | GTG#3,4,5LEB - GROUND FLOOR PLUMBING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | FI | 3EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-08-01 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | false | 92 | 12 | 9.0540 | 0.6655 | 0.0205 | 0.0154 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0BAT-181800 | ROOF FOR STG TR - CALCULATION | CALCULATION |  |  |  |  | Calculation sheet for Steam Turbine Generator |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.4935 | 0.5680 | 0.5680 | FI | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match |  | stg | stg | rule | electrical¦gsut_uat¦stg | match | false | 1 | 5 | 7.9053 | 0.4601 | 0.0318 | 0.0318 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-11-08 | 2024-12-08 | 2025-01-07 | fi_complete | 0.90 | 1.00 | fi_complete | activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P6BAT-181811 | ROOF FOR STG TR - PLAN, SECTION, ELEVATION | PLAN, SECTION, ELEVATION |  |  |  |  | PLAN, SECTION, ELEVATION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.7143 | 0.8199 | 0.7460 | 0.7460 | FA | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  | stg | stg | rule | stg | match | false | 5 | 1 | 14.8429 | 0.5664 | 0.0318 | 0.0238 | hybrid | structured_no_phase | stg |  |  | 2025-04-23 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-07-07 | 2025-08-06 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P6BAT-181812 | ROOF FOR STG TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | [5 empty] | for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6706 | 0.6212 | 0.6212 | FA | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  | stg | stg | rule | stg | match | false | 2 | 9 | 24.4905 | 0.5235 | 0.0306 | 0.0230 | hybrid | structured_no_phase | stg |  |  | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P6BAT-181813 | ROOF FOR STG TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | [5 empty] | for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6706 | 0.6212 | 0.6212 | FA | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  | stg | stg | rule | stg | match | false | 3 | 1 | 24.4905 | 0.5039 | 0.0323 | 0.0242 | hybrid | structured_no_phase | stg |  |  | 2025-04-23 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-07-07 | 2025-08-06 | generated | 0.90 | 0.75 | usable | activity_phase_status=query_unknown;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UGD-181900 | WATER TREATMENT BUILDING - CALCULATION | CALCULATION |  |  | WATER TREATMENT BUILDING |  | Calculation sheet for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8605 | 0.9581 | 0.9581 | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 6 | 2 | 13.2405 | 0.5724 | 0.0313 | 0.0313 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181901 | WATER TREATMENT BUILDING - GROUND FLOOR PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 15 | 2 | 13.2405 | 0.6399 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181902 | WATER TREATMENT BUILDING - 1ST FLOOR PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 15 | 1 | 13.2405 | 0.6352 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181903 | WATER TREATMENT BUILDING - ROOF FLOOR PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 10 | 14.1670 | 0.5648 | 0.0299 | 0.0224 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181904 | WATER TREATMENT BUILDING - ELEVATION | ELEVATION |  |  | WATER TREATMENT BUILDING |  | Elevation Drawing for WATER TREATMENT BUILDING | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6491 | 0.5947 | 0.5947 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 8 | 1 | 12.7557 | 0.6091 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181905 | WATER TREATMENT BUILDING - SECTION | SECTION |  |  | WATER TREATMENT BUILDING |  | SECTION for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9057 | 0.9717 | 0.9717 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 2 | 8 | 14.1670 | 0.6045 | 0.0308 | 0.0231 | hybrid | structured_no_phase | wts | [5 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181906 | WATER TREATMENT BUILDING - INTERIOR FINISH & DOOR SCHEDULE | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7905 | 0.7038 | 0.7038 | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 2 | 1 | 20.3766 | 0.5790 | 0.0325 | 0.0244 | hybrid | structured_no_phase | wts | [5 empty] | 2025-04-03 | 2025-05-03 | 2025-06-02 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181908 | WATER TREATMENT BUILDING - WALL SECTION DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.8224 | 0.7134 | 0.7134 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 1 | 6 | 14.1670 | 0.5683 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181909 | WATER TREATMENT BUILDING - TOILET ENLARGED PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 14 | 3 | 13.4917 | 0.5713 | 0.0294 | 0.0220 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181910 | WATER TREATMENT BUILDING - WALL OPENING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 16 | 3 | 13.2405 | 0.5666 | 0.0290 | 0.0218 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181911 | WATER TREATMENT BUILDING - CEILING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 8 | 14.1670 | 0.5695 | 0.0303 | 0.0227 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181912 | WATER TREATMENT BUILDING - STAIR ENLARGED PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 14 | 2 | 13.4917 | 0.5865 | 0.0296 | 0.0222 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181913 | WATER TREATMENT BUILDING - STAIR ENLARGED SECTION | SECTION |  |  | WATER TREATMENT BUILDING |  | SECTION for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9057 | 0.9717 | 0.9717 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 12 | 1 | 13.4917 | 0.5851 | 0.0303 | 0.0227 | hybrid | structured_no_phase | wts | [5 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181914 | WATER TREATMENT BUILDING - ARCHITECTURAL MISC. |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - ARCHITECTURAL MISC. | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | other | other | water_treatment_building_architectural_misc | water_treatment_building_architectural_misc | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6000 | 0.8192 | 0.6658 | 0.6658 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 12 | 1 | 13.4917 | 0.6165 | 0.0303 | 0.0227 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181951 | WATER TREATMENT BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 4 | 3 | 16.4515 | 0.6263 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181952 | WATER TREATMENT BUILDING - GROUND FLOOR FRAMING |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - GROUND FLOOR FRAMING | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | water_treatment_building_ground_floor_framing | water_treatment_building_ground_floor_framing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7752 | 0.5825 | 0.5825 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 13 | 1 | 13.2405 | 0.6004 | 0.0301 | 0.0226 | hybrid | structured_no_phase | wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181953 | WATER TREATMENT BUILDING - 1ST FLOOR FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 15 | 2 | 13.2405 | 0.5985 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181954 | WATER TREATMENT BUILDING - ROOF FLOOR FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 18 | 2 | 13.2405 | 0.5735 | 0.0289 | 0.0217 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181955 | WATER TREATMENT BUILDING - FRAMING ELEVATION | ELEVATION |  |  | WATER TREATMENT BUILDING |  | Elevation Drawing for WATER TREATMENT BUILDING | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6491 | 0.5947 | 0.5947 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 5 | 2 | 13.2405 | 0.5835 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181956 | WATER TREATMENT BUILDING - STAIR FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 14 | 2 | 13.4917 | 0.5850 | 0.0296 | 0.0222 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181957 | WATER TREATMENT BUILDING - STAIR FRAMING SECTION | SECTION |  |  | WATER TREATMENT BUILDING |  | SECTION for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9057 | 0.9717 | 0.9717 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 12 | 2 | 13.4917 | 0.5977 | 0.0300 | 0.0225 | hybrid | structured_no_phase | wts | [5 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181958 | WATER TREATMENT BUILDING - FOUNDATION REBAR DETAIL |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7893 | 0.5868 | 0.5868 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 3 | 1 | 15.3516 | 0.5667 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181959 | WATER TREATMENT BUILDING - COLUMN REBAR DETAIL |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7893 | 0.5868 | 0.5868 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 13 | 1 | 13.2405 | 0.5411 | 0.0301 | 0.0226 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181960 | WATER TREATMENT BUILDING - GIRDER & BEAM REBAR SCHEDULE | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7905 | 0.7038 | 0.7038 | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 11 | 4 | 13.6716 | 0.5484 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181961 | WATER TREATMENT BUILDING - SLAB REBAR DETAIL |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7893 | 0.5868 | 0.5868 | FI | 0EF4035W16A02.2 | (WWT LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 6 | 14.0739 | 0.5099 | 0.0308 | 0.0231 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181962 | WATER TREATMENT BUILDING - EQUIPMENT FOUNDTAION ARRANGEMENT PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 4 | 6 | 16.4515 | 0.6153 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181963 | WATER TREATMENT BUILDING - EMBEDDED PLATE & SLEEVE PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 12 | 14.1670 | 0.5527 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181964 | WATER TREATMENT BUILDING - MISC. REBAR DETAIL |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7893 | 0.5868 | 0.5868 | FI | 0CF4035W32A05 | (WWT LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2008-06-03 | 2008-10-02 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 3 | 18 | 14.1670 | 0.5188 | 0.0287 | 0.0215 | hybrid | structured_no_phase | wts | [5 empty] | 2025-09-02 | 2025-10-02 | 2025-11-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181965 | WATER TREATMENT BUILDING - ROOF COLUMN LOCATION PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 15 | 14.1670 | 0.5564 | 0.0290 | 0.0217 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181966 | WATER TREATMENT BUILDING - ENLARGED ROOF FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 9 | 14.1670 | 0.5226 | 0.0301 | 0.0226 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181967 | WATER TREATMENT BUILDING - GIRT LINE & ROW ELEVATION | ELEVATION |  |  | WATER TREATMENT BUILDING |  | Elevation Drawing for WATER TREATMENT BUILDING | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6491 | 0.5947 | 0.5947 | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 4 | 3 | 13.6713 | 0.5663 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181968 | WATER TREATMENT BUILDING - STEEL CONNECTION DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.8224 | 0.7134 | 0.7134 | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 6 | 3 | 13.2405 | 0.5712 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181981 | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7905 | 0.7038 | 0.7038 | FI | 0CF5534W74A08 | (DWP BLDG) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-05-21 | 2008-08-05 |  | commissioning | query_unknown | wts | wts | wts | query | wts | match | false | 17 | 2 | 13.1297 | 0.6080 | 0.0291 | 0.0218 | hybrid | structured_no_phase | wts | [5 empty] | 2025-02-21 | 2025-03-23 | 2025-04-22 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181982 | WATER TREATMENT BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | WATER TREATMENT BUILDING |  | Diagram for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.8559 | 0.7234 | 0.7234 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 21 | 1 | 13.2405 | 0.6356 | 0.0287 | 0.0287 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181983 | WATER TREATMENT BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 15 | 2 | 13.2405 | 0.6317 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181984 | WATER TREATMENT BUILDING - 1ST FLOOR PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 12 | 4 | 13.8170 | 0.6050 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2025-09-30 | 2025-10-30 | 2025-11-29 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181985 | WATER TREATMENT BUILDING - ROOF PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  | query_unknown | wts | wts | wts | query | wts | match | false | 12 | 4 | 13.8170 | 0.5863 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2025-09-30 | 2025-10-30 | 2025-11-29 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181986 | WATER TREATMENT BUILDING - ENLARGED PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7863 | 0.7959 | 0.7959 | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | false | 4 | 12 | 14.1670 | 0.5606 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UST-182000 | WORKSHOP & STORAGE BUILDING - CALCULATION | CALCULATION |  |  | WORKSHOP & STORAGE BUILDING |  | Calculation sheet for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8451 | 0.9535 | 0.9535 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 31 | 2 | 9.7017 | 0.4877 | 0.0271 | 0.0203 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182001 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 4 | 2 | 13.3926 | 0.4887 | 0.0318 | 0.0179 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182002 | WORKSHOP & STORAGE BUILDING - ROOF PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 5 | 1 | 13.7004 | 0.4960 | 0.0318 | 0.0179 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182003 | WORKSHOP & STORAGE BUILDING - ELEVATION | ELEVATION |  |  | WORKSHOP & STORAGE BUILDING |  | Elevation Drawing for WORKSHOP & STORAGE BUILDING | Mechanical Workshop Equipment | Equipment Arrangement draWing for Workshop Equipment | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | drawing | drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5505 | 0.5151 | 0.5151 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 50 | 3 | 9.7017 | 0.5349 | 0.0250 | 0.0187 | hybrid | structured_no_system |  | civil_design |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182004 | WORKSHOP & STORAGE BUILDING - SECTION | SECTION |  |  | WORKSHOP & STORAGE BUILDING |  | SECTION for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9008 | 0.9702 | 0.9702 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 3 | 13.3926 | 0.4926 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182005 | WORKSHOP & STORAGE BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | SCHEDULE |  |  | WORKSHOP & STORAGE BUILDING |  | Schedule for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - INTERIOR finish, DOOR & WINDOW SCHEDULE | 1 | start+5M<=FC<=start+5M+2M | FC ∈ [start+150d, start+210d] | title | schedule | schedule | schedule | schedule | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9687 | 0.9906 | 0.9906 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 1 | 19.8798 | 0.5022 | 0.0325 | 0.0183 | hybrid | structured_no_system | [6 empty] | 2026-05-29 | 2026-06-28 | 2026-07-28 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182006 | WORKSHOP & STORAGE BUILDING - ENLARGED PLAN, CEILING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 4 | 4 | 13.3926 | 0.4675 | 0.0312 | 0.0176 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182051 | WORKSHOP & STORAGE BUILDING - FOUNDATION PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0CF5560W16A03 | (M&E WORKSHOP BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-04-10 | 2008-06-06 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 10 | 75 | 12.0359 | 0.4594 | 0.0217 | 0.0163 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2025-01-11 | 2025-02-10 | 2025-03-12 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182052 | WORKSHOP & STORAGE BUILDING - COLUMN LOCATION PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 4 | 16 | 13.3926 | 0.4643 | 0.0288 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182053 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 4 | 19 | 13.3926 | 0.4509 | 0.0283 | 0.0159 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182054 | WORKSHOP & STORAGE BUILDING - ROOF FRAMING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 4 | 1 | 13.7004 | 0.4474 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182055 | WORKSHOP & STORAGE BUILDING - STEEL ROOF FRAMING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 8 | 1 | 13.7004 | 0.4756 | 0.0311 | 0.0175 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182056 | WORKSHOP & STORAGE BUILDING - FRAMING ELEVATION | Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | Drawing for WORKSHOP & STORAGE BUILDING | Mechanical Workshop Equipment | Equipment Arrangement draWing for Workshop Equipment | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | drawing | drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5552 | 0.5166 | 0.5166 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 50 | 4 | 9.7017 | 0.5246 | 0.0247 | 0.0185 | hybrid | structured_no_system |  | civil_design |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182058 | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9672 | 0.9902 | 0.9902 | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 3 | 139 | 13.0440 | 0.3994 | 0.0209 | 0.0157 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-04 | 2024-08-03 | 2024-09-02 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182059 | WORKSHOP & STORAGE BUILDING - RC COLUMN DETAIL | Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - RC COLUMN DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9747 | 0.9924 | 0.9924 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 33 | 3 | 9.7017 | 0.4591 | 0.0266 | 0.0200 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182060 | WORKSHOP & STORAGE BUILDING - SLAB DETAIL | Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - SLAB DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9708 | 0.9912 | 0.9912 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 37 | 7 | 9.7017 | 0.4067 | 0.0252 | 0.0189 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182061 | WORKSHOP & STORAGE BUILDING - CRANE GIRDER & MISC. DETAIL | Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CRANE GIRDER & MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9804 | 0.9941 | 0.9941 | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match |  | crane_hoist | crane_hoist | rule |  | activity_unscoped | true | 101 | 21 | 4.0527 | 0.4690 | 0.0186 | 0.0056 | hybrid | structured_phase_gap | crane_hoist | civil_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182062 | WORKSHOP & STORAGE BUILDING - STEEL COLUMN & BASE PLATE DETAIL | Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - STEEL COLUMN & BASE PLATE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9767 | 0.9930 | 0.9930 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 33 | 1 | 9.7017 | 0.4556 | 0.0271 | 0.0204 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182063 | WORKSHOP & STORAGE BUILDING - CONNECTION DETAIL | Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CONNECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9706 | 0.9912 | 0.9912 | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 33 | 1 | 9.7017 | 0.4295 | 0.0271 | 0.0204 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182081 | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | WORKSHOP & STORAGE BUILDING |  | Schedule for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9749 | 0.9925 | 0.9925 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 2 | 2 | 17.0739 | 0.5542 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182082 | WORKSHOP & STORAGE BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | WORKSHOP & STORAGE BUILDING |  | Diagram for WORKSHOP & STORAGE BUILDING |  | PLUMBING SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7957 | 0.9387 | 0.6571 | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 50 | 4 | 9.7017 | 0.5324 | 0.0247 | 0.0185 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182083 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 4 | 26 | 13.3926 | 0.4893 | 0.0273 | 0.0153 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182084 | WORKSHOP & STORAGE BUILDING - ROOF PLUMBING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 4 | 13 | 13.7004 | 0.4683 | 0.0293 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182085 | WORKSHOP & STORAGE BUILDING - ENLARGED PLUMBING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8246 | 0.8074 | 0.8074 | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | false | 4 | 13 | 13.3926 | 0.4661 | 0.0293 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULA-182151 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION PLAN | PLAN |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match |  |  |  |  | stg | query_unscoped | false | 3 | 40 | 11.0757 | 0.5360 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182152 | DEAERATOR SUPPORT STRUCTURE - COLUMN LOCATION PLAN | PLAN |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - COLUMN LOCATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  | installation | query_unknown |  |  |  |  | hrsg | query_unscoped | false | 14 | 40 | 6.0176 | 0.5235 | 0.0235 | 0.0132 | hybrid | structured_no_system | [6 empty] | 2025-02-19 | 2025-03-21 | 2025-04-20 | fi_complete | 0.90 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182153 | DEAERATOR SUPPORT STRUCTURE - GROUND FLOOR FRAMING PLAN | PLAN |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  |  | civil_design | query_unknown |  |  |  |  | wts | query_unscoped | false | 409 | 1 |  | 0.5438 | 0.0185 | 0.0104 | hybrid | structured_no_system | [6 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182154 | DEAERATOR SUPPORT STRUCTURE - DEAERATOR FLOOR FRAMING PLAN | PLAN |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - DEAERATOR FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  | installation | query_unknown |  |  |  |  | hrsg | query_unscoped | false | 20 | 73 | 6.0176 | 0.5055 | 0.0200 | 0.0113 | hybrid | structured_no_system | [6 empty] | 2025-02-19 | 2025-03-21 | 2025-04-20 | fi_complete | 0.90 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182155 | DEAERATOR SUPPORT STRUCTURE - FRAMING ELEVATION | Drawing |  |  |  |  | Drawing |  | Support DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.3600 | 0.3413 | 0.3413 | FA | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | 513 | 127 | 4.7662 | 0.5179 | 0.0071 | 0.0053 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:query_unscoped;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182157 | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | Drawing |  |  |  |  | Drawing |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | 258 | 1 | 2.1802 | 0.5834 | 0.0195 | 0.0147 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182160 | DEAERATOR SUPPORT STRUCTURE - BASE PLATE DETAIL | Drawing |  |  |  |  | Drawing |  | DEAERATOR SUPPORT STRUCTURE - BASE PLATE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | 2244 | 1 |  | 0.5396 | 0.0168 | 0.0126 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULA-182190 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 0EF1600W14A10 | HRSG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-06-15 | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | false | 3 | 38 | 11.0107 | 0.5053 | 0.0261 | 0.0196 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULA-182191 | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | false | 3859 | 1 |  | 0.5352 | 0.0166 | 0.0125 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-08 | 2024-06-07 | 2024-07-07 | fi_complete | 0.90 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0USG-182700 | FIRE WATER PUMP HOUSE - CALCULATION | CALCULATION |  |  | FIRE WATER PUMP HOUSE |  | Calculation sheet for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8736 | 0.9621 | 0.9621 | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 3 | 7 | 13.5235 | 0.5375 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182701 | FIRE WATER PUMP HOUSE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | PLAN, SCHEDULE |  |  | FIRE WATER PUMP HOUSE |  | PLAN, SCHEDULE for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - GROUND FLOOR PLAN, INTERIOR finish SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.6000 | 0.7956 | 0.6587 | 0.6587 | FI | 0CF4500W24A11 | (Fire WTR Pump Shelter) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-20 | 2008-07-16 |  |  | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 3 | 2 | 19.8707 | 0.6013 | 0.0320 | 0.0240 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2025-02-20 | 2025-03-22 | 2025-04-21 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182702 | FIRE WATER PUMP HOUSE - ROOF PLAN | PLAN |  |  | FIRE WATER PUMP HOUSE |  | Plan for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.8333 | 0.8449 | 0.8368 | 0.8368 | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 6 | 2 | 13.5235 | 0.6101 | 0.0313 | 0.0235 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182703 | FIRE WATER PUMP HOUSE - ELEVATION | ELEVATION |  |  | FIRE WATER PUMP HOUSE |  | Elevation Drawing for FIRE WATER PUMP HOUSE |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6257 | 0.6544 | 0.4581 | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 3 | 13.5235 | 0.5519 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.85 | usable | rule_score_medium | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182704 | FIRE WATER PUMP HOUSE - MAIN SECTION | MAIN SECTION |  |  | FIRE WATER PUMP HOUSE |  | MAIN SECTION for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 1.0000 | 0.9016 | 0.9705 | 0.9705 | FI | 0CF4500W16A03 | (Fire WTR Pump Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-08-31 | 2007-10-27 |  | civil_design | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 6 | 1 | 13.5235 | 0.5898 | 0.0315 | 0.0237 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182751 | FIRE WATER PUMP HOUSE - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  | FIRE WATER PUMP HOUSE |  | Plan for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.8333 | 0.8449 | 0.8368 | 0.8368 | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 3 | 1 | 15.5387 | 0.6104 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182752 | FIRE WATER PUMP HOUSE - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN |  |  | FIRE WATER PUMP HOUSE |  | Plan for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.8333 | 0.8449 | 0.8368 | 0.8368 | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 6 | 2 | 13.5235 | 0.6024 | 0.0313 | 0.0235 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182753 | FIRE WATER PUMP HOUSE - FRAMING ELEVATION | ELEVATION |  |  | FIRE WATER PUMP HOUSE |  | Elevation Drawing for FIRE WATER PUMP HOUSE |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6257 | 0.6544 | 0.4581 | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 5 | 13.5235 | 0.5549 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 0.85 | usable | rule_score_medium | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0USG-182754 | FIRE WATER PUMP HOUSE - FOUNDATION REBAR SCHEDULE, SLAB REBAR DETAIL | SCHEDULE, DETAIL |  |  | FIRE WATER PUMP HOUSE |  | SCHEDULE, DETAIL for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - FOUNDATION REBAR SCHEDULE, SLAB REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7758 | 0.6994 | 0.6994 | FI | 0CF4500W16A03 | (Fire WTR Pump Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-08-31 | 2007-10-27 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 2 | 15.5391 | 0.5483 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0USG-182755 | FIRE WATER PUMP HOUSE - COLUMN, GIRDER, BEAM SHEDULE |  |  |  | FIRE WATER PUMP HOUSE |  | for FIRE WATER PUMP HOUSE | Fire Water Pump House | FIRE WATER PUMP HOUSE - COLUMN, GIRDER, BEAM SHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | fire_water_pump_house_column_girder_beam_shedule | fire_water_pump_house_column_girder_beam_shedule | fire¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.5000 | 0.7373 | 0.5712 | 0.5712 | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | false | 4 | 6 | 13.5235 | 0.5500 | 0.0308 | 0.0231 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTF-182800 | AIR COMPRESSOR SHELTER - CALCULATION SHEET | CALCULATION SHEET |  |  | AIR COMPRESSOR SHELTER |  | CALCULATION SHEET for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9190 | 0.9757 | 0.9757 | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 1 | 3 | 12.3084 | 0.5971 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182801 | AIR COMPRESSOR SHELTER - GROUND FLOOR PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8396 | 0.8119 | 0.8119 | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 3 | 1 | 12.3084 | 0.6420 | 0.0323 | 0.0242 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182802 | AIR COMPRESSOR SHELTER - ROOF PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8396 | 0.8119 | 0.8119 | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 4 | 1 | 12.3084 | 0.6246 | 0.0320 | 0.0240 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182803 | AIR COMPRESSOR SHELTER - SIDE ELEVATION | ELEVATION |  |  | AIR COMPRESSOR SHELTER |  | Elevation Drawing for AIR COMPRESSOR SHELTER | Air Compressor | Instrument Installation DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6168 | 0.6051 | 0.6051 | FA | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 6 | 2 | 12.3084 | 0.5934 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182804 | AIR COMPRESSOR SHELTER - MAIN SECTION | MAIN SECTION |  |  | AIR COMPRESSOR SHELTER |  | MAIN SECTION for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9119 | 0.9736 | 0.9736 | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 12 | 3 | 12.3084 | 0.6202 | 0.0298 | 0.0223 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182851 | AIR COMPRESSOR SHELTER - FOUNDATION ARRANGEMENT PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8396 | 0.8119 | 0.8119 | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 4 | 1 | 14.4195 | 0.6815 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182852 | AIR COMPRESSOR SHELTER - COLUMN ARRANGEMENT PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8396 | 0.8119 | 0.8119 | FI | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 3 | 1 | 15.4447 | 0.6545 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182853 | AIR COMPRESSOR SHELTER - GROUND FLOOR FRAMING PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8396 | 0.8119 | 0.8119 | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 3 | 1 | 12.3084 | 0.6286 | 0.0323 | 0.0242 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182854 | AIR COMPRESSOR SHELTER - ROOF FRAMING PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8396 | 0.8119 | 0.8119 | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 4 | 1 | 12.3084 | 0.6233 | 0.0320 | 0.0240 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182855 | AIR COMPRESSOR SHELTER - LINE FRAMING ELEVATION | ELEVATION |  |  | AIR COMPRESSOR SHELTER |  | Elevation Drawing for AIR COMPRESSOR SHELTER | Air Compressor | Instrument Installation DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6168 | 0.6051 | 0.6051 | FA | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 6 | 2 | 12.3084 | 0.6044 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182856 | AIR COMPRESSOR SHELTER - ROW FRAMING ELEVATION | ELEVATION |  |  | AIR COMPRESSOR SHELTER |  | Elevation Drawing for AIR COMPRESSOR SHELTER | Air Compressor | Instrument Installation DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6168 | 0.6051 | 0.6051 | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 5 | 2 | 12.3084 | 0.5886 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTF-182857 | AIR COMPRESSOR SHELTER - REBAR DETAIL | REBAR DETAIL |  |  | AIR COMPRESSOR SHELTER |  | REBAR DETAIL for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9083 | 0.9725 | 0.9725 | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | false | 3 | 1 | 12.3084 | 0.6191 | 0.0323 | 0.0242 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYC-182900 | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | CALCULATION SHEET |  |  | ADMINISTRATION & SOCIAL BUILDING |  | CALCULATION SHEET for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9282 | 0.9785 | 0.9785 | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 4 | 15.1429 | 0.5206 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182901 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 11 | 7 | 14.7383 | 0.5419 | 0.0290 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182902 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 7 | 14.7383 | 0.5201 | 0.0292 | 0.0164 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182903 | ADMINISTRATION & SOCIAL BUILDING - SIDE ELEVATION | ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Elevation Drawing for ADMINISTRATION & SOCIAL BUILDING |  | DraWing Building DraWing_Arch | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5452 | 0.6302 | 0.4412 | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 3 | 15.1429 | 0.5330 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182904 | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | SECTION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | SECTION for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8706 | 0.8212 | 0.8212 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 9 | 7 | 14.7383 | 0.4443 | 0.0294 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182905 | ADMINISTRATION & SOCIAL BUILDING - INTERIOR FINISH & DOOR / WINDOW SCHEDULE | SCHEDULE |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Schedule for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - INTERIOR finish & DOOR / WINDOW SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9667 | 0.9900 | 0.9900 | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 8 | 5 | 14.7387 | 0.4860 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182906 | ADMINISTRATION & SOCIAL BUILDING - WALL SECTION | SECTION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | SECTION for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8706 | 0.8212 | 0.8212 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 9 | 7 | 14.7383 | 0.4642 | 0.0294 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182907 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED REST ROOM PLAN & ELEVATION | PLAN & ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | PLAN & ELEVATION for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8376 | 0.8113 | 0.8113 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 11 | 10 | 14.7383 | 0.4529 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182908 | ADMINISTRATION & SOCIAL BUILDING - CEILING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 6 | 14.7383 | 0.5398 | 0.0294 | 0.0166 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182951 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 18 | 14 | 7.5640 | 0.4889 | 0.0263 | 0.0198 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182952 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 11 | 7 | 14.7383 | 0.5293 | 0.0290 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182953 | ADMINISTRATION & SOCIAL BUILDING - ROOF FRAMING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 10 | 7 | 14.7383 | 0.4820 | 0.0292 | 0.0164 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182954 | ADMINISTRATION & SOCIAL BUILDING - LINE FRAMING ELEVATION | ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Elevation Drawing for ADMINISTRATION & SOCIAL BUILDING |  | DraWing Building DraWing_Arch | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5452 | 0.6302 | 0.4412 | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 3 | 15.1429 | 0.5312 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182955 | ADMINISTRATION & SOCIAL BUILDING - ROW FRAMING ELEVATION | ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Elevation Drawing for ADMINISTRATION & SOCIAL BUILDING |  | DraWing Building DraWing_Arch | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5452 | 0.6302 | 0.4412 | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 2 | 15.1429 | 0.5190 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182956 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN REBAR DETAIL | REBAR DETAIL |  |  | ADMINISTRATION & SOCIAL BUILDING |  | REBAR DETAIL for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8677 | 0.7603 | 0.7603 | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 1 | 17.5175 | 0.5243 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYC-182957 | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | REBAR DETAIL |  |  | ADMINISTRATION & SOCIAL BUILDING |  | REBAR DETAIL for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8677 | 0.7603 | 0.7603 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 10 | 19 | 14.7383 | 0.4482 | 0.0269 | 0.0152 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYC-182958 | ADMINISTRATION & SOCIAL BUILDING - SLAB & MISC REBAR DETAIL | REBAR DETAIL |  |  | ADMINISTRATION & SOCIAL BUILDING |  | REBAR DETAIL for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8677 | 0.7603 | 0.7603 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 10 | 9 | 14.7383 | 0.4553 | 0.0288 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182981 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Schedule for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9684 | 0.9905 | 0.9905 | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 8 | 1 | 18.6344 | 0.5708 | 0.0311 | 0.0175 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182982 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Diagram for ADMINISTRATION & SOCIAL BUILDING |  | PLUMBING SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7693 | 0.9308 | 0.6516 | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 4 | 11 | 15.1429 | 0.5108 | 0.0297 | 0.0178 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182983 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 11 | 2 | 14.7383 | 0.5848 | 0.0302 | 0.0170 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182984 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLUMBING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 11 | 2 | 14.7383 | 0.5573 | 0.0302 | 0.0170 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182985 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED PLUMBING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7503 | 0.7851 | 0.7851 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 11 | 2 | 14.7383 | 0.5470 | 0.0302 | 0.0170 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYA-183100 | SECURITY BUILDING - CALCULATION | CALCULATION |  |  | SECURITY BUILDING |  | Calculation sheet for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8272 | 0.9482 | 0.9482 | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 7 | 12 | 4.2752 | 0.4403 | 0.0288 | 0.0173 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183101 | SECURITY BUILDING - GROUND FLOOR PLAN | PLAN |  |  | SECURITY BUILDING |  | Plan for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7534 | 0.7510 | 0.7510 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 41 | 9 | 4.1610 | 0.4920 | 0.0244 | 0.0137 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183102 | SECURITY BUILDING - ROOF PLAN | PLAN |  |  | SECURITY BUILDING |  | Plan for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7534 | 0.7510 | 0.7510 | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 3 | 1 | 13.7004 | 0.5347 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183103 | SECURITY BUILDING - SIDE WALL ELEVATION |  |  |  | SECURITY BUILDING |  | for SECURITY BUILDING | [5 empty] | rule_query | other | other | elevation | security_building | security |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.9186 | 0.7422 | 0.7422 |  | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 7 | 16 | 4.2752 | 0.4475 | 0.0281 | 0.0126 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183104 | SECURITY BUILDING - MAIN SECTION |  |  |  | SECURITY BUILDING |  | for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9749 | 0.9925 | 0.9925 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 189 | 6 | 4.1610 | 0.4938 | 0.0192 | 0.0108 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.41 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183105 | SECURITY BUILDING - INTERIOR FINISH SCHEDULE | SCHEDULE |  |  | SECURITY BUILDING |  | Schedule for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - INTERIOR finish SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9492 | 0.9848 | 0.9848 | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 7 | 1 | 11.0547 | 0.5196 | 0.0313 | 0.0176 | hybrid | structured_no_system | [6 empty] | 2025-02-21 | 2025-03-23 | 2025-04-22 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183151 | SECURITY BUILDING - FOUNDATION & COLUMN LOCATION PLAN | PLAN |  |  | SECURITY BUILDING |  | Plan for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7534 | 0.7510 | 0.7510 | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 5 | 1 | 6.5301 | 0.5486 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183152 | SECURITY BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | SECURITY BUILDING |  | Plan for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7534 | 0.7510 | 0.7510 | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 14 | 7 | 4.2752 | 0.4755 | 0.0284 | 0.0128 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183153 | SECURITY BUILDING - ROOF FLOOR FRAMING PLAN | PLAN |  |  | SECURITY BUILDING |  | Plan for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7534 | 0.7510 | 0.7510 | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 4 | 1 | 13.7004 | 0.4992 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183154 | SECURITY BUILDING - FRAMING ELEVATION |  |  |  | SECURITY BUILDING |  | for SECURITY BUILDING | [5 empty] | rule_query | other | other | elevation | security_building | security |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.9186 | 0.7422 | 0.7422 |  | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 6 | 18 | 4.2752 | 0.4390 | 0.0280 | 0.0126 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYA-183155 | SECURITY BUILDING - RE - BAR DETAIL |  |  |  | SECURITY BUILDING |  | for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9770 | 0.9931 | 0.9931 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | [5 empty] | query_unscoped | true | 3 | 2 | 4.6631 | 0.4441 | 0.0320 | 0.0144 | hybrid | structured_no_system | [6 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183181 | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | SECURITY BUILDING |  | Schedule for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9744 | 0.9923 | 0.9923 | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 16 | 15 | 8.0571 | 0.5004 | 0.0265 | 0.0149 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183182 | SECURITY BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | SECURITY BUILDING |  | Diagram for SECURITY BUILDING |  | PLUMBING SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8017 | 0.9405 | 0.6584 | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 154 | 3 | 3.8682 | 0.5173 | 0.0205 | 0.0154 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183183 | SECURITY BUILDING - PLUMBING PLAN | PLAN |  |  | SECURITY BUILDING |  | Plan for SECURITY BUILDING | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7534 | 0.7510 | 0.7510 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown |  |  |  |  | wts | query_unscoped | false | 29 | 1 | 4.1610 | 0.5397 | 0.0276 | 0.0155 | hybrid | structured_no_system | [6 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYP-183200 | FIRE BRIGADE - CALCULATION | CALCULATION |  |  | FIRE BRIGADE |  | Calculation sheet for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8659 | 0.9598 | 0.9598 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 6 | 7 | 6.8830 | 0.4364 | 0.0301 | 0.0226 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183201 | FIRE BRIGADE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | PLAN, SCHEDULE |  |  | FIRE BRIGADE |  | PLAN, SCHEDULE for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - GROUND FLOOR PLAN, INTERIOR finish SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9570 | 0.9871 | 0.9871 | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 3 | 2 | 13.3977 | 0.5480 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-02-21 | 2025-03-23 | 2025-04-22 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183202 | FIRE BRIGADE - ROOF PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 14 | 1 | 6.8830 | 0.5474 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183203 | FIRE BRIGADE - ELEVATION | ELEVATION |  |  | FIRE BRIGADE |  | Elevation Drawing for FIRE BRIGADE |  | FIRE PROTECTION SYSTEM DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6905 | 0.5572 | 0.3900 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  | fire_fighting | fire_fighting | rule | fire_fighting¦hvac | match | false | 7 | 3 | 6.8830 | 0.5103 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.68 | usable | rule_score_medium;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183204 | FIRE BRIGADE - MAIN SECTION | SECTION |  |  | FIRE BRIGADE |  | SECTION for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8360 | 0.7758 | 0.7758 | FI | 0CF4500W38A06 | (Fire Fighting BLDG) Installation - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-31 | 2008-07-11 |  | installation | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 2 | 15 | 7.0772 | 0.4545 | 0.0295 | 0.0166 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183205 | FIRE BRIGADE - ENLARGED PLAN, CEILING PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 8 | 2 | 6.8830 | 0.5304 | 0.0308 | 0.0173 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183251 | FIRE BRIGADE - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 3 | 1 | 8.9292 | 0.5745 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183252 | FIRE BRIGADE - GROUND FLOOR FRAMING PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 14 | 2 | 6.8830 | 0.5700 | 0.0296 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183253 | FIRE BRIGADE - ROOF FRAMING PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 14 | 2 | 6.8830 | 0.5471 | 0.0296 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183254 | FIRE BRIGADE - FRAMING ELEVATION | ELEVATION |  |  | FIRE BRIGADE |  | Elevation Drawing for FIRE BRIGADE |  | FIRE PROTECTION SYSTEM DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6905 | 0.5572 | 0.3900 | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  | fire_fighting | fire_fighting | rule | fire_fighting¦hvac | match | false | 7 | 3 | 6.8830 | 0.5183 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 0.68 | usable | rule_score_medium;activity_scope_source=rule;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183255 | FIRE BRIGADE - MISC. STRUCTURAL DETAIL | DETAIL |  |  | FIRE BRIGADE |  | Detail Drawing for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - MISC. STRUCTURAL DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9758 | 0.9927 | 0.9927 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | design_drawing | civil_design | compatible |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 14 | 3 | 6.8830 | 0.5186 | 0.0294 | 0.0165 | hybrid | structured_no_system |  | system_design¦civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYP-183256 | FIRE BRIGADE - FOUNDATION, SLAB REBAR SCHEDULE | SCHEDULE |  |  | FIRE BRIGADE |  | Schedule for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - FOUNDATION, SLAB REBAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9719 | 0.9916 | 0.9916 | FI | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 6 | 1 | 8.9295 | 0.5420 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYP-183257 | FIRE BRIGADE - COLUMN, GIRDER, BEAM SHEDULE | SHEDULE |  |  | FIRE BRIGADE |  | SHEDULE for FIRE BRIGADE | [5 empty] | rule_query | other | calculation | shedule | calculation | brigade¦fire |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.6667 | 0.7331 | 0.6866 | 0.6866 |  | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 6 | 12 | 6.8830 | 0.4727 | 0.0290 | 0.0163 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183281 | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | FIRE BRIGADE |  | Schedule for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9700 | 0.9910 | 0.9910 | FI | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 |  | procurement | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 3 | 1 | 9.3383 | 0.5563 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183282 | FIRE BRIGADE - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | FIRE BRIGADE |  | Diagram for FIRE BRIGADE |  | PLUMBING SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8175 | 0.9453 | 0.6617 | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 1 | 1 | 16.2958 | 0.5433 | 0.0328 | 0.0184 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183283 | FIRE BRIGADE - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 14 | 1 | 6.8830 | 0.5937 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183284 | FIRE BRIGADE - ROOF PLUMBING PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 14 | 1 | 6.8830 | 0.5565 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183285 | FIRE BRIGADE - ENLARGED PLUMBING PLAN | PLAN |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 8 | 4 | 6.8830 | 0.5390 | 0.0303 | 0.0171 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYE-183300 | MAIN GATE HOUSE - CALCULATION | CALCULATION |  |  | MAIN GATE HOUSE |  | Calculation sheet for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8554 | 0.9566 | 0.9566 | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 2 | 17.1992 | 0.5812 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183301 | MAIN GATE HOUSE - GROUND FLOOR , ROOF PLAN, INTERIOR FINISH, DOOR & WINDOW SCHEDULES | PLAN, SCHEDULES |  |  | MAIN GATE HOUSE |  | PLAN, SCHEDULES for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - GROUND FLOOR , ROOF PLAN, INTERIOR finish, DOOR & WINDOW SCHEDULES | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9608 | 0.9882 | 0.9882 | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 10 | 6 | 16.5970 | 0.4815 | 0.0294 | 0.0166 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183302 | MAIN GATE HOUSE - ELEVATIONS | ELEVATIONS |  |  | MAIN GATE HOUSE |  | ELEVATIONS for MAIN GATE HOUSE | [5 empty] | rule_query | other | other | elevations | main_gate_house_elevations | gate¦house¦main |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8465 | 0.9540 | 0.9540 |  | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 9 | 6 | 16.5970 | 0.4931 | 0.0296 | 0.0167 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183303 | MAIN GATE HOUSE - SECTIONS & DETAILS | SECTIONS & DETAILS |  |  | MAIN GATE HOUSE |  | SECTIONS & DETAILS for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - SECTIONS & DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9199 | 0.9760 | 0.9760 | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 8 | 5 | 16.5970 | 0.5029 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183351 | MAIN GATE HOUSE - FOUNDATION ARRANGEMENT, GROUND FLOOR FRAMING PLAN |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - FOUNDATION ARRANGEMENT, GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9555 | 0.9866 | 0.9866 | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 1 | 19.5739 | 0.6060 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183352 | MAIN GATE HOUSE - ROOF FRAMING PLAN |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9468 | 0.9840 | 0.9840 | FI | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 9 | 6 | 16.5970 | 0.4572 | 0.0296 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183353 | MAIN GATE HOUSE - FRAMING ELEVATION |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | [5 empty] | rule_query | other | other | elevation | main_gate_house_elevations | gate¦house¦main |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.7500 | 0.8355 | 0.7757 | 0.7757 |  | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 8 | 8 | 16.5970 | 0.4870 | 0.0294 | 0.0165 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYE-183354 | MAIN GATE HOUSE - COLUMN, GIRDER & BEAM RE - BAR DETAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - COLUMN, GIRDER & BEAM RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9667 | 0.9900 | 0.9900 | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | 8 | 6 | 16.5970 | 0.4831 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYE-183355 | MAIN GATE HOUSE - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | main_gate_house_foundation_slab_and_misc_re_bar_dedail | main_gate_house_foundation_slab_and_misc_re_bar_dedail | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9616 | 0.9885 | 0.9885 | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 1 | 19.5739 | 0.5938 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTX-183361 | MAIN GATE HOUSE SUNSHADE - GROUND FLOOR, ROOF PLAN & ELEVATION |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - GROUND FLOOR, ROOF PLAN & ELEVATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9548 | 0.9864 | 0.9864 | FI | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 9 | 6 | 16.5970 | 0.4443 | 0.0296 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183371 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (TOP CHORD) |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (TOP CHORD) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9612 | 0.9884 | 0.9884 | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 1 | 2 | 17.1992 | 0.4758 | 0.0325 | 0.0146 | hybrid | structured_no_system | [6 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183372 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (BOTTOM CHORD) |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (BOTTOM CHORD) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9592 | 0.9878 | 0.9878 | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | 1 | 2 | 17.1992 | 0.4805 | 0.0325 | 0.0146 | hybrid | structured_no_system | [6 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183373 | MAIN GATE HOUSE SUNSHADE - FRAMING ELEVATION |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | [5 empty] | rule_query | other | other | elevation | main_gate_house_elevations | gate¦house¦main |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.7500 | 0.8355 | 0.7757 | 0.7757 |  | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 9 | 5 | 16.5970 | 0.4666 | 0.0299 | 0.0168 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183375 | MAIN GATE HOUSE SUNSHADE - BASE PLATE & CONNECTION DETAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - BASE PLATE & CONNECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9599 | 0.9880 | 0.9880 | FI | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | 9 | 13 | 16.5970 | 0.4238 | 0.0282 | 0.0159 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTX-183377 | MAIN GATE HOUSE SUNSHADE - FOUNDATION RE - BAR DETAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - FOUNDATION RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9509 | 0.9853 | 0.9853 | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 1 | 1 | 19.5739 | 0.5376 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTX-183390 | MAIN GATE HOUSE SUNSHADE - CALCULATION | CALCULATION |  |  | MAIN GATE HOUSE |  | Calculation sheet for MAIN GATE HOUSE | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gate¦house¦main |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8554 | 0.9566 | 0.9566 | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 2 | 1 | 17.1992 | 0.4682 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYB-183500 | SUPPORT BUILDING - CALCULATION | CALCULATION |  |  | SUPPORT BUILDING |  | Calculation sheet for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8578 | 0.9573 | 0.9573 | FI | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 44 | 1 | 4.1062 | 0.4598 | 0.0260 | 0.0156 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYB-183501 | SUPPORT BUILDING - GROUND FLOOR PLAN, ROOF PLAN, ELEVATIONS & MAIN SECTION |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - GROUND FLOOR PLAN, ROOF PLAN, ELEVATIONS & MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9655 | 0.9896 | 0.9896 | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 5 | 65 | 13.7004 | 0.4435 | 0.0234 | 0.0132 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYB-183502 | SUPPORT BUILDING - TOILET PLAN & ELEVATION |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - TOILET PLAN & ELEVATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9738 | 0.9921 | 0.9921 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown |  |  |  |  | wts | query_unscoped | false | 35 | 2 | 4.1610 | 0.4988 | 0.0267 | 0.0150 | hybrid | structured_no_system | [6 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYB-183551 | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9610 | 0.9883 | 0.9883 | FI | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | 34 | 18 | 5.9962 | 0.4610 | 0.0235 | 0.0176 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYB-183552 | SUPPORT BUILDING - FRAMING ELEVATIONS |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING | [5 empty] | rule_query | other | other | elevation | support_building | support |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.9166 | 0.7416 | 0.7416 |  | 0CF3520W24A10.3 | (Foam Station BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Foam Station Building | 2008-05-31 | 2008-07-28 |  |  | query_unknown |  |  |  |  | fgp¦fire_fighting | query_unscoped | false | 11 | 34 | 4.5408 | 0.4075 | 0.0247 | 0.0139 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYB-183553 | SUPPORT BUILDING - COLUMN, GIRDER & BEAM RE - BAR DETAIL |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - COLUMN, GIRDER & BEAM RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9715 | 0.9915 | 0.9915 | FI | 0PF6020W46A08P | (Hanger & Support & Fitting) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-02-29 |  | procurement | query_unknown |  |  |  |  | bop | query_unscoped | false | 3 | 249 | 9.6476 | 0.3946 | 0.0191 | 0.0107 | hybrid | structured_no_system | [6 empty] | 2024-06-16 | 2024-07-16 | 2024-08-15 | fi_complete | 0.90 | 0.41 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYB-183554 | SUPPORT BUILDING - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | support_building_foundation_slab_and_misc_re_bar_dedail | support_building_foundation_slab_and_misc_re_bar_dedail | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9793 | 0.9938 | 0.9938 | FI | 3CF3520W16A08 | (FGSS #32) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | false | 6 | 78 | 11.1818 | 0.4518 | 0.0224 | 0.0168 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYB-183581 | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM |  |  | SUPPORT BUILDING |  | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | rule_query | schedule | schedule | schedule | schedule | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9356 | 0.9807 | 0.9807 | FI | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 24 | 7 | 11.7639 | 0.5245 | 0.0268 | 0.0161 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | fi_complete | 0.90 | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYB-183582 | SUPPORT BUILDING - PLUMBING PLAN | PLAN |  |  | SUPPORT BUILDING |  | Plan for SUPPORT BUILDING | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING PLAN | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | rule_query | plan | plan | plan | plan | support |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7074 | 0.7372 | 0.7372 | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown |  |  |  |  | wts | query_unscoped | false | 35 | 2 | 4.1610 | 0.5361 | 0.0267 | 0.0150 | hybrid | structured_no_system | [6 empty] | 2024-10-03 | 2024-11-02 | 2024-12-02 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYF-183600 | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | CALCULATION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Calculation sheet for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8468 | 0.7541 | 0.7541 | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 222 | 13 |  | 0.3382 | 0.0172 | 0.0129 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183601 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.7778 | 0.9277 | 0.8227 | 0.8227 | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | 1 | 36 | 24.0608 | 0.3551 | 0.0268 | 0.0121 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183602 | SEARCH FACILITY & VISITORS CENTRE - ROOF PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9187 | 0.8006 | 0.8006 | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 5 | 10 | 9.6476 | 0.4217 | 0.0297 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183603 | SEARCH FACILITY & VISITORS CENTRE - ELEVATION | ELEVATION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Elevation Drawing for SEARCH FACILITY & VISITORS CENTRE |  | ELEVATION | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5483 | 0.3978 | 0.3381 | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | 32 | 19 |  | 0.3802 | 0.0235 | 0.0141 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183604 | SEARCH FACILITY & VISITORS CENTRE - MAIN SECTION | SECTION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | SECTION for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9375 | 0.8063 | 0.8063 | FI | 2CF1625W42A08.0 | (HRSG #21 Main Stack) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2008-12-15 | 2009-03-14 |  | installation | query_unknown |  |  |  |  | hrsg | query_unscoped | false | 14 | 87 | 5.8734 | 0.2956 | 0.0203 | 0.0114 | hybrid | structured_no_system | [6 empty] | 2025-09-17 | 2025-10-17 | 2025-11-16 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183651 | SEARCH FACILITY & VISITORS CENTRE - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.9195 | 0.8359 | 0.8359 | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 10 | 19 | 3.9283 | 0.4219 | 0.0269 | 0.0202 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183652 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR & ROOF FRAMING PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR & ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.8182 | 0.9255 | 0.8504 | 0.8504 | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 5 | 24 | 9.6476 | 0.4030 | 0.0273 | 0.0154 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183653 | SEARCH FACILITY & VISITORS CENTRE - FRAMING ELEVATION | ELEVATION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Elevation Drawing for SEARCH FACILITY & VISITORS CENTRE |  | ELEVATION | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5483 | 0.3978 | 0.3381 | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 223 | 12 |  | 0.3890 | 0.0174 | 0.0131 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYF-183654 | SEARCH FACILITY & VISITORS CENTRE - REBAR SCHEDULE & DETAIL | SCHEDULE & DETAIL |  |  | SEARCH FACILITY & VISITORS CENTRE |  | SCHEDULE & DETAIL for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - REBAR SCHEDULE & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.7778 | 0.9432 | 0.8274 | 0.8274 | FI | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 |  | installation | query_unknown | [5 empty] | query_unscoped | true | 1 | 118 | 25.7249 | 0.3609 | 0.0220 | 0.0099 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-12 | 2024-04-11 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYF-183681 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM |  |  | SEARCH FACILITY & VISITORS CENTRE |  | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.8182 | 0.8308 | 0.8220 | 0.8220 | FI | 0EF4035W00A01 | (STS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible |  |  |  |  | wts | query_unscoped | false | 6 | 6 | 10.1914 | 0.4860 | 0.0303 | 0.0170 | hybrid | structured_no_system |  | system_design¦civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYF-183682 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - PLUMBING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | centre¦facility¦search¦visitors |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9373 | 0.8062 | 0.8062 | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | 1 | 17 | 24.0608 | 0.4434 | 0.0294 | 0.0132 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULD-183900 | CPP & CPP REGEN BUILDING - CALCULATION | CALCULATION |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Calculation sheet for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7754 | 0.7926 | 0.7926 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 3 |  | 0.3815 | 0.0317 | 0.0317 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183902 | CPP & CPP REGEN BUILDING - GROUND FLOOR PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - GROUND FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9397 | 0.8819 | 0.8819 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 10 | 2 | 4.6631 | 0.5222 | 0.0304 | 0.0137 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183903 | CPP & CPP REGEN BUILDING - ROOF FLOOR PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ROOF FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9396 | 0.8819 | 0.8819 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 16 | 2 | 4.6631 | 0.5139 | 0.0293 | 0.0132 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183904 | CPP & CPP REGEN BUILDING - ELEVATION | ELEVATION |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Elevation Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4965 | 0.6156 | 0.4309 | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 9 | 2 |  | 0.3541 | 0.0306 | 0.0306 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183905 | CPP & CPP REGEN BUILDING - SECTION | SECTION |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | SECTION for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8247 | 0.8074 | 0.8074 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 2 | 3 | 4.6631 | 0.5382 | 0.0320 | 0.0144 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183906 | CPP & CPP REGEN BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | SCHEDULE |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Schedule for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - INTERIOR finish, DOOR & WINDOW SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9493 | 0.9070 | 0.9070 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 2 | 1 | 11.4108 | 0.4777 | 0.0325 | 0.0146 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183908 | CPP & CPP REGEN BUILDING - WALL SECTION DETAIL | SECTION DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | SECTION DETAIL for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - WALL SECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.7604 | 0.7281 | 0.7281 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 4 | 1 | 4.6631 | 0.4624 | 0.0320 | 0.0144 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183909 | CPP & CPP REGEN BUILDING - WALL OPENING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - WALL OPENING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9515 | 0.8855 | 0.8855 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 5 | 2 | 4.6631 | 0.4834 | 0.0315 | 0.0142 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183910 | CPP & CPP REGEN BUILDING - ARCHITECTURAL MISC. DETAIL | DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9058 | 0.8717 | 0.8717 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 1 |  | 0.4021 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183951 | CPP & CPP REGEN BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9366 | 0.8935 | 0.8935 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 3 | 2.1802 | 0.4710 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183952 | CPP & CPP REGEN BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9500 | 0.8975 | 0.8975 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 10 | 5 | 4.6631 | 0.4929 | 0.0297 | 0.0134 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183953 | CPP & CPP REGEN BUILDING - ROOF FLOOR FRAMING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ROOF FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9358 | 0.8933 | 0.8933 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 16 | 3 | 4.6631 | 0.4668 | 0.0290 | 0.0131 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183954 | CPP & CPP REGEN BUILDING - FRAMING ELEVATION | ELEVATION |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Elevation Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4965 | 0.6156 | 0.4309 | FA | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 3 |  | 0.3501 | 0.0317 | 0.0317 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183955 | CPP & CPP REGEN BUILDING - FOUNDATION REBAR DETAIL | DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9408 | 0.8822 | 0.8822 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 1 | 1 | 2.1802 | 0.4808 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183956 | CPP & CPP REGEN BUILDING - COLUMN REBAR DETAIL | DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - COLUMN REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9480 | 0.8844 | 0.8844 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 1 |  | 0.4186 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183957 | CPP & CPP REGEN BUILDING - GIRDER & BEAM REBAR SCHEDULE | SCHEDULE |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Schedule for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - GIRDER & BEAM REBAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9612 | 0.9008 | 0.9008 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 2 | 26 | 4.6635 | 0.4331 | 0.0278 | 0.0125 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183958 | CPP & CPP REGEN BUILDING - SLAB REBAR DETAIL | DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - SLAB REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9425 | 0.8827 | 0.8827 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 1 |  | 0.4105 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183959 | CPP & CPP REGEN BUILDING - EQUIPMENT FOUNDTAION REBAR DETAIL | DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - EQUIPMENT FOUNDTAION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9413 | 0.8949 | 0.8949 | FI | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | 1 | 3 | 2.6045 | 0.5054 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183960 | CPP & CPP REGEN BUILDING - EMBEDDED PLATE & SLEEVE PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - EMBEDDED PLATE & SLEEVE PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9532 | 0.8985 | 0.8985 | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 1 | 8 | 24.0608 | 0.4746 | 0.0311 | 0.0140 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183961 | CPP & CPP REGEN BUILDING - MISC. REBAR DETAIL | DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - MISC. REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9343 | 0.8803 | 0.8803 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 1 |  | 0.4080 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183962 | CPP & CPP REGEN BUILDING - ROOF COLUMN LOCATION PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ROOF COLUMN LOCATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9511 | 0.8978 | 0.8978 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 10 | 9 | 4.6631 | 0.5048 | 0.0288 | 0.0130 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183963 | CPP & CPP REGEN BUILDING - ENLARGED ROOF FRAMING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ENLARGED ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9463 | 0.8964 | 0.8964 | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | 10 | 6 | 4.6631 | 0.4430 | 0.0294 | 0.0132 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183964 | CPP & CPP REGEN BUILDING - GIRT LINE & ROW ELEVATION | ELEVATION |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Elevation Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4965 | 0.6156 | 0.4309 | FA | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 1 |  | 0.3314 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183965 | CPP & CPP REGEN BUILDING - STEEL CONNECTION DETAIL | DETAIL |  |  | CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CPP & CPP REGEN BUILDING ¦ CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - STEEL CONNECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦cpp¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9233 | 0.8770 | 0.8770 | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | 3 | 3 |  | 0.4124 | 0.0317 | 0.0317 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0USR-184700 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | CALCULATION |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Calculation sheet for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | tank | scoped | match | match | match | passed |  | 1.0000 | 0.8863 | 0.9659 | 0.9659 | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts |  | wts | query | wts | match | false | 2 | 2 | 28.7086 | 0.5969 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USR-184701 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - GROUND & ROOF FLOOR PLAN | PLAN |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Plan for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - GROUND & ROOF FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | tank | scoped | match | match | match | passed |  | 0.7000 | 0.8507 | 0.7452 | 0.7452 | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  | query_unknown | wts |  | wts | query | wts | match | false | 1 | 4 | 29.9534 | 0.6620 | 0.0320 | 0.0240 | hybrid | structured_no_phase | wts | [5 empty] | 2025-05-25 | 2025-06-24 | 2025-07-24 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USR-184702 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - ELEVATIONS & SECTIONS | ELEVATIONS & SECTIONS |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | ELEVATIONS & SECTIONS for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - ELEVATIONS & SECTIONS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | tank | scoped | match | match | match | passed |  | 1.0000 | 0.9270 | 0.9781 | 0.9781 | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | wts |  | wts | query | wts | match | false | 2 | 2 | 28.7086 | 0.6206 | 0.0323 | 0.0242 | hybrid | structured_no_phase | wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0USR-184751 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL COLUMN LOCATION & ROOF PLAN | PLAN |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Plan for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - GROUND & ROOF FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | tank | scoped | match | match | match | passed |  | 0.7000 | 0.8507 | 0.7452 | 0.7452 | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | wts |  | wts | query | wts | match | false | 2 | 2 | 28.7086 | 0.6406 | 0.0323 | 0.0242 | hybrid | structured_no_phase | wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0USR-184752 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL FRAMING ELEVATIONS | ELEVATIONS |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | ELEVATIONS for WWT & BULK CHEMICAL STORAGE TANK SHELTER ¦ Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | [5 empty] | rule_query | other | drawing | elevations | sectional_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts¦wwt | tank | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.8750 | 0.8621 | 0.8711 | 0.8711 |  | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | wts |  | wts | query | wts | match | false | 2 | 2 | 28.7086 | 0.6138 | 0.0323 | 0.0242 | hybrid | structured_no_phase | wts | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0QJA-184800 | N2 STORAGE SHELTER - CALCULATION | CALCULATION |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | Calculation sheet for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8679 | 0.8204 | 0.8204 | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 | n2 | n2 | query | n2 | match | false | 1 | 4 | 13.1604 | 0.5622 | 0.0320 | 0.0320 | hybrid | structured_preferred | n2 | civil_design | 9 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184801 | N2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | PLAN |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | Plan for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9234 | 0.8895 | 0.8895 | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  | civil_design | query_unknown | n2 | n2 | n2 | query | n2 | match | false | 11 | 1 | 13.1604 | 0.5966 | 0.0305 | 0.0229 | hybrid | structured_no_phase | n2 | [5 empty] | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184802 | N2 STORAGE SHELTER - ELEVATION | ELEVATION |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | Elevation Drawing for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | ELEVATION | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5689 | 0.4040 | 0.3434 | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | false | 1 | 4 | 13.1604 | 0.5464 | 0.0320 | 0.0320 | hybrid | structured_preferred | n2 | civil_design | 9 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184803 | N2 STORAGE SHELTER - MAIN SECTION | SECTION |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | SECTION for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8656 | 0.7263 | 0.7263 | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  | civil_design | query_unknown | n2 | n2 | n2 | query | n2 | match | false | 9 | 1 | 13.1604 | 0.5430 | 0.0309 | 0.0232 | hybrid | structured_no_phase | n2 | [5 empty] | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184851 | N2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | Plan for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9415 | 0.8950 | 0.8950 | FI | 1CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2008-03-04 | 2008-04-30 | civil_design | civil_design | match | n2 | n2 | n2 | query | n2 | match | false | 1 | 1 | 14.0316 | 0.6175 | 0.0328 | 0.0328 | hybrid | structured_preferred | n2 | civil_design | 9 |  |  |  | 2024-12-05 | 2025-01-04 | 2025-02-03 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184852 | N2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | Plan for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9350 | 0.9027 | 0.9027 | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  | civil_design | query_unknown | n2 | n2 | n2 | query | n2 | match | false | 11 | 4 | 13.1604 | 0.5582 | 0.0297 | 0.0223 | hybrid | structured_no_phase | n2 | [5 empty] | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184853 | N2 STORAGE SHELTER - FRAMING ELEVATION | ELEVATION |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | Elevation Drawing for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | ELEVATION | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5050 | 0.3848 | 0.3271 | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | false | 1 | 5 | 13.1604 | 0.5288 | 0.0318 | 0.0318 | hybrid | structured_preferred | n2 | civil_design | 9 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0QJA-184854 | N2 STORAGE SHELTER - REBAR DETAIL | REBAR DETAIL |  |  | N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER |  | REBAR DETAIL for N2 STORAGE SHELTER ¦ Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.9041 | 0.8546 | 0.8546 | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  | civil_design | query_unknown | n2 | n2 | n2 | query | n2 | match | false | 10 | 4 | 13.1604 | 0.5416 | 0.0299 | 0.0224 | hybrid | structured_no_phase | n2 | [5 empty] | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTG-184900 | H2, CO2 STORAGE SHELTER - CALCULATION | CALCULATION |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Calculation sheet for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8766 | 0.8463 | 0.8463 | FI | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | false | 1 | 1 | 8.8427 | 0.4297 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 |  |  |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184901 | H2, CO2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | PLAN |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Plan for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9590 | 0.9099 | 0.9099 | FI | 0EF3515W32A03 | (H2) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-23 |  |  | query_unknown | h2 | h2 | h2 | query | h2 | match | false | 19 | 9 | 8.9497 | 0.5336 | 0.0272 | 0.0204 | hybrid | structured_no_phase | h2 | [5 empty] | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184902 | H2, CO2 STORAGE SHELTER - ELEVATION | ELEVATION |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Elevation Drawing for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | H2, CO2 Supply System | Nameplate DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5982 | 0.5295 | 0.5295 | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | false | 1 | 1 | 8.8427 | 0.4338 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184903 | H2, CO2 STORAGE SHELTER - MAIN SECTION | SECTION |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | SECTION for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8804 | 0.7641 | 0.7641 | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  | query_unknown | h2 | h2 | h2 | query | wts | mismatch | false | 1 | 17 | 16.7713 | 0.5311 | 0.0294 | 0.0055 | hybrid | structured_no_phase | h2 | [8 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184951 | H2, CO2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Plan for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9641 | 0.9114 | 0.9114 | FI | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | false | 1 | 1 | 11.1757 | 0.5686 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 |  |  |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184952 | H2, CO2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Plan for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.9000 | 0.9602 | 0.9181 | 0.9181 | FI | 0EF3515W32A03 | (H2) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-23 |  |  | query_unknown | h2 | h2 | h2 | query | h2 | match | false | 19 | 14 | 8.9497 | 0.5280 | 0.0262 | 0.0196 | hybrid | structured_no_phase | h2 | [5 empty] | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184953 | H2, CO2 STORAGE SHELTER - FRAMING ELEVATION | ELEVATION |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Elevation Drawing for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | H2, CO2 Supply System | Nameplate DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5982 | 0.5295 | 0.5295 | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | false | 1 | 1 | 8.8427 | 0.4428 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTG-184954 | H2, CO2 STORAGE SHELTER - REBAR DETAIL | REBAR DETAIL |  |  | H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER |  | REBAR DETAIL for H2, CO2 STORAGE SHELTER ¦ Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | carbon¦co2¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9009 | 0.8703 | 0.8703 | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  | civil_design | query_unknown | h2 | h2 | h2 | query | wts | mismatch | false | 9 | 14 | 14.9977 | 0.4922 | 0.0280 | 0.0053 | hybrid | structured_no_phase | h2 | [8 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185151 | PIPE RACK #1 - FOUNDATION PLAN | PLAN |  |  | PIPE RACK #1 |  | Plan for PIPE RACK #1 | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8564 | 0.7819 | 0.7819 | FI | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 9 | 1 | 19.4405 | 0.7712 | 0.0309 | 0.0232 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-03 | 2024-07-03 | 2024-08-02 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185152 | PIPE RACK #1 - COLUMN LOCATION PLAN & BASE PLATE DETAIL | PLAN & BASE PLATE DETAIL |  |  | PIPE RACK #1 |  | PLAN & BASE PLATE DETAIL for PIPE RACK #1 | PIPE RACK | PIPE RACK #2 - BASE PLATE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8911 | 0.9673 | 0.9673 | FI | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | 20 | 1 | 17.3784 | 0.6491 | 0.0289 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2024-06-03 | 2024-07-03 | 2024-08-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185153 | PIPE RACK #1 - FRAMING PLAN | PLAN |  |  | PIPE RACK #1 |  | Plan for PIPE RACK #1 | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8564 | 0.7819 | 0.7819 | FI | 1CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2008-02-18 | 2008-05-31 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | 17 | 1 | 17.7192 | 0.7151 | 0.0294 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2024-11-20 | 2024-12-20 | 2025-01-19 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185154 | PIPE RACK #1 - ELEVATION | ELEVATION |  |  | PIPE RACK #1 |  | Elevation Drawing for PIPE RACK #1 |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6978 | 0.6760 | 0.4732 | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 16 | 1 | 17.4914 | 0.6624 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185155 | PIPE RACK #1 - FOUNDATION & PEDETAL DETAIL | DETAIL |  |  | PIPE RACK #1 |  | Detail Drawing for PIPE RACK #1 | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8253 | 0.7726 | 0.7726 | FI | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 4 | 3 | 20.3280 | 0.7161 | 0.0315 | 0.0236 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185160 | PIPE RACK #2 - FOUNDATION PLAN | PLAN |  |  | PIPE RACK #2 |  | Plan for PIPE RACK #2 | PIPE RACK | PIPE RACK #2 - FRAMING PLAN - 2 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8546 | 0.7814 | 0.7814 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 3 | 1 | 21.0420 | 0.7495 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185161 | PIPE RACK #2 - COLUMN LOCATION PLAN | PLAN |  |  | PIPE RACK #2 |  | Plan for PIPE RACK #2 | PIPE RACK | PIPE RACK #2 - FRAMING PLAN - 2 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8546 | 0.7814 | 0.7814 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | 6 | 7 | 18.8795 | 0.6432 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185162 | PIPE RACK #2 - FRAMING PLAN - 1 | PLAN |  |  | PIPE RACK #2 |  | Plan for PIPE RACK #2 | PIPE RACK | PIPE RACK #2 - FRAMING PLAN - 2 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8546 | 0.7814 | 0.7814 | FI | 2CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2008-03-18 | 2008-06-30 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | 7 | 2 | 19.5068 | 0.6956 | 0.0311 | 0.0175 | hybrid | structured_no_system | [6 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185163 | PIPE RACK #2 - FRAMING PLAN - 2 | PLAN |  |  | PIPE RACK #2 |  | Plan for PIPE RACK #2 | PIPE RACK | PIPE RACK #2 - FRAMING PLAN - 2 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8546 | 0.7814 | 0.7814 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | 5 | 4 | 21.2217 | 0.6700 | 0.0310 | 0.0174 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185164 | PIPE RACK #2 - LINE ELEVATION | ELEVATION |  |  | PIPE RACK #2 |  | Elevation Drawing for PIPE RACK #2 |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6874 | 0.6729 | 0.4710 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 4 | 6 | 18.8795 | 0.6259 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185165 | PIPE RACK #2 - ROW ELEVATION | ELEVATION |  |  | PIPE RACK #2 |  | Elevation Drawing for PIPE RACK #2 |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6874 | 0.6729 | 0.4710 | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 4 | 9 | 18.8795 | 0.6263 | 0.0301 | 0.0226 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185166 | PIPE RACK #2 - FOUNDATION DETAIL | DETAIL |  |  | PIPE RACK #2 |  | Detail Drawing for PIPE RACK #2 | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8218 | 0.7715 | 0.7715 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 2 | 2 | 21.0420 | 0.7346 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185167 | PIPE RACK #2 - PEDETAL DETAIL | DETAIL |  |  | PIPE RACK #2 |  | Detail Drawing for PIPE RACK #2 | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8218 | 0.7715 | 0.7715 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 5 | 1 | 18.8795 | 0.6739 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185168 | PIPE RACK #2 - BASE PLATE DETAIL | DETAIL |  |  | PIPE RACK #2 |  | Detail Drawing for PIPE RACK #2 | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8218 | 0.7715 | 0.7715 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 5 | 1 | 18.8795 | 0.6667 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185169 | PIPE RACK #3 - FOUNDATION PLAN | PLAN |  |  | PIPE RACK #3 |  | Plan for PIPE RACK #3 | PIPE RACK | PIPE RACK #3 - FRAMING PLAN - 1 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8487 | 0.7796 | 0.7796 | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 3 | 2 | 21.0730 | 0.7457 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185170 | PIPE RACK #3 - COLUMN LOCATION PLAN | PLAN |  |  | PIPE RACK #3 |  | Plan for PIPE RACK #3 | PIPE RACK | PIPE RACK #3 - FRAMING PLAN - 1 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8487 | 0.7796 | 0.7796 | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | 7 | 6 | 18.9105 | 0.6389 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185171 | PIPE RACK #3 - FRAMING PLAN - 1 | PLAN |  |  | PIPE RACK #3 |  | Plan for PIPE RACK #3 | PIPE RACK | PIPE RACK #3 - FRAMING PLAN - 1 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8487 | 0.7796 | 0.7796 | FI | 3CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2008-04-19 | 2008-08-01 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | 7 | 3 | 19.5369 | 0.6858 | 0.0308 | 0.0173 | hybrid | structured_no_system | [6 empty] | 2025-01-20 | 2025-02-19 | 2025-03-21 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185172 | PIPE RACK #3 - FRAMING PLAN - 2 | PLAN |  |  | PIPE RACK #3 |  | Plan for PIPE RACK #3 | PIPE RACK | PIPE RACK #3 - FRAMING PLAN - 1 | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8487 | 0.7796 | 0.7796 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | 10 | 4 | 18.8795 | 0.6730 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185173 | PIPE RACK #3 - LINE ELEVATION | ELEVATION |  |  | PIPE RACK #3 |  | Elevation Drawing for PIPE RACK #3 |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6829 | 0.6715 | 0.4701 | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 5 | 6 | 18.9105 | 0.6176 | 0.0305 | 0.0229 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.30 | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185174 | PIPE RACK #3 - ROW SECTION | SECTION |  |  | PIPE RACK #3 |  | SECTION for PIPE RACK #3 | PIPE RACK | PIPE RACK #3 - ROW SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8811 | 0.7893 | 0.7893 | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  | procurement | query_unknown |  |  |  |  | bop | query_unscoped | false | 1 | 3 | 20.9512 | 0.6082 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185175 | PIPE RACK #3 - FOUNDATION DETAIL | DETAIL |  |  | PIPE RACK #3 |  | Detail Drawing for PIPE RACK #3 | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8150 | 0.7695 | 0.7695 | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 2 | 3 | 21.0730 | 0.7342 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185176 | PIPE RACK #3 - PEDETAL & TIE GIRDER DETAIL | DETAIL |  |  | PIPE RACK #3 |  | Detail Drawing for PIPE RACK #3 | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8150 | 0.7695 | 0.7695 | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 6 | 2 | 18.9105 | 0.6507 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185177 | PIPE RACK #3 - BASE PLATE DETAIL | DETAIL |  |  | PIPE RACK #3 |  | Detail Drawing for PIPE RACK #3 | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8150 | 0.7695 | 0.7695 | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 6 | 2 | 18.9105 | 0.6630 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185178 | PIPE RACK - MISC DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8340 | 0.7752 | 0.7752 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 15 | 1 | 16.5373 | 0.6781 | 0.0297 | 0.0223 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185190 | PIPE RACK #1 - CALCULATION | CALCULATION |  |  | PIPE RACK #1 |  | Calculation sheet for PIPE RACK #1 | PIPE RACK | PIPE RACK #1 - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8823 | 0.9647 | 0.9647 | FI | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 16 | 1 | 17.4914 | 0.6952 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185191 | PIPE RACK #2 - CALCULATION | CALCULATION |  |  | PIPE RACK #2 |  | Calculation sheet for PIPE RACK #2 | PIPE RACK | PIPE RACK #2 - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8784 | 0.9635 | 0.9635 | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 4 | 4 | 18.8795 | 0.6560 | 0.0312 | 0.0234 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185192 | PIPE RACK #3 - CALCULATION | CALCULATION |  |  | PIPE RACK #3 |  | Calculation sheet for PIPE RACK #3 | PIPE RACK | PIPE RACK #3 - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8829 | 0.9649 | 0.9649 | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | 5 | 5 | 18.9105 | 0.6546 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185701 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR PLAN, ROOF PLAN | PLAN | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7622 | 0.6953 | 0.6953 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 12 | 8 | 23.1098 | 0.6149 | 0.0286 | 0.0286 | hybrid | structured_preferred | hrsg | procurement | 10 | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185751 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR FRAMING PLAN | PLAN | HRSG ¦ Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7622 | 0.6953 | 0.6953 | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | false | 14 | 16 | 23.1098 | 0.6469 | 0.0267 | 0.0267 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0GEN-185800 | CHEMICAL DOSING SHELTER FOR STG & HRSG - CALCULATION | CALCULATION | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | Calculation sheet for STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7495 | 0.6915 | 0.6915 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | hrsg¦stg | hrsg | hrsg¦stg | query | gsut_uat¦stg | match | false | 1 | 7 | 24.7338 | 0.6030 | 0.0313 | 0.0313 | hybrid | structured_preferred | hrsg¦stg | civil_design | 10 | 2025-05-11 | 2025-06-10 | 2025-07-10 | 2025-07-25 | 2025-08-09 | 2025-08-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185801 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR PLAN, ROOF PLAN | PLAN | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7622 | 0.6953 | 0.6953 | FA | 2PF6500W70A07P | (STG #20 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-06-29 | 2008-07-14 | procurement | procurement | match | hrsg¦stg | hrsg | hrsg¦stg | query | gsut_uat¦stg | match | false | 4 | 3 | 29.5583 | 0.6531 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | hrsg¦stg | procurement |  | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185802 | CHEMICAL DOSING SHELTER FOR STG & HRSG - ELEVATION | ELEVATION | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | Elevation Drawing for HRSG | Chemical Dosing System | Name Plate DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5890 | 0.4100 | 0.4100 | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | hrsg¦stg | wts | hrsg¦stg | query | gsut_uat¦stg | match | false | 1 | 4 | 24.7338 | 0.6425 | 0.0320 | 0.0320 | hybrid | structured_preferred | hrsg¦stg | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185803 | CHEMICAL DOSING SHELTER FOR STG & HRSG - MAIN SECTION | MAIN SECTION | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | MAIN SECTION for HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦heat¦hrsg¦recovery¦steam¦stg | hrsg¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.6155 | 0.5346 | 0.5346 | FI | 1CF6500W70A09 | (STG #10 & UST Shelter) Installation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-08-10 | 2008-10-08 |  | installation | query_unknown | hrsg¦stg | hrsg¦stg¦wts | hrsg¦stg | query | gsut_uat¦stg | match | false | 2 | 20 | 31.9494 | 0.6112 | 0.0286 | 0.0215 | hybrid | structured_no_phase | hrsg¦stg | [5 empty] | 2025-05-13 | 2025-06-12 | 2025-07-12 | fi_complete | 0.90 | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185851 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN | PLAN | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7622 | 0.6953 | 0.6953 | FA | 2PF6500W70A07P | (STG #20 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-06-29 | 2008-07-14 | procurement | procurement | match | hrsg¦stg | hrsg | hrsg¦stg | query | gsut_uat¦stg | match | false | 2 | 3 | 29.5583 | 0.6775 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg¦stg | procurement |  | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185852 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7622 | 0.6953 | 0.6953 | FA | 2PF6500W70A07P | (STG #20 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-06-29 | 2008-07-14 | procurement | procurement | match | hrsg¦stg | hrsg | hrsg¦stg | query | gsut_uat¦stg | match | false | 4 | 3 | 29.5583 | 0.6684 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | hrsg¦stg | procurement |  | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185853 | CHEMICAL DOSING SHELTER FOR STG & HRSG - FRAMING ELEVATION | FRAMING ELEVATION | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | FRAMING ELEVATION for STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator | [5 empty] | rule_query | other | other | framing_elevation | chemical_dosing_shelter_for_stg_and_hrsg_framing_elevation | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine | hrsg¦stg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6250 | 0.7123 | 0.6512 | 0.6512 |  | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  | civil_design | query_unknown | hrsg¦stg |  | hrsg¦stg | query | gsut_uat¦stg | match | false | 1 | 2 | 24.7338 | 0.6655 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hrsg¦stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0GEN-185854 | CHEMICAL DOSING SHELTER FOR STG & HRSG - REBAR DETAIL | DETAIL | STG & HRSG ¦ Steam Turbine Generator & Heat Recovery Steam Generator |  |  |  | Detail Drawing for HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam¦stg | hrsg¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9720 | 0.9916 | 0.9916 | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | hrsg¦stg | hrsg¦stg¦wts | hrsg¦stg | query | gsut_uat¦stg | match | false | 2 | 11 | 24.7338 | 0.6315 | 0.0302 | 0.0302 | hybrid | structured_cell_found_text_preferred | hrsg¦stg | civil_design |  |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-186100 | FGS ELECTRICAL BUILDING - CALCULATION | CALCULATION |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8172 | 0.9452 | 0.9452 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 4 | 2 | 10.8160 | 0.5121 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186101 | FGS ELECTRICAL BUILDING - GROUND FLOOR, ROOF PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | PLAN |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Plan for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - GROUND FLOOR, ROOF PLAN & INTERIOR finish SCHEDULE(INCL. DOOR & WINDOW) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9636 | 0.9891 | 0.9891 | FI | 0CF3520W24A10.1 | (FGS LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 |  |  | query_unknown | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 3 | 27 | 18.4989 | 0.5176 | 0.0274 | 0.0205 | hybrid | structured_no_phase | electrical¦fgp | [5 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186103 | FGS ELECTRICAL BUILDING - SIDE WALL ELEVATION | ELEVATION |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Elevation Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6063 | 0.6486 | 0.6486 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 4 | 1 | 10.8160 | 0.5584 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186104 | FGS ELECTRICAL BUILDING - MAIN SECTION | MAIN SECTION |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | MAIN SECTION for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8491 | 0.9547 | 0.9547 | FI | 0CF3520W24A10.1 | (FGS LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 |  |  | query_unknown | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 1 | 60 | 12.3509 | 0.5630 | 0.0247 | 0.0185 | hybrid | structured_no_phase | electrical¦fgp | [5 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186151 | FGS ELECTRICAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Plan for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9589 | 0.9877 | 0.9877 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 3 | 13 | 14.2104 | 0.5944 | 0.0296 | 0.0296 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | civil_design |  |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186152 | FGS ELECTRICAL BUILDING - GROUND FLOOR & ROOF FRAMING PLAN | PLAN |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Plan for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - GROUND FLOOR & ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9560 | 0.9868 | 0.9868 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  |  | civil_design | query_unknown | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 18 | 1 | 10.8160 | 0.5643 | 0.0292 | 0.0219 | hybrid | structured_no_phase | electrical¦fgp | [5 empty] | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186154 | FGS ELECTRICAL BUILDING - LINE & ROW FRAMING ELEVATION | ELEVATION |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Elevation Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6063 | 0.6486 | 0.6486 | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 4 | 1 | 10.8160 | 0.5710 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186155 | FGS ELECTRICAL BUILDING - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Detail Drawing for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Equipment (incl. pump) Detail DraWing | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | electrical¦fgp¦fgs¦fuel¦gas | fgp¦pump | scoped | match | match | match | passed |  | 0.6250 | 0.6959 | 0.6463 | 0.6463 | FA | 0CF3520W16A03.1 | (FGS LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-09-14 | 2007-11-10 | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | 3 | 11 | 13.3499 | 0.5510 | 0.0300 | 0.0300 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | civil_design |  | 2025-02-01 | 2025-03-01 | 2025-03-29 | 2025-03-22 | 2025-04-19 | 2025-05-17 | generated | 0.90 | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186156 | FGS ELECTRICAL BUILDING - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING |  | Schedule for FGS ELECTRICAL BUILDING ¦ Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦fgp¦fgs¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9662 | 0.9899 | 0.9899 | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  |  | civil_design | query_unknown | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | 10 | 1 | 10.8163 | 0.5396 | 0.0307 | 0.0230 | hybrid | structured_no_phase | electrical¦fgp | [5 empty] | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UGD-186600 | NAOCL DOSING SKID SHELTER - CALCULATION | CALCULATION |  |  | NAOCL DOSING SKID SHELTER |  | Calculation sheet for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8953 | 0.9686 | 0.9686 | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 8 | 4 | 7.8531 | 0.5318 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-186601 | NAOCL DOSING SKID SHELTER - GROUND & ROOF FLOOR PLAN | PLAN |  |  | NAOCL DOSING SKID SHELTER |  | Plan for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - GROUND & ROOF FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  | civil_design | query_unknown |  |  |  |  | wts | query_unscoped | false | 22 | 29 | 7.8531 | 0.4795 | 0.0234 | 0.0132 | hybrid | structured_no_system | [6 empty] | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-186602 | NAOCL DOSING SKID SHELTER - ELEVATION & SECTION | DRAWING |  |  | NAOCL DOSING SKID SHELTER |  | DRAWING for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - ELEVATION & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7916 | 0.7041 | 0.7041 | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 9 | 6 | 7.8531 | 0.5708 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-186651 | NAOCL DOSING SKID SHELTER - FND, GROUND, ROOF FRAMING PLAN & FRAMING ELEVATION | DRAWING |  |  | NAOCL DOSING SKID SHELTER |  | DRAWING for NAOCL DOSING SKID SHELTER | Chemical Dosing System | Name Plate DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | drawing | drawing | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5793 | 0.4071 | 0.4071 | FI | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | 1 | 7 | 7.8531 | 0.5537 | 0.0313 | 0.0313 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-186652 | NAOCL DOSING SKID SHELTER - REBAR DETAIL | DETAIL |  |  | NAOCL DOSING SKID SHELTER |  | Detail Drawing for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7864 | 0.8192 | 0.8192 | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 10 | 9 | 7.8531 | 0.5197 | 0.0288 | 0.0216 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-186800 | AUX. LEB - CALCULATION | CALCULATION |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Calculation sheet for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 0.7548 | 0.9264 | 0.9264 | FI | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | 4 | 4 | 3.1906 | 0.3575 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186801 | AUX. LEB - GROUND FLOOR PLAN & ROOF PLAN | PLAN |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Plan for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 0.5000 | 0.7080 | 0.5624 | 0.5624 | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | electrical |  | electrical | query |  | activity_unscoped | true | 1 | 20 | 36.0912 | 0.4632 | 0.0289 | 0.0130 | hybrid | structured_no_phase | electrical | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186802 | AUX. LEB - SIDE WALL ELEVATION | ELEVATION |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Elevation Drawing for AUX. LEB ¦ Auxiliary Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | aux¦auxiliary¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.4971 | 0.8491 | 0.5944 | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 5 | 4 |  | 0.4093 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186803 | AUX. LEB - MAIN SECTION | SECTION |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | SECTION for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 0.7500 | 0.7631 | 0.7539 | 0.7539 | FI | 2PF1600W90A11.1T | (HRSG #22 LEB) Transportataion - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2008-08-02 | 2008-09-15 |  |  | query_unknown | electrical |  | electrical | query | hrsg | mismatch | false | 255 | 1 | 4.4572 | 0.4630 | 0.0196 | 0.0037 | hybrid | structured_no_phase | electrical | [8 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186851 | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Plan for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 0.5000 | 0.7080 | 0.5624 | 0.5624 | FI | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 10 | 1 | 3.4893 | 0.4679 | 0.0307 | 0.0307 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186852 | AUX. LEB - GROUND FLOOR FRAMING PLAN & ROOF FRAMING PLAN | PLAN |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Plan for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 0.5000 | 0.7080 | 0.5624 | 0.5624 | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | electrical |  | electrical | query |  | activity_unscoped | true | 1 | 19 | 36.0912 | 0.4584 | 0.0291 | 0.0131 | hybrid | structured_no_phase | electrical | [5 empty] | 2024-03-01 | 2024-03-01 | 2024-03-01 | fi_complete | 0.90 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186853 | AUX. LEB - LINE & ROW FRAMING ELEVATION | ELEVATION |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Elevation Drawing for AUX. LEB ¦ Auxiliary Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | aux¦auxiliary¦electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.4971 | 0.8491 | 0.5944 | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | 5 | 6 |  | 0.4322 | 0.0305 | 0.0305 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186854 | AUX. LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Detail Drawing for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | 24 | 2 | 2.0152 | 0.4583 | 0.0280 | 0.0280 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186855 | AUX. LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | AUX. LEB ¦ Auxiliary Local Electrical Building |  | Schedule for AUX. LEB ¦ Auxiliary Local Electrical Building |  | AUX. LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | aux¦auxiliary¦electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 0.3750 | 0.6499 | 0.4575 | 0.4575 | FI | 2CF1600W32A04 | (HRSG #21 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2008-03-31 | 2008-06-25 |  |  | query_unknown | electrical |  | electrical | query | hrsg | mismatch | false | 76 | 10 | 4.5740 | 0.5006 | 0.0216 | 0.0041 | hybrid | structured_no_phase | electrical | [8 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0ZEN-189000 | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | DESIGN CRITERIA |  |  |  |  | DESIGN CRITERIA |  | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | criteria | criteria | design_criteria | design_criteria |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | [5 empty] | query_unscoped | true | 1 | 1 | 62.3058 | 0.6559 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | design_criteria¦system_design¦civil_design |  | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | 0.46 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0HBD-189001 | YARD PLATFORM | PLATFORM |  |  |  |  | PLATFORM | [5 empty] | rule_query | other | other | platform | yard_platform |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.6285 | 0.4219 | 0.2953 |  | 1CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Oil Supply System (GTG) | 2008-03-03 | 2008-05-02 |  |  | query_unknown |  |  |  |  | bop¦gtg | query_unscoped | false | 4 | 18 | 8.9418 | 0.4343 | 0.0284 | 0.0160 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0HBD-189002 | PEECC PLATFORM | [7 empty] | PEECC PLATFORM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | peecc_platform | peecc_platform |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | 21 | 22 |  | 0.3841 | 0.0245 | 0.0110 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VL00-P0MPA-220001 | CIVIL - STG FOUNDATION - SHAPE UNIT P6 |  | STG ¦ Steam Turbine Generator |  |  |  | for STG ¦ Steam Turbine Generator | [5 empty] | rule_query | other | drawing | civil_stg_foundation_shape_unit_p6 | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6160 | 0.6048 | 0.6048 |  | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg |  | stg | query | gsut_uat¦stg | match | false | 1 | 15 | 25.3597 | 0.6841 | 0.0297 | 0.0297 | hybrid | structured_cell_found_text_preferred | stg | civil_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VL00-P7MPA-220002 | CIVIL - STG FOUNDATION - SHAPE - UNIT P7 |  | STG ¦ Steam Turbine Generator |  |  |  | for STG ¦ Steam Turbine Generator | [5 empty] | rule_query | other | drawing | civil_stg_foundation_shape_unit_p7 | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6160 | 0.6048 | 0.6048 |  | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg |  | stg | query | gsut_uat¦stg | match | false | 1 | 16 | 25.3597 | 0.6789 | 0.0296 | 0.0296 | hybrid | structured_cell_found_text_preferred | stg | civil_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UF00-P0MAA-220003 | ST FOUNDATION LOAD - PLAN | PLAN | ST ¦ Steam Turbine |  |  |  | Plan for ST ¦ Steam Turbine |  | ST FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.8593 | 0.9578 | 0.9578 | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | false | 1 | 1 | 15.7722 | 0.6937 | 0.0328 | 0.0328 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XM00-P0MAA-220015 | LAYDOWN PLAN - UNIT P6 & P7 | PLAN |  |  |  |  | Plan |  | LAYDOWN PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7937 | 0.7048 | 0.4933 | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | 1 | 1 | 24.0608 | 0.5139 | 0.0328 | 0.0148 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0MPA-220023 | STG FOUNDATION - DESIGN CRITERIA - UNIT P6 & P7 |  | STG ¦ Steam Turbine Generator |  |  |  | for STG ¦ Steam Turbine Generator | Intake Screening System | Design Criteria | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | criteria | criteria | design_criteria | design_criteria | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.4281 | 0.4084 | 0.4084 | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_criteria | civil_design | compatible | stg |  | stg | query | gsut_uat¦stg | match | false | 4 | 10 | 25.8126 | 0.6686 | 0.0299 | 0.0224 | hybrid | structured_preferred | stg | design_criteria¦system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220025 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P6 | P&I DIAGRAM |  | STEAM TURBINE SYSTEM |  |  | P&ID for STEAM TURBINE SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6637 | 0.5491 | 0.5491 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | stg | h2 | stg | query |  | activity_unscoped | true | 22 | 28 | 20.5703 | 0.6336 | 0.0236 | 0.0141 | hybrid | structured_blocked_procurement_conflict | stg | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.46 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220026 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P7 | P&I DIAGRAM |  | STEAM TURBINE SYSTEM |  |  | P&ID for STEAM TURBINE SYSTEM | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6608 | 0.5482 | 0.5482 | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | stg |  | stg | query |  | activity_unscoped | true | 22 | 37 | 20.5703 | 0.6278 | 0.0225 | 0.0135 | hybrid | structured_blocked_procurement_conflict | stg | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 0.46 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220027 | P&I DIAGRAM HPH - UNIT P6 | P&I DIAGRAM |  |  |  |  | P&ID |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6785 | 0.6702 | 0.6702 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match |  | hrsg | hrsg | rule | hrsg | match | false | 1 | 1 | 15.5570 | 0.6358 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design¦procurement | 10 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220028 | P&I DIAGRAMS HPH - UNIT P7 | P&I DIAGRAMS |  |  |  |  | P&I DIAGRAMS |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7073 | 0.4455 | 0.4455 | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match |  | hrsg | hrsg | rule | hrsg | match | false | 504 | 9 | 6.2923 | 0.5912 | 0.0163 | 0.0163 | hybrid | structured_blocked_procurement_conflict | hrsg | system_design¦procurement |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 0.52 | needs_review | default_fc_window;rule_scope_status=query_unscoped;rule_score_medium;activity_scope_source=rule;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220029 | P&I DIAGRAM LUBRICATION OIL - UNIT P6 | P&I DIAGRAM |  | LUBE OIL SYSTEM |  |  | P&ID for LUBE OIL SYSTEM |  | P&I Diagram Oil | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | p_id | p_id | lube¦oil |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7673 | 0.9302 | 0.6511 | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 1 | 2 | 21.9247 | 0.6355 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220030 | P&I DIAGRAM LUBRICATION OIL - UNIT P7 | P&I DIAGRAM |  | LUBE OIL SYSTEM |  |  | P&ID for LUBE OIL SYSTEM |  | P&I Diagram Oil | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | p_id | p_id | lube¦oil |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7667 | 0.9300 | 0.6510 | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 1 | 2 | 21.9247 | 0.6375 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE01-P6MAA-220047 | ALLOWABLE LOADINGS AND DISPLACEMENTS | [7 empty] | AlloWable loadings and displacements | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | allowable_loadings_and_displacements | allowable_loadings_and_displacements |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8484 | 0.9545 | 0.6682 | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | 2442 | 1 |  | 0.3865 | 0.0168 | 0.0094 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR00-P6MAA-220073 | CONTROL SYSTEM ARCHITECTURE |  |  | control system |  |  | for control system |  | Control system architecture | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | control_system_architecture | control_system_architecture |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8950 | 0.9685 | 0.6780 | FA | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | 1 | 1 | 10.5120 | 0.5008 | 0.0328 | 0.0184 | hybrid | structured_no_system |  |  |  | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-04-19 | 2025-05-19 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG01-P6MAA-220089 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P6 | DETAIL DRAWINGS |  | Piping |  |  | DETAIL DRAWINGS for Piping |  | Detail DraWings. Piping and BOM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | piping |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7094 | 0.9128 | 0.6390 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 104 | 3 | 7.7414 | 0.5721 | 0.0220 | 0.0124 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG01-P7MAA-220090 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P7 | DETAIL DRAWINGS |  | Piping |  |  | DETAIL DRAWINGS for Piping |  | Detail DraWings. Piping and BOM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | piping |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7081 | 0.9124 | 0.6387 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 104 | 8 | 7.7414 | 0.5641 | 0.0208 | 0.0117 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XS01-P6MAA-220093 | CONTROL SYSTEM FUNCTIONS PHILOSOPHY | Philosophy |  | control system |  |  | Philosophy for control system | [5 empty] | rule_query | other | description | philosophy | control_description |  | fgp | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.6000 | 0.5196 | 0.5759 | 0.5759 |  | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | 2 | 2 | 10.5120 | 0.4590 | 0.0323 | 0.0181 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL13-P6MAA-220095 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (HW) | LIST | TCS AND DCS ¦ TURBINE CONTROL SYSTEM AND Distributed Control System |  |  |  | LIST for TCS AND DCS ¦ TURBINE CONTROL SYSTEM AND Distributed Control System | [5 empty] | rule_query | other | list | list | io_list | dcs¦distributed¦tcs¦turbine | dcs¦hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6050 | 0.6482 | 0.6482 |  | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 |  | commissioning | query_unknown | dcs |  | dcs | query | dcs¦electrical | match | false | 1 | 1 | 48.9330 | 0.6343 | 0.0328 | 0.0246 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P6MAA-220097 | LOGIC DIAGRAMS FOR ST | LOGIC DIAGRAMS | ST ¦ Steam Turbine |  |  |  | LOGIC DIAGRAMS for ST ¦ Steam Turbine |  | Logic Diagrams | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6113 | 0.6501 | 0.4550 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 16.8199 | 0.6118 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | stg | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.68 | needs_review | rule_scope_status=rule_generic;rule_score_medium;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL13-P6MAA-220143 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (SW) - UNIT 1+2 | LIST | TCS AND DCS ¦ TURBINE CONTROL SYSTEM AND Distributed Control System |  |  |  | LIST for TCS AND DCS ¦ TURBINE CONTROL SYSTEM AND Distributed Control System | [5 empty] | rule_query | other | list | list | io_list | dcs¦distributed¦tcs¦turbine | dcs¦hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6050 | 0.6482 | 0.6482 |  | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 |  | commissioning | query_unknown | dcs |  | dcs | query | dcs¦electrical | match | false | 1 | 1 | 48.9330 | 0.6394 | 0.0328 | 0.0246 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CM01-P6MAA-220205 | DRAWINGS, PART LISTS OF TURBINE – UNIT P6 | [7 empty] | DRAWINGS, PART LISTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7287 | 0.9186 | 0.6430 | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible |  |  |  |  | gsut_uat¦stg | query_unscoped | false | 1 | 709 | 7.9900 | 0.4729 | 0.0177 | 0.0100 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CM01-P7MAA-220206 | DRAWINGS, PART LISTS OF TURBINE – UNIT P7 | [7 empty] | DRAWINGS, PART LISTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7266 | 0.9180 | 0.6426 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible |  |  |  |  | gsut_uat¦stg | query_unscoped | false | 23 | 87 | 7.7130 | 0.5194 | 0.0189 | 0.0106 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL08-P6MAA-220207 | TRIPS & ALARMS SETTINGS UNIT P6+P7 | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [6 empty] | 0PF6500W70A03.6T | (Electrical Protection Panel) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-03-11 | 2008-04-24 |  | delivery | query_unknown |  |  |  |  | electrical | query_unscoped | false | 613 | 1 |  | 0.4250 | 0.0179 | 0.0101 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P6CJJ-220275 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P6 | SPECIFICATION |  | CONTROL SYSTEM |  |  | Technical Specification for CONTROL SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5852 | 0.5256 | 0.5256 | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match |  |  |  |  | dcs | query_unscoped | false | 1 | 1 | 18.3160 | 0.5277 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P7CJJ-220276 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P7 | SPECIFICATION |  | CONTROL SYSTEM |  |  | Technical Specification for CONTROL SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5852 | 0.5256 | 0.5256 | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match |  |  |  |  | dcs | query_unscoped | false | 1 | 1 | 18.3160 | 0.5212 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P6CJJ-220277 | HMI DESIGN – UNIT P6 | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [6 empty] | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 |  | civil_design | query_unknown |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | 16 | 19 | 6.9050 | 0.4090 | 0.0258 | 0.0145 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P7CJJ-220278 | HMI DESIGN – UNIT P7 | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [6 empty] | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 |  | civil_design | query_unknown |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | 16 | 9 | 6.9050 | 0.4198 | 0.0277 | 0.0156 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P6CJJ-220293 | INSTRUMENTATION DATA SHEETS - UNIT P6 | DATA SHEETS |  |  |  |  | DATA SHEETS |  | Instrumentation data sheets | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | datasheet | datasheet | data_sheet | data_sheet |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7793 | 0.9338 | 0.6537 | FA | 1EF3515W00A02 | (N2 Gas System) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-27 | 2007-07-31 | procurement | procurement | match |  |  |  |  | n2 | query_unscoped | false | 41 | 33 | 9.3892 | 0.4526 | 0.0207 | 0.0155 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-28 | generated | 0.30 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT02-P7CJJ-220294 | INSTRUMENTATION DATA SHEETS - UNIT P7 | DATA SHEETS |  |  |  |  | DATA SHEETS |  | Instrumentation data sheets | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | datasheet | datasheet | data_sheet | data_sheet |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7840 | 0.9352 | 0.6546 | FA | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 81 | 20 | 9.0366 | 0.4557 | 0.0196 | 0.0147 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P6MAA-220383 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P6 | ISOMETRIC DRAWINGS |  | PIPELINES |  |  | ISOMETRIC DRAWINGS for PIPELINES | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | pipelines |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6363 | 0.4709 | 0.4709 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  | compressed_air | compressed_air | rule | compressed_air | match | false | 1 | 1 | 4.8366 | 0.5189 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P7MAA-220384 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P7 | ISOMETRIC DRAWINGS |  | PIPELINES |  |  | ISOMETRIC DRAWINGS for PIPELINES | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | pipelines |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6323 | 0.4697 | 0.4697 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  | compressed_air | compressed_air | rule | compressed_air | match | false | 1 | 1 | 4.8366 | 0.5251 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAA-220801 | STEAM TURBINE OUTLINE DRAWING | OUTLINE DRAWING | STEAM TURBINE |  |  |  | Outline Drawing for STEAM TURBINE |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6577 | 0.6640 | 0.6640 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | false | 1 | 2 | 9.7265 | 0.5817 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P6MKA-250001 | ST GENERATOR UNIT#P6 FOUNDATION ARRANGEMENT DRAWING | ARRANGEMENT DRAWING |  |  |  |  | General Arrangement Drawing |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.9450 | 0.9835 | 0.9835 | FA | 3EF6500W00A01 | (STG #30 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match |  |  |  |  | gsut_uat¦stg | query_unscoped | false | 5 | 5 | 17.1205 | 0.6098 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P7MKA-250002 | ST GENERATOR UNIT#P7 FOUNDATION ARRANGEMENT DRAWING | ARRANGEMENT DRAWING |  |  |  |  | General Arrangement Drawing |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.9450 | 0.9835 | 0.9835 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match |  |  |  |  | gsut_uat¦stg | query_unscoped | false | 3 | 5 | 17.1205 | 0.6123 | 0.0313 | 0.0234 | hybrid | structured_no_system |  | civil_design |  | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UF00-P6MKA-250003 | ST GENERATOR FOUNDATION LOADING | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [6 empty] | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match |  |  |  |  | stg | query_unscoped | false | 1 | 4 | 7.4565 | 0.5959 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | civil_design | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250004 | GENERATOR PIPING CONNECTION |  | GENERATOR | PIPING |  |  | for GENERATOR | [5 empty] | rule_query | other | other | generator_piping_connection | gt_generator_outline | generator | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.3333 | 0.7146 | 0.4477 | 0.4477 |  | 1CF2035W58A01 | (ST #10) Piping Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | 2008-08-11 | 2009-01-10 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | false | 1 | 19 | 11.0196 | 0.5712 | 0.0291 | 0.0163 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250005 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION |  | GENERATOR |  |  |  | for GENERATOR | [5 empty] | rule_query | other | other | generator_stator_handling_and_shipping_dimension | gt_generator_outline | generator | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.3333 | 0.7146 | 0.4477 | 0.4477 |  | 2PF1213W42A09T | (GEN #21) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2008-03-01 | 2008-04-15 |  | delivery | query_unknown |  |  |  |  | gtg | query_unscoped | false | 472 | 1 | 2.0660 | 0.4994 | 0.0183 | 0.0103 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250006 | HANDLING DIMENSION FOR GENERATOR ROTOR |  | GENERATOR |  |  |  | for GENERATOR | [5 empty] | rule_query | other | other | handling_dimension_for_generator_rotor | gt_generator_outline | generator | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.3333 | 0.7146 | 0.4477 | 0.4477 |  | 2EF1213W16A06 | (GEN #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-08-29 |  | civil_design | query_unknown |  |  |  |  | gtg | query_unscoped | false | 470 | 1 | 2.0540 | 0.5297 | 0.0183 | 0.0103 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0MKA-250007 | BRUSH HOLDER RIGGING ASSEMBLY | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [6 empty] | 1CF1265W74A04 | (Turning Gear) Installation- Elec. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | 2008-04-24 | 2008-05-01 |  | installation | query_unknown |  |  |  |  | gtg | query_unscoped | false | 1230 | 1 |  | 0.4267 | 0.0172 | 0.0097 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P6MKA-250008 | ST GENERATOR UNIT HYDROGEN COOLER OUTLINE | [7 empty] | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | outline | outline | stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.2472 | 0.3075 | 0.2153 | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | design_drawing | civil_design | compatible |  |  |  |  | h2 | query_unscoped | false | 10 | 106 | 8.8427 | 0.5085 | 0.0203 | 0.0114 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-250009 | GENERATOR DATA SHEET | DATA SHEET | GENERATOR |  |  |  | Data Sheet for GENERATOR |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | title | datasheet | datasheet | data_sheet | data_sheet | generator |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.7328 | 0.6865 | 0.6865 | FA | 3PF1213W42A08P | (GEN #31) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2008-03-31 | procurement | procurement | match |  |  |  |  | gtg | query_unscoped | false | 129 | 1 | 9.4154 | 0.6054 | 0.0217 | 0.0163 | hybrid | structured_no_system |  | procurement |  | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250010 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL | OUTLINE | GENERATOR |  |  |  | OUTLINE for GENERATOR |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | generator |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5070 | 0.3854 | 0.2698 | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 489 | 1268 | 4.0370 | 0.3613 | 0.0026 | 0.0019 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_rule_activity |  | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P6MKA-250011 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P6) | LAYOUT | GENERATOR |  |  |  | Layout Drawing for GENERATOR | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6825 | 0.5548 | 0.5548 | SKIP | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | 16 | 23 | 9.5065 | 0.5660 | 0.0252 | 0.0189 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P7MKA-250012 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P7) | LAYOUT | GENERATOR |  |  |  | Layout Drawing for GENERATOR | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6825 | 0.5548 | 0.5548 | SKIP | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | 50 | 2 | 7.6543 | 0.5872 | 0.0252 | 0.0189 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250013 | CURRENT TRANSFORMER ASSEMBLY | ASSEMBLY | CURRENT TRANSFORMER |  |  |  | ASSEMBLY for CURRENT TRANSFORMER | [5 empty] | rule_query | other | other | assembly | current_transformer_assembly | current¦transformer |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8538 | 0.9561 | 0.6693 |  | 1CF6500W70A14 | (STG TR) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-11-05 | 2008-12-19 |  | installation | query_unknown | gsut_uat |  | gsut_uat | query | electrical¦gsut_uat¦stg | match | false | 19 | 5 | 11.9134 | 0.4956 | 0.0280 | 0.0210 | hybrid | structured_no_phase | gsut_uat | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250014 | STATOR WINDING DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | STATOR WINDING DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | 11 | 101 | 10.0268 | 0.3674 | 0.0203 | 0.0114 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250015 | FIELD CLEARANCE DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FIELD CLEARANCE DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | 31 | 5 | 9.2794 | 0.4282 | 0.0264 | 0.0119 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250016 | ST GENERATOR MECHANICAL OUTLINE | OUTLINE | ST GENERATOR ¦ Steam Turbine GENERATOR |  |  |  | OUTLINE for ST GENERATOR ¦ Steam Turbine GENERATOR |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4079 | 0.3557 | 0.2490 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | false | 1 | 1 | 19.2443 | 0.6431 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | stg | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250017 | STG SOLE PLATE LAYOUT | LAYOUT | STG ¦ Steam Turbine Generator |  |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | design_drawing | civil_design | compatible | stg | stg | stg | query | stg | match | false | 4 | 2 | 18.9069 | 0.6552 | 0.0318 | 0.0238 | hybrid | structured_cell_found_text_preferred | stg | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250018 | STG FLOOR PLATE LAYOUT | LAYOUT | STG ¦ Steam Turbine Generator |  |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | design_drawing | civil_design | compatible | stg | stg | stg | query | stg | match | false | 6 | 1 | 18.9069 | 0.6969 | 0.0315 | 0.0237 | hybrid | structured_cell_found_text_preferred | stg | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MKA-250019 | SUGGESTIONS FOR GROUTING STG WITH FLOWABLE GROUT |  | STG ¦ Steam Turbine Generator |  |  |  | for STG ¦ Steam Turbine Generator | [5 empty] | rule_query | other | drawing | suggestions_for_grouting_stg_with_flowable_grout | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6160 | 0.6048 | 0.6048 |  | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  | civil_design | query_unknown | stg |  | stg | query | gsut_uat¦stg | match | false | 1 | 7 | 16.6112 | 0.5568 | 0.0313 | 0.0235 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250020 | ST GENERATOR TERMINAL BOX ASSEMBLY | ASSEMBLY | ST GENERATOR ¦ Steam Turbine GENERATOR |  |  |  | ASSEMBLY for ST GENERATOR ¦ Steam Turbine GENERATOR | [5 empty] | rule_query | other | drawing | assembly | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6562 | 0.6169 | 0.6169 |  | 1CF2040W42A04 | (STG #10) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2008-10-17 | 2009-02-17 |  | installation | query_unknown | stg |  | stg | query | stg | match | false | 8 | 4 | 16.5145 | 0.6620 | 0.0303 | 0.0227 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MKA-250021 | ROTOR ASSEMBLY DISASSEMBLY NOTE | ASSEMBLY DISASSEMBLY NOTE |  |  |  |  | ASSEMBLY DISASSEMBLY NOTE | [5 empty] | rule_query | other | other | assembly_disassembly_note | disassembly_note |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.6667 | 0.9388 | 0.7483 | 0.5238 |  | 3CF1265W42A03.1 | (Turning Gear) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | 2008-06-14 | 2008-06-21 |  | installation | query_unknown |  |  |  |  | gtg | query_unscoped | false | 3612 | 1 |  | 0.4365 | 0.0167 | 0.0094 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250022 | ROTOR ASSEMBLY DISASSEMBLY DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | ROTOR ASSEMBLY AND DISASSEMBLY DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.9851 | 0.8555 | 0.5989 | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible |  |  |  |  | h2 | query_unscoped | false | 4 | 3310 | 10.5360 | 0.2441 | 0.0159 | 0.0090 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250023 | ST GENERATOR END SHIELD ASSY CE |  | ST GENERATOR ¦ Steam Turbine GENERATOR |  |  |  | for ST GENERATOR ¦ Steam Turbine GENERATOR | [5 empty] | rule_query | other | drawing | st_generator_end_shield_assy_ce | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6911 | 0.6273 | 0.6273 |  | 1PF2040W42A03T | (STG #10) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2008-09-02 | 2008-10-16 |  | delivery | query_unknown | stg |  | stg | query | stg | match | false | 7 | 5 | 16.5145 | 0.6350 | 0.0303 | 0.0227 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250024 | ST GENERATOR END SHIELD ASSY TE |  | ST GENERATOR ¦ Steam Turbine GENERATOR |  |  |  | for ST GENERATOR ¦ Steam Turbine GENERATOR | [5 empty] | rule_query | other | drawing | st_generator_end_shield_assy_te | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6911 | 0.6273 | 0.6273 |  | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg |  | stg | query | stg | match | false | 1 | 11 | 19.2443 | 0.6217 | 0.0305 | 0.0229 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260001 | SEAL OIL DRAIN ENLARGEMENT OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 1CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | 2007-10-01 | 2007-12-26 | design_drawing | civil_design | compatible |  |  |  |  | gtg | query_unscoped | false | 23 | 44 | 10.5155 | 0.4232 | 0.0217 | 0.0122 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-05-19 | 2024-06-03 | 2024-06-18 | 2024-07-03 | 2024-08-02 | 2024-09-01 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260002 | BEARING OIL DRAIN ENLARGEMENT OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 1EF3020W16A09.1 | (Clean Drain Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-12-06 | 2008-05-05 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 15 | 47 | 6.2231 | 0.4277 | 0.0227 | 0.0102 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | 2024-10-07 | 2024-11-06 | generated | 0.30 | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P6MKA-260003 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ISO | ISO | ST GENERATOR ¦ Steam Turbine GENERATOR | AUX SYSTEM PIPING ¦ Auxiliary SYSTEM PIPING |  |  | ISO for ST GENERATOR ¦ Steam Turbine GENERATOR | [5 empty] | rule_query | other | drawing | iso | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6450 | 0.6135 | 0.6135 |  | 1CF2035W58A01 | (ST #10) Piping Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | 2008-08-11 | 2009-01-10 |  |  | query_unknown | stg |  | stg | query | stg | match | false | 4 | 1 | 29.5123 | 0.6811 | 0.0320 | 0.0240 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6MKA-260004 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ARRANGEMENT | ARRANGEMENT | ST GENERATOR ¦ Steam Turbine GENERATOR | AUX SYSTEM PIPING ¦ Auxiliary SYSTEM PIPING |  |  | ARRANGEMENT for ST GENERATOR ¦ Steam Turbine GENERATOR |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4546 | 0.3697 | 0.3143 | FA | 1EF2070W16A01 | (STG #10 Aux. Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-12-24 | 2008-05-21 | design_drawing | civil_design | compatible | stg |  | stg | query | stg | match | false | 1 | 2 | 22.2463 | 0.6325 | 0.0325 | 0.0244 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P6MKA-260005 | ST GENERATOR UNIT#P6 AUX SYSTEM HANGER & SUPPORT |  |  | ST GENERATOR UNIT#P6 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P6 Auxiliary SYSTEM |  |  | for ST GENERATOR UNIT#P6 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P6 Auxiliary SYSTEM | [5 empty] | rule_query | other | diagram | st_generator_unit_p6_aux_system_hanger_and_support | p_id | aux¦auxiliary¦generator¦steam¦stg¦turbine¦unit | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5714 | 0.6588 | 0.5976 | 0.5976 |  | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  | query_unknown | stg |  | stg | query | stg | match | false | 1 | 19 | 32.4322 | 0.6080 | 0.0291 | 0.0218 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P7MKA-260006 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ISO | ISO |  | ST GENERATOR UNIT#P7 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM |  |  | ISO for ST GENERATOR UNIT#P7 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM | [5 empty] | rule_query | other | diagram | iso | p_id | aux¦auxiliary¦generator¦steam¦stg¦turbine¦unit | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5714 | 0.6712 | 0.6013 | 0.6013 |  | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  | query_unknown | stg |  | stg | query | stg | match | false | 1 | 21 | 32.4322 | 0.6360 | 0.0287 | 0.0216 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7MKA-260007 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ARRANGEMENT | ARRANGEMENT |  | ST GENERATOR UNIT#P7 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM |  |  | ARRANGEMENT for ST GENERATOR UNIT#P7 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | aux¦auxiliary¦generator¦steam¦stg¦turbine¦unit |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4251 | 0.3608 | 0.3067 | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | stg |  | stg | query | gsut_uat¦stg | match | false | 1 | 9 | 32.4054 | 0.5849 | 0.0309 | 0.0232 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P7MKA-260008 | ST GENERATOR UNIT#P7 AUX SYSTEM HANGER & SUPPORT |  |  | ST GENERATOR UNIT#P7 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM |  |  | for ST GENERATOR UNIT#P7 AUX SYSTEM ¦ Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM | [5 empty] | rule_query | other | drawing | st_generator_unit_p7_aux_system_hanger_and_support | layout_drawing | aux¦auxiliary¦generator¦steam¦stg¦turbine¦unit | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.5972 | 0.5992 | 0.5992 |  | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  | query_unknown | stg |  | stg | query | stg | match | false | 1 | 16 | 32.4322 | 0.6106 | 0.0296 | 0.0222 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260011 | H2 SEAL OIL UNIT OUTLINE | OUTLINE |  | H2 SEAL OIL UNIT ¦ Hydrogen SEAL OIL UNIT |  |  | OUTLINE for H2 SEAL OIL UNIT ¦ Hydrogen SEAL OIL UNIT |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | hydrogen¦oil¦seal¦unit |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.3708 | 0.3446 | 0.2412 | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | design_drawing | civil_design | compatible | h2 |  | h2 | query | h2 | match | false | 1 | 1 | 26.5282 | 0.4582 | 0.0328 | 0.0246 | hybrid | structured_preferred | h2 | system_design¦civil_design | 3 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260012 | FLOAT TRAP OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 1EF3030W16A01 | (EXP Head Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | ccw | query_unscoped | false | 941 | 1 |  | 0.3672 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 | 0.35 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260013 | LIQUID LEVEL DETECTOR OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | design_drawing | civil_design | compatible |  |  |  |  | condensate¦fgp | query_unscoped | false | 73 | 63 |  | 0.3316 | 0.0156 | 0.0088 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | 2024-04-02 | 2024-05-02 | generated | 0.30 | 0.35 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260014 | GAS CONTROL VALVE STATION OUTLINE | OUTLINE | CONTROL VALVE | GAS CONTROL |  |  | OUTLINE for CONTROL VALVE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | valve |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4373 | 0.3645 | 0.2552 | FA | 1EF3520W32A28 | (Gas COMP House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-05-01 | 2007-10-01 | design_drawing | civil_design | compatible |  |  |  |  | fgp | query_unscoped | false | 637 | 21 | 2.9727 | 0.5484 | 0.0138 | 0.0078 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260015 | H2 BOTTLE MANIFOLD OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible |  |  |  |  | h2 | query_unscoped | false | 15 | 1 | 8.6363 | 0.4601 | 0.0297 | 0.0167 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260016 | CO2 BOTTLE MANIFOLD OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 0CF3520W16A02 | (Gas Buffer) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-12-05 | 2008-02-04 | design_drawing | civil_design | compatible |  |  |  |  | fgp | query_unscoped | false | 81 | 10 |  | 0.4405 | 0.0214 | 0.0120 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | 2024-10-06 | 2024-11-05 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260017 | H2 CONTROL CABINET OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | 31 | 2 | 4.3671 | 0.4268 | 0.0271 | 0.0122 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260018 | H2 GAS DRYER OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible |  |  |  |  | h2 | query_unscoped | false | 16 | 10 | 8.6363 | 0.4972 | 0.0274 | 0.0154 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-260019 | GENERATOR AUX SYSTEM MOTOR & PUMP DATA SHEET | DATA SHEET |  | GENERATOR AUX SYSTEM ¦ GENERATOR Auxiliary SYSTEM |  |  | Data Sheet for GENERATOR AUX SYSTEM ¦ GENERATOR Auxiliary SYSTEM | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | title | datasheet | datasheet | data_sheet | data_sheet | aux¦auxiliary¦generator¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6678 | 0.7254 | 0.7254 | FA | 1PF1265W42A02.8P | (Purge Air System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | 2007-03-01 | 2008-01-31 | procurement | procurement | match |  |  |  |  | compressed_air¦gtg | query_unscoped | false | 40 | 1 | 15.3342 | 0.6154 | 0.0264 | 0.0198 | hybrid | structured_no_system |  | procurement |  | 2024-06-07 | 2024-07-12 | 2024-08-16 | 2024-08-02 | 2024-09-06 | 2024-10-11 | generated | 0.90 | 0.80 | usable | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-260020 | GENERATOR AUX SYSTEM INSTRUMENT DATA SHEET | DATA SHEET |  | GENERATOR AUX SYSTEM ¦ GENERATOR Auxiliary SYSTEM |  |  | Data Sheet for GENERATOR AUX SYSTEM ¦ GENERATOR Auxiliary SYSTEM |  | Instrument Data Sheet & Catalogue | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | datasheet | datasheet | data_sheet | data_sheet | aux¦auxiliary¦generator |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6352 | 0.7156 | 0.7156 | FI | 2PF2070W42A04P | (STG #20 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Auxiliary Equipment | 2007-04-30 | 2008-09-01 | procurement | procurement | match |  |  |  |  | stg | query_unscoped | false | 5 | 38 | 25.2261 | 0.5559 | 0.0256 | 0.0192 | hybrid | structured_no_system |  | procurement |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MKW-260021 | H2 SEAL OIL SYSTEM - WIRING DIAGRAMS | WIRING DIAGRAMS |  | H2 SEAL OIL SYSTEM ¦ Hydrogen SEAL OIL SYSTEM |  |  | WIRING DIAGRAMS for H2 SEAL OIL SYSTEM ¦ Hydrogen SEAL OIL SYSTEM | FinFan Cooler | Wiring diagrams | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | diagram | diagram | wiring_diagram | wiring_diagram | hydrogen¦oil¦seal |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5973 | 0.5292 | 0.5292 | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 |  | h2 | query | h2 | match | false | 1 | 1 | 29.7813 | 0.5449 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | system_design¦engineering | 1 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MKG-260022 | GAS CONTROL SYSTEM - WIRING DIAGRAMS | WIRING DIAGRAMS |  | GAS CONTROL SYSTEM |  |  | WIRING DIAGRAMS for GAS CONTROL SYSTEM | FinFan Cooler | Wiring diagrams | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | gas |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5824 | 0.5247 | 0.5247 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 659 | 11 | 6.3682 | 0.5989 | 0.0155 | 0.0116 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-06-13 | 2024-07-13 | 2024-08-12 | 2024-08-27 | 2024-09-11 | 2024-09-26 | generated | 0.90 | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CY03-P0MKW-260031 | H2 SEAL OIL SYSTEM - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION |  | H2 SEAL OIL SYSTEM ¦ Hydrogen SEAL OIL SYSTEM |  |  | System Description for H2 SEAL OIL SYSTEM ¦ Hydrogen SEAL OIL SYSTEM | H2, CO2 Supply System | System Description | 1 | start+2M<= FA<=start + 2M+2M | FA ∈ [start+60d, start+120d] | rule_query | description | description | system_description | system_description | hydrogen¦oil¦seal |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6474 | 0.6142 | 0.6142 | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 | h2 | h2 | query | h2 | match | false | 1 | 1 | 36.5841 | 0.5933 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | h2 | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CY03-P0MKG-260032 | GAS CONTROL SYSTEM - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION |  | GAS CONTROL SYSTEM |  |  | System Description for GAS CONTROL SYSTEM | N2 Gas System | System Description | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | description | description | system_description | system_description | gas |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6919 | 0.7326 | 0.7326 | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match |  | n2 | n2 | rule | n2 | match | false | 1 | 1 | 12.7845 | 0.6795 | 0.0328 | 0.0328 | hybrid | structured_preferred | n2 | system_design¦procurement | 6 | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MKW-260033 | H2 SEAL OIL SYTSEM P&ID | P&ID ¦ Piping and Instrumentation Diagram |  | H2 SEAL OIL SYTSEM ¦ Hydrogen SEAL OIL SYTSEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for H2 SEAL OIL SYTSEM ¦ Hydrogen SEAL OIL SYTSEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | hydrogen¦oil¦seal¦sytsem |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7056 | 0.9117 | 0.6382 | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 |  | h2 | query | h2 | match | false | 1 | 1 | 55.0522 | 0.6753 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | h2 | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MKG-260034 | GAS CONTROL SYSTEM P&ID | P&ID ¦ Piping and Instrumentation Diagram |  | GAS CONTROL SYSTEM |  |  | P&ID ¦ Piping and Instrumentation Diagram for GAS CONTROL SYSTEM |  | Piping & Instrumentation Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | p_id | p_id | gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7434 | 0.9230 | 0.6461 | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | 2 | 1 | 31.2193 | 0.7186 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0MKA-260035 | LINE LIST FOR ST GENERATOR | LINE LIST | ST GENERATOR ¦ Steam Turbine GENERATOR |  |  |  | LINE LIST for ST GENERATOR ¦ Steam Turbine GENERATOR | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5753 | 0.5226 | 0.5226 | FI | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | procurement | procurement | match | stg | compressed_air | stg | query | stg | match | false | 3 | 3 | 24.0758 | 0.6950 | 0.0317 | 0.0317 | hybrid | structured_cell_found_text_preferred | stg | procurement |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0MKA-260036 | VALVE LIST FOR ST GENERATOR | VALVE LIST | ST GENERATOR ¦ Steam Turbine GENERATOR |  |  |  | Valve List for ST GENERATOR ¦ Steam Turbine GENERATOR |  | ST - MANUAL VALVE LIST FOR STG PIPING | 1 | start+250D<=FA<=start+250D+2M | FA ∈ [start+250d, start+310d] | rule_query | list | list | valve_list | valve_list | generator¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7143 | 0.7148 | 0.7144 | 0.7144 | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | procurement | procurement | match | stg | stg | stg | query | stg | match | false | 1 | 1 | 24.0758 | 0.6903 | 0.0328 | 0.0328 | hybrid | structured_preferred | stg | procurement | 10 | 2024-11-06 | 2024-12-06 | 2025-01-05 | 2025-01-20 | 2025-02-04 | 2025-02-19 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0CJN-290001 | ELECTRICAL DIAGRAM STATIC EXCITATION SYSTEM FOR ST | DIAGRAM |  | STATIC EXCITATION SYSTEM |  |  | Diagram for STATIC EXCITATION SYSTEM | Substation | Electrical Logic Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | diagram | diagram | excitation¦static¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5204 | 0.5061 | 0.5061 | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible |  | electrical | electrical | rule |  | activity_unscoped | true | 1 | 1391 | 16.1582 | 0.4095 | 0.0171 | 0.0038 | hybrid | structured_phase_gap | electrical | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CJN-290002 | EXCITER PANEL OUTLINE DRAWING FOR ST | OUTLINE DRAWING | EXCITER PANEL |  |  |  | Outline Drawing for EXCITER PANEL | Cathodic | Outline DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | exciter¦panel¦stg |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5542 | 0.6329 | 0.6329 | SKIP | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | 885 | 351 | 2.0974 | 0.4411 | 0.0035 | 0.0026 | hybrid | structured_no_system |  | system_design | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0CJN-290003 | PSS STUDY REPORT FOR ST | REPORT |  |  |  |  | REPORT |  | PSS STUDY REPORT_DRAFT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | study_report | study_report | stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8286 | 0.7736 | 0.5415 | FA | 3EF2020W00A01 | (ST #30) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown |  |  |  |  | stg | query_unscoped | false | 3 | 55 | 5.9784 | 0.4164 | 0.0246 | 0.0138 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CJN-290004 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST | DRAWINGS | EXCITATION TRANSFORMER |  |  |  | DRAWINGS for EXCITATION TRANSFORMER |  | DRAWINGS OF EXCITATION TRANSFORMER | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | excitation¦stg¦transformer |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8814 | 0.9644 | 0.6751 | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦stg | match | false | 2 | 1 | 11.8118 | 0.6034 | 0.0325 | 0.0244 | hybrid | structured_preferred | gsut_uat | system_design¦civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0CJN-290005 | AC/DC POWER CABLE/RACEWAY LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | FireFighting | Cable RaceWay Plan(=Layout) DraWing | 1 | start+16W<=FA<=FC<=start+24W | FA ∈ [start+112d, start+168d] ¦ FC ∈ [start+112d, start+168d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6297 | 0.5389 | 0.5389 | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | 21 | 26 | 8.4512 | 0.4663 | 0.0240 | 0.0135 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-11-22 | 2024-12-20 | 2025-01-17 | 2025-01-10 | 2025-02-07 | 2025-03-07 | generated | 0.90 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MKY-290006 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION | SINGLE LINE DIAGRAMS |  |  |  |  | SINGLE LINE DIAGRAMS |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8640 | 0.7259 | 0.7259 | SKIP | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | 842 | 158 | 2.5734 | 0.5247 | 0.0057 | 0.0034 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MKY-290007 | LOGIC DIAGRAMS OF GENERATOR CONTROL PANEL FOR STG | LOGIC DIAGRAMS | STG ¦ Steam Turbine Generator |  |  |  | LOGIC DIAGRAMS for STG ¦ Steam Turbine Generator |  | Control & Protection Logic Diagrams | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6992 | 0.7348 | 0.5143 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | false | 1 | 1 | 6.4795 | 0.6070 | 0.0328 | 0.0328 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290008 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG | SCHEMATIC DIAGRAMS | STG ¦ Steam Turbine Generator |  |  |  | SCHEMATIC DIAGRAMS for STG ¦ Steam Turbine Generator | Substation | Schematic Diagram (for Protection & Control System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.7014 | 0.5104 | 0.5104 | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | false | 1 | 2 | 6.4795 | 0.6033 | 0.0325 | 0.0244 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | [6 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290009 | SCHEMATIC DIAGRAMS FOR GENERATOR CONTROL PANEL | SCHEMATIC DIAGRAMS |  |  |  |  | SCHEMATIC DIAGRAMS |  | GT - TYPICAL SCHEMATIC DIAGRAM FOR ELECTRICAL PANEL | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | title | diagram | diagram | schematic_diagram | schematic_diagram |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.4286 | 0.6899 | 0.5070 | 0.5070 | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible |  | electrical¦gtg | electrical¦gtg | rule | ccw¦gtg | match | false | 1 | 2 | 1.0037 | 0.4435 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical¦gtg | system_design¦engineering | 3 | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 | 0.54 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0MKY-290010 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG | CALCULATION | STG ¦ Steam Turbine Generator |  |  |  | Calculation sheet for STG ¦ Steam Turbine Generator |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5739 | 0.5922 | 0.5922 | FI | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | false | 4 | 6 | 18.6801 | 0.6121 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290011 | SCHEMATIC DIAGRAMS FOR EMERGENCY SEAL OIL DC MOTOR STARTER PANEL | SCHEMATIC DIAGRAMS |  |  |  |  | SCHEMATIC DIAGRAMS | Substation | Schematic Diagram (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | schematic_diagram | schematic_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5913 | 0.5274 | 0.5274 | SKIP | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | 2007-04-02 | 2007-10-31 | design_drawing | system_design | compatible |  | dc_ups | dc_ups | rule |  | activity_unscoped | true | 648 | 42 | 5.4234 | 0.5219 | 0.0112 | 0.0025 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290012 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG | SCHEMATIC DIAGRAMS | STG ¦ Steam Turbine Generator |  |  |  | SCHEMATIC DIAGRAMS for STG ¦ Steam Turbine Generator | GENERATOR CIRCUIT BREAKER | Schematic diagram | 1 | start+8M<=FA<=start+8M+2M | FA ∈ [start+240d, start+300d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6097 | 0.4629 | 0.4629 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | false | 1 | 2 | 5.6714 | 0.6145 | 0.0325 | 0.0244 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | 2024-10-27 | 2024-11-26 | 2024-12-26 | 2025-01-10 | 2025-01-25 | 2025-02-09 | generated | 0.90 | 0.46 | needs_review | default_fc_window;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290013 | SCHEMATIC DIAGRAMS FOR PT/SA PANEL FOR STG | SCHEMATIC DIAGRAMS | STG ¦ Steam Turbine Generator |  |  |  | SCHEMATIC DIAGRAMS for STG ¦ Steam Turbine Generator | GENERATOR CIRCUIT BREAKER | Schematic diagram | 1 | start+8M<=FA<=start+8M+2M | FA ∈ [start+240d, start+300d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6097 | 0.4629 | 0.4629 | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | false | 1 | 2 | 5.6714 | 0.6305 | 0.0325 | 0.0244 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | 2024-10-27 | 2024-11-26 | 2024-12-26 | 2025-01-10 | 2025-01-25 | 2025-02-09 | generated | 0.90 | 0.46 | needs_review | default_fc_window;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0CJN-290014 | TECHNICAL SPECIFICATION OF EXCITATION SYSTEM FOR ST | TECHNICAL SPECIFICATION |  | EXCITATION SYSTEM |  |  | Technical Specification for EXCITATION SYSTEM |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | excitation¦stg |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5535 | 0.6327 | 0.4429 | FA | 1EF6500W86A06 | (ST GCB) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) |  | 2007-07-02 | procurement | procurement | match |  |  |  |  | electrical¦stg | query_unscoped | false | 12 | 62 | 11.2623 | 0.4874 | 0.0221 | 0.0166 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LCP-410001 | OUTLINE DRAWING FOR CONDENSATE STORAGE TANK | OUTLINE DRAWING | CONDENSATE STORAGE TANK |  |  |  | Outline Drawing for CONDENSATE STORAGE TANK |  | ACC - ConDensate Collecting Tank Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | condensate¦storage¦tank | acc¦tank | scoped | match | match | match | passed |  | 0.6667 | 0.7983 | 0.7062 | 0.7062 | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate | acc¦condensate | condensate | query | condensate | match | false | 1 | 1 | 14.3810 | 0.5468 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-10-18 | 2024-11-17 | 2024-12-17 | 2025-01-01 | 2025-01-16 | 2025-01-31 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0LCP-410002 | STRENGTH CALCULATION FOR CONDENSATE STORAGE TANK | STRENGTH CALCULATION | CONDENSATE STORAGE TANK |  |  |  | STRENGTH CALCULATION for CONDENSATE STORAGE TANK |  | Condensate Tank & Pump FOUNDATION Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | condensate¦storage¦tank | pump¦tank | scoped | match | match | match | passed |  | 0.6000 | 0.7299 | 0.6390 | 0.6390 | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate | condensate | condensate | query | condensate¦fgp | match | false | 1 | 4 | 22.9126 | 0.4860 | 0.0320 | 0.0320 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-03 | 2024-04-02 | 2024-05-02 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GHC-410011 | OUTLINE DRAWING FOR DEMINERALIZED WATER STORAGE TANK | OUTLINE DRAWING | DEMINERALIZED WATER STORAGE TANK |  |  |  | Outline Drawing for DEMINERALIZED WATER STORAGE TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | demineralized¦storage¦tank¦water | tank | scoped | match | match | match | passed |  | 0.6667 | 0.6909 | 0.6739 | 0.6739 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | false | 1 | 1 | 9.4878 | 0.5219 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GHC-410012 | STRENGTH CALCULATION FOR DEMINERALIZED WATER STORAGE TANK | STRENGTH CALCULATION | DEMINERALIZED WATER STORAGE TANK |  |  |  | STRENGTH CALCULATION for DEMINERALIZED WATER STORAGE TANK |  | CALCULATION OF DEMINERALIZED WATER TANK FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | demineralized¦storage¦tank¦water | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7883 | 0.7032 | 0.7032 | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | false | 1 | 1 | 56.2385 | 0.5414 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GKB-410021 | OUTLINE DRAWING FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 75 | 99 | 14.9659 | 0.4699 | 0.0137 | 0.0103 | hybrid | structured_no_system |  | system_design |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.61 | usable | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GKB-410022 | STRENGTH CALCULATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | STRENGTH CALCULATION | TANK |  |  |  | STRENGTH CALCULATION for TANK | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.8319 | 0.5996 | 0.5996 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 2 | 26 | 26.4743 | 0.4711 | 0.0278 | 0.0208 | hybrid | structured_no_system |  | civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GKB-410031 | OUTLINE DRAWING FOR POTABLE WATER STORAGE TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 47 | 73 | 14.9659 | 0.4749 | 0.0169 | 0.0126 | hybrid | structured_no_system |  | system_design |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 0.61 | usable | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GKB-410032 | STRENGTH CALCULATION FOR POTABLE WATER STORAGE TANK | STRENGTH CALCULATION | TANK |  |  |  | STRENGTH CALCULATION for TANK | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.8319 | 0.5996 | 0.5996 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | 2 | 21 | 26.4743 | 0.4748 | 0.0285 | 0.0214 | hybrid | structured_no_system |  | civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411001 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR CONDENSATE STORAGE TANK | TECHNICAL SPECIFICATION | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | FA | 0EF3520W68A03 | (Condensate Tank) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System |  | 2007-03-30 | procurement | procurement | match |  |  |  |  | condensate¦fgp | query_unscoped | false | 4 | 1 | 24.6839 | 0.6023 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411011 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR DEMINERALIZED WATER STORAGE TANK | TECHNICAL SPECIFICATION | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | FA | 1EF3030W68A03 | (EXP Head Tank) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 15 | 12 | 22.4895 | 0.5372 | 0.0272 | 0.0204 | hybrid | structured_no_system |  | procurement |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411021 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | TECHNICAL SPECIFICATION | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | FA | 1EF3030W68A03 | (EXP Head Tank) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 14 | 1 | 22.4895 | 0.5367 | 0.0299 | 0.0224 | hybrid | structured_no_system |  | procurement |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411031 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE WATER STORAGE TANK | TECHNICAL SPECIFICATION | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | FA | 1EF3030W68A03 | (EXP Head Tank) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | 14 | 2 | 22.4895 | 0.5405 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | procurement |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PGB-420010 | OUTLINE DRAWING FOR CCW EXPANSION HEAD TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  |  |  |  | compressed_air | query_unscoped | false | 948 | 159 | 2.2471 | 0.4529 | 0.0056 | 0.0042 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PGB-420020 | OUTLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 139 | 45 | 9.5798 | 0.4838 | 0.0145 | 0.0109 | hybrid | structured_no_system |  | system_design |  | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 | 0.61 | usable | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LCM-420030 | OUTLINE DRAWING FOR ATMOSPHERIC FLASH TANK | OUTLINE DRAWING | flash Tank |  |  |  | Outline Drawing for flash Tank |  | ACC - Flash Tank Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | flash¦tank | acc¦tank | scoped | match | match | match | passed |  | 0.8000 | 0.7500 | 0.7850 | 0.7850 | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | 938 | 346 | 2.2471 | 0.4167 | 0.0035 | 0.0010 | hybrid | structured_phase_gap | acc | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LCM-420040 | OUTLINE DRAWING FOR VACUUM FLASH TANK | OUTLINE DRAWING | flash Tank |  |  |  | Outline Drawing for flash Tank |  | ACC - Flash Tank Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | flash¦tank | acc¦tank | scoped | match | match | match | passed |  | 0.8000 | 0.7500 | 0.7850 | 0.7850 | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | 954 | 175 | 2.1131 | 0.4351 | 0.0052 | 0.0016 | hybrid | structured_phase_gap | acc | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rule_scope_unmatched;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0GKC-420050 | OUTLINE DRAWING FOR CHILLED WATER STORAGE TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | 688 | 125 | 5.9042 | 0.4678 | 0.0067 | 0.0051 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0GKC-420051 | INSULATION DETAIL DRAWING FOR CHILLED WATER STORAGE TANK | DRAWING | TANK |  |  |  | DRAWING for Tank |  | Day Tank FOUNDATION REINF. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 0.2000 | 0.5003 | 0.2901 | 0.2901 | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | 3 | 5 | 26.4743 | 0.5038 | 0.0313 | 0.0176 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755001 | SAT Procedure for Isolated Phase Busbar (IPB) | Procedure | IPB ¦ Isolated Phase Busduct |  |  |  | Procedure for IPB ¦ Isolated Phase Busduct | Isolated Phase Bus | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | busduct¦ipb¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.7521 | 0.5256 | 0.5256 | FI | 1PF6500W74A03T | (IPB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-05-02 | 2008-06-16 | delivery | delivery | match | electrical |  | electrical | query | electrical | match | false | 1 | 5 | 69.7044 | 0.7239 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical | delivery¦procurement |  | 2025-01-24 | 2025-02-23 | 2025-03-25 | 2025-04-09 | 2025-04-24 | 2025-05-09 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755002 | SAT Procedure for GSUT | Procedure | GSUT ¦ Generator Step-Up Transformer |  |  |  | Procedure for GSUT ¦ Generator Step-Up Transformer | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | generator¦gsut¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5780 | 0.4534 | 0.4534 | FI | 2PF6500W70A08T | (STG #20 & UST Shelter) Transportation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2008-07-15 | 2008-08-28 | delivery | delivery | match | gsut_uat | gsut_uat | gsut_uat | query | gsut_uat¦stg | match | false | 2 | 13 | 25.3315 | 0.5926 | 0.0298 | 0.0298 | hybrid | structured_cell_found_text_preferred | gsut_uat | delivery¦procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755003 | SAT Procedure for 380kv EHV Cable and Accessories | Procedure | Cable |  |  |  | Procedure for Cable | PoWer Cable | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | cable |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5302 | 0.5091 | 0.5091 | FI | 2PF6040W74A07T | (EHV Cable) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-02 | 2008-05-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | false | 2 | 1 | 25.7684 | 0.5990 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755004 | SAT Procedure for Non Segregated Phase Busduct (NSPBD) | Procedure | NSPBD ¦ Non-Segregated Phase Bus Duct |  |  |  | Procedure for NSPBD ¦ Non-Segregated Phase Bus Duct | Isolated Phase Bus | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | bus¦duct¦non¦nspbd¦phase¦segregated |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6836 | 0.5051 | 0.5051 | FI | 1PF6500W74A03T | (IPB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-05-02 | 2008-06-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | false | 1 | 5 | 33.5442 | 0.5917 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | delivery¦procurement |  | 2025-01-24 | 2025-02-23 | 2025-03-25 | 2025-04-09 | 2025-04-24 | 2025-05-09 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755005 | SAT Procedure for Unit Auxillary Transformer (UAT) | Procedure | UAT ¦ Unit Auxiliary Transformer |  |  |  | Procedure for UAT ¦ Unit Auxiliary Transformer | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | auxiliary¦transformer¦uat¦unit |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5947 | 0.4584 | 0.4584 | FI | 1PF6500W70A05.1T | (GTG UAT) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-03-18 | 2008-05-01 | delivery | delivery | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | false | 1 | 3 | 36.3769 | 0.6682 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | gsut_uat | delivery¦procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755006 | SAT Procedure for Protection Relay Panel, GSUT HV Side Energy Metering Panel | Procedure | GSUT ¦ Generator Step-Up Transformer |  |  |  | Procedure for GSUT ¦ Generator Step-Up Transformer | Protection & Metering System | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | generator¦gsut¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6164 | 0.4849 | 0.4849 | FI | 1PF6500W70A08T | (STG #10 & UST Shelter) Transportation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-06-23 | 2008-08-06 | delivery | delivery | match | gsut_uat | electrical | gsut_uat | query | gsut_uat¦stg | match | false | 1 | 6 | 25.3315 | 0.6066 | 0.0315 | 0.0315 | hybrid | structured_preferred | gsut_uat | delivery¦procurement | 10 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755007 | SAT Procedure for AC-UPS System | Procedure |  | AC-UPS System ¦ AC-Uninterruptible Power Supply System |  |  | Procedure for AC-UPS System ¦ AC-Uninterruptible Power Supply System | Sampling System | Packing Procedure | 1 | finish-2M-2M<=FA<=finish-2M | FA ∈ [finish-120d, finish-60d] | title | procedure | procedure | procedure | procedure | power¦supply¦uninterruptible¦ups |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4432 | 0.4830 | 0.4830 | FI | 0PF6500W70A03.4T | (DC & UPS) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2008-03-07 | 2008-04-21 | delivery | delivery | match | dc_ups | sampling | dc_ups | query | dc_ups¦electrical | match | false | 1 | 2 | 34.6267 | 0.5259 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dc_ups | delivery¦procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755008 | SAT Procedure for DC Battery Charger System | Procedure |  | DC Battery Charger System ¦ DIRECT CURRENT Battery Charger System |  |  | Procedure for DC Battery Charger System ¦ DIRECT CURRENT Battery Charger System | Sampling System | Packing Procedure | 1 | finish-2M-2M<=FA<=finish-2M | FA ∈ [finish-120d, finish-60d] | title | procedure | procedure | procedure | procedure | battery¦charger¦current¦direct |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.3813 | 0.4644 | 0.4644 | FI | 0PF6500W70A03.4T | (DC & UPS) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2008-03-07 | 2008-04-21 | delivery | delivery | match | dc_ups | sampling | dc_ups | query | dc_ups¦electrical | match | false | 1 | 2 | 41.2157 | 0.5490 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dc_ups | delivery¦procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755009 | SAT Procedure for Generator Circuit Breaker (GCB) | Procedure | Generator Circuit Breaker (GCB) ¦ Generator Circuit Breaker (Generator Circuit Breaker) |  |  |  | Procedure for Generator Circuit Breaker (GCB) ¦ Generator Circuit Breaker (Generator Circuit Breaker) | GENERATOR CIRCUIT BREAKER | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | breaker¦circuit¦gcb¦generator |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7461 | 0.6238 | 0.6238 | FI | 1PF6500W86A03T | (GT GCB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2008-04-01 | 2008-05-15 | delivery | delivery | match |  |  |  |  | electrical¦gtg | query_unscoped | false | 1 | 9 | 90.9483 | 0.7016 | 0.0309 | 0.0232 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-23 | 2025-01-22 | 2025-02-21 | 2025-03-08 | 2025-03-23 | 2025-04-07 | generated | 0.90 | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755010 | SAT Procedure for LV Cable | Procedure | LV Cable ¦ Low Voltage Cable |  |  |  | Procedure for LV Cable ¦ Low Voltage Cable | PoWer Cable | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | cable¦low¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6027 | 0.4141 | 0.4141 | FI | 2PF6040W74A07T | (EHV Cable) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-02 | 2008-05-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | false | 7 | 7 | 35.8303 | 0.5200 | 0.0299 | 0.0224 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755011 | SAT Procedure for MV Cable | Procedure | MV Cable ¦ Medium Voltage Cable |  |  |  | Procedure for MV Cable ¦ Medium Voltage Cable | PoWer Cable | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | cable¦medium¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6222 | 0.4200 | 0.4200 | FI | 2PF6040W74A07T | (EHV Cable) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-02 | 2008-05-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | false | 7 | 8 | 35.8303 | 0.5330 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755012 | SAT Procedure for 480V Motor Control Center | Procedure | 480V Motor Control Center |  |  |  | Procedure for 480V Motor Control Center | Motor Operated Valve | NDE Procedure | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | procedure | procedure | procedure | procedure | 480v¦center¦motor |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5831 | 0.4549 | 0.4549 | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | procurement | procurement | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | false | 1 | 1 | 37.8652 | 0.5678 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755013 | SAT Procedure for 13.8 kV MV Switch Gear | Procedure | 13.8 kV MV Switch Gear ¦ 13.8 kV Medium Voltage Switch Gear |  |  |  | Procedure for 13.8 kV MV Switch Gear ¦ 13.8 kV Medium Voltage Switch Gear | FireFighting | Packing Procedure | 1 | start-8W<=FA<=FC<=start-4W | FA ∈ [start-56d, start-28d] ¦ FC ∈ [start-56d, start-28d] | rule_query | procedure | procedure | procedure | procedure | gear¦medium¦switch¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4156 | 0.3580 | 0.3580 | FA | 0PF6500W70A03.2T | (MV SWGR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2008-04-01 | 2008-05-15 | delivery | delivery | match |  |  |  |  | electrical¦mv_lv | query_unscoped | false | 1 | 1 | 41.3453 | 0.5939 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | delivery¦procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755014 | SAT Procedure for LV Switchgear | Procedure | LV Switchgear ¦ Low Voltage Switchgear |  |  |  | Procedure for LV Switchgear ¦ Low Voltage Switchgear |  | Packing Procedure | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | procedure | procedure | procedure | procedure | low¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4257 | 0.3611 | 0.3611 | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | procurement | procurement | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | false | 1 | 1 | 60.4660 | 0.6816 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755015 | SAT Procedure for Lighting Distribution Board (LDB) | Procedure |  | Lighting & Small Power System |  |  | Procedure for Lighting & Small Power System | Lighting&small PoWer System | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6918 | 0.5075 | 0.5075 | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 | delivery | delivery | match | electrical | electrical | electrical | query | electrical | match | false | 1 | 4 | 31.3384 | 0.5479 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical | delivery¦procurement |  | 2024-11-20 | 2024-12-20 | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | generated | 0.90 | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755016 | SAT Procedure for Mold / Dry Transformer | Procedure | Mold / Dry Transformer |  |  |  | Procedure for Mold / Dry Transformer | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | dry¦mold¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7232 | 0.4970 | 0.4970 | FI | 1PF6500W70A13T | (STG TR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-07-31 | 2008-09-13 | delivery | delivery | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦stg | match | false | 5 | 15 | 15.2309 | 0.4574 | 0.0287 | 0.0287 | hybrid | structured_preferred | gsut_uat | delivery¦procurement | 10 | 2025-04-23 | 2025-05-23 | 2025-06-22 | 2025-07-07 | 2025-07-22 | 2025-08-06 | generated | 0.90 | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755017 | SAT Procedure for MV & LV Motors | Procedure | MV & LV Motors ¦ Medium Voltage & Low Voltage Motors |  |  |  | Procedure for MV & LV Motors ¦ Medium Voltage & Low Voltage Motors | SumpPump | Packing Procedure | 1 | start-4W-2M<=FA<=start-4W | FA ∈ [start-88d, start-28d] | title | procedure | procedure | procedure | procedure | low¦medium¦motors¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.3951 | 0.3519 | 0.3519 | FA | 0PF6500W70A03.3T | (LV SWGR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2008-04-01 | 2008-05-15 | delivery | delivery | match |  |  |  |  | electrical¦mv_lv | query_unscoped | false | 2 | 6 | 46.9707 | 0.5099 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | delivery¦procurement | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755019 | SAT Procedure for STG Excitation Transformer (Oil Type) | Procedure | STG ¦ Steam Turbine Generator |  |  |  | Procedure for STG ¦ Steam Turbine Generator | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5909 | 0.4573 | 0.4573 | FI | 2PF6500W70A13T | (STG TR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2008-08-30 | 2008-10-14 | delivery | delivery | match | stg | gsut_uat | stg | query | electrical¦gsut_uat¦stg | match | false | 9 | 4 | 19.6338 | 0.6576 | 0.0301 | 0.0301 | hybrid | structured_preferred | stg | delivery¦procurement | 10 | [6 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755020 | SAT Procedure for Neutral Grounding Transformer (NGTR) Neutral Grounding Resistor (NGR) | Procedure |  |  |  |  | Procedure |  | DCS - SAT ProceDure | 1 | start+364D<=FA<=start+346D+2M | FA ∈ [start+364d, start+406d] | title | procedure | procedure | procedure | procedure |  | dcs | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.4022 | 0.5873 | 0.5873 | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match |  | dcs | dcs | rule | dcs | match | false | 1 | 1 | 11.7558 | 0.3732 | 0.0328 | 0.0328 | hybrid | structured_preferred | dcs | procurement | 3 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755021 | SAT Procedure for Ground, Step & touch Voltage | Procedure |  |  |  |  | Procedure |  | DCS - SAT ProceDure | 1 | start+364D<=FA<=start+346D+2M | FA ∈ [start+364d, start+406d] | title | procedure | procedure | procedure | procedure |  | dcs | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.4309 | 0.5959 | 0.5959 | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match |  | dcs | dcs | rule | dcs | match | false | 1 | 1 | 11.7558 | 0.3945 | 0.0328 | 0.0328 | hybrid | structured_preferred | dcs | procurement | 3 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 0.72 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755022 | Site Acceptance Test Procedure for Generator & Exc. TR Protection Relay, Control Panel | Procedure |  | Protection & Metering System |  |  | Procedure for Protection & Metering System |  | Site Acceptance Test Procedure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | test_procedure | test_procedure | metering¦protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7534 | 0.9260 | 0.6482 | FA | 0SF6500W62A05.6 | (Electrical Protection Panel) Function Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-05-27 | 2008-06-05 | commissioning | commissioning | match | electrical |  | electrical | query | electrical | match | false | 1 | 1 | 35.0381 | 0.6720 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical | commissioning |  | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-29 | 2025-04-28 | generated | 0.30 | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755023 | Site Acceptance Test Procedure for HCIS Security System | Procedure |  | HCIS Security System |  |  | Procedure for HCIS Security System |  | Site Acceptance Test Procedure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | test_procedure | test_procedure | hcis¦security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7976 | 0.9393 | 0.6575 | FA | 1SF3030W62A25 | (CCWS) System Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-10-24 | 2008-10-28 | commissioning | commissioning | match |  |  |  |  | ccw | query_unscoped | false | 18 | 15 | 6.8786 | 0.4752 | 0.0262 | 0.0196 | hybrid | structured_no_system |  | commissioning |  | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | 2025-08-26 | 2025-09-25 | generated | 0.30 | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DN05-P8MB-810006 | GAS TURBINE FUEL CHANGE-OVER TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report | gtg |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-27 | 2008-11-27 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | false | 1 | 1 | 23.4908 | 0.7344 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P8ZEN-810030 | PLANT EMERGENCY FUEL CHANGE-OVER TEST | TEST |  |  |  |  | TEST |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.2500 | 0.3904 | 0.2921 | 0.2921 | FA | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-27 | 2008-11-27 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | false | 1 | 1 | 20.4072 | 0.6676 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | commissioning | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860001 | GT LOAD REJECTION TEST | TEST | GT ¦ Gas Turbine |  |  |  | TEST for GT ¦ Gas Turbine | [5 empty] | rule_query | other | other | test | gt_gas_turbine_name_plate | gas¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6000 | 0.7161 | 0.6348 | 0.6348 |  | 1SF3520W62A08 | (GPRS #11) Function Test for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2008-08-04 | 2008-08-05 | commissioning | commissioning | match | gtg |  | gtg | query | fgp¦gtg | match | false | 13 | 1 | 12.6560 | 0.6827 | 0.0301 | 0.0301 | hybrid | structured_cell_found_text_preferred | gtg | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860002 | TRIAL RUN TEST OF THE PLANT | TEST |  |  |  |  | TEST |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.2500 | 0.4171 | 0.3001 | 0.3001 | FA | 1SF9012W62A10 | (GTG #11) Trial Run Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-01 | 2008-11-01 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | false | 4 | 6 | 21.7218 | 0.5225 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | commissioning | [7 empty] | blocked_rule |  | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860003 | ST LOAD REJECTION TEST | TEST | ST ¦ Steam Turbine |  |  |  | TEST for ST ¦ Steam Turbine | [5 empty] | rule_query | other | specification | test | specification | steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.6950 | 0.7335 | 0.5135 |  | 1SF2000W62A01 | (ST #10) Aux. Equipment Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Test & Commissioning | 2009-03-09 | 2009-03-28 | commissioning | commissioning | match | stg |  | stg | query | stg | match | false | 1 | 12 | 18.8206 | 0.6281 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | stg | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860004 | ACTIVE POWER RESPONSE AND VOLTAGE CONTROL RESPONSE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF6500W62A05.3 | (LV SWGR) Function Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2008-06-22 | 2008-07-01 | commissioning | commissioning | match |  |  |  |  | electrical¦mv_lv | query_unscoped | false | 2 | 35 | 14.1407 | 0.4887 | 0.0267 | 0.0200 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860006 | ISLAND MODE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 1SF9040W62A13 | (Comm'g) Initial Operation Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-07-21 | 2009-07-21 | commissioning | commissioning | match | [5 empty] | query_unscoped | true | 28 | 6 | 5.2662 | 0.4775 | 0.0265 | 0.0159 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860007 | LOAD SWING TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF3035W62A13.0 | (SWS) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2009-01-10 | 2009-01-11 | commissioning | commissioning | match |  |  |  |  | service_water | query_unscoped | false | 1 | 1 | 10.2097 | 0.4166 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860008 | LDC Integration | [7 empty] | LDC Integration | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | ldc_integration | ldc_integration |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.9998 | 0.7666 | 0.5366 | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | 27 | 9 |  | 0.3480 | 0.0260 | 0.0146 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860009 | STARTUP TIME TEST (COLD/WARM/HOT) | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 2SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | 2009-07-17 | 2009-08-19 | commissioning | commissioning | match | [5 empty] | query_unscoped | true | 2 | 7 | 12.9540 | 0.4303 | 0.0311 | 0.0186 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860010 | MINIMUM LOAD TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF3510W62A16 | (COMP Air System) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2008-10-21 | 2008-10-22 | commissioning | commissioning | match |  |  |  |  | compressed_air | query_unscoped | false | 3 | 1 | 10.2097 | 0.5014 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860011 | AGC | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [6 empty] | 2SF0500W00A04 | GTG #21 TOD | CCPP Project Standard Schedule_20181012_Idea > Plant General > Key Milestones > Guaranteed Completion Date |  | 2009-01-03 |  |  | query_unknown |  |  |  |  | gtg | query_unscoped | false | 4 | 453 |  | 0.3118 | 0.0176 | 0.0099 | hybrid | structured_no_system | [9 empty] | no_rule |  | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860012 | PERFORMANCE TEST PROCEDURE FOR THERMAL PERFORMANCE | PROCEDURE |  |  |  |  | PROCEDURE | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6453 | 0.7186 | 0.7186 | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match |  |  |  |  | fgp | query_unscoped | false | 1 | 2 | 21.2250 | 0.6182 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | commissioning |  | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860013 | RELIABILITY TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 1SF9013W62A11 | (GTG #11) Reliability Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-02 | 2008-11-16 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | false | 4 | 4 | 13.4130 | 0.4898 | 0.0312 | 0.0234 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860014 | NET DEPENDABLE CAPACITY TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF6500W62A01 | (Power Receiving) Interface signal Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-08-01 | 2008-08-02 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | false | 23 | 15 | 5.2980 | 0.4728 | 0.0254 | 0.0190 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860015 | REACTIVE POWER TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF6500W62A05.7 | (Power Metering Equip) Function Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2008-04-30 | 2008-05-29 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | false | 46 | 1 | 5.1731 | 0.5663 | 0.0258 | 0.0194 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860016 | PRIMARY RESPONSE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF6500W62A04 | (Power Receiving) Protection Secondary & Primary Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-09-05 | 2008-09-11 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | false | 1 | 14 | 16.9776 | 0.4214 | 0.0299 | 0.0224 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860017 | BLACK START-UP TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 2SF9012W62A09 | (GTG #21) Black start Test with GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | 2008-12-03 | 2008-12-03 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | false | 2 | 3 | 20.9158 | 0.5374 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860018 | PSS TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF3035W62A13.1 | (PWS) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2009-01-20 | 2009-01-24 | commissioning | commissioning | match |  |  |  |  | wts | query_unscoped | false | 64 | 2 | 5.1125 | 0.5319 | 0.0242 | 0.0181 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860019 | RESERVE BOILER THERMAL PERFORMANCE TEST PROCEDURE | PROCEDURE | RESERVE BOILER |  |  |  | PROCEDURE for RESERVE BOILER | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5960 | 0.7038 | 0.7038 | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | 2 | 18 | 11.8832 | 0.5560 | 0.0289 | 0.0072 | hybrid | structured_system_absent | reserve_boiler | commissioning | [7 empty] | blocked_activity |  | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860020 | PERFORMANCE TEST PROCEDURE FOR NOISE EMISSION | PROCEDURE |  |  |  |  | PROCEDURE | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.5480 | 0.6894 | 0.6894 | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match |  |  |  |  | fgp | query_unscoped | false | 7 | 5 | 11.8832 | 0.5496 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | commissioning |  | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860021 | PERFORMANCE TEST PROCEDURE FOR AIR EMISSION | PROCEDURE |  |  |  |  | PROCEDURE | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6337 | 0.7151 | 0.7151 | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match |  |  |  |  | fgp | query_unscoped | false | 8 | 1 | 11.8832 | 0.6656 | 0.0311 | 0.0233 | hybrid | structured_no_system |  | commissioning |  | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860022 | SUPPLEMENTARY FIRING FOR HRSG |  | HRSG ¦ Heat Recovery Steam Generator |  |  |  | for HRSG ¦ Heat Recovery Steam Generator | [5 empty] | rule_query | other | diagram | supplementary_firing_for_hrsg | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6763 | 0.5529 | 0.5529 |  | 3SF1600W62A01.1 | (HRSG #32)Cold Commissioning for HRSG #32 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Commissioning | 2009-04-23 | 2009-05-12 |  | commissioning | query_unknown | hrsg |  | hrsg | query | hrsg | match | false | 11 | 5 | 19.8735 | 0.6072 | 0.0295 | 0.0221 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860027 | REACTIVE POWER TEST OF STG | TEST | STG ¦ Steam Turbine Generator |  |  |  | TEST for STG ¦ Steam Turbine Generator | [5 empty] | rule_query | other | drawing | test | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6103 | 0.6031 | 0.6031 |  | 1CF2010W74A11 | (STG #10 BLDG) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-10-13 | 2009-01-12 | commissioning | commissioning | match | stg |  | stg | query | stg | match | false | 1 | 17 | 20.5552 | 0.6350 | 0.0294 | 0.0294 | hybrid | structured_cell_found_text_preferred | stg | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860028 | PSS TEST OF STG | TEST | STG ¦ Steam Turbine Generator | PSS ¦ Power Stability System |  |  | TEST for STG ¦ Steam Turbine Generator | [5 empty] | rule_query | other | drawing | test | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6103 | 0.6031 | 0.6031 |  | 3CF2010W74A11 | (STG #30 BLDG) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-11-12 | 2009-02-11 | commissioning | commissioning | match | stg |  | stg | query | stg | match | false | 3 | 21 | 20.5552 | 0.6656 | 0.0282 | 0.0282 | hybrid | structured_cell_found_text_preferred | stg | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860029 | SECONDARY RESPONSE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 |  | 0SF6500W62A04 | (Power Receiving) Protection Secondary & Primary Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-09-05 | 2008-09-11 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | false | 1 | 1 | 16.9776 | 0.4590 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210