## Generated Schedule
source_file | document_no | title | deliverable | equipment | system | building | itb_sources | rule_query | matched_rule | submission_type | matched_activity_id | matched_activity_name | matched_activity_wbs_path | matched_activity_start_date | matched_activity_finish_date | fa_earliest | fa_recommended | fa_latest | fc_earliest | fc_recommended | fc_latest | date_range_status | date_range_confidence | ntp_shift_days
itb_candidates |  | Calculation of Air Cooled Condenser & Duct Support Foundation | CALCULATION | Air Cooled Condenser |  |  | R&N_ITB:p80, 81(score=1.43) | Calculation sheet for Air Cooled Condenser | Air Cooled Condenser | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 | 6210
itb_candidates |  | Air Cooled Condenser Fan Technical Specification | TECHNICAL SPECIFICATION | Air Cooled Condenser |  |  | R&N_ITB:p80, 81(score=1.42) | Technical Specification for Air Cooled Condenser | Air Cooled Condenser | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 6210
itb_candidates |  | CEP & CONDENSER FOUNDATION (CCPP PLANT AREA) CALCULATION | CALCULATION | Condensate Extraction Pump |  |  | R&N_ITB:p80, 81(score=1.41) | Calculation sheet for Condensate Extraction Pump | Condensate Extraction Pump | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-12-06 | 2025-01-05 | 2025-02-04 | 2025-02-19 | 2025-03-06 | 2025-03-21 | generated | 0.90 | 6210
itb_candidates |  | CALCULATION OF AIR COOLED CONDENSER FOUNDATION | CALCULATION | Air Cooled Condenser |  |  | R&N_ITB:p80, 81(score=1.41) | Calculation sheet for Air Cooled Condenser | Air Cooled Condenser | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 | 6210
itb_candidates |  | Air Cooled Condenser FAN CONTROL STEPS |  | Air Cooled Condenser |  |  | R&N_ITB:p80, 81(score=1.41) | for Air Cooled Condenser | Air Cooled Condenser | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 6210
itb_candidates |  | Reliability Test | TEST | Commissioning Procedure |  |  | R&N_ITB:p88(score=1.36) ¦ R&N_ITB:p88, 89(score=1.35) ¦ R&N_ITB:p89(score=1.33) | TEST for Commissioning Procedure | Commissioning | FI | 1SF9041W62A14 | (Comm'g) Reliability Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-07-21 | 2009-08-19 | 2026-08-21 | 2026-09-20 | 2026-10-20 | 2026-11-04 | 2026-11-19 | 2026-12-04 | generated | 0.90 | 6210
itb_candidates |  | Capacity Test | TEST | Commissioning Procedure |  |  | R&N_ITB:p88(score=1.35) | TEST for Commissioning Procedure | Commissioning | FI | 1SF2000W62A02 | (ST #10) Pre-Commissioning | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Test & Commissioning | 2009-02-27 | 2009-03-28 | 2026-03-30 | 2026-04-29 | 2026-05-29 | 2026-06-13 | 2026-06-28 | 2026-07-13 | generated | 0.90 | 6210
itb_candidates |  | GENERATOR O&M MANUAL (Block #2) | MANUAL |  |  |  | R&N_ITB:p88(score=1.35) | MANUAL |  | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
itb_candidates |  | O&M MANUAL FOR GENERATOR PROTECTION RELAY | MANUAL |  |  |  | R&N_ITB:p88(score=1.35) ¦ R&N_ITB:p89(score=1.33) | MANUAL |  | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA POWER CABLE | DESIGN CRITERIA |  |  |  | R&N_ITB:p88(score=1.35) | DESIGN CRITERIA |  | SKIP | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | [6 empty] | skip |  | 6210
itb_candidates |  | Power Plant Layout | LAYOUT |  |  |  | R&N_ITB:p89(score=1.34) | Layout Drawing |  | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
itb_candidates |  | OPERATION & MAINTENANCE MANUAL | OPERATION & MAINTENANCE MANUAL | ACWP |  |  | R&N_ITB:p89(score=1.34) | OPERATION & MAINTENANCE MANUAL for ACWP | DCS | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2025-05-16 | 2025-06-15 | 2025-07-15 | 2025-07-30 | 2025-08-14 | 2025-08-29 | generated | 0.90 | 6210
itb_candidates |  | RELIABILITY TEST | TEST |  |  |  | R&N_ITB:p88, 89(score=1.34) | TEST |  | SKIP | 1SF9041W62A14 | (Comm'g) Reliability Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-07-21 | 2009-08-19 | [6 empty] | skip |  | 6210
itb_candidates |  | NET DEPENDABLE CAPACITY TEST | TEST |  |  |  | R&N_ITB:p88, 89(score=1.33) | TEST |  | SKIP | 1SF2000W62A01 | (ST #10) Aux. Equipment Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Test & Commissioning | 2009-03-09 | 2009-03-28 | [6 empty] | skip |  | 6210
itb_candidates |  | Plant Control & Monitoring Concept Block Diagram | PLAN | Condensate Extraction Pump |  |  | R&N_ITB:p88, 89(score=1.32) | Plan for Condensate Extraction Pump | Condensate Extraction Pump | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-12-06 | 2025-01-05 | 2025-02-04 | 2025-02-19 | 2025-03-06 | 2025-03-21 | generated | 0.90 | 6210
itb_candidates |  | STG Training Program (on site) |  | Steam Turbine & Generator |  |  | R&N_ITB:p89(score=1.20) | for Steam Turbine & Generator |  | SKIP | 0PF7000W86A04T | (Control Valve) 1st Delivery(On site) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves |  | 2008-05-15 | [6 empty] | skip |  | 6210
itb_candidates |  | DCS IO Database(For Block 2) | DATABASE | DCS |  |  | R&N_ITB:p88, 89(score=1.18) | DATABASE for DCS | DCS | FI | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 | 6210
itb_candidates |  | GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | ELECTRICAL CONTROL LOGIC DIAGRAM | Gas Turbine Generator |  |  | R&N_ITB:p91(score=1.08) ¦ R&N_ITB:p92(score=0.92) | ELECTRICAL CONTROL LOGIC DIAGRAM for Gas Turbine Generator | Gas Turbine Generator | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
itb_candidates |  | PERFORMANCE AND OPERATIONAL DATA | OPERATIONAL DATA | Heat Recovery Steam Generator |  |  | R&N_ITB:p82(score=0.96) ¦ R&N_ITB:p82(score=0.94) ¦ R&N_ITB:p82, 83(score=0.98) | OPERATIONAL DATA for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FI | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 | 2024-09-20 | 2024-10-20 | 2024-11-19 | 2024-12-04 | 2024-12-19 | 2025-01-03 | generated | 0.90 | 6210
itb_candidates |  | GTG Foundation Design Requirements | DESIGN REQUIREMENTS | Gas Turbine Generator |  |  | R&N_ITB:p81(score=0.97) ¦ R&N_ITB:p84(score=0.95) | DESIGN REQUIREMENTS for Gas Turbine Generator | Gas Turbine Generator | FA | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-01 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | CONTROL SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.97) ¦ R&N_ITB:p94(score=0.94) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | SCR PERFORMANCE SUMMARY INCLUDING AMMONIA CONSUMPTION FOR HRSG SCR | SUMMARY | Heat Recovery Steam Generator |  |  | R&N_ITB:p82, 83(score=0.97) | SUMMARY for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FI | 1EF1600W00A04 | (HRSG #11/#12) Utility Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-04-26 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
itb_candidates |  | SYSTEM DESCRIPTION FOR WASTE WATER TREATMENT PLANT | SYSTEM DESCRIPTION | Water Treatment Plant |  |  | R&N_ITB:p86, 87(score=0.97) | System Description for Water Treatment Plant | Water Treatment Plant | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
itb_candidates |  | CONTROL SYSTEM OVERVIEW | OVERVIEW | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.96) ¦ R&N_ITB:p94(score=0.94) ¦ R&N_ITB:p95(score=0.91) ¦ R&N_ITB:p95(score=0.92) | OVERVIEW for Gas Turbine Generator | Gas Turbine Generator | FI | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | GENERATOR CAPABILITY CURVES AND DATA | CURVES | Gas Turbine Generator |  |  | R&N_ITB:p95, 96(score=0.96) | CURVES for Gas Turbine Generator | Gas Turbine Generator | FI | 1PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | 2007-03-01 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
itb_candidates |  | SYSTEM CONFIGURATION FOR HRSG SCR |  | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.96) | for Heat Recovery Steam Generator |  | SKIP | 1SF1600W62A01 | (HRSG #11) Cold Commissioning for HRSG #11 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Commissioning | 2009-02-19 | 2009-03-10 | [6 empty] | skip |  | 6210
itb_candidates |  | HRSG SYSTEM CONFIGURATION DIAGRAM | DIAGRAM | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.96) | Diagram for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-05-18 | 2024-06-17 | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | generated | 0.90 | 6210
itb_candidates |  | ST Condenser Tube Cleaning System P&I Diagram | P&I DIAGRAM | Steam Turbine |  |  | R&N_ITB:p81(score=0.96) | P&ID for Steam Turbine | Steam Turbine | FA | 1PF3020W42A02P | (CTCS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | 2007-10-31 | 2008-09-01 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
itb_candidates |  | HRSG Control Valves and Desuperheater |  | Heat Recovery Steam Generator |  |  | R&N_ITB:p82, 83(score=0.96) | for Heat Recovery Steam Generator |  | SKIP | 1PF1600W90A11T | (HRSG #11 LEB) Transportataion - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2008-07-11 | 2008-08-24 | [6 empty] | skip |  | 6210
itb_candidates |  | HRSG SYSTEM CONFIGURATION FOR CEMS |  | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.96) | for Heat Recovery Steam Generator |  | SKIP | 1SF1615W62A08 | (HRSG #11) CEMS Function Test for GT #11(Bypass stack) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | 2008-08-05 | 2008-08-10 | [6 empty] | skip |  | 6210
itb_candidates |  | HRSG |  | Heat Recovery Steam Generator |  |  | R&N_ITB:p82, 83(score=0.96) | for Heat Recovery Steam Generator |  | SKIP | 3PF1615W64A11T | (HRSG #31(HRSG #11 Damper) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2008-05-02 | 2008-06-16 | [6 empty] | skip |  | 6210
itb_candidates |  | HRSG Flow Elements |  | Heat Recovery Steam Generator |  |  | R&N_ITB:p82, 83(score=0.96) | for Heat Recovery Steam Generator |  | SKIP | 3PF1615W64A11T | (HRSG #31(HRSG #11 Damper) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2008-05-02 | 2008-06-16 | [6 empty] | skip |  | 6210
itb_candidates |  | GTG System Description Fuel Oil | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p81(score=0.95) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1265W42A02.00P | (Fuel oil injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | ST Condenser Vacuum Pump Terminal Box |  | Steam Turbine |  |  | R&N_ITB:p81(score=0.95) | for Steam Turbine | Steam Turbine | FA | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-07-01 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 6210
itb_candidates |  | GTG Auxiliary System Layout | LAYOUT | Gas Turbine Generator |  |  | R&N_ITB:p90(score=0.89) ¦ R&N_ITB:p94(score=0.95) ¦ R&N_ITB:p95(score=0.92) | Layout Drawing for Gas Turbine Generator | Gas Turbine Generator | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2024-05-29 | 2024-06-28 | 2024-07-28 | 2024-08-12 | 2024-08-27 | 2024-09-11 | generated | 0.90 | 6210
itb_candidates |  | Air Cooled Condenser Instrument List | INSTRUMENT LIST | Air Cooled Condenser |  |  | R&N_ITB:p81(score=0.95) | INSTRUMENT LIST for Air Cooled Condenser | Air Cooled Condenser | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Gas Turbine Instrumentation | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.95) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | Process idividual specification for Water treatment system | SPECIFICATION | Water Treatment Plant |  |  | R&N_ITB:p86(score=0.92) ¦ R&N_ITB:p86, 87(score=0.95) | Technical Specification for Water Treatment Plant | Water Treatment Plant | FA | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
itb_candidates |  | INSTRUMENT LIST FOR WASTE WATER TREATMENT PLANT | INSTRUMENT LIST | Water Treatment Plant |  |  | R&N_ITB:p86, 87(score=0.95) | INSTRUMENT LIST for Water Treatment Plant | Water Treatment Plant | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 6210
itb_candidates |  | WASTE WATER TREATMENT PLANT PLAN AND SECTION | PLAN AND SECTION | Water Treatment Plant |  |  | R&N_ITB:p86(score=0.91) ¦ R&N_ITB:p86, 87(score=0.95) | PLAN AND SECTION for Water Treatment Plant | Water Treatment Plant | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 6210
itb_candidates |  | HRSG PERFORMANCE AND OPERATIONAL DATA | OPERATIONAL DATA | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.93) ¦ R&N_ITB:p79(score=0.92) ¦ R&N_ITB:p82(score=0.95) ¦ R&N_ITB:p82(score=0.95) | OPERATIONAL DATA for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FI | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 | 2024-09-20 | 2024-10-20 | 2024-11-19 | 2024-12-04 | 2024-12-19 | 2025-01-03 | generated | 0.90 | 6210
itb_candidates |  | HRSG ARRANGEMENT OF MAIN STACK & FIELD ERECTION | ARRANGEMENT | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.95) | ARRANGEMENT for Heat Recovery Steam Generator |  | SKIP | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | [6 empty] | skip |  | 6210
itb_candidates |  | BYPASS & PRDS OPERATING AND MAINTENANCE MANUAL | MANUAL | BYPASS & PRDS |  |  | R&N_ITB:p83(score=0.95) | MANUAL for BYPASS & PRDS | BYPASS VALVE & PRDS | FI | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-03-21 | 2007-05-17 | 2024-02-19 | 2024-03-20 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Instrument Air System | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.95) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
itb_candidates |  | General Arrangement HRSG Unit MCC | GENERAL ARRANGEMENT | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.95) | General Arrangement Drawing for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
itb_candidates |  | DESIGN REQUIREMENTS FOR VT & SURGE, BAB36 | DESIGN REQUIREMENTS | Gas Turbine Generator |  |  | R&N_ITB:p81(score=0.95) ¦ R&N_ITB:p84(score=0.94) | DESIGN REQUIREMENTS for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Fuel Gas | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p81(score=0.95) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1265W42A02.00P | (Fuel oil injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | TEHCNICAL DATA SHEET FOR WASTE WATER TREATMENT PLANT | DATA SHEET | Water Treatment Plant |  |  | R&N_ITB:p86(score=0.92) ¦ R&N_ITB:p86, 87(score=0.95) | Data Sheet for Water Treatment Plant | Water Treatment Plant | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 | 6210
itb_candidates |  | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA) DETAIL | PLAN |  |  |  | R&N_ITB:p81(score=0.95) | Plan |  | SKIP | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | [6 empty] | skip |  | 6210
itb_candidates |  | FUEL OIL FALSE START STORAGE TANK PIT PLAN & SECTION | PLAN & SECTION | Fuel Oil System |  |  | R&N_ITB:p81(score=0.95) | PLAN & SECTION for Fuel Oil System |  | SKIP | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 | [6 empty] | skip |  | 6210
itb_candidates |  | OPERATION & MAINTENANCE Manual for Metering System (Gas) | OPERATION & MAINTENANCE MANUAL |  |  |  | R&N_ITB:p91(score=0.95) | OPERATION & MAINTENANCE MANUAL |  | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
itb_candidates |  | Air Cooled Condenser System Description | SYSTEM DESCRIPTION | Air Cooled Condenser |  |  | R&N_ITB:p81(score=0.95) | System Description for Air Cooled Condenser | Air Cooled Condenser | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Gas Fuel System | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p81(score=0.95) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1265W42A02.00P | (Fuel oil injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | ST Vent Steam Condenser Operating and Maintenance Manual | MANUAL | Steam Turbine |  |  | R&N_ITB:p81(score=0.94) | MANUAL for Steam Turbine | Steam Turbine | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 6210
itb_candidates |  | CONTROL LOGIC DIAGRAM FUEL OIL/GAS SYSTEM BOP | CONTROL LOGIC DIAGRAM | Fuel Oil System |  |  | R&N_ITB:p93(score=0.94) ¦ R&N_ITB:p94(score=0.94) | CONTROL LOGIC DIAGRAM for Fuel Oil System | Fuel Oil System | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 6210
itb_candidates |  | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA) PLAN AND SECTION | PLAN AND SECTION |  |  |  | R&N_ITB:p81(score=0.94) | PLAN AND SECTION |  | SKIP | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 | [6 empty] | skip |  | 6210
itb_candidates |  | SEQUENCES & CONTROLS |  | Heat Recovery Steam Generator |  |  | R&N_ITB:p82(score=0.94) | for Heat Recovery Steam Generator |  | SKIP | 3PF1615W64A11T | (HRSG #31(HRSG #11 Damper) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2008-05-02 | 2008-06-16 | [6 empty] | skip |  | 6210
itb_candidates |  | Technical Datasheet for Bypass & PRDS | TECHNICAL DATASHEET |  |  |  | R&N_ITB:p83(score=0.94) | TECHNICAL DATASHEET |  | SKIP | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-03-21 | 2007-05-17 | [6 empty] | skip |  | 6210
itb_candidates |  | BYPASS & PRDS PNEUMATIC DIAGRAM | DIAGRAM | BYPASS & PRDS |  |  | R&N_ITB:p83(score=0.94) | Diagram for BYPASS & PRDS | DCS | FA | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-03-21 | 2007-05-17 | 2024-05-20 | 2024-06-19 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-09-02 | generated | 0.90 | 6210
itb_candidates |  | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA) REBAR DETAIL | PLAN |  |  |  | R&N_ITB:p81(score=0.94) | Plan |  | SKIP | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | [6 empty] | skip |  | 6210
itb_candidates |  | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA) CALCULATION | CALCULATION |  |  |  | R&N_ITB:p81(score=0.94) | Calculation sheet |  | SKIP | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | [6 empty] | skip |  | 6210
itb_candidates |  | Main Building(GTG & HRSG Area) | DATA | Heat Recovery Steam Generator |  |  | R&N_ITB:p95, 96(score=0.94) | DATA for Heat Recovery Steam Generator |  | SKIP | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-05 | [7 empty] | skip |  | 6210
itb_candidates |  | P&I DIAGRAM FOR GT ROTOR COOLING AIR COOLER SYSTEM | P&I DIAGRAM | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.94) | P&ID for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
itb_candidates |  | GTG ELECTRICAL PROTECTION AND OPERATION SETTINGS | SETTINGS | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.94) ¦ R&N_ITB:p95(score=0.92) | SETTINGS for Gas Turbine Generator | Gas Turbine Generator | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 | 6210
itb_candidates |  | OPERATION & MAINTENANCE Manual for Bypass Valve & PRDS | OPERATION & MAINTENANCE MANUAL |  |  |  | R&N_ITB:p83(score=0.94) | OPERATION & MAINTENANCE MANUAL |  | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Air Intake System | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.94) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | 2007-03-01 | 2008-01-31 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | ST AVR mathematical model | MODEL | Steam Turbine |  |  | R&N_ITB:p95, 96(score=0.94) | MODEL for Steam Turbine | Steam Turbine | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Cooling And Sealing Air System | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.94) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | 2007-03-01 | 2008-01-31 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Lube Oil System | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p93(score=0.93) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2007-03-01 | 2008-01-30 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | FUNCTIONAL LOOP DIAGRAM FUEL OIL/GAS SYSTEM BOP | FUNCTIONAL LOOP DIAGRAM | Fuel Oil System |  |  | R&N_ITB:p93(score=0.93) ¦ R&N_ITB:p94(score=0.93) | FUNCTIONAL LOOP DIAGRAM for Fuel Oil System | Fuel Oil System | FA | 1PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2007-03-01 | 2008-01-30 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
itb_candidates |  | GENERATOR SEAL OIL SUPPLY UNIT OUTLINE (Block #3,4) | OUTLINE |  |  |  | R&N_ITB:p95(score=0.93) | OUTLINE |  | SKIP | 3SF1250W62A08 | (GEN Seal Oil Sys.) Oil Flushing | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | 2008-06-30 | 2008-07-04 | [6 empty] | skip |  | 6210
itb_candidates |  | GTG Turbine Foundation Design Requirements | DESIGN REQUIREMENTS | Gas Turbine Generator |  |  | R&N_ITB:p84(score=0.93) | DESIGN REQUIREMENTS for Gas Turbine Generator | Gas Turbine Generator | FA | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-01 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | Technical Datasheet for Metering System (Gas) | TECHNICAL DATASHEET |  |  |  | R&N_ITB:p91(score=0.93) | TECHNICAL DATASHEET |  | SKIP | 0PF3520W42A02P | (FO Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Metering System | 2007-06-29 | 2008-03-17 | [6 empty] | skip |  | 6210
itb_candidates |  | BYPASS & PRDS DATA SHEET | DATA SHEET | BYPASS & PRDS |  |  | R&N_ITB:p83(score=0.93) | Data Sheet for BYPASS & PRDS | BYPASS VALVE & PRDS | FA | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-03-21 | 2007-05-17 | 2024-04-18 | 2024-05-18 | 2024-06-17 | 2024-07-02 | 2024-07-17 | 2024-08-01 | generated | 0.90 | 6210
itb_candidates |  | Technical Datasheet for Metering System (Utility) | TECHNICAL DATASHEET |  |  |  | R&N_ITB:p91(score=0.93) | TECHNICAL DATASHEET |  | SKIP | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | [6 empty] | skip |  | 6210
itb_candidates |  | MV/LV SWGR |  |  |  |  | R&N_ITB:p92(score=0.93) |  |  |  | 0PF6500W70A03.2T | (MV SWGR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2008-04-01 | 2008-05-15 | [6 empty] | no_rule |  | 6210
itb_candidates |  | ELECTRICAL CONTROL LOGIC DIAGRAM GSUT/UAT/OVERALL PROTECTION FOR GTG | ELECTRICAL CONTROL LOGIC DIAGRAM | Gas Turbine Generator |  |  | R&N_ITB:p91(score=0.93) | ELECTRICAL CONTROL LOGIC DIAGRAM for Gas Turbine Generator | Gas Turbine Generator | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
itb_candidates |  | GSUT/UAT/OVERALL | STUDY |  |  |  | R&N_ITB:p91(score=0.93) | STUDY |  | SKIP | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 | [6 empty] | skip |  | 6210
itb_candidates |  | ROTOR COOLING AIR SYSTEM REQUIREMENTS | REQUIREMENTS | Gas Turbine Generator |  |  | R&N_ITB:p84(score=0.93) | REQUIREMENTS for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1265W42A13P | (TCA Cooler) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2008-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | Electrical system description | SYSTEM DESCRIPTION | Steam Turbine & Generator |  |  | R&N_ITB:p92(score=0.93) | System Description for Steam Turbine & Generator | Steam Turbine | FA | 1PF6500W70A12P | (STG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2008-07-30 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 6210
itb_candidates |  | LIST OF OIL SYSTEM EQUIPMENTS (BLOCK #3,4) | LIST | Steam Turbine |  |  | R&N_ITB:p93(score=0.93) | LIST for Steam Turbine | Steam Turbine | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
itb_candidates |  | GAS TURBINE FUEL CHANGE-OVER TEST | TEST | Gas Turbine Generator |  |  | R&N_ITB:p93(score=0.93) | TEST for Gas Turbine Generator | Gas Turbine Generator | FI | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-27 | 2008-11-27 | 2025-12-28 | 2026-01-27 | 2026-02-26 | 2026-03-13 | 2026-03-28 | 2026-04-12 | generated | 0.90 | 6210
itb_candidates |  | GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | STUDY | Gas Turbine Generator |  |  | R&N_ITB:p91(score=0.92) | STUDY for Gas Turbine Generator |  | SKIP | 0CF5544W70A06 | (GIS Equip) Installation for overall plant | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2008-08-29 | 2008-11-28 | [6 empty] | skip |  | 6210
itb_candidates |  | Technical Specification for Air Intake Silencer Filter for Emergency Engine | TECHNICAL SPECIFICATION |  |  |  | R&N_ITB:p85(score=0.92) | Technical Specification |  | SKIP | 0EF6020W00A02 | (BOP Piping) Pipe Material Specification | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-03-01 | 2008-01-28 | [6 empty] | skip |  | 6210
itb_candidates |  | GSUT, UAT | STUDY |  |  |  | R&N_ITB:p91(score=0.92) | STUDY |  | SKIP | 1PF6500W70A05.1T | (GTG UAT) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-03-18 | 2008-05-01 | [6 empty] | skip |  | 6210
itb_candidates |  | Technical Specification for Metering System ULSD and LNG Pipeline | TECHNICAL SPECIFICATION |  |  |  | R&N_ITB:p91(score=0.92) | Technical Specification |  | SKIP | 0EF6500W70A01.7 | (Power Metering Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System |  | 2007-05-01 | [6 empty] | skip |  | 6210
itb_candidates |  | DATA SHEET FOR Silencer | DATA SHEET | Silencer |  |  | R&N_ITB:p85(score=0.92) ¦ R&N_ITB:p85(score=0.92) | Data Sheet for Silencer |  | SKIP | 1EF2510W00A02 | (Steam System) Silencer Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-03-30 | 2007-07-13 | [6 empty] | skip |  | 6210
itb_candidates |  | OPERATION & MAINTENANCE Manual for Gas Turbine Generator | OPERATION & MAINTENANCE MANUAL | Gas Turbine Generator |  |  | R&N_ITB:p84(score=0.92) | OPERATION & MAINTENANCE MANUAL for Gas Turbine Generator | Gas Turbine Generator | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2025-05-16 | 2025-06-15 | 2025-07-15 | 2025-07-30 | 2025-08-14 | 2025-08-29 | generated | 0.90 | 6210
itb_candidates |  | HRSG Protection System Description | SYSTEM DESCRIPTION | Heat Recovery Steam Generator |  |  | R&N_ITB:p92(score=0.92) | System Description for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FA | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 6210
itb_candidates |  | HRSG SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.92) ¦ R&N_ITB:p79(score=0.92) | System Description for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FA | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 6210
itb_candidates |  | HRSG Protection System Diagram | DIAGRAM | Heat Recovery Steam Generator |  |  | R&N_ITB:p92(score=0.92) | Diagram for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-05-18 | 2024-06-17 | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | generated | 0.90 | 6210
itb_candidates |  | Hazardous Area Classification | HAZARDOUS AREA CLASSIFICATION | Plant Overall |  |  | R&N_ITB:p83(score=0.92) | HAZARDOUS AREA CLASSIFICATION for Plant Overall |  | SKIP | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | [6 empty] | skip |  | 6210
itb_candidates |  | HEAT RECOVERY STEAM GENERATOR FOUNDATION (CCPP PLANT AREA) CALCULATION | CALCULATION | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.92) | Calculation sheet for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
itb_candidates |  | MV SWITCHGEAR | ELECTRICAL CONTROL LOGIC DIAGRAM |  |  |  | R&N_ITB:p92(score=0.92) | ELECTRICAL CONTROL LOGIC DIAGRAM |  | SKIP | 0PF6500W70A03.2T | (MV SWGR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2008-04-01 | 2008-05-15 | [6 empty] | skip |  | 6210
itb_candidates |  | HAZARDOUS AREA CLASSIFICATION | HAZARDOUS AREA CLASSIFICATION |  |  |  | R&N_ITB:p83(score=0.92) ¦ R&N_ITB:p83(score=0.92) | HAZARDOUS AREA CLASSIFICATION |  | SKIP | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | [6 empty] | skip |  | 6210
itb_candidates |  | PERFORMANCE TEST PROCEDURE FOR AIR EMISSION | TEST PROCEDURE |  |  |  | R&N_ITB:p83(score=0.92) | TEST PROCEDURE |  | SKIP | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | [6 empty] | skip |  | 6210
itb_candidates |  | GTG System Description Blow Off | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.92) | System Description for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
itb_candidates |  | FUEL OIL SYSTEM | CONTROL LOGIC DIAGRAM | Fuel Oil System |  |  | R&N_ITB:p94(score=0.92) | CONTROL LOGIC DIAGRAM for Fuel Oil System | Fuel Oil System | FA | 0PF3520W42A04.3P | (FOFP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 | 2008-03-28 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
itb_candidates |  | UFD Fuel Oil System |  | UFD |  |  | R&N_ITB:p94(score=0.92) | for UFD |  | SKIP | 0SF3520W62A06 | (FOSS) Fuel Oil Filling DFO Tank | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2008-08-08 | 2008-08-14 | [6 empty] | skip |  | 6210
itb_candidates |  | FUEL OIL SYSTEM | CONTROL LOOP DIAGRAM | Fuel Oil System |  |  | R&N_ITB:p94(score=0.92) | CONTROL LOOP DIAGRAM for Fuel Oil System | Fuel Oil System | FA | 0PF3520W42A04.3P | (FOFP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 | 2008-03-28 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
itb_candidates |  | HVAC SYSTEM GAS TURBINE BUILDING LOAD CALCULATION | CALCULATION | HVAC |  |  | R&N_ITB:p79(score=0.92) | Calculation sheet for HVAC |  | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
itb_candidates |  | CALCULATION SHEET FOR WASTE WATER TREATMENT PLANT | CALCULATION SHEET | Water Treatment Plant |  |  | R&N_ITB:p86(score=0.92) | CALCULATION SHEET for Water Treatment Plant | Water Treatment Plant | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 6210
itb_candidates |  | POWER SUPPLY DISTRIBUTION DRAWING | DRAWING | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.92) | DRAWING for Gas Turbine Generator |  | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
itb_candidates |  | FIELD INSTRUMENT MONITORING SYSTEM |  | DCS |  |  | R&N_ITB:p93(score=0.92) | for DCS | DCS | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
itb_candidates |  | MCC & 125VDC SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.92) | Single Line Diagram for Gas Turbine Generator | Gas Turbine Generator | FA | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
itb_candidates |  | CALCULATION OF WASTE WATER TREATMENT PLANT | CALCULATION | Water Treatment Plant |  |  | R&N_ITB:p86(score=0.92) | Calculation sheet for Water Treatment Plant | Water Treatment Plant | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 6210
itb_candidates |  | HAZARDOUS AREA CLASSIFICATION SPECIFICATION & DRAWING FOR DUCT BURNER SYSTEM | DRAWING | Heat Recovery Steam Generator |  |  | R&N_ITB:p83(score=0.91) | DRAWING for Heat Recovery Steam Generator |  | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
itb_candidates |  | DATA SHEET FOR SILENCER | DATA SHEET |  |  |  | R&N_ITB:p85(score=0.91) | Data Sheet |  | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 | 6210
itb_candidates |  | SILENCER OPERATING AND MAINTENANCE MANUAL | MANUAL | SILENCER |  |  | R&N_ITB:p85(score=0.91) | MANUAL for SILENCER | Silencer | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
itb_candidates |  | CALCULATION | CALCULATION | GTG #3,4,5 LEB |  |  | R&N_ITB:p81(score=0.91) ¦ R&N_ITB:p84, 85(score=0.89) | Calculation sheet for GTG #3,4,5 LEB |  | FI | 0EF3520W16A02.4 | (FO LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Supply System LEB | 2007-05-01 | 2007-08-30 |  |  |  | 2024-02-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 6210
itb_candidates |  | CONTROL DESCRIPTION (PHILOSOPHY) | CONTROL DESCRIPTION | Air Compressor |  |  | R&N_ITB:p90, 91(score=0.90) | CONTROL DESCRIPTION for Air Compressor |  | SKIP | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 | [6 empty] | skip |  | 6210
itb_candidates |  | P&I DIAGRAM | P&I DIAGRAM | Air Compressor |  |  | R&N_ITB:p90, 91(score=0.90) | P&ID for Air Compressor |  | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
itb_candidates |  | PLANT INFORMATION HISTORIAN | PLAN | DCS |  |  | R&N_ITB:p93(score=0.90) | Plan for DCS | DCS | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
itb_candidates |  | GAS TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA) CALCULATION | CALCULATION | Gas Turbine Generator |  |  | R&N_ITB:p84, 85(score=0.90) | Calculation sheet for Gas Turbine Generator | Gas Turbine Generator | FA | 1PF1213W42A03P | (GT #11) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2008-01-31 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
itb_candidates |  | FUNCTIONAL DESIGN SPECIFICATION FOR PLANT INFORMATION SYSTEM | SPECIFICATION | DCS |  |  | R&N_ITB:p93(score=0.90) | Technical Specification for DCS | DCS | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
itb_candidates |  | FUNCTIONAL DESIGN SPECIFICATION FOR SAFETY RELATED SYSTEM | SPECIFICATION | DCS |  |  | R&N_ITB:p93(score=0.90) | Technical Specification for DCS | DCS | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
itb_candidates |  | Condenser #3,4 Performance Curves | PERFORMANCE CURVE | Condenser #3,4 |  |  | R&N_ITB:p97(score=0.90) | PERFORMANCE CURVE for Condenser #3,4 |  | FA | 3PF3020W42A02P | (CTCS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | 2007-10-31 | 2008-10-31 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 6210
itb_candidates |  | DCS Power Distribution Concept Diagram | DIAGRAM | INC_Plant_Overall_Design |  |  | R&N_ITB:p93(score=0.90) | Diagram for INC_Plant_Overall_Design | DCS | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
itb_candidates |  | GTG Noise Protection Concept |  | Gas Turbine Generator |  |  | R&N_ITB:p84, 85(score=0.89) | for Gas Turbine Generator |  | SKIP | 1SF9012W62A04 | (GTG #11) TBN & GEN Protection Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-10-22 | 2008-10-23 | [6 empty] | skip |  | 6210
itb_candidates |  | PLUMBING EQUIPMENT SCHEDULE | SCHEDULE | GTG #1,2 LEB |  |  | R&N_ITB:p96, 97(score=0.89) | Schedule for GTG #1,2 LEB |  | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
itb_candidates |  | GTG Foundation Loads Intensity |  | Gas Turbine Generator |  |  | R&N_ITB:p84, 85(score=0.89) | for Gas Turbine Generator |  | SKIP | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-01 | [6 empty] | skip |  | 6210
itb_candidates |  | GAS TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA) DETAIL | PLAN | Gas Turbine Generator |  |  | R&N_ITB:p84, 85(score=0.89) | Plan for Gas Turbine Generator |  | SKIP | 1CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2008-05-20 | 2008-07-04 | [6 empty] | skip |  | 6210
itb_candidates |  | ILLUMINATION LEVEL CALCULATION FOR HRSG#1,2 OF Main Building | CALCULATION | Heat Recovery Steam Generator |  |  | R&N_ITB:p96, 97(score=0.89) | Calculation sheet for Heat Recovery Steam Generator | Heat Recovery Steam Generator | FA | 2PF1625W42A06.0P | (HRSG #21 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2007-06-04 | 2008-03-03 | 2024-09-02 | 2024-10-02 | 2024-11-01 | 2024-11-16 | 2024-12-01 | 2024-12-16 | generated | 0.90 | 6210