## Generated Schedule
source_file | document_no | title | deliverable | equipment | system | building | rule_query | matched_rule | submission_type | matched_activity_id | matched_activity_name | matched_activity_wbs_path | matched_activity_start_date | matched_activity_finish_date | fa_earliest | fa_recommended | fa_latest | fc_earliest | fc_recommended | fc_latest | date_range_status | date_range_confidence
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION | [6 empty] | SKIP | 1SF0500W00A01 | NTP | CCPP Project Standard Schedule_20181012_Idea > Plant General > Key Milestones > Guaranteed Completion Date | 2007-03-01 | [7 empty] | skip
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | [6 empty] | SKIP | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 | [6 empty] | skip
Fadhili_MDL.xlsx | T16182-VA08-P0ZEN-020003 | CONTRACTORS ADMIN PLAN | PLAN |  |  |  | Plan | FinFan Cooler | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 | 2007-05-30 | 2007-06-29 | 2007-07-29 | 2007-08-13 | 2007-08-28 | 2007-09-12 | generated | 0.90
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020004 | PAINTING SPECIFICATION | SPECIFICATION |  |  |  | Technical Specification |  | SKIP | 0CF3035W68A16 | (PWT) Installation(incl. painting & Test) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2008-05-06 | 2008-11-03 | [6 empty] | skip
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020005 | PACKING SPECIFICATION | SPECIFICATION |  |  |  | Technical Specification |  | SKIP | 0EF6020W00A02 | (BOP Piping) Pipe Material Specification | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-03-01 | 2008-01-28 | [6 empty] | skip
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020006 | NAME AND TAG PLATE | [6 empty] | SKIP | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | [6 empty] | skip
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020007 | ABBREVIATION LIST | LIST |  |  |  | LIST | Water Treatment System | FI | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2007-06-29 | 2007-07-29 | 2007-08-28 | 2007-09-12 | 2007-09-27 | 2007-10-12 | generated | 0.90
Fadhili_MDL.xlsx | T16182-YK08-P0ZEN-020008 | LABELING LAYOUT FOR WATER STORAGE TANKS | LAYOUT | TANKS |  |  | Layout Drawing for TANKS |  | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020009 | TYPICAL DANGER SIGN DRAWING | DRAWING |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2007-07-13 | 2007-08-12 | 2007-09-11 | 2007-09-26 | 2007-10-11 | 2007-10-26 | generated | 0.90
Fadhili_MDL.xlsx | T16182-CA07-P0ZEN-020010 | UNDERGROUND PIPE MARKER DETAIL | DETAIL |  | PIPE |  | Detail Drawing for PIPE |  | SKIP | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | [6 empty] | skip