## Generated Schedule
source_file | document_no | title | deliverable | equipment | system | building | itb_sources | rule_query | matched_rule | matched_rule_keyword | matched_rule_priority | matched_rule_validation_time | matched_rule_date_formula | rule_match_query_source | rule_match_query_family | rule_match_rule_family | rule_match_query_subtype | rule_match_rule_subtype | rule_match_query_scope | rule_match_rule_scope | rule_match_rule_scope_type | rule_match_family_status | rule_match_subtype_status | rule_match_scope_status | rule_match_guard_status | rule_match_guard_reason | rule_match_token_score | rule_match_semantic_score | rule_match_hybrid_score | rule_match_final_score | rule_generic_judge_bucket | rule_generic_judge_verdict | rule_generic_judge_confidence | rule_generic_judge_chosen_rule | rule_generic_judge_competing | rule_generic_judge_rationale | submission_type | matched_activity_id | matched_activity_name | matched_activity_wbs_path | matched_activity_start_date | matched_activity_finish_date | activity_match_query_phase | activity_match_activity_phase | activity_match_phase_status | activity_match_query_scope | activity_match_rule_scope | activity_match_effective_scope | activity_match_scope_source | activity_match_activity_scope | activity_match_scope_status | activity_match_equipment_agreement | activity_match_generic_activity | activity_match_bm25_rank | activity_match_semantic_rank | activity_match_bm25_score | activity_match_semantic_score | activity_match_rrf_score | activity_match_adjusted_score | activity_match_resolver_mode | activity_match_resolution_reason | activity_match_structured_scope | activity_match_structured_allowed_phases | activity_match_structured_cell_size | fa_earliest | fa_recommended | fa_latest | fc_earliest | fc_recommended | fc_latest | date_range_status | date_range_confidence | date_range_floored_fields | date_range_floored_degenerate | date_range_ntp_anchored | schedule_confidence | schedule_quality_status | schedule_quality_reasons | date_range_notes | ntp_shift_days
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION |  |  | Plant General System |  |  | for Plant General System |  | DOCUMENT IDENTIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | document_identification | document_identification | plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | g_safe | [5 empty] | FA | 0EF1000W00A03 | Plant General Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-10-08 |  |  | query_unknown | [5 empty] | query_unscoped | true | true | 2 | 2 | 6.5829 | 0.5265 | 0.0323 | 0.0145 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION |  |  | Plant General System |  |  | for Plant General System |  | EQUIPMENT AND SYSTEM IDENTIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | equipment_and_system_identification | equipment_and_system_identification | plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 |  | system_design | query_unknown |  |  |  |  | h2 | query_unscoped | false | false | 31 | 8 | 7.4827 | 0.5401 | 0.0257 | 0.0145 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VA08-P0ZEN-020003 | CONTRACTORS ADMIN PLAN | Plan |  |  |  |  | Plan |  | CONTRACTORS ADMIN PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | [6 empty] | FA | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | true | false | 10 | 6 | 6.7010 | 0.4445 | 0.0294 | 0.0166 | hybrid | structured_no_system |  |  |  | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020004 | PAINTING SPECIFICATION | Painting Specification |  |  |  |  | Painting Specification | [5 empty] | rule_query | specification | specification | painting_specification | specification |  |  | scoped | match | mismatch | query_unscoped | rejected | blocked_deliverable_family | 0.6667 | 0.8723 | 0.7283 | 0.7283 | [7 empty] | 0EF6040W70A01 | (Lighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System |  | 2007-05-30 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | false | 9 | 8 | 8.0179 | 0.4097 | 0.0292 | 0.0219 | hybrid | structured_no_system |  | procurement | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:blocked_deliverable_family |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020005 | PACKING SPECIFICATION | Technical Specification |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | [6 empty] | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | false | 9 | 28 | 8.9176 | 0.4951 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | procurement |  | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020006 | NAME AND TAG PLATE |  |  | Plant General System |  |  | for Plant General System |  | NAME AND TAG PLATE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | name_and_tag_plate | name_and_tag_plate | plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 0EF1000W00A03 | Plant General Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-10-08 |  |  | query_unknown | [5 empty] | query_unscoped | true | true | 5 | 2 | 6.5829 | 0.4914 | 0.0315 | 0.0142 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020007 | ABBREVIATION LIST | LIST |  | Plant General System |  |  | LIST for Plant General System | [5 empty] | rule_query | other | specification | list | specification | plant |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.6160 | 0.5348 | 0.5348 | [7 empty] | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 2 | 1 | 23.1585 | 0.4874 | 0.0325 | 0.0183 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0ZEN-020008 | LABELING LAYOUT FOR WATER STORAGE TANKS | Layout Drawing | WATER STORAGE TANKS |  |  |  | Layout Drawing for Tank | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6051 | 0.5315 | 0.5315 | g_safe | [5 empty] | SKIP | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | true | false | 2 | 5 | 29.5568 | 0.5557 | 0.0315 | 0.0177 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020009 | TYPICAL DANGER SIGN DRAWING | DRAWING |  | Plant General System |  |  | DRAWING for Plant General System |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6332 | 0.6566 | 0.4596 | g_safe | [5 empty] | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | false | 61 | 16 | 3.7857 | 0.4477 | 0.0214 | 0.0121 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0ZEN-020010 | UNDERGROUND PIPE MARKER DETAIL | Detail Drawing |  | Plant General System |  |  | Detail Drawing for Plant General System |  | UNDERGROUND PIPE MARKER DETAIL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 5 | 21 | 11.1000 | 0.4460 | 0.0277 | 0.0156 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020020 | MAINTAINABILITY STUDY | STUDY |  | Plant General System |  |  | STUDY for Plant General System | [5 empty] | rule_query | other | specification | study | specification | plant |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.5619 | 0.5186 | 0.5186 | [7 empty] | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 31 | 112 | 5.4354 | 0.3915 | 0.0168 | 0.0101 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020030 | CORROSION AND MATERIAL STUDY | STUDY |  | Plant General System |  |  | STUDY for Plant General System | [5 empty] | rule_query | other | specification | study | specification | plant |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.5619 | 0.5186 | 0.5186 | [7 empty] | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 1 | 232 | 8.2293 | 0.4031 | 0.0198 | 0.0119 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020040 | FIRE STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 | [7 empty] | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 6 | 4 | 6.8830 | 0.4439 | 0.0308 | 0.0173 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-050001 | BUILDING RISK ASSESSMENT | ASSESSMENT |  | Plant General System |  |  | ASSESSMENT for Plant General System | [5 empty] | rule_query | other | specification | assessment | specification | plant |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.5682 | 0.5205 | 0.5205 | [7 empty] | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  |  | civil_design | query_unknown |  |  |  |  | wts | query_unscoped | false | false | 18 | 19 | 6.5598 | 0.4729 | 0.0255 | 0.0143 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100001 | SITE PLAN | Plan |  | Plant General System |  |  | Plan for Plant General System |  | SITE PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | g_safe | [5 empty] | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1 | 2 | 39.9279 | 0.6125 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100002 | OVERALL PLOT PLAN WITH ESF AREA | Plan |  | Plant General System |  |  | Plan for Plant General System |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | plant |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4645 | 0.4893 | 0.4893 | g_safe | [5 empty] | FA | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 | civil_design | civil_design | match |  |  |  |  | gtg | query_unscoped | false | false | 6 | 12 | 13.7085 | 0.4718 | 0.0290 | 0.0218 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100003 | OVERALL PLOT PLAN | Plan |  | Plant General System |  |  | Plan for Plant General System |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | plant |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4645 | 0.4893 | 0.4893 | g_safe | [5 empty] | FA | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 | civil_design | civil_design | match |  |  |  |  | gtg | query_unscoped | false | false | 15 | 14 | 6.4396 | 0.4627 | 0.0268 | 0.0201 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100004 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 1&2 (PLAN VIEW) | General Arrangement Drawing | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7865 | 0.9359 | 0.9359 | [6 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | true | false | 1 | 1 | 30.1184 | 0.6661 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg¦hrsg | system_design | 9 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100005 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 3&4&5 (PLAN VIEW) | General Arrangement Drawing | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7865 | 0.9359 | 0.9359 | [6 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | true | false | 3 | 1 | 28.3604 | 0.6585 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg¦hrsg | system_design | 9 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100006 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION A - A) | General Arrangement Drawing | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7865 | 0.9359 | 0.9359 | [6 empty] | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | true | false | 12 | 6 | 26.6586 | 0.6559 | 0.0290 | 0.0290 | hybrid | structured_preferred | gtg¦hrsg | civil_design | 10 | 2024-09-15 | 2024-10-15 | 2024-11-14 | 2024-11-29 | 2024-12-14 | 2024-12-29 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100007 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION B - B) | General Arrangement Drawing | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7865 | 0.9359 | 0.9359 | [6 empty] | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | gtg¦hrsg | hrsg | gtg¦hrsg | query | hrsg | match | true | false | 12 | 6 | 26.6586 | 0.6607 | 0.0290 | 0.0290 | hybrid | structured_preferred | gtg¦hrsg | civil_design | 10 | 2024-09-15 | 2024-10-15 | 2024-11-14 | 2024-11-29 | 2024-12-14 | 2024-12-29 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100008 | PLANT GENERAL ARRANGEMENT FOR STG AREA (PLAN VIEW) | General Arrangement Drawing | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 5.6716 | 0.6281 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100009 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION A - A) | General Arrangement Drawing | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 6 | 27.4330 | 0.6503 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100010 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION B - B) | General Arrangement Drawing | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 6 | 27.4330 | 0.6479 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG05-P0ZEN-110001 | HEAT BALANCE DIAGRAMS | DIAGRAMS |  | Plant General System |  |  | DIAGRAMS for Plant General System |  | HEAT BALANCE DIAGRAMS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible |  |  |  |  | hrsg | query_unscoped | false | false | 25 | 39 | 6.4475 | 0.4762 | 0.0219 | 0.0123 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0ZEN-110002 | P&I DIAGRAM FOR SYMBOL AND LEGEND | P&ID |  |  |  |  | P&ID |  | GT - P&I DIAGRAM LEGEND | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | title | diagram | diagram | p_id | p_id |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7813 | 0.7594 | 0.7594 | [6 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match |  | gtg | gtg | rule |  | activity_unscoped | true | true | 1 | 1 | 21.8815 | 0.6844 | 0.0328 | 0.0098 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-07-22 | 2024-08-21 | 2024-09-20 | 2024-10-05 | 2024-10-20 | 2024-11-04 | generated | 0.90 |  | false | false | 0.23 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=activity_unscoped;activity_rule_scope_unmatched;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBA-110003 | P&I DIAGRAM FOR HP STEAM SYSTEM | P&ID |  | HIGH PRESSURE STEAM SYSTEM |  |  | P&ID for HIGH PRESSURE STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7201 | 0.5660 | 0.5660 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | true | false | 4 | 4 | 23.7046 | 0.7712 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBC-110004 | P&I DIAGRAM FOR IP STEAM SYSTEM | P&ID |  | Intermediate Pressure STEAM SYSTEM |  |  | P&ID for Intermediate Pressure STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7335 | 0.5700 | 0.5700 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | true | false | 4 | 4 | 23.7046 | 0.7691 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBG-110005 | P&I DIAGRAM FOR LP STEAM SYSTEM | P&ID |  | LOW PRESSURE STEAM SYSTEM |  |  | P&ID for LOW PRESSURE STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7047 | 0.5614 | 0.5614 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | true | false | 5 | 4 | 23.7046 | 0.7580 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBS-110006 | P&I DIAGRAM FOR PROCESS STEAM SYSTEM | P&ID |  | PROCESS STEAM SYSTEM |  |  | P&ID for PROCESS STEAM SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7273 | 0.5682 | 0.5682 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | true | false | 4 | 4 | 23.7046 | 0.8064 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | steam | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6LCM-110007 | P&I DIAGRAM FOR STEAM DRAIN SYSTEM | P&ID |  | STEAM DRAIN SYSTEM |  |  | P&ID for STEAM DRAIN SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7033 | 0.5610 | 0.5610 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | h2 | steam | query | steam | match | true | false | 1 | 4 | 23.7046 | 0.7779 | 0.0320 | 0.0320 | hybrid | structured_preferred | steam | system_design¦procurement | 10 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6LCA-110008 | P&I DIAGRAM FOR CONDENSATE SYSTEM | P&ID |  | CONDENSATE SYSTEM |  |  | P&ID for CONDENSATE SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | condensate |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7209 | 0.5663 | 0.5663 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate | h2 | condensate | query | condensate | match | true | false | 1 | 1 | 29.6320 | 0.7999 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAA-110009 | P&I DIAGRAM FOR FEEDWATER SYSTEM | P&ID |  | FEEDWATER SYSTEM |  |  | P&ID for FEEDWATER SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7098 | 0.5629 | 0.5629 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater | h2 | feedwater | query | feedwater | match | true | false | 1 | 4 | 17.3813 | 0.7930 | 0.0320 | 0.0320 | hybrid | structured_preferred | feedwater | system_design¦procurement | 10 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0PGB-110010 | P&I DIAGRAM FOR CLOSED COOLING WATER SYSTEM | P&ID |  | CLOSED COOLING WATER SYSTEM |  |  | P&ID for CLOSED COOLING WATER SYSTEM | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7404 | 0.5721 | 0.5721 | g_safe | [5 empty] | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | true | 29 | 18 | 31.9057 | 0.6546 | 0.0241 | 0.0144 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GHC-110011 | P&I DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | P&ID |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | P&ID for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6876 | 0.5563 | 0.5563 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | h2 | wts | query | wts | match | true | false | 1 | 1 | 30.7530 | 0.6894 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦procurement | 10 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QJA-110012 | P&I DIAGRAM FOR NITROGEN GAS SYSTEM | P&ID | Nitrogen System | NITROGEN GAS SYSTEM |  |  | P&ID for NITROGEN GAS SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7583 | 0.5775 | 0.5775 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 | h2 | n2 | query | n2 | match | true | false | 1 | 1 | 42.0002 | 0.8400 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P1MBH-110013 | GTG - P&I DIAGRAM FOR GT ROTOR COOLING AIR COOLER SYSTEM | P&ID | Gas Turbine Generator | Gas Turbine ROTOR COOLING AIR COOLER SYSTEM |  |  | P&ID for Gas Turbine ROTOR COOLING AIR COOLER SYSTEM |  | GT - GT FUEL GAS HEATER & GT COOLING AIR COOLER SYSTEM P&I DIAGRAM | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | rule_query | diagram | diagram | p_id | p_id | air¦cooler¦cooling¦gas¦generator¦gtg¦rotor¦turbine | fgp¦gt¦gtg | scoped | match | match | match | passed |  | 0.6000 | 0.7091 | 0.6327 | 0.6327 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gtg | fgp¦gtg | gtg | query |  | activity_unscoped | true | true | 84 | 952 | 26.1209 | 0.5483 | 0.0079 | 0.0048 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P1EKC-110014 | P&I DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | P&ID | Gas Turbine Generator | Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | P&ID for Gas Turbine PERFORMANCE HEATER SYSTEM |  | GT - FUEL GAS SYSTEM P&I DIAGRAM | 1 | start+86D<=FA<=start+86D+2M | FA ∈ [start+86d, start+146d] | rule_query | diagram | diagram | p_id | p_id | gas¦gtg¦heater¦performance¦turbine | fgp¦gt¦gtg | scoped | match | match | match | passed |  | 0.5000 | 0.6805 | 0.5542 | 0.5542 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gtg | fgp¦gtg | gtg | query |  | activity_unscoped | true | true | 35 | 1748 | 20.5703 | 0.5056 | 0.0111 | 0.0066 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-06-09 | 2024-07-09 | 2024-08-08 | 2024-08-23 | 2024-09-07 | 2024-09-22 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0LA-110031 | PROCESS FLOW DIAGRAM FOR STEAM/CONDENSATE/FW SYSTEM | PROCESS FLOW DIAGRAM |  | STEAM/CONDENSATE/Feed Water SYSTEM |  |  | PROCESS FLOW DIAGRAM for STEAM/CONDENSATE/Feed Water SYSTEM | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | title | diagram | diagram | diagram | diagram | condensate¦feed¦steam¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5888 | 0.5266 | 0.5266 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | condensate¦feedwater |  | condensate¦feedwater | query | feedwater | match | false | false | 2 | 1 | 23.1574 | 0.6912 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate¦feedwater | system_design¦engineering | 2 | 2024-04-16 | 2024-05-21 | 2024-06-25 | 2024-06-11 | 2024-07-16 | 2024-08-20 | generated | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0PG-110032 | PROCESS FLOW DIAGRAM FOR CCW SYSTEM | PROCESS FLOW DIAGRAM |  | Closed Cooling Water SYSTEM |  |  | PROCESS FLOW DIAGRAM for Closed Cooling Water SYSTEM | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | title | diagram | diagram | diagram | diagram | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6105 | 0.5332 | 0.5332 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 27.6951 | 0.4758 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-03-15 | 2024-04-19 | 2024-05-24 | 2024-05-10 | 2024-06-14 | 2024-07-19 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GHC-110033 | PROCESS FLOW DIAGRAM FOR DM WATER SYSTEM | PROCESS FLOW DIAGRAM |  | Demineralized WATER SYSTEM |  |  | PROCESS FLOW DIAGRAM for Demineralized WATER SYSTEM | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | title | diagram | diagram | diagram | diagram | demineralized¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5549 | 0.5165 | 0.5165 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 21.0132 | 0.5734 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦engineering | 5 | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-110035 | DESIGN CRITERIA FOR STEAM AND BYPASS SYSTEM | DESIGN CRITERIA |  | STEAM AND BYPASS SYSTEM |  |  | DESIGN CRITERIA for STEAM AND BYPASS SYSTEM | Intake Screening System | Design Criteria | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | criteria | criteria | design_criteria | design_criteria | bypass¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5394 | 0.5818 | 0.5818 | g_safe | [5 empty] | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | [5 empty] | query_unscoped | true | true | 1 | 4 | 62.3058 | 0.6070 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | design_criteria¦system_design¦civil_design |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LC-110036 | DESIGN CRITERIA FOR CONDENSATE SYSTEM | DESIGN CRITERIA |  | CONDENSATE SYSTEM |  |  | DESIGN CRITERIA for CONDENSATE SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | condensate |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6209 | 0.6063 | 0.6063 | g_safe | [5 empty] | FA | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | design_criteria | civil_design | compatible | condensate | wts | condensate | query | condensate | match | true | false | 7 | 4 | 23.3948 | 0.6677 | 0.0306 | 0.0229 | hybrid | structured_cell_found_text_preferred | condensate | design_criteria¦system_design¦civil_design |  | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LA-110037 | DESIGN CRITERIA FOR FEEDWATER SYSTEM | DESIGN CRITERIA |  | FEEDWATER SYSTEM |  |  | DESIGN CRITERIA for FEEDWATER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6526 | 0.6158 | 0.6158 | g_safe | [5 empty] | FA | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | design_criteria | civil_design | compatible | feedwater | wts | feedwater | query | feedwater | match | true | false | 1 | 1 | 10.6433 | 0.6337 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater | design_criteria¦system_design¦civil_design | 10 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0PGB-110038 | DESIGN CRITERIA FOR CLOSED COOLING WATER SYSTEM | DESIGN CRITERIA |  | CLOSED COOLING WATER SYSTEM |  |  | DESIGN CRITERIA for CLOSED COOLING WATER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6211 | 0.6063 | 0.6063 | g_safe | [5 empty] | FA | 2EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | 2007-09-03 | 2008-01-30 | design_criteria | civil_design | compatible | ccw | wts | ccw | query | ccw | match | true | false | 3 | 2 | 38.1569 | 0.5971 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | ccw | design_criteria¦system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0GHC-110039 | DESIGN CRITERIA FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | DESIGN CRITERIA |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | DESIGN CRITERIA for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6451 | 0.6135 | 0.6135 | g_safe | [5 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | design_criteria | civil_design | compatible | wts | wts | wts | query | wts | match | true | false | 3 | 1 | 54.7606 | 0.6092 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | wts | design_criteria¦system_design¦civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-110040 | SYSTEM DESCRIPTION FOR STEAM AND BYPASS SYSTEM | System Description |  | STEAM AND BYPASS SYSTEM |  |  | System Description for STEAM AND BYPASS SYSTEM | Sampling System | System Description for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | bypass¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.6771 | 0.6406 | 0.6406 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match |  | sampling | sampling | rule | sampling | match | false | false | 1 | 1 | 15.1307 | 0.5730 | 0.0328 | 0.0328 | hybrid | structured_preferred | sampling | system_design¦procurement | 5 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LC-110041 | SYSTEM DESCRIPTION FOR CONDENSATE SYSTEM | System Description |  | CONDENSATE SYSTEM |  |  | System Description for CONDENSATE SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | condensate |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6085 | 0.6492 | 0.5518 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 22.4052 | 0.8082 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦procurement |  | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LA-110042 | SYSTEM DESCRIPTION FOR FEEDWATER SYSTEM | System Description |  | FEEDWATER SYSTEM |  |  | System Description for FEEDWATER SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | feedwater |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5742 | 0.6389 | 0.5431 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 1 | 1 | 10.0830 | 0.7584 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design¦procurement | 10 | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PGB-110043 | SYSTEM DESCRIPTION FOR CLOSED COOLING WATER SYSTEM | System Description |  | CLOSED COOLING WATER SYSTEM |  |  | System Description for CLOSED COOLING WATER SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | title | description | description | system_description | system_description | closed¦cooling¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5717 | 0.6382 | 0.5425 | g_safe | [5 empty] | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | true | 233 | 1 | 17.9791 | 0.6611 | 0.0198 | 0.0119 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | generated | 0.60 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GHC-110044 | SYSTEM DESCRIPTION FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | System Description |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | System Description for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Sampling System | System Description for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.5732 | 0.6095 | 0.6095 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | sampling | wts | query | wts | match | true | false | 1 | 1 | 23.0179 | 0.6478 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦procurement | 10 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LB-110045 | PRESSURE LOSS CALCULATIONS FOR MAIN STEAM SYSTEM | CALCULATIONS |  | MAIN STEAM SYSTEM |  |  | CALCULATIONS for MAIN STEAM SYSTEM | Sampling System | Calculation Sheet for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | main¦steam |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6950 | 0.4418 | 0.4418 | g_safe | [5 empty] | FI | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | civil_design | civil_design | match | steam | sampling | steam | query | hrsg | mismatch | true | false | 25 | 953 | 16.7068 | 0.4379 | 0.0128 | 0.0032 | hybrid | structured_phase_gap | steam | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LC-110046 | SIZING CALCULATION FOR CONDENSATE EXTRACTION PUMP | Calculation sheet | Condensate Extraction Pump | Condensate System |  |  | Calculation sheet for CEP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4871 | 0.4961 | 0.4961 | g_safe | [5 empty] | SKIP | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 2 | 47.0897 | 0.6190 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LC-110047 | SIZING CALCULATION FOR FGP CONDENSATE PUMP | Calculation sheet | Fuel Gas Package CONDENSATE PUMP | Condensate System |  |  | Calculation sheet for Fuel Gas Package CONDENSATE PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | condensate¦fgp¦fuel¦gas¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4720 | 0.4916 | 0.4916 | g_safe | [5 empty] | SKIP | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate¦fgp |  | condensate¦fgp | query | condensate¦fgp | match | true | false | 1 | 1 | 32.9456 | 0.6519 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fgp | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110048 | SIZING CALCULATION FOR HRSG FEEDWATER PUMP | Calculation sheet | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | Calculation sheet for Heat Recovery Steam Generator FEEDWATER PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4870 | 0.4961 | 0.4961 | g_safe | [5 empty] | SKIP | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | true | false | 9 | 30 | 12.9120 | 0.5322 | 0.0256 | 0.0256 | hybrid | structured_preferred | feedwater¦hrsg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110049 | SIZING CALCULATION FOR FGP FEEDWATER PUMP | Calculation sheet | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | Calculation sheet for Fuel Gas Package FEEDWATER PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | feedwater¦fgp¦fuel¦gas¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4688 | 0.4906 | 0.4906 | g_safe | [5 empty] | SKIP | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | true | false | 15 | 11 | 8.2715 | 0.5878 | 0.0274 | 0.0274 | hybrid | structured_preferred | feedwater¦fgp | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0PGB-110050 | SIZING CALCULATION FOR CLOSED COOLING WATER SYSTEM | Calculation sheet |  | CLOSED COOLING WATER SYSTEM |  |  | Calculation sheet for CLOSED COOLING WATER SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5643 | 0.5193 | 0.5193 | g_safe | [5 empty] | SKIP | 1EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-01-30 | civil_design | civil_design | match | ccw | dc_ups | ccw | query | ccw | match | true | false | 1 | 9 | 28.9307 | 0.5496 | 0.0309 | 0.0309 | hybrid | structured_preferred | ccw | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GHC-110051 | SIZING CALCULATION FOR CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP | Calculation sheet | CYCLE MAKEUP WATER PUMP AND Demineralized WATER SUPPLY PUMP | Water Treatment System |  |  | Calculation sheet for CYCLE MAKEUP WATER PUMP AND Demineralized WATER SUPPLY PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | cycle¦demineralized¦makeup¦pump¦supply¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4680 | 0.4904 | 0.4904 | g_safe | [5 empty] | SKIP | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 1 | 2 | 37.4657 | 0.5776 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0QJA-110052 | SIZING CALCULATION FOR NITROGEN GAS SYSTEM | Calculation sheet | Nitrogen System | NITROGEN GAS SYSTEM |  |  | Calculation sheet for Nitrogen System | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5561 | 0.5168 | 0.5168 | g_safe | [5 empty] | SKIP | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 | dc_ups | n2 | query | n2 | match | true | false | 1 | 5 | 26.0914 | 0.5664 | 0.0318 | 0.0318 | hybrid | structured_preferred | n2 | civil_design | 9 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0MJ-110053 | BSEDG - CALCULATION | Calculation sheet | BLACK START EMERGENCY Diesel Generator |  |  |  | Calculation sheet for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | HVAC Calculation | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | calculation | calculation | calculation | calculation | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8020 | 0.7073 | 0.7073 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg¦hvac | bsedg | query | bsedg | match | true | false | 1 | 2 | 7.2736 | 0.6195 | 0.0325 | 0.0325 | hybrid | structured_preferred | bsedg | civil_design | 6 | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110061 | HRSG/FGP FEEDWATER PUMP NPSH TRANSIENT ANALYSIS | ANALYSIS | Heat Recovery Steam Generator/Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | ANALYSIS for Heat Recovery Steam Generator/Fuel Gas Package FEEDWATER PUMP | [5 empty] | rule_query | other | drawing | analysis | drawing | feedwater¦fgp¦fuel¦gas¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg¦pump | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.7005 | 0.5601 | 0.5601 | [7 empty] | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | feedwater¦fgp¦hrsg |  | feedwater¦fgp¦hrsg | query | hrsg | match | true | false | 37 | 21 | 13.4377 | 0.6147 | 0.0227 | 0.0170 | hybrid | structured_no_phase | feedwater¦fgp¦hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110101 | DATA SHEET FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | Data Sheet | SAFETY RELIEF VALVE AND RUPTURE DISC | Balance of Plant SYSTEMS |  |  | Data Sheet for SAFETY RELIEF VALVE AND RUPTURE DISC | BYPASS VALVE & PRDS | Data Sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | datasheet | datasheet | data_sheet | data_sheet | bop¦disc¦relief¦rupture¦safety¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7348 | 0.6404 | 0.6404 | g_safe | [5 empty] | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 1 | 1 | 71.7061 | 0.7245 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop | procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LF-110102 | OUTLINE DRAWING FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | Outline Drawing | SAFETY RELIEF VALVE AND RUPTURE DISC | Balance of Plant SYSTEMS |  |  | Outline Drawing for SAFETY RELIEF VALVE AND RUPTURE DISC | BYPASS VALVE & PRDS | Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | bop¦disc¦relief¦rupture¦safety¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7412 | 0.6424 | 0.6424 | g_safe | [5 empty] | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | bop |  | bop | query |  | activity_unscoped | true | true | 768 | 30 | 6.9073 | 0.5263 | 0.0123 | 0.0074 | hybrid | structured_phase_gap | bop | system_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAN-110153 | DATA SHEET FOR BYPASS AND PRDS | Data Sheet | BYPASS AND Pressure Reducing and Desuperheating Station |  |  |  | Data Sheet for BYPASS AND Pressure Reducing and Desuperheating Station | BYPASS VALVE & PRDS | Data Sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | datasheet | datasheet | data_sheet | data_sheet | bypass¦desuperheating¦pressure¦reducing¦station |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8876 | 0.8263 | 0.8263 | g_safe | [5 empty] | FA | 1PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-07-03 | 2008-04-30 | procurement | procurement | match |  |  |  |  | fgp¦hrsg | query_unscoped | false | false | 8 | 9 | 21.9400 | 0.6178 | 0.0292 | 0.0219 | hybrid | structured_no_system |  | procurement |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MAN-110154 | OUTLINE DRAWING FOR BYPASS AND PRDS | Outline Drawing | BYPASS AND Pressure Reducing and Desuperheating Station |  |  |  | Outline Drawing for BYPASS AND Pressure Reducing and Desuperheating Station | BYPASS VALVE & PRDS | Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | bypass¦desuperheating¦pressure¦reducing¦station |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8345 | 0.8103 | 0.8103 | g_safe | [5 empty] | FA | 3EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 5 | 2 | 22.5548 | 0.6231 | 0.0315 | 0.0189 | hybrid | structured_no_system |  | system_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0ZEN-110201 | STEAM BLOWING - OUT PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | STEAM BLOWING - OUT PROCEDURE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | procedure | procedure |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | [6 empty] | FA | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Compressed Air System (BOP) | 2008-09-02 | 2008-12-31 |  |  | query_unknown |  |  |  |  | bop¦compressed_air | query_unscoped | true | false | 6 | 31 | 7.7635 | 0.5223 | 0.0261 | 0.0147 | hybrid | structured_no_system |  |  |  | 2025-04-21 | 2025-05-06 | 2025-05-21 | 2025-06-05 | 2025-07-05 | 2025-08-04 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LBG-110251 | DATA SHEET FOR SILENCER | Data Sheet | SILENCER |  |  |  | Data Sheet for SILENCER | Silencer | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | silencer |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8574 | 0.7822 | 0.7822 | g_safe | [5 empty] | FA | 1PF2510W42A04P | (Silencer) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-15 | 2008-07-15 | procurement | procurement | match |  |  |  |  | steam | query_unscoped | true | false | 2 | 2 | 21.2416 | 0.7137 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LBG-110252 | OUTLINE DRAWING FOR SILENCER | Outline Drawing | SILENCER |  |  |  | Outline Drawing for SILENCER |  | OUTLINE DRAWING FOR SILENCER | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | outline_drawing | outline_drawing | silencer |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match |  |  |  |  | n2 | query_unscoped | false | false | 1175 | 72 |  | 0.3534 | 0.0084 | 0.0063 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCP-110301 | DATA SHEET FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | Data Sheet | CONDENSATE PLATE TYPE HEAT EXCHANGER | Condensate System |  |  | Data Sheet for CONDENSATE PLATE TYPE HEAT EXCHANGER |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | condensate¦exchanger¦heat¦plate¦type |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5777 | 0.6400 | 0.6400 | g_safe | [5 empty] | FA | 1EF3020W00A02 | (COND System) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-13 | 2007-05-31 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 4 | 7 | 28.8690 | 0.6810 | 0.0306 | 0.0306 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-06-22 | 2024-07-22 | 2024-08-21 | 2024-09-05 | 2024-09-20 | 2024-10-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCP-110302 | OUTLINE DRAWING FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | Outline Drawing | CONDENSATE PLATE TYPE HEAT EXCHANGER | Condensate System |  |  | Outline Drawing for CONDENSATE PLATE TYPE HEAT EXCHANGER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | condensate¦exchanger¦heat¦plate¦type |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5325 | 0.6264 | 0.6264 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 21.1197 | 0.6559 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110401 | GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | GENERAL ARRANGEMENT DRAWING | CLOSED COOLING WATER PUMP | Closed Cooling Water System |  |  | GENERAL ARRANGEMENT DRAWING for CLOSED COOLING WATER PUMP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | closed¦cooling¦pump¦water |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6420 | 0.8926 | 0.8926 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 21.0648 | 0.3953 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0PGB-110402 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | DRAWING | CLOSED COOLING WATER PUMP | Closed Cooling Water System |  |  | DRAWING for CLOSED COOLING WATER PUMP |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | closed¦cooling¦pump¦water | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6803 | 0.6708 | 0.4695 | [6 empty] | FA | 1EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | true | false | 7 | 2 | 41.9663 | 0.6342 | 0.0311 | 0.0233 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.64 | usable | rule_score_medium;activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0PGB-110403 | DATA SHEET FOR CLOSED COOLING WATER PUMP | Data Sheet | CLOSED COOLING WATER PUMP | Closed Cooling Water System |  |  | Data Sheet for CLOSED COOLING WATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | closed¦cooling¦pump¦water | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6906 | 0.7322 | 0.7322 | [6 empty] | FA | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match | ccw |  | ccw | query | ccw | match | true | false | 1 | 1 | 55.1544 | 0.7399 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-06-07 | 2024-07-12 | 2024-08-16 | 2024-08-02 | 2024-09-06 | 2024-10-11 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110404 | OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | Outline Drawing | CLOSED COOLING WATER PUMP MOTOR | Closed Cooling Water System |  |  | Outline Drawing for CLOSED COOLING WATER PUMP MOTOR |  | Pump Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | closed¦cooling¦motor¦pump¦water | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7034 | 0.9110 | 0.9110 | [6 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 21.0648 | 0.3760 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110405 | MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | DRAWING | CLOSED COOLING WATER PUMP MOTOR | Closed Cooling Water System |  |  | DRAWING for CLOSED COOLING WATER PUMP MOTOR |  | Name Plate DraWing for Pump and Motor | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | closed¦cooling¦motor¦pump¦water | pump | scoped | match | match | match | passed |  | 0.5714 | 0.6774 | 0.6032 | 0.6032 | [6 empty] | FI | 1EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | true | false | 7 | 3 | 41.9663 | 0.6270 | 0.0308 | 0.0231 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0PGB-110406 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | DRAWING | CLOSED COOLING WATER PUMP MOTOR | Closed Cooling Water System |  |  | DRAWING for CLOSED COOLING WATER PUMP MOTOR |  | Name Plate DraWing for Pump and Motor | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | closed¦cooling¦motor¦pump¦water | pump | scoped | match | match | match | passed |  | 0.5714 | 0.6774 | 0.6032 | 0.6032 | [6 empty] | FI | 1EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | true | false | 7 | 3 | 41.9663 | 0.6162 | 0.0308 | 0.0231 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0PGB-110407 | DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | Data Sheet | CLOSED COOLING WATER PUMP MOTOR | Closed Cooling Water System |  |  | Data Sheet for CLOSED COOLING WATER PUMP MOTOR | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | closed¦cooling¦motor¦pump¦water | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6384 | 0.7165 | 0.7165 | [6 empty] | FA | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match | ccw |  | ccw | query | ccw | match | true | false | 1 | 1 | 55.1544 | 0.7117 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-06-07 | 2024-07-12 | 2024-08-16 | 2024-08-02 | 2024-09-06 | 2024-10-11 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QJA-110500 | SYSTEM DESCRIPTION FOR NITROGEN GAS SYSTEM | System Description | Nitrogen System | NITROGEN GAS SYSTEM |  |  | System Description for NITROGEN GAS SYSTEM | N2 Gas System | System Description | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | description | description | system_description | system_description | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8613 | 0.7834 | 0.7834 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 | n2 | n2 | query | n2 | match | true | false | 1 | 1 | 34.9021 | 0.8295 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | system_design¦procurement |  | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0QJA-110501 | EQUIPMENT ASSEMBLY AND DETAIL DRAWING FOR NITROGEN GAS SYSTEM | EQUIPMENT ASSEMBLY AND DETAIL DRAWING | Nitrogen System | NITROGEN GAS SYSTEM |  |  | EQUIPMENT ASSEMBLY AND DETAIL DRAWING for NITROGEN GAS SYSTEM | N2 Gas System | Equipment Assembly and Detail DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.8509 | 0.8678 | 0.8678 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | design_drawing | system_design | compatible | n2 | n2 | n2 | query | n2 | match | true | false | 7 | 1 | 32.8926 | 0.7274 | 0.0313 | 0.0235 | hybrid | structured_cell_found_text_preferred | n2 | system_design¦civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QJA-110502 | GENERAL ARRANGEMENT DRAWING FOR NITROGEN GAS SYSTEM | GENERAL ARRANGEMENT DRAWING | Nitrogen System | NITROGEN GAS SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for Nitrogen System |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | nitrogen |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6842 | 0.9053 | 0.9053 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 |  | n2 | query | n2 | match | true | false | 1 | 1 | 28.2351 | 0.7460 | 0.0328 | 0.0328 | hybrid | structured_preferred | n2 | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QJA-110503 | DATA SHEET FOR NITROGEN GAS SYSTEM | Data Sheet | Nitrogen System | NITROGEN GAS SYSTEM |  |  | Data Sheet for Nitrogen System | N2 Gas System | Instrument Data Sheet | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | datasheet | datasheet | data_sheet | data_sheet | nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8129 | 0.7105 | 0.7105 | g_safe | [5 empty] | FA | 1EF3515W00A02 | (N2 Gas System) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-27 | 2007-07-31 | procurement | procurement | match | n2 | n2 | n2 | query | n2 | match | true | false | 1 | 1 | 36.1195 | 0.7365 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | procurement |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MJ-110504 | BSEDG - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | BLACK START EMERGENCY Diesel Generator |  |  |  | GENERAL ARRANGEMENT DRAWING for BLACK START EMERGENCY Diesel Generator |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | black¦diesel¦emergency¦generator¦start |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6474 | 0.8942 | 0.8942 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg |  | bsedg | query |  | activity_unscoped | true | true | 111 | 689 | 13.4438 | 0.4941 | 0.0072 | 0.0043 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MJ-110505 | BSEDG - P&I DIAGRAM | P&ID | BLACK START EMERGENCY Diesel Generator |  |  |  | P&ID for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8760 | 0.8228 | 0.8228 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | true | 8 | 76 | 19.0877 | 0.5779 | 0.0221 | 0.0132 | hybrid | structured_blocked_procurement_conflict | bsedg | system_design¦procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MJ-110506 | BSEDG - OUTLINE DRAWING | Outline Drawing | BLACK START EMERGENCY Diesel Generator |  |  |  | Outline Drawing for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Equipment Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8716 | 0.7615 | 0.7615 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | true | 605 | 659 | 2.5734 | 0.4630 | 0.0029 | 0.0017 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MJ-110507 | BSEDG - SINGLE LINE DIAGRAM | Single Line Diagram | BLACK START EMERGENCY Diesel Generator |  |  |  | Single Line Diagram for BLACK START EMERGENCY Diesel Generator |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7166 | 0.9150 | 0.9150 | g_safe | [5 empty] | SKIP | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg |  | bsedg | query |  | activity_unscoped | true | true | 27 | 553 | 13.8746 | 0.4724 | 0.0131 | 0.0079 | hybrid | structured_phase_gap | bsedg | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MJ-110508 | BSEDG - DATA SHEET | Data Sheet | BLACK START EMERGENCY Diesel Generator |  |  |  | Data Sheet for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Equipment Data Sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8944 | 0.7683 | 0.7683 | g_safe | [5 empty] | FA | 0EF3530W00A01 | (BSDG) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-03-01 | 2007-04-30 | procurement | procurement | match | bsedg | bsedg | bsedg | query | bsedg | match | true | false | 1 | 2 | 17.3361 | 0.6887 | 0.0325 | 0.0325 | hybrid | structured_preferred | bsedg | procurement | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0MJ-110509 | BSEDG - PIPING ISOMETRIC DRAWING | PIPING ISOMETRIC DRAWING | BLACK START EMERGENCY Diesel Generator |  |  |  | PIPING ISOMETRIC DRAWING for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Pipe Isometric DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8629 | 0.7589 | 0.7589 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | true | 216 | 59 | 8.5049 | 0.5698 | 0.0120 | 0.0072 | hybrid | structured_phase_gap | bsedg | system_design |  | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MJ-110510 | BSEDG - SYSTEM DESCRIPTION | System Description | BLACK START EMERGENCY Diesel Generator |  |  |  | System Description for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | System description including Operation Philosophy | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | description | description | system_description | system_description | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.5556 | 0.8416 | 0.6414 | 0.6414 | g_safe | [5 empty] | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | true | 119 | 113 | 8.9278 | 0.5360 | 0.0114 | 0.0068 | hybrid | structured_blocked_procurement_conflict | bsedg | system_design¦procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MJ-110511 | BSEDG - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | BLACK START EMERGENCY Diesel Generator |  |  |  | Control Logic Diagram for BLACK START EMERGENCY Diesel Generator | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6301 | 0.7140 | 0.7140 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg |  | bsedg | query |  | activity_unscoped | true | true | 35 | 908 | 13.8746 | 0.4482 | 0.0116 | 0.0069 | hybrid | structured_phase_gap | bsedg | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0MJ-110512 | BSEDG - EMBEDDED CONDUIT LAYOUT | EMBEDDED CONDUIT LAYOUT | BLACK START EMERGENCY Diesel Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for BLACK START EMERGENCY Diesel Generator |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8758 | 0.9628 | 0.6739 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg |  | bsedg | query | bsedg | match | true | false | 1 | 4 | 7.2736 | 0.6597 | 0.0320 | 0.0320 | hybrid | structured_preferred | bsedg | civil_design | 6 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MJ-110561 | BSEDG - CONTROL PANEL OUTLINE DRAWING | Outline Drawing | BLACK START EMERGENCY Diesel Generator |  |  |  | Outline Drawing for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Equipment Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8716 | 0.7615 | 0.7615 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | true | 864 | 354 | 2.5734 | 0.4791 | 0.0035 | 0.0021 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XG11-P0MJ-110564 | BSEDG - SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM | BLACK START EMERGENCY Diesel Generator |  |  |  | SCHEMATIC DIAGRAM for BLACK START EMERGENCY Diesel Generator |  | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | schematic_diagram | schematic_diagram | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6489 | 0.6613 | 0.6613 | g_safe | [5 empty] | SKIP | 0EF3530W32A16.1 | (Common EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Common Emergency Diesel Generator | 2007-07-27 | 2007-11-27 | design_drawing | civil_design | compatible | bsedg |  | bsedg | query |  | activity_unscoped | true | true | 31 | 94 | 13.5569 | 0.5420 | 0.0175 | 0.0079 | hybrid | structured_phase_gap | bsedg | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0MJ-110568 | BSEDG - PROTECTION RELAY SETTING REPORT | REPORT | BLACK START EMERGENCY Diesel Generator |  |  |  | REPORT for BLACK START EMERGENCY Diesel Generator |  | PROTECTION RELAY SETTING REPORT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8747 | 0.9624 | 0.6737 | g_safe | [5 empty] | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bsedg |  | bsedg | query | ccw¦gtg | mismatch | false | false | 370 | 979 | 1.0037 | 0.4295 | 0.0033 | 0.0008 | hybrid | structured_phase_gap | bsedg | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MJ-110578 | BSEDG – MV SWGR DRAWING | DRAWING | BLACK START EMERGENCY Diesel Generator |  |  |  | DRAWING for BLACK START EMERGENCY Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | Piping Arrangement DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | black¦diesel¦emergency¦generator¦start |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.8113 | 0.6434 | 0.6434 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | design_drawing | civil_design | compatible | bsedg¦mv_lv | bsedg | bsedg¦mv_lv | query | bsedg | match | true | false | 1 | 1 | 7.2736 | 0.6406 | 0.0328 | 0.0246 | hybrid | structured_preferred | bsedg¦mv_lv | system_design¦civil_design | 6 | 2025-05-01 | 2025-05-31 | 2025-06-30 | 2025-07-15 | 2025-07-30 | 2025-08-14 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110601 | VALVE LIST & DATA SHEET FOR MOV (G&G) | VALVE LIST & DATA SHEET | Motor Operated Valve |  |  |  | Valve List for Motor Operated Valve |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | motor¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7202 | 0.6827 | 0.6827 | g_safe | [5 empty] | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 1 | 69.8949 | 0.6924 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-110602 | OUTLINE DRAWING FOR MOV (G&G) | Outline Drawing | Motor Operated Valve |  |  |  | Outline Drawing for Motor Operated Valve |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | motor¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6547 | 0.8964 | 0.8964 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 556 | 277 | 5.3193 | 0.4288 | 0.0046 | 0.0028 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110603 | VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | VALVE LIST & DATA SHEET | Motor Operated Valve |  |  |  | Valve List for Motor Operated Valve |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | motor¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7202 | 0.6827 | 0.6827 | g_safe | [5 empty] | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 1 | 69.8949 | 0.7007 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-110604 | OUTLINE DRAWING FOR MOV (BUTTERFLY) | Outline Drawing | Motor Operated Valve |  |  |  | Outline Drawing for Motor Operated Valve |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | motor¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6547 | 0.8964 | 0.8964 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 505 | 110 | 5.3193 | 0.4346 | 0.0077 | 0.0046 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110701 | OPERATION PHILOSOPHY OF OVERALL PLANT | OPERATION PHILOSOPHY |  |  |  |  | OPERATION PHILOSOPHY |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.2500 | 0.4212 | 0.3013 | 0.3013 | [6 empty] | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | true | false | 6 | 9 | 15.6495 | 0.4584 | 0.0296 | 0.0167 | hybrid | structured_no_system | [9 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110702 | PLANT START-UP AND SHUT-DOWN PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | PLANT start - UP AND SHUT - DOWN PROCEDURE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | procedure | procedure |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9355 | 0.9807 | 0.6865 | [6 empty] | FA | 0SF7000W62A08 | (DCS) Start up | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-02 | 2008-07-11 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | true | false | 1 | 4 | 15.9027 | 0.5304 | 0.0320 | 0.0180 | hybrid | structured_no_system |  |  |  | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-04-04 | 2025-05-04 | 2025-06-03 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110703 | HAZARD AND OPERABILITY STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 | [7 empty] | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | false | 1 | 1412 | 4.2192 | 0.2942 | 0.0171 | 0.0128 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110704 | SAFETY INTEGRITY LEVEL STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 | [7 empty] | 0PF6050W86A04.1T | (Safety Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2008-05-24 | 2008-07-08 |  | delivery | query_unknown |  |  |  |  | bop | query_unscoped | true | false | 4 | 25 | 11.5474 | 0.3922 | 0.0274 | 0.0154 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110705 | HAZARDOUS AREA CLASSIFICATION REPORT | REPORT |  |  |  |  | Hazardous Area Classification |  | GT - HAZARDOUS AREA CLASSIFICATION | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | rule_query | classification | classification | hazardous_area_classification | hazardous_area_classification |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8089 | 0.7677 | 0.7677 | [6 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  | gtg | gtg | rule | ccw¦gtg | match | false | false | 1 | 1 |  | 0.3454 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110706 | HAZOP AND SIL STUDY PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.4221 | 0.4766 | 0.4766 | [6 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | false | 28 | 3058 | 4.2192 | 0.3344 | 0.0117 | 0.0088 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GKB-120001 | P&I DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | P&ID |  | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | P&ID for POTABLE WATER STORAGE AND SUPPLY SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | potable¦storage¦supply¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6937 | 0.6748 | 0.6748 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts | h2 | wts | query | wts | match | true | false | 1 | 1 | 53.6325 | 0.7591 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GKC-120002 | P&I DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | P&ID |  | POTABLE WATER DISTRIBUTION SYSTEM |  |  | P&ID for POTABLE WATER DISTRIBUTION SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | distribution¦potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6436 | 0.5431 | 0.5431 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts | h2 | wts | query | wts | match | true | false | 1 | 1 | 43.8375 | 0.7558 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120004 | P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | P&ID |  | COMPRESSED AIR SYSTEM |  |  | P&ID for COMPRESSED AIR SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7275 | 0.5683 | 0.5683 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | h2 | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 42.1472 | 0.7797 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120005 | P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | P&ID |  | INSTRUMENT AIR SYSTEM |  |  | P&ID for INSTRUMENT AIR SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦instrument |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7293 | 0.5688 | 0.5688 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | h2 | compressed_air | query | compressed_air | match | true | false | 5 | 1 | 25.8024 | 0.7249 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120006 | P&I DIAGRAM FOR SERVICE AIR SYSTEM | P&ID |  | SERVICE AIR SYSTEM |  |  | P&ID for SERVICE AIR SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦service |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6992 | 0.5598 | 0.5598 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | h2 | compressed_air | query | compressed_air | match | true | false | 5 | 1 | 25.8024 | 0.7159 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0EK-120007 | P&I DIAGRAM FOR FUEL GAS SYSTEM | P&ID | Fuel Gas Package | FUEL GAS SYSTEM |  |  | P&ID for FUEL GAS SYSTEM | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8032 | 0.7660 | 0.7660 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 1 | 32.0350 | 0.7639 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-120008 | P&I DIAGRAM FOR WASTE WATER TRANSFER SYSTEM | P&ID |  | WASTE WATER TRANSFER SYSTEM |  |  | P&ID for WASTE WATER TRANSFER SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | transfer¦waste¦water |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6807 | 0.5542 | 0.5542 | g_safe | [5 empty] | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | h2 | wts | query | wts | match | true | false | 1 | 1 | 40.9993 | 0.7320 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GKS-120012 | DESIGN CRITERIA FOR POTABLE WATER SYSTEM | DESIGN CRITERIA |  | POTABLE WATER SYSTEM |  |  | DESIGN CRITERIA for POTABLE WATER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6420 | 0.6126 | 0.6126 | g_safe | [5 empty] | FA | 0EF3035W16A14 | (PWT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-11-02 | 2008-03-04 | design_criteria | civil_design | compatible | wts | wts | wts | query | wts | match | true | false | 3 | 2 | 35.0193 | 0.5962 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | wts | design_criteria¦system_design¦civil_design |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GKS-120013 | SIZING CALCULATION - POTABLE WATER DISTRIBUTION PUMP | Calculation sheet | POTABLE WATER DISTRIBUTION PUMP | Water Treatment System |  |  | Calculation sheet for POTABLE WATER DISTRIBUTION PUMP | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | distribution¦potable¦pump¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5154 | 0.5046 | 0.5046 | g_safe | [5 empty] | SKIP | 0EF3035W16A14 | (PWT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-11-02 | 2008-03-04 | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 1 | 2 | 27.6387 | 0.5719 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SCA-120014 | PROCESS FLOW DIAGRAM FOR COMPRESSED AIR SYSTEM | PROCESS FLOW DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | PROCESS FLOW DIAGRAM for COMPRESSED AIR SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6337 | 0.8901 | 0.6231 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 35.3482 | 0.6720 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SCA-120015 | SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | System Description |  | COMPRESSED AIR SYSTEM |  |  | System Description for COMPRESSED AIR SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | title | description | description | system_description | system_description | air¦compressed |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6218 | 0.6532 | 0.5552 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 34.7443 | 0.7578 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | generated | 0.60 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SCA-120016 | DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | DESIGN CRITERIA |  | COMPRESSED AIR SYSTEM |  |  | DESIGN CRITERIA for COMPRESSED AIR SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5608 | 0.5882 | 0.5882 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_criteria | system_design | compatible | compressed_air | wts | compressed_air | query | compressed_air | match | true | false | 2 | 3 | 35.0666 | 0.5859 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | compressed_air | design_criteria¦system_design¦civil_design |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SCA-120017 | SIZING CALCULATION - COMPRESSED AIR SYSTEM | Calculation sheet |  | COMPRESSED AIR SYSTEM |  |  | Calculation sheet for COMPRESSED AIR SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6166 | 0.5350 | 0.5350 | g_safe | [5 empty] | SKIP | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | civil_design | civil_design | match | compressed_air | dc_ups | compressed_air | query | compressed_air | match | true | false | 2 | 1 | 23.9477 | 0.5954 | 0.0325 | 0.0325 | hybrid | structured_preferred | compressed_air | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0EKG-120018 | PROCESS FLOW DIAGRAM FOR FUEL GAS SYSTEM | PROCESS FLOW DIAGRAM | Fuel Gas Package | FUEL GAS SYSTEM |  |  | PROCESS FLOW DIAGRAM for FUEL GAS SYSTEM | Fuel Gas System | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | rule_query | diagram | diagram | diagram | diagram | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8183 | 0.7705 | 0.7705 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 4 | 27.5189 | 0.7265 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering |  | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-120019 | SYSTEM DESCRIPTION FOR FUEL GAS SYSTEM | System Description | Fuel Gas Package | FUEL GAS SYSTEM |  |  | System Description for FUEL GAS SYSTEM | Fuel Gas System | System description | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | rule_query | description | description | system_description | system_description | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 1.0000 | 0.9117 | 0.9735 | 0.9735 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 1 | 24.5374 | 0.7266 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-120020 | DESIGN CRITERIA FOR FUEL GAS SYSTEM | DESIGN CRITERIA | Fuel Gas Package | FUEL GAS SYSTEM |  |  | DESIGN CRITERIA for FGP | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | criteria | criteria | design_criteria | design_criteria | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5649 | 0.5895 | 0.5895 | g_safe | [5 empty] | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | design_criteria | civil_design | compatible | fgp | wts | fgp | query | fgp | match | true | false | 2 | 5 | 25.6505 | 0.6377 | 0.0315 | 0.0236 | hybrid | structured_cell_found_text_preferred | fgp | design_criteria¦system_design¦civil_design |  | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0EKG-120021 | SIZING CALCULATION - FUEL GAS SYSTEM | Calculation sheet | Fuel Gas Package | FUEL GAS SYSTEM |  |  | Calculation sheet for FGP | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5952 | 0.5286 | 0.5286 | g_safe | [5 empty] | SKIP | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match | fgp | dc_ups | fgp | query | fgp | match | true | false | 1 | 2 | 16.4735 | 0.6373 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GM-120022 | SYSTEM DESCRIPTION FOR WASTE WATER TRANSFER SYSTEM | System Description |  | WASTE WATER TRANSFER SYSTEM |  |  | System Description for WASTE WATER TRANSFER SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | transfer¦waste¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5377 | 0.6280 | 0.5338 | g_safe | [5 empty] | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 33.6246 | 0.6912 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GM-120023 | DESIGN CRITERIA FOR WASTE WATER TRANSFER SYSTEM | DESIGN CRITERIA |  | WASTE WATER TRANSFER SYSTEM |  |  | DESIGN CRITERIA for WASTE WATER TRANSFER SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | transfer¦waste¦water |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6499 | 0.6150 | 0.6150 | g_safe | [5 empty] | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | design_criteria | civil_design | compatible | wts | wts | wts | query | wts | match | true | false | 7 | 2 | 34.2095 | 0.5748 | 0.0311 | 0.0233 | hybrid | structured_cell_found_text_preferred | wts | design_criteria¦system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0ZEN-120050 | WATER BALANCE DIAGRAM | Diagram |  | Plant General System |  |  | Diagram for Plant General System |  | System Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | plant |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6815 | 0.6711 | 0.4698 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 4 | 3 | 14.4420 | 0.5229 | 0.0315 | 0.0177 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GKS-120051 | SYSTEM DESCRIPTION FOR POTABLE WATER SYSTEM | System Description |  | POTABLE WATER SYSTEM |  |  | System Description for POTABLE WATER SYSTEM |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | potable¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5764 | 0.6396 | 0.5436 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 36.1024 | 0.7404 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | generated | 0.60 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MBA-121001 | GTG - EQUIPMENT ARRANGEMENT | ARRANGEMENT | Gas Turbine Generator |  |  |  | ARRANGEMENT for GTG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6411 | 0.4257 | 0.3618 | g_safe | [5 empty] | FA | 2EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | true | false | 2 | 7 | 12.7873 | 0.6452 | 0.0311 | 0.0233 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-31 | 2024-04-15 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | generated | 0.60 |  | false | false | 0.46 | needs_review | default_fc_window;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121002 | GTG - GT EXHAUST MECHANICAL INTERFACE REQUIREMENTS | REQUIREMENTS | Gas Turbine Generator | Gas Turbine EXHAUST SYSTEM |  |  | REQUIREMENTS for GTG |  | Gas Turbine EXHAUST MECHANICAL INTERFACE REQUIREMENTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | requirements | requirements | design_requirements | design_requirements | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7606 | 0.6948 | 0.4864 | [6 empty] | FA | 1CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | 2008-03-18 | 2008-04-17 |  | installation | query_unknown | gtg | gtg | gtg | query | gtg | match | true | false | 2 | 5 | 23.0797 | 0.6649 | 0.0315 | 0.0236 | hybrid | structured_no_phase | gtg |  |  | 2024-11-04 | 2024-11-19 | 2024-12-04 | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.30 |  | false | false | 0.64 | usable | rule_score_medium;activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MBA-121003 | GTG - P&I DIAGRAM | P&ID | Gas Turbine Generator |  |  |  | P&ID for GTG |  | GT - P&I DIAGRAM LEGEND | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | title | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.5000 | 0.8113 | 0.5934 | 0.5934 | [6 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | gtg | gtg | gtg | query |  | activity_unscoped | true | true | 2 | 273 | 19.0877 | 0.6173 | 0.0191 | 0.0115 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-07-22 | 2024-08-21 | 2024-09-20 | 2024-10-05 | 2024-10-20 | 2024-11-04 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121004 | GTG - ROTOR COOLING AIR SYSTEM REQUIREMENTS | REQUIREMENTS | Gas Turbine Generator | ROTOR COOLING AIR SYSTEM |  |  | REQUIREMENTS for GTG |  | ROTOR COOLING AIR SYSTEM REQUIREMENTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | requirements | requirements | design_requirements | design_requirements | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8555 | 0.9566 | 0.6696 | g_safe | [5 empty] | FA | 1CF1265W42A15 | (TCA Cooler) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2008-04-16 | 2008-05-16 |  | installation | query_unknown | gtg |  | gtg | query | fgp¦gtg | match | true | false | 5 | 3 | 15.4436 | 0.6189 | 0.0313 | 0.0234 | hybrid | structured_no_phase | gtg |  |  | 2024-12-03 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121005 | GTG - GOVERNOR AND TURBINE MODEL | MODEL | Gas Turbine Generator |  |  |  | MODEL for GTG |  | GOVERNOR AND TURBINE MODEL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | model | model | model | model | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8314 | 0.9494 | 0.6646 | g_safe | [5 empty] | FA | 2CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | 2008-06-02 | 2008-06-14 |  | installation | query_unknown | gtg |  | gtg | query | gtg | match | true | false | 12 | 51 | 10.6987 | 0.6309 | 0.0229 | 0.0172 | hybrid | structured_no_phase | gtg |  |  | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-04-04 | 2025-05-04 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121006 | GTG - GENERATOR, EXCITATION SYSTEM, AND POWER SYSTEM STABILIZER MODEL | MODEL | Gas Turbine Generator | EXCITATION SYSTEM |  |  | MODEL for GTG |  | GOVERNOR AND TURBINE MODEL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | model | model | model | model | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6188 | 0.5356 | 0.3749 | g_safe | [5 empty] | FA | 2CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | 2008-06-02 | 2008-06-14 |  | installation | query_unknown | gtg |  | gtg | query | gtg | match | true | false | 12 | 6 | 11.7621 | 0.6118 | 0.0290 | 0.0218 | hybrid | structured_no_phase | gtg |  |  | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-04-04 | 2025-05-04 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0MBA-121007 | GTG - AUXILIARY EQUIPMENT FOUNDATION INTERFACE DRAWINGS | DRAWINGS | Gas Turbine Generator |  |  |  | DRAWINGS for GTG |  | GT - AUXILIARY EQUIPMENT FOUNDATION DRAWINGS | 1 | start+102D<=FA<=start+102D+2M | FA ∈ [start+102d, start+162d] | title | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.8970 | 0.8291 | 0.8291 | [6 empty] | FA | 1CF1265W16A11 | (Control Oil) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-10-01 | 2007-11-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 1 | 6 | 11.1337 | 0.6539 | 0.0315 | 0.0315 | hybrid | structured_preferred | gtg | civil_design | 10 | 2025-01-11 | 2025-02-10 | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBA-121008 | GTG - CUSTOMER PIPING CONNECTIONS PHYSICAL AND PROCESS DATA | DATA | Gas Turbine Generator | PIPING |  |  | DATA for GTG | Process Metering | Heat Loss Data | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | data | data | data | data | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.4266 | 0.4080 | 0.4080 | g_ambig | uncertain | 0.35 |  | 3 | The document is about customer piping connections data and does not clearly match air intake/exhaust loading data or signal interface list. | FI | 2PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | 2007-03-30 | 2008-02-29 | procurement | procurement | match | gtg |  | gtg | query | gtg | match | true | false | 2 | 6 | 15.3940 | 0.6590 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | procurement | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MBA-121009 | GTG - INLET FILTER AND DUCT SUPPLIER DRAWINGS | DRAWINGS | Gas Turbine Generator |  |  |  | DRAWINGS for GTG |  | INLET FILTER AND DUCT SUPPLIER DRAWINGS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8784 | 0.9635 | 0.6745 | g_ambig | generic_ok | 0.72 |  | 12 | The title is specifically inlet filter/duct supplier drawings, while the competing specifics are for foundations, FM200, tubing, impulse piping, etc., not the inlet filter/duct package itself. | FA | 1EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2007-08-31 | design_drawing | civil_design | compatible | gtg |  | gtg | query | fgp¦gtg | match | true | false | 1 | 2 | 10.6350 | 0.6283 | 0.0325 | 0.0244 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MBA-121010 | GTG_STG-PAC INSTRUCTION BOOK VOLUME I (GAS TURBINE AND AUXILIARIES | INSTRUCTION BOOK | Gas Turbine Generator Steam Turbine Generator-PAC |  |  |  | INSTRUCTION BOOK for Gas Turbine Generator Steam Turbine Generator-PAC | [5 empty] | rule_query | other | other | instruction_book | gt_generator_outline | gas¦generator¦gtg¦pac¦steam¦stg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5918 | 0.6442 | 0.6442 | [7 empty] | 1CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | 2008-05-03 | 2008-05-16 |  | installation | query_unknown | gtg¦stg |  | gtg¦stg | query | gtg | match | true | false | 4 | 3 | 17.5155 | 0.6340 | 0.0315 | 0.0236 | hybrid | structured_no_phase | gtg¦stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MBA-121011 | GTG - SYSTEM DESCRIPTION | System Description | Gas Turbine Generator |  |  |  | System Description for GTG |  | GT - SYSTEM DESCRIPTION | 1 | start+158D<=FA<=start+158D+2M | FA ∈ [start+158d, start+218d] | rule_query | description | description | system_description | system_description | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.8149 | 0.7111 | 0.7111 | [6 empty] | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | gtg | gtg | gtg | query |  | activity_unscoped | true | true | 4 | 1567 | 9.5174 | 0.5053 | 0.0162 | 0.0097 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MBA-121012 | GTG - GENERATOR/MEDIUM VOLTAGE SINGLE LINE DIAGRAM | Single Line Diagram | Gas Turbine Generator |  |  |  | Single Line Diagram for GTG |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7837 | 0.9351 | 0.9351 | g_ambig | use_specific | 0.78 | GT - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | 5 | A generator/medium-voltage SLD aligns directly with the generator circuit single line diagram specific rule. | SKIP | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 6.8504 | 0.5631 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121013 | GTG - GENERATOR CAPABILITY CURVES AND DATA | Generator Capability Curves and Data | Gas Turbine Generator |  |  |  | Generator Capability Curves and Data for GTG |  | GENERATOR CAPABILITY CURVES AND DATA | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | curve | curve | generator_capability_curve | generator_capability_curve | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8630 | 0.9589 | 0.6712 | g_safe | [5 empty] | FA | 1EF1225W00A08 | (CCWP) Key data for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-03-01 | 2007-05-01 | procurement | procurement | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 15.9288 | 0.5561 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | installation¦erection¦procurement | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121014 | GTG - GENERATOR ISOPHASE BUS INTERFACE | INTERFACE | Gas Turbine Generator |  |  |  | INTERFACE for GTG | [5 empty] | rule_query | other | procedure | interface | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5876 | 0.4563 | 0.4563 | [7 empty] | 1CF1213W52A11 | (GTG #11) Insulation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2008-06-16 | 2008-06-30 |  |  | query_unknown | gtg |  | gtg | query | gtg | match | true | false | 11 | 27 | 6.9660 | 0.6260 | 0.0256 | 0.0192 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121015 | GTG - DESIGN REQUIREMENTS FOR VT & SURGE, BAB36 | DESIGN REQUIREMENTS | Gas Turbine Generator |  |  |  | DESIGN REQUIREMENTS for GTG |  | DESIGN REQUIREMENTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | requirements | requirements | design_requirements | design_requirements | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7661 | 0.6965 | 0.4875 | g_safe | [5 empty] | FA | 3EF1210W20A09 | (GTG Common BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-08-31 |  | civil_design | query_unknown | gtg |  | gtg | query | gtg | match | true | false | 6 | 1 | 11.9847 | 0.6208 | 0.0315 | 0.0237 | hybrid | structured_no_phase | gtg |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL06-P0MBA-121016 | GTG - ELECTRICAL LOAD LIST | LIST | Gas Turbine Generator |  |  |  | LIST for GTG | [5 empty] | rule_query | other | other | list | gt_painting_color_list_for_gtg | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.5000 | 0.6377 | 0.5413 | 0.5413 | [7 empty] | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | procurement | procurement | match | gtg |  | gtg | query | electrical¦gtg | match | true | false | 1 | 1 | 8.9549 | 0.6412 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | procurement | 10 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU05-P0MBA-121017 | GTG - THREE - LINE SCHEMATICS | THREE - LINE SCHEMATICS | Gas Turbine Generator |  |  |  | THREE - LINE SCHEMATICS for GTG |  | Single line /Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.2500 | 0.6346 | 0.3654 | 0.3654 | g_ambig | uncertain | 0.40 |  | 7 | The title is a broad three-line schematics package and does not indicate which specific schematic subset (electrical panel, safety PLC, GT control system, etc.) it corresponds to. | SKIP | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2007-04-30 | 2008-05-28 | procurement | procurement | match | gtg |  | gtg | query | electrical¦gtg | match | true | false | 11 | 1 | 13.0087 | 0.7017 | 0.0305 | 0.0305 | hybrid | structured_cell_found_text_preferred | gtg | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MBA-121018 | GTG - MCC & 125VDC SINGLE LINE DIAGRAM | Single Line Diagram | Gas Turbine Generator |  |  |  | Single Line Diagram for GTG |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7837 | 0.9351 | 0.9351 | g_ambig | use_specific | 0.78 | GT - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | 5 | A generator/medium-voltage SLD aligns directly with the generator circuit single line diagram specific rule. | SKIP | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 5.8467 | 0.5619 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0MBA-121019 | GTG - CUSTOMER ELECTRICAL CONNECTIONS |  | Gas Turbine Generator |  |  |  | for GTG | [5 empty] | rule_query | other | procedure | gtg_customer_electrical_connections | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.6030 | 0.4609 | 0.4609 | [7 empty] | 1CF1255W70A03 | (GTG#11 Electrical) Installation- PCC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-01 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | true | false | 10 | 6 | 9.0138 | 0.6581 | 0.0294 | 0.0221 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121020 | GTG - ELECTRICAL SCHEMATICS | SCHEMATICS | Gas Turbine Generator |  |  |  | SCHEMATICS for GTG |  | GT - TYPICAL SCHEMATIC DIAGRAM FOR ELECTRICAL PANEL | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | title | diagram | diagram | schematic_diagram | schematic_diagram | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.1429 | 0.7254 | 0.3176 | 0.3176 | [6 empty] | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | procurement | procurement | match | gtg | electrical¦gtg | gtg | query | electrical¦gtg | match | true | false | 1 | 2 | 16.1394 | 0.7487 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gtg | system_design¦engineering |  | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 |  | false | false | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0MBA-121021 | GTG - ABOVE - GRADE FIELD CONDUIT PLAN | Plan | Gas Turbine Generator |  |  |  | Plan for GTG |  | GTG LEB FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.5000 | 0.6383 | 0.5415 | 0.5415 | [6 empty] | FA | 1CF1255W70A03 | (GTG#11 Electrical) Installation- PCC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-01 | 2008-09-15 |  | installation | query_unknown | gtg | gtg | gtg | query | electrical¦gtg | match | true | false | 55 | 19 | 5.8619 | 0.6132 | 0.0214 | 0.0160 | hybrid | structured_no_phase | gtg |  |  | 2025-03-20 | 2025-04-04 | 2025-04-19 | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121022 | GTG - CABLE AND CONDUIT LIST | LIST | Gas Turbine Generator |  |  |  | LIST for GTG | [5 empty] | rule_query | other | other | list | gt_painting_color_list_for_gtg | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.5000 | 0.6377 | 0.5413 | 0.5413 | [7 empty] | 1CF1255W74A09 | (GTG#11 Electrical) Cable work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-01 | 2008-09-15 |  |  | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | true | false | 3 | 1 | 12.3280 | 0.6650 | 0.0323 | 0.0242 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121023 | GTG_ELECTRICAL PROTECTION AND OPERATION SETTINGS | SETTINGS | Gas Turbine Generator |  |  |  | SETTINGS for GTG | [5 empty] | rule_query | other | procedure | settings | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5749 | 0.4525 | 0.4525 | [7 empty] | 1CF1255W70A05 | (GTG#11 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-01 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | true | false | 1 | 2 | 15.9965 | 0.6716 | 0.0325 | 0.0244 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121024 | GTG - DCS SIGNAL INTERFACE INFORMATION |  | Gas Turbine Generator |  |  |  | for GTG | [5 empty] | rule_query | other | procedure | gtg_dcs_signal_interface_information | procedure | dcs¦gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.6030 | 0.4609 | 0.4609 | [7 empty] | 3CF1255W86A06 | (GTG#31 Electrical) Installation- GT control Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-04 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | true | false | 53 | 2 | 5.8997 | 0.6477 | 0.0250 | 0.0187 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121025 | GTG - INSTRUMENT, VALVE AND CONTROL SETTINGS LIST | LIST | Gas Turbine Generator |  |  |  | LIST for GTG | [5 empty] | rule_query | other | other | list | gt_painting_color_list_for_gtg | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.5000 | 0.6377 | 0.5413 | 0.5413 | [7 empty] | 3EF1200W00A02 | (GTG #31/#32) Instrument, Service Air, Aux steam Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-29 |  |  | query_unknown | gtg |  | gtg | query | compressed_air¦gtg¦steam | match | true | false | 20 | 1 | 12.6657 | 0.6700 | 0.0289 | 0.0217 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121026 | GTG - CONTROL PHILOSOPHY | PHILOSOPHY | Gas Turbine Generator | CONTROL |  |  | PHILOSOPHY for CONTROL | Air Compressor | Control Philosophy | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | description | description | control_description | control_description | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5164 | 0.5049 | 0.5049 | g_safe | [5 empty] | FA | 2PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | 2007-03-30 | 2008-02-29 | procurement | procurement | match | gtg | compressed_air | gtg | query | gtg | match | true | false | 3 | 1 | 19.5701 | 0.6892 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | gtg | procurement |  | 2024-06-22 | 2024-07-22 | 2024-08-21 | 2024-09-05 | 2024-09-20 | 2024-10-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121027 | GTG - CONTROL SYSTEM DESCRIPTION | DESCRIPTION | Gas Turbine Generator | CONTROL SYSTEM |  |  | DESCRIPTION for CONTROL SYSTEM |  | GT - SYSTEM DESCRIPTION | 1 | start+158D<=FA<=start+158D+2M | FA ∈ [start+158d, start+218d] | title | description | description | system_description | system_description | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7788 | 0.7003 | 0.7003 | [6 empty] | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | gtg | gtg | query | ccw¦gtg | match | true | false | 1587 | 402 | 5.8467 | 0.5927 | 0.0028 | 0.0028 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121028 | GTG - CONTROL SYSTEM INPUT/OUTPUT DATABASE (I/O DATABASE) | DATABASE | Gas Turbine Generator | CONTROL SYSTEM |  |  | DATABASE for GTG |  | INPUT/OUTPUT DATABASE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6805 | 0.9042 | 0.6329 | g_ambig | generic_ok | 0.70 |  | 3 | An I/O database is a control-system deliverable and is not the same as air intake/exhaust loading data or a signal interface list. | FA | 2CF1265W90A17 | (Control Oil) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | 2008-06-02 | 2008-06-14 |  | installation | query_unknown | gtg |  | gtg | query | gtg | match | true | false | 3 | 1 | 17.1699 | 0.6517 | 0.0323 | 0.0242 | hybrid | structured_no_phase | gtg |  |  | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-04-04 | 2025-05-04 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121029 | GTG - POWER SUPPLY DISTRIBUTION DRAWING | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5815 | 0.4544 | 0.4544 | [6 empty] | FA | 3CF1265W16A12 | (TCA Cooler) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | 2007-11-30 | 2008-01-30 | design_drawing | civil_design | compatible | gtg | gtg | gtg | query | fgp¦gtg | match | true | false | 3 | 42 | 7.7463 | 0.6017 | 0.0257 | 0.0193 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121030 | GTG - DATA SHEETS FOR I&C EQUIPMENT | DATA SHEETS | Gas Turbine Generator | Instrumentation and Control |  |  | DATA SHEETS for GTG |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | title | datasheet | datasheet | data_sheet | data_sheet | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6304 | 0.6558 | 0.6558 | g_safe | [5 empty] | FA | 2PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | 2007-03-30 | 2008-02-29 | procurement | procurement | match | gtg |  | gtg | query | gtg | match | true | false | 4 | 4 | 16.1454 | 0.6720 | 0.0312 | 0.0312 | hybrid | structured_preferred | gtg | procurement | 10 | 2024-06-08 | 2024-07-08 | 2024-08-07 | 2024-08-22 | 2024-09-06 | 2024-09-21 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0MBA-121031 | GTG - CABINET / PANEL TERMINAL BLOCK DETAILS | Detail Drawing | Gas Turbine Generator |  |  |  | Detail Drawing for GTG |  | CABINET / PANEL TERMINAL BLOCK DETAILS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8622 | 0.9587 | 0.6711 | g_ambig | generic_ok | 0.76 |  | 5 | The competing specifics are LEB civil/structural detail drawings, not cabinet/panel terminal block details. | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | true | false | 8 | 10 | 5.8848 | 0.5958 | 0.0290 | 0.0217 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0MBA-121032 | GTG - HMI GRAPHIC | GRAPHIC | Gas Turbine Generator |  |  |  | GRAPHIC for GTG | [5 empty] | rule_query | other | procedure | graphic | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.6447 | 0.4734 | 0.4734 | [7 empty] | 1PF1255W70A02T | (GTG#11 Electrical) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-04-01 | 2008-05-15 |  | delivery | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | true | false | 23 | 1 | 5.9002 | 0.6348 | 0.0284 | 0.0213 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121033 | GTG - CONTROL SYSTEM OVERVIEW | OVERVIEW | Gas Turbine Generator | CONTROL SYSTEM |  |  | OVERVIEW for GTG | [5 empty] | rule_query | other | procedure | overview | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.6295 | 0.4689 | 0.4689 | [7 empty] | 3CF1255W86A06 | (GTG#31 Electrical) Installation- GT control Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-04 | 2008-09-15 |  | installation | query_unknown | gtg |  | gtg | query | electrical¦gtg | match | true | false | 15 | 1 | 14.0671 | 0.6647 | 0.0297 | 0.0223 | hybrid | structured_no_phase | gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121034 | GTG - FOUNDATION DESIGN BASIS DOCUMENT | DOCUMENT | Gas Turbine Generator |  |  |  | DOCUMENT for GTG | [5 empty] | rule_query | other | procedure | document | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.6045 | 0.4613 | 0.4613 | [7 empty] | 3EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-08-01 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | true | false | 3 | 7 | 10.9004 | 0.7237 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121035 | GTG - POWER BLOCK FOUNDATION GENERAL NOTES | GENERAL NOTES | Gas Turbine Generator |  |  |  | GENERAL NOTES for GTG |  | GENERAL NOTES FORMWORK | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | notes | notes | general_notes | general_notes | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5855 | 0.6423 | 0.4496 | g_safe | [5 empty] | FA | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-08-01 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | true | false | 22 | 5 | 7.9925 | 0.6943 | 0.0276 | 0.0276 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0CY-121036 | GTG – ELECTRICAL PACKAGE COMMUNICATION LAYOUT DRAWING | Layout Drawing | Gas Turbine Generator | Communication System & Security System |  |  | Layout Drawing for GTG |  | ELECTRICAL PACKAGE COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8600 | 0.9580 | 0.6706 | g_ambig | generic_ok | 0.62 |  | 1 | An electrical package communication layout is different in scope from generator foundation embedded metals layout. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | true | false | 11 | 4 | 7.6052 | 0.6163 | 0.0297 | 0.0223 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121037 | GTG - PSS STUDY REPORT_DRAFT | REPORT | Gas Turbine Generator |  |  |  | REPORT for GTG |  | GT - SIL STUDY REPORT | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | rule_query | report | report | study_report | study_report | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.2500 | 0.6901 | 0.3820 | 0.3820 | [6 empty] | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | procurement | procurement | match | gtg | gtg | gtg | query | electrical¦gtg | match | true | false | 1 | 2 | 13.0087 | 0.7019 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gtg | procurement |  | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 |  | false | false | 0.77 | usable | default_fc_window;rule_score_medium |  | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MBA-121038 | GTG_STG-PAC INSTRUCTION BOOK VOLUME II (GENERATOR AND AUXILIARIES) | INSTRUCTION BOOK VOLUME II | Gas Turbine Generator Steam Turbine Generator |  |  |  | INSTRUCTION BOOK VOLUME II for Gas Turbine Generator Steam Turbine Generator | [5 empty] | rule_query | other | other | instruction_book_volume_ii | gt_generator_outline | gas¦generator¦gtg¦steam¦stg¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5610 | 0.6350 | 0.6350 | [7 empty] | 1CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | 2008-05-03 | 2008-05-16 |  | installation | query_unknown | gtg¦stg |  | gtg¦stg | query | gtg | match | true | false | 91 | 7 | 12.8089 | 0.6175 | 0.0215 | 0.0162 | hybrid | structured_no_phase | gtg¦stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MBA-121044 | GTG - ACCESS PLATFORM LAYOUT | Layout Drawing | Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | ACCESS PLATFORM LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7204 | 0.9161 | 0.6413 | g_ambig | generic_ok | 0.66 |  | 1 | Access platform layout is unrelated to generator foundation embedded metals layout, so the specific rule does not target this document. | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | true | false | 4 | 9 | 5.6083 | 0.6193 | 0.0301 | 0.0226 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121051 | GTG_GAS TURBINE AND AUXILIARIES INSTALLATION MANUAL | INSTALLATION MANUAL | Gas Turbine Generator |  |  |  | INSTALLATION MANUAL for GTG |  | Installation and Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5875 | 0.7013 | 0.7013 | g_safe | [5 empty] | FI | 1CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | 2008-05-03 | 2008-05-16 | manual | installation | compatible | gtg |  | gtg | query | gtg | match | true | false | 13 | 14 | 15.9945 | 0.6405 | 0.0272 | 0.0204 | hybrid | structured_cell_found_text_preferred | gtg | delivery¦procurement¦installation |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121073 | GTG_GAS TURBINE AND AUXILIARIES COMMISSIOINING MANUAL | COMMISSIOINING MANUAL | Gas Turbine Generator |  |  |  | COMMISSIOINING MANUAL for GTG |  | Installation and Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5337 | 0.5101 | 0.5101 | g_safe | [5 empty] | FI | 2PF1213W42A04T | (GT #21) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2008-03-01 | 2008-04-14 | manual | delivery | match | gtg |  | gtg | query | gtg | match | true | false | 26 | 1 | 12.0057 | 0.6594 | 0.0280 | 0.0280 | hybrid | structured_preferred | gtg | delivery¦procurement¦installation | 10 | 2024-11-22 | 2024-12-22 | 2025-01-21 | 2025-02-05 | 2025-02-20 | 2025-03-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121076 | GTG_INSTALLATION MANUAL | INSTALLATION MANUAL | Gas Turbine Generator |  |  |  | INSTALLATION MANUAL for GTG |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6360 | 0.6575 | 0.6575 | g_safe | [5 empty] | FI | 3CF1213W42A10 | (GEN #31) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2008-06-27 | 2008-10-27 | manual | installation | compatible | gtg |  | gtg | query | gtg | match | true | false | 27 | 6 | 9.7211 | 0.6400 | 0.0266 | 0.0200 | hybrid | structured_preferred | gtg | delivery¦procurement¦installation | 10 | 2025-06-06 | 2025-07-06 | 2025-08-05 | 2025-08-20 | 2025-09-04 | 2025-09-19 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121077 | GTG_GENERATOR REMOVAL PROCEDURE | PROCEDURE | Gas Turbine Generator |  |  |  | PROCEDURE for GTG |  | GT - PAINTING PROCEDURE FOR GTG | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | rule_query | procedure | procedure | procedure | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6000 | 0.7321 | 0.6396 | 0.6396 | [6 empty] | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | procurement | procurement | match | gtg | gtg | gtg | query | electrical¦gtg | match | true | false | 1 | 10 | 14.0181 | 0.6855 | 0.0307 | 0.0307 | hybrid | structured_cell_found_text_preferred | gtg | procurement |  | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121099 | GTG ERECTION DRAWING PACKAGE | ERECTION DRAWING PACKAGE | Gas Turbine Generator |  |  |  | ERECTION DRAWING PACKAGE for GTG |  | ERECTION DRAWING PACKAGE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8826 | 0.9648 | 0.6753 | g_ambig | uncertain | 0.38 |  | 12 | The erection drawing package could be an umbrella package containing several of the listed specific drawings, but the title alone does not confirm which specific rule should override. | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | true | false | 6 | 13 | 5.6083 | 0.6242 | 0.0289 | 0.0216 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-121100 | GTG – DRAIN INTERFACE FLOW DIAGRAM | FLOW DIAGRAM | Gas Turbine Generator | Drain System |  |  | FLOW DIAGRAM for Drain System |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | drain¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6520 | 0.6623 | 0.4636 | g_ambig | uncertain | 0.30 |  | 15 | A drain interface flow diagram does not clearly correspond to any of the listed specific logic/conduit/generator auxiliary diagrams. | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 5.8467 | 0.6022 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;rule_score_medium;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121555 | GTG_CONDUIT LAYOUT DRAWING | Layout Drawing | Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | CONDUIT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8690 | 0.9607 | 0.6725 | g_ambig | generic_ok | 0.60 |  | 1 | Conduit layout drawings are not the same as generator foundation embedded metals layout, so the competing specific rule appears to target different content. | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | design_drawing | civil_design | compatible | gtg |  | gtg | query | gtg | match | true | false | 6 | 7 | 5.6083 | 0.6330 | 0.0301 | 0.0226 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121677 | GTG_GAS TURBINE GENERATOR COMMISSIOINING MANUAL | COMMISSIOINING MANUAL | Gas Turbine Generator |  |  |  | COMMISSIOINING MANUAL for GTG |  | COMMISSIOINING MANUAL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | manual | manual | manual | manual | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8090 | 0.7094 | 0.4966 | g_safe | [5 empty] | FA | 3CF1255W86A06 | (GTG#31 Electrical) Installation- GT control Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-04 | 2008-09-15 | manual | installation | compatible | gtg |  | gtg | query | electrical¦gtg | match | true | false | 3 | 27 | 10.0721 | 0.6215 | 0.0274 | 0.0205 | hybrid | structured_preferred | gtg | delivery¦procurement¦installation | 10 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-06-06 | 2025-07-06 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121678 | GTG_I&C SCHEMATICS | SCHEMATICS | Gas Turbine Generator | Instrumentation and Control |  |  | SCHEMATICS for Instrumentation and Control |  | I&C SCHEMATICS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | gas¦generator¦gtg¦instrumentation¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8164 | 0.7116 | 0.4981 | g_ambig | uncertain | 0.40 |  | 7 | The I&C schematics title is generic and could map to multiple specific schematic rules (GT control, safety PLC, server cabinet, etc.) without more detail. | FA | 1CF1265W90A17 | (Control Oil) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2008-05-03 | 2008-05-16 |  | installation | query_unknown | gtg |  | gtg | query | gtg | match | true | false | 1 | 8 | 19.8221 | 0.6885 | 0.0311 | 0.0233 | hybrid | structured_cell_found_text_preferred | gtg | system_design¦engineering |  | 2024-12-20 | 2025-01-04 | 2025-01-19 | 2025-02-03 | 2025-03-05 | 2025-04-04 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_scope_status=rule_generic;rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121824 | GTG_FIRE PROTECTION SYSTEM DRAWING | DRAWING | Gas Turbine Generator | FIRE PROTECTION SYSTEM |  |  | DRAWING for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5815 | 0.4544 | 0.4544 | [6 empty] | FA | 3CF1265W16A01.6 | (Purge Air System) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | 2007-11-28 | 2008-01-28 | design_drawing | civil_design | compatible | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query | compressed_air¦gtg | match | true | false | 16 | 15 | 6.5125 | 0.5947 | 0.0265 | 0.0199 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121971 | GTG – SFC / SEE CIRCUIT DIAGRAM | CIRCUIT DIAGRAM | Gas Turbine Generator |  |  |  | CIRCUIT DIAGRAM for GTG |  | Circuit Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7311 | 0.6860 | 0.4802 | g_ambig | uncertain | 0.42 |  | 15 | SFC/SEE circuit diagram suggests a specific SFC-related diagram, but none of the competing keywords explicitly mention SFC/SEE circuit diagram (only SFC selection logic). | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 5.8467 | 0.5454 | 0.0323 | 0.0242 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | rule_scope_status=rule_generic;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0LB-122001 | HRSG - INSTALLATION AND INSTRUCTION MANUAL | INSTALLATION AND INSTRUCTION MANUAL | Heat Recovery Steam Generator |  |  |  | INSTALLATION AND INSTRUCTION MANUAL for HRSG |  | Installation and Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6623 | 0.7237 | 0.7237 | g_ambig | use_specific | 0.74 | Shop Quality Manual for HRSG | 1 | The competing specific rule explicitly targets the HRSG shop quality manual, which is a distinct manual type from a generic installation/erection manual. | FI | 3PF1655W86A12T | (HRSG #31 I&C Vendor Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | 2008-10-04 | 2008-11-18 | manual | delivery | match | hrsg |  | hrsg | query | hrsg | match | true | false | 9 | 24 | 19.9102 | 0.6168 | 0.0264 | 0.0264 | hybrid | structured_preferred | hrsg | delivery¦procurement¦installation | 10 | 2025-06-28 | 2025-07-28 | 2025-08-27 | 2025-09-11 | 2025-09-26 | 2025-10-11 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122003 | HRSG - STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | Isometric Drawing | Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG |  | HRSG - Erection Isometric DraWing for PIPNG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7867 | 0.7027 | 0.7027 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 19.2297 | 0.6644 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122004 | HRSG - CFD REPORT FOR INLET DUCT | REPORT | Heat Recovery Steam Generator |  |  |  | CFD Report for HRSG |  | HRSG - HRSG CFD Report | 1 | start+149D<=FA<=start+149D+2M | FA ∈ [start+149d, start+209d] | rule_query | report | report | cfd_report | cfd_report | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9143 | 0.9743 | 0.9743 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 4 | 14.3954 | 0.5999 | 0.0320 | 0.0320 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122005 | HRSG - CFD REPORT FOR DUCT BURNER SYSTEM | REPORT | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | CFD Report for HRSG |  | HRSG - HRSG CFD Report | 1 | start+149D<=FA<=start+149D+2M | FA ∈ [start+149d, start+209d] | rule_query | report | report | cfd_report | cfd_report | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9143 | 0.9743 | 0.9743 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 15.2888 | 0.5946 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122006 | HRSG - SPEC. & DRAWING FOR HOIST | DRAWING | Heat Recovery Steam Generator |  |  |  | DRAWING for HRSG |  | HRSG - Valve DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.7501 | 0.6450 | 0.6450 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 3 | 14.3954 | 0.6426 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122007 | HRSG - GENERAL ARRANGEMENT | General Arrangement Drawing | Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for HRSG |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8594 | 0.9578 | 0.9578 | [6 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 5 | 27.3986 | 0.6994 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122008 | HRSG - ARRANGEMENT OF CASING & FIELD ERECTION | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 1 | 20.8292 | 0.6602 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122009 | HRSG - ARRANGEMENT OF INLET DUCT | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 4 | 24.9319 | 0.6451 | 0.0318 | 0.0238 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122010 | HRSG - ARRANGEMENT OF MAIN STACK& FIELD ERECTION | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 3 | 2 | 30.6762 | 0.7032 | 0.0320 | 0.0240 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122011 | HRSG - GENERAL ARRANGEMENT FOR DUCT BURNER SYSTEM | General Arrangement Drawing | Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for HRSG |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8594 | 0.9578 | 0.9578 | [6 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 1 | 27.3986 | 0.6912 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122012 | HRSG - DETAIL ARRANGEMENT FOR DUCT BURNER SYSTEM | DETAIL ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | DETAIL ARRANGEMENT for HRSG |  | HRSG FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6534 | 0.5460 | 0.5460 | [6 empty] | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 1 | 24.9319 | 0.6606 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122013 | HRSG - FUEL GAS SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | fgp¦generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 8 | 1 | 20.8292 | 0.6629 | 0.0311 | 0.0233 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122014 | HRSG - COOLING AIR SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 8 | 1 | 20.8292 | 0.6519 | 0.0311 | 0.0233 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-VN03-P0LB-122015 | HRSG - ARRANGEMENT FOR PLATFORM STRUCTURE | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 15 | 19.7008 | 0.5982 | 0.0295 | 0.0295 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122016 | HRSG - COLUMN LOCATION FOR STEEL STRUCTURE AND STACK |  | Heat Recovery Steam Generator |  |  |  | for HRSG | [5 empty] | rule_query | other | diagram | hrsg_column_location_for_steel_structure_and_stack | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6685 | 0.5505 | 0.5505 | [7 empty] | 3CF1610W20A05 | (HRSG #31 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  | installation | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 3 | 35 | 25.3292 | 0.6564 | 0.0264 | 0.0198 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122017 | HRSG - FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | TABLE | Heat Recovery Steam Generator |  |  |  | TABLE for HRSG | [5 empty] | rule_query | other | diagram | table | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6342 | 0.5403 | 0.5403 | [7 empty] | 2EF1625W00A02 | (HRSG #21 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2007-07-05 |  | civil_design | civil_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 4 | 8 | 22.4214 | 0.7190 | 0.0303 | 0.0303 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122018 | HRSG - BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | Detail Drawing | Heat Recovery Steam Generator |  |  |  | Detail Drawing for HRSG |  | HRSG - Base Plate anD Anchor Bolts Detail for HRSG (Steel Structure) | 1 | start+118D<=FA<=start+118D+2M | FA ∈ [start+118d, start+178d] | title | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9475 | 0.9842 | 0.9842 | [6 empty] | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 6 | 12.9120 | 0.6226 | 0.0296 | 0.0296 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-10-16 | 2024-11-15 | 2024-12-15 | 2024-12-30 | 2025-01-14 | 2025-01-29 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122019 | HRSG - ANCHOR BOLT & TEMPLATE DETAIL FOR STACK | Detail Drawing | Heat Recovery Steam Generator |  |  |  | Detail Drawing for HRSG |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5841 | 0.6419 | 0.6419 | g_ambig | uncertain | 0.33 |  | 24 | The document is for stack anchor bolt/template detail, but no competing specific keyword explicitly matches that stack anchor bolt/template scope (only stack foundation reinforcement details are liste | FI | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 4 | 17 | 18.5838 | 0.6433 | 0.0286 | 0.0215 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122020 | HRSG - FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | DRAWING | Heat Recovery Steam Generator |  |  |  | DRAWING for HRSG |  | HRSG - Valve DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.7501 | 0.6450 | 0.6450 | [6 empty] | FA | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 22 | 1 | 14.4007 | 0.6514 | 0.0286 | 0.0286 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0LB-122021 | HRSG - LARGE BORE PIPING ARRANGEMENT | ARRANGEMENT | Heat Recovery Steam Generator | Piping |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 4 | 20.8292 | 0.6240 | 0.0318 | 0.0238 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LB-122022 | HRSG - P&I DIAGRAM | P&ID | Heat Recovery Steam Generator |  |  |  | P&ID for HRSG |  | HRSG - P&ID for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | diagram | diagram | p_id | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.8159 | 0.7698 | 0.7698 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 27.8550 | 0.7243 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦procurement |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LB-122023 | HRSG - P&I DIAGRAM FOR HRSG DUCT BURNER SYSTEM | P&ID | Heat Recovery Steam Generator |  |  |  | P&ID for HRSG |  | HRSG - P&ID for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | diagram | diagram | p_id | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.8159 | 0.7698 | 0.7698 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 13 | 1 | 31.3337 | 0.7349 | 0.0301 | 0.0301 | hybrid | structured_blocked_procurement_conflict | hrsg | system_design¦procurement |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122024 | HRSG - PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | DRAWING | Heat Recovery Steam Generator | Piping |  |  | DRAWING for HRSG |  | HRSG - Valve DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.7501 | 0.6450 | 0.6450 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 19.2297 | 0.6485 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122025 | HRSG - TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | DRAWING | Heat Recovery Steam Generator | Piping |  |  | DRAWING for HRSG |  | HRSG - Valve DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.7501 | 0.6450 | 0.6450 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 19.2297 | 0.6536 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122026 | HRSG - PIPE SUPPORT DRAWINGS | DRAWINGS | Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG |  | HRSG - PoWer Distribution Panel DraWings | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7476 | 0.5043 | 0.5043 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 3 | 14.3954 | 0.6410 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122027 | HRSG - LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | Isometric Drawing | Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG |  | HRSG - Erection Isometric DraWing for PIPNG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7867 | 0.7027 | 0.7027 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 19.2297 | 0.6565 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122028 | HRSG - SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | Isometric Drawing | Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG |  | HRSG - Erection Isometric DraWing for PIPNG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7867 | 0.7027 | 0.7027 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 19.2297 | 0.6586 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122029 | HRSG - VENT & DRAIN LINE (MODULE /FIELD WELD) |  | Heat Recovery Steam Generator |  |  |  | for HRSG |  | HRSG - Vent & Drain Line (MoDule /FielD WelD) | 1 | start+286D<=FA<=start+286D+2M | FA ∈ [start+286d, start+346d] | rule_query | other | other | hrsg_vent_and_drain_line_module_field_weld | hrsg_vent_and_drain_line_module_field_weld | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.1429 | 0.5890 | 0.2767 | 0.2767 | [6 empty] | FA | 1PF1610W42A02P | (HRSG #11 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Module | 2007-07-03 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 12 | 27.4870 | 0.6979 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | hrsg | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0LB-122030 | HRSG - LINE LIST | LINE LIST | Heat Recovery Steam Generator |  |  |  | LINE LIST for HRSG | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5857 | 0.5257 | 0.5257 | g_safe | [5 empty] | FI | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | compressed_air | hrsg | query | hrsg | match | true | false | 12 | 13 | 20.0267 | 0.6838 | 0.0276 | 0.0276 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0LB-122031 | HRSG - LINE LIST FOR DUCT BURNER SYSTEM | LINE LIST | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LINE LIST for HRSG | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5857 | 0.5257 | 0.5257 | g_safe | [5 empty] | FI | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | compressed_air | hrsg | query | hrsg | match | true | false | 2 | 1 | 31.4016 | 0.7379 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122032 | HRSG - MANUAL VALVE LIST | LIST | Heat Recovery Steam Generator |  |  |  | Valve List for HRSG |  | HRSG - Valve List for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | list | list | valve_list | valve_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8422 | 0.8127 | 0.8127 | [6 empty] | FA | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-13 | 2008-02-29 | manual | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 10 | 20.0267 | 0.6841 | 0.0288 | 0.0288 | hybrid | structured_cell_found_text_preferred | hrsg | delivery¦procurement¦installation |  | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122033 | HRSG - MOV & CV LIST | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG | [5 empty] | rule_query | other | list | list | io_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.7048 | 0.7364 | 0.7364 | [7 empty] | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 5 | 1 | 13.4377 | 0.6121 | 0.0318 | 0.0238 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122034 | HRSG - VALVE LIST FOR DUCT BURNER SYSTEM | LIST | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Valve List for HRSG |  | HRSG - Valve List for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | list | list | valve_list | valve_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8422 | 0.8127 | 0.8127 | [6 empty] | FA | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-14 | 2008-04-02 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 4 | 1 | 31.4016 | 0.7288 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122035 | HRSG - SYSTEM DESCRIPTION | System Description | Heat Recovery Steam Generator |  |  |  | System Description for HRSG |  | HRSG - System Description | 1 | start+103D<=FA<=start+103D+2M | FA ∈ [start+103d, start+163d] | rule_query | description | description | system_description | system_description | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8473 | 0.9542 | 0.9542 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 20.3949 | 0.6909 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦procurement |  | 2024-06-30 | 2024-07-30 | 2024-08-29 | 2024-09-13 | 2024-09-28 | 2024-10-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122036 | HRSG - SYSTEM DESCRIPTION FOR HRSG DUCT BURNER SYSTEM | System Description | Heat Recovery Steam Generator | Heat Recovery Steam Generator DUCT BURNER SYSTEM |  |  | System Description for Heat Recovery Steam Generator DUCT BURNER SYSTEM |  | HRSG - System Description for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | description | description | system_description | system_description | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8676 | 0.9603 | 0.9603 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 113 | 1 | 33.5863 | 0.6661 | 0.0222 | 0.0222 | hybrid | structured_blocked_procurement_conflict | hrsg | system_design¦procurement |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122037 | HRSG - BLOWDOWN SYSTEM SUMMARY | SUMMARY | Heat Recovery Steam Generator |  |  |  | SUMMARY for HRSG | [5 empty] | rule_query | other | other | summary | hrsg_hrsg_blowdown_system_summary | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.5000 | 0.7835 | 0.5850 | 0.5850 | [7 empty] | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 1 | 13.4377 | 0.6206 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0LB-122038 | HRSG - BMS PANEL PART LIST FOR DUCT BURNER SYSTEM | LIST | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LIST for HRSG | [5 empty] | rule_query | other | list | list | io_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.7048 | 0.7364 | 0.7364 | [7 empty] | 1EF1615W64A04 | (HRSG #11 Duct) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-04-17 | 2007-10-18 |  |  | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 8 | 11 | 24.2528 | 0.6654 | 0.0288 | 0.0216 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0LB-122039 | HRSG - EQUIPMENT LIST | LIST | Heat Recovery Steam Generator |  |  |  | Equipment List for HRSG |  | HRSG - Equipment List | 1 | start+134D<=FA<=start+134D+2M | FA ∈ [start+134d, start+194d] | rule_query | list | list | equipment_list | equipment_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8635 | 0.9591 | 0.9591 | [6 empty] | FA | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 1 | 21.8614 | 0.7035 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0LB-122040 | HRSG - HAZARDOUS AREA CLASSIFICATION SPECIFICATION & DRAWING FOR DUCT BURNER SYSTEM | SPECIFICATION & DRAWING | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Hazardous Area Classification for DUCT BURNER SYSTEM |  | HRSG - HazarDous Area Classification Specification & DraWing for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | classification | classification | hazardous_area_classification | hazardous_area_classification | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7640 | 0.6959 | 0.6959 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 15.2888 | 0.6288 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122041 | HRSG - TECHNICAL SPECIFICATION FOR AC & DC DISTRIBUTION BOARD | Technical Specification | Heat Recovery Steam Generator |  |  |  | Technical Specification for HRSG |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7699 | 0.6976 | 0.6976 | [6 empty] | FA | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-09-15 | 2008-08-23 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 28 | 20.1314 | 0.6009 | 0.0272 | 0.0272 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-13 | 2025-04-12 | 2025-05-12 | 2025-05-27 | 2025-06-11 | 2025-06-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122042 | HRSG - COOLING AIR FAN & MOTOR DATASHEET FOR DUCT BURNER SYSTEM | Data Sheet | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Data Sheet for HRSG |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7374 | 0.7462 | 0.7462 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 1 | 31.4016 | 0.6544 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122044 | HRSG - BMS SHELTER LAYOUT FOR DUCT BURNER SYSTEM | Layout Drawing | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 15 | 1 | 23.2546 | 0.6890 | 0.0297 | 0.0297 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-03-11 | 2025-04-10 | 2025-05-10 | 2025-05-25 | 2025-06-09 | 2025-06-24 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122045 | HRSG - TECHNICAL SPECIFICATION FOR EARTHING & LIGHTNING PROTECTION SYSTEM | Technical Specification | Heat Recovery Steam Generator | EARTHING & LIGHTNING PROTECTION SYSTEM |  |  | Technical Specification for HRSG |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7699 | 0.6976 | 0.6976 | [6 empty] | FA | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-09-15 | 2008-08-23 | procurement | procurement | match | electrical¦hrsg | hrsg | electrical¦hrsg | query | hrsg | match | true | false | 19 | 7 | 20.1314 | 0.5841 | 0.0276 | 0.0276 | hybrid | structured_cell_found_text_preferred | electrical¦hrsg | procurement |  | 2025-03-13 | 2025-04-12 | 2025-05-12 | 2025-05-27 | 2025-06-11 | 2025-06-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122046 | HRSG - TECHNICAL SPECIFICATION FOR COMMUNICATION SYSTEM | Technical Specification | Heat Recovery Steam Generator | COMMUNICATION SYSTEM |  |  | Technical Specification for HRSG |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7699 | 0.6976 | 0.6976 | [6 empty] | FA | 2PF1665W42A02P | (HRSG #21 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | 2007-09-10 | 2008-09-02 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 13 | 20.3118 | 0.6090 | 0.0296 | 0.0296 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-08 | 2025-04-07 | 2025-05-07 | 2025-05-22 | 2025-06-06 | 2025-06-21 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0LB-122047 | HRSG - CABLE CONNECTION DIAGRAM | CABLE CONNECTION DIAGRAM | Heat Recovery Steam Generator |  |  |  | CABLE CONNECTION DIAGRAM for HRSG |  | HRSG - PoWer Cable Connection Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8570 | 0.8171 | 0.8171 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 23.6062 | 0.6279 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0LB-122048 | HRSG - PRESSURE PART ARRANGEMENT | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 1 | 20.8292 | 0.6670 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122049 | HRSG - SPEC. & DRAWING FOR STEAM DRUM | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8088 | 0.8026 | 0.8026 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 16.8549 | 0.6340 | 0.0328 | 0.0246 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122050 | HRSG - SPEC. & DRAWING FOR BLOWDOWN PUMP | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8088 | 0.8026 | 0.8026 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 14.3954 | 0.6332 | 0.0328 | 0.0246 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122051 | HRSG - SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8088 | 0.8026 | 0.8026 | [6 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 1 | 14.3954 | 0.6374 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122052 | HRSG - SPEC. & DRAWING FOR STACK DAMPER | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8088 | 0.8026 | 0.8026 | [6 empty] | FA | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 4 | 18 | 18.5838 | 0.6269 | 0.0284 | 0.0213 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122053 | HRSG - SPEC. & DRAWING FOR VENT SILENCER | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8088 | 0.8026 | 0.8026 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 5 | 14.3954 | 0.6098 | 0.0318 | 0.0238 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122054 | HRSG - SPEC. & DRAWING FOR DEAERATOR & STORAGE TANK | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | HRSG - Spec. & DraWing for Deaerator | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8088 | 0.8026 | 0.8026 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 14.3954 | 0.6365 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122055 | HRSG - EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | EQUIPMENT OUTLINE DRAWING | Heat Recovery Steam Generator |  |  |  | EQUIPMENT OUTLINE DRAWING for HRSG |  | HRSG - Equipment Outline DraWing for BloWDoWn Tank | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg¦tank | scoped | match | match | match | passed |  | 0.7143 | 0.8132 | 0.7440 | 0.7440 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 14.3954 | 0.6441 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122056 | HRSG - POWER DISTRIBUTION PANEL DRAWINGS | DRAWINGS | Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG |  | HRSG - PoWer Distribution Panel DraWings | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7476 | 0.5043 | 0.5043 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 14.3956 | 0.6602 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122057 | HRSG - HEADER AND SUPPORT DRAWING FOR DUCT BURNER SYSTEM | DRAWING | Heat Recovery Steam Generator |  |  |  | DRAWING for HRSG |  | HRSG - Valve DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.7501 | 0.6450 | 0.6450 | [6 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 15 | 1 | 17.7009 | 0.6728 | 0.0297 | 0.0223 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-03-11 | 2025-04-10 | 2025-05-10 | 2025-05-25 | 2025-06-09 | 2025-06-24 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122058 | HRSG - BMS PANEL LAYOUT FOR DUCT BURNER SYSTEM | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 19 | 1 | 14.8421 | 0.6839 | 0.0291 | 0.0218 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0LB-122059 | HRSG - HMI SCREEN LAYOUT FOR DUCT BURNER SYSTEM | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 19 | 1 | 14.8421 | 0.6813 | 0.0291 | 0.0218 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122060 | HRSG - JUNCTION BOX DATASHEET FOR DUCT BURNER SYSTEM | Data Sheet | Heat Recovery Steam Generator |  |  |  | Data Sheet for HRSG |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7374 | 0.7462 | 0.7462 | [6 empty] | FA | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-14 | 2008-04-02 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 6 | 25.7141 | 0.6714 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122061 | HRSG - FLAME SCANNER & IGNITION BURNER SPECIFICATION FOR DUCT BURNER SYSTEM | Technical Specification | Heat Recovery Steam Generator |  |  |  | Technical Specification for HRSG |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7699 | 0.6976 | 0.6976 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 2 | 25.7141 | 0.6720 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-12-10 | 2025-01-09 | 2025-02-08 | 2025-02-23 | 2025-03-10 | 2025-03-25 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122062 | HRSG - ARRANGEMENT OF STACK SILENCER | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | design_drawing | civil_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 6 | 1 | 24.9780 | 0.6593 | 0.0315 | 0.0237 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122063 | HRSG - CONDUIT LAYOUT DRAWING | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 14.3954 | 0.6619 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122064 | HRSG - CABLE TRAY & RACEWAY LAYOUT DIAGRAM | LAYOUT DIAGRAM | Heat Recovery Steam Generator |  |  |  | LAYOUT DIAGRAM for HRSG |  | HRSG - Cable Tray & RaceWay Layout Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7121 | 0.5636 | 0.5636 | [6 empty] | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 4 | 5 | 23.6062 | 0.6449 | 0.0310 | 0.0233 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦engineering |  | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122065 | HRSG - GROUNDING AND LIGHTNING PLAN DIAGRAMS | PLAN DIAGRAMS | Heat Recovery Steam Generator |  |  |  | PLAN DIAGRAMS for HRSG |  | HRSG - Lighting Plan Diagrams | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7300 | 0.7440 | 0.7440 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 16.6725 | 0.6347 | 0.0328 | 0.0246 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122066 | HRSG - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | Heat Recovery Steam Generator |  |  |  | Control Logic Diagram for HRSG |  | HRSG - Control Logic Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8808 | 0.9642 | 0.9642 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 23.6062 | 0.6755 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0LB-122067 | HRSG - CONTROL LOOP DIAGRAM | CONTROL LOOP DIAGRAM | Heat Recovery Steam Generator |  |  |  | Control Loop Diagram for HRSG |  | HRSG - Control Loop Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8896 | 0.9669 | 0.9669 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 23.6062 | 0.6753 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122068 | HRSG - LOGIC DIAGRAM FOR DUCT BURNER SYSTEM | LOGIC DIAGRAM | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LOGIC DIAGRAM for DUCT BURNER SYSTEM |  | HRSG - Cable Interconnection Diagram for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | title | diagram | diagram | diagram | diagram | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7143 | 0.7681 | 0.7304 | 0.7304 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 24.4996 | 0.6511 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YM03-P0LB-122069 | HRSG - INSTRUMENT LOCATION | LOCATION | Heat Recovery Steam Generator |  |  |  | LOCATION for HRSG | [5 empty] | rule_query | other | other | location | hrsg_instrument_location_for_scr | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6000 | 0.7480 | 0.6444 | 0.6444 | [7 empty] | 1EF1600W00A03 | (HRSG #11/#12) Instrument, Service Air Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-29 |  |  | query_unknown | hrsg |  | hrsg | query | compressed_air¦hrsg | match | true | false | 1 | 3 | 19.8717 | 0.6522 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122070 | HRSG - BMS SYSTEM CONFIGURATION FOR DUCT BURNER SYSTEM |  | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | for HRSG | [5 empty] | rule_query | other | diagram | hrsg_bms_system_configuration_for_duct_burner_system | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6685 | 0.5505 | 0.5505 | [7 empty] | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 2 | 13.6381 | 0.6101 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122071 | HRSG - LINK ASSEMBLY DRAWING | ASSEMBLY DRAWING | Heat Recovery Steam Generator |  |  |  | ASSEMBLY DRAWING for HRSG |  | HRSG - Link Assembly DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.8193 | 0.7708 | 0.7708 | [6 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 1 | 14.3954 | 0.6491 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-03-01 | 2025-03-31 | 2025-04-30 | 2025-05-15 | 2025-05-30 | 2025-06-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122072 | HRSG - INSTRUMENT INSTALLATION DETAIL DRAWINGS | DRAWINGS | Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG |  | HRSG - Instrument Installation Detail DraWings | 1 | start+134D<=FA<=start+134D+2M | FA ∈ [start+134d, start+194d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7876 | 0.5163 | 0.5163 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 14.3954 | 0.6801 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122073 | HRSG - SPECIALTY DRAWING FOR EXTERNAL PIPING | DRAWING | Heat Recovery Steam Generator | PIPING |  |  | DRAWING for HRSG |  | HRSG - Valve DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.7501 | 0.6450 | 0.6450 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 19.2297 | 0.6833 | 0.0328 | 0.0246 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LB-122074 | HRSG - MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | DRAWING | Heat Recovery Steam Generator | PIPING |  |  | DRAWING for HRSG |  | Shop Quality Manual for HRSG | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | manual | manual | manual | manual | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.6158 | 0.4647 | 0.3253 | [6 empty] | FA | 3CF1650W52A04 | (HRSG #31 Insulation) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | 2009-03-19 | 2009-04-22 | manual | installation | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 6 | 15 | 19.7770 | 0.6123 | 0.0285 | 0.0214 | hybrid | structured_preferred | hrsg | delivery¦procurement¦installation | 10 | 2025-11-05 | 2025-11-20 | 2025-12-05 | 2025-12-20 | 2026-01-19 | 2026-02-18 | generated | 0.30 |  | false | false | 0.64 | usable | rule_score_medium;activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122075 | HRSG - INSTRUMENT LIST | INSTRUMENT LIST | Heat Recovery Steam Generator |  |  |  | Instrument List for HRSG |  | HRSG - Instrument List | 1 | start+133D<=FA<=start+133D+2M | FA ∈ [start+133d, start+193d] | rule_query | list | list | instrument_list | instrument_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8483 | 0.9545 | 0.9545 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 26 | 20.0267 | 0.6931 | 0.0261 | 0.0261 | hybrid | structured_preferred | hrsg | procurement | 10 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122076 | HRSG - INSTRUMENT LIST FOR DUCT BURNER SYSTEM | INSTRUMENT LIST | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Instrument List for HRSG |  | HRSG - Instrument List | 1 | start+133D<=FA<=start+133D+2M | FA ∈ [start+133d, start+193d] | rule_query | list | list | instrument_list | instrument_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8483 | 0.9545 | 0.9545 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 1 | 31.4016 | 0.7262 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LB-122077 | HRSG - ALARM AND TRIP SETTING LIST FOR DUCT BURNER SYSTEM | LIST | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LIST for HRSG | [5 empty] | rule_query | other | list | list | io_list | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.7048 | 0.7364 | 0.7364 | [7 empty] | 3CF1615W64A08.1 | (HRSG #32 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | 2008-11-18 | 2009-02-17 |  | installation | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 7 | 3 | 24.9962 | 0.6150 | 0.0308 | 0.0231 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0LB-122078 | HRSG - CABLE SCHEDULE | CABLE SCHEDULE | Heat Recovery Steam Generator |  |  |  | CABLE SCHEDULE for HRSG |  | HRSG - PoWer Cable ScheDule | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | list | list | cable_schedule | cable_schedule | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7681 | 0.7554 | 0.7554 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 13 | 7 | 20.0270 | 0.6417 | 0.0286 | 0.0286 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122079 | HRSG - LIGHTING PLAN DIAGRAMS | PLAN DIAGRAMS | Heat Recovery Steam Generator | Lighting & Small Power System |  |  | PLAN DIAGRAMS for Lighting & Small Power System |  | HRSG - Lighting Plan Diagrams | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | diagram | diagram | generator¦heat¦hrsg¦lighting¦power¦recovery¦small¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7036 | 0.7361 | 0.7361 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | electrical¦hrsg | hrsg | electrical¦hrsg | query | hrsg | match | true | false | 1 | 1 | 14.8423 | 0.6564 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical¦hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0LB-122080 | HRSG - COMMUNICATION BLOCK DIAGRAM | BLOCK DIAGRAM | Heat Recovery Steam Generator | Communication System & Security System |  |  | BLOCK DIAGRAM for Communication System & Security System |  | HRSG - Cable Block Diagram for HRSG | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | diagram | diagram | diagram | diagram | communication¦generator¦heat¦hrsg¦recovery¦security¦steam | hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.8163 | 0.6649 | 0.6649 | [6 empty] | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 1 | 25.0468 | 0.6506 | 0.0325 | 0.0244 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦engineering |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-US02-P0LB-122081 | HRSG - COMMUNICATION LAYOUT DRAWING | Layout Drawing | Heat Recovery Steam Generator | Communication System & Security System |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 15.2888 | 0.6563 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0LB-122082 | HRSG - CHEMICAL CLEANING PROCEDURE | PROCEDURE | Heat Recovery Steam Generator |  |  |  | PROCEDURE for HRSG |  | CHEMICAL CLEANING PROCEDURE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | procedure | procedure | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7717 | 0.9315 | 0.6520 | g_safe | [5 empty] | FA | 1CF1640W60A07 | (HRSG #11) Acid Cleaning | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2009-01-26 | 2009-02-17 |  |  | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 2 | 20.5495 | 0.6880 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hrsg |  |  | 2025-09-14 | 2025-09-29 | 2025-10-14 | 2025-10-29 | 2025-11-28 | 2025-12-28 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL08-P0LB-122083 | HRSG - PRESERVATION AND STORAGE PROCEDURE | PROCEDURE | Heat Recovery Steam Generator |  |  |  | PROCEDURE for HRSG |  | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6450 | 0.7185 | 0.7185 | g_safe | [5 empty] | FI | 1PF1615W64A07T | (HRSG #11 Duct) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2008-02-01 | 2008-03-17 | delivery | delivery | match | hrsg |  | hrsg | query | hrsg | match | true | false | 8 | 11 | 16.0182 | 0.6211 | 0.0288 | 0.0288 | hybrid | structured_cell_found_text_preferred | hrsg | delivery¦procurement |  | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0LB-122084 | HRSG - PANEL ELECTRIC SCHEME FOR DUCT BURNER SYSTEM |  | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | for HRSG | [5 empty] | rule_query | other | diagram | hrsg_panel_electric_scheme_for_duct_burner_system | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6685 | 0.5505 | 0.5505 | [7 empty] | 1CF1615W64A08 | (HRSG #11 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2008-09-16 | 2008-12-16 |  | installation | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 8 | 25.1656 | 0.6537 | 0.0311 | 0.0233 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0LB-122085 | HRSG - WIRING & SCHEMATIC DIAGRAM | WIRING & SCHEMATIC DIAGRAM | Heat Recovery Steam Generator |  |  |  | WIRING & SCHEMATIC DIAGRAM for HRSG |  | WIRING & SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7315 | 0.9194 | 0.6436 | g_safe | [5 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 1 | 21.5087 | 0.6491 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122086 | HRSG - DATA & BOM OF INSULATION FOR BLOWDOWN TANK | DATA & BOM | Heat Recovery Steam Generator |  |  |  | DATA & BOM for HRSG |  | HRSG - Data & BOM of Insulation for Piping | 1 | start+317D<=FA<=start+317D+2M | FA ∈ [start+317d, start+377d] | rule_query | data | data | data | data | generator¦heat¦hrsg¦recovery¦steam¦tank | hrsg | scoped | match | match | match | passed |  | 0.5714 | 0.7983 | 0.6395 | 0.6395 | [6 empty] | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 26.4285 | 0.7056 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-11-22 | 2025-12-22 | 2026-01-21 | 2026-02-05 | 2026-02-20 | 2026-03-07 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122087 | HRSG - DATA & BOM OF INSULATION FOR INTERNAL PIPING | DATA & BOM | Heat Recovery Steam Generator | PIPING |  |  | DATA & BOM for HRSG |  | HRSG - Data & BOM of Insulation for Piping | 1 | start+317D<=FA<=start+317D+2M | FA ∈ [start+317d, start+377d] | rule_query | data | data | data | data | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5714 | 0.7983 | 0.6395 | 0.6395 | [6 empty] | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 33.4406 | 0.7544 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-11-22 | 2025-12-22 | 2026-01-21 | 2026-02-05 | 2026-02-20 | 2026-03-07 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122088 | HRSG - PERFORMANCE AND OPERATIONAL DATA | DATA | Heat Recovery Steam Generator |  |  |  | DATA for HRSG | [5 empty] | rule_query | data | datasheet | operational_data | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.7242 | 0.5672 | 0.5672 | [7 empty] | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 2 | 22.3783 | 0.6622 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0LB-122089 | HRSG - MOV DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 1 | 20.0267 | 0.6681 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0LB-122090 | HRSG - CV DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 1 | 20.0267 | 0.6790 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0LB-122091 | HRSG - DESH. DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 1 | 20.0267 | 0.6674 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0LB-122092 | HRSG - AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | DATASHEET & LAYOUT DIAGRAM | Heat Recovery Steam Generator |  |  |  | DATASHEET & LAYOUT DIAGRAM for HRSG |  | HRSG - Aircraft Warning Light Data sheet / layout Diagram | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.9510 | 0.8103 | 0.8103 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 1 | 20.0267 | 0.6195 | 0.0309 | 0.0309 | hybrid | structured_preferred | hrsg | procurement | 10 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122093 | HRSG - CEMS DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cems¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 2PF1660W86A04P | (CEMS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | 2007-08-29 | 2008-04-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | cems¦hrsg | match | true | false | 2 | 1 | 24.9146 | 0.7291 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-05-11 | 2025-06-10 | 2025-07-10 | 2025-07-25 | 2025-08-09 | 2025-08-24 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LB-122094 | HRSG - LOCAL INSTRUMENT DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 18 | 1 | 20.0267 | 0.6745 | 0.0292 | 0.0292 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122095 | HRSG - TRANSMITTER DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 1 | 20.0267 | 0.6857 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122096 | HRSG - DRUM LEVEL GAUGE DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 1PF1645W42A03P | (HRSG #11 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | 2007-06-13 | 2008-04-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 4 | 29.2247 | 0.6956 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-23 | 2025-03-25 | 2025-04-24 | 2025-05-09 | 2025-05-24 | 2025-06-08 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122097 | HRSG - FLOW ELEMENT DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 1 | 20.0267 | 0.6876 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122098 | HRSG - REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | HRSG - Drum Level Gauge Datasheet/DraWings | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.7182 | 0.5655 | 0.5655 | [6 empty] | FA | 1PF1645W42A03P | (HRSG #11 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | 2007-06-13 | 2008-04-30 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 4 | 29.2247 | 0.6700 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-23 | 2025-03-25 | 2025-04-24 | 2025-05-09 | 2025-05-24 | 2025-06-08 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122099 | HRSG - TECHNICAL SPECIFICATION FOR LIGHTING & SMALL POWER SYSTEM | Technical Specification | Heat Recovery Steam Generator | LIGHTING & SMALL POWER SYSTEM |  |  | Technical Specification for HRSG |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7699 | 0.6976 | 0.6976 | [6 empty] | FA | 1PF1660W70A06P | (HRSG #11 ELEC Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-10-02 | 2008-08-04 | procurement | procurement | match | electrical¦hrsg | hrsg | electrical¦hrsg | query | hrsg | match | true | false | 6 | 6 | 20.3122 | 0.6233 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | electrical¦hrsg | procurement |  | 2025-03-30 | 2025-04-29 | 2025-05-29 | 2025-06-13 | 2025-06-28 | 2025-07-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122100 | HRSG - ELECTRICAL SINGLE LINE DIAGRAMS | SINGLE LINE DIAGRAMS | Heat Recovery Steam Generator | Electrical System |  |  | SINGLE LINE DIAGRAMS for Electrical System |  | HRSG - Electrical Single Line Diagrams | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | electrical¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.7286 | 0.7786 | 0.7786 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | electrical¦hrsg | electrical¦hrsg | electrical¦hrsg | query | hrsg | match | true | false | 1 | 1 | 14.8421 | 0.6731 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦hrsg | system_design¦engineering | 6 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122101 | HRSG - ILLUMINATION CALCULATION | Calculation sheet | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7948 | 0.7051 | 0.7051 | [6 empty] | FA | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 11 | 2 | 12.8284 | 0.5824 | 0.0302 | 0.0302 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-12-01 | 2024-12-31 | 2025-01-30 | 2025-02-14 | 2025-03-01 | 2025-03-16 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122102 | HRSG - I/O LIST FOR BMS AND CEMS | LIST | Heat Recovery Steam Generator |  |  |  | I/O List for HRSG |  | HRSG - I/O List for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | list | list | io_list | io_list | cems¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.8267 | 0.7730 | 0.7730 | [6 empty] | FA | 1PF1660W86A04P | (CEMS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | 2007-08-29 | 2008-03-31 | procurement | procurement | match | hrsg | hrsg | hrsg | query | cems¦hrsg | match | true | false | 2 | 2 | 27.1678 | 0.7150 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122103 | HRSG - ARRANGEMENT OF PARTITION PLATE & GAS BAFFLE | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 1 | 20.8292 | 0.6516 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LB-122104 | HRSG - PIPING MATERIAL CLASSIFICATION | CLASSIFICATION | Heat Recovery Steam Generator | Piping |  |  | CLASSIFICATION for HRSG | [5 empty] | rule_query | other | other | classification | hrsg_piping_material_classification_for_hrsg | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6000 | 0.7670 | 0.6501 | 0.6501 | [7 empty] | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 1 | 17.1322 | 0.6146 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122105 | HRSG - INSTRUMENT SPECIFICATION & DATASHEET FOR DUCT BURNER SYSTEM | SPECIFICATION & DATASHEET | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | SPECIFICATION & DATASHEET for HRSG |  | HRSG - Equipment Specification for CEMS | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | specification | specification | specification | specification | generator¦heat¦hrsg¦recovery¦steam | cems¦hrsg | scoped | match | match | match | passed |  | 0.6000 | 0.6995 | 0.6298 | 0.6298 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | cems¦hrsg | hrsg | query | hrsg | match | true | false | 2 | 1 | 31.4016 | 0.6936 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122106 | HRSG - SHUT OFF AND CONTROL VALVE DATASHEET FOR DUCT BURNER SYSTEM | Data Sheet | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Data Sheet for HRSG |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.7374 | 0.7462 | 0.7462 | [6 empty] | FA | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-14 | 2008-04-02 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 3 | 31.4016 | 0.6844 | 0.0317 | 0.0317 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0LB-122107 | HRSG - INTERCONNECTION WIRING DIAGRAM FOR DUCT BURNER SYSTEM | WIRING DIAGRAM | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | WIRING DIAGRAM for DUCT BURNER SYSTEM |  | HRSG - Wiring Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | burner¦duct¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.6474 | 0.6609 | 0.6609 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 24.4996 | 0.6439 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122108 | HRSG - BMS SPECIFICATION FOR DUCT BURNER SYSTEM | Technical Specification | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | Technical Specification for HRSG |  | HRSG - Technical Specification for Duct Burner | 1 | start+179D<=FA<=start+179D+2M | FA ∈ [start+179d, start+239d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7699 | 0.6976 | 0.6976 | [6 empty] | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | procurement | procurement | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 2 | 1 | 31.4016 | 0.6960 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hrsg | procurement |  | 2024-12-10 | 2025-01-09 | 2025-02-08 | 2025-02-23 | 2025-03-10 | 2025-03-25 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122109 | HRSG - UNDERGROUND EARTHING CABLE LAYOUT DRAWING | Layout Drawing | Heat Recovery Steam Generator | EARTHING & Lightning Protection System |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | electrical¦hrsg | hrsg | electrical¦hrsg | query | hrsg | match | true | false | 1 | 16 | 14.8421 | 0.5796 | 0.0296 | 0.0222 | hybrid | structured_preferred | electrical¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LB-122110 | HRSG - STRENGTH CALCULATION REPORT FOR STEEL STRUCTURE | CALCULATION REPORT | Heat Recovery Steam Generator |  |  |  | CALCULATION REPORT for HRSG |  | HRSG - Strength Calculation Report for HRSG Stack | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | report | report | report | report | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.8121 | 0.7103 | 0.7103 | [6 empty] | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 15 | 12.9120 | 0.5953 | 0.0278 | 0.0278 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122111 | HRSG – PERPENDICULAR BAFFLE AND TIE PLATE ASSY DRAWINGS | DRAWINGS | Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG |  | HRSG - PoWer Distribution Panel DraWings | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7476 | 0.5043 | 0.5043 | [6 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 3 | 1 | 16.6725 | 0.6334 | 0.0323 | 0.0242 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-122112 | HRSG – DRAIN FLOW DIAGRAM | FLOW DIAGRAM | Heat Recovery Steam Generator | Drain System |  |  | FLOW DIAGRAM for Drain System |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | drain¦generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6520 | 0.6623 | 0.4636 | g_ambig | uncertain | 0.35 |  | 14 | The document is an HRSG drain flow diagram, but none of the listed HRSG-specific competing rules clearly correspond to a drain flow diagram. | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 4 | 1 | 21.9555 | 0.6382 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;rule_score_medium;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123001 | ACC - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Air Cooled Condenser |  |  |  | GENERAL ARRANGEMENT DRAWING for ACC |  | ACC - General Arrangement | 1 | start+79D<=FA<=start+79D+2M | FA ∈ [start+79d, start+139d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7973 | 0.9392 | 0.9392 | [6 empty] | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc | acc | acc | query |  | activity_unscoped | true | true | 1115 | 46 | 2.1289 | 0.5809 | 0.0103 | 0.0062 | hybrid | structured_phase_gap | acc | system_design |  | 2024-06-20 | 2024-07-20 | 2024-08-19 | 2024-09-03 | 2024-09-18 | 2024-10-03 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MAG-123002 | ACC - P&I DIAGRAM | P&ID | Air Cooled Condenser |  |  |  | P&ID for ACC |  | ACC - P&I Diagram_Steam & ConDensate System | 1 | start+79D<=FA<=start+79D+2M | FA ∈ [start+79d, start+139d] | title | diagram | diagram | p_id | p_id | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.7846 | 0.5854 | 0.5854 | [6 empty] | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | acc | acc¦condensate | acc | query |  | activity_unscoped | true | true | 10 | 26 | 20.1145 | 0.6223 | 0.0259 | 0.0155 | hybrid | structured_blocked_procurement_conflict | acc | system_design¦procurement |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-15 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123004 | ACC - PERFORMANCE CURVE | Performance Curve | Air Cooled Condenser |  |  |  | Performance Curve for ACC |  | ACC - Performance Curve | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | rule_query | curve | curve | performance_curve | performance_curve | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8662 | 0.9599 | 0.9599 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 2 | 15.9757 | 0.6529 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123005 | ACC - EQUIPMENT LIST | EQUIPMENT LIST | Air Cooled Condenser |  |  |  | Equipment List for ACC |  | ACC - Equipment List | 1 | start+99D<=FA<=start+99D+2M | FA ∈ [start+99d, start+159d] | rule_query | list | list | equipment_list | equipment_list | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8736 | 0.9621 | 0.9621 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 3 | 2 | 21.1047 | 0.7453 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-10 | 2025-02-09 | 2025-03-11 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0MAG-123006 | ACC - FAN SPECIFICATION | Technical Specification | Air Cooled Condenser |  |  |  | Fan Specification for ACC |  | FAN SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | fan_specification | fan_specification | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8330 | 0.7166 | 0.5016 | g_safe | [5 empty] | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | true | false | 1 | 1 | 15.3123 | 0.5247 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc | procurement | 4 | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MAG-123007 | ACC - CONDENSATE COLLECTING TANK OUTLINE DRAWING | Outline Drawing | Air Cooled Condenser | Condensate System |  |  | Outline Drawing for ACC |  | ACC - Fan Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | acc¦air¦condenser¦cooled¦tank | acc | scoped | match | match | match | passed |  | 0.7500 | 0.7852 | 0.7606 | 0.7606 | [6 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | acc¦condensate | acc | acc¦condensate | query | condensate | match | true | false | 1 | 1 | 20.6461 | 0.6482 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc¦condensate | system_design | 1 | 2024-10-18 | 2024-11-17 | 2024-12-17 | 2025-01-01 | 2025-01-16 | 2025-01-31 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123008 | ACC - GEARBOX DATASHEET | Data Sheet | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | ACC - Gearbox Datasheet | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9688 | 0.9906 | 0.9906 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 2 | 15.9757 | 0.6318 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123009 | ACC - FAN MOTOR DATA SHEET | Data Sheet | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | ACC - Fan Motor Datasheet | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.9362 | 0.8059 | 0.8059 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 1 | 15.9757 | 0.6061 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc | procurement | 4 | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123010 | ACC - CONDENSATE DRAIN PUMP SPECIFICATION | Technical Specification | Air Cooled Condenser | Condensate System |  |  | Drain Pump Specification for ACC |  | CONDENSATE DRAIN PUMP SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | drain_pump_specification | drain_pump_specification | acc¦air¦condenser¦cooled¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.7633 | 0.7540 | 0.5278 | [6 empty] | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc¦condensate | condensate | acc¦condensate | query | acc¦condensate | match | true | false | 1 | 1 | 27.9742 | 0.6106 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc¦condensate | procurement | 10 | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DH02-P0MAG-123011 | ACC - SJAE DATASHEET | Data Sheet | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | ACC - Datasheet | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.6667 | 0.8221 | 0.7133 | 0.7133 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 5 | 15.9757 | 0.6524 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAJ-123012 | ACC - CLEANING WATER PUMP DATASHEET | Data Sheet | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | ACC - Cleaning Water Pump Datasheet | 1 | start+269D<=FA<=start+269D+2M | FA ∈ [start+269d, start+329d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled¦pump | acc¦pump | scoped | match | match | match | passed |  | 1.0000 | 0.9668 | 0.9900 | 0.9900 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 2 | 15.9757 | 0.6449 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2025-06-29 | 2025-07-29 | 2025-08-28 | 2025-09-12 | 2025-09-27 | 2025-10-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XR00-P0MAG-123013 | ACC - ELECTRICAL LIFTING HOIST DATASHEET | Data Sheet | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | ACC - Electrical Lifting Hoist Datasheet | 1 | start+269D<=FA<=start+269D+2M | FA ∈ [start+269d, start+329d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9658 | 0.9897 | 0.9897 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc¦crane_hoist¦electrical | acc | query | acc¦condensate | match | true | false | 2 | 2 | 15.9757 | 0.6168 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-06-29 | 2025-07-29 | 2025-08-28 | 2025-09-12 | 2025-09-27 | 2025-10-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123014 | ACC - MANUAL VALVE LIST | LIST | Air Cooled Condenser |  |  |  | Valve List for ACC |  | ACC - Valve List | 1 | start+137D<=FA<=start+137D+2M | FA ∈ [start+137d, start+197d] | rule_query | list | list | valve_list | valve_list | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8788 | 0.9636 | 0.9636 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | manual | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 2 | 15.9757 | 0.6755 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | delivery¦procurement¦installation | 10 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0MAG-123015 | ACC - MANUAL VALVE OUTLINE DRAWING | Outline Drawing | Air Cooled Condenser |  |  |  | Outline Drawing for ACC |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8454 | 0.9536 | 0.6675 | g_safe | [5 empty] | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc |  | acc | query |  | activity_unscoped | true | true | 1416 | 14 |  | 0.5468 | 0.0142 | 0.0085 | hybrid | structured_phase_gap | acc | system_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0MAG-123016 | ACC - PIPING ARRANGEMENT DRAWING | General Arrangement Drawing | Air Cooled Condenser | Piping |  |  | General Arrangement Drawing for ACC |  | ACC - General Arrangement | 1 | start+79D<=FA<=start+79D+2M | FA ∈ [start+79d, start+139d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8403 | 0.9521 | 0.9521 | [6 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | acc | acc | acc | query |  | activity_unscoped | true | true | 42 | 99 | 13.9400 | 0.5567 | 0.0161 | 0.0097 | hybrid | structured_phase_gap | acc | system_design |  | 2024-07-18 | 2024-08-17 | 2024-09-16 | 2024-10-01 | 2024-10-16 | 2024-10-31 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MAG-123017 | ACC - PIPING ISOMETRIC DRAWING | Isometric Drawing | Air Cooled Condenser | Piping |  |  | Isometric Drawing for ACC | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7024 | 0.6307 | 0.6307 | g_ambig | uncertain | 0.40 |  | 7 | The title is a general ACC piping isometric drawing, but the competing rules are for specific ACC line groups and it is unclear which one (if any) this document represents. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | acc | compressed_air | acc | query |  | activity_unscoped | true | true | 48 | 82 | 13.1146 | 0.5488 | 0.0163 | 0.0098 | hybrid | structured_phase_gap | acc | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MAG-123019 | ACC - LINE LIST | LINE LIST | Air Cooled Condenser |  |  |  | LINE LIST for ACC | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | other | other | line_list | line_list | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4927 | 0.4978 | 0.4978 | g_safe | [5 empty] | FI | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | compressed_air | acc | query | acc¦condensate | match | true | false | 1 | 2 | 15.9757 | 0.7048 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0MAG-123020 | ACC - STEEL STRUCTURE SPECIFICATION | Technical Specification | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5241 | 0.5072 | 0.5072 | g_safe | [5 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | true | false | 1 | 1 | 15.9757 | 0.6382 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc | procurement | 4 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0MAG-123021 | ACC - FOUNDATION DRAWINGS / CIVIL LOADING DATA | DRAWINGS | Air Cooled Condenser |  |  |  | DRAWINGS for ACC | H2, CO2 Supply System | Foundation DraWings/Civil Loading Data | 1 | start+1M-2M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.5556 | 0.6360 | 0.5797 | 0.5797 | g_ambig | generic_ok | 0.75 |  | 17 | This is ACC foundation/civil loading data, while the competing rules target other ACC drawings (piping, supports, motors, electrical) rather than foundation/loading data. | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | h2 | acc | query | acc¦condensate | match | true | false | 1 | 3 | 10.5740 | 0.6259 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc | civil_design | 6 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0MAG-123022 | ACC - EMBEDDED MATERIAL SPECIFICATION | Technical Specification | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5241 | 0.5072 | 0.5072 | g_safe | [5 empty] | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | true | false | 1 | 4 | 18.6280 | 0.6496 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2024-08-27 | 2024-09-26 | 2024-10-26 | 2024-11-10 | 2024-11-25 | 2024-12-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0MAG-123023 | ACC - ELECTRICAL LOAD LIST | LOAD LIST | Air Cooled Condenser | ELECTRICAL |  |  | LOAD LIST for ACC | [5 empty] | rule_query | other | other | load_list | acc_elec_load_list | acc¦air¦condenser¦cooled | acc | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.7500 | 0.7974 | 0.7642 | 0.7642 | [7 empty] | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc¦electrical |  | acc¦electrical | query | acc¦condensate | match | true | false | 2 | 2 | 8.4032 | 0.5387 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc¦electrical | procurement | 10 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0MAG-123025 | ACC - MOTOR THERMAL LIMIT CURVE | Performance Curve | Air Cooled Condenser |  |  |  | Performance Curve for ACC |  | ACC - Performance Curve | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | rule_query | curve | curve | performance_curve | performance_curve | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8662 | 0.9599 | 0.9599 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 2 | 1 | 15.9757 | 0.6075 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MAG-123026 | ACC - SPEED - TORQUE & CURRENT CURVE | Performance Curve | Air Cooled Condenser |  |  |  | Performance Curve for ACC |  | ACC - Performance Curve | 1 | start+109D<=FA<=start+109D+2M | FA ∈ [start+109d, start+169d] | rule_query | curve | curve | performance_curve | performance_curve | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8662 | 0.9599 | 0.9599 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 2 | 2 | 15.9757 | 0.5895 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123027 | ACC - FUNCTIONAL DESCRIPTION | FUNCTIONAL DESCRIPTION | Air Cooled Condenser |  |  |  | FUNCTIONAL DESCRIPTION for ACC |  | Functional Description | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | functional_description | functional_description | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6052 | 0.6482 | 0.4538 | g_safe | [5 empty] | FA | 1CF3020W42A08 | (COND Air EXT Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-09-27 | 2008-11-10 |  | installation | query_unknown | acc |  | acc | query | acc¦condensate | match | true | false | 26 | 5 | 8.5906 | 0.5759 | 0.0270 | 0.0203 | hybrid | structured_no_phase | acc |  |  | 2025-05-16 | 2025-05-31 | 2025-06-15 | 2025-06-30 | 2025-07-30 | 2025-08-29 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MAG-123029 | ACC - CONTROL LOGIC & LOOP DIAGRAM | CONTROL LOGIC & LOOP DIAGRAM | Air Cooled Condenser |  |  |  | CONTROL LOGIC & LOOP DIAGRAM for ACC |  | Logic & Loop Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | diagram | diagram | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6998 | 0.9099 | 0.9099 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | acc |  | acc | query |  | activity_unscoped | true | true | 3 | 224 | 17.6592 | 0.4925 | 0.0194 | 0.0116 | hybrid | structured_phase_gap | acc | system_design¦engineering |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0MAG-123030 | ACC - I&C WIRING DIAGRAMS | WIRING DIAGRAMS | Air Cooled Condenser | Instrumentation and Control |  |  | WIRING DIAGRAMS for Instrumentation and Control |  | ACC - Wiring Diagram | 1 | start+289D<=FA<=start+289D+2M | FA ∈ [start+289d, start+349d] | title | diagram | diagram | wiring_diagram | wiring_diagram | acc¦air¦condenser¦cooled¦instrumentation | acc | scoped | match | match | match | passed |  | 0.6667 | 0.8129 | 0.7105 | 0.7105 | [6 empty] | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc | acc | acc | query |  | activity_unscoped | true | true | 575 | 13 | 7.1447 | 0.6020 | 0.0153 | 0.0092 | hybrid | structured_phase_gap | acc | system_design¦engineering |  | 2025-01-16 | 2025-02-15 | 2025-03-17 | 2025-04-01 | 2025-04-16 | 2025-05-01 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0MAG-123031 | ACC - INSTRUMENT LIST | LIST | Air Cooled Condenser | INSTRUMENT |  |  | Instrument List for ACC |  | ACC - Instrument List | 1 | start+137D<=FA<=start+137D+2M | FA ∈ [start+137d, start+197d] | rule_query | list | list | instrument_list | instrument_list | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8600 | 0.9580 | 0.9580 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 2 | 15.9757 | 0.6902 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | procurement | 4 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MAG-123032 | ACC - INSTRUMENT DATASHEET | Data Sheet | Air Cooled Condenser | INSTRUMENT |  |  | Data Sheet for ACC |  | ACC - Instrument Datasheet | 1 | start+151D<=FA<=start+151D+2M | FA ∈ [start+151d, start+211d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9430 | 0.9829 | 0.9829 | [6 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 1 | 15.9757 | 0.6580 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc | procurement | 4 | 2025-03-03 | 2025-04-02 | 2025-05-02 | 2025-05-17 | 2025-06-01 | 2025-06-16 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MAG-123033 | ACC - INSTRUMENT DRAWING | DRAWING | Air Cooled Condenser | INSTRUMENT |  |  | DRAWING for ACC |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.6055 | 0.5317 | 0.5317 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5368 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MAG-123034 | ACC - INSTRUMENT CALIBRATION SHEET | CALIBRATION SHEET | Air Cooled Condenser | INSTRUMENT |  |  | CALIBRATION SHEET for ACC | [5 empty] | rule_query | other | other | calibration_sheet | instrument_calibration_sheet | acc¦air¦condenser¦cooled |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.7620 | 0.6953 | 0.6953 | [7 empty] | 1CF3020W42A08 | (COND Air EXT Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-09-27 | 2008-11-10 |  | installation | query_unknown | acc |  | acc | query | acc¦condensate | match | true | false | 32 | 15 | 8.5906 | 0.5530 | 0.0242 | 0.0182 | hybrid | structured_no_phase | acc | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0MAG-123035 | ACC - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | Air Cooled Condenser | INSTRUMENTATION |  |  | HOOK - UP DRAWING for ACC |  | ACC - Instrument Hook-up DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.8000 | 0.8198 | 0.8059 | 0.8059 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.4915 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-09-17 | 2025-10-17 | 2025-11-16 | 2025-12-01 | 2025-12-16 | 2025-12-31 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123036 | ACC-MOTORISED VALVE SPECIFICATION | Technical Specification | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5241 | 0.5072 | 0.5072 | g_safe | [5 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | true | false | 7 | 1 | 15.9757 | 0.6325 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0MAG-123037 | ACC - I&C JB OUTLINE AND LAYOUT DRAWING | DRAWING | Air Cooled Condenser | Instrumentation and Control |  |  | DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.5371 | 0.5111 | 0.5111 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5243 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123038 | ACC - TERMINAL POINT LIST | LIST | Air Cooled Condenser |  |  |  | LIST for ACC | [5 empty] | rule_query | other | list | list | instrument_list | acc¦air¦condenser¦cooled | acc | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.7302 | 0.6857 | 0.6857 | [7 empty] | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | true | false | 2 | 2 | 8.4032 | 0.5766 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc | procurement | 4 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123039 | ACC - UTILITY CONSUMPTION LIST | LIST | Air Cooled Condenser |  |  |  | LIST for ACC | [5 empty] | rule_query | other | list | list | instrument_list | acc¦air¦condenser¦cooled | acc | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.7302 | 0.6857 | 0.6857 | [7 empty] | 1CF3020W42A08 | (COND Air EXT Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-09-27 | 2008-11-10 |  | installation | query_unknown | acc |  | acc | query | acc¦condensate | match | true | false | 14 | 12 | 8.5906 | 0.5589 | 0.0274 | 0.0206 | hybrid | structured_no_phase | acc | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123045 | ACC ERECTION DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.6055 | 0.5317 | 0.5317 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5707 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123046 | ACC REFERENCE DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.6055 | 0.5317 | 0.5317 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5616 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123047 | ACC ERECTION MANUAL | MANUAL | Air Cooled Condenser |  |  |  | MANUAL for ACC |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6898 | 0.6736 | 0.6736 | g_safe | [5 empty] | FI | 2PF3020W42A07T | (COND Air EXT Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-09-12 | 2008-10-27 | manual | delivery | match | acc |  | acc | query | acc¦condensate | match | true | false | 2 | 1 | 11.9081 | 0.5931 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc | delivery¦procurement¦installation | 10 | 2025-06-06 | 2025-07-06 | 2025-08-05 | 2025-08-20 | 2025-09-04 | 2025-09-19 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XA00-P0MAG-123048 | ACC - HOLDING EJECTOR DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.6055 | 0.5317 | 0.5317 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5795 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XA00-P0MAG-123049 | ACC - HOGGING EJECTOR DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.6055 | 0.5317 | 0.5317 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5738 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123050 | ACC - WINDWALL DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.6055 | 0.5317 | 0.5317 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5299 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123051 | ACC CABLE TRAY LAYOUT DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.5371 | 0.5111 | 0.5111 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | true | false | 1 | 3 | 8.4959 | 0.5353 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-123052 | ACC_LIGHTING & SMALL POWER LAYOUT DRAWING | Layout Drawing | Air Cooled Condenser | LIGHTING & SMALL POWER |  |  | Layout Drawing for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.6746 | 0.7274 | 0.7274 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc¦electrical | acc¦electrical | acc¦electrical | query | acc¦condensate | match | true | false | 1 | 7 | 8.4964 | 0.5042 | 0.0313 | 0.0235 | hybrid | structured_preferred | acc¦electrical | system_design¦civil_design | 10 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-DS00-P0MAG-123053 | ACC – CLEANING PROCEDURE | PROCEDURE | Air Cooled Condenser |  |  |  | PROCEDURE for ACC |  | Cleaning & Painting Procedure | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | procedure | procedure | procedure | procedure | acc¦air¦condenser¦cooled |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6248 | 0.6541 | 0.6541 | g_safe | [5 empty] | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | procurement | procurement | match | acc |  | acc | query | acc¦condensate | match | true | false | 4 | 2 | 15.9757 | 0.7045 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | acc | procurement |  | 2025-01-23 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123054 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COOLED CONDENSER | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦bop¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.5000 | 0.5371 | 0.5111 | 0.5111 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | true | false | 1 | 3 | 16.9918 | 0.5780 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123055 | WINDWALL LOGO FOR AIR COOLED CONDENSER |  | Air Cooled Condenser |  |  |  | for ACC | [5 empty] | rule_query | other | drawing | windwall_logo_for_air_cooled_condenser | general_arrangement_drawing | acc¦air¦condenser¦cooled | acc | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.3333 | 0.6558 | 0.4301 | 0.4301 | [7 empty] | 1CF3020W42A08 | (COND Air EXT Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-09-27 | 2008-11-10 |  | installation | query_unknown | acc |  | acc | query | acc¦condensate | match | true | false | 2 | 13 | 17.1813 | 0.5295 | 0.0298 | 0.0224 | hybrid | structured_no_phase | acc | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0EKG-124001 | FGS - FUEL GAS SYSTEM GENERAL LAYOUT DRAWING | Layout Drawing | Fuel Gas Package | Fuel Gas System - FUEL GAS SYSTEM |  |  | Layout Drawing for Fuel Gas System - FUEL GAS SYSTEM | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7879 | 0.7030 | 0.7030 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | true | false | 2 | 2 | 29.5567 | 0.7091 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0EKG-124002 | FGS - P&I DIAGRAM | P&ID |  | Fuel Gas System |  |  | P&ID for Fuel Gas System | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8215 | 0.7714 | 0.7714 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | false | false | 1 | 1 | 21.9084 | 0.8152 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.36 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0EKG-124003 | FGS - GAS FILTER & SEPARATOR ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System - GAS FILTER & SEPARATOR |  |  | ASSEMBLY DRAWING for Fuel Gas System - GAS FILTER & SEPARATOR | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦filter¦fuel¦gas¦separator | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7449 | 0.6901 | 0.6901 | [6 empty] | FA | 3EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | 2007-04-30 | 2007-10-30 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp¦gtg | match | true | false | 14 | 2 | 17.6458 | 0.6288 | 0.0296 | 0.0222 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-08-20 | 2024-10-01 | 2024-11-12 | 2024-10-22 | 2024-12-03 | 2025-01-14 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124004 | FGS - GAS HEATER ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System - GAS HEATER |  |  | ASSEMBLY DRAWING for Fuel Gas System - GAS HEATER | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fuel¦gas¦heater | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7502 | 0.6917 | 0.6917 | [6 empty] | FA | 1EF3520W16A01.2 | (Gas HTR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2007-10-01 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | false | 2 | 1 | 22.7337 | 0.6998 | 0.0325 | 0.0244 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-10-23 | 2024-12-04 | 2025-01-15 | 2024-12-25 | 2025-02-05 | 2025-03-19 | generated | 0.90 |  | false | false | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124005 | FGS - MAIN GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.8245 | 0.7140 | 0.7140 | [6 empty] | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp¦gtg | match | false | false | 1 | 2 | 17.8543 | 0.6814 | 0.0325 | 0.0244 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-03 | 2025-02-14 | 2025-01-24 | 2025-03-07 | 2025-04-18 | generated | 0.90 |  | false | false | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124006 | FGS - 2ND GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.8245 | 0.7140 | 0.7140 | [6 empty] | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp¦gtg | match | false | false | 1 | 3 | 17.8543 | 0.6925 | 0.0323 | 0.0242 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-03 | 2025-02-14 | 2025-01-24 | 2025-03-07 | 2025-04-18 | generated | 0.90 |  | false | false | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124007 | FGS - COLD VENT STACK ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.8245 | 0.7140 | 0.7140 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | fgp | fgp | query | fgp | match | false | false | 5 | 1 | 7.6021 | 0.6432 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-07-05 | 2024-08-16 | 2024-09-27 | 2024-09-06 | 2024-10-18 | 2024-11-29 | generated | 0.90 |  | false | false | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124008 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP ASSEMBLY DRAWING | ASSEMBLY DRAWING | Tank | Fuel Gas System |  |  | ASSEMBLY DRAWING for Tank |  | Tank DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | fgp¦pump¦tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7244 | 0.6840 | 0.4788 | [6 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | design_drawing | civil_design | compatible | condensate¦fgp |  | condensate¦fgp | query | condensate¦fgp | match | true | false | 1 | 1 | 31.8927 | 0.6898 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | condensate¦fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_score_medium;activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124009 | FGS - PANEL LAYOUT FOR LOCAL ELECTRICAL ROOM FOR FUEL GAS SUPPLY SYSTEM | Layout Drawing | Fuel Gas Package | FUEL GAS SUPPLY SYSTEM | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦leb¦local | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8036 | 0.8244 | 0.8244 | [6 empty] | FA | 0EF3520W32A04.1 | (FGS LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | true | false | 4 | 2 | 35.0372 | 0.7329 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124010 | FGS - GAS CHROMATOGRAPH OUTLINE DRAWING | Outline Drawing |  | Fuel Gas System |  |  | Outline Drawing for Fuel Gas System |  | GAS CHROMATOGRAPH OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | outline_drawing | outline_drawing | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8764 | 0.9629 | 0.6740 | g_ambig | generic_ok | 0.70 |  | 3 | The document is specifically a gas chromatograph outline drawing, and the competing rules are generic equipment/motor outline drawing rules not clearly specific to the gas chromatograph. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | false | 1 | 1 | 6.8233 | 0.6901 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124011 | FGS - ESD VALVE ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | Instrument Installation DraWing | 1 | start+16W<=FA<=FC<=start+28W | FA ∈ [start+112d, start+196d] ¦ FC ∈ [start+112d, start+196d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.8245 | 0.7140 | 0.7140 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | fgp | fgp | query | fgp | match | false | false | 5 | 1 | 7.6021 | 0.6224 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-07-05 | 2024-08-16 | 2024-09-27 | 2024-09-06 | 2024-10-18 | 2024-11-29 | generated | 0.90 |  | false | false | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124012 | FGS - CABLE ROUTE LAYOUT FOR FUEL GAS SUPPLY SYSTEM | CABLE ROUTE LAYOUT | Fuel Gas Package | Fuel Gas System |  |  | CABLE ROUTE LAYOUT for Fuel Gas System | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7210 | 0.6830 | 0.6830 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | electrical¦fgp | fgp | query | fgp | match | true | false | 5 | 1 | 20.7952 | 0.6954 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-05-10 | 2024-06-21 | 2024-08-02 | 2024-07-12 | 2024-08-23 | 2024-10-04 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124013 | FGS - FOUDATION & LOADS FOR FUEL GAS SUPPLY SYSTEM |  | Fuel Gas Package | Fuel Gas System |  |  | for FGP | [5 empty] | rule_query | other |  | for_fgp |  | fgp |  |  |  |  | no_rule | no_match | [12 empty] | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 |  | civil_design | query_unknown | fgp |  | fgp | query | fgp | match | true | false | 1 | 8 | 24.8661 | 0.7279 | 0.0311 | 0.0233 | hybrid | structured_no_phase | fgp | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0EKG-124014 | FGS - CONTROL LOOP, LOGIC DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | LOGIC DIAGRAM | Fuel Gas Package | Fuel Gas System |  |  | Control Loop Diagram for Fuel Gas System | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7811 | 0.7593 | 0.7593 | g_safe | [5 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 30.5855 | 0.7321 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0EKG-124015 | FGS - CABLE BLOCK DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | BLOCK DIAGRAM | Fuel Gas Package | Fuel Gas System |  |  | BLOCK DIAGRAM for Fuel Gas System | Cathodic | Block Diagram | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | diagram | diagram | diagram | diagram | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5561 | 0.6335 | 0.6335 | g_ambig | generic_ok | 0.70 |  | 3 | The document is a cable block diagram, whereas the competing rules are for process flow/mass balance, control logic/loop, or startup/shutdown diagrams. | SKIP | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 30.5855 | 0.7348 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0EKG-124016 | FGS - TERMINAL BOX DRAWING FOR FUEL GAS SUPPLY SYSTEM | DRAWING | Fuel Gas Package | Fuel Gas System |  |  | DRAWING for FGP |  | Motor Terminal box draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5620 | 0.6936 | 0.6936 | g_ambig | generic_ok | 0.65 |  | 18 | This is a terminal box drawing for the fuel gas supply system, and none of the competing specific rules explicitly target terminal box drawings. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp |  | fgp | query | fgp | match | true | false | 5 | 1 | 20.7952 | 0.7070 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0EKG-124017 | FGS - SINGLE LINE DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | Single Line Diagram | Fuel Gas Package | Fuel Gas System |  |  | Single Line Diagram for Fuel Gas System | Fuel Gas System | Single Line Diagram | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 1.0000 | 0.9829 | 0.9949 | 0.9949 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 3 | 1 | 30.5855 | 0.7596 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering |  | 2024-05-10 | 2024-06-21 | 2024-08-02 | 2024-07-12 | 2024-08-23 | 2024-10-04 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124018 | FGS - MEASUREMENT LIST FOR FUEL GAS SUPPLY SYSTEM | LIST | Fuel Gas Package | Fuel Gas System |  |  | LIST for FGP | [5 empty] | rule_query | other | list | list | io_list | fgp¦fuel¦gas | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.5000 | 0.4244 | 0.4773 | 0.4773 | [7 empty] | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 |  | civil_design | query_unknown | fgp |  | fgp | query | fgp | match | true | false | 2 | 15 | 24.8661 | 0.6692 | 0.0295 | 0.0221 | hybrid | structured_no_phase | fgp | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BX03-P0EKG-124020 | FGS - WIRING DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | WIRING DIAGRAM | Fuel Gas Package | Fuel Gas System |  |  | WIRING DIAGRAM for Fuel Gas System | Fuel Gas System | Interconnection Wiring Diagram | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8423 | 0.8360 | 0.8360 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 1 | 30.5855 | 0.7538 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦engineering |  | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-124021 | FGS - VALVE LIST | LIST |  | Fuel Gas System |  |  | Valve List for Fuel Gas System |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7443 | 0.6900 | 0.6900 | g_safe | [5 empty] | FA | 2PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-05-14 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | false | 17 | 1 | 11.5658 | 0.6581 | 0.0294 | 0.0294 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0EKG-124022 | FGS - VALVE DATA SHEET | Data Sheet |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.9097 | 0.8563 | 0.8563 | [6 empty] | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | false | 1 | 2 | 14.9235 | 0.6510 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0EKG-124023 | FGS - BUFFER TANK OUTLINE DRAWING | Outline Drawing |  | Fuel Gas System |  |  | Outline Drawing for Fuel Gas System |  | BUFFER TANK OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | outline_drawing | outline_drawing | fgp¦fuel¦gas¦tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.8537 | 0.9561 | 0.6693 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | false | false | 1 | 1 | 5.3727 | 0.6342 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124024 | FGS - BOOSTER COMPRESSOR OUTLINE DRAWING | Outline Drawing |  | Fuel Gas System |  |  | Outline Drawing for Fuel Gas System | Substation | Outline DraWing (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6404 | 0.6588 | 0.6588 | g_ambig | use_specific | 0.60 | Equipment (incl. pump) Assembly/Outline DraWing | 3 | A booster compressor is equipment (not a DC system drawing), so the equipment assembly/outline drawing rule is the closest specific match among the competing rules. | SKIP | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | dc_ups | fgp | query | fgp | match | false | false | 1 | 1 | 7.6021 | 0.6404 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124025 | FGS - GAS HEATER DATA SHEET | Data Sheet |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.9097 | 0.8563 | 0.8563 | [6 empty] | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | false | 1 | 1 | 20.8124 | 0.7674 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-09-11 | 2024-10-30 | 2024-12-18 | 2024-11-20 | 2025-01-08 | 2025-02-26 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124026 | FGS - MAIN GAS PRESSURE REDUCING STATION DATA SHEET | Data Sheet |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.9097 | 0.8563 | 0.8563 | [6 empty] | FA | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-04-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp¦gtg | match | false | false | 5 | 1 | 24.7216 | 0.7366 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124027 | FGS - 2ND GAS PRESSURE REDUCING STATION DATA SHEET | Data Sheet |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.9097 | 0.8563 | 0.8563 | [6 empty] | FA | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-04-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp¦gtg | match | false | false | 5 | 1 | 24.7216 | 0.7090 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124028 | FGS - COLD VENT STACK DATA SHEET | Data Sheet |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.9097 | 0.8563 | 0.8563 | [6 empty] | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | false | 2 | 1 | 14.9235 | 0.6307 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124029 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP DATA SHEET | Data Sheet |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas¦pump¦tank | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.9097 | 0.8563 | 0.8563 | [6 empty] | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | procurement | procurement | match | condensate¦fgp | fgp | condensate¦fgp | query | condensate¦fgp | match | true | false | 1 | 1 | 31.1873 | 0.7533 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate¦fgp | procurement |  | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124030 | FGS - GAS CHROMATOGRAPH DATA SHEET | Data Sheet |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | Equipment Data Sheet | 1 | start+10W<=FA<=FC<=start+24W | FA ∈ [start+70d, start+168d] ¦ FC ∈ [start+70d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.9097 | 0.8563 | 0.8563 | [6 empty] | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | false | 2 | 2 | 16.4325 | 0.6913 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124031 | FGS - ESD VALVE DATA SHEET | Data Sheet | ESD VALVE | Fuel Gas System |  |  | Data Sheet for ESD VALVE |  | Valve Data Sheet | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | esd¦fgp¦valve |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7540 | 0.9262 | 0.6483 | g_ambig | use_specific | 0.70 | Valve/Specilty Data Sheet | 10 | An ESD valve data sheet is a valve specialty data sheet, which has a different timeline than the generic valve data sheet rule. | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | false | false | 1 | 2 | 14.9235 | 0.5937 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review_activity | rule_scope_status=rule_generic;activity_equipment_unconfirmed;rule_generic_judge=use_specific;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124032 | FGS - BOOSTER COMPRESSOR DATA SHEET | Data Sheet | BOOSTER COMPRESSOR | Fuel Gas System |  |  | Data Sheet for BOOSTER COMPRESSOR | Air Compressor | Data Sheet for Valves | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | booster¦compressor¦fgp |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7470 | 0.6908 | 0.6908 | g_ambig | use_specific | 0.75 | Equipment Data Sheet | 10 | A booster compressor data sheet is equipment data sheet content, not a valve data sheet, so the equipment data sheet specific rule should govern. | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | procurement | procurement | match | fgp | compressed_air | fgp | query | fgp | match | true | false | 1 | 2 | 38.8465 | 0.6869 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124033 | FGS - BUFFER TANK DATA SHEET | Data Sheet | BUFFER TANK | Fuel Gas System |  |  | Data Sheet for BUFFER TANK |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | buffer¦fgp¦tank |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5984 | 0.6462 | 0.6462 | g_ambig | uncertain | 0.30 |  | 13 | There are two conflicting 'Equipment Data Sheet' rules with different timelines and no equipment qualifier to determine which applies to a buffer tank. | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 33.9800 | 0.7599 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-CH01-P0EKG-124039 | INSTALLATION & ERECTION MANUAL | INSTALLATION & ERECTION MANUAL |  |  |  |  | INSTALLATION & ERECTION MANUAL |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9423 | 0.9827 | 0.9827 | [6 empty] | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | manual | delivery | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 5 | 29.1386 | 0.4819 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | delivery¦procurement¦installation |  | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124040 | FGS_DATASHEET AND OUTLINE DRAWING FOR GTG INLET STRAINERS | DATASHEET AND OUTLINE DRAWING | Gas Turbine Generator INLET STRAINERS | Fuel Gas System |  |  | DATASHEET AND OUTLINE DRAWING for Gas Turbine Generator INLET STRAINERS |  | Valve datasheet & draWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | datasheet | datasheet | data_sheet | data_sheet | fgp¦gas¦generator¦gtg¦inlet¦strainers¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5919 | 0.6442 | 0.6442 | g_ambig | generic_ok | 0.55 |  | 10 | The competing rules are generic data sheet categories and do not specifically target GTG inlet strainers more than the already-matched valve datasheet & drawing rule. | FA | 2PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | 2007-03-30 | 2008-02-29 | procurement | procurement | match | fgp¦gtg |  | fgp¦gtg | query | gtg | match | true | false | 9 | 2 | 25.7707 | 0.6520 | 0.0306 | 0.0306 | hybrid | structured_cell_found_text_preferred | fgp¦gtg | procurement |  | 2024-06-22 | 2024-07-22 | 2024-08-21 | 2024-09-05 | 2024-09-20 | 2024-10-05 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0EKG-124048 | CABLE CONNECTION DIAGRAM | CABLE CONNECTION DIAGRAM |  |  |  |  | CABLE CONNECTION DIAGRAM | Substation | Cable Connection Diagram | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7653 | 0.7546 | 0.7546 | [6 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 18 | 111 | 16.9020 | 0.4439 | 0.0187 | 0.0105 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-UB01-P0EKG-124075 | FGS - FUNCTIONAL DESCRIPTION | FUNCTIONAL DESCRIPTION |  | Fuel Gas System |  |  | FUNCTIONAL DESCRIPTION for Fuel Gas System | Fuel Gas System | Functional description | 1 | start+10W<=FA<=FC<=start+18W | FA ∈ [start+70d, start+126d] ¦ FC ∈ [start+70d, start+126d] | rule_query | other | other | functional_description | functional_description | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 1.0000 | 0.9195 | 0.9759 | 0.9759 | [6 empty] | FA | 0PF3520W42A04.3P | (FOFP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 | 2008-03-28 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | false | false | 4 | 13 | 12.4076 | 0.6189 | 0.0293 | 0.0293 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-09-10 | 2024-10-08 | 2024-11-05 | 2024-10-29 | 2024-11-26 | 2024-12-24 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKG-124077 | FGS – ISO DRAWING | ISO DRAWING |  | Fuel Gas System |  |  | ISO DRAWING for Fuel Gas System | Fuel Gas System | Piping ISO DraWing | 1 | start+20W<=FA<=FC<=start+36W | FA ∈ [start+140d, start+252d] ¦ FC ∈ [start+140d, start+252d] | rule_query | drawing | drawing | drawing | drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8004 | 0.8235 | 0.8235 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | fgp | fgp | query | fgp | match | false | false | 5 | 1 | 7.6021 | 0.6976 | 0.0318 | 0.0238 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-08-02 | 2024-09-27 | 2024-11-22 | 2024-10-18 | 2024-12-13 | 2025-02-07 | generated | 0.90 |  | false | false | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YL30-P0EKG-124078 | FGS – SALES GAS CONTROL VALVE STATION DOCUMENT & DRAWING | DOCUMENT & DRAWING | SALES GAS CONTROL VALVE STATION | Fuel Gas System |  |  | DOCUMENT & DRAWING for SALES GAS CONTROL VALVE STATION |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | fgp¦gas¦sales¦station¦valve |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5002 | 0.5001 | 0.5001 | g_ambig | uncertain | 0.35 |  | 19 | The document is a bundled 'document & drawing' for the station, and it is unclear whether it should follow the FI control system configuration drawing rule or another specific drawing category. | FI | 0EF3520W00A10.3 | (FO FWD Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 |  | design_drawing | civil_design | compatible | fgp |  | fgp | query | fgp | match | true | false | 10 | 2 | 19.6206 | 0.6070 | 0.0304 | 0.0228 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-19 | 2024-12-19 | 2025-01-18 | 2025-02-02 | 2025-02-17 | 2025-03-04 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124079 | FGS – DUPLEX STRAINER INSTRUMENT DATA & DRAWING | DATA & DRAWING | DUPLEX STRAINER | Fuel Gas System |  |  | DATA & DRAWING for DUPLEX STRAINER |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | duplex¦fgp¦strainer |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5643 | 0.6359 | 0.6359 | g_ambig | use_specific | 0.65 | Instrument Installation DraWing | 18 | A duplex strainer instrument installation drawing aligns with the specific 'Instrument Installation DraWing' rule that has a different timeline than the generic match. | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp |  | fgp | query | fgp | match | false | false | 1 | 8 | 19.2215 | 0.5285 | 0.0311 | 0.0233 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-07-10 | 2024-08-09 | 2024-09-08 | 2024-09-23 | 2024-10-08 | 2024-10-23 | generated | 0.90 |  | false | false | 0.22 | needs_review_activity | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;activity_equipment_unconfirmed;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-DN04-P0EKG-124161 | INSULATION PROCEDURE FOR FGSS AREA AND HEATER SKIDS | PROCEDURE | HEATER SKIDS | Fuel Gas Package |  |  | PROCEDURE for HEATER SKIDS |  | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | fgp¦heater¦skids |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4185 | 0.4755 | 0.4755 | g_ambig | uncertain | 0.25 |  | 11 | The document is an insulation procedure, but the competing rules are for storage/handling, packing, FAT, NDE, etc., and none clearly map to insulation. | FI | 1PF3520W42A08.2T | (Gas HTR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2008-04-02 | 2008-05-16 | delivery | delivery | match | fgp |  | fgp | query | fgp | match | false | false | 1 | 5 | 22.7163 | 0.5888 | 0.0318 | 0.0318 | hybrid | structured_preferred | fgp | delivery¦procurement | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0EKG-124180 | FGS - 120V TR PANEL FOR GAS CHROMATOGRAPH |  | 120V Transformer PANEL | Fuel Gas System |  |  | for 120V Transformer PANEL | [5 empty] | rule_query | other | other | fgs_120v_tr_panel_for_gas_chromatograph | rating_plate | 120v¦fgp¦panel¦transformer |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.3333 | 0.6113 | 0.4167 | 0.4167 | [7 empty] | 1CF6500W70A06 | (GTG TR) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-05-31 | 2008-07-16 |  | installation | query_unknown | fgp¦gsut_uat |  | fgp¦gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 17 | 2 | 12.3682 | 0.5796 | 0.0291 | 0.0218 | hybrid | structured_no_phase | fgp¦gsut_uat | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P8ZEN-125001 | RESERVE BOILER - SUPPLY/EQUIPMENT LIST | LIST | RESERVE BOILER |  |  |  | Equipment List for RESERVE BOILER |  | Equipment list | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | equipment_list | equipment_list | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6505 | 0.6618 | 0.6618 | g_safe | [5 empty] | FI | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 52 | 2 | 9.6644 | 0.5951 | 0.0251 | 0.0063 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P8QHA-125002 | RESERVE BOILER - SYSTEM DESCRIPTION | System Description | RESERVE BOILER |  |  |  | System Description for RESERVE BOILER |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | description | description | system_description | system_description | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5362 | 0.6275 | 0.5334 | g_safe | [5 empty] | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 2 | 21 | 9.5174 | 0.5345 | 0.0285 | 0.0171 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.60 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P8ZEN-125012 | RESERVE BOILER - BOILER PREDICTED PERFORMANCE DATA & CURVE | DATA & CURVE | RESERVE BOILER |  |  |  | Performance Curve for RESERVE BOILER |  | Boiler Predicted Performance Data & Curve | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | curve | curve | performance_curve | performance_curve | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8565 | 0.9569 | 0.6699 | g_safe | [5 empty] | FA | 0EF3530W00A01.1 | (Common EDG) Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Common Emergency Diesel Generator | 2007-03-01 | 2007-04-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 6 | 145 | 9.7142 | 0.4188 | 0.0200 | 0.0120 | hybrid | structured_system_absent | reserve_boiler | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P8ZEN-125014 | RESERVE BOILER - BOILER START - UP CURVE | Performance Curve | RESERVE BOILER |  |  |  | Performance Curve for RESERVE BOILER | FinFan Cooler | Performance Curve | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | curve | curve | performance_curve | performance_curve | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6100 | 0.5330 | 0.5330 | g_safe | [5 empty] | FI | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 22 | 11 | 8.5035 | 0.5031 | 0.0263 | 0.0066 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P8ZEN-125019 | RESERVE BOILER_ERECTION MANUAL | ERECTION MANUAL | RESERVE BOILER |  |  |  | ERECTION MANUAL for RESERVE BOILER |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6179 | 0.6520 | 0.6520 | g_safe | [5 empty] | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | manual | delivery | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 1 | 1 | 29.1386 | 0.5699 | 0.0328 | 0.0082 | hybrid | structured_system_absent | reserve_boiler | delivery¦procurement¦installation | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC00-P8QHA-125101 | RESERVE BOILER - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | GENERAL ARRANGEMENT DRAWING for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6751 | 0.9025 | 0.9025 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 49 | 458 | 13.4438 | 0.4833 | 0.0111 | 0.0067 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8QHB-125151 | RESERVE BOILER - FOUNDATION LOADING DATA FOR STEEL STRUCTURE & STACK | DATA | RESERVE BOILER |  |  |  | DATA for RESERVE BOILER |  | FOUNDATION AND LOADING DATA | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5484 | 0.6895 | 0.4827 | g_safe | [5 empty] | FA | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-05 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | true | false | 3 | 2 | 14.6190 | 0.6628 | 0.0320 | 0.0080 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XT00-P8QHB-125152 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STEEL STRUCTURE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | FinFan Cooler | Fin Fan Cooler Steel structure assembly draWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3750 | 0.5536 | 0.4286 | 0.4286 | g_safe | [5 empty] | FA | 3EF1625W00A02.1 | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | 2007-08-01 |  | civil_design | civil_design | match | reserve_boiler | ccw | reserve_boiler | query | hrsg | mismatch | false | false | 776 | 38 | 3.4651 | 0.5265 | 0.0114 | 0.0029 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XT00-P8QHB-125153 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STACK | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Arrangement DraWing for Stack | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5540 | 0.8662 | 0.6064 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 177 | 218 | 3.6958 | 0.4701 | 0.0078 | 0.0020 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P8QHB-125161 | RESERVE BOILER - DESIGN CRITERIA FOR STEEL STRUCTURE | DESIGN CRITERIA | RESERVE BOILER |  |  |  | DESIGN CRITERIA for RESERVE BOILER |  | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | criteria | criteria | design_criteria | design_criteria | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.5964 | 0.4789 | 0.4789 | g_safe | [5 empty] | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 1 | 1 | 62.3058 | 0.6051 | 0.0328 | 0.0197 | hybrid | structured_system_absent | reserve_boiler | design_criteria¦system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P8QHB-125162 | RESERVE BOILER - CONNECTION DETAIL DRAWING FOR STEEL STRUCTURE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5634 | 0.6357 | 0.6357 | g_safe | [5 empty] | FI | 3EF1625W00A02.2 | (HRSG #32 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | 2007-08-06 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3955 | 37 |  | 0.5236 | 0.0106 | 0.0026 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC02-P8QHB-125164 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STEEL STRUCTURE | General Arrangement Drawing | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | g_safe | [5 empty] | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 134 | 7 | 10.1506 | 0.5725 | 0.0201 | 0.0050 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC02-P8QHB-125172 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STACK | General Arrangement Drawing | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 82 | 106 | 10.6763 | 0.5372 | 0.0131 | 0.0033 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD07-P8QHA-125201 | RESERVE BOILER - PRESSURE PART ARRANGEMENT OF BOILER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7057 | 0.5617 | 0.3932 | g_safe | [5 empty] | FA | 1EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | fgp¦gtg¦hrsg | mismatch | false | false | 4 | 132 | 8.9279 | 0.4650 | 0.0208 | 0.0039 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125202 | RESERVE BOILER - DESUPERHEATER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Desuperheater DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7904 | 0.7038 | 0.4927 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3792 | 1 |  | 0.5642 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125207 | RESERVE BOILER - ECONOMIZER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Economizer - DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6967 | 0.6757 | 0.4730 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3792 | 3 |  | 0.5259 | 0.0161 | 0.0030 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8QHA-125300 | RESERVE BOILER - FOUNDATION LOADING DATA FOR BOILER PROPER | DATA | RESERVE BOILER |  |  |  | DATA for RESERVE BOILER |  | FOUNDATION AND LOADING DATA | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5985 | 0.7046 | 0.4932 | g_safe | [5 empty] | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | false | 87 | 6 | 8.9406 | 0.5649 | 0.0220 | 0.0055 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P8QHA-125303 | RESERVE BOILER - REFRACTORY LINING PROCEDURE FOR BOILER PROPER | PROCEDURE | RESERVE BOILER |  |  |  | PROCEDURE for RESERVE BOILER | FireFighting | Rubber Lining Procedure (if applicable) | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | title | procedure | procedure | procedure | procedure | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5651 | 0.4029 | 0.4029 | g_safe | [5 empty] | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 7 | 2 | 11.9765 | 0.5724 | 0.0311 | 0.0078 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P8QHA-125304 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR BOILER PROPER | SPECIFICATION & DRAWING | RESERVE BOILER |  |  |  | Insulation Specification for RESERVE BOILER | FireFighting | Insulation Specification | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | specification | specification | insulation_specification | insulation_specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6906 | 0.6738 | 0.6738 | g_safe | [5 empty] | FA | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-10-01 | 2008-04-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | true | false | 5 | 1 | 19.4219 | 0.5985 | 0.0318 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125308 | RESERVE BOILER - NAME PLATE DRAWING OF BOILER PROPER | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6275 | 0.8882 | 0.8882 | g_safe | [5 empty] | FI | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 581 | 82 | 2.0974 | 0.5123 | 0.0086 | 0.0016 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125310 | RESERVE BOILER - NAME PLATE DRAWING OF VALVE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5845 | 0.8754 | 0.8754 | g_safe | [5 empty] | FI | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 604 | 60 | 2.0974 | 0.5132 | 0.0098 | 0.0018 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P8QHL-125400 | RESERVE BOILER - GAS & AIR DUCT ARRANGEMENT DRAWING | General Arrangement Drawing | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | g_safe | [5 empty] | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 131 | 69 | 10.6763 | 0.5631 | 0.0130 | 0.0032 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XA00-P8QHL-125401 | RESERVE BOILER - DAMPER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | g_safe | [5 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3831 | 40 |  | 0.5442 | 0.0103 | 0.0019 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XA00-P8QHL-125402 | RESERVE BOILER - EXPANSION JOINT DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Expansion Joint Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7411 | 0.9223 | 0.6456 | g_safe | [5 empty] | FA | 1EF3030W16A01 | (EXP Head Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | ccw | mismatch | false | false | 47 | 28 | 4.3847 | 0.5000 | 0.0207 | 0.0039 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P8QHL-125403 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR DUCT | SPECIFICATION & DRAWING | RESERVE BOILER |  |  |  | Insulation Specification for RESERVE BOILER | FireFighting | Insulation Specification | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | specification | specification | insulation_specification | insulation_specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6906 | 0.6738 | 0.6738 | g_safe | [5 empty] | FA | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-10-01 | 2008-04-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | true | false | 4 | 1 | 19.4219 | 0.5867 | 0.0320 | 0.0080 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P8ZEN-125502 | RESERVE BOILER - PMS (PIPE MATERIAL SPECIFICATION) | PMS (PIPE MATERIAL SPECIFICATION) | RESERVE BOILER |  |  |  | PMS (PIPE MATERIAL SPECIFICATION) for RESERVE BOILER | FinFan Cooler | Pipe Material Specification | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | specification | specification | specification | specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6314 | 0.6094 | 0.6094 | g_safe | [5 empty] | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 11 | 1 | 21.2319 | 0.6904 | 0.0305 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P8ZEN-125503 | RESERVE BOILER - LINE LIST | LINE LIST | RESERVE BOILER |  |  |  | LINE LIST for RESERVE BOILER | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5878 | 0.5263 | 0.5263 | g_safe | [5 empty] | FI | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | procurement | procurement | match | reserve_boiler | compressed_air | reserve_boiler | query | bop | mismatch | false | false | 21 | 11 | 8.5035 | 0.5778 | 0.0264 | 0.0066 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P8ZEN-125504 | RESERVE BOILER - VALVE LIST | VALVE LIST | RESERVE BOILER |  |  |  | Valve List for RESERVE BOILER |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7560 | 0.6935 | 0.6935 | g_safe | [5 empty] | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 6 | 4 | 22.3249 | 0.5992 | 0.0308 | 0.0185 | hybrid | structured_system_absent | reserve_boiler | procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P8ZEN-125505 | RESERVE BOILER - PIPING SPECIALITY DRAWING & LIST | DRAWING & LIST | RESERVE BOILER | PIPING |  |  | DRAWING & LIST for RESERVE BOILER |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6711 | 0.5513 | 0.5513 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 49 | 328 | 10.3393 | 0.4831 | 0.0118 | 0.0053 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125506 | RESERVE BOILER - MANUAL VALVE DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | MANUAL VALVE ASSEMBLY DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7880 | 0.7614 | 0.5330 | g_safe | [5 empty] | FA | 0PF7000W86A03T | (Control Valve) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2008-08-16 | 2008-09-30 | manual | delivery | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 14 | 58 | 7.5359 | 0.4712 | 0.0220 | 0.0099 | hybrid | structured_system_absent | reserve_boiler | delivery¦procurement¦installation |  | 2025-04-04 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-18 | 2025-07-18 | generated | 0.30 |  | false | false | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125507 | RESERVE BOILER - PIPING & PIPING SUPPORT PLAN DRAWING | DRAWING | RESERVE BOILER | PIPING |  |  | DRAWING for RESERVE BOILER | FireFighting | Piping Support DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6250 | 0.7125 | 0.7125 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 104 | 180 | 12.8493 | 0.5145 | 0.0103 | 0.0046 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125509 | RESERVE BOILER - PIPING SUPPORT DETAIL DRAWING FOR SMALL BORE PIPING. | DRAWING | RESERVE BOILER | PIPING |  |  | DRAWING for PIPING |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | piping¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6485 | 0.8946 | 0.6262 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | false | 325 | 5 | 7.8939 | 0.5152 | 0.0180 | 0.0034 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL30-P8ZEN-125514 | RESERVE BOILER - CONTROL VALVE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5196 | 0.5059 | 0.5059 | g_safe | [5 empty] | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 479 | 569 | 5.3193 | 0.4647 | 0.0034 | 0.0016 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125520 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6063 | 0.6019 | 0.6019 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 92 | 73 | 11.6136 | 0.5181 | 0.0141 | 0.0085 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125521 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦pump¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6016 | 0.6005 | 0.6005 | g_ambig | generic_ok | 0.85 |  | 1 | The only competing specific rule is explicitly for ACC drain pump lines, which is different equipment than a reserve boiler piping isometric. | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater¦reserve_boiler | compressed_air | feedwater¦reserve_boiler | query | feedwater | match | true | false | 1 | 1 | 8.4247 | 0.6315 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater¦reserve_boiler | system_design | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125522 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5968 | 0.5990 | 0.5990 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 32 | 38 | 18.6136 | 0.5438 | 0.0211 | 0.0126 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125523 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5957 | 0.5987 | 0.5987 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦steam | compressed_air | reserve_boiler¦steam | query | steam | match | true | false | 1 | 1 | 14.3151 | 0.6358 | 0.0328 | 0.0328 | hybrid | structured_preferred | reserve_boiler¦steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125524 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5935 | 0.5981 | 0.5981 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 92 | 263 | 11.6136 | 0.4990 | 0.0097 | 0.0058 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125525 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5874 | 0.5962 | 0.5962 | g_safe | [5 empty] | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 321 | 25 | 8.4723 | 0.5410 | 0.0144 | 0.0086 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125526 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5872 | 0.5962 | 0.5962 | g_safe | [5 empty] | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | ccw¦reserve_boiler¦service_water | compressed_air | ccw¦reserve_boiler¦service_water | query | service_water | match | true | false | 1 | 1 | 38.8077 | 0.6284 | 0.0328 | 0.0328 | hybrid | structured_preferred | ccw¦reserve_boiler¦service_water | system_design | 4 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125527 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6385 | 0.7515 | 0.7515 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler | compressed_air | compressed_air¦reserve_boiler | query | compressed_air | match | true | false | 1 | 1 | 24.3472 | 0.5604 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125530 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for DEAERATOR SYSTEM |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | deaerator¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7256 | 0.6377 | 0.6377 | g_safe | [5 empty] | FI | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | false | 327 | 1 | 6.4487 | 0.5631 | 0.0190 | 0.0036 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125531 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for Pump | FireFighting | Equipment (incl. pump) Detail DraWing | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump¦reserve_boiler | pump | scoped | match | match | match | passed |  | 0.3333 | 0.5981 | 0.4128 | 0.4128 | [6 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | feedwater¦reserve_boiler |  | feedwater¦reserve_boiler | query | feedwater | match | true | false | 1 | 1 | 8.4247 | 0.6253 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater¦reserve_boiler | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125532 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for BOILER WATER SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve_boiler¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5304 | 0.6258 | 0.6258 | g_safe | [5 empty] | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 34 | 45 | 18.6136 | 0.5349 | 0.0202 | 0.0091 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125533 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for BOILER STEAM SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve_boiler¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5272 | 0.6248 | 0.6248 | g_safe | [5 empty] | FI | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler¦steam |  | reserve_boiler¦steam | query | steam | match | true | false | 1 | 1 | 14.3151 | 0.6221 | 0.0328 | 0.0246 | hybrid | structured_preferred | reserve_boiler¦steam | system_design¦civil_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125534 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for BURNER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | burner¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6308 | 0.8892 | 0.6225 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | false | 327 | 1 | 6.4487 | 0.5565 | 0.0190 | 0.0036 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125535 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for BLOWDOWN SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | blowdown¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5294 | 0.6255 | 0.6255 | g_safe | [5 empty] | FI | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 325 | 24 | 8.4723 | 0.5367 | 0.0145 | 0.0065 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125536 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for CLOSED COOLING WATER & SERVICE WATER SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | closed¦cooling¦reserve_boiler¦service¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5312 | 0.6260 | 0.6260 | g_safe | [5 empty] | FI | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | ccw¦reserve_boiler¦service_water |  | ccw¦reserve_boiler¦service_water | query | service_water | match | true | false | 1 | 1 | 38.8077 | 0.6128 | 0.0328 | 0.0246 | hybrid | structured_preferred | ccw¦reserve_boiler¦service_water | system_design¦civil_design | 10 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125537 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for SERVICE AIR & SEALING AIR SYSTEM |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦reserve_boiler¦sealing¦service |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.6275 | g_safe | [5 empty] | FI | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible | compressed_air¦reserve_boiler |  | compressed_air¦reserve_boiler | query | compressed_air | match | true | false | 1 | 1 | 24.3472 | 0.5478 | 0.0328 | 0.0246 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design¦civil_design | 10 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125540 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6156 | 0.6047 | 0.6047 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 92 | 58 | 11.6136 | 0.5264 | 0.0151 | 0.0090 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125541 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦pump¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6105 | 0.6031 | 0.6031 | g_ambig | generic_ok | 0.85 |  | 1 | The only competing specific rule is explicitly for ACC drain pump lines, which is different equipment than a reserve boiler piping isometric. | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater¦reserve_boiler | compressed_air | feedwater¦reserve_boiler | query | feedwater | match | true | false | 1 | 1 | 8.4247 | 0.6419 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater¦reserve_boiler | system_design | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125542 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6092 | 0.6028 | 0.6028 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 32 | 39 | 18.6136 | 0.5488 | 0.0210 | 0.0126 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125543 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6079 | 0.6024 | 0.6024 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦steam | compressed_air | reserve_boiler¦steam | query | steam | match | true | false | 1 | 1 | 14.3151 | 0.6463 | 0.0328 | 0.0328 | hybrid | structured_preferred | reserve_boiler¦steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125544 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(COMBUSTION AIR & FLUE GAS SYSTEM) | DRAWING | RESERVE BOILER | COMBUSTION Air and Flue Gas System |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6327 | 0.7498 | 0.7498 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query | compressed_air | mismatch | false | false | 66 | 26 | 19.0013 | 0.5583 | 0.0196 | 0.0049 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125545 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6085 | 0.6026 | 0.6026 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 92 | 225 | 11.6136 | 0.5015 | 0.0101 | 0.0061 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125546 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6003 | 0.6001 | 0.6001 | g_safe | [5 empty] | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 321 | 18 | 8.4723 | 0.5468 | 0.0154 | 0.0093 | hybrid | structured_system_absent | reserve_boiler | system_design |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125547 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CHEMICAL DOSING SYSTEM) | DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6044 | 0.6013 | 0.6013 | g_safe | [5 empty] | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦wts | compressed_air | reserve_boiler¦wts | query | wts | match | true | false | 1 | 1 | 38.6097 | 0.6565 | 0.0328 | 0.0328 | hybrid | structured_preferred | reserve_boiler¦wts | system_design | 5 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125548 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5972 | 0.5992 | 0.5992 | g_safe | [5 empty] | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | ccw¦reserve_boiler¦service_water | compressed_air | ccw¦reserve_boiler¦service_water | query | service_water | match | true | false | 1 | 1 | 38.8077 | 0.6281 | 0.0328 | 0.0328 | hybrid | structured_preferred | ccw¦reserve_boiler¦service_water | system_design | 4 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125549 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(INSTRUMENT AIR SYSTEM) | DRAWING | RESERVE BOILER | INSTRUMENT AIR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6597 | 0.7579 | 0.7579 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler | compressed_air | compressed_air¦reserve_boiler | query | compressed_air | match | true | false | 1 | 1 | 16.5618 | 0.5889 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125550 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for RESERVE BOILER | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6513 | 0.7554 | 0.7554 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler | compressed_air | compressed_air¦reserve_boiler | query | compressed_air | match | true | false | 1 | 1 | 24.3472 | 0.5611 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125570 | RESERVE BOILER_ FUEL SKID DETAIL DRAWING | Detail Drawing | RESERVE BOILER |  |  |  | Detail Drawing for RESERVE BOILER |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5311 | 0.6260 | 0.6260 | g_safe | [5 empty] | FI | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | false | 479 | 8 | 5.4788 | 0.5536 | 0.0166 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG05-P8ZEN-125571 | RESERVE BOILER - HEAT & MASS BLANCE DIAGRAM | Diagram | RESERVE BOILER |  |  |  | Diagram for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5980 | 0.4127 | 0.2889 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query | hrsg | mismatch | false | false | 4 | 5 | 12.1052 | 0.5357 | 0.0310 | 0.0058 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125582 | RESERVE BOILER - P&ID OF DEAERATOR SYSTEM | P&ID | RESERVE BOILER | DEAERATOR SYSTEM |  |  | P&ID for DEAERATOR SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | deaerator¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6635 | 0.4324 | 0.4324 | g_safe | [5 empty] | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 4 | 31 | 18.6333 | 0.5697 | 0.0266 | 0.0160 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125583 | RESERVE BOILER - P&ID OF FEEDWATER PUMP SYSTEM | P&ID | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | P&ID for FEEDWATER PUMP SYSTEM | Boiler Feed Pump | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | p_id | p_id | feedwater¦pump¦reserve_boiler | pump | scoped | match | match | match | passed |  | 0.7500 | 0.7649 | 0.7545 | 0.7545 | [6 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater¦reserve_boiler | feedwater | feedwater¦reserve_boiler | query | feedwater | match | true | false | 56 | 7 | 17.4373 | 0.6872 | 0.0235 | 0.0235 | hybrid | structured_blocked_procurement_conflict | feedwater¦reserve_boiler | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125584 | RESERVE BOILER - P&ID OF BOILER WATER SYSTEM | P&ID | RESERVE BOILER | BOILER WATER SYSTEM |  |  | P&ID for BOILER WATER SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | boiler¦reserve_boiler¦water |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6915 | 0.4408 | 0.4408 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 2 | 21 | 27.6262 | 0.5852 | 0.0285 | 0.0171 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125585 | RESERVE BOILER - P&ID OF BOILER STEAM SYSTEM | P&ID | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | P&ID for BOILER STEAM SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | boiler¦reserve_boiler¦steam |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6935 | 0.4414 | 0.4414 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦steam |  | reserve_boiler¦steam | query | steam | match | true | false | 2 | 2 | 23.7633 | 0.6907 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦steam | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125586 | RESERVE BOILER - P&ID OF COMBUSTION AIR & FLUE GAS SYSTEM | P&ID | RESERVE BOILER | COMBUSTION Air and Flue Gas System |  |  | P&ID for COMBUSTION Air and Flue Gas System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | air¦combustion¦flue¦gas¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6353 | 0.4239 | 0.4239 | g_safe | [5 empty] | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 52 | 40 | 26.9565 | 0.5681 | 0.0189 | 0.0114 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.33 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125587 | RESERVE BOILER - P&ID OF BURNER & FUEL GAS SYSTEM | P&ID | RESERVE BOILER | FUEL GAS SYSTEM |  |  | P&ID for FUEL GAS SYSTEM | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fgp¦fuel¦gas¦reserve_boiler | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8032 | 0.7660 | 0.7660 | [6 empty] | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | fgp¦reserve_boiler | fgp | fgp¦reserve_boiler | query | fgp | match | true | false | 2 | 1 | 26.2979 | 0.6670 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp¦reserve_boiler | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125588 | RESERVE BOILER - P&ID OF BLOWDOWN SYSTEM | P&ID | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | P&ID for BLOWDOWN SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | blowdown¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6684 | 0.4338 | 0.4338 | g_safe | [5 empty] | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 23 | 13 | 17.4850 | 0.5810 | 0.0257 | 0.0154 | hybrid | structured_system_absent | reserve_boiler | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125589 | RESERVE BOILER - P&ID OF SAMPLING SYSTEM | P&ID | RESERVE BOILER | SAMPLING SYSTEM |  |  | P&ID for SAMPLING SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | reserve_boiler¦sampling |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6751 | 0.4359 | 0.4359 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | reserve_boiler¦sampling |  | reserve_boiler¦sampling | query | sampling | match | true | false | 1 | 1 | 34.9512 | 0.6522 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦sampling | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125590 | RESERVE BOILER - P&ID OF CHEMICAL DOSING SYSTEM | P&ID | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | P&ID for CHEMICAL DOSING SYSTEM | Chemical Dosing System | P&ID | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | p_id | p_id | chemical¦dosing¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8992 | 0.9698 | 0.9698 | g_safe | [5 empty] | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler¦wts | wts | reserve_boiler¦wts | query | wts | match | true | false | 1 | 1 | 47.4860 | 0.6938 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125591 | RESERVE BOILER - P&ID OF CLOSED COOLING WATER & SERVICE WATER SYSTEM | P&ID | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | P&ID for CLOSED COOLING WATER & SERVICE WATER SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | closed¦cooling¦reserve_boiler¦service¦water |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6214 | 0.4198 | 0.4198 | g_safe | [5 empty] | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | ccw¦reserve_boiler¦service_water |  | ccw¦reserve_boiler¦service_water | query | service_water | match | true | false | 1 | 1 | 48.2559 | 0.6383 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | ccw¦reserve_boiler¦service_water | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125592 | RESERVE BOILER - P&ID OF INSTRUMENT AIR SYSTEM | P&ID | RESERVE BOILER | INSTRUMENT AIR SYSTEM |  |  | P&ID for INSTRUMENT AIR SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | air¦instrument¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6788 | 0.4370 | 0.4370 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler |  | compressed_air¦reserve_boiler | query | compressed_air | match | true | false | 1 | 1 | 25.8602 | 0.6296 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design¦procurement | 10 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125593 | RESERVE BOILER - P&ID OF SERVICE AIR & SEALING AIR SYSTEM | P&ID | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | P&ID for SERVICE AIR & SEALING AIR SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | air¦reserve_boiler¦sealing¦service |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6313 | 0.4227 | 0.4227 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air¦reserve_boiler |  | compressed_air¦reserve_boiler | query | compressed_air | match | true | false | 1 | 1 | 33.6456 | 0.5991 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air¦reserve_boiler | system_design¦procurement | 10 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR01-P8ZEN-125597 | METHODS STATEMENTS OF STEAM FLUSHING FOR RESERVE BOILER |  | RESERVE BOILER |  |  |  | for RESERVE BOILER | [5 empty] | rule_query | other | diagram | methods_statements_of_steam_flushing_for_reserve_boiler | p_id | boiler¦reserve¦reserve_boiler | pump | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.2500 | 0.5144 | 0.3293 | 0.3293 | [7 empty] | 2CF1615W62A19 | (HRSG #21) Diverter Damper Control Unit Flushing | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2008-07-08 | 2008-07-24 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | true | false | 11 | 1 | 8.6797 | 0.5553 | 0.0305 | 0.0057 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125601 | RESERVE BOILER - F.D FAN DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FAN STACK DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5903 | 0.6438 | 0.4506 | g_safe | [5 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | condensate¦fgp | mismatch | false | false | 186 | 12 |  | 0.5167 | 0.0180 | 0.0034 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125602 | RESERVE BOILER - BURNER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Burner Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5555 | 0.8666 | 0.6067 | g_safe | [5 empty] | FA | 3EF1625W00A02.1 | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | 2007-08-01 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3928 | 2 |  | 0.5335 | 0.0164 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125604 | RESERVE BOILER - BFP DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | g_safe | [5 empty] | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | true | false | 990 | 4 |  | 0.5325 | 0.0166 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125605 | RESERVE BOILER - DEAERATOR WITH STORAGE TANK DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Tank DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler¦tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.5124 | 0.6204 | 0.4343 | [6 empty] | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | wts | mismatch | true | false | 9 | 15 | 16.4358 | 0.5122 | 0.0278 | 0.0052 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125606 | RESERVE BOILER - SILENCER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Silencer Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6205 | 0.8862 | 0.6203 | g_safe | [5 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3826 | 46 |  | 0.5189 | 0.0097 | 0.0018 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125607 | RESERVE BOILER - SAMPLING SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | SAMPLING SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Sampling System Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6786 | 0.9036 | 0.6325 | g_safe | [5 empty] | FA | 1EF3040W16A02 | (Sampling Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2008-01-01 | 2008-04-02 | design_drawing | civil_design | compatible | reserve_boiler¦sampling | sampling | reserve_boiler¦sampling | query | sampling | match | true | false | 1 | 3 | 18.5328 | 0.4693 | 0.0323 | 0.0242 | hybrid | structured_preferred | reserve_boiler¦sampling | system_design¦civil_design | 7 | 2024-08-19 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-11-02 | 2024-12-02 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125608 | RESERVE BOILER - CHEMICAL DOSING SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER | Chemical Dosing System | Piping Arrangement DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7101 | 0.6797 | 0.6797 | g_safe | [5 empty] | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler¦wts | wts | reserve_boiler¦wts | query | wts | match | true | false | 4 | 4 | 33.6657 | 0.6539 | 0.0312 | 0.0234 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦wts | system_design¦civil_design |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125609 | RESERVE BOILER - MONORAIL HOIST DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Monorail Hoist Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7286 | 0.9186 | 0.6430 | g_safe | [5 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler | crane_hoist | reserve_boiler | query | hrsg | mismatch | false | false | 3814 | 1 |  | 0.5184 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125610 | RESERVE BOILER - SRV DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3792 | 1 |  | 0.5456 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125611 | RESERVE BOILER - BLOWDOWN TANK DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | HRSG - Spec. & DraWing for BloWDoWn Tank Pump | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler¦tank | hrsg¦pump¦tank | scoped | match | match | match | passed |  | 0.4286 | 0.7259 | 0.5178 | 0.5178 | [6 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler | hrsg | reserve_boiler | query | hrsg | mismatch | false | false | 634 | 143 | 2.0974 | 0.5212 | 0.0064 | 0.0012 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125612 | RESERVE BOILER - LEVEL GAUGE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | LEVEL REINFORCEMENT DRAWING BASEMAT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4512 | 0.4853 | 0.3397 | g_safe | [5 empty] | FA | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3849 | 1 |  | 0.5304 | 0.0166 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125614 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR F.D FAN | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5337 | 0.6268 | 0.6268 | g_safe | [5 empty] | SKIP | 3EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | false | 686 | 1 | 4.4703 | 0.5952 | 0.0177 | 0.0044 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125615 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BOILER FEED WATER PUMP | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | Boiler Feed Pump | 3D Modeling DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | boiler¦pump¦reserve¦reserve_boiler | pump | scoped | match | match | match | passed |  | 0.3333 | 0.5895 | 0.4102 | 0.4102 | [6 empty] | FA | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | civil_design | civil_design | match | reserve_boiler | feedwater | reserve_boiler | query |  | activity_unscoped | true | true | 68 | 27 | 12.2665 | 0.5493 | 0.0193 | 0.0116 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125616 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR FUEL SKID | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5383 | 0.6282 | 0.6282 | g_safe | [5 empty] | SKIP | 0EF3520W00A10.3 | (FO FWD Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | false | 196 | 4 | 7.6594 | 0.5848 | 0.0195 | 0.0049 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125617 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR SAMPLING SYSTEM | DRAWING | RESERVE BOILER | SAMPLING SYSTEM |  |  | DRAWING for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5295 | 0.6255 | 0.6255 | g_safe | [5 empty] | SKIP | 1EF3040W16A02 | (Sampling Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2008-01-01 | 2008-04-02 | civil_design | civil_design | match | reserve_boiler¦sampling |  | reserve_boiler¦sampling | query | sampling | match | true | false | 1 | 3 | 20.7130 | 0.5173 | 0.0323 | 0.0323 | hybrid | structured_preferred | reserve_boiler¦sampling | civil_design | 6 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125618 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR CHEMICAL DOSING SYSTEM | DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DRAWING for RESERVE BOILER | Chemical Dosing System | Piping Arrangement DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7111 | 0.6800 | 0.6800 | g_safe | [5 empty] | FI | 2EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | 2007-09-26 |  | civil_design | civil_design | match | reserve_boiler¦wts | wts | reserve_boiler¦wts | query | wts | match | true | false | 5 | 1 | 35.3086 | 0.6594 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | reserve_boiler¦wts | civil_design |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125619 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BLOW DOWN TANK | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | HRSG - FounDation LoaDing & Location DraWing for BloWDoWn Tank | 1 | start+103D<=FA<=start+103D+2M | FA ∈ [start+103d, start+163d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler¦tank | hrsg¦tank | scoped | match | match | match | passed |  | 0.6250 | 0.7972 | 0.6767 | 0.6767 | [6 empty] | FA | 3EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | reserve_boiler | hrsg | reserve_boiler | query | feedwater | mismatch | false | false | 714 | 1 | 4.4703 | 0.5779 | 0.0177 | 0.0044 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125620 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR ELECTRICAL & CONTROL ROOM | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER | Substation | Foundation DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | drawing | drawing | boiler¦ccr¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5851 | 0.6422 | 0.6422 | g_safe | [5 empty] | SKIP | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 123 | 31 | 8.9442 | 0.5552 | 0.0165 | 0.0099 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8SGK-125650 | RESERVE BOILER_ FM GAS SYSTEM CALCULATION & DOCUMENT | CALCULATION & DOCUMENT | RESERVE BOILER | FM GAS SYSTEM |  |  | CALCULATION & DOCUMENT for RESERVE BOILER |  | Gas HTR Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5486 | 0.5146 | 0.5146 | g_safe | [5 empty] | FA | 1EF3520W16A01 | (GPRS) FDN Design for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-08-02 | 2007-10-16 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | fgp¦gtg | mismatch | false | false | 63 | 8 | 4.1061 | 0.5687 | 0.0228 | 0.0057 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS01-P8ZEN-125700 | RESERVE BOILER - OPERATION PHILOSOPHY | PHILOSOPHY | RESERVE BOILER |  |  |  | PHILOSOPHY for RESERVE BOILER | [5 empty] | rule_query | other | other | philosophy | gt_design_philosophy_for_emergency_air_system | boiler¦reserve¦reserve_boiler | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.2857 | 0.4734 | 0.3420 | 0.3420 | [7 empty] | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 1 | 9 | 25.1097 | 0.4704 | 0.0309 | 0.0139 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P8ZEN-125701 | RESERVE BOILER - CONTROL SYSTEM CONFIGURATION |  | RESERVE BOILER | CONTROL SYSTEM |  |  | for RESERVE BOILER | [5 empty] | rule_query | other | diagram | reserve_boiler_control_system_configuration | p_id | boiler¦reserve¦reserve_boiler | pump | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.2500 | 0.5144 | 0.3293 | 0.3293 | [7 empty] | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | steam | mismatch | false | false | 662 | 5 | 1.1861 | 0.5397 | 0.0168 | 0.0042 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125702 | RESERVE BOILER - BMS SPECIFICATION | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | g_safe | [5 empty] | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | false | 1 | 10 | 16.3955 | 0.4832 | 0.0307 | 0.0077 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125703 | RESERVE BOILER - BMS I/O LIST | Input / Output LIST | RESERVE BOILER |  |  |  | I/O List for RESERVE BOILER | [5 empty] | rule_query | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | match | match | mismatch | rejected | scope_mismatch | 0.5000 | 0.6729 | 0.5519 | 0.5519 | [7 empty] | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | false | 3 | 9 | 16.3955 | 0.4700 | 0.0304 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125704 | RESERVE BOILER - BCS I/O LIST | Input / Output LIST | RESERVE BOILER |  |  |  | I/O List for RESERVE BOILER | [5 empty] | rule_query | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | match | match | mismatch | rejected | scope_mismatch | 0.5000 | 0.6729 | 0.5519 | 0.5519 | [7 empty] | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | false | 3 | 9 | 16.3955 | 0.4664 | 0.0304 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125705 | RESERVE BOILER - VMS I/O LIST | Input / Output LIST | RESERVE BOILER | Vibration Monitoring System |  |  | I/O List for RESERVE BOILER | [5 empty] | rule_query | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | match | match | mismatch | rejected | scope_mismatch | 0.5000 | 0.6729 | 0.5519 | 0.5519 | [7 empty] | 1PF1260W86A02P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-05-01 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | gtg | mismatch | false | false | 2 | 5 | 25.1569 | 0.5752 | 0.0315 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125706 | RESERVE BOILER - DATALINK I/O LIST | Input / Output LIST | RESERVE BOILER |  |  |  | I/O List for RESERVE BOILER | Air Compressor | Datalink interface IO List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | io_list | io_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6409 | 0.4256 | 0.4256 | g_safe | [5 empty] | FI | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | procurement | procurement | match | reserve_boiler | compressed_air | reserve_boiler | query | hrsg | mismatch | false | false | 11 | 2 | 11.5018 | 0.5214 | 0.0302 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P8ZEN-125707 | RESERVE BOILER - INSTRUMENT LIST | LIST | RESERVE BOILER |  |  |  | Instrument List for RESERVE BOILER | FireFighting | Instrument List | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | list | list | instrument_list | instrument_list | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6778 | 0.6700 | 0.6700 | g_safe | [5 empty] | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 5 | 45 | 15.9566 | 0.5591 | 0.0249 | 0.0149 | hybrid | structured_system_absent | reserve_boiler | procurement |  | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P8ZEN-125708 | RESERVE BOILER - ALARM AND TRIP SETTING LIST | LIST | RESERVE BOILER |  |  |  | LIST for RESERVE BOILER | [5 empty] | rule_query | other | list | list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.5000 | 0.5269 | 0.5081 | 0.5081 | [7 empty] | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 2 | 5 | 22.6729 | 0.4745 | 0.0315 | 0.0059 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125709 | RESERVE BOILER - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | RESERVE BOILER |  |  |  | Control Logic Diagram for RESERVE BOILER | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6985 | 0.7345 | 0.7345 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 8 | 301 | 14.8839 | 0.4823 | 0.0175 | 0.0105 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125710 | RESERVE BOILER - CONTROL LOOP DIAGRAM | CONTROL LOOP DIAGRAM | RESERVE BOILER |  |  |  | Control Loop Diagram for RESERVE BOILER | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7519 | 0.7506 | 0.7506 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 15 | 228 | 14.8839 | 0.5010 | 0.0168 | 0.0101 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125711 | RESERVE BOILER - BMS LOGIC DIAGRAM | LOGIC DIAGRAM | RESERVE BOILER |  |  |  | LOGIC DIAGRAM for RESERVE BOILER |  | Logic & Loop Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6023 | 0.6474 | 0.6474 | g_ambig | use_specific | 0.72 | Auxiliary Boiler – PoWer Cable Connection Diagram | 1 | Reserve boiler is an auxiliary boiler, so the auxiliary-boiler-specific logic/wiring rule should override the generic logic diagram timeline. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 4 | 305 | 14.8839 | 0.4848 | 0.0184 | 0.0110 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125713 | RESERVE BOILER - MOV DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | g_safe | [5 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3814 | 5 |  | 0.5033 | 0.0156 | 0.0029 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125714 | RESERVE BOILER - TRANSMITTER SPECIFICATION | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | g_safe | [5 empty] | FA | 0EF7000W86A01 | (Control Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves |  | 2007-06-28 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 8 | 131 | 7.8774 | 0.4503 | 0.0199 | 0.0120 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125715 | RESERVE BOILER - LOCAL GAUGE SPECIFICATION | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | g_safe | [5 empty] | FA | 1EF1600W74A05.1 | (HRSG #12 LEB) MPS Issue - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB |  | 2007-06-15 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3 | 52 | 10.7369 | 0.4552 | 0.0248 | 0.0062 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125716 | RESERVE BOILER - TEMP. ELEMENT SPECIFICATION | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | g_safe | [5 empty] | FA | 1EF3030W42A01 | (Temp. Cooling Tower) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower |  | 2007-10-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | ccw | mismatch | true | false | 2 | 1 | 13.9920 | 0.4746 | 0.0325 | 0.0081 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125717 | RESERVE BOILER - FLOW ELEMENT SPECIFICATION | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER | FloW element | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6483 | 0.4945 | 0.4945 | g_safe | [5 empty] | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 9 | 2 | 10.1928 | 0.5666 | 0.0306 | 0.0077 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125718 | RESERVE BOILER - REMOTE DRUM LEVEL INDICATOR SPECIFICATION | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | g_safe | [5 empty] | FA | 1EF1645W42A02 | (HRSG #11 Drum) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | 2007-05-15 |  | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | true | false | 2 | 8 | 16.0544 | 0.4435 | 0.0308 | 0.0077 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125719 | RESERVE BOILER - AIR OPERATED VALVE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER | Air Compressor | Instrument Installation DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5791 | 0.4537 | 0.4537 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler | compressed_air | reserve_boiler | query |  | activity_unscoped | true | true | 88 | 517 | 8.0946 | 0.4666 | 0.0085 | 0.0038 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P8ZEN-125720 | RESERVE BOILER - INSTRUMENT INSTALLATION DETAIL DRAWING | DRAWING | RESERVE BOILER | INSTRUMENT INSTALLATION MATERIAL |  |  | DRAWING for INSTRUMENT INSTALLATION MATERIAL | FinFan Cooler | Instrument Installation Detail DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | detail_drawing | detail_drawing | installation¦instrument¦material¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6540 | 0.6629 | 0.6629 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 488 | 329 | 5.3193 | 0.5040 | 0.0044 | 0.0020 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YM03-P8ZEN-125721 | RESERVE BOILER - INSTRUMENT LOCATION DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6060 | 0.6485 | 0.6485 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 520 | 21 | 2.0974 | 0.5547 | 0.0141 | 0.0026 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125722 | RESERVE BOILER - TRANSMITTER CALIBRATION SHEET | SHEET | RESERVE BOILER |  |  |  | SHEET for RESERVE BOILER | [5 empty] | rule_query | other | calculation | sheet | calculation | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.3333 | 0.5893 | 0.4101 | 0.4101 | [7 empty] | 1SF3520W62A14 | (FGSS #12) Metering System Calibration with supplier | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2008-09-24 | 2008-09-28 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | electrical¦fgp | mismatch | true | false | 2 | 6 | 9.0842 | 0.5144 | 0.0313 | 0.0059 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125723 | RESERVE BOILER - FLOW ELEMENT CALIBRATION SHEET | SHEET | RESERVE BOILER |  |  |  | SHEET for RESERVE BOILER | [5 empty] | rule_query | other | calculation | sheet | calculation | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.3333 | 0.5893 | 0.4101 | 0.4101 | [7 empty] | 0EF1000W00A01 | Heat Balance Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-07-02 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 27 | 77 |  | 0.4564 | 0.0188 | 0.0085 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125724 | RESERVE BOILER - MONITOR SCREEN DIAGRAM | MONITOR SCREEN DIAGRAM | RESERVE BOILER |  |  |  | MONITOR SCREEN DIAGRAM for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5545 | 0.3997 | 0.2798 | [6 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query |  | activity_unscoped | true | true | 15 | 42 | 9.8679 | 0.4558 | 0.0231 | 0.0104 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125725 | RESERVE BOILER - GAS LEAK DETECTION SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | GAS LEAK DETECTION SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | g_safe | [5 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | false | false | 46 | 8 | 4.1389 | 0.5458 | 0.0241 | 0.0045 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125726 | RESERVE BOILER - O2 ANALYZER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Name Plate DraWing of Boiler Proper | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7059 | 0.4451 | 0.3116 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 3792 | 1 |  | 0.5345 | 0.0167 | 0.0031 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125727 | RESERVE BOILER - CEMS DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | Continuous Emissions Monitoring System |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | HRSG - SPEC. & DraWing for CEMS | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | title | drawing | drawing | drawing | drawing | boiler¦cems¦reserve¦reserve_boiler | cems¦hrsg | scoped | match | match | match | passed |  | 0.4000 | 0.7203 | 0.4961 | 0.4961 | [6 empty] | FA | 1EF1660W16A01 | (CEMS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | 2007-10-30 | 2008-01-25 | design_drawing | civil_design | compatible | cems¦reserve_boiler | cems¦hrsg | cems¦reserve_boiler | query | cems¦hrsg | match | true | false | 1 | 6 | 26.2416 | 0.6296 | 0.0315 | 0.0237 | hybrid | structured_preferred | cems¦reserve_boiler | system_design¦civil_design | 10 | 2025-07-12 | 2025-08-11 | 2025-09-10 | 2025-09-25 | 2025-10-10 | 2025-10-25 | generated | 0.90 |  | false | false | 0.57 | usable | default_fc_window;rule_score_medium;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125728 | RESERVE BOILER - CONTROL ROOM & ELECTRICAL ROOM ARRANGEMENT DRAWING | General Arrangement Drawing | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦ccr¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7032 | 0.9110 | 0.9110 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 1345 | 5 | 2.0974 | 0.5699 | 0.0161 | 0.0040 | hybrid | structured_system_absent | reserve_boiler | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XF00-P8ZEN-125729 | RESERVE BOILER - JUNCTION BOX DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Motor Terminal box draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6025 | 0.5308 | 0.5308 | g_safe | [5 empty] | FA | 1EF3020W16A09 | (COND Flash Box) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-01-02 | 2008-03-31 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | condensate | mismatch | false | false | 36 | 609 | 8.1584 | 0.4536 | 0.0119 | 0.0022 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P8ZEN-125731 | RESERVE BOILER - I&C CABLE SCHEDULE | Schedule | RESERVE BOILER |  |  |  | Schedule for RESERVE BOILER | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6143 | 0.6510 | 0.6510 | g_safe | [5 empty] | SKIP | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-10-02 | 2008-08-04 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 7 | 1 | 12.4890 | 0.5881 | 0.0313 | 0.0078 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P8ZEN-125732 | RESERVE BOILER - I&C CABLE CONNECTION DIAGRAM | Diagram | RESERVE BOILER |  |  |  | Diagram for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5980 | 0.4127 | 0.2889 | [6 empty] | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query |  | activity_unscoped | true | true | 12 | 80 | 10.1910 | 0.4703 | 0.0210 | 0.0095 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125734 | RESERVE BOILER - BCS SPECIFICATION | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | g_safe | [5 empty] | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | false | 1 | 11 | 16.3955 | 0.4605 | 0.0305 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125735 | RESERVE BOILER - HAZARDOUS AREA CLASSFICATION | CLASSFICATION | RESERVE BOILER |  |  |  | CLASSFICATION for RESERVE BOILER | [5 empty] | rule_query | other | drawing | classfication | drawing | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.2500 | 0.5243 | 0.3323 | 0.3323 | [7 empty] | 0EF1600W14A10 | HRSG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-06-15 |  | civil_design | query_unknown | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 4 | 293 | 7.2263 | 0.4085 | 0.0185 | 0.0035 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125737 | RESERVE BOILER _ VMS SPECIFICATION | Technical Specification | RESERVE BOILER | Vibration Monitoring System |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5201 | 0.6227 | 0.4359 | g_safe | [5 empty] | FA | 1EF1260W86A01.1 | (VMS) MPS Issue for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) |  | 2007-05-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | gtg | mismatch | false | false | 2 | 2 | 29.0733 | 0.6024 | 0.0323 | 0.0081 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125749 | RESERVE BOILER - MOTOR LIST | LIST | RESERVE BOILER |  |  |  | LIST for RESERVE BOILER | [5 empty] | rule_query | other | list | list | io_list | boiler¦reserve¦reserve_boiler | hrsg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.5000 | 0.5269 | 0.5081 | 0.5081 | [7 empty] | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 2 | 4 | 22.6729 | 0.4813 | 0.0318 | 0.0060 | hybrid | structured_no_phase | reserve_boiler | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125750 | RESERVE BOILER - POWER DISTRIBUTION PANEL DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | POWER SUPPLY DISTRIBUTION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7332 | 0.7450 | 0.5215 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 2011 | 1 | 0.0002 | 0.5658 | 0.0169 | 0.0032 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P8ZEN-125751 | RESERVE BOILER - RACEWAY PLAN DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6005 | 0.8802 | 0.8802 | g_safe | [5 empty] | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 9 | 3155 | 12.0304 | 0.3415 | 0.0148 | 0.0067 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P8ZEN-125752 | RESERVE BOILER - RACEWAY DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5448 | 0.6301 | 0.6301 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 504 | 138 | 2.0974 | 0.5113 | 0.0068 | 0.0013 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125754 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR MCC | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5533 | 0.6327 | 0.4429 | g_safe | [5 empty] | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 11 | 1 | 10.4900 | 0.5037 | 0.0305 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P8ZEN-125755 | RESERVE BOILER - MCC SINGLE LINE DIAGRAM | Single Line Diagram | RESERVE BOILER |  |  |  | Single Line Diagram for RESERVE BOILER |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7137 | 0.9141 | 0.9141 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 11 | 177 | 14.8839 | 0.4972 | 0.0183 | 0.0110 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P8ZEN-125756 | RESERVE BOILER - MCC SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM | RESERVE BOILER |  |  |  | SCHEMATIC DIAGRAM for RESERVE BOILER |  | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6055 | 0.6483 | 0.6483 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 4 | 89 | 14.8839 | 0.5205 | 0.0223 | 0.0101 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125757 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLE | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5819 | 0.6412 | 0.4489 | g_safe | [5 empty] | FA | 1EF6040W74A05 | (EHV Cable) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable |  | 2007-05-01 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | electrical | mismatch | true | false | 2 | 5 | 15.0390 | 0.4462 | 0.0315 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125758 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5742 | 0.6389 | 0.4472 | g_safe | [5 empty] | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | bop | mismatch | false | false | 10 | 2 | 10.4900 | 0.4768 | 0.0304 | 0.0076 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125759 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR FIRE STOP MATERIALS | Technical Specification | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5338 | 0.6268 | 0.4388 | g_safe | [5 empty] | FA | 0EF4500W38A02 | (Fire Fighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | fire_fighting¦hvac | mismatch | true | false | 4 | 3 | 13.8924 | 0.4713 | 0.0315 | 0.0079 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P8ZEN-125760 | RESERVE BOILER - POWER CABLE SCHEDULE | Schedule | RESERVE BOILER |  |  |  | Schedule for RESERVE BOILER | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6270 | 0.6548 | 0.6548 | g_safe | [5 empty] | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | electrical | mismatch | true | false | 5 | 18 | 15.3884 | 0.5399 | 0.0282 | 0.0071 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P8ZEN-125761 | RESERVE BOILER - POWER CABLE CONNECTION DIAGRAM | Diagram | RESERVE BOILER |  |  |  | Diagram for RESERVE BOILER |  | Auxiliary Boiler – PoWer Cable Connection Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | boiler¦reserve¦reserve_boiler | reserve_boiler | scoped | match | match | match | passed |  | 0.3333 | 0.5980 | 0.4127 | 0.2889 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | reserve_boiler | reserve_boiler | reserve_boiler | query | steam | mismatch | false | false | 14 | 10 | 10.0271 | 0.4742 | 0.0278 | 0.0052 | hybrid | structured_system_absent | reserve_boiler | system_design¦engineering | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P8ZEN-125762 | RESERVE BOILER - EMBEDDED CONDUIT LAYOUT DRAWING | Layout Drawing | RESERVE BOILER |  |  |  | Layout Drawing for RESERVE BOILER |  | EMBEDDED CONDUIT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7644 | 0.9293 | 0.6505 | g_safe | [5 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 2 | 1803 | 24.0608 | 0.3676 | 0.0167 | 0.0100 | hybrid | structured_system_absent | reserve_boiler | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125763 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR LIGHTING SYSTEM | Technical Specification | RESERVE BOILER | LIGHTING SYSTEM |  |  | Technical Specification for RESERVE BOILER |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5738 | 0.6388 | 0.4472 | g_safe | [5 empty] | FA | 0EF6040W70A01 | (Lighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System |  | 2007-05-30 | procurement | procurement | match | reserve_boiler |  | reserve_boiler | query | electrical | mismatch | true | false | 1 | 1 | 35.8808 | 0.5113 | 0.0328 | 0.0082 | hybrid | structured_system_absent | reserve_boiler | procurement | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125764 | RESERVE BOILER - ILLUMINATION CALCULATION | Calculation sheet | RESERVE BOILER |  |  |  | Calculation sheet for RESERVE BOILER | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5375 | 0.5112 | 0.5112 | g_safe | [5 empty] | FA | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 678 | 96 |  | 0.4533 | 0.0078 | 0.0047 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P8ZEN-125765 | RESERVE BOILER - LIGHTING LAYOUT DRAWING | Layout Drawing | RESERVE BOILER | LIGHTING |  |  | Layout Drawing for LIGHTING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7105 | 0.7382 | 0.7382 | g_safe | [5 empty] | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 6 | 2220 | 24.0608 | 0.3695 | 0.0156 | 0.0070 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125766 | RESERVE BOILER - AIRCRAFT WARNING LIGHT DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | Aircraft Warning Light DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7190 | 0.9157 | 0.6410 | g_safe | [5 empty] | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query | compressed_air | mismatch | false | false | 411 | 1 |  | 0.4850 | 0.0185 | 0.0035 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P8ZEN-125767 | RESERVE BOILER - EARTHING DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | EARTHING |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Earthing Concept – DraWing Document | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6049 | 0.7065 | 0.4945 | g_safe | [5 empty] | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | design_drawing | civil_design | compatible | electrical¦reserve_boiler | electrical | electrical¦reserve_boiler | query | electrical | discipline_only | true | false | 29 | 1 |  | 0.5117 | 0.0276 | 0.0104 | hybrid | structured_preferred | electrical¦reserve_boiler | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.26 | needs_review | rule_score_medium;activity_phase_status=compatible;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE01-P8ZEN-125768 | RESERVE BOILER - LIGHTNING PROTECTION DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | LIGHTNING PROTECTION |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Lightning Protection Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7393 | 0.9218 | 0.6452 | g_safe | [5 empty] | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical¦reserve_boiler | electrical | electrical¦reserve_boiler | query | electrical | discipline_only | true | false | 1 | 21 |  | 0.4464 | 0.0287 | 0.0108 | hybrid | structured_preferred | electrical¦reserve_boiler | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_phase_status=compatible;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P8ZEN-125769 | RESERVE BOILER - COMMUNICATION SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | COMMUNICATION SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | Communication System Document & DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6501 | 0.8950 | 0.6265 | g_safe | [5 empty] | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | design_drawing | system_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 6 | 240 | 1.3610 | 0.4533 | 0.0185 | 0.0083 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.33 | needs_review | activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126001 | HRSG FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | GENERAL ARRANGEMENT DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7364 | 0.9209 | 0.9209 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 4 | 1 | 14.8421 | 0.6378 | 0.0320 | 0.0320 | hybrid | structured_preferred | feedwater¦hrsg | system_design | 7 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAC-126003 | HRSG FEEDWATER PUMP - P&I DIAGRAM | P&ID | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | P&ID for Feedwater System |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.8182 | 0.9455 | 0.9455 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 1 | 5 | 28.3017 | 0.7059 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | feedwater¦hrsg | system_design¦procurement |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126004 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | DATA SHEET AND CHARACTERISTIC CURVE | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Heat Recovery Steam Generator FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7320 | 0.9196 | 0.9196 | [6 empty] | FA | 3PF1615W64A10P | (HRSG #31 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-13 | 2008-05-01 | procurement | procurement | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | true | false | 24 | 18 | 20.0267 | 0.5606 | 0.0247 | 0.0247 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126005 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | DATA SHEET AND CHARACTERISTIC CURVE | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Heat Recovery Steam Generator FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7320 | 0.9196 | 0.9196 | [6 empty] | FA | 3PF1615W64A10P | (HRSG #31 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-13 | 2008-05-01 | procurement | procurement | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | true | false | 24 | 18 | 20.0267 | 0.5485 | 0.0247 | 0.0247 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LAC-126006 | HRSG FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | SECTIONAL DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | SECTIONAL DRAWING for HRSG |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦heat¦hrsg¦pump¦recovery¦steam | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6399 | 0.6586 | 0.6586 | [6 empty] | FA | 3EF1600W00A01.1 | (HRSG #32 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | true | false | 12 | 6 | 12.8284 | 0.5694 | 0.0290 | 0.0290 | hybrid | structured_preferred | feedwater¦hrsg | civil_design | 10 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126007 | HRSG FEEDWATER PUMP - NAME PLATE DRAWING | DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6678 | 0.5503 | 0.5503 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 1 | 2 | 14.8421 | 0.6264 | 0.0325 | 0.0244 | hybrid | structured_preferred | feedwater¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126009 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | OUTLINE DRAWING AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | OUTLINE DRAWING AND DATA SHEET for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Elevator Data Sheet anD DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.6686 | 0.7839 | 0.7839 | [6 empty] | FA | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-14 | 2008-04-02 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 25 | 14 | 20.0267 | 0.5820 | 0.0253 | 0.0253 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126010 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | OUTLINE DRAWING AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | OUTLINE DRAWING AND DATA SHEET for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Elevator Data Sheet anD DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.6686 | 0.7839 | 0.7839 | [6 empty] | FA | 3PF1665W42A02P | (HRSG #31 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | 2007-09-10 | 2008-10-02 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 35 | 8 | 19.8698 | 0.5828 | 0.0252 | 0.0252 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-06-24 | 2025-07-24 | 2025-08-23 | 2025-09-07 | 2025-09-22 | 2025-10-07 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LAC-126011 | HRSG FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | LIST AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | Instrument List for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Instrument List | 1 | start+133D<=FA<=start+133D+2M | FA ∈ [start+133d, start+193d] | rule_query | list | list | instrument_list | instrument_list | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7009 | 0.9103 | 0.9103 | [6 empty] | FA | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-10-02 | 2008-08-04 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 4 | 21 | 23.9692 | 0.6165 | 0.0280 | 0.0280 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-02-12 | 2025-03-14 | 2025-04-13 | 2025-04-28 | 2025-05-13 | 2025-05-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-DM01-P0LAC-126012 | HRSG FEEDWATER PUMP - INSTALLATION MANUAL | INSTALLATION MANUAL | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | INSTALLATION MANUAL for Heat Recovery Steam Generator FEEDWATER PUMP |  | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | manual | manual | manual | manual | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5803 | 0.6408 | 0.6408 | g_ambig | generic_ok | 0.78 |  | 2 | The competing specific rules target HRSG shop quality manual and condenser vacuum pump installation manual, not an HRSG feedwater pump installation manual. | FI | 3CF1665W42A04 | (HRSG #31 MECH Vendor Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | 2008-11-18 | 2009-03-02 | manual | procurement | compatible | feedwater¦hrsg |  | feedwater¦hrsg | query | hrsg | match | true | false | 14 | 18 | 16.9474 | 0.5928 | 0.0263 | 0.0198 | hybrid | structured_preferred | feedwater¦hrsg | delivery¦procurement¦installation | 10 | 2025-10-10 | 2025-11-09 | 2025-12-09 | 2025-12-24 | 2026-01-08 | 2026-01-23 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126016 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | OUTLINE DRAWING AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | OUTLINE DRAWING AND DATA SHEET for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Elevator Data Sheet anD DraWing | 1 | start+287D<=FA<=start+287D+2M | FA ∈ [start+287d, start+347d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8333 | 0.6686 | 0.7839 | 0.7839 | [6 empty] | FA | 3PF1665W42A02P | (HRSG #31 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | 2007-09-10 | 2008-10-02 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 35 | 11 | 19.8698 | 0.5923 | 0.0246 | 0.0246 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-06-24 | 2025-07-24 | 2025-08-23 | 2025-09-07 | 2025-09-22 | 2025-10-07 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126019 | HRSG FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6678 | 0.5503 | 0.5503 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 1 | 1 | 14.8421 | 0.6305 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LAC-126027 | HRSG FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | DATA SHEET & DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | DATA SHEET & DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Motor Data Sheet | 1 | start+263D<=FA<=start+263D+2M | FA ∈ [start+263d, start+323d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.6625 | 0.7237 | 0.7237 | [6 empty] | FA | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-13 | 2008-02-29 | procurement | procurement | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 4 | 18 | 20.0267 | 0.5759 | 0.0284 | 0.0284 | hybrid | structured_preferred | feedwater¦hrsg | procurement | 10 | 2025-03-03 | 2025-04-02 | 2025-05-02 | 2025-05-17 | 2025-06-01 | 2025-06-16 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126051 | FGP FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | GENERAL ARRANGEMENT DRAWING for Fuel Gas Package FEEDWATER PUMP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | feedwater¦fgp¦fuel¦gas¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6604 | 0.8981 | 0.8981 | g_ambig | uncertain | 0.45 |  | 2 | The competing rules are either generic again or PLC-specific, and it is unclear whether this GA drawing is for the pump package or for a PLC panel. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | true | false | 1 | 2 | 7.6021 | 0.6445 | 0.0325 | 0.0325 | hybrid | structured_preferred | feedwater¦fgp | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAC-126053 | FGP FEEDWATER PUMP - P&I DIAGRAM | P&ID | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | P&ID for Feedwater System | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | feedwater¦fgp¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6959 | 0.5588 | 0.5588 | g_ambig | uncertain | 0.40 |  | 8 | Competing specific rules reference GT fuel gas system P&IDs, while the document equipment is a fuel gas package feedwater pump, so the intended system/equipment scope is ambiguous. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | true | false | 13 | 8 | 21.9084 | 0.7305 | 0.0284 | 0.0284 | hybrid | structured_blocked_procurement_conflict | feedwater¦fgp | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126054 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | DATA SHEET AND CHARACTERISTIC CURVE | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Fuel Gas Package FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7549 | 0.9265 | 0.9265 | [6 empty] | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | true | false | 7 | 1 | 18.1071 | 0.6800 | 0.0313 | 0.0313 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126055 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | DATA SHEET AND CHARACTERISTIC CURVE | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Fuel Gas Package FEEDWATER PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7549 | 0.9265 | 0.9265 | [6 empty] | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | condensate¦fgp | match | true | false | 5 | 13 | 20.7878 | 0.6182 | 0.0291 | 0.0291 | hybrid | structured_cell_found_text_preferred | feedwater¦fgp | procurement |  | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LAC-126056 | FGP FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | SECTIONAL DRAWING | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | SECTIONAL DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8877 | 0.9663 | 0.9663 | [6 empty] | FA | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | civil_design | civil_design | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | true | false | 15 | 3 | 9.0246 | 0.6624 | 0.0292 | 0.0292 | hybrid | structured_preferred | feedwater¦fgp | civil_design | 10 | 2024-12-26 | 2025-01-25 | 2025-02-24 | 2025-03-11 | 2025-03-26 | 2025-04-10 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126057 | FGP FEEDWATER PUMP - NAME PLATE DRAWING | DRAWING | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | DRAWING for Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.7144 | 0.5643 | 0.5643 | [6 empty] | FA | 1EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | design_drawing | civil_design | compatible | feedwater¦fgp | fgp | feedwater¦fgp | query | feedwater | match | true | false | 23 | 4 | 6.1745 | 0.6539 | 0.0277 | 0.0208 | hybrid | structured_preferred | feedwater¦fgp | system_design¦civil_design | 10 | 2025-02-20 | 2025-04-17 | 2025-06-12 | 2025-05-08 | 2025-07-03 | 2025-08-28 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126059 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | OUTLINE DRAWING AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | OUTLINE DRAWING AND DATA SHEET for Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6451 | 0.7185 | 0.7185 | [6 empty] | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | condensate¦fgp | match | true | false | 5 | 9 | 20.7878 | 0.6499 | 0.0299 | 0.0299 | hybrid | structured_cell_found_text_preferred | feedwater¦fgp | procurement |  | 2024-09-07 | 2024-10-12 | 2024-11-16 | 2024-11-02 | 2024-12-07 | 2025-01-11 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126060 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | OUTLINE DRAWING AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | OUTLINE DRAWING AND DATA SHEET for Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6451 | 0.7185 | 0.7185 | [6 empty] | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | feedwater | match | true | false | 11 | 1 | 15.3460 | 0.6718 | 0.0305 | 0.0305 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-07-09 | 2024-08-13 | 2024-09-17 | 2024-09-03 | 2024-10-08 | 2024-11-12 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LAC-126061 | FGP FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | LIST AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | Instrument List for Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Instrument List | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | list | list | instrument_list | instrument_list | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.7536 | 0.7861 | 0.7861 | [6 empty] | FI | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | procurement | procurement | match | feedwater¦fgp | fgp | feedwater¦fgp | query | condensate¦fgp | match | true | false | 6 | 9 | 20.7878 | 0.6669 | 0.0296 | 0.0296 | hybrid | structured_cell_found_text_preferred | feedwater¦fgp | procurement |  | 2024-08-24 | 2024-10-05 | 2024-11-16 | 2024-10-26 | 2024-12-07 | 2025-01-18 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-DM01-P0LAC-126062 | FGP FEEDWATER PUMP - INSTALLATION MANUAL | INSTALLATION MANUAL | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | INSTALLATION MANUAL for Fuel Gas Package FEEDWATER PUMP | Fuel Gas Compressor | Installation & Erection Manual | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | manual | manual | manual | manual | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7624 | 0.6954 | 0.6954 | [6 empty] | FI | 0CF3520W42A06.3 | (FOFP) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2008-05-14 | 2008-06-13 | manual | installation | compatible | feedwater¦fgp | fgp | feedwater¦fgp | query | fgp | match | true | false | 10 | 10 | 14.7142 | 0.6447 | 0.0286 | 0.0214 | hybrid | structured_preferred | feedwater¦fgp | delivery¦procurement¦installation | 10 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126066 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | OUTLINE DRAWING AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | OUTLINE DRAWING AND DATA SHEET for Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6451 | 0.7185 | 0.7185 | [6 empty] | FA | 0EF3520W00A01.2 | (FOSS) FO Forwarding Pump, FO Unloading Pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-04-02 | 2007-04-30 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | true | false | 2 | 11 | 27.1745 | 0.6395 | 0.0302 | 0.0302 | hybrid | structured_cell_found_text_preferred | feedwater¦fgp | procurement |  | 2024-07-09 | 2024-08-13 | 2024-09-17 | 2024-09-03 | 2024-10-08 | 2024-11-12 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126069 | FGP FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | DRAWING for Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.7144 | 0.5643 | 0.5643 | [6 empty] | FA | 0CF3520W16A04 | (Transfer Pump) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > DFO Tank & Pump | 2007-10-31 | 2007-12-27 | design_drawing | civil_design | compatible | feedwater¦fgp | fgp | feedwater¦fgp | query | fgp | match | true | false | 1 | 26 | 14.6824 | 0.5750 | 0.0280 | 0.0210 | hybrid | structured_preferred | feedwater¦fgp | system_design¦civil_design | 10 | 2025-02-20 | 2025-04-17 | 2025-06-12 | 2025-05-08 | 2025-07-03 | 2025-08-28 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LAC-126077 | FGP FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | DATA SHEET & DRAWING | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | DATA SHEET & DRAWING for Fuel Gas Package FEEDWATER PUMP | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | feedwater¦fgp¦fuel¦gas¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6743 | 0.7273 | 0.7273 | [6 empty] | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | procurement | procurement | match | feedwater¦fgp |  | feedwater¦fgp | query | condensate¦fgp | match | true | false | 3 | 9 | 20.7878 | 0.6149 | 0.0304 | 0.0304 | hybrid | structured_preferred | feedwater¦fgp | procurement | 10 | 2024-09-07 | 2024-10-12 | 2024-11-16 | 2024-11-02 | 2024-12-07 | 2025-01-11 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0LAC-126301 | HRSG FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP | Instrumentation and Control |  |  | DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | HRSG - Assembly DraWing of Steam Drum | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6678 | 0.5503 | 0.5503 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 1 | 1 | 19.3369 | 0.6686 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0LAC-126302 | HRSG FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | Heat Recovery Steam Generator FEEDWATER PUMP | Feedwater System |  |  | WIRING DIAGRAM for Feedwater System |  | HRSG - Wiring Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | feedwater¦generator¦heat¦hrsg¦pump¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.6950 | 0.6752 | 0.6752 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | feedwater¦hrsg | hrsg | feedwater¦hrsg | query | hrsg | match | true | false | 1 | 8 | 24.0529 | 0.6523 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | feedwater¦hrsg | system_design¦engineering |  | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0LAC-126351 | FGP FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | DRAWING | Fuel Gas Package FEEDWATER PUMP | Instrumentation and Control |  |  | DRAWING for Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | feedwater¦fgp¦fuel¦gas¦pump | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.7144 | 0.5643 | 0.5643 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | feedwater¦fgp | fgp | feedwater¦fgp | query | fgp | match | true | false | 6 | 2 | 12.2357 | 0.6176 | 0.0313 | 0.0235 | hybrid | structured_preferred | feedwater¦fgp | system_design¦civil_design | 10 | 2024-07-05 | 2024-08-30 | 2024-10-25 | 2024-09-20 | 2024-11-15 | 2025-01-10 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0LAC-126352 | FGP FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | Fuel Gas Package FEEDWATER PUMP | Feedwater System |  |  | WIRING DIAGRAM for Feedwater System |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | feedwater¦fgp¦pump |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6372 | 0.8911 | 0.8911 | g_ambig | use_specific | 0.74 | Cable Interconnection Wiring Diagram | 7 | The document title explicitly is a cable interconnection wiring diagram, matching the specific rule keyword more precisely than the generic interconnection wiring diagram. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | feedwater¦fgp |  | feedwater¦fgp | query | fgp | match | true | false | 1 | 2 | 17.3923 | 0.6699 | 0.0325 | 0.0325 | hybrid | structured_preferred | feedwater¦fgp | system_design¦engineering | 3 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126501 | FIN FAN COOLER - SYSTEM DESCRIPTION | System Description | Fin Fan Cooler | Closed Cooling Water System |  |  | System Description for Closed Cooling Water System | FinFan Cooler | System Description | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | description | description | system_description | system_description | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8315 | 0.7745 | 0.7745 | g_safe | [5 empty] | FI | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | true | 45 | 40 | 16.7398 | 0.5570 | 0.0195 | 0.0117 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0PCA-126502 | FIN FAN COOLER - P&I DIAGRAM | P&ID | Fin Fan Cooler | Closed Cooling Water System |  |  | P&ID for Closed Cooling Water System | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8616 | 0.7835 | 0.7835 | g_safe | [5 empty] | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | ccw |  | ccw | query |  | activity_unscoped | true | true | 48 | 56 | 23.8482 | 0.5935 | 0.0179 | 0.0107 | hybrid | structured_blocked_procurement_conflict | ccw | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PCA-126503 | FIN FAN COOLER - GENERAL ARRANGEMENT & PLOT PLAN DRAWING | GENERAL ARRANGEMENT & PLOT PLAN DRAWING | Fin Fan Cooler | Closed Cooling Water System |  |  | GENERAL ARRANGEMENT & PLOT PLAN DRAWING for Fin Fan Cooler |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cooler¦fan¦fin |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6485 | 0.8945 | 0.8945 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 3 | 1 | 47.8511 | 0.6569 | 0.0323 | 0.0323 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126504 | FIN FAN COOLER - PERFORMANCE CURVE | Performance Curve | Fin Fan Cooler | Closed Cooling Water System |  |  | Performance Curve for Fin Fan Cooler | FinFan Cooler | Performance Curve | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | curve | curve | performance_curve | performance_curve | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9642 | 0.8143 | 0.8143 | g_safe | [5 empty] | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 2 | 1 | 54.1534 | 0.6867 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0PCA-126505 | FIN FAN COOLER - TERMINAL POINT LIST & DRAWING | LIST & DRAWING | Fin Fan Cooler | Closed Cooling Water System |  |  | LIST & DRAWING for Fin Fan Cooler | FinFan Cooler | RaceWay draWing | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | drawing | drawing | drawing | drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7913 | 0.5874 | 0.5874 | g_safe | [5 empty] | FA | 3PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 3 | 1 | 54.1534 | 0.6911 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0PCA-126506 | FIN FAN COOLER - EQUIPMENT LIST | EQUIPMENT LIST | Fin Fan Cooler | Closed Cooling Water System |  |  | Equipment List for Fin Fan Cooler | FinFan Cooler | Equipment List | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | list | list | equipment_list | equipment_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9632 | 0.8140 | 0.8140 | g_safe | [5 empty] | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 2 | 1 | 54.1534 | 0.7276 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0PCA-126507 | FIN FAN COOLER - VALVE LIST | VALVE LIST | Fin Fan Cooler | Closed Cooling Water System |  |  | Valve List for Fin Fan Cooler |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7437 | 0.6898 | 0.6898 | g_safe | [5 empty] | FA | 3PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 3 | 1 | 54.1534 | 0.6871 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126508 | FIN FAN COOLER - BELT PULLEY DATA SHEET | Data Sheet | Fin Fan Cooler | Closed Cooling Water System |  |  | Data Sheet for Fin Fan Cooler | FinFan Cooler | Fan Data Sheet & Outline DraWing | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.8389 | 0.6517 | 0.6517 | g_safe | [5 empty] | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 2 | 1 | 54.1534 | 0.6556 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126509 | FIN FAN COOLER - FAN MOTOR DATA SHEET | Data Sheet | Fin Fan Cooler | Closed Cooling Water System |  |  | Data Sheet for Fin Fan Cooler | FireFighting | Motor Data Sheet | 1 | start+20W<=FA<=FC<=start+30W | FA ∈ [start+140d, start+210d] ¦ FC ∈ [start+140d, start+210d] | title | datasheet | datasheet | data_sheet | data_sheet | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5475 | 0.6893 | 0.6893 | g_safe | [5 empty] | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 2 | 1 | 60.3011 | 0.6641 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-11-20 | 2024-12-25 | 2025-01-29 | 2025-01-15 | 2025-02-19 | 2025-03-26 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126512 | FIN FAN COOLER - FAN OUTLINE DRAWING (WITH MOTOR) | OUTLINE DRAWING (WITH MOTOR) | Fin Fan Cooler | Closed Cooling Water System |  |  | OUTLINE DRAWING (WITH MOTOR) for Fin Fan Cooler |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6907 | 0.9072 | 0.9072 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 7.0216 | 0.4196 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126513 | FIN FAN COOLER - VALVE OUTLINE DRAWING | Outline Drawing | Fin Fan Cooler | Closed Cooling Water System |  |  | Outline Drawing for Fin Fan Cooler |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5956 | 0.6453 | 0.6453 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 7.0216 | 0.4156 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126514 | FIN FAN COOLER - PIPING ARRANGEMENT DRAWING | General Arrangement Drawing | Fin Fan Cooler | PIPING |  |  | General Arrangement Drawing for Fin Fan Cooler |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cooler¦fan¦fin |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7130 | 0.9139 | 0.9139 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 |  | 0.4427 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126515 | FIN FAN COOLER - PIPING ISOMETRIC DRAWRING | ISOMETRIC DRAWRING | Fin Fan Cooler | PIPING |  |  | ISOMETRIC DRAWRING for Fin Fan Cooler | H2, CO2 Supply System | Piping Isometric DraWring | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | isometric_drawing | isometric_drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6364 | 0.4909 | 0.4909 | g_safe | [5 empty] | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw | h2 | ccw | query | ccw¦gtg | match | true | false | 2 | 4 | 42.1378 | 0.6183 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126516 | FIN FAN COOLER - PIPE MATERIAL SPECIFICATION | MATERIAL SPECIFICATION | Fin Fan Cooler | PIPE |  |  | MATERIAL SPECIFICATION for Fin Fan Cooler | FinFan Cooler | Pipe Material Specification | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | specification | specification | specification | specification | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8616 | 0.8185 | 0.8185 | g_safe | [5 empty] | FA | 1EF1225W42A17.1 | (CCW H/EX) MPS Issue_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System |  | 2007-05-01 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 2 | 5 | 46.7736 | 0.5860 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-07-30 | 2024-08-29 | 2024-09-28 | 2024-10-13 | 2024-10-28 | 2024-11-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0PCA-126517 | FIN FAN COOLER - PIPE LINE LIST | LINE LIST | Fin Fan Cooler | PIPE |  |  | LINE LIST for Fin Fan Cooler | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | other | other | line_list | line_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6428 | 0.5428 | 0.5428 | g_safe | [5 empty] | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw | compressed_air | ccw | query | ccw¦gtg | match | true | false | 2 | 1 | 42.1378 | 0.6344 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0PCA-126519 | FIN FAN COOLER - CONTROL DESCRIPTION (PHILOSOPHY) | CONTROL DESCRIPTION (PHILOSOPHY) | Fin Fan Cooler | Closed Cooling Water System |  |  | CONTROL DESCRIPTION (PHILOSOPHY) for Closed Cooling Water System |  | CONTROL DESCRIPTION (PHILOSOPHY) | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | description | description | control_description | control_description | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7277 | 0.9183 | 0.6428 | g_safe | [5 empty] | FA | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2008-06-16 | 2008-07-30 |  | installation | query_unknown | ccw |  | ccw | query | ccw¦gtg | match | true | false | 4 | 7 | 48.3109 | 0.6032 | 0.0306 | 0.0229 | hybrid | structured_no_phase | ccw |  |  | 2025-02-02 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-18 | 2025-05-18 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0PCA-126522 | FIN FAN COOLER - LOGIC / FUNCTIONAL LOOP DIAGRAMS | LOGIC / FUNCTIONAL LOOP DIAGRAMS | Fin Fan Cooler | Closed Cooling Water System |  |  | LOGIC / FUNCTIONAL LOOP DIAGRAMS for Closed Cooling Water System |  | FUNCTIONAL LOOP DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | functional_loop_diagram | functional_loop_diagram | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7100 | 0.6797 | 0.4758 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 7.0216 | 0.4706 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_score_medium;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0PCA-126523 | FIN FAN COOLER - INSTRUMENT LIST | LIST | Fin Fan Cooler | INSTRUMENT |  |  | Instrument List for Fin Fan Cooler | FinFan Cooler | Instrument list | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | list | list | instrument_list | instrument_list | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.9518 | 0.8105 | 0.8105 | g_safe | [5 empty] | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 2 | 1 | 42.1378 | 0.6441 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126524 | FIN FAN COOLER - INSTRUMENT CATALOG | CATALOG | Fin Fan Cooler | INSTRUMENT |  |  | CATALOG for Fin Fan Cooler | [5 empty] | rule_query | other | other | catalog | instrument_catalog | cooler¦fan¦fin |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.5000 | 0.8460 | 0.6038 | 0.6038 | [7 empty] | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2008-06-16 | 2008-07-30 |  | installation | query_unknown | ccw |  | ccw | query | ccw¦gtg | match | true | false | 4 | 9 | 36.1017 | 0.5228 | 0.0301 | 0.0226 | hybrid | structured_no_phase | ccw | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0PCA-126525 | FIN FAN COOLER - INSTRUMENT INSTALLATION DETAIL DRAWING | DRAWING | Fin Fan Cooler | INSTRUMENT INSTALLATION MATERIAL |  |  | DRAWING for INSTRUMENT INSTALLATION MATERIAL | FinFan Cooler | Instrument Installation Detail DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | detail_drawing | detail_drawing | installation¦instrument¦material |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8215 | 0.8298 | 0.8298 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | true | false | 3 | 2 | 35.7395 | 0.5194 | 0.0320 | 0.0240 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126526 | FIN FAN COOLER - INSTRUMENT DATA SHEET | Data Sheet | Fin Fan Cooler | INSTRUMENT |  |  | Data Sheet for Fin Fan Cooler | FireFighting | Instrument Data Sheet | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | title | datasheet | datasheet | data_sheet | data_sheet | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6163 | 0.7099 | 0.7099 | g_safe | [5 empty] | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 2 | 1 | 42.1378 | 0.5957 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | ccw | procurement |  | 2024-11-20 | 2024-12-05 | 2024-12-20 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126527 | FIN FAN COOLER - DRIVE LIST (MOVS, MOTORS, CONTROL VALVES, SOLENOID VALVES, ETC..) | LIST | Fin Fan Cooler | Closed Cooling Water System |  |  | LIST for Fin Fan Cooler | [5 empty] | rule_query | other | list | list | equipment_list | cooler¦fan¦fin |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.8569 | 0.6071 | 0.6071 | [7 empty] | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2008-06-16 | 2008-07-30 |  | installation | query_unknown | ccw |  | ccw | query | ccw¦gtg | match | true | false | 4 | 6 | 48.3109 | 0.6418 | 0.0308 | 0.0231 | hybrid | structured_no_phase | ccw | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0PCA-126529 | FIN FAN COOLER - RACEWAY DRAWING | DRAWING | Fin Fan Cooler | Closed Cooling Water System |  |  | DRAWING for Fin Fan Cooler | FinFan Cooler | RaceWay draWing | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | drawing | drawing | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8134 | 0.7690 | 0.7690 | g_safe | [5 empty] | FA | 3EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | true | false | 5 | 1 | 47.8511 | 0.6409 | 0.0318 | 0.0238 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PCA-126530 | JUNCTION BOX OUTLINE AND LAYOUT DRAWING | OUTLINE AND LAYOUT DRAWING | JUNCTION BOX |  |  |  | OUTLINE AND LAYOUT DRAWING for JUNCTION BOX |  | I&C junction box outline and layout draWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | box¦junction |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.8108 | 0.8432 | 0.8432 | g_safe | [5 empty] | FI | 1EF3020W16A09 | (COND Flash Box) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-01-02 | 2008-03-31 | design_drawing | civil_design | compatible |  |  |  |  | condensate | query_unscoped | false | false | 13 | 203 | 16.3168 | 0.3892 | 0.0175 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2025-03-27 | 2025-04-26 | 2025-05-26 | 2025-06-10 | 2025-06-25 | 2025-07-10 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0PCA-126533 | FIN FAN COOLER - WIRING DIAGRAMS FOR JUNCTION BOXES | WIRING DIAGRAMS | Fin Fan Cooler | Closed Cooling Water System |  |  | WIRING DIAGRAMS for Closed Cooling Water System | FinFan Cooler | Wiring diagrams | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | diagram | diagram | wiring_diagram | wiring_diagram | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7682 | 0.7555 | 0.7555 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 7.0216 | 0.4230 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126538 | FIN FAN COOLER - FOUNDATION DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING (INCLUDE AUXILIARY EQUIPMENT) | DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING | Fin Fan Cooler | Closed Cooling Water System |  |  | DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING for Closed Cooling Water System | FinFan Cooler | Foundation DraWings / Civil Loading Data (With Embedded Material DraWing (include Auxiliary equipment)) | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.9286 | 0.8263 | 0.8979 | 0.8979 | g_safe | [5 empty] | FA | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 5 | 49.6733 | 0.6481 | 0.0318 | 0.0318 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126539 | FIN FAN COOLER - STEEL STRUCTURE CALCULATION | Calculation sheet | Fin Fan Cooler | Closed Cooling Water System |  |  | Calculation sheet for Fin Fan Cooler | FinFan Cooler | Steel Structure Calculation | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | title | calculation | calculation | calculation | calculation | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8587 | 0.8176 | 0.8176 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 3 | 1 | 47.8511 | 0.6154 | 0.0323 | 0.0323 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0PCA-126540 | FIN FAN COOLER – DETAIL DRAWING FOR CLEANING COMPRESSOR | Detail Drawing | Fin Fan Cooler | Closed Cooling Water System |  |  | Detail Drawing for Closed Cooling Water System |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5557 | 0.6334 | 0.6334 | g_safe | [5 empty] | FI | 3EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw¦gtg | match | true | false | 5 | 1 | 47.8511 | 0.6239 | 0.0318 | 0.0238 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127001 | FGP COP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Fuel Gas Package COP |  |  |  | GENERAL ARRANGEMENT DRAWING for Fuel Gas Package COP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6650 | 0.8995 | 0.8995 | g_ambig | uncertain | 0.45 |  | 2 | The competing rules are generic again or PLC-specific, and there is not enough information to confirm whether this GA is PLC-related or standard equipment GA. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 6.9833 | 0.6197 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LCB-127002 | FGP COP - P&I DIAGRAM | P&ID | Fuel Gas Package COP |  |  |  | P&ID for Fuel Gas Package COP | Fuel Gas Compressor | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8167 | 0.7700 | 0.7700 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 4 | 21.2897 | 0.7175 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127003 | FGP COP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package COP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for Fuel Gas Package COP | Fuel Gas Compressor | Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8571 | 0.8044 | 0.8413 | 0.8413 | [6 empty] | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 1 | 16.6251 | 0.7082 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127004 | FGP COP - PUMP SECTIONAL DRAWING | DRAWING | Fuel Gas Package COP |  |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | [6 empty] | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match | fgp |  | fgp | query | fgp | match | true | false | 11 | 2 | 7.8224 | 0.6734 | 0.0302 | 0.0302 | hybrid | structured_preferred | fgp | civil_design | 10 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127005 | FGP COP - MECHANICAL SEAL SPECIFICATION | Technical Specification | Fuel Gas Package COP |  |  |  | Technical Specification for Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5139 | 0.6208 | 0.4346 | g_safe | [5 empty] | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 2 | 14.3363 | 0.5764 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | procurement | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127006 | FGP COP - COUPLING SPECIFICATION | Technical Specification | Fuel Gas Package COP |  |  |  | Technical Specification for Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5139 | 0.6208 | 0.4346 | g_safe | [5 empty] | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 5 | 14.3363 | 0.6187 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | fgp | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127007 | FGP COP - SUCTION STRAINER SPECIFICATION | Technical Specification | Fuel Gas Package COP |  |  |  | Technical Specification for Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5139 | 0.6208 | 0.4346 | g_safe | [5 empty] | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 2 | 14.3363 | 0.5854 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fgp | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127009 | FGP COP - FOUNDATION DRAWINGS | DRAWINGS | Fuel Gas Package COP |  |  |  | DRAWINGS for Fuel Gas Package COP | Fuel Gas System | Control System Configuration DraWings | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.7004 | 0.5601 | 0.5601 | [6 empty] | FA | 1CF3520W16A02.1 | (Gas COMP PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-11-02 | 2008-01-31 | civil_design | civil_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 2 | 1 | 9.8076 | 0.6933 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | civil_design | 10 | 2025-01-25 | 2025-03-08 | 2025-04-19 | 2025-03-29 | 2025-05-10 | 2025-06-21 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0LCB-127010 | FGP COP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package COP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for Fuel Gas Package COP | Fuel Gas Compressor | Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8571 | 0.8044 | 0.8413 | 0.8413 | [6 empty] | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | true | false | 3 | 1 | 16.6251 | 0.7034 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127011 | FGP COP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | Fuel Gas Package COP |  |  |  | DRAWING for Fuel Gas Package COP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.7044 | 0.5613 | 0.5613 | [6 empty] | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 2 | 7.8224 | 0.6311 | 0.0325 | 0.0244 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-17 | 2025-03-14 | 2025-02-07 | 2025-04-04 | 2025-05-30 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LCB-127013 | FGP COP - INSTRUMENT LIST AND DATA SHEET | LIST AND DATA SHEET | Fuel Gas Package COP |  |  |  | Instrument List for Fuel Gas Package COP | Fuel Gas System | Instrument List | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | list | list | instrument_list | instrument_list | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.8203 | 0.8061 | 0.8061 | [6 empty] | FI | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 1 | 16.6251 | 0.7067 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | procurement | 10 | 2024-05-24 | 2024-07-05 | 2024-08-16 | 2024-07-26 | 2024-09-06 | 2024-10-18 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LCB-127015 | FGP COP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | Fuel Gas Package COP |  |  |  | HOOK - UP DRAWING for Fuel Gas Package COP | Fuel Gas Compressor | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7143 | 0.7643 | 0.7293 | 0.7293 | [6 empty] | FI | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | true | false | 3 | 2 | 7.8224 | 0.6293 | 0.0320 | 0.0240 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2024-12-22 | 2025-01-21 | 2025-02-05 | 2025-02-20 | 2025-03-07 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127016 | FGP COP - VMS SPECIFICATION | Technical Specification | Fuel Gas Package COP | Vibration Monitoring System |  |  | Technical Specification for Fuel Gas Package COP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | cop¦fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5139 | 0.6208 | 0.4346 | g_safe | [5 empty] | FA | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor |  | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 2 | 14.7807 | 0.6110 | 0.0325 | 0.0325 | hybrid | structured_preferred | fgp | procurement | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0LCB-127018 | FGP COP - NAME PLATE DRAWING | DRAWING | Fuel Gas Package COP |  |  |  | DRAWING for Fuel Gas Package COP | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | cop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.7044 | 0.5613 | 0.5613 | [6 empty] | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 2 | 7.8224 | 0.6460 | 0.0325 | 0.0244 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-11-22 | 2025-01-17 | 2025-03-14 | 2025-02-07 | 2025-04-04 | 2025-05-30 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127031 | CEP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Condensate Extraction Pump | Condensate System |  |  | GENERAL ARRANGEMENT DRAWING for CEP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | condensate¦extraction¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7473 | 0.9242 | 0.9242 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 15.0182 | 0.6480 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LCB-127032 | CEP - P&I DIAGRAM | P&ID | Condensate Extraction Pump | Condensate System |  |  | P&ID for Condensate System | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | condensate¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5816 | 0.5245 | 0.5245 | g_ambig | use_specific | 0.70 | P&ID | 1 | The specific rule keyword exactly matches the deliverable naming used for this CEP P&ID and provides a different timeline than the generic P&I Diagram rule. | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 21 | 14 | 28.9948 | 0.7314 | 0.0259 | 0.0259 | hybrid | structured_blocked_procurement_conflict | condensate | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127033 | CEP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Condensate Extraction Pump | Condensate System |  |  | DATA SHEET & CHARACTERISTIC CURVE for CEP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | condensate¦extraction¦pump | pump | scoped | match | match | match | passed |  | 0.8000 | 0.6601 | 0.7580 | 0.7580 | [6 empty] | FA | 2PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-09-08 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 2 | 1 | 40.3033 | 0.7791 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127034 | CEP - PUMP SECTIONAL DRAWING | DRAWING | Condensate Extraction Pump | Condensate System |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | [6 empty] | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 2 | 37.5391 | 0.7282 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-12-04 | 2025-01-03 | 2025-02-02 | 2025-02-17 | 2025-03-04 | 2025-03-19 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127035 | CEP - MECHANICAL SEAL SPECIFICATION | Technical Specification | Condensate Extraction Pump | Condensate System |  |  | Technical Specification for CEP |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4451 | 0.4835 | 0.4835 | g_safe | [5 empty] | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 2 | 40.3033 | 0.7400 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | condensate | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127036 | CEP - COUPLING SPECIFICATION | Technical Specification | Condensate Extraction Pump | Condensate System |  |  | Technical Specification for CEP |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4451 | 0.4835 | 0.4835 | g_safe | [5 empty] | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 40.3033 | 0.7822 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127037 | CEP - SUCTION STRAINER SPECIFICATION | Technical Specification | Condensate Extraction Pump | Condensate System |  |  | Technical Specification for CEP |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4451 | 0.4835 | 0.4835 | g_safe | [5 empty] | FA | 2PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-09-08 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 2 | 2 | 40.3033 | 0.7678 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | condensate | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127038 | CEP - FOUNDATION DRAWINGS | DRAWINGS | Condensate Extraction Pump | Condensate System |  |  | DRAWINGS for CEP |  | FOUNDATION DRAWINGS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7607 | 0.6949 | 0.4864 | g_ambig | generic_ok | 0.76 |  | 16 | None of the competing specific rules clearly targets CEP foundation drawings (they refer to nameplates, 3D model, ACC/HRSG items, or a different foundation/load-data deliverable). | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 2 | 35.0917 | 0.7812 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | condensate | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.30 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0LCB-127039 | CEP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Condensate Extraction Pump | Condensate System |  |  | DATA SHEET & CHARACTERISTIC CURVE for CEP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | condensate¦extraction¦pump | pump | scoped | match | match | match | passed |  | 0.8000 | 0.6601 | 0.7580 | 0.7580 | [6 empty] | FA | 2PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-09-08 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 2 | 1 | 40.3033 | 0.7535 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LCB-127040 | CEP - INSTRUMENT LIST AND DATA SHEET | LIST AND DATA SHEET | Condensate Extraction Pump | Condensate System |  |  | Instrument List for CEP |  | Instrument List | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | list | list | instrument_list | instrument_list | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7761 | 0.6995 | 0.6995 | g_ambig | use_specific | 0.73 | Instrument List and datasheet / draWing | 1 | The document title includes both instrument list and datasheet, aligning with the combined specific rule rather than the generic instrument list rule. | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 40.3033 | 0.7995 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LCB-127041 | CEP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | Condensate Extraction Pump | Condensate System |  |  | HOOK - UP DRAWING for CEP |  | Instruments Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6891 | 0.7317 | 0.7317 | g_ambig | generic_ok | 0.77 |  | 21 | The competing rules are for other drawing types (nameplate, foundation/load data, pump arrangement, etc.) and do not specifically target an instrumentation hook-up drawing for CEP. | FI | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | design_drawing | civil_design | compatible | condensate |  | condensate | query | condensate | match | true | false | 1 | 2 | 33.0135 | 0.6703 | 0.0325 | 0.0244 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0LCB-127042 | CEP - NAME PLATE DRAWING | DRAWING | Condensate Extraction Pump | Condensate System |  |  | DRAWING for CEP |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | condensate¦extraction¦pump |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7608 | 0.9282 | 0.9282 | g_ambig | use_specific | 0.80 | Name Plate DraWing for Pump and Motor | 22 | A CEP name plate drawing is inherently for the pump and motor nameplate, matching the specific 'for Pump and Motor' rule more directly than the generic name plate drawing rule. | FI | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | design_drawing | civil_design | compatible | condensate |  | condensate | query | condensate | match | true | false | 1 | 2 | 33.0135 | 0.7228 | 0.0325 | 0.0244 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127501 | AIR COMPRESSOR - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Air Compressor | Compressed Air System |  |  | GENERAL ARRANGEMENT DRAWING for Air Compressor |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | air¦compressor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7128 | 0.9138 | 0.9138 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 22.7727 | 0.6722 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-127502 | AIR COMPRESSOR - P&I DIAGRAM | P&ID | Air Compressor | Compressed Air System |  |  | P&ID for Compressed Air System | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6790 | 0.5537 | 0.5537 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 2 | 1 | 37.1924 | 0.7721 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127503 | AIR COMPRESSOR - AIR COMPRESSOR SPECIFICATION | Technical Specification | Air Compressor | Compressed Air System |  |  | Technical Specification for Air Compressor |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 2 | 42.9553 | 0.5795 | 0.0325 | 0.0325 | hybrid | structured_preferred | compressed_air | procurement | 9 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127504 | AIR COMPRESSOR - AIR DRYER SPECIFICATION | Technical Specification | Air Compressor | Compressed Air System |  |  | Technical Specification for Air Compressor |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 2 | 7 | 39.0393 | 0.5844 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127505 | AIR COMPRESSOR - AIR RECEIVER SPECIFICATION | Technical Specification | Air Compressor | Compressed Air System |  |  | Technical Specification for Air Compressor |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 39.0393 | 0.5487 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | procurement | 9 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127506 | AIR COMPRESSOR - AIR FILTER SPECIFICATION | Technical Specification | Air Compressor | Compressed Air System |  |  | Technical Specification for Air Compressor |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 8 | 39.0393 | 0.5509 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0SCA-127509 | AIR COMPRESSOR - FOUNDATION DRAWINGS | DRAWINGS | Air Compressor | Compressed Air System |  |  | DRAWINGS for Air Compressor | Air Compressor | Control System Configuration DraWings | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7726 | 0.5818 | 0.5818 | g_safe | [5 empty] | FA | 0EF3510W16A03 | (COMP Air PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-12-03 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 4 | 1 | 30.1400 | 0.6500 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0SCA-127510 | AIR COMPRESSOR - SINGLE LINE DIAGRAM | Single Line Diagram | Air Compressor | Compressed Air System |  |  | Single Line Diagram for Compressed Air System |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7573 | 0.9272 | 0.9272 | g_safe | [5 empty] | SKIP | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 3 | 1 | 32.6405 | 0.6822 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0SCA-127511 | AIR COMPRESSOR - SCHEMATIC & WIRING DIAGRAM | SCHEMATIC & WIRING DIAGRAM | Air Compressor | Compressed Air System |  |  | SCHEMATIC & WIRING DIAGRAM for Compressed Air System | Air Compressor | Interconnection Wiring Diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7319 | 0.7796 | 0.7796 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 1 | 32.6405 | 0.6453 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0SCA-127514 | AIR COMPRESSOR - CONTROL DESCRIPTION (PHILOSOPHY) | CONTROL DESCRIPTION | Air Compressor | Compressed Air System |  |  | CONTROL DESCRIPTION for Compressed Air System | Air Compressor | Control Philosophy | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | description | description | control_description | control_description | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7480 | 0.9244 | 0.9244 | g_safe | [5 empty] | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 35.7245 | 0.6602 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0SCA-127515 | AIR COMPRESSOR - PLC HMI GRAPHICS | Human Machine Interface GRAPHICS | Air Compressor | Compressed Air System |  |  | Human Machine Interface GRAPHICS for Air Compressor | [5 empty] | rule_query | other | other | human_machine_interface_graphics | o_andm | air¦compressor |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5663 | 0.6365 | 0.6365 | [7 empty] | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 |  | civil_design | query_unknown | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 4 | 4 | 27.8860 | 0.5388 | 0.0312 | 0.0234 | hybrid | structured_no_phase | compressed_air | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SCA-127516 | AIR COMPRESSOR - PLC HARDWIRED IO LIST | LIST | Air Compressor | Compressed Air System |  |  | I/O List for Air Compressor | Air Compressor | Datalink interface IO List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | io_list | io_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7048 | 0.6781 | 0.6781 | g_safe | [5 empty] | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 35.7245 | 0.6312 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SCA-127517 | AIR COMPRESSOR - DATALINK INTERFACE IO LIST | LIST | Air Compressor | Compressed Air System |  |  | I/O List for Air Compressor | Air Compressor | Datalink interface IO List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | io_list | io_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8822 | 0.9647 | 0.9647 | g_safe | [5 empty] | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 35.7245 | 0.6160 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0SCA-127518 | AIR COMPRESSOR - CONTROL LOGIC & LOOP DIAGRAM | & LOOP DIAGRAM | Air Compressor | Compressed Air System |  |  | & LOOP DIAGRAM for Compressed Air System | Air Compressor | Control Logic & Loop Diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | diagram | diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8622 | 0.9587 | 0.9587 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 2 | 32.6405 | 0.6654 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0SCA-127520 | AIR COMPRESSOR - INSTRUMENT LIST | INSTRUMENT LIST | Air Compressor | Compressed Air System |  |  | Instrument List for Air Compressor | Air Compressor | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9643 | 0.9893 | 0.9893 | g_safe | [5 empty] | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 35.7245 | 0.6196 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | procurement | 9 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SCA-127521 | AIR COMPRESSOR - INSTRUMENT SPECIFICATION | Technical Specification | Air Compressor | Compressed Air System |  |  | Technical Specification for Air Compressor |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 5 | 35.0861 | 0.6010 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0SCA-127522 | AIR COMPRESSOR - INSTRUMENTATION HOOK - UP DRAWING | DRAWING | Air Compressor | Compressed Air System |  |  | DRAWING for Air Compressor |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8077 | 0.9423 | 0.9423 | g_safe | [5 empty] | FI | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | design_drawing | civil_design | compatible | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 2 | 3 | 27.8860 | 0.5771 | 0.0320 | 0.0240 | hybrid | structured_preferred | compressed_air | system_design¦civil_design | 10 | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SCA-127523 | AIR COMPRESSOR - PLC PANEL DRAWING | DRAWING | Air Compressor | Compressed Air System |  |  | DRAWING for Air Compressor |  | PLC PANEL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8356 | 0.9507 | 0.6655 | g_safe | [5 empty] | FA | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | design_drawing | civil_design | compatible | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 4 | 3 | 27.8860 | 0.6046 | 0.0315 | 0.0236 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XF00-P0SCA-127524 | AIR COMPRESSOR - NAME PLATE DRAWING | DRAWING | Air Compressor | Compressed Air System |  |  | DRAWING for Air Compressor | Air Compressor | Name Plate draWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | drawing | drawing | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8608 | 0.9582 | 0.9582 | g_safe | [5 empty] | FA | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | design_drawing | civil_design | compatible | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 4 | 27.8860 | 0.6023 | 0.0318 | 0.0238 | hybrid | structured_preferred | compressed_air | system_design¦civil_design | 10 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0SCA-127525 | AIR COMPRESSOR - VALVE LIST | VALVE LIST | Air Compressor | Compressed Air System |  |  | Valve List for Air Compressor | Air Compressor | Valve List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | list | list | valve_list | valve_list | air¦compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9621 | 0.9886 | 0.9886 | g_safe | [5 empty] | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 1 | 35.7245 | 0.6136 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SCA-127526 | AIR COMPRESSOR - VALVE SPECIFICATION | Technical Specification | Air Compressor | Compressed Air System |  |  | Technical Specification for Air Compressor |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | air¦compressor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5363 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF3510W42A05 | (COMP Air PKG) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System |  | 2007-04-30 | procurement | procurement | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 5 | 35.0861 | 0.5327 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD16-P0SCA-127546 | AIR COMPRESSOR - EMBEDDED CONDUIT LAYOUT FOR CONTROL CABLES (FROM MCP TO EQUIPMENT) | Layout Drawing | Air Compressor | Compressed Air System |  |  | Layout Drawing for Compressed Air System |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7172 | 0.9151 | 0.6406 | g_safe | [5 empty] | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 2 | 2 | 32.1543 | 0.5956 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0SCA-127548 | AIR COMPRESSOR – I&C CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | Air Compressor | Compressed Air System |  |  | WIRING DIAGRAM for Compressed Air System | Air Compressor | Interconnection Wiring Diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7886 | 0.9366 | 0.9366 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 1 | 32.6405 | 0.6361 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127555 | AIR COMPRESSOR - AIR CHILLER - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | AIR COMPRESSOR - AIR CHILLER | Compressed Air System |  |  | GENERAL ARRANGEMENT DRAWING for AIR COMPRESSOR - AIR CHILLER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | air¦chiller¦compressor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6506 | 0.8952 | 0.8952 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 30.5581 | 0.6281 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127556 | AIR COMPRESSOR - AIR CHILLER - DATA SHEET | Data Sheet | AIR COMPRESSOR - AIR CHILLER | Compressed Air System |  |  | Data Sheet for AIR COMPRESSOR - AIR CHILLER | Air Compressor | Data Sheet for Valves | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | air¦chiller¦compressor |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7510 | 0.8086 | 0.8086 | g_safe | [5 empty] | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 4 | 43.6309 | 0.6210 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-127557 | AIR COMPRESSOR - AIR CHILLER - P&I DIAGRAM | P&ID | AIR COMPRESSOR - AIR CHILLER | Compressed Air System |  |  | P&ID for Compressed Air System | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6760 | 0.5528 | 0.5528 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 2 | 1 | 44.9779 | 0.7097 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128001 | CRANE - GA DRAWING FOR STEAM TURBINE BUILDING CRANE | GENERAL ARRANGEMENT DRAWING | CRANE |  | Steam Turbine Building |  | GENERAL ARRANGEMENT DRAWING for CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane¦stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7726 | 0.9318 | 0.9318 | g_safe | [5 empty] | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist¦stg |  | crane_hoist¦stg | query | stg | match | true | false | 1 | 2 | 19.0572 | 0.6294 | 0.0325 | 0.0325 | hybrid | structured_preferred | crane_hoist¦stg | civil_design | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128002 | CRANE - GA DRAWING FOR WORKSHOP CRANE | GENERAL ARRANGEMENT DRAWING | CRANE |  | Workshop & Storage Building |  | GENERAL ARRANGEMENT DRAWING for CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7726 | 0.9318 | 0.9318 | g_safe | [5 empty] | FA | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 27 | 4 | 12.3409 | 0.5758 | 0.0271 | 0.0163 | hybrid | structured_phase_gap | crane_hoist | civil_design |  | 2025-01-16 | 2025-02-15 | 2025-03-17 | 2025-04-01 | 2025-04-16 | 2025-05-01 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMM-128004 | CRANE - DATA SHEETS FOR STEAM TURBINE BUILDING CRANE | DATA SHEETS | CRANE |  | Steam Turbine Building |  | DATA SHEETS for CRANE | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | crane¦stg |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7509 | 0.5053 | 0.5053 | g_ambig | generic_ok | 0.86 |  | 3 | The competing specific rules are for steam turbine valve data sheets, not for a crane motor data sheet. | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist¦stg | crane_hoist | crane_hoist¦stg | query | crane_hoist | match | true | false | 1 | 1 | 40.5637 | 0.6137 | 0.0328 | 0.0328 | hybrid | structured_preferred | crane_hoist¦stg | procurement | 10 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMS-128005 | CRANE - DATA SHEETS FOR WORKSHOP CRANE | DATA SHEETS | CRANE |  | Workshop & Storage Building |  | DATA SHEETS for CRANE | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | crane |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7509 | 0.5053 | 0.5053 | g_safe | [5 empty] | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | true | false | 1 | 1 | 40.5637 | 0.6455 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMM-128007 | CRANE - MECHNICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | Detail Drawing | CRANE |  | Steam Turbine Building |  | Detail Drawing for Steam Turbine Building |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5518 | 0.6322 | 0.6322 | g_ambig | generic_ok | 0.84 |  | 19 | All competing specific rules are civil/structural ST building foundation/rebar details, not a crane mechanical coupling detail drawing. | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist¦stg |  | crane_hoist¦stg | query | stg | match | true | false | 4 | 2 | 8.1992 | 0.5274 | 0.0318 | 0.0318 | hybrid | structured_preferred | crane_hoist¦stg | civil_design | 10 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMS-128008 | CRANE - MECHNICAL DETAIL FOR WORKSHOP CRANE | Detail Drawing | CRANE |  | Workshop & Storage Building |  | Detail Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7561 | 0.7868 | 0.7868 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query | electrical | mismatch | true | false | 41 | 4 | 9.7017 | 0.5113 | 0.0255 | 0.0064 | hybrid | structured_phase_gap | crane_hoist | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMM-128010 | CRANE - ELECTRICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | Detail Drawing | CRANE |  | Steam Turbine Building |  | Detail Drawing for Steam Turbine Building |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5518 | 0.6322 | 0.6322 | g_ambig | generic_ok | 0.84 |  | 19 | All competing specific rules are civil/structural ST building foundation/rebar details, not a crane mechanical coupling detail drawing. | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist¦stg |  | crane_hoist¦stg | query | stg | match | true | false | 4 | 2 | 8.1992 | 0.5491 | 0.0318 | 0.0318 | hybrid | structured_preferred | crane_hoist¦stg | civil_design | 10 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMS-128011 | CRANE - ELECTRICAL DETAIL FOR WORKSHOP CRANE | Detail Drawing | CRANE |  | Workshop & Storage Building |  | Detail Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7561 | 0.7868 | 0.7868 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query | electrical | mismatch | true | false | 41 | 7 | 12.8430 | 0.5252 | 0.0248 | 0.0062 | hybrid | structured_phase_gap | crane_hoist | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SML-128013 | CRANE - GA DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | GENERAL ARRANGEMENT DRAWING | CRANE |  |  |  | GENERAL ARRANGEMENT DRAWING for CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7726 | 0.9318 | 0.9318 | g_safe | [5 empty] | FA | 0EF5550W00A01 | (Pipe Rack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 43 | 45 | 11.9335 | 0.5488 | 0.0192 | 0.0115 | hybrid | structured_phase_gap | crane_hoist | civil_design |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMQ-128014 | HOIST - GA DRAWING FOR FF PUMP HOUSE HOIST | GENERAL ARRANGEMENT DRAWING | HOIST |  | Fire Fighting PUMP HOUSE |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fire_protection¦hoist¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | crane_hoist¦fire_fighting |  | crane_hoist¦fire_fighting | query | fire_fighting¦hvac | match | false | false | 1 | 1 | 2.2120 | 0.4533 | 0.0328 | 0.0328 | hybrid | structured_preferred | crane_hoist¦fire_fighting | system_design | 2 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128015 | HOIST - GA DRAWING FOR AIR COMPRSSOR HOUSE HOIST | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 228 | 723 | 8.0086 | 0.4395 | 0.0047 | 0.0028 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128016 | HOIST - GA DRAWING FOR DM WATER TREATMENT HOIST | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_ambig | uncertain | 0.50 |  | 1 | The specific rule is for Water Treatment System GA, and while the title mentions DM water treatment hoist, it is unclear if it is governed under WTS or hoist equipment rules. | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | crane_hoist |  | crane_hoist | query | wts | mismatch | true | false | 61 | 120 | 12.3186 | 0.4982 | 0.0138 | 0.0035 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128017 | HOIST - GA DRAWING FOR CHAIN BLOCK | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 209 | 501 | 8.0086 | 0.4195 | 0.0055 | 0.0033 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SML-128018 | CRANE - DATA SHEETS FOR DEAERATOR SUPPORT STRUCTURE CRANE | DATA SHEETS | CRANE |  |  |  | DATA SHEETS for CRANE | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | crane |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7509 | 0.5053 | 0.5053 | g_safe | [5 empty] | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | true | false | 1 | 2 | 40.5637 | 0.6101 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMQ-128019 | HOIST - DATA SHEETS FOR FF PUMP HOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist¦pump | pump | scoped | match | match | match | passed |  | 0.5000 | 0.6443 | 0.5433 | 0.5433 | [6 empty] | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist |  | crane_hoist | query | crane_hoist | match | true | false | 1 | 1 | 42.1824 | 0.5736 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-11-07 | 2024-12-12 | 2025-01-16 | 2025-01-02 | 2025-02-06 | 2025-03-13 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128020 | HOIST - DATA SHEETS FOR AIR COMPRSSOR HOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Air Compressor | Data Sheet for Valves | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6084 | 0.5325 | 0.5325 | g_safe | [5 empty] | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | compressed_air | crane_hoist | query | crane_hoist | match | true | false | 1 | 2 | 42.1824 | 0.5744 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMG-128021 | HOIST - DATA SHEETS FOR DM WATER TREATMENT HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Water Treatment System | Motor Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6703 | 0.6011 | 0.6011 | [6 empty] | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | wts | crane_hoist | query | crane_hoist | match | true | false | 1 | 1 | 42.1824 | 0.5496 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128022 | HOIST - DATA SHEETS FOR CHAIN BLOCK | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | g_safe | [5 empty] | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | true | false | 1 | 1 | 30.9529 | 0.5957 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SML-128023 | CRANE - MECHNICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | MECHNICAL DETAIL | CRANE |  |  |  | MECHNICAL DETAIL for CRANE |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | crane |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7571 | 0.7871 | 0.7871 | g_safe | [5 empty] | FI | 0CF3530W42A09 | (Crane & Hoist) Crane Erection for BSDG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-03-08 | 2008-04-08 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | bsedg¦crane_hoist | match | true | false | 2 | 1 | 37.7358 | 0.5706 | 0.0325 | 0.0244 | hybrid | structured_no_phase | crane_hoist | [5 empty] | 2024-12-09 | 2025-01-08 | 2025-02-07 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMQ-128024 | HOIST - MECHANICAL DETAIL FOR FF PUMP HOUSE HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for Pump |  | Pump Pit Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7122 | 0.6803 | 0.5783 | [6 empty] | FA | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-04-16 | 2008-05-16 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | compressed_air¦crane_hoist | match | true | false | 3 | 1 | 36.5994 | 0.5247 | 0.0323 | 0.0242 | hybrid | structured_no_phase | crane_hoist |  |  | 2024-12-03 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.60 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMU-128025 | HOIST - MECHANICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for HOIST |  | MECHANICAL DETAIL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7646 | 0.6961 | 0.4872 | g_safe | [5 empty] | FA | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-04-16 | 2008-05-16 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | compressed_air¦crane_hoist | match | true | false | 1 | 1 | 39.5348 | 0.6193 | 0.0328 | 0.0246 | hybrid | structured_no_phase | crane_hoist |  |  | 2024-12-03 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMG-128026 | HOIST - MECHANICAL DETAIL FOR DM WATER TREATMENT HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for HOIST | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.6000 | 0.5745 | 0.5924 | 0.5924 | [6 empty] | FA | 0CF3530W42A09 | (Crane & Hoist) Crane Erection for BSDG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-03-08 | 2008-04-08 |  | installation | query_unknown | crane_hoist | wts | crane_hoist | query | bsedg¦crane_hoist | match | true | false | 2 | 4 | 36.5994 | 0.4991 | 0.0318 | 0.0238 | hybrid | structured_no_phase | crane_hoist |  |  | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | 2025-01-08 | 2025-02-07 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SML-128027 | CRANE - ELECTRICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | ELECTRICAL DETAIL | CRANE |  |  |  | ELECTRICAL DETAIL for CRANE |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | crane |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7400 | 0.7820 | 0.7820 | g_safe | [5 empty] | FI | 0CF3530W42A09 | (Crane & Hoist) Crane Erection for BSDG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-03-08 | 2008-04-08 |  | installation | query_unknown | crane_hoist |  | crane_hoist | query | bsedg¦crane_hoist | match | true | false | 2 | 3 | 37.7358 | 0.5764 | 0.0320 | 0.0240 | hybrid | structured_no_phase | crane_hoist | [5 empty] | 2024-12-09 | 2025-01-08 | 2025-02-07 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMC-128028 | HOIST - GA DRAWING FOR CENTRAL CONTROL BUILDING HOIST | GENERAL ARRANGEMENT DRAWING | HOIST |  | Central Control Building |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | ccr¦central¦hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_safe | [5 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 13 | 1 | 29.3125 | 0.6285 | 0.0301 | 0.0181 | hybrid | structured_phase_gap | crane_hoist | civil_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128029 | HOIST - GA DRAWING FOR WAREHOUSE HOIST | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 185 | 548 | 8.0086 | 0.4250 | 0.0057 | 0.0034 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128030 | HOIST - GA DRAWING FOR WASTE WATER TREATMENT HOIST | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_ambig | uncertain | 0.50 |  | 1 | The specific rule is for Water Treatment System GA, and while the title mentions DM water treatment hoist, it is unclear if it is governed under WTS or hoist equipment rules. | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | crane_hoist |  | crane_hoist | query | wts | mismatch | true | false | 20 | 176 | 20.0784 | 0.4901 | 0.0167 | 0.0042 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128031 | HOIST - GA DRAWING FOR CPP HOIST | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 176 | 457 | 8.0086 | 0.4569 | 0.0062 | 0.0037 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128032 | JIB CRANE - GA DRAWING FOR AIR COOLED CONDENSER JIB CRANE | GENERAL ARRANGEMENT DRAWING | JIB CRANE |  |  |  | GENERAL ARRANGEMENT DRAWING for JIB CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | acc¦air¦condenser¦cooled¦crane¦jib |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7260 | 0.9178 | 0.9178 | g_ambig | use_specific | 0.78 | ACC - General Arrangement | 1 | The jib crane is explicitly for the Air Cooled Condenser area, aligning with the ACC-specific GA rule rather than the generic GA timeline. | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 247 | 406 | 8.0086 | 0.4557 | 0.0054 | 0.0032 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMC-128033 | HOIST - DATA SHEETS FOR CENTRAL CONTROL BUILDING HOIST | DATA SHEETS | HOIST |  | Central Control Building |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | ccr¦central¦hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for DCS/CCR emergency push button (control system), not for a hoist motor datasheet. | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | true | false | 1 | 2 | 42.1824 | 0.5898 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMS-128034 | HOIST - DATA SHEETS FOR WAREHOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | g_safe | [5 empty] | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | true | false | 1 | 1 | 42.1824 | 0.6114 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMG-128035 | HOIST - DATA SHEETS FOR WASTE WATER TREATMENT HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Water Treatment System | Pump Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | datasheet | datasheet | data_sheet | data_sheet | hoist¦wts | pump¦wts | scoped | match | match | match | passed |  | 0.5714 | 0.6075 | 0.5823 | 0.5823 | [6 empty] | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | wts | crane_hoist | query | crane_hoist | match | true | false | 1 | 1 | 42.1824 | 0.5577 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMM-128036 | HOIST - DATA SHEETS FOR CPP HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | Motor data sheet | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hoist |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7211 | 0.4963 | 0.4963 | g_safe | [5 empty] | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | crane_hoist | crane_hoist | query | crane_hoist | match | true | false | 1 | 1 | 42.1824 | 0.6211 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128037 | JIB CRANE - DATA SHEETS FOR AIR COOLED CONDENSER JIB CRANE | DATA SHEETS | JIB CRANE |  |  |  | DATA SHEETS for JIB CRANE | Air Compressor | Data Sheet for Valves | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | datasheet | datasheet | data_sheet | data_sheet | acc¦air¦condenser¦cooled¦crane¦jib |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5171 | 0.5051 | 0.5051 | g_ambig | generic_ok | 0.85 |  | 16 | All competing specific rules are for ACC equipment datasheets, whereas this document is for an ACC jib crane. | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | compressed_air | crane_hoist | query | crane_hoist | match | true | false | 2 | 2 | 40.5637 | 0.5804 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMC-128038 | HOIST - MECHANICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | Detail Drawing | HOIST |  | Central Control Building |  | Detail Drawing for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8054 | 0.8016 | 0.8016 | [6 empty] | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 24 | 3 | 17.6674 | 0.5518 | 0.0278 | 0.0167 | hybrid | structured_phase_gap | crane_hoist | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMS-128039 | HOIST - MECHANICAL DETAIL FOR WAREHOUSE HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | g_safe | [5 empty] | FI | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 37 | 13 | 11.4430 | 0.5063 | 0.0240 | 0.0108 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 |  | false | false | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMG-128040 | HOIST - MECHANICAL DETAIL FOR WASTE WATER TREATMENT HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.6731 | 0.7619 | 0.7619 | [6 empty] | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | design_drawing | civil_design | compatible | crane_hoist | wts | crane_hoist | query | wts | mismatch | true | false | 30 | 2 | 19.2922 | 0.4878 | 0.0272 | 0.0051 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMM-128041 | HOIST - MECHANICAL DETAIL FOR CPP HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | g_safe | [5 empty] | FI | 0EF5560W16A02 | (M&E WORKSHOP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 | 2008-04-09 | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | electrical | mismatch | false | false | 79 | 2441 | 8.2543 | 0.3240 | 0.0076 | 0.0014 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMU-128042 | JIB CRANE - MECHANICAL DETAIL FOR AIR COOLED CONDENSER JIB CRANE | Detail Drawing | JIB CRANE |  |  |  | Detail Drawing for ACC | CONDENSER | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.8000 | 0.6664 | 0.7599 | 0.7599 | [6 empty] | FA | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | crane_hoist | acc | crane_hoist | query | acc¦condensate | mismatch | true | false | 30 | 4 | 8.4959 | 0.5172 | 0.0267 | 0.0050 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMC-128043 | HOIST - ELECTRICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | Detail Drawing | HOIST |  | Central Control Building |  | Detail Drawing for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8054 | 0.8016 | 0.8016 | [6 empty] | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 28 | 2 | 17.6674 | 0.5501 | 0.0275 | 0.0165 | hybrid | structured_phase_gap | crane_hoist | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMS-128044 | HOIST - ELECTRICAL DETAIL FOR WAREHOUSE HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | g_safe | [5 empty] | FI | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 40 | 26 | 11.4430 | 0.4985 | 0.0216 | 0.0097 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 |  | false | false | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMQ-128045 | HOIST - ELECTRICAL DETAIL FOR FF PUMP HOUSE HOIST | Detail Drawing | HOIST |  | Fire Fighting PUMP HOUSE |  | Detail Drawing for Fire Fighting PUMP HOUSE |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | fighting¦fire¦fire_protection¦house¦pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5336 | 0.6268 | 0.6268 | g_ambig | uncertain | 0.45 |  | 30 | The title indicates an electrical detail for a hoist, while the competing rules are mostly civil/structural foundation/pump pit details, so equipment applicability is unclear. | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | crane_hoist¦fire_fighting |  | crane_hoist¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 4.6749 | 0.5103 | 0.0320 | 0.0240 | hybrid | structured_preferred | crane_hoist¦fire_fighting | system_design¦civil_design | 10 | 2024-06-12 | 2024-07-12 | 2024-08-11 | 2024-08-26 | 2024-09-10 | 2024-09-25 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMU-128046 | HOIST - ELECTRICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | g_safe | [5 empty] | FI | 2EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-02 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | fgp | mismatch | true | false | 474 | 2 | 6.7600 | 0.5724 | 0.0180 | 0.0034 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMG-128047 | HOIST - ELECTRICAL DETAIL FOR DM WATER TREATMENT HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | g_ambig | uncertain | 0.50 |  | 11 | The document is a hoist electrical detail for DM water treatment, but the competing rules target water treatment building/pipe support/equipment assembly details rather than a hoist detail specificall | FI | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 760 | 30 | 3.6346 | 0.4823 | 0.0123 | 0.0055 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMG-128048 | HOIST - ELECTRICAL DETAIL FOR WASTE WATER TREATMENT HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST | WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | hoist¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.6598 | 0.7579 | 0.7579 | [6 empty] | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | design_drawing | civil_design | compatible | crane_hoist | wts | crane_hoist | query | wts | mismatch | true | false | 23 | 1 | 21.6660 | 0.4981 | 0.0284 | 0.0053 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMM-128049 | HOIST - ELECTRICAL DETAIL FOR CPP HOIST | Detail Drawing | HOIST |  |  |  | Detail Drawing for HOIST |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | hoist |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5985 | 0.6462 | 0.6462 | g_safe | [5 empty] | FI | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-06-20 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query | hrsg | mismatch | false | false | 1247 | 122 | 2.3034 | 0.4729 | 0.0063 | 0.0012 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128051 | JIB CRANE - GA DRAWING FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | GENERAL ARRANGEMENT DRAWING | JIB CRANE |  |  |  | GENERAL ARRANGEMENT DRAWING for JIB CRANE |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | crane¦jib¦pump¦tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7260 | 0.9178 | 0.9178 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 294 | 349 | 8.0086 | 0.4366 | 0.0053 | 0.0032 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128052 | JIB CRANE - DATA SHEETS FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | DATA SHEETS | JIB CRANE |  |  |  | DATA SHEETS for JIB CRANE |  | ACC - Drain Pump Datasheet | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | title | datasheet | datasheet | data_sheet | data_sheet | crane¦jib¦pump¦tank | acc¦pump | scoped | match | match | match | passed |  | 0.5000 | 0.5764 | 0.5229 | 0.5229 | [6 empty] | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | procurement | procurement | match | crane_hoist | acc | crane_hoist | query | crane_hoist | match | true | false | 1 | 2 | 40.5637 | 0.5573 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | crane_hoist | procurement |  | 2025-03-18 | 2025-04-17 | 2025-05-17 | 2025-06-01 | 2025-06-16 | 2025-07-01 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128053 | JIB CRANE - MECHANICAL DETAIL FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | Detail Drawing | JIB CRANE |  |  |  | Detail Drawing for Tank |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump¦tank |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6199 | 0.6526 | 0.6526 | g_ambig | generic_ok | 0.80 |  | 50 | The competing rules are for pump pits/tanks/foundations and other equipment details, not for a jib crane detail drawing. | FI | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | design_drawing | civil_design | compatible | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 721 | 33 | 4.9357 | 0.4579 | 0.0120 | 0.0054 | hybrid | structured_phase_gap | crane_hoist | system_design¦civil_design |  | 2024-05-29 | 2024-06-28 | 2024-07-28 | 2024-08-12 | 2024-08-27 | 2024-09-11 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128060 | PORTABLE GANTRY - GA DRAWING | GENERAL ARRANGEMENT DRAWING | PORTABLE GANTRY |  |  |  | GENERAL ARRANGEMENT DRAWING for PORTABLE GANTRY |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gantry¦portable |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7097 | 0.9129 | 0.9129 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | false | 34 | 306 | 10.6973 | 0.4512 | 0.0134 | 0.0100 | hybrid | structured_no_system |  | system_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128070 | HOIST - GA DRAWING FOR ST GSUT | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | hoist¦stg |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7429 | 0.9229 | 0.9229 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | crane_hoist |  | crane_hoist | query |  | activity_unscoped | true | true | 182 | 772 | 8.0086 | 0.4132 | 0.0053 | 0.0032 | hybrid | structured_phase_gap | crane_hoist | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128101 | CRANE - NAME PLATE DRAWING FOR STEAM TURBINE BUILDING CRANE | DRAWING | CRANE |  | Steam Turbine Building |  | DRAWING for Steam Turbine Building |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6508 | 0.8952 | 0.8952 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for steam turbine control cabinet internal arrangement, not a crane name plate drawing. | FI | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | crane_hoist¦stg |  | crane_hoist¦stg | query | stg | match | true | false | 6 | 1 | 8.1992 | 0.5234 | 0.0315 | 0.0315 | hybrid | structured_preferred | crane_hoist¦stg | civil_design | 10 | 2024-07-19 | 2024-08-18 | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-11-01 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128102 | CRANE - NAME PLATE DRAWING FOR WORKSHOP CRANE | DRAWING | CRANE |  | Workshop & Storage Building |  | DRAWING for CRANE |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | crane |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6723 | 0.9017 | 0.9017 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query | electrical | mismatch | true | false | 85 | 66 | 9.7017 | 0.4854 | 0.0148 | 0.0037 | hybrid | structured_phase_gap | crane_hoist | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SML-128103 | CRANE - NAME PLATE DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | DRAWING | CRANE |  |  |  | DRAWING for CRANE |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | crane |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6570 | 0.8971 | 0.8971 | g_safe | [5 empty] | FI | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match | crane_hoist |  | crane_hoist | query | bop | mismatch | false | false | 99 | 643 | 8.2027 | 0.4417 | 0.0077 | 0.0019 | hybrid | structured_phase_gap | crane_hoist | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GM-128501 | SUMP PUMP - PUMP OUTLINE DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for SUMP PUMP |  | Pump Outline DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | pump¦sump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.7869 | 0.9361 | 0.9361 | [6 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 81 | 52 | 14.0842 | 0.5014 | 0.0160 | 0.0096 | hybrid | structured_no_system |  | system_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GM-128502 | SUMP PUMP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | SUMP PUMP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for SUMP PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | pump¦sump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8104 | 0.9431 | 0.9431 | [6 empty] | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | true | false | 5 | 4 | 17.2807 | 0.5292 | 0.0310 | 0.0233 | hybrid | structured_no_system |  | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GM-128503 | SUMP PUMP - PUMP SECTIONAL DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | [6 empty] | FA | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 40 | 41 | 14.8071 | 0.5144 | 0.0199 | 0.0119 | hybrid | structured_no_system |  | civil_design |  | 2024-05-29 | 2024-06-28 | 2024-07-28 | 2024-08-12 | 2024-08-27 | 2024-09-11 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0GM-128504 | SUMP PUMP - MECHANICAL SEAL SPECIFICATION | Technical Specification | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | g_safe | [5 empty] | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | false | 2 | 2 | 15.8838 | 0.5019 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0GM-128505 | SUMP PUMP - COUPLING SPECIFICATION | Technical Specification | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | g_safe | [5 empty] | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | false | 2 | 2 | 15.8838 | 0.4781 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0GM-128506 | SUMP PUMP - FOUNDATION DRAWINGS | DRAWINGS | SUMP PUMP |  |  |  | DRAWINGS for SUMP PUMP |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pump¦sump | pump | scoped | match | match | match | passed |  | 0.3333 | 0.6794 | 0.4372 | 0.3060 | [6 empty] | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | false | 10 | 14 | 11.1294 | 0.5068 | 0.0278 | 0.0208 | hybrid | structured_no_system |  | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.30 |  | false | false | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0GM-128507 | SUMP PUMP - MOTOR SPECIFICATION | Technical Specification | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | g_safe | [5 empty] | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | false | 3 | 2 | 15.8838 | 0.4590 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0GM-128508 | SUMP PUMP - INSTRUMENT SPECIFICATION | Technical Specification | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | pump¦sump |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5219 | 0.6232 | 0.4363 | g_safe | [5 empty] | FA | 1EF3020W42A03 | (CEP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump |  | 2007-05-31 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | false | 3 | 2 | 15.8838 | 0.5059 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GM-128509 | SUMP PUMP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | SUMP PUMP |  |  |  | HOOK - UP DRAWING for SUMP PUMP | FireFighting | Hook Up DraWing | 1 | start+4W<=FA<=FC<=start+10W | FA ∈ [start+28d, start+70d] ¦ FC ∈ [start+28d, start+70d] | rule_query | drawing | drawing | drawing | drawing | pump¦sump |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6441 | 0.7182 | 0.7182 | g_ambig | use_specific | 0.75 | Instrumentation Hook-up DraWing | 22 | The document title is explicitly an instrumentation hook-up drawing, matching the specific rule with a different VT than the generic hook-up drawing rule. | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 19 | 24 | 23.1671 | 0.5261 | 0.0246 | 0.0111 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-12 | 2024-05-03 | 2024-05-24 | 2024-05-24 | 2024-06-14 | 2024-07-05 | generated | 0.90 |  | false | false | 0.38 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XF00-P0GM-128510 | SUMP PUMP - NAME PLATE DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for SUMP PUMP |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pump¦sump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.6652 | 0.6662 | 0.4664 | [6 empty] | FA | 0EF3025W16A12 | (Intake Pump Station) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-06-04 | 2007-10-03 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 5 | 6 | 10.1912 | 0.4818 | 0.0305 | 0.0137 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.41 | needs_review | rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0GM-128511 | SUMP PUMP - SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING FOR WASTE WATER TRANSFER SYSTEM | DRAWING | SUMP PUMP | WASTE WATER TRANSFER SYSTEM |  |  | DRAWING for WASTE WATER TRANSFER SYSTEM |  | SCHEMATIC AND WIRING DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | wiring_diagram | wiring_diagram | pump¦transfer¦waste¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6143 | 0.8843 | 0.6190 | g_ambig | uncertain | 0.55 |  | 3 | The title is a schematic/wiring diagram with control panel layout, but the competing rules are for interconnection/rotation sensor wiring and may or may not be the intended subtype. | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 3 | 31.7790 | 0.5242 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GM-128512 | SUMP PUMP - INSTRUMENT LIST | LIST | SUMP PUMP |  |  |  | Instrument List for SUMP PUMP |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | list | list | instrument_list | instrument_list | pump¦sump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6310 | 0.6560 | 0.6560 | g_ambig | use_specific | 0.70 | Instrument List and datasheet / draWing | 1 | The competing rule explicitly covers an instrument list bundled with datasheet/drawing, which is a plausible intended scope for this instrument list deliverable. | FI | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | procurement | procurement | match |  |  |  |  | condensate | query_unscoped | false | false | 4 | 9 | 16.5472 | 0.5514 | 0.0301 | 0.0226 | hybrid | structured_no_system |  | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129001 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | PLANT INTERNAL WATER DISTRIBUTION |  |  |  | GENERAL ARRANGEMENT DRAWING for PLANT INTERNAL WATER DISTRIBUTION |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | distribution¦internal¦plant¦water |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6644 | 0.8993 | 0.8993 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | false | 235 | 12 | 9.4882 | 0.6055 | 0.0173 | 0.0130 | hybrid | structured_no_system |  | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129002 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | PLANT INTERNAL WATER DISTRIBUTION |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for PLANT INTERNAL WATER DISTRIBUTION |  | DATA SHEET & CHARACTERISTIC CURVE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | distribution¦internal¦plant¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6541 | 0.8962 | 0.6274 | g_safe | [5 empty] | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | true | false | 3 | 4 | 16.9363 | 0.5626 | 0.0315 | 0.0236 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129003 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - PUMP SECTIONAL DRAWING | DRAWING | PLANT INTERNAL WATER DISTRIBUTION |  |  |  | DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7061 | 0.6785 | 0.6785 | [6 empty] | FA | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 131 | 11 | 10.2606 | 0.5746 | 0.0193 | 0.0116 | hybrid | structured_no_system |  | civil_design |  | 2024-05-29 | 2024-06-28 | 2024-07-28 | 2024-08-12 | 2024-08-27 | 2024-09-11 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129004 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MECHANICAL SEAL SPECIFICATION | Technical Specification | PLANT INTERNAL WATER DISTRIBUTION |  |  |  | Technical Specification for PLANT INTERNAL WATER DISTRIBUTION |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | distribution¦internal¦plant¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5129 | 0.6205 | 0.4344 | g_safe | [5 empty] | FA | 0EF3010W42A04 | (WTS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System |  | 2007-05-30 | procurement | procurement | match |  |  |  |  | wts | query_unscoped | false | false | 2 | 7 | 14.8649 | 0.5556 | 0.0311 | 0.0233 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129008 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | PLANT INTERNAL WATER DISTRIBUTION |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for PLANT INTERNAL WATER DISTRIBUTION | FireFighting | Motor Data Sheet | 1 | start+20W<=FA<=FC<=start+30W | FA ∈ [start+140d, start+210d] ¦ FC ∈ [start+140d, start+210d] | title | datasheet | datasheet | data_sheet | data_sheet | distribution¦internal¦plant¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.4994 | 0.6748 | 0.6748 | g_safe | [5 empty] | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | true | false | 4 | 1 | 16.9363 | 0.5850 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement |  | 2024-09-14 | 2024-10-19 | 2024-11-23 | 2024-11-09 | 2024-12-14 | 2025-01-18 | generated | 0.90 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129011 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | PUMPS |  |  |  | Instrument List for PUMPS |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | pumps |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7164 | 0.6816 | 0.6816 | g_safe | [5 empty] | FI | 3PF3015W58A14P | (FW PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | 2007-11-02 | 2008-08-29 | procurement | procurement | match |  |  |  |  | feedwater | query_unscoped | false | false | 50 | 9 | 13.1532 | 0.5848 | 0.0236 | 0.0177 | hybrid | structured_no_system |  | procurement |  | 2025-01-25 | 2025-02-24 | 2025-03-26 | 2025-04-10 | 2025-04-25 | 2025-05-10 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129013 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING | PUMPS |  |  |  | INSTRUMENTATION HOOK - UP DRAWING for PUMPS |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | pumps |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8231 | 0.9469 | 0.9469 | g_safe | [5 empty] | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 1 | 1 | 29.4341 | 0.6251 | 0.0328 | 0.0148 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 |  | false | false | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129014 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - NAME PLATE DRAWING | DRAWING |  |  |  |  | DRAWING |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.5508 | 0.8652 | 0.8652 | [6 empty] | FI | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 975 | 2 | 2.6624 | 0.5995 | 0.0171 | 0.0077 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-08-21 | 2024-09-20 | 2024-10-20 | 2024-11-04 | 2024-11-19 | 2024-12-04 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129031 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | PUMPS | Steam System |  |  | GENERAL ARRANGEMENT DRAWING for PUMPS |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fgp¦pumps |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7413 | 0.9224 | 0.9224 | g_ambig | uncertain | 0.40 |  | 2 | A competing rule has the exact same keyword 'General Arrangement DraWing' but a different VT, and there is no equipment qualifier to determine which GA timeline applies. | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 8.4595 | 0.6495 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129032 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for FGP |  | DATA SHEET & CHARACTERISTIC CURVE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7842 | 0.9353 | 0.6547 | g_ambig | uncertain | 0.35 |  | 10 | The document title is for steam drain/FGP demin supply pumps while the equipment field says Fuel Gas Package, so it is unclear which specific datasheet/curve rule set should govern. | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 18.8274 | 0.6872 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129033 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - PUMP SECTIONAL DRAWING | PUMP SECTIONAL DRAWING | PUMPS | Steam System |  |  | PUMP SECTIONAL DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.9013 | 0.9704 | 0.9704 | [6 empty] | FA | 2EF3020W16A15.1 | (Clean Drain Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-02-29 | civil_design | civil_design | match | steam |  | steam | query |  | activity_unscoped | true | true | 20 | 665 | 16.7930 | 0.5210 | 0.0139 | 0.0083 | hybrid | structured_phase_gap | steam | civil_design |  | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129034 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MECHANICAL SEAL SPECIFICATION | Technical Specification | Fuel Gas Package |  |  |  | Technical Specification for FGP |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.3967 | 0.4690 | 0.4690 | g_safe | [5 empty] | FA | 2PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-05-14 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 19.4509 | 0.6644 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fgp | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129035 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for FGP | FireFighting | Motor Data Sheet | 1 | start+20W<=FA<=FC<=start+30W | FA ∈ [start+140d, start+210d] ¦ FC ∈ [start+140d, start+210d] | title | datasheet | datasheet | data_sheet | data_sheet | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5362 | 0.6859 | 0.6859 | g_ambig | uncertain | 0.35 |  | 10 | Although it is a motor datasheet/curve, the title/equipment mismatch (pumps vs Fuel Gas Package) prevents confidently selecting a more specific rule. | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp |  | fgp | query | fgp | match | true | false | 3 | 1 | 18.8274 | 0.6990 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fgp | procurement |  | 2024-07-19 | 2024-08-23 | 2024-09-27 | 2024-09-13 | 2024-10-18 | 2024-11-22 | generated | 0.90 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129036 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | PUMPS | Steam System |  |  | Instrument List for PUMPS |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | fgp¦pumps |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7164 | 0.6816 | 0.6816 | g_ambig | uncertain | 0.45 |  | 2 | There are competing rules including an identical 'Instrument List' keyword with a different VT, but no additional qualifier is provided to choose between them. | FI | 2PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-10-01 | 2008-06-02 | procurement | procurement | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 16.2844 | 0.6588 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | procurement | 9 | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129037 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING | PUMPS | Steam System |  |  | INSTRUMENTATION HOOK - UP DRAWING for PUMPS |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | fgp¦pumps |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8231 | 0.9469 | 0.9469 | g_ambig | generic_ok | 0.80 |  | 18 | None of the competing specific rules target instrumentation hook-up drawings for pumps; they address other drawing subtypes (piping, platforms, nameplates, etc.). | FI | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | true | false | 2 | 1 | 14.2605 | 0.6780 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129038 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - NAME PLATE DRAWING | DRAWING | Fuel Gas Package |  |  |  | DRAWING for FGP |  | Name Plate DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | title | drawing | drawing | drawing | drawing | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5955 | 0.8786 | 0.8786 | g_ambig | use_specific | 0.70 | Name Plate DraWing | 19 | A competing specific rule exactly matches 'Name Plate DraWing' and provides a different VT, indicating the nameplate timeline should follow that specific rule set. | FI | 2EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | fgp |  | fgp | query | fgp | match | true | false | 1 | 3 | 12.3026 | 0.6444 | 0.0323 | 0.0242 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-12-20 | 2025-01-19 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-04-04 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129050 | CHILLED WATER DISTRIBUTION PUMP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | PUMP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for PUMP |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8856 | 0.9657 | 0.9657 | [6 empty] | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | true | false | 3 | 18 | 21.0540 | 0.5535 | 0.0287 | 0.0215 | hybrid | structured_no_system |  | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129051 | CHILLED WATER DISTRIBUTION PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for PUMP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7387 | 0.9216 | 0.9216 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | false | 69 | 708 | 13.9610 | 0.4652 | 0.0091 | 0.0068 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129053 | CHILLED WATER DISTRIBUTION PUMP - PUMP SECTIONAL DRAWING | PUMP SECTIONAL DRAWING | PUMP |  |  |  | PUMP SECTIONAL DRAWING for Pump |  | Pump Sectional DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.9013 | 0.9704 | 0.9704 | [6 empty] | FA | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 47 | 36 | 22.3341 | 0.5777 | 0.0198 | 0.0119 | hybrid | structured_no_system |  | civil_design |  | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129055 | CHILLED WATER DISTRIBUTION PUMP - MECHANICAL SEAL SPECIFICATION | Technical Specification |  |  |  |  | Technical Specification for Pump |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | pump |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4967 | 0.4990 | 0.4990 | g_safe | [5 empty] | FA | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | false | 25 | 1 | 12.9248 | 0.6023 | 0.0282 | 0.0211 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129056 | CHILLED WATER DISTRIBUTION PUMP - NAME PLATE DRAWING | DRAWING |  |  |  |  | DRAWING for Pump |  | HRSG - Spec. & DraWing for Recirculation Pump | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | drawing | drawing | drawing | drawing | pump | hrsg¦pump | scoped | match | match | match | passed |  | 0.5000 | 0.5158 | 0.5047 | 0.5047 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible |  | hrsg | hrsg | rule | hrsg | match | false | false | 1 | 2 | 2.0974 | 0.4828 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.27 | needs_review_activity | default_fc_window;activity_phase_status=compatible;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129060 | CHILLED WATER DISTRIBUTION PUMP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE |  |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for Pump |  | Pump Data sheet & Characteristic curve | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.8909 | 0.9673 | 0.9673 | [6 empty] | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | procurement | procurement | match |  |  |  |  | service_water | query_unscoped | true | false | 2 | 17 | 17.1083 | 0.5426 | 0.0291 | 0.0218 | hybrid | structured_no_system |  | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129063 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | PUMP |  |  |  | Instrument List for PUMP |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | pump |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7420 | 0.6893 | 0.6893 | g_ambig | generic_ok | 0.55 |  | 1 | The competing rule is not clearly equipment-specific to chilled water distribution pumps (it reads like an alternate naming of the same deliverable), so the generic Instrument List timeline can stand. | FI | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | false | 35 | 13 | 17.3579 | 0.5503 | 0.0242 | 0.0182 | hybrid | structured_no_system |  | procurement |  | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=query_unscoped;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129064 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING | PUMP |  |  |  | INSTRUMENTATION HOOK - UP DRAWING for PUMP |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | pump |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8256 | 0.9477 | 0.9477 | g_ambig | generic_ok | 0.70 |  | 21 | All competing rules refer to different drawing types or specific pump services (ACC/HRSG/BFW/etc.) rather than an instrumentation hook-up drawing for the chilled water distribution pump. | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 14 | 9 | 29.4339 | 0.5765 | 0.0280 | 0.0126 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 |  | false | false | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GCF-130001 | SYSTEM DESCRIPTION FOR WATER TREATMENT PLANT | System Description | Water Treatment Plant | Water Treatment System |  |  | System Description for Water Treatment System | Water Treatment System | System Description for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9748 | 0.9925 | 0.9925 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 40.1390 | 0.7495 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130002 | GENERAL ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | GENERAL ARRANGEMENT DRAWING | Water Treatment Plant | Water Treatment System |  |  | GENERAL ARRANGEMENT DRAWING for Water Treatment Plant |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | plant¦treatment¦water¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6772 | 0.9032 | 0.9032 | g_ambig | use_specific | 0.90 | General Arrangement DraWing for Water Treatment System | 1 | The document is a GA for the Water Treatment Plant, which matches the water treatment system-specific GA rule. | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 32.9822 | 0.6977 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GCF-130003 | PROCESS FLOW DIAGRAM FOR WATER TREATMENT PLANT | PROCESS FLOW DIAGRAM | Water Treatment Plant | Water Treatment System |  |  | PROCESS FLOW DIAGRAM for Water Treatment System | Water Treatment System | Process FloW Diagram & Mass Balance for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7778 | 0.8387 | 0.7961 | 0.7961 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 2 | 43.1731 | 0.7034 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GCF-130004 | PIPING & INSTRUMENT DIAGRAM FOR WATER TREATMENT PLANT | PIPING & INSTRUMENT DIAGRAM | Water Treatment Plant | Water Treatment System |  |  | PIPING & INSTRUMENT DIAGRAM for Water Treatment System | Water Treatment System | Control Configuration Diagram for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.7289 | 0.7187 | 0.7187 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 48.5219 | 0.8024 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GCF-130005 | CALCULATION SHEET FOR WATER TREATMENT PLANT | CALCULATION SHEET | Water Treatment Plant | Water Treatment System |  |  | CALCULATION SHEET for Water Treatment Plant | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | plant¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.9017 | 0.8539 | 0.8539 | [6 empty] | FA | 0EF3010W16A01 | (WTS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-01-09 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 1 | 31.3486 | 0.6345 | 0.0318 | 0.0318 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130006 | MCC ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | General Arrangement Drawing | Motor Control Center |  |  |  | General Arrangement Drawing for Motor Control Center |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | center¦motor¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6473 | 0.8942 | 0.8942 | g_ambig | uncertain | 0.45 |  | 1 | Although the title mentions water & waste water treatment plant, the equipment is MCC, so it is unclear whether the water treatment system GA rule should override the generic GA rule. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 110 | 13 | 14.6840 | 0.5437 | 0.0196 | 0.0117 | hybrid | structured_phase_gap | mv_lv | system_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0GCF-130007 | CONTROL PANEL ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | General Arrangement Drawing |  | Water Treatment System |  |  | General Arrangement Drawing for Water Treatment System | Water Treatment System | General Arrangement DraWing for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9598 | 0.9879 | 0.9879 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 2 | 1 | 29.0869 | 0.6958 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | system_design | 5 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GCF-130008 | VALVE LIST FOR WATER TREATMENT PLANT | LIST | VALVE | Water Treatment System |  |  | Valve List for VALVE |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | valve¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.9375 | 0.7479 | 0.7479 | g_ambig | use_specific | 0.85 | Valve List & Data Sheet for Water Treatment System | 1 | The valve list is explicitly for the Water Treatment Plant, aligning with the water treatment system-specific valve list/data sheet rule. | FA | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match | wts |  | wts | query | wts | match | true | false | 3 | 1 | 29.1893 | 0.6819 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GCF-130009 | INSTRUMENT LIST FOR WATER TREATMENT PLANT | LIST | INSTRUMENT | Water Treatment System |  |  | Instrument List for INSTRUMENT |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | instrument¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8087 | 0.7093 | 0.7093 | g_ambig | use_specific | 0.85 | Instrument List & Data Sheet for Water Treatment System | 1 | The instrument list is explicitly for the Water Treatment Plant, aligning with the water treatment system-specific instrument list/data sheet rule. | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 29.1893 | 0.7131 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0GCF-130010 | SINGLE LINE DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | Single Line Diagram |  | Water Treatment System |  |  | Single Line Diagram for Water Treatment System | Water Treatment System | Single Line Diagram for Water Treatment System | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9778 | 0.9933 | 0.9933 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 4 | 1 | 39.2779 | 0.7080 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0GCF-130011 | CONTROL CONFIGURATION DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | Diagram |  | Water Treatment System |  |  | Diagram for Water Treatment System | Water Treatment System | Control Configuration Diagram for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.8131 | 0.7439 | 0.7439 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 3 | 1 | 39.2779 | 0.7018 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GCF-130012 | EQUIPMENT ASSEMBLY DRAWING FOR WATER TREATMENT PLANT | ASSEMBLY DRAWING |  | Water Treatment System |  |  | ASSEMBLY DRAWING for Water Treatment System | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.8123 | 0.7437 | 0.7437 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 22.9840 | 0.6884 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-06-13 | 2024-07-13 | 2024-08-12 | 2024-08-27 | 2024-09-11 | 2024-09-26 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0GCF-130013 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | General Arrangement Drawing |  | PIPING |  |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_ambig | uncertain | 0.40 |  | 1 | The title indicates piping arrangement for the water treatment plant, but the equipment is listed as PIPING, so it is unclear whether the water treatment system-specific GA rule is intended to govern. | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 17.6675 | 0.6974 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GCF-130014 | TEHCNICAL DATA SHEET FOR WATER TREATMENT PLANT | TEHCNICAL DATA SHEET |  | Water Treatment System |  |  | TEHCNICAL DATA SHEET for Water Treatment System | Water Treatment System | Pump Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | treatment¦water¦wts | pump¦wts | scoped | match | match | match | passed |  | 0.8571 | 0.8273 | 0.8482 | 0.8482 | [6 empty] | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 2 | 1 | 29.1893 | 0.6980 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0GCF-130015 | CABLE TRAY LAYOUT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | Layout Drawing | CABLE TRAY | Water Treatment System |  |  | Layout Drawing for Water Treatment System | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.7621 | 0.8120 | 0.8120 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | electrical¦wts | wts | query | wts | match | true | false | 4 | 4 | 36.4975 | 0.5944 | 0.0312 | 0.0234 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GCF-130016 | HOOK - UP DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | HOOK - UP DRAWING |  | Water Treatment System |  |  | HOOK - UP DRAWING for Water Treatment System | Water Treatment System | Hook Up DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8908 | 0.9672 | 0.9672 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 4 | 5 | 36.4975 | 0.6279 | 0.0310 | 0.0233 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0GCF-130017 | SCHEMATIC AND WIRING DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | SCHEMATIC AND WIRING DIAGRAM |  | Water Treatment System |  |  | SCHEMATIC AND WIRING DIAGRAM for Water Treatment System | Water Treatment System | Interconnection Wiring Diagram for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8571 | 0.8473 | 0.8542 | 0.8542 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 2 | 1 | 44.3167 | 0.6995 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0GCF-130018 | CONTROL LOOP & LOGIC DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | Diagram |  | Water Treatment System |  |  | Control Loop Diagram for Water Treatment System | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | treatment¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7474 | 0.7492 | 0.7492 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 3 | 1 | 39.2779 | 0.6658 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130019 | SLEEVE AND WALL OPENING FOR WATER AND WASTE WATER TREATMENT PLANT | Plan |  | Water Treatment System |  |  | Plan for Water Treatment System | Water Treatment System | Inspection & test plan for Shop | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6250 | 0.6932 | 0.6455 | 0.6455 | [6 empty] | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 1 | 2 | 40.2482 | 0.6598 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0GCF-130035 | PLC IO LIST FOR WATER AND WASTE WATER TREATMENT PLANT | LIST |  | Water Treatment System |  |  | I/O List for Water Treatment System | Water Treatment System | PLC I/O List for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | list | list | io_list | io_list | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.7993 | 0.8231 | 0.8231 | [6 empty] | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 1 | 2 | 40.2482 | 0.6721 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GCF-130042 | FOUNDATION AND LOADING DATA FOR WATER AND WASTE WATER TREATMENT PLANT | DATA |  | Water Treatment System |  |  | DATA for Water Treatment System | Water Treatment System | Inspection & test plan for Shop | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.6483 | 0.5445 | 0.5445 | [6 empty] | FI | 0EF5535W00A15.1 | (WWT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 |  | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 2 | 5 | 40.4315 | 0.6323 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0GCF-130055 | PIPING MATERIAL CLASSIFICATION FOR WATER AND WASTE WATER TREATMENT PLANT | Plan |  | WATER AND WASTE WATER TREATMENT PLANT |  |  | Plan for WATER AND WASTE WATER TREATMENT PLANT |  | Water Treatment Plant | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7266 | 0.9180 | 0.6426 | [6 empty] | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 3 | 3 | 50.1701 | 0.6689 | 0.0317 | 0.0317 | hybrid | structured_cell_found_text_preferred | wts | system_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GNR-130101 | SYSTEM DESCRIPTION FOR WASTE WATER TREATMENT PLANT | System Description |  | WASTE WATER TREATMENT PLANT |  |  | System Description for WASTE WATER TREATMENT PLANT | Water Treatment System | System Description for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7934 | 0.9380 | 0.9380 | [6 empty] | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 44.8597 | 0.7226 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GNR-130102 | PROCESS FLOW DIAGRAM FOR WASTE WATER TREATMENT PLANT | PROCESS FLOW DIAGRAM |  | WASTE WATER TREATMENT PLANT |  |  | PROCESS FLOW DIAGRAM for WASTE WATER TREATMENT PLANT | Water Treatment System | Process FloW Diagram & Mass Balance for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7310 | 0.6860 | 0.6860 | [6 empty] | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 4 | 47.7182 | 0.6434 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GNR-130103 | PIPING & INSTRUMENT DIAGRAM FOR WASTE WATER TREATMENT PLANT | PIPING & INSTRUMENT DIAGRAM |  | WASTE WATER TREATMENT PLANT |  |  | PIPING & INSTRUMENT DIAGRAM for WASTE WATER TREATMENT PLANT |  | Piping & Instrument Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | plant¦treatment¦waste¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7424 | 0.9227 | 0.6459 | g_ambig | generic_ok | 0.75 |  | 4 | None of the competing rules are a P&ID rule (they are PFD/mass balance, control/cable diagrams), so they do not supersede the generic P&ID timeline. | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts |  | wts | query | wts | match | true | false | 1 | 1 | 50.6272 | 0.7676 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GNR-130104 | CALCULATION SHEET FOR WASTE WATER TREATMENT PLANT | CALCULATION SHEET |  | WASTE WATER TREATMENT PLANT |  |  | CALCULATION SHEET for WASTE WATER TREATMENT PLANT | WASTE WATER TREATMENT PLANT | CALCULATION OF WASTE WATER TREATMENT PLANT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8768 | 0.8464 | 0.8464 | [6 empty] | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 8 | 1 | 35.9876 | 0.5790 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GNR-130105 | VALVE LIST FOR WASTE WATER TREATMENT PLANT | VALVE LIST |  | WASTE WATER TREATMENT PLANT |  |  | Valve List for WASTE WATER TREATMENT PLANT |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | plant¦treatment¦waste¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7069 | 0.6787 | 0.6787 | g_ambig | use_specific | 0.75 | Valve List & Data Sheet for Water Treatment System | 1 | Waste water treatment is part of the overall water/waste water treatment system context, so the water treatment system-specific valve list/data sheet rule is the closest targeted match. | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 44.2306 | 0.6628 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-11-26 | 2024-12-26 | 2025-01-25 | 2025-02-09 | 2025-02-24 | 2025-03-11 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GNR-130106 | INSTRUMENT LIST FOR WASTE WATER TREATMENT PLANT | INSTRUMENT LIST |  | WASTE WATER TREATMENT PLANT |  |  | Instrument List for WASTE WATER TREATMENT PLANT | Water Treatment System | Instrument List & Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | list | list | instrument_list | instrument_list | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6250 | 0.7702 | 0.6685 | 0.6685 | [6 empty] | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 44.2306 | 0.6822 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GNR-130107 | EQUIPMENT ASSEMBLY DRAWING FOR WASTE WATER TREATMENT PLANT | ASSEMBLY DRAWING |  | WASTE WATER TREATMENT PLANT |  |  | ASSEMBLY DRAWING for WASTE WATER TREATMENT PLANT | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | plant¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.7104 | 0.6131 | 0.6131 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 5 | 2 | 37.9279 | 0.6432 | 0.0315 | 0.0236 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GNR-130108 | TEHCNICAL DATA SHEET FOR WASTE WATER TREATMENT PLANT | TEHCNICAL DATA SHEET |  | WASTE WATER TREATMENT PLANT |  |  | TEHCNICAL DATA SHEET for WASTE WATER TREATMENT PLANT | Water Treatment System | Pump Data Sheet for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | plant¦treatment¦waste¦water¦wts | pump¦wts | scoped | match | match | match | passed |  | 0.7143 | 0.6924 | 0.7077 | 0.7077 | [6 empty] | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 3 | 1 | 44.2306 | 0.6946 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LD-130201 | SYSTEM DESCRIPTION FOR CONDENSATE POLISHING PLANT | System Description |  | CONDENSATE POLISHING PLANT |  |  | System Description for CONDENSATE POLISHING PLANT |  | System Description | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | title | description | description | system_description | system_description | condensate¦plant¦polishing |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5207 | 0.6229 | 0.5294 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 21.1313 | 0.6932 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦procurement |  | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LD-130202 | GENERAL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | GENERAL ARRANGEMENT DRAWING |  | CONDENSATE POLISHING PLANT |  |  | GENERAL ARRANGEMENT DRAWING for CONDENSATE POLISHING PLANT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | condensate¦plant¦polishing |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6365 | 0.8910 | 0.8910 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 14.3814 | 0.5840 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0LD-130203 | PROCESS FLOW DIAGRAM FOR CONDENSATE POLISHING PLANT | PROCESS FLOW DIAGRAM |  | CONDENSATE POLISHING PLANT |  |  | PROCESS FLOW DIAGRAM for CONDENSATE POLISHING PLANT | FireFighting | Process FloW Diagram & Mass Balance | 1 | start+2W<=FA<=FC<=start+12W | FA ∈ [start+14d, start+84d] ¦ FC ∈ [start+14d, start+84d] | rule_query | diagram | diagram | diagram | diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5430 | 0.5129 | 0.5129 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 23.9460 | 0.6078 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design¦engineering | 1 | 2024-04-16 | 2024-05-21 | 2024-06-25 | 2024-06-11 | 2024-07-16 | 2024-08-20 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LD-130204 | PIPING & INSTRUMENT DIAGRAM FOR CONDENSATE POLISHING PLANT | PIPING & INSTRUMENT DIAGRAM |  | CONDENSATE POLISHING PLANT |  |  | PIPING & INSTRUMENT DIAGRAM for CONDENSATE POLISHING PLANT |  | Piping & Instrument Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7279 | 0.9184 | 0.6429 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 26.7880 | 0.6903 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LD-130205 | CALCULATION SHEET FOR CONDENSATE POLISHING PLANT | CALCULATION SHEET |  | CONDENSATE POLISHING PLANT |  |  | CALCULATION SHEET for CONDENSATE POLISHING PLANT |  | Chlorination Plant Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5518 | 0.5156 | 0.5156 | g_safe | [5 empty] | FA | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | true | false | 11 | 1 | 12.6306 | 0.5021 | 0.0305 | 0.0305 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LD-130206 | MCC ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | General Arrangement Drawing | Motor Control Center | CONDENSATE POLISHING PLANT |  |  | General Arrangement Drawing for Motor Control Center |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | center¦motor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6473 | 0.8942 | 0.8942 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate¦mv_lv |  | condensate¦mv_lv | query | condensate | match | true | false | 1 | 1 | 14.3814 | 0.5354 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦mv_lv | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0LD-130207 | CONTROL PANEL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | General Arrangement Drawing |  | CONDENSATE POLISHING PLANT |  |  | General Arrangement Drawing for CONDENSATE POLISHING PLANT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | condensate¦plant¦polishing |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6658 | 0.8998 | 0.8998 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 14.3814 | 0.5941 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LD-130208 | VALVE LIST FOR CONDENSATE POLISHING PLANT | VALVE LIST |  | CONDENSATE POLISHING PLANT |  |  | Valve List for CONDENSATE POLISHING PLANT |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6922 | 0.6743 | 0.6743 | g_safe | [5 empty] | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 5 | 21.6012 | 0.6095 | 0.0318 | 0.0318 | hybrid | structured_preferred | condensate | procurement | 10 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LD-130209 | INSTRUMENT LIST FOR CONDENSATE POLISHING PLANT | INSTRUMENT LIST |  | CONDENSATE POLISHING PLANT |  |  | Instrument List for CONDENSATE POLISHING PLANT |  | Instrument List | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | list | list | instrument_list | instrument_list | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5988 | 0.6463 | 0.6463 | g_safe | [5 empty] | FA | 2PF3020W42A20P | (COND) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-29 | procurement | procurement | match | condensate |  | condensate | query | condensate | match | true | false | 12 | 1 | 20.4139 | 0.6468 | 0.0303 | 0.0303 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0LD-130210 | SINGLE LINE DIAGRAM FOR CONDENSATE POLISHING PLANT | Single Line Diagram |  | CONDENSATE POLISHING PLANT |  |  | Single Line Diagram for CONDENSATE POLISHING PLANT |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6848 | 0.9054 | 0.9054 | g_safe | [5 empty] | SKIP | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 2 | 5 | 23.9460 | 0.6279 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0LD-130211 | CONTROL CONFIGURATION DIAGRAM FOR CONDENSATE POLISHING PLANT | CONTROL CONFIGURATION DIAGRAM |  | CONDENSATE POLISHING PLANT |  |  | CONTROL CONFIGURATION DIAGRAM for CONDENSATE POLISHING PLANT |  | CONTROL CONFIGURATION DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | condensate¦plant¦polishing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6780 | 0.9034 | 0.6324 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 21.7680 | 0.6001 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LD-130212 | EQUIPMENT ASSEMBLY DRAWING FOR CONDENSATE POLISHING PLANT | EQUIPMENT ASSEMBLY DRAWING |  | Condensate System |  |  | EQUIPMENT ASSEMBLY DRAWING for Condensate System |  | EQUIPMENT ASSEMBLY DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7813 | 0.9344 | 0.6541 | g_safe | [5 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | condensate |  | condensate | query | acc¦condensate | match | true | false | 1 | 3 | 17.9803 | 0.6071 | 0.0323 | 0.0242 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LD-130213 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | General Arrangement Drawing |  | PIPING |  |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 13.2997 | 0.6336 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LD-130214 | TECHNICAL DATA SHEET FOR CONDENSATE POLISHING PLANT | TECHNICAL DATA SHEET |  | Condensate System |  |  | TECHNICAL DATA SHEET for Condensate System | Chemical Dosing System | Technical Data Sheet | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | datasheet | datasheet | technical_data_sheet | technical_data_sheet | condensate |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6837 | 0.6718 | 0.6718 | g_safe | [5 empty] | FA | 1EF3020W00A02 | (COND System) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-13 | 2007-05-31 | procurement | procurement | match | condensate | wts | condensate | query | condensate | match | true | false | 1 | 10 | 22.6090 | 0.6355 | 0.0307 | 0.0307 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-07-12 | 2024-08-11 | 2024-09-10 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0LD-130215 | CABLE TRAY LAYOUT DRAWING FOR CONDENSATE POLISHING PLANT | Layout Drawing | CABLE TRAY | Condensate System |  |  | Layout Drawing for Condensate System | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7024 | 0.6774 | 0.6774 | g_safe | [5 empty] | SKIP | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 15.0184 | 0.6060 | 0.0328 | 0.0246 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LD-130216 | HOOK - UP DRAWING FOR CONDENSATE POLISHING PLANT | HOOK - UP DRAWING |  | Condensate System |  |  | HOOK - UP DRAWING for Condensate System |  | Instrumentation Hook-up DraWing | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | drawing | drawing | drawing | drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6892 | 0.7317 | 0.7317 | g_safe | [5 empty] | FI | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 15.0184 | 0.6405 | 0.0328 | 0.0246 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0LD-130217 | SCHEMATIC & WIRING DIAGRAM FOR CONDENSATE POLISHING PLANT | SCHEMATIC & WIRING DIAGRAM |  | Condensate System |  |  | SCHEMATIC & WIRING DIAGRAM for Condensate System |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | condensate |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5553 | 0.6333 | 0.6333 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 24.5830 | 0.6917 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LD-130218 | CONTROL LOOP & LOGIC DIAGRAM FOR CONDENSATE POLISHING PLANT | CONTROL LOOP & LOGIC DIAGRAM |  | Condensate System |  |  | Control Loop Diagram for Condensate System | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | condensate |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7385 | 0.7466 | 0.7466 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 24.5830 | 0.6645 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0LD-130219 | PIPING MATERIAL SPECIFICATION FOR CONDENSATE POLISHING PLANT | MATERIAL SPECIFICATION |  | PIPING |  |  | MATERIAL SPECIFICATION for PIPING | FireFighting | Piping Material Specification | 1 | start+4W<=FA<=FC<=start+12W | FA ∈ [start+28d, start+84d] ¦ FC ∈ [start+28d, start+84d] | rule_query | specification | specification | specification | specification | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7302 | 0.7441 | 0.7441 | g_safe | [5 empty] | FA | 0EF3520W68A03 | (Condensate Tank) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System |  | 2007-03-30 | procurement | procurement | match | condensate |  | condensate | query | condensate¦fgp | match | true | false | 1 | 6 | 20.7047 | 0.6335 | 0.0315 | 0.0315 | hybrid | structured_preferred | condensate | procurement | 10 | 2024-04-27 | 2024-05-25 | 2024-06-22 | 2024-06-15 | 2024-07-13 | 2024-08-10 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LD-130220 | FOUNDATION AND LOADING DATA FOR CONDENSATE POLISHING PLANT | DATA |  | Condensate System |  |  | DATA for Condensate System | FireFighting | Foundation Plan and Loading Data | 1 | start+16W<=FA<=FC<=start+24W | FA ∈ [start+112d, start+168d] ¦ FC ∈ [start+112d, start+168d] | title | plan | plan | plan | plan | condensate |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5665 | 0.6366 | 0.6366 | g_safe | [5 empty] | FA | 0CF3520W16A02.1 | (Condensate Tank & Pump) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-10-12 | 2007-12-08 | civil_design | civil_design | match | condensate |  | condensate | query | condensate¦fgp | match | true | false | 8 | 1 | 16.0387 | 0.6029 | 0.0311 | 0.0311 | hybrid | structured_preferred | condensate | civil_design | 10 | 2025-02-01 | 2025-03-01 | 2025-03-29 | 2025-03-22 | 2025-04-19 | 2025-05-17 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YM03-P0LD-130221 | INSTRUMENT LOCATION DRAWING FOR CONDENSATE POLISHING PLANT | LOCATION DRAWING |  | INSTRUMENT |  |  | LOCATION DRAWING for INSTRUMENT |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | instrument |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6713 | 0.6681 | 0.6681 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 8.2797 | 0.5998 | 0.0328 | 0.0246 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QC-130301 | SYSTEM DESCRIPTION FOR CHEMICAL DOSING SYSTEM | System Description |  | CHEMICAL DOSING SYSTEM |  |  | System Description for CHEMICAL DOSING SYSTEM | Chemical Dosing System | System Description | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | description | description | system_description | system_description | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9489 | 0.9847 | 0.9847 | g_safe | [5 empty] | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 40.3327 | 0.8290 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QC-130302 | GENERAL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | GENERAL ARRANGEMENT DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for CHEMICAL DOSING SYSTEM | Chemical Dosing System | General Arrangement DraWing | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9342 | 0.9803 | 0.9803 | g_safe | [5 empty] | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 33.6657 | 0.7599 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QC-130303 | PIPING & INSTRUMENT DIAGRAM FOR CHEMICAL DOSING SYSTEM | PIPING & INSTRUMENT DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | PIPING & INSTRUMENT DIAGRAM for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Control Configuration Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | diagram | diagram | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7569 | 0.6937 | 0.6937 | g_safe | [5 empty] | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 48.0296 | 0.8466 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0QC-130304 | CALCULATION SHEET FOR CHEMICAL DOSING SYSTEM | CALCULATION SHEET |  | CHEMICAL DOSING SYSTEM |  |  | CALCULATION SHEET for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Calculation Sheet | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9523 | 0.9857 | 0.9857 | g_safe | [5 empty] | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 2 | 1 | 31.8262 | 0.6463 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0QC-130305 | INSTRUMENT LIST FOR CHEMICAL DOSING SYSTEM | INSTRUMENT LIST |  | CHEMICAL DOSING SYSTEM |  |  | Instrument List for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Instrument List and Data Sheet | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | list | list | instrument_list | instrument_list | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.8763 | 0.7004 | 0.7004 | g_safe | [5 empty] | FI | 2PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-08-25 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 2 | 1 | 39.2774 | 0.7887 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0QC-130306 | CONTROL PANEL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | General Arrangement Drawing |  | CHEMICAL DOSING SYSTEM |  |  | General Arrangement Drawing for CHEMICAL DOSING SYSTEM | Chemical Dosing System | General Arrangement DraWing | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9436 | 0.9831 | 0.9831 | g_safe | [5 empty] | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 33.6657 | 0.7582 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QC-130307 | TECHNICAL DATA SHEET FOR CHEMICAL DOSING SYSTEM | TECHNICAL DATA SHEET |  | CHEMICAL DOSING SYSTEM |  |  | TECHNICAL DATA SHEET for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Technical Data Sheet | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | datasheet | datasheet | technical_data_sheet | technical_data_sheet | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9253 | 0.9776 | 0.9776 | g_safe | [5 empty] | FA | 2PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-08-25 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 5 | 1 | 39.2774 | 0.7775 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0QC-130308 | SCHEMATIC & WIRING DIAGRAM FOR CHEMICAL DOSING SYSTEM | SCHEMATIC & WIRING DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | SCHEMATIC & WIRING DIAGRAM for CHEMICAL DOSING SYSTEM | Chemical Dosing System | Interconnection Wiring Diagram | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8379 | 0.8347 | 0.8347 | g_safe | [5 empty] | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 43.0856 | 0.7730 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0QC-130309 | CONTROL LOOP & LOGIC DIAGRAM FOR CHEMICAL DOSING SYSTEM | CONTROL LOOP & LOGIC DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | Control Loop Diagram for CHEMICAL DOSING SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7293 | 0.7438 | 0.7438 | g_safe | [5 empty] | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 4 | 43.0856 | 0.7331 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QU-130401 | SYSTEM DESCRIPTION FOR SAMPLING SYSTEM | System Description |  | SAMPLING SYSTEM |  |  | System Description for SAMPLING SYSTEM | Sampling System | System Description for Steam and Water Analysis System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | description | description | system_description | system_description | sampling |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7375 | 0.5712 | 0.5712 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling | sampling | sampling | query | sampling | match | true | false | 1 | 1 | 27.5345 | 0.8105 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦procurement |  | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QU-130402 | GENERAL ARRANGEMENT DRAWING FOR SAMPLING SYSTEM | GENERAL ARRANGEMENT DRAWING |  | SAMPLING SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for SAMPLING SYSTEM |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | sampling |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7090 | 0.9127 | 0.9127 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | true | false | 6 | 1 | 20.6995 | 0.7191 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | sampling | system_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QU-130403 | PIPING & INSTRUMENT DIAGRAM FOR SAMPLING SYSTEM | PIPING & INSTRUMENT DIAGRAM |  | SAMPLING SYSTEM |  |  | PIPING & INSTRUMENT DIAGRAM for SAMPLING SYSTEM |  | Piping & Instrument Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | sampling |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7544 | 0.9263 | 0.6484 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | design_drawing | system_design | compatible | sampling |  | sampling | query | sampling | match | true | false | 1 | 1 | 33.2997 | 0.8257 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0QU-130404 | INSTRUMENT LIST FOR SAMPLING SYSTEM | LIST |  | SAMPLING SYSTEM |  |  | Instrument List for SAMPLING SYSTEM |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | sampling |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7034 | 0.6777 | 0.6777 | g_safe | [5 empty] | FI | 3PF3040W42A05P | (Sampling Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | 2007-10-01 | 2008-09-30 | procurement | procurement | match | sampling |  | sampling | query | sampling | match | true | false | 4 | 1 | 26.2910 | 0.7264 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | sampling | procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QU-130405 | TECHNICAL DATA SHEET FOR SAMPLING SYSTEM | TECHNICAL DATA SHEET |  | SAMPLING SYSTEM |  |  | TECHNICAL DATA SHEET for SAMPLING SYSTEM | Intake Screening System | Technical Data Sheet | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | datasheet | datasheet | technical_data_sheet | technical_data_sheet | sampling |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6685 | 0.6672 | 0.6672 | g_safe | [5 empty] | FA | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-10-01 | 2008-07-30 | procurement | procurement | match | sampling |  | sampling | query | sampling | match | true | false | 1 | 3 | 26.2910 | 0.7138 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | sampling | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0QU-130406 | SCHEMATIC & WIRING DIAGRAM FOR SAMPLING SYSTEM | SCHEMATIC & WIRING DIAGRAM |  | SAMPLING SYSTEM |  |  | SCHEMATIC & WIRING DIAGRAM for SAMPLING SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | sampling |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5692 | 0.6374 | 0.6374 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | true | false | 1 | 1 | 30.4134 | 0.7184 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0QU-130407 | CONTROL LOOP & LOGIC DIAGRAM FOR SAMPLING SYSTEM | CONTROL LOOP & LOGIC DIAGRAM |  | SAMPLING SYSTEM |  |  | Control Loop Diagram for SAMPLING SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | sampling |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7233 | 0.7420 | 0.7420 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | true | false | 1 | 1 | 30.4134 | 0.6533 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | sampling | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0STG-130501 | EQUIPMENT SPECIFICATION FOR CHEMICAL LABORATORY | EQUIPMENT SPECIFICATION | CHEMICAL LABORATORY |  |  |  | EQUIPMENT SPECIFICATION for CHEMICAL LABORATORY | Chemical Dosing System | Piping Material Specification | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | title | specification | specification | specification | specification | chemical¦laboratory |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5168 | 0.3884 | 0.3884 | g_safe | [5 empty] | FI | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | procurement | procurement | match | lab | wts | lab | query | lab | match | true | false | 1 | 4 | 37.8834 | 0.6092 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | lab | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0STG-130502 | ARRANGEMENT DRAWING FOR CHEMICAL LABORATORY EQUIPMENT | General Arrangement Drawing | CHEMICAL LABORATORY EQUIPMENT |  |  |  | General Arrangement Drawing for CHEMICAL LABORATORY EQUIPMENT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chemical¦laboratory |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6765 | 0.9029 | 0.9029 | g_safe | [5 empty] | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | system_design | system_design | match | lab |  | lab | query |  | activity_unscoped | true | true | 1230 | 21 | 2.3206 | 0.4997 | 0.0131 | 0.0079 | hybrid | structured_phase_gap | lab | system_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0STG-130503 | EQUIPMENT LIST FOR CHEMICAL LABORATORY | EQUIPMENT LIST | CHEMICAL LABORATORY |  |  |  | Equipment List for CHEMICAL LABORATORY | Chemical Laboratory Equipment | Equipment List & Specification for Chemical Laboratory Equipment | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | list | list | equipment_list | equipment_list | chemical¦laboratory |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8158 | 0.8281 | 0.8281 | g_safe | [5 empty] | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | procurement | procurement | match | lab | lab | lab | query | lab | match | true | false | 1 | 4 | 37.8834 | 0.6060 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | lab | procurement |  | 2025-05-01 | 2025-05-31 | 2025-06-30 | 2025-07-15 | 2025-07-30 | 2025-08-14 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GK-130601 | GENERAL ARRANGEMENT DRAWING FOR POTABLE WATER CHILLER | GENERAL ARRANGEMENT DRAWING | POTABLE WATER CHILLER | Water Treatment System |  |  | GENERAL ARRANGEMENT DRAWING for POTABLE WATER CHILLER |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | chiller¦potable¦water¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6462 | 0.8939 | 0.8939 | g_ambig | generic_ok | 0.85 |  | 1 | A potable water chiller is not the water treatment system, so the water treatment system-specific GA rule should not override the generic GA rule. | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 2 | 1 | 20.1530 | 0.6332 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | system_design | 5 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0GK-130602 | ELECTRICAL DRAWING FOR POTABLE WATER CHILLER | DRAWING | POTABLE WATER CHILLER | Water Treatment System |  |  | DRAWING for POTABLE WATER CHILLER | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | chiller¦potable¦water¦wts | wts | scoped | match | match | match | passed |  | 0.4286 | 0.6396 | 0.4919 | 0.4919 | [6 empty] | FI | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 1 | 2 | 31.8619 | 0.6001 | 0.0325 | 0.0244 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-06-13 | 2024-07-13 | 2024-08-12 | 2024-08-27 | 2024-09-11 | 2024-09-26 | generated | 0.90 |  | false | false | 0.57 | usable | default_fc_window;rule_score_medium;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SAA-133301 | DESIGN CRITERIA FOR HVAC SYSTEM | DESIGN CRITERIA |  | Heating Ventilating and Air Conditioning SYSTEM |  |  | DESIGN CRITERIA for Heating Ventilating and Air Conditioning SYSTEM | Intake Screening System | Design Criteria | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | criteria | criteria | design_criteria | design_criteria | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5274 | 0.5782 | 0.5782 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_criteria | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 3 | 44.3110 | 0.5800 | 0.0320 | 0.0240 | hybrid | structured_cell_found_text_preferred | hvac | design_criteria¦system_design¦civil_design |  | 2024-04-13 | 2024-05-13 | 2024-06-12 | 2024-06-27 | 2024-07-12 | 2024-07-27 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SAA-133302 | STANDARD DRAIWNG FOR HVAC SYSTEM | STANDARD DRAIWNG |  | Heating Ventilating and Air Conditioning SYSTEM |  |  | STANDARD DRAIWNG for Heating Ventilating and Air Conditioning SYSTEM | [5 empty] | rule_query | other | model | standard_draiwng | model | air¦conditioning¦heating¦ventilating |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.4986 | 0.4996 | 0.4996 | [7 empty] | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 35.0354 | 0.6640 | 0.0320 | 0.0240 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAH-133401 | LOAD CALCULATION OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | Calculation sheet | Steam Turbine & Generator | Heating Ventilating and Air Conditioning SYSTEM | Steam Turbine Building |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | hvac¦stg | stg | hvac¦stg | query | stg | match | true | false | 10 | 1 | 18.1530 | 0.5738 | 0.0307 | 0.0307 | hybrid | structured_preferred | hvac¦stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAH-133402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | AIR FLOW DIAGRAM | Steam Turbine & Generator | Heating Ventilating and Air Conditioning SYSTEM | Steam Turbine Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦stg¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for an ST/STG trip-protection diagram, not an HVAC air flow diagram, so it targets different content/equipment. | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | hvac¦stg |  | hvac¦stg | query | stg | match | true | false | 319 | 73 | 13.4660 | 0.5467 | 0.0102 | 0.0102 | hybrid | structured_cell_found_text_preferred | hvac¦stg | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_rrf_low;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAH-133403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR STEAM TURBINE BUILDING | EQUIPMENT SCHEDULE | Steam Turbine & Generator | Heating Ventilating and Air Conditioning SYSEM | Steam Turbine Building |  | EQUIPMENT SCHEDULE for STG | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6400 | 0.6120 | 0.6120 | g_ambig | generic_ok | 0.80 |  | 2 | The competing rules are door/interior finish schedules, which are different deliverables than an HVAC equipment schedule, so they do not apply. | FI | 1CF2010W36A10 | (STG #10 BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-10-13 | 2008-12-08 |  | commissioning | query_unknown | hvac¦stg |  | hvac¦stg | query | hvac¦stg | match | true | false | 7 | 1 | 33.9919 | 0.6601 | 0.0313 | 0.0235 | hybrid | structured_no_phase | hvac¦stg | [5 empty] | 2025-07-16 | 2025-08-15 | 2025-09-14 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAH-133404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSEM FOR STEAM TURBINE BUILDING | Plan | Steam Turbine & Generator | Heating Ventilating and Air Conditioning SYSEM | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1CF2010W36A10 | (STG #10 BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-10-13 | 2008-12-08 |  | commissioning | query_unknown | hvac¦stg | stg | hvac¦stg | query | hvac¦stg | match | true | false | 3 | 1 | 33.9916 | 0.6517 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac¦stg | [5 empty] | 2025-07-16 | 2025-08-15 | 2025-09-14 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAC-133501 | LOAD CALCULATION OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | Calculation sheet |  | Heating Ventilating and Air Conditioning SYSTEM | Central Control Building |  | Calculation sheet for Heating Ventilating and Air Conditioning SYSTEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦ccr¦central¦conditioning¦heating¦ventilating | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.7933 | 0.9380 | 0.9380 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 28.5316 | 0.6023 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAC-133502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Central Control Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦ccr¦central¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 20 | 3 | 29.3983 | 0.6051 | 0.0284 | 0.0284 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAC-133503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CENTRAL CONTROL BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Central Control Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦ccr¦central¦conditioning¦heating¦sysem¦ventilating | ccr | scoped | match | match | match | passed |  | 0.8333 | 0.7829 | 0.8182 | 0.8182 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | true | false | 1 | 1 | 49.1936 | 0.6475 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAC-133504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | true | false | 1 | 2 | 41.7906 | 0.6437 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAK-133601 | LOAD CALCULATION OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Water Treatment Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7738 | 0.9321 | 0.9321 | [6 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | hvac¦wts | wts | hvac¦wts | query | wts | match | true | false | 4 | 3 | 25.8735 | 0.5674 | 0.0315 | 0.0315 | hybrid | structured_preferred | hvac¦wts | civil_design | 10 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAK-133602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Water Treatment Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM | Water Treatment System | Control Configuration Diagram for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.6331 | 0.6899 | 0.6899 | [6 empty] | FI | 0EF3010W16A01 | (WTS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-01-09 | civil_design | civil_design | match | hvac¦wts | wts | hvac¦wts | query | wts | match | true | false | 139 | 45 | 20.5292 | 0.5733 | 0.0145 | 0.0145 | hybrid | structured_cell_found_text_preferred | hvac¦wts | system_design¦engineering |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.77 | usable | default_fc_window;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAK-133603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WATER TREATMENT BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Water Treatment Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8262 | 0.8312 | 0.8312 | [6 empty] | FI | 0CF5534W36A07 | (DWP BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-15 |  | commissioning | query_unknown | hvac¦wts | wts | hvac¦wts | query | hvac¦wts | match | true | false | 8 | 2 | 34.2563 | 0.6451 | 0.0308 | 0.0231 | hybrid | structured_no_phase | hvac¦wts | [5 empty] | 2025-04-03 | 2025-05-03 | 2025-06-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAK-133604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0CF5534W36A07 | (DWP BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-15 |  | commissioning | query_unknown | hvac¦wts | wts | hvac¦wts | query | hvac¦wts | match | true | false | 5 | 2 | 35.4095 | 0.6732 | 0.0315 | 0.0236 | hybrid | structured_no_phase | hvac¦wts | [5 empty] | 2025-09-30 | 2025-10-30 | 2025-11-29 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAJ-133701 | LOAD CALCULATION OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Fuel Gas System ELECTRICAL BUILDING |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦fgp¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7715 | 0.9315 | 0.9315 | g_ambig | generic_ok | 0.70 |  | 2 | The competing rules are generic calculation sheets or a foundation calculation, not specifically an HVAC load calculation for the FGS electrical building, so the matched generic calculation timeline r | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp¦hvac | electrical | electrical¦fgp¦hvac | query | fgp | match | false | false | 9 | 6 | 20.7036 | 0.5199 | 0.0296 | 0.0296 | hybrid | structured_preferred | electrical¦fgp¦hvac | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | fc_earliest | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAJ-133702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Fuel Gas System ELECTRICAL BUILDING |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦fgp¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_ambig | generic_ok | 0.80 |  | 3 | The competing rules are for PFD/mass balance, control logic/loop, or startup/shutdown diagrams, not an HVAC air flow diagram. | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fgp¦hvac |  | electrical¦fgp¦hvac | query | fire_fighting¦hvac | discipline_only | true | false | 21 | 2 | 29.3983 | 0.6297 | 0.0285 | 0.0142 | hybrid | structured_cell_found_text_preferred | electrical¦fgp¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAJ-133703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FGS ELECTRICAL BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Fuel Gas System ELECTRICAL BUILDING |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦fgp¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6433 | 0.6130 | 0.6130 | g_safe | [5 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | electrical¦fgp¦hvac |  | electrical¦fgp¦hvac | query | fire_fighting¦hvac | discipline_only | true | false | 1 | 4 | 42.0373 | 0.6412 | 0.0320 | 0.0120 | hybrid | structured_no_phase | electrical¦fgp¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.30 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAJ-133704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Fuel Gas System ELECTRICAL BUILDING |  | Plan for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Foundation Plan and Loading Data | 1 | start+16W<=FA<=FC<=start+24W | FA ∈ [start+112d, start+168d] ¦ FC ∈ [start+112d, start+168d] | rule_query | plan | plan | plan | plan | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6738 | 0.5521 | 0.5521 | [6 empty] | FA | 1PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-07-03 | 2008-04-30 | procurement | procurement | match | electrical¦fgp¦hvac | fgp | electrical¦fgp¦hvac | query | fgp¦hrsg | match | false | false | 22 | 12 | 11.2894 | 0.5254 | 0.0261 | 0.0261 | hybrid | structured_preferred | electrical¦fgp¦hvac | procurement | 10 | 2024-10-23 | 2024-11-20 | 2024-12-18 | 2024-12-11 | 2025-01-08 | 2025-02-05 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133801 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #1/2 LEB | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦gtg¦heating¦leb¦local¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.6932 | 0.9080 | 0.9080 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 30.4639 | 0.5753 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAI-133802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #1/2 LEB | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦gtg¦heating¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_ambig | generic_ok | 0.90 |  | 15 | All competing rules are GT electrical/control/auxiliary diagrams rather than HVAC air flow diagrams, so they do not supersede the generic air flow diagram timeline. | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 37 | 41 | 26.7038 | 0.5633 | 0.0202 | 0.0202 | hybrid | structured_cell_found_text_preferred | electrical¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #1/2 LEB | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦gtg¦heating¦leb¦local¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.8000 | 0.7222 | 0.7767 | 0.7767 | [6 empty] | FI | 0PF5000W36A05T | (HVAC Equipment) 1st Delivery on site_Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System |  | 2008-05-14 |  | delivery | query_unknown | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 4 | 4 | 40.5552 | 0.6379 | 0.0312 | 0.0234 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2025-02-14 | 2025-03-16 | 2025-04-15 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAI-133804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #1/2 LEB | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | Plan for Local Electrical Building |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7564 | 0.9269 | 0.6489 | g_ambig | generic_ok | 0.90 |  | 41 | Competing rules shown are for GT piping route plans or building/structural plans, not HVAC duct & refrigerant piping plans. | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6465 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133901 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #3/4/5 LEB | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦gtg¦heating¦leb¦local¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.6878 | 0.9063 | 0.9063 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2672 | 0.5894 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAI-133902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #3/4/5 LEB | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦gtg¦heating¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_ambig | generic_ok | 0.90 |  | 15 | All competing rules are GT electrical/control/auxiliary diagrams rather than HVAC air flow diagrams, so they do not supersede the generic air flow diagram timeline. | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 55 | 14 | 25.4483 | 0.5777 | 0.0222 | 0.0222 | hybrid | structured_cell_found_text_preferred | electrical¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #3/4/5 LEB | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦gtg¦heating¦leb¦local¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.8000 | 0.6716 | 0.7615 | 0.7615 | [6 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 5 | 42.0373 | 0.6273 | 0.0318 | 0.0238 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAI-133904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #3/4/5 LEB | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | Plan for Local Electrical Building |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7482 | 0.9244 | 0.6471 | g_ambig | generic_ok | 0.90 |  | 41 | Competing rules shown are for GT piping route plans or building/structural plans, not HVAC duct & refrigerant piping plans. | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6492 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAL-134001 | LOAD CALCULATION OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Administration & Social Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5995 | 0.6465 | 0.6465 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 33.0724 | 0.5737 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAL-134002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Administration & Social Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 20 | 4 | 29.3983 | 0.6026 | 0.0281 | 0.0281 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAL-134003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ADMIN & SOCIAL BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Administration & Social Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7587 | 0.6943 | 0.6943 | g_safe | [5 empty] | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | true | false | 4 | 1 | 41.1004 | 0.6429 | 0.0320 | 0.0240 | hybrid | structured_no_phase | hvac | [5 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAL-134004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6643 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134101 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #1 LEB | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦heating¦leb¦local¦stg¦ventilating | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.6757 | 0.9027 | 0.9027 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦hvac | stg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 30.4639 | 0.5725 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAR-134102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #1 LEB | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦heating¦leb¦local¦stg¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_ambig | generic_ok | 0.95 |  | 1 | The competing specific rule is for steam turbine trip/protection, not an HVAC air flow diagram. | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 34 | 9 | 26.7038 | 0.5880 | 0.0251 | 0.0251 | hybrid | structured_cell_found_text_preferred | electrical¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#1 LEB | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦heating¦leb¦local¦stg¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6448 | 0.6134 | 0.6134 | [6 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 42.0373 | 0.6093 | 0.0323 | 0.0242 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAR-134104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #1 LEB | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac | stg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6261 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134201 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #2 LEB | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM |  | ST #2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦heating¦leb¦local¦stg¦ventilating | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.6852 | 0.9056 | 0.9056 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦hvac | stg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2672 | 0.5748 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAR-134202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #2 LEB | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦heating¦leb¦local¦stg¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_ambig | generic_ok | 0.95 |  | 1 | The competing specific rule is for steam turbine trip/protection, not an HVAC air flow diagram. | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 52 | 10 | 25.4483 | 0.5871 | 0.0232 | 0.0232 | hybrid | structured_cell_found_text_preferred | electrical¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#2 LEB | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦heating¦leb¦local¦stg¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6451 | 0.6135 | 0.6135 | [6 empty] | FI | 0PF5000W36A05T | (HVAC Equipment) 1st Delivery on site_Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System |  | 2008-05-14 |  | delivery | query_unknown | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 40.5552 | 0.6277 | 0.0320 | 0.0240 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2025-02-14 | 2025-03-16 | 2025-04-15 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAR-134204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #2 LEB | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac | stg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6302 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134301 | LOAD CALCULATION OF HVAC SYSTEM FOR MAIN GATE HOUSE | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7184 | 0.9155 | 0.9155 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2672 | 0.5693 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-134302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR MAIN GATE HOUSE | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 37 | 4 | 25.4483 | 0.5760 | 0.0259 | 0.0259 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR MAIN GATE HOUSE | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Security Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | PLUMBING EQUIPMENT SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6979 | 0.6760 | 0.4732 | g_safe | [5 empty] | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | true | false | 1 | 1 | 46.8354 | 0.6574 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-134304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR MAIN GATE HOUSE | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 37.5070 | 0.6576 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAN-134401 | LOAD CALCULATION OF HVAC SYSTEM FOR SUPPORT BUILDING | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Support Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7227 | 0.9168 | 0.9168 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 7 | 1 | 33.0724 | 0.6013 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | hvac | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAN-134402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SUPPORT BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Support Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 20 | 2 | 29.3983 | 0.6173 | 0.0286 | 0.0286 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAN-134403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SUPPORT BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Support Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7385 | 0.6216 | 0.6216 | g_safe | [5 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 42.0373 | 0.6378 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2025-02-28 | 2025-03-30 | 2025-04-29 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAN-134404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SUPPORT BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Support Building |  | Plan for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING PLAN | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | rule_query | plan | plan | plan | plan | support |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6612 | 0.7234 | 0.7234 | g_safe | [5 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6648 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-30 | 2024-04-29 | fi_complete | 0.90 | fc_earliest | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAD-134501 | LOAD CALCULATION OF HVAC SYSTEM FOR SECURITY BUILDING | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7123 | 0.9137 | 0.9137 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 7 | 1 | 33.0724 | 0.6112 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | hvac | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAD-134502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SECURITY BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 20 | 1 | 29.3983 | 0.6264 | 0.0289 | 0.0289 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAD-134503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SECURITY BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Security Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7616 | 0.7885 | 0.7885 | g_safe | [5 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 42.0373 | 0.6279 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAD-134504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SECURITY BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6686 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134601 | LOAD CALCULATION OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.7093 | 0.7128 | 0.7128 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2672 | 0.5536 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-134602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 37 | 4 | 25.4483 | 0.5554 | 0.0259 | 0.0259 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SEARCH FACILITY & VISITORS CENTRE | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Security Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.5455 | 0.6811 | 0.5862 | 0.5862 | g_safe | [5 empty] | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 41.2828 | 0.6181 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-05-17 | 2024-06-16 | 2024-07-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-134604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6310 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAF-134701 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE BRIGADE | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦fire_protection¦heating¦ventilating | fire_protection | scoped | match | match | match | passed |  | 1.0000 | 0.7604 | 0.9281 | 0.9281 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 36.0291 | 0.6705 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAF-134702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE BRIGADE | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦fire_protection¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 55.5198 | 0.6607 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAF-134703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE BRIGADE | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | FIRE BRIGADE |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦fire_protection¦heating¦sysem¦ventilating | fire_protection | scoped | match | match | match | passed |  | 0.8000 | 0.8000 | 0.8000 | 0.8000 | [6 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 46.9134 | 0.6805 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAF-134704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE BRIGADE | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 42.1727 | 0.7035 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAB-134801 | LOAD CALCULATION OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Workshop & Storage Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7538 | 0.9261 | 0.9261 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 7 | 1 | 33.0724 | 0.5626 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | hvac | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAB-134802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Workshop & Storage Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 22 | 4 | 29.3983 | 0.5746 | 0.0278 | 0.0278 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAB-134803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WORKSHOP & STORAGE BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Workshop & Storage Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7876 | 0.8196 | 0.8196 | g_safe | [5 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 42.0373 | 0.6246 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAB-134804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6424 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAG-134901 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Fire Water Pump House |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | Fire Water Pump House | FIRE WATER PUMP HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦fire_protection¦heating¦pump¦ventilating | fire_protection¦pump | scoped | match | match | match | passed |  | 1.0000 | 0.7970 | 0.9391 | 0.9391 | [6 empty] | FI | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦hvac | fire_fighting | fire_fighting¦hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 41.5961 | 0.6663 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hvac | civil_design |  |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | fi_complete | 0.90 | fc_earliest | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAG-134902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Fire Water Pump House |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦fire_protection¦heating¦pump¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule targets a startup/shutdown diagram deliverable, not an HVAC air flow diagram for the fire water pump house. | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦hvac |  | fire_fighting¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 55.5198 | 0.6901 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAG-134903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE WATER PUMP HOUSE | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Fire Water Pump House |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦fire_protection¦heating¦pump¦sysem¦ventilating | fire_protection | scoped | match | match | match | passed |  | 0.6000 | 0.7052 | 0.6316 | 0.6316 | [6 empty] | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | fire_fighting¦hvac |  | fire_fighting¦hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 46.0514 | 0.6819 | 0.0323 | 0.0242 | hybrid | structured_no_phase | fire_fighting¦hvac | [5 empty] | 2024-05-17 | 2024-06-16 | 2024-07-16 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAG-134904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Fire Water Pump House |  | Plan for Fire Water Pump House | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦fire_protection¦house¦pump¦water | fire_protection¦pump | scoped | match | match | match | passed |  | 0.8333 | 0.8318 | 0.8329 | 0.8329 | [6 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | fire_fighting¦hvac | fire_fighting | fire_fighting¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 42.1727 | 0.7148 | 0.0328 | 0.0246 | hybrid | structured_no_phase | fire_fighting¦hvac | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAM-135001 | LOAD CALCULATION OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | CPP Regeneration Building | CPP & CPP REGEN BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7996 | 0.7999 | 0.7999 | g_safe | [5 empty] | FI | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate¦hvac |  | condensate¦hvac | query | acc¦condensate | match | false | false | 9 | 11 | 3.7338 | 0.4494 | 0.0286 | 0.0286 | hybrid | structured_preferred | condensate¦hvac | civil_design | 10 |  |  |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAM-135002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | condensate¦hvac |  | condensate¦hvac | query | fire_fighting¦hvac | discipline_only | true | false | 20 | 7 | 29.3983 | 0.5784 | 0.0274 | 0.0137 | hybrid | structured_cell_found_text_preferred | condensate¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.40 | needs_review | activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAM-135003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CPP & CPP REGEN BUILDING | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6006 | 0.6002 | 0.6002 | g_safe | [5 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | condensate¦hvac |  | condensate¦hvac | query | fire_fighting¦hvac | discipline_only | true | false | 1 | 2 | 42.0373 | 0.6473 | 0.0325 | 0.0122 | hybrid | structured_no_phase | condensate¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.30 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAM-135004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7415 | 0.9225 | 0.6457 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | condensate¦hvac |  | condensate¦hvac | query | fire_fighting¦hvac | discipline_only | true | false | 1 | 1 | 37.5070 | 0.6698 | 0.0328 | 0.0123 | hybrid | structured_no_phase | condensate¦hvac |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_phase_status=query_unknown;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAV-135101 | LOAD CALCULATION OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM |  |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | WASTE WATER TREATMENT PLANT | CALCULATION OF WASTE WATER TREATMENT PLANT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.6626 | 0.7821 | 0.7821 | [6 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | hvac | wts | hvac | query | fire_fighting¦hvac | match | true | false | 5 | 1 | 37.4408 | 0.6057 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | hvac | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAV-135102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM |  |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM | Water Treatment System | Control Configuration Diagram for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.5483 | 0.6645 | 0.6645 | [6 empty] | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | hvac | wts | hvac | query | fire_fighting¦hvac | match | true | false | 27 | 3 | 34.4673 | 0.6215 | 0.0274 | 0.0274 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-05-31 | 2024-06-30 | 2024-07-30 | 2024-08-14 | 2024-08-29 | 2024-09-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAV-135103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM |  |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7216 | 0.6831 | 0.6831 | [6 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | hvac | wts | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 42.0373 | 0.6504 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAV-135104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | Plan |  | Heating Ventilating and Air Conditioning SYSTEM |  |  | Plan for Heating Ventilating and Air Conditioning SYSTEM |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | air¦conditioning¦heating¦ventilating¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7287 | 0.9186 | 0.6430 | g_ambig | generic_ok | 0.90 |  | 20 | Competing rules are for water treatment building civil/architectural plans or an ITP, not HVAC duct & refrigerant piping plans. | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 37.5070 | 0.6572 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAQ-135201 | LOAD CALCULATION OF HVAC SYSTEM FOR AUX. LEB | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM |  | AUX. LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦electrical¦heating¦leb¦local¦ventilating | leb | scoped | match | match | match | passed |  | 1.0000 | 0.7531 | 0.9259 | 0.9259 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2672 | 0.5478 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAQ-135202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR AUX. LEB | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦electrical¦heating¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 48 | 11 | 25.4483 | 0.5565 | 0.0233 | 0.0233 | hybrid | structured_cell_found_text_preferred | electrical¦hvac | system_design¦engineering |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAQ-135203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR AUX. LEB | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | air¦conditioning¦electrical¦heating¦leb¦local¦sysem¦ventilating | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.6033 | 0.6010 | 0.6010 | [6 empty] | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  | delivery | query_unknown | electrical¦hvac | gtg | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 42.0373 | 0.6400 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac | [5 empty] | 2024-12-30 | 2025-01-29 | 2025-02-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAQ-135204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR AUX. LEB | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | Local Electrical Building |  | Plan for Local Electrical Building |  | DUCT & PIPING PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7422 | 0.9227 | 0.6459 | g_ambig | uncertain |  |  | 28 |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 37.5070 | 0.6496 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦hvac |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135301 | LOAD CALCULATION OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | PLANT ACCESS GATE HOUSE |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6553 | 0.7216 | 0.7216 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2674 | 0.5680 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-135302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | PLANT ACCESS GATE HOUSE |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 50.8544 | 0.6431 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PLANT ACCESS GATE HOUSE | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | PLANT ACCESS GATE HOUSE |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | PLUMBING EQUIPMENT SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6979 | 0.6760 | 0.4732 | g_safe | [5 empty] | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | true | false | 1 | 1 | 46.8356 | 0.6598 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-135304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | PLANT ACCESS GATE HOUSE |  | Plan for PLANT ACCESS GATE HOUSE |  | Gate House FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | access¦gate¦house¦plant |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6017 | 0.7055 | 0.7055 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 37.5073 | 0.6692 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135401 | LOAD CALCULATION OF HVAC SYSTEM FOR PIC GATE HOUSE | LOAD CALCULATION |  | Heating Ventilating and Air Conditioning SYSTEM | PIC GATE HOUSE |  | LOAD CALCULATION for Heating Ventilating and Air Conditioning SYSTEM | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6417 | 0.7175 | 0.7175 | g_safe | [5 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2672 | 0.5613 | 0.0328 | 0.0328 | hybrid | structured_preferred | hvac | civil_design | 8 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-135402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PIC GATE HOUSE | AIR FLOW DIAGRAM |  | Heating Ventilating and Air Conditioning SYSTEM | PIC GATE HOUSE |  | AIR FLOW DIAGRAM for Heating Ventilating and Air Conditioning SYSTEM |  | Air FloW Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7245 | 0.9173 | 0.6421 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 50.8542 | 0.6397 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PIC GATE HOUSE | EQUIPMENT SCHEDULE |  | Heating Ventilating and Air Conditioning SYSEM | PIC GATE HOUSE |  | EQUIPMENT SCHEDULE for Heating Ventilating and Air Conditioning SYSEM |  | PLUMBING EQUIPMENT SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | air¦conditioning¦heating¦sysem¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6979 | 0.6760 | 0.4732 | g_safe | [5 empty] | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown | hvac |  | hvac | query | hvac | match | true | false | 1 | 1 | 46.8354 | 0.6508 | 0.0328 | 0.0246 | hybrid | structured_no_phase | hvac |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.30 |  | false | false | 0.51 | needs_review | rule_score_medium;activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-135404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PIC GATE HOUSE | Plan |  | Heating Ventilating and Air Conditioning SYSTEM | PIC GATE HOUSE |  | Plan for PIC GATE HOUSE |  | Gate House FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | gate¦house¦pic |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6163 | 0.7099 | 0.7099 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  | system_design | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 37.5070 | 0.6731 | 0.0325 | 0.0244 | hybrid | structured_no_phase | hvac |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136001 | VENDOR PRINT FOR HVAC EQUIPMENT-1 | VENDOR PRINT | Heating Ventilating and Air Conditioning EQUIPMENT-1 | HVAC System |  |  | VENDOR PRINT for Heating Ventilating and Air Conditioning EQUIPMENT-1 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5949 | 0.6451 | 0.4516 | [7 empty] | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 48.5498 | 0.6771 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136002 | VENDOR PRINT FOR HVAC EQUIPMENT-2 | VENDOR PRINT | Heating Ventilating and Air Conditioning EQUIPMENT-2 | HVAC System |  |  | VENDOR PRINT for Heating Ventilating and Air Conditioning EQUIPMENT-2 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6094 | 0.6495 | 0.4546 | [7 empty] | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 48.5498 | 0.6841 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136003 | VENDOR PRINT FOR HVAC EQUIPMENT-3 | VENDOR PRINT | Heating Ventilating and Air Conditioning EQUIPMENT-3 | HVAC System |  |  | VENDOR PRINT for Heating Ventilating and Air Conditioning EQUIPMENT-3 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.6068 | 0.6487 | 0.4541 | [7 empty] | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 48.5498 | 0.6735 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136004 | VENDOR PRINT FOR HVAC EQUIPMENT-4 | VENDOR PRINT | Heating Ventilating and Air Conditioning EQUIPMENT-4 | HVAC System |  |  | VENDOR PRINT for Heating Ventilating and Air Conditioning EQUIPMENT-4 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5983 | 0.6462 | 0.4523 | [7 empty] | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 48.5498 | 0.6717 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136005 | VENDOR PRINT FOR HVAC EQUIPMENT-5 | VENDOR PRINT | Heating Ventilating and Air Conditioning EQUIPMENT-5 | HVAC System |  |  | VENDOR PRINT for Heating Ventilating and Air Conditioning EQUIPMENT-5 | [5 empty] | rule_query | other | other | vendor_print | motor_vendor_print | air¦conditioning¦heating¦ventilating |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5988 | 0.6463 | 0.4524 | [7 empty] | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 |  | procurement | query_unknown | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 48.5498 | 0.6710 | 0.0323 | 0.0242 | hybrid | structured_no_phase | hvac | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SG-136601 | FIRE FIGHTING SYSTEM CONCEPTUAL DESIGN | DESIGN |  | FIRE FIGHTING SYSTEM |  |  | DESIGN for FIRE FIGHTING SYSTEM | [5 empty] | rule_query | other | other | design | fire_fighting_system | fighting¦fire¦fire_protection | fire_protection | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.7606 | 0.9282 | 0.6497 | [7 empty] | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 34.9449 | 0.6981 | 0.0328 | 0.0246 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SG-136602 | FIRE RISK EVALUATION | EVALUATION |  |  |  |  | EVALUATION | [5 empty] | rule_query | other | other | evaluation | technical_bid_evaluation |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.4798 | 0.3773 | 0.2641 | [7 empty] | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 6 | 9 | 6.8830 | 0.4210 | 0.0296 | 0.0167 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136603 | FIRE SERVICE RING MAIN SYSTEM - P&ID | P&ID |  | FIRE SERVICE RING MAIN SYSTEM |  |  | P&ID for FIRE SERVICE RING MAIN SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6421 | 0.4260 | 0.4260 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 3 | 3 | 30.9723 | 0.6274 | 0.0317 | 0.0317 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136604 | FIRE SERVICE RING MAIN SYSTEM - PIPE LAYOUT AND DETAIL DRAWING | LAYOUT AND DETAIL DRAWING |  | FIRE SERVICE RING MAIN SYSTEM |  |  | LAYOUT AND DETAIL DRAWING for FIRE SERVICE RING MAIN SYSTEM |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7303 | 0.9191 | 0.6434 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 21.2965 | 0.5294 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGA-136605 | FIRE SERVICE RING MAIN SYSTEM - HYDRAULIC CALCULATION | HYDRAULIC CALCULATION |  | FIRE SERVICE RING MAIN SYSTEM |  |  | HYDRAULIC CALCULATION for FIRE SERVICE RING MAIN SYSTEM | MAIN GATE | MAIN GATE HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5252 | 0.5076 | 0.5076 | g_safe | [5 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 14.9275 | 0.4779 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CYE-136606 | FIRE DETECTION AND ALARM SYSTEM - BLOCK DIAGRAM | BLOCK DIAGRAM |  | FIRE DETECTION AND ALARM SYSTEM |  |  | BLOCK DIAGRAM for FIRE DETECTION AND ALARM SYSTEM | Cathodic | Block Diagram | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | diagram | diagram | diagram | diagram | alarm¦detection¦fire |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4697 | 0.6076 | 0.6076 | g_safe | [5 empty] | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 33.2223 | 0.5510 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136607 | FIRE DETECTION AND ALARM SYSTEM - NETWORK SINGLE LINE DIAGRAM | Single Line Diagram |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Single Line Diagram for FIRE DETECTION AND ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦detection¦fire |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6995 | 0.9099 | 0.9099 | g_safe | [5 empty] | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 5 | 33.2223 | 0.5638 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136609 | FIRE FIGHTING PUMP SYSTEM - DATASHEET | Data Sheet |  | FIRE FIGHTING PUMP SYSTEM |  |  | Data Sheet for FIRE FIGHTING PUMP SYSTEM | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fighting¦fire¦fire_protection¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.8726 | 0.7868 | 0.7868 | [6 empty] | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 35.6767 | 0.6790 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-11-07 | 2024-12-12 | 2025-01-16 | 2025-01-02 | 2025-02-06 | 2025-03-13 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136610 | OUTDOOR HYDRANT SYSTEM - DATASHEET | Data Sheet |  | OUTDOOR HYDRANT SYSTEM |  |  | Data Sheet for OUTDOOR HYDRANT SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | hydrant¦outdoor |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5768 | 0.6397 | 0.6397 | g_safe | [5 empty] | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 9.0704 | 0.5505 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136611 | STAND PIPE SYSTEM - DATASHEET | Data Sheet |  | STAND PIPE SYSTEM |  |  | Data Sheet for STAND PIPE SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fire_protection¦pipe¦stand |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5920 | 0.6443 | 0.6443 | g_ambig | generic_ok | 0.75 |  | 3 | Competing specific rules are for fire alarm system or deluge spray pump, not a stand pipe system datasheet. | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 9.0704 | 0.5736 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGE-136612 | SPRINKLER SYSTEM - DATASHEET | Data Sheet |  | SPRINKLER SYSTEM |  |  | Data Sheet for SPRINKLER SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | fire_protection¦sprinkler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6035 | 0.6477 | 0.6477 | g_ambig | generic_ok | 0.75 |  | 3 | Competing specific rules are for fire alarm system or deluge spray pump, not a sprinkler system datasheet. | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 9.0704 | 0.5428 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGC-136613 | WATER SPRAY SYSTEM - DATASHEET | Data Sheet |  | WATER SPRAY SYSTEM |  |  | Data Sheet for WATER SPRAY SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | spray¦water |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5937 | 0.6448 | 0.6448 | g_safe | [5 empty] | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 9.0704 | 0.5350 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGK-136614 | CLEAN AGENT SYSTEM - DATASHEET | Data Sheet |  | CLEAN AGENT SYSTEM |  |  | Data Sheet for CLEAN AGENT SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | agent¦clean¦fire_protection |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5721 | 0.6383 | 0.6383 | g_ambig | generic_ok | 0.75 |  | 3 | Competing specific rules are for fire alarm system or deluge spray pump, not a clean agent system datasheet. | FA | 3PF1265W38A04P | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2007-04-30 | 2008-05-13 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦gtg | match | true | false | 3 | 4 | 30.3054 | 0.6102 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | fire_fighting | procurement |  | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGZ-136615 | FIRE EXTINGUISHER SYSTEM - DATASHEET | Data Sheet |  | FIRE EXTINGUISHER SYSTEM |  |  | Data Sheet for FIRE EXTINGUISHER SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | extinguisher¦fire |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6167 | 0.6517 | 0.6517 | g_safe | [5 empty] | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | procurement | procurement | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 1 | 1 | 22.3779 | 0.6048 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGX-136616 | PIPE AND BULK MATERIAL - DATASHEET | Data Sheet |  |  |  |  | Data Sheet |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet |  |  | generic | match | match | query_unscoped | passed |  | 0.6667 | 0.7755 | 0.6993 | 0.6993 | [6 empty] | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 2 | 15.8120 | 0.6399 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | 2024-11-20 | 2024-12-05 | 2024-12-20 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CYE-136617 | FIRE DETECTION AND ALARM SYSTEM - DATASHEET | Data Sheet |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Data Sheet for FIRE DETECTION AND ALARM SYSTEM |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet | alarm¦detection¦fire |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5742 | 0.6389 | 0.6389 | g_safe | [5 empty] | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 7 | 1 | 27.3355 | 0.6073 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | procurement |  | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CYE-136618 | CABLE AND BULK MATERIAL - DATASHEET | Data Sheet |  |  |  |  | Data Sheet |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | rule_query | datasheet | datasheet | data_sheet | data_sheet |  |  | generic | match | match | query_unscoped | passed |  | 0.6667 | 0.7755 | 0.6993 | 0.6993 | [6 empty] | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 2 | 15.7092 | 0.5632 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0SG-136620 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR ESOD | PROCEDURE |  | FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  |  | PROCEDURE for FIRE FIGHTING, DETECTION AND ALARM SYSTEM | Chemical Dosing System | Commissioning Procedure | 1 | start-2M-2M<=FA<=start-2M | FA ∈ [start-120d, start-60d] | title | procedure | procedure | procedure | procedure | alarm¦detection¦fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5430 | 0.5829 | 0.5829 | g_safe | [5 empty] | FI | 0CF4500W90A08 | (Fire WTR Pump Shelter) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-06 | 2008-07-02 | commissioning | commissioning | match | fire_fighting | wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 9 | 6 | 36.3490 | 0.5776 | 0.0296 | 0.0296 | hybrid | structured_preferred | fire_fighting | commissioning | 10 | 2025-03-05 | 2025-04-04 | 2025-05-04 | 2025-05-19 | 2025-06-03 | 2025-06-18 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SG-136621 | PIPING MATERIAL SPECIFICATION FOR FIRE FIGHTING SYSTEM | Technical Specification |  | FIRE FIGHTING SYSTEM |  |  | Technical Specification for FIRE FIGHTING SYSTEM |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | fighting¦fire¦fire_protection |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5606 | 0.6348 | 0.4444 | g_safe | [5 empty] | FA | 0EF4500W38A08 | (Fire Fighting System) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 38.6106 | 0.6776 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SGA-136622 | ISOMETRIC DRAWING FOR FIRE SERVICE RING MAIN SYSTEM | Isometric Drawing |  | FIRE SERVICE RING MAIN SYSTEM |  |  | Isometric Drawing for FIRE SERVICE RING MAIN SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | fire¦main¦ring¦service |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6071 | 0.4621 | 0.4621 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting | compressed_air | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 16.7207 | 0.5272 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design | 2 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0SG-136623 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR NON ESOD | PROCEDURE |  | FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  |  | PROCEDURE for FIRE FIGHTING, DETECTION AND ALARM SYSTEM | Chemical Dosing System | Commissioning Procedure | 1 | start-2M-2M<=FA<=start-2M | FA ∈ [start-120d, start-60d] | title | procedure | procedure | procedure | procedure | alarm¦detection¦fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5346 | 0.5804 | 0.5804 | g_safe | [5 empty] | FI | 0CF4500W90A09 | (Fire Fighting BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-02-02 | 2008-03-31 | commissioning | commissioning | match | fire_fighting | wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 7 | 8 | 37.4743 | 0.5800 | 0.0296 | 0.0296 | hybrid | structured_preferred | fire_fighting | commissioning | 10 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136624 | FIRE DETECTION AND ALARM SYSTEM LAYOUT FOR YARD AREA | Layout Drawing |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Layout Drawing for FIRE DETECTION AND ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦detection¦fire |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6255 | 0.5376 | 0.5376 | g_safe | [5 empty] | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 23.5084 | 0.5410 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SUPPORT BUILDING | ARRANGEMENT |  |  | Support Building |  | ARRANGEMENT for Support Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | support |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5715 | 0.4048 | 0.3441 | g_safe | [5 empty] | FA | 0EF3520W00A01.3 | (Foam Station BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Foam Station Building | 2007-05-01 |  | civil_design | civil_design | match |  |  |  |  | fgp¦fire_fighting | query_unscoped | false | false | 29 | 113 | 10.9843 | 0.4795 | 0.0170 | 0.0128 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136641 | FIRE ALARM SYSTEM LAYOUT FOR SUPPORT BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | Support Building |  | Layout Drawing for Support Building | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦support | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6311 | 0.5393 | 0.5393 | [6 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 18.8774 | 0.5966 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SUPPORT BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | Support Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 27 | 12 | 18.8774 | 0.5385 | 0.0254 | 0.0254 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136701 | P&ID OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | P&ID |  | STAND PIPE SYSTEM | Central Control Building |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | rule_query | diagram | diagram | p_id | p_id | ccr¦central¦fire_protection¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7537 | 0.4594 | 0.4594 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 17.8084 | 0.6095 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136702 | P&ID OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | P&ID |  | SPRINKLER SYSTEM | Central Control Building |  | P&ID for SPRINKLER SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | ccr¦central¦fire_protection¦sprinkler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6783 | 0.4368 | 0.4368 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 17.8084 | 0.5936 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136703 | P&ID OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | P&ID |  | CLEAN AGENT SYSTEM | Central Control Building |  | P&ID for CLEAN AGENT SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | agent¦ccr¦central¦clean¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6797 | 0.4372 | 0.4372 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 80 | 10 | 17.8084 | 0.6075 | 0.0214 | 0.0214 | hybrid | structured_blocked_procurement_conflict | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | Central Control Building |  | PIPE LAYOUT AND DETAIL for Central Control Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7696 | 0.7909 | 0.5536 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 4 | 9.8406 | 0.5013 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136712 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | Central Control Building |  | PIPE LAYOUT AND DETAIL for Central Control Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7542 | 0.7863 | 0.5504 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 9.8406 | 0.4864 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136713 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | Central Control Building |  | PIPE LAYOUT AND DETAIL for Central Control Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7542 | 0.7863 | 0.5504 | g_safe | [5 empty] | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 9.3549 | 0.5264 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136722 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | Calculation sheet |  | SPRINKLER SYSTEM | Central Control Building |  | Calculation sheet for SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | ccr¦central¦fire_protection¦sprinkler | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.7082 | 0.9124 | 0.9124 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 5.1115 | 0.5098 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136723 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | Calculation sheet |  | CLEAN AGENT SYSTEM | Central Control Building |  | Calculation sheet for CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦ccr¦central¦clean¦fire_protection | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.6795 | 0.9039 | 0.9039 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 5.1115 | 0.5183 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CENTRAL CONTROL BUILDING | ARRANGEMENT |  |  | Central Control Building |  | ARRANGEMENT for Central Control Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | ccr¦central |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5039 | 0.3845 | 0.3268 | g_safe | [5 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1 | 3 | 25.7139 | 0.5492 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136741 | FIRE ALARM SYSTEM LAYOUT FOR CENTRAL CONTROL BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | Central Control Building |  | Layout Drawing for Central Control Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6861 | 0.5558 | 0.5558 | g_ambig | generic_ok | 0.90 |  | 5 | Competing rules are for stormwater/wastewater drainage layouts, not fire alarm system layout drawings. | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 18.8774 | 0.5502 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | Central Control Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦ccr¦central¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 30 | 19 | 18.8774 | 0.5153 | 0.0238 | 0.0238 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | Calculation sheet |  | FIRE ALARM SYSTEM | Central Control Building |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦ccr¦central¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.6591 | 0.6644 | 0.6644 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 18.8774 | 0.4854 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | Central Control Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦ccr¦central¦fire¦fire_protection | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 | [7 empty] | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting | match | true | false | 1 | 1 | 31.1845 | 0.5515 | 0.0328 | 0.0246 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136801 | P&ID OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | P&ID | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | P&ID for Gas Turbine Generator #1,2 | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6484 | 0.4745 | 0.4745 | g_ambig | generic_ok | 0.85 |  | 18 | Competing specific rules are GT process/system P&IDs (fuel, lube oil, cooling, etc.), not a stand pipe system P&ID. | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | electrical¦gtg | bsedg | electrical¦gtg | query |  | activity_unscoped | true | true | 4 | 1660 | 23.9298 | 0.5320 | 0.0162 | 0.0097 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.33 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136802 | P&ID OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | P&ID | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | P&ID for Gas Turbine Generator #1,2 | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6484 | 0.4745 | 0.4745 | g_ambig | generic_ok | 0.85 |  | 18 | Competing specific rules are GT process/system P&IDs (fuel, lube oil, cooling, etc.), not a stand pipe system P&ID. | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | electrical¦gtg | bsedg | electrical¦gtg | query |  | activity_unscoped | true | true | 2 | 1850 | 23.9298 | 0.5093 | 0.0167 | 0.0100 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.33 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136803 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | P&ID | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | P&ID for Gas Turbine Generator #1,2 | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6484 | 0.4745 | 0.4745 | g_ambig | generic_ok | 0.85 |  | 18 | Competing specific rules are GT process/system P&IDs (fuel, lube oil, cooling, etc.), not a stand pipe system P&ID. | FA | 2EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match | electrical¦gtg | bsedg | electrical¦gtg | query |  | activity_unscoped | true | true | 5 | 1175 | 29.2829 | 0.5611 | 0.0162 | 0.0097 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.33 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for generator foundation embedded metals layout, not stand pipe system pipe layout/detail. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4061 | 0.6808 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136812 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for generator foundation embedded metals layout, not stand pipe system pipe layout/detail. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4061 | 0.6651 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136813 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for generator foundation embedded metals layout, not stand pipe system pipe layout/detail. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4061 | 0.6648 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136822 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | Calculation sheet | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Calculation sheet for Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5503 | 0.6318 | 0.6318 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4061 | 0.6186 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136823 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | Calculation sheet | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Calculation sheet for Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5503 | 0.6318 | 0.6318 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 2 | 15.4061 | 0.6220 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #1,2 LEB | ARRANGEMENT | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | ARRANGEMENT for Gas Turbine Generator #1,2 |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4671 | 0.3735 | 0.3174 | g_safe | [5 empty] | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 7 | 22.3846 | 0.6440 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136841 | FIRE ALARM SYSTEM LAYOUT FOR GTG #1,2 LEB | Layout Drawing | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7161 | 0.5648 | 0.5648 | g_ambig | generic_ok | 0.85 |  | 7 | Competing rules relate to drainage layouts or GT foundations/embedded metals, not a fire alarm system layout. | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4061 | 0.6983 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | Single Line Diagram | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Single Line Diagram for Gas Turbine Generator #1,2 |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7242 | 0.9173 | 0.9173 | g_ambig | generic_ok | 0.80 |  | 5 | Competing specific rules are GT electrical distribution/generator circuit SLDs, not a fire alarm system single line diagram. | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 144 | 4 | 15.4061 | 0.6541 | 0.0205 | 0.0205 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | BATTERY CALCULATION | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | BATTERY CALCULATION for Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.4814 | 0.6111 | 0.6111 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4061 | 0.6308 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | CAUSE & EFFECT MATRIX | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | CAUSE & EFFECT MATRIX for Gas Turbine Generator #1,2 | [5 empty] | rule_query | other | other | cause_and_effect_matrix | gt_generator_outline | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gt¦gtg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6667 | 0.5185 | 0.6222 | 0.6222 | [7 empty] | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-31 | 2008-07-04 |  | commissioning | query_unknown | electrical¦gtg |  | electrical¦gtg | query | fire_fighting¦gtg | match | true | false | 7 | 3 | 18.1913 | 0.6328 | 0.0308 | 0.0231 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136901 | P&ID OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | P&ID | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | P&ID for Gas Turbine Generator #3,4,5 | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6287 | 0.4686 | 0.4686 | g_ambig | generic_ok | 0.85 |  | 18 | Competing specific rules are GT process/system P&IDs, not a stand pipe system P&ID for GTG #3/4/5 LEB. | FA | 3EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | electrical¦gtg | bsedg | electrical¦gtg | query |  | activity_unscoped | true | true | 19 | 1278 | 21.4795 | 0.5315 | 0.0134 | 0.0080 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.33 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136902 | P&ID OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | P&ID | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | P&ID for Gas Turbine Generator #3,4,5 | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6287 | 0.4686 | 0.4686 | g_ambig | generic_ok | 0.85 |  | 18 | Competing specific rules are GT process/system P&IDs, not a stand pipe system P&ID for GTG #3/4/5 LEB. | FA | 3EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | electrical¦gtg | bsedg | electrical¦gtg | query |  | activity_unscoped | true | true | 17 | 1532 | 21.4795 | 0.5067 | 0.0136 | 0.0082 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.33 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136903 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | P&ID | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | P&ID for Gas Turbine Generator #3,4,5 | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6287 | 0.4686 | 0.4686 | g_ambig | generic_ok | 0.85 |  | 18 | Competing specific rules are GT process/system P&IDs, not a stand pipe system P&ID for GTG #3/4/5 LEB. | FA | 3EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match | electrical¦gtg | bsedg | electrical¦gtg | query |  | activity_unscoped | true | true | 7 | 686 | 26.8853 | 0.5707 | 0.0163 | 0.0098 | hybrid | structured_blocked_procurement_conflict | electrical¦gtg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.33 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for generator foundation embedded metals layout, not stand pipe system pipe layout/detail. | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 10 | 2 | 13.8021 | 0.6587 | 0.0304 | 0.0304 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136912 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for generator foundation embedded metals layout, not stand pipe system pipe layout/detail. | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 10 | 2 | 13.8021 | 0.6380 | 0.0304 | 0.0304 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136913 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_ambig | generic_ok | 0.90 |  | 1 | The competing rule is for generator foundation embedded metals layout, not stand pipe system pipe layout/detail. | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 10 | 2 | 13.8021 | 0.6489 | 0.0304 | 0.0304 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136922 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | Calculation sheet | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Calculation sheet for Gas Turbine Generator #3,4,5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5681 | 0.6371 | 0.6371 | [6 empty] | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 12 | 1 | 13.1061 | 0.5942 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136923 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | Calculation sheet | Gas Turbine Generator | CLEAN AGENT SYSTEM | Local Electrical Building |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg | gtg | electrical¦fire_fighting¦gtg | query | gtg | match | true | false | 12 | 1 | 11.3974 | 0.5828 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #3,4,5 LEB | ARRANGEMENT | Gas Turbine Generator |  | Local Electrical Building |  | ARRANGEMENT for GTG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦gas¦generator¦gtg¦leb¦local¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6411 | 0.4257 | 0.3618 | g_safe | [5 empty] | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 6 | 18.3759 | 0.6045 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-06-30 | 2024-07-15 | 2024-07-30 | 2024-08-29 | 2024-09-13 | 2024-09-28 | generated | 0.60 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136941 | FIRE ALARM SYSTEM LAYOUT FOR GTG #3,4,5 LEB | Layout Drawing | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7161 | 0.5648 | 0.5648 | g_ambig | generic_ok | 0.86 |  | 7 | The document is a fire alarm system layout, not a GT foundation embedded metals/heater foundation or storm/wastewater drainage layout. | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg |  | electrical¦fire_fighting¦gtg | query | gtg | match | true | false | 20 | 1 | 11.3974 | 0.6585 | 0.0289 | 0.0289 | hybrid | structured_preferred | electrical¦fire_fighting¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | Single Line Diagram | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦fire_protection¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | use_specific | 0.78 | GT - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | 5 | A generator/medium-voltage SLD aligns directly with the generator circuit single line diagram specific rule. | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg |  | electrical¦fire_fighting¦gtg | query | gtg | match | true | false | 465 | 41 | 11.3974 | 0.6174 | 0.0118 | 0.0118 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting¦gtg | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | Calculation sheet | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦fire_fighting¦gtg | gtg | electrical¦fire_fighting¦gtg | query | gtg | match | true | false | 20 | 1 | 11.3974 | 0.6010 | 0.0289 | 0.0289 | hybrid | structured_preferred | electrical¦fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | CAUSE & EFFECT MATRIX | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | CAUSE & EFFECT MATRIX for GTG | [5 empty] | rule_query | other | procedure | cause_and_effect_matrix | procedure | electrical¦fire_protection¦gas¦generator¦gtg¦leb¦local¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.4756 | 0.4227 | 0.4227 | [7 empty] | 3SF1265W62A09.00 | (F/F GTG#31) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2008-08-14 | 2008-08-23 |  | commissioning | query_unknown | electrical¦fire_fighting¦gtg |  | electrical¦fire_fighting¦gtg | query | fire_fighting¦gtg | match | true | false | 1 | 2 | 35.3318 | 0.6213 | 0.0325 | 0.0244 | hybrid | structured_no_phase | electrical¦fire_fighting¦gtg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137001 | P&ID OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | P&ID | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID for WATER SPRAY SYSTEM |  | GT - COOLING WATER SYSTEM FOR GT P&I DIAGRAM | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | rule_query | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦spray¦turbine¦water | gt¦gtg | scoped | match | match | match | passed |  | 0.4286 | 0.6437 | 0.4931 | 0.4931 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query |  | activity_unscoped | true | true | 1 | 183 | 27.6262 | 0.6040 | 0.0205 | 0.0123 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦gtg | system_design¦procurement |  | 2024-06-06 | 2024-07-06 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-09-19 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137011 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | PIPE LAYOUT AND DETAIL | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6115 | 0.8834 | 0.6184 | g_ambig | generic_ok | 0.84 |  | 1 | This is a water spray piping layout for a transformer, which does not match the GT generator foundation embedded metals layout rule. | FA | 2EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | fire_fighting¦gtg | fire_fighting | fire_fighting¦gtg | query | ccw¦gtg | match | true | false | 3 | 19 | 12.1518 | 0.5763 | 0.0285 | 0.0214 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137021 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | Calculation sheet | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 2EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query | ccw¦gtg | match | true | false | 3 | 13 | 12.1518 | 0.5488 | 0.0296 | 0.0296 | hybrid | structured_preferred | fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG GSU TRANSFORMER | ARRANGEMENT | Gas Turbine Generator |  |  |  | ARRANGEMENT for GTG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6411 | 0.4257 | 0.3618 | g_safe | [5 empty] | FA | 3EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | design_drawing | civil_design | compatible | gtg |  | gtg | query | fgp¦gtg¦hrsg | match | true | false | 18 | 2 | 9.1051 | 0.6154 | 0.0289 | 0.0217 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | generated | 0.60 |  | false | false | 0.46 | needs_review | default_fc_window;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137041 | FIRE ALARM SYSTEM LAYOUT FOR GTG GSU TRANSFORMER | Layout Drawing | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for GTG | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5650 | 0.5195 | 0.5195 | g_ambig | generic_ok | 0.86 |  | 7 | The document is a fire alarm system layout, not a GT foundation embedded metals/heater foundation or storm/wastewater drainage layout. | SKIP | 1CF6500W16A02 | (GTG TR) FDN & Firewall Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-12-01 | 2008-04-01 | design_drawing | civil_design | compatible | fire_fighting¦gtg |  | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 14 | 3 | 10.0670 | 0.6471 | 0.0294 | 0.0220 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG GSU TRANSFORMER | Single Line Diagram | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | use_specific | 0.78 | GT - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | 5 | A generator/medium-voltage SLD aligns directly with the generator circuit single line diagram specific rule. | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦gtg |  | fire_fighting¦gtg | query | fire_fighting¦hvac | match | true | false | 1 | 4 | 26.4345 | 0.4948 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦engineering | 5 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137101 | P&ID OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | P&ID | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID for WATER SPRAY SYSTEM |  | GT - COOLING WATER SYSTEM FOR GT P&I DIAGRAM | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | rule_query | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦spray¦turbine¦water | gt¦gtg | scoped | match | match | match | passed |  | 0.4286 | 0.6437 | 0.4931 | 0.4931 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query |  | activity_unscoped | true | true | 1 | 325 | 27.6262 | 0.5834 | 0.0190 | 0.0114 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦gtg | system_design¦procurement |  | 2024-06-06 | 2024-07-06 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-09-19 | generated | 0.90 |  | false | false | 0.42 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | PIPE LAYOUT AND DETAIL | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6177 | 0.8853 | 0.6197 | g_ambig | generic_ok | 0.84 |  | 1 | This is a water spray piping layout for a transformer, which does not match the GT generator foundation embedded metals layout rule. | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | design_drawing | civil_design | compatible | fire_fighting¦gtg | fire_fighting | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 5 | 2 | 13.6978 | 0.6048 | 0.0315 | 0.0236 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | fa_earliest | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | Calculation sheet | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | fire_fighting¦gtg | gtg | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 15 | 13.8624 | 0.5496 | 0.0297 | 0.0297 | hybrid | structured_preferred | fire_fighting¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG UNIT AUX. TRANSFORMER | ARRANGEMENT | Gas Turbine Generator |  |  |  | ARRANGEMENT for GTG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6411 | 0.4257 | 0.3618 | g_safe | [5 empty] | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 8 | 3 | 12.7996 | 0.6402 | 0.0306 | 0.0229 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-15 | 2024-10-30 | generated | 0.60 |  | false | false | 0.46 | needs_review | default_fc_window;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137141 | FIRE ALARM SYSTEM LAYOUT FOR GTG UNIT AUX. TRANSFORMER | Layout Drawing | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for GTG | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5650 | 0.5195 | 0.5195 | g_ambig | generic_ok | 0.86 |  | 7 | The document is a fire alarm system layout, not a GT foundation embedded metals/heater foundation or storm/wastewater drainage layout. | SKIP | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | design_drawing | civil_design | compatible | fire_fighting¦gtg |  | fire_fighting¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 14 | 3 | 13.6978 | 0.6592 | 0.0294 | 0.0220 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG UNIT AUX. TRANSFORMER | Single Line Diagram | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | use_specific | 0.78 | GT - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | 5 | A generator/medium-voltage SLD aligns directly with the generator circuit single line diagram specific rule. | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦gtg |  | fire_fighting¦gtg | query | fire_fighting¦hvac | match | true | false | 1 | 4 | 26.4345 | 0.4882 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦gtg | system_design¦engineering | 5 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137201 | P&ID OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | P&ID | Steam Turbine & Generator | WATER SPRAY SYSTEM |  |  | P&ID for WATER SPRAY SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | generator¦spray¦steam¦stg¦turbine¦water |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6624 | 0.4320 | 0.4320 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG instrument air, while the document is for a water spray system P&ID. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query |  | activity_unscoped | true | true | 1 | 119 | 27.6262 | 0.6036 | 0.0220 | 0.0132 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7359 | 0.7808 | 0.7808 | [6 empty] | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | fire_fighting¦stg | stg | fire_fighting¦stg | query | gsut_uat¦stg | match | true | false | 1 | 7 | 16.6240 | 0.5865 | 0.0313 | 0.0235 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | Calculation sheet | Steam Turbine Generator GSU TRANSFORMER | WATER SPRAY SYSTEM |  |  | Calculation sheet for Steam Turbine Generator GSU TRANSFORMER |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦gsu¦steam¦stg¦transformer¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5125 | 0.5737 | 0.5737 | [6 empty] | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | gsut_uat¦stg | match | true | false | 1 | 8 | 22.2198 | 0.5396 | 0.0311 | 0.0311 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | civil_design | 10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG GSU TRANSFORMER | ARRANGEMENT | Steam Turbine Generator GSU TRANSFORMER |  |  |  | ARRANGEMENT for Steam Turbine Generator GSU TRANSFORMER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦gsu¦steam¦stg¦transformer¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4375 | 0.3646 | 0.3099 | g_safe | [5 empty] | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | gsut_uat¦stg |  | gsut_uat¦stg | query | gsut_uat¦stg | match | true | false | 4 | 1 | 22.2198 | 0.6360 | 0.0320 | 0.0240 | hybrid | structured_preferred | gsut_uat¦stg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137241 | FIRE ALARM SYSTEM LAYOUT FOR STG GSU TRANSFORMER | Layout Drawing | Steam Turbine Generator GSU TRANSFORMER | FIRE ALARM SYSTEM |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | [6 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 13 | 2 | 19.3427 | 0.6403 | 0.0298 | 0.0224 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG GSU TRANSFORMER | Single Line Diagram | Steam Turbine Generator GSU TRANSFORMER | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | fire_fighting¦gsut_uat¦stg |  | fire_fighting¦gsut_uat¦stg | query | stg | match | true | false | 3 | 1 | 5.6714 | 0.5336 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦engineering | 5 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137301 | P&ID OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | P&ID |  | STAND PIPE SYSTEM | Fire Water Pump House |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | title | diagram | diagram | p_id | p_id | fire_protection¦pipe¦pump¦stand |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7668 | 0.4634 | 0.4634 | g_ambig | use_specific | 0.62 | P&ID | 1 | The document is a stand pipe system P&ID and the specific rule 'P&ID' appears to be the governing P&ID timeline versus the broader 'Pipe and Instrument Diagrams (P&ID)' rule. | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 24.3903 | 0.6435 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | needs_review | rule_scope_status=rule_generic;rule_score_medium;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137302 | P&ID OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | P&ID |  | SPRINKLER SYSTEM | Fire Water Pump House |  | P&ID for SPRINKLER SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦pump¦sprinkler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6783 | 0.4368 | 0.4368 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 24.3903 | 0.6449 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137303 | P&ID OF FIRE WATER PUMP FOR FIRE WATER PUMP HOUSE | P&ID | FIRE WATER PUMP | Fire Fighting System | Fire Water Pump House |  | P&ID for Fire Fighting System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fighting¦fire¦fire_protection¦pump |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6987 | 0.4429 | 0.4429 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 50.0458 | 0.6866 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | Fire Water Pump House |  | PIPE LAYOUT AND DETAIL for Fire Water Pump House | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦fire_protection¦house¦pump¦water | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5714 | 0.6727 | 0.6018 | 0.6018 | [6 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 18.4726 | 0.5625 | 0.0320 | 0.0240 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-137312 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | Fire Water Pump House |  | PIPE LAYOUT AND DETAIL for Fire Water Pump House | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦fire_protection¦house¦pump¦water | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5714 | 0.7075 | 0.6122 | 0.6122 | [6 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 18.4726 | 0.5680 | 0.0320 | 0.0240 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-137322 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | Calculation sheet |  | SPRINKLER SYSTEM | Fire Water Pump House |  | Calculation sheet for SPRINKLER SYSTEM | Fire Water Pump House | FIRE WATER PUMP HOUSE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | fire_protection¦pump¦sprinkler | fire_protection¦pump | scoped | match | match | match | passed |  | 1.0000 | 0.8124 | 0.9437 | 0.9437 | [6 empty] | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 2 | 14.6770 | 0.5488 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137331 | FIRE WATER PUMP ARRANGEMENT FOR FIRE WATER PUMP HOUSE | ARRANGEMENT | FIRE WATER PUMP | Fire Fighting System | Fire Water Pump House |  | ARRANGEMENT for FIRE WATER PUMP |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | fire¦fire_protection¦pump¦water |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4432 | 0.3663 | 0.3114 | g_safe | [5 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 59.7685 | 0.6579 | 0.0325 | 0.0244 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137332 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE WATER PUMP HOUSE | ARRANGEMENT |  | Fire Fighting System | Fire Water Pump House |  | ARRANGEMENT for Fire Fighting System |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | fighting¦fire¦fire_protection¦pump |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5065 | 0.3853 | 0.3275 | g_safe | [5 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 6 | 33.6458 | 0.6213 | 0.0315 | 0.0237 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137341 | FIRE ALARM SYSTEM LAYOUT FOR FIRE WATER PUMP HOUSE | Layout Drawing |  | FIRE ALARM SYSTEM | Fire Water Pump House |  | Layout Drawing for Fire Water Pump House | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦fire_protection¦house¦pump¦water | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5714 | 0.7021 | 0.6106 | 0.6106 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | design_drawing | civil_design | compatible | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 2 | 28.3884 | 0.6096 | 0.0323 | 0.0242 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE WATER PUMP HOUSE | Single Line Diagram |  | FIRE ALARM SYSTEM | Fire Water Pump House |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦pump |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | generic_ok | 0.88 |  | 1 | The competing specific rule targets a boiler feedwater pump single line diagram, not a fire alarm system single line diagram for the fire water pump house. | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 33.0165 | 0.5914 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137401 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | P&ID | RESERVE BOILER | WATER SPRAY SYSTEM |  |  | P&ID for WATER SPRAY SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | reserve_boiler¦spray¦water |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6624 | 0.4320 | 0.4320 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 17.8084 | 0.5299 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦procurement | 10 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137411 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | PIPE LAYOUT AND DETAIL | RESERVE BOILER | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for WATER SPRAY SYSTEM |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | reserve_boiler¦spray¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7060 | 0.9118 | 0.6383 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting¦reserve_boiler | fire_fighting | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | true | false | 1 | 6 | 9.7725 | 0.4261 | 0.0315 | 0.0237 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137421 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | Calculation sheet | RESERVE BOILER | WATER SPRAY SYSTEM |  |  | Calculation sheet for RESERVE BOILER |  | Water injection System Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6276 | 0.6083 | 0.6083 | g_safe | [5 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 4.4658 | 0.4633 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR RESERVE BOILER | ARRANGEMENT | RESERVE BOILER |  |  |  | ARRANGEMENT for RESERVE BOILER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4671 | 0.3735 | 0.3174 | g_safe | [5 empty] | FA | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2007-12-05 |  | design_drawing | civil_design | compatible | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 56 | 3339 | 8.5272 | 0.3435 | 0.0089 | 0.0040 | hybrid | structured_system_absent | reserve_boiler | system_design¦civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137441 | FIRE ALARM SYSTEM LAYOUT FOR RESERVE BOILER | Layout Drawing | RESERVE BOILER | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦fire¦fire_protection¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6352 | 0.5405 | 0.5405 | g_ambig | generic_ok | 0.86 |  | 5 | This is a fire alarm system layout, whereas the competing rules are for stormwater/wastewater drainage layouts/calculations. | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 16.7207 | 0.5323 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR RESERVE BOILER | Single Line Diagram | RESERVE BOILER | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦reserve_boiler |  | fire_fighting¦reserve_boiler | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 26.4345 | 0.5276 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting¦reserve_boiler | system_design¦engineering | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-137603 | P&ID OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | P&ID |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | P&ID for Electrical System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | electrical¦fgp¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7356 | 0.4540 | 0.4540 | g_ambig | generic_ok | 0.83 |  | 6 | The document is a clean agent system P&ID for an electrical building, not a GT fuel gas system P&ID nor a generic extended-window P&ID rule clearly tied to this equipment. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | electrical¦fgp |  | electrical¦fgp | query | fgp | match | false | false | 25 | 1 | 17.8306 | 0.6461 | 0.0282 | 0.0282 | hybrid | structured_preferred | electrical¦fgp | system_design¦procurement | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.24 | needs_review_activity | default_fc_window;rule_score_medium;activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-137613 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | Layout Drawing |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fire_protection¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7072 | 0.6788 | 0.6788 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 14.3112 | 0.5948 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-137623 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | Calculation sheet |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for Electrical System | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | electrical¦fgp¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6876 | 0.9063 | 0.9063 | g_ambig | generic_ok | 0.78 |  | 5 | The competing specific rules are for foundations/stormwater or generic calculation sheets, while this is a clean agent system flow calculation for the FGS electrical building. | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 14.3112 | 0.5411 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | fc_earliest | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FGS ELECTRICAL BUILDING | ARRANGEMENT |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | ARRANGEMENT for Electrical System |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦fgp |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5967 | 0.4123 | 0.3505 | g_safe | [5 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp |  | electrical¦fgp | query | fgp | match | false | false | 1 | 1 | 20.5156 | 0.5517 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137641 | FIRE ALARM SYSTEM LAYOUT FOR FGS ELECTRICAL BUILDING | Layout Drawing |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fire_protection¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7072 | 0.6788 | 0.6788 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 14.3112 | 0.5761 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | Single Line Diagram |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Single Line Diagram for Electrical System |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | electrical¦fgp¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8935 | 0.9681 | 0.9681 | g_ambig | use_specific | 0.70 | Single Line Diagram | 2 | For Electrical System, the specific 'Single Line Diagram' rule explicitly provides the applicable FA/FC window versus the generic SKIP rule. | SKIP | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp |  | electrical¦fgp | query | fgp | match | false | false | 69 | 11 | 14.3112 | 0.5472 | 0.0218 | 0.0218 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-137643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | Calculation sheet |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for Electrical System | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | electrical¦fgp¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6809 | 0.9043 | 0.9043 | g_ambig | generic_ok | 0.78 |  | 5 | The competing specific rules are for foundations/stormwater or generic calculation sheets, while this is a clean agent system flow calculation for the FGS electrical building. | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | false | 4 | 5 | 14.3112 | 0.5054 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | fc_earliest | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-137644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | CAUSE & EFFECT MATRIX |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | CAUSE & EFFECT MATRIX for Electrical System | [5 empty] | rule_query | other | diagram | cause_and_effect_matrix | diagram | electrical¦fgp¦fire_protection | gt¦gtg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.4286 | 0.4795 | 0.4438 | 0.4438 | [7 empty] | 0CF3520W38A06.1 | (FGS LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 |  | commissioning | query_unknown | electrical¦fgp |  | electrical¦fgp | query | fgp¦fire_fighting | match | true | false | 1 | 119 | 18.9852 | 0.4787 | 0.0220 | 0.0165 | hybrid | structured_no_phase | electrical¦fgp | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137701 | P&ID OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | P&ID |  | Compressed Air System | Air Compressor Shelter |  | P&ID for Compressed Air System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | air¦compressed¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6767 | 0.4363 | 0.4363 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 34.0326 | 0.7412 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | Layout Drawing |  | Compressed Air System | Air Compressor Shelter |  | Layout Drawing for Air Compressor Shelter |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦fire_protection¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6486 | 0.8946 | 0.6262 | g_safe | [5 empty] | FA | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 5 | 2 | 24.4433 | 0.6614 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AIR COMPRESSOR SHELTER | ARRANGEMENT |  | Compressed Air System | Air Compressor Shelter |  | ARRANGEMENT for Compressed Air System |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | air¦compressed |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4920 | 0.3809 | 0.3238 | g_safe | [5 empty] | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 5 | 30.2436 | 0.6430 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137741 | FIRE ALARM SYSTEM LAYOUT FOR AIR COMPRESSOR SHELTER | Layout Drawing |  | Compressed Air System | Air Compressor Shelter |  | Layout Drawing for Air Compressor Shelter |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦fire_protection¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6486 | 0.8946 | 0.6262 | g_safe | [5 empty] | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 2 | 2 | 24.4433 | 0.6517 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AIR COMPRESSOR SHELTER | Single Line Diagram |  | Compressed Air System | Air Compressor Shelter |  | Single Line Diagram for Compressed Air System |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | air¦compressed¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7573 | 0.9272 | 0.9272 | g_safe | [5 empty] | SKIP | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 11 | 6 | 24.4433 | 0.6352 | 0.0292 | 0.0292 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137801 | P&ID OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | P&ID |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | P&ID for Tank | Water Treatment System | P&ID for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦tank¦wts | wts | scoped | match | match | match | passed |  | 0.4000 | 0.7048 | 0.4914 | 0.4914 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦wts | wts | fire_fighting¦wts | query | wts | match | false | false | 5 | 1 | 17.9395 | 0.6744 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting¦wts | system_design¦procurement | 10 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.31 | needs_review_activity | default_fc_window;rule_score_medium;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | Layout Drawing |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦fire_protection¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6378 | 0.6378 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | fire_fighting¦wts | electrical¦wts | fire_fighting¦wts | query | wts | match | true | false | 6 | 3 | 29.2776 | 0.6044 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | civil_design |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | ARRANGEMENT |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | ARRANGEMENT for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.3519 | 0.3389 | 0.2881 | g_safe | [5 empty] | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 34.6729 | 0.5971 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137841 | FIRE ALARM SYSTEM LAYOUT FORSHELTER FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | Layout Drawing |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦fire_protection¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6378 | 0.6378 | [6 empty] | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | fire_fighting¦wts | electrical¦wts | fire_fighting¦wts | query | wts | match | true | false | 3 | 9 | 29.2776 | 0.5863 | 0.0304 | 0.0304 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | Single Line Diagram |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Single Line Diagram for Tank |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | fire_protection¦tank¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8141 | 0.9442 | 0.9442 | g_ambig | uncertain | 0.45 |  | 1 | The title references WWT/bulk chemical storage shelter but equipment is blank, so it is unclear whether it should be treated as Water Treatment System for the specific rule. | SKIP | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | fire_fighting¦wts |  | fire_fighting¦wts | query | wts | match | true | false | 9 | 5 | 28.3427 | 0.5464 | 0.0299 | 0.0299 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137901 | P&ID OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | P&ID |  | Water Treatment System | Water Treatment Building |  | P&ID for Water Treatment System | Water Treatment System | P&ID for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9767 | 0.9930 | 0.9930 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 38.6026 | 0.7768 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-137902 | P&ID OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | P&ID |  | Water Treatment System | Water Treatment Building |  | P&ID for Water Treatment System | Water Treatment System | P&ID for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9767 | 0.9930 | 0.9930 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 38.6026 | 0.7608 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137903 | P&ID OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | P&ID |  | SPRINKLER SYSTEM | Water Treatment Building |  | P&ID for SPRINKLER SYSTEM | Water Treatment System | P&ID for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | fire_protection¦sprinkler¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.7640 | 0.9292 | 0.9292 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦wts | wts | fire_fighting¦wts | query | wts | match | true | false | 1 | 1 | 28.6047 | 0.6861 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | system_design¦procurement |  | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  | Water Treatment System | Water Treatment Building |  | PIPE LAYOUT AND DETAIL for Water Treatment Building | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7016 | 0.5605 | 0.5605 | [6 empty] | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 6 | 4 | 23.6410 | 0.6128 | 0.0308 | 0.0308 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-137912 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  | Water Treatment System | Water Treatment Building |  | PIPE LAYOUT AND DETAIL for Water Treatment Building | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7016 | 0.5605 | 0.5605 | [6 empty] | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 6 | 3 | 23.6410 | 0.6227 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-137913 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | Water Treatment Building |  | PIPE LAYOUT AND DETAIL for Water Treatment Building | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7016 | 0.5605 | 0.5605 | [6 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match | fire_fighting¦wts | wts | fire_fighting¦wts | query | wts | match | true | false | 10 | 1 | 12.6263 | 0.5752 | 0.0307 | 0.0307 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-137922 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | FLOW CALCULATION |  | Water Treatment System | Water Treatment Building |  | FLOW CALCULATION for Water Treatment System | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.8026 | 0.8241 | 0.8241 | [6 empty] | FA | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 6 | 3 | 23.6410 | 0.5692 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-137923 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | Water Treatment Building |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦sprinkler¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.5478 | 0.5144 | 0.5144 | [6 empty] | FA | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | fire_fighting¦wts | wts | fire_fighting¦wts | query | wts | match | true | false | 6 | 2 | 14.4183 | 0.5220 | 0.0313 | 0.0313 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WATER TREATMENT BUILDING | ARRANGEMENT |  | Water Treatment System | Water Treatment Building |  | ARRANGEMENT for Water Treatment System |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | treatment¦water¦wts |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5188 | 0.3890 | 0.3306 | g_safe | [5 empty] | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 2 | 9 | 29.6058 | 0.5486 | 0.0306 | 0.0306 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137941 | FIRE ALARM SYSTEM LAYOUT FOR WATER TREATMENT BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | Water Treatment Building |  | Layout Drawing for Water Treatment Building | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7016 | 0.6771 | 0.6771 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦wts | electrical¦wts | fire_fighting¦wts | query | fire_fighting¦hvac | match | true | false | 1 | 6 | 18.8774 | 0.5622 | 0.0315 | 0.0315 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 | 2024-12-05 | 2025-01-04 | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-03-20 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | Water Treatment Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | use_specific | 0.74 | Single Line Diagram for Water Treatment System | 1 | The document is for the water treatment building, matching the Water Treatment System-specific single line diagram rule. | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting¦wts |  | fire_fighting¦wts | query | fire_fighting¦hvac | match | true | false | 41 | 71 | 18.8774 | 0.5196 | 0.0175 | 0.0175 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-137943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | Water Treatment Building |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦fire¦fire_protection¦wts | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6377 | 0.6377 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting¦wts |  | fire_fighting¦wts | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 18.4555 | 0.4907 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting¦wts | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-137944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | MATRIX |  | FIRE ALARM SYSTEM | Water Treatment Building |  | MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | matrix | data_sheet | alarm¦fire¦fire_protection¦wts | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6852 | 0.6722 | 0.4706 | [7 empty] | 0CF5534W38A06 | (DWP BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-08-27 |  | commissioning | query_unknown | fire_fighting¦wts |  | fire_fighting¦wts | query | fire_fighting¦wts | match | true | false | 8 | 1 | 23.4638 | 0.5379 | 0.0311 | 0.0233 | hybrid | structured_no_phase | fire_fighting¦wts | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138001 | P&ID OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | P&ID | Nitrogen System |  | Nitrogen GAS STORAGE SHELTER |  | P&ID for Nitrogen System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6930 | 0.4412 | 0.4412 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 |  | n2 | query | n2 | match | true | false | 1 | 1 | 32.9079 | 0.7801 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | n2 | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138011 | PIPE LAYOUT AND DETAIL OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | PIPE LAYOUT AND DETAIL | Nitrogen System |  | Nitrogen GAS STORAGE SHELTER |  | PIPE LAYOUT AND DETAIL for Nitrogen GAS STORAGE SHELTER |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦gas¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7206 | 0.7762 | 0.5433 | g_safe | [5 empty] | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | true | false | 1 | 5 | 22.7786 | 0.7228 | 0.0318 | 0.0318 | hybrid | structured_preferred | n2 | civil_design | 9 | 2024-07-21 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR N2 GAS STORAGE SHELTER | ARRANGEMENT | Nitrogen System |  | Nitrogen GAS STORAGE SHELTER |  | ARRANGEMENT for Nitrogen System |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | nitrogen |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5036 | 0.3844 | 0.3267 | g_safe | [5 empty] | FA | 1EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 |  | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | true | false | 1 | 11 | 27.4167 | 0.6733 | 0.0305 | 0.0305 | hybrid | structured_cell_found_text_preferred | n2 | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138041 | FIRE ALARM SYSTEM LAYOUT FOR N2 GAS STORAGE SHELTER | Layout Drawing | Nitrogen System | FIRE ALARM SYSTEM | Nitrogen GAS STORAGE SHELTER |  | Layout Drawing for Nitrogen GAS STORAGE SHELTER |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦gas¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6971 | 0.9091 | 0.6364 | g_safe | [5 empty] | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | fire_fighting¦n2 |  | fire_fighting¦n2 | query | n2 | match | true | false | 1 | 2 | 23.2425 | 0.7071 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting¦n2 | civil_design | 10 | 2024-07-21 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR N2 GAS STORAGE SHELTER | Single Line Diagram | Nitrogen System | FIRE ALARM SYSTEM | Nitrogen GAS STORAGE SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | fire_fighting¦n2 |  | fire_fighting¦n2 | query | n2 | match | true | false | 19 | 6 | 23.2425 | 0.6548 | 0.0278 | 0.0278 | hybrid | structured_cell_found_text_preferred | fire_fighting¦n2 | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138101 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | P&ID | Heat Recovery Steam Generator |  |  |  | P&ID for HRSG |  | HRSG - P&ID for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | diagram | diagram | p_id | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.8159 | 0.7698 | 0.7698 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 28.3556 | 0.6896 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hrsg | system_design¦procurement |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138102 | P&ID OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | P&ID | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | P&ID for LUBE OIL SYSTEM |  | GT - LUBE OIL SYSTEM P&I DIAGRAM | 1 | start+86D<=FA<=start+86D+2M | FA ∈ [start+86d, start+146d] | rule_query | diagram | diagram | p_id | p_id | gas¦generator¦gtg¦lube¦oil¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.5000 | 0.7940 | 0.5882 | 0.5882 | [6 empty] | FA | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | 2007-04-02 | 2007-10-31 | system_design | system_design | match | gtg | gtg | gtg | query |  | activity_unscoped | true | true | 142 | 285 | 23.4343 | 0.6064 | 0.0078 | 0.0047 | hybrid | structured_blocked_procurement_conflict | gtg | system_design¦procurement | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | PIPE LAYOUT AND DETAIL | Heat Recovery Steam Generator |  |  |  | PIPE LAYOUT AND DETAIL for HRSG |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7193 | 0.6825 | 0.6825 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 2 | 17.2988 | 0.6350 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138112 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | PIPE LAYOUT AND DETAIL | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6350 | 0.8905 | 0.6233 | g_ambig | generic_ok | 0.84 |  | 1 | This is a water spray piping layout for a transformer, which does not match the GT generator foundation embedded metals layout rule. | FA | 2CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | 2007-10-31 | 2007-12-31 | design_drawing | civil_design | compatible | gtg | fire_fighting | gtg | query | gtg | match | true | false | 6 | 2 | 26.4817 | 0.6311 | 0.0313 | 0.0235 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | Calculation sheet | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7948 | 0.7051 | 0.7051 | [6 empty] | FA | 1EF3520W16A12 | (GPRS) FDN Design for HRSG | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-07-03 | 2007-11-09 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | fgp¦hrsg | match | true | false | 1 | 23 | 14.0070 | 0.5354 | 0.0284 | 0.0284 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138122 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | Calculation sheet | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 1CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2007-10-01 | 2007-11-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 2 | 7 | 26.4817 | 0.6072 | 0.0311 | 0.0311 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-07-03 | 2024-08-02 | 2024-09-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR HRSG | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | hrsg |  | hrsg | query | hrsg | match | true | false | 2 | 1 | 20.8292 | 0.6468 | 0.0325 | 0.0244 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138141 | FIRE ALARM SYSTEM LAYOUT FOR HRSG | Layout Drawing | Heat Recovery Steam Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | design_drawing | system_design | compatible | fire_fighting¦hrsg | hrsg | fire_fighting¦hrsg | query | hrsg | match | true | false | 2 | 1 | 15.2888 | 0.6552 | 0.0325 | 0.0244 | hybrid | structured_preferred | fire_fighting¦hrsg | system_design¦civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR HRSG | Single Line Diagram | Heat Recovery Steam Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | uncertain | 0.50 |  | 3 | The competing HRSG-specific rules are for electrical distribution/CEMS/diverter-damper, and it is unclear if a fire alarm system SLD should follow any of those. | SKIP | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | fire_fighting¦hrsg |  | fire_fighting¦hrsg | query | hrsg | match | true | false | 2 | 2 | 24.4996 | 0.6568 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦hrsg | system_design¦engineering | 8 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138143 | FIRE ALARM SYSTEM LAYOUT FOR GTG LUBE OIL UNIT | Layout Drawing | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | Layout Drawing for GTG | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦gas¦generator¦gtg¦turbine | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6028 | 0.5308 | 0.5308 | [6 empty] | FA | 2CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | 2007-10-31 | 2007-12-31 | design_drawing | civil_design | compatible | gtg | fire_fighting | gtg | query | gtg | match | true | false | 4 | 1 | 26.4817 | 0.6385 | 0.0320 | 0.0240 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138144 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG LUBE OIL UNIT | Single Line Diagram | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | Single Line Diagram for LUBE OIL SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | fire_protection¦gas¦generator¦gtg¦lube¦oil¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7480 | 0.9244 | 0.9244 | g_ambig | use_specific | 0.78 | GT - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | 5 | A generator/medium-voltage SLD aligns directly with the generator circuit single line diagram specific rule. | SKIP | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 9.3722 | 0.5203 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138201 | P&ID OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | P&ID | Blackstart Diesel Generator |  |  |  | P&ID for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | blackstart¦diesel¦generator¦tank |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8628 | 0.8188 | 0.8188 | g_safe | [5 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | bsedg | bsedg | bsedg | query |  | activity_unscoped | true | true | 65 | 11 | 20.0454 | 0.5886 | 0.0221 | 0.0133 | hybrid | structured_blocked_procurement_conflict | bsedg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | PIPE LAYOUT AND DETAIL | Blackstart Diesel Generator |  |  |  | PIPE LAYOUT AND DETAIL for Tank |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6009 | 0.8803 | 0.6162 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | design_drawing | civil_design | compatible | bsedg | fire_fighting | bsedg | query | bsedg | match | true | false | 1 | 2 | 28.8922 | 0.5782 | 0.0325 | 0.0244 | hybrid | structured_preferred | bsedg | system_design¦civil_design | 6 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | Calculation sheet | Blackstart Diesel Generator |  |  |  | Calculation sheet for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | HVAC Calculation | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | calculation | calculation | calculation | calculation | blackstart¦diesel¦generator¦tank |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7813 | 0.7011 | 0.7011 | g_ambig | generic_ok | 0.72 |  | 33 | This is a hydraulic calculation for a water spray system for a diesel oil day tank, not an HVAC calculation nor a tank foundation/strength calculation explicitly covered by the listed specific rules. | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg¦hvac | bsedg | query | bsedg | match | true | false | 1 | 2 | 28.8922 | 0.5706 | 0.0325 | 0.0325 | hybrid | structured_preferred | bsedg | civil_design | 6 | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR BSDG DIESEL OIL DAY TANK | ARRANGEMENT | Blackstart Diesel Generator |  |  |  | ARRANGEMENT for Blackstart Diesel Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | blackstart¦diesel¦generator¦tank |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4421 | 0.3660 | 0.3111 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | design_drawing | civil_design | compatible | bsedg |  | bsedg | query | bsedg | match | true | false | 2 | 1 | 28.8922 | 0.6575 | 0.0325 | 0.0244 | hybrid | structured_preferred | bsedg | system_design¦civil_design | 6 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138241 | FIRE ALARM SYSTEM LAYOUT FOR BSDG DIESEL OIL DAY TANK | Layout Drawing | Blackstart Diesel Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for Tank | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦tank | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6058 | 0.5317 | 0.5317 | [6 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | design_drawing | civil_design | compatible | bsedg¦fire_fighting | fire_fighting | bsedg¦fire_fighting | query | bsedg | match | true | false | 1 | 3 | 28.8922 | 0.5969 | 0.0323 | 0.0242 | hybrid | structured_preferred | bsedg¦fire_fighting | system_design¦civil_design | 10 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR BSDG DIESEL OIL DAY TANK | Single Line Diagram | Blackstart Diesel Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | bsedg¦fire_fighting |  | bsedg¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 26.4345 | 0.4971 | 0.0328 | 0.0328 | hybrid | structured_preferred | bsedg¦fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138301 | P&ID OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | P&ID | GAS COMPRESSOR | Fire Fighting System |  |  | P&ID for Fire Fighting System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6987 | 0.4429 | 0.4429 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 30.9723 | 0.6339 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138311 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | PIPE LAYOUT AND DETAIL | GAS COMPRESSOR | Fire Fighting System |  |  | PIPE LAYOUT AND DETAIL for Fire Fighting System | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fighting¦fire¦fire_protection | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.7555 | 0.6933 | 0.6933 | [6 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 21.2965 | 0.5686 | 0.0325 | 0.0244 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138321 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | Calculation sheet | GAS COMPRESSOR | Fire Fighting System |  |  | Calculation sheet for GAS COMPRESSOR | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | compressor¦fire_protection¦gas |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7077 | 0.6323 | 0.6323 | g_ambig | generic_ok | 0.80 |  | 3 | The competing specific rules are for tank foundations/stormwater/fire fighting building foundations, while the document is a hydraulic calculation for a water spray system for the gas compressor. | FI | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting | compressed_air | fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 15.8388 | 0.5710 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | fi_complete | 0.90 | fc_earliest | false | false | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GPRS AREA | ARRANGEMENT |  |  |  |  | ARRANGEMENT |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement |  |  | generic | match | match | query_unscoped | passed |  | 0.3333 | 0.8688 | 0.4940 | 0.4199 | [6 empty] | FA | 3EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | design_drawing | civil_design | compatible |  |  |  |  | fgp¦gtg¦hrsg | query_unscoped | true | false | 65 | 34 | 9.6939 | 0.5183 | 0.0186 | 0.0105 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | generated | 0.60 |  | false | false | 0.31 | needs_review | default_fc_window;rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138341 | FIRE ALARM SYSTEM LAYOUT FOR GPRS AREA | Layout Drawing |  | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6352 | 0.5405 | 0.5405 | g_ambig | generic_ok | 0.90 |  | 5 | Competing rules are for stormwater/wastewater drainage layouts, not fire alarm system layout drawings. | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 16.7207 | 0.5119 | 0.0323 | 0.0242 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GPRS AREA | Single Line Diagram |  | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 26.4345 | 0.5198 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138401 | P&ID of Standpipe system for H2, CO2 Gas Storage Shelter | P&ID | Hydrogen System |  | Hydrogen, Carbon Dioxide Gas Storage Shelter |  | P&ID for Hydrogen System | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | fire_protection¦hydrogen |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7344 | 0.5703 | 0.5703 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 | h2 | h2 | query | h2 | match | true | false | 1 | 1 | 36.1117 | 0.7222 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | h2 | system_design¦procurement |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138411 | Pipe layout and detail of Standpipe system for H2, CO2 Gas Storage Shelter | Pipe layout and detail | Hydrogen System |  | Hydrogen, Carbon Dioxide Gas Storage Shelter |  | Pipe layout and detail for Hydrogen, Carbon Dioxide Gas Storage Shelter | H2, CO2 Supply System | Panel/shelter/JB outline and layout draWings | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | layout_drawing | layout_drawing | carbon¦dioxide¦fire_protection¦gas¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.5455 | 0.6935 | 0.5899 | 0.5899 | g_ambig | generic_ok | 0.82 |  | 5 | This is standpipe piping layout/detail for an H2/CO2 gas storage shelter, not stormwater/wastewater drainage layouts or calculations. | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | true | false | 1 | 1 | 17.6855 | 0.5245 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR H2, CO2 GAS STORAGE SHELTER | ARRANGEMENT | Hydrogen System |  | Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | ARRANGEMENT for Hydrogen System |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | hydrogen |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5164 | 0.3882 | 0.3300 | g_safe | [5 empty] | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 |  | h2 | query | h2 | match | true | false | 1 | 1 | 17.6855 | 0.4999 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138441 | FIRE ALARM SYSTEM LAYOUT FOR H2, CO2 GAS STORAGE SHELTER | Layout Drawing | Hydrogen System | FIRE ALARM SYSTEM | Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | Layout Drawing for Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | SHELTER LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | carbon¦dioxide¦fire_protection¦gas¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6558 | 0.8967 | 0.6277 | g_safe | [5 empty] | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting¦h2 |  | fire_fighting¦h2 | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 21.2030 | 0.5578 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦h2 | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR H2, CO2 GAS STORAGE SHELTER | Single Line Diagram | Hydrogen System | FIRE ALARM SYSTEM | Hydrogen, Carbon Dioxide GAS STORAGE SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦h2 |  | fire_fighting¦h2 | query | fire_fighting¦hvac | match | true | false | 40 | 8 | 20.6383 | 0.5500 | 0.0247 | 0.0247 | hybrid | structured_cell_found_text_preferred | fire_fighting¦h2 | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138502 | P&ID OF CLEAN AGENT SYSTEM FOR AUX. LEB | P&ID |  | CLEAN AGENT SYSTEM | Local Electrical Building |  | P&ID for CLEAN AGENT SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦electrical¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6797 | 0.4372 | 0.4372 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 66 | 24 | 17.8084 | 0.5901 | 0.0198 | 0.0198 | hybrid | structured_blocked_procurement_conflict | electrical¦fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.52 | needs_review | default_fc_window;rule_score_medium;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138512 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR AUX. LEB | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 10 | 3 | 5.8906 | 0.4871 | 0.0302 | 0.0302 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138522 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR AUX. LEB | Calculation sheet |  | CLEAN AGENT SYSTEM | Local Electrical Building |  | Calculation sheet for CLEAN AGENT SYSTEM |  | AUX. LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦clean¦electrical¦fire_protection¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 0.6479 | 0.8944 | 0.8944 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 5 | 4 | 1.1615 | 0.4402 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AUX. LEB | ARRANGEMENT |  |  | Local Electrical Building |  | ARRANGEMENT for Local Electrical Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦leb¦local |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5301 | 0.3924 | 0.3335 | g_safe | [5 empty] | FA | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | false | 4 | 1 | 7.0774 | 0.4177 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138541 | FIRE ALARM SYSTEM LAYOUT FOR AUX. LEB | Layout Drawing |  | FIRE ALARM SYSTEM | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7161 | 0.5648 | 0.5648 | g_ambig | generic_ok | 0.90 |  | 5 | Competing rules are for stormwater/wastewater drainage layouts, not fire alarm system layout drawings. | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 14.9275 | 0.5149 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AUX. LEB | Single Line Diagram |  | FIRE ALARM SYSTEM | Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 49 | 63 | 14.9275 | 0.4896 | 0.0173 | 0.0173 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138601 | P&ID OF STAND PIPE SYSTEM FOR ST BUILDING | P&ID | Steam Turbine & Generator | STAND PIPE SYSTEM | Steam Turbine Building |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦pipe¦stand¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7537 | 0.4594 | 0.4594 | g_ambig | uncertain |  |  | 1 |  | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query |  | activity_unscoped | true | true | 72 | 75 | 18.0120 | 0.6018 | 0.0150 | 0.0090 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement |  | 2024-04-12 | 2024-06-07 | 2024-08-02 | 2024-06-28 | 2024-08-23 | 2024-10-18 | generated | 0.90 |  | false | false | 0.37 | needs_review | rule_scope_status=rule_generic;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-138602 | P&ID OF SPRINKLER SYSTEM FOR ST BUILDING | P&ID | Steam Turbine & Generator | SPRINKLER SYSTEM | Steam Turbine Building |  | P&ID for SPRINKLER SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦sprinkler¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6783 | 0.4368 | 0.4368 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG instrument air, while the document is for a water spray system P&ID. | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query |  | activity_unscoped | true | true | 38 | 35 | 18.0120 | 0.5883 | 0.0207 | 0.0124 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-138603 | P&ID OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | P&ID | Steam Turbine & Generator | PRE - ACTION SPRINKLER SYSTEM | Steam Turbine Building |  | P&ID for PRE - ACTION SPRINKLER SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | action¦fire_protection¦pre¦sprinkler¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6394 | 0.4251 | 0.4251 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG instrument air, while the document is for a water spray system P&ID. | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦hvac | match | true | false | 50 | 83 | 17.8084 | 0.5685 | 0.0161 | 0.0161 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.52 | needs_review | default_fc_window;rule_score_medium;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138604 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | P&ID | Steam Turbine & Generator | WATER SPRAY SYSTEM | Steam Turbine Building |  | P&ID for WATER SPRAY SYSTEM | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | p_id | p_id | spray¦stg¦water |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5546 | 0.4464 | 0.4464 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG instrument air, while the document is for a water spray system P&ID. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦stg | bsedg | fire_fighting¦stg | query |  | activity_unscoped | true | true | 4 | 92 | 27.6262 | 0.5991 | 0.0222 | 0.0133 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138606 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | P&ID | Steam Turbine & Generator | WATER SPRAY SYSTEM | Steam Turbine Building |  | P&ID for WATER SPRAY SYSTEM | Emergency Diesel Generator/Blackstart Diesel Generator | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | p_id | p_id | spray¦stg¦water |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5327 | 0.4398 | 0.4398 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG instrument air, while the document is for a water spray system P&ID. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦stg | bsedg | fire_fighting¦stg | query |  | activity_unscoped | true | true | 1 | 111 | 27.6262 | 0.6008 | 0.0222 | 0.0133 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138608 | P&ID of Clean agent system for Excitation Panel Room for ST Building | P&ID | Steam Turbine & Generator | Clean agent system | Steam Turbine Building |  | P&ID for Clean agent system |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦fire_protection¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6761 | 0.4362 | 0.4362 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG instrument air, while the document is for a water spray system P&ID. | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query |  | activity_unscoped | true | true | 7 | 63 | 28.9060 | 0.5882 | 0.0231 | 0.0138 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ST BUILDING | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator | STAND PIPE SYSTEM | Steam Turbine Building |  | PIPE LAYOUT AND DETAIL for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6794 | 0.6238 | 0.6238 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | stg | match | true | false | 1 | 5 | 9.9602 | 0.6087 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-138612 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR ST BUILDING | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator | SPRINKLER SYSTEM | Steam Turbine Building |  | PIPE LAYOUT AND DETAIL for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6794 | 0.6238 | 0.6238 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | stg | match | true | false | 1 | 5 | 9.9602 | 0.5768 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-138613 | PIPE LAYOUT AND DETAIL OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator | PRE - ACTION SPRINKLER SYSTEM | Steam Turbine Building |  | PIPE LAYOUT AND DETAIL for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6794 | 0.6238 | 0.6238 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | stg | match | true | false | 4 | 6 | 9.9602 | 0.5634 | 0.0308 | 0.0308 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138614 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator | WATER SPRAY SYSTEM | Steam Turbine Building |  | PIPE LAYOUT AND DETAIL for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6794 | 0.6238 | 0.6238 | [6 empty] | FA | 1EF2030W16A01 | (Lube Oil Sys.) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2007-10-23 | 2008-01-22 | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | stg | match | true | false | 1 | 3 | 16.0926 | 0.6224 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-06-10 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-24 | 2024-09-23 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138616 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator |  | Steam Turbine Building |  | PIPE LAYOUT AND DETAIL for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6794 | 0.6238 | 0.6238 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 4 | 10.7824 | 0.6161 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138618 | Pipe Layout and detail of Clean agent system for Excitation Panel Room for ST Building | Pipe Layout and detail | Steam Turbine & Generator |  | Steam Turbine Building |  | Pipe Layout and detail for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6102 | 0.6030 | 0.6030 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 11 | 9.9602 | 0.5757 | 0.0305 | 0.0305 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-138622 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR ST BUILDING | HYDRAULIC CALCULATION | Steam Turbine & Generator |  | Steam Turbine Building |  | HYDRAULIC CALCULATION for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6460 | 0.6138 | 0.6138 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 2 | 9.9602 | 0.5631 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-138623 | HYDRAULIC CALCULATION OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | HYDRAULIC CALCULATION | Steam Turbine & Generator |  | Steam Turbine Building |  | HYDRAULIC CALCULATION for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6460 | 0.6138 | 0.6138 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 4 | 2 | 9.9602 | 0.5619 | 0.0318 | 0.0318 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138624 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL FOR ST BUILDING | HYDRAULIC CALCULATION | Steam Turbine & Generator |  | Steam Turbine Building |  | HYDRAULIC CALCULATION for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6460 | 0.6138 | 0.6138 | [6 empty] | FI | 1EF2030W16A01 | (Lube Oil Sys.) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2007-10-23 | 2008-01-22 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 3 | 15.5404 | 0.6262 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-07-25 | 2024-08-24 | 2024-09-23 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138626 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | HYDRAULIC CALCULATION | Steam Turbine & Generator |  | Steam Turbine Building |  | HYDRAULIC CALCULATION for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6460 | 0.6138 | 0.6138 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 2 | 10.7824 | 0.5829 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138628 | Flow calculation of Clean Agent system for Excitation Panel Room for ST Building | Flow calculation | Steam Turbine & Generator |  | Steam Turbine Building |  | Flow calculation for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5442 | 0.5833 | 0.5833 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 6 | 9.9602 | 0.5478 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST BUILDING | ARRANGEMENT | Steam Turbine & Generator |  | Steam Turbine Building |  | ARRANGEMENT for STG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6752 | 0.4359 | 0.3705 | g_safe | [5 empty] | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 3 | 1 | 16.6699 | 0.5997 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-31 | 2024-04-15 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | generated | 0.60 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138641 | FIRE ALARM SYSTEM LAYOUT FOR ST BUILDING | Layout Drawing | Steam Turbine & Generator | FIRE ALARM SYSTEM | Steam Turbine Building |  | Layout Drawing for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6641 | 0.6192 | 0.6192 | [6 empty] | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | fire_fighting¦hvac | match | true | false | 4 | 11 | 18.4555 | 0.5613 | 0.0297 | 0.0297 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST BUILDING | Single Line Diagram | Steam Turbine & Generator | FIRE ALARM SYSTEM | Steam Turbine Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query | stg | match | true | false | 687 | 17 | 9.1673 | 0.5717 | 0.0143 | 0.0143 | hybrid | structured_cell_found_text_preferred | fire_fighting¦stg | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST BUILDING | BATTERY CALCULATION | Steam Turbine & Generator | FIRE ALARM SYSTEM | Steam Turbine Building |  | BATTERY CALCULATION for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.5534 | 0.5860 | 0.5860 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting¦stg | stg | fire_fighting¦stg | query | fire_fighting¦hvac | match | true | false | 4 | 5 | 18.4555 | 0.5074 | 0.0310 | 0.0310 | hybrid | structured_preferred | fire_fighting¦stg | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST BUILDING | CAUSE & EFFECT MATRIX | Steam Turbine & Generator | FIRE ALARM SYSTEM | Steam Turbine Building |  | CAUSE & EFFECT MATRIX for STG | [5 empty] | rule_query | other | other | cause_and_effect_matrix | hrsg_bms_cause_and_effect_chart | fire_protection¦generator¦steam¦stg¦turbine | hrsg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.3333 | 0.5860 | 0.4091 | 0.4091 | [7 empty] | 1CF2010W38A09 | (STG #10 BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-11-01 | 2008-12-27 |  | commissioning | query_unknown | fire_fighting¦stg |  | fire_fighting¦stg | query | fire_fighting¦stg | match | true | false | 8 | 1 | 19.3508 | 0.5982 | 0.0311 | 0.0233 | hybrid | structured_no_phase | fire_fighting¦stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138702 | P&ID OF CLEAN AGENT SYSTEM FOR ST#1 LEB | P&ID |  | CLEAN AGENT SYSTEM | Local Electrical Building |  | P&ID for CLEAN AGENT SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦electrical¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6797 | 0.4372 | 0.4372 | g_ambig | uncertain |  |  | 1 |  | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query |  | activity_unscoped | true | true | 7 | 1 | 30.6317 | 0.6513 | 0.0313 | 0.0188 | hybrid | structured_blocked_procurement_conflict | electrical¦fire_fighting | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138712 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#1 LEB | PIPE LAYOUT AND DETAIL |  |  | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_safe | [5 empty] | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting¦stg |  | electrical¦fire_fighting¦stg | query | fire_fighting¦hvac | match | true | false | 12 | 3 | 6.1832 | 0.5078 | 0.0298 | 0.0298 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138722 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#1 LEB | FLOW CALCULATION |  |  | Local Electrical Building |  | FLOW CALCULATION for Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7653 | 0.7546 | 0.7546 | g_ambig | uncertain |  |  | 15 |  | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦fire_fighting¦stg | electrical | electrical¦fire_fighting¦stg | query | stg | match | true | false | 1 | 26 | 5.7347 | 0.3851 | 0.0280 | 0.0280 | hybrid | structured_preferred | electrical¦fire_fighting¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#1 LEB | ARRANGEMENT |  |  | Local Electrical Building |  | ARRANGEMENT for Local Electrical Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦leb¦local¦stg |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5301 | 0.3924 | 0.3335 | g_safe | [5 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | gsut_uat¦stg | match | true | false | 6 | 12 | 8.0965 | 0.3766 | 0.0290 | 0.0290 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138741 | FIRE ALARM SYSTEM LAYOUT FOR ST#1 LEB | Layout Drawing |  | FIRE ALARM SYSTEM | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7161 | 0.5648 | 0.5648 | g_ambig | uncertain |  |  | 6 |  | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 16.1829 | 0.5157 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#1 LEB | Single Line Diagram |  | FIRE ALARM SYSTEM | Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 42 | 61 | 15.8470 | 0.4897 | 0.0181 | 0.0181 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#1 LEB | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | Local Electrical Building |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦electrical¦fire¦fire_protection¦leb¦local¦stg | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6377 | 0.6377 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 15.8470 | 0.4415 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#1 LEB | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | Local Electrical Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦electrical¦fire¦fire_protection¦leb¦local¦stg | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 | [7 empty] | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2008-11-01 | 2008-12-15 |  | commissioning | query_unknown | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hrsg | match | true | false | 16 | 5 | 15.1475 | 0.5126 | 0.0285 | 0.0214 | hybrid | structured_no_phase | electrical¦fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138802 | P&ID OF CLEAN AGENT SYSTEM FOR ST#2 LEB | P&ID |  | CLEAN AGENT SYSTEM | Local Electrical Building |  | P&ID for CLEAN AGENT SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦electrical¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6797 | 0.4372 | 0.4372 | g_ambig | uncertain |  |  | 1 |  | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query |  | activity_unscoped | true | true | 8 | 1 | 28.9060 | 0.6521 | 0.0311 | 0.0187 | hybrid | structured_blocked_procurement_conflict | electrical¦fire_fighting | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138812 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#2 LEB | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | Local Electrical Building |  | PIPE LAYOUT AND DETAIL for Local Electrical Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7896 | 0.7969 | 0.5578 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 10 | 5 | 5.8906 | 0.4826 | 0.0297 | 0.0297 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138822 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#2 LEB | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | Local Electrical Building |  | FLOW CALCULATION for CLEAN AGENT SYSTEM |  | ST #2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦clean¦electrical¦fire_protection¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.5975 | 0.8793 | 0.8793 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting | stg | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 27 | 4 | 1.1615 | 0.4357 | 0.0271 | 0.0271 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#2 LEB | ARRANGEMENT |  |  | Local Electrical Building |  | ARRANGEMENT for Local Electrical Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | electrical¦leb¦local¦stg |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5301 | 0.3924 | 0.3335 | g_safe | [5 empty] | FA | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | gsut_uat¦stg | match | true | false | 6 | 7 | 8.6080 | 0.3967 | 0.0301 | 0.0301 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138841 | FIRE ALARM SYSTEM LAYOUT FOR ST#2 LEB | Layout Drawing |  | FIRE ALARM SYSTEM | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7161 | 0.5648 | 0.5648 | g_ambig | uncertain |  |  | 6 |  | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 14.9275 | 0.5193 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#2 LEB | Single Line Diagram |  | FIRE ALARM SYSTEM | Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦electrical¦fire¦fire_protection¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 54 | 78 | 14.9275 | 0.4881 | 0.0160 | 0.0160 | hybrid | structured_cell_found_text_preferred | electrical¦fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#2 LEB | Calculation sheet |  | FIRE ALARM SYSTEM | Local Electrical Building |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦electrical¦fire¦fire_protection¦leb¦local¦stg | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.6591 | 0.6644 | 0.6644 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 7 | 1 | 14.6503 | 0.4818 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#2 LEB | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | Local Electrical Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦electrical¦fire¦fire_protection¦leb¦local¦stg | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 | [7 empty] | 2CF1600W38A13 | (HRSG #21 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2008-11-01 | 2008-12-15 |  | commissioning | query_unknown | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hrsg | match | true | false | 8 | 2 | 15.4601 | 0.5336 | 0.0308 | 0.0231 | hybrid | structured_no_phase | electrical¦fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138901 | P&ID OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | P&ID |  | STAND PIPE SYSTEM |  |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7537 | 0.4594 | 0.4594 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 17.8084 | 0.5819 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138902 | P&ID OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | P&ID |  | WATER SPRAY SYSTEM |  |  | P&ID for WATER SPRAY SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | spray¦water |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6624 | 0.4320 | 0.4320 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 17.8084 | 0.5821 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM |  |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8189 | 0.8057 | 0.5640 | g_safe | [5 empty] | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 4 | 10.2173 | 0.4581 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138912 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | PIPE LAYOUT AND DETAIL |  | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for WATER SPRAY SYSTEM |  | Water Spray Layout | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | spray¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7060 | 0.9118 | 0.6383 | g_safe | [5 empty] | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 13.8506 | 0.4843 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138922 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | Calculation sheet |  | WATER SPRAY SYSTEM |  |  | Calculation sheet for WATER SPRAY SYSTEM |  | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | spray¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7476 | 0.7843 | 0.7843 | g_safe | [5 empty] | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 9.1931 | 0.4942 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | fi_complete | 0.90 | fc_earliest | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR DEAERATOR SUPPORT STRUCTURE | ARRANGEMENT |  |  |  |  | ARRANGEMENT |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement |  |  | generic | match | match | query_unscoped | passed |  | 0.3333 | 0.8688 | 0.4940 | 0.4199 | [6 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 34 | 756 | 10.9575 | 0.4533 | 0.0119 | 0.0089 | hybrid | structured_no_system |  | civil_design |  | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.60 |  | false | false | 0.42 | needs_review | default_fc_window;rule_scope_status=query_unscoped;rule_score_medium;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138941 | FIRE ALARM SYSTEM LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | Layout Drawing |  | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6352 | 0.5405 | 0.5405 | g_ambig | generic_ok | 0.90 |  | 5 | Competing rules are for stormwater/wastewater drainage layouts, not fire alarm system layout drawings. | SKIP | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 5 | 19.3818 | 0.5457 | 0.0318 | 0.0318 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | Single Line Diagram |  | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 21 | 91 | 19.3818 | 0.4913 | 0.0190 | 0.0190 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139001 | P&ID OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | P&ID |  | STAND PIPE SYSTEM | Administration & Social Building |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7537 | 0.4594 | 0.4594 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 17.8084 | 0.5946 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139002 | P&ID of Clean Agent system for Administration & Social Building | P&ID |  | Clean Agent system | Administration & Social Building |  | P&ID for Clean Agent system |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6764 | 0.4363 | 0.4363 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 66 | 4 | 17.8084 | 0.6083 | 0.0236 | 0.0236 | hybrid | structured_blocked_procurement_conflict | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139011 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | Administration & Social Building |  | PIPE LAYOUT AND DETAIL for Administration & Social Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | administration¦fire_protection¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7735 | 0.7920 | 0.5544 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 9.8406 | 0.5192 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139012 | Pipe Layout and detail of Clean Agent system for Administration & Social Building | Pipe Layout and detail |  | Clean Agent system | Administration & Social Building |  | Pipe Layout and detail for Administration & Social Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | administration¦fire_protection¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6961 | 0.7688 | 0.5382 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 4 | 9.8406 | 0.5431 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139023 | Flow calculation of Clean Agent system for Administration & Social Building | Flow calculation |  | Fire Fighting System | Administration & Social Building |  | Flow calculation for Fire Fighting System | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fighting¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.6348 | 0.6571 | 0.6571 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 18.8774 | 0.5889 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ADMINISTRATION & SOCIAL BUILDING | ARRANGEMENT |  |  | Administration & Social Building |  | ARRANGEMENT for Administration & Social Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | administration¦social |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5594 | 0.4012 | 0.3410 | g_safe | [5 empty] | FA | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1 | 42 | 22.7898 | 0.4916 | 0.0262 | 0.0157 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139041 | FIRE ALARM SYSTEM LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | Administration & Social Building |  | Layout Drawing for Administration & Social Building | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦fire_protection¦social | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.5763 | 0.5229 | 0.5229 | [6 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 18.8774 | 0.5676 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | Administration & Social Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 25 | 14 | 18.8774 | 0.5183 | 0.0253 | 0.0253 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139043 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | Administration & Social Building |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6377 | 0.6377 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 18.8774 | 0.4671 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139044 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | Administration & Social Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦fire¦fire_protection | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 | [7 empty] | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting | match | true | false | 7 | 1 | 25.5441 | 0.5662 | 0.0313 | 0.0235 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139101 | P&ID OF STAND PIPE SYSTEM FOR SECURITY BUILDING | P&ID |  | STAND PIPE SYSTEM | Security Building |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7537 | 0.4594 | 0.4594 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 17.8084 | 0.6158 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139103 | P&ID OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | P&ID |  | Fire Fighting System | Security Building |  | P&ID for Fire Fighting System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6987 | 0.4429 | 0.4429 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 7 | 1 | 30.9723 | 0.7031 | 0.0313 | 0.0313 | hybrid | structured_blocked_procurement_conflict | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139111 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR SECURITY BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | Security Building |  | PIPE LAYOUT AND DETAIL for Security Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦security |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7834 | 0.7950 | 0.5565 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 9.8406 | 0.5102 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139113 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | PIPE LAYOUT AND DETAIL |  | Fire Fighting System | Security Building |  | PIPE LAYOUT AND DETAIL for Security Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦security |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7834 | 0.7950 | 0.5565 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 23.6065 | 0.6112 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139123 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | FLOW CALCULATION |  | Fire Fighting System | Security Building |  | FLOW CALCULATION for Fire Fighting System | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fighting¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.6807 | 0.6709 | 0.6709 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 18.8774 | 0.5868 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SECURITY BUILDING | ARRANGEMENT |  |  | Security Building |  | ARRANGEMENT for Security Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | security |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5787 | 0.4070 | 0.3459 | g_safe | [5 empty] | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | false | 28 | 211 | 10.9843 | 0.4621 | 0.0151 | 0.0113 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139141 | FIRE ALARM SYSTEM LAYOUT FOR SECURITY BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | Security Building |  | Layout Drawing for Security Building | Substation | Security Configuration & Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦security |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6443 | 0.6133 | 0.6133 | g_ambig | uncertain |  |  | 5 |  | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 18.8774 | 0.5558 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | Security Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 24 | 12 | 18.8774 | 0.5239 | 0.0258 | 0.0258 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139143 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | Security Building |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6377 | 0.6377 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 18.8774 | 0.4743 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139144 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | Security Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦fire¦fire_protection | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 | [7 empty] | 0CF4500W90A09 | (Fire Fighting BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-02-02 | 2008-03-31 |  | commissioning | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 14 | 2 | 18.7344 | 0.4737 | 0.0296 | 0.0222 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR MAIN GATE HOUSE | ARRANGEMENT |  |  | Security Building |  | ARRANGEMENT for Security Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | security |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5787 | 0.4070 | 0.3459 | g_safe | [5 empty] | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 13 | 17.1992 | 0.5104 | 0.0298 | 0.0179 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139241 | FIRE ALARM SYSTEM LAYOUT FOR MAIN GATE HOUSE | Layout Drawing |  | FIRE ALARM SYSTEM | Security Building |  | Layout Drawing for Security Building | Substation | Security Configuration & Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦security |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6443 | 0.6133 | 0.6133 | g_ambig | uncertain |  |  | 5 |  | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 14.9275 | 0.5129 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR MAIN GATE HOUSE | Single Line Diagram |  | FIRE ALARM SYSTEM | Security Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 77 | 25 | 14.6503 | 0.4895 | 0.0191 | 0.0191 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139301 | P&ID OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | P&ID |  | STAND PIPE SYSTEM | X-RAY SEARCHING ROOM |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7537 | 0.4594 | 0.4594 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 17.8084 | 0.5701 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | PIPE LAYOUT AND DETAIL |  | Fire Fighting System | X-RAY SEARCHING ROOM |  | PIPE LAYOUT AND DETAIL for X-RAY SEARCHING ROOM |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7071 | 0.7721 | 0.5405 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 21.2965 | 0.5429 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR X-RAY SEARCHING ROOM | ARRANGEMENT |  |  | X-RAY SEARCHING ROOM |  | ARRANGEMENT for X-RAY SEARCHING ROOM |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | ray¦room¦searching |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4991 | 0.3831 | 0.3256 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 18 | 702 | 10.9575 | 0.3812 | 0.0141 | 0.0079 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139341 | FIRE ALARM SYSTEM LAYOUT FOR X-RAY SEARCHING ROOM | Layout Drawing |  | FIRE ALARM SYSTEM | X-RAY SEARCHING ROOM |  | Layout Drawing for X-RAY SEARCHING ROOM | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5456 | 0.5137 | 0.5137 | g_ambig | uncertain |  |  | 5 |  | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 16.7207 | 0.5020 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR X-RAY SEARCHING ROOM | Single Line Diagram |  | FIRE ALARM SYSTEM | X-RAY SEARCHING ROOM |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 26.4345 | 0.5130 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design¦engineering | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139401 | P&ID OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | P&ID |  | Fire Fighting System | FIRE BRIGADE BUILDING |  | P&ID for Fire Fighting System | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | title | diagram | diagram | p_id | p_id | fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7652 | 0.4629 | 0.4629 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 37.5543 | 0.7041 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139411 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | PIPE LAYOUT AND DETAIL |  | Fire Fighting System | FIRE BRIGADE BUILDING |  | PIPE LAYOUT AND DETAIL for FIRE BRIGADE BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7945 | 0.7984 | 0.5588 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 30.4895 | 0.6302 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE BRIGADE BUILDING | ARRANGEMENT |  |  | FIRE BRIGADE BUILDING |  | ARRANGEMENT for FIRE BRIGADE BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | brigade¦fire¦fire_protection |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4760 | 0.3761 | 0.3197 | g_safe | [5 empty] | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 1 | 46 | 17.7462 | 0.4977 | 0.0258 | 0.0194 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139441 | FIRE ALARM SYSTEM LAYOUT FOR FIRE BRIGADE BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | Layout Drawing for FIRE BRIGADE BUILDING | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire¦fire_protection | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6847 | 0.5554 | 0.5554 | [6 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 25.7604 | 0.6228 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 17 | 8 | 25.7604 | 0.5515 | 0.0277 | 0.0277 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139443 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6377 | 0.6377 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 25.7604 | 0.5023 | 0.0325 | 0.0325 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139444 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | cause_and_effect_matrix | data_sheet | alarm¦fire¦fire_protection | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6150 | 0.6512 | 0.4558 | [7 empty] | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 9 | 3 | 25.7604 | 0.5092 | 0.0304 | 0.0228 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139501 | P&ID OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | P&ID |  | Fire Fighting System | Workshop & Storage Building |  | P&ID for Fire Fighting System | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | title | diagram | diagram | p_id | p_id | fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7063 | 0.4452 | 0.4452 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 30.9723 | 0.7037 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-139502 | P&ID OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | P&ID |  | Fire Fighting System | Workshop & Storage Building |  | P&ID for Fire Fighting System |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6987 | 0.4429 | 0.4429 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 30.9723 | 0.6916 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139511 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | PIPE LAYOUT AND DETAIL |  | Fire Fighting System | Workshop & Storage Building |  | PIPE LAYOUT AND DETAIL for Workshop & Storage Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7717 | 0.7915 | 0.5541 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 23.6065 | 0.6007 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-139512 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | PIPE LAYOUT AND DETAIL |  | Fire Fighting System | Workshop & Storage Building |  | PIPE LAYOUT AND DETAIL for Workshop & Storage Building |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7717 | 0.7915 | 0.5541 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 23.6065 | 0.5938 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-139522 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | Calculation sheet |  | Fire Fighting System | Workshop & Storage Building |  | Calculation sheet for Fire Fighting System | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fighting¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.6973 | 0.6758 | 0.6758 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 5 | 3 | 18.8774 | 0.5971 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WORKSHOP & STORAGE BUILDING | ARRANGEMENT |  |  | Workshop & Storage Building |  | ARRANGEMENT for Workshop & Storage Building |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | storage¦workshop |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4939 | 0.3815 | 0.3243 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 3 | 120 | 16.9855 | 0.4881 | 0.0214 | 0.0161 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139541 | FIRE ALARM SYSTEM LAYOUT FOR MAINTENANCE AND WORKSHOP & STORAGE BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | Workshop & Storage Building |  | Layout Drawing for Workshop & Storage Building | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦storage¦workshop | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6134 | 0.5340 | 0.5340 | [6 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 21.2420 | 0.5674 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | Workshop & Storage Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 28 | 11 | 18.8774 | 0.5390 | 0.0254 | 0.0254 | hybrid | structured_cell_found_text_preferred | fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139543 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | Workshop & Storage Building |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | alarm¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6377 | 0.6377 | [6 empty] | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 18.4555 | 0.4715 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139544 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | MATRIX |  | FIRE ALARM SYSTEM | Workshop & Storage Building |  | MATRIX for FIRE ALARM SYSTEM | [5 empty] | rule_query | other | datasheet | matrix | data_sheet | alarm¦fire¦fire_protection | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.6852 | 0.6722 | 0.4706 | [7 empty] | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 |  | civil_design | query_unknown | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 13 | 4 | 18.8774 | 0.5067 | 0.0293 | 0.0220 | hybrid | structured_no_phase | fire_fighting | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139601 | P&ID OF STAND PIPE SYSTEM FOR CPP BUILDING | P&ID |  | STAND PIPE SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | P&ID for STAND PIPE SYSTEM | FireFighting | Pipe and Instrument Diagrams (P&ID) | 1 | start+4W<=FA<=FC<=start+20W | FA ∈ [start+28d, start+140d] ¦ FC ∈ [start+28d, start+140d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦pipe¦stand |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7537 | 0.4594 | 0.4594 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 17.8084 | 0.6051 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate¦fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-06-22 | 2024-08-17 | 2024-07-13 | 2024-09-07 | 2024-11-02 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139602 | P&ID OF CLEAN AGENT SYSTEM FOR CPP BUILDING | P&ID |  | CLEAN AGENT SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | P&ID for CLEAN AGENT SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | agent¦clean¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6797 | 0.4372 | 0.4372 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 66 | 12 | 17.8084 | 0.6118 | 0.0218 | 0.0218 | hybrid | structured_blocked_procurement_conflict | condensate¦fire_fighting | system_design¦procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-139603 | P&ID OF SPRINKLER SYSTEM FOR CPP BUILDING | P&ID |  | SPRINKLER SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | P&ID for SPRINKLER SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | fire_protection¦sprinkler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6783 | 0.4368 | 0.4368 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 17.8084 | 0.6108 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fire_fighting | system_design¦procurement | 10 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL for CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦fire_protection¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7648 | 0.7894 | 0.5526 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 4 | 9.8406 | 0.4948 | 0.0320 | 0.0320 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139612 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL for CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦fire_protection¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7648 | 0.7894 | 0.5526 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 4 | 9.8406 | 0.5173 | 0.0320 | 0.0320 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-139613 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL for CONDENSATE POLISING PLANT BUILDING |  | PIPE LAYOUT AND DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦fire_protection¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7648 | 0.7894 | 0.5526 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 9.8406 | 0.4861 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139622 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CPP BUILDING | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | agent¦clean¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5477 | 0.6310 | 0.6310 | g_ambig | uncertain |  |  | 3 |  | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 5.1115 | 0.4973 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-139623 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CPP BUILDING | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | fire_protection¦sprinkler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5603 | 0.6348 | 0.6348 | g_ambig | uncertain |  |  | 3 |  | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 5.1115 | 0.4995 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CPP BUILDING | ARRANGEMENT |  |  | CONDENSATE POLISING PLANT BUILDING |  | ARRANGEMENT for CONDENSATE POLISING PLANT BUILDING |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | condensate¦plant¦polising |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4115 | 0.3568 | 0.3033 | g_safe | [5 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | false | 6 | 2 |  | 0.3836 | 0.0313 | 0.0313 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139641 | FIRE ALARM SYSTEM LAYOUT FOR CPP BUILDING | Layout Drawing |  | FIRE ALARM SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | Layout Drawing for CONDENSATE POLISING PLANT BUILDING | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦fire_protection¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6079 | 0.5324 | 0.5324 | g_ambig | generic_ok | 0.90 |  | 5 | Competing rules are for stormwater/wastewater drainage layouts, not fire alarm system layout drawings. | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 18.8774 | 0.5368 | 0.0325 | 0.0325 | hybrid | structured_preferred | condensate¦fire_fighting | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CPP BUILDING | Single Line Diagram |  | FIRE ALARM SYSTEM | CONDENSATE POLISING PLANT BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | condensate¦fire_fighting |  | condensate¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 24 | 17 | 18.8774 | 0.5076 | 0.0249 | 0.0249 | hybrid | structured_cell_found_text_preferred | condensate¦fire_fighting | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | ARRANGEMENT | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | ARRANGEMENT for Steam Turbine Generator & Heat Recovery Steam Generator |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine¦wts |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4061 | 0.3552 | 0.3019 | g_safe | [5 empty] | FA | 3EF1600W00A01.1 | (HRSG #32 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg¦stg¦wts |  | hrsg¦stg¦wts | query | hrsg | match | true | false | 10 | 25 | 23.0097 | 0.5839 | 0.0261 | 0.0261 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139741 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | Layout Drawing | Steam Turbine Generator & Heat Recovery Steam Generator | FIRE ALARM SYSTEM | Chemical Dosing Shelter |  | Layout Drawing for Chemical Dosing Shelter |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦fire_protection¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.5845 | 0.6420 | 0.6420 | [6 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦stg¦wts | hrsg | fire_fighting¦hrsg¦stg¦wts | query | gsut_uat¦stg | match | true | false | 14 | 6 | 17.5443 | 0.6111 | 0.0287 | 0.0287 | hybrid | structured_preferred | fire_fighting¦hrsg¦stg¦wts | civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | Single Line Diagram | Steam Turbine Generator & Heat Recovery Steam Generator | FIRE ALARM SYSTEM | Chemical Dosing Shelter |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦generator¦heat¦hrsg¦recovery¦steam¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | uncertain |  |  | 3 |  | SKIP | 1EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦stg¦wts |  | fire_fighting¦hrsg¦stg¦wts | query | fgp¦gtg¦hrsg | match | true | false | 948 | 5 | 14.1240 | 0.6223 | 0.0164 | 0.0164 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hrsg¦stg¦wts | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR HRSG | ARRANGEMENT | Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam¦wts |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 3EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | civil_design | civil_design | match | hrsg¦wts |  | hrsg¦wts | query | fgp¦gtg¦hrsg | match | true | false | 36 | 4 | 17.5307 | 0.6109 | 0.0260 | 0.0260 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139841 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | Layout Drawing | Heat Recovery Steam Generator | FIRE ALARM SYSTEM | Chemical Dosing Shelter |  | Layout Drawing for Chemical Dosing Shelter |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦fire_protection¦generator¦heat¦hrsg¦recovery¦shelter¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.5943 | 0.6450 | 0.6450 | [6 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦wts | hrsg | fire_fighting¦hrsg¦wts | query | fire_fighting¦hvac | match | true | false | 4 | 13 | 20.0824 | 0.5934 | 0.0293 | 0.0293 | hybrid | structured_preferred | fire_fighting¦hrsg¦wts | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR HRSG | Single Line Diagram | Heat Recovery Steam Generator | FIRE ALARM SYSTEM | Chemical Dosing Shelter |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_ambig | uncertain | 0.50 |  | 3 | The competing HRSG-specific rules are for electrical distribution/CEMS/diverter-damper, and it is unclear if a fire alarm system SLD should follow any of those. | SKIP | 1EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | civil_design | civil_design | match | fire_fighting¦hrsg¦wts |  | fire_fighting¦hrsg¦wts | query | fgp¦gtg¦hrsg | match | true | false | 963 | 5 | 11.6234 | 0.5962 | 0.0164 | 0.0164 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hrsg¦wts | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-139901 | P&ID OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | P&ID | Steam Turbine & Generator | WATER SPRAY SYSTEM |  |  | P&ID for WATER SPRAY SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | generator¦spray¦steam¦stg¦turbine¦water |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6624 | 0.4320 | 0.4320 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG instrument air, while the document is for a water spray system P&ID. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | fire_fighting¦stg |  | fire_fighting¦stg | query |  | activity_unscoped | true | true | 1 | 125 | 27.6262 | 0.5882 | 0.0218 | 0.0131 | hybrid | structured_blocked_procurement_conflict | fire_fighting¦stg | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-139911 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7359 | 0.7808 | 0.7808 | [6 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | fire_fighting¦stg | stg | fire_fighting¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 13 | 1 | 13.4368 | 0.5863 | 0.0301 | 0.0226 | hybrid | structured_preferred | fire_fighting¦stg | system_design¦civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-139921 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | HYDRAULIC CALCULATION | Steam Turbine Generator EXCITATION TRANSFORMER | WATER SPRAY SYSTEM |  |  | HYDRAULIC CALCULATION for Steam Turbine Generator EXCITATION TRANSFORMER |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | excitation¦generator¦steam¦stg¦transformer¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.4301 | 0.5490 | 0.5490 | [6 empty] | FI | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 13 | 1 | 19.3427 | 0.5601 | 0.0301 | 0.0301 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | civil_design | 10 |  |  |  | 2024-11-08 | 2024-12-08 | 2025-01-07 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG EXCITATION TRANSFORMER | ARRANGEMENT | Steam Turbine Generator EXCITATION TRANSFORMER |  |  |  | ARRANGEMENT for Steam Turbine Generator EXCITATION TRANSFORMER |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | excitation¦generator¦steam¦stg¦transformer¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.4363 | 0.3642 | 0.3096 | g_safe | [5 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | gsut_uat¦stg |  | gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 16 | 1 | 18.4148 | 0.6345 | 0.0296 | 0.0222 | hybrid | structured_preferred | gsut_uat¦stg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139941 | FIRE ALARM SYSTEM LAYOUT FOR STG EXCITATION TRANSFORMER | Layout Drawing | Steam Turbine Generator EXCITATION TRANSFORMER | FIRE ALARM SYSTEM |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | [6 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | fire_fighting¦gsut_uat¦stg | stg | fire_fighting¦gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 13 | 1 | 19.3427 | 0.6483 | 0.0301 | 0.0226 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG EXCITATION TRANSFORMER | Single Line Diagram | Steam Turbine Generator EXCITATION TRANSFORMER | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | alarm¦fire¦fire_protection¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7291 | 0.9187 | 0.9187 | g_safe | [5 empty] | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | fire_fighting¦gsut_uat¦stg |  | fire_fighting¦gsut_uat¦stg | query | stg | match | true | false | 3 | 1 | 5.6714 | 0.5167 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting¦gsut_uat¦stg | system_design¦engineering | 5 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-140001 | PIPING MATERIAL SPECIFICATION | Technical Specification |  | PIPING |  |  | Technical Specification for PIPING |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | specification | specification | technical_specification | technical_specification | piping |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.5672 | 0.6368 | 0.4458 | g_safe | [5 empty] | FA | 0EF6020W58A01 | (Piping) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | true | false | 2 | 4 | 23.3500 | 0.6855 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-140002 | PIPING INSULATION SPECIFICATION | Technical Specification |  | PIPING |  |  | Insulation Specification for PIPING |  | Piping Insulation Specification | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | insulation_specification | insulation_specification | piping |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9448 | 0.9834 | 0.6884 | g_safe | [5 empty] | FA | 0EF6020W58A10 | (Piping Insulation) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | true | false | 2 | 2 | 24.4809 | 0.6648 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-03-17 | 2024-04-01 | 2024-04-16 | 2024-05-01 | 2024-05-31 | 2024-06-30 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0ZEN-140003 | MANUAL VALVE LIST | LIST |  |  |  |  | Valve List |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.7667 | [6 empty] | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | manual | procurement | match |  |  |  |  | bop | query_unscoped | true | false | 1 | 1 | 30.3466 | 0.7074 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | delivery¦procurement¦installation |  | 2024-12-17 | 2025-01-16 | 2025-02-15 | 2025-03-02 | 2025-03-17 | 2025-04-01 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140004 | PIPING SPECIALTY LIST | LIST |  | PIPING |  |  | LIST for PIPING | [5 empty] | rule_query | other | other | list | st_line_list_for_stg_piping | piping | st¦stg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.5000 | 0.7375 | 0.5713 | 0.5713 | [7 empty] | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | true | false | 1 | 4 | 32.0146 | 0.5642 | 0.0320 | 0.0180 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140005 | PIPING LINE LIST | LIST |  | PIPING |  |  | LIST for PIPING | [5 empty] | rule_query | other | other | list | st_line_list_for_stg_piping | piping | st¦stg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.5000 | 0.7375 | 0.5713 | 0.5713 | [7 empty] | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | true | false | 1 | 10 | 32.0146 | 0.4955 | 0.0307 | 0.0173 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140006 | PIPING TERMINAL POINT LIST BETWEEN FCHPP AND FGP | LIST | Fuel Conditioning & Heating Preparation Package AND Fuel Gas Package | PIPING |  |  | LIST for Fuel Conditioning & Heating Preparation Package AND Fuel Gas Package | [5 empty] | rule_query | other | list | list | instrument_list | conditioning¦fgp¦fuel¦gas¦heating¦preparation | fgp | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6000 | 0.6828 | 0.6249 | 0.6249 | [7 empty] | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | procurement | procurement | match | fgp¦hvac |  | fgp¦hvac | query | fgp | match | true | false | 4 | 4 | 13.9919 | 0.5953 | 0.0312 | 0.0312 | hybrid | structured_preferred | fgp¦hvac | procurement | 10 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBA-140011 | STRESS ANALYSIS REPORT FOR HP STEAM SYSTEM | REPORT |  | HIGH PRESSURE STEAM SYSTEM |  |  | REPORT for HIGH PRESSURE STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7451 | 0.9235 | 0.6465 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.5690 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBC-140012 | STRESS ANALYSIS REPORT FOR IP STEAM SYSTEM | REPORT |  | Intermediate Pressure STEAM SYSTEM |  |  | REPORT for Intermediate Pressure STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7482 | 0.9245 | 0.6471 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.5962 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBS-140013 | STRESS ANALYSIS REPORT FOR PROCESS STEAM SYSTEM | REPORT |  | PROCESS STEAM SYSTEM |  |  | REPORT for PROCESS STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7683 | 0.9305 | 0.6513 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.6095 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LAB-140014 | STRESS ANALYSIS REPORT FOR FEED WATER SYSTEM | REPORT |  | FEED WATER SYSTEM |  |  | REPORT for FEED WATER SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | feed¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7648 | 0.9295 | 0.6506 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 1 | 1 | 21.6028 | 0.6223 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design | 1 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0EKG-140015 | STRESS ANALYSIS REPORT FOR FUEL SYSTEM | REPORT |  | FUEL SYSTEM |  |  | REPORT for FUEL SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | fuel |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7684 | 0.9305 | 0.6514 | g_safe | [5 empty] | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 135 | 212 | 7.7981 | 0.4650 | 0.0088 | 0.0066 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBG-140016 | STRESS ANALYSIS REPORT FOR LP STEAM SYSTEM | REPORT |  | LOW PRESSURE STEAM SYSTEM |  |  | REPORT for LOW PRESSURE STEAM SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7422 | 0.9227 | 0.6459 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.5688 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LCA-140017 | STRESS ANALYSIS REPORT FOR CONDENSATE SYSTEM | REPORT |  | CONDENSATE SYSTEM |  |  | REPORT for CONDENSATE SYSTEM |  | Stress Analysis Report | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | report | report | condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7640 | 0.9292 | 0.6504 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 13.4774 | 0.5982 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140020 | KEY PLAN DRAWING | PLAN DRAWING |  |  |  |  | PLAN DRAWING |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6060 | 0.6485 | 0.6485 | [6 empty] | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 327 | 24.0608 | 0.4477 | 0.0187 | 0.0084 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140021 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 GROUND FLOOR | General Arrangement Drawing | Steam Turbine & Generator | PIPING | Steam Turbine Building |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 20.1363 | 0.6751 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140022 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 OPERATING FLOOR | General Arrangement Drawing | Steam Turbine & Generator | PIPING | Steam Turbine Building |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 20.1363 | 0.6712 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140023 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 GROUND FLOOR | PIPING ARRANGEMENT DRAWING | Steam Turbine & Generator | Piping | Steam Turbine Building |  | PIPING ARRANGEMENT DRAWING for STG |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7959 | 0.7638 | 0.7638 | g_ambig | uncertain |  |  | 1 |  | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 3 | 17.3440 | 0.6624 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140024 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 OPERATING FLOOR | PIPING ARRANGEMENT DRAWING | Steam Turbine & Generator | Piping | Steam Turbine Building |  | PIPING ARRANGEMENT DRAWING for STG |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7959 | 0.7638 | 0.7638 | g_ambig | uncertain |  |  | 1 |  | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 3 | 17.3440 | 0.6508 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140025 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #1 AREA | PIPING ARRANGEMENT DRAWING | AIR COOLED CONDENSER #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for AIR COOLED CONDENSER #1 |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7544 | 0.9263 | 0.9263 | [6 empty] | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | acc | acc | acc | query |  | activity_unscoped | true | true | 366 | 19 | 12.6343 | 0.5820 | 0.0150 | 0.0090 | hybrid | structured_phase_gap | acc | system_design |  | 2024-11-17 | 2024-12-17 | 2025-01-16 | 2025-01-31 | 2025-02-15 | 2025-03-02 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140026 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #2 & H2 CO2 N2 STORAGE SHELTER AREA | PIPING ARRANGEMENT DRAWING | AIR COOLED CONDENSER #2 | Piping | Hydrogen Carbon Dioxide Nitrogen STORAGE SHELTER |  | PIPING ARRANGEMENT DRAWING for AIR COOLED CONDENSER #2 |  | ACC - Piping Arrangement DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | drawing | drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.7458 | 0.9237 | 0.9237 | [6 empty] | FA | 2EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 |  | civil_design | civil_design | match | acc¦h2¦n2 | acc | acc¦h2¦n2 | query | n2 | match | true | false | 1 | 1 | 23.1354 | 0.5798 | 0.0328 | 0.0328 | hybrid | structured_preferred | acc¦h2¦n2 | civil_design | 10 | 2025-07-20 | 2025-08-19 | 2025-09-18 | 2025-10-03 | 2025-10-18 | 2025-11-02 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140027 | PIPING ARRANGEMENT DRAWING FOR ST BLDG PIPE RACK AREA | PIPING ARRANGEMENT DRAWING | Steam Turbine & Generator | Piping | Steam Turbine Building |  | PIPING ARRANGEMENT DRAWING for Steam Turbine Building |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7589 | 0.7527 | 0.7527 | g_ambig | uncertain |  |  | 1 |  | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 15.5671 | 0.6381 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140028 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #1 MAIN PIPE RACK AREA | PIPING ARRANGEMENT DRAWING | Steam Turbine & Generator | Piping | Steam Turbine Building |  | PIPING ARRANGEMENT DRAWING for Steam Turbine Building |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7589 | 0.7527 | 0.7527 | g_ambig | uncertain |  |  | 1 |  | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 22.1184 | 0.6409 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140029 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #2 MAIN PIPE RACK AREA | PIPING ARRANGEMENT DRAWING | Steam Turbine & Generator | Piping | Steam Turbine Building |  | PIPING ARRANGEMENT DRAWING for Steam Turbine Building |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7589 | 0.7527 | 0.7527 | g_ambig | uncertain |  |  | 1 |  | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 3 | 22.6601 | 0.6364 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140030 | PIPING ARRANGEMENT DRAWING FOR TO MAIN FCP GATE HOUSE AREA | PIPING ARRANGEMENT DRAWING |  | Piping | GATE HOUSE |  | PIPING ARRANGEMENT DRAWING for Piping |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8446 | 0.7784 | 0.7784 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 299 | 7 | 11.4706 | 0.5891 | 0.0177 | 0.0106 | hybrid | structured_no_system |  | system_design |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140031 | PIPING ARRANGEMENT DRAWING FOR TO ESF AREA | PIPING ARRANGEMENT DRAWING |  | Piping |  |  | PIPING ARRANGEMENT DRAWING for Piping |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8446 | 0.7784 | 0.7784 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 262 | 13 | 11.4706 | 0.5776 | 0.0168 | 0.0101 | hybrid | structured_no_system |  | system_design |  | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140032 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +0 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #1 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7206 | 0.7412 | 0.7412 | g_ambig | uncertain |  |  | 52 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 6 | 2 | 30.0721 | 0.6972 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140034 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #1 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7206 | 0.7412 | 0.7412 | g_ambig | uncertain |  |  | 52 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 2 | 24.0910 | 0.6970 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140036 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +108,000 & ABOVE | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #1 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #1 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7206 | 0.7412 | 0.7412 | g_ambig | uncertain |  |  | 52 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 2 | 24.0910 | 0.7067 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140037 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +0 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #2 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #2 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7230 | 0.7419 | 0.7419 | g_ambig | uncertain |  |  | 52 |  | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 4 | 1 | 31.1440 | 0.7053 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140038 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #2 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #2 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7230 | 0.7419 | 0.7419 | g_ambig | uncertain |  |  | 52 |  | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 1 | 25.1629 | 0.7019 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140039 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +108,000 & ABOVE | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #2 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #2 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7230 | 0.7419 | 0.7419 | g_ambig | uncertain |  |  | 52 |  | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 1 | 25.1629 | 0.7101 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-07-11 | 2024-08-10 | 2024-09-09 | 2024-09-24 | 2024-10-09 | 2024-10-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140040 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +0 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #3 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #3 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7216 | 0.7415 | 0.7415 | g_ambig | uncertain |  |  | 52 |  | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 4 | 2 | 31.1905 | 0.6802 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | hrsg | system_design |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140041 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #3 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #3 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7216 | 0.7415 | 0.7415 | g_ambig | uncertain |  |  | 52 |  | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 3 | 25.2094 | 0.6790 | 0.0323 | 0.0323 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140042 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +108,000 & ABOVE | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #3 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #3 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7216 | 0.7415 | 0.7415 | g_ambig | uncertain |  |  | 52 |  | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 3 | 25.2094 | 0.6868 | 0.0323 | 0.0323 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140043 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +0 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #4 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #4 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7126 | 0.7388 | 0.7388 | g_ambig | uncertain |  |  | 52 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 2 | 27.6279 | 0.6794 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140044 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +106,000 | PIPING ARRANGEMENT DRAWING | Heat Recovery Steam Generator #4 | Piping |  |  | PIPING ARRANGEMENT DRAWING for Heat Recovery Steam Generator #4 |  | Aux. Piping Arrangement DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | drawing | drawing | generator¦heat¦hrsg¦recovery¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7126 | 0.7388 | 0.7388 | g_ambig | uncertain |  |  | 52 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 1 | 2 | 21.6468 | 0.6813 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140045 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +108,000 & ABOVE | General Arrangement Drawing | Heat Recovery Steam Generator #4 | PIPING |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #4 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7720 | 0.9316 | 0.9316 | [6 empty] | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 5 | 24.1139 | 0.6661 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140046 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +0 | General Arrangement Drawing | Heat Recovery Steam Generator #5 | PIPING |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #5 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7791 | 0.9337 | 0.9337 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 1 | 25.2107 | 0.6948 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140047 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +106,000 | General Arrangement Drawing | Heat Recovery Steam Generator #5 | PIPING |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #5 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7791 | 0.9337 | 0.9337 | [6 empty] | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 5 | 24.1139 | 0.6571 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140048 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +108,000 & ABOVE | General Arrangement Drawing | Heat Recovery Steam Generator #5 | PIPING |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #5 |  | HRSG - General Arrangement | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7791 | 0.9337 | 0.9337 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 4 | 1 | 19.2297 | 0.6990 | 0.0320 | 0.0320 | hybrid | structured_preferred | hrsg | system_design | 6 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1MBA-140049 | PIPING ARRANGEMENT DRAWING FOR GT #1 AREA | General Arrangement Drawing | Gas Turbine #1 | PIPING |  |  | General Arrangement Drawing for Gas Turbine #1 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7061 | 0.9118 | 0.9118 | g_ambig | uncertain |  |  | 3 |  | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 2 | 1 | 3.1086 | 0.5504 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2MBA-140050 | PIPING ARRANGEMENT DRAWING FOR GT #2 AREA | General Arrangement Drawing | Gas Turbine #2 | PIPING |  |  | General Arrangement Drawing for Gas Turbine #2 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6995 | 0.9099 | 0.9099 | g_ambig | generic_ok | 0.78 |  | 3 | The document is a piping arrangement for the GT area, not specifically the GT air intake, exhaust system, or auxiliary foundation GA. | FA | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 1 | 6.5338 | 0.5649 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3MBA-140051 | PIPING ARRANGEMENT DRAWING FOR GT #3 AREA | General Arrangement Drawing | Gas Turbine #3 | PIPING |  |  | General Arrangement Drawing for Gas Turbine #3 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6929 | 0.9079 | 0.9079 | g_ambig | generic_ok | 0.78 |  | 3 | The title indicates a general piping arrangement for the GT area and does not clearly match the intake/exhaust system GA or auxiliary foundation GA specific rules. | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 1 | 6.5791 | 0.5543 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4MBA-140052 | PIPING ARRANGEMENT DRAWING FOR GT #4 AREA | General Arrangement Drawing | Gas Turbine #4 | PIPING |  |  | General Arrangement Drawing for Gas Turbine #4 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6867 | 0.9060 | 0.9060 | g_ambig | generic_ok | 0.78 |  | 3 | No explicit linkage in the title to the GT air intake system, GT exhaust system, or GTG auxiliary foundation deliverables. | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 3.1086 | 0.5543 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5MBA-140053 | PIPING ARRANGEMENT DRAWING FOR GT #5 AREA | General Arrangement Drawing | Gas Turbine #5 | PIPING |  |  | General Arrangement Drawing for Gas Turbine #5 |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6883 | 0.9065 | 0.9065 | g_ambig | generic_ok | 0.78 |  | 3 | This is a GT area piping arrangement drawing and the competing specific rules are for distinct sub-systems (intake/exhaust) or foundations. | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 3.1086 | 0.5424 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140054 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +0 | General Arrangement Drawing | Boiler Feed Pump | PIPING |  |  | General Arrangement Drawing for BFP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦feed¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7739 | 0.9322 | 0.9322 | g_safe | [5 empty] | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 4 | 2 | 24.7520 | 0.6756 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | feedwater | civil_design |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140055 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +111,500 | General Arrangement Drawing | Boiler Feed Pump | PIPING |  |  | General Arrangement Drawing for BFP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦feed¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7739 | 0.9322 | 0.9322 | g_safe | [5 empty] | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 3 | 2 | 24.7520 | 0.6733 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | feedwater | civil_design |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140056 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +114,500 | General Arrangement Drawing | Boiler Feed Pump | PIPING |  |  | General Arrangement Drawing for BFP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | boiler¦feed¦pump |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7739 | 0.9322 | 0.9322 | g_safe | [5 empty] | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 3 | 2 | 24.7520 | 0.6771 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | feedwater | civil_design |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140057 | PIPING ARRANGEMENT DRAWING FOR DEAERATOR AREA | General Arrangement Drawing |  | PIPING |  |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 63 | 11 | 13.9400 | 0.5864 | 0.0222 | 0.0133 | hybrid | structured_no_system |  | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140058 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 1 | General Arrangement Drawing |  | PIPING | Pipe Rack |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 5 | 38.8580 | 0.6651 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140059 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 2 | General Arrangement Drawing |  | PIPING | Pipe Rack |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_safe | [5 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 6 | 39.5500 | 0.6613 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140060 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 3 | General Arrangement Drawing |  | PIPING | Pipe Rack |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_safe | [5 empty] | FA | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 6 | 39.5800 | 0.6639 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140061 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 4 | General Arrangement Drawing |  | PIPING | Pipe Rack |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | pipe¦piperack¦piping¦rack |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 2 | 5 | 37.2801 | 0.6604 | 0.0315 | 0.0236 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140062 | PIPING ARRANGEMENT DRAWING FOR CCW FIN FAN COOLER AREA | General Arrangement Drawing | Fin Fan Cooler | PIPING |  |  | General Arrangement Drawing for Fin Fan Cooler |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | cooler¦fan¦fin |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7130 | 0.9139 | 0.9139 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 3 | 4.0191 | 0.4531 | 0.0323 | 0.0323 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UTF-140063 | PIPING ARRANGEMENT DRAWING FOR AIR COMPRESSOR AREA | General Arrangement Drawing | Air Compressor | PIPING |  |  | General Arrangement Drawing for Air Compressor |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | air¦compressor |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7316 | 0.9195 | 0.9195 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 15.2116 | 0.6680 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0GRK-140064 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT BLDG AREA | General Arrangement Drawing |  | PIPING | Water Treatment Building |  | General Arrangement Drawing for PIPING |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping¦wts |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7999 | 0.9400 | 0.9400 | g_ambig | uncertain | 0.40 |  | 1 | The title indicates piping arrangement for the water treatment plant, but the equipment is listed as PIPING, so it is unclear whether the water treatment system-specific GA rule is intended to govern. | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 6 | 2 | 22.3201 | 0.6597 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-10-12 | 2024-11-11 | 2024-12-11 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGD-140065 | PIPING ARRANGEMENT DRAWING FOR DEMI & POTABLE WATER TANK AREA | General Arrangement Drawing | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 20.3146 | 0.5670 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGA-140066 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK A/B AREA | General Arrangement Drawing | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fire_protection¦tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 13.8923 | 0.5396 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design | 2 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGA-140067 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK C AREA | General Arrangement Drawing | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fire_protection¦tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 13.8923 | 0.5356 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design | 2 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UCB-140068 | PIPING ARRANGEMENT DRAWING FOR CCB AREA | General Arrangement Drawing |  | Piping | Central Control Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | ccr¦piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 6 | 9 | 21.3666 | 0.5871 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LCA-140069 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK C AREA | General Arrangement Drawing | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 13.2995 | 0.6040 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LCA-140070 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A/B AREA | General Arrangement Drawing | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 13.2995 | 0.6007 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LDK-140071 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 1 | General Arrangement Drawing |  | Piping | CONDENSATE POLISING PLANT Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 7 | 3 | 1.5999 | 0.4155 | 0.0308 | 0.0308 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-11-20 | 2024-12-20 | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LDK-140072 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 2 | General Arrangement Drawing |  | Piping | CONDENSATE POLISING PLANT Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | false | 5 | 3 | 2.3015 | 0.4167 | 0.0313 | 0.0313 | hybrid | structured_preferred | condensate | civil_design | 10 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0EKG-140073 | PIPING ARRANGEMENT DRAWING FOR GPRS AREA | General Arrangement Drawing |  | Piping |  |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 63 | 31 | 13.9400 | 0.5811 | 0.0191 | 0.0115 | hybrid | structured_no_system |  | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYE-140074 | PIPING ARRANGEMENT DRAWING FOR MAIN GATE HOUSE AREA | General Arrangement Drawing |  | Piping | GATE HOUSE |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 81 | 6 | 13.9400 | 0.5997 | 0.0222 | 0.0133 | hybrid | structured_no_system |  | system_design |  | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYF-140075 | PIPING ARRANGEMENT DRAWING FOR SECURITY BUILDING AREA | General Arrangement Drawing |  | Piping | Security Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 6 | 4 | 21.3666 | 0.6000 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYC-140076 | PIPING ARRANGEMENT DRAWING FOR MAIN ADMIN BUILDING AREA | General Arrangement Drawing |  | Piping | Administration & Social Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 7 | 8 | 21.3666 | 0.6029 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UST-140077 | PIPING ARRANGEMENT DRAWING FOR MAINTENANCE & WORKSHOP BUILDING AREA | General Arrangement Drawing |  | Piping | Workshop & Storage Building |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 7 | 5 | 21.3666 | 0.6082 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | civil_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYP-140078 | PIPING ARRANGEMENT DRAWING FOR FIRE BRIGATE AREA | General Arrangement Drawing |  | Piping |  |  | General Arrangement Drawing for Piping |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | piping |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8306 | 0.9492 | 0.9492 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 68 | 11 | 13.8923 | 0.5867 | 0.0219 | 0.0164 | hybrid | structured_no_system |  | system_design |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UBA-140079 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #2 AREA | General Arrangement Drawing | Steam Turbine & Generator | Piping | ELECTRICAL BUILDING |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 4 | 1 | 24.9483 | 0.6886 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UBA-140080 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #1 & SWAS CONTAINER AREA | General Arrangement Drawing | Steam Turbine & Generator | Piping | ELECTRICAL BUILDING |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 4 | 1 | 24.9483 | 0.6735 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140081 | PIPING ARRANGEMENT DRAWING FOR FGP TP AREA | General Arrangement Drawing | Fuel Gas Package | Piping |  |  | General Arrangement Drawing for FGP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_ambig | uncertain | 0.45 |  | 2 | The competing specific rule keyword is identical to the generic one and the title does not clarify whether it is the package GA or PLC GA timeline. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 12.1217 | 0.6812 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140082 | PIPING ARRANGEMENT DRAWING FOR YARD AREA TO FGP TP | General Arrangement Drawing | Fuel Gas Package | Piping |  |  | General Arrangement Drawing for FGP |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | fgp¦fuel¦gas |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_ambig | uncertain | 0.45 |  | 2 | The competing specific rule keyword is identical to the generic one and the title does not clarify whether it is the package GA or PLC GA timeline. | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp |  | fgp | query | fgp | match | true | false | 1 | 1 | 12.1217 | 0.6689 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140083 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A & YARD AREA | General Arrangement Drawing | Tank | Piping |  |  | General Arrangement Drawing for Tank |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | tank |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.8024 | 0.9407 | 0.9407 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 13.2995 | 0.6017 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140100 | FABRICATION STANDARD DRAWING | DRAWING |  |  |  |  | DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8031 | 0.7076 | 0.4953 | [6 empty] | FA | 0EF3040W16A01 | (Lab) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-06-30 | design_drawing | civil_design | compatible |  |  |  |  | lab | query_unscoped | false | false | 15 | 123 | 0.0002 | 0.3967 | 0.0188 | 0.0106 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-11-17 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-31 | 2025-03-02 | generated | 0.30 |  | false | false | 0.35 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBA-140101 | FABRICATION ISOMETRIC DRAWING FOR HP STEAM SYSTEM | Isometric Drawing |  | HIGH PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for HIGH PRESSURE STEAM SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6996 | 0.4899 | 0.4899 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | compressed_air | steam | query | steam | match | true | false | 2 | 1 | 9.0525 | 0.6771 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBC-140102 | FABRICATION ISOMETRIC DRAWING FOR IP STEAM SYSTEM | Isometric Drawing |  | Intermediate Pressure STEAM SYSTEM |  |  | Isometric Drawing for Intermediate Pressure STEAM SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6793 | 0.4838 | 0.4838 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | compressed_air | steam | query | steam | match | true | false | 1 | 1 | 9.0525 | 0.6818 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140103 | FABRICATION ISOMETRIC DRAWING FOR LP STEAM SYSTEM | Isometric Drawing |  | LOW PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for LOW PRESSURE STEAM SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6808 | 0.4842 | 0.4842 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | compressed_air | steam | query | steam | match | true | false | 2 | 1 | 9.0525 | 0.6701 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140104 | FABRICATION ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM | Isometric Drawing |  | Steam System |  |  | Isometric Drawing for Steam System | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | steam |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7072 | 0.4922 | 0.4922 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | compressed_air | steam | query | steam | match | true | false | 1 | 1 | 9.0525 | 0.6939 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCM-140105 | FABRICATION ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM | Isometric Drawing |  | STEAM DRAIN SYSTEM |  |  | Isometric Drawing for STEAM DRAIN SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6575 | 0.4772 | 0.4772 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam | compressed_air | steam | query | steam | match | true | false | 1 | 1 | 9.0525 | 0.6713 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCA-140106 | FABRICATION ISOMETRIC DRAWING FOR CONDENSATE SYSTEM | Isometric Drawing |  | CONDENSATE SYSTEM |  |  | Isometric Drawing for CONDENSATE SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7083 | 0.4925 | 0.4925 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate | compressed_air | condensate | query | condensate | match | true | false | 1 | 1 | 15.6554 | 0.6746 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LAB-140108 | FABRICATION ISOMETRIC DRAWING FOR FEED WATER SYSTEM | Isometric Drawing |  | FEED WATER SYSTEM |  |  | Isometric Drawing for FEED WATER SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | feed¦water |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6867 | 0.4860 | 0.4860 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater | compressed_air | feedwater | query | feedwater | match | true | false | 1 | 1 | 23.7808 | 0.6842 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PGB-140109 | FABRICATION ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM | Isometric Drawing |  | CLOSED COOLING WATER SYSTEM |  |  | Isometric Drawing for CLOSED COOLING WATER SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6724 | 0.4817 | 0.4817 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw | compressed_air | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 14.0432 | 0.3498 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SCA-140110 | FABRICATION ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM | Isometric Drawing |  | SERVICE AIR SYSTEM |  |  | Isometric Drawing for SERVICE AIR SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | air¦service |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7366 | 0.6410 | 0.6410 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 11.3826 | 0.6183 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140112 | FABRICATION ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM | Isometric Drawing |  | POTABLE WATER SYSTEM |  |  | Isometric Drawing for POTABLE WATER SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6403 | 0.4721 | 0.4721 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts | compressed_air | wts | query | wts | match | true | false | 4 | 1 | 28.9455 | 0.6492 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | system_design |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GHC-140113 | FABRICATION ISOMETRIC DRAWING FOR DEMI WATER SYSTEM | Isometric Drawing |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.8333 | 0.7006 | 0.7935 | 0.7935 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | false | 1 | 1 | 6.5714 | 0.5517 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PDA-140114 | FABRICATION ISOMETRIC DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | Isometric Drawing |  | Water Treatment System |  |  | Isometric Drawing for Water Treatment System | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9517 | 0.9855 | 0.9855 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 1 | 16.1724 | 0.6528 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | wts | system_design |  | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBH-140116 | FABRICATION ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | Isometric Drawing | Gas Turbine Generator |  |  |  | Isometric Drawing for GTG | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6204 | 0.6061 | 0.6061 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | compressed_air | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 9.1752 | 0.4925 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKC-140117 | FABRICATION ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM | Isometric Drawing | Gas Turbine Generator |  |  |  | Isometric Drawing for GTG |  | ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5763 | 0.6396 | 0.4477 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 4.1124 | 0.4824 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKG-140118 | FABRICATION ISOMETRIC DRAWING FOR FUEL GAS SYSTEM | Isometric Drawing | Fuel Gas Package | FUEL GAS SYSTEM |  |  | Isometric Drawing for FGP | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6377 | 0.4713 | 0.4713 | g_safe | [5 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | fgp | compressed_air | fgp | query | fgp | match | true | false | 1 | 1 | 17.7286 | 0.6671 | 0.0328 | 0.0328 | hybrid | structured_preferred | fgp | system_design | 2 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140119 | FABRICATION ISOMETRIC DRAWING FOR TG MISCELLANEOUS SYSTEM | Isometric Drawing |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.5800 | 0.6407 | 0.6407 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | false | 1 | 1 | 2.9879 | 0.4550 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140120 | ISOMETRIC DRAWING FOR TG MISCELLANEOUS SMALL BORE SYSTEM | Isometric Drawing |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6013 | 0.6470 | 0.6470 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | false | 1 | 1 | 2.9879 | 0.4674 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GM-140121 | FABRICATION ISOMETRIC DRAWING FOR WASTE WATER SYSTEM | Isometric Drawing |  | Water Treatment System |  |  | Isometric Drawing for Water Treatment System | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9517 | 0.9855 | 0.9855 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | wts | wts | query | wts | match | true | false | 4 | 4 | 24.9288 | 0.6187 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | wts | system_design |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBA-140201 | ISOMETRIC DRAWING FOR HP STEAM SYSTEM SMALL BORE | Isometric Drawing |  | HIGH PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for HIGH PRESSURE STEAM SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7612 | 0.7884 | 0.5519 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.6816 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBC-140202 | ISOMETRIC DRAWING FOR IP STEAM SYSTEM SMALL BORE | Isometric Drawing |  | Intermediate Pressure STEAM SYSTEM |  |  | Isometric Drawing for Intermediate Pressure STEAM SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7691 | 0.7907 | 0.5535 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.6861 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140203 | ISOMETRIC DRAWING FOR LP STEAM SYSTEM SMALL BORE | Isometric Drawing |  | LOW PRESSURE STEAM SYSTEM |  |  | Isometric Drawing for LOW PRESSURE STEAM SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7617 | 0.7885 | 0.5520 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.6681 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140204 | ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM SMALL BORE | Isometric Drawing |  | Steam System |  |  | Isometric Drawing for Steam System |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7883 | 0.7965 | 0.5575 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 6.7693 | 0.7005 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCM-140205 | ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM SMALL BORE | Isometric Drawing |  | STEAM DRAIN SYSTEM |  |  | Isometric Drawing for STEAM DRAIN SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7886 | 0.7966 | 0.5576 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 2 | 1 | 6.7693 | 0.6743 | 0.0325 | 0.0325 | hybrid | structured_preferred | steam | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCA-140206 | ISOMETRIC DRAWING FOR CONDENSATE SYSTEM SMALL BORE | Isometric Drawing |  | CONDENSATE SYSTEM |  |  | Isometric Drawing for CONDENSATE SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7858 | 0.7957 | 0.5570 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 13.4774 | 0.6658 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LAB-140208 | ISOMETRIC DRAWING FOR FEED WATER SYSTEM SMALL BORE | Isometric Drawing |  | FEED WATER SYSTEM |  |  | Isometric Drawing for FEED WATER SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | feed¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7963 | 0.7989 | 0.5592 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 1 | 1 | 21.6028 | 0.6591 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design | 1 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PGB-140209 | ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM SMALL BORE | Isometric Drawing |  | CLOSED COOLING WATER SYSTEM |  |  | Isometric Drawing for CLOSED COOLING WATER SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7725 | 0.7917 | 0.5542 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 14.0432 | 0.3458 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SCA-140210 | ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM SMALL BORE | Isometric Drawing |  | SERVICE AIR SYSTEM |  |  | Isometric Drawing for SERVICE AIR SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | air¦service |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7366 | 0.6410 | 0.6410 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 11.3826 | 0.6139 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QFB-140211 | ISOMETRIC DRAWING FOR INSTRUMENT AIR SYSTEM SMALL BORE | Isometric Drawing |  | INSTRUMENT AIR SYSTEM |  |  | Isometric Drawing for INSTRUMENT AIR SYSTEM | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | air¦instrument |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7311 | 0.6393 | 0.6393 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 11.3826 | 0.6460 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140212 | ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM SMALL BORE | Isometric Drawing |  | POTABLE WATER SYSTEM |  |  | Isometric Drawing for POTABLE WATER SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7671 | 0.7901 | 0.5531 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 26.6249 | 0.6445 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GHC-140213 | ISOMETRIC DRAWING FOR DEMI WATER SYSTEM SMALL BORE | Isometric Drawing |  |  |  |  | Isometric Drawing | Water Treatment System | Isometric DraWing for Water Treatment System | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | drawing | drawing | isometric_drawing | isometric_drawing |  | wts | scoped | match | match | query_unscoped | passed |  | 0.8333 | 0.7332 | 0.8033 | 0.8033 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | wts | wts | rule | wts | match | false | false | 1 | 1 | 6.5714 | 0.5733 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140215 | ISOMETRIC DRAWING FOR UNDERGROUND PIPING SYSTEM | Isometric Drawing |  | PIPING |  |  | Isometric Drawing for PIPING | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | isometric_drawing | isometric_drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7662 | 0.6499 | 0.6499 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  | compressed_air | compressed_air | rule | compressed_air | match | false | false | 1 | 1 | 8.1013 | 0.5589 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBH-140216 | ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM SMALL BORE | Isometric Drawing | Gas Turbine Generator | COOLING SYSTEM |  |  | Isometric Drawing for GTG | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6510 | 0.6153 | 0.6153 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg | compressed_air | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 11.7067 | 0.4917 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKC-140217 | ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM SMALL BORE | Isometric Drawing | Gas Turbine Generator |  |  |  | Isometric Drawing for GTG |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7196 | 0.7759 | 0.5431 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 4.1124 | 0.4944 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QUB-140219 | ISOMETRIC DRAWING FOR SAMPLING SYSTEM SMALL BORE | Isometric Drawing |  | SAMPLING SYSTEM |  |  | Isometric Drawing for SAMPLING SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | sampling |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7897 | 0.7969 | 0.5578 | g_safe | [5 empty] | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | system_design | system_design | match | sampling |  | sampling | query | sampling | match | true | false | 1 | 1 | 18.4875 | 0.6614 | 0.0328 | 0.0328 | hybrid | structured_preferred | sampling | system_design | 1 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QCA-140221 | ISOMETRIC DRAWING FOR CHEMICAL DOSING SYSTEM SMALL BORE | Isometric Drawing |  | CHEMICAL DOSING SYSTEM |  |  | Isometric Drawing for CHEMICAL DOSING SYSTEM |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7580 | 0.7874 | 0.5512 | g_safe | [5 empty] | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 31.5207 | 0.7257 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QJA-140223 | ISOMETRIC DRAWING FOR N2 GAS SYSTEM SMALL BORE | Isometric Drawing | Nitrogen System | Nitrogen GAS SYSTEM |  |  | Isometric Drawing for Nitrogen System |  | SMALL BORE ERECTION ISOMETRIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | isometric_drawing | isometric_drawing | nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7576 | 0.7873 | 0.5511 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match | n2 |  | n2 | query | n2 | match | true | false | 1 | 1 | 26.0900 | 0.7385 | 0.0328 | 0.0328 | hybrid | structured_preferred | n2 | system_design | 1 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GM-140224 | ISOMETRIC DRAWING FOR WASTE WATER SYSTEM SMALL BORE | OUTLINE DRAWINGS |  | Water Treatment System |  |  | OUTLINE DRAWINGS for Water Treatment System | Substation | Outline DraWing (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | treatment¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6154 | 0.5346 | 0.5346 | g_safe | [5 empty] | SKIP | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | system_design | system_design | match | wts | dc_ups | wts | query | wts | match | true | false | 4 | 3 | 24.9288 | 0.6398 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | wts | system_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140301 | MANUAL BUTTERFLY VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS | MANUAL BUTTERFLY VALVE |  |  |  | OUTLINE DRAWINGS for MANUAL BUTTERFLY VALVE |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual | butterfly¦valve |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8725 | 0.7868 | 0.5507 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 65 | 112 |  | 0.3152 | 0.0138 | 0.0083 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.44 | needs_review | activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140302 | MANUAL LOW PRESSURE CASTING VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8247 | 0.7724 | 0.5407 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | false | 1182 | 29 |  | 0.3804 | 0.0120 | 0.0090 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140303 | MANUAL HIGH PRESSURE CASTING VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8372 | 0.7762 | 0.5433 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | false | 1200 | 27 |  | 0.3884 | 0.0123 | 0.0092 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140304 | MANUAL FORGING VALVE OUTLINE DRAWINGS | DRAWINGS |  |  |  |  | DRAWINGS |  | MANUAL VALVE OUTLINE DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | manual | manual | manual | manual |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8738 | 0.7871 | 0.5510 | [6 empty] | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 130 | 17 |  | 0.4338 | 0.0183 | 0.0137 | hybrid | structured_no_system |  | system_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140401 | PIPING SUPPORT DETAIL DRAWING FOR HP STEAM SYSTEM | DRAWING |  | HIGH PRESSURE STEAM SYSTEM |  |  | DRAWING for HIGH PRESSURE STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6437 | 0.8931 | 0.6252 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | true | false | 2 | 1 | 9.4005 | 0.6837 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140402 | PIPING SUPPORT DETAIL DRAWING FOR IP STEAM SYSTEM | DRAWING |  | Intermediate Pressure STEAM SYSTEM |  |  | DRAWING for Intermediate Pressure STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6583 | 0.8975 | 0.6283 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | true | false | 2 | 1 | 9.4005 | 0.7114 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140403 | PIPING SUPPORT DETAIL DRAWING FOR LP STEAM SYSTEM | DRAWING |  | LOW PRESSURE STEAM SYSTEM |  |  | DRAWING for LOW PRESSURE STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6662 | 0.8999 | 0.6299 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | true | false | 2 | 1 | 9.4005 | 0.6584 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140404 | PIPING SUPPORT DETAIL DRAWING FOR PROCESS STEAM SYSTEM | DRAWING |  | PROCESS STEAM SYSTEM |  |  | DRAWING for PROCESS STEAM SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6819 | 0.9046 | 0.6332 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | true | false | 1 | 1 | 9.4005 | 0.7327 | 0.0328 | 0.0246 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140405 | PIPING SUPPORT DETAIL DRAWING FOR STEAM DRAIN SYSTEM | DRAWING |  | STEAM DRAIN SYSTEM |  |  | DRAWING for STEAM DRAIN SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6695 | 0.9008 | 0.6306 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | steam |  | steam | query | steam | match | true | false | 2 | 1 | 9.4005 | 0.6679 | 0.0325 | 0.0244 | hybrid | structured_preferred | steam | system_design¦civil_design | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140406 | PIPING SUPPORT DETAIL DRAWING FOR CONDENSATE SYSTEM | DRAWING |  | CONDENSATE SYSTEM |  |  | DRAWING for CONDENSATE SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6849 | 0.9055 | 0.6338 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | design_drawing | system_design | compatible | condensate |  | condensate | query | condensate | match | true | false | 1 | 1 | 15.9873 | 0.6892 | 0.0328 | 0.0246 | hybrid | structured_preferred | condensate | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140407 | PIPING SUPPORT DETAIL DRAWING FOR FEEDWATER SYSTEM | DRAWING |  | FEEDWATER SYSTEM |  |  | DRAWING for FEEDWATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | feedwater |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6717 | 0.9015 | 0.6311 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | feedwater |  | feedwater | query | feedwater | match | true | false | 1 | 1 | 3.7367 | 0.6870 | 0.0328 | 0.0246 | hybrid | structured_preferred | feedwater | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140408 | PIPING SUPPORT DETAIL DRAWING FOR CLOSED COOLING WATER SYSTEM | DRAWING |  | CLOSED COOLING WATER SYSTEM |  |  | DRAWING for CLOSED COOLING WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6507 | 0.8952 | 0.6267 | g_safe | [5 empty] | FA | 1EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-01-30 | design_drawing | civil_design | compatible | ccw |  | ccw | query | ccw | match | true | false | 1 | 6 | 28.9307 | 0.5880 | 0.0315 | 0.0237 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140410 | PIPING SUPPORT DETAIL DRAWING FOR SERVICE AIR SYSTEM | DRAWING |  | SERVICE AIR SYSTEM |  |  | DRAWING for SERVICE AIR SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦service |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6965 | 0.9089 | 0.6363 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 11.7251 | 0.6358 | 0.0328 | 0.0246 | hybrid | structured_preferred | compressed_air | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140411 | PIPING SUPPORT DETAIL DRAWING FOR POTABLE WATER SYSTEM | DRAWING |  | POTABLE WATER SYSTEM |  |  | DRAWING for POTABLE WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | potable¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6645 | 0.8993 | 0.6295 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | wts |  | wts | query | wts | match | true | false | 1 | 1 | 29.2993 | 0.6488 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140412 | PIPING SUPPORT DETAIL DRAWING FOR DEMI. WATER SYSTEM | DRAWING |  | Demineralized WATER SYSTEM |  |  | DRAWING for Demineralized WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | demineralized¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6572 | 0.8971 | 0.6280 | g_safe | [5 empty] | FA | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | design_drawing | civil_design | compatible | wts |  | wts | query | wts | match | false | false | 3 | 1 | 22.2057 | 0.6498 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 |  | false | false | 0.24 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140415 | PIPING SUPPORT DETAIL DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5300 | 0.2990 | 0.2990 | [6 empty] | FI | 1EF1225W16A09 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | gtg | gtg | gtg | query | ccw¦gtg | match | true | false | 1 | 24 | 13.0382 | 0.5684 | 0.0283 | 0.0212 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140416 | PIPING SUPPORT DETAIL DRAWING FOR GT PERFORMANCE HEATER SYSTEM | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5300 | 0.2990 | 0.2990 | [6 empty] | FI | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | design_drawing | civil_design | compatible | gtg | gtg | gtg | query | gtg | match | true | false | 11 | 8 | 7.2288 | 0.5873 | 0.0288 | 0.0216 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140417 | PIPING SUPPORT DETAIL DRAWING FOR FUEL GAS SYSTEM | DRAWING | Fuel Gas Package | FUEL GAS SYSTEM |  |  | DRAWING for FUEL GAS SYSTEM | Fuel Gas System | Equipment (incl. pump) Detail DraWing | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | fgp¦fuel¦gas | fgp¦pump | scoped | match | match | match | passed |  | 0.5000 | 0.7621 | 0.5786 | 0.5786 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | design_drawing | system_design | compatible | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 1 | 20.2978 | 0.6937 | 0.0328 | 0.0246 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-08-02 | 2024-08-30 | 2024-09-27 | 2024-09-20 | 2024-10-18 | 2024-11-15 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140418 | PIPING SUPPORT DETAIL DRAWING FOR STEAM BLOWING | DRAWING |  |  |  |  | DRAWING |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.6690 | 0.9007 | 0.6305 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | true | false | 219 | 4 | 5.4229 | 0.6259 | 0.0192 | 0.0108 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140419 | PIPING SUPPORT DETAIL DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | DRAWING |  | Water Treatment System |  |  | DRAWING for Water Treatment System | Water Treatment System | Equipment Assembly and Detail DraWing for Water Treatment System | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5556 | 0.7136 | 0.6030 | 0.6030 | [6 empty] | FI | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 7 | 1 | 18.8468 | 0.6953 | 0.0313 | 0.0235 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140420 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING ESOD AREA | DRAWING |  |  |  |  | DRAWING | FireFighting | Piping Support DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6666 | 0.7250 | 0.7250 | [6 empty] | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 25 | 133 | 17.3706 | 0.5110 | 0.0169 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-12-22 | 2025-02-16 | 2025-04-13 | 2025-03-09 | 2025-05-04 | 2025-06-29 | generated | 0.90 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140421 | PIPING SUPPORT DETAIL DRAWING FOR WASTE WATER SYSTEM | DRAWING |  | WASTE WATER SYSTEM |  |  | DRAWING for WASTE WATER SYSTEM |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | waste¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6667 | 0.9000 | 0.6300 | g_safe | [5 empty] | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts |  | wts | query | wts | match | true | false | 1 | 1 | 27.0327 | 0.6384 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140422 | PIPING SUPPORT DETAIL DRAWING FOR TG MISCELLANEOUS SYSTEM | DRAWING |  |  |  |  | DRAWING |  | SUPPORT DETAIL DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.6989 | 0.9097 | 0.6368 | [6 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 115 | 4 | 6.9231 | 0.5641 | 0.0213 | 0.0120 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140423 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING NON ESOD AREA | DRAWING |  | SB PIPING |  |  | DRAWING for SB PIPING | FireFighting | Piping Support DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | title | drawing | drawing | drawing | drawing | piping |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6668 | 0.7250 | 0.7250 | g_safe | [5 empty] | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 33 | 103 | 20.9535 | 0.5091 | 0.0169 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-12-22 | 2025-02-16 | 2025-04-13 | 2025-03-09 | 2025-05-04 | 2025-06-29 | generated | 0.90 |  | false | false | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-150001 | DESIGN CRITERIA FOR ELECTRICAL SYSTEM | DESIGN CRITERIA |  | ELECTRICAL SYSTEM |  |  | DESIGN CRITERIA for ELECTRICAL SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | criteria | criteria | design_criteria | design_criteria | electrical |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5023 | 0.5707 | 0.5707 | g_safe | [5 empty] | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_criteria | civil_design | compatible | electrical | wts | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 7 | 4 | 15.5488 | 0.4792 | 0.0306 | 0.0229 | hybrid | structured_preferred | electrical | design_criteria¦system_design¦civil_design | 10 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL06-P0ZEN-150101 | ELECTRICAL LOAD LIST | LOAD LIST |  | ELECTRICAL |  |  | LOAD LIST for ELECTRICAL | [5 empty] | rule_query | other | other | load_list | electrical_load_list | electrical |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8329 | 0.9499 | 0.9499 | [7 empty] | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | true | false | 4 | 2 | 7.2798 | 0.4438 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | procurement | 10 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150201 | SYMBOL & LEGEND FOR ELECTRICAL SYSTEM | SYMBOL & LEGEND |  | ELECTRICAL SYSTEM |  |  | SYMBOL & LEGEND for ELECTRICAL SYSTEM | [5 empty] | rule_query | other | diagram | symbol_and_legend | diagram | electrical | gt¦gtg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.4286 | 0.5688 | 0.4706 | 0.4706 | [7 empty] | 0CF6500W70A04.6 | (Electrical Protection Panel) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-04-25 | 2008-05-26 |  | installation | query_unknown | electrical |  | electrical | query | electrical | match | true | false | 18 | 1 | 8.3620 | 0.5143 | 0.0292 | 0.0219 | hybrid | structured_no_phase | electrical | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150202 | KEY SINGLE LINE DIAGRAM | Single Line Diagram |  |  |  |  | Single Line Diagram |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | SKIP | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | false | 19 | 127 | 12.3101 | 0.5019 | 0.0180 | 0.0135 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150211 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR GTG UNIT | Single Line Diagram | Gas Turbine Generator UNIT | PROTECTION AND METERING |  |  | Single Line Diagram for PROTECTION AND METERING |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦metering¦protection¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7277 | 0.9183 | 0.9183 | g_ambig | uncertain | 0.55 |  | 5 | “Protection and metering SLD for GTG unit” could correspond to generator circuit or an auxiliary distribution SLD, but the exact target system is not stated. | SKIP | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 2 | 1 | 5.8467 | 0.5426 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150212 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR STG UNIT | Single Line Diagram | Steam Turbine Generator UNIT | PROTECTION AND METERING |  |  | Single Line Diagram for PROTECTION AND METERING |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | generator¦metering¦protection¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7277 | 0.9183 | 0.9183 | g_safe | [5 empty] | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 1 | 5.6714 | 0.6040 | 0.0328 | 0.0328 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU05-P0ZEN-150221 | PHASING DIAGRAM | PHASING DIAGRAM |  |  |  |  | PHASING DIAGRAM |  | System Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram |  |  | generic | match | match | query_unscoped | passed |  | 0.3333 | 0.5362 | 0.3942 | 0.2759 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | false | 11 | 2 | 10.0268 | 0.4219 | 0.0302 | 0.0170 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150301 | SHORT CIRCUIT STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 | [7 empty] | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 85 | 3092 |  | 0.2245 | 0.0072 | 0.0054 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150302 | LOAD FLOW & LARGE MOTOR STARTING STUDY | STUDY |  |  |  |  | STUDY | [5 empty] | rule_query | other | other | study | hrsg_dispersion_study |  | hrsg | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.3953 | 0.3519 | 0.3519 | [7 empty] | 3EF2020W00A01 | (ST #30) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  |  |  |  | stg | query_unscoped | false | false | 3992 | 217 |  | 0.3953 | 0.0039 | 0.0029 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150303 | CT PT CALCULATION STUDY REPORT FOR HV EQUIPMENT | REPORT | HIGH VOLTAGE EQUIPMENT |  |  |  | REPORT for HIGH VOLTAGE EQUIPMENT |  | STUDY REPORT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | study_report | study_report | high¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5602 | 0.6347 | 0.4443 | g_safe | [5 empty] | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | false | 33 | 72 | 12.7293 | 0.4819 | 0.0183 | 0.0137 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150304 | HARMONIC STUDY REPORT | REPORT |  |  |  |  | REPORT |  | GT - HAZOP STUDY REPORT | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | title | report | report | study_report | study_report |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5847 | 0.5254 | 0.5254 | [6 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match |  | gtg | gtg | rule | ccw¦gtg | match | false | false | 1 | 2 |  | 0.3670 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150305 | INSULATION STUDY REPORT | REPORT |  |  |  |  | REPORT |  | GT - SIL STUDY REPORT | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | title | report | report | study_report | study_report |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5367 | 0.5110 | 0.5110 | [6 empty] | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | procurement | procurement | match |  | gtg | gtg | rule | electrical¦gsut_uat¦gtg | match | false | false | 1 | 4 | 7.5725 | 0.4786 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | procurement | 10 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150306 | TAP RATIO STUDY REPORT | REPORT |  |  |  |  | REPORT |  | GT - SIL STUDY REPORT | 1 | start+130D<=FA<=start+130D+2M | FA ∈ [start+130d, start+190d] | title | report | report | study_report | study_report |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5917 | 0.5275 | 0.5275 | [6 empty] | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | procurement | procurement | match |  | gtg | gtg | rule | electrical¦gsut_uat¦gtg | match | false | false | 1 | 4 | 7.5725 | 0.4619 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | procurement | 10 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150311 | PROTECTION RELAY COORDINATION STUDY - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | STUDY | Generator Step-Up Transformer / Unit Auxiliary Transformer |  |  |  | STUDY for Generator Step-Up Transformer / Unit Auxiliary Transformer | [5 empty] | rule_query | other | calculation | study | calculation | auxiliary¦gas¦generator¦gtg¦step¦transformer¦turbine¦unit | gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4444 | 0.6987 | 0.5207 | 0.5207 | [7 empty] | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 188 | 3362 | 7.5405 | 0.3292 | 0.0043 | 0.0026 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150312 | PROTECTION RELAY COORDINATION STUDY - MV SWITCHGEAR | STUDY | Medium Voltage SWITCHGEAR |  |  |  | STUDY for Medium Voltage SWITCHGEAR | [5 empty] | rule_query | other | drawing | study | drawing | medium¦switchgear¦voltage |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.7500 | 0.7305 | 0.7442 | 0.5209 | [7 empty] | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 111 | 1123 |  | 0.3473 | 0.0067 | 0.0040 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150313 | PROTECTION RELAY COORDINATION STUDY - LV SWITCHGEAR | STUDY | Low Voltage SWITCHGEAR |  |  |  | STUDY for Low Voltage SWITCHGEAR | [5 empty] | rule_query | other | drawing | study | drawing | low¦switchgear¦voltage |  | scoped | mismatch | not_applicable | rule_generic | rejected | deliverable_family_mismatch | 0.5000 | 0.7103 | 0.5631 | 0.3942 | [7 empty] | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 111 | 992 |  | 0.3391 | 0.0068 | 0.0041 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150314 | PROTECTION RELAY COORDINATION STUDY - GSUT / OVERALL PROTECTION FOR STG UNIT | STUDY | Generator Step-Up Transformer |  |  |  | STUDY for Generator Step-Up Transformer | [5 empty] | rule_query | other | drawing | study | sectional_drawing | generator¦steam¦step¦stg¦transformer¦turbine | stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.3750 | 0.6366 | 0.4535 | 0.4535 | [7 empty] | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 154 | 3454 | 7.5405 | 0.3068 | 0.0050 | 0.0030 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BA-150401 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | LOGIC DIAGRAM | Generator Step-Up Transformer / Unit Auxiliary Transformer |  |  |  | Control Logic Diagram for Generator Step-Up Transformer / Unit Auxiliary Transformer | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | title | diagram | diagram | control_logic_diagram | control_logic_diagram | auxiliary¦gas¦generator¦gtg¦step¦transformer¦turbine¦unit |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5697 | 0.6959 | 0.6959 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 75 | 1980 | 22.4244 | 0.4262 | 0.0079 | 0.0047 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BB-150402 | ELECTRICAL CONTROL LOGIC DIAGRAM - MV SWITCHGEAR | LOGIC DIAGRAM | Medium Voltage SWITCHGEAR |  |  |  | Control Logic Diagram for Medium Voltage SWITCHGEAR | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | medium¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6670 | 0.7251 | 0.7251 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 40 | 416 | 14.8839 | 0.4552 | 0.0121 | 0.0073 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BB-150403 | ELECTRICAL CONTROL LOGIC DIAGRAM - LV SWITCHGEAR | LOGIC DIAGRAM | Low Voltage SWITCHGEAR |  |  |  | Control Logic Diagram for Low Voltage SWITCHGEAR | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | low¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6647 | 0.7244 | 0.7244 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 41 | 755 | 13.8746 | 0.4030 | 0.0111 | 0.0067 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BA-150404 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / OVERALL PROTECTION FOR STG UNIT | LOGIC DIAGRAM | Generator Step-Up Transformer |  |  |  | Control Logic Diagram for Generator Step-Up Transformer | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | generator¦steam¦step¦stg¦transformer¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5863 | 0.7009 | 0.7009 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 26 | 2535 | 22.4244 | 0.3737 | 0.0120 | 0.0072 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UCA-150501 | ELECTRICAL ROOM LAYOUT DRAWING - CENTRAL CONTROL BUILDING | Layout Drawing |  | Electrical System | Central Control Building |  | Layout Drawing for Central Control Building | Substation | Electrical Room Layout DraWing_Control BLDG | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8384 | 0.7515 | 0.7515 | g_safe | [5 empty] | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 7 | 10 | 8.6342 | 0.5029 | 0.0292 | 0.0292 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150502 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #1,2 LEB | Layout Drawing | Gas Turbine Generator #1,2 | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8693 | 0.9608 | 0.6726 | g_ambig | generic_ok | 0.80 |  | 1 | An electrical room layout drawing is different in scope from a generator foundation embedded metals layout, so the specific rule does not apply. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 4 | 2 | 20.1538 | 0.7349 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150503 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #3,4,5 LEB | Layout Drawing | Gas Turbine Generator #3,4,5 | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8577 | 0.9573 | 0.6701 | g_ambig | generic_ok | 0.80 |  | 1 | The document concerns electrical room layout (LEB), not generator foundation embedded metals, so the competing specific rule targets different equipment/scope. | FA | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 3 | 5 | 18.8315 | 0.6758 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150504 | ELECTRICAL ROOM LAYOUT DRAWING - STG #1 LEB | Layout Drawing | Steam Turbine Generator #1 | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8769 | 0.9631 | 0.6742 | g_safe | [5 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 1 | 6 | 15.4069 | 0.6160 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150505 | ELECTRICAL ROOM LAYOUT DRAWING - STG #2 LEB | Layout Drawing | Steam Turbine Generator #2 | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8681 | 0.9604 | 0.6723 | g_safe | [5 empty] | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 7 | 1 | 13.7650 | 0.6274 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150506 | ELECTRICAL ROOM LAYOUT DRAWING - WATER TREATMENT PLANT BUILDING | Layout Drawing |  | Water Treatment System | WATER TREATMENT PLANT BUILDING |  | Layout Drawing for WATER TREATMENT PLANT BUILDING | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | plant¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6778 | 0.6700 | 0.6700 | [6 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | true | false | 8 | 1 | 22.2145 | 0.6303 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150508 | ELECTRICAL ROOM LAYOUT DRAWING –AUX. LEB | Layout Drawing |  | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | ELECTRICAL ROOM LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8659 | 0.9598 | 0.6718 | g_safe | [5 empty] | FA | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 4 | 14 | 9.4733 | 0.4981 | 0.0291 | 0.0291 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | 2024-10-06 | 2024-11-05 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAT-150601 | SIZING CALCULATION - GENERATOR STEP - UP TRANSFORMER | Calculation sheet | GENERATOR STEP - UP TRANSFORMER |  |  |  | Calculation sheet for GENERATOR STEP - UP TRANSFORMER | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6310 | 0.5393 | 0.5393 | g_safe | [5 empty] | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat |  | gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 13 | 1 | 12.9176 | 0.5651 | 0.0301 | 0.0301 | hybrid | structured_preferred | gsut_uat | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAT-150611 | TECHNICAL SPECIFICATION - GENERATOR STEP - UP TRANSFORMER | Technical Specification | GENERATOR STEP - UP TRANSFORMER |  |  |  | Technical Specification for GENERATOR STEP - UP TRANSFORMER | Transformer | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7088 | 0.5626 | 0.5626 | g_safe | [5 empty] | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | procurement | procurement | match | gsut_uat | gsut_uat | gsut_uat | query | gsut_uat¦stg | match | true | false | 1 | 13 | 50.7844 | 0.6184 | 0.0301 | 0.0301 | hybrid | structured_cell_found_text_preferred | gsut_uat | procurement |  | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAT-150621 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (GTG) | Outline Drawing | GENERATOR STEP - UP TRANSFORMER |  |  |  | Outline Drawing for GENERATOR STEP - UP TRANSFORMER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | gas¦generator¦gtg¦step¦transformer¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5940 | 0.6449 | 0.6449 | g_ambig | generic_ok | 0.86 |  | 6 | All competing specific rules are for GT motors/filters/valves/receptacles/pump skids, not for a generator step-up transformer outline drawing. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 34 | 2288 | 20.4002 | 0.4014 | 0.0111 | 0.0066 | hybrid | structured_phase_gap | gsut_uat | system_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAT-150626 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (STG) | Outline Drawing | GENERATOR STEP - UP TRANSFORMER |  |  |  | Outline Drawing for GENERATOR STEP - UP TRANSFORMER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | generator¦steam¦step¦stg¦transformer¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5848 | 0.6421 | 0.6421 | g_ambig | generic_ok | 0.82 |  | 3 | Steam turbine auxiliaries outline drawing rules do not clearly cover a generator step-up transformer outline drawing. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 31 | 2278 | 20.4002 | 0.3913 | 0.0114 | 0.0069 | hybrid | structured_phase_gap | gsut_uat | system_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAT-150631 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER | SCHEMATIC DIAGRAM | GENERATOR STEP - UP TRANSFORMER |  |  |  | SCHEMATIC DIAGRAM for GENERATOR STEP - UP TRANSFORMER | Transformer | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7417 | 0.9225 | 0.9225 | g_safe | [5 empty] | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | gsut_uat | gsut_uat | gsut_uat | query | gsut_uat¦stg | match | true | false | 11 | 64 | 43.6949 | 0.5626 | 0.0221 | 0.0166 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering |  | 2025-01-23 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAT-150636 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER (STG) | SCHEMATIC DIAGRAM | GENERATOR STEP - UP TRANSFORMER |  |  |  | SCHEMATIC DIAGRAM for GENERATOR STEP - UP TRANSFORMER | Transformer | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦step¦stg¦transformer¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7417 | 0.9225 | 0.9225 | g_safe | [5 empty] | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | gsut_uat | gsut_uat | gsut_uat | query | gsut_uat¦stg | match | true | false | 10 | 35 | 48.5867 | 0.6022 | 0.0248 | 0.0186 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering |  | 2025-01-23 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BBT-150651 | SIZING CALCULATION - UNIT AUXILIARY TRANSFORMER | Calculation sheet | UNIT AUXILIARY TRANSFORMER |  |  |  | Calculation sheet for UNIT AUXILIARY TRANSFORMER | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6349 | 0.5405 | 0.5405 | g_safe | [5 empty] | SKIP | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gsut_uat |  | gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 2 | 28.0819 | 0.6079 | 0.0325 | 0.0325 | hybrid | structured_preferred | gsut_uat | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BBT-150661 | TECHNICAL SPECIFICATION - UNIT AUXILIARY TRANSFORMER | Technical Specification | UNIT AUXILIARY TRANSFORMER |  |  |  | Technical Specification for UNIT AUXILIARY TRANSFORMER | Transformer | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7178 | 0.5654 | 0.5654 | g_safe | [5 empty] | FA | 2PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-04-16 | procurement | procurement | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 2 | 1 | 35.1702 | 0.6843 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gsut_uat | procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BBT-150671 | OUTLINE DRAWING - UNIT AUXILIARY TRANSFORMER | Outline Drawing | UNIT AUXILIARY TRANSFORMER |  |  |  | Outline Drawing for UNIT AUXILIARY TRANSFORMER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5652 | 0.6362 | 0.6362 | g_safe | [5 empty] | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 169 | 178 | 10.7524 | 0.4523 | 0.0086 | 0.0051 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BBT-150681 | SCHEMATIC DIAGRAM - UNIT AUXILIARY TRANSFORMER | SCHEMATIC DIAGRAM | UNIT AUXILIARY TRANSFORMER |  |  |  | SCHEMATIC DIAGRAM for UNIT AUXILIARY TRANSFORMER | Transformer | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7293 | 0.9188 | 0.9188 | g_safe | [5 empty] | FA | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | design_drawing | civil_design | compatible | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 13 | 8 | 28.0819 | 0.6295 | 0.0284 | 0.0213 | hybrid | structured_phase_gap | gsut_uat | system_design¦engineering |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAA-150701 | SIZING CALCULATION - GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | Calculation sheet | GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | Electrical System |  |  | Calculation sheet for GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | breaker¦busduct¦circuit¦generator¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6534 | 0.5460 | 0.5460 | g_safe | [5 empty] | SKIP | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 16 | 1 | 4.5485 | 0.5316 | 0.0296 | 0.0296 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAC-150711 | TECHNICAL SPECIFICATION - GENERATOR CIRCUIT BREAKER | Technical Specification | GENERATOR CIRCUIT BREAKER |  |  |  | Technical Specification for GENERATOR CIRCUIT BREAKER | GENERATOR CIRCUIT BREAKER | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | breaker¦circuit¦generator |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.8684 | 0.6980 | 0.6980 | g_safe | [5 empty] | FA | 1PF6500W86A02P | (GT GCB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2007-05-31 | 2008-03-31 | procurement | procurement | match |  |  |  |  | electrical¦gtg | query_unscoped | false | false | 1 | 1 | 43.7256 | 0.7168 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAC-150721 | OUTLINE DRAWING - GENERATOR CIRCUIT BREAKER | Outline Drawing | GENERATOR CIRCUIT BREAKER |  |  |  | Outline Drawing for GENERATOR CIRCUIT BREAKER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | breaker¦circuit¦generator |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5975 | 0.6459 | 0.6459 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | false | 475 | 1135 | 3.8574 | 0.4038 | 0.0027 | 0.0020 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAC-150731 | SCHEMATIC DIAGRAM - GENERATOR CIRCUIT BREAKER | SCHEMATIC DIAGRAM | GENERATOR CIRCUIT BREAKER |  |  |  | SCHEMATIC DIAGRAM for GENERATOR CIRCUIT BREAKER | GENERATOR CIRCUIT BREAKER | Schematic diagram | 1 | start+8M<=FA<=start+8M+2M | FA ∈ [start+240d, start+300d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | breaker¦circuit¦generator |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9701 | 0.9910 | 0.9910 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible |  |  |  |  | hrsg | query_unscoped | false | false | 39 | 912 | 13.0682 | 0.4248 | 0.0111 | 0.0063 | hybrid | structured_no_system |  | system_design¦engineering |  | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAA-150751 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR GTG UNIT | Technical Specification | ISOLATED PHASE BUSDUCT | Electrical System |  |  | Technical Specification for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8742 | 0.6123 | 0.6123 | g_ambig | generic_ok | 0.90 |  | 1 | The only competing specific rule is for the GT air intake filter system, which is unrelated to an isolated phase busduct technical specification. | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | true | false | 1 | 2 | 70.0833 | 0.7261 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAA-150752 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR STG UNIT | Technical Specification | ISOLATED PHASE BUSDUCT | Electrical System |  |  | Technical Specification for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8742 | 0.6123 | 0.6123 | g_safe | [5 empty] | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | true | false | 1 | 2 | 70.0833 | 0.7331 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150761 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | GENERAL ARRANGEMENT DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | GENERAL ARRANGEMENT DRAWING for ISOLATED PHASE BUSDUCT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6165 | 0.8850 | 0.8850 | g_ambig | generic_ok | 0.88 |  | 3 | The document is a GA for isolated phase busduct, while the competing specific rules are for GT intake/exhaust systems or GTG auxiliary foundations. | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | true | 103 | 1010 | 13.4438 | 0.4882 | 0.0071 | 0.0042 | hybrid | structured_phase_gap | electrical | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150762 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | GENERAL ARRANGEMENT DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | GENERAL ARRANGEMENT DRAWING for ISOLATED PHASE BUSDUCT |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.6165 | 0.8850 | 0.8850 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | true | 115 | 861 | 13.4438 | 0.4783 | 0.0068 | 0.0041 | hybrid | structured_phase_gap | electrical | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150766 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | CONNECTION DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | CONNECTION DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8683 | 0.8205 | 0.8205 | g_ambig | generic_ok | 0.84 |  | 13 | The competing specific rules are for GT foundations, FM200, impulse/air tubing, etc., not for isolated phase busduct connection drawings. | FA | 2EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-01 | 2007-08-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 2 | 5 | 7.9515 | 0.5506 | 0.0315 | 0.0236 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-10-28 | 2024-11-27 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-10 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150767 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | CONNECTION DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | CONNECTION DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8683 | 0.8205 | 0.8205 | g_ambig | generic_ok | 0.86 |  | 1 | The specific rule is for an STG TCS/TPS cabinet internal arrangement drawing, which does not match an isolated phase busduct connection drawing. | FA | 2EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-01 | 2007-08-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 2 | 7 | 6.8729 | 0.5106 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-10-28 | 2024-11-27 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-10 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150771 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | PRESSURIZATION PANEL DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | PRESSURIZATION PANEL DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7627 | 0.6488 | 0.6488 | g_ambig | generic_ok | 0.72 |  | 13 | A pressurization panel drawing for isolated phase busduct does not clearly fall under the listed GT foundation/FM200/impulse/air tubing specific rules. | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 5 | 2 | 7.8455 | 0.5472 | 0.0315 | 0.0236 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150772 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | PRESSURIZATION PANEL DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | PRESSURIZATION PANEL DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Connection DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7627 | 0.6488 | 0.6488 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG TCS/TPS cabinet internal arrangement, not for isolated phase busduct pressurization panel. | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 5 | 1 | 6.7830 | 0.5021 | 0.0318 | 0.0238 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150776 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | Detail Drawing | ISOLATED PHASE BUSDUCT | Electrical System |  |  | Detail Drawing for GTG | Isolated Phase Bus | Foundation detail draWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7482 | 0.6911 | 0.6911 | g_ambig | generic_ok | 0.85 |  | 31 | All competing specifics are GT/LEB/foundation reinforcement details, which do not target isolated phase busduct detail drawings. | FA | 2EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-01 | 2007-08-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 2 | 7 | 7.9515 | 0.5498 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-10-28 | 2024-11-27 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-10 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150777 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | Detail Drawing | ISOLATED PHASE BUSDUCT | Electrical System |  |  | Detail Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7167 | 0.7750 | 0.7750 | [6 empty] | FA | 2EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-01 | 2007-08-30 | design_drawing | civil_design | compatible | electrical | stg | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 2 | 7 | 6.8729 | 0.5332 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150781 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | STEEL SUPPORT STRUCTURE DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | STEEL SUPPORT STRUCTURE DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Support DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦gas¦generator¦gtg¦isolated¦phase¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7793 | 0.7938 | 0.7938 | g_ambig | generic_ok | 0.85 |  | 13 | The competing specific rules are for GT foundations, piping, FM200, etc., not for isolated phase busduct steel support structure. | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 1 | 16.5639 | 0.5688 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150782 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | STEEL SUPPORT STRUCTURE DRAWING | ISOLATED PHASE BUSDUCT | Electrical System |  |  | STEEL SUPPORT STRUCTURE DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | Support DraWing | 1 | start+6M<=FA<=start+6M+2M | FA ∈ [start+180d, start+240d] | rule_query | drawing | drawing | drawing | drawing | busduct¦generator¦isolated¦phase¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7793 | 0.7938 | 0.7938 | g_ambig | generic_ok | 0.90 |  | 1 | The competing specific rule is for STG TCS/TPS cabinet internal arrangement, unrelated to isolated phase busduct support structure. | FA | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 4 | 15.5014 | 0.5267 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BB-150801 | TECHNICAL SPECIFICATION - MV SWITCHGEAR | Technical Specification | Medium Voltage SWITCHGEAR |  |  |  | Technical Specification for Medium Voltage SWITCHGEAR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | medium¦switchgear¦voltage |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6677 | 0.6670 | 0.4669 | g_safe | [5 empty] | FA | 0EF6500W70A01.2 | (MV SWGR) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries |  | 2007-03-30 | procurement | procurement | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | true | false | 1 | 1 | 44.7985 | 0.6398 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_score_medium;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150811 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #1 | Single Line Diagram | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | g_ambig | uncertain | 0.55 |  | 5 | The document is a 13.8kV GTG switchgear SLD, but the competing specifics are GT auxiliary/MCC/DC/AC distribution/generator circuit SLDs and it's unclear which category this switchgear SLD belongs to. | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 29 | 2441 | 14.8839 | 0.4163 | 0.0116 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150812 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #2 | Single Line Diagram | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | g_ambig | uncertain | 0.55 |  | 5 | The document is a 13.8kV GTG switchgear SLD, but the competing specifics are GT auxiliary/MCC/DC/AC distribution/generator circuit SLDs and it's unclear which category this switchgear SLD belongs to. | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 29 | 2378 | 14.8839 | 0.4184 | 0.0116 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150813 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #3 | Single Line Diagram | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | g_ambig | uncertain | 0.55 |  | 5 | The document is a 13.8kV GTG switchgear SLD, but the competing specifics are GT auxiliary/MCC/DC/AC distribution/generator circuit SLDs and it's unclear which category this switchgear SLD belongs to. | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 29 | 2247 | 14.8839 | 0.4174 | 0.0117 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150814 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #4 | Single Line Diagram | SWITCHGEAR |  |  |  | Single Line Diagram for SWITCHGEAR |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦switchgear¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8145 | 0.9444 | 0.9444 | g_ambig | uncertain | 0.55 |  | 5 | The document is a 13.8kV GTG switchgear SLD, but the competing specifics are GT auxiliary/MCC/DC/AC distribution/generator circuit SLDs and it's unclear which category this switchgear SLD belongs to. | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 29 | 2338 | 14.8839 | 0.4187 | 0.0117 | 0.0070 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150815 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #5 | Single Line Diagram | Gas Turbine Generator |  |  |  | Single Line Diagram for GTG |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7837 | 0.9351 | 0.9351 | g_ambig | use_specific | 0.78 | GT - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | 5 | A generator/medium-voltage SLD aligns directly with the generator circuit single line diagram specific rule. | SKIP | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 1 | 5.8467 | 0.5706 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150816 | SINGLE LINE DIAGRAM – 13.8kV COMMON SWITCHGEAR | Single Line Diagram | MV/LV Switchgear |  |  |  | Single Line Diagram for MV/LV Switchgear |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 36 | 483 | 15.9270 | 0.4316 | 0.0123 | 0.0074 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BB-150821 | OUTLINE DRAWING - MV SWITCHGEAR | Outline Drawing | Medium Voltage SWITCHGEAR |  |  |  | Outline Drawing for Medium Voltage SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | medium¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5824 | 0.6414 | 0.6414 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 500 | 353 | 5.3193 | 0.4383 | 0.0042 | 0.0025 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BB-150831 | WIRING DIAGRAM - MV SWITCHGEAR | WIRING DIAGRAM | Medium Voltage SWITCHGEAR |  |  |  | WIRING DIAGRAM for Medium Voltage SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | medium¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6073 | 0.6488 | 0.6488 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 33 | 319 | 14.8839 | 0.4628 | 0.0134 | 0.0080 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BB-150836 | DRAWINGS - HTS | DRAWINGS |  |  |  |  | DRAWINGS | [5 empty] | rule_query | drawing |  | drawing | [6 empty] | query_unscoped | no_match | [12 empty] | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | design_drawing | system_design | compatible |  |  |  |  | hrsg | query_unscoped | false | false | 3792 | 1 |  | 0.4343 | 0.0167 | 0.0094 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150901 | TECHNICAL SPECIFICATION - LV SWITCHGEAR | Technical Specification | Low Voltage SWITCHGEAR |  |  |  | Technical Specification for Low Voltage SWITCHGEAR |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | low¦switchgear¦voltage |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6637 | 0.6658 | 0.4660 | g_safe | [5 empty] | FA | 0EF6500W70A01.3 | (LV SWGR) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries |  | 2007-03-30 | procurement | procurement | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | true | false | 1 | 1 | 43.6145 | 0.6144 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_score_medium;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150902 | TECHNICAL SPECIFICATION - 13.8/0.48kV MOLD TRANSFORMER | Technical Specification | GSUT/UAT Transformer |  |  |  | Technical Specification for GSUT/UAT Transformer | Transformer | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | gsut¦transformer¦uat |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7069 | 0.5621 | 0.5621 | g_safe | [5 empty] | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | procurement | procurement | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 1 | 23.3169 | 0.6508 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | gsut_uat | procurement |  | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150903 | TECHNICAL SPECIFICATION - 480V NON SEGREGATED PHASE BUS DUCT | Technical Specification | NON SEGREGATED PHASE BUS |  |  |  | Technical Specification for NON SEGREGATED PHASE BUS | Isolated Phase Bus | Technical Specification With Data sheet | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | specification | specification | technical_specification | technical_specification | bus¦non¦phase¦segregated |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8229 | 0.5969 | 0.5969 | g_safe | [5 empty] | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | false | 1 | 3 | 27.2976 | 0.6306 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150911 | SINGLE LINE DIAGRAM - 480V GTG/HRSG SWITCHGEAR | Single Line Diagram | Gas Turbine Generator/Heat Recovery Steam Generator |  |  |  | Single Line Diagram for Gas Turbine Generator/Heat Recovery Steam Generator |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6958 | 0.9088 | 0.9088 | g_ambig | uncertain | 0.50 |  | 8 | A 480V GTG/HRSG switchgear SLD could fall under GT or HRSG electrical SLD specifics, but the exact intended specific category is not determinable from the title alone. | SKIP | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | gtg¦hrsg |  | gtg¦hrsg | query | hrsg | match | true | false | 1 | 1 | 24.4862 | 0.6271 | 0.0328 | 0.0328 | hybrid | structured_preferred | gtg¦hrsg | system_design¦engineering | 9 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150912 | SINGLE LINE DIAGRAM - 480V STG/ACC SWITCHGEAR | Single Line Diagram | Steam Turbine Generator/Air Cooled Condenser |  |  |  | Single Line Diagram for Steam Turbine Generator/Air Cooled Condenser |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | acc¦air¦condenser¦cooled¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7203 | 0.9161 | 0.9161 | g_safe | [5 empty] | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | acc¦stg |  | acc¦stg | query | stg | match | true | false | 1 | 2 | 5.6714 | 0.6073 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc¦stg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150913 | SINGLE LINE DIAGRAM - 480V COMMON SWITCHGEAR | Single Line Diagram | MV/LV Switchgear |  |  |  | Single Line Diagram for MV/LV Switchgear |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 36 | 243 | 15.9270 | 0.4589 | 0.0137 | 0.0082 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150914 | SINGLE LINE DIAGRAM - 480V WT SWITCHGEAR | Single Line Diagram | MV/LV Switchgear |  |  |  | Single Line Diagram for MV/LV Switchgear |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 37 | 195 | 14.8839 | 0.4769 | 0.0142 | 0.0085 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150915 | SINGLE LINE DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | Single Line Diagram | MV/LV Switchgear |  |  |  | Single Line Diagram for MV/LV Switchgear |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | fire_protection¦switchgear |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 39 | 332 | 14.8839 | 0.4564 | 0.0127 | 0.0076 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150916 | SINGLE LINE DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | Single Line Diagram | MV/LV Switchgear |  |  |  | Single Line Diagram for MV/LV Switchgear |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 37 | 748 | 14.8839 | 0.4426 | 0.0115 | 0.0069 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150917 | SINGLE LINE DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | Single Line Diagram | MV/LV Switchgear |  |  |  | Single Line Diagram for MV/LV Switchgear |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 38 | 824 | 14.8839 | 0.4445 | 0.0113 | 0.0068 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150918 | SINGLE LINE DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | Single Line Diagram | MV/LV Switchgear |  |  |  | Single Line Diagram for MV/LV Switchgear |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7621 | 0.9286 | 0.9286 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 36 | 350 | 15.9270 | 0.4512 | 0.0129 | 0.0077 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150931 | OUTLINE DRAWING - 480V GTG/HRSG SWITCHGEAR | Outline Drawing | Gas Turbine Generator/Heat Recovery Steam Generator |  |  |  | Outline Drawing for Gas Turbine Generator/Heat Recovery Steam Generator |  | GT - OUTLINE DRAWING OF VALVES FOR GAS TURBINE PART | 1 | start+345D<=FA<=start+345D+2M | FA ∈ [start+345d, start+405d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | gas¦generator¦gtg¦heat¦hrsg¦recovery¦steam¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.7086 | 0.6792 | 0.6792 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match | gtg¦hrsg | gtg | gtg¦hrsg | query | hrsg | match | true | false | 1 | 5 | 15.2754 | 0.5961 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg¦hrsg | system_design | 9 | 2025-02-27 | 2025-03-29 | 2025-04-28 | 2025-05-13 | 2025-05-28 | 2025-06-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150932 | OUTLINE DRAWING - 480V STG/ACC SWITCHGEAR | Outline Drawing | Steam Turbine Generator/Air Cooled Condenser |  |  |  | Outline Drawing for Steam Turbine Generator/Air Cooled Condenser |  | ACC - Steam Jet Air Ejector Outline DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | acc¦air¦condenser¦cooled¦generator¦steam¦stg¦turbine | acc | scoped | match | match | match | passed |  | 0.7143 | 0.6790 | 0.7037 | 0.7037 | [6 empty] | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | acc¦stg | acc | acc¦stg | query | stg | match | true | false | 1 | 2 | 5.6714 | 0.5982 | 0.0325 | 0.0325 | hybrid | structured_preferred | acc¦stg | system_design | 3 | 2024-10-16 | 2024-11-15 | 2024-12-15 | 2024-12-30 | 2025-01-14 | 2025-01-29 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150933 | OUTLINE DRAWING - 480V COMMON SWITCHGEAR | Outline Drawing | MV/LV Switchgear |  |  |  | Outline Drawing for MV/LV Switchgear | Substation | Outline DraWing (for MV / LV AC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.7942 | 0.6758 | 0.6758 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 478 | 393 | 6.3624 | 0.4310 | 0.0041 | 0.0024 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150934 | OUTLINE DRAWING - 480V WT SWITCHGEAR | Outline Drawing | MV/LV Switchgear |  |  |  | Outline Drawing for MV/LV Switchgear | Substation | Outline DraWing (for MV / LV AC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6250 | 0.7942 | 0.6758 | 0.6758 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 478 | 229 | 5.3193 | 0.4545 | 0.0053 | 0.0032 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150935 | OUTLINE DRAWING - 480V FIRE BRIGADE SWITCHGEAR | Outline Drawing | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | fire_protection¦switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | g_safe | [5 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | mv_lv |  | mv_lv | query | fire_fighting¦hvac | mismatch | true | false | 54 | 159 | 8.7940 | 0.4752 | 0.0133 | 0.0033 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150936 | OUTLINE DRAWING - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | Outline Drawing | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | g_safe | [5 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 526 | 519 | 2.2471 | 0.4450 | 0.0034 | 0.0021 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150937 | OUTLINE DRAWING - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | Outline Drawing | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | g_safe | [5 empty] | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 480 | 1015 | 4.8538 | 0.4151 | 0.0028 | 0.0017 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150938 | OUTLINE DRAWING - 480V COMMON ESSENTIAL SWITCHGEAR | Outline Drawing | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5613 | 0.6350 | 0.6350 | g_safe | [5 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 507 | 360 | 3.3134 | 0.4483 | 0.0041 | 0.0025 | hybrid | structured_phase_gap | mv_lv | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150939 | OUTLINE DRAWING - 13.8/0.48kV MOLD TRANSFORMER | Outline Drawing | TRANSFORMER |  |  |  | Outline Drawing for TRANSFORMER |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | transformer |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6166 | 0.6516 | 0.6516 | g_safe | [5 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match | gsut_uat |  | gsut_uat | query |  | activity_unscoped | true | true | 128 | 1011 | 8.5282 | 0.3570 | 0.0063 | 0.0038 | hybrid | structured_phase_gap | gsut_uat | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150940 | OUTLINE DRAWING - 480V NON SEGREGATED PHASE BUS DUCT | Outline Drawing | NON SEGREGATED PHASE BUS DUCT |  |  |  | Outline Drawing for NON SEGREGATED PHASE BUS DUCT |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | bus¦duct¦non¦phase¦segregated |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5134 | 0.6207 | 0.6207 | g_safe | [5 empty] | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | system_design | system_design | match |  |  |  |  | hrsg | query_unscoped | false | false | 655 | 188 | 2.0974 | 0.4291 | 0.0054 | 0.0041 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150951 | WIRING DIAGRAM - 480V GTG/HRSG SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | HRSG - Wiring Diagram | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | title | diagram | diagram | wiring_diagram | wiring_diagram | generator¦gtg¦heat¦hrsg¦recovery¦steam¦switchgear | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.7507 | 0.9252 | 0.9252 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv | hrsg | mv_lv | query |  | activity_unscoped | true | true | 22 | 2268 | 14.8839 | 0.4540 | 0.0126 | 0.0076 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150952 | WIRING DIAGRAM - 480V STG/ACC SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | ACC - Wiring Diagram | 1 | start+289D<=FA<=start+289D+2M | FA ∈ [start+289d, start+349d] | title | diagram | diagram | wiring_diagram | wiring_diagram | acc¦air¦condenser¦cooled¦stg¦switchgear | acc | scoped | match | match | match | passed |  | 1.0000 | 0.6387 | 0.8916 | 0.8916 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv | acc | mv_lv | query |  | activity_unscoped | true | true | 22 | 1080 | 14.8839 | 0.4334 | 0.0131 | 0.0078 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150953 | WIRING DIAGRAM - 480V COMMON SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 20 | 453 | 15.9270 | 0.4610 | 0.0144 | 0.0087 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150954 | WIRING DIAGRAM - 480V WT SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 22 | 519 | 14.8839 | 0.4544 | 0.0139 | 0.0084 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150955 | WIRING DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | fire_protection¦switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 24 | 805 | 14.8839 | 0.4330 | 0.0131 | 0.0078 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150956 | WIRING DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 22 | 1059 | 14.8839 | 0.4386 | 0.0131 | 0.0079 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150957 | WIRING DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 23 | 1076 | 14.8839 | 0.4378 | 0.0129 | 0.0078 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150958 | WIRING DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | switchgear |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6528 | 0.6625 | 0.6625 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | mv_lv |  | mv_lv | query |  | activity_unscoped | true | true | 20 | 647 | 15.9270 | 0.4449 | 0.0139 | 0.0083 | hybrid | structured_phase_gap | mv_lv | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BT-151001 | SIZING CALCULATION - DC & AC UPS SYSTEM | Calculation sheet |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Calculation sheet for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Substation | Sizing Calculation_DC & UPS System | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.8623 | 0.8420 | 0.8420 | g_safe | [5 empty] | SKIP | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-09-03 |  | civil_design | civil_design | match | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | true | 546 | 36 | 3.8665 | 0.4660 | 0.0121 | 0.0072 | hybrid | structured_phase_gap | dc_ups | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BT-151011 | TECHNICAL SPECIFICATION - DC & AC UPS SYSTEM | Technical Specification |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Technical Specification for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4900 | 0.4970 | 0.4970 | g_safe | [5 empty] | FA | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | procurement | procurement | match | dc_ups |  | dc_ups | query | dc_ups¦electrical | match | true | false | 1 | 1 | 55.3898 | 0.7263 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dc_ups | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151021 | SINGLE LINE DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | Single Line Diagram |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Single Line Diagram for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6777 | 0.9033 | 0.9033 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups |  | dc_ups | query |  | activity_unscoped | true | true | 16 | 108 | 19.3162 | 0.4931 | 0.0191 | 0.0115 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151026 | SINGLE LINE DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | Single Line Diagram |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Single Line Diagram for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6777 | 0.9033 | 0.9033 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups |  | dc_ups | query |  | activity_unscoped | true | true | 16 | 110 | 19.3162 | 0.4970 | 0.0190 | 0.0114 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151031 | SINGLE LINE DIAGRAM - COMMON DC & UPS SYSTEM | Single Line Diagram |  | Direct Current and Uninterruptible Power Supply SYSTEM |  |  | Single Line Diagram for Direct Current and Uninterruptible Power Supply SYSTEM |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6920 | 0.9076 | 0.9076 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups |  | dc_ups | query |  | activity_unscoped | true | true | 14 | 46 | 22.7239 | 0.5173 | 0.0229 | 0.0138 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151041 | OUTLINE DRAWING - BLOCK #1 DC & AC UPS SYSTEM | Outline Drawing |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | Outline DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6061 | 0.7418 | 0.7418 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups | electrical | dc_ups | query |  | activity_unscoped | true | true | 112 | 125 | 9.7516 | 0.4773 | 0.0112 | 0.0067 | hybrid | structured_phase_gap | dc_ups | system_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151046 | OUTLINE DRAWING - BLOCK #2 DC & AC UPS SYSTEM | Outline Drawing |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | Outline DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6061 | 0.7418 | 0.7418 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups | electrical | dc_ups | query |  | activity_unscoped | true | true | 142 | 149 | 9.7516 | 0.4772 | 0.0097 | 0.0058 | hybrid | structured_phase_gap | dc_ups | system_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151051 | OUTLINE DRAWING - COMMON DC & AC UPS SYSTEM | Outline Drawing |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | Outline DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6061 | 0.7418 | 0.7418 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dc_ups | electrical | dc_ups | query |  | activity_unscoped | true | true | 52 | 58 | 10.7947 | 0.4895 | 0.0174 | 0.0104 | hybrid | structured_phase_gap | dc_ups | system_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151061 | SCHEMATIC DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | Schematic Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6189 | 0.7457 | 0.7457 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | dc_ups | electrical | dc_ups | query |  | activity_unscoped | true | true | 12 | 108 | 19.3162 | 0.4693 | 0.0198 | 0.0089 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151066 | SCHEMATIC DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | Schematic Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6189 | 0.7457 | 0.7457 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | dc_ups | electrical | dc_ups | query |  | activity_unscoped | true | true | 12 | 125 | 19.3162 | 0.4651 | 0.0193 | 0.0087 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151071 | SCHEMATIC DIAGRAM - COMMON DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for DIRECT CURRENT & AC Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | Schematic Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | current¦direct¦power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6189 | 0.7457 | 0.7457 | g_safe | [5 empty] | SKIP | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | dc_ups | electrical | dc_ups | query |  | activity_unscoped | true | true | 12 | 63 | 20.3593 | 0.4756 | 0.0220 | 0.0099 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CHB-151101 | TECHNICAL SPECIFICATION - PROTECTION RELAY PANEL | Technical Specification |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | [6 empty] | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 1 | 30.2650 | 0.6876 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151111 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | Outline Drawing | Gas Turbine Generator | FAULT MONITORING SYSTEM |  |  | Outline Drawing for GTG |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6153 | 0.6513 | 0.6513 | g_ambig | generic_ok | 0.75 |  | 6 | The competing specifics are for motors/filters/pumps/valves/receptacles, while this is an outline drawing for a protection relay panel & FMS, so none clearly match. | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 5.8467 | 0.5658 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151112 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR STG UNIT | Outline Drawing | Steam Turbine & Generator | FAULT MONITORING SYSTEM |  |  | Outline Drawing for STG |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6011 | 0.6470 | 0.6470 | g_ambig | uncertain | 0.55 |  | 3 | A protection relay panel & FMS for STG could be considered a steam turbine auxiliary, but the specific rule wording is too broad to confirm applicability. | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 5.6714 | 0.5809 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CHB-151121 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | WIRING DIAGRAM | Gas Turbine Generator | FAULT MONITORING SYSTEM |  |  | WIRING DIAGRAM for FAULT MONITORING SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | fault¦gas¦generator¦gtg¦monitoring¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6040 | 0.6479 | 0.6479 | g_ambig | generic_ok | 0.80 |  | 3 | The competing specifics are for GT terminal boxes and air intake filter LCP wiring, not for a protection relay panel & FMS wiring diagram. | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 5.8467 | 0.5754 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CHB-151122 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR STG UNIT | WIRING DIAGRAM | Steam Turbine & Generator | FAULT MONITORING SYSTEM |  |  | WIRING DIAGRAM for FAULT MONITORING SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | fault¦generator¦monitoring¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6040 | 0.6479 | 0.6479 | g_safe | [5 empty] | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 3 | 5.6714 | 0.5744 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151131 | CONFIGURATION DIAGRM - FAULT MONITORING SYSTEM | CONFIGURATION DIAGRM |  | FAULT MONITORING SYSTEM |  |  | CONFIGURATION DIAGRM for FAULT MONITORING SYSTEM | [5 empty] | rule_query | other | other | configuration_diagrm | vms_system_configuration | fault¦monitoring |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.4397 | 0.5986 | 0.5986 | [7 empty] | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | feedwater | query_unscoped | false | false | 266 | 8 | 1.2267 | 0.4333 | 0.0178 | 0.0133 | hybrid | structured_no_system |  | system_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CFA-151161 | TECHNICAL SPECIFICATION - METERING PANEL | Technical Specification |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | [6 empty] | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 3 | 20.5628 | 0.6117 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | procurement |  | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CFA-151171 | OUTLINE DRAWING - METERING PANEL | Outline Drawing |  |  |  |  | Outline Drawing |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | outline_drawing | outline_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6885 | 0.6732 | 0.6732 | [6 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 547 | 85 | 2.5734 | 0.4628 | 0.0085 | 0.0051 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CFA-151181 | WIRING DIAGRAM - METERING PANEL | WIRING DIAGRAM |  |  |  |  | WIRING DIAGRAM |  | ACC - Wiring Diagram | 1 | start+289D<=FA<=start+289D+2M | FA ∈ [start+289d, start+349d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram |  | acc | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6629 | 0.6655 | 0.6655 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | true | 6 | 312 | 14.8839 | 0.4633 | 0.0178 | 0.0054 | hybrid | structured_phase_gap | acc | system_design¦engineering | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YQ02-P0ZEN-152001 | TYPICAL INSTALLATION DRAWING - RACEWAY | TYPICAL INSTALLATION DRAWING |  |  |  |  | TYPICAL INSTALLATION DRAWING |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | [6 empty] | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 3537 | 7 |  | 0.4680 | 0.0152 | 0.0086 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152002 | TECHNICAL SPECIFICATION - CABLE TRAY AND ACCESSORIES | Technical Specification |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | [6 empty] | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | true | false | 4 | 1 | 15.3878 | 0.5457 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | procurement |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YD16-P0ZEN-152003 | MAIN CABLE ROUTE PLAN | Plan |  |  |  |  | Plan |  | MAIN CABLE ROUTE PLAN OVERALL | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.9548 | 0.8464 | 0.5925 | [6 empty] | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 3 | 2 | 9.2252 | 0.5276 | 0.0320 | 0.0180 | hybrid | structured_no_system |  |  |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152004 | 380KV CABLE ROUTE PLAN | Plan |  |  |  |  | Plan |  | Cable Conduit Plan | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6495 | 0.6615 | 0.4631 | [6 empty] | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 3 | 1 | 9.2252 | 0.6073 | 0.0323 | 0.0181 | hybrid | structured_no_system |  |  |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152005 | CABLE TRAY LAYOUT FOR CENTRAL CONTROL BUILDING | CABLE TRAY LAYOUT |  |  | Central Control Building |  | CABLE TRAY LAYOUT for Central Control Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7557 | 0.5767 | 0.5767 | g_safe | [5 empty] | SKIP | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 20 | 4 | 18.3850 | 0.5885 | 0.0281 | 0.0169 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152006 | CABLE TRAY LAYOUT FOR GTG #1,2 LEB | CABLE TRAY LAYOUT | Gas Turbine Generator |  | Local Electrical Building |  | CABLE TRAY LAYOUT for Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7507 | 0.5752 | 0.5752 | g_ambig | generic_ok | 0.80 |  | 2 | The competing specifics are for generator foundation embedded metals and performance heater foundation layouts, not for LEB cable tray layout. | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 7 | 1 | 12.5474 | 0.6463 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152007 | CABLE TRAY LAYOUT FOR GTG #3,4,5 LEB | CABLE TRAY LAYOUT | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | CABLE TRAY LAYOUT for Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7507 | 0.5752 | 0.5752 | g_ambig | generic_ok | 0.80 |  | 2 | The competing specifics relate to foundation embedded metals/performance heater foundation, which do not clearly match an LEB cable tray layout. | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 18 | 1 | 13.1061 | 0.6441 | 0.0292 | 0.0292 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152008 | CABLE TRAY LAYOUT FOR ST #1 LEB | CABLE TRAY LAYOUT | Steam Turbine #1 |  | Local Electrical Building |  | CABLE TRAY LAYOUT for Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7507 | 0.5752 | 0.5752 | g_ambig | generic_ok | 0.80 |  | 1 | The competing specific rule is for STG foundation layout, whereas the document is a cable tray layout for ST #1 LEB. | SKIP | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | gsut_uat¦stg | match | true | false | 20 | 1 | 6.4758 | 0.5800 | 0.0289 | 0.0289 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152009 | CABLE TRAY LAYOUT FOR ST #2 LEB | CABLE TRAY LAYOUT | Steam Turbine #2 |  | Local Electrical Building |  | CABLE TRAY LAYOUT for Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7507 | 0.5752 | 0.5752 | g_ambig | generic_ok | 0.80 |  | 1 | The competing specific rule is for STG foundation layout, whereas the document is a cable tray layout for ST #2 LEB. | SKIP | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | gsut_uat¦stg | match | true | false | 20 | 5 | 7.4988 | 0.5698 | 0.0279 | 0.0279 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152010 | CABLE TRAY LAYOUT FOR ST BUILDING | CABLE TRAY LAYOUT | Steam Turbine & Generator |  | Steam Turbine Building |  | CABLE TRAY LAYOUT for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6277 | 0.6083 | 0.6083 | [6 empty] | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 10 | 1 | 9.1673 | 0.6281 | 0.0307 | 0.0307 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152011 | CABLE TRAY LAYOUT FOR WATER TREATMENT BUILDING | CABLE TRAY LAYOUT |  | Water Treatment System | Water Treatment Building |  | CABLE TRAY LAYOUT for Water Treatment Building | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7500 | 0.8537 | 0.7811 | 0.7811 | [6 empty] | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 7 | 25.5501 | 0.5624 | 0.0313 | 0.0313 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152012 | CABLE TRAY LAYOUT FOR FGS ELECTRICAL BUILDING | CABLE TRAY LAYOUT |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | CABLE TRAY LAYOUT for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6972 | 0.6758 | 0.6758 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 10 | 4 | 13.7268 | 0.5468 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152013 | CABLE TRAY LAYOUT FOR WORKSHOP & STORAGE BUILDING | CABLE TRAY LAYOUT |  |  | Workshop & Storage Building |  | CABLE TRAY LAYOUT for Workshop & Storage Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6955 | 0.5586 | 0.5586 | g_safe | [5 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 18 | 34 | 16.9020 | 0.4878 | 0.0235 | 0.0176 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152014 | CABLE TRAY LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | CABLE TRAY LAYOUT |  |  | Administration & Social Building |  | CABLE TRAY LAYOUT for Administration & Social Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7055 | 0.5616 | 0.5616 | g_safe | [5 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 17 | 17 | 16.9020 | 0.4958 | 0.0260 | 0.0195 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152015 | CABLE TRAY LAYOUT FOR PIPE RACK | CABLE TRAY LAYOUT |  |  | Pipe Rack |  | CABLE TRAY LAYOUT for Pipe Rack | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7371 | 0.5711 | 0.5711 | g_safe | [5 empty] | SKIP | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 22 | 5 | 20.1089 | 0.6334 | 0.0276 | 0.0207 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152016 | CABLE TRAY LAYOUT FOR AUX LEB | CABLE TRAY LAYOUT |  |  | Local Electrical Building |  | CABLE TRAY LAYOUT for Local Electrical Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7507 | 0.5752 | 0.5752 | g_safe | [5 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 2 | 4 | 16.9020 | 0.5008 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152017 | CABLE TRAY LAYOUT FOR GTG PCC #1,2,3,4,5 | CABLE TRAY LAYOUT | Gas Turbine Generator |  |  |  | CABLE TRAY LAYOUT for GTG | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7399 | 0.5720 | 0.5720 | g_ambig | generic_ok | 0.80 |  | 2 | The competing specifics are for generator foundation embedded metals and performance heater foundation layouts, not for LEB cable tray layout. | SKIP | 2CF1265W16A12.4 | (TCA Cooler) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | 2007-10-30 | 2007-12-29 | design_drawing | civil_design | compatible | gtg |  | gtg | query | fgp¦gtg | match | true | false | 3 | 40 | 13.2698 | 0.5622 | 0.0259 | 0.0194 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152018 | CABLE TRAY LAYOUT FOR TANK SLEEPER AREA | CABLE TRAY LAYOUT | TANK |  |  |  | CABLE TRAY LAYOUT for Tank | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7368 | 0.5710 | 0.5710 | g_safe | [5 empty] | SKIP | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | design_drawing | civil_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | false | 118 | 16 | 10.7403 | 0.5033 | 0.0188 | 0.0106 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152019 | CABLE TRAY LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | CABLE TRAY LAYOUT |  |  |  |  | CABLE TRAY LAYOUT | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.7578 | 0.5773 | 0.5773 | [6 empty] | SKIP | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 125 | 7 | 8.2027 | 0.5441 | 0.0203 | 0.0152 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152020 | CABLE TRAY LAYOUT FOR SECURITY BUILDING | CABLE TRAY LAYOUT |  |  | Security Building |  | CABLE TRAY LAYOUT for Security Building | Substation | Cable Tray & Conduit Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7150 | 0.5645 | 0.5645 | g_safe | [5 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 17 | 10 | 16.9020 | 0.5007 | 0.0273 | 0.0205 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-152052 | CONTROL CABLE CONNECTION DIAGRAM | Diagram |  |  |  |  | Diagram | Substation | Cable Connection Diagram | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7178 | 0.7403 | 0.7403 | [6 empty] | SKIP | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible |  |  |  |  | h2 | query_unscoped | false | false | 13 | 1833 | 12.9352 | 0.3277 | 0.0142 | 0.0080 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152201 | TYPICAL INSTALLATION DRAWING - LIGHTING AND SMALL POWER | DRAWING |  | LIGHTING AND SMALL POWER |  |  | DRAWING for LIGHTING AND SMALL POWER |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8144 | 0.9443 | 0.6610 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical | match | true | false | 7 | 9 | 7.5816 | 0.4445 | 0.0294 | 0.0221 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152202 | TECHNICAL SPECIFICATION - LIGHTING AND SMALL POWER | Technical Specification |  | LIGHTING AND SMALL POWER |  |  | Technical Specification for LIGHTING AND SMALL POWER |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5711 | 0.6380 | 0.6380 | g_safe | [5 empty] | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | true | false | 1 | 1 | 35.2503 | 0.6816 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152203 | ILLUMINATION CALCULATION - CENTRAL CONTROL BUILDING | ILLUMINATION CALCULATION |  |  | Central Control Building |  | ILLUMINATION CALCULATION for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | ccr¦central | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.8104 | 0.9431 | 0.9431 | [6 empty] | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 3 | 4 | 18.3850 | 0.5500 | 0.0315 | 0.0189 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | fi_complete | activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152204 | ILLUMINATION CALCULATION - GTG #1,2 LEB | ILLUMINATION CALCULATION | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | ILLUMINATION CALCULATION for Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.4988 | 0.6163 | 0.6163 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4061 | 0.6352 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152205 | ILLUMINATION CALCULATION - GTG #3,4,5 LEB | ILLUMINATION CALCULATION | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | ILLUMINATION CALCULATION for Gas Turbine Generator #3,4,5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5179 | 0.6220 | 0.6220 | [6 empty] | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 12 | 1 | 13.1061 | 0.6109 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152206 | ILLUMINATION CALCULATION - ST #1 LEB | Calculation sheet |  |  | Local Electrical Building |  | Calculation sheet for Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7687 | 0.7556 | 0.7556 | g_ambig | generic_ok | 0.70 |  | 12 | This is an illumination calculation (not a foundation calculation), so the competing foundation-calculation-specific rules do not clearly apply. | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 3 | 36 | 4.3991 | 0.3290 | 0.0263 | 0.0263 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152207 | ILLUMINATION CALCULATION - ST #2 LEB | Calculation sheet |  |  | Local Electrical Building |  | Calculation sheet for Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7687 | 0.7556 | 0.7556 | g_ambig | generic_ok | 0.70 |  | 12 | This is an illumination calculation (not a foundation calculation), so the competing foundation-calculation-specific rules do not clearly apply. | FI | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | gsut_uat¦stg | match | true | false | 44 | 1 | 1.6779 | 0.4001 | 0.0260 | 0.0260 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152208 | ILLUMINATION CALCULATION - ST BUILDING | Calculation sheet | Steam Turbine & Generator |  | Steam Turbine Building |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 8 | 9.9602 | 0.5483 | 0.0311 | 0.0311 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152209 | ILLUMINATION CALCULATION - FGS ELECTRICAL BUILDING | Calculation sheet |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for Electrical System | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | electrical¦fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8196 | 0.9459 | 0.9459 | g_ambig | generic_ok | 0.75 |  | 2 | The document is an illumination calculation for the FGS electrical building, and the competing specifics are either generic 'Calculation Sheets' or foundation calculation, neither clearly a better equ | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | false | 4 | 3 | 13.7268 | 0.5019 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | fc_earliest | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152210 | ILLUMINATION CALCULATION - ADMINISTRATION | Calculation sheet |  |  | ADMINISTRATION |  | Calculation sheet for ADMINISTRATION | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | administration |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7488 | 0.6446 | 0.6446 | g_safe | [5 empty] | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 3 | 10.8677 | 0.4394 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152211 | ILLUMINATION CALCULATION - SECURITY BUILDING | Calculation sheet |  |  | Security Building |  | Calculation sheet for Security Building | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8153 | 0.9446 | 0.9446 | g_safe | [5 empty] | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 7 | 18 | 4.2752 | 0.4014 | 0.0277 | 0.0166 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152212 | ILLUMINATION CALCULATION - MAIN GATE HOUSE | Calculation sheet |  |  | Security Building |  | Calculation sheet for Security Building | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8153 | 0.9446 | 0.9446 | g_safe | [5 empty] | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 17.1992 | 0.4918 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152213 | ILLUMINATION CALCULATION - SUPPORT BUILDING | Calculation sheet |  |  | Support Building |  | Calculation sheet for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8107 | 0.9432 | 0.9432 | g_safe | [5 empty] | FI | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 44 | 2 | 4.1062 | 0.4477 | 0.0257 | 0.0154 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152214 | ILLUMINATION CALCULATION - X-RAY SEARCHING ROOM | Calculation sheet |  |  | X-RAY SEARCHING ROOM |  | Calculation sheet for X-RAY SEARCHING ROOM | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4786 | 0.4936 | 0.4936 | g_safe | [5 empty] | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match |  |  |  |  | feedwater | query_unscoped | false | false | 1378 | 10 |  | 0.4074 | 0.0150 | 0.0112 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152215 | ILLUMINATION CALCULATION - MAIN GATE HOUSE SUNSHADE | Calculation sheet |  |  | Security Building |  | Calculation sheet for Security Building | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8153 | 0.9446 | 0.9446 | g_safe | [5 empty] | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 4 | 17.1992 | 0.4389 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152216 | ILLUMINATION CALCULATION - FIRE BRIGADE & AUX. LEB | Calculation sheet |  |  | Local Electrical Building |  | Calculation sheet for Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7687 | 0.7556 | 0.7556 | g_ambig | generic_ok | 0.72 |  | 9 | The competing rules are for foundations/drainage calculations, while this document is an illumination calculation for Fire Brigade & Aux. LEB. | FI | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | false | 4 | 4 | 3.1906 | 0.3977 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152217 | ILLUMINATION CALCULATION - WORKSHOP & STORAGE BUILDING | Calculation sheet |  |  | Workshop & Storage Building |  | Calculation sheet for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8265 | 0.9479 | 0.9479 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 31 | 3 | 9.7017 | 0.4597 | 0.0269 | 0.0201 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152218 | ILLUMINATION CALCULATION - H2, CO2, N2 STORAGE SHELTER | Calculation sheet | Hydrogen System |  | Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | Calculation sheet for Hydrogen System | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | hydrogen |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7909 | 0.8206 | 0.8206 | g_safe | [5 empty] | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | h2¦n2 | h2 | h2¦n2 | query | n2 | match | true | false | 3 | 5 | 13.6244 | 0.5801 | 0.0313 | 0.0313 | hybrid | structured_preferred | h2¦n2 | civil_design | 10 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152219 | ILLUMINATION CALCULATION - AIR COMPRESSOR SHELTER | Calculation sheet |  | Compressed Air System | Air Compressor Shelter |  | Calculation sheet for Compressed Air System | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7891 | 0.7967 | 0.7967 | g_safe | [5 empty] | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 2 | 23.8545 | 0.5856 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152220 | ILLUMINATION CALCULATION - DEAERATOR SUPPORT STRUCTURE | Calculation sheet |  |  |  |  | Calculation sheet |  | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7787 | 0.7936 | 0.7936 | [6 empty] | FI | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match |  |  |  |  | feedwater | query_unscoped | false | false | 1096 | 2 |  | 0.5149 | 0.0170 | 0.0127 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-02 | 2024-09-01 | 2024-10-01 | fi_complete | 0.90 |  | false | false | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152221 | ILLUMINATION CALCULATION - FIRE WATER PUMP HOUSE | Calculation sheet |  | Fire Fighting System | Fire Water Pump House |  | Calculation sheet for Fire Fighting System | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fighting¦fire¦fire_protection¦pump | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.6973 | 0.6758 | 0.6758 | [6 empty] | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 2 | 27.4718 | 0.5953 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152222 | ILLUMINATION CALCULATION - WWT & BULK CHEMICAL STORAGE TANK SHELTER | Calculation sheet |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Calculation sheet for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | tank | scoped | match | match | match | passed |  | 0.8571 | 0.8250 | 0.8475 | 0.8475 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 2 | 2 | 28.7086 | 0.5488 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152223 | ILLUMINATION CALCULATION - WATER TREATMENT BUILDING | Calculation sheet |  | Water Treatment System | Water Treatment Building |  | Calculation sheet for Water Treatment System | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9782 | 0.9934 | 0.9934 | [6 empty] | FA | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 6 | 3 | 23.0521 | 0.5700 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152224 | ILLUMINATION CALCULATION - CPP & CPP REGENERATION BUILDING | Calculation sheet |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Calculation sheet for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | condensate¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8134 | 0.8040 | 0.8040 | g_safe | [5 empty] | FI | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | false | 6 | 2 |  | 0.3580 | 0.0313 | 0.0313 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152225 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR STG & HRSG | Calculation sheet | Steam Turbine Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | Chemical Dosing Shelter |  | Calculation sheet for Steam Turbine Generator & Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7452 | 0.6902 | 0.6902 | [6 empty] | FA | 2EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | 2007-09-26 |  | civil_design | civil_design | match | hrsg¦stg¦wts | hrsg | hrsg¦stg¦wts | query | wts | match | true | false | 11 | 4 | 29.9448 | 0.5943 | 0.0297 | 0.0297 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152226 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR HRSG | Calculation sheet | Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Calculation sheet for HRSG |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam¦wts | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7948 | 0.7051 | 0.7051 | [6 empty] | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | hrsg¦wts | hrsg | hrsg¦wts | query | wts | match | true | false | 1 | 5 | 21.1937 | 0.5719 | 0.0318 | 0.0318 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152229 | ILLUMINATION CALCULATION - YARD | Calculation sheet |  |  |  |  | Calculation sheet | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6392 | 0.5418 | 0.5418 | [6 empty] | FA | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | civil_design | civil_design | match |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | false | 3250 | 7 |  | 0.4149 | 0.0152 | 0.0114 | hybrid | structured_no_system |  | civil_design |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152230 | ILLUMINATION CALCULATION – TANK AREA | Calculation sheet |  |  |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | [6 empty] | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | true | false | 500 | 9 | 5.6753 | 0.4692 | 0.0163 | 0.0122 | hybrid | structured_no_system |  | civil_design |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152231 | ILLUMINATION CALCULATION – GTG #1, 2 TRANSFORMER AREA | Calculation sheet | Gas Turbine Generator |  |  |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 6 | 1 | 11.5520 | 0.6173 | 0.0315 | 0.0315 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152232 | ILLUMINATION CALCULATION – GTG #3, 4, 5 TRANSFORMER AREA | Calculation sheet | Gas Turbine Generator |  |  |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 5 | 3 | 11.5824 | 0.6076 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152233 | ILLUMINATION CALCULATION – STG #1, 2 TRANSFORMER AREA | Calculation sheet | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 6 | 2 | 16.9516 | 0.6072 | 0.0313 | 0.0313 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152234 | ILLUMINATION CALCULATION – FUEL GAS SYSTEM AREA | Calculation sheet | Fuel Gas Package | FUEL GAS SYSTEM |  |  | Calculation sheet for FGP | Fuel Gas System | Calculation Sheets | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | title | calculation | calculation | calculation | calculation | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.6496 | 0.7549 | 0.7549 | [6 empty] | FA | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match | fgp | fgp | fgp | query | fgp | match | true | false | 1 | 3 | 16.4735 | 0.5732 | 0.0323 | 0.0323 | hybrid | structured_preferred | fgp | civil_design | 10 | 2024-12-20 | 2025-01-17 | 2025-02-14 | 2025-02-07 | 2025-03-07 | 2025-04-04 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152301 | LIGHTING & SMALL POWER LAYOUT DRAWING - CENTRAL CONTROL BUILDING | Layout Drawing |  | LIGHTING & SMALL POWER | Central Control Building |  | Layout Drawing for Central Control Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7422 | 0.7477 | 0.7477 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 12 | 1 | 2.3394 | 0.5346 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152302 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #1,2 LEB | Layout Drawing | Gas Turbine Generator | LIGHTING & SMALL POWER | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7395 | 0.7468 | 0.7468 | g_ambig | generic_ok | 0.70 |  | 2 | The specific rules relate to GT foundation embedded metals/performance heater foundation layouts, not a lighting & small power layout for GTG LEB. | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 12.5478 | 0.7184 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152303 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #3,4,5 LEB | Layout Drawing | Gas Turbine Generator | LIGHTING & SMALL POWER | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7383 | 0.7465 | 0.7465 | g_ambig | generic_ok | 0.70 |  | 2 | The specific rules relate to GT foundation embedded metals/performance heater foundation layouts, not a lighting & small power layout for GTG LEB. | SKIP | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 4 | 4 | 11.9923 | 0.6686 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152304 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #1 LEB | Layout Drawing | Steam Turbine | LIGHTING & SMALL POWER | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7358 | 0.7457 | 0.7457 | g_ambig | generic_ok | 0.70 |  | 1 | The competing specific rule is for steam turbine generator foundation layout, which is different from a lighting & small power layout drawing. | SKIP | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 10 | 4 | 5.5343 | 0.6057 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152305 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #2 LEB | Layout Drawing | Steam Turbine | LIGHTING & SMALL POWER | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7365 | 0.7459 | 0.7459 | g_ambig | generic_ok | 0.70 |  | 1 | The competing specific rule is for steam turbine generator foundation layout, which is different from a lighting & small power layout drawing. | SKIP | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 11 | 2 | 6.0760 | 0.6083 | 0.0302 | 0.0302 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152306 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST BUILDING | Layout Drawing | Steam Turbine & Generator | LIGHTING & SMALL POWER | Steam Turbine Building |  | Layout Drawing for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6641 | 0.6192 | 0.6192 | [6 empty] | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 11 | 1 | 9.1677 | 0.6622 | 0.0305 | 0.0305 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152307 | LIGHTING & SMALL POWER LAYOUT DRAWING - FGS ELECTRICAL BUILDING | Layout Drawing |  | LIGHTING & SMALL POWER | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7072 | 0.6788 | 0.6788 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 10.8162 | 0.5669 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152308 | LIGHTING & SMALL POWER LAYOUT DRAWING - ADMINISTRATION | Layout Drawing |  | LIGHTING & SMALL POWER | ADMINISTRATION |  | Layout Drawing for ADMINISTRATION | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | administration |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7152 | 0.7396 | 0.7396 | g_safe | [5 empty] | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 30 | 0.0005 | 0.4068 | 0.0275 | 0.0206 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152309 | LIGHTING & SMALL POWER LAYOUT DRAWING - SECURITY BUILDING | Layout Drawing |  | LIGHTING & SMALL POWER | Security Building |  | Layout Drawing for Security Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7241 | 0.7422 | 0.7422 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 4 | 1 | 2.3394 | 0.5228 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152310 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE | Layout Drawing |  | LIGHTING & SMALL POWER | Security Building |  | Layout Drawing for Security Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7158 | 0.7397 | 0.7397 | g_safe | [5 empty] | SKIP | 1CF6500W16A02 | (GTG TR) FDN & Firewall Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-12-01 | 2008-04-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 7 | 18 | 0.0005 | 0.4633 | 0.0277 | 0.0277 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152311 | LIGHTING & SMALL POWER LAYOUT DRAWING - SUPPORT BUILDING | Layout Drawing |  | LIGHTING & SMALL POWER | Support Building |  | Layout Drawing for Support Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7348 | 0.7454 | 0.7454 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 4 | 1 | 2.3394 | 0.5336 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152312 | LIGHTING & SMALL POWER LAYOUT DRAWING - X-RAY SEARCHING ROOM | Layout Drawing |  | LIGHTING & SMALL POWER | X-RAY SEARCHING ROOM |  | Layout Drawing for X-RAY SEARCHING ROOM | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6763 | 0.7279 | 0.7279 | g_safe | [5 empty] | SKIP | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦stg | match | true | false | 2 | 33 | 0.0005 | 0.3897 | 0.0269 | 0.0202 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152313 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE SUNSHADE | Layout Drawing |  | LIGHTING & SMALL POWER | Security Building |  | Layout Drawing for Security Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6893 | 0.7318 | 0.7318 | g_safe | [5 empty] | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 25 | 0.0005 | 0.4410 | 0.0282 | 0.0282 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152314 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | Layout Drawing |  | LIGHTING & SMALL POWER | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6956 | 0.7337 | 0.7337 | g_ambig | generic_ok | 0.78 |  | 5 | All competing rules are stormwater/wastewater drainage layouts, not lighting & small power layouts for the Fire Brigade & Aux. LEB. | SKIP | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 4 | 8 | 3.1908 | 0.4991 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152315 | LIGHTING & SMALL POWER LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | Layout Drawing |  | LIGHTING & SMALL POWER | Workshop & Storage Building |  | Layout Drawing for Workshop & Storage Building | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6998 | 0.7349 | 0.7349 | g_safe | [5 empty] | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 7 | 1 | 9.7019 | 0.5831 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152316 | LIGHTING & SMALL POWER LAYOUT DRAWING - H2, CO2, N2 STORAGE SHELTER | Layout Drawing | Hydrogen System | LIGHTING & SMALL POWER | Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | Layout Drawing for Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | carbon¦dioxide¦hydrogen¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6707 | 0.7262 | 0.7262 | g_safe | [5 empty] | SKIP | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | electrical¦h2¦n2 |  | electrical¦h2¦n2 | query | n2 | match | true | false | 3 | 5 | 13.6249 | 0.5902 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦h2¦n2 | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152317 | LIGHTING & SMALL POWER LAYOUT DRAWING - AIR COMPRESSOR SHELTER | Layout Drawing | Air Compressor | LIGHTING & SMALL POWER | Air Compressor Shelter |  | Layout Drawing for Air Compressor Shelter | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6693 | 0.7258 | 0.7258 | g_safe | [5 empty] | SKIP | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air¦electrical |  | compressed_air¦electrical | query | compressed_air | match | true | false | 2 | 2 | 19.9312 | 0.6129 | 0.0323 | 0.0323 | hybrid | structured_preferred | compressed_air¦electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152318 | LIGHTING & SMALL POWER LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | Layout Drawing |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7511 | 0.7503 | 0.7503 | g_safe | [5 empty] | SKIP | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 5 | 4 | 4.3597 | 0.5451 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152319 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE WATER PUMP HOUSE | Layout Drawing |  | LIGHTING & SMALL POWER | Fire Water Pump House |  | Layout Drawing for Fire Water Pump House | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦fire_protection¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7108 | 0.7382 | 0.7382 | g_ambig | generic_ok | 0.66 |  | 8 | The competing rules target I&C JB/panel outlines, pump foundations, and drainage layouts rather than a lighting & small power layout for the Fire Water Pump House. | SKIP | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | design_drawing | civil_design | compatible | electrical¦fire_fighting |  | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 13.5237 | 0.5560 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical¦fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152320 | LIGHTING & SMALL POWER LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | Layout Drawing | TANK | LIGHTING & SMALL POWER | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6378 | 0.6378 | [6 empty] | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | true | false | 4 | 2 | 34.5568 | 0.6046 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦wts | civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152321 | LIGHTING & SMALL POWER LAYOUT DRAWING - WATER TREATMENT BUILDING | Layout Drawing |  | LIGHTING & SMALL POWER | Water Treatment Building |  | Layout Drawing for Water Treatment Building | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7016 | 0.6771 | 0.6771 | [6 empty] | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | true | false | 1 | 5 | 14.1673 | 0.5813 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152322 | LIGHTING & SMALL POWER LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | Layout Drawing |  | LIGHTING & SMALL POWER | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Layout Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7050 | 0.7365 | 0.7365 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | condensate¦electrical |  | condensate¦electrical | query | electrical | discipline_only | true | false | 4 | 1 | 2.3394 | 0.5305 | 0.0320 | 0.0160 | hybrid | structured_preferred | condensate¦electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152323 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR STG & HRSG | Layout Drawing | Steam Turbine Generator & Heat Recovery Steam Generator | LIGHTING & SMALL POWER | Chemical Dosing Shelter |  | Layout Drawing for Chemical Dosing Shelter | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6968 | 0.7340 | 0.7340 | g_ambig | generic_ok | 0.62 |  | 6 | The competing rules are HRSG piping/JB layouts and foundation/concrete layouts, not a lighting & small power layout for a chemical dosing shelter. | SKIP | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | electrical¦hrsg¦stg¦wts |  | electrical¦hrsg¦stg¦wts | query | gsut_uat¦stg | match | true | false | 1 | 12 | 19.1512 | 0.6254 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦hrsg¦stg¦wts | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152324 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR HRSG | Layout Drawing | Heat Recovery Steam Generator | LIGHTING & SMALL POWER | Chemical Dosing Shelter |  | Layout Drawing for Chemical Dosing Shelter | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6904 | 0.7321 | 0.7321 | g_ambig | generic_ok | 0.62 |  | 5 | The specific rules refer to HRSG JB/piping/foundation/concrete layouts, which do not clearly apply to a lighting & small power layout for a chemical dosing shelter. | SKIP | 1EF1600W00A01 | (HRSG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | electrical¦hrsg¦wts |  | electrical¦hrsg¦wts | query | hrsg | match | true | false | 19 | 7 | 12.9124 | 0.6409 | 0.0276 | 0.0276 | hybrid | structured_preferred | electrical¦hrsg¦wts | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152327 | LIGHTING & SMALL POWER LAYOUT DRAWING - YARD | Layout Drawing |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7511 | 0.7503 | 0.7503 | g_safe | [5 empty] | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 26 | 0.0005 | 0.4397 | 0.0280 | 0.0210 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152328 | LIGHTING & SMALL POWER LAYOUT DRAWING – TANK AREA | Layout Drawing |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for Tank | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7201 | 0.7410 | 0.7410 | g_safe | [5 empty] | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 17 | 0.0005 | 0.4646 | 0.0294 | 0.0220 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152329 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #1, 2 TRANSFORMER AREA | Layout Drawing | Gas Turbine Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for GTG | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7368 | 0.7460 | 0.7460 | g_ambig | generic_ok | 0.70 |  | 2 | The specific rules relate to GT foundation embedded metals/performance heater foundation layouts, not a lighting & small power layout for GTG LEB. | SKIP | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 | design_drawing | civil_design | compatible | electrical¦gtg |  | electrical¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 10 | 3 | 11.2085 | 0.6609 | 0.0302 | 0.0226 | hybrid | structured_preferred | electrical¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152330 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #3, 4, 5 TRANSFORMER AREA | Layout Drawing | Gas Turbine Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for GTG | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7248 | 0.7424 | 0.7424 | g_ambig | generic_ok | 0.70 |  | 2 | The specific rules relate to GT foundation embedded metals/performance heater foundation layouts, not a lighting & small power layout for GTG LEB. | SKIP | 3EF6500W32A12 | (GTG #31 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 | design_drawing | civil_design | compatible | electrical¦gtg |  | electrical¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 15 | 1 | 11.2384 | 0.6625 | 0.0297 | 0.0223 | hybrid | structured_preferred | electrical¦gtg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152331 | LIGHTING & SMALL POWER LAYOUT DRAWING – STG #1, 2 TRANSFORMER AREA | Layout Drawing | Steam Turbine & Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | [6 empty] | FA | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | electrical¦stg | stg | electrical¦stg | query | gsut_uat¦stg | match | true | false | 6 | 2 | 16.9520 | 0.6624 | 0.0313 | 0.0235 | hybrid | structured_preferred | electrical¦stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152332 | LIGHTING & SMALL POWER LAYOUT DRAWING – FUEL GAS SYSTEM AREA | Layout Drawing | Fuel Gas Package | Fuel Gas System |  |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7646 | 0.6960 | 0.6960 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | true | false | 10 | 1 | 15.7236 | 0.6683 | 0.0307 | 0.0230 | hybrid | structured_preferred | fgp | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152333 | LIGHTING & SMALL POWER LAYOUT DRAWING – WELDING SHED AND CONTAINER AT OPEN STORAGE AREA | Layout Drawing |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | Lighting Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7511 | 0.7503 | 0.7503 | g_safe | [5 empty] | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical | match | true | false | 7 | 1 | 3.7909 | 0.5197 | 0.0313 | 0.0235 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152401 | LIGHTING PANEL BOARD SCHEDULE - CENTRAL CONTROL BUILDING | Schedule |  | LIGHTING | Central Control Building |  | Schedule for LIGHTING | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - DOOR & WINDOW SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | schedule | schedule | schedule | schedule | ccr¦central¦lighting | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7533 | 0.6927 | 0.6927 | [6 empty] | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 |  | delivery | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 1 | 8 | 27.0226 | 0.5300 | 0.0311 | 0.0175 | hybrid | structured_no_system |  |  |  | 2025-07-28 | 2025-08-27 | 2025-09-26 | 2025-10-11 | 2025-10-26 | 2025-11-10 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152402 | LIGHTING PANEL BOARD SCHEDULE - GTG #1,2 LEB | Schedule |  | LIGHTING | Local Electrical Building |  | Schedule for LIGHTING |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦gtg¦leb¦lighting¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8706 | 0.9612 | 0.6728 | g_ambig | generic_ok | 0.74 |  | 13 | Competing rules are for civil/architectural rebar/interior/plumbing schedules, not for a lighting panel board schedule. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 11 | 2 | 8.7681 | 0.5655 | 0.0302 | 0.0227 | hybrid | structured_no_phase | electrical¦gtg |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152403 | LIGHTING PANEL BOARD SCHEDULE - GTG #3,4,5 LEB | Schedule |  |  | Local Electrical Building |  | Schedule for Local Electrical Building |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8548 | 0.9564 | 0.6695 | g_ambig | generic_ok | 0.74 |  | 13 | The competing specific rules listed are rebar/interior/plumbing schedules rather than a lighting panel board schedule for GTG #3,4,5 LEB. | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 55 | 1 | 7.6181 | 0.5925 | 0.0251 | 0.0188 | hybrid | structured_no_phase | electrical¦gtg |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152404 | LIGHTING PANEL BOARD SCHEDULE - ST #1 LEB | Schedule |  |  | Local Electrical Building |  | Schedule for Local Electrical Building | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5814 | 0.5244 | 0.5244 | [6 empty] | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 |  | delivery | query_unknown | electrical¦stg | stg | electrical¦stg | query | electrical | discipline_only | true | false | 1 | 2 | 13.5115 | 0.5357 | 0.0325 | 0.0122 | hybrid | structured_no_phase | electrical¦stg |  |  | 2025-07-28 | 2025-08-27 | 2025-09-26 | 2025-10-11 | 2025-10-26 | 2025-11-10 | generated | 0.90 |  | false | false | 0.34 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152405 | LIGHTING PANEL BOARD SCHEDULE - ST #2 LEB | Schedule |  |  | Local Electrical Building |  | Schedule for Local Electrical Building | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5814 | 0.5244 | 0.5244 | [6 empty] | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 |  | delivery | query_unknown | electrical¦stg | stg | electrical¦stg | query | electrical | discipline_only | true | false | 1 | 2 | 13.5115 | 0.5326 | 0.0325 | 0.0122 | hybrid | structured_no_phase | electrical¦stg |  |  | 2025-07-28 | 2025-08-27 | 2025-09-26 | 2025-10-11 | 2025-10-26 | 2025-11-10 | generated | 0.90 |  | false | false | 0.34 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152406 | LIGHTING PANEL BOARD SCHEDULE - ST BUILDING | Schedule | Steam Turbine & Generator |  | Steam Turbine Building |  | Schedule for STG | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | schedule | schedule | schedule | schedule | generator¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.7627 | 0.7538 | 0.7538 | [6 empty] | FI | 1EF2020W00A05 | (ST #10) Emergency Load Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-04-16 |  |  | query_unknown | stg | stg | stg | query | stg | match | true | false | 36 | 5 | 9.8501 | 0.6308 | 0.0258 | 0.0194 | hybrid | structured_no_phase | stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152407 | LIGHTING PANEL BOARD SCHEDULE - FGS ELECTRICAL BUILDING | Schedule |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Schedule for Electrical System |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8822 | 0.9647 | 0.6753 | g_safe | [5 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  |  | civil_design | query_unknown | electrical¦fgp |  | electrical¦fgp | query | fgp | match | false | false | 20 | 8 | 13.7271 | 0.5332 | 0.0272 | 0.0204 | hybrid | structured_no_phase | electrical¦fgp |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.24 | needs_review_activity | activity_phase_status=query_unknown;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152408 | LIGHTING PANEL BOARD SCHEDULE - ADMINISTRATION | Schedule |  |  |  |  | Schedule |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9003 | 0.9701 | 0.6791 | [6 empty] | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 2 | 13.5115 | 0.5350 | 0.0323 | 0.0181 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152409 | LIGHTING PANEL BOARD SCHEDULE - SECURITY BUILDING | Schedule |  |  | Security Building |  | Schedule for Security Building |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8720 | 0.9616 | 0.6731 | g_safe | [5 empty] | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 1 | 13.5115 | 0.5507 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152411 | LIGHTING PANEL BOARD SCHEDULE - SUPPORT BUILDING | Schedule |  |  | Support Building |  | Schedule for Support Building |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8824 | 0.9647 | 0.6753 | g_safe | [5 empty] | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 1 | 13.5115 | 0.5691 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152414 | LIGHTING PANEL BOARD SCHEDULE - FIRE BRIGADE & AUX. LEB | Schedule |  |  | Local Electrical Building |  | Schedule for Local Electrical Building |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8088 | 0.9426 | 0.6599 | g_ambig | generic_ok | 0.74 |  | 17 | The competing rules are civil/architectural/plumbing schedules for various buildings, not a lighting panel board schedule. | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown | electrical |  | electrical | query | electrical | match | true | false | 2 | 5 | 13.5115 | 0.5527 | 0.0315 | 0.0236 | hybrid | structured_no_phase | electrical |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152415 | LIGHTING PANEL BOARD SCHEDULE - WORKSHOP & STORAGE BUILDING | Schedule |  |  | Workshop & Storage Building |  | Schedule for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7095 | 0.6795 | 0.6795 | g_safe | [5 empty] | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 2 | 13.5115 | 0.5362 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2025-01-15 | 2025-02-14 | 2025-03-16 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152418 | LIGHTING PANEL BOARD SCHEDULE - DEAERATOR SUPPORT STRUCTURE | Schedule |  |  |  |  | Schedule |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8201 | 0.9460 | 0.6622 | [6 empty] | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 |  | procurement | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 4 | 43 | 13.3126 | 0.5076 | 0.0253 | 0.0143 | hybrid | structured_no_system |  |  |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152419 | LIGHTING PANEL BOARD SCHEDULE - FIRE WATER PUMP HOUSE | Schedule |  | Fire Fighting System | Fire Water Pump House |  | Schedule for Fire Fighting System | Fire Fighting System | WASTE WATER DRAINAGE MANHOLE SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | fighting¦fire¦fire_protection¦pump | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6978 | 0.5593 | 0.5593 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 2 | 27.4721 | 0.6179 | 0.0313 | 0.0235 | hybrid | structured_no_phase | fire_fighting |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152421 | LIGHTING PANEL BOARD SCHEDULE - WATER TREATMENT BUILDING | Schedule |  | Water Treatment System | Water Treatment Building |  | Schedule for Water Treatment System | Water Treatment System | Cable Schdule(inculde drum schedule) | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7315 | 0.5695 | 0.5695 | [6 empty] | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 29.1895 | 0.6566 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152422 | LIGHTING PANEL BOARD SCHEDULE - CPP & CPP REGENERATION BUILDING | Schedule |  | Condensate System |  |  | Schedule for Condensate System |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8309 | 0.9493 | 0.6645 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 |  | system_design | query_unknown | condensate |  | condensate | query | condensate | match | false | false | 62 | 1 | 6.7390 | 0.6021 | 0.0246 | 0.0184 | hybrid | structured_no_phase | condensate |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.24 | needs_review_activity | activity_phase_status=query_unknown;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152427 | LIGHTING PANEL BOARD SCHEDULE - YARD | Schedule |  |  |  |  | Schedule |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8955 | 0.9686 | 0.6780 | [6 empty] | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 1 | 13.5115 | 0.5435 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152428 | LIGHTING PANEL BOARD SCHEDULE – TANK AREA | Schedule |  |  |  |  | Schedule for Tank |  | LIGHTING PANEL BOARD SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8731 | 0.9619 | 0.6733 | g_safe | [5 empty] | FA | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  | installation | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 1 | 13.5115 | 0.5179 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-01 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE04-P0BAU-152501 | TYPICAL INSTALLATION DRAWING - EARTHING AND LIGHTNING PROTECTION | DRAWING |  | EARTHING AND LIGHTNING PROTECTION |  |  | DRAWING for EARTHING AND LIGHTNING PROTECTION |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | earthing¦lightning¦protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7825 | 0.9348 | 0.6543 | g_safe | [5 empty] | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical |  | electrical | query | electrical | match | true | false | 9 | 1 |  | 0.4626 | 0.0309 | 0.0232 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0BAU-152502 | TECHNICAL SPECIFICATION - EARTHING AND LIGHTNING PROTECTION SYSTEM | Technical Specification |  | EARTHING AND LIGHTNING PROTECTION SYSTEM |  |  | Technical Specification for EARTHING AND LIGHTNING PROTECTION SYSTEM |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | earthing¦lightning¦protection |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6981 | 0.6761 | 0.4733 | g_safe | [5 empty] | FA | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | true | false | 1 | 3 | 61.2120 | 0.6683 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_score_medium;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAU-152503 | MAIN EARTHING GRID CALCULATION | Calculation sheet |  | Electrical System |  |  | Calculation sheet for Electrical System | Chemical Dosing System | Calculation Sheet | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | electrical |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6526 | 0.6158 | 0.6158 | g_safe | [5 empty] | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | electrical | wts | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 12 | 8 | 3.0341 | 0.4868 | 0.0286 | 0.0286 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152504 | EARTHING LAYOUT DRAWING - MAIN GRID | DRAWING |  | Electrical System |  |  | DRAWING for Electrical System | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7883 | 0.7615 | 0.7615 | g_safe | [5 empty] | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 10 | 8 | 3.1025 | 0.5220 | 0.0290 | 0.0217 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152505 | EARTHING LAYOUT DRAWING - CENTRAL CONTROL BUILDING | Layout Drawing |  | EARTHING | Central Control Building |  | Layout Drawing for Central Control Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7854 | 0.7606 | 0.7606 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 12 | 1 | 2.3392 | 0.5347 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152506 | EARTHING LAYOUT DRAWING - GTG #1,2 LEB | Layout Drawing |  | EARTHING | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7571 | 0.7521 | 0.7521 | g_ambig | generic_ok | 0.70 |  | 2 | The specific rules are for GT foundation embedded metals/performance heater foundation layouts, not an earthing layout drawing for GTG LEB. | SKIP | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 6 | 7 | 3.4137 | 0.5516 | 0.0301 | 0.0301 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152507 | EARTHING LAYOUT DRAWING - GTG #3,4,5 LEB | Layout Drawing |  | EARTHING | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7439 | 0.7482 | 0.7482 | g_ambig | generic_ok | 0.70 |  | 2 | The specific rules are for GT foundation embedded metals/performance heater foundation layouts, not an earthing layout drawing for GTG LEB. | SKIP | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 4 | 3.4441 | 0.5452 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P6BAU-152508 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #1 LEB | Layout Drawing | Steam Turbine | EARTHING & LIGHTNING PROTECTION | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7606 | 0.7882 | 0.7882 | g_ambig | generic_ok | 0.70 |  | 1 | The competing specific rule is for steam turbine generator foundation layout, not an earthing & lightning protection layout drawing. | SKIP | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | gsut_uat¦stg | match | true | false | 14 | 1 | 5.3094 | 0.5919 | 0.0299 | 0.0299 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P7BAU-152509 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #2 LEB | Layout Drawing | Steam Turbine | EARTHING & LIGHTNING PROTECTION | Local Electrical Building |  | Layout Drawing for Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7606 | 0.7882 | 0.7882 | g_ambig | generic_ok | 0.70 |  | 1 | The competing specific rule is for steam turbine generator foundation layout, not an earthing & lightning protection layout drawing. | SKIP | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | gsut_uat¦stg | match | true | false | 14 | 3 | 5.8209 | 0.5858 | 0.0294 | 0.0294 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152510 | EARTHING LAYOUT DRAWING - ST BUILDING | Layout Drawing | Steam Turbine & Generator | EARTHING | Steam Turbine Building |  | Layout Drawing for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6641 | 0.6192 | 0.6192 | [6 empty] | FA | 3EF2020W16A06 | (ST #30) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 5 | 4 | 9.9602 | 0.6304 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152511 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7072 | 0.6788 | 0.6788 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 4 | 10.8160 | 0.5272 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152512 | EARTHING LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | Layout Drawing |  | EARTHING | Administration & Social Building |  | Layout Drawing for Administration & Social Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7268 | 0.7430 | 0.7430 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 4 | 1 | 2.3392 | 0.5427 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152513 | EARTHING LAYOUT DRAWING - SECURITY BUILDING | Layout Drawing |  | EARTHING | Security Building |  | Layout Drawing for Security Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7446 | 0.7484 | 0.7484 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 4 | 1 | 2.3392 | 0.5272 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152514 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GATE HOUSE | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | GATE HOUSE |  | Layout Drawing for GATE HOUSE | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | gate¦house |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7606 | 0.7882 | 0.7882 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 1 | 1 |  | 0.5427 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152515 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SUPPORT BUILDING | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | Support Building |  | Layout Drawing for Support Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7592 | 0.7878 | 0.7878 | g_safe | [5 empty] | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 2 | 2 | 2.5087 | 0.5105 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152516 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SEARCH FACILITY AND VISITORS CENTRE | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | Security Building |  | Layout Drawing for Security Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6545 | 0.7564 | 0.7564 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 9 | 1 |  | 0.5036 | 0.0309 | 0.0309 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152517 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE BRIGADE | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | FIRE BRIGADE |  | Layout Drawing for FIRE BRIGADE | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7502 | 0.7851 | 0.7851 | g_ambig | generic_ok | 0.78 |  | 5 | Competing rules are stormwater/wastewater drainage layouts and do not target earthing & lightning protection layouts for Fire Brigade. | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 1 | 1 |  | 0.5153 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152518 | EARTHING LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | Layout Drawing |  | EARTHING | Workshop & Storage Building |  | Layout Drawing for Workshop & Storage Building | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7366 | 0.7460 | 0.7460 | g_safe | [5 empty] | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 7 | 1 | 9.7017 | 0.5715 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152519 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - N2 STORAGE SHELTER | Layout Drawing | Nitrogen System | EARTHING & LIGHTNING PROTECTION | Nitrogen STORAGE SHELTER |  | Layout Drawing for Nitrogen STORAGE SHELTER | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7257 | 0.7777 | 0.7777 | g_safe | [5 empty] | SKIP | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | electrical¦n2 | electrical | electrical¦n2 | query | n2 | match | true | false | 1 | 5 | 20.9435 | 0.6771 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦n2 | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152520 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COMPRESSOR SHELTER | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | Air Compressor Shelter |  | Layout Drawing for Air Compressor Shelter | Air Compressor | Earthing point layout | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7398 | 0.7819 | 0.7819 | g_safe | [5 empty] | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air¦electrical | compressed_air¦electrical | compressed_air¦electrical | query | compressed_air | match | true | false | 1 | 3 | 12.3084 | 0.5709 | 0.0323 | 0.0323 | hybrid | structured_preferred | compressed_air¦electrical | civil_design | 10 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152521 | EARTHING LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | Layout Drawing |  | EARTHING |  |  | Layout Drawing for EARTHING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | earthing |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7641 | 0.7542 | 0.7542 | g_safe | [5 empty] | SKIP | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 5 | 4 | 4.3592 | 0.5340 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152522 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | Fire Water Pump House |  | Layout Drawing for Fire Water Pump House | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦fire_protection¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7465 | 0.7839 | 0.7839 | g_ambig | generic_ok | 0.66 |  | 8 | The competing rules relate to I&C JB/panel outlines, pump foundations, and drainage layouts rather than earthing & lightning protection layout for the Fire Water Pump House. | SKIP | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | design_drawing | civil_design | compatible | electrical¦fire_fighting | electrical | electrical¦fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 13.5235 | 0.5459 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical¦fire_fighting | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152523 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | Layout Drawing |  | EARTHING & LIGHTNING PROTECTION | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.5703 | 0.6378 | 0.6378 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | true | false | 1 | 3 | 28.7086 | 0.5705 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152524 | EARTHING LAYOUT DRAWING - WATER TREATMENT BUILDING | Layout Drawing |  | EARTHING | Water Treatment Building |  | Layout Drawing for Water Treatment Building | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7016 | 0.6771 | 0.6771 | [6 empty] | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | true | false | 4 | 3 | 13.6713 | 0.5857 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152525 | EARTHING LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | EARTHING LAYOUT DRAWING |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | EARTHING LAYOUT DRAWING for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | condensate¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7172 | 0.7402 | 0.7402 | g_safe | [5 empty] | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | condensate¦electrical | electrical | condensate¦electrical | query |  | activity_unscoped | true | true | 6 | 27 | 24.0608 | 0.4999 | 0.0266 | 0.0160 | hybrid | structured_cell_found_text_preferred | condensate¦electrical | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152526 | EARTHING LAYOUT DRAWING - PIPE RACK FOR HRSG | EARTHING LAYOUT DRAWING | Heat Recovery Steam Generator |  | Pipe Rack |  | EARTHING LAYOUT DRAWING for Pipe Rack | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | hrsg¦pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7524 | 0.7507 | 0.7507 | g_ambig | generic_ok | 0.60 |  | 5 | The competing rules are HRSG JB/piping/foundation/concrete layouts and do not clearly apply to an earthing layout drawing for an HRSG pipe rack. | SKIP | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg | electrical | hrsg | query | hrsg | match | true | false | 9 | 4 | 12.9120 | 0.6321 | 0.0301 | 0.0301 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152527 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AUX. LEB | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  | Electrical System | Local Electrical Building |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7714 | 0.7914 | 0.7914 | g_safe | [5 empty] | SKIP | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 4 | 15 | 6.3319 | 0.4910 | 0.0290 | 0.0290 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152528 | EARTHING LAYOUT DRAWING - TANK AREA | EARTHING LAYOUT DRAWING |  | Electrical System |  |  | EARTHING LAYOUT DRAWING for Tank | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7782 | 0.7585 | 0.7585 | g_safe | [5 empty] | SKIP | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 12 | 11 | 3.0341 | 0.5121 | 0.0280 | 0.0210 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152529 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #1,2 AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | Gas Turbine Generator |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for GTG | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7761 | 0.7928 | 0.7928 | g_ambig | uncertain | 0.55 |  | 2 | Document is for GTG/TR area lightning/earthing, but competing specifics are foundation embedded metals and performance heater foundation, which may or may not be the intended scope. | SKIP | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 8 | 9 | 9.9563 | 0.6096 | 0.0292 | 0.0219 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152530 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #3,4,5 AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | Gas Turbine Generator |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for GTG | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7761 | 0.7928 | 0.7928 | g_ambig | uncertain | 0.55 |  | 2 | Document is for GTG/TR area lightning/earthing, but competing specifics are foundation embedded metals and performance heater foundation, which may or may not be the intended scope. | SKIP | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 16 | 9 | 9.9868 | 0.6032 | 0.0277 | 0.0207 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152531 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - STG TR AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | Steam Turbine & Generator |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Steam Turbine Generator | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7647 | 0.7894 | 0.7894 | g_ambig | uncertain | 0.55 |  | 1 | Equipment matches STG, but the only specific rule is for STG foundation layout and it is unclear if the lightning/earthing layout drawing is tied to the foundation package. | SKIP | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | stg | electrical | stg | query | electrical¦gsut_uat¦stg | match | true | false | 9 | 3 | 10.9132 | 0.6196 | 0.0304 | 0.0228 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152532 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-1 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | AIR COOLED CONDENSER-1 |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8244 | 0.9473 | 0.9473 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | true | false | 1 | 3 | 20.1915 | 0.5506 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152533 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-2 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | AIR COOLED CONDENSER-2 |  |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.8244 | 0.9473 | 0.9473 | [6 empty] | FA | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc¦electrical | acc | query | acc¦condensate | match | true | false | 1 | 1 | 21.5947 | 0.5523 | 0.0328 | 0.0246 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152534 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIN FAN COOLER & CCW PUMP AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | FIN FAN COOLER & Closed Cooling Water PUMP | Closed Cooling Water System |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Pump | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | pump |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7511 | 0.7853 | 0.7853 | g_ambig | generic_ok | 0.75 |  | 3 | Competing specifics target I&C JB/panels or general service pump foundations, not fin fan cooler/CCW pump lightning protection layout. | SKIP | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw | electrical | ccw | query | ccw¦gtg | match | true | false | 3 | 1 | 63.3948 | 0.6064 | 0.0323 | 0.0242 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152535 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  | Fuel Gas System |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Fuel Gas System | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8274 | 0.8316 | 0.8316 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | design_drawing | civil_design | compatible | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 10.8164 | 0.6310 | 0.0320 | 0.0240 | hybrid | structured_preferred | electrical¦fgp | system_design¦civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152536 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - BLACK START DIESEL GENERATOR AREA | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | BLACK START DIESEL GENERATOR | Electrical System |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Electrical System | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8041 | 0.8012 | 0.8012 | g_safe | [5 empty] | SKIP | 1EF3530W16A02 | (Block #1 EDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-10-29 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 1 | 8 | 16.4183 | 0.5616 | 0.0311 | 0.0233 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152537 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - H2, CO2 STORAGE SHELTER | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Hydrogen, Carbon Dioxide STORAGE SHELTER | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6999 | 0.7700 | 0.7700 | g_safe | [5 empty] | SKIP | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | electrical | h2 | query | h2 | match | true | false | 1 | 1 | 17.6855 | 0.5187 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152538 | EARTHING LAYOUT DRAWING - 380kV EHV CABLE INSULATION JOINT AREA | EARTHING LAYOUT DRAWING |  | Electrical System |  |  | EARTHING LAYOUT DRAWING for Electrical System | Substation | Earthing Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8206 | 0.7712 | 0.7712 | g_safe | [5 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 2 | 1 | 11.4520 | 0.5767 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152539 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - CHEMICAL DOSING SYSTEM | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for CHEMICAL DOSING SYSTEM | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7174 | 0.7752 | 0.7752 | g_safe | [5 empty] | SKIP | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible | wts | electrical | wts | query | wts | match | true | false | 1 | 1 | 33.6657 | 0.6704 | 0.0328 | 0.0246 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152540 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - PRELIMINARY INSPECTION CHECK POINT (PIC) | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING |  | Electrical System |  |  | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING for Electrical System | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8041 | 0.8012 | 0.8012 | g_safe | [5 empty] | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 10 | 6 | 3.1025 | 0.5032 | 0.0294 | 0.0221 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152600 | LIGHTNING PROTECTION LAYOUT DRAWING - OVERALL AREA | LIGHTNING PROTECTION LAYOUT DRAWING |  | Electrical System |  |  | LIGHTNING PROTECTION LAYOUT DRAWING for Electrical System | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8432 | 0.8129 | 0.8129 | g_safe | [5 empty] | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 10 | 10 | 3.1025 | 0.4773 | 0.0286 | 0.0214 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152601 | LIGHTNING PROTECTION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LIGHTNING PROTECTION LAYOUT DRAWING |  | Electrical System | Central Control Building |  | LIGHTNING PROTECTION LAYOUT DRAWING for Central Control Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7980 | 0.7994 | 0.7994 | g_safe | [5 empty] | SKIP | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 12 | 1 | 5.2919 | 0.5317 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152602 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #1,2 LEB | LIGHTNING PROTECTION LAYOUT DRAWING | Gas Turbine Generator | Electrical System | Local Electrical Building |  | LIGHTNING PROTECTION LAYOUT DRAWING for Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8111 | 0.8033 | 0.8033 | g_ambig | uncertain | 0.55 |  | 2 | Document is lightning protection for GTG LEB, while competing specifics are GT generator foundation embedded metals and performance heater foundation, so the intended equipment linkage is ambiguous. | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 14.9212 | 0.6641 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152603 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #3,4,5 LEB | LIGHTNING PROTECTION LAYOUT DRAWING | Gas Turbine Generator | Electrical System | Local Electrical Building |  | LIGHTNING PROTECTION LAYOUT DRAWING for Local Electrical Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8111 | 0.8033 | 0.8033 | g_ambig | uncertain | 0.55 |  | 2 | Document is lightning protection for GTG LEB, while competing specifics are GT generator foundation embedded metals and performance heater foundation, so the intended equipment linkage is ambiguous. | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 5 | 2 | 13.7712 | 0.6409 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152606 | LIGHTNING PROTECTION LAYOUT DRAWING - ST BUILDING | Layout Drawing | Steam Turbine & Generator | LIGHTNING PROTECTION | Steam Turbine Building |  | Layout Drawing for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6641 | 0.6192 | 0.6192 | [6 empty] | FA | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 12 | 1 | 9.1673 | 0.6423 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152608 | LIGHTNING PROTECTION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | Layout Drawing |  | LIGHTNING PROTECTION | Administration & Social Building |  | Layout Drawing for Administration & Social Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7462 | 0.7839 | 0.7839 | g_safe | [5 empty] | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 2 | 2 | 2.5087 | 0.4929 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152609 | LIGHTNING PROTECTION LAYOUT DRAWING - SECURITY BUILDING | Layout Drawing |  | LIGHTNING PROTECTION | Security Building |  | Layout Drawing for Security Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7690 | 0.7907 | 0.7907 | g_safe | [5 empty] | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 2 | 2 | 2.5087 | 0.4882 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152614 | LIGHTNING PROTECTION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | Layout Drawing |  | LIGHTNING PROTECTION | Workshop & Storage Building |  | Layout Drawing for Workshop & Storage Building | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7586 | 0.7876 | 0.7876 | g_safe | [5 empty] | SKIP | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 7 | 2 | 9.7017 | 0.5110 | 0.0311 | 0.0311 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152620 | LIGHTNING PROTECTION LAYOUT DRAWING - WATER TREATMENT BUILDING | Layout Drawing |  | LIGHTNING PROTECTION | Water Treatment Building |  | Layout Drawing for Water Treatment Building | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7016 | 0.6771 | 0.6771 | [6 empty] | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | electrical¦wts | electrical¦wts | electrical¦wts | query | wts | match | true | false | 1 | 4 | 14.1670 | 0.5388 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152621 | LIGHTNING PROTECTION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | Layout Drawing |  | LIGHTNING PROTECTION | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Layout Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING | Substation | Lightning Protection Layout DraWing | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7601 | 0.7880 | 0.7880 | g_safe | [5 empty] | SKIP | 0EF5544W32A11 | (GIS BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | civil_design | civil_design | match | condensate¦electrical | electrical | condensate¦electrical | query | electrical | discipline_only | true | false | 2 | 2 | 2.5087 | 0.4905 | 0.0323 | 0.0161 | hybrid | structured_preferred | condensate¦electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152701 | TECHNICAL SPECIFICATION - PVC CONDUIT AND ACCESSORIES | Technical Specification |  |  |  |  | Technical Specification |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7963 | 0.9389 | 0.9389 | [6 empty] | FA | 0EF6020W58A01 | (Piping) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | false | 5 | 15 | 10.8065 | 0.4730 | 0.0287 | 0.0215 | hybrid | structured_no_system |  | procurement |  | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152702 | TECHNICAL SPECIFICATION - STEEL CONDUIT AND ACCESSORIES | Technical Specification |  |  |  |  | Technical Specification |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8202 | 0.9461 | 0.9461 | [6 empty] | FA | 0EF6020W46A07 | (Hanger & Support & Fitting) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | false | 29 | 9 | 10.4905 | 0.5033 | 0.0257 | 0.0193 | hybrid | structured_no_system |  | procurement |  | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152705 | EMBEDDED CONDUIT LAYOUT FOR ST #1 LEB | Layout Drawing |  |  | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8331 | 0.9499 | 0.6650 | g_safe | [5 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 20 | 5 | 1.5999 | 0.4647 | 0.0279 | 0.0279 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152706 | EMBEDDED CONDUIT LAYOUT FOR ST #2 LEB | Layout Drawing |  |  | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8265 | 0.9480 | 0.6636 | g_safe | [5 empty] | FA | 2EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 18 | 14 | 2.3015 | 0.4562 | 0.0263 | 0.0263 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152707 | EMBEDDED CONDUIT LAYOUT FOR ST BUILDING | Layout Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Layout Drawing for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6641 | 0.6192 | 0.6192 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 6 | 9.9602 | 0.6269 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152708 | EMBEDDED CONDUIT LAYOUT FOR FGS ELECTRICAL BUILDING | Layout Drawing |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7072 | 0.6788 | 0.6788 | [6 empty] | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 1 | 3 | 14.4574 | 0.5546 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152709 | EMBEDDED CONDUIT LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | Layout Drawing |  |  | Administration & Social Building |  | Layout Drawing for Administration & Social Building |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8169 | 0.9451 | 0.6616 | g_safe | [5 empty] | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 6 | 2 | 15.1429 | 0.5568 | 0.0313 | 0.0188 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152710 | EMBEDDED CONDUIT LAYOUT FOR SECURITY BUILDING | Layout Drawing |  |  | Security Building |  | Layout Drawing for Security Building |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8706 | 0.9612 | 0.6728 | g_safe | [5 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 102 | 24.0608 | 0.4312 | 0.0223 | 0.0134 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152711 | EMBEDDED CONDUIT LAYOUT FOR MAIN GATE HOUSE AREA | Layout Drawing |  |  | Security Building |  | Layout Drawing for Security Building |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8581 | 0.9574 | 0.6702 | g_safe | [5 empty] | FA | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 3 | 1 | 17.1992 | 0.5519 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152715 | EMBEDDED CONDUIT LAYOUT FOR FIRE BRIGADE | Layout Drawing |  |  | FIRE BRIGADE |  | Layout Drawing for FIRE BRIGADE |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | brigade¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8749 | 0.9625 | 0.6737 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 10 | 20 | 6.8830 | 0.4754 | 0.0268 | 0.0201 | hybrid | structured_no_system |  | civil_design |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152716 | EMBEDDED CONDUIT LAYOUT FOR WORKSHOP & STORAGE BUILDING | Layout Drawing |  |  | Workshop & Storage Building |  | Layout Drawing for Workshop & Storage Building |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8342 | 0.9502 | 0.6652 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 34 | 1 | 9.7017 | 0.5195 | 0.0270 | 0.0203 | hybrid | structured_no_system |  | civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152717 | EMBEDDED CONDUIT LAYOUT FOR H2, CO2, N2 STORAGE SHELTER | Layout Drawing | Hydrogen System |  | Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | Layout Drawing for Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | carbon¦dioxide¦hydrogen¦nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7329 | 0.9199 | 0.6439 | g_safe | [5 empty] | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | h2¦n2 |  | h2¦n2 | query | n2 | match | true | false | 3 | 2 | 13.6244 | 0.5987 | 0.0320 | 0.0320 | hybrid | structured_preferred | h2¦n2 | civil_design | 10 | 2024-07-21 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152718 | EMBEDDED CONDUIT LAYOUT FOR AIR COMPRESSOR SHELTER | Layout Drawing | Air Compressor | Compressed Air System | Air Compressor Shelter |  | Layout Drawing for Air Compressor Shelter |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7982 | 0.9395 | 0.6576 | g_safe | [5 empty] | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 2 | 3 | 31.4769 | 0.6431 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152719 | EMBEDDED CONDUIT LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | Layout Drawing |  |  |  |  | Layout Drawing |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8158 | 0.9447 | 0.6613 | [6 empty] | FA | 2EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 14 | 16 | 8.2027 | 0.5265 | 0.0267 | 0.0200 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152720 | EMBEDDED CONDUIT LAYOUT FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER(CPP) | EMBEDDED CONDUIT LAYOUT | Fire water pump | Fire Fighting System | Fire Water Pump House |  | EMBEDDED CONDUIT LAYOUT for Fire Water Pump House | CPP FIN FAN COOLER | CPP FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦fire_protection¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.6715 | 0.7848 | 0.7848 | g_ambig | generic_ok | 0.80 |  | 2 | Competing specifics are for I&C JB/panel layout drawings, not embedded conduit layout for fire water pump house/fin fan cooler. | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | ccw | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 1 | 40.9952 | 0.6664 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152721 | EMBEDDED CONDUIT LAYOUT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | EMBEDDED CONDUIT LAYOUT | BULK CHEMICAL STORAGE TANK |  | Water Treatment Plant |  | EMBEDDED CONDUIT LAYOUT for Water Treatment Plant |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | plant¦tank¦treatment¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7941 | 0.9382 | 0.6568 | g_ambig | generic_ok | 0.80 |  | 2 | Competing specifics are explicitly for Water Treatment System cable tray/earthing drawings, not bulk chemical storage tank embedded conduit layout. | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 2 | 3 | 52.9788 | 0.6042 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152722 | EMBEDDED CONDUIT LAYOUT FOR WATER TREATMENT BUILDING | EMBEDDED CONDUIT LAYOUT |  | Water Treatment System | Water Treatment Building |  | EMBEDDED CONDUIT LAYOUT for Water Treatment Building |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8417 | 0.9525 | 0.6667 | g_ambig | uncertain | 0.50 |  | 2 | Document equipment is Water Treatment System, but competing specifics are for WTS cable tray/earthing drawings rather than embedded conduit layout, so applicability is unclear. | FA | 0EF4035W16A02.2 | (WWT LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 2 | 3 | 25.3958 | 0.5883 | 0.0320 | 0.0320 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152724 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | EMBEDDED CONDUIT LAYOUT | Steam Turbine Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | Chemical Dosing Shelter |  | EMBEDDED CONDUIT LAYOUT for Chemical Dosing Shelter |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.6258 | 0.6544 | 0.6544 | [6 empty] | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match | hrsg¦stg¦wts | hrsg | hrsg¦stg¦wts | query | wts | match | true | false | 2 | 1 | 30.8879 | 0.6073 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2024-05-14 | 2024-05-29 | 2024-06-13 | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152725 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | EMBEDDED CONDUIT LAYOUT | Heat Recovery Steam Generator | CHEMICAL DOSING | Chemical Dosing Shelter |  | EMBEDDED CONDUIT LAYOUT for Chemical Dosing Shelter |  | HRSG FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.6297 | 0.6556 | 0.6556 | [6 empty] | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match | hrsg¦wts | hrsg | hrsg¦wts | query | wts | match | true | false | 2 | 1 | 30.8879 | 0.6075 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | 2024-05-14 | 2024-05-29 | 2024-06-13 | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152726 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | EMBEDDED CONDUIT LAYOUT | Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | g_ambig | uncertain | 0.55 |  | 1 | Equipment is GTG but the specific rule is for GT generator foundation embedded metals layout, which may not govern an embedded conduit layout without clearer scope linkage. | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 4 | 2 | 10.8503 | 0.6644 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152727 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | EMBEDDED CONDUIT LAYOUT | Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | g_ambig | uncertain | 0.55 |  | 1 | Equipment is GTG but the specific rule is for GT generator foundation embedded metals layout, which may not govern an embedded conduit layout without clearer scope linkage. | FA | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 3 | 2 | 11.5520 | 0.6580 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152728 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | EMBEDDED CONDUIT LAYOUT | Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | g_ambig | uncertain | 0.55 |  | 1 | Equipment is GTG but the specific rule is for GT generator foundation embedded metals layout, which may not govern an embedded conduit layout without clearer scope linkage. | FA | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 3 | 4 | 11.5824 | 0.6574 | 0.0315 | 0.0315 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152729 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | EMBEDDED CONDUIT LAYOUT | Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | g_ambig | uncertain | 0.55 |  | 1 | Equipment is GTG but the specific rule is for GT generator foundation embedded metals layout, which may not govern an embedded conduit layout without clearer scope linkage. | FA | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 15 | 3 | 9.2505 | 0.6547 | 0.0292 | 0.0292 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152730 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | EMBEDDED CONDUIT LAYOUT | Gas Turbine Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for GTG |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8812 | 0.9644 | 0.6751 | g_ambig | uncertain | 0.55 |  | 1 | Equipment is GTG but the specific rule is for GT generator foundation embedded metals layout, which may not govern an embedded conduit layout without clearer scope linkage. | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 10 | 1 | 9.2505 | 0.6517 | 0.0307 | 0.0307 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.80 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152731 | EMBEDDED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | EMBEDDED CONDUIT LAYOUT | POTABLE STORAGE WATER TANK & FIRE WATER TANK | Fire Fighting System |  |  | EMBEDDED CONDUIT LAYOUT for Tank |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fire_protection¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8735 | 0.9620 | 0.6734 | g_safe | [5 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 2 | 2 | 34.9263 | 0.5728 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152732 | EMBEDDED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | EMBEDDED CONDUIT LAYOUT |  |  |  |  | EMBEDDED CONDUIT LAYOUT for Tank |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8735 | 0.9620 | 0.6734 | g_safe | [5 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | true | false | 2 | 2 | 25.7879 | 0.5788 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152733 | EMBEDDED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | EMBEDDED CONDUIT LAYOUT |  | Condensate System |  |  | EMBEDDED CONDUIT LAYOUT for Tank |  | EMBEDDED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8735 | 0.9620 | 0.6734 | g_safe | [5 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate |  | condensate | query | condensate¦fgp | match | true | false | 1 | 5 | 18.7289 | 0.5891 | 0.0318 | 0.0318 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152735 | EMBEDDED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | EMBEDDED CONDUIT LAYOUT | Fin Fan Cooler & Closed Cooling Water PUMP | Closed Cooling Water System |  |  | EMBEDDED CONDUIT LAYOUT for Pump | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | pump |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7635 | 0.8124 | 0.8124 | g_ambig | generic_ok | 0.80 |  | 2 | Competing specifics are I&C JB/panel layout drawings and do not target embedded conduit layout for fin fan cooler/CCW pump area. | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | true | false | 3 | 2 | 67.2488 | 0.6523 | 0.0320 | 0.0320 | hybrid | structured_preferred | ccw | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152736 | EMBEDDED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | EMBEDDED CONDUIT LAYOUT | Steam Turbine & Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7058 | 0.7717 | 0.7717 | [6 empty] | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 3 | 9 | 18.3278 | 0.6348 | 0.0304 | 0.0304 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152750 | ELECTRICAL DUCT BANK LAYOUT DRAWING CENTRAL CONTROL BUILDING AREA | Layout Drawing |  | Electrical System | Central Control Building |  | Layout Drawing for Central Control Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8588 | 0.9576 | 0.9576 | g_safe | [5 empty] | FA | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 14 | 3 | 7.7465 | 0.5450 | 0.0294 | 0.0294 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152751 | ELECTRICAL DUCT BANK LAYOUT GTG #1 AREA | ELECTRICAL DUCT BANK LAYOUT | Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | g_ambig | uncertain | 0.55 |  | 1 | Document is electrical duct bank layout for GTG area, while the specific rule is for GT generator foundation embedded metals layout, and the relationship is not explicit. | FA | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | true | false | 2 | 1 | 11.7313 | 0.6606 | 0.0325 | 0.0244 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152752 | ELECTRICAL DUCT BANK LAYOUT GTG #2 AREA | ELECTRICAL DUCT BANK LAYOUT | Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | g_ambig | uncertain | 0.55 |  | 1 | Document is electrical duct bank layout for GTG area, while the specific rule is for GT generator foundation embedded metals layout, and the relationship is not explicit. | FA | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | true | false | 3 | 5 | 12.2760 | 0.6513 | 0.0313 | 0.0234 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152753 | ELECTRICAL DUCT BANK LAYOUT GTG #3,#4 AREA | ELECTRICAL DUCT BANK LAYOUT | Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | g_ambig | uncertain | 0.55 |  | 1 | Document is electrical duct bank layout for GTG area, while the specific rule is for GT generator foundation embedded metals layout, and the relationship is not explicit. | FA | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | true | false | 3 | 2 | 12.2996 | 0.6382 | 0.0320 | 0.0240 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152754 | ELECTRICAL DUCT BANK LAYOUT GTG #5 AREA | ELECTRICAL DUCT BANK LAYOUT | Gas Turbine Generator |  |  |  | ELECTRICAL DUCT BANK LAYOUT for GTG |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9055 | 0.9717 | 0.9717 | g_ambig | uncertain | 0.55 |  | 1 | Document is electrical duct bank layout for GTG area, while the specific rule is for GT generator foundation embedded metals layout, and the relationship is not explicit. | FA | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-08-01 | 2007-11-27 | design_drawing | civil_design | compatible | gtg | electrical | gtg | query | gtg | match | true | false | 9 | 1 | 10.4895 | 0.6530 | 0.0309 | 0.0232 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;rule_generic_judge=uncertain | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152755 | ELECTRICAL DUCT BANK LAYOUT HRSG #1 AREA | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 17 | 1 | 17.7009 | 0.6858 | 0.0294 | 0.0220 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152756 | ELECTRICAL DUCT BANK LAYOUT HRSG #2 AREA | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 2EF1615W00A02.1 | (HRSG #22 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | 2007-05-30 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 6 | 2 | 19.2779 | 0.6875 | 0.0313 | 0.0235 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152757 | ELECTRICAL DUCT BANK LAYOUT HRSG #3,#4 AREA | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 5 | 3 | 19.4542 | 0.6758 | 0.0313 | 0.0234 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-03-11 | 2025-04-10 | 2025-05-10 | 2025-05-25 | 2025-06-09 | 2025-06-24 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152758 | ELECTRICAL DUCT BANK LAYOUT HRSG #5 AREA | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | design_drawing | civil_design | compatible | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 15 | 4 | 17.7009 | 0.6675 | 0.0290 | 0.0217 | hybrid | structured_preferred | hrsg | system_design¦civil_design | 10 | 2025-03-11 | 2025-04-10 | 2025-05-10 | 2025-05-25 | 2025-06-09 | 2025-06-24 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152759 | ELECTRICAL DUCT BANK LAYOUT AIR COMPRESSOR & ACC AREA | Layout Drawing | AIR COMPRESSOR & Air Cooled Condenser | Compressed Air System |  |  | Layout Drawing for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.6746 | 0.7274 | 0.7274 | [6 empty] | FA | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | design_drawing | civil_design | compatible | acc¦compressed_air | acc¦electrical | acc¦compressed_air | query | compressed_air | match | true | false | 5 | 3 | 31.8598 | 0.6395 | 0.0313 | 0.0234 | hybrid | structured_cell_found_text_preferred | acc¦compressed_air | system_design¦civil_design |  | 2025-03-18 | 2025-04-17 | 2025-05-17 | 2025-06-01 | 2025-06-16 | 2025-07-01 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152760 | ELECTRICAL DUCT BANK LAYOUT ST #1 LEB | Layout Drawing | Steam Turbine | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8813 | 0.9644 | 0.9644 | g_safe | [5 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 6 | 1 | 9.6592 | 0.6317 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152761 | ELECTRICAL DUCT BANK LAYOUT ST #2 LEB | Layout Drawing | Steam Turbine | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8730 | 0.9619 | 0.9619 | g_safe | [5 empty] | FA | 2EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 3 | 3 | 10.3608 | 0.6304 | 0.0317 | 0.0317 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152762 | ELECTRICAL DUCT BANK LAYOUT TANK AREA | Layout Drawing | TANK | Electrical System |  |  | Layout Drawing for Tank |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9305 | 0.9791 | 0.9791 | g_safe | [5 empty] | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 12 | 16 | 5.6043 | 0.5360 | 0.0270 | 0.0203 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152763 | ELECTRICAL DUCT BANK LAYOUT WATER TREATMENT BUILDING AREA | Layout Drawing |  | Water Treatment System | Water Treatment Building |  | Layout Drawing for Water Treatment Building | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7016 | 0.6771 | 0.6771 | [6 empty] | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | true | false | 4 | 4 | 27.0998 | 0.6117 | 0.0312 | 0.0312 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152764 | ELECTRICAL DUCT BANK LAYOUT CPP REGEN BUILDING AREA | Layout Drawing |  | Condensate System |  |  | Layout Drawing for Condensate System |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8508 | 0.9552 | 0.9552 | g_safe | [5 empty] | FA | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate¦electrical | electrical | condensate¦electrical | query | condensate | match | false | false | 9 | 1 | 6.7949 | 0.5928 | 0.0309 | 0.0309 | hybrid | structured_preferred | condensate¦electrical | civil_design | 10 | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152765 | ELECTRICAL DUCT BANK LAYOUT FGS & RESERVE BOILER AREA | Layout Drawing | RESERVE BOILER | Fuel Gas System |  |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fuel¦gas¦reserve_boiler | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7646 | 0.6960 | 0.6960 | [6 empty] | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | design_drawing | civil_design | compatible | fgp¦reserve_boiler | fgp | fgp¦reserve_boiler | query | fgp | match | false | false | 5 | 6 | 13.7132 | 0.6072 | 0.0305 | 0.0229 | hybrid | structured_cell_found_text_preferred | fgp¦reserve_boiler | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152766 | ELECTRICAL DUCT BANK LAYOUT ADMINISTRATION & SOCIAL BUILDING AREA | Layout Drawing |  | Electrical System | Administration & Social Building |  | Layout Drawing for Administration & Social Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8395 | 0.9519 | 0.9519 | g_safe | [5 empty] | FA | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 6 | 3 | 7.7465 | 0.5315 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152767 | ELECTRICAL DUCT BANK LAYOUT SECURITY BUILDING AREA | Layout Drawing |  | Electrical System | Security Building |  | Layout Drawing for Security Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8811 | 0.9643 | 0.9643 | g_safe | [5 empty] | FA | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-11-29 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 6 | 2 | 7.7465 | 0.5439 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152768 | ELECTRICAL DUCT BANK LAYOUT MAIN GATE HOUSE AREA | Layout Drawing |  | Electrical System | Security Building |  | Layout Drawing for Security Building |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8816 | 0.9645 | 0.9645 | g_safe | [5 empty] | FA | 1CF6500W16A02 | (GTG TR) FDN & Firewall Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-12-01 | 2008-04-01 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 20 | 14 | 5.5432 | 0.5168 | 0.0260 | 0.0260 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-09-02 | 2024-10-02 | 2024-11-01 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152769 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 1 | Layout Drawing | Extra High Voltage CABLE | Electrical System |  |  | Layout Drawing for Electrical System |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8644 | 0.9593 | 0.9593 | g_safe | [5 empty] | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 1 | 1 | 43.2720 | 0.6578 | 0.0328 | 0.0246 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152770 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 2 | Layout Drawing | Extra High Voltage CABLE | Electrical System |  |  | Layout Drawing for Electrical System |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8635 | 0.9591 | 0.9591 | g_safe | [5 empty] | FA | 2CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 2 | 2 | 43.9688 | 0.6638 | 0.0323 | 0.0242 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152771 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 3 | Layout Drawing | Extra High Voltage CABLE | Electrical System |  |  | Layout Drawing for Electrical System |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8639 | 0.9592 | 0.9592 | g_safe | [5 empty] | FA | 3CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 2 | 2 | 43.9990 | 0.6591 | 0.0323 | 0.0242 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152791 | RACEWAY DRAWING FOR HCIS – MAIN GATE HOUSE | RACEWAY DRAWING |  |  | Security Building |  | RACEWAY DRAWING for Security Building |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6578 | 0.6640 | 0.6640 | g_safe | [5 empty] | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 9 | 7 | 17.1992 | 0.5072 | 0.0294 | 0.0177 | hybrid | structured_no_system |  | civil_design |  | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152792 | RACEWAY DRAWING FOR HCIS – PLANT ACCESS GATE HOUSE | RACEWAY DRAWING |  |  | PLANT ACCESS GATE HOUSE |  | RACEWAY DRAWING for PLANT ACCESS GATE HOUSE |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | access¦gate¦house¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6921 | 0.6743 | 0.6743 | g_safe | [5 empty] | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 9 | 7 | 17.1995 | 0.5316 | 0.0294 | 0.0132 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 |  | false | false | 0.35 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152793 | RACEWAY DRAWING FOR HCIS – SEARCH FACILITY & VISITOR CENTRE | RACEWAY DRAWING |  |  | Security Building |  | RACEWAY DRAWING for Security Building |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6578 | 0.6640 | 0.6640 | g_safe | [5 empty] | FA | 0EF5570W32A03.1 | (Convered Parking Place shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-15 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1336 | 13 |  | 0.4367 | 0.0144 | 0.0086 | hybrid | structured_no_system |  | civil_design |  | 2024-12-27 | 2025-01-26 | 2025-02-25 | 2025-03-12 | 2025-03-27 | 2025-04-11 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152794 | RACEWAY DRAWING FOR HCIS – SUPPORT BUILDING | RACEWAY DRAWING |  |  | Support Building |  | RACEWAY DRAWING for Support Building |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7158 | 0.6814 | 0.6814 | g_safe | [5 empty] | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 1072 | 71 | 2.4495 | 0.4382 | 0.0085 | 0.0064 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152795 | RACEWAY DRAWING FOR HCIS – PRELIMINARY INSPECTION CHECKPOINT | RACEWAY DRAWING |  |  |  |  | RACEWAY DRAWING |  | RaceWay plan draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7881 | 0.7031 | 0.7031 | [6 empty] | FA | 1CF3030W16A18 | (CCWP) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-01-31 | 2008-03-28 | design_drawing | civil_design | compatible |  |  |  |  | ccw | query_unscoped | false | false | 550 | 211 | 3.3799 | 0.4149 | 0.0053 | 0.0030 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-152801 | SIZING CALCULATION - MV/LV POWER CABLES | Calculation sheet | Medium Voltage/Low Voltage POWER CABLES |  |  |  | Calculation sheet for Medium Voltage/Low Voltage POWER CABLES | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | cables¦low¦medium¦power¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7350 | 0.5705 | 0.5705 | g_safe | [5 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | false | 48 | 15 | 12.4416 | 0.4994 | 0.0226 | 0.0169 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152810 | SIZING CALCULATION - 380KV EHV CABLE AND ACCESSOIRES | Calculation sheet | 380KV Extra High Voltage CABLE AND ACCESSOIRES |  |  |  | Calculation sheet for 380KV Extra High Voltage CABLE AND ACCESSOIRES | Substation | Cable Sizing Calculation | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | calculation | calculation | sizing_calculation | sizing_calculation | 380kv¦accessoires¦cable¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6928 | 0.7329 | 0.7329 | g_safe | [5 empty] | SKIP | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 21 | 8 | 36.1401 | 0.5846 | 0.0271 | 0.0203 | hybrid | structured_no_system |  | civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152820 | TECHNICAL SPECIFICATION - 380KV EHV CABLE AND ACCESSORIES | Technical Specification | 380KV Extra High Voltage CABLE AND ACCESSORIES |  |  |  | Technical Specification for 380KV Extra High Voltage CABLE AND ACCESSORIES |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | 380kv¦accessories¦cable¦extra¦high¦voltage |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6540 | 0.6629 | 0.4640 | g_safe | [5 empty] | FA | 1EF6040W74A05 | (EHV Cable) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable |  | 2007-05-01 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 7 | 50.8237 | 0.6499 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0ZEN-152822 | OUTLINE & SCHEMATIC DRAWING - 380KV EHV CABLE AND ACCESSOIRES | OUTLINE & SCHEMATIC DRAWING | 380KV Extra High Voltage CABLE AND ACCESSOIRES |  |  |  | OUTLINE & SCHEMATIC DRAWING for 380KV Extra High Voltage CABLE AND ACCESSOIRES |  | OUTLINE & SCHEMATIC DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | 380kv¦accessoires¦cable¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7234 | 0.9170 | 0.6419 | g_safe | [5 empty] | FA | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 22 | 12 | 36.1401 | 0.6012 | 0.0261 | 0.0147 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152823 | INSTALLATION DRAWING - 380KV EHV CABLE AND ACCESSOIRES | INSTALLATION DRAWING | 380KV Extra High Voltage CABLE AND ACCESSOIRES |  |  |  | INSTALLATION DRAWING for 380KV Extra High Voltage CABLE AND ACCESSOIRES |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | 380kv¦accessoires¦cable¦extra¦high¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5999 | 0.6466 | 0.6466 | g_safe | [5 empty] | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 21 | 8 | 36.1401 | 0.5995 | 0.0271 | 0.0152 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-12-28 | 2025-01-27 | 2025-02-26 | 2025-03-13 | 2025-03-28 | 2025-04-12 | generated | 0.90 |  | false | false | 0.43 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152830 | TECHNICAL SPECIFICATION - POWER & CONTROL & F/O CABLE | Technical Specification | POWER & CONTROL & F/O CABLE |  |  |  | Technical Specification for POWER & CONTROL & F/O CABLE |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | cable¦power |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7686 | 0.6973 | 0.6973 | g_safe | [5 empty] | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 1 | 35.0262 | 0.6846 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152840 | TECHNICAL SPECIFICATION - CABLING ACCESSORIES | Technical Specification |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | [6 empty] | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | false | 15 | 9 | 8.6256 | 0.5057 | 0.0278 | 0.0209 | hybrid | structured_no_system |  | procurement |  | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-152850 | POWER CABLE SCHEDULE | Schedule | POWER CABLE |  |  |  | Schedule for POWER CABLE |  | POWER CABLE SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | list | list | cable_schedule | cable_schedule | cable¦power |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 1 | 8 | 18.4512 | 0.4723 | 0.0311 | 0.0175 | hybrid | structured_no_system |  |  |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-152860 | CONTROL CABLE SCHEDULE | Schedule | CONTROL CABLE |  |  |  | Schedule for CONTROL CABLE |  | CONTROL CABLE SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | list | list | cable_schedule | cable_schedule | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 0CF6040W74A05.1 | (Electrical Cable) Cable Pulling for CCB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2008-05-10 | 2008-05-20 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 1 | 2 | 24.8983 | 0.5334 | 0.0325 | 0.0183 | hybrid | structured_no_system |  |  |  | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-03-12 | 2025-04-11 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152870 | TECHNICAL SPECIFICATION - FIRE STOP MATERIAL | Technical Specification |  |  |  |  | Technical Specification |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.8090 | 0.5227 | 0.5227 | [6 empty] | FA | 0EF4500W38A02 | (Fire Fighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 2 | 1 | 17.3684 | 0.5334 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-05-15 | 2024-06-14 | 2024-07-14 | 2024-07-29 | 2024-08-13 | 2024-08-28 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0CY-154001 | TECHNICAL SPECIFICATION - COMMUNICATION SYSTEM | Technical Specification |  | COMMUNICATION SYSTEM |  |  | Technical Specification for COMMUNICATION SYSTEM |  | TECHNICAL SPECIFICATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | specification | specification | technical_specification | technical_specification | communication |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.7527 | 0.6925 | 0.4847 | g_safe | [5 empty] | FA | 0EF6040W74A01 | (Raceway) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System |  | 2007-07-02 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | false | 3 | 11 | 9.4111 | 0.4157 | 0.0300 | 0.0225 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-04 | 2024-03-19 | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | fa_earliest | false | false | 0.54 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYA-154011 | CONFIGURATION DIAGRAM - OFFICE TELEPHONE & LAN SYSTEM | CONFIGURATION DIAGRAM |  |  |  |  | CONFIGURATION DIAGRAM |  | DCS - LAN Configuration Diagram | 1 | start+121D<=FA<=start+121D+2M | FA ∈ [start+121d, start+181d] | title | diagram | diagram | diagram | diagram |  | dcs | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6103 | 0.7081 | 0.7081 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | dcs | dcs | rule |  | activity_unscoped | true | true | 1 | 209 | 15.5211 | 0.4132 | 0.0201 | 0.0060 | hybrid | structured_phase_gap | dcs | system_design¦engineering | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYM-154013 | CONFIGURATION DIAGRAM - PUBLIC ADDRESS SYSTEM (SIREN SYSTEM) | CONFIGURATION DIAGRAM |  |  |  |  | CONFIGURATION DIAGRAM |  | HRSG - System Configuration Diagram | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | title | diagram | diagram | diagram | diagram |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.5000 | 0.6750 | 0.6750 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match |  | hrsg | hrsg | rule | hrsg | match | false | false | 1 | 2 | 12.2016 | 0.4149 | 0.0325 | 0.0325 | hybrid | structured_preferred | hrsg | system_design¦engineering | 6 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0CY-154021 | TYPICAL INSTALLATION DRAWING - COMMUNICATION SYSTEM | TYPICAL INSTALLATION DRAWING |  | COMMUNICATION SYSTEM |  |  | TYPICAL INSTALLATION DRAWING for COMMUNICATION SYSTEM |  | TYPICAL INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | communication |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8205 | 0.9461 | 0.6623 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | false | 970 | 39 | 1.3501 | 0.4580 | 0.0111 | 0.0062 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154031 | COMMUNICATION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | Layout Drawing |  | COMMUNICATION | Central Control Building |  | Layout Drawing for Central Control Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8491 | 0.9547 | 0.6683 | g_safe | [5 empty] | FA | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 6 | 2 | 18.3850 | 0.6302 | 0.0313 | 0.0188 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154032 | COMMUNICATION LAYOUT DRAWING - GTG #1,2 LEB | Layout Drawing |  | COMMUNICATION | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8346 | 0.9504 | 0.6653 | g_ambig | generic_ok | 0.85 |  | 1 | Competing specific rule is for GT generator foundation embedded metals, which is unrelated to a communication layout drawing deliverable. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 4 | 1 | 8.7678 | 0.5914 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154033 | COMMUNICATION LAYOUT DRAWING - GTG #3,4,5 LEB | Layout Drawing |  | COMMUNICATION | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8277 | 0.9483 | 0.6638 | g_ambig | generic_ok | 0.85 |  | 1 | Competing specific rule is for GT generator foundation embedded metals, which is unrelated to a communication layout drawing deliverable. | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 6 | 2 | 7.6178 | 0.5655 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154034 | COMMUNICATION LAYOUT DRAWING - ST #1 LEB | Layout Drawing |  | COMMUNICATION | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8444 | 0.9533 | 0.6673 | g_safe | [5 empty] | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 3 | 38 | 4.3991 | 0.3722 | 0.0261 | 0.0261 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154035 | COMMUNICATION LAYOUT DRAWING - ST #2 LEB | Layout Drawing | Steam Turbine #2 | COMMUNICATION | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8435 | 0.9530 | 0.6671 | g_safe | [5 empty] | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 1 | 6 | 12.9805 | 0.5839 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154036 | COMMUNICATION LAYOUT DRAWING - ST BUILDING | Layout Drawing | Steam Turbine | COMMUNICATION | Steam Turbine Building |  | Layout Drawing for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6641 | 0.6192 | 0.6192 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 9 | 9.1380 | 0.5796 | 0.0309 | 0.0309 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154037 | COMMUNICATION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | Layout Drawing |  | COMMUNICATION | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7072 | 0.6788 | 0.6788 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 10.8160 | 0.5386 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154038 | COMMUNICATION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | Layout Drawing |  | COMMUNICATION | Administration & Social Building |  | Layout Drawing for Administration & Social Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7931 | 0.9379 | 0.6566 | g_safe | [5 empty] | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 6 | 2 | 15.1429 | 0.5983 | 0.0313 | 0.0188 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154039 | COMMUNICATION LAYOUT DRAWING - SECURITY BUILDING | Layout Drawing |  | COMMUNICATION | Security Building |  | Layout Drawing for Security Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8361 | 0.9508 | 0.6656 | g_safe | [5 empty] | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 10 | 8 | 4.2752 | 0.4907 | 0.0290 | 0.0174 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154040 | COMMUNICATION LAYOUT DRAWING – MAIN GATE & PLANT ACCESS GATE HOUSE | Layout Drawing |  | COMMUNICATION | MAIN GATE & PLANT ACCESS GATE HOUSE |  | Layout Drawing for MAIN GATE & PLANT ACCESS GATE HOUSE |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | access¦gate¦house¦main¦plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7788 | 0.9337 | 0.6536 | g_safe | [5 empty] | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 1 | 26.3714 | 0.5709 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 |  | false | false | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154041 | COMMUNICATION LAYOUT DRAWING - SUPPORT BUILDING | Layout Drawing |  | COMMUNICATION | Support Building |  | Layout Drawing for Support Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8587 | 0.9576 | 0.6703 | g_safe | [5 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 23 | 24.0608 | 0.4679 | 0.0282 | 0.0169 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154042 | COMMUNICATION LAYOUT DRAWING - X-RAY SEARCHING ROOM | Layout Drawing |  | COMMUNICATION | X-RAY SEARCHING ROOM |  | Layout Drawing for X-RAY SEARCHING ROOM |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ray¦room¦searching |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7759 | 0.9328 | 0.6529 | g_safe | [5 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 96 | 24.0608 | 0.3633 | 0.0225 | 0.0101 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154044 | COMMUNICATION LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | Layout Drawing |  | COMMUNICATION | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦fire_protection¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7598 | 0.9279 | 0.6495 | g_safe | [5 empty] | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | false | false | 5 | 1 |  | 0.4469 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154045 | COMMUNICATION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | Layout Drawing |  | COMMUNICATION | Workshop & Storage Building |  | Layout Drawing for Workshop & Storage Building |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8191 | 0.9457 | 0.6620 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 34 | 1 | 9.7017 | 0.5535 | 0.0270 | 0.0203 | hybrid | structured_no_system |  | civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154049 | COMMUNICATION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | Layout Drawing |  | COMMUNICATION | Fire Water Pump House |  | Layout Drawing for Fire Water Pump House |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | fire¦fire_protection¦house¦pump¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7991 | 0.9397 | 0.6578 | g_ambig | generic_ok | 0.85 |  | 2 | Competing specifics are for I&C junction box/panel layout drawings, not communication layout drawings. | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | design_drawing | civil_design | compatible | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 13.5235 | 0.5220 | 0.0325 | 0.0244 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154051 | COMMUNICATION LAYOUT DRAWING - WATER TREATMENT BUILDING | Layout Drawing |  | COMMUNICATION | Water Treatment Building |  | Layout Drawing for Water Treatment Building | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7016 | 0.6771 | 0.6771 | [6 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | true | false | 8 | 1 | 12.7557 | 0.5940 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154052 | COMMUNICATION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | Layout Drawing |  | COMMUNICATION | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | Layout Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | condensate¦plant¦polising¦regeneration |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8097 | 0.9429 | 0.6600 | g_safe | [5 empty] | FA | 1EF3020W16A09 | (COND Flash Box) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-01-02 | 2008-03-31 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 4 | 3 |  | 0.3785 | 0.0315 | 0.0315 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-10-04 | 2024-11-03 | 2024-12-03 | generated | 0.30 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154053 | COMMUNICATION LAYOUT DRAWING – PIPE RACK | Layout Drawing |  | COMMUNICATION | Pipe Rack |  | Layout Drawing for Pipe Rack |  | COMMUNICATION LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8414 | 0.9524 | 0.6667 | g_safe | [5 empty] | FA | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 15 | 3 | 16.5373 | 0.6441 | 0.0292 | 0.0219 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0ASS-155001 | RELAY SETTING CALCULATION OF 380kV SYNCHRONIZING SYSTEM | Calculation sheet |  | SYNCHRONIZING SYSTEM |  |  | Calculation sheet for SYNCHRONIZING SYSTEM | Chemical Dosing System | Calculation Sheet | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | synchronizing |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6051 | 0.6015 | 0.6015 | g_safe | [5 empty] | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  | wts | wts | rule | wts | match | false | false | 6 | 4 | 1.2375 | 0.3663 | 0.0308 | 0.0308 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155011 | RELAY SETTING CALCULATION FOR GTG1 & GTG2 CABLE PROTECTION | Calculation sheet | GTG1 & GTG2 |  |  |  | Calculation sheet for GTG1 & GTG2 | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation | gtg1¦gtg2 |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5442 | 0.5133 | 0.5133 | g_safe | [5 empty] | FA | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | civil_design | civil_design | match |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | false | 2487 | 6 |  | 0.5601 | 0.0155 | 0.0117 | hybrid | structured_no_system |  | civil_design |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155012 | RELAY SETTING CALCULATION FOR GTG #3, 4, 5 CABLE PROTECTION | Calculation sheet | Gas Turbine Generator #3, 4, 5 |  |  |  | Calculation sheet for Gas Turbine Generator #3, 4, 5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5739 | 0.6388 | 0.6388 | [6 empty] | FI | 3EF1210W20A09 | (GTG Common BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-08-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 13 | 19 | 9.3352 | 0.5182 | 0.0264 | 0.0264 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155013 | RELAY SETTING CALCULATION FOR STG #1, 2 CABLE PROTECTION | Calculation sheet | Steam Turbine Generator #1, 2 |  |  |  | Calculation sheet for Steam Turbine Generator #1, 2 |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.4770 | 0.5631 | 0.5631 | [6 empty] | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 1 | 9 | 14.4357 | 0.5592 | 0.0309 | 0.0309 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155014 | RELAY SETTING CALCULATION FOR 13.8kV CABLE PROTECTION – COGEN TO ESF | Calculation sheet |  |  |  |  | Calculation sheet | FloW element | FloW Calculation sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6392 | 0.5418 | 0.5418 | [6 empty] | FA | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 77 | 15 | 8.4510 | 0.4746 | 0.0206 | 0.0155 | hybrid | structured_no_system |  | civil_design |  | 2024-08-16 | 2024-09-15 | 2024-10-15 | 2024-10-30 | 2024-11-14 | 2024-11-29 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0ZEN-161001 | DESIGN CRITERIA FOR GENERAL I&C SYSTEM | DESIGN CRITERIA |  | GENERAL Instrumentation and Control SYSTEM |  |  | DESIGN CRITERIA for GENERAL Instrumentation and Control SYSTEM | Chemical Dosing System | Design Criteria | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | criteria | criteria | design_criteria | design_criteria | instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.5625 | 0.5887 | 0.5887 | g_safe | [5 empty] | FA | 0EF4035W00A01 | (STS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-04-02 | 2007-12-07 | design_criteria | system_design | compatible |  | wts | wts | rule | wts | match | false | false | 5 | 2 | 16.6068 | 0.4489 | 0.0315 | 0.0236 | hybrid | structured_preferred | wts | design_criteria¦system_design¦civil_design | 10 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 |  | false | false | 0.22 | needs_review_activity | default_fc_window;activity_phase_status=compatible;activity_equipment_unconfirmed;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0ZEN-161011 | MASTER CLOCK CONCEPT DIAGRAM | Diagram |  |  |  |  | Diagram |  | MASTER CONTROL DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6714 | 0.6681 | 0.4677 | [6 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | false | 15 | 57 | 9.8679 | 0.3012 | 0.0219 | 0.0123 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161021 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM – SYMBOL & LEGEND | Diagram |  |  |  |  | Diagram |  | Plant start-up & ShutdoWn Sequence Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8459 | 0.9538 | 0.6676 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | false | 15 | 3 | 10.0270 | 0.5373 | 0.0292 | 0.0164 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161022 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR START - UP | Diagram |  |  |  |  | Diagram |  | Plant start-up & ShutdoWn Sequence Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8887 | 0.9666 | 0.6766 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | false | 86 | 14 | 10.0270 | 0.4841 | 0.0204 | 0.0115 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161025 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR SHUTDOWN | Diagram |  |  |  |  | Diagram |  | Plant start-up & ShutdoWn Sequence Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8662 | 0.9599 | 0.6719 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | false | 28 | 12 | 10.0270 | 0.4794 | 0.0253 | 0.0142 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0ZEN-161031 | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | Diagram |  | PLANT CONTROL SYSTEM |  |  | Diagram for PLANT CONTROL SYSTEM |  | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | plant |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  |  |  |  | compressed_air | query_unscoped | false | false | 11 | 5 | 11.2184 | 0.5440 | 0.0295 | 0.0221 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJA-161041 | PLANT MASTER CONTROL DIAGRAM | Diagram |  |  |  |  | Diagram |  | Plant Master Control Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8924 | 0.9677 | 0.6774 | [6 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | design_drawing | system_design | compatible |  |  |  |  | compressed_air | query_unscoped | false | false | 15 | 16 | 9.8681 | 0.4877 | 0.0265 | 0.0149 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF01-P0BYA-161051 | PLANT PROTECTION & INTERLOCK DIAGRAM | Diagram |  |  |  |  | Diagram |  | PLANT PROTECTION & INTERLOCK DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9992 | 0.9998 | 0.6998 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 10 | 46 | 10.1912 | 0.4608 | 0.0237 | 0.0133 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0CBA-161101 | DCS I/O DATABASE | DATABASE | Distributed Control System |  |  |  | DATABASE for Distributed Control System | H2, CO2 Supply System | Input/Output database (included internal I/O) | 1 | start+2M<= FA<=start + 2M+2M | FA ∈ [start+60d, start+120d] | rule_query | data | data | data | data | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.2222 | 0.5355 | 0.3162 | 0.3162 | g_safe | [5 empty] | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs | h2 | dcs | query | dcs | match | true | false | 2 | 1 | 33.5255 | 0.7497 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0CRV-161102 | DCS - LAN CONFIGURATION DIAGRAM | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | DCS - LAN Configuration Diagram | 1 | start+121D<=FA<=start+121D+2M | FA ∈ [start+121d, start+181d] | title | diagram | diagram | diagram | diagram | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.9764 | 0.9929 | 0.9929 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs | dcs | dcs | query |  | activity_unscoped | true | true | 11 | 86 | 15.5211 | 0.4595 | 0.0209 | 0.0126 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-07-14 | 2024-08-13 | 2024-09-12 | 2024-09-27 | 2024-10-12 | 2024-10-27 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=activity_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161103 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HARDWARE | FUNCTIONAL DESIGN SPECIFICATION | Distributed Control System |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for Distributed Control System |  | Functional Design Specification for SoftWare | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | specification | specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6818 | 0.7645 | 0.7645 | g_ambig | use_specific | 0.95 | DCS - Functional Design Specification for HarDWare | 9 | Title explicitly matches the DCS hardware FDS specific rule, which has a different VT than the generic software FDS rule. | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 2 | 1 | 34.7167 | 0.6961 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161104 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR SOFTWARE | FUNCTIONAL DESIGN SPECIFICATION | Distributed Control System |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for Distributed Control System |  | Functional Design Specification for SoftWare | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | specification | specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6818 | 0.7645 | 0.7645 | g_ambig | use_specific | 0.95 | DCS - Functional Design Specification for HarDWare | 9 | Title explicitly matches the DCS hardware FDS specific rule, which has a different VT than the generic software FDS rule. | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 2 | 1 | 34.7167 | 0.7073 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161105 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HMI GRAPHIC | FUNCTIONAL DESIGN SPECIFICATION | Distributed Control System |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for Distributed Control System |  | Functional Design Specification for SoftWare | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | specification | specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6818 | 0.7645 | 0.7645 | g_ambig | use_specific | 0.95 | DCS - Functional Design Specification for HarDWare | 9 | Title explicitly matches the DCS hardware FDS specific rule, which has a different VT than the generic software FDS rule. | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 2 | 1 | 34.7167 | 0.6836 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0CUQ-161111 | DCS POWER DISTRIBUTION CONCEPT DIAGRAM | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | PoWer Distribution Concept Diagram | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | title | diagram | diagram | power_distribution_diagram | power_distribution_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7536 | 0.9261 | 0.9261 | g_ambig | use_specific | 0.90 | DCS POWER DISTRIBUTION DIAGRAMS | 1 | Document is a DCS power distribution concept diagram and the competing specific rule explicitly targets DCS power distribution diagrams with a different timeline. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | true | 11 | 85 | 15.5212 | 0.4900 | 0.0210 | 0.0094 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.35 | needs_review | default_fc_window;rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=use_specific |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CUQ-161112 | DCS - POWER DISTRIBUTION DRAWING | DRAWING | Distributed Control System |  |  |  | DRAWING for Distributed Control System |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7250 | 0.7425 | 0.7425 | g_safe | [5 empty] | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | design_drawing | system_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | true | 454 | 173 | 5.9566 | 0.5086 | 0.0062 | 0.0028 | hybrid | structured_phase_gap | dcs | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CRN-161113 | DCS - IO & MODULE ALLOCATION | ALLOCATION | Distributed Control System |  |  |  | ALLOCATION for Distributed Control System | [5 empty] | rule_query | other | other | allocation | distributed_control_system | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.7472 | 0.9242 | 0.6469 | [7 empty] | 0CF7000W86A04 | (DCS) Installation for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-02 | 2008-06-16 |  | installation | query_unknown | dcs |  | dcs | query | dcs | match | true | false | 4 | 2 | 23.8752 | 0.6284 | 0.0318 | 0.0238 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0CRN-161114 | DCS - INTERNAL CABLE CONNECTION DIAGRAM | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System | FireFighting | Cable Connection Diagram | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | title | diagram | diagram | diagram | diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6613 | 0.7234 | 0.7234 | g_ambig | uncertain | 0.55 |  | 3 | ‘DCS - INTERNAL CABLE CONNECTION DIAGRAM’ could align with generic cable connection or with the more specific JB/PCP-to-DCS or terminal block rules, but the scope is not explicit. | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | true | 27 | 53 | 13.1789 | 0.4838 | 0.0203 | 0.0092 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-08-02 | 2024-08-30 | 2024-09-27 | 2024-09-20 | 2024-10-18 | 2024-11-15 | generated | 0.90 |  | false | false | 0.38 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0CRN-161115 | DCS - CABLE LIST | LIST | Distributed Control System |  |  |  | LIST for Distributed Control System | [5 empty] | rule_query | other | other | list | distributed_control_system | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.7651 | 0.9295 | 0.6507 | [7 empty] | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 1 | 1 | 23.8752 | 0.5681 | 0.0328 | 0.0328 | hybrid | structured_preferred | dcs | procurement | 3 | [6 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0CRN-161116 | DCS - HMI GRAPHIC DISPLAY DIAGRAM | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | HMI GRAPHIC DISPLAY DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8742 | 0.9623 | 0.6736 | g_ambig | uncertain | 0.55 |  | 2 | The document title is generic HMI graphic display, while the competing specifics are LAN configuration and panel terminal block/cable connection details, so the intended specific scope is unclear. | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | dcs |  | dcs | query |  | activity_unscoped | true | true | 19 | 26 | 10.8582 | 0.4638 | 0.0243 | 0.0109 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | rule_scope_status=rule_generic;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0CRN-161117 | 3RD PARTY DATA - LINK INTERFACE SIGNAL DATABASE | DATABASE |  |  |  |  | DATABASE |  | LINK INTERFACE SIGNAL DATABASE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | data | data | data | data |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8030 | 0.9409 | 0.6586 | [6 empty] | FA | 0SF6500W62A01 | (Power Receiving) Interface signal Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-08-01 | 2008-08-02 |  | commissioning | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 1 | 1 | 24.5916 | 0.4312 | 0.0328 | 0.0184 | hybrid | structured_no_system |  |  |  | 2025-03-20 | 2025-04-04 | 2025-04-19 | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0CUQ-161118 | I&C GROUNDING CONCEPT DIAGRAM | Diagram |  | Instrumentation and Control |  |  | Diagram for Instrumentation and Control |  | I&C GROUNDING CONCEPT DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | instrumentation |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | electrical | electrical | electrical | query |  | activity_unscoped | true | true | 3 | 42 | 17.3642 | 0.5041 | 0.0257 | 0.0116 | hybrid | structured_phase_gap | electrical | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CUQ-161119 | DCS - GROUNDING DRAWING | DRAWING | Distributed Control System | GROUNDING |  |  | DRAWING for Distributed Control System |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7250 | 0.7425 | 0.7425 | g_safe | [5 empty] | FI | 0EF5544W16A09 | (GIS BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | design_drawing | civil_design | compatible | dcs¦electrical |  | dcs¦electrical | query | electrical | discipline_only | true | false | 21 | 8 | 0.4744 | 0.4876 | 0.0271 | 0.0101 | hybrid | structured_preferred | dcs¦electrical | system_design¦civil_design | 10 | 2024-07-19 | 2024-08-18 | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-11-01 | generated | 0.90 |  | false | false | 0.27 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=discipline_only;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161121 | DCS - PERFORMANCE MONITORING SYSTEM |  | Distributed Control System | PERFORMANCE MONITORING SYSTEM |  |  | for Distributed Control System | [5 empty] | rule_query | other | other | dcs_performance_monitoring_system | distributed_control_system | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.9312 | 0.9793 | 0.6855 | [7 empty] | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 |  | procurement | query_unknown | dcs |  | dcs | query | dcs | match | true | false | 3 | 1 | 24.8689 | 0.6568 | 0.0323 | 0.0242 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161122 | DCS - PLANT INFORMATION HISTORIAN | Plan | Distributed Control System | PLANT INFORMATION HISTORIAN |  |  | Plan for Distributed Control System |  | Control Oil FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4002 | 0.4701 | 0.4701 | g_safe | [5 empty] | FA | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 |  |  | query_unknown | dcs |  | dcs | query | dcs | match | true | false | 1 | 3 | 24.4089 | 0.6152 | 0.0323 | 0.0242 | hybrid | structured_no_phase | dcs | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161123 | DCS - FIELD INSTRUMENT MONITORING SYSTEM |  | Distributed Control System | FIELD INSTRUMENT MONITORING SYSTEM |  |  | for Distributed Control System | [5 empty] | rule_query | other | other | dcs_field_instrument_monitoring_system | distributed_control_system | dcs¦distributed | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.9312 | 0.9793 | 0.6855 | [7 empty] | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 |  |  | query_unknown | dcs |  | dcs | query | dcs | match | true | false | 1 | 2 | 41.8525 | 0.6688 | 0.0325 | 0.0244 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161132 | DCS - TECHNICAL SPECIFICATION FOR TIME SYNCHRONIZATION | Technical Specification | Distributed Control System |  |  |  | Technical Specification for Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5020 | 0.5006 | 0.5006 | g_safe | [5 empty] | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 1 | 1 | 35.1212 | 0.6507 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161133 | DCS - TECHNICAL SPECIFICATION FOR EMERGENCY PUSH BUTTON | Technical Specification | Distributed Control System |  |  |  | Technical Specification for Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5020 | 0.5006 | 0.5006 | g_safe | [5 empty] | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 2 | 1 | 34.7167 | 0.6437 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161134 | TECHNICAL SPECIFICATION & DATA SHEET FOR SETTLEMENT SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | SETTLEMENT SYSTEM |  |  | TECHNICAL SPECIFICATION & DATA SHEET for SETTLEMENT SYSTEM |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | settlement |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.5774 | 0.7332 | 0.7332 | g_safe | [5 empty] | FA | 1PF3030W68A04P | (EXP Head Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-30 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | false | 35 | 10 | 11.4927 | 0.4759 | 0.0248 | 0.0186 | hybrid | structured_no_system |  | procurement |  | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161135 | DCS - TECHNICAL SPECIFICATION FOR LARGE SCREEN DISPLAY | Technical Specification | Distributed Control System |  |  |  | Technical Specification for Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5020 | 0.5006 | 0.5006 | g_safe | [5 empty] | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 1 | 1 | 35.1212 | 0.6779 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161141 | DCS - OUTLINE & DETAIL DRAWING FOR DCS SYSTEM CABINET | OUTLINE & DETAIL DRAWING | Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for Provision Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.8571 | 0.8683 | 0.8605 | 0.8605 | [6 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | design_drawing | system_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | true | 874 | 25 | 3.5344 | 0.4876 | 0.0128 | 0.0058 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161142 | DCS - OUTLINE & DETAIL DRAWING FOR LAN/SERVER CABINET | OUTLINE & DETAIL DRAWING | Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for LAN/Server Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.9420 | 0.9826 | 0.9826 | [6 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | true | 506 | 16 | 4.1967 | 0.4871 | 0.0149 | 0.0067 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161143 | DCS - OUTLINE & DETAIL DRAWING FOR MARSHALLING CABINET | OUTLINE & DETAIL DRAWING | Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for Relay Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.8571 | 0.8573 | 0.8572 | 0.8572 | [6 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | true | 506 | 20 | 4.1967 | 0.4808 | 0.0143 | 0.0064 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161146 | DCS - OUTLINE & DETAIL DRAWING FOR DCS CONSOLE & DESK | OUTLINE & DETAIL DRAWING | Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for Provision Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 0.7143 | 0.8084 | 0.7425 | 0.7425 | [6 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | true | 506 | 17 | 4.1967 | 0.4847 | 0.0148 | 0.0066 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161147 | DCS - OUTLINE & DETAIL DRAWING FOR DCS POWER DISTRIBUTION CABINET | OUTLINE & DETAIL DRAWING | Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - Outline & Detail DraWing for PoWer Distribution Cabinet | 1 | start+212D<=FA<=start+212D+2M | FA ∈ [start+212d, start+272d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.9249 | 0.9775 | 0.9775 | [6 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs | dcs | query |  | activity_unscoped | true | true | 506 | 31 | 4.1968 | 0.5001 | 0.0128 | 0.0057 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161148 | DCS - OUTLINE & DETAIL DRAWING FOR DCS GROUNDING BOX | OUTLINE & DETAIL DRAWING | Distributed Control System |  |  |  | OUTLINE & DETAIL DRAWING for Distributed Control System |  | DCS - GrounDing Detail DraWing | 1 | start+230D<=FA<=start+230D+2M | FA ∈ [start+230d, start+290d] | title | drawing | drawing | detail_drawing | detail_drawing | dcs¦distributed | dcs | scoped | match | match | match | passed |  | 1.0000 | 0.7817 | 0.9345 | 0.9345 | [6 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | dcs | dcs¦electrical | dcs | query |  | activity_unscoped | true | true | 519 | 24 | 4.1967 | 0.5093 | 0.0136 | 0.0061 | hybrid | structured_phase_gap | dcs | system_design¦civil_design |  | 2024-11-18 | 2024-12-18 | 2025-01-17 | 2025-02-01 | 2025-02-16 | 2025-03-03 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRT-161149 | DCS - TECHNICAL SPECIFICATION FOR FIELDBUS MOV | Technical Specification | Distributed Control System |  |  |  | Technical Specification for Distributed Control System |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5020 | 0.5006 | 0.5006 | g_safe | [5 empty] | FA | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 | procurement | procurement | match | dcs |  | dcs | query | dcs | match | true | false | 3 | 1 | 31.6170 | 0.6432 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | dcs | procurement |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0CRU-161150 | INTEGRATED SAT(SITE ACCEPTANCE TEST) PROCEDURE FOR DCS | PROCEDURE | Distributed Control System |  |  |  | PROCEDURE for Distributed Control System |  | Site Acceptance Test Procedure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | test_procedure | test_procedure | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7121 | 0.9136 | 0.6395 | g_safe | [5 empty] | FA | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 | commissioning | commissioning | match | dcs |  | dcs | query | dcs¦electrical | match | true | false | 1 | 1 | 29.5256 | 0.6768 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | dcs | commissioning |  | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-26 | 2025-06-25 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161201 | CONTROL LOGIC DIAGRAM - SYMBOL & LEGEND | CONTROL LOGIC DIAGRAM |  |  |  |  | Control Logic Diagram |  | ACC - Control Logic Diagram | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram |  | acc | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7929 | 0.7629 | 0.7629 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | true | 7 | 158 | 14.8839 | 0.4693 | 0.0195 | 0.0059 | hybrid | structured_phase_gap | acc | system_design¦engineering | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161202 | CONTROL LOGIC DIAGRAM - TYPICAL FUNCTION | CONTROL LOGIC DIAGRAM |  |  |  |  | Control Logic Diagram |  | ACC - Control Logic Diagram | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram |  | acc | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.7929 | 0.7629 | 0.7629 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | true | 7 | 329 | 14.8839 | 0.4429 | 0.0175 | 0.0052 | hybrid | structured_phase_gap | acc | system_design¦engineering | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rule_scope_unmatched |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161203 | CONTROL LOGIC DIAGRAM FOR HP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | HIGH PRESSURE STEAM SYSTEM |  |  | Control Logic Diagram for HIGH PRESSURE STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7082 | 0.7374 | 0.7374 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6796 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161204 | CONTROL LOGIC DIAGRAM FOR IP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | Intermediate Pressure STEAM SYSTEM |  |  | Control Logic Diagram for Intermediate Pressure STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6726 | 0.7268 | 0.7268 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6691 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161205 | CONTROL LOGIC DIAGRAM FOR LP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | LOW PRESSURE STEAM SYSTEM |  |  | Control Logic Diagram for LOW PRESSURE STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6872 | 0.7312 | 0.7312 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6741 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161206 | CONTROL LOGIC DIAGRAM FOR PROCESS STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | Control Logic Diagram for PROCESS STEAM SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7134 | 0.7390 | 0.7390 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6915 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161207 | CONTROL LOGIC DIAGRAM FOR STEAM DRAIN SYSTEM | CONTROL LOGIC DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | Control Logic Diagram for STEAM DRAIN SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7034 | 0.7360 | 0.7360 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6690 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161208 | CONTROL LOGIC DIAGRAM FOR CONDENSATE SYSTEM | CONTROL LOGIC DIAGRAM |  | CONDENSATE SYSTEM |  |  | Control Logic Diagram for CONDENSATE SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | condensate |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7134 | 0.7390 | 0.7390 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 4 | 25.2200 | 0.6791 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161209 | CONTROL LOGIC DIAGRAM FOR FEEDWATER SYSTEM | CONTROL LOGIC DIAGRAM |  | FEEDWATER SYSTEM |  |  | Control Logic Diagram for FEEDWATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7428 | 0.7478 | 0.7478 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 1 | 1 | 12.9693 | 0.6778 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design¦engineering | 1 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161210 | CONTROL LOGIC DIAGRAM FOR CLOSED COOLING WATER SYSTEM | CONTROL LOGIC DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | Control Logic Diagram for CLOSED COOLING WATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6871 | 0.7311 | 0.7311 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 14.0432 | 0.4349 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161211 | CONTROL LOGIC DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | CONTROL LOGIC DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | Control Logic Diagram for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6377 | 0.7163 | 0.7163 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 26.0520 | 0.5846 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦engineering | 5 | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161212 | CONTROL LOGIC DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOGIC DIAGRAM | Gas Turbine Generator | Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | Control Logic Diagram for Gas Turbine ROTOR COOLING AIR SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | air¦cooling¦gas¦gtg¦rotor¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6695 | 0.7259 | 0.7259 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 12.2839 | 0.5999 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161213 | CONTROL LOGIC DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | CONTROL LOGIC DIAGRAM | Gas Turbine Generator | Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | Control Logic Diagram for Gas Turbine PERFORMANCE HEATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | gas¦gtg¦heater¦performance¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6735 | 0.7271 | 0.7271 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 7.2210 | 0.5848 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161214 | CONTROL LOGIC DIAGRAM FOR POTABLE WATER SYSTEM | CONTROL LOGIC DIAGRAM |  | POTABLE WATER SYSTEM |  |  | Control Logic Diagram for POTABLE WATER SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7179 | 0.7404 | 0.7404 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 39.1365 | 0.6469 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161216 | CONTROL LOGIC DIAGRAM FOR COMPRESSED AIR SYSTEM | CONTROL LOGIC DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | Control Logic Diagram for COMPRESSED AIR SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6947 | 0.7334 | 0.7334 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 37.5953 | 0.6523 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161220 | CONTROL LOGIC DIAGRAM FOR ELECTRICAL SYSTEM | CONTROL LOGIC DIAGRAM |  | ELECTRICAL SYSTEM |  |  | Control Logic Diagram for ELECTRICAL SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | electrical |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7332 | 0.7450 | 0.7450 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | true | 13 | 472 | 16.1582 | 0.4562 | 0.0156 | 0.0093 | hybrid | structured_phase_gap | electrical | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161221 | CONTROL LOGIC DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | CONTROL LOGIC DIAGRAM |  | OTHER CONTROL SYSTEM |  |  | Control Logic Diagram for OTHER CONTROL SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | other |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7151 | 0.7395 | 0.7395 | g_safe | [5 empty] | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 164 | 34 | 13.0638 | 0.4711 | 0.0151 | 0.0113 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161222 | CONTROL LOGIC DIAGRAM FOR MISCELLANEOUS SYSTEM | CONTROL LOGIC DIAGRAM |  | MISCELLANEOUS SYSTEM |  |  | Control Logic Diagram for MISCELLANEOUS SYSTEM | FireFighting | Control Logic Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_logic_diagram | control_logic_diagram | miscellaneous |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7013 | 0.7354 | 0.7354 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 6 | 35 | 16.1582 | 0.4950 | 0.0257 | 0.0154 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161301 | CONTROL LOOP DIAGRAM - SYMBOL & LEGEND | CONTROL LOOP DIAGRAM |  |  |  |  | Control Loop Diagram | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8073 | 0.7672 | 0.7672 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match |  |  |  |  | steam | query_unscoped | false | false | 31 | 17 | 12.3101 | 0.5665 | 0.0240 | 0.0180 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161302 | CONTROL LOOP DIAGRAM - TYPICAL FUNCTION | CONTROL LOOP DIAGRAM |  |  |  |  | Control Loop Diagram | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.8073 | 0.7672 | 0.7672 | [6 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 14 | 60 | 14.8839 | 0.5353 | 0.0218 | 0.0131 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161303 | CONTROL LOOP DIAGRAM FOR HP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | HIGH PRESSURE STEAM SYSTEM |  |  | Control Loop Diagram for HIGH PRESSURE STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7378 | 0.7463 | 0.7463 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6930 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161304 | CONTROL LOOP DIAGRAM FOR IP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | Intermediate Pressure STEAM SYSTEM |  |  | Control Loop Diagram for Intermediate Pressure STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7199 | 0.7410 | 0.7410 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6813 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161305 | CONTROL LOOP DIAGRAM FOR LP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | LOW PRESSURE STEAM SYSTEM |  |  | Control Loop Diagram for LOW PRESSURE STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7222 | 0.7417 | 0.7417 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6791 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161306 | CONTROL LOOP DIAGRAM FOR PROCESS STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | Control Loop Diagram for PROCESS STEAM SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7494 | 0.7498 | 0.7498 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.7071 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161307 | CONTROL LOOP DIAGRAM FOR STEAM DRAIN SYSTEM | CONTROL LOOP DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | Control Loop Diagram for STEAM DRAIN SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | drain¦steam |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7397 | 0.7469 | 0.7469 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | steam |  | steam | query | steam | match | true | false | 1 | 1 | 19.0793 | 0.6900 | 0.0328 | 0.0328 | hybrid | structured_preferred | steam | system_design¦engineering | 3 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161308 | CONTROL LOOP DIAGRAM FOR CONDENSATE SYSTEM | CONTROL LOOP DIAGRAM |  | CONDENSATE SYSTEM |  |  | Control Loop Diagram for CONDENSATE SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | condensate |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7417 | 0.7475 | 0.7475 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate |  | condensate | query | condensate | match | true | false | 1 | 4 | 25.2200 | 0.7033 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | system_design¦engineering |  | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161309 | CONTROL LOOP DIAGRAM FOR FEEDWATER SYSTEM | CONTROL LOOP DIAGRAM |  | FEEDWATER SYSTEM |  |  | Control Loop Diagram for FEEDWATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | feedwater |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7870 | 0.7611 | 0.7611 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | feedwater |  | feedwater | query | feedwater | match | true | false | 1 | 1 | 12.9693 | 0.6897 | 0.0328 | 0.0328 | hybrid | structured_preferred | feedwater | system_design¦engineering | 1 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161310 | CONTROL LOOP DIAGRAM FOR CLOSED COOLING WATER SYSTEM | CONTROL LOOP DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | Control Loop Diagram for CLOSED COOLING WATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7406 | 0.7472 | 0.7472 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 14.0432 | 0.4106 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161311 | CONTROL LOOP DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | CONTROL LOOP DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | Control Loop Diagram for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6727 | 0.7268 | 0.7268 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 26.0520 | 0.6034 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design¦engineering | 5 | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161312 | CONTROL LOOP DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOOP DIAGRAM | Gas Turbine Generator | Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | Control Loop Diagram for Gas Turbine ROTOR COOLING AIR SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | air¦cooling¦gas¦gtg¦rotor¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7115 | 0.7384 | 0.7384 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 12.2839 | 0.5714 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161313 | CONTROL LOOP DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | CONTROL LOOP DIAGRAM | Gas Turbine Generator | Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | Control Loop Diagram for Gas Turbine PERFORMANCE HEATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | gas¦gtg¦heater¦performance¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7073 | 0.7372 | 0.7372 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | gtg |  | gtg | query | ccw¦gtg | match | true | false | 1 | 2 | 7.2210 | 0.5754 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | system_design¦engineering | 3 | 2024-07-19 | 2024-08-03 | 2024-08-18 | 2024-08-24 | 2024-09-08 | 2024-09-23 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161314 | CONTROL LOOP DIAGRAM FOR POTABLE WATER SYSTEM | CONTROL LOOP DIAGRAM |  | POTABLE WATER SYSTEM |  |  | Control Loop Diagram for POTABLE WATER SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | potable¦water |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7422 | 0.7477 | 0.7477 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 39.1365 | 0.6649 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161316 | CONTROL LOOP DIAGRAM FOR COMPRESSED AIR SYSTEM | CONTROL LOOP DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | Control Loop Diagram for COMPRESSED AIR SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7151 | 0.7395 | 0.7395 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | compressed_air |  | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 37.5953 | 0.6591 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | system_design¦engineering |  | 2024-09-17 | 2024-10-02 | 2024-10-17 | 2024-10-23 | 2024-11-07 | 2024-11-22 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161320 | CONTROL LOOP DIAGRAM FOR ELECTRICAL SYSTEM | CONTROL LOOP DIAGRAM |  | ELECTRICAL SYSTEM |  |  | Control Loop Diagram for ELECTRICAL SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | electrical |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7590 | 0.7527 | 0.7527 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | true | 20 | 195 | 16.1582 | 0.4937 | 0.0164 | 0.0099 | hybrid | structured_phase_gap | electrical | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161321 | CONTROL LOOP DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | CONTROL LOOP DIAGRAM |  | INTERFACE WITH OTHER CONTROL SYSTEM |  |  | Control Loop Diagram for INTERFACE WITH OTHER CONTROL SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | interface¦other¦with |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7362 | 0.7459 | 0.7459 | g_safe | [5 empty] | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 180 | 35 | 13.0638 | 0.4988 | 0.0147 | 0.0110 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161322 | CONTROL LOOP DIAGRAM FOR MISCELLANEOUS SYSTEM | CONTROL LOOP DIAGRAM |  | MISCELLANEOUS SYSTEM |  |  | Control Loop Diagram for MISCELLANEOUS SYSTEM | FireFighting | Control Loop Diagram | 1 | start+20W<=FA<=FC<=start+20W+1M | FA ∈ [start+140d, start+170d] ¦ FC ∈ [start+140d, start+170d] | rule_query | diagram | diagram | control_loop_diagram | control_loop_diagram | miscellaneous |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7309 | 0.7443 | 0.7443 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 13 | 9 | 16.1582 | 0.5505 | 0.0282 | 0.0169 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161401 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL CONTROL ROOM | Layout Drawing |  |  | CENTRAL CONTROL ROOM |  | Layout Drawing for CENTRAL CONTROL ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | ccr¦central¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9107 | 0.9732 | 0.6812 | g_safe | [5 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 14 | 1 | 17.3786 | 0.6476 | 0.0299 | 0.0135 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161402 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL ELECTRONIC ROOM | Layout Drawing |  |  | CENTRAL ELECTRONIC ROOM |  | Layout Drawing for CENTRAL ELECTRONIC ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | central¦electronic¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8956 | 0.9687 | 0.6781 | g_safe | [5 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 14 | 1 | 13.1819 | 0.6025 | 0.0299 | 0.0135 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.38 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161403 | I&C EQUIPMENT LAYOUT DRAWING FOR COMPUTER ROOM | Layout Drawing |  |  | COMPUTER ROOM |  | Layout Drawing for COMPUTER ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | computer¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8878 | 0.9663 | 0.6764 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | false | 33 | 15 | 9.0197 | 0.5041 | 0.0241 | 0.0135 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161404 | I&C EQUIPMENT LAYOUT DRAWING FOR IT & COMMUNICATION ROOM | Layout Drawing |  |  | IT & COMMUNICATION ROOM |  | Layout Drawing for IT & COMMUNICATION ROOM |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | communication¦room |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8450 | 0.9535 | 0.6674 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | false | false | 33 | 12 | 9.0197 | 0.4973 | 0.0246 | 0.0139 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161405 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #1,2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | Layout Drawing | Gas Turbine Generator | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8258 | 0.9477 | 0.6634 | g_ambig | generic_ok | 0.78 |  | 1 | The document is an I&C equipment layout for LEB room, not a generator foundation embedded metals layout. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 21.8168 | 0.7349 | 0.0328 | 0.0328 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161406 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #3,4,5 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | Layout Drawing | Gas Turbine Generator | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8203 | 0.9461 | 0.6623 | g_ambig | generic_ok | 0.78 |  | 1 | The document is an I&C equipment layout for LEB room, not a generator foundation embedded metals layout. | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg |  | electrical¦gtg | query | gtg | match | true | false | 4 | 1 | 20.6668 | 0.7229 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161407 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #1 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | Layout Drawing | Steam Turbine | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8425 | 0.9528 | 0.6669 | g_safe | [5 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 13 | 1 | 9.6592 | 0.5816 | 0.0301 | 0.0301 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161408 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | Layout Drawing | Steam Turbine | Electrical System | Local Electrical Building |  | Layout Drawing for Local Electrical Building |  | I&C EQUIPMENT LAYOUT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8353 | 0.9506 | 0.6654 | g_safe | [5 empty] | FA | 2EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | electrical¦stg |  | electrical¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 13 | 5 | 10.3608 | 0.5772 | 0.0291 | 0.0291 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161409 | I&C EQUIPMENT LAYOUT DRAWING FOR FGS ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM | Layout Drawing |  | Instrumentation and Control | Fuel Gas System ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical¦electronic¦fgp¦fuel¦gas¦local¦room | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6668 | 0.6667 | 0.6667 | [6 empty] | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | false | 9 | 2 | 16.0620 | 0.5688 | 0.0306 | 0.0306 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0ZEN-163101 | FIELD INSTRUMENT LIST FOR BOP | LIST |  | Balance of Plant |  |  | Instrument List for BOP |  | Instrument List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | instrument_list | instrument_list | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7497 | 0.6916 | 0.6916 | g_safe | [5 empty] | FI | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 3 | 1 | 24.5539 | 0.7030 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | bop | procurement |  | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163102 | TECHNICAL SPECIFICATION & DATA SHEET FOR LOCAL INSTRUMENT - BOP | TECHNICAL SPECIFICATION & DATA SHEET |  | Balance of Plant |  |  | TECHNICAL SPECIFICATION & DATA SHEET for BOP |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6504 | 0.7551 | 0.7551 | g_safe | [5 empty] | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 3 | 7 | 27.5446 | 0.6051 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | bop | procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163103 | TECHNICAL SPECIFICATION & DATA SHEET FOR PROCESS TRANSMITTER - BOP | TECHNICAL SPECIFICATION & DATA SHEET |  | Balance of Plant |  |  | TECHNICAL SPECIFICATION & DATA SHEET for BOP |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6504 | 0.7551 | 0.7551 | g_safe | [5 empty] | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 3 | 4 | 27.5446 | 0.6079 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | bop | procurement |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163104 | TECHNICAL SPECIFICATION & DATA SHEET FOR FLOW ELEMENT - BOP | TECHNICAL SPECIFICATION & DATA SHEET | FLOW ELEMENT | Balance of Plant |  |  | TECHNICAL SPECIFICATION & DATA SHEET for FLOW ELEMENT | FloW element | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | bop¦element¦flow |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.8883 | 0.8665 | 0.8665 | g_safe | [5 empty] | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 3 | 1 | 27.5446 | 0.6290 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | bop | procurement |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163201 | TECHNICAL SPECIFICATION & DATA SHEET FOR CONTROL VALVE - BOP | TECHNICAL SPECIFICATION & DATA SHEET | CONTROL VALVE | Balance of Plant |  |  | TECHNICAL SPECIFICATION & DATA SHEET for CONTROL VALVE | CONTROL VALVE | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | bop¦valve |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9180 | 0.8754 | 0.8754 | g_safe | [5 empty] | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 1 | 1 | 44.7762 | 0.7240 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop | procurement |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0EKU-163202 | TECHNICAL SPECIFICATION & DATA SHEET FOR GAS METERING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | GAS METERING SYSTEM |  |  | TECHNICAL SPECIFICATION & DATA SHEET for GAS METERING SYSTEM |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | gas¦metering |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6096 | 0.7429 | 0.7429 | g_safe | [5 empty] | FA | 1PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | 2007-07-03 | 2008-04-01 | procurement | procurement | match | electrical |  | electrical | query | electrical¦fgp | match | true | false | 6 | 2 | 24.2092 | 0.6748 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-07-17 | 2024-08-16 | 2024-09-15 | 2024-09-30 | 2024-10-15 | 2024-10-30 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0UCL-163203 | TECHNICAL SPECIFICATION & DATA SHEET FOR STEAM/WATER METERING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | Electrical System |  |  | TECHNICAL SPECIFICATION & DATA SHEET for Electrical System |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | electrical |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6886 | 0.7666 | 0.7666 | g_safe | [5 empty] | FA | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | procurement | procurement | match | electrical |  | electrical | query | electrical | match | true | false | 1 | 1 | 19.4931 | 0.6246 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical | procurement |  | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163204 | TECHNICAL SPECIFICATION & DATA SHEET FOR WEATHER STATION | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7990 | 0.7997 | 0.7997 | [6 empty] | FA | 1PF3030W42A02P | (Temp. Cooling Tower) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower | 2008-02-21 | 2008-06-19 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | false | 68 | 4 | 10.2297 | 0.4553 | 0.0234 | 0.0176 | hybrid | structured_no_system |  | procurement |  | 2025-03-21 | 2025-04-20 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-07-04 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163301 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM - INDEX | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7351 | 0.9205 | 0.9205 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 20 | 31 | 13.1789 | 0.4995 | 0.0235 | 0.0141 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163302 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR INCOMER | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6412 | 0.8924 | 0.8924 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 18 | 148 | 15.5211 | 0.4775 | 0.0176 | 0.0106 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163303 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR MOTOR FEEDER | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6380 | 0.8914 | 0.8914 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 21 | 152 | 15.5211 | 0.4655 | 0.0171 | 0.0102 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163304 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR TR FEEDER | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6538 | 0.8962 | 0.8962 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 18 | 189 | 15.5211 | 0.4693 | 0.0168 | 0.0101 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163305 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR BUS TIE | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6286 | 0.8886 | 0.8886 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 18 | 137 | 15.5211 | 0.4755 | 0.0179 | 0.0107 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163306 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR UNIT/COMMON TIE | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6319 | 0.8896 | 0.8896 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 18 | 63 | 16.5642 | 0.5011 | 0.0210 | 0.0126 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163307 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PT PANEL | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7320 | 0.9196 | 0.9196 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 17 | 82 | 13.8746 | 0.4964 | 0.0200 | 0.0120 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163308 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR INCOMER | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6576 | 0.8973 | 0.8973 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 18 | 309 | 15.5211 | 0.4480 | 0.0155 | 0.0093 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163309 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (ACB) | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6219 | 0.8866 | 0.8866 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 20 | 350 | 15.5211 | 0.4324 | 0.0149 | 0.0090 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163310 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (MCCB) | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6211 | 0.8863 | 0.8863 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 20 | 221 | 15.5211 | 0.4461 | 0.0161 | 0.0096 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163311 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (ACB) | Diagram | Distributed Control System |  |  |  | Diagram for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6322 | 0.8897 | 0.8897 | g_ambig | generic_ok | 0.72 |  | 1 | An index of typical DCS elementary wiring diagrams does not clearly correspond to the specific DCS internal interconnection wiring diagram deliverable. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 20 | 383 | 15.5211 | 0.4303 | 0.0148 | 0.0089 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163312 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (MCCB EHS) | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6188 | 0.8856 | 0.8856 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 20 | 445 | 15.5211 | 0.4278 | 0.0145 | 0.0087 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163313 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR BUS TIE | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6465 | 0.8940 | 0.8940 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 18 | 412 | 15.5211 | 0.4366 | 0.0149 | 0.0090 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163314 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG INPUT | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6810 | 0.9043 | 0.9043 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 22 | 42 | 13.1789 | 0.4793 | 0.0220 | 0.0132 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163315 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG OUTPUT | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6774 | 0.9032 | 0.9032 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 12 | 81 | 15.5211 | 0.4687 | 0.0210 | 0.0126 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163316 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY INPUT | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6673 | 0.9002 | 0.9002 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 12 | 116 | 15.5211 | 0.4552 | 0.0196 | 0.0117 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163317 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY OUTPUT | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6762 | 0.9029 | 0.9029 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 12 | 99 | 15.5211 | 0.4589 | 0.0202 | 0.0121 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163318 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC CONTROL VALVE - MODULATING | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6075 | 0.8823 | 0.8823 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 22 | 32 | 15.5211 | 0.4896 | 0.0231 | 0.0138 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163319 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC SHUT - OFF VALVE (SOLENOID VALVE) | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6059 | 0.8818 | 0.8818 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3025W00A01 | (CWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 60 | 26 | 13.1789 | 0.4716 | 0.0200 | 0.0120 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163320 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - INTERNAL MCC | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6317 | 0.8895 | 0.8895 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 22 | 37 | 15.5211 | 0.4734 | 0.0225 | 0.0135 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163321 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - FIELDBUS | WIRING DIAGRAM | Distributed Control System |  |  |  | WIRING DIAGRAM for Distributed Control System |  | Typical Elementary Wiring Diagram | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | diagram | diagram | wiring_diagram | wiring_diagram | dcs¦distributed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5959 | 0.8788 | 0.8788 | g_ambig | generic_ok | 0.70 |  | 1 | This is a typical elementary wiring diagram for an LV switchgear feeder, not a DCS internal interconnection wiring diagram. | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | dcs |  | dcs | query |  | activity_unscoped | true | true | 21 | 51 | 15.5211 | 0.4497 | 0.0214 | 0.0128 | hybrid | structured_phase_gap | dcs | system_design¦engineering |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163331 | TECHNICAL SPECIFICATION & DATA SHEET FOR VIBRATION MONITORING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | VIBRATION MONITORING SYSTEM |  |  | TECHNICAL SPECIFICATION & DATA SHEET for VIBRATION MONITORING SYSTEM |  | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | monitoring¦vibration |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6318 | 0.7495 | 0.7495 | g_safe | [5 empty] | FA | 1PF1260W86A02P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-05-01 | procurement | procurement | match |  |  |  |  | gtg | query_unscoped | false | false | 1 | 2 | 42.8426 | 0.5959 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | procurement |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0SAY-163401 | CONTROL SYSTEM CONFIGURATION DIAGRAM FOR HVAC | Diagram |  | Heating Ventilating and Air Conditioning |  |  | Diagram for Heating Ventilating and Air Conditioning |  | CONTROL SYSTEM CONFIGURATION DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8398 | 0.9519 | 0.6664 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 43.7879 | 0.6363 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SAY-163402 | I/O LIST FOR HVAC | Input / Output LIST |  | Heating Ventilating and Air Conditioning |  |  | I/O List for Heating Ventilating and Air Conditioning | Air Compressor | HardWire Input /Output List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | io_list | io_list | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5773 | 0.4065 | 0.4065 | g_safe | [5 empty] | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac | compressed_air | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 43.8852 | 0.6512 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hvac | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SAY-163403 | TECHNICAL SPECIFICATION & DATA SHEET FOR FIELD INSTRUMENT - HVAC | TECHNICAL SPECIFICATION & DATA SHEET |  | Heating Ventilating and Air Conditioning |  |  | TECHNICAL SPECIFICATION & DATA SHEET for Heating Ventilating and Air Conditioning |  | Technical Specification With Data sheet | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | specification | specification | technical_specification | technical_specification | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.6352 | 0.7506 | 0.7506 | g_safe | [5 empty] | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 41.5969 | 0.6736 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | procurement |  | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0SAY-163404 | INSTRUMENT INSTALLATION DETAIL DRAWING FOR HVAC | DRAWING |  | Heating Ventilating and Air Conditioning |  |  | DRAWING for Heating Ventilating and Air Conditioning | FinFan Cooler | Instrument Installation Detail DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7100 | 0.6797 | 0.6797 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 2 | 35.8460 | 0.6382 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦civil_design |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0SAY-163405 | CONTROL LOGIC & LOOP DIAGRAM FOR HVAC | Diagram |  | Heating Ventilating and Air Conditioning |  |  | Diagram for Heating Ventilating and Air Conditioning |  | Logic & Loop Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6791 | 0.9037 | 0.9037 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 45.2659 | 0.6649 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0SAY-163406 | I&C CABLE SCHEDULE FOR HVAC | Schedule |  | Heating Ventilating and Air Conditioning |  |  | Schedule for Heating Ventilating and Air Conditioning | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.8159 | 0.6648 | 0.6648 | g_safe | [5 empty] | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 41.5973 | 0.6297 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | procurement |  | 2024-11-13 | 2024-12-13 | 2025-01-12 | 2025-01-27 | 2025-02-11 | 2025-02-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0SAY-163407 | I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HVAC | WIRING DIAGRAM |  | Heating Ventilating and Air Conditioning |  |  | WIRING DIAGRAM for Heating Ventilating and Air Conditioning |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6844 | 0.9053 | 0.9053 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 45.2659 | 0.6115 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163408 | HVAC I&C CABLE RACEWAY DRAWING FOR CCB | DRAWING |  | Heating Ventilating and Air Conditioning | Central Control Building |  | DRAWING for Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦ccr¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8124 | 0.9437 | 0.6606 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 20.3770 | 0.5139 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163409 | HVAC I&C CABLE RACEWAY DRAWING FOR STEAM TURBINE BUILDING | DRAWING | Steam Turbine & Generator | Heating Ventilating and Air Conditioning | Steam Turbine Building |  | DRAWING for Steam Turbine Building |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7660 | 0.9298 | 0.6509 | g_ambig | generic_ok | 0.80 |  | 1 | An HVAC I&C cable raceway drawing for the steam turbine building is different in scope from an ST cabinet internal arrangement drawing. | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | hvac¦stg |  | hvac¦stg | query | stg | match | true | false | 13 | 1 | 13.4660 | 0.5924 | 0.0301 | 0.0301 | hybrid | structured_preferred | hvac¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163411 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #1 | DRAWING | Steam Turbine & Generator | Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7540 | 0.9262 | 0.6483 | g_ambig | generic_ok | 0.80 |  | 1 | An HVAC I&C cable raceway drawing for the steam turbine building is different in scope from an ST cabinet internal arrangement drawing. | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦hvac¦stg |  | electrical¦hvac¦stg | query | stg | match | true | false | 10 | 2 | 15.3469 | 0.6326 | 0.0304 | 0.0304 | hybrid | structured_preferred | electrical¦hvac¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163412 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #2 | DRAWING | Steam Turbine & Generator | Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7436 | 0.9231 | 0.6462 | g_ambig | generic_ok | 0.80 |  | 1 | An HVAC I&C cable raceway drawing for the steam turbine building is different in scope from an ST cabinet internal arrangement drawing. | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | electrical¦hvac¦stg |  | electrical¦hvac¦stg | query | stg | match | true | false | 10 | 1 | 15.8886 | 0.6442 | 0.0307 | 0.0307 | hybrid | structured_preferred | electrical¦hvac¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163413 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #1,2 | DRAWING | Gas Turbine Generator | Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7481 | 0.9244 | 0.6471 | g_ambig | generic_ok | 0.74 |  | 12 | The document is an HVAC I&C cable raceway drawing for the GTG electrical building, while the competing specifics are foundations, FM200, tubing/impulse piping, and other non-raceway drawings. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | gtg | match | true | false | 9 | 10 | 13.6364 | 0.6270 | 0.0288 | 0.0288 | hybrid | structured_preferred | electrical¦gtg¦hvac | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163414 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #3, 4, 5 | DRAWING | Gas Turbine Generator | Heating Ventilating and Air Conditioning | ELECTRICAL BUILDING |  | DRAWING for ELECTRICAL BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | electrical¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7462 | 0.9239 | 0.6467 | g_ambig | generic_ok | 0.74 |  | 12 | The document is an HVAC I&C cable raceway drawing for the GTG electrical building, while the competing specifics are foundations, FM200, tubing/impulse piping, and other non-raceway drawings. | FA | 1CF1265W16A12.4 | (TCA Cooler) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | 2007-10-01 | 2007-11-30 | civil_design | civil_design | match | electrical¦gtg¦hvac |  | electrical¦gtg¦hvac | query | fgp¦gtg | match | true | false | 10 | 11 | 13.3726 | 0.6073 | 0.0284 | 0.0284 | hybrid | structured_preferred | electrical¦gtg¦hvac | civil_design | 10 | 2024-05-19 | 2024-06-03 | 2024-06-18 | 2024-07-03 | 2024-08-02 | 2024-09-01 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163415 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING | DRAWING |  | Heating Ventilating and Air Conditioning | Administration & Social Building |  | DRAWING for Administration & Social Building |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6958 | 0.9088 | 0.6361 | g_safe | [5 empty] | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 28.2769 | 0.5827 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163416 | HVAC I&C CABLE RACEWAY DRAWING FOR SECURITY BUILDING | DRAWING |  | Heating Ventilating and Air Conditioning | Security Building |  | DRAWING for Security Building |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7731 | 0.9319 | 0.6524 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 1 | 24.3270 | 0.5913 | 0.0325 | 0.0325 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163417 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE BRIGADE & AUX LEB | DRAWING |  | Heating Ventilating and Air Conditioning | Local Electrical Building |  | DRAWING for Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦conditioning¦electrical¦fire_protection¦heating¦leb¦local¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7490 | 0.9247 | 0.6473 | g_ambig | generic_ok | 0.77 |  | 2 | An HVAC I&C cable raceway drawing for fire brigade & aux LEB is not the same deliverable as GT FM200 fire fighting system drawings. | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match | electrical¦hvac |  | electrical¦hvac | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 27.2600 | 0.6225 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦hvac | civil_design | 10 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163418 | HVAC I&C CABLE RACEWAY DRAWING FOR MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE | DRAWING |  | Heating Ventilating and Air Conditioning | Workshop & Storage Building |  | DRAWING for Workshop & Storage Building |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7351 | 0.9205 | 0.6444 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 2 | 26.6915 | 0.5731 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163419 | HVAC I&C CABLE RACEWAY DRAWING FOR FGS ELECTRICAL BUILDING | DRAWING |  | Heating Ventilating and Air Conditioning | Fuel Gas System ELECTRICAL BUILDING |  | DRAWING for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7390 | 0.6884 | 0.6884 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp¦hvac | fgp | electrical¦fgp¦hvac | query | fgp | match | false | false | 26 | 9 | 10.8160 | 0.5194 | 0.0261 | 0.0261 | hybrid | structured_preferred | electrical¦fgp¦hvac | civil_design | 10 | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163420 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE WATER PUMP HOUSE | DRAWING |  | Heating Ventilating and Air Conditioning | Fire Water Pump House |  | DRAWING for Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦conditioning¦fire_protection¦heating¦pump¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7756 | 0.9327 | 0.6529 | g_ambig | generic_ok | 0.70 |  | 18 | The competing specifics listed are unrelated drawing types (nameplate, 3D model, hook-up, foundations, FM200, etc.) and do not clearly target an HVAC I&C cable raceway drawing. | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | fire_fighting¦hvac |  | fire_fighting¦hvac | query | fire_fighting¦hvac | match | true | false | 6 | 1 | 38.3666 | 0.6594 | 0.0315 | 0.0237 | hybrid | structured_cell_found_text_preferred | fire_fighting¦hvac | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163421 | HVAC I&C CABLE RACEWAY DRAWING FOR WATER TREATMENT BUILDING /W MAIN LABORATORY | DRAWING |  | Heating Ventilating and Air Conditioning | Water Treatment Building |  | DRAWING for Water Treatment Building | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.7119 | 0.6136 | 0.6136 | [6 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | hvac¦wts | wts | hvac¦wts | query | wts | match | true | false | 16 | 3 | 15.4574 | 0.5781 | 0.0290 | 0.0290 | hybrid | structured_preferred | hvac¦wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163422 | HVAC I&C CABLE RACEWAY DRAWING FOR CPP BUILDING | DRAWING |  | Heating Ventilating and Air Conditioning | CONDENSATE POLISING PLANT BUILDING |  | DRAWING for CONDENSATE POLISING PLANT BUILDING |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | condensate¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7571 | 0.9271 | 0.6490 | g_safe | [5 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate¦hvac |  | condensate¦hvac | query | acc¦condensate | match | false | false | 9 | 11 | 2.8059 | 0.4632 | 0.0286 | 0.0286 | hybrid | structured_preferred | condensate¦hvac | civil_design | 10 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.30 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SAY-163423 | CONTROL PANEL OUTLINE & DETAIL DRAWING FOR HVAC | DRAWING |  | Heating Ventilating and Air Conditioning |  |  | DRAWING for Heating Ventilating and Air Conditioning |  | Coupling detail draWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | detail_drawing | detail_drawing | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4965 | 0.6156 | 0.6156 | g_safe | [5 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 2 | 35.8460 | 0.6258 | 0.0323 | 0.0242 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦civil_design |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0SAY-163424 | HMI GRAPHIC DISPLAY DIAGRAM FOR HVAC | Diagram | Human Machine Interface | Heating Ventilating and Air Conditioning |  |  | Diagram for Heating Ventilating and Air Conditioning |  | HMI GRAPHIC DISPLAY DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8910 | 0.9673 | 0.6771 | g_safe | [5 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 43.1208 | 0.6057 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | hvac | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SAY-163425 | TECHNICAL SPECIFICATION - HVAC CONTROL SYSTEM | Technical Specification |  | Heating Ventilating and Air Conditioning CONTROL SYSTEM |  |  | Technical Specification for Heating Ventilating and Air Conditioning CONTROL SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4800 | 0.6107 | 0.6107 | g_safe | [5 empty] | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | procurement | procurement | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 42.7665 | 0.7012 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | hvac | procurement |  | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163426 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN GATE HOUSE AREA | DRAWING |  | Heating Ventilating and Air Conditioning | Security Building |  | DRAWING for Heating Ventilating and Air Conditioning |  | I&C Cable RaceWay DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | air¦conditioning¦heating¦ventilating |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7806 | 0.9342 | 0.6539 | g_safe | [5 empty] | FA | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | civil_design | civil_design | match | hvac |  | hvac | query | fire_fighting¦hvac | match | true | false | 2 | 2 | 20.3770 | 0.5316 | 0.0323 | 0.0323 | hybrid | structured_preferred | hvac | civil_design | 8 | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0ZEN-165001 | DESIGN CRITERIA FOR I&C CABLE | DESIGN CRITERIA | Instrumentation and Control CABLE |  |  |  | DESIGN CRITERIA for Instrumentation and Control CABLE |  | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | rule_query | criteria | criteria | design_criteria | design_criteria | cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.4981 | 0.5494 | 0.5494 | g_safe | [5 empty] | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | [5 empty] | query_unscoped | true | true | 1 | 1 | 62.3058 | 0.5963 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | design_criteria¦system_design¦civil_design |  | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | fa_earliest | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL02-P0ZEN-165011 | I&C CABLE PRINCIPLE DIAGRAM | PRINCIPLE DIAGRAM | Instrumentation and Control CABLE |  |  |  | PRINCIPLE DIAGRAM for Instrumentation and Control CABLE |  | Cable Principle Diagram | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7299 | 0.9190 | 0.6433 | g_safe | [5 empty] | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 16 | 56 | 16.9020 | 0.4802 | 0.0218 | 0.0123 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165301 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONTROL VALVE | DRAWINGS | CONTROL VALVE |  |  |  | DRAWINGS for CONTROL VALVE |  | TYPICAL I&C CABLE INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | valve |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8678 | 0.8203 | 0.5742 | g_safe | [5 empty] | FA | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 338 | 158 | 8.3933 | 0.4368 | 0.0071 | 0.0032 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165302 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - MOV | DRAWINGS | Motor Operated Valve |  |  |  | DRAWINGS for Motor Operated Valve |  | TYPICAL I&C CABLE INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | motor¦operated¦valve |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8233 | 0.8070 | 0.5649 | g_safe | [5 empty] | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 35 | 160 | 8.4510 | 0.4163 | 0.0151 | 0.0085 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 |  | false | false | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165303 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - INSTRUMENT RACK AND JUNCTION BOX | INSTALLATION DRAWINGS |  | Instrumentation and Control Cable |  |  | INSTALLATION DRAWINGS for Instrumentation and Control Cable |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6134 | 0.6507 | 0.6507 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 313 | 95 | 11.4303 | 0.4806 | 0.0091 | 0.0041 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165304 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - FIELD INSTRUMENT | INSTALLATION DRAWINGS |  | Instrumentation and Control Cable |  |  | INSTALLATION DRAWINGS for Instrumentation and Control Cable |  | Instrument Installation DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | drawing | drawing | cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6760 | 0.6695 | 0.6695 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 315 | 47 | 8.6365 | 0.5152 | 0.0120 | 0.0054 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.29 | needs_review | default_fc_window;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165305 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONDUIT SUPPORT | INSTALLATION DRAWINGS |  | Instrumentation and Control Cable |  |  | INSTALLATION DRAWINGS for Instrumentation and Control Cable |  | TYPICAL I&C CABLE INSTALLATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8739 | 0.8222 | 0.5755 | g_safe | [5 empty] | FA | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 113 | 38 | 16.9020 | 0.4874 | 0.0160 | 0.0090 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.41 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165311 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - GENERAL NOTE | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 1 | 1 | 14.2724 | 0.4692 | 0.0328 | 0.0246 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165312 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - SYMBOL & LEGEND | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 3 | 4 | 11.7106 | 0.3993 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165313 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - MATERIAL LISTS | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 3 | 4 | 11.7106 | 0.3940 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165314 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR FLOW TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 3 | 6 | 15.2822 | 0.3994 | 0.0310 | 0.0233 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165315 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR LEVEL TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 2 | 4 | 15.2822 | 0.3901 | 0.0318 | 0.0238 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165316 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 3 | 4 | 15.2822 | 0.3849 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165317 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR DIFF. PRESSURE TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 3 | 4 | 15.2822 | 0.3806 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165318 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE GAUGE | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 3 | 4 | 15.2822 | 0.4010 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165319 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE TRANSMITTER (RTD/TC) | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 2 | 4 | 15.2822 | 0.3873 | 0.0318 | 0.0238 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165320 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE GAUGE | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 3 | 4 | 15.2822 | 0.3870 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165321 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEST WELL | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 1CF3035W62A02 | (SWS) Hydro Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Service Water System (BOP) | 2008-12-17 | 2009-01-01 | commissioning | commissioning | match | bop |  | bop | query | bop¦service_water | match | true | false | 1 | 4 | 21.5552 | 0.5183 | 0.0320 | 0.0320 | hybrid | structured_preferred | bop | commissioning | 10 | 2025-08-05 | 2025-08-20 | 2025-09-04 | 2025-09-19 | 2025-10-19 | 2025-11-18 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165322 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PNEUMATIC CONTROL VALVES | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 2 | 6 | 15.2822 | 0.3794 | 0.0313 | 0.0235 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165323 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR STANCHION & RACK | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION |  |  | DETAIL DRAWINGS for INSTRUMENT INSTALLATION |  | Instrument Installation Detail DraWings | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | bop¦installation¦instrument |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8218 | 0.9465 | 0.6626 | g_safe | [5 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 2 | 4 | 23.7756 | 0.5110 | 0.0318 | 0.0238 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165501 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CENTRAL CONTROL BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant | Balance of Plant | Central Control Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for Central Control Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦ccr¦central | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9183 | 0.9755 | 0.6828 | [6 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match | bop | bop | bop | query | bop | match | true | false | 3 | 7 | 23.0761 | 0.4245 | 0.0308 | 0.0308 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165502 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #1,2 LEB | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant | Balance of Plant | Local Electrical Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for Local Electrical Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦gtg¦leb¦local | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9031 | 0.9709 | 0.6796 | [6 empty] | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | civil_design | civil_design | match | bop¦electrical | bop | bop¦electrical | query | bop | match | true | false | 1 | 62 | 25.6083 | 0.4518 | 0.0246 | 0.0246 | hybrid | structured_preferred | bop¦electrical | civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165503 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #3,4,5 LEB | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant | Balance of Plant | Local Electrical Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for Local Electrical Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦gtg¦leb¦local | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9017 | 0.9705 | 0.6794 | [6 empty] | FA | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match | bop¦electrical | bop | bop¦electrical | query | bop | match | true | false | 4 | 43 | 23.8744 | 0.4722 | 0.0253 | 0.0253 | hybrid | structured_preferred | bop¦electrical | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165504 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #1 LEB | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant | Balance of Plant | Local Electrical Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for Local Electrical Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦leb¦local¦stg | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9071 | 0.9721 | 0.6805 | [6 empty] | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | civil_design | civil_design | match | bop¦electrical | bop | bop¦electrical | query | bop | match | true | false | 4 | 27 | 23.3148 | 0.4665 | 0.0271 | 0.0271 | hybrid | structured_preferred | bop¦electrical | civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165505 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #2 LEB | DRAWING |  |  | Local Electrical Building |  | DRAWING for Local Electrical Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦leb¦local¦stg | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8979 | 0.9694 | 0.6786 | [6 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match | bop¦electrical¦stg | bop | bop¦electrical¦stg | query | bop | match | true | false | 4 | 30 | 9.3180 | 0.4495 | 0.0267 | 0.0267 | hybrid | structured_preferred | bop¦electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165506 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST BUILDING | DRAWING | Steam Turbine & Generator |  | Steam Turbine Building |  | DRAWING for Steam Turbine Building | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.4000 | 0.6158 | 0.4647 | 0.4647 | [6 empty] | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 10 | 1 | 9.1673 | 0.6608 | 0.0307 | 0.0307 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_score_medium;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165507 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FGS ELECTRICAL BUILDING | DRAWING |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | DRAWING for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Earthing point layout | 1 | start+8W<=FA<=FC<=start+20W | FA ∈ [start+56d, start+140d] ¦ FC ∈ [start+56d, start+140d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6649 | 0.5495 | 0.5495 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical¦fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 13.7268 | 0.5834 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-07-10 | 2024-08-21 | 2024-10-02 | 2024-09-11 | 2024-10-23 | 2024-12-04 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165508 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ADMINISTRATION & SOCIAL BUILDING | DRAWING |  | Balance of Plant | Administration & Social Building |  | DRAWING for Administration & Social Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | administration¦bop¦social | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8912 | 0.9674 | 0.6772 | [6 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match | bop | bop | bop | query | bop | match | true | false | 3 | 7 | 15.2822 | 0.4199 | 0.0308 | 0.0308 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165509 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR SECURITY BUILDING | DRAWING |  | Balance of Plant | Security Building |  | DRAWING for Security Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦security | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9168 | 0.9751 | 0.6825 | [6 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match | bop | bop | bop | query | bop | match | true | false | 10 | 1 | 14.3113 | 0.4696 | 0.0307 | 0.0307 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165510 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR MAIN GATE HOUSE AREA | DRAWING |  | Balance of Plant | Security Building |  | DRAWING for Security Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦security | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9140 | 0.9742 | 0.6819 | [6 empty] | FA | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | civil_design | civil_design | match | bop | bop | bop | query | bop | match | true | false | 1 | 6 | 21.3714 | 0.4645 | 0.0315 | 0.0315 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165514 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE BRIGADE | DRAWING |  | Balance of Plant | FIRE BRIGADE |  | DRAWING for FIRE BRIGADE | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦brigade¦fire¦fire_protection | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.1667 | 0.5177 | 0.2720 | 0.2720 | [6 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible | bop | fire_fighting | bop | query | bop | match | true | false | 3 | 4 | 15.2822 | 0.4577 | 0.0315 | 0.0236 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165515 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WORKSHOP & STORAGE BUILDING | DRAWING |  | Balance of Plant | Workshop & Storage Building |  | DRAWING for Workshop & Storage Building |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦storage¦workshop | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9079 | 0.9724 | 0.6807 | [6 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match | bop | bop | bop | query | bop | match | true | false | 3 | 7 | 15.2822 | 0.4432 | 0.0308 | 0.0308 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165516 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR H2, CO2, N2 STORAGE SHELTER | DRAWING | Hydrogen System |  | Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | DRAWING for Hydrogen, Carbon Dioxide, Nitrogen STORAGE SHELTER |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦carbon¦dioxide¦hydrogen¦nitrogen¦shelter¦storage | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8618 | 0.9585 | 0.6710 | [6 empty] | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | h2¦n2 | bop | h2¦n2 | query | n2 | match | true | false | 3 | 5 | 13.6244 | 0.5763 | 0.0313 | 0.0313 | hybrid | structured_preferred | h2¦n2 | civil_design | 10 | 2024-07-21 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.30 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165517 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COMPRESSOR SHELTER | DRAWING | Air Compressor | Compressed Air System | Air Compressor Shelter |  | DRAWING for Air Compressor Shelter |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | air¦bop¦compressor¦shelter | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8739 | 0.9622 | 0.6735 | [6 empty] | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | bop | compressed_air | query | compressed_air | match | true | false | 3 | 5 | 31.4769 | 0.6351 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.30 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165518 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR DEAERATOR SUPPORT STRUCTURE | DRAWING |  | Balance of Plant |  |  | DRAWING for BOP |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | balance¦bop¦plant | bop | scoped | match | match | match | passed |  | 0.2500 | 0.5666 | 0.3450 | 0.2415 | [6 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match | bop | bop | bop | query | bop | match | true | false | 10 | 1 | 14.3113 | 0.4919 | 0.0307 | 0.0307 | hybrid | structured_preferred | bop | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165519 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER (CPP) | DRAWING | Fin Fan Cooler | Closed Cooling Water System | Fire Water Pump House |  | DRAWING for Fire Water Pump House | Fire Fighting System | WASTE WATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦fire¦fire_protection¦house¦pump¦water | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.2857 | 0.5687 | 0.3706 | 0.3706 | [6 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw¦fire_fighting | fire_fighting¦wts | ccw¦fire_fighting | query | ccw¦gtg | match | true | false | 3 | 2 | 50.7028 | 0.6683 | 0.0320 | 0.0240 | hybrid | structured_preferred | ccw¦fire_fighting | system_design¦civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165520 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | DRAWING | Tank |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | DRAWING for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | Water Treatment System | Cable Tray Layout DraWing for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.6003 | 0.5301 | 0.5301 | [6 empty] | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | bop¦wts | wts | bop¦wts | query | wts | match | true | false | 4 | 2 | 34.5566 | 0.6028 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | bop¦wts | civil_design |  | 2025-01-30 | 2025-03-01 | 2025-03-31 | 2025-04-15 | 2025-04-30 | 2025-05-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165521 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WATER TREATMENT BUILDING | DRAWING |  | Water Treatment System | Water Treatment Building |  | DRAWING for Water Treatment Building | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.6497 | 0.5449 | 0.5449 | [6 empty] | FI | 0EF3010W16A01 | (WTS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-01-09 | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | true | false | 10 | 1 | 21.1119 | 0.6425 | 0.0307 | 0.0307 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165522 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CPP & CPP REGENERATION BUILDING | DRAWING |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | DRAWING for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGENERATION BUILDING |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦condensate¦plant¦polising¦regeneration | bop | scoped | match | match | match | passed |  | 1.0000 | 0.9000 | 0.9700 | 0.6790 | [6 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match | bop¦condensate | bop | bop¦condensate | query | bop | match | true | false | 10 | 1 | 7.0481 | 0.4605 | 0.0307 | 0.0307 | hybrid | structured_preferred | bop¦condensate | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165523 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | DRAWING | Steam Turbine Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | Chemical Dosing Shelter |  | DRAWING for Chemical Dosing Shelter |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8401 | 0.9520 | 0.6664 | [6 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | hrsg¦stg¦wts | bop | hrsg¦stg¦wts | query | gsut_uat¦stg | match | true | false | 26 | 11 | 17.5443 | 0.6342 | 0.0257 | 0.0257 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165524 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR HRSG | DRAWING | Heat Recovery Steam Generator | CHEMICAL DOSING | Chemical Dosing Shelter |  | DRAWING for Chemical Dosing Shelter |  | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam | bop | scoped | match | match | match | passed |  | 1.0000 | 0.8422 | 0.9527 | 0.6669 | [6 empty] | FA | 3EF1600W00A01.1 | (HRSG #32 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg¦wts | bop | hrsg¦wts | query | hrsg | match | true | false | 34 | 3 | 12.8284 | 0.6461 | 0.0265 | 0.0265 | hybrid | structured_preferred | hrsg¦wts | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165525 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | Layout Drawing | Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7636 | 0.9291 | 0.6504 | g_ambig | generic_ok | 0.76 |  | 1 | An exposed conduit layout for a transformer area is not a generator foundation embedded metals layout. | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 4 | 1 | 10.8503 | 0.6609 | 0.0320 | 0.0240 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165526 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | Layout Drawing | Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7613 | 0.9284 | 0.6499 | g_ambig | generic_ok | 0.76 |  | 1 | An exposed conduit layout for a transformer area is not a generator foundation embedded metals layout. | FA | 2EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 3 | 4 | 11.5520 | 0.6575 | 0.0315 | 0.0236 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165527 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | Layout Drawing | Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7585 | 0.9275 | 0.6493 | g_ambig | generic_ok | 0.76 |  | 1 | An exposed conduit layout for a transformer area is not a generator foundation embedded metals layout. | FA | 3EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 3 | 3 | 11.5824 | 0.6572 | 0.0317 | 0.0238 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165528 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | Layout Drawing | Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7536 | 0.9261 | 0.6482 | g_ambig | generic_ok | 0.76 |  | 1 | An exposed conduit layout for a transformer area is not a generator foundation embedded metals layout. | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 14 | 3 | 9.2505 | 0.6544 | 0.0294 | 0.0220 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165529 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | Layout Drawing | Gas Turbine Generator |  |  |  | Layout Drawing for GTG |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7580 | 0.9274 | 0.6492 | g_ambig | generic_ok | 0.76 |  | 1 | An exposed conduit layout for a transformer area is not a generator foundation embedded metals layout. | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | design_drawing | civil_design | compatible | gtg |  | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 10 | 1 | 9.2505 | 0.6514 | 0.0307 | 0.0230 | hybrid | structured_preferred | gtg | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165531 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM - GENERAL INFORMATION | WIRING DIAGRAM | Balance of Plant | Instrumentation and Control Cable |  |  | WIRING DIAGRAM for Instrumentation and Control Cable |  | Cable Interconnection Wiring Diagram | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | bop¦cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6900 | 0.7320 | 0.7320 | g_safe | [5 empty] | FI | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bop |  | bop | query |  | activity_unscoped | true | true | 3 | 26 | 25.3730 | 0.5706 | 0.0275 | 0.0165 | hybrid | structured_phase_gap | bop | system_design¦engineering |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165532 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HP STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | HIGH PRESSURE STEAM SYSTEM |  |  | WIRING DIAGRAM for HIGH PRESSURE STEAM SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦high¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6361 | 0.8908 | 0.8908 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | true | false | 2 | 1 | 19.0796 | 0.6327 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165533 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR IP STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | Intermediate Pressure STEAM SYSTEM |  |  | WIRING DIAGRAM for Intermediate Pressure STEAM SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦intermediate¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6449 | 0.8935 | 0.8935 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | true | false | 1 | 1 | 19.0796 | 0.6581 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165534 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR LP STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | LOW PRESSURE STEAM SYSTEM |  |  | WIRING DIAGRAM for LOW PRESSURE STEAM SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦low¦pressure¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6307 | 0.8892 | 0.8892 | g_safe | [5 empty] | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | true | false | 2 | 1 | 19.0796 | 0.6312 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165535 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR PROCESS STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | PROCESS STEAM SYSTEM |  |  | WIRING DIAGRAM for PROCESS STEAM SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6221 | 0.8866 | 0.8866 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | true | false | 1 | 1 | 19.0796 | 0.6475 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165536 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR STEAM DRAIN SYSTEM | WIRING DIAGRAM | Balance of Plant | STEAM DRAIN SYSTEM |  |  | WIRING DIAGRAM for STEAM DRAIN SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦drain¦steam |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6204 | 0.8861 | 0.8861 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦steam |  | bop¦steam | query | steam | match | true | false | 1 | 1 | 19.0796 | 0.6417 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦steam | system_design¦engineering | 3 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165537 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CONDENSATE SYSTEM | WIRING DIAGRAM | Balance of Plant | CONDENSATE SYSTEM |  |  | WIRING DIAGRAM for CONDENSATE SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦condensate |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6348 | 0.8904 | 0.8904 | g_safe | [5 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | bop¦condensate |  | bop¦condensate | query | condensate | match | true | false | 1 | 1 | 25.2202 | 0.6994 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦condensate | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165538 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FEEDWATER SYSTEM | WIRING DIAGRAM | Balance of Plant | FEEDWATER SYSTEM |  |  | WIRING DIAGRAM for FEEDWATER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦feedwater |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6389 | 0.8917 | 0.8917 | g_safe | [5 empty] | FA | 1EF3015W00A02 | (FWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-11-14 | system_design | system_design | match | bop¦feedwater |  | bop¦feedwater | query | feedwater | match | true | false | 1 | 1 | 12.9695 | 0.6861 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦feedwater | system_design¦engineering | 1 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165539 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CLOSED COOLING WATER SYSTEM | WIRING DIAGRAM | Balance of Plant | CLOSED COOLING WATER SYSTEM |  |  | WIRING DIAGRAM for CLOSED COOLING WATER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6257 | 0.8877 | 0.8877 | g_safe | [5 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bop¦ccw |  | bop¦ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 14.0434 | 0.4357 | 0.0325 | 0.0325 | hybrid | structured_preferred | bop¦ccw | system_design¦engineering | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165540 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | WIRING DIAGRAM | Balance of Plant | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | WIRING DIAGRAM for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦demineralized¦storage¦transfer¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6080 | 0.8824 | 0.8824 | g_safe | [5 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | bop¦wts |  | bop¦wts | query | wts | match | true | false | 1 | 1 | 26.0522 | 0.6296 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | system_design¦engineering | 5 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165541 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | WIRING DIAGRAM | Balance of Plant | Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | WIRING DIAGRAM for Gas Turbine ROTOR COOLING AIR SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦bop¦cooling¦gas¦gtg¦rotor¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6156 | 0.8847 | 0.8847 | g_ambig | generic_ok | 0.66 |  | 3 | A BOP interconnection wiring diagram for the GT rotor cooling air system is not clearly a GT terminal box wiring diagram or GT air intake filter local control panel logic/wiring diagram. | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bop¦gtg |  | bop¦gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 8.1717 | 0.5538 | 0.0323 | 0.0323 | hybrid | structured_preferred | bop¦gtg | system_design¦engineering | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165542 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | WIRING DIAGRAM | Balance of Plant | Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | WIRING DIAGRAM for Gas Turbine PERFORMANCE HEATER SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦gas¦gtg¦heater¦performance¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6078 | 0.8823 | 0.8823 | g_ambig | generic_ok | 0.66 |  | 3 | A BOP interconnection wiring diagram for the GT rotor cooling air system is not clearly a GT terminal box wiring diagram or GT air intake filter local control panel logic/wiring diagram. | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | bop¦gtg |  | bop¦gtg | query | ccw¦gtg | match | true | false | 1 | 3 | 3.1088 | 0.5464 | 0.0323 | 0.0323 | hybrid | structured_preferred | bop¦gtg | system_design¦engineering | 3 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165543 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | WIRING DIAGRAM | Balance of Plant | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | WIRING DIAGRAM for POTABLE WATER STORAGE AND SUPPLY SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦potable¦storage¦supply¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6098 | 0.8829 | 0.8829 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | bop¦wts |  | bop¦wts | query | wts | match | true | false | 1 | 7 | 48.9317 | 0.6793 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | bop¦wts | system_design¦engineering |  | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165544 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | WIRING DIAGRAM | Balance of Plant | POTABLE WATER DISTRIBUTION SYSTEM |  |  | WIRING DIAGRAM for POTABLE WATER DISTRIBUTION SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦distribution¦potable¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6210 | 0.8863 | 0.8863 | g_safe | [5 empty] | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | system_design | system_design | match | bop¦wts |  | bop¦wts | query | wts | match | true | false | 1 | 1 | 39.1368 | 0.6703 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | system_design¦engineering | 5 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165545 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR COMPRESSED AIR SYSTEM | WIRING DIAGRAM | Balance of Plant | COMPRESSED AIR SYSTEM |  |  | WIRING DIAGRAM for COMPRESSED AIR SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | air¦bop¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6367 | 0.8910 | 0.8910 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match | bop¦compressed_air |  | bop¦compressed_air | query | compressed_air | match | true | false | 4 | 4 | 37.5955 | 0.6918 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | bop¦compressed_air | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165546 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FUEL GAS SYSTEM | WIRING DIAGRAM | Balance of Plant | FUEL GAS SYSTEM |  |  | WIRING DIAGRAM for FUEL GAS SYSTEM | Fuel Gas System | Interconnection Wiring Diagram | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | bop¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.8270 | 0.8314 | 0.8314 | [6 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match | bop¦fgp | fgp | bop¦fgp | query | fgp | match | true | false | 1 | 1 | 22.7652 | 0.6752 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦fgp | system_design¦engineering | 2 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165547 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR ELECTRICAL SYSTEM | WIRING DIAGRAM | Balance of Plant | ELECTRICAL SYSTEM |  |  | WIRING DIAGRAM for ELECTRICAL SYSTEM |  | Interconnection Wiring Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6879 | 0.9064 | 0.9064 | g_safe | [5 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | bop¦electrical |  | bop¦electrical | query |  | activity_unscoped | true | true | 173 | 85 | 13.8749 | 0.5558 | 0.0112 | 0.0067 | hybrid | structured_phase_gap | bop¦electrical | system_design¦engineering |  | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165548 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | WIRING DIAGRAM | Balance of Plant | INTERFACE WITH OTHER CONTROL SYSTEM |  |  | WIRING DIAGRAM for INTERFACE WITH OTHER CONTROL SYSTEM |  | Interconnection Wiring diagram | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | wiring_diagram | wiring_diagram | bop¦interface¦other¦with |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6667 | 0.9000 | 0.9000 | g_safe | [5 empty] | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | bop |  | bop | query |  | activity_unscoped | true | true | 102 | 135 | 16.1585 | 0.5158 | 0.0113 | 0.0068 | hybrid | structured_phase_gap | bop | system_design¦engineering |  | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 |  | false | false | 0.39 | needs_review | default_fc_window;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165551 | BOP - I&C CABLE SCHEDULE - GENERAL INFORMATION | Schedule | Balance of Plant | Balance of Plant |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6334 | 0.6567 | 0.6567 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 1 | 1 | 28.9095 | 0.6927 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165552 | BOP - I&C CABLE SCHEDULE FOR HP STEAM SYSTEM | Schedule | Balance of Plant | HIGH PRESSURE STEAM SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5764 | 0.6396 | 0.6396 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | true | false | 1 | 1 | 24.5543 | 0.6666 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165553 | BOP - I&C CABLE SCHEDULE FOR IP STEAM SYSTEM | Schedule | Balance of Plant | Intermediate Pressure STEAM SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5848 | 0.6421 | 0.6421 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | true | false | 1 | 1 | 24.5543 | 0.6820 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165554 | BOP - I&C CABLE SCHEDULE FOR LP STEAM SYSTEM | Schedule | Balance of Plant | LOW PRESSURE STEAM SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5868 | 0.6427 | 0.6427 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | true | false | 1 | 1 | 24.5543 | 0.6674 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165555 | BOP - I&C CABLE SCHEDULE FOR PROCESS STEAM SYSTEM | Schedule | Balance of Plant | PROCESS STEAM SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5751 | 0.6392 | 0.6392 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | true | false | 1 | 1 | 24.5543 | 0.6896 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165556 | BOP - I&C CABLE SCHEDULE FOR STEAM DRAIN SYSTEM | Schedule | Balance of Plant | STEAM DRAIN SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5714 | 0.6381 | 0.6381 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦steam |  | bop¦steam | query | bop | match | true | false | 1 | 1 | 24.5543 | 0.6503 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦steam | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165557 | BOP - I&C CABLE SCHEDULE FOR CONDENSATE SYSTEM | Schedule | Balance of Plant | CONDENSATE SYSTEM |  |  | Schedule for BOP | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7541 | 0.6462 | 0.6462 | g_safe | [5 empty] | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦condensate |  | bop¦condensate | query | bop | match | true | false | 1 | 4 | 24.5543 | 0.6563 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | bop¦condensate | procurement |  | 2024-12-13 | 2025-01-12 | 2025-02-11 | 2025-02-26 | 2025-03-13 | 2025-03-28 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165558 | BOP - I&C CABLE SCHEDULE FOR FEEDWATER SYSTEM | Schedule | Balance of Plant | FEEDWATER SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5763 | 0.6396 | 0.6396 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦feedwater |  | bop¦feedwater | query | bop | match | true | false | 1 | 9 | 24.5543 | 0.6406 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | bop¦feedwater | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165559 | BOP - I&C CABLE SCHEDULE FOR CLOSED COOLING WATER SYSTEM | Schedule | Balance of Plant | CLOSED COOLING WATER SYSTEM |  |  | Schedule for BOP | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7679 | 0.6504 | 0.6504 | g_safe | [5 empty] | FA | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | procurement | procurement | match | bop¦ccw |  | bop¦ccw | query | ccw | match | true | false | 1 | 1 | 36.0068 | 0.6528 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop¦ccw | procurement |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165560 | BOP - I&C CABLE SCHEDULE FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Schedule | Balance of Plant | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5595 | 0.6345 | 0.6345 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦wts |  | bop¦wts | query | bop | match | true | false | 1 | 1 | 24.5543 | 0.6397 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | procurement | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165561 | BOP - I&C CABLE SCHEDULE FOR GT ROTOR COOLING AIR SYSTEM | Schedule | Balance of Plant | Gas Turbine ROTOR COOLING AIR SYSTEM |  |  | Schedule for BOP | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦gtg¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7627 | 0.6488 | 0.6488 | g_safe | [5 empty] | FA | 1PF1265W42A13P | (TCA Cooler) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2008-02-29 | procurement | procurement | match | bop¦gtg |  | bop¦gtg | query | fgp¦gtg | match | true | false | 16 | 2 | 19.7670 | 0.6700 | 0.0293 | 0.0293 | hybrid | structured_preferred | bop¦gtg | procurement | 10 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165562 | BOP - I&C CABLE SCHEDULE FOR GT PERFORMANCE HEATER SYSTEM | Schedule | Balance of Plant | Gas Turbine PERFORMANCE HEATER SYSTEM |  |  | Schedule for BOP | FinFan Cooler | I&C Cable Schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦gtg¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.7178 | 0.6353 | 0.6353 | g_safe | [5 empty] | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦gtg |  | bop¦gtg | query | bop | match | true | false | 4 | 23 | 24.5543 | 0.6283 | 0.0277 | 0.0277 | hybrid | structured_cell_found_text_preferred | bop¦gtg | procurement |  | 2024-12-13 | 2025-01-12 | 2025-02-11 | 2025-02-26 | 2025-03-13 | 2025-03-28 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165563 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | Schedule | Balance of Plant | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | Schedule for BOP | H2, CO2 Supply System | Cable schedule | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5962 | 0.6455 | 0.6455 | g_safe | [5 empty] | FA | 0PF3035W42A06P | (PWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | bop¦wts | h2 | bop¦wts | query | wts | match | true | false | 1 | 1 | 37.7825 | 0.6834 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | procurement | 10 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165564 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER DISTRIBUTION SYSTEM | Schedule | Balance of Plant | POTABLE WATER DISTRIBUTION SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5597 | 0.6346 | 0.6346 | g_safe | [5 empty] | SKIP | 0PF3035W42A06P | (PWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | bop¦wts |  | bop¦wts | query | wts | match | true | false | 1 | 1 | 32.8578 | 0.6599 | 0.0328 | 0.0328 | hybrid | structured_preferred | bop¦wts | procurement | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165565 | BOP - I&C CABLE SCHEDULE FOR COMPRESSED AIR SYSTEM | Schedule | Balance of Plant | COMPRESSED AIR SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5568 | 0.6337 | 0.6337 | g_safe | [5 empty] | SKIP | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | procurement | procurement | match | bop¦compressed_air |  | bop¦compressed_air | query | compressed_air | match | true | false | 4 | 4 | 31.8503 | 0.6751 | 0.0312 | 0.0312 | hybrid | structured_cell_found_text_preferred | bop¦compressed_air | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165566 | BOP - I&C CABLE SCHEDULE FOR FUEL GAS SYSTEM | Schedule | Balance of Plant | FUEL GAS SYSTEM |  |  | Schedule for BOP | Fuel Gas System | Cable schedule & Sizing | 1 | start+12W<=FA<=FC<=start+24W | FA ∈ [start+84d, start+168d] ¦ FC ∈ [start+84d, start+168d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦fgp¦plant | fgp | scoped | match | match | match | passed |  | 0.8333 | 0.7085 | 0.7959 | 0.7959 | [6 empty] | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦fgp | fgp | bop¦fgp | query | bop | match | true | false | 1 | 17 | 24.5543 | 0.6263 | 0.0294 | 0.0294 | hybrid | structured_cell_found_text_preferred | bop¦fgp | procurement |  | 2024-12-07 | 2025-01-18 | 2025-03-01 | 2025-02-08 | 2025-03-22 | 2025-05-03 | generated | 0.90 |  | false | false | 1.00 | usable |  |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165567 | BOP - I&C CABLE SCHEDULE FOR ELECTRICAL SYSTEM | Schedule | Balance of Plant | ELECTRICAL SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6342 | 0.6569 | 0.6569 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop¦electrical |  | bop¦electrical | query | bop | match | true | false | 1 | 2 | 24.5543 | 0.6519 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | bop¦electrical | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165568 | BOP - I&C CABLE SCHEDULE FOR INTERFACE WITH OTHER CONTROL SYSTEM | Schedule | Balance of Plant | OTHER CONTROL SYSTEM |  |  | Schedule for BOP | Substation | Cable Schedule | 1 | start+16W<=FA<=start+16W+2M | FA ∈ [start+112d, start+172d] | title | list | list | cable_schedule | cable_schedule | balance¦bop¦plant |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5931 | 0.6446 | 0.6446 | g_safe | [5 empty] | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | procurement | procurement | match | bop |  | bop | query | bop | match | true | false | 1 | 1 | 24.5543 | 0.6734 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | bop | procurement | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165571 | BOP EXPOSED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | EXPOSED CONDUIT LAYOUT | Balance of Plant | Balance of Plant |  |  | EXPOSED CONDUIT LAYOUT for Tank |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦fire_protection¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8615 | 0.9584 | 0.6709 | g_safe | [5 empty] | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 2 | 1 | 28.8032 | 0.5044 | 0.0325 | 0.0244 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165572 | BOP EXPOSED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | EXPOSED CONDUIT LAYOUT | Balance of Plant | Balance of Plant |  |  | EXPOSED CONDUIT LAYOUT for Tank |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8615 | 0.9584 | 0.6709 | g_safe | [5 empty] | FA | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 2 | 1 | 28.8032 | 0.5051 | 0.0325 | 0.0244 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165573 | BOP EXPOSED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | Layout Drawing | Tank | Balance of Plant |  |  | Layout Drawing for Tank |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦tank |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7389 | 0.9217 | 0.6452 | g_safe | [5 empty] | FA | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | design_drawing | civil_design | compatible | bop |  | bop | query | bop | match | true | false | 1 | 9 | 21.3714 | 0.4998 | 0.0309 | 0.0232 | hybrid | structured_preferred | bop | system_design¦civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165575 | BOP EXPOSED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | Layout Drawing | Fin Fan Cooler | Closed Cooling Water System |  |  | Layout Drawing for Pump | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦pump |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7421 | 0.8060 | 0.8060 | g_ambig | generic_ok | 0.62 |  | 2 | The document is an exposed conduit layout for the fin fan cooler/pump area, which does not clearly match the specific JB/panel outline and layout drawing rules. | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | design_drawing | civil_design | compatible | ccw | ccw | ccw | query | ccw¦gtg | match | true | false | 3 | 2 | 55.5593 | 0.6767 | 0.0320 | 0.0240 | hybrid | structured_preferred | ccw | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165576 | BOP EXPOSED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | Layout Drawing | Steam Turbine & Generator |  |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | bop¦generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | [6 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 9 | 1 | 16.4401 | 0.6502 | 0.0309 | 0.0232 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165577 | BOP EXPOSED CONDUIT LAYOUT FOR PIPE RACK AREA | Layout Drawing |  | Balance of Plant | Pipe Rack |  | Layout Drawing for Pipe Rack |  | EXPOSED CONDUIT LAYOUT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | bop¦pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7878 | 0.9363 | 0.6554 | g_safe | [5 empty] | FA | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | civil_design | civil_design | match | bop |  | bop | query | bop | match | true | false | 1 | 6 | 37.4875 | 0.5901 | 0.0315 | 0.0315 | hybrid | structured_preferred | bop | civil_design | 10 | 2024-04-19 | 2024-05-04 | 2024-05-19 | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165701 | TECHNICAL SPECIFICATION FOR I&C CABLE | Technical Specification | Instrumentation and Control Cable |  |  |  | Technical Specification for Instrumentation and Control Cable |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | cable¦instrumentation |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7046 | 0.6780 | 0.6780 | g_safe | [5 empty] | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 1 | 26.2974 | 0.6382 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165711 | TECHNICAL SPECIFICATION FOR JUNCTION BOX & RACK | Technical Specification | Junction Box |  |  |  | Technical Specification for Junction Box | LOCAL BOX | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | box¦junction |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6596 | 0.4979 | 0.4979 | g_safe | [5 empty] | FA | 2PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-06-28 | 2008-02-01 | procurement | procurement | match |  |  |  |  | bop | query_unscoped | false | false | 6 | 1 | 19.7891 | 0.5383 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | procurement |  | 2024-07-12 | 2024-08-11 | 2024-09-10 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165731 | TECHNICAL SPECIFICATION FOR INSTRUMENT INSTALLATION MATERIALS | Technical Specification |  | INSTRUMENT INSTALLATION MATERIALS |  |  | Technical Specification for INSTRUMENT INSTALLATION MATERIALS | INSTRUMENT INSTALLATION MATERIA | Technical Specification With Data sheet | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | specification | specification | technical_specification | technical_specification | installation¦instrument¦materials |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.8404 | 0.6021 | 0.6021 | g_safe | [5 empty] | FA | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 | procurement | procurement | match |  |  |  |  | electrical | query_unscoped | false | false | 2 | 5 | 29.1037 | 0.5548 | 0.0315 | 0.0236 | hybrid | structured_no_system |  | procurement |  | 2024-06-13 | 2024-07-13 | 2024-08-12 | 2024-08-27 | 2024-09-11 | 2024-09-26 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-165900 | DESCRIPTION OF SETTLEMENT SYSTEM | DESCRIPTION |  | SETTLEMENT SYSTEM |  |  | DESCRIPTION for SETTLEMENT SYSTEM | [5 empty] | rule_query | other | description | description | system_description | settlement | gt¦gtg | scoped | mismatch | not_applicable | mismatch | rejected | scope_mismatch | 0.6667 | 0.4512 | 0.6020 | 0.6020 | [7 empty] | 2CF3035W58A01 | (SWS) Piping Work(Block #2) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Service Water System (BOP) | 2008-10-17 | 2008-12-16 |  |  | query_unknown |  |  |  |  | bop¦service_water | query_unscoped | false | false | 13 | 72 | 6.1593 | 0.3252 | 0.0213 | 0.0120 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0ZEN-167001 | CYBER SECURITY PLAN | Plan |  |  |  |  | Plan |  | CYBER SECURITY PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | [6 empty] | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | true | 2 | 15 | 24.0608 | 0.3306 | 0.0295 | 0.0133 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170101 | SOIL INVESTIGATION REPORT | REPORT |  |  |  |  | REPORT |  | SOIL INVESTIGATION REPORT | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | report | report | report | report |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 |  | civil_design | query_unknown |  |  |  |  | stg | query_unscoped | false | false | 5 | 9 | 8.3777 | 0.4075 | 0.0299 | 0.0168 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | fa_earliest | false | false | 0.43 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170102 | TOPOGRAPHIC SURVEY REPORT | REPORT |  |  |  |  | REPORT |  | TOPOGRAPHIC SURVEY REPORT | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | report | report | report | report |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | true | 30 | 1 |  | 0.4617 | 0.0275 | 0.0124 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-15 | 2024-04-30 | 2024-05-15 | generated | 0.90 | fa_earliest | false | false | 0.35 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ZEN-170103 | PILE CAPACITY CALCULATION | Calculation sheet |  |  |  |  | Calculation sheet |  | PILE CAPACITY CALCULATION | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match |  |  |  |  | stg | query_unscoped | true | false | 1 | 12 | 11.0757 | 0.4423 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | civil_design |  | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ZEN-170104 | WORKING PILE DETAIL | Detail Drawing |  |  |  |  | Detail Drawing |  | WORKING PILE DETAIL | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | design_drawing | civil_design | compatible |  |  |  |  | stg | query_unscoped | true | false | 3 | 5 | 11.0757 | 0.4827 | 0.0313 | 0.0176 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 |  | false | false | 0.43 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170105 | REPORT FOR PILE LOAD TEST OF BORED CAST - IN - PLACE PILE | REPORT |  |  |  |  | REPORT |  | REPORT FOR PILE LOAD TEST OF BORED CAST - IN - PLACE PILE | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | report | report | test_report | test_report |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 2CF3035W62A02.1 | (PWS) Hydro Test(Block #2) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Potable Water System (BOP) | 2009-01-03 | 2009-01-19 | commissioning | commissioning | match |  |  |  |  | bop¦wts | query_unscoped | true | false | 15 | 107 | 10.6956 | 0.3746 | 0.0193 | 0.0145 | hybrid | structured_no_system |  | commissioning |  | 2025-12-05 | 2026-01-04 | 2026-02-03 | 2026-02-18 | 2026-03-05 | 2026-03-20 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171001 | GTG FOUNDATION - PILE CALCULATION SHEET | CALCULATION SHEET | Gas Turbine Generator |  |  |  | CALCULATION SHEET for GTG |  | GTG #1,2 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6970 | 0.6758 | 0.6758 | [6 empty] | FI | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 1 | 1 | 14.7658 | 0.6787 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | fi_complete | date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171002 | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | General Arrangement Drawing | Gas Turbine Generator |  |  |  | General Arrangement Drawing for GTG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7920 | 0.9376 | 0.9376 | g_ambig | uncertain | 0.50 |  | 3 | The title is GTG foundation pile arrangement, and it is unclear whether it should be governed by the GTG auxiliary foundation GA specific rule or remain under the generic GA rule. | FA | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | true | false | 2 | 1 | 21.2052 | 0.6911 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171004 | GTG FOUNDATION - DESIGN REPORT | DESIGN REPORT | Gas Turbine Generator |  |  |  | Design Report for GTG |  | GTG FOUNDATION - DESIGN REPORT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | report | report | design_report | design_report | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.7500 | 0.7775 | 0.7583 | 0.7583 | [6 empty] | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 4 | 7 | 13.7592 | 0.6901 | 0.0306 | 0.0306 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171005 | GT FDN GENERAL NOTES FORMWORK DWG | Drawing | Gas Turbine Generator |  |  |  | Drawing for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5713 | 0.4514 | 0.4514 | [6 empty] | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 4 | 2 | 9.2289 | 0.6672 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171006 | GT FDN TOP PLAN VIEW INSERT PLATE ARRANGEMENT AND DETAILS FORMWORK DWG, PART 1/6 | Drawing | Gas Turbine Generator |  |  |  | Drawing for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5044 | 0.2913 | 0.2913 | [6 empty] | FI | 2EF1213W16A01.1 | (GT #22) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | 2007-03-30 | 2007-08-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 12 | 4 | 10.3503 | 0.6577 | 0.0295 | 0.0295 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171007 | GT FDN TOP PLAN VIEW ANCHOR BOLT ARRANGEMENT AND DETAILS FORMWORK DRAWING, PART 2/6 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5300 | 0.2990 | 0.2990 | [6 empty] | FI | 2EF1213W16A01.1 | (GT #22) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | 2007-03-30 | 2007-08-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 9 | 1 | 10.8863 | 0.6863 | 0.0309 | 0.0309 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171008 | GT FDN TOP PLAN VIEW EXPANSION BOLT ARRGMNT AND DETAIL FORMWORK DWG, 3/6 | Drawing | Gas Turbine Generator |  |  |  | Drawing for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5044 | 0.2913 | 0.2913 | [6 empty] | FI | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 11 | 5 | 11.0293 | 0.6494 | 0.0295 | 0.0295 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171009 | GT FDN VIEWS & SECTIONS FORMWORK DWG, PART 4/6 | Drawing | Gas Turbine Generator |  |  |  | Drawing for GTG |  | GTG #1,2 LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2500 | 0.4878 | 0.3213 | 0.3213 | [6 empty] | FI | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 13 | 3 | 9.2289 | 0.6425 | 0.0296 | 0.0296 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171010 | GT FDN ANCHOR BOLT DETAILS FORMWORK DWG, PART 5/6 | Drawing | Gas Turbine Generator |  |  |  | Drawing for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5044 | 0.2913 | 0.2913 | [6 empty] | FI | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 11 | 1 | 9.2289 | 0.6522 | 0.0305 | 0.0305 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171011 | GT FDN TOP PLAN VIEW SCHEDULE OF EMBEDDED PARTS FORMWORK DRAWING, PART 6/6 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.2000 | 0.5056 | 0.2917 | 0.2917 | [6 empty] | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 7 | 1 | 9.2291 | 0.6602 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171012 | GT FDN BOTTOM LONGITUDINAL & LATERAL REINFORCEMENT REINFORCEMENT DRAWING BASEMAT, PART 1/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5815 | 0.4544 | 0.4544 | [6 empty] | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 4 | 1 | 10.4641 | 0.6637 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171013 | GT FDN TOP LOGITUDINAL & LATERAL REINFORCEMENT DWG BASEMAT, PART 2/9 | Drawing | Gas Turbine Generator |  |  |  | Drawing for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5713 | 0.4514 | 0.4514 | [6 empty] | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 5 | 1 | 11.0058 | 0.6830 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171014 | GT FDN BOTTOM & TOP (3rd + 4th LAYER) LATERAL & LONGITUDINAL REINFORCEMENT, PART 3/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5815 | 0.4544 | 0.4544 | [6 empty] | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 6 | 5 | 11.0293 | 0.6660 | 0.0305 | 0.0305 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171015 | GT FDN CONNECTION AND SIDE FACE REINFORCEMENT PLAN AT +0.152M & 1.099M LEVEL REINFORCEMENT DRAWING BASEMAT, PART 4/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5815 | 0.4544 | 0.4544 | [6 empty] | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 12 | 1 | 10.4641 | 0.6575 | 0.0303 | 0.0303 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171016 | GT FDN SPACER REBARS AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 5/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5300 | 0.2990 | 0.2990 | [6 empty] | FI | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 3 | 2 | 9.2289 | 0.6466 | 0.0320 | 0.0320 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171017 | GT FDN SECTION 1-1 AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 6/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5300 | 0.2990 | 0.2990 | [6 empty] | FI | 1EF1213W16A01.1 | (GT #12) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | 2007-03-01 | 2007-07-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 7 | 6 | 12.2520 | 0.6681 | 0.0301 | 0.0301 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171018 | GT FDN REINFORCEMENT SECTION 2-2 AND 3-3 REINFORCEMENT DRAWING BASEMAT, PART 7/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #3,4,5 LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2500 | 0.5116 | 0.3285 | 0.3285 | [6 empty] | FI | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 4 | 2 | 12.7827 | 0.6483 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171019 | GT FDN REINFORCEMENT DETAILS SECTION 4-4 AND 5-5 REINFORCEMENT DRAWING BASEMAT, PART 8/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5300 | 0.2990 | 0.2990 | [6 empty] | FI | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 14 | 1 | 9.2289 | 0.6327 | 0.0299 | 0.0299 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171020 | GT FDN REINFORCEMENT PLAN & SECTIONS FOR COMPRESSION SUPPORT, TURNING GEAR PEDESTAL AND MOUNTING PAD PEDESTAL REINFORCEMENT DRAWING BASEMAT, PART 9/9 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #3,4,5 LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2500 | 0.5116 | 0.3285 | 0.3285 | [6 empty] | FI | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 7 | 1 | 9.2289 | 0.6594 | 0.0313 | 0.0313 | hybrid | structured_preferred | gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171021 | GT FDN REINFORCEMENT PLAN AT +1.099M LEVEL AND SPACER & SIDE FACE REBARS GENERATOR DECK REINFORCEMENT, PART 1/2 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | 1 | start-1M<=FC<=start-1M-2M | FC ∈ [start-30d, start-90d] | rule_query | drawing | drawing | drawing | drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5815 | 0.4544 | 0.4544 | [6 empty] | FA | 2EF1213W16A01.1 | (GT #22) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | 2007-03-30 | 2007-08-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 1 | 9 | 14.2920 | 0.6596 | 0.0309 | 0.0309 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171022 | GT FDN SECTIONS & DETAILS GENERATOR DECK REINFORCEMENT, PART 2/2 | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5300 | 0.2990 | 0.2990 | [6 empty] | FI | 2EF1213W16A01.1 | (GT #22) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | 2007-03-30 | 2007-08-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 3 | 4 | 13.6059 | 0.6751 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171023 | GTG FOUNDATION BAR BENDING SCHEDULE | Schedule | Gas Turbine Generator |  |  |  | Schedule for GTG |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5758 | 0.4527 | 0.4527 | [6 empty] | FA | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-08-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 3 | 7 | 7.7053 | 0.6210 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | gtg | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171024 | GT FDN BENDING SCHEDULES - GENERATOR DECK | SCHEDULES | Gas Turbine Generator |  |  |  | SCHEDULES for GTG |  | GT FDN BENDING SCHEDULES - GENERATOR DECK | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.1667 | 0.6004 | 0.2968 | 0.2968 | [6 empty] | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 |  | civil_design | query_unknown | gtg | gtg | gtg | query | gtg | match | true | false | 5 | 5 | 10.1970 | 0.6115 | 0.0308 | 0.0231 | hybrid | structured_no_phase | gtg |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.52 | needs_review | rule_score_low;activity_phase_status=query_unknown;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171051 | GTG AUXILIARY FOUNDATION - DESIGN REPORT | DESIGN REPORT | Gas Turbine Generator |  |  |  | Design Report for GTG |  | GTG FOUNDATION - DESIGN REPORT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | report | report | design_report | design_report | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 0.7500 | 0.7775 | 0.7583 | 0.7583 | [6 empty] | FA | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 6 | 15.7724 | 0.7000 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171052 | GTG AUXILIARY FOUNDATION - GENERAL ARRANGEMENT | General Arrangement Drawing | Gas Turbine Generator |  |  |  | General Arrangement Drawing for GTG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | gas¦generator¦gtg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7920 | 0.9376 | 0.9376 | g_ambig | uncertain | 0.50 |  | 3 | The title is GTG foundation pile arrangement, and it is unclear whether it should be governed by the GTG auxiliary foundation GA specific rule or remain under the generic GA rule. | FA | 1EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 |  | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | true | false | 5 | 11 | 19.3566 | 0.6767 | 0.0295 | 0.0295 | hybrid | structured_cell_found_text_preferred | gtg | civil_design |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171053 | FOUNDATION FOR SFC & SEE TRANSFORMER PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING | Static Frequency Converter |  |  |  | DRAWING for Static Frequency Converter |  | TRANSFORMER PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | converter¦frequency¦static |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8551 | 0.9565 | 0.6696 | g_safe | [5 empty] | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦stg | match | true | false | 2 | 2 | 7.9841 | 0.5801 | 0.0323 | 0.0323 | hybrid | structured_preferred | gsut_uat | civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171054 | FOUNDATION FOR EXHAUST TRANSITION DUCT & COMPRESSOR BLEED PIPE SUPPORT PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DUCT |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for DUCT |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | duct |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8720 | 0.9616 | 0.6731 | g_safe | [5 empty] | FA | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-08-02 | 2007-12-13 | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | true | false | 33 | 1 | 13.5157 | 0.6195 | 0.0271 | 0.0204 | hybrid | structured_no_system |  | civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171055 | FOUNDATION FOR WOBBE METER CABINET, GT ENCLOSURE RIGHT SIDE EXHAUST END EXTERIOR PLATFORM & AIR COMPRESSOR SKID(DAIS) PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | Gas Turbine Generator |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for GTG |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8638 | 0.9591 | 0.6714 | g_ambig | generic_ok | 0.73 |  | 5 | The document concerns foundations for Wobbe meter cabinet/platform/air compressor skid, not the GTG LEB architectural or rebar detail specific rules. | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 | civil_design | civil_design | match | gtg |  | gtg | query | gtg | match | true | false | 29 | 5 | 9.2289 | 0.6584 | 0.0266 | 0.0266 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171056 | FOUNDATION FOR SEE/ SFC PACKAGE FOUNDATION INTERFACE-SEE ONLY PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | Static Frequency Converter PACKAGE |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for Static Frequency Converter PACKAGE |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | converter¦frequency¦static |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6467 | 0.6607 | 0.6607 | g_safe | [5 empty] | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | false | 25 | 6 | 13.4685 | 0.5310 | 0.0269 | 0.0202 | hybrid | structured_no_system |  | civil_design |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | 2025-03-31 | 2025-04-15 | 2025-04-30 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171057 | FOUNDATION FOR SEE/ SFC PACKAGE SEE WITH SFC NORMAL START PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | Static Frequency Converter PACKAGE |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for Static Frequency Converter PACKAGE |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | converter¦frequency¦static |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6174 | 0.6519 | 0.6519 | g_safe | [5 empty] | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | false | 52 | 6 | 11.2145 | 0.5281 | 0.0241 | 0.0181 | hybrid | structured_no_system |  | civil_design |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | 2025-03-31 | 2025-04-15 | 2025-04-30 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171058 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS FORMWORK DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK DRAWING |  | Electrical System |  |  | PLAN, SECTIONS AND DETAILS FORMWORK DRAWING for Electrical System |  | PLAN, SECTIONS AND DETAILS FORMWORK DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8753 | 0.9626 | 0.6738 | g_safe | [5 empty] | FA | 2EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | 2007-06-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦fgp | match | true | false | 21 | 2 | 10.5035 | 0.5824 | 0.0285 | 0.0285 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171059 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING |  | Electrical System |  |  | PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING for Electrical System |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5639 | 0.6358 | 0.6358 | g_safe | [5 empty] | FA | 2EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | 2007-06-01 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦fgp | match | true | false | 21 | 4 | 10.5035 | 0.5603 | 0.0280 | 0.0280 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171060 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM BAR BENDING SCHEDULE | BAR BENDING SCHEDULE |  | Electrical System |  |  | BAR BENDING SCHEDULE for Electrical System |  | FOUNDATION BAR BENDING SCHEDULE | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.6395 | 0.8919 | 0.6243 | g_safe | [5 empty] | FA | 1CF3530W16A03 | (Block #1 EDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-10-30 | 2007-12-29 | civil_design | civil_design | match | electrical |  | electrical | query | electrical | match | true | false | 26 | 5 | 8.3900 | 0.5699 | 0.0270 | 0.0270 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-06-17 | 2024-07-02 | 2024-07-17 | 2024-08-01 | 2024-08-31 | 2024-09-30 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171061 | FOUNDATION FOR ROTOR AIR COOLER(KETTLE BOILER) & ROTOR COOLING AIR PIPE SUPPORTS PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING |  |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | [6 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 47 | 4 | 13.7780 | 0.5436 | 0.0250 | 0.0187 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171062 | FOUNDATION FOR SFC CROSSOVER SWITCH & FIRE PROTECTION SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | Static Frequency Converter | Fire Fighting |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for Fire Fighting |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8615 | 0.9585 | 0.6709 | g_ambig | generic_ok | 0.60 |  | 1 | Although it mentions fire protection skid, the specific rule is for fire brigade misc structural detail and the match is not clear enough to override the generic timeline. | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 5 | 26.9000 | 0.5701 | 0.0305 | 0.0305 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171063 | FOUNDATION FOR PULSE AIR COMPRESSIOR SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | Compressor |  |  |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING for Compressor |  | PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | compressor |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8090 | 0.9427 | 0.6599 | g_safe | [5 empty] | FA | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | false | 65 | 7 | 10.2101 | 0.5876 | 0.0229 | 0.0172 | hybrid | structured_no_system |  | civil_design |  | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-10-05 | 2024-11-04 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171101 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION PILE DESIGN | Calculation sheet | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 4 | 21.0973 | 0.6506 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171102 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION DYNAMIC ANALYSIS | Calculation sheet | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 1 | 13.3572 | 0.6708 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171103 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION R.C DESIGN | Calculation sheet | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 1 | 16.6824 | 0.6903 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171104 | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | FOUNDATION LAYOUT | Steam Turbine & Generator |  |  |  | FOUNDATION LAYOUT for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 1.0000 | 0.8796 | 0.9639 | 0.9639 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 3 | 1 | 15.5923 | 0.7328 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171105 | STEAM TURBINE GENERATOR FOUNDATION PILE ARRANGEMENT | FOUNDATION PILE ARRANGEMENT | Steam Turbine & Generator |  |  |  | FOUNDATION PILE ARRANGEMENT for STG | [5 empty] | rule_query | other | other | foundation_pile_arrangement | hrsg_foundation_arrangement | generator¦steam¦stg¦turbine | hrsg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.6667 | 0.6362 | 0.6575 | 0.6575 | [7 empty] | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 3 | 28.7888 | 0.6828 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | stg | civil_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171106 | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Steam Turbine & Generator |  |  |  | PLAN AND SECTION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8571 | 0.8361 | 0.8508 | 0.8508 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 2 | 13.3572 | 0.7140 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171113 | STEAM TURBINE GENERATOR FOUNDATION ANCHOR BOLTS AND EMBEDMENT |  | Steam Turbine & Generator |  |  |  | for STG | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION ANCHOR BOLTS AND EMBEDMENT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | steam_turbine_generator_foundation_anchor_bolts_and_embedment | steam_turbine_generator_foundation_anchor_bolts_and_embedment | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 1.0000 | 0.9565 | 0.9869 | 0.9869 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 1 | 13.3572 | 0.6992 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0MPA-171117 | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | FOUNDATION R.C DETAIL | Steam Turbine & Generator |  |  |  | FOUNDATION R.C DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 1.0000 | 0.8664 | 0.9599 | 0.9599 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 1 | 15.5923 | 0.7079 | 0.0328 | 0.0328 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171201 | CALCULATION OF CCW FIN FAN COOLER FOUNDATION | Calculation sheet | Fin Fan Cooler | Closed Cooling Water |  |  | Calculation sheet for Fin Fan Cooler | CCW FIN FAN COOLER | CALCULATION OF CCW FIN FAN COOLER FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | cooler¦fan¦fin |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9617 | 0.9885 | 0.9885 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | true | false | 3 | 7 | 53.1054 | 0.6747 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | ccw | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171202 | CCW FIN FAN COOLER FOUNDATION LAYOUT | FOUNDATION LAYOUT | Fin Fan Cooler | Closed Cooling Water |  |  | FOUNDATION LAYOUT for Closed Cooling Water | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9568 | 0.9871 | 0.9871 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | true | false | 3 | 4 | 54.9276 | 0.7311 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | ccw | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171203 | CCW FIN FAN COOLER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Closed Cooling Water FIN FAN COOLER | Closed Cooling Water System |  |  | PLAN AND SECTION for Closed Cooling Water System | CCW FIN FAN COOLER | CCW FIN FAN COOLER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9659 | 0.9898 | 0.9898 | g_safe | [5 empty] | FA | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw | ccw | ccw | query | ccw¦gtg | match | true | false | 1 | 4 | 65.2170 | 0.7297 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | ccw | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171221 | CALCULATION OF CPP FIN FAN COOLER FOUNDATION | Calculation sheet | CONDENSATE POLISING PLANT FIN FAN COOLER | Closed Cooling Water System |  |  | Calculation sheet for CONDENSATE POLISING PLANT FIN FAN COOLER | CPP FIN FAN COOLER | CALCULATION OF CPP FIN FAN COOLER FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | condensate¦cooler¦fan¦fin¦plant¦polising |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9632 | 0.9889 | 0.9889 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw¦condensate | ccw | ccw¦condensate | query | ccw¦gtg | match | true | false | 3 | 10 | 49.6735 | 0.6265 | 0.0302 | 0.0302 | hybrid | structured_cell_found_text_preferred | ccw¦condensate | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171222 | CPP FIN FAN COOLER FOUNDATION LAYOUT | Layout Drawing | CONDENSATE POLISING PLANT FIN FAN COOLER | Closed Cooling Water System |  |  | Layout Drawing for Closed Cooling Water System | CPP FIN FAN COOLER | CPP FIN FAN COOLER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9044 | 0.9713 | 0.9713 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw¦condensate | ccw | ccw¦condensate | query | ccw¦gtg | match | true | false | 3 | 1 | 49.6735 | 0.6472 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | ccw¦condensate | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171223 | CPP FIN FAN COOLER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | CONDENSATE POLISING PLANT FIN FAN COOLER | Closed Cooling Water System |  |  | PLAN AND SECTION for Closed Cooling Water System | CPP FIN FAN COOLER | CPP FIN FAN COOLER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | closed¦cooling¦water |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9166 | 0.9750 | 0.9750 | g_safe | [5 empty] | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | civil_design | civil_design | match | ccw¦condensate | ccw | ccw¦condensate | query | ccw¦gtg | match | true | false | 3 | 4 | 49.6735 | 0.6415 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | ccw¦condensate | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULC-171301 | CALCULATION OF AIR COOLED CONDENSER FOUNDATION | Calculation sheet | Air Cooled Condenser |  |  |  | Calculation sheet for ACC |  | ACC - Noise Calculation | 1 | start+249D<=FA<=start+249D+2M | FA ∈ [start+249d, start+309d] | rule_query | calculation | calculation | calculation | calculation | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.6667 | 0.6647 | 0.6661 | 0.6661 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 19.0699 | 0.6537 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc | civil_design | 6 | 2025-11-06 | 2025-12-06 | 2026-01-05 | 2026-01-20 | 2026-02-04 | 2026-02-19 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-171302 | AIR COOLED CONDENSER FOUNDATION LAYOUT | Layout Drawing | Air Cooled Condenser |  |  |  | Layout Drawing for ACC |  | ACC - Earthing Layout DraWing | 1 | start+229D<=FA<=start+229D+2M | FA ∈ [start+229d, start+289d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 0.7500 | 0.6746 | 0.7274 | 0.7274 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc¦electrical | acc | query | acc¦condensate | match | true | false | 1 | 3 | 19.0699 | 0.6536 | 0.0323 | 0.0323 | hybrid | structured_preferred | acc | civil_design | 6 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-171303 | AIR COOLED CONDENSER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Air Cooled Condenser |  |  |  | PLAN AND SECTION for ACC | CONDENSER | AIR COOLED CONDENSER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9706 | 0.9912 | 0.9912 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc | acc | query | acc¦condensate | match | true | false | 3 | 5 | 19.0699 | 0.6601 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | acc | civil_design |  | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-171308 | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | Detail Drawing | Air Cooled Condenser |  |  |  | Detail Drawing for ACC | CONDENSER | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | acc¦air¦condenser¦cooled | acc | scoped | match | match | match | passed |  | 1.0000 | 0.9794 | 0.9938 | 0.9938 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | acc | acc | acc | query | acc¦condensate | match | true | false | 2 | 6 | 19.0699 | 0.6427 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | acc | civil_design |  | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-171309 | AIR COOLED CONDENSER DRAIN WATER PUMP PIT DETAIL | Detail Drawing | Air Cooled Condenser |  |  |  | Detail Drawing for ACC | CONDENSER | AIR COOLED CONDENSER DRAIN WATER PUMP PIT DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | acc¦air¦condenser¦cooled¦pump | acc¦pump | scoped | match | match | match | passed |  | 1.0000 | 0.9753 | 0.9926 | 0.9926 | [6 empty] | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | design_drawing | civil_design | compatible | acc | acc | acc | query | acc¦condensate | match | true | false | 1 | 3 | 16.9918 | 0.6081 | 0.0323 | 0.0242 | hybrid | structured_preferred | acc | system_design¦civil_design | 6 | 2024-10-18 | 2024-11-02 | 2024-11-17 | 2024-12-02 | 2025-01-01 | 2025-01-31 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UNX-171401 | CALCULATION OF PIPE SLEEPER FOUNDATION | Calculation sheet |  |  |  |  | Calculation sheet |  | CALCULATION OF PIPE SLEEPER FOUNDATION | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 1 | 1 | 14.0934 | 0.5014 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | civil_design |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171402 | PIPE SLEEPER FOUNDATION OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | PIPE SLEEPER FOUNDATION OVERALL LAYOUT | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9990 | 0.9997 | 0.9997 | [6 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 11 | 1 | 10.2065 | 0.5723 | 0.0305 | 0.0229 | hybrid | structured_no_system |  | civil_design |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171403 | PIPE SLEEPER FOUNDATION LAYOUT | Layout Drawing |  |  |  |  | Layout Drawing |  | PIPE SLEEPER FOUNDATION LAYOUT | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 8 | 1 | 10.2065 | 0.6048 | 0.0311 | 0.0233 | hybrid | structured_no_system |  | civil_design |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171410 | PIPE SLEEPER FOUNDATION PLAN AND SECTION | PLAN AND SECTION |  |  |  |  | PLAN AND SECTION |  | PIPE SLEEPER FOUNDATION PLAN AND SECTION | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | sectional_drawing | sectional_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 7 | 1 | 10.2065 | 0.5531 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UEG-171501 | FGS AREA FOUNDATION CALCULATION | Calculation sheet |  | Fuel Gas System |  |  | Calculation sheet for Fuel Gas System | Fuel Gas System | Calculation Sheets | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | calculation | calculation | calculation | calculation | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.8000 | 0.9557 | 0.8467 | 0.8467 | [6 empty] | FA | 0CF3520W16A03.1 | (FGS LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-09-14 | 2007-11-10 | civil_design | civil_design | match | fgp | fgp | fgp | query | fgp | match | false | false | 2 | 44 | 13.2051 | 0.5859 | 0.0257 | 0.0257 | hybrid | structured_cell_found_text_preferred | fgp | civil_design |  | 2025-02-01 | 2025-03-01 | 2025-03-29 | 2025-03-22 | 2025-04-19 | 2025-05-17 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEG-171502 | FGS AREA LAYOUT | Layout Drawing |  | Fuel Gas System |  |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FGS AREA LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.7646 | 0.6960 | 0.6960 | [6 empty] | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | design_drawing | civil_design | compatible | fgp | fgp | fgp | query | fgp | match | false | false | 5 | 3 | 11.2773 | 0.6757 | 0.0313 | 0.0234 | hybrid | structured_cell_found_text_preferred | fgp | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEG-171504 | FGS AREA PLAN AND SECTION | PLAN AND SECTION |  | Fuel Gas System |  |  | PLAN AND SECTION for Fuel Gas System | Fuel Gas System | FGS AREA PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.7500 | 0.8781 | 0.7884 | 0.7884 | [6 empty] | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 |  | civil_design | query_unknown | fgp | fgp | fgp | query | fgp | match | false | false | 6 | 5 | 11.2773 | 0.6535 | 0.0305 | 0.0229 | hybrid | structured_no_phase | fgp |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_phase_status=query_unknown;activity_equipment_unconfirmed;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171601 | CALCULATION OF GT PERFORMANCE HEATER FOUNDATION | Calculation sheet | Gas Turbine PERFORMANCE HEATER |  |  |  | Calculation sheet for Gas Turbine PERFORMANCE HEATER |  | CALCULATION OF GT PERFORMANCE HEATER FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.6945 | 0.6750 | 0.6750 | [6 empty] | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 3 | 1 | 8.2608 | 0.5605 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171602 | GT PERFORMANCE HEATER FOUNDATION LAYOUT | Layout Drawing | Gas Turbine PERFORMANCE HEATER |  |  |  | Layout Drawing for Gas Turbine PERFORMANCE HEATER |  | GT PERFORMANCE HEATER FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.6589 | 0.7577 | 0.7577 | [6 empty] | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 1 | 3 | 8.2608 | 0.5925 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171603 | GT PERFORMANCE HEATER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Gas Turbine PERFORMANCE HEATER |  |  |  | PLAN AND SECTION for Gas Turbine PERFORMANCE HEATER |  | GT PERFORMANCE HEATER FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8571 | 0.7207 | 0.8162 | 0.8162 | [6 empty] | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 1 | 2 | 8.2608 | 0.5916 | 0.0325 | 0.0325 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULX-171604 | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | Detail Drawing | Gas Turbine PERFORMANCE HEATER |  |  |  | Detail Drawing for Gas Turbine PERFORMANCE HEATER |  | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦gtg¦heater¦performance¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.8000 | 0.5932 | 0.7380 | 0.7380 | [6 empty] | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | civil_design | civil_design | match | gtg | gtg | gtg | query | gtg | match | true | false | 3 | 1 | 8.2608 | 0.5686 | 0.0323 | 0.0323 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UEM-171701 | CALCULATION OF WASTE WATER TREATMENT PLANT | Calculation sheet | Water Treatment Plant | Water Treatment System |  |  | Calculation sheet for Water Treatment Plant | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | plant¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.9247 | 0.8607 | 0.8607 | [6 empty] | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 8 | 1 | 38.3825 | 0.6311 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEM-171702 | WASTE WATER TREATMENT PLANT PLAN AND SECTION | PLAN AND SECTION | Water Treatment Plant | Water Treatment System |  |  | PLAN AND SECTION for Water Treatment System | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7500 | 0.7583 | 0.7525 | 0.7525 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 |  | system_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 4 | 11 | 42.9657 | 0.6412 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEM-171708 | WASTE WATER TREATMENT PLANT EMBEDMENT DETAIL | Detail Drawing | Water Treatment Plant | Water Treatment System |  |  | Detail Drawing for Water Treatment System | Water Treatment System | Equipment Assembly and Detail DraWing for Water Treatment System | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.8363 | 0.7176 | 0.7176 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 5 | 5 | 40.3545 | 0.6387 | 0.0308 | 0.0231 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-06-01 | 2024-07-01 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UEM-171711 | WASTE WATER TREATMENT R.C DETAIL | Detail Drawing |  | Water Treatment System |  |  | Detail Drawing for Water Treatment System | Water Treatment System | Equipment Assembly and Detail DraWing for Water Treatment System | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.8363 | 0.7176 | 0.7176 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | wts | wts | query | wts | match | true | false | 4 | 5 | 30.5461 | 0.6182 | 0.0310 | 0.0233 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-06-01 | 2024-07-01 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-14 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171801 | CALCULATION OF HRSG FOUNDATION PILING | Calculation sheet | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7948 | 0.7051 | 0.7051 | [6 empty] | FA | 0CF1600W14A11 | HRSG Block #1 Area Piling Work | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-07-02 | 2007-09-17 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 1 | 3 | 18.4853 | 0.6500 | 0.0323 | 0.0323 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-12-13 | 2025-01-12 | 2025-02-11 | 2025-02-26 | 2025-03-13 | 2025-03-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171802 | CALCULATION OF HRSG FOUNDATION | Calculation sheet | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7948 | 0.7051 | 0.7051 | [6 empty] | FA | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-09-03 | 2008-01-14 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 11 | 14.6733 | 0.6156 | 0.0286 | 0.0286 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-02-14 | 2025-03-16 | 2025-04-15 | 2025-04-30 | 2025-05-15 | 2025-05-30 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171803 | HRSG FOUNDATION ARRANGEMENT | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦heat¦hrsg¦recovery¦steam |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.5405 | 0.3955 | 0.3362 | g_safe | [5 empty] | FA | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-06-20 |  | civil_design | civil_design | match | hrsg |  | hrsg | query | hrsg | match | true | false | 3 | 37 | 19.7008 | 0.6179 | 0.0262 | 0.0262 | hybrid | structured_preferred | hrsg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171804 | HRSG FOUNDATION PILE ARRANGEMENT PLAN | ARRANGEMENT PLAN | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT PLAN for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7211 | 0.6830 | 0.6830 | [6 empty] | FA | 0EF1600W14A10 | HRSG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-06-15 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 7 | 1 | 19.4631 | 0.7267 | 0.0313 | 0.0313 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171805 | HRSG FOUNDATION LAYOUT | Layout Drawing | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | HRSG - Piping Layout DraWing for SCR | 1 | start+255D<=FA<=start+255D+2M | FA ∈ [start+255d, start+315d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7732 | 0.6986 | 0.6986 | [6 empty] | FA | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 22 | 2 | 14.4007 | 0.6487 | 0.0283 | 0.0283 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171806 | HRSG FOUNDATION PLAN SECTION & DETAIL | PLAN SECTION & DETAIL | Heat Recovery Steam Generator |  |  |  | PLAN SECTION & DETAIL for HRSG |  | HRSG FOUNDATION PLAN SECTION & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.8000 | 0.8222 | 0.8066 | 0.8066 | [6 empty] | FA | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-09-03 | 2008-01-14 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 12 | 14 | 14.6733 | 0.6531 | 0.0274 | 0.0274 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171807 | HRSG FOUNDATION REBAR DETAIL | REBAR DETAIL | Heat Recovery Steam Generator |  |  |  | REBAR DETAIL for HRSG |  | HRSG FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.7500 | 0.8521 | 0.7806 | 0.7806 | [6 empty] | FA | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-09-03 | 2008-01-14 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 10 | 7 | 14.6733 | 0.6429 | 0.0292 | 0.0292 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171815 | HRSG MISC. FOUNDATION PLAN | Plan | Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | HRSG - ConDuit Plan | 1 | start+194D<=FA<=start+194D+2M | FA ∈ [start+194d, start+254d] | rule_query | plan | plan | plan | plan | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7622 | 0.6953 | 0.6953 | [6 empty] | FA | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 22 | 1 | 14.4007 | 0.6566 | 0.0286 | 0.0286 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-03-20 | 2025-04-19 | 2025-05-19 | 2025-06-03 | 2025-06-18 | 2025-07-03 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171816 | HRSG MISC. FOUNDATION DETAILS | DETAILS | Heat Recovery Steam Generator |  |  |  | DETAILS for HRSG |  | HRSG MISC. FOUNDATION DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.5000 | 0.6971 | 0.5591 | 0.5591 | [6 empty] | FA | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-09-03 | 2008-01-14 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 9 | 7 | 14.6733 | 0.6628 | 0.0294 | 0.0294 | hybrid | structured_cell_found_text_preferred | hrsg | civil_design |  | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171819 | CALCULATION OF HRSG MISC. FOUNDATION | Calculation sheet | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7948 | 0.7051 | 0.7051 | [6 empty] | FA | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-09-07 | 2008-01-16 | civil_design | civil_design | match | hrsg | hrsg | hrsg | query | hrsg | match | true | false | 22 | 2 | 14.4007 | 0.6287 | 0.0283 | 0.0283 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P8UTH-172001 | CALCULATION OF RESERVE BOILER FOUNDATION | Calculation sheet | Reserve Boiler |  |  |  | Calculation sheet for Reserve Boiler |  | CALCULATION OF IPB FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6845 | 0.7303 | 0.7303 | g_safe | [5 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match | reserve_boiler | electrical | reserve_boiler | query | bop | mismatch | false | false | 2 | 122 | 6.0495 | 0.4399 | 0.0216 | 0.0054 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172003 | RESERVE BOILER FOUNDATION LAYOUT | Layout Drawing | Reserve Boiler |  |  |  | Layout Drawing for Reserve Boiler |  | PIPE SLEEPER FOUNDATION LAYOUT | 1 | start+12M<= FC<=start+12M+2M | FC ∈ [start+360d, start+420d] | title | drawing | drawing | layout_drawing | layout_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6655 | 0.5496 | 0.5496 | g_safe | [5 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 2 | 412 | 24.0608 | 0.4402 | 0.0182 | 0.0109 | hybrid | structured_system_absent | reserve_boiler | civil_design |  | 2025-01-10 | 2025-01-25 | 2025-02-09 | 2025-02-24 | 2025-03-26 | 2025-04-25 | generated | 0.90 |  | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172004 | RESERVE BOILER FOUNDATION SECTION & DETAIL | SECTION & DETAIL | Reserve Boiler |  |  |  | SECTION & DETAIL for Reserve Boiler |  | Foundation detail draWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5970 | 0.6458 | 0.6458 | g_safe | [5 empty] | FA | 3EF1625W16A03.2 | (HRSG #32 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | 2007-11-08 | 2008-03-18 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | hrsg | mismatch | false | false | 875 | 63 | 1.9705 | 0.5338 | 0.0092 | 0.0023 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P8UTH-172005 | RESERVE BOILER FOUNDATION REBAR DETAIL | REBAR DETAIL | Reserve Boiler |  |  |  | REBAR DETAIL for Reserve Boiler |  | Foundation Rebar Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7481 | 0.9244 | 0.7858 | g_safe | [5 empty] | FA | 0EF5550W16A03 | (Pipe Rack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | 2007-10-26 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 13 | 160 | 2.3746 | 0.4484 | 0.0182 | 0.0109 | hybrid | structured_system_absent | reserve_boiler | civil_design |  | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-30 | 2024-05-30 | generated | 0.60 | fa_earliest | false | false | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172007 | RESERVE BOILER GRADE SLAB PLAN & SECTION | PLAN & SECTION | Reserve Boiler |  |  |  | PLAN & SECTION for Reserve Boiler |  | Plan & Section | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | boiler¦reserve¦reserve_boiler |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.6578 | 0.6640 | 0.5644 | g_safe | [5 empty] | FA | 0CF3025W16A15 | (Intake Pump Station) Structure Work(Wall & Top Slab) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2008-03-07 | 2008-07-12 |  |  | query_unknown | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 7 | 154 | 10.1992 | 0.4638 | 0.0196 | 0.0088 | hybrid | structured_no_phase | reserve_boiler |  |  | 2024-10-24 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2025-01-07 | 2025-02-06 | generated | 0.60 |  | false | false | 0.33 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P8UTH-172008 | RESERVE BOILER GRADE SLAB REBAR DETAIL | REBAR DETAIL | Reserve Boiler |  |  |  | REBAR DETAIL for Reserve Boiler |  | Rebar Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7289 | 0.6853 | 0.5825 | g_safe | [5 empty] | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 |  | installation | query_unknown | reserve_boiler |  | reserve_boiler | query |  | activity_unscoped | true | true | 1 | 807 | 25.7245 | 0.3786 | 0.0175 | 0.0079 | hybrid | structured_no_phase | reserve_boiler |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.60 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.33 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P8UTH-172011 | CALCULATION OF FD FAN AND MISC. FOUNDATION | Calculation sheet |  |  |  |  | Calculation sheet |  | CALCULATION OF HRSG MISC. FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.7454 | 0.7836 | 0.7836 | [6 empty] | FA | 1CF1615W16A03 | (HRSG #11 Duct) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-12-14 | 2008-03-15 | civil_design | civil_design | match |  | hrsg | hrsg | rule | hrsg | match | false | false | 8 | 5 | 2.0621 | 0.4790 | 0.0301 | 0.0301 | hybrid | structured_preferred | hrsg | civil_design | 10 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-15 | 2024-10-15 | 2024-11-14 | generated | 0.90 |  | false | false | 0.32 | needs_review_activity | rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172012 | RESERVE BOILER FD FAN FOUNDATION | FOUNDATION | Reserve Boiler |  |  |  | FOUNDATION for Reserve Boiler |  | Foundation | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | foundation | foundation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4707 | 0.3745 | 0.3184 | g_safe | [5 empty] | FA | 3EF3015W16A03 | (FWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | 2007-10-31 | 2008-01-30 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | feedwater | mismatch | false | false | 129 | 1 | 4.2902 | 0.6087 | 0.0217 | 0.0054 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172013 | RESERVE BOILER MISC. FOUNDATION | FOUNDATION | Reserve Boiler |  |  |  | FOUNDATION for Reserve Boiler |  | Foundation | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | foundation | foundation | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4707 | 0.3745 | 0.3184 | g_safe | [5 empty] | FA | 1CF3520W16A01 | (FGSS #11) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 | civil_design | civil_design | match | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | true | false | 2 | 34 | 13.1819 | 0.5285 | 0.0268 | 0.0067 | hybrid | structured_system_absent | reserve_boiler | civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172100 | TRANSFORMER FOUNDATION ARRANGEMENT PLAN | ARRANGEMENT PLAN | TRANSFORMER |  |  |  | ARRANGEMENT PLAN for TRANSFORMER |  | TRANSFORMER FOUNDATION ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | transformer |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8398 | 0.7769 | 0.7769 | g_safe | [5 empty] | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 9 | 2 | 13.8900 | 0.6372 | 0.0306 | 0.0306 | hybrid | structured_cell_found_text_preferred | gsut_uat | civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAG-172101 | CALCULATION OF STG STEP - UP AND EXCITATION TRANSFORMER FOUNDATION | Calculation sheet | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | stg | stg | stg | query | electrical¦gsut_uat¦stg | match | true | false | 13 | 2 | 14.5870 | 0.6912 | 0.0298 | 0.0298 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-11-08 | 2024-12-08 | 2025-01-07 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172102 | STG STEP UP AND EXCITATION TRANSFORMER PLAN & SECTION | PLAN & SECTION | Steam Turbine & Generator |  |  |  | PLAN & SECTION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.7143 | 0.8341 | 0.7502 | 0.7502 | [6 empty] | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  | civil_design | query_unknown | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 1 | 15 | 31.4079 | 0.6223 | 0.0297 | 0.0223 | hybrid | structured_no_phase | stg |  |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172108 | STG STEP UP AND EXCITATION TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | ARRANGEMENT PLAN & SECTION | Steam Turbine & Generator |  |  |  | ARRANGEMENT PLAN & SECTION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.7143 | 0.7711 | 0.7313 | 0.7313 | [6 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 1 | 1 | 36.8107 | 0.6655 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAG-172109 | STG STEP UP AND EXCITATION TRANSFORMER RE-BAR DETAIL | RE-BAR DETAIL | Steam Turbine & Generator |  |  |  | RE-BAR DETAIL for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7561 | 0.7868 | 0.7868 | [6 empty] | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  | civil_design | query_unknown | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 1 | 8 | 31.4079 | 0.6392 | 0.0311 | 0.0233 | hybrid | structured_no_phase | stg |  |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAG-172151 | CALCULATION OF GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION | Calculation sheet | Gas Turbine Generator |  |  |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 5 | 14.9697 | 0.6850 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172162 | GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION PLAN & SECTION | PLAN & SECTION | Gas Turbine Generator |  |  |  | PLAN & SECTION for GTG |  | GTG #1,2 LEB - STAIR PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6000 | 0.7576 | 0.6473 | 0.6473 | [6 empty] | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 5 | 14.9697 | 0.6972 | 0.0318 | 0.0318 | hybrid | structured_preferred | gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172168 | GTG STEP UP & UNIT AUX. TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | ARRANGEMENT PLAN & SECTION | Gas Turbine Generator |  |  |  | ARRANGEMENT PLAN & SECTION for GTG |  | GTG STEP UP & UNIT AUX. TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine | gtg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 1EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 |  | civil_design | civil_design | match | gtg | gsut_uat¦gtg | gtg | query | gtg | match | true | false | 16 | 1 | 12.7873 | 0.6655 | 0.0296 | 0.0296 | hybrid | structured_preferred | gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAG-172170 | GTG STEP UP & UNIT AUX. TRANSFORMER RE-BAR DETAIL | RE-BAR DETAIL | Gas Turbine Generator |  |  |  | RE-BAR DETAIL for GTG |  | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.7849 | 0.7021 | 0.7021 | [6 empty] | FI | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-01 |  | civil_design | query_unknown | gtg | gtg | gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 42 | 3 | 12.7996 | 0.6620 | 0.0257 | 0.0193 | hybrid | structured_no_phase | gtg | [5 empty] | 2024-04-03 | 2024-05-03 | 2024-06-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UBN-172201 | CALCULATION OF BSDG FOUNDATION | Calculation sheet | Blackstart Diesel Generator |  |  |  | Calculation sheet for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | HVAC Calculation | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | calculation | calculation | calculation | calculation | blackstart¦diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7813 | 0.7011 | 0.7011 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg¦hvac | bsedg | query | bsedg | match | true | false | 2 | 2 | 24.9154 | 0.6706 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | bsedg | civil_design |  | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UBN-172202 | BSDG FOUNDATION PLAN & SECTION | PLAN & SECTION | Blackstart Diesel Generator |  |  |  | PLAN & SECTION for Blackstart Diesel Generator |  | BSDG FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | blackstart¦diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg | bsedg | query | bsedg | match | true | false | 1 | 3 | 24.9154 | 0.6892 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | bsedg | civil_design |  | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UBN-172203 | BSDG FOUNDATION R.C DETAIL | R.C DETAIL | Blackstart Diesel Generator |  |  |  | R.C DETAIL for Blackstart Diesel Generator |  | BSDG FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | blackstart¦diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | civil_design | civil_design | match | bsedg | bsedg | bsedg | query | bsedg | match | true | false | 6 | 1 | 24.9154 | 0.6931 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | bsedg | civil_design |  | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0BAA-172401 | CALCULATION OF IPB FOUNDATION | Calculation sheet | Isolated Phase Busduct | Electrical System |  |  | Calculation sheet for Isolated Phase Busduct |  | CALCULATION OF IPB FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | busduct¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 7 | 1 | 5.1123 | 0.5112 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0BAA-172402 | IPB FOUNDATION PLAN & SECTION | PLAN & SECTION | Isolated Phase Busduct | Electrical System |  |  | PLAN & SECTION for Electrical System |  | IPB FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0CF5544W16A10 | (GIS BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-06-30 | 2007-08-27 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 6 | 1 | 5.2477 | 0.5317 | 0.0315 | 0.0315 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-02 | 2024-03-17 | 2024-04-01 | 2024-05-01 | 2024-05-31 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0BAA-172403 | IPB FOUNDATION R.C DETAIL | R.C DETAIL | Isolated Phase Busduct | Electrical System |  |  | R.C DETAIL for Electrical System |  | IPB FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0CF5544W16A10 | (GIS BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-06-30 | 2007-08-27 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 10 | 6 | 5.2477 | 0.5075 | 0.0294 | 0.0294 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-02 | 2024-03-17 | 2024-04-01 | 2024-05-01 | 2024-05-31 | generated | 0.90 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULC-172501 | CALCULATION OF CONDENSATE WATER TANK FOUNDATION | Calculation sheet | Tank | Condensate System |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | [6 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate |  | condensate | query | condensate¦fgp | match | true | false | 2 | 5 | 25.5756 | 0.6125 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | condensate | civil_design |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-172502 | CONDENSATE WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank | Condensate System |  |  | PLAN & SECTION for Tank | Condensate | CONDENSATE WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.9338 | 0.9801 | 0.9801 | [6 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate | condensate | condensate | query | condensate¦fgp | match | true | false | 1 | 4 | 25.5756 | 0.6705 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-172503 | CONDENSATE WATER TANK FOUNDATION REBAR DETAIL | Detail Drawing | Tank | Condensate System |  |  | Detail Drawing for Tank | Condensate | CONDENSATE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.9297 | 0.9789 | 0.9789 | [6 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate | condensate | condensate | query | condensate¦fgp | match | true | false | 2 | 7 | 25.5756 | 0.6197 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | condensate | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGF-172521 | CALCULATION OF POTABLE & FIRE FIGHTING WATER TANK FOUNDATION | Calculation sheet | Tank | Fire Fighting System |  |  | Calculation sheet for Tank | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.7129 | 0.5639 | 0.5639 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 3 | 1 | 31.1518 | 0.6032 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-06-30 | 2024-07-30 | 2024-08-29 | 2024-09-13 | 2024-09-28 | 2024-10-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-172522 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank | Fire Fighting System |  |  | PLAN & SECTION for Tank |  | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | fire_protection¦tank | fire_protection¦tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 31.1518 | 0.6545 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGF-172523 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION REBAR DETAIL | Detail Drawing | Tank | Fire Fighting System |  |  | Detail Drawing for Tank |  | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | fire_protection¦tank | fire_protection¦tank | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 31.1518 | 0.6086 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGD-172541 | CALCULATION OF DEMINERALIZED WATER TANK FOUNDATION | Calculation sheet | Tank | Water Treatment System |  |  | Calculation sheet for Tank | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7363 | 0.5709 | 0.5709 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 34.2563 | 0.6537 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGD-172542 | DEMINERALIZED WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank | Water Treatment System |  |  | PLAN & SECTION for Tank |  | DEMINERALIZED WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | tank¦wts | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 34.2563 | 0.6801 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGD-172543 | DEMINERALIZED WATER TANK FOUNDATION REBAR DETAIL | Detail Drawing | Tank | Water Treatment System |  |  | Detail Drawing for Tank |  | DEMINERALIZED WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank¦wts | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 34.2563 | 0.6442 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGG-172561 | CALCULATION OF POTABLE WATER TANK FOUNDATION | Calculation sheet | Tank | Water Treatment System |  |  | Calculation sheet for Tank | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7363 | 0.5709 | 0.5709 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 3 | 26.7634 | 0.5977 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGG-172562 | POTABLE WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank | Water Treatment System |  |  | PLAN & SECTION for Tank |  | POTABLE WATER TANK FOUNDATION PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | tank¦wts | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 5 | 26.7634 | 0.6132 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGG-172563 | POTABLE WATER TANK FOUNDATION REBAR DETAIL | Detail Drawing | Tank | Water Treatment System |  |  | Detail Drawing for Tank |  | POTABLE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank¦wts | tank | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 8 | 26.7634 | 0.5652 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-172581 | CALCULATION OF GENERAL SERVICE PUMP FOUNDATION | Calculation sheet | Pump |  |  |  | Calculation sheet for Pump |  | Transfer Pump Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pump | pump | scoped | match | match | match | passed |  | 0.5000 | 0.6749 | 0.5525 | 0.5525 | [6 empty] | FA | 0CF3520W16A04 | (Transfer Pump) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > DFO Tank & Pump | 2007-10-31 | 2007-12-27 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | true | false | 14 | 34 | 11.9153 | 0.4976 | 0.0242 | 0.0181 | hybrid | structured_no_system |  | civil_design |  | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.90 |  | false | false | 0.80 | usable | activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172582 | GENERAL SERVICE PUMP FOUNDATIONS LAYOUT | Layout Drawing | Pump |  |  |  | Layout Drawing for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | pump | pump | scoped | match | match | match | passed |  | 1.0000 | 0.9217 | 0.9765 | 0.9765 | [6 empty] | FA | 0CF3520W16A04 | (Transfer Pump) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > DFO Tank & Pump | 2007-10-31 | 2007-12-27 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | true | false | 17 | 18 | 9.8371 | 0.5141 | 0.0258 | 0.0194 | hybrid | structured_no_system |  | civil_design |  | 2024-06-18 | 2024-07-03 | 2024-07-18 | 2024-08-02 | 2024-09-01 | 2024-10-01 | generated | 0.90 |  | false | false | 0.80 | usable | activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172583 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (1) | DETAILS (1) | Pump |  |  |  | DETAILS (1) for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (1) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.4000 | 0.6852 | 0.4855 | 0.4855 | [6 empty] | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | false | 8 | 34 | 12.2510 | 0.5110 | 0.0253 | 0.0190 | hybrid | structured_no_system |  | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172584 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (2) | DETAILS (2) | Pump |  |  |  | DETAILS (2) for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (2) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.4000 | 0.6882 | 0.4865 | 0.4865 | [6 empty] | FA | 2EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | 2007-09-03 | 2008-01-30 | civil_design | civil_design | match |  |  |  |  | ccw | query_unscoped | false | false | 51 | 1 | 10.2923 | 0.5892 | 0.0254 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-04-21 | 2024-05-06 | 2024-05-21 | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172585 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (3) | DETAILS (3) | Pump |  |  |  | DETAILS (3) for Pump | General Service Pump | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (3) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.4000 | 0.7016 | 0.4905 | 0.4905 | [6 empty] | FA | 3EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | false | 5 | 35 | 13.7151 | 0.4934 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | civil_design |  | 2024-05-27 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.90 |  | false | false | 0.68 | usable | rule_score_medium;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAZ-172601 | CALCULATION OF EHV CABLE TRENCH & DIRECT BURIED CABLE | Calculation sheet | Cable |  |  |  | Calculation sheet for Cable |  | CALCULATION OF EHV CABLE TRENCH & DIRECT BURIED CABLE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 21 | 4 | 25.3530 | 0.6135 | 0.0280 | 0.0210 | hybrid | structured_no_system |  | civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172602 | EHV CABLE TRENCH & DIRECT BURIED CABLE OVERALL LAYOUT | OVERALL LAYOUT | Cable |  |  |  | OVERALL LAYOUT for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 21 | 4 | 25.3530 | 0.6553 | 0.0280 | 0.0157 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172603 | EHV CABLE TRENCH & DIRECT BURIED CABLE LAYOUT | Layout Drawing | Cable |  |  |  | Layout Drawing for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 22 | 4 | 25.3530 | 0.6422 | 0.0278 | 0.0156 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172608 | EHV CABLE TRENCH & DIRECT BURIED CABLE PLAN & SECTION | PLAN & SECTION | Cable |  |  |  | PLAN & SECTION for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 2CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-05-17 | 2008-08-01 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 13 | 32.9909 | 0.5641 | 0.0298 | 0.0168 | hybrid | structured_no_system |  |  |  | 2025-01-03 | 2025-01-18 | 2025-02-02 | 2025-02-17 | 2025-03-19 | 2025-04-18 | generated | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAZ-172613 | EHV CABLE TRENCH & DIRECT BURIED CABLE DETAIL | Detail Drawing | Cable |  |  |  | Detail Drawing for Cable |  | EHV CABLE TRENCH & DIRECT BURIED CABLE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | cable |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 1CF6040W16A03 | (Cable tunnel) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | electrical | query_unscoped | true | false | 22 | 4 | 25.3530 | 0.6390 | 0.0278 | 0.0156 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZT-172701 | CALCULATION OF ELECTRICAL DUCT BANK MANHOLE | Calculation sheet |  | Electrical System |  |  | Calculation sheet for Electrical System |  | CALCULATION OF ELECTRICAL DUCT BANK MANHOLE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9988 | 0.9996 | 0.9996 | g_safe | [5 empty] | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | true | false | 18 | 3 | 5.5432 | 0.5227 | 0.0287 | 0.0287 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172702 | ELECTRICAL DUCT BANK OVERALL LAYOUT | OVERALL LAYOUT |  | Electrical System |  |  | OVERALL LAYOUT for Electrical System |  | ELECTRICAL DUCT BANK OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 18 | 4 | 5.5432 | 0.5431 | 0.0284 | 0.0213 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172703 | ELECTRICAL DUCT BANK LAYOUT | Layout Drawing |  | Electrical System |  |  | Layout Drawing for Electrical System |  | ELECTRICAL DUCT BANK LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9997 | 0.9999 | 0.9999 | g_safe | [5 empty] | FA | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | design_drawing | civil_design | compatible | electrical | electrical | electrical | query | electrical | match | true | false | 18 | 9 | 5.5432 | 0.4990 | 0.0273 | 0.0205 | hybrid | structured_preferred | electrical | system_design¦civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-172704 | ELECTRICAL DUCT BANK TYPICAL SECTION & R.C DETAILS | SECTION |  | Electrical System |  |  | SECTION for Electrical System |  | ELECTRICAL DUCT BANK TYPICAL SECTION & R.C DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0CF6500W70A04.6 | (Electrical Protection Panel) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-04-25 | 2008-05-26 |  | installation | query_unknown | electrical | electrical | electrical | query | electrical | match | true | false | 38 | 15 | 7.8592 | 0.4891 | 0.0235 | 0.0177 | hybrid | structured_no_phase | electrical |  |  | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-25 | 2025-03-27 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-172713 | ELECTRICAL DUCT BANK MANHOLE SCHEDULE | Schedule |  | Electrical System |  |  | Schedule for Electrical System |  | ELECTRICAL DUCT BANK MANHOLE SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0CF6500W70A04.6 | (Electrical Protection Panel) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-04-25 | 2008-05-26 |  | installation | query_unknown | electrical | electrical | electrical | query | electrical | match | true | false | 3 | 113 | 7.8596 | 0.4512 | 0.0217 | 0.0162 | hybrid | structured_no_phase | electrical |  |  | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-25 | 2025-03-27 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172716 | ELECTRICAL DUCT BANK MANHOLE PLAN, SECTION & R.C DETAILS | Plan |  | Electrical System |  |  | Plan for Electrical System |  | ELECTRICAL DUCT BANK MANHOLE PLAN, SECTION & R.C DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0CF6500W70A04.6 | (Electrical Protection Panel) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-04-25 | 2008-05-26 |  | installation | query_unknown | electrical | electrical | electrical | query | electrical | match | true | false | 40 | 5 | 7.8592 | 0.5174 | 0.0254 | 0.0190 | hybrid | structured_no_phase | electrical |  |  | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | 2025-02-25 | 2025-03-27 | generated | 0.90 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GUC-172801 | CALCULATION OF STORMWATER POND | Calculation sheet |  |  |  |  | Calculation sheet |  | CALCULATION OF STORMWATER POND | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | calculation | calculation | calculation | calculation | drainage | drainage | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF5535W00A15.1 | (WWT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 363 | 1 |  | 0.4244 | 0.0188 | 0.0141 | hybrid | structured_no_system |  | civil_design |  | 2025-02-15 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-05-01 | 2025-05-31 | generated | 0.90 |  | false | false | 0.68 | usable | activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUC-172802 | CLEAN STORM WATER PONDS OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | CLEAN STORM WATER PONDS OVERALL LAYOUT | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | layout_drawing | layout_drawing | drainage | drainage | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 1 | 24.0608 | 0.5140 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-27 | 2024-11-26 | generated | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUC-172803 | CLEAN STORM WATER PONDS PLAN AND SECTION | PLAN AND SECTION |  |  |  |  | PLAN AND SECTION |  | CLEAN STORM WATER PONDS PLAN AND SECTION | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | sectional_drawing | sectional_drawing | drainage | drainage | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 |  | system_design | query_unknown | [5 empty] | query_unscoped | true | true | 6 | 2 | 10.5466 | 0.5071 | 0.0313 | 0.0141 | hybrid | structured_no_system |  |  |  | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GUC-172804 | STORMWATER POND DETAIL | Detail Drawing |  |  |  |  | Detail Drawing |  | STORMWATER POND DETAIL | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | detail_drawing | detail_drawing | drainage | drainage | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 287 | 1 |  | 0.4881 | 0.0193 | 0.0108 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2025-04-16 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-30 | 2025-07-30 | generated | 0.90 |  | false | false | 0.51 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZA-172901 | CALCULATION OF ROAD AND PAVING | Calculation sheet |  |  |  |  | Calculation sheet |  | CALCULATION OF ROAD AND PAVING | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1 | 2 | 12.1336 | 0.4913 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 |  | false | false | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172902 | ROAD AND PAVING OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | ROAD AND PAVING OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 1 | 24.0608 | 0.6057 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172903 | ROAD AND PAVING LAYOUT | Layout Drawing |  |  |  |  | Layout Drawing |  | ROAD AND PAVING LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 1 | 24.0608 | 0.5456 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172904 | ROAD AND PAVING - GRAVEL PAVEMENT PLAN & SECTION | PLAN & SECTION |  |  |  |  | PLAN & SECTION |  | ROAD AND PAVING - GRAVEL PAVEMENT PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9998 | 0.9999 | 0.9999 | [6 empty] | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | true | 3 | 1 | 12.1336 | 0.5060 | 0.0323 | 0.0145 | hybrid | structured_no_system |  |  |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 |  | false | false | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZA-172908 | ROAD AND PAVING DETAIL | Detail Drawing |  |  |  |  | Detail Drawing |  | ROAD AND PAVING DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 1 | 12.1336 | 0.5360 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 |  | false | false | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172911 | ROAD MARKING AND SIGN BOARD LAYOUT | Layout Drawing |  |  |  |  | Layout Drawing |  | ROAD MARKING AND SIGN BOARD LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 1 | 24.0608 | 0.4722 | 0.0325 | 0.0146 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZA-172912 | ROAD MARKING AND SIGN BOARD DETAIL | Detail Drawing |  |  |  |  | Detail Drawing |  | ROAD MARKING AND SIGN BOARD DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 2 | 12.1336 | 0.4477 | 0.0323 | 0.0145 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-19 | 2024-07-04 | 2024-07-19 | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 |  | false | false | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZT-173001 | CALCULATION OF LIGHTING POLE FOUNDATION | Calculation sheet |  |  |  |  | Calculation sheet |  | CALCULATION OF LIGHTING POLE FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 5 | 4 | 6.0495 | 0.4546 | 0.0310 | 0.0233 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-173002 | LIGHTING POLE FOUNDATION OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | LIGHTING POLE FOUNDATION OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 24.0608 | 0.5321 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-173003 | LIGHTING POLE FOUNDATION LAYOUT | Layout Drawing |  |  |  |  | Layout Drawing |  | LIGHTING POLE FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 24.0608 | 0.4982 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-173008 | LIGHTING POLE FOUNDATION PLAN & DETAIL | PLAN & DETAIL |  | Lighting |  |  | PLAN & DETAIL for Lighting |  | LIGHTING POLE FOUNDATION PLAN & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | lighting |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0EF3040W16A01 | (Lab) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-06-30 | civil_design | civil_design | match |  |  |  |  | lab | query_unscoped | false | false | 10 | 74 | 2.4624 | 0.4066 | 0.0217 | 0.0163 | hybrid | structured_no_system |  | civil_design |  | 2024-11-17 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-31 | 2025-03-02 | generated | 0.90 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-173101 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS OVERALL LAYOUT | OVERALL LAYOUT |  | Fire Fighting |  |  | OVERALL LAYOUT for Fire Fighting | Fire Fighting System | STORMWATER DRAINAGE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fighting¦fire¦fire_protection | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5714 | 0.7568 | 0.6271 | 0.6271 | [6 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦wts | fire_fighting | fire_fighting¦wts | query | fire_fighting¦hvac | match | false | false | 6 | 3 | 19.5197 | 0.6467 | 0.0310 | 0.0310 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-173102 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS LAYOUT | Layout Drawing |  | Fire Fighting |  |  | Layout Drawing for Fire Fighting | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | fighting¦fire¦fire_protection | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6920 | 0.5576 | 0.5576 | [6 empty] | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | civil_design | civil_design | match | fire_fighting¦wts | fire_fighting | fire_fighting¦wts | query | fire_fighting¦hvac | match | false | false | 3 | 1 | 19.5197 | 0.6491 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | fire_fighting¦wts | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGF-173107 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS |  |  | Fire Fighting |  |  | for Fire Fighting |  | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | firefighting_and_potable_water_pipe_civil_works | firefighting_and_potable_water_pipe_civil_works | fighting¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | g_safe | [5 empty] | FA | 0CF4500W32A05 | (Fire WTR Pump Shelter) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-10-29 | 2008-02-27 |  |  | query_unknown | fire_fighting¦wts | wts | fire_fighting¦wts | query | fire_fighting¦hvac | match | false | false | 10 | 3 | 15.1882 | 0.6254 | 0.0302 | 0.0226 | hybrid | structured_no_phase | fire_fighting¦wts |  |  | 2024-06-16 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-30 | 2024-09-29 | generated | 0.90 |  | false | false | 0.24 | needs_review_activity | activity_phase_status=query_unknown;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZJ-173202 | FENCE AND GATE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FENCE AND GATE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0EF5570W16A10 | (Fence & Gate) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-12-12 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 7 | 2 | 20.4841 | 0.5854 | 0.0311 | 0.0140 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 |  | false | false | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173208 | FENCE AND GATE PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL |  | FENCE AND GATE PLAN AND DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | true | false | 3 | 14 | 25.6351 | 0.4341 | 0.0294 | 0.0165 | hybrid | structured_no_system |  |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.90 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173209 | INTERNAL FENCE AND GATE PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL |  | INTERNAL FENCE AND GATE PLAN AND DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | true | false | 3 | 12 | 25.6351 | 0.4394 | 0.0298 | 0.0167 | hybrid | structured_no_system |  |  |  | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.90 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GUB-173301 | CALCULATION OF STORMWATER DRAINAGE | Calculation sheet |  |  |  |  | Calculation sheet |  | CALCULATION OF STORMWATER POND | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | calculation | calculation | calculation | calculation | drainage | drainage | scoped | match | match | match | passed |  | 0.7500 | 0.8106 | 0.7682 | 0.7682 | [6 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 95 | 12 | 3.6223 | 0.4085 | 0.0203 | 0.0153 | hybrid | structured_no_system |  | civil_design |  | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-25 | 2024-12-25 | generated | 0.90 |  | false | false | 0.80 | usable | activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUB-173302 | STORMWATER DRAINAGE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT | Fire Fighting System | STORMWATER DRAINAGE OVERALL LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | drainage | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5714 | 0.8345 | 0.6503 | 0.6503 | [6 empty] | FA | 0EF3520W00A01.3 | (Foam Station BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Foam Station Building | 2007-05-01 |  | design_drawing | civil_design | compatible |  | fire_fighting | fire_fighting | rule | fgp¦fire_fighting | match | false | false | 1 | 1 |  | 0.4324 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed;activity_scope_source=rule;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUB-173303 | STORMWATER DRAINAGE LAYOUT | Layout Drawing |  |  |  |  | Layout Drawing | Fire Fighting System | STORMWATER DRAINAGE LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | layout_drawing | layout_drawing | drainage | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.8168 | 0.5951 | 0.5951 | [6 empty] | FA | 0EF3520W00A01.3 | (Foam Station BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Foam Station Building | 2007-05-01 |  | design_drawing | civil_design | compatible |  | fire_fighting | fire_fighting | rule | fgp¦fire_fighting | match | false | false | 1 | 1 |  | 0.4004 | 0.0328 | 0.0246 | hybrid | structured_preferred | fire_fighting | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review_activity | activity_phase_status=compatible;activity_equipment_unconfirmed;activity_scope_source=rule;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GUB-173313 | STORMWATER DRAINAGE STRUCTURAL DETAIL | Detail Drawing |  |  |  |  | Detail Drawing |  | STORMWATER POND DETAIL | 1 | start+7M<= FC<=start+7M+2M | FC ∈ [start+210d, start+270d] | title | drawing | drawing | detail_drawing | detail_drawing | drainage | drainage | scoped | match | match | match | passed |  | 0.6667 | 0.8110 | 0.7100 | 0.7100 | [6 empty] | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 287 | 4 |  | 0.5134 | 0.0185 | 0.0104 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2025-04-16 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-30 | 2025-07-30 | generated | 0.90 |  | false | false | 0.51 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GQB-173401 | CALCULATION OF WASTE WATER DRAINAGE OVERALL LAYOUT | CALCULATION OF OVERALL LAYOUT |  | Water Treatment System |  |  | CALCULATION OF OVERALL LAYOUT for Water Treatment System | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | drainage¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.6570 | 0.6638 | 0.6638 | [6 empty] | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | wts | electrical¦wts | wts | query | wts | match | true | false | 1 | 8 | 24.1800 | 0.5655 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173402 | WASTE WATER DRAINAGE OVERALL LAYOUT | OVERALL LAYOUT |  | Water Treatment System |  |  | OVERALL LAYOUT for Water Treatment System | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | drainage¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7215 | 0.6831 | 0.6831 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | electrical¦wts | wts | query | wts | match | true | false | 1 | 5 | 24.2691 | 0.6432 | 0.0318 | 0.0238 | hybrid | structured_preferred | wts | system_design¦civil_design | 10 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173403 | WASTE WATER DRAINAGE LAYOUT | Layout Drawing |  | Water Treatment System |  |  | Layout Drawing for Water Treatment System | Water Treatment System | Earthing Layout DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | drainage¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8333 | 0.7621 | 0.8120 | 0.8120 | [6 empty] | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | design_drawing | system_design | compatible | wts | electrical¦wts | wts | query | wts | match | true | false | 2 | 5 | 24.2691 | 0.6508 | 0.0315 | 0.0236 | hybrid | structured_cell_found_text_preferred | wts | system_design¦civil_design |  | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=compatible |  | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173413 | WASTE WATER DRAINAGE MANHOLE SCHEDULE | Schedule |  | Water Treatment System |  |  | Schedule for Water Treatment System | Water Treatment System | Cable Schdule(inculde drum schedule) | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | schedule | schedule | schedule | schedule | drainage¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7315 | 0.5695 | 0.5695 | [6 empty] | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 30.2890 | 0.6721 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GQB-173417 | WASTE WATER DRAINAGE STRUCTURE MANHOLE RE-BAR DETAIL | Detail Drawing |  | Water Treatment System |  |  | Detail Drawing for Water Treatment System | Water Treatment System | Equipment Assembly and Detail DraWing for Water Treatment System | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | drainage¦treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.8363 | 0.7176 | 0.7176 | [6 empty] | FI | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 8 | 1 | 22.1678 | 0.6252 | 0.0311 | 0.0311 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZK-173501 | LANDSCAPE LAYOUT | Layout Drawing |  |  |  |  | Layout Drawing | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.6252 | 0.5376 | 0.5376 | [6 empty] | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 2 | 13 | 24.0608 | 0.5069 | 0.0298 | 0.0134 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173502 | LANDSCAPING CROSS SECTION & DETAIL | & DETAIL |  |  |  |  | & DETAIL |  | Arrangement Section & Detail | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | generic | match | match | query_unscoped | passed |  | 0.6667 | 0.5582 | 0.6341 | 0.4439 | [6 empty] | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 |  | installation | query_unknown | [5 empty] | query_unscoped | true | true | 1 | 5 | 25.7245 | 0.4175 | 0.0318 | 0.0143 | hybrid | structured_no_system | [9 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173503 | WATER TANK SECTION & DETAIL | SECTION & DETAIL |  |  |  |  | SECTION & DETAIL for Tank |  | POTABLE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.6601 | 0.5480 | 0.5480 | [6 empty] | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown |  | wts | wts | rule | wts | match | true | false | 2 | 6 | 9.5384 | 0.5003 | 0.0313 | 0.0235 | hybrid | structured_no_phase | wts |  |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173504 | PAVILION PLAN & DETAIL | PLAN & DETAIL |  |  |  |  | PLAN & DETAIL |  | FENCE AND GATE PLAN AND DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.4000 | 0.6382 | 0.4715 | 0.4715 | [6 empty] | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | true | 2 | 2 | 24.0608 | 0.4649 | 0.0323 | 0.0145 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173505 | PUMP ROOM PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL for Pump |  | Pump Pit Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pump | pump | scoped | match | match | match | passed |  | 0.6667 | 0.7546 | 0.6930 | 0.5891 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 10 | 8 | 9.5086 | 0.5058 | 0.0290 | 0.0163 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.60 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GKC-173601 | CALCULATION OF CHILLED WATER STORAGE TANK FOUNDATION | Calculation sheet | CHILLED WATER STORAGE TANK |  |  |  | Calculation sheet for CHILLED WATER STORAGE TANK | Condensate | CALCULATION OF CONDENSATE WATER TANK FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | chilled¦storage¦tank¦water | tank | scoped | match | match | match | passed |  | 0.5000 | 0.6598 | 0.5479 | 0.5479 | [6 empty] | FA | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match |  | condensate | condensate | rule | condensate | match | false | false | 5 | 1 | 2.1802 | 0.5166 | 0.0318 | 0.0318 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed;activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GKC-173602 | CHILLED WATER STORAGE TANK FOUNDATION DETAIL | Detail Drawing | CHILLED WATER STORAGE TANK |  |  |  | Detail Drawing for Tank |  | POTABLE WATER TANK FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7611 | 0.6950 | 0.6950 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | true | false | 1 | 1 | 43.2088 | 0.5449 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-05-20 | 2024-06-04 | 2024-06-19 | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 |  | false | false | 1.00 | usable | activity_scope_source=rule | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GKC-173702 | POTABLE WATER CHILLER FOUNDATION DETAIL | Detail Drawing | POTABLE WATER CHILLER | Water Treatment System |  |  | Detail Drawing for Water Treatment System | Water Treatment System | Equipment Assembly and Detail DraWing for Water Treatment System | 1 | start+2M<=FA<=start+2M+2M | FA ∈ [start+60d, start+120d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.8363 | 0.7176 | 0.7176 | [6 empty] | FI | 0EF3035W16A14 | (PWT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-11-02 | 2008-03-04 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 4 | 6 | 29.9718 | 0.6035 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GHC-173801 | CALCULATION OF ATM FLASH TANK & DRAIN PUMP PIT | Calculation sheet | FLASH TANK, Pump |  |  |  | Calculation sheet for FLASH TANK, Pump |  | Flash tank calculation | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | flash¦pump¦tank | tank | scoped | match | match | match | passed |  | 1.0000 | 0.6847 | 0.9054 | 0.6338 | [6 empty] | FA | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-02-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 11 | 2 | 20.1740 | 0.5713 | 0.0302 | 0.0181 | hybrid | structured_no_system |  | civil_design |  | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GHC-173802 | ATM FLASH TANK & DRAIN PUMP PIT DETAIL | Detail Drawing | FLASH TANK, Pump |  |  |  | Detail Drawing for Tank |  | Pump Pit Detail | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | pump¦tank | pump | scoped | match | match | match | passed |  | 1.0000 | 0.6761 | 0.9028 | 0.7674 | [6 empty] | FA | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-02-29 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 12 | 3 | 20.1740 | 0.5816 | 0.0298 | 0.0134 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-05-21 | 2024-06-05 | 2024-06-20 | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.60 |  | false | false | 0.48 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZJ-173902 | POWER PLANT DIESEL GENERATOR FOUNDATION PLAN | Plan | DIESEL GENERATOR |  |  |  | Plan for DIESEL GENERATOR |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6940 | 0.7332 | 0.7332 | g_safe | [5 empty] | FA | 1EF3530W16A02 | (Block #1 EDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-10-29 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | false | 11 | 1 | 15.4653 | 0.6124 | 0.0305 | 0.0229 | hybrid | structured_no_system |  | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173903 | POWER PLANT DIESEL GENERATOR FOUNDATION REINF. DETAIL | Detail Drawing | DIESEL GENERATOR |  |  |  | Detail Drawing for DIESEL GENERATOR |  | Chlorination Plant FOUNDATION REINF. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | diesel¦generator |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7080 | 0.7724 | 0.7724 | g_safe | [5 empty] | FA | 1EF3530W16A02 | (Block #1 EDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2007-10-29 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | false | false | 10 | 3 | 15.4653 | 0.6156 | 0.0302 | 0.0226 | hybrid | structured_no_system |  | civil_design |  | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180001 | STANDARD DRAWING - GENERAL NOTES, ABBREVIATION, LEGEND & SIMBOLS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | [6 empty] | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 58 | 2 | 3.4917 | 0.4700 | 0.0246 | 0.0138 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180002 | STANDARD DRAWING - INTERIOR FINISH DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | INTERIOR finish DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7798 | 0.9339 | 0.9339 | [6 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 975 | 2 | 0.0004 | 0.4534 | 0.0171 | 0.0096 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180006 | STANDARD DRAWING - CLADDING JOINT DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | CLADDING JOINT DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8762 | 0.9629 | 0.9629 | [6 empty] | FI | 1EF1615W00A01 | (HRSG #11 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-04-30 |  | design_drawing | civil_design | compatible |  |  |  |  | hrsg | query_unscoped | false | false | 2797 | 6 | 0.0003 | 0.3903 | 0.0155 | 0.0087 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180008 | STANDARD DRAWING - MISC. ARCHITECTURAL DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | MISC. ARCHITECTURAL DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8136 | 0.9441 | 0.9441 | [6 empty] | FI | 1CF3520W16A01 | (FGSS #11) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | true | false | 2 | 356 | 9.1821 | 0.3573 | 0.0185 | 0.0139 | hybrid | structured_no_system |  | civil_design |  | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180019 | STANDARD DRAWING - DOOR SCHEDULE | Schedule |  |  |  |  | Schedule |  | DOOR SCHEDULE | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8450 | 0.7202 | 0.7202 | [6 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 945 | 1 | 0.0005 | 0.4172 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180020 | STANDARD DRAWING - DOOR DETAILS | DETAILS |  |  |  |  | DETAILS |  | DOOR DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7779 | 0.7000 | 0.7000 | [6 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 945 | 1 | 0.0002 | 0.3907 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180024 | STANDARD DRAWING - WINDOW SCHEDULE | Schedule |  |  |  |  | Schedule |  | WINDOW SCHEDULE | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | schedule | schedule | schedule | schedule |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8000 | 0.7067 | 0.7067 | [6 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 945 | 1 | 0.0005 | 0.4272 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180025 | STANDARD DRAWING - WINDOW DETAILS | DETAILS |  |  |  |  | DETAILS |  | WINDOW DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6694 | 0.6675 | 0.6675 | [6 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 945 | 1 | 0.0002 | 0.4099 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180030 | STANDARD DRAWING - RE - BAR STANDARD | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | [6 empty] | FA | 0EF3040W16A01 | (Lab) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-06-30 | design_drawing | civil_design | compatible |  |  |  |  | lab | query_unscoped | false | false | 15 | 172 | 0.0006 | 0.3666 | 0.0176 | 0.0099 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-11-17 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-31 | 2025-03-02 | generated | 0.30 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180033 | STANDARD DRAWING - GENERAL NOTES, MATERIALS, CONNECTIONS & MEMBER SIZE DESIGNATION | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | [6 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 69 | 1 | 3.3596 | 0.5123 | 0.0241 | 0.0136 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180034 | STANDARD DRAWING - ABBREVIATIONS & WELDING | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | STANDARD DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | [6 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 23 | 24 | 0.0004 | 0.4189 | 0.0240 | 0.0108 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180035 | STANDARD DRAWING - MOMENT CONNECTION DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | MOMENT CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8474 | 0.9542 | 0.9542 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 582 | 4 | 0.0004 | 0.4109 | 0.0172 | 0.0097 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180036 | STANDARD DRAWING - SHEAR CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | SHEAR CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8745 | 0.9624 | 0.9624 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 582 | 4 | 0.0002 | 0.4412 | 0.0172 | 0.0097 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180037 | STANDARD DRAWING - TYPICAL VERTICAL & HORIZONTAL BRACING CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL VERTICAL & HORIZONTAL BRACING CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9244 | 0.9773 | 0.9773 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 582 | 4 | 0.0002 | 0.4587 | 0.0172 | 0.0097 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180038 | STANDARD DRAWING - TYPICAL STAIR & HANDRAIL DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL STAIR & HANDRAIL DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9183 | 0.9755 | 0.9755 | [6 empty] | FI | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 1667 | 1 | 0.0002 | 0.4407 | 0.0170 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | fa_earliest | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180039 | STANDARD DRAWING - TYPICAL STAIR STRINGER CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL STAIR STRINGER CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9084 | 0.9725 | 0.9725 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 582 | 1 | 0.0002 | 0.4129 | 0.0180 | 0.0101 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180040 | STANDARD DRAWING - GIRTH & PURLIN CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | GIRTH & PURLIN CONNECTION DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8707 | 0.9612 | 0.9612 | [6 empty] | FI | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-30 |  | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 1759 | 1 | 0.0002 | 0.4874 | 0.0169 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | fa_earliest | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180041 | STANDARD DRAWING - TYPICAL GRATING AND CHK'D PLATE DETAILS | DRAWING |  |  |  |  | DRAWING |  | TYPICAL GRATING AND CHK'D PLATE DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9039 | 0.9712 | 0.9712 | [6 empty] | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | false | 2 | 473 | 4.2194 | 0.3388 | 0.0180 | 0.0101 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | fa_earliest | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180042 | STANDARD DRAWING - LADDER DETAILS | DRAWING |  |  |  |  | DRAWING |  | LADDER DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7976 | 0.7059 | 0.7059 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | design_drawing | civil_design | compatible |  |  |  |  | bop | query_unscoped | false | false | 576 | 5 | 0.0002 | 0.4532 | 0.0170 | 0.0095 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.37 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180043 | STANDARD DRAWING - PLUMBING STANDARD SYMBOL & ABBREVIATION | DRAWING |  |  |  |  | DRAWING |  | PLUMBING ISO DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7911 | 0.7040 | 0.4928 | [6 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 23 | 15 | 0.0004 | 0.4761 | 0.0254 | 0.0114 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180044 | STANDARD DRAWING - PLUMBING STANDARD GENERAL DETAILS | DRAWING |  |  |  |  | DRAWING |  | PLUMBING STANDARD GENERAL DETAILS | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.9316 | 0.9795 | 0.9795 | [6 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | false | false | 58 | 1 | 3.4917 | 0.5458 | 0.0249 | 0.0140 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 |  | false | false | 0.43 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180401 | ST BUILDING - GROUND FLOOR PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 3CF2020W42A12 | (ST #30) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2008-12-16 | 2009-05-18 |  | installation | query_unknown | stg | stg | stg | query | stg | match | true | false | 20 | 14 | 10.0736 | 0.6733 | 0.0260 | 0.0195 | hybrid | structured_no_phase | stg | [5 empty] | 2025-09-18 | 2025-10-18 | 2025-11-17 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180402 | ST BUILDING - ROOF PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | stg | stg | stg | query | stg | match | true | false | 3 | 1 | 19.1342 | 0.7306 | 0.0323 | 0.0242 | hybrid | structured_no_phase | stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180403 | ST BUILDING - ELEVATION | Elevation Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Elevation Drawing for Steam Turbine Building |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6195 | 0.6525 | 0.4568 | g_ambig | generic_ok | 0.82 |  | 1 | A building elevation drawing is not the same as an ST cabinet internal arrangement drawing for TCS/TPS. | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 6 | 9.9602 | 0.6579 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180404 | ST BUILDING - SECTION | SECTION | Steam Turbine & Generator |  | Steam Turbine Building |  | SECTION for Steam Turbine Building | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.6618 | 0.6652 | 0.6652 | [6 empty] | FI | 3CF2020W42A12 | (ST #30) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2008-12-16 | 2009-05-18 |  | installation | query_unknown | stg | stg | stg | query | stg | match | true | false | 12 | 3 | 10.0736 | 0.7233 | 0.0298 | 0.0223 | hybrid | structured_no_phase | stg | [5 empty] | 2025-09-18 | 2025-10-18 | 2025-11-17 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180405 | ST BUILDING - INTERIOR FINISH SCHEDULE | Schedule | Steam Turbine & Generator |  | Steam Turbine Building |  | Schedule for STG | ST BUILDING | ST BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | schedule | schedule | schedule | schedule | generator¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9429 | 0.9829 | 0.9829 | [6 empty] | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg | stg | stg | query | stg | match | true | false | 10 | 31 | 11.6501 | 0.6218 | 0.0253 | 0.0190 | hybrid | structured_no_phase | stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180406 | ST BUILDING - DOOR SCHEDULE | Schedule | Steam Turbine & Generator |  | Steam Turbine Building |  | Schedule for STG | ST BUILDING | ST BUILDING - DOOR SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | title | schedule | schedule | schedule | schedule | generator¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9596 | 0.9879 | 0.9879 | [6 empty] | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg | stg | stg | query | stg | match | true | false | 1 | 13 | 11.6501 | 0.6533 | 0.0301 | 0.0226 | hybrid | structured_no_phase | stg |  |  | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 |  | false | false | 0.68 | usable | default_fc_window;activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180408 | ST BUILDING - WALL SECTION | SECTION | Steam Turbine & Generator |  | Steam Turbine Building |  | SECTION for Steam Turbine Building | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.6618 | 0.6652 | 0.6652 | [6 empty] | FI | 3CF2020W42A12 | (ST #30) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2008-12-16 | 2009-05-18 |  | installation | query_unknown | stg | stg | stg | query | stg | match | true | false | 13 | 4 | 10.0736 | 0.6817 | 0.0293 | 0.0220 | hybrid | structured_no_phase | stg | [5 empty] | 2025-09-18 | 2025-10-18 | 2025-11-17 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180451 | ST BUILDING - PILE ARRANGEMENT | ARRANGEMENT | Steam Turbine & Generator |  | Steam Turbine Building |  | ARRANGEMENT for STG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6752 | 0.4359 | 0.3705 | g_safe | [5 empty] | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 4 | 1 | 14.3944 | 0.6919 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.60 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180452 | ST BUILDING - FOUNDATION LOCATION PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 3 | 1 | 12.1953 | 0.7473 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180454 | ST BUILDING - PILE CAP & FOUNDATION REINFORCEMENT DETAIL | Detail Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Detail Drawing for Steam Turbine Building | ST BUILDING | ST BUILDING - PILE CAP & FOUNDATION REINFORCEMENT DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9647 | 0.9894 | 0.9894 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 5 | 1 | 12.1953 | 0.6994 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180458 | ST BUILDING - COLUMN LOCATION PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1CF2020W42A12 | (ST #10) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2008-10-17 | 2009-03-18 |  | installation | query_unknown | stg | stg | stg | query | stg | match | true | false | 10 | 14 | 10.0736 | 0.6724 | 0.0278 | 0.0208 | hybrid | structured_no_phase | stg | [5 empty] | 2025-07-20 | 2025-08-19 | 2025-09-18 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180459 | ST BUILDING - BASE PLATE DETAIL | Detail Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Detail Drawing for Steam Turbine Building | ST BUILDING | ST BUILDING - BASE PLATE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9610 | 0.9883 | 0.9883 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 2 | 9.9602 | 0.6776 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180460 | ST BUILDING - CRANE GIRDER FRAMING PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 |  | installation | query_unknown | stg | stg | stg | query | crane_hoist¦stg | match | true | false | 3 | 4 | 18.1691 | 0.6787 | 0.0315 | 0.0236 | hybrid | structured_no_phase | stg | [5 empty] | 2025-04-19 | 2025-05-19 | 2025-06-18 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180462 | ST BUILDING - ROOF FRAMING PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | stg | stg | stg | query | stg | match | true | false | 3 | 2 | 19.1342 | 0.7115 | 0.0320 | 0.0240 | hybrid | structured_no_phase | stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180463 | ST BUILDING - FRAMING ELEVATION | Elevation Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Elevation Drawing for Steam Turbine Building |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6195 | 0.6525 | 0.4568 | g_ambig | generic_ok | 0.82 |  | 1 | A building elevation drawing is not the same as an ST cabinet internal arrangement drawing for TCS/TPS. | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 5 | 9.9602 | 0.6654 | 0.0318 | 0.0318 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180464 | ST BUILDING - GIRT NORTH - SOUTH ELEVATION | Elevation Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Elevation Drawing for Steam Turbine Building |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6195 | 0.6525 | 0.4568 | g_ambig | generic_ok | 0.82 |  | 1 | A building elevation drawing is not the same as an ST cabinet internal arrangement drawing for TCS/TPS. | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 7 | 9.9602 | 0.6405 | 0.0313 | 0.0313 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180465 | ST BUILDING - GIRT EAST - WEST ELEVATION | Elevation Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Elevation Drawing for Steam Turbine Building |  | Steam Drum – DraWing | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6195 | 0.6525 | 0.4568 | g_ambig | generic_ok | 0.82 |  | 1 | A building elevation drawing is not the same as an ST cabinet internal arrangement drawing for TCS/TPS. | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 8 | 9.9602 | 0.6478 | 0.0311 | 0.0311 | hybrid | structured_preferred | stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.68 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180466 | ST BUILDING - MISC. PLATFORM PLAN & SECTION | PLAN & SECTION | Steam Turbine & Generator |  | Steam Turbine Building |  | PLAN & SECTION for Steam Turbine Building | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.5945 | 0.6450 | 0.6450 | [6 empty] | FI | 1CF2020W42A12 | (ST #10) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2008-10-17 | 2009-03-18 |  | installation | query_unknown | stg | stg | stg | query | stg | match | true | false | 10 | 11 | 10.0736 | 0.6551 | 0.0284 | 0.0213 | hybrid | structured_no_phase | stg | [5 empty] | 2025-07-20 | 2025-08-19 | 2025-09-18 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180467 | ST BUILDING - STAIR PLAN, ELEVATION & DETAIL | PLAN, ELEVATION & DETAIL | Steam Turbine & Generator |  | Steam Turbine Building |  | PLAN, ELEVATION & DETAIL for Steam Turbine Building | ST BUILDING | ST BUILDING - STAIR PLAN, ELEVATION & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.6446 | 0.6601 | 0.6601 | [6 empty] | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg | stg | stg | query | stg | match | true | false | 4 | 18 | 11.6497 | 0.6370 | 0.0284 | 0.0213 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180468 | ST BUILDING – MAIN TRUSS DETAIL | Detail Drawing | Steam Turbine & Generator |  | Steam Turbine Building |  | Detail Drawing for Steam Turbine Building | ST BUILDING | ST BUILDING – MAIN TRUSS DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9559 | 0.9868 | 0.9868 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 5 | 9.9602 | 0.6488 | 0.0318 | 0.0318 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180469 | ST BUILDING - ROOF WALKWAY FRAMING PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | stg | stg | stg | query | stg | match | true | false | 3 | 1 | 19.1342 | 0.6918 | 0.0323 | 0.0242 | hybrid | structured_no_phase | stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180471 | ST BUILDING - ROOF PURLIN PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | stg | stg | stg | query | stg | match | true | false | 3 | 2 | 19.1342 | 0.6934 | 0.0320 | 0.0240 | hybrid | structured_no_phase | stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UMA-180481 | ST BUILDING - EQUIPMENT DRAIN PLAN | Plan | Steam Turbine & Generator |  | Steam Turbine Building |  | Plan for Steam Turbine Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5734 | 0.5220 | 0.5220 | [6 empty] | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg | stg | stg | query | stg | match | true | false | 6 | 20 | 11.6497 | 0.6428 | 0.0277 | 0.0207 | hybrid | structured_no_phase | stg | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UMA-180482 | ST BUILDING - EQUIPMENT DRAIN PLAN (ISO) | PLAN (ISO) | Steam Turbine & Generator |  | Steam Turbine Building |  | PLAN (ISO) for Steam Turbine Building | ST BUILDING | ST BUILDING - EQUIPMENT DRAIN PLAN (ISO) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.6493 | 0.5448 | 0.5448 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  | civil_design | query_unknown | stg | stg | stg | query | stg | match | true | false | 25 | 8 | 9.9602 | 0.6323 | 0.0265 | 0.0199 | hybrid | structured_no_phase | stg | [5 empty] | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180490 | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | Calculation sheet | Steam Turbine & Generator |  | Steam Turbine Building |  | Calculation sheet for STG | ST BUILDING | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | design_calculation | design_calculation | generator¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9589 | 0.9877 | 0.9877 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 1 | 15.5205 | 0.7259 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180491 | ST BUILDING - DESIGN CALCULATION FOR BASE PLATE, COLUMN, BEAM & ROOF TRUSS | Calculation sheet | Steam Turbine & Generator |  | Steam Turbine Building |  | Calculation sheet for STG | ST BUILDING | ST BUILDING - DESIGN CALCULATION FOR BASE PLATE, COLUMN, BEAM & ROOF TRUSS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | design_calculation | design_calculation | generator¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9645 | 0.9893 | 0.9893 | [6 empty] | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 4 | 1 | 12.2427 | 0.6833 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180492 | ST BUILDING - DESIGN CALCULATION FOR CRANE GIRDER, PURLIN & SIDE GIRT | Calculation sheet | Steam Turbine & Generator |  | Steam Turbine Building |  | Calculation sheet for STG | ST BUILDING | ST BUILDING - DESIGN CALCULATION FOR CRANE GIRDER, PURLIN & SIDE GIRT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | design_calculation | design_calculation | generator¦steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9749 | 0.9925 | 0.9925 | [6 empty] | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | crane_hoist¦stg | stg | query | stg | match | true | false | 4 | 1 | 12.2427 | 0.6755 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0BAT-180500 | ROOF FOR GTG TR - CALCULATION | Calculation sheet | Gas Turbine Generator Transformer |  |  |  | Calculation sheet for Gas Turbine Generator Transformer |  | GT Foundation Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | gas¦generator¦gtg¦transformer¦turbine | gt¦gtg | scoped | match | match | match | passed |  | 0.6667 | 0.4803 | 0.6108 | 0.6108 | [6 empty] | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat¦gtg | gtg | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 1 | 13.5608 | 0.6831 | 0.0328 | 0.0328 | hybrid | structured_preferred | gsut_uat¦gtg | civil_design | 10 | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180500 | ST BUILDING_MISC. PLATFORM PLAN & SECTION | PLAN & SECTION | Steam Turbine & Generator |  | Steam Turbine Building |  | PLAN & SECTION for Steam Turbine Building | ST BUILDING | ST BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | steam¦stg¦turbine | st¦stg | scoped | match | match | match | passed |  | 0.6667 | 0.5945 | 0.6450 | 0.6450 | [6 empty] | FI | 3CF2020W42A12 | (ST #30) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2008-12-16 | 2009-05-18 |  | installation | query_unknown | stg | stg | stg | query | stg | match | true | false | 14 | 10 | 10.0736 | 0.6477 | 0.0278 | 0.0208 | hybrid | structured_no_phase | stg | [5 empty] | 2025-09-18 | 2025-10-18 | 2025-11-17 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P1BAT-180511 | ROOF FOR GTG #1 TR - PLAN, SECTION, ELEVATION | PLAN, SECTION, ELEVATION | Gas Turbine Generator #1 Transformer |  |  |  | PLAN, SECTION, ELEVATION for GTG |  | PLAN, SECTION, ELEVATION | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7867 | 0.9360 | 0.6552 | g_ambig | generic_ok | 0.90 |  | 13 | Document is for GTG #1 transformer roof, while competing specifics target GT auxiliary coolers/heaters or GTG LEB sections, not the transformer building roof. | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 |  | civil_design | query_unknown | gsut_uat¦gtg |  | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 6 | 4 | 16.7605 | 0.6701 | 0.0308 | 0.0231 | hybrid | structured_no_phase | gsut_uat¦gtg |  |  | 2024-03-20 | 2024-04-04 | 2024-04-19 | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P1BAT-180512 | ROOF FOR GTG #1 TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | PLAN, BASEPLATE DETAILS | Gas Turbine Generator #1 Transformer |  |  |  | PLAN, BASEPLATE DETAILS for GTG | SUPPORT BUILDING | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4444 | 0.6523 | 0.5068 | 0.5068 | g_ambig | uncertain | 0.55 |  | 26 | Competing specifics include transformer-related 'GTG STEP UP & UNIT AUX. TRANSFORMER' but not clearly 'GTG #1 TR roof/baseplate', so equipment applicability is ambiguous. | FI | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 |  | civil_design | query_unknown | gsut_uat¦gtg |  | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 11 | 3 | 16.7605 | 0.6833 | 0.0300 | 0.0225 | hybrid | structured_no_phase | gsut_uat¦gtg | [5 empty] | 2024-05-04 | 2024-06-03 | 2024-07-03 | fi_complete | 0.90 |  | false | false | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P1BAT-180513 | ROOF FOR GTG #1 TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | Drawing | Gas Turbine Generator #1 Transformer |  |  |  | Drawing for GTG |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | gas¦generator¦gtg¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.2000 | 0.5044 | 0.2913 | 0.2913 | [6 empty] | FI | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 | civil_design | civil_design | match | gsut_uat¦gtg | gtg | gsut_uat¦gtg | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 2 | 16.7605 | 0.6802 | 0.0325 | 0.0325 | hybrid | structured_preferred | gsut_uat¦gtg | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UCB-180600 | CENTRAL CONTROL BUILDING - CALCULATION | Calculation sheet |  |  | Central Control Building |  | Calculation sheet for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | ccr¦central | ccr | scoped | match | match | match | passed |  | 1.0000 | 0.8290 | 0.9487 | 0.9487 | [6 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 3 | 18.3850 | 0.6093 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | fi_complete | activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180601 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 10 | 17.4405 | 0.6164 | 0.0280 | 0.0157 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180602 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 10 | 17.4405 | 0.6154 | 0.0280 | 0.0157 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180603 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 8 | 17.4405 | 0.6124 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180604 | CENTRAL CONTROL BUILDING - ROOF PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 12 | 8 | 17.4405 | 0.5971 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180605 | CENTRAL CONTROL BUILDING - SIDE WALL ELEVATION | Elevation Drawing |  |  | Central Control Building |  | Elevation Drawing for Central Control Building |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5248 | 0.5074 | 0.5074 | g_safe | [5 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 4 | 18.3850 | 0.5955 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180606 | CENTRAL CONTROL BUILDING - MAIN SECTION | SECTION |  |  | Central Control Building |  | SECTION for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8618 | 0.8185 | 0.8185 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 11 | 9 | 17.4405 | 0.6223 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180607 | CENTRAL CONTROL BUILDING - INTERIOR FINISH SCHEDULE | Schedule |  |  | Central Control Building |  | Schedule for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7428 | 0.6895 | 0.6895 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 8 | 17.4408 | 0.5762 | 0.0290 | 0.0163 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180608 | CENTRAL CONTROL BUILDING - DOOR & WINDOW SCHEDULE | Schedule |  |  | Central Control Building |  | Schedule for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7428 | 0.6895 | 0.6895 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 8 | 17.4408 | 0.5255 | 0.0290 | 0.0163 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180609 | CENTRAL CONTROL BUILDING - STAIRCASE#1 ENLARGED PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 8 | 17.4405 | 0.5229 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180610 | CENTRAL CONTROL BUILDING - STAIRCASE#2 ENLARGED PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 8 | 17.4405 | 0.5281 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180611 | CENTRAL CONTROL BUILDING - ENLARGED TOILET PLAN & ELEVATION | PLAN & ELEVATION |  |  | Central Control Building |  | PLAN & ELEVATION for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8482 | 0.8145 | 0.8145 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 12 | 10 | 17.4405 | 0.5184 | 0.0282 | 0.0158 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180612 | CENTRAL CONTROL BUILDING - WALL OPENING ELEVATION | Elevation Drawing |  |  | Central Control Building |  | Elevation Drawing for Central Control Building |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5248 | 0.5074 | 0.5074 | g_safe | [5 empty] | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 3 | 3 | 18.3850 | 0.5855 | 0.0317 | 0.0190 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180613 | CENTRAL CONTROL BUILDING - CEILING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 12 | 8 | 17.4405 | 0.5894 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180614 | CENTRAL CONTROL BUILDING - MISC. DETAIL | Detail Drawing |  |  | Central Control Building |  | Detail Drawing for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8054 | 0.8016 | 0.8016 | [6 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 3 | 4 | 18.3850 | 0.6304 | 0.0315 | 0.0189 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180651 | CENTRAL CONTROL BUILDING - FDN & COLUMN ARRANGEMENT PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 4 | 1 | 20.6978 | 0.7055 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | fi_complete | activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180652 | CENTRAL CONTROL BUILDING - GROUND FLOOR FRAMING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 10 | 17.4405 | 0.5732 | 0.0280 | 0.0157 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180653 | CENTRAL CONTROL BUILDING - 1ST FLOOR FRAMING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 9 | 17.4405 | 0.5629 | 0.0282 | 0.0159 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180654 | CENTRAL CONTROL BUILDING - 2ND FLOOR FRAMING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 8 | 17.4405 | 0.5610 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180655 | CENTRAL CONTROL BUILDING - ROOF FRAMING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 12 | 9 | 17.4405 | 0.5349 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180656 | CENTRAL CONTROL BUILDING - LINE FRAMING ELEVATION | Elevation Drawing |  |  | Central Control Building |  | Elevation Drawing for Central Control Building |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5248 | 0.5074 | 0.5074 | g_safe | [5 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 4 | 18.3850 | 0.6142 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180657 | CENTRAL CONTROL BUILDING - ROW FRAMING ELEVATION | Elevation Drawing |  |  | Central Control Building |  | Elevation Drawing for Central Control Building |  | Control System Configuration DraWing | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | drawing | drawing | drawing | drawing | ccr¦central |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5248 | 0.5074 | 0.5074 | g_safe | [5 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 4 | 18.3850 | 0.5947 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 |  | false | false | 0.46 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180658 | CENTRAL CONTROL BUILDING - STAIRCASE#1 FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | Central Control Building |  | PLAN & ELEVATION for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8482 | 0.8145 | 0.8145 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 11 | 17.4405 | 0.4941 | 0.0278 | 0.0156 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180659 | CENTRAL CONTROL BUILDING - STAIRCASE#2 FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | Central Control Building |  | PLAN & ELEVATION for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8482 | 0.8145 | 0.8145 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 13 | 17.4405 | 0.4947 | 0.0274 | 0.0154 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180660 | CENTRAL CONTROL BUILDING - 1ST FLOOR OPENING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 8 | 17.4405 | 0.5904 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180661 | CENTRAL CONTROL BUILDING - 2ND FLOOR OPENING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 8 | 17.4405 | 0.5835 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180664 | CENTRAL CONTROL BUILDING - FOUNDATION RE - BAR DETAIL | Detail Drawing |  |  | Central Control Building |  | Detail Drawing for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8054 | 0.8016 | 0.8016 | [6 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 20.6978 | 0.6343 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180665 | CENTRAL CONTROL BUILDING - COLUMN RE - BAR SCHEDULE | Schedule |  |  | Central Control Building |  | Schedule for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7428 | 0.6895 | 0.6895 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 9 | 17.4408 | 0.5707 | 0.0288 | 0.0162 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180666 | CENTRAL CONTROL BUILDING - BEAM & GIRDER RE - BAR SCHEDULE | Schedule |  |  | Central Control Building |  | Schedule for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7428 | 0.6895 | 0.6895 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 10 | 17.4408 | 0.5210 | 0.0286 | 0.0161 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180667 | CENTRAL CONTROL BUILDING - SLAB & MISC. RE - BAR SCHEDULE | Schedule |  |  | Central Control Building |  | Schedule for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7428 | 0.6895 | 0.6895 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 11 | 17.4408 | 0.5191 | 0.0284 | 0.0160 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180668 | CENTRAL CONTROL BUILDING - STRUCTURAL MISC. DETAIL | Detail Drawing |  |  | Central Control Building |  | Detail Drawing for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - MISC. DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.8054 | 0.8016 | 0.8016 | [6 empty] | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 4 | 1 | 18.3850 | 0.6323 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180681 | CENTRAL CONTROL BUILDING - PLUMBING EQUIPMENT SCHEDULE | Schedule |  |  | Central Control Building |  | Schedule for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - INTERIOR finish SCHEDULE | 1 | start+5M<=FA<=start+5M+2M | FA ∈ [start+150d, start+210d] | rule_query | schedule | schedule | schedule | schedule | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7428 | 0.6895 | 0.6895 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 1 | 21.1421 | 0.5843 | 0.0307 | 0.0173 | hybrid | structured_no_system |  |  |  | 2025-10-13 | 2025-11-12 | 2025-12-12 | 2025-12-27 | 2026-01-11 | 2026-01-26 | generated | 0.90 |  | false | false | 0.54 | needs_review | default_fc_window;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180682 | CENTRAL CONTROL BUILDING - PLUMBING SCHEMATIC DIAGRAM | Diagram |  |  | Central Control Building |  | Diagram for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.6667 | 0.7681 | 0.6971 | 0.6971 | [6 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 18.3850 | 0.5973 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | system_design¦engineering |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | fi_complete | activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180683 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLUMBING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 7 | 17.4405 | 0.6012 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180684 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLUMBING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 6 | 17.4405 | 0.5924 | 0.0289 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180685 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLUMBING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 13 | 6 | 17.4405 | 0.5884 | 0.0289 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180686 | CENTRAL CONTROL BUILDING - ROOF PLUMBING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 12 | 6 | 17.4405 | 0.5798 | 0.0290 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180687 | CENTRAL CONTROL BUILDING - ENLARGED TOILET & SHOWER PLUMBING PLAN | Plan |  |  | Central Control Building |  | Plan for Central Control Building | CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | ccr¦central | ccr | scoped | match | match | match | passed |  | 0.8000 | 0.7987 | 0.7996 | 0.7996 | [6 empty] | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 12 | 8 | 17.4405 | 0.5454 | 0.0286 | 0.0161 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181000 | ST #1 LEB - CALCULATION | Calculation sheet | Steam Turbine #1 |  | Local Electrical Building |  | Calculation sheet for Steam Turbine #1 |  | ST #1 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 1 | 2 | 11.8090 | 0.6102 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181001 | ST #1 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | PLAN & INTERIOR FINISH SCHEDULE | Steam Turbine |  | Local Electrical Building |  | PLAN & INTERIOR FINISH SCHEDULE for STG |  | INTERIOR finish SCHEDULE | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7922 | 0.9377 | 0.7970 | g_ambig | use_specific | 0.95 | ST #1 LEB - GROUND FLOOR PLAN & INTERIOR finish SCHEDULE(INCL. DOOR & WINDOW) | 14 | There is an exact equipment-specific rule for the same ST #1 LEB interior finish schedule document, so it should override the generic. | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  | civil_design | query_unknown | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 65 | 22 | 10.4739 | 0.5857 | 0.0202 | 0.0151 | hybrid | structured_no_phase | electrical¦stg |  |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.60 | fa_earliest | false | false | 0.60 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181002 | ST #1 LEB - ROOF PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 3 | 1 | 15.3806 | 0.6507 | 0.0323 | 0.0242 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181003 | ST #1 LEB - SIDE WALL ELEVATION | Elevation Drawing | Steam Turbine |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 1 | Document is a building wall elevation (ST #1 LEB) and the only specific rule is for an ST control cabinet internal arrangement, which is different equipment/deliverable content. | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 1 | 2 | 10.4735 | 0.5995 | 0.0325 | 0.0325 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181004 | ST #1 LEB - MAIN SECTION | MAIN SECTION | Steam Turbine |  | Local Electrical Building |  | MAIN SECTION for Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7635 | 0.7890 | 0.7890 | g_ambig | uncertain | 0.55 |  | 4 | ST #1 LEB main section could fall under ST building/LEB-related specifics, but none explicitly match 'ST #1 LEB - MAIN SECTION' so applicability is unclear. | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 84 | 4 | 12.1543 | 0.6455 | 0.0226 | 0.0169 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;rule_generic_judge=uncertain;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181005 | ST #1 LEB - ARCHITECTURAL MISC. DETAIL | Detail Drawing | Steam Turbine |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | ST #1 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF2020W16A06 | (ST #30) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 5 | 1 | 9.1380 | 0.6301 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181051 | ST #1 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 3 | 1 | 12.7086 | 0.7161 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181052 | ST #1 LEB - GROUND FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  | civil_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 15 | 2 | 10.4735 | 0.6553 | 0.0295 | 0.0221 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181053 | ST #1 LEB - ROOF FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 3 | 2 | 15.3806 | 0.6366 | 0.0320 | 0.0240 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181054 | ST #1 LEB - LINE & ROW FRAMING ELEVATION | Elevation Drawing | Steam Turbine |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 1 | Document is a building wall elevation (ST #1 LEB) and the only specific rule is for an ST control cabinet internal arrangement, which is different equipment/deliverable content. | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 1 | 5 | 10.4735 | 0.6063 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181055 | ST #1 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | Detail Drawing | Steam Turbine |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | ST #1 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 7 | 1 | 12.7086 | 0.6659 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181056 | ST #1 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | Schedule | Steam Turbine |  | Local Electrical Building |  | Schedule for STG |  | ST #1 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | [6 empty] | FI | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 1 | 11 | 12.1546 | 0.6088 | 0.0305 | 0.0229 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181100 | ST #2 LEB - CALCULATION | Calculation sheet | Steam Turbine |  | Local Electrical Building |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 1 | 3 | 11.0592 | 0.5812 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181101 | ST #2 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | PLAN & INTERIOR FINISH SCHEDULE | Steam Turbine |  | Local Electrical Building |  | PLAN & INTERIOR FINISH SCHEDULE for STG |  | INTERIOR finish SCHEDULE | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7922 | 0.9377 | 0.7970 | g_ambig | use_specific | 0.95 | ST #1 LEB - GROUND FLOOR PLAN & INTERIOR finish SCHEDULE(INCL. DOOR & WINDOW) | 14 | There is an exact equipment-specific rule for the same ST #1 LEB interior finish schedule document, so it should override the generic. | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 |  | civil_design | query_unknown | electrical¦stg |  | electrical¦stg | query | stg | match | true | false | 61 | 33 | 11.0596 | 0.5705 | 0.0190 | 0.0143 | hybrid | structured_no_phase | electrical¦stg |  |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.60 | fa_earliest | false | false | 0.51 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;activity_rrf_low;rule_generic_judge=use_specific | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181102 | ST #2 LEB - ROOF PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 4 | 1 | 14.0827 | 0.6496 | 0.0320 | 0.0240 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181103 | ST #2 LEB - SIDE WALL ELEVATION | Elevation Drawing | Steam Turbine |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 1 | Document is a building wall elevation (ST #1 LEB) and the only specific rule is for an ST control cabinet internal arrangement, which is different equipment/deliverable content. | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 1 | 4 | 11.0592 | 0.5932 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181104 | ST #2 LEB - MAIN SECTION | MAIN SECTION | Steam Turbine |  | Local Electrical Building |  | MAIN SECTION for Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7635 | 0.7890 | 0.7890 | g_ambig | uncertain | 0.55 |  | 4 | ST #1 LEB main section could fall under ST building/LEB-related specifics, but none explicitly match 'ST #1 LEB - MAIN SECTION' so applicability is unclear. | FI | 2EF2020W00A01 | (ST #20) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 78 | 10 | 12.7300 | 0.6335 | 0.0215 | 0.0161 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;activity_phase_status=query_unknown;rule_generic_judge=uncertain;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181105 | ST #2 LEB - ARCHITECTURAL MISC. DETAIL | Detail Drawing | Steam Turbine |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | ST #2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 1 | 4 | 11.0592 | 0.6173 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181151 | ST #2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 3 | 1 | 13.2943 | 0.7133 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181152 | ST #2 LEB - GROUND FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 |  | civil_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 9 | 4 | 11.0592 | 0.6488 | 0.0301 | 0.0226 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181153 | ST #2 LEB - ROOF FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for Local Electrical Building | ST BUILDING | ST BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | electrical¦leb¦local¦stg | st¦stg | scoped | match | match | match | passed |  | 0.5000 | 0.5391 | 0.5117 | 0.5117 | [6 empty] | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 3 | 2 | 15.9498 | 0.6365 | 0.0320 | 0.0240 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181154 | ST #2 LEB - LINE & ROW FRAMING ELEVATION | Elevation Drawing | Steam Turbine |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local¦stg |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 1 | Document is a building wall elevation (ST #1 LEB) and the only specific rule is for an ST control cabinet internal arrangement, which is different equipment/deliverable content. | FA | 3EF2020W16A06 | (ST #30) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | electrical | electrical¦stg | query | stg | match | true | false | 5 | 1 | 9.1380 | 0.6196 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦stg | civil_design | 10 | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.30 | fa_earliest | false | false | 0.80 | usable | rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181155 | ST #2 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | Detail Drawing | Steam Turbine |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | ST #2 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local¦stg | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 7 | 3 | 13.2943 | 0.6591 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | electrical¦stg | civil_design |  |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181156 | ST #2 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | Schedule | Steam Turbine |  | Local Electrical Building |  | Schedule for STG |  | ST #2 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦leb¦local¦steam¦stg¦turbine | leb¦st¦stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF2020W00A01 | (ST #20) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | electrical¦stg | stg | electrical¦stg | query | stg | match | true | false | 1 | 28 | 12.7303 | 0.5923 | 0.0278 | 0.0208 | hybrid | structured_no_phase | electrical¦stg | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181200 | GTG #1,2 LEB - CALCULATION | Calculation sheet | Gas Turbine Generator |  | Local Electrical Building |  | Calculation sheet for GTG |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.6691 | 0.6674 | 0.6674 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 12.5474 | 0.6675 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181201 | GTG #1,2 LEB - BASEMENT FLOOR PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - BASEMENT FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 10 | 1 | 11.9683 | 0.7347 | 0.0307 | 0.0230 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181202 | GTG #1,2 LEB - GROUND FLOOR PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 9 | 1 | 12.5474 | 0.7421 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181203 | GTG #1,2 LEB - ROOF PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 8 | 2 | 12.5474 | 0.7273 | 0.0308 | 0.0231 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181204 | GTG #1,2 LEB - SIDE WALL ELEVATION | Elevation Drawing | Gas Turbine Generator |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 12 | GTG #1,2 LEB side wall elevation is a building drawing, while competing specifics are for GT equipment/foundation/firefighting/tubing drawings, not LEB elevations. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 12.5474 | 0.7049 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181205 | GTG #1,2 LEB - MAIN SECTION | SECTION | Gas Turbine Generator |  | Local Electrical Building |  | SECTION for Local Electrical Building |  | GTG #1,2 LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W32A04 | (GTG #21 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 18 | 4 | 11.9683 | 0.7276 | 0.0284 | 0.0213 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181206 | GTG #1,2 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | Schedule | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5758 | 0.4527 | 0.4527 | [6 empty] | FA | 2CF1200W24A10 | (GTG #21 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-27 | 2008-08-04 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 2 | 18.3156 | 0.6818 | 0.0325 | 0.0244 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181207 | GTG #1,2 LEB - STAIR PLAN & SECTION | PLAN & SECTION | Gas Turbine Generator |  | Local Electrical Building |  | PLAN & SECTION for Local Electrical Building |  | GTG #1,2 LEB - STAIR PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 3 | 1 | 12.5474 | 0.7279 | 0.0323 | 0.0242 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181208 | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | Detail Drawing | Gas Turbine Generator |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 4 | 2 | 12.5474 | 0.7299 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181251 | GTG #1,2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 3 | 4 | 16.0366 | 0.7210 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181252 | GTG #1,2 LEB - GROUND FLOOR FRAMING PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 9 | 1 | 12.5474 | 0.7343 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181253 | GTG #1,2 LEB - ROOF FRAMING PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 8 | 1 | 12.5474 | 0.7086 | 0.0311 | 0.0233 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181254 | GTG #1,2 LEB - LINE & ROW FRAMING ELEVATION | Elevation Drawing | Gas Turbine Generator |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 12 | GTG #1,2 LEB side wall elevation is a building drawing, while competing specifics are for GT equipment/foundation/firefighting/tubing drawings, not LEB elevations. | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 12.5474 | 0.7154 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181255 | GTG #1,2 LEB - STAIR FRAMING PLAN & ELEVATION | PLAN & ELEVATION | Gas Turbine Generator |  | Local Electrical Building |  | PLAN & ELEVATION for Local Electrical Building |  | GTG #1,2 LEB - STAIR FRAMING PLAN & ELEVATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 3 | 1 | 12.5474 | 0.7294 | 0.0323 | 0.0242 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181256 | GTG #1,2 LEB - GROUND FLOOR OPENING PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR OPENING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 9 | 1 | 12.5474 | 0.7191 | 0.0309 | 0.0232 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181257 | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | Detail Drawing | Gas Turbine Generator |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 2 | 2 | 13.9836 | 0.7009 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181258 | GTG #1,2 LEB - COLUMN RE - BAR SCHEDULE | Schedule | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5758 | 0.4527 | 0.4527 | [6 empty] | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 2 | 12.5477 | 0.6874 | 0.0325 | 0.0244 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181259 | GTG #1,2 LEB - BEAM & GIRDER RE - BAR SCHEDULE | Schedule | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Schedule for Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5081 | 0.4324 | 0.4324 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 1 | 15.4064 | 0.6981 | 0.0328 | 0.0246 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181260 | GTG #1,2 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | Detail Drawing | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | GTG #1,2 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 4 | 2 | 15.4061 | 0.6989 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181281 | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | Schedule | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Schedule for Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5081 | 0.4324 | 0.4324 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 1 | 2 | 15.4064 | 0.6512 | 0.0325 | 0.0244 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181282 | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | Diagram | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Diagram for Gas Turbine Generator #1,2 |  | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 3 | 4 | 15.4061 | 0.6551 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | system_design¦engineering |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181284 | GTG #1,2 LEB - GROUND FLOOR PLUMBING PLAN | Plan | Gas Turbine Generator #1,2 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #1,2 LEB - GROUND FLOOR PLUMBING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 8 | 1 | 15.4061 | 0.7008 | 0.0311 | 0.0233 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181300 | GTG #3,4,5 LEB - CALCULATION | Calculation sheet | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Calculation sheet for Gas Turbine Generator #3,4,5 |  | GTG #3,4,5 LEB - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.6667 | 0.5681 | 0.6371 | 0.6371 | [6 empty] | FI | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 12 | 1 | 13.1061 | 0.6597 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181301 | GTG #3,4,5 LEB - BASEMENT FLOOR PLAN | Plan | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #3,4,5 LEB - BASEMENT FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 70 | 1 | 13.8021 | 0.7083 | 0.0241 | 0.0181 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181302 | GTG #3,4,5 LEB - GROUND FLOOR PLAN | Plan | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #3,4,5 LEB - GROUND FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 70 | 2 | 13.8021 | 0.7063 | 0.0238 | 0.0179 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181303 | GTG #3,4,5 LEB - ROOF PLAN | Plan | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #3,4,5 LEB - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 71 | 2 | 13.8021 | 0.6931 | 0.0238 | 0.0178 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181304 | GTG #3,4,5 LEB - SIDE WALL ELEVATION | Elevation Drawing | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 12 | GTG #3,4,5 LEB side wall elevation is not targeted by the GT equipment/foundation/firefighting/tubing specific rules listed. | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 12 | 1 | 13.1061 | 0.6740 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181305 | GTG #3,4,5 LEB - MAIN SECTION | SECTION | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | SECTION for Local Electrical Building |  | GTG #3,4,5 LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3CF1213W42A10 | (GEN #31) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2008-06-27 | 2008-10-27 |  | installation | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 65 | 1 | 13.9075 | 0.7294 | 0.0244 | 0.0183 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2025-03-30 | 2025-04-29 | 2025-05-29 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181306 | GTG #3,4,5 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | Schedule | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Schedule for Gas Turbine Generator #3,4,5 |  | GTG#3,4,5LEB - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5335 | 0.4400 | 0.4400 | [6 empty] | FI | 3CF1200W24A10 | (GTG #31 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-27 | 2008-08-04 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 12 | 1 | 20.1493 | 0.6842 | 0.0303 | 0.0227 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181307 | GTG #3,4,5 LEB - STAIR PLAN & SECTION | PLAN & SECTION | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | PLAN & SECTION for Local Electrical Building |  | GTG #3,4,5 LEB - STAIR PLAN & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9994 | 0.9998 | 0.9998 | [6 empty] | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 67 | 2 | 13.8021 | 0.6865 | 0.0240 | 0.0180 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181351 | GTG #3,4,5 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #3,4,5 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 10 | 3 | 15.8173 | 0.7077 | 0.0302 | 0.0302 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181352 | GTG #3,4,5 LEB - GROUND FLOOR FRAMING PLAN | Plan | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #3,4,5 LEB - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9998 | 0.9999 | 0.9999 | [6 empty] | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 71 | 2 | 13.8021 | 0.7013 | 0.0238 | 0.0178 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181353 | GTG #3,4,5 LEB - ROOF FRAMING PLAN | Plan | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #3,4,5 LEB - ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | [6 empty] | FI | 3CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2008-03-18 | 2008-07-19 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 25 | 16 | 18.1313 | 0.6589 | 0.0249 | 0.0187 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181354 | GTG #3,4,5 LEB - LINE & ROW FRAMING ELEVATION | Elevation Drawing | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦gtg¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_ambig | generic_ok | 0.85 |  | 12 | GTG #3,4,5 LEB side wall elevation is not targeted by the GT equipment/foundation/firefighting/tubing specific rules listed. | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | civil_design | civil_design | match | electrical¦gtg | electrical | electrical¦gtg | query | gtg | match | true | false | 12 | 1 | 13.1061 | 0.6838 | 0.0303 | 0.0303 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181355 | GTG #3,4,5 LEB - STAIR FRAMING PLAN & ELEVATION | PLAN & ELEVATION | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | PLAN & ELEVATION for Local Electrical Building |  | GTG #3,4,5 LEB - STAIR FRAMING PLAN & ELEVATION | 1 | start+2M<=FC<=start+2M+2M | FC ∈ [start+60d, start+120d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 67 | 1 | 13.8021 | 0.6802 | 0.0243 | 0.0182 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-09-30 | 2024-10-30 | 2024-11-29 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181356 | GTG #3,4,5 LEB - GROUND FLOOR OPENING PLAN | Plan | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG #3,4,5 LEB - GROUND FLOOR OPENING PLAN | 1 | start+2M<=FC<=start+2M+2M | FC ∈ [start+60d, start+120d] | title | plan | plan | plan | plan | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9994 | 0.9998 | 0.9998 | [6 empty] | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 70 | 4 | 13.8021 | 0.6836 | 0.0233 | 0.0175 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-09-30 | 2024-10-30 | 2024-11-29 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181357 | GTG #3,4,5 LEB - FOUNDATION RE - BAR DETAIL | Detail Drawing | Gas Turbine Generator #3,4,5 |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | GTG #3,4,5 LEB - FOUNDATION RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9998 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 9 | 1 | 15.8173 | 0.6890 | 0.0309 | 0.0309 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181358 | GTG #3,4,5 LEB - COLUMN RE - BAR SCHEDULE | Schedule | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5758 | 0.4527 | 0.4527 | [6 empty] | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 22 | 4 | 11.9923 | 0.6741 | 0.0278 | 0.0209 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181359 | GTG #3,4,5 LEB - BEAM & GIRDER RE - BAR SCHEDULE | Schedule | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5758 | 0.4527 | 0.4527 | [6 empty] | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 22 | 5 | 11.9923 | 0.6776 | 0.0276 | 0.0207 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181360 | GTG #3,4,5 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | Detail Drawing | Gas Turbine Generator |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | GTG #3,4,5 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦gtg¦leb¦local | gtg¦leb | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 3 | 5 | 11.9919 | 0.6634 | 0.0313 | 0.0313 | hybrid | structured_preferred | electrical¦gtg | civil_design | 10 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181381 | GTG#3,4,5LEB - PLUMBING EQUIPMENT SCHEDULE | Schedule | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | GTG FOUNDATION BAR BENDING SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | gas¦generator¦gtg¦leb¦turbine | gtg | scoped | match | match | match | passed |  | 0.4000 | 0.5758 | 0.4527 | 0.4527 | [6 empty] | FA | 3CF1265W38A07 | (F/F GTG#31) Piping work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2008-07-14 | 2008-08-06 |  |  | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | fire_fighting¦gtg | match | true | false | 73 | 1 | 7.5224 | 0.6341 | 0.0239 | 0.0179 | hybrid | structured_no_phase | electrical¦gtg | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181382 | GTG#3,4,5LEB - PLUMBING SCHEMATIC DIAGRAM | Diagram | Gas Turbine Generator |  | Local Electrical Building |  | Diagram for GTG |  | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | gas¦generator¦gtg¦leb¦turbine | gtg¦leb | scoped | match | match | match | passed |  | 0.4000 | 0.5740 | 0.4522 | 0.4522 | [6 empty] | FI | 1CF1265W16A12.4 | (TCA Cooler) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | 2007-10-01 | 2007-11-30 | civil_design | civil_design | match | electrical¦gtg | gtg | electrical¦gtg | query | fgp¦gtg | match | true | false | 17 | 469 | 11.5572 | 0.5693 | 0.0149 | 0.0149 | hybrid | structured_cell_found_text_preferred | electrical¦gtg | system_design¦engineering | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181384 | GTG#3,4,5LEB - GROUND FLOOR PLUMBING PLAN | Plan | Gas Turbine Generator |  | Local Electrical Building |  | Plan for Local Electrical Building |  | GTG#3,4,5LEB - GROUND FLOOR PLUMBING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦gas¦generator¦gtg¦leb¦local¦turbine | gtg | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  | civil_design | query_unknown | electrical¦gtg | gtg | electrical¦gtg | query | gtg | match | true | false | 152 | 5 | 7.2702 | 0.6675 | 0.0201 | 0.0151 | hybrid | structured_no_phase | electrical¦gtg | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0BAT-181800 | ROOF FOR STG TR - CALCULATION | Calculation sheet | GSUT/UAT Transformer |  |  |  | Calculation sheet for GSUT/UAT Transformer |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | generator¦gsut¦steam¦stg¦transformer¦turbine¦uat | stg | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | civil_design | civil_design | match | gsut_uat¦stg | stg | gsut_uat¦stg | query | electrical¦gsut_uat¦stg | match | true | false | 1 | 18 | 13.8112 | 0.6047 | 0.0292 | 0.0292 | hybrid | structured_preferred | gsut_uat¦stg | civil_design | 10 |  |  |  | 2024-11-08 | 2024-12-08 | 2025-01-07 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P6BAT-181811 | ROOF FOR STG TR - PLAN, SECTION, ELEVATION | PLAN, SECTION, ELEVATION | GSUT/UAT Transformer |  |  |  | PLAN, SECTION, ELEVATION for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.7143 | 0.8199 | 0.7460 | 0.7460 | [6 empty] | FA | 1CF6500W70A09 | (STG #10 & UST Shelter) Installation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-08-10 | 2008-10-08 |  | installation | query_unknown | gsut_uat¦stg | stg | gsut_uat¦stg | query | gsut_uat¦stg | match | true | false | 4 | 44 | 15.0919 | 0.6116 | 0.0252 | 0.0189 | hybrid | structured_no_phase | gsut_uat¦stg |  |  | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | 2025-06-12 | 2025-07-12 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P6BAT-181812 | ROOF FOR STG TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | Plan | GSUT/UAT Transformer |  |  |  | Plan for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6327 | 0.6098 | 0.6098 | [6 empty] | FA | 2CF6500W70A09 | (STG #20 & UST Shelter) Installation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2008-08-29 | 2008-10-27 |  | installation | query_unknown | gsut_uat¦stg | stg | gsut_uat¦stg | query | gsut_uat¦stg | match | true | false | 12 | 36 | 15.0919 | 0.6027 | 0.0243 | 0.0182 | hybrid | structured_no_phase | gsut_uat¦stg |  |  | 2025-04-17 | 2025-05-02 | 2025-05-17 | 2025-06-01 | 2025-07-01 | 2025-07-31 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P6BAT-181813 | ROOF FOR STG TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | Elevation Drawing | GSUT/UAT Transformer |  |  |  | Elevation Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6620 | 0.6186 | 0.6186 | [6 empty] | FA | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | gsut_uat¦stg | stg | gsut_uat¦stg | query | electrical¦gsut_uat¦gtg | match | true | false | 16 | 6 | 10.3003 | 0.6548 | 0.0283 | 0.0283 | hybrid | structured_preferred | gsut_uat¦stg | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UGD-181900 | WATER TREATMENT BUILDING - CALCULATION | Calculation sheet |  | Water Treatment System | Water Treatment Building |  | Calculation sheet for Water Treatment System | Water Treatment System | Calculation sheet for Water Treatment System | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.9782 | 0.9934 | 0.9934 | [6 empty] | FA | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 6 | 3 | 23.0521 | 0.6105 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181901 | WATER TREATMENT BUILDING - GROUND FLOOR PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.6530 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181902 | WATER TREATMENT BUILDING - 1ST FLOOR PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.6425 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181903 | WATER TREATMENT BUILDING - ROOF FLOOR PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.6280 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181904 | WATER TREATMENT BUILDING - ELEVATION | Elevation Drawing |  | Water Treatment System | Water Treatment Building |  | Elevation Drawing for Water Treatment Building | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6606 | 0.5982 | 0.5982 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 4 | 23.0521 | 0.6003 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181905 | WATER TREATMENT BUILDING - SECTION | SECTION |  | Water Treatment System | Water Treatment Building |  | SECTION for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8821 | 0.9646 | 0.9646 | [6 empty] | FI | 0CF5534W74A08 | (DWP BLDG) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-05-21 | 2008-08-05 |  | commissioning | query_unknown | wts | wts | wts | query | wts | match | true | false | 17 | 6 | 22.8598 | 0.6628 | 0.0281 | 0.0211 | hybrid | structured_no_phase | wts | [5 empty] | 2025-02-21 | 2025-03-23 | 2025-04-22 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181906 | WATER TREATMENT BUILDING - INTERIOR FINISH & DOOR SCHEDULE | Schedule |  | Water Treatment System | Water Treatment Building |  | Schedule for Water Treatment System | Water Treatment System | Cable Schdule(inculde drum schedule) | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7315 | 0.5695 | 0.5695 | [6 empty] | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 3 | 1 | 29.1895 | 0.6648 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181908 | WATER TREATMENT BUILDING - WALL SECTION DETAIL | Detail Drawing |  | Water Treatment System | Water Treatment Building |  | Detail Drawing for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7860 | 0.7025 | 0.7025 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 2 | 23.0521 | 0.6110 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181909 | WATER TREATMENT BUILDING - TOILET ENLARGED PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | true | false | 14 | 1 | 23.4580 | 0.6030 | 0.0299 | 0.0224 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181910 | WATER TREATMENT BUILDING - WALL OPENING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 2 | 23.0521 | 0.5990 | 0.0295 | 0.0221 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181911 | WATER TREATMENT BUILDING - CEILING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 2 | 17 | 25.5501 | 0.5834 | 0.0291 | 0.0218 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181912 | WATER TREATMENT BUILDING - STAIR ENLARGED PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | true | false | 14 | 1 | 23.4580 | 0.6309 | 0.0299 | 0.0224 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181913 | WATER TREATMENT BUILDING - STAIR ENLARGED SECTION | SECTION |  | Water Treatment System | Water Treatment Building |  | SECTION for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8821 | 0.9646 | 0.9646 | [6 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | true | false | 12 | 1 | 23.4580 | 0.6407 | 0.0303 | 0.0227 | hybrid | structured_no_phase | wts | [5 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181914 | WATER TREATMENT BUILDING - ARCHITECTURAL MISC. |  |  | Water Treatment System | Water Treatment Building |  | for Water Treatment System | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - ARCHITECTURAL MISC. | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | other | other | water_treatment_building_architectural_misc | water_treatment_building_architectural_misc | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.4000 | 0.5542 | 0.4463 | 0.4463 | [6 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | true | false | 12 | 1 | 23.4580 | 0.6620 | 0.0303 | 0.0227 | hybrid | structured_no_phase | wts | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181951 | WATER TREATMENT BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 10 | 2 | 25.1632 | 0.6576 | 0.0304 | 0.0304 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181952 | WATER TREATMENT BUILDING - GROUND FLOOR FRAMING |  |  | Water Treatment System | Water Treatment Building |  | for Water Treatment System | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - GROUND FLOOR FRAMING | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | water_treatment_building_ground_floor_framing | water_treatment_building_ground_floor_framing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.3333 | 0.5147 | 0.3877 | 0.3877 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 13 | 1 | 23.0521 | 0.6417 | 0.0301 | 0.0226 | hybrid | structured_no_phase | wts | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181953 | WATER TREATMENT BUILDING - 1ST FLOOR FRAMING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.6183 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181954 | WATER TREATMENT BUILDING - ROOF FLOOR FRAMING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.5931 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181955 | WATER TREATMENT BUILDING - FRAMING ELEVATION | Elevation Drawing |  | Water Treatment System | Water Treatment Building |  | Elevation Drawing for Water Treatment Building | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6606 | 0.5982 | 0.5982 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 2 | 23.0521 | 0.6066 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181956 | WATER TREATMENT BUILDING - STAIR FRAMING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | true | false | 14 | 1 | 23.4580 | 0.6407 | 0.0299 | 0.0224 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181957 | WATER TREATMENT BUILDING - STAIR FRAMING SECTION | SECTION |  | Water Treatment System | Water Treatment Building |  | SECTION for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 1.0000 | 0.8821 | 0.9646 | 0.9646 | [6 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | true | false | 12 | 1 | 23.4580 | 0.6458 | 0.0303 | 0.0227 | hybrid | structured_no_phase | wts | [5 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181958 | WATER TREATMENT BUILDING - FOUNDATION REBAR DETAIL | Detail Drawing |  | Water Treatment System | Water Treatment Building |  | Detail Drawing for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7860 | 0.7025 | 0.7025 | [6 empty] | FI | 0EF4035W16A02.2 | (WWT LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 5 | 27.3810 | 0.5977 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181959 | WATER TREATMENT BUILDING - COLUMN REBAR DETAIL | Detail Drawing |  | Water Treatment System | Water Treatment Building |  | Detail Drawing for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7860 | 0.7025 | 0.7025 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 2 | 23.0521 | 0.5839 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181960 | WATER TREATMENT BUILDING - GIRDER & BEAM REBAR SCHEDULE | Schedule |  | Water Treatment System | Water Treatment Building |  | Schedule for Water Treatment System | Water Treatment System | Cable Schdule(inculde drum schedule) | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7315 | 0.5695 | 0.5695 | [6 empty] | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 29.1895 | 0.6548 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181961 | WATER TREATMENT BUILDING - SLAB REBAR DETAIL | Detail Drawing |  | Water Treatment System | Water Treatment Building |  | Detail Drawing for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7860 | 0.7025 | 0.7025 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 2 | 23.0521 | 0.5822 | 0.0315 | 0.0315 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181962 | WATER TREATMENT BUILDING - EQUIPMENT FOUNDTAION ARRANGEMENT PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 8 | 3 | 23.0521 | 0.6571 | 0.0306 | 0.0306 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181963 | WATER TREATMENT BUILDING - EMBEDDED PLATE & SLEEVE PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 16 | 8 | 23.0521 | 0.5781 | 0.0279 | 0.0209 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181964 | WATER TREATMENT BUILDING - MISC. REBAR DETAIL | Detail Drawing |  | Water Treatment System | Water Treatment Building |  | Detail Drawing for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7860 | 0.7025 | 0.7025 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 5 | 4 | 23.0521 | 0.5845 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181965 | WATER TREATMENT BUILDING - ROOF COLUMN LOCATION PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.6109 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181966 | WATER TREATMENT BUILDING - ENLARGED ROOF FRAMING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.5803 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181967 | WATER TREATMENT BUILDING - GIRT LINE & ROW ELEVATION | Elevation Drawing |  | Water Treatment System | Water Treatment Building |  | Elevation Drawing for Water Treatment Building | Water Treatment System | Piping Arrangement DraWing for Water Treatment System | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5714 | 0.6606 | 0.5982 | 0.5982 | [6 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 8 | 2 | 22.2142 | 0.5945 | 0.0308 | 0.0308 | hybrid | structured_preferred | wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181968 | WATER TREATMENT BUILDING - STEEL CONNECTION DETAIL | Detail Drawing |  | Water Treatment System | Water Treatment Building |  | Detail Drawing for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - WALL SECTION DETAIL | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.6667 | 0.7860 | 0.7025 | 0.7025 | [6 empty] | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 6 | 3 | 23.0521 | 0.5998 | 0.0310 | 0.0310 | hybrid | structured_preferred | wts | civil_design | 10 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181981 | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | Schedule |  | Water Treatment System | Water Treatment Building |  | Schedule for Water Treatment System | Water Treatment System | Cable Schdule(inculde drum schedule) | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | schedule | schedule | schedule | schedule | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.5000 | 0.7315 | 0.5695 | 0.5695 | [6 empty] | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | procurement | procurement | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 29.1895 | 0.7085 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | procurement |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181982 | WATER TREATMENT BUILDING - PLUMBING SCHEMATIC DIAGRAM | Diagram |  | Water Treatment System | Water Treatment Building |  | Diagram for Water Treatment System | Water Treatment System | Control Schematic Diagram for Water Treatment System | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.7143 | 0.8373 | 0.7512 | 0.7512 | [6 empty] | FI | 0EF3010W16A01 | (WTS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-01-09 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 38 | 6 | 21.1119 | 0.6624 | 0.0254 | 0.0254 | hybrid | structured_cell_found_text_preferred | wts | system_design¦engineering |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181983 | WATER TREATMENT BUILDING - GROUND FLOOR PLUMBING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.6390 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181984 | WATER TREATMENT BUILDING - 1ST FLOOR PLUMBING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 15 | 1 | 23.0521 | 0.6300 | 0.0297 | 0.0223 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181985 | WATER TREATMENT BUILDING - ROOF PLUMBING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  | civil_design | query_unknown | wts | wts | wts | query | wts | match | true | false | 16 | 1 | 23.0521 | 0.6044 | 0.0296 | 0.0222 | hybrid | structured_no_phase | wts | [5 empty] | 2024-11-29 | 2024-12-29 | 2025-01-28 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181986 | WATER TREATMENT BUILDING - ENLARGED PLUMBING PLAN | Plan |  | Water Treatment System | Water Treatment Building |  | Plan for Water Treatment Building | WATER TREATMENT BUILDING | WATER TREATMENT BUILDING - CEILING PLAN | 1 | start+3M<=FC<=start+3M+2M | FC ∈ [start+90d, start+150d] | rule_query | plan | plan | plan | plan | treatment¦water¦wts | wts | scoped | match | match | match | passed |  | 0.8000 | 0.7457 | 0.7837 | 0.7837 | [6 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown | wts | wts | wts | query | wts | match | true | false | 14 | 2 | 23.4580 | 0.5981 | 0.0296 | 0.0222 | hybrid | structured_no_phase | wts | [5 empty] | 2025-01-31 | 2025-03-02 | 2025-04-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UST-182000 | WORKSHOP & STORAGE BUILDING - CALCULATION | Calculation sheet |  |  | Workshop & Storage Building |  | Calculation sheet for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8265 | 0.9479 | 0.9479 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 31 | 2 | 9.7017 | 0.4877 | 0.0271 | 0.0203 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182001 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 4 | 2 | 13.3926 | 0.4887 | 0.0318 | 0.0179 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182002 | WORKSHOP & STORAGE BUILDING - ROOF PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 5 | 1 | 13.7004 | 0.4960 | 0.0318 | 0.0179 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182003 | WORKSHOP & STORAGE BUILDING - ELEVATION | Elevation Drawing |  |  | Workshop & Storage Building |  | Elevation Drawing for Workshop & Storage Building | Mechanical Workshop Equipment | Equipment Arrangement draWing for Workshop Equipment | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | drawing | drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5529 | 0.5159 | 0.5159 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 50 | 3 | 9.7017 | 0.5349 | 0.0250 | 0.0187 | hybrid | structured_no_system |  | civil_design |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182004 | WORKSHOP & STORAGE BUILDING - SECTION | SECTION |  |  | Workshop & Storage Building |  | SECTION for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8885 | 0.9666 | 0.9666 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 3 | 13.3926 | 0.4926 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182005 | WORKSHOP & STORAGE BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | Schedule |  |  | Workshop & Storage Building |  | Schedule for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - INTERIOR finish, DOOR & WINDOW SCHEDULE | 1 | start+5M<=FC<=start+5M+2M | FC ∈ [start+150d, start+210d] | title | schedule | schedule | schedule | schedule | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9687 | 0.9906 | 0.9906 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 1 | 19.8798 | 0.5022 | 0.0325 | 0.0183 | hybrid | structured_no_system | [6 empty] | 2026-05-29 | 2026-06-28 | 2026-07-28 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182006 | WORKSHOP & STORAGE BUILDING - ENLARGED PLAN, CEILING PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 4 | 4 | 13.3926 | 0.4675 | 0.0312 | 0.0176 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182051 | WORKSHOP & STORAGE BUILDING - FOUNDATION PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0CF5560W16A03 | (M&E WORKSHOP BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-04-10 | 2008-06-06 | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 10 | 75 | 12.0359 | 0.4594 | 0.0217 | 0.0163 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2025-01-11 | 2025-02-10 | 2025-03-12 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182052 | WORKSHOP & STORAGE BUILDING - COLUMN LOCATION PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 4 | 16 | 13.3926 | 0.4643 | 0.0288 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182053 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR FRAMING PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 4 | 19 | 13.3926 | 0.4509 | 0.0283 | 0.0159 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182054 | WORKSHOP & STORAGE BUILDING - ROOF FRAMING PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 4 | 1 | 13.7004 | 0.4474 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182055 | WORKSHOP & STORAGE BUILDING - STEEL ROOF FRAMING PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 8 | 1 | 13.7004 | 0.4756 | 0.0311 | 0.0175 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182056 | WORKSHOP & STORAGE BUILDING - FRAMING ELEVATION | Drawing |  |  | Workshop & Storage Building |  | Drawing for Workshop & Storage Building | Mechanical Workshop Equipment | Equipment Arrangement draWing for Workshop Equipment | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | drawing | drawing | drawing | drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6046 | 0.5314 | 0.5314 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 50 | 4 | 9.7017 | 0.5246 | 0.0247 | 0.0185 | hybrid | structured_no_system |  | civil_design |  | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182058 | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | Drawing |  |  | Workshop & Storage Building |  | Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9672 | 0.9902 | 0.9902 | g_safe | [5 empty] | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | true | false | 3 | 139 | 13.0440 | 0.3994 | 0.0209 | 0.0157 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-04 | 2024-08-03 | 2024-09-02 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182059 | WORKSHOP & STORAGE BUILDING - RC COLUMN DETAIL | Drawing |  |  | Workshop & Storage Building |  | Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - RC COLUMN DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9747 | 0.9924 | 0.9924 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 33 | 3 | 9.7017 | 0.4591 | 0.0266 | 0.0200 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182060 | WORKSHOP & STORAGE BUILDING - SLAB DETAIL | Drawing |  |  | Workshop & Storage Building |  | Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - SLAB DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9708 | 0.9912 | 0.9912 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 37 | 7 | 9.7017 | 0.4067 | 0.0252 | 0.0189 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182061 | WORKSHOP & STORAGE BUILDING - CRANE GIRDER & MISC. DETAIL | Drawing | Crane & Hoist |  | Workshop & Storage Building |  | Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CRANE GIRDER & MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9804 | 0.9941 | 0.9941 | g_safe | [5 empty] | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | crane_hoist | crane_hoist | crane_hoist | query |  | activity_unscoped | true | true | 101 | 31 | 4.0527 | 0.5059 | 0.0172 | 0.0103 | hybrid | structured_phase_gap | crane_hoist | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.44 | needs_review | activity_scope_status=activity_unscoped;activity_generic;activity_rrf_low;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182062 | WORKSHOP & STORAGE BUILDING - STEEL COLUMN & BASE PLATE DETAIL | Drawing |  |  | Workshop & Storage Building |  | Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - STEEL COLUMN & BASE PLATE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9767 | 0.9930 | 0.9930 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 33 | 1 | 9.7017 | 0.4556 | 0.0271 | 0.0204 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182063 | WORKSHOP & STORAGE BUILDING - CONNECTION DETAIL | Drawing |  |  | Workshop & Storage Building |  | Drawing for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - CONNECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9706 | 0.9912 | 0.9912 | g_safe | [5 empty] | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 33 | 1 | 9.7017 | 0.4295 | 0.0271 | 0.0204 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182081 | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | Schedule |  |  | Workshop & Storage Building |  | Schedule for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9749 | 0.9925 | 0.9925 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 2 | 2 | 17.0739 | 0.5542 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182082 | WORKSHOP & STORAGE BUILDING - PLUMBING SCHEMATIC DIAGRAM | Diagram |  |  | Workshop & Storage Building |  | Diagram for Workshop & Storage Building |  | PLUMBING SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7957 | 0.9387 | 0.6571 | g_safe | [5 empty] | FA | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  | civil_design | civil_design | match |  |  |  |  | electrical | query_unscoped | true | false | 50 | 4 | 9.7017 | 0.5324 | 0.0247 | 0.0185 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-07-17 | 2024-08-01 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182083 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLUMBING PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 4 | 26 | 13.3926 | 0.4893 | 0.0273 | 0.0153 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182084 | WORKSHOP & STORAGE BUILDING - ROOF PLUMBING PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 4 | 13 | 13.7004 | 0.4683 | 0.0293 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182085 | WORKSHOP & STORAGE BUILDING - ENLARGED PLUMBING PLAN | Plan |  |  | Workshop & Storage Building |  | Plan for Workshop & Storage Building | WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | storage¦workshop |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7783 | 0.7935 | 0.7935 | g_safe | [5 empty] | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  | query_unknown |  |  |  |  | electrical | query_unscoped | true | false | 4 | 13 | 13.3926 | 0.4661 | 0.0293 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-10-01 | 2025-10-31 | 2025-11-30 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULA-182151 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION PLAN | Plan |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | civil_design | civil_design | match |  |  |  |  | stg | query_unscoped | true | false | 3 | 40 | 11.0757 | 0.5360 | 0.0259 | 0.0194 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182152 | DEAERATOR SUPPORT STRUCTURE - COLUMN LOCATION PLAN | Plan |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - COLUMN LOCATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  | installation | query_unknown |  |  |  |  | hrsg | query_unscoped | false | false | 14 | 40 | 6.0176 | 0.5235 | 0.0235 | 0.0132 | hybrid | structured_no_system | [6 empty] | 2025-02-19 | 2025-03-21 | 2025-04-20 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182153 | DEAERATOR SUPPORT STRUCTURE - GROUND FLOOR FRAMING PLAN | Plan |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  |  | civil_design | query_unknown |  |  |  |  | wts | query_unscoped | false | false | 409 | 1 |  | 0.5438 | 0.0185 | 0.0104 | hybrid | structured_no_system | [6 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182154 | DEAERATOR SUPPORT STRUCTURE - DEAERATOR FLOOR FRAMING PLAN | Plan |  |  |  |  | Plan |  | DEAERATOR SUPPORT STRUCTURE - DEAERATOR FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  | installation | query_unknown |  |  |  |  | hrsg | query_unscoped | false | false | 20 | 73 | 6.0176 | 0.5055 | 0.0200 | 0.0113 | hybrid | structured_no_system | [6 empty] | 2025-02-19 | 2025-03-21 | 2025-04-20 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182155 | DEAERATOR SUPPORT STRUCTURE - FRAMING ELEVATION | Drawing |  |  |  |  | Drawing |  | Support DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.3600 | 0.3413 | 0.3413 | [6 empty] | FA | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | civil_design | civil_design | match |  |  |  |  | compressed_air | query_unscoped | false | false | 513 | 127 | 4.7662 | 0.5179 | 0.0071 | 0.0053 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:query_unscoped;activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182157 | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | Drawing |  |  |  |  | Drawing |  | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | false | 258 | 1 | 2.1802 | 0.5834 | 0.0195 | 0.0147 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182160 | DEAERATOR SUPPORT STRUCTURE - BASE PLATE DETAIL | Drawing |  |  |  |  | Drawing |  | DEAERATOR SUPPORT STRUCTURE - BASE PLATE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match |  |  |  |  | condensate | query_unscoped | false | false | 2244 | 1 |  | 0.5396 | 0.0168 | 0.0126 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULA-182190 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION CALCULATION | Calculation sheet |  |  |  |  | Calculation sheet |  | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 0EF1600W14A10 | HRSG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-06-15 | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | true | false | 3 | 38 | 11.0107 | 0.5053 | 0.0261 | 0.0196 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULA-182191 | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | Calculation sheet |  |  |  |  | Calculation sheet |  | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-08-06 |  | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | false | false | 3859 | 1 |  | 0.5352 | 0.0166 | 0.0125 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-08 | 2024-06-07 | 2024-07-07 | fi_complete | 0.90 |  | false | false | 0.54 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0USG-182700 | FIRE WATER PUMP HOUSE - CALCULATION | Calculation sheet |  | Fire Fighting System | Fire Water Pump House |  | Calculation sheet for Fire Fighting System | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | fighting¦fire¦fire_protection¦pump | fire_protection | scoped | match | match | match | passed |  | 0.6667 | 0.6973 | 0.6758 | 0.6758 | [6 empty] | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 2 | 27.4718 | 0.6191 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182701 | FIRE WATER PUMP HOUSE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | PLAN, SCHEDULE |  | Fire Fighting System | Fire Water Pump House |  | PLAN, SCHEDULE for Fire Fighting System | Fire Fighting System | WASTE WATER DRAINAGE MANHOLE SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | fighting¦fire¦fire_protection¦pump | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6759 | 0.5528 | 0.5528 | [6 empty] | FA | 0CF4500W24A11 | (Fire WTR Pump Shelter) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-20 | 2008-07-16 |  |  | query_unknown | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 33.8190 | 0.6770 | 0.0325 | 0.0244 | hybrid | structured_no_phase | fire_fighting |  |  | 2025-01-06 | 2025-01-21 | 2025-02-05 | 2025-02-20 | 2025-03-22 | 2025-04-21 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182702 | FIRE WATER PUMP HOUSE - ROOF PLAN | Plan |  | Fire Fighting System | Fire Water Pump House |  | Plan for Fire Water Pump House | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦fire_protection¦house¦pump¦water | fire_protection¦pump | scoped | match | match | match | passed |  | 0.8333 | 0.8318 | 0.8329 | 0.8329 | [6 empty] | FI | 0CF4500W38A06.0 | (Fire WTR Pump Shelter) Installation F/F pump | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-31 | 2008-07-02 |  | installation | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 7 | 27.9791 | 0.6229 | 0.0313 | 0.0235 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182703 | FIRE WATER PUMP HOUSE - ELEVATION | Elevation Drawing |  | Fire Fighting System | Fire Water Pump House |  | Elevation Drawing for Fire Water Pump House |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | fire¦fire_protection¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.6667 | 0.5989 | 0.6463 | 0.4524 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 2 | 27.4718 | 0.6475 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182704 | FIRE WATER PUMP HOUSE - MAIN SECTION | MAIN SECTION |  | Fire Fighting System | Fire Water Pump House |  | MAIN SECTION for Fire Water Pump House | Fire Water Pump House | FIRE WATER PUMP HOUSE - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | fire¦fire_protection¦house¦pump¦water | fire_protection¦pump | scoped | match | match | match | passed |  | 1.0000 | 0.8957 | 0.9687 | 0.9687 | [6 empty] | FI | 0SF4500W62A12 | (Fire WTR Pump) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-07-17 | 2008-07-18 |  |  | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 4 | 27.6246 | 0.6392 | 0.0312 | 0.0234 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2025-04-19 | 2025-05-19 | 2025-06-18 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182751 | FIRE WATER PUMP HOUSE - FOUNDATION, COLUMN ARRAGEMENT PLAN | Plan |  | Fire Fighting System | Fire Water Pump House |  | Plan for Fire Water Pump House | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦fire_protection¦house¦pump¦water | fire_protection¦pump | scoped | match | match | match | passed |  | 0.8333 | 0.8318 | 0.8329 | 0.8329 | [6 empty] | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.4870 | 0.6715 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182752 | FIRE WATER PUMP HOUSE - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | Plan |  | Fire Fighting System | Fire Water Pump House |  | Plan for Fire Water Pump House | Fire Water Pump House | FIRE WATER PUMP HOUSE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | fire¦fire_protection¦house¦pump¦water | fire_protection¦pump | scoped | match | match | match | passed |  | 0.8333 | 0.8318 | 0.8329 | 0.8329 | [6 empty] | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 8 | 2 | 27.4718 | 0.6637 | 0.0308 | 0.0231 | hybrid | structured_no_phase | fire_fighting | [5 empty] | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182753 | FIRE WATER PUMP HOUSE - FRAMING ELEVATION | Elevation Drawing |  | Fire Fighting System | Fire Water Pump House |  | Elevation Drawing for Fire Water Pump House |  | PUMP ARRANGEMENT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | fire¦fire_protection¦house¦pump¦water | pump | scoped | match | match | match | passed |  | 0.6667 | 0.5989 | 0.6463 | 0.4524 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 2 | 27.4718 | 0.6614 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0USG-182754 | FIRE WATER PUMP HOUSE - FOUNDATION REBAR SCHEDULE, SLAB REBAR DETAIL | SCHEDULE, DETAIL |  | Fire Fighting System | Fire Water Pump House |  | SCHEDULE, DETAIL for Fire Fighting System | Fire Fighting System | WASTE WATER DRAINAGE MANHOLE SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | fighting¦fire¦fire_protection¦pump | drainage¦fire_protection | scoped | match | match | match | passed |  | 0.5000 | 0.6999 | 0.5600 | 0.5600 | [6 empty] | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | civil_design | civil_design | match | fire_fighting | fire_fighting¦wts | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 2 | 29.4874 | 0.6446 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0USG-182755 | FIRE WATER PUMP HOUSE - COLUMN, GIRDER, BEAM SHEDULE |  |  | Fire Fighting System | Fire Water Pump House |  | for Fire Fighting System | Fire Water Pump House | FIRE WATER PUMP HOUSE - COLUMN, GIRDER, BEAM SHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | fire_water_pump_house_column_girder_beam_shedule | fire_water_pump_house_column_girder_beam_shedule | fighting¦fire¦fire_protection¦pump | fire_protection¦pump | scoped | match | match | match | passed |  | 0.1250 | 0.4932 | 0.2355 | 0.2355 | [6 empty] | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  | civil_design | query_unknown | fire_fighting | fire_fighting | fire_fighting | query | fire_fighting¦hvac | match | true | false | 6 | 2 | 27.4718 | 0.6454 | 0.0313 | 0.0235 | hybrid | structured_no_phase | fire_fighting | [8 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTF-182800 | AIR COMPRESSOR SHELTER - CALCULATION SHEET | CALCULATION SHEET |  | Compressed Air System | Air Compressor Shelter |  | CALCULATION SHEET for Compressed Air System | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | air¦compressed |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9691 | 0.9907 | 0.9907 | g_safe | [5 empty] | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 4 | 23.8545 | 0.6363 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182801 | AIR COMPRESSOR SHELTER - GROUND FLOOR PLAN | Plan |  | Compressed Air System | Air Compressor Shelter |  | Plan for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7958 | 0.7987 | 0.7987 | g_safe | [5 empty] | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 3 | 2 | 23.8545 | 0.6752 | 0.0320 | 0.0240 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182802 | AIR COMPRESSOR SHELTER - ROOF PLAN | Plan |  | Compressed Air System | Air Compressor Shelter |  | Plan for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7958 | 0.7987 | 0.7987 | g_safe | [5 empty] | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 4 | 2 | 23.8545 | 0.6734 | 0.0318 | 0.0238 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182803 | AIR COMPRESSOR SHELTER - SIDE ELEVATION | Elevation Drawing |  | Compressed Air System | Air Compressor Shelter |  | Elevation Drawing for Air Compressor Shelter | Air Compressor | Piping Arrangement DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6258 | 0.6077 | 0.6077 | g_safe | [5 empty] | FA | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 3 | 2 | 23.8545 | 0.6512 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182804 | AIR COMPRESSOR SHELTER - MAIN SECTION | MAIN SECTION |  | Compressed Air System | Air Compressor Shelter |  | MAIN SECTION for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8847 | 0.9654 | 0.9654 | g_safe | [5 empty] | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 4 | 23.8545 | 0.6721 | 0.0320 | 0.0240 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182851 | AIR COMPRESSOR SHELTER - FOUNDATION ARRANGEMENT PLAN | Plan |  | Compressed Air System | Air Compressor Shelter |  | Plan for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7958 | 0.7987 | 0.7987 | g_safe | [5 empty] | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 1 | 25.9655 | 0.7140 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182852 | AIR COMPRESSOR SHELTER - COLUMN ARRANGEMENT PLAN | Plan |  | Compressed Air System | Air Compressor Shelter |  | Plan for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7958 | 0.7987 | 0.7987 | g_safe | [5 empty] | FI | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 1 | 1 | 26.5478 | 0.6746 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182853 | AIR COMPRESSOR SHELTER - GROUND FLOOR FRAMING PLAN | Plan |  | Compressed Air System | Air Compressor Shelter |  | Plan for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7958 | 0.7987 | 0.7987 | g_safe | [5 empty] | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 3 | 1 | 23.8545 | 0.6563 | 0.0323 | 0.0242 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182854 | AIR COMPRESSOR SHELTER - ROOF FRAMING PLAN | Plan |  | Compressed Air System | Air Compressor Shelter |  | Plan for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7958 | 0.7987 | 0.7987 | g_safe | [5 empty] | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 4 | 1 | 23.8545 | 0.6602 | 0.0320 | 0.0240 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182855 | AIR COMPRESSOR SHELTER - LINE FRAMING ELEVATION | Elevation Drawing |  | Compressed Air System | Air Compressor Shelter |  | Elevation Drawing for Air Compressor Shelter | Air Compressor | Piping Arrangement DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6258 | 0.6077 | 0.6077 | g_safe | [5 empty] | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 2 | 3 | 23.8545 | 0.6597 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182856 | AIR COMPRESSOR SHELTER - ROW FRAMING ELEVATION | Elevation Drawing |  | Compressed Air System | Air Compressor Shelter |  | Elevation Drawing for Air Compressor Shelter | Air Compressor | Piping Arrangement DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | drawing | drawing | drawing | drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6258 | 0.6077 | 0.6077 | g_safe | [5 empty] | FA | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 | civil_design | civil_design | match | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 3 | 2 | 23.8545 | 0.6525 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | compressed_air | civil_design |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTF-182857 | AIR COMPRESSOR SHELTER - REBAR DETAIL | REBAR DETAIL |  | Compressed Air System | Air Compressor Shelter |  | REBAR DETAIL for Air Compressor Shelter | AIR COMPRESSOR | AIR COMPRESSOR SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | air¦compressor¦shelter |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8956 | 0.9687 | 0.9687 | g_safe | [5 empty] | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  | civil_design | query_unknown | compressed_air | compressed_air | compressed_air | query | compressed_air | match | true | false | 3 | 2 | 23.8545 | 0.6814 | 0.0320 | 0.0240 | hybrid | structured_no_phase | compressed_air | [5 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYC-182900 | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | CALCULATION SHEET |  |  | Administration & Social Building |  | CALCULATION SHEET for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9215 | 0.9764 | 0.9764 | g_safe | [5 empty] | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 4 | 15.1429 | 0.5206 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182901 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 11 | 7 | 14.7383 | 0.5419 | 0.0290 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182902 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 7 | 14.7383 | 0.5201 | 0.0292 | 0.0164 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182903 | ADMINISTRATION & SOCIAL BUILDING - SIDE ELEVATION | Elevation Drawing |  |  | Administration & Social Building |  | Elevation Drawing for Administration & Social Building |  | DraWing Building DraWing_Arch | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5441 | 0.6299 | 0.4409 | g_safe | [5 empty] | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 3 | 15.1429 | 0.5330 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182904 | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | SECTION |  |  | Administration & Social Building |  | SECTION for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8533 | 0.8160 | 0.8160 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 9 | 7 | 14.7383 | 0.4443 | 0.0294 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182905 | ADMINISTRATION & SOCIAL BUILDING - INTERIOR FINISH & DOOR / WINDOW SCHEDULE | Schedule |  |  | Administration & Social Building |  | Schedule for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - INTERIOR finish & DOOR / WINDOW SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9667 | 0.9900 | 0.9900 | g_safe | [5 empty] | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 8 | 5 | 14.7387 | 0.4860 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182906 | ADMINISTRATION & SOCIAL BUILDING - WALL SECTION | SECTION |  |  | Administration & Social Building |  | SECTION for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8533 | 0.8160 | 0.8160 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 9 | 7 | 14.7383 | 0.4642 | 0.0294 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182907 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED REST ROOM PLAN & ELEVATION | PLAN & ELEVATION |  |  | Administration & Social Building |  | PLAN & ELEVATION for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.8385 | 0.8115 | 0.8115 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 11 | 10 | 14.7383 | 0.4529 | 0.0284 | 0.0160 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182908 | ADMINISTRATION & SOCIAL BUILDING - CEILING PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 6 | 14.7383 | 0.5398 | 0.0294 | 0.0166 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182951 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 18 | 14 | 7.5640 | 0.4889 | 0.0263 | 0.0198 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182952 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR FRAMING PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 11 | 7 | 14.7383 | 0.5293 | 0.0290 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182953 | ADMINISTRATION & SOCIAL BUILDING - ROOF FRAMING PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 10 | 7 | 14.7383 | 0.4820 | 0.0292 | 0.0164 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182954 | ADMINISTRATION & SOCIAL BUILDING - LINE FRAMING ELEVATION | Elevation Drawing |  |  | Administration & Social Building |  | Elevation Drawing for Administration & Social Building |  | DraWing Building DraWing_Arch | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5441 | 0.6299 | 0.4409 | g_safe | [5 empty] | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 3 | 15.1429 | 0.5312 | 0.0320 | 0.0192 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182955 | ADMINISTRATION & SOCIAL BUILDING - ROW FRAMING ELEVATION | Elevation Drawing |  |  | Administration & Social Building |  | Elevation Drawing for Administration & Social Building |  | DraWing Building DraWing_Arch | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5441 | 0.6299 | 0.4409 | g_safe | [5 empty] | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 2 | 15.1429 | 0.5190 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182956 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN REBAR DETAIL | REBAR DETAIL |  |  | Administration & Social Building |  | REBAR DETAIL for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8599 | 0.7580 | 0.7580 | g_safe | [5 empty] | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 17.5175 | 0.5243 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYC-182957 | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | REBAR DETAIL |  |  | Administration & Social Building |  | REBAR DETAIL for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8599 | 0.7580 | 0.7580 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 10 | 19 | 14.7383 | 0.4482 | 0.0269 | 0.0152 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYC-182958 | ADMINISTRATION & SOCIAL BUILDING - SLAB & MISC REBAR DETAIL | REBAR DETAIL |  |  | Administration & Social Building |  | REBAR DETAIL for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.7143 | 0.8599 | 0.7580 | 0.7580 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 10 | 9 | 14.7383 | 0.4553 | 0.0288 | 0.0162 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182981 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | Schedule |  |  | Administration & Social Building |  | Schedule for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9684 | 0.9905 | 0.9905 | g_safe | [5 empty] | FI | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | false | false | 8 | 1 | 18.6344 | 0.5708 | 0.0311 | 0.0175 | hybrid | structured_no_system | [6 empty] | 2025-02-15 | 2025-03-17 | 2025-04-16 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182982 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING SCHEMATIC DIAGRAM | Diagram |  |  | Administration & Social Building |  | Diagram for Administration & Social Building |  | PLUMBING SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | administration¦social |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7693 | 0.9308 | 0.6516 | g_safe | [5 empty] | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 4 | 11 | 15.1429 | 0.5108 | 0.0297 | 0.0178 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182983 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLUMBING PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 11 | 2 | 14.7383 | 0.5848 | 0.0302 | 0.0170 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182984 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLUMBING PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 11 | 2 | 14.7383 | 0.5573 | 0.0302 | 0.0170 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182985 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED PLUMBING PLAN | Plan |  |  | Administration & Social Building |  | Plan for Administration & Social Building | ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | administration¦social |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7856 | 0.7957 | 0.7957 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 11 | 2 | 14.7383 | 0.5470 | 0.0302 | 0.0170 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYA-183100 | SECURITY BUILDING - CALCULATION | Calculation sheet |  |  | Security Building |  | Calculation sheet for Security Building | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8153 | 0.9446 | 0.9446 | g_safe | [5 empty] | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 7 | 12 | 4.2752 | 0.4403 | 0.0288 | 0.0173 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183101 | SECURITY BUILDING - GROUND FLOOR PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 41 | 9 | 4.1610 | 0.4920 | 0.0244 | 0.0137 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183102 | SECURITY BUILDING - ROOF PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 3 | 1 | 13.7004 | 0.5347 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183103 | SECURITY BUILDING - SIDE WALL ELEVATION | Elevation Drawing |  |  | Security Building |  | Elevation Drawing for Security Building |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5361 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 8 | 19 | 4.2752 | 0.4354 | 0.0274 | 0.0164 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183104 | SECURITY BUILDING - MAIN SECTION | SECTION |  |  | Security Building |  | SECTION for Security Building | SECURITY BUILDING | SECURITY BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7988 | 0.7647 | 0.7647 | g_safe | [5 empty] | FI | 3EF1625W42A01 | (HRSG #31 Main Stack) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | 2007-06-18 | 2007-12-28 |  |  | query_unknown |  |  |  |  | hrsg | query_unscoped | true | false | 3 | 244 | 5.9138 | 0.3878 | 0.0192 | 0.0108 | hybrid | structured_no_system | [6 empty] | 2024-03-20 | 2024-04-19 | 2024-05-19 | fi_complete | 0.90 |  | false | false | 0.41 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183105 | SECURITY BUILDING - INTERIOR FINISH SCHEDULE | Schedule |  |  | Security Building |  | Schedule for Security Building | SECURITY BUILDING | SECURITY BUILDING - INTERIOR finish SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9492 | 0.9848 | 0.9848 | g_safe | [5 empty] | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 7 | 1 | 11.0547 | 0.5196 | 0.0313 | 0.0176 | hybrid | structured_no_system | [6 empty] | 2025-02-21 | 2025-03-23 | 2025-04-22 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183151 | SECURITY BUILDING - FOUNDATION & COLUMN LOCATION PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 5 | 1 | 6.5301 | 0.5486 | 0.0318 | 0.0191 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183152 | SECURITY BUILDING - GROUND FLOOR FRAMING PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  | civil_design | query_unknown | [5 empty] | query_unscoped | true | true | 14 | 7 | 4.2752 | 0.4755 | 0.0284 | 0.0128 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183153 | SECURITY BUILDING - ROOF FLOOR FRAMING PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 4 | 1 | 13.7004 | 0.4992 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-05-08 | 2025-06-07 | 2025-07-07 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183154 | SECURITY BUILDING - FRAMING ELEVATION | Elevation Drawing |  |  | Security Building |  | Elevation Drawing for Security Building |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5361 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 7 | 14 | 4.2752 | 0.4250 | 0.0284 | 0.0171 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYA-183155 | SECURITY BUILDING - RE - BAR DETAIL | Detail Drawing |  |  | Security Building |  | Detail Drawing for Security Building | SECURITY BUILDING | SECURITY BUILDING - RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9770 | 0.9931 | 0.9931 | g_safe | [5 empty] | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 17 | 7 | 4.2174 | 0.4334 | 0.0279 | 0.0167 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183181 | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | Schedule |  |  | Security Building |  | Schedule for Security Building | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9744 | 0.9923 | 0.9923 | g_safe | [5 empty] | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | false | false | 16 | 15 | 8.0571 | 0.5004 | 0.0265 | 0.0149 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183182 | SECURITY BUILDING - PLUMBING SCHEMATIC DIAGRAM | Diagram |  |  | Security Building |  | Diagram for Security Building |  | PLUMBING SCHEMATIC DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | schematic_diagram | schematic_diagram | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8017 | 0.9405 | 0.6584 | g_safe | [5 empty] | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 154 | 3 | 3.8682 | 0.5173 | 0.0205 | 0.0154 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183183 | SECURITY BUILDING - PLUMBING PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown |  |  |  |  | wts | query_unscoped | false | false | 29 | 1 | 4.1610 | 0.5397 | 0.0276 | 0.0155 | hybrid | structured_no_system | [6 empty] | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYP-183200 | FIRE BRIGADE - CALCULATION | Calculation sheet |  |  | FIRE BRIGADE |  | Calculation sheet for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 1.0000 | 0.8659 | 0.9598 | 0.9598 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 6 | 7 | 6.8830 | 0.4364 | 0.0301 | 0.0226 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183201 | FIRE BRIGADE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | PLAN, SCHEDULE |  |  | FIRE BRIGADE |  | PLAN, SCHEDULE for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6000 | 0.7220 | 0.6366 | 0.6366 | [6 empty] | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 3 | 2 | 13.3977 | 0.5480 | 0.0320 | 0.0180 | hybrid | structured_no_system | [6 empty] | 2025-02-21 | 2025-03-23 | 2025-04-22 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183202 | FIRE BRIGADE - ROOF PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 14 | 1 | 6.8830 | 0.5474 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183203 | FIRE BRIGADE - ELEVATION | Elevation Drawing |  |  | FIRE BRIGADE |  | Elevation Drawing for FIRE BRIGADE |  | FIRE PROTECTION SYSTEM DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | brigade¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6905 | 0.5572 | 0.3900 | g_ambig | generic_ok | 0.70 |  | 2 | Fire brigade elevation is a general building elevation and not clearly the GT FM200 system electrical/mechanical drawings referenced by the specific rules. | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  | fire_fighting | fire_fighting | rule | fire_fighting¦hvac | match | true | false | 7 | 3 | 6.8830 | 0.5103 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.68 | usable | rule_score_medium;activity_scope_source=rule;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183204 | FIRE BRIGADE - MAIN SECTION | SECTION |  |  | FIRE BRIGADE |  | SECTION for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.8360 | 0.7758 | 0.7758 | [6 empty] | FI | 0CF4500W38A06 | (Fire Fighting BLDG) Installation - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-31 | 2008-07-11 |  | installation | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 2 | 15 | 7.0772 | 0.4545 | 0.0295 | 0.0166 | hybrid | structured_no_system | [6 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183205 | FIRE BRIGADE - ENLARGED PLAN, CEILING PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 8 | 2 | 6.8830 | 0.5304 | 0.0308 | 0.0173 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183251 | FIRE BRIGADE - FOUNDATION, COLUMN ARRAGEMENT PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 3 | 1 | 8.9292 | 0.5745 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183252 | FIRE BRIGADE - GROUND FLOOR FRAMING PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 14 | 2 | 6.8830 | 0.5700 | 0.0296 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183253 | FIRE BRIGADE - ROOF FRAMING PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 14 | 2 | 6.8830 | 0.5471 | 0.0296 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183254 | FIRE BRIGADE - FRAMING ELEVATION | Elevation Drawing |  |  | FIRE BRIGADE |  | Elevation Drawing for FIRE BRIGADE |  | FIRE PROTECTION SYSTEM DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | brigade¦fire¦fire_protection |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6905 | 0.5572 | 0.3900 | g_ambig | generic_ok | 0.70 |  | 2 | Fire brigade elevation is a general building elevation and not clearly the GT FM200 system electrical/mechanical drawings referenced by the specific rules. | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | civil_design | civil_design | match |  | fire_fighting | fire_fighting | rule | fire_fighting¦hvac | match | true | false | 7 | 3 | 6.8830 | 0.5183 | 0.0308 | 0.0308 | hybrid | structured_cell_found_text_preferred | fire_fighting | civil_design |  | 2024-03-25 | 2024-04-09 | 2024-04-24 | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 |  | false | false | 0.68 | usable | rule_score_medium;activity_scope_source=rule;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183255 | FIRE BRIGADE - MISC. STRUCTURAL DETAIL | Detail Drawing |  |  | FIRE BRIGADE |  | Detail Drawing for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - MISC. STRUCTURAL DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6000 | 0.7952 | 0.6586 | 0.6586 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 | design_drawing | civil_design | compatible |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 14 | 3 | 6.8830 | 0.5186 | 0.0294 | 0.0165 | hybrid | structured_no_system |  | system_design¦civil_design |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=compatible;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYP-183256 | FIRE BRIGADE - FOUNDATION, SLAB REBAR SCHEDULE | Schedule |  |  | FIRE BRIGADE |  | Schedule for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6000 | 0.7414 | 0.6424 | 0.6424 | [6 empty] | FI | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 6 | 1 | 8.9295 | 0.5420 | 0.0315 | 0.0237 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYP-183257 | FIRE BRIGADE - COLUMN, GIRDER, BEAM SHEDULE | SHEDULE |  |  | FIRE BRIGADE |  | SHEDULE for FIRE BRIGADE | [5 empty] | rule_query | other | calculation | shedule | calculation | brigade¦fire¦fire_protection | fire_protection | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.6667 | 0.7331 | 0.6866 | 0.6866 | [7 empty] | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 6 | 12 | 6.8830 | 0.4727 | 0.0290 | 0.0163 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183281 | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | Schedule |  |  | FIRE BRIGADE |  | Schedule for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6000 | 0.7414 | 0.6424 | 0.6424 | [6 empty] | FI | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 |  | procurement | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 3 | 1 | 9.3383 | 0.5563 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2024-05-03 | 2024-06-02 | 2024-07-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183282 | FIRE BRIGADE - PLUMBING SCHEMATIC DIAGRAM | Diagram |  |  | FIRE BRIGADE |  | Diagram for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.6000 | 0.8182 | 0.6655 | 0.6655 | [6 empty] | FI | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | design_drawing | system_design | compatible |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 1 | 1 | 16.2958 | 0.5433 | 0.0328 | 0.0184 | hybrid | structured_no_system |  | system_design¦engineering |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183283 | FIRE BRIGADE - GROUND FLOOR PLUMBING PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 14 | 1 | 6.8830 | 0.5937 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183284 | FIRE BRIGADE - ROOF PLUMBING PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 14 | 1 | 6.8830 | 0.5565 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183285 | FIRE BRIGADE - ENLARGED PLUMBING PLAN | Plan |  |  | FIRE BRIGADE |  | Plan for FIRE BRIGADE | FIRE BRIGADE | FIRE BRIGADE - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | brigade¦fire¦fire_protection | fire_protection | scoped | match | match | match | passed |  | 0.7500 | 0.7807 | 0.7592 | 0.7592 | [6 empty] | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  | civil_design | query_unknown |  |  |  |  | fire_fighting¦hvac | query_unscoped | true | false | 8 | 4 | 6.8830 | 0.5390 | 0.0303 | 0.0171 | hybrid | structured_no_system | [6 empty] | 2024-05-09 | 2024-06-08 | 2024-07-08 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYE-183300 | MAIN GATE HOUSE - CALCULATION | Calculation sheet |  |  | Security Building |  | Calculation sheet for Security Building | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8153 | 0.9446 | 0.9446 | g_safe | [5 empty] | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 2 | 17.1992 | 0.5812 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183301 | MAIN GATE HOUSE - GROUND FLOOR , ROOF PLAN, INTERIOR FINISH, DOOR & WINDOW SCHEDULES | PLAN, SCHEDULES |  |  | Security Building |  | PLAN, SCHEDULES for Security Building | MAIN GATE | MAIN GATE HOUSE - GROUND FLOOR , ROOF PLAN, INTERIOR finish, DOOR & WINDOW SCHEDULES | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9608 | 0.9882 | 0.9882 | g_safe | [5 empty] | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | true | false | 10 | 6 | 16.5970 | 0.4815 | 0.0294 | 0.0166 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183302 | MAIN GATE HOUSE - ELEVATIONS | ELEVATIONS |  |  | Security Building |  | ELEVATIONS for Security Building | [5 empty] | rule_query | other | other | elevations | security_building | security |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 0.6667 | 0.7406 | 0.6889 | 0.6889 | [7 empty] | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | hvac | query_unscoped | true | false | 9 | 6 | 16.5970 | 0.4931 | 0.0296 | 0.0167 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183303 | MAIN GATE HOUSE - SECTIONS & DETAILS | SECTIONS & DETAILS |  |  | Security Building |  | SECTIONS & DETAILS for Security Building | MAIN GATE | MAIN GATE HOUSE - SECTIONS & DETAILS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9529 | 0.9859 | 0.9859 | g_safe | [5 empty] | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | true | false | 8 | 5 | 16.5970 | 0.5029 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183351 | MAIN GATE HOUSE - FOUNDATION ARRANGEMENT, GROUND FLOOR FRAMING PLAN | ARRANGEMENT |  |  | Security Building |  | ARRANGEMENT for Security Building | MAIN GATE | MAIN GATE HOUSE - FOUNDATION ARRANGEMENT, GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9555 | 0.9866 | 0.9866 | g_safe | [5 empty] | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1 | 1 | 19.5739 | 0.5874 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183352 | MAIN GATE HOUSE - ROOF FRAMING PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | true | false | 10 | 6 | 16.5970 | 0.4905 | 0.0294 | 0.0166 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183353 | MAIN GATE HOUSE - FRAMING ELEVATION | Elevation Drawing |  |  | Security Building |  | Elevation Drawing for Security Building |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5361 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1 | 2 | 17.1992 | 0.5112 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYE-183354 | MAIN GATE HOUSE - COLUMN, GIRDER & BEAM RE - BAR DETAIL | Detail Drawing |  |  | Security Building |  | Detail Drawing for Security Building | MAIN GATE | MAIN GATE HOUSE - COLUMN, GIRDER & BEAM RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9667 | 0.9900 | 0.9900 | g_safe | [5 empty] | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 3 | 1 | 17.1992 | 0.5466 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYE-183355 | MAIN GATE HOUSE - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL |  |  |  | Security Building |  | for Security Building | MAIN GATE | MAIN GATE HOUSE - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | main_gate_house_foundation_slab_and_misc_re_bar_dedail | main_gate_house_foundation_slab_and_misc_re_bar_dedail | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9616 | 0.9885 | 0.9885 | g_safe | [5 empty] | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 1 | 1 | 19.5739 | 0.5938 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTX-183361 | MAIN GATE HOUSE SUNSHADE - GROUND FLOOR, ROOF PLAN & ELEVATION | Elevation Drawing |  |  | Security Building |  | Elevation Drawing for Security Building |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5361 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 17.1992 | 0.5021 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183371 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (TOP CHORD) | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | true | false | 10 | 15 | 16.5970 | 0.4396 | 0.0276 | 0.0155 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183372 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (BOTTOM CHORD) | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  | commissioning | query_unknown |  |  |  |  | fire_fighting | query_unscoped | true | false | 10 | 16 | 16.5970 | 0.4410 | 0.0274 | 0.0154 | hybrid | structured_no_system | [6 empty] | 2025-02-05 | 2025-03-07 | 2025-04-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183373 | MAIN GATE HOUSE SUNSHADE - FRAMING ELEVATION | Elevation Drawing |  |  | Security Building |  | Elevation Drawing for Security Building |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5361 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 17.1992 | 0.5036 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183375 | MAIN GATE HOUSE SUNSHADE - BASE PLATE & CONNECTION DETAIL | Detail Drawing |  |  | Security Building |  | Detail Drawing for Security Building | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - BASE PLATE & CONNECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9599 | 0.9880 | 0.9880 | g_safe | [5 empty] | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 3 | 1 | 17.1992 | 0.4936 | 0.0323 | 0.0194 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTX-183377 | MAIN GATE HOUSE SUNSHADE - FOUNDATION RE - BAR DETAIL | Detail Drawing |  |  | Security Building |  | Detail Drawing for Security Building | Main Gate House & Sunshade | MAIN GATE HOUSE SUNSHADE - FOUNDATION RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9509 | 0.9853 | 0.9853 | g_safe | [5 empty] | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 19.5739 | 0.5349 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTX-183390 | MAIN GATE HOUSE SUNSHADE - CALCULATION | Calculation sheet |  |  | Security Building |  | Calculation sheet for Security Building | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8153 | 0.9446 | 0.9446 | g_safe | [5 empty] | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 2 | 1 | 17.1992 | 0.4682 | 0.0325 | 0.0195 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYB-183500 | SUPPORT BUILDING - CALCULATION | Calculation sheet |  |  | Support Building |  | Calculation sheet for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8107 | 0.9432 | 0.9432 | g_safe | [5 empty] | FI | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 44 | 1 | 4.1062 | 0.4598 | 0.0260 | 0.0156 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYB-183501 | SUPPORT BUILDING - GROUND FLOOR PLAN, ROOF PLAN, ELEVATIONS & MAIN SECTION | Elevation Drawing |  |  | Support Building |  | Elevation Drawing for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - GROUND FLOOR PLAN, ROOF PLAN, ELEVATIONS & MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9655 | 0.9896 | 0.9896 | g_safe | [5 empty] | FI | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-05 |  | civil_design | civil_design | match |  |  |  |  | hrsg | query_unscoped | true | false | 79 | 26 | 5.6982 | 0.4450 | 0.0188 | 0.0141 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-07 | 2024-04-06 | 2024-05-06 | fi_complete | 0.90 |  | false | false | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYB-183502 | SUPPORT BUILDING - TOILET PLAN & ELEVATION | Elevation Drawing |  |  | Support Building |  | Elevation Drawing for Support Building |  | Support DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | drawing | drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4318 | 0.5962 | 0.5962 | g_safe | [5 empty] | FA | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 775 | 4 | 2.4495 | 0.5233 | 0.0168 | 0.0126 | hybrid | structured_no_system |  | civil_design |  | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYB-183551 | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | Plan |  |  | Support Building |  | Plan for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9610 | 0.9883 | 0.9883 | g_safe | [5 empty] | FI | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 | civil_design | civil_design | match |  |  |  |  | fire_fighting¦hvac | query_unscoped | false | false | 34 | 16 | 5.9962 | 0.4597 | 0.0238 | 0.0178 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYB-183552 | SUPPORT BUILDING - FRAMING ELEVATIONS | Elevation Drawing |  |  | Support Building |  | Elevation Drawing for Support Building |  | Support DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | drawing | drawing | support |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4318 | 0.5962 | 0.5962 | g_safe | [5 empty] | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | civil_design | civil_design | match |  |  |  |  | feedwater | query_unscoped | false | false | 1585 | 32 |  | 0.4754 | 0.0115 | 0.0086 | hybrid | structured_no_system |  | civil_design |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYB-183553 | SUPPORT BUILDING - COLUMN, GIRDER & BEAM RE - BAR DETAIL | Detail Drawing |  |  | Support Building |  | Detail Drawing for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - COLUMN, GIRDER & BEAM RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9715 | 0.9915 | 0.9915 | g_safe | [5 empty] | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 53 | 9 | 4.0527 | 0.4715 | 0.0233 | 0.0140 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYB-183554 | SUPPORT BUILDING - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL |  |  |  | Support Building |  | for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | support_building_foundation_slab_and_misc_re_bar_dedail | support_building_foundation_slab_and_misc_re_bar_dedail | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9793 | 0.9938 | 0.9938 | g_safe | [5 empty] | FI | 3CF3520W16A08 | (FGSS #32) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 | civil_design | civil_design | match |  |  |  |  | fgp | query_unscoped | true | false | 6 | 78 | 11.1818 | 0.4518 | 0.0224 | 0.0168 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYB-183581 | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM |  |  | Support Building |  | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | rule_query | schedule | schedule | schedule | schedule | support |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9289 | 0.9787 | 0.9787 | g_safe | [5 empty] | FI | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 24 | 7 | 11.7639 | 0.5245 | 0.0268 | 0.0161 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | fi_complete | 0.90 | fc_earliest | false | false | 0.51 | needs_review | activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYB-183582 | SUPPORT BUILDING - PLUMBING PLAN | Plan |  |  | Support Building |  | Plan for Support Building | SUPPORT BUILDING | SUPPORT BUILDING - PLUMBING PLAN | 1 | start-1M<=FC<=start+1M | FC ∈ [start-30d, start+30d] | rule_query | plan | plan | plan | plan | support |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6612 | 0.7234 | 0.7234 | g_safe | [5 empty] | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  | query_unknown |  |  |  |  | wts | query_unscoped | false | false | 35 | 2 | 4.1610 | 0.5361 | 0.0267 | 0.0150 | hybrid | structured_no_system | [6 empty] | 2024-10-03 | 2024-11-02 | 2024-12-02 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYF-183600 | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | Calculation sheet |  |  | Security Building |  | Calculation sheet for Security Building | SECURITY BUILDING | SECURITY BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8153 | 0.9446 | 0.9446 | g_safe | [5 empty] | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 222 | 13 |  | 0.3382 | 0.0172 | 0.0129 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183601 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | true | 1 | 36 | 24.0608 | 0.3551 | 0.0268 | 0.0121 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183602 | SEARCH FACILITY & VISITORS CENTRE - ROOF PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 5 | 10 | 9.6476 | 0.4217 | 0.0297 | 0.0167 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183603 | SEARCH FACILITY & VISITORS CENTRE - ELEVATION | Elevation Drawing |  |  | Security Building |  | Elevation Drawing for Security Building |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5361 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | civil_design | civil_design | match | [5 empty] | query_unscoped | true | true | 32 | 19 |  | 0.3802 | 0.0235 | 0.0141 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183604 | SEARCH FACILITY & VISITORS CENTRE - MAIN SECTION | SECTION |  |  | Security Building |  | SECTION for Security Building | SECURITY BUILDING | SECURITY BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7988 | 0.7647 | 0.7647 | g_safe | [5 empty] | FI | 2CF1625W42A08.0 | (HRSG #21 Main Stack) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2008-12-15 | 2009-03-14 |  | installation | query_unknown |  |  |  |  | hrsg | query_unscoped | true | false | 14 | 87 | 5.8734 | 0.2956 | 0.0203 | 0.0114 | hybrid | structured_no_system | [6 empty] | 2025-09-17 | 2025-10-17 | 2025-11-16 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183651 | SEARCH FACILITY & VISITORS CENTRE - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 10 | 19 | 3.9283 | 0.4219 | 0.0269 | 0.0202 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183652 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR & ROOF FRAMING PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 5 | 24 | 9.6476 | 0.4030 | 0.0273 | 0.0154 | hybrid | structured_no_system | [6 empty] | 2025-06-07 | 2025-07-07 | 2025-08-06 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183653 | SEARCH FACILITY & VISITORS CENTRE - FRAMING ELEVATION | Elevation Drawing |  |  | Security Building |  | Elevation Drawing for Security Building |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | security |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5361 | 0.6275 | 0.4393 | g_safe | [5 empty] | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 223 | 12 |  | 0.3890 | 0.0174 | 0.0131 | hybrid | structured_no_system |  | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYF-183654 | SEARCH FACILITY & VISITORS CENTRE - REBAR SCHEDULE & DETAIL | SCHEDULE & DETAIL |  |  | Security Building |  | SCHEDULE & DETAIL for Security Building | Search Facility & Visitor Center | SEARCH FACILITY & VISITORS CENTRE - REBAR SCHEDULE & DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 0.7778 | 0.9432 | 0.8274 | 0.8274 | g_safe | [5 empty] | FI | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 |  | installation | query_unknown | [5 empty] | query_unscoped | true | true | 1 | 118 | 25.7249 | 0.3609 | 0.0220 | 0.0099 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-12 | 2024-04-11 | fi_complete | 0.90 | fc_earliest | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYF-183681 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM |  |  | Security Building |  | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM for Security Building | SECURITY BUILDING | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | schedule | schedule | schedule | schedule | security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8617 | 0.9585 | 0.9585 | g_safe | [5 empty] | FI | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 |  | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | false | false | 1101 | 1 | 0.0004 | 0.5358 | 0.0173 | 0.0129 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | fi_complete | 0.90 |  | false | false | 0.54 | needs_review | activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYF-183682 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING PLAN | Plan |  |  | Security Building |  | Plan for Security Building | SECURITY BUILDING | SECURITY BUILDING - ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | security |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7021 | 0.7356 | 0.7356 | g_safe | [5 empty] | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | true | 1 | 17 | 24.0608 | 0.4434 | 0.0294 | 0.0132 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULD-183900 | CPP & CPP REGEN BUILDING - CALCULATION | Calculation sheet |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Calculation sheet for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.9385 | 0.8416 | 0.8416 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 3 |  | 0.3815 | 0.0317 | 0.0317 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183902 | CPP & CPP REGEN BUILDING - GROUND FLOOR PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - GROUND FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9397 | 0.8819 | 0.8819 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 10 | 2 | 4.6631 | 0.5222 | 0.0304 | 0.0137 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183903 | CPP & CPP REGEN BUILDING - ROOF FLOOR PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ROOF FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9396 | 0.8819 | 0.8819 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 16 | 2 | 4.6631 | 0.5139 | 0.0293 | 0.0132 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183904 | CPP & CPP REGEN BUILDING - ELEVATION | Elevation Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Elevation Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4865 | 0.6126 | 0.4288 | g_safe | [5 empty] | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 9 | 2 |  | 0.3541 | 0.0306 | 0.0306 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183905 | CPP & CPP REGEN BUILDING - SECTION | SECTION |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | SECTION for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.9435 | 0.8431 | 0.8431 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 2 | 3 | 4.6631 | 0.5382 | 0.0320 | 0.0144 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183906 | CPP & CPP REGEN BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | Schedule |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Schedule for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - INTERIOR finish, DOOR & WINDOW SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9493 | 0.9070 | 0.9070 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 2 | 1 | 11.4108 | 0.4777 | 0.0325 | 0.0146 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183908 | CPP & CPP REGEN BUILDING - WALL SECTION DETAIL | SECTION DETAIL |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | SECTION DETAIL for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - WALL SECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9267 | 0.8780 | 0.8780 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 4 | 1 | 4.6631 | 0.4624 | 0.0320 | 0.0144 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183909 | CPP & CPP REGEN BUILDING - WALL OPENING PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - WALL OPENING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9515 | 0.8855 | 0.8855 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 5 | 2 | 4.6631 | 0.4834 | 0.0315 | 0.0142 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183910 | CPP & CPP REGEN BUILDING - ARCHITECTURAL MISC. DETAIL | Detail Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ARCHITECTURAL MISC. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9058 | 0.8717 | 0.8717 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 1 |  | 0.4021 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183951 | CPP & CPP REGEN BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9366 | 0.8935 | 0.8935 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 1 | 3 | 2.1802 | 0.4710 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183952 | CPP & CPP REGEN BUILDING - GROUND FLOOR FRAMING PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9500 | 0.8975 | 0.8975 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 10 | 5 | 4.6631 | 0.4929 | 0.0297 | 0.0134 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183953 | CPP & CPP REGEN BUILDING - ROOF FLOOR FRAMING PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ROOF FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9358 | 0.8933 | 0.8933 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 16 | 3 | 4.6631 | 0.4668 | 0.0290 | 0.0131 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183954 | CPP & CPP REGEN BUILDING - FRAMING ELEVATION | Elevation Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Elevation Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4865 | 0.6126 | 0.4288 | g_safe | [5 empty] | FA | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 3 |  | 0.3501 | 0.0317 | 0.0317 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183955 | CPP & CPP REGEN BUILDING - FOUNDATION REBAR DETAIL | Detail Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - FOUNDATION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9408 | 0.8822 | 0.8822 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 1 | 1 | 2.1802 | 0.4808 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183956 | CPP & CPP REGEN BUILDING - COLUMN REBAR DETAIL | Detail Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - COLUMN REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9480 | 0.8844 | 0.8844 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 1 |  | 0.4186 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183957 | CPP & CPP REGEN BUILDING - GIRDER & BEAM REBAR SCHEDULE | Schedule |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Schedule for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - GIRDER & BEAM REBAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9612 | 0.9008 | 0.9008 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 2 | 26 | 4.6635 | 0.4331 | 0.0278 | 0.0125 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183958 | CPP & CPP REGEN BUILDING - SLAB REBAR DETAIL | Detail Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - SLAB REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9425 | 0.8827 | 0.8827 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 1 |  | 0.4105 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183959 | CPP & CPP REGEN BUILDING - EQUIPMENT FOUNDTAION REBAR DETAIL | Detail Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - EQUIPMENT FOUNDTAION REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9413 | 0.8949 | 0.8949 | g_safe | [5 empty] | FI | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | civil_design | civil_design | match | condensate |  | condensate | query | acc¦condensate | match | false | false | 1 | 3 | 2.6045 | 0.5054 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183960 | CPP & CPP REGEN BUILDING - EMBEDDED PLATE & SLEEVE PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - EMBEDDED PLATE & SLEEVE PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9532 | 0.8985 | 0.8985 | g_safe | [5 empty] | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 1 | 8 | 24.0608 | 0.4746 | 0.0311 | 0.0140 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183961 | CPP & CPP REGEN BUILDING - MISC. REBAR DETAIL | Detail Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - MISC. REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9343 | 0.8803 | 0.8803 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 1 |  | 0.4080 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183962 | CPP & CPP REGEN BUILDING - ROOF COLUMN LOCATION PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ROOF COLUMN LOCATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9511 | 0.8978 | 0.8978 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 10 | 9 | 4.6631 | 0.5048 | 0.0288 | 0.0130 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183963 | CPP & CPP REGEN BUILDING - ENLARGED ROOF FRAMING PLAN | Plan |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Plan for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - ENLARGED ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9463 | 0.8964 | 0.8964 | g_safe | [5 empty] | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  | query_unknown | condensate |  | condensate | query |  | activity_unscoped | true | true | 10 | 6 | 4.6631 | 0.4430 | 0.0294 | 0.0132 | hybrid | structured_no_phase | condensate | [5 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.38 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183964 | CPP & CPP REGEN BUILDING - GIRT LINE & ROW ELEVATION | Elevation Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Elevation Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | DraWing Building DraWing_Structure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.4865 | 0.6126 | 0.4288 | g_safe | [5 empty] | FA | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 1 |  | 0.3314 | 0.0323 | 0.0323 | hybrid | structured_preferred | condensate | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183965 | CPP & CPP REGEN BUILDING - STEEL CONNECTION DETAIL | Detail Drawing |  |  | CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING |  | Detail Drawing for CONDENSATE POLISING PLANT & CONDENSATE POLISING PLANT REGEN BUILDING | CPP Regeneration Building | CPP & CPP REGEN BUILDING - STEEL CONNECTION DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | condensate¦plant¦polising¦regen |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9233 | 0.8770 | 0.8770 | g_safe | [5 empty] | FI | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 | civil_design | civil_design | match | condensate |  | condensate | query | condensate | match | false | false | 3 | 3 |  | 0.4124 | 0.0317 | 0.0317 | hybrid | structured_preferred | condensate | civil_design | 10 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0USR-184700 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | Calculation sheet |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Calculation sheet for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | tank | scoped | match | match | match | passed |  | 0.8571 | 0.8250 | 0.8475 | 0.8475 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 2 | 2 | 28.7086 | 0.5969 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USR-184701 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - GROUND & ROOF FLOOR PLAN | Plan |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Plan for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | DWP Chemical Storage Tank Shelter FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | tank | scoped | match | match | match | passed |  | 0.7143 | 0.6675 | 0.7003 | 0.7003 | [6 empty] | FA | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  | query_unknown | wts |  | wts | query | wts | match | true | false | 1 | 4 | 29.9534 | 0.6620 | 0.0320 | 0.0240 | hybrid | structured_no_phase | wts |  |  | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USR-184702 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - ELEVATIONS & SECTIONS | ELEVATIONS & SECTIONS |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | ELEVATIONS & SECTIONS for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER - ELEVATIONS & SECTIONS | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | tank | scoped | match | match | match | passed |  | 0.8750 | 0.8778 | 0.8758 | 0.8758 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | wts |  | wts | query | wts | match | true | false | 2 | 2 | 28.7086 | 0.6206 | 0.0323 | 0.0242 | hybrid | structured_no_phase | wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0USR-184751 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL COLUMN LOCATION & ROOF PLAN | Plan |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | Plan for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | DWP Chemical Storage Tank Shelter FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | tank | scoped | match | match | match | passed |  | 0.7143 | 0.6675 | 0.7003 | 0.7003 | [6 empty] | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | wts |  | wts | query | wts | match | true | false | 2 | 2 | 28.7086 | 0.6406 | 0.0323 | 0.0242 | hybrid | structured_no_phase | wts |  |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=query_unknown | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0USR-184752 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL FRAMING ELEVATIONS | ELEVATIONS |  |  | Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER |  | ELEVATIONS for Waste Water Treatment & BULK CHEMICAL STORAGE TANK SHELTER | [5 empty] | rule_query | other | drawing | elevations | sectional_drawing | bulk¦chemical¦shelter¦storage¦tank¦treatment¦waste¦water¦wts | tank | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.7500 | 0.8038 | 0.7662 | 0.7662 | [7 empty] | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | wts |  | wts | query | wts | match | true | false | 2 | 2 | 28.7086 | 0.6138 | 0.0323 | 0.0242 | hybrid | structured_no_phase | wts | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0QJA-184800 | N2 STORAGE SHELTER - CALCULATION | Calculation sheet | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | Calculation sheet for Nitrogen System | Gas Storage Shelter | N2 STORAGE SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | nitrogen |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.9327 | 0.8398 | 0.8398 | g_safe | [5 empty] | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 | n2 | n2 | query | n2 | match | true | false | 1 | 2 | 20.9435 | 0.6896 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | n2 | civil_design |  |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184801 | N2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | Plan | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | Plan for Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9234 | 0.8895 | 0.8895 | g_safe | [5 empty] | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  | civil_design | query_unknown | n2 | n2 | n2 | query | n2 | match | true | false | 3 | 2 | 20.9435 | 0.7280 | 0.0320 | 0.0240 | hybrid | structured_no_phase | n2 | [5 empty] | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184802 | N2 STORAGE SHELTER - ELEVATION | Elevation Drawing | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | Elevation Drawing for Nitrogen STORAGE SHELTER |  | ELEVATION | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5689 | 0.4040 | 0.3434 | g_safe | [5 empty] | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | true | false | 1 | 5 | 20.9435 | 0.6993 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | n2 | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184803 | N2 STORAGE SHELTER - MAIN SECTION | SECTION | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | SECTION for Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.9353 | 0.8639 | 0.8639 | g_safe | [5 empty] | FI | 1CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2008-05-01 | 2008-08-09 |  |  | query_unknown | n2 | n2 | n2 | query | n2 | match | true | false | 2 | 1 | 20.9435 | 0.7494 | 0.0325 | 0.0244 | hybrid | structured_no_phase | n2 | [5 empty] | 2025-02-01 | 2025-03-03 | 2025-04-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184851 | N2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | Plan | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | Plan for Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8750 | 0.9415 | 0.8950 | 0.8950 | g_safe | [5 empty] | FI | 1CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2008-03-04 | 2008-04-30 | civil_design | civil_design | match | n2 | n2 | n2 | query | n2 | match | true | false | 3 | 2 | 21.8146 | 0.7287 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | n2 | civil_design |  |  |  |  | 2024-12-05 | 2025-01-04 | 2025-02-03 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184852 | N2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | Plan | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | Plan for Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9350 | 0.9027 | 0.9027 | g_safe | [5 empty] | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  | civil_design | query_unknown | n2 | n2 | n2 | query | n2 | match | true | false | 3 | 5 | 20.9435 | 0.7001 | 0.0313 | 0.0234 | hybrid | structured_no_phase | n2 | [5 empty] | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184853 | N2 STORAGE SHELTER - FRAMING ELEVATION | Elevation Drawing | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | Elevation Drawing for Nitrogen STORAGE SHELTER |  | ELEVATION | 2 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5463 | 0.3972 | 0.3376 | g_safe | [5 empty] | FA | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 | civil_design | civil_design | match | n2 |  | n2 | query | n2 | match | true | false | 1 | 3 | 20.9435 | 0.6925 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | n2 | civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0QJA-184854 | N2 STORAGE SHELTER - REBAR DETAIL | REBAR DETAIL | Nitrogen System |  | Nitrogen STORAGE SHELTER |  | REBAR DETAIL for Nitrogen STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | nitrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8689 | 0.7274 | 0.7274 | g_safe | [5 empty] | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  | civil_design | query_unknown | n2 | n2 | n2 | query | n2 | match | true | false | 2 | 2 | 20.9435 | 0.7044 | 0.0323 | 0.0242 | hybrid | structured_no_phase | n2 | [5 empty] | 2024-09-04 | 2024-10-04 | 2024-11-03 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTG-184900 | H2, CO2 STORAGE SHELTER - CALCULATION | Calculation sheet | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Calculation sheet for Hydrogen System | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | hydrogen |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.9589 | 0.8710 | 0.8710 | g_safe | [5 empty] | FI | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | true | false | 1 | 1 | 17.6855 | 0.4832 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 |  |  |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184901 | H2, CO2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | Plan | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Plan for Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9590 | 0.9099 | 0.9099 | g_safe | [5 empty] | FI | 0EF3515W32A03 | (H2) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-23 |  |  | query_unknown | h2 | h2 | h2 | query | h2 | match | true | false | 7 | 1 | 17.8994 | 0.5856 | 0.0313 | 0.0235 | hybrid | structured_no_phase | h2 | [5 empty] | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184902 | H2, CO2 STORAGE SHELTER - ELEVATION | Elevation Drawing | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Elevation Drawing for Hydrogen, Carbon Dioxide STORAGE SHELTER | H2, CO2 Supply System | Nameplate DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5938 | 0.4115 | 0.4115 | g_safe | [5 empty] | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | true | false | 1 | 1 | 17.6855 | 0.5152 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184903 | H2, CO2 STORAGE SHELTER - MAIN SECTION | SECTION | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | SECTION for Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8571 | 0.9679 | 0.8904 | 0.8904 | g_safe | [5 empty] | FI | 0EF3515W32A03 | (H2) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-23 |  |  | query_unknown | h2 | h2 | h2 | query | h2 | match | true | false | 5 | 21 | 17.8994 | 0.5599 | 0.0277 | 0.0208 | hybrid | structured_no_phase | h2 | [5 empty] | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184951 | H2, CO2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | Plan | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Plan for Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.8889 | 0.9641 | 0.9114 | 0.9114 | g_safe | [5 empty] | FI | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | true | false | 3 | 1 | 20.0185 | 0.6207 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | h2 | civil_design |  |  |  |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184952 | H2, CO2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | Plan | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Plan for Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | H2, CO2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.9000 | 0.9602 | 0.9181 | 0.9181 | g_safe | [5 empty] | FI | 0EF3515W32A03 | (H2) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-23 |  |  | query_unknown | h2 | h2 | h2 | query | h2 | match | true | false | 7 | 2 | 17.8994 | 0.5829 | 0.0311 | 0.0233 | hybrid | structured_no_phase | h2 | [5 empty] | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184953 | H2, CO2 STORAGE SHELTER - FRAMING ELEVATION | Elevation Drawing | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | Elevation Drawing for Hydrogen, Carbon Dioxide STORAGE SHELTER | H2, CO2 Supply System | Nameplate DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | title | drawing | drawing | drawing | drawing | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5849 | 0.4088 | 0.4088 | g_safe | [5 empty] | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | civil_design | civil_design | match | h2 | h2 | h2 | query | h2 | match | true | false | 1 | 1 | 17.6855 | 0.5219 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | civil_design | 2 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTG-184954 | H2, CO2 STORAGE SHELTER - REBAR DETAIL | REBAR DETAIL | Hydrogen System |  | Hydrogen, Carbon Dioxide STORAGE SHELTER |  | REBAR DETAIL for Hydrogen, Carbon Dioxide STORAGE SHELTER | Gas Storage Shelter | N2 STORAGE SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | carbon¦dioxide¦hydrogen¦shelter¦storage |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8042 | 0.7079 | 0.7079 | g_safe | [5 empty] | FI | 0EF3515W32A03 | (H2) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-23 |  |  | query_unknown | h2 | n2 | h2 | query | h2 | match | true | false | 6 | 13 | 17.8994 | 0.5392 | 0.0289 | 0.0216 | hybrid | structured_no_phase | h2 | [5 empty] | 2024-07-26 | 2024-08-25 | 2024-09-24 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185151 | PIPE RACK #1 - FOUNDATION PLAN | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 9 | 1 | 19.4405 | 0.7712 | 0.0309 | 0.0232 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-03 | 2024-07-03 | 2024-08-02 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185152 | PIPE RACK #1 - COLUMN LOCATION PLAN & BASE PLATE DETAIL | PLAN & BASE PLATE DETAIL |  |  | Pipe Rack |  | PLAN & BASE PLATE DETAIL for Pipe Rack | PIPE RACK | PIPE RACK #2 - BASE PLATE DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8642 | 0.9592 | 0.9592 | [6 empty] | FI | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-09-01 | 2008-01-01 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 20 | 1 | 17.3784 | 0.6491 | 0.0289 | 0.0163 | hybrid | structured_no_system | [6 empty] | 2024-06-03 | 2024-07-03 | 2024-08-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185153 | PIPE RACK #1 - FRAMING PLAN | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 1CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2008-02-18 | 2008-05-31 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 17 | 1 | 17.7192 | 0.7151 | 0.0294 | 0.0165 | hybrid | structured_no_system | [6 empty] | 2024-11-20 | 2024-12-20 | 2025-01-19 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185154 | PIPE RACK #1 - ELEVATION | Elevation Drawing |  |  | Pipe Rack |  | Elevation Drawing for Pipe Rack |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6910 | 0.6740 | 0.4718 | g_safe | [5 empty] | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 16 | 1 | 17.4914 | 0.6624 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185155 | PIPE RACK #1 - FOUNDATION & PEDETAL DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 4 | 3 | 20.3280 | 0.7161 | 0.0315 | 0.0236 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185160 | PIPE RACK #2 - FOUNDATION PLAN | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 3 | 1 | 21.0420 | 0.7495 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185161 | PIPE RACK #2 - COLUMN LOCATION PLAN | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 6 | 7 | 18.8795 | 0.6432 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185162 | PIPE RACK #2 - FRAMING PLAN - 1 | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 2CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2008-03-18 | 2008-06-30 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 7 | 2 | 19.5068 | 0.6956 | 0.0311 | 0.0175 | hybrid | structured_no_system | [6 empty] | 2024-12-19 | 2025-01-18 | 2025-02-17 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185163 | PIPE RACK #2 - FRAMING PLAN - 2 | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 5 | 4 | 21.2217 | 0.6700 | 0.0310 | 0.0174 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185164 | PIPE RACK #2 - LINE ELEVATION | Elevation Drawing |  |  | Pipe Rack |  | Elevation Drawing for Pipe Rack |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6910 | 0.6740 | 0.4718 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 4 | 6 | 18.8795 | 0.6259 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185165 | PIPE RACK #2 - ROW ELEVATION | Elevation Drawing |  |  | Pipe Rack |  | Elevation Drawing for Pipe Rack |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6910 | 0.6740 | 0.4718 | g_safe | [5 empty] | FA | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 4 | 9 | 18.8795 | 0.6263 | 0.0301 | 0.0226 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185166 | PIPE RACK #2 - FOUNDATION DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 2 | 2 | 21.0420 | 0.7346 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185167 | PIPE RACK #2 - PEDETAL DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 5 | 1 | 18.8795 | 0.6739 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185168 | PIPE RACK #2 - BASE PLATE DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 5 | 1 | 18.8795 | 0.6667 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185169 | PIPE RACK #3 - FOUNDATION PLAN | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 3 | 2 | 21.0730 | 0.7457 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185170 | PIPE RACK #3 - COLUMN LOCATION PLAN | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 7 | 6 | 18.9105 | 0.6389 | 0.0301 | 0.0169 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185171 | PIPE RACK #3 - FRAMING PLAN - 1 | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 3CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2008-04-19 | 2008-08-01 |  |  | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 7 | 3 | 19.5369 | 0.6858 | 0.0308 | 0.0173 | hybrid | structured_no_system | [6 empty] | 2025-01-20 | 2025-02-19 | 2025-03-21 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185172 | PIPE RACK #3 - FRAMING PLAN - 2 | Plan |  |  | Pipe Rack |  | Plan for Pipe Rack | PIPE RACK | PIPE RACK #1 - FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.7799 | 0.7590 | 0.7590 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 10 | 4 | 18.8795 | 0.6730 | 0.0299 | 0.0168 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185173 | PIPE RACK #3 - LINE ELEVATION | Elevation Drawing |  |  | Pipe Rack |  | Elevation Drawing for Pipe Rack |  | PIPE SUPPORT DRAWING | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | pipe¦piperack¦rack |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6910 | 0.6740 | 0.4718 | g_safe | [5 empty] | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 5 | 6 | 18.9105 | 0.6176 | 0.0305 | 0.0229 | hybrid | structured_no_system |  | civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185174 | PIPE RACK #3 - ROW SECTION | SECTION |  |  | Pipe Rack |  | SECTION for Pipe Rack | PIPE RACK | PIPE RACK #3 - ROW SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8050 | 0.7665 | 0.7665 | [6 empty] | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  | procurement | query_unknown |  |  |  |  | bop | query_unscoped | true | false | 1 | 3 | 20.9512 | 0.6082 | 0.0323 | 0.0181 | hybrid | structured_no_system | [6 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185175 | PIPE RACK #3 - FOUNDATION DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 2 | 3 | 21.0730 | 0.7342 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185176 | PIPE RACK #3 - PEDETAL & TIE GIRDER DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 6 | 2 | 18.9105 | 0.6507 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185177 | PIPE RACK #3 - BASE PLATE DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 6 | 2 | 18.9105 | 0.6630 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185178 | PIPE RACK - MISC DETAIL | Detail Drawing |  |  | Pipe Rack |  | Detail Drawing for Pipe Rack | PIPE RACK | PIPE RACK - MISC DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 0.7500 | 0.8015 | 0.7654 | 0.7654 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 15 | 1 | 16.5373 | 0.6781 | 0.0297 | 0.0223 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185190 | PIPE RACK #1 - CALCULATION | Calculation sheet |  |  | Pipe Rack |  | Calculation sheet for Pipe Rack | PIPE RACK | PIPE RACK #1 - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8413 | 0.9524 | 0.9524 | [6 empty] | FI | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 16 | 1 | 17.4914 | 0.6952 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185191 | PIPE RACK #2 - CALCULATION | Calculation sheet |  |  | Pipe Rack |  | Calculation sheet for Pipe Rack | PIPE RACK | PIPE RACK #1 - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8413 | 0.9524 | 0.9524 | [6 empty] | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 4 | 4 | 18.8795 | 0.6560 | 0.0312 | 0.0234 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185192 | PIPE RACK #3 - CALCULATION | Calculation sheet |  |  | Pipe Rack |  | Calculation sheet for Pipe Rack | PIPE RACK | PIPE RACK #1 - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | pipe¦piperack¦rack | piperack | scoped | match | match | match | passed |  | 1.0000 | 0.8413 | 0.9524 | 0.9524 | [6 empty] | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | civil_design | civil_design | match |  |  |  |  | bop | query_unscoped | false | false | 5 | 5 | 18.9105 | 0.6546 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 |  | false | false | 0.80 | fi_complete | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185701 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR PLAN, ROOF PLAN | Plan | Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Plan for Chemical Dosing Shelter | CHEMICAL DOSING SHELTER FOR HRSG | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR PLAN, ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦wts | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9768 | 0.9930 | 0.9930 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | hrsg¦wts | hrsg¦wts | hrsg¦wts | query | wts | match | true | false | 4 | 7 | 21.1937 | 0.6032 | 0.0306 | 0.0229 | hybrid | structured_no_phase | hrsg¦wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185751 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR FRAMING PLAN | Plan | Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Plan for Chemical Dosing Shelter | CHEMICAL DOSING SHELTER FOR HRSG | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦wts | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9785 | 0.9935 | 0.9935 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | hrsg¦wts | hrsg¦wts | hrsg¦wts | query | wts | match | true | false | 4 | 8 | 21.1937 | 0.6072 | 0.0303 | 0.0227 | hybrid | structured_no_phase | hrsg¦wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0GEN-185800 | CHEMICAL DOSING SHELTER FOR STG & HRSG - CALCULATION | Calculation sheet | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Calculation sheet for Steam Turbine Generator & Heat Recovery Steam Generator |  | HRSG - Equipment Calculation Sheet for SCR | 1 | start+164D<=FA<=start+164D+2M | FA ∈ [start+164d, start+224d] | rule_query | calculation | calculation | calculation | calculation | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine¦wts | hrsg | scoped | match | match | match | passed |  | 0.6667 | 0.7452 | 0.6902 | 0.6902 | [6 empty] | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | hrsg¦stg¦wts | hrsg | hrsg¦stg¦wts | query | wts | match | true | false | 4 | 4 | 20.4532 | 0.5738 | 0.0312 | 0.0312 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185801 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR PLAN, ROOF PLAN | Plan | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Plan for Chemical Dosing Shelter | CHEMICAL DOSING SHELTER FOR HRSG | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR PLAN, ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg¦wts | hrsg | scoped | match | match | match | passed |  | 1.0000 | 0.9576 | 0.9873 | 0.9873 | [6 empty] | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  | civil_design | query_unknown | hrsg¦stg¦wts | hrsg¦wts | hrsg¦stg¦wts | query | wts | match | true | false | 7 | 1 | 21.1937 | 0.6115 | 0.0313 | 0.0235 | hybrid | structured_no_phase | hrsg¦stg¦wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185802 | CHEMICAL DOSING SHELTER FOR STG & HRSG - ELEVATION | Elevation Drawing | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Elevation Drawing for Chemical Dosing Shelter | Chemical Dosing System | Piping Arrangement DraWing | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | drawing | drawing | drawing | drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg¦wts |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6532 | 0.5460 | 0.5460 | g_ambig | uncertain | 0.50 |  | 61 | Chemical dosing shelter elevation suggests Water Treatment/Chemical dosing scope, but no competing specific rule explicitly covers 'chemical dosing shelter elevation' to confidently override the gener | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | hrsg¦stg¦wts | wts | hrsg¦stg¦wts | query | wts | match | true | false | 4 | 4 | 20.4532 | 0.5995 | 0.0312 | 0.0312 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185803 | CHEMICAL DOSING SHELTER FOR STG & HRSG - MAIN SECTION | MAIN SECTION | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | MAIN SECTION for Chemical Dosing Shelter | CHEMICAL DOSING SHELTER FOR STG & HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg¦wts | hrsg¦stg | scoped | match | match | match | passed |  | 0.7500 | 0.8359 | 0.7758 | 0.7758 | [6 empty] | FI | 1EF1625W42A01 | (HRSG #11 Main Stack) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-04-17 | 2007-10-29 |  |  | query_unknown | hrsg¦stg¦wts | hrsg¦stg¦wts | hrsg¦stg¦wts | query | hrsg | match | true | false | 1 | 65 | 27.7283 | 0.5806 | 0.0244 | 0.0183 | hybrid | structured_no_phase | hrsg¦stg¦wts | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended | false | true | 0.55 | fi_complete | activity_phase_status=query_unknown;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185851 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN | Plan | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Plan for Chemical Dosing Shelter | CHEMICAL DOSING SHELTER FOR STG & HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg¦wts | hrsg¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9791 | 0.9937 | 0.9937 | [6 empty] | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 |  | civil_design | query_unknown | hrsg¦stg¦wts | hrsg¦stg¦wts | hrsg¦stg¦wts | query | wts | match | true | false | 5 | 4 | 21.1937 | 0.6224 | 0.0310 | 0.0233 | hybrid | structured_no_phase | hrsg¦stg¦wts | [5 empty] | 2024-07-04 | 2024-08-03 | 2024-09-02 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185852 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | Plan | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Plan for Chemical Dosing Shelter | CHEMICAL DOSING SHELTER FOR STG & HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg¦wts | hrsg¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9564 | 0.9869 | 0.9869 | [6 empty] | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  | civil_design | query_unknown | hrsg¦stg¦wts | hrsg¦stg¦wts | hrsg¦stg¦wts | query | wts | match | true | false | 13 | 8 | 20.4532 | 0.6224 | 0.0284 | 0.0213 | hybrid | structured_no_phase | hrsg¦stg¦wts | [5 empty] | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 0.75 | fi_complete | activity_phase_status=query_unknown |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185853 | CHEMICAL DOSING SHELTER FOR STG & HRSG - FRAMING ELEVATION | FRAMING ELEVATION | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | FRAMING ELEVATION for Steam Turbine Generator & Heat Recovery Steam Generator | [5 empty] | rule_query | other | other | framing_elevation | chemical_dosing_shelter_for_stg_and_hrsg_framing_elevation | generator¦heat¦hrsg¦recovery¦steam¦stg¦turbine¦wts | hrsg¦stg | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 0.6250 | 0.6477 | 0.6318 | 0.6318 | [7 empty] | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 |  | civil_design | query_unknown | hrsg¦stg¦wts |  | hrsg¦stg¦wts | query | wts | match | true | false | 3 | 25 | 21.1937 | 0.6090 | 0.0276 | 0.0207 | hybrid | structured_no_phase | hrsg¦stg¦wts | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0GEN-185854 | CHEMICAL DOSING SHELTER FOR STG & HRSG - REBAR DETAIL | Detail Drawing | Steam Turbine Generator & Heat Recovery Steam Generator | Water Treatment System | Chemical Dosing Shelter |  | Detail Drawing for Chemical Dosing Shelter | CHEMICAL DOSING SHELTER FOR STG & HRSG | CHEMICAL DOSING SHELTER FOR STG & HRSG - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | chemical¦dosing¦generator¦heat¦hrsg¦recovery¦shelter¦steam¦stg¦wts | hrsg¦stg | scoped | match | match | match | passed |  | 1.0000 | 0.9720 | 0.9916 | 0.9916 | [6 empty] | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | civil_design | civil_design | match | hrsg¦stg¦wts | hrsg¦stg¦wts | hrsg¦stg¦wts | query | wts | match | true | false | 4 | 7 | 20.4532 | 0.5975 | 0.0306 | 0.0306 | hybrid | structured_preferred | hrsg¦stg¦wts | civil_design | 10 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | fi_complete | 0.90 |  | false | false | 1.00 | fi_complete |  |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-186100 | FGS ELECTRICAL BUILDING - CALCULATION | Calculation sheet |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for Electrical System | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | calculation | calculation | calculation | calculation | electrical¦fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9538 | 0.9861 | 0.9861 | g_ambig | generic_ok | 0.75 |  | 2 | The document is an illumination calculation for the FGS electrical building, and the competing specifics are either generic 'Calculation Sheets' or foundation calculation, neither clearly a better equ | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | false | 4 | 2 | 13.7268 | 0.5434 | 0.0318 | 0.0318 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | fc_earliest | false | false | 0.32 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186101 | FGS ELECTRICAL BUILDING - GROUND FLOOR, ROOF PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | Plan |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Plan for Electrical System | Electrical Building | FGS ELECTRICAL BUILDING - GROUND FLOOR, ROOF PLAN & INTERIOR finish SCHEDULE(INCL. DOOR & WINDOW) | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9636 | 0.9891 | 0.9891 | g_safe | [5 empty] | FI | 0CF3520W24A10.1 | (FGS LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 |  |  | query_unknown | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | true | false | 3 | 23 | 21.5342 | 0.5573 | 0.0279 | 0.0209 | hybrid | structured_no_phase | electrical¦fgp | [5 empty] | 2025-03-03 | 2025-04-02 | 2025-05-02 | fi_complete | 0.90 |  | false | false | 0.60 | fi_complete | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186103 | FGS ELECTRICAL BUILDING - SIDE WALL ELEVATION | Elevation Drawing |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Elevation Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6879 | 0.6730 | 0.6730 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 13.7268 | 0.5873 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186104 | FGS ELECTRICAL BUILDING - MAIN SECTION | MAIN SECTION |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | MAIN SECTION for Fuel Gas System ELECTRICAL BUILDING | Electrical Building | FGS ELECTRICAL BUILDING - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦fgp¦fuel¦gas |  | scoped | match | match | rule_generic | passed |  | 0.8000 | 0.7652 | 0.7896 | 0.7896 | g_ambig | generic_ok | 0.90 |  | 4 | Document is explicitly FGS Electrical Building main section, and competing specifics relate to GT equipment sectional assemblies or generic equipment sectional drawings, not the FGS building section. | FI | 0CF3520W74A08.1 | (FGS LEB) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-01-11 | 2008-03-08 |  | commissioning | query_unknown | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | false | 2 | 16 | 15.1382 | 0.5974 | 0.0293 | 0.0220 | hybrid | structured_no_phase | electrical¦fgp | [5 empty] | 2024-10-13 | 2024-11-12 | 2024-12-12 | fi_complete | 0.90 |  | false | false | 0.24 | needs_review_activity | activity_phase_status=query_unknown;activity_equipment_unconfirmed;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186151 | FGS ELECTRICAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Plan for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Foundation Plan and Loading Data | 1 | start+16W<=FA<=FC<=start+24W | FA ∈ [start+112d, start+168d] ¦ FC ∈ [start+112d, start+168d] | rule_query | plan | plan | plan | plan | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6738 | 0.5521 | 0.5521 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | false | 3 | 8 | 17.1212 | 0.6029 | 0.0306 | 0.0306 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | civil_design |  | 2024-09-04 | 2024-10-02 | 2024-10-30 | 2024-10-23 | 2024-11-20 | 2024-12-18 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186152 | FGS ELECTRICAL BUILDING - GROUND FLOOR & ROOF FRAMING PLAN | Plan |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Plan for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Foundation Plan and Loading Data | 1 | start+16W<=FA<=FC<=start+24W | FA ∈ [start+112d, start+168d] ¦ FC ∈ [start+112d, start+168d] | rule_query | plan | plan | plan | plan | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.5000 | 0.6738 | 0.5521 | 0.5521 | [6 empty] | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | procurement | procurement | match | electrical¦fgp | fgp | electrical¦fgp | query | electrical | discipline_only | true | false | 4 | 1 | 16.0133 | 0.6259 | 0.0320 | 0.0160 | hybrid | structured_cell_found_text_preferred | electrical¦fgp | procurement |  | 2024-12-20 | 2025-01-17 | 2025-02-14 | 2025-02-07 | 2025-03-07 | 2025-04-04 | generated | 0.90 |  | false | false | 0.50 | needs_review | activity_scope_status=discipline_only |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186154 | FGS ELECTRICAL BUILDING - LINE & ROW FRAMING ELEVATION | Elevation Drawing |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Elevation Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Piping Arrangement DraWing | 1 | start+16W<=FA<=FC<=start+32W | FA ∈ [start+112d, start+224d] ¦ FC ∈ [start+112d, start+224d] | rule_query | drawing | drawing | drawing | drawing | electrical¦fgp¦fuel¦gas | fgp | scoped | match | match | match | passed |  | 0.6667 | 0.6879 | 0.6730 | 0.6730 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 1 | 13.7268 | 0.5975 | 0.0320 | 0.0320 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186155 | FGS ELECTRICAL BUILDING - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | Detail Drawing |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Detail Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | Equipment (incl. pump) Detail DraWing | 1 | start+20W<=FA<=FC<=start+28W | FA ∈ [start+140d, start+196d] ¦ FC ∈ [start+140d, start+196d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | electrical¦fgp¦fuel¦gas | fgp¦pump | scoped | match | match | match | passed |  | 0.6250 | 0.7609 | 0.6658 | 0.6658 | [6 empty] | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | civil_design | civil_design | match | electrical¦fgp | fgp | electrical¦fgp | query | fgp | match | false | false | 4 | 7 | 13.7268 | 0.5888 | 0.0306 | 0.0306 | hybrid | structured_preferred | electrical¦fgp | civil_design | 10 | 2024-10-02 | 2024-10-30 | 2024-11-27 | 2024-11-20 | 2024-12-18 | 2025-01-15 | generated | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186156 | FGS ELECTRICAL BUILDING - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | Schedule |  | Electrical System | Fuel Gas System ELECTRICAL BUILDING |  | Schedule for Electrical System | Electrical Building | FGS ELECTRICAL BUILDING - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦fgp |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9662 | 0.9899 | 0.9899 | g_safe | [5 empty] | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  |  | civil_design | query_unknown | electrical¦fgp | electrical | electrical¦fgp | query | fgp | match | false | false | 10 | 1 | 13.7271 | 0.5570 | 0.0307 | 0.0230 | hybrid | structured_no_phase | electrical¦fgp | [5 empty] | 2024-03-01 | 2024-03-16 | 2024-04-15 | fi_complete | 0.90 | fc_earliest | false | false | 0.24 | needs_review_activity | activity_phase_status=query_unknown;activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UGD-186600 | NAOCL DOSING SKID SHELTER - CALCULATION | Calculation sheet |  |  | NAOCL DOSING SKID SHELTER |  | Calculation sheet for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8953 | 0.9686 | 0.9686 | g_safe | [5 empty] | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | true | false | 8 | 4 | 7.8531 | 0.5318 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-186601 | NAOCL DOSING SKID SHELTER - GROUND & ROOF FLOOR PLAN | Plan |  |  | NAOCL DOSING SKID SHELTER |  | Plan for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - GROUND & ROOF FLOOR PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | g_safe | [5 empty] | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  | civil_design | query_unknown |  |  |  |  | wts | query_unscoped | true | false | 22 | 29 | 7.8531 | 0.4795 | 0.0234 | 0.0132 | hybrid | structured_no_system | [6 empty] | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 |  | false | false | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-186602 | NAOCL DOSING SKID SHELTER - ELEVATION & SECTION | DRAWING |  |  | NAOCL DOSING SKID SHELTER |  | DRAWING for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - ELEVATION & SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | sectional_drawing | sectional_drawing | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7916 | 0.7041 | 0.7041 | g_safe | [5 empty] | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | true | false | 9 | 6 | 7.8531 | 0.5708 | 0.0296 | 0.0222 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-186651 | NAOCL DOSING SKID SHELTER - FND, GROUND, ROOF FRAMING PLAN & FRAMING ELEVATION | DRAWING |  |  | NAOCL DOSING SKID SHELTER |  | DRAWING for NAOCL DOSING SKID SHELTER | Chemical Dosing System | Name Plate DraWing | 1 | start+4M<=FA<=start+4M+2M | FA ∈ [start+120d, start+180d] | rule_query | drawing | drawing | drawing | drawing | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5793 | 0.4071 | 0.4071 | g_safe | [5 empty] | FI | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  | wts | wts | rule | wts | match | true | false | 1 | 7 | 7.8531 | 0.5537 | 0.0313 | 0.0313 | hybrid | structured_preferred | wts | civil_design | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-186652 | NAOCL DOSING SKID SHELTER - REBAR DETAIL | Detail Drawing |  |  | NAOCL DOSING SKID SHELTER |  | Detail Drawing for NAOCL DOSING SKID SHELTER |  | NAOCL DOSING SKID SHELTER - REBAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | dosing¦naocl¦shelter¦skid |  | scoped | match | match | rule_generic | passed |  | 0.8333 | 0.7864 | 0.8192 | 0.8192 | g_safe | [5 empty] | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | civil_design | civil_design | match |  |  |  |  | wts | query_unscoped | true | false | 10 | 9 | 7.8531 | 0.5197 | 0.0288 | 0.0216 | hybrid | structured_no_system |  | civil_design |  |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | fi_complete | 0.90 |  | false | false | 0.64 | fi_complete | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-186800 | AUX. LEB - CALCULATION | Calculation sheet |  |  | Local Electrical Building |  | Calculation sheet for Local Electrical Building | Electrical Building | FGS ELECTRICAL BUILDING - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.7687 | 0.7556 | 0.7556 | g_ambig | uncertain | 0.45 |  | 6 | Document title is 'AUX. LEB - CALCULATION' but available specific rules are for other LEB foundation calculations (FGS/FO/GTG/HRSG/etc.), so the correct specific mapping cannot be determined. | FI | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | false | 4 | 4 | 3.1906 | 0.3575 | 0.0312 | 0.0312 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | fi_complete | 0.90 |  | false | false | 0.32 | needs_review_activity | rule_scope_status=rule_generic;activity_equipment_unconfirmed;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186801 | AUX. LEB - GROUND FLOOR PLAN & ROOF PLAN | Plan |  |  | Local Electrical Building |  | Plan for Local Electrical Building |  | AUX. LEB - GROUND FLOOR PLAN & ROOF PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | electrical |  | electrical | query |  | activity_unscoped | true | true | 1 | 20 | 36.0912 | 0.4632 | 0.0289 | 0.0130 | hybrid | structured_no_phase | electrical | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186802 | AUX. LEB - SIDE WALL ELEVATION | Elevation Drawing |  |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_safe | [5 empty] | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | false | 5 | 4 |  | 0.4093 | 0.0310 | 0.0310 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186803 | AUX. LEB - MAIN SECTION | SECTION |  |  | Local Electrical Building |  | SECTION for Local Electrical Building |  | AUX. LEB - MAIN SECTION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | sectional_drawing | sectional_drawing | electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 2PF1600W90A11.1T | (HRSG #22 LEB) Transportataion - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2008-08-02 | 2008-09-15 |  |  | query_unknown | electrical |  | electrical | query | hrsg | mismatch | false | false | 255 | 1 | 4.4572 | 0.4630 | 0.0196 | 0.0037 | hybrid | structured_no_phase | electrical | [8 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186851 | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan |  |  | Local Electrical Building |  | Plan for Local Electrical Building |  | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | [6 empty] | FI | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | false | 10 | 1 | 3.4893 | 0.4679 | 0.0307 | 0.0307 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186852 | AUX. LEB - GROUND FLOOR FRAMING PLAN & ROOF FRAMING PLAN | Plan |  |  | Local Electrical Building |  | Plan for Local Electrical Building |  | AUX. LEB - GROUND FLOOR FRAMING PLAN & ROOF FRAMING PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan | electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 0.9998 | 0.9999 | 0.9999 | [6 empty] | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | electrical |  | electrical | query |  | activity_unscoped | true | true | 1 | 19 | 36.0912 | 0.4584 | 0.0291 | 0.0131 | hybrid | structured_no_phase | electrical | [5 empty] | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.48 | needs_review | activity_phase_status=query_unknown;activity_scope_status=activity_unscoped;activity_generic;date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186853 | AUX. LEB - LINE & ROW FRAMING ELEVATION | Elevation Drawing |  |  | Local Electrical Building |  | Elevation Drawing for Local Electrical Building |  | DraWing for Electrical | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | drawing | drawing | electrical¦leb¦local |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.5752 | 0.8726 | 0.6108 | g_safe | [5 empty] | FA | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 |  | civil_design | civil_design | match | electrical | electrical | electrical | query | electrical | match | false | false | 5 | 6 |  | 0.4322 | 0.0305 | 0.0305 | hybrid | structured_preferred | electrical | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review_activity | activity_equipment_unconfirmed;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186854 | AUX. LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | Detail Drawing |  |  | Local Electrical Building |  | Detail Drawing for Local Electrical Building |  | AUX. LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | false | false | 24 | 2 | 2.0152 | 0.4583 | 0.0280 | 0.0280 | hybrid | structured_preferred | electrical | civil_design | 10 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | fi_complete | 0.90 |  | false | false | 0.40 | needs_review_activity | activity_equipment_unconfirmed |  | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186855 | AUX. LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | Schedule |  |  | Local Electrical Building |  | Schedule for Local Electrical Building |  | AUX. LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | schedule | schedule | schedule | schedule | electrical¦leb¦local | leb | scoped | match | match | match | passed |  | 1.0000 | 0.9999 | 1.0000 | 1.0000 | [6 empty] | FI | 2CF1600W32A04 | (HRSG #21 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2008-03-31 | 2008-06-25 |  |  | query_unknown | electrical |  | electrical | query | hrsg | mismatch | false | false | 76 | 10 | 4.5740 | 0.5006 | 0.0216 | 0.0041 | hybrid | structured_no_phase | electrical | [8 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0ZEN-189000 | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | DESIGN CRITERIA |  |  |  |  | DESIGN CRITERIA |  | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | title | criteria | criteria | design_criteria | design_criteria |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 1.0000 | [6 empty] | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | design_criteria | design_criteria | match | [5 empty] | query_unscoped | true | true | 1 | 1 | 62.3058 | 0.6559 | 0.0328 | 0.0197 | hybrid | structured_no_system |  | design_criteria¦system_design¦civil_design |  | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | fa_earliest | false | false | 0.46 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_generic |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0HBD-189001 | YARD PLATFORM | PLATFORM |  |  |  |  | PLATFORM | [5 empty] | rule_query | other | other | platform | yard_platform |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.3333 | 0.6285 | 0.4219 | 0.2953 | [7 empty] | 1CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Oil Supply System (GTG) | 2008-03-03 | 2008-05-02 |  |  | query_unknown |  |  |  |  | bop¦gtg | query_unscoped | true | false | 4 | 18 | 8.9418 | 0.4343 | 0.0284 | 0.0160 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0HBD-189002 | PEECC PLATFORM | [7 empty] | PEECC PLATFORM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | peecc_platform | peecc_platform |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 1.0000 | 0.7667 | 0.5367 | [6 empty] | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | true | 21 | 22 |  | 0.3841 | 0.0245 | 0.0110 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VL00-P0MPA-220001 | CIVIL - STG FOUNDATION - SHAPE UNIT P6 |  | Steam Turbine & Generator |  |  |  | for STG | [5 empty] | rule_query | other | specification | civil_stg_foundation_shape_unit_p6 | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg |  | stg | query | gsut_uat¦stg | match | true | false | 1 | 18 | 20.6909 | 0.6670 | 0.0292 | 0.0292 | hybrid | structured_cell_found_text_preferred | stg | civil_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-VL00-P7MPA-220002 | CIVIL - STG FOUNDATION - SHAPE - UNIT P7 |  | Steam Turbine & Generator |  |  |  | for STG | [5 empty] | rule_query | other | specification | civil_stg_foundation_shape_unit_p7 | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg |  | stg | query | gsut_uat¦stg | match | true | false | 1 | 20 | 20.6909 | 0.6676 | 0.0289 | 0.0289 | hybrid | structured_cell_found_text_preferred | stg | civil_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UF00-P0MAA-220003 | ST FOUNDATION LOAD - PLAN | Plan | Steam Turbine |  |  |  | Plan for STG |  | STG BLDG FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | plan | plan | plan | plan | steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.5000 | 0.5797 | 0.5239 | 0.5239 | [6 empty] | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 6 | 1 | 11.3731 | 0.6987 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | stg | civil_design |  | 2024-03-01 | 2024-03-05 | 2024-03-20 | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | fa_earliest | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XM00-P0MAA-220015 | LAYDOWN PLAN - UNIT P6 & P7 | Plan |  |  |  |  | Plan |  | LAYDOWN PLAN | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.7937 | 0.7048 | 0.4933 | [6 empty] | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  | query_unknown | [5 empty] | query_unscoped | true | true | 1 | 1 | 24.0608 | 0.5139 | 0.0328 | 0.0148 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0MPA-220023 | STG FOUNDATION - DESIGN CRITERIA - UNIT P6 & P7 | DESIGN CRITERIA | Steam Turbine & Generator |  |  |  | DESIGN CRITERIA for STG |  | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | 1 | start-1M<=FA<=start+1M | FA ∈ [start-30d, start+30d] | rule_query | criteria | criteria | design_criteria | design_criteria | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.5561 | 0.4668 | 0.4668 | g_safe | [5 empty] | FI | 1EF6500W16A02 | (STG #10 & UST Shelter) FDN & Firewall Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_criteria | civil_design | compatible | stg |  | stg | query | gsut_uat¦stg | match | true | false | 2 | 14 | 27.3657 | 0.6436 | 0.0296 | 0.0222 | hybrid | structured_cell_found_text_preferred | stg | design_criteria¦system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220025 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P6 | P&ID | Steam Turbine & Generator | STEAM TURBINE SYSTEM |  |  | P&ID for STEAM TURBINE SYSTEM | H2, CO2 Supply System | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6637 | 0.5491 | 0.5491 | g_ambig | generic_ok | 0.75 |  | 1 | The specific rule is for the STG instrument air system P&ID, while the document title is a general 'Steam Turbine System - Unit P6' P&ID without indicating instrument air. | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg | h2 | stg | query | stg | match | true | false | 370 | 19 | 15.3978 | 0.6510 | 0.0150 | 0.0150 | hybrid | structured_blocked_procurement_conflict | stg | system_design¦procurement |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220026 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P7 | P&ID | Steam Turbine & Generator | STEAM TURBINE SYSTEM |  |  | P&ID for STEAM TURBINE SYSTEM | FinFan Cooler | P&I Diagram | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | title | diagram | diagram | p_id | p_id | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6608 | 0.5482 | 0.5482 | g_ambig | generic_ok | 0.75 |  | 1 | The specific rule is for the STG instrument air system P&ID, while the document title is a general 'Steam Turbine System - Unit P6' P&ID without indicating instrument air. | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 370 | 18 | 15.3978 | 0.6580 | 0.0151 | 0.0151 | hybrid | structured_blocked_procurement_conflict | stg | system_design¦procurement |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;activity_rrf_low;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220027 | P&I DIAGRAM HPH - UNIT P6 | P&ID |  |  |  |  | P&ID |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.6785 | 0.6702 | 0.6702 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match |  | hrsg | hrsg | rule | hrsg | match | false | false | 1 | 1 | 15.5570 | 0.6358 | 0.0328 | 0.0328 | hybrid | structured_preferred | hrsg | system_design¦procurement | 10 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220028 | P&I DIAGRAMS HPH - UNIT P7 | P&I DIAGRAMS |  |  |  |  | P&I DIAGRAMS |  | HRSG - P&I Diagram | 1 | start+87D<=FA<=start+87D+2M | FA ∈ [start+87d, start+147d] | title | diagram | diagram | p_id | p_id |  | hrsg | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7073 | 0.4455 | 0.4455 | [6 empty] | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | system_design | system_design | match |  | hrsg | hrsg | rule | hrsg | match | false | false | 504 | 9 | 6.2923 | 0.5912 | 0.0163 | 0.0163 | hybrid | structured_blocked_procurement_conflict | hrsg | system_design¦procurement |  | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 |  | false | false | 0.21 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;rule_score_medium;activity_equipment_unconfirmed;activity_scope_source=rule;activity_rrf_low |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220029 | P&I DIAGRAM LUBRICATION OIL - UNIT P6 | P&ID |  | LUBE OIL SYSTEM |  |  | P&ID for LUBE OIL SYSTEM |  | P&I Diagram Oil | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | p_id | p_id | lube¦oil |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7673 | 0.9302 | 0.6511 | g_safe | [5 empty] | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 1 | 2 | 21.9247 | 0.6355 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220030 | P&I DIAGRAM LUBRICATION OIL - UNIT P7 | P&ID |  | LUBE OIL SYSTEM |  |  | P&ID for LUBE OIL SYSTEM |  | P&I Diagram Oil | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | p_id | p_id | lube¦oil |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7667 | 0.9300 | 0.6510 | g_safe | [5 empty] | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 1 | 2 | 21.9247 | 0.6375 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-VE01-P6MAA-220047 | ALLOWABLE LOADINGS AND DISPLACEMENTS | [7 empty] | AlloWable loadings and displacements | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | allowable_loadings_and_displacements | allowable_loadings_and_displacements |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8484 | 0.9545 | 0.6682 | [6 empty] | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  |  | civil_design | query_unknown |  |  |  |  | bop | query_unscoped | false | false | 2442 | 1 |  | 0.3865 | 0.0168 | 0.0094 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR00-P6MAA-220073 | CONTROL SYSTEM ARCHITECTURE |  |  | control system |  |  | for control system |  | Control system architecture | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | control_system_architecture | control_system_architecture |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.8950 | 0.9685 | 0.6780 | [6 empty] | FA | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | false | 1 | 1 | 10.5120 | 0.5008 | 0.0328 | 0.0184 | hybrid | structured_no_system |  |  |  | 2025-02-03 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-04-19 | 2025-05-19 | generated | 0.30 |  | false | false | 0.48 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG01-P6MAA-220089 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P6 | DETAIL DRAWINGS |  | Piping |  |  | DETAIL DRAWINGS for Piping |  | Detail DraWings. Piping and BOM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | piping |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7094 | 0.9128 | 0.6390 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | false | 104 | 3 | 7.7414 | 0.5721 | 0.0220 | 0.0124 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XG01-P7MAA-220090 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P7 | DETAIL DRAWINGS |  | Piping |  |  | DETAIL DRAWINGS for Piping |  | Detail DraWings. Piping and BOM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | detail_drawing | detail_drawing | piping |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7081 | 0.9124 | 0.6387 | g_safe | [5 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | false | 104 | 8 | 7.7414 | 0.5641 | 0.0208 | 0.0117 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | activity_phase_status=compatible;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XS01-P6MAA-220093 | CONTROL SYSTEM FUNCTIONS PHILOSOPHY | Philosophy |  | control system |  |  | Philosophy for control system | [5 empty] | rule_query | other | description | philosophy | control_description |  | fgp | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.6000 | 0.5196 | 0.5759 | 0.5759 | [7 empty] | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | false | 2 | 2 | 10.5120 | 0.4590 | 0.0323 | 0.0181 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YL13-P6MAA-220095 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (HW) | LIST | TURBINE CONTROL SYSTEM AND Distributed Control System |  |  |  | LIST for TURBINE CONTROL SYSTEM AND Distributed Control System | [5 empty] | rule_query | other | other | list | distributed_control_system | dcs¦distributed¦turbine | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.6863 | 0.9059 | 0.6341 | [7 empty] | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 |  | commissioning | query_unknown | dcs |  | dcs | query | dcs¦electrical | match | true | false | 2 | 1 | 39.7987 | 0.6562 | 0.0325 | 0.0244 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P6MAA-220097 | LOGIC DIAGRAMS FOR ST | LOGIC DIAGRAMS | Steam Turbine |  |  |  | LOGIC DIAGRAMS for STG |  | Logic Diagrams | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | diagram | diagram | diagram | diagram | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7023 | 0.6773 | 0.4741 | g_ambig | generic_ok | 0.75 |  | 1 | The competing specific rule targets an STG trip/protection diagram, but the document is a generic 'Logic Diagrams for ST' without confirming it is the trip/protection diagram. | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 10.8416 | 0.5899 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | stg | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | rule_score_medium;rule_generic_judge=g_ambig:generic_ok;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL13-P6MAA-220143 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (SW) - UNIT 1+2 | LIST | TURBINE CONTROL SYSTEM AND Distributed Control System |  |  |  | LIST for TURBINE CONTROL SYSTEM AND Distributed Control System | [5 empty] | rule_query | other | other | list | distributed_control_system | dcs¦distributed¦turbine | dcs | scoped | match | mismatch | match | rejected | deliverable_subtype_mismatch | 1.0000 | 0.6863 | 0.9059 | 0.6341 | [7 empty] | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 |  | commissioning | query_unknown | dcs |  | dcs | query | dcs¦electrical | match | true | false | 2 | 1 | 39.7987 | 0.6538 | 0.0325 | 0.0244 | hybrid | structured_no_phase | dcs | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-CM01-P6MAA-220205 | DRAWINGS, PART LISTS OF TURBINE – UNIT P6 | DRAWING |  |  |  |  | DRAWING |  | DRAWINGS, PART LISTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7287 | 0.9186 | 0.6430 | [6 empty] | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible |  |  |  |  | gsut_uat¦stg | query_unscoped | false | false | 2 | 761 | 7.9900 | 0.4731 | 0.0173 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-CM01-P7MAA-220206 | DRAWINGS, PART LISTS OF TURBINE – UNIT P7 | DRAWING |  |  |  |  | DRAWING |  | DRAWINGS, PART LISTS | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7266 | 0.9180 | 0.6426 | [6 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible |  |  |  |  | gsut_uat¦stg | query_unscoped | false | false | 24 | 69 | 7.7130 | 0.5195 | 0.0197 | 0.0111 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YL08-P6MAA-220207 | TRIPS & ALARMS SETTINGS UNIT P6+P7 | SETTINGS |  |  |  |  | SETTINGS | [5 empty] | rule_query | other | other | settings | electrical_protection_and_operation_settings |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.2000 | 0.4106 | 0.2632 | 0.1842 | [7 empty] | 2CF6500W38A07.1 | (GTG UAT) F/F Install & test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-07-18 | 2008-08-02 |  | commissioning | query_unknown |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | false | 71 | 42 | 3.7895 | 0.3462 | 0.0174 | 0.0098 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P6CJJ-220275 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P6 | Technical Specification |  | CONTROL SYSTEM |  |  | Technical Specification for CONTROL SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5852 | 0.5256 | 0.5256 | [6 empty] | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match |  |  |  |  | dcs | query_unscoped | false | false | 1 | 1 | 18.3160 | 0.5277 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P7CJJ-220276 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P7 | Technical Specification |  | CONTROL SYSTEM |  |  | Technical Specification for CONTROL SYSTEM |  | Technical specification_poWer and control cables | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification |  |  | scoped | match | match | query_unscoped | passed |  | 0.5000 | 0.5852 | 0.5256 | 0.5256 | [6 empty] | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match |  |  |  |  | dcs | query_unscoped | false | false | 1 | 1 | 18.3160 | 0.5212 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | procurement |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 |  | false | false | 0.58 | needs_review | default_fc_window;rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P6CJJ-220277 | HMI DESIGN – UNIT P6 | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [12 empty] | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 |  | civil_design | query_unknown |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | false | 16 | 19 | 6.9050 | 0.4090 | 0.0258 | 0.0145 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P7CJJ-220278 | HMI DESIGN – UNIT P7 | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [12 empty] | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-07-02 | 2007-10-11 |  | civil_design | query_unknown |  |  |  |  | electrical¦gsut_uat¦gtg | query_unscoped | false | false | 16 | 9 | 6.9050 | 0.4198 | 0.0277 | 0.0156 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P6CJJ-220293 | INSTRUMENTATION DATA SHEETS - UNIT P6 | DATA SHEETS |  |  |  |  | DATA SHEETS |  | Instrumentation data sheets | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | datasheet | datasheet | data_sheet | data_sheet |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7793 | 0.9338 | 0.6537 | [6 empty] | FA | 1EF3515W00A02 | (N2 Gas System) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-27 | 2007-07-31 | procurement | procurement | match |  |  |  |  | n2 | query_unscoped | false | false | 41 | 33 | 9.3892 | 0.4526 | 0.0207 | 0.0155 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YT02-P7CJJ-220294 | INSTRUMENTATION DATA SHEETS - UNIT P7 | DATA SHEETS |  |  |  |  | DATA SHEETS |  | Instrumentation data sheets | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | datasheet | datasheet | data_sheet | data_sheet |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 0.7840 | 0.9352 | 0.6546 | [6 empty] | FA | 1EF3030W00A19 | (CCWP) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-03-01 | 2007-05-31 | procurement | procurement | match |  |  |  |  | ccw | query_unscoped | false | false | 81 | 20 | 9.0366 | 0.4557 | 0.0196 | 0.0147 | hybrid | structured_no_system |  | procurement |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P6MAA-220383 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P6 | ISOMETRIC DRAWINGS |  | PIPELINES |  |  | ISOMETRIC DRAWINGS for PIPELINES | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | pipelines |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6363 | 0.4709 | 0.4709 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  | compressed_air | compressed_air | rule | compressed_air | match | false | false | 1 | 1 | 4.8366 | 0.5189 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.24 | needs_review_activity | default_fc_window;rule_score_medium;activity_equipment_unconfirmed;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P7MAA-220384 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P7 | ISOMETRIC DRAWINGS |  | PIPELINES |  |  | ISOMETRIC DRAWINGS for PIPELINES | Air Compressor | Piping Isometric DraWing | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | drawing | drawing | isometric_drawing | isometric_drawing | pipelines |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6323 | 0.4697 | 0.4697 | g_safe | [5 empty] | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | system_design | system_design | match |  | compressed_air | compressed_air | rule | compressed_air | match | false | false | 1 | 1 | 4.8366 | 0.5251 | 0.0328 | 0.0328 | hybrid | structured_preferred | compressed_air | system_design | 1 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 |  | false | false | 0.24 | needs_review_activity | default_fc_window;rule_score_medium;activity_equipment_unconfirmed;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAA-220801 | STEAM TURBINE OUTLINE DRAWING | Outline Drawing | Steam Turbine |  |  |  | Outline Drawing for STG |  | Motor Outline draWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | title | drawing | drawing | outline_drawing | outline_drawing | steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.6439 | 0.6599 | 0.6599 | g_ambig | uncertain | 0.50 |  | 3 | It is unclear whether 'STEAM TURBINE OUTLINE DRAWING' refers to the main turbine outline or the auxiliaries outline covered by the specific rules. | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 2 | 9.7265 | 0.5966 | 0.0325 | 0.0325 | hybrid | structured_preferred | stg | system_design | 3 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.72 | needs_review | default_fc_window;rule_scope_status=rule_generic;rule_generic_judge=uncertain |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P6MKA-250001 | ST GENERATOR UNIT#P6 FOUNDATION ARRANGEMENT DRAWING | General Arrangement Drawing | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg |  | stg | query | gsut_uat¦stg | match | true | false | 1 | 6 | 22.1966 | 0.6576 | 0.0315 | 0.0315 | hybrid | structured_preferred | stg | civil_design | 10 | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P7MKA-250002 | ST GENERATOR UNIT#P7 FOUNDATION ARRANGEMENT DRAWING | General Arrangement Drawing | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | General Arrangement DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | general_arrangement_drawing | general_arrangement_drawing | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 1.0000 | 0.7953 | 0.9386 | 0.9386 | g_safe | [5 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | civil_design | civil_design | match | stg |  | stg | query | gsut_uat¦stg | match | true | false | 1 | 5 | 22.1966 | 0.6679 | 0.0318 | 0.0318 | hybrid | structured_preferred | stg | civil_design | 10 | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UF00-P6MKA-250003 | ST GENERATOR FOUNDATION LOADING |  | Steam Turbine & Generator |  |  |  | for STG | [5 empty] | rule_query | other | specification | st_generator_foundation_loading | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | civil_design | civil_design | match | stg |  | stg | query | stg | match | true | false | 1 | 1 | 13.0175 | 0.7509 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | stg | civil_design | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250004 | GENERATOR PIPING CONNECTION |  | GENERATOR | PIPING |  |  | for GENERATOR | [5 empty] | rule_query | other | other | generator_piping_connection | gt_generator_outline | generator | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.3333 | 0.7146 | 0.4477 | 0.4477 | [7 empty] | 1CF2035W58A01 | (ST #10) Piping Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | 2008-08-11 | 2009-01-10 |  |  | query_unknown |  |  |  |  | stg | query_unscoped | true | false | 1 | 19 | 11.0196 | 0.5712 | 0.0291 | 0.0163 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250005 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION |  | GENERATOR |  |  |  | for GENERATOR | [5 empty] | rule_query | other | other | generator_stator_handling_and_shipping_dimension | gt_generator_outline | generator | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.3333 | 0.7146 | 0.4477 | 0.4477 | [7 empty] | 2PF1213W42A09T | (GEN #21) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2008-03-01 | 2008-04-15 |  | delivery | query_unknown |  |  |  |  | gtg | query_unscoped | false | false | 472 | 1 | 2.0660 | 0.4994 | 0.0183 | 0.0103 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250006 | HANDLING DIMENSION FOR GENERATOR ROTOR |  | GENERATOR |  |  |  | for GENERATOR | [5 empty] | rule_query | other | other | handling_dimension_for_generator_rotor | gt_generator_outline | generator | gt¦gtg | scoped | match | mismatch | mismatch | rejected | scope_mismatch | 0.3333 | 0.7146 | 0.4477 | 0.4477 | [7 empty] | 2EF1213W16A06 | (GEN #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-08-29 |  | civil_design | query_unknown |  |  |  |  | gtg | query_unscoped | false | false | 470 | 1 | 2.0540 | 0.5297 | 0.0183 | 0.0103 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0MKA-250007 | BRUSH HOLDER RIGGING ASSEMBLY | ASSEMBLY |  |  |  |  | ASSEMBLY | [5 empty] | rule_query | other | drawing | assembly | outline_drawing |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.2500 | 0.5857 | 0.3507 | 0.3507 | [7 empty] | 3CF1615W64A16 | (HRSG #31 EXP Joint & Bellows) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2009-01-20 | 2009-03-06 |  | installation | query_unknown |  |  |  |  | hrsg | query_unscoped | false | false | 3828 | 1 |  | 0.4488 | 0.0167 | 0.0094 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P6MKA-250008 | ST GENERATOR UNIT HYDROGEN COOLER OUTLINE | OUTLINE | Hydrogen System |  |  |  | OUTLINE for Hydrogen System |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | hydrogen¦stg |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4381 | 0.3648 | 0.2553 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible | h2 |  | h2 | query | h2 | match | true | false | 1 | 1 | 17.7637 | 0.5079 | 0.0328 | 0.0246 | hybrid | structured_preferred | h2 | system_design¦civil_design | 3 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-250009 | GENERATOR DATA SHEET | Data Sheet | GENERATOR |  |  |  | Data Sheet for GENERATOR |  | Equipment Data Sheet | 1 | start+10W<=FA<=start+10W+2M | FA ∈ [start+70d, start+130d] | title | datasheet | datasheet | data_sheet | data_sheet | generator |  | generic | match | match | rule_generic | passed |  | 0.6667 | 0.7328 | 0.6865 | 0.6865 | g_safe | [5 empty] | FA | 3PF1213W42A08P | (GEN #31) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2008-03-31 | procurement | procurement | match |  |  |  |  | gtg | query_unscoped | false | false | 129 | 1 | 9.4154 | 0.6054 | 0.0217 | 0.0163 | hybrid | structured_no_system |  | procurement |  | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250010 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL | OUTLINE | GENERATOR | Electrical System |  |  | OUTLINE for GENERATOR |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | generator |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5070 | 0.3854 | 0.2698 | g_safe | [5 empty] | FA | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | system_design | system_design | match | electrical |  | electrical | query |  | activity_unscoped | true | true | 1021 | 2095 | 3.0017 | 0.3422 | 0.0014 | 0.0008 | hybrid | structured_phase_gap | electrical | system_design | [7 empty] | blocked_rule_activity |  |  | false | false | 0.00 | blocked_rule_activity | rule_score_below_gate;rule_scope_ambiguous:rule_generic;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P6MKA-250011 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P6) | Layout Drawing | GENERATOR | Electrical System |  |  | Layout Drawing for Electrical System | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7499 | 0.5750 | 0.5750 | g_safe | [5 empty] | SKIP | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 17 | 12.4752 | 0.5793 | 0.0294 | 0.0294 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P7MKA-250012 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P7) | Layout Drawing | GENERATOR | Electrical System |  |  | Layout Drawing for Electrical System | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | electrical |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.7499 | 0.5750 | 0.5750 | g_safe | [5 empty] | SKIP | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 | civil_design | civil_design | match | electrical |  | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 16 | 12.4752 | 0.5827 | 0.0296 | 0.0296 | hybrid | structured_preferred | electrical | civil_design | 10 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250013 | CURRENT TRANSFORMER ASSEMBLY | ASSEMBLY | CURRENT TRANSFORMER |  |  |  | ASSEMBLY for CURRENT TRANSFORMER | [5 empty] | rule_query | other | other | assembly | current_transformer_assembly | current¦transformer |  | scoped | match | mismatch | rule_generic | rejected | deliverable_subtype_mismatch | 1.0000 | 0.8538 | 0.9561 | 0.6693 | [7 empty] | 1CF6500W70A14 | (STG TR) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-11-05 | 2008-12-19 |  | installation | query_unknown | gsut_uat |  | gsut_uat | query | electrical¦gsut_uat¦stg | match | true | false | 19 | 5 | 11.9134 | 0.4956 | 0.0280 | 0.0210 | hybrid | structured_no_phase | gsut_uat | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250014 | STATOR WINDING DIAGRAM | Diagram |  |  |  |  | Diagram |  | STATOR WINDING DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | [6 empty] | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | design_drawing | system_design | compatible |  |  |  |  | steam | query_unscoped | false | false | 11 | 101 | 10.0268 | 0.3674 | 0.0203 | 0.0114 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250015 | FIELD CLEARANCE DIAGRAM | Diagram |  |  |  |  | Diagram |  | FIELD CLEARANCE DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 1.0000 | 1.0000 | 1.0000 | 0.7000 | [6 empty] | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | design_drawing | system_design | compatible | [5 empty] | query_unscoped | true | true | 31 | 5 | 9.2794 | 0.4282 | 0.0264 | 0.0119 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.38 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250016 | ST GENERATOR MECHANICAL OUTLINE | OUTLINE | Steam Turbine & Generator |  |  |  | OUTLINE for STG |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.5318 | 0.3929 | 0.2750 | g_safe | [5 empty] | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | true | false | 1 | 1 | 12.4579 | 0.6628 | 0.0328 | 0.0246 | hybrid | structured_cell_found_text_preferred | stg | system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250017 | STG SOLE PLATE LAYOUT | Layout Drawing | Steam Turbine & Generator |  |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | [6 empty] | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | design_drawing | civil_design | compatible | stg | stg | stg | query | gsut_uat¦stg | match | true | false | 1 | 14 | 11.0282 | 0.6123 | 0.0299 | 0.0224 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | 2024-07-16 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 |  | false | false | 0.75 | usable | activity_phase_status=compatible | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250018 | STG FLOOR PLATE LAYOUT | Layout Drawing | Steam Turbine & Generator |  |  |  | Layout Drawing for Steam Turbine Generator | STEAM TURBINE GENERATOR | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.8000 | 0.7205 | 0.7761 | 0.7761 | [6 empty] | FA | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-03-01 |  | design_drawing | civil_design | compatible | stg | stg | stg | query | stg | match | true | false | 12 | 2 | 10.2112 | 0.6861 | 0.0300 | 0.0225 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=compatible;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MKA-250019 | SUGGESTIONS FOR GROUTING STG WITH FLOWABLE GROUT |  | Steam Turbine & Generator |  |  |  | for STG | [5 empty] | rule_query | other | specification | suggestions_for_grouting_stg_with_flowable_grout | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  | civil_design | query_unknown | stg |  | stg | query | gsut_uat¦stg | match | true | false | 1 | 19 | 11.0282 | 0.5263 | 0.0291 | 0.0218 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250020 | ST GENERATOR TERMINAL BOX ASSEMBLY | ASSEMBLY | Steam Turbine & Generator |  |  |  | ASSEMBLY for STG | [5 empty] | rule_query | other | specification | assembly | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5307 | 0.4392 | 0.4392 | [7 empty] | 1CF2040W42A04 | (STG #10) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2008-10-17 | 2009-02-17 |  | installation | query_unknown | stg |  | stg | query | stg | match | true | false | 8 | 3 | 11.0482 | 0.6679 | 0.0306 | 0.0229 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MKA-250021 | ROTOR ASSEMBLY DISASSEMBLY NOTE | ASSEMBLY DISASSEMBLY NOTE |  |  |  |  | ASSEMBLY DISASSEMBLY NOTE | [5 empty] | rule_query | other | other | assembly_disassembly_note | disassembly_note |  |  | scoped | match | mismatch | query_unscoped | rejected | deliverable_subtype_mismatch | 0.6667 | 0.9388 | 0.7483 | 0.5238 | [7 empty] | 3CF1265W42A03.1 | (Turning Gear) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | 2008-06-14 | 2008-06-21 |  | installation | query_unknown |  |  |  |  | gtg | query_unscoped | false | false | 3612 | 1 |  | 0.4365 | 0.0167 | 0.0094 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_subtype_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250022 | ROTOR ASSEMBLY DISASSEMBLY DIAGRAM | Diagram |  |  |  |  | Diagram |  | ROTOR ASSEMBLY AND DISASSEMBLY DIAGRAM | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.8000 | 0.9851 | 0.8555 | 0.5989 | [6 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible |  |  |  |  | h2 | query_unscoped | false | false | 4 | 3310 | 10.5360 | 0.2441 | 0.0159 | 0.0090 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250023 | ST GENERATOR END SHIELD ASSY CE |  | Steam Turbine & Generator |  |  |  | for STG | [5 empty] | rule_query | other | specification | st_generator_end_shield_assy_ce | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg |  | stg | query | stg | match | true | false | 1 | 13 | 12.4579 | 0.6189 | 0.0301 | 0.0226 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250024 | ST GENERATOR END SHIELD ASSY TE |  | Steam Turbine & Generator |  |  |  | for STG | [5 empty] | rule_query | other | specification | st_generator_end_shield_assy_te | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg |  | stg | query | stg | match | true | false | 1 | 8 | 12.4579 | 0.6410 | 0.0311 | 0.0233 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260001 | SEAL OIL DRAIN ENLARGEMENT OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | [6 empty] | FA | 1CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | 2007-10-01 | 2007-12-26 | design_drawing | civil_design | compatible |  |  |  |  | gtg | query_unscoped | true | false | 23 | 44 | 10.5155 | 0.4232 | 0.0217 | 0.0122 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-05-19 | 2024-06-03 | 2024-06-18 | 2024-07-03 | 2024-08-02 | 2024-09-01 | generated | 0.30 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260002 | BEARING OIL DRAIN ENLARGEMENT OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | [6 empty] | FA | 1EF3020W16A09.1 | (Clean Drain Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-12-06 | 2008-05-05 | design_drawing | civil_design | compatible | [5 empty] | query_unscoped | true | true | 15 | 47 | 6.2231 | 0.4277 | 0.0227 | 0.0102 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | 2024-10-07 | 2024-11-06 | generated | 0.30 |  | false | false | 0.33 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_generic | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P6MKA-260003 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ISO | ISO | Steam Turbine & Generator | Auxiliary SYSTEM PIPING |  |  | ISO for STG | [5 empty] | rule_query | other | specification | iso | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5268 | 0.4381 | 0.4381 | [7 empty] | 1CF2035W58A01 | (ST #10) Piping Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | 2008-08-11 | 2009-01-10 |  |  | query_unknown | stg |  | stg | query | stg | match | true | false | 4 | 1 | 19.6034 | 0.6951 | 0.0320 | 0.0240 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6MKA-260004 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ARRANGEMENT | ARRANGEMENT | Steam Turbine & Generator | Auxiliary SYSTEM PIPING |  |  | ARRANGEMENT for STG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6752 | 0.4359 | 0.3705 | g_safe | [5 empty] | FA | 1EF2070W16A01 | (STG #10 Aux. Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-12-24 | 2008-05-21 | design_drawing | civil_design | compatible | stg |  | stg | query | stg | match | true | false | 4 | 2 | 16.0041 | 0.6254 | 0.0318 | 0.0238 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | generated | 0.60 |  | false | false | 0.46 | needs_review | default_fc_window;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P6MKA-260005 | ST GENERATOR UNIT#P6 AUX SYSTEM HANGER & SUPPORT |  | Steam Turbine & Generator | Steam Turbine GENERATOR UNIT#P6 Auxiliary SYSTEM |  |  | for STG | [5 empty] | rule_query | other | specification | st_generator_unit_p6_aux_system_hanger_and_support | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  | query_unknown | stg |  | stg | query | stg | match | true | false | 1 | 11 | 26.2080 | 0.6289 | 0.0305 | 0.0229 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P7MKA-260006 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ISO | ISO | Steam Turbine & Generator | Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM |  |  | ISO for STG | [5 empty] | rule_query | other | specification | iso | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5268 | 0.4381 | 0.4381 | [7 empty] | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  | query_unknown | stg |  | stg | query | stg | match | true | false | 1 | 5 | 26.2080 | 0.6663 | 0.0318 | 0.0238 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7MKA-260007 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ARRANGEMENT | ARRANGEMENT | Steam Turbine & Generator | Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM |  |  | ARRANGEMENT for STG |  | Arrangement | 2 | start+1M <= FA <= start+2M | FA ∈ [start+30d, start+60d] | rule_query | other | other | arrangement | arrangement | generator¦steam¦stg¦turbine |  | generic | match | match | rule_generic | passed |  | 0.3333 | 0.6752 | 0.4359 | 0.3705 | g_safe | [5 empty] | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | design_drawing | civil_design | compatible | stg |  | stg | query | gsut_uat¦stg | match | true | false | 1 | 13 | 30.3707 | 0.6098 | 0.0301 | 0.0226 | hybrid | structured_preferred | stg | system_design¦civil_design | 10 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-26 | 2025-03-13 | 2025-03-28 | generated | 0.60 |  | false | false | 0.46 | needs_review | default_fc_window;rule_score_medium;activity_phase_status=compatible;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XK00-P7MKA-260008 | ST GENERATOR UNIT#P7 AUX SYSTEM HANGER & SUPPORT |  | Steam Turbine & Generator | Steam Turbine GENERATOR UNIT#P7 Auxiliary SYSTEM |  |  | for STG | [5 empty] | rule_query | other | specification | st_generator_unit_p7_aux_system_hanger_and_support | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5289 | 0.4387 | 0.4387 | [7 empty] | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  | query_unknown | stg |  | stg | query | stg | match | true | false | 1 | 13 | 26.2080 | 0.6373 | 0.0301 | 0.0226 | hybrid | structured_no_phase | stg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260011 | H2 SEAL OIL UNIT OUTLINE | OUTLINE | Hydrogen System | Hydrogen SEAL OIL UNIT |  |  | OUTLINE for Hydrogen System |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | hydrogen |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4381 | 0.3648 | 0.2553 | g_safe | [5 empty] | FA | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 | design_drawing | civil_design | compatible | h2 |  | h2 | query | h2 | match | true | false | 1 | 2 | 26.5282 | 0.4732 | 0.0325 | 0.0244 | hybrid | structured_preferred | h2 | system_design¦civil_design | 3 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260012 | FLOAT TRAP OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | [6 empty] | FA | 1EF3030W16A01 | (EXP Head Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-11-02 | 2008-04-01 | design_drawing | civil_design | compatible |  |  |  |  | ccw | query_unscoped | false | false | 941 | 1 |  | 0.3672 | 0.0174 | 0.0098 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-06-20 | 2024-07-05 | 2024-07-20 | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 |  | false | false | 0.35 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260013 | LIQUID LEVEL DETECTOR OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | [6 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | design_drawing | civil_design | compatible |  |  |  |  | condensate¦fgp | query_unscoped | false | false | 73 | 63 |  | 0.3316 | 0.0156 | 0.0088 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped;activity_rrf_low;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260014 | GAS CONTROL VALVE STATION OUTLINE | OUTLINE | CONTROL VALVE | GAS CONTROL |  |  | OUTLINE for CONTROL VALVE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | valve |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4373 | 0.3645 | 0.2552 | g_safe | [5 empty] | FA | 1EF3520W32A28 | (Gas COMP House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-05-01 | 2007-10-01 | design_drawing | civil_design | compatible |  |  |  |  | fgp | query_unscoped | false | false | 637 | 21 | 2.9727 | 0.5484 | 0.0138 | 0.0078 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260015 | H2 BOTTLE MANIFOLD OUTLINE | OUTLINE | Hydrogen System |  |  |  | OUTLINE for Hydrogen System |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | hydrogen |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4381 | 0.3648 | 0.2553 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible | h2 |  | h2 | query | h2 | match | true | false | 1 | 1 | 17.7637 | 0.5346 | 0.0328 | 0.0246 | hybrid | structured_preferred | h2 | system_design¦civil_design | 3 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260016 | CO2 BOTTLE MANIFOLD OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline |  |  | scoped | match | match | query_unscoped | passed |  | 0.3333 | 0.7230 | 0.4502 | 0.3152 | [6 empty] | FA | 0CF3520W16A02 | (Gas Buffer) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-12-05 | 2008-02-04 | design_drawing | civil_design | compatible |  |  |  |  | fgp | query_unscoped | false | false | 81 | 10 |  | 0.4405 | 0.0214 | 0.0120 | hybrid | structured_no_system |  | system_design¦civil_design |  | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | 2024-10-06 | 2024-11-05 | generated | 0.30 |  | false | false | 0.41 | needs_review | rule_scope_status=query_unscoped;rule_score_medium;activity_phase_status=compatible;activity_scope_status=query_unscoped | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260017 | H2 CONTROL CABINET OUTLINE | OUTLINE | Hydrogen System |  |  |  | OUTLINE for Hydrogen System |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | hydrogen |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4381 | 0.3648 | 0.2553 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible | h2 |  | h2 | query | h2 | match | true | false | 1 | 1 | 17.7637 | 0.5169 | 0.0328 | 0.0246 | hybrid | structured_preferred | h2 | system_design¦civil_design | 3 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260018 | H2 GAS DRYER OUTLINE | OUTLINE | Hydrogen System |  |  |  | OUTLINE for Hydrogen System |  | outline | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | other | other | outline | outline | hydrogen |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4381 | 0.3648 | 0.2553 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | design_drawing | system_design | compatible | h2 |  | h2 | query | h2 | match | true | false | 1 | 1 | 17.7637 | 0.5288 | 0.0328 | 0.0246 | hybrid | structured_preferred | h2 | system_design¦civil_design | 3 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-260019 | GENERATOR AUX SYSTEM MOTOR & PUMP DATA SHEET | Data Sheet |  | GENERATOR Auxiliary SYSTEM |  |  | Data Sheet for GENERATOR Auxiliary SYSTEM | FireFighting | Pump Data Sheet | 1 | start+14W<=FA<=FC<=start+24W | FA ∈ [start+98d, start+168d] ¦ FC ∈ [start+98d, start+168d] | title | datasheet | datasheet | data_sheet | data_sheet | auxiliary¦generator¦pump | pump | scoped | match | match | match | passed |  | 0.7500 | 0.6678 | 0.7254 | 0.7254 | [6 empty] | FA | 1PF1265W42A02.8P | (Purge Air System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | 2007-03-01 | 2008-01-31 | procurement | procurement | match |  |  |  |  | compressed_air¦gtg | query_unscoped | false | false | 32 | 5 | 13.8172 | 0.6070 | 0.0263 | 0.0197 | hybrid | structured_no_system |  | procurement |  | 2024-06-07 | 2024-07-12 | 2024-08-16 | 2024-08-02 | 2024-09-06 | 2024-10-11 | generated | 0.90 |  | false | false | 0.80 | usable | activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-260020 | GENERATOR AUX SYSTEM INSTRUMENT DATA SHEET | Data Sheet |  | GENERATOR Auxiliary SYSTEM |  |  | Data Sheet for GENERATOR Auxiliary SYSTEM |  | Instrument Data Sheet & Catalogue | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | datasheet | datasheet | data_sheet | data_sheet | auxiliary¦generator |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6352 | 0.7156 | 0.7156 | g_safe | [5 empty] | FI | 1PF1265W42A12.8P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | 2007-03-01 | 2008-01-31 | procurement | procurement | match |  |  |  |  | gtg | query_unscoped | false | false | 32 | 2 | 13.7948 | 0.6003 | 0.0270 | 0.0202 | hybrid | structured_no_system |  | procurement |  | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MKW-260021 | H2 SEAL OIL SYSTEM - WIRING DIAGRAMS | WIRING DIAGRAMS | Hydrogen System | Hydrogen SEAL OIL SYSTEM |  |  | WIRING DIAGRAMS for Hydrogen SEAL OIL SYSTEM | FinFan Cooler | Wiring diagrams | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | hydrogen¦oil¦seal |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6166 | 0.5350 | 0.5350 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 |  | h2 | query | h2 | match | true | false | 1 | 1 | 29.7813 | 0.5443 | 0.0328 | 0.0328 | hybrid | structured_preferred | h2 | system_design¦engineering | 1 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MKG-260022 | GAS CONTROL SYSTEM - WIRING DIAGRAMS | WIRING DIAGRAMS |  | GAS CONTROL SYSTEM |  |  | WIRING DIAGRAMS for GAS CONTROL SYSTEM | FinFan Cooler | Wiring diagrams | 1 | start+3M<=FA<=start+3M+2M | FA ∈ [start+90d, start+150d] | rule_query | diagram | diagram | wiring_diagram | wiring_diagram | gas |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5824 | 0.5247 | 0.5247 | g_safe | [5 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 659 | 11 | 6.3682 | 0.5989 | 0.0155 | 0.0116 | hybrid | structured_no_system |  | system_design¦engineering |  | 2024-06-13 | 2024-07-13 | 2024-08-12 | 2024-08-27 | 2024-09-11 | 2024-09-26 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;activity_scope_status=query_unscoped;activity_rrf_low;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CY03-P0MKW-260031 | H2 SEAL OIL SYSTEM - SYSTEM DESCRIPTION | System Description | Hydrogen System | Hydrogen SEAL OIL SYSTEM |  |  | System Description for Hydrogen SEAL OIL SYSTEM | H2, CO2 Supply System | System Description | 1 | start+2M<= FA<=start + 2M+2M | FA ∈ [start+60d, start+120d] | title | description | description | system_description | system_description | hydrogen¦oil¦seal |  | scoped | match | match | rule_generic | passed |  | 0.6000 | 0.6064 | 0.6019 | 0.6019 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 | h2 | h2 | query | h2 | match | true | false | 1 | 2 | 36.5841 | 0.5854 | 0.0325 | 0.0325 | hybrid | structured_cell_found_text_preferred | h2 | system_design¦procurement |  | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CY03-P0MKG-260032 | GAS CONTROL SYSTEM - SYSTEM DESCRIPTION | System Description |  | GAS CONTROL SYSTEM |  |  | System Description for GAS CONTROL SYSTEM | N2 Gas System | System Description | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | description | description | system_description | system_description | gas |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6919 | 0.7326 | 0.7326 | g_safe | [5 empty] | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | system_design | system_design | match |  | n2 | n2 | rule | n2 | match | false | false | 1 | 1 | 12.7845 | 0.6795 | 0.0328 | 0.0328 | hybrid | structured_preferred | n2 | system_design¦procurement | 6 | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;activity_equipment_unconfirmed;activity_scope_source=rule;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MKW-260033 | H2 SEAL OIL SYTSEM P&ID | P&ID | Hydrogen System | Hydrogen SEAL OIL SYTSEM |  |  | P&ID for Hydrogen SEAL OIL SYTSEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | hydrogen¦oil¦seal¦sytsem |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6790 | 0.4370 | 0.4370 | g_safe | [5 empty] | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | system_design | system_design | match | h2 |  | h2 | query | h2 | match | true | false | 1 | 7 | 44.2570 | 0.6360 | 0.0313 | 0.0313 | hybrid | structured_cell_found_text_preferred | h2 | system_design¦procurement |  | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MKG-260034 | GAS CONTROL SYSTEM P&ID | P&ID |  | GAS CONTROL SYSTEM |  |  | P&ID for GAS CONTROL SYSTEM |  | P&ID | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | diagram | diagram | p_id | p_id | gas |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.7136 | 0.4474 | 0.4474 | g_safe | [5 empty] | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | system_design | system_design | match |  |  |  |  | fgp | query_unscoped | false | false | 11 | 10 | 20.7320 | 0.6863 | 0.0284 | 0.0213 | hybrid | structured_no_system |  | system_design¦procurement |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0MKA-260035 | LINE LIST FOR ST GENERATOR | LINE LIST | Steam Turbine & Generator |  |  |  | LINE LIST for STG | Air Compressor | Line List | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | other | other | line_list | line_list | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5221 | 0.5066 | 0.5066 | g_safe | [5 empty] | FI | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | procurement | procurement | match | stg | compressed_air | stg | query | stg | match | true | false | 1 | 3 | 18.7650 | 0.6927 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | procurement | 10 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0MKA-260036 | VALVE LIST FOR ST GENERATOR | VALVE LIST | Steam Turbine & Generator |  |  |  | Valve List for STG |  | Valve List | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | list | list | valve_list | valve_list | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.8319 | 0.7162 | 0.7162 | g_ambig | generic_ok | 0.70 |  | 1 | The specific rule is for the manual valve list for STG piping, while the document title 'Valve list for ST generator' does not clearly indicate it is that piping manual valve list. | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | procurement | procurement | match | stg |  | stg | query | stg | match | true | false | 1 | 3 | 18.7650 | 0.6697 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | procurement | 10 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_ambig:generic_ok |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0CJN-290001 | ELECTRICAL DIAGRAM STATIC EXCITATION SYSTEM FOR ST | Diagram | Steam Turbine & Generator | STATIC EXCITATION SYSTEM |  |  | Diagram for STATIC EXCITATION SYSTEM | Substation | Electrical Logic Diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | title | diagram | diagram | diagram | diagram | excitation¦static¦stg |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5204 | 0.5061 | 0.5061 | g_ambig | uncertain | 0.55 |  | 1 | The document is for the static excitation system, and it’s unclear whether it is specifically an STG trip/protection diagram versus a general excitation logic diagram. | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg | electrical | stg | query | stg | match | true | false | 1 | 1 | 11.6497 | 0.5614 | 0.0328 | 0.0246 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CJN-290002 | EXCITER PANEL OUTLINE DRAWING FOR ST | Outline Drawing | EXCITER PANEL |  |  |  | Outline Drawing for EXCITER PANEL | Cathodic | Outline DraWing | 1 | start+6W<=FA<=start+6W+2M | FA ∈ [start+42d, start+102d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | exciter¦panel¦stg |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.5542 | 0.6329 | 0.6329 | g_ambig | use_specific | 0.78 | Steam Turbine Auxiliaries Outline DraWing | 3 | An exciter panel for the steam turbine is typically part of steam turbine auxiliaries, so the Steam Turbine Auxiliaries outline drawing rule is the better equipment-specific match. | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 3 | 5.9784 | 0.4051 | 0.0323 | 0.0323 | hybrid | structured_preferred | stg | system_design | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0CJN-290003 | PSS STUDY REPORT FOR ST | REPORT | Steam Turbine & Generator |  |  |  | REPORT for STG |  | PSS STUDY REPORT_DRAFT | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | report | report | study_report | study_report | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.8286 | 0.7736 | 0.5415 | g_safe | [5 empty] | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 |  | system_design | query_unknown | stg |  | stg | query | stg | match | true | false | 1 | 2 | 11.6497 | 0.6601 | 0.0325 | 0.0244 | hybrid | structured_no_phase | stg |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | usable | activity_phase_status=query_unknown;rule_generic_judge=g_safe:safe;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CJN-290004 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST | DRAWINGS | EXCITATION TRANSFORMER |  |  |  | DRAWINGS for EXCITATION TRANSFORMER |  | DRAWINGS OF EXCITATION TRANSFORMER | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | drawing | drawing | drawing | drawing | excitation¦stg¦transformer |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.8814 | 0.9644 | 0.6751 | g_ambig | generic_ok | 0.80 |  | 1 | The competing specific rule targets an STG TCS/TPS cabinet internal arrangement, which is different equipment than an excitation transformer drawing. | FA | 1EF6500W16A09 | (STG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-02-06 | 2008-07-04 | design_drawing | civil_design | compatible | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦stg | match | true | false | 2 | 1 | 11.8118 | 0.6034 | 0.0325 | 0.0244 | hybrid | structured_preferred | gsut_uat | system_design¦civil_design | 10 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-12-08 | 2025-01-07 | generated | 0.30 |  | false | false | 0.60 | usable | activity_phase_status=compatible;rule_generic_judge=g_ambig:generic_ok | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0CJN-290005 | AC/DC POWER CABLE/RACEWAY LAYOUT | Layout Drawing |  | DC & UPS System |  |  | Layout Drawing for DC & UPS System | Substation | General Layout DraWing | 1 | start+4W<=FA<=start+4W+2M | FA ∈ [start+28d, start+88d] | rule_query | drawing | drawing | layout_drawing | layout_drawing | ups |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.6645 | 0.5493 | 0.5493 | g_safe | [5 empty] | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | design_drawing | civil_design | compatible | dc_ups |  | dc_ups | query |  | activity_unscoped | true | true | 7 | 634 | 24.0610 | 0.4047 | 0.0164 | 0.0074 | hybrid | structured_phase_gap | dc_ups | system_design¦civil_design | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MKY-290006 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION | SINGLE LINE DIAGRAMS |  |  |  |  | SINGLE LINE DIAGRAMS |  | Single Line Diagram | 1 | start+3W<=FA<=start+3W+2M | FA ∈ [start+21d, start+81d] | rule_query | diagram | diagram | single_line_diagram | single_line_diagram |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.8640 | 0.7259 | 0.7259 | [6 empty] | SKIP | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | system_design | system_design | match | [5 empty] | query_unscoped | true | true | 842 | 158 | 2.5734 | 0.5247 | 0.0057 | 0.0034 | hybrid | structured_no_system |  | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MKY-290007 | LOGIC DIAGRAMS OF GENERATOR CONTROL PANEL FOR STG | LOGIC DIAGRAMS | Steam Turbine & Generator |  |  |  | LOGIC DIAGRAMS for STG |  | Control & Protection Logic Diagrams | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | diagram | diagram | diagram | diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.6992 | 0.7348 | 0.5143 | g_ambig | uncertain | 0.55 |  | 1 | The title refers to generator control panel logic diagrams, and without explicit trip/protection scope it’s unclear whether the STG trip/protection specific rule applies. | FA | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | system_design | system_design | match | stg |  | stg | query | stg | match | true | false | 1 | 1 | 6.4795 | 0.6078 | 0.0328 | 0.0328 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | needs_review | rule_scope_status=rule_generic;rule_generic_judge=uncertain;date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290008 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG | SCHEMATIC DIAGRAMS | Steam Turbine & Generator |  |  |  | SCHEMATIC DIAGRAMS for STG | Substation | Schematic Diagram (for Protection & Control System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | title | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.7014 | 0.5104 | 0.5104 | g_safe | [5 empty] | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | true | false | 1 | 2 | 6.4795 | 0.6007 | 0.0325 | 0.0244 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290009 | SCHEMATIC DIAGRAMS FOR GENERATOR CONTROL PANEL | SCHEMATIC DIAGRAMS |  |  |  |  | SCHEMATIC DIAGRAMS |  | GT - TYPICAL SCHEMATIC DIAGRAM FOR ELECTRICAL PANEL | 1 | start+83D<=FA<=start+83D+2M | FA ∈ [start+83d, start+143d] | title | diagram | diagram | schematic_diagram | schematic_diagram |  | gt¦gtg | scoped | match | match | query_unscoped | passed |  | 0.4286 | 0.6899 | 0.5070 | 0.5070 | [6 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible |  | electrical¦gtg | electrical¦gtg | rule | ccw¦gtg | match | false | false | 1 | 2 | 1.0037 | 0.4435 | 0.0325 | 0.0244 | hybrid | structured_preferred | electrical¦gtg | system_design¦engineering | 3 | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 |  | false | false | 0.22 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_phase_status=compatible;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0MKY-290010 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG | Calculation sheet | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | ROOF FOR STG TR - CALCULATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | generator¦steam¦stg¦turbine | stg | scoped | match | match | match | passed |  | 0.6000 | 0.6512 | 0.6154 | 0.6154 | [6 empty] | FI | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | civil_design | civil_design | match | stg | stg | stg | query | stg | match | true | false | 1 | 4 | 14.7295 | 0.5693 | 0.0320 | 0.0320 | hybrid | structured_preferred | stg | civil_design | 10 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | fi_complete | 0.90 | fc_earliest¦fc_recommended¦fc_latest | false | true | 0.55 | fi_complete | date_range_ntp_anchored |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290011 | SCHEMATIC DIAGRAMS FOR EMERGENCY SEAL OIL DC MOTOR STARTER PANEL | SCHEMATIC DIAGRAMS |  | DC & UPS System |  |  | SCHEMATIC DIAGRAMS for DC & UPS System | Substation | Schematic Diagram (for DC System) | 1 | start+12W<=FA<=start+12W+2M | FA ∈ [start+84d, start+144d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | ups |  | scoped | match | match | rule_generic | passed |  | 0.6667 | 0.7232 | 0.6836 | 0.6836 | g_safe | [5 empty] | SKIP | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | 2007-04-02 | 2007-10-31 | design_drawing | system_design | compatible | dc_ups | dc_ups | dc_ups | query |  | activity_unscoped | true | true | 645 | 22 | 6.0510 | 0.5351 | 0.0136 | 0.0061 | hybrid | structured_phase_gap | dc_ups | system_design¦engineering | [7 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290012 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG | SCHEMATIC DIAGRAMS | Steam Turbine & Generator |  |  |  | SCHEMATIC DIAGRAMS for STG |  | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6810 | 0.4376 | 0.4376 | g_safe | [5 empty] | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | true | false | 1 | 2 | 5.6714 | 0.6186 | 0.0325 | 0.0244 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290013 | SCHEMATIC DIAGRAMS FOR PT/SA PANEL FOR STG | SCHEMATIC DIAGRAMS | Steam Turbine & Generator |  |  |  | SCHEMATIC DIAGRAMS for STG |  | Schematic diagram | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | diagram | diagram | schematic_diagram | schematic_diagram | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6810 | 0.4376 | 0.4376 | g_safe | [5 empty] | SKIP | 1EF2020W00A01 | (ST #10) ST Process Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-30 | design_drawing | system_design | compatible | stg |  | stg | query | stg | match | true | false | 1 | 2 | 5.6714 | 0.6406 | 0.0325 | 0.0244 | hybrid | structured_preferred | stg | system_design¦engineering | 3 | [6 empty] | skip |  |  | false | false | 0.00 | skip | date_status=skip |  | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0CJN-290014 | TECHNICAL SPECIFICATION OF EXCITATION SYSTEM FOR ST | Technical Specification | Steam Turbine & Generator | EXCITATION SYSTEM |  |  | Technical Specification for STG |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4436 | 0.4831 | 0.4831 | g_safe | [5 empty] | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | procurement | procurement | match | stg |  | stg | query | stg | match | true | false | 5 | 1 | 17.9135 | 0.6340 | 0.0318 | 0.0318 | hybrid | structured_cell_found_text_preferred | stg | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LCP-410001 | OUTLINE DRAWING FOR CONDENSATE STORAGE TANK | Outline Drawing | CONDENSATE STORAGE TANK | Condensate System |  |  | Outline Drawing for CONDENSATE STORAGE TANK |  | ACC - ConDensate Collecting Tank Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | condensate¦storage¦tank | acc¦tank | scoped | match | match | match | passed |  | 0.6667 | 0.7983 | 0.7062 | 0.7062 | [6 empty] | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | system_design | system_design | match | condensate | acc¦condensate | condensate | query | condensate | match | true | false | 1 | 1 | 21.1197 | 0.6145 | 0.0328 | 0.0328 | hybrid | structured_preferred | condensate | system_design | 1 | 2024-10-18 | 2024-11-17 | 2024-12-17 | 2025-01-01 | 2025-01-16 | 2025-01-31 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0LCP-410002 | STRENGTH CALCULATION FOR CONDENSATE STORAGE TANK | STRENGTH CALCULATION | CONDENSATE STORAGE TANK | Condensate System |  |  | STRENGTH CALCULATION for CONDENSATE STORAGE TANK |  | Condensate Tank & Pump FOUNDATION Calculation | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | condensate¦storage¦tank | pump¦tank | scoped | match | match | match | passed |  | 0.6000 | 0.7299 | 0.6390 | 0.6390 | [6 empty] | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | civil_design | civil_design | match | condensate | condensate | condensate | query | condensate¦fgp | match | true | false | 1 | 4 | 30.1852 | 0.5352 | 0.0320 | 0.0320 | hybrid | structured_preferred | condensate | civil_design | 10 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.90 | fa_earliest¦fa_recommended¦fa_latest | false | true | 0.55 | usable | date_range_ntp_anchored | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GHC-410011 | OUTLINE DRAWING FOR DEMINERALIZED WATER STORAGE TANK | Outline Drawing | DEMINERALIZED WATER STORAGE TANK | Water Treatment System |  |  | Outline Drawing for DEMINERALIZED WATER STORAGE TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | demineralized¦storage¦tank¦water¦wts | tank | scoped | match | match | match | passed |  | 0.6667 | 0.6909 | 0.6739 | 0.6739 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 1 | 1 | 20.1530 | 0.6024 | 0.0328 | 0.0328 | hybrid | structured_preferred | wts | system_design | 5 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GHC-410012 | STRENGTH CALCULATION FOR DEMINERALIZED WATER STORAGE TANK | STRENGTH CALCULATION | DEMINERALIZED WATER STORAGE TANK | Water Treatment System |  |  | STRENGTH CALCULATION for DEMINERALIZED WATER STORAGE TANK |  | CALCULATION OF DEMINERALIZED WATER TANK FOUNDATION | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | calculation | calculation | calculation | calculation | demineralized¦storage¦tank¦water¦wts | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7883 | 0.7032 | 0.7032 | [6 empty] | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts | wts | wts | query | wts | match | true | false | 1 | 1 | 65.6595 | 0.6072 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-04-18 | 2024-05-03 | 2024-05-18 | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 |  | false | false | 1.00 | usable |  | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GKB-410021 | OUTLINE DRAWING FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | Outline Drawing | TANK | Fire Fighting System |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | fire_protection¦tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | [6 empty] | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | system_design | system_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 1 | 29.2122 | 0.5571 | 0.0328 | 0.0328 | hybrid | structured_preferred | fire_fighting | system_design | 2 | 2024-04-13 | 2024-05-13 | 2024-06-12 | 2024-06-27 | 2024-07-12 | 2024-07-27 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GKB-410022 | STRENGTH CALCULATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | STRENGTH CALCULATION | TANK | Fire Fighting System |  |  | STRENGTH CALCULATION for TANK | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | fire_protection¦tank | tank | scoped | match | match | match | passed |  | 0.5000 | 0.8319 | 0.5996 | 0.5996 | [6 empty] | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 | civil_design | civil_design | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 1 | 3 | 29.1365 | 0.5246 | 0.0323 | 0.0323 | hybrid | structured_preferred | fire_fighting | civil_design | 10 | 2024-05-31 | 2024-06-30 | 2024-07-30 | 2024-08-14 | 2024-08-29 | 2024-09-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GKB-410031 | OUTLINE DRAWING FOR POTABLE WATER STORAGE TANK | Outline Drawing | TANK | Water Treatment System |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank¦wts | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match | wts |  | wts | query | wts | match | true | false | 2 | 1 | 16.5694 | 0.5800 | 0.0325 | 0.0325 | hybrid | structured_preferred | wts | system_design | 5 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GKB-410032 | STRENGTH CALCULATION FOR POTABLE WATER STORAGE TANK | STRENGTH CALCULATION | TANK | Water Treatment System |  |  | STRENGTH CALCULATION for TANK | shop Tank | Strenght Calculation for each Tank | 1 | start+1M<=FA<=start+1M+2M | FA ∈ [start+30d, start+90d] | rule_query | calculation | calculation | calculation | calculation | tank¦wts | tank | scoped | match | match | match | passed |  | 0.5000 | 0.8319 | 0.5996 | 0.5996 | [6 empty] | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | civil_design | civil_design | match | wts |  | wts | query | wts | match | true | false | 1 | 8 | 35.8953 | 0.5334 | 0.0311 | 0.0311 | hybrid | structured_cell_found_text_preferred | wts | civil_design |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411001 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR CONDENSATE STORAGE TANK | Technical Specification | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | g_safe | [5 empty] | FA | 0EF3520W68A03 | (Condensate Tank) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System |  | 2007-03-30 | procurement | procurement | match | condensate |  | condensate | query | condensate¦fgp | match | true | false | 4 | 1 | 24.6839 | 0.6023 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | condensate | procurement |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411011 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR DEMINERALIZED WATER STORAGE TANK | Technical Specification | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | g_safe | [5 empty] | FA | 0EF3010W42A04 | (WTS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System |  | 2007-05-30 | procurement | procurement | match | wts |  | wts | query | wts | match | true | false | 4 | 1 | 12.5088 | 0.5446 | 0.0320 | 0.0320 | hybrid | structured_preferred | wts | procurement | 10 | 2024-07-25 | 2024-08-24 | 2024-09-23 | 2024-10-08 | 2024-10-23 | 2024-11-07 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411021 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | Technical Specification | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | fire_protection¦tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | g_safe | [5 empty] | FA | 0EF4500W38A02 | (Fire Fighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | procurement | procurement | match | fire_fighting |  | fire_fighting | query | fire_fighting¦hvac | match | true | false | 4 | 1 | 21.7279 | 0.5105 | 0.0320 | 0.0320 | hybrid | structured_preferred | fire_fighting | procurement | 10 | 2024-06-26 | 2024-07-26 | 2024-08-25 | 2024-09-09 | 2024-09-24 | 2024-10-09 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411031 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE WATER STORAGE TANK | Technical Specification | TANK | CATHODIC PROTECTION SYSTEM |  |  | Technical Specification for TANK |  | Technical specification_conduit & accessories | 1 | start+8W<=FA<=start+8W+2M | FA ∈ [start+56d, start+116d] | rule_query | specification | specification | technical_specification | technical_specification | tank |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5009 | 0.5003 | 0.5003 | g_safe | [5 empty] | FA | 0EF3035W42A05 | (PWP) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System |  | 2007-05-31 | procurement | procurement | match | wts |  | wts | query | wts | match | true | false | 2 | 3 | 20.5975 | 0.5303 | 0.0320 | 0.0320 | hybrid | structured_preferred | wts | procurement | 10 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PGB-420010 | OUTLINE DRAWING FOR CCW EXPANSION HEAD TANK | Outline Drawing | TANK | Closed Cooling Water System |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | [6 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 11.0407 | 0.4242 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-15 | 2024-04-14 | 2024-05-14 | 2024-05-29 | 2024-06-13 | 2024-06-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PGB-420020 | OUTLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | Outline Drawing | TANK | Closed Cooling Water System |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | [6 empty] | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | system_design | system_design | match | ccw |  | ccw | query | ccw¦gtg | match | true | false | 1 | 2 | 11.0407 | 0.4234 | 0.0325 | 0.0325 | hybrid | structured_preferred | ccw | system_design | 3 | 2024-03-15 | 2024-04-14 | 2024-05-14 | 2024-05-29 | 2024-06-13 | 2024-06-28 | generated | 0.90 |  | false | false | 0.90 | usable | default_fc_window |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LCM-420030 | OUTLINE DRAWING FOR ATMOSPHERIC FLASH TANK | Outline Drawing | flash Tank |  |  |  | Outline Drawing for flash Tank |  | ACC - Flash Tank Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | flash¦tank | acc¦tank | scoped | match | match | match | passed |  | 0.8000 | 0.7500 | 0.7850 | 0.7850 | [6 empty] | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | true | 938 | 346 | 2.2471 | 0.4167 | 0.0035 | 0.0010 | hybrid | structured_phase_gap | acc | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rule_scope_unmatched;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LCM-420040 | OUTLINE DRAWING FOR VACUUM FLASH TANK | Outline Drawing | flash Tank |  |  |  | Outline Drawing for flash Tank |  | ACC - Flash Tank Outline DraWing | 1 | start+199D<=FA<=start+199D+2M | FA ∈ [start+199d, start+259d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | flash¦tank | acc¦tank | scoped | match | match | match | passed |  | 0.8000 | 0.7500 | 0.7850 | 0.7850 | [6 empty] | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | system_design | system_design | match |  | acc | acc | rule |  | activity_unscoped | true | true | 954 | 175 | 2.1131 | 0.4351 | 0.0052 | 0.0016 | hybrid | structured_phase_gap | acc | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rule_scope_unmatched;activity_rrf_below_gate;activity_generic_low_confidence |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0GKC-420050 | OUTLINE DRAWING FOR CHILLED WATER STORAGE TANK | Outline Drawing | TANK |  |  |  | Outline Drawing for TANK | shop Tank | Outline DraWing for Shop Fabricated Tank | 1 | start+2W<=FA<=start+2W+2M | FA ∈ [start+14d, start+74d] | rule_query | drawing | drawing | outline_drawing | outline_drawing | tank | tank | scoped | match | match | match | passed |  | 0.6667 | 0.7362 | 0.6875 | 0.6875 | [6 empty] | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | system_design | system_design | match |  |  |  |  | wts | query_unscoped | false | false | 688 | 125 | 5.9042 | 0.4678 | 0.0067 | 0.0051 | hybrid | structured_no_system |  | system_design | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_rrf_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0GKC-420051 | INSULATION DETAIL DRAWING FOR CHILLED WATER STORAGE TANK | DRAWING | TANK |  |  |  | DRAWING for Tank |  | Day Tank FOUNDATION REINF. DETAIL | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | rule_query | drawing | drawing | detail_drawing | detail_drawing | tank | tank | scoped | match | match | match | passed |  | 0.2000 | 0.5003 | 0.2901 | 0.2901 | [6 empty] | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | design_drawing | civil_design | compatible |  |  |  |  | wts | query_unscoped | true | false | 3 | 5 | 26.4743 | 0.5038 | 0.0313 | 0.0176 | hybrid | structured_no_system |  | system_design¦civil_design | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755001 | SAT Procedure for Isolated Phase Busbar (IPB) | Procedure | Isolated Phase Busduct | Electrical System |  |  | Procedure for Isolated Phase Busduct | Isolated Phase Bus | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | busduct¦isolated¦phase |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.7767 | 0.5330 | 0.5330 | g_safe | [5 empty] | FI | 2PF6500W74A03T | (IPB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-04-16 | 2008-05-30 | delivery | delivery | match | electrical |  | electrical | query | electrical | match | true | false | 2 | 5 | 64.7250 | 0.7241 | 0.0315 | 0.0315 | hybrid | structured_cell_found_text_preferred | electrical | delivery¦procurement |  | 2025-01-07 | 2025-02-06 | 2025-03-08 | 2025-03-23 | 2025-04-07 | 2025-04-22 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755002 | SAT Procedure for GSUT | Procedure | Generator Step-Up Transformer |  |  |  | Procedure for Generator Step-Up Transformer | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6353 | 0.4706 | 0.4706 | g_safe | [5 empty] | FI | 1PF6500W70A08T | (STG #10 & UST Shelter) Transportation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-06-23 | 2008-08-06 | delivery | delivery | match | gsut_uat | gsut_uat | gsut_uat | query | gsut_uat¦stg | match | true | false | 1 | 11 | 25.3315 | 0.5481 | 0.0305 | 0.0305 | hybrid | structured_cell_found_text_preferred | gsut_uat | delivery¦procurement |  | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755003 | SAT Procedure for 380kv EHV Cable and Accessories | Procedure | Cable |  |  |  | Procedure for Cable | PoWer Cable | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | cable |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.5302 | 0.5091 | 0.5091 | g_safe | [5 empty] | FI | 2PF6040W74A07T | (EHV Cable) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-02 | 2008-05-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | true | false | 2 | 1 | 25.7684 | 0.5990 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755004 | SAT Procedure for Non Segregated Phase Busduct (NSPBD) | Procedure | Non-Segregated Phase Bus Duct |  |  |  | Procedure for Non-Segregated Phase Bus Duct | Isolated Phase Bus | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | bus¦duct¦non¦phase¦segregated |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.7131 | 0.5139 | 0.5139 | g_safe | [5 empty] | FI | 1PF6500W74A03T | (IPB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-05-02 | 2008-06-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | false | false | 1 | 5 | 33.5442 | 0.5608 | 0.0318 | 0.0238 | hybrid | structured_no_system |  | delivery¦procurement |  | 2025-01-24 | 2025-02-23 | 2025-03-25 | 2025-04-09 | 2025-04-24 | 2025-05-09 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755005 | SAT Procedure for Unit Auxillary Transformer (UAT) | Procedure | Unit Auxiliary Transformer |  |  |  | Procedure for Unit Auxiliary Transformer | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | auxiliary¦transformer¦unit |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.6406 | 0.4722 | 0.4722 | g_safe | [5 empty] | FI | 1PF6500W70A05.1T | (GTG UAT) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-03-18 | 2008-05-01 | delivery | delivery | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 3 | 31.8144 | 0.6592 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | gsut_uat | delivery¦procurement |  | 2024-12-09 | 2025-01-08 | 2025-02-07 | 2025-02-22 | 2025-03-09 | 2025-03-24 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755006 | SAT Procedure for Protection Relay Panel, GSUT HV Side Energy Metering Panel | Procedure | Generator Step-Up Transformer |  |  |  | Procedure for Generator Step-Up Transformer | Protection & Metering System | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | generator¦step¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6164 | 0.4849 | 0.4849 | g_safe | [5 empty] | FI | 1PF6500W70A08T | (STG #10 & UST Shelter) Transportation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-06-23 | 2008-08-06 | delivery | delivery | match | gsut_uat | electrical | gsut_uat | query | gsut_uat¦stg | match | true | false | 1 | 2 | 25.3315 | 0.5645 | 0.0325 | 0.0325 | hybrid | structured_preferred | gsut_uat | delivery¦procurement | 10 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755007 | SAT Procedure for AC-UPS System | Procedure |  | AC-Uninterruptible Power Supply System |  |  | Procedure for AC-Uninterruptible Power Supply System | Sampling System | Packing Procedure | 1 | finish-2M-2M<=FA<=finish-2M | FA ∈ [finish-120d, finish-60d] | title | procedure | procedure | procedure | procedure | power¦supply¦uninterruptible |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4432 | 0.4830 | 0.4830 | g_safe | [5 empty] | FI | 0PF6500W70A03.4T | (DC & UPS) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2008-03-07 | 2008-04-21 | delivery | delivery | match | dc_ups | sampling | dc_ups | query | dc_ups¦electrical | match | true | false | 1 | 3 | 25.0305 | 0.5592 | 0.0323 | 0.0323 | hybrid | structured_cell_found_text_preferred | dc_ups | delivery¦procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755008 | SAT Procedure for DC Battery Charger System | Procedure |  | DIRECT CURRENT Battery Charger System |  |  | Procedure for DIRECT CURRENT Battery Charger System | Sampling System | Packing Procedure | 1 | finish-2M-2M<=FA<=finish-2M | FA ∈ [finish-120d, finish-60d] | title | procedure | procedure | procedure | procedure | battery¦charger¦current¦direct |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.3813 | 0.4644 | 0.4644 | g_safe | [5 empty] | FI | 0PF6500W70A03.4T | (DC & UPS) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2008-03-07 | 2008-04-21 | delivery | delivery | match | dc_ups | sampling | dc_ups | query | dc_ups¦electrical | match | false | false | 1 | 4 | 31.6195 | 0.5133 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | dc_ups | delivery¦procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755009 | SAT Procedure for Generator Circuit Breaker (GCB) | Procedure | Generator Circuit Breaker |  |  |  | Procedure for Generator Circuit Breaker | GENERATOR CIRCUIT BREAKER | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | breaker¦circuit¦generator |  | scoped | match | match | rule_generic | passed |  | 0.5714 | 0.7816 | 0.6345 | 0.6345 | g_safe | [5 empty] | FI | 1PF6500W86A03T | (GT GCB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2008-04-01 | 2008-05-15 | delivery | delivery | match |  |  |  |  | electrical¦gtg | query_unscoped | false | false | 1 | 7 | 47.0706 | 0.6557 | 0.0313 | 0.0235 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-23 | 2025-01-22 | 2025-02-21 | 2025-03-08 | 2025-03-23 | 2025-04-07 | generated | 0.90 |  | false | false | 0.58 | usable | default_fc_window;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755010 | SAT Procedure for LV Cable | Procedure | Low Voltage Cable |  |  |  | Procedure for Low Voltage Cable | PoWer Cable | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | cable¦low¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6297 | 0.4222 | 0.4222 | g_safe | [5 empty] | FI | 2PF6040W74A07T | (EHV Cable) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-02 | 2008-05-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | true | false | 5 | 16 | 27.3793 | 0.5123 | 0.0285 | 0.0214 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755011 | SAT Procedure for MV Cable | Procedure | Medium Voltage Cable |  |  |  | Procedure for Medium Voltage Cable | PoWer Cable | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | cable¦medium¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.6560 | 0.4301 | 0.4301 | g_safe | [5 empty] | FI | 2PF6040W74A07T | (EHV Cable) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-02 | 2008-05-16 | delivery | delivery | match |  |  |  |  | electrical | query_unscoped | true | false | 5 | 14 | 27.3793 | 0.5234 | 0.0289 | 0.0217 | hybrid | structured_no_system |  | delivery¦procurement |  | 2024-12-24 | 2025-01-23 | 2025-02-22 | 2025-03-09 | 2025-03-24 | 2025-04-08 | generated | 0.90 |  | false | false | 0.49 | needs_review | default_fc_window;rule_score_medium;activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755012 | SAT Procedure for 480V Motor Control Center | Procedure | 480V Motor Control Center |  |  |  | Procedure for 480V Motor Control Center | Motor Operated Valve | NDE Procedure | 1 | start+20W<=FA<=start+20W+2M | FA ∈ [start+140d, start+200d] | rule_query | procedure | procedure | procedure | procedure | 480v¦center¦motor |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5831 | 0.4549 | 0.4549 | g_safe | [5 empty] | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | procurement | procurement | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | true | false | 1 | 1 | 37.8652 | 0.5678 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755013 | SAT Procedure for 13.8 kV MV Switch Gear | Procedure | 13.8 kV Medium Voltage Switch Gear |  |  |  | Procedure for 13.8 kV Medium Voltage Switch Gear | FireFighting | Packing Procedure | 1 | start-8W<=FA<=FC<=start-4W | FA ∈ [start-56d, start-28d] ¦ FC ∈ [start-56d, start-28d] | rule_query | procedure | procedure | procedure | procedure | gear¦medium¦switch¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4475 | 0.3676 | 0.3676 | g_safe | [5 empty] | FA | 0PF6500W70A03.2T | (MV SWGR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2008-04-01 | 2008-05-15 | delivery | delivery | match |  |  |  |  | electrical¦mv_lv | query_unscoped | false | false | 1 | 3 | 30.9796 | 0.5948 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | delivery¦procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755014 | SAT Procedure for LV Switchgear | Procedure | Low Voltage Switchgear |  |  |  | Procedure for Low Voltage Switchgear | FireFighting | Packing Procedure | 1 | start-8W<=FA<=FC<=start-4W | FA ∈ [start-56d, start-28d] ¦ FC ∈ [start-56d, start-28d] | rule_query | procedure | procedure | procedure | procedure | low¦switchgear¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4594 | 0.3711 | 0.3711 | g_safe | [5 empty] | FA | 0PF6500W70A03.3T | (LV SWGR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2008-04-01 | 2008-05-15 | delivery | delivery | match | mv_lv |  | mv_lv | query | electrical¦mv_lv | match | true | false | 1 | 1 | 40.7467 | 0.5851 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | mv_lv | delivery¦procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755015 | SAT Procedure for Lighting Distribution Board (LDB) | Procedure |  | Lighting & Small Power System |  |  | Procedure for Lighting & Small Power System | Lighting&small PoWer System | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | lighting¦power¦small |  | scoped | match | match | rule_generic | passed |  | 0.4286 | 0.6918 | 0.5075 | 0.5075 | g_safe | [5 empty] | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 | delivery | delivery | match | electrical | electrical | electrical | query | electrical | match | true | false | 1 | 4 | 31.3384 | 0.5479 | 0.0320 | 0.0320 | hybrid | structured_cell_found_text_preferred | electrical | delivery¦procurement |  | 2024-11-20 | 2024-12-20 | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | generated | 0.90 |  | false | false | 0.72 | usable | default_fc_window;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755016 | SAT Procedure for Mold / Dry Transformer | Procedure | Mold / Dry Transformer |  |  |  | Procedure for Mold / Dry Transformer | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | rule_query | procedure | procedure | procedure | procedure | dry¦mold¦transformer |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.7232 | 0.4970 | 0.4970 | g_safe | [5 empty] | FI | 1PF6500W70A13T | (STG TR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-07-31 | 2008-09-13 | delivery | delivery | match | gsut_uat | gsut_uat | gsut_uat | query | electrical¦gsut_uat¦stg | match | true | false | 5 | 15 | 15.2309 | 0.4574 | 0.0287 | 0.0287 | hybrid | structured_preferred | gsut_uat | delivery¦procurement | 10 | 2025-04-23 | 2025-05-23 | 2025-06-22 | 2025-07-07 | 2025-07-22 | 2025-08-06 | generated | 0.90 |  | false | false | 0.61 | usable | default_fc_window;rule_score_medium;rule_generic_judge=g_safe:safe |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755017 | SAT Procedure for MV & LV Motors | Procedure | Medium Voltage & Low Voltage Motors |  |  |  | Procedure for Medium Voltage & Low Voltage Motors | SumpPump | Packing Procedure | 1 | start-4W-2M<=FA<=start-4W | FA ∈ [start-88d, start-28d] | rule_query | procedure | procedure | procedure | procedure | low¦medium¦motors¦voltage |  | scoped | match | match | rule_generic | passed |  | 0.3333 | 0.4224 | 0.3601 | 0.3601 | g_safe | [5 empty] | FA | 0PF6500W70A03.3T | (LV SWGR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2008-04-01 | 2008-05-15 | delivery | delivery | match |  |  |  |  | electrical¦mv_lv | query_unscoped | false | false | 2 | 13 | 36.8441 | 0.4847 | 0.0298 | 0.0224 | hybrid | structured_no_system |  | delivery¦procurement | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755019 | SAT Procedure for STG Excitation Transformer (Oil Type) | Procedure | Steam Turbine & Generator |  |  |  | Procedure for STG | Transformer | Storage and Handling Procedure | 1 | start-12W-2M<=FA<=start-12W | FA ∈ [start-144d, start-84d] | title | procedure | procedure | procedure | procedure | generator¦steam¦stg¦turbine |  | scoped | match | match | rule_generic | passed |  | 0.4000 | 0.5909 | 0.4573 | 0.4573 | g_safe | [5 empty] | FI | 2PF6500W70A13T | (STG TR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | 2008-08-30 | 2008-10-14 | delivery | delivery | match | stg | gsut_uat | stg | query | electrical¦gsut_uat¦stg | match | true | false | 9 | 7 | 15.9818 | 0.6323 | 0.0294 | 0.0294 | hybrid | structured_preferred | stg | delivery¦procurement | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755020 | SAT Procedure for Neutral Grounding Transformer (NGTR) Neutral Grounding Resistor (NGR) | Procedure |  | Electrical System |  |  | Procedure for Electrical System | Sampling System | Packing Procedure | 1 | finish-2M-2M<=FA<=finish-2M | FA ∈ [finish-120d, finish-60d] | rule_query | procedure | procedure | procedure | procedure | electrical |  | scoped | match | match | rule_generic | passed |  | 0.5000 | 0.4571 | 0.4871 | 0.4871 | g_safe | [5 empty] | FI | 1PF6500W70A05T | (GTG TR) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-04-16 | 2008-05-30 | delivery | delivery | match | electrical | sampling | electrical | query | electrical¦gsut_uat¦gtg | match | true | false | 1 | 3 | 12.3421 | 0.6147 | 0.0323 | 0.0323 | hybrid | structured_preferred | electrical | delivery¦procurement | 10 | [6 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:rule_generic |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755021 | SAT Procedure for Ground, Step & touch Voltage | Procedure |  |  |  |  | Procedure |  | DCS - SAT ProceDure | 1 | start+364D<=FA<=start+346D+2M | FA ∈ [start+364d, start+406d] | title | procedure | procedure | procedure | procedure |  | dcs | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.4309 | 0.5959 | 0.5959 | [6 empty] | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | procurement | procurement | match |  | dcs | dcs | rule | dcs | match | false | false | 1 | 1 | 11.7558 | 0.3945 | 0.0328 | 0.0328 | hybrid | structured_preferred | dcs | procurement | 3 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 |  | false | false | 0.29 | needs_review_activity | default_fc_window;rule_scope_status=query_unscoped;activity_equipment_unconfirmed;activity_scope_source=rule |  | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755022 | Site Acceptance Test Procedure for Generator & Exc. TR Protection Relay, Control Panel | Procedure |  | Protection & Metering System |  |  | Procedure for Protection & Metering System |  | Site Acceptance Test Procedure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | test_procedure | test_procedure | metering¦protection |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7534 | 0.9260 | 0.6482 | g_safe | [5 empty] | FA | 0SF6500W62A05.6 | (Electrical Protection Panel) Function Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-05-27 | 2008-06-05 | commissioning | commissioning | match | electrical |  | electrical | query | electrical | match | true | false | 1 | 1 | 35.0381 | 0.6720 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | electrical | commissioning |  | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-29 | 2025-04-28 | generated | 0.30 |  | false | false | 0.80 | usable | rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755023 | Site Acceptance Test Procedure for HCIS Security System | Procedure |  | HCIS Security System |  |  | Procedure for HCIS Security System |  | Site Acceptance Test Procedure | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | procedure | procedure | test_procedure | test_procedure | hcis¦security |  | scoped | match | match | rule_generic | passed |  | 1.0000 | 0.7976 | 0.9393 | 0.6575 | g_safe | [5 empty] | FA | 1SF3030W62A25 | (CCWS) System Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-10-24 | 2008-10-28 | commissioning | commissioning | match |  |  |  |  | ccw | query_unscoped | true | false | 18 | 15 | 6.8786 | 0.4752 | 0.0262 | 0.0196 | hybrid | structured_no_system |  | commissioning |  | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | 2025-08-26 | 2025-09-25 | generated | 0.30 |  | false | false | 0.64 | usable | activity_scope_status=query_unscoped;rule_generic_judge=g_safe:safe | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DN05-P8MB-810006 | GAS TURBINE FUEL CHANGE-OVER TEST | TEST | Gas Turbine Generator |  |  |  | TEST for GTG | [5 empty] | rule_query | other | procedure | test | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5964 | 0.4589 | 0.4589 | [7 empty] | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-27 | 2008-11-27 | commissioning | commissioning | match | gtg |  | gtg | query | gtg | match | true | false | 1 | 1 | 27.5898 | 0.7947 | 0.0328 | 0.0328 | hybrid | structured_cell_found_text_preferred | gtg | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P8ZEN-810030 | PLANT EMERGENCY FUEL CHANGE-OVER TEST | TEST |  |  |  |  | TEST |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.2500 | 0.3904 | 0.2921 | 0.2921 | [6 empty] | FA | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-27 | 2008-11-27 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | true | false | 1 | 1 | 20.4072 | 0.6676 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | commissioning | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860001 | GT LOAD REJECTION TEST | TEST | Gas Turbine Generator |  |  |  | TEST for GTG | [5 empty] | rule_query | other | procedure | test | procedure | gas¦generator¦gtg¦turbine | gt¦gtg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5964 | 0.4589 | 0.4589 | [7 empty] | 1SF1230W62A15 | (Air Intake) Load(Running) Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | 2008-06-14 | 2008-06-16 | commissioning | commissioning | match | gtg |  | gtg | query | gtg | match | true | false | 1 | 11 | 13.1083 | 0.6559 | 0.0305 | 0.0305 | hybrid | structured_cell_found_text_preferred | gtg | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860002 | TRIAL RUN TEST OF THE PLANT | TEST |  |  |  |  | TEST |  | Chlorination Plant FOUNDATION PLAN | 1 | start-1M-2M<=FC<=start-1M | FC ∈ [start-90d, start-30d] | title | plan | plan | plan | plan |  |  | scoped | match | match | query_unscoped | passed |  | 0.2500 | 0.4171 | 0.3001 | 0.3001 | [6 empty] | FA | 1SF9012W62A10 | (GTG #11) Trial Run Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-01 | 2008-11-01 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | true | false | 4 | 6 | 21.7218 | 0.5225 | 0.0308 | 0.0231 | hybrid | structured_no_system |  | commissioning | [7 empty] | blocked_rule |  |  | false | false | 0.00 | blocked_rule | rule_score_below_gate;rule_scope_ambiguous:query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860003 | ST LOAD REJECTION TEST | TEST | Steam Turbine |  |  |  | TEST for STG | [5 empty] | rule_query | other | specification | test | painting_specification | steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5349 | 0.4405 | 0.4405 | [7 empty] | 1SF2000W62A01 | (ST #10) Aux. Equipment Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Test & Commissioning | 2009-03-09 | 2009-03-28 | commissioning | commissioning | match | stg |  | stg | query | stg | match | true | false | 1 | 16 | 14.5644 | 0.6130 | 0.0296 | 0.0296 | hybrid | structured_cell_found_text_preferred | stg | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860004 | ACTIVE POWER RESPONSE AND VOLTAGE CONTROL RESPONSE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF6500W62A05.3 | (LV SWGR) Function Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2008-06-22 | 2008-07-01 | commissioning | commissioning | match |  |  |  |  | electrical¦mv_lv | query_unscoped | true | false | 2 | 35 | 14.1407 | 0.4887 | 0.0267 | 0.0200 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860006 | ISLAND MODE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 1SF9040W62A13 | (Comm'g) Initial Operation Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-07-21 | 2009-07-21 | commissioning | commissioning | match | [5 empty] | query_unscoped | true | true | 28 | 6 | 5.2662 | 0.4775 | 0.0265 | 0.0159 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860007 | LOAD SWING TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF3035W62A13.0 | (SWS) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2009-01-10 | 2009-01-11 | commissioning | commissioning | match |  |  |  |  | service_water | query_unscoped | true | false | 1 | 1 | 10.2097 | 0.4166 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860008 | LDC Integration | [7 empty] | LDC Integration | 3 | start-3M<= FC<=start-1M | FC ∈ [start-90d, start-30d] | title | other | other | ldc_integration | ldc_integration |  |  | scoped | match | match | query_unscoped | passed |  | 0.6667 | 0.9998 | 0.7666 | 0.5366 | [6 empty] | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 |  |  | query_unknown |  |  |  |  | dcs | query_unscoped | false | false | 27 | 9 |  | 0.3480 | 0.0260 | 0.0146 | hybrid | structured_no_system |  |  |  | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-05-15 | 2024-06-14 | generated | 0.30 | fa_earliest¦fa_recommended¦fa_latest¦fc_earliest | false | true | 0.30 | needs_review | rule_scope_status=query_unscoped;activity_phase_status=query_unknown;activity_scope_status=query_unscoped;date_range_ntp_anchored_untrusted | FA derived from FC constraint (FC-only VT rule) | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860009 | STARTUP TIME TEST (COLD/WARM/HOT) | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 2SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | 2009-07-17 | 2009-08-19 | commissioning | commissioning | match | [5 empty] | query_unscoped | true | true | 2 | 7 | 12.9540 | 0.4303 | 0.0311 | 0.0186 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860010 | MINIMUM LOAD TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF3510W62A16 | (COMP Air System) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2008-10-21 | 2008-10-22 | commissioning | commissioning | match |  |  |  |  | compressed_air | query_unscoped | true | false | 3 | 1 | 10.2097 | 0.5014 | 0.0323 | 0.0242 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860011 | AGC | [11 empty] | rule_query | [9 empty] | query_unscoped | no_match | [12 empty] | 2SF0500W00A04 | GTG #21 TOD | CCPP Project Standard Schedule_20181012_Idea > Plant General > Key Milestones > Guaranteed Completion Date |  | 2009-01-03 |  |  | query_unknown |  |  |  |  | gtg | query_unscoped | false | false | 4 | 453 |  | 0.3118 | 0.0176 | 0.0099 | hybrid | structured_no_system | [9 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | no_rule |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860012 | PERFORMANCE TEST PROCEDURE FOR THERMAL PERFORMANCE | PROCEDURE |  |  |  |  | PROCEDURE | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6453 | 0.7186 | 0.7186 | [6 empty] | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match |  |  |  |  | fgp | query_unscoped | true | false | 1 | 2 | 21.2250 | 0.6182 | 0.0325 | 0.0244 | hybrid | structured_no_system |  | commissioning |  | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860013 | RELIABILITY TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 1SF9013W62A11 | (GTG #11) Reliability Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-02 | 2008-11-16 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | true | false | 4 | 4 | 13.4130 | 0.4898 | 0.0312 | 0.0234 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860014 | NET DEPENDABLE CAPACITY TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF6500W62A01 | (Power Receiving) Interface signal Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-08-01 | 2008-08-02 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | true | false | 23 | 15 | 5.2980 | 0.4728 | 0.0254 | 0.0190 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860015 | REACTIVE POWER TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF6500W62A05.7 | (Power Metering Equip) Function Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2008-04-30 | 2008-05-29 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | true | false | 46 | 1 | 5.1731 | 0.5663 | 0.0258 | 0.0194 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860016 | PRIMARY RESPONSE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF6500W62A04 | (Power Receiving) Protection Secondary & Primary Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-09-05 | 2008-09-11 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 14 | 16.9776 | 0.4214 | 0.0299 | 0.0224 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860017 | BLACK START-UP TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 2SF9012W62A09 | (GTG #21) Black start Test with GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | 2008-12-03 | 2008-12-03 | commissioning | commissioning | match |  |  |  |  | gtg | query_unscoped | true | false | 2 | 3 | 20.9158 | 0.5374 | 0.0320 | 0.0240 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860018 | PSS TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF3035W62A13.1 | (PWS) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2009-01-20 | 2009-01-24 | commissioning | commissioning | match |  |  |  |  | wts | query_unscoped | true | false | 64 | 2 | 5.1125 | 0.5319 | 0.0242 | 0.0181 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860019 | RESERVE BOILER THERMAL PERFORMANCE TEST PROCEDURE | PROCEDURE | RESERVE BOILER |  |  |  | PROCEDURE for RESERVE BOILER | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure | boiler¦reserve¦reserve_boiler |  | scoped | match | match | rule_generic | passed |  | 0.7500 | 0.5960 | 0.7038 | 0.7038 | g_safe | [5 empty] | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match | reserve_boiler |  | reserve_boiler | query | fgp | mismatch | true | false | 2 | 18 | 11.8832 | 0.5560 | 0.0289 | 0.0072 | hybrid | structured_system_absent | reserve_boiler | commissioning | [7 empty] | blocked_activity |  |  | false | false | 0.00 | blocked_activity | activity_scope_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860020 | PERFORMANCE TEST PROCEDURE FOR NOISE EMISSION | PROCEDURE |  |  |  |  | PROCEDURE | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.5480 | 0.6894 | 0.6894 | [6 empty] | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match |  |  |  |  | fgp | query_unscoped | true | false | 7 | 5 | 11.8832 | 0.5496 | 0.0303 | 0.0227 | hybrid | structured_no_system |  | commissioning |  | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860021 | PERFORMANCE TEST PROCEDURE FOR AIR EMISSION | PROCEDURE |  |  |  |  | PROCEDURE | FireFighting | Performance Test Procedure | 1 | start+3W<=FA<=FC<=start+12W | FA ∈ [start+21d, start+84d] ¦ FC ∈ [start+21d, start+84d] | title | procedure | procedure | test_procedure | test_procedure |  |  | scoped | match | match | query_unscoped | passed |  | 0.7500 | 0.6337 | 0.7151 | 0.7151 | [6 empty] | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | commissioning | commissioning | match |  |  |  |  | fgp | query_unscoped | true | false | 8 | 1 | 11.8832 | 0.6656 | 0.0311 | 0.0233 | hybrid | structured_no_system |  | commissioning |  | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 |  | false | false | 0.64 | needs_review | rule_scope_status=query_unscoped;activity_scope_status=query_unscoped |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860022 | SUPPLEMENTARY FIRING FOR HRSG |  | Heat Recovery Steam Generator |  |  |  | for HRSG | [5 empty] | rule_query | other | diagram | supplementary_firing_for_hrsg | p_id | generator¦heat¦hrsg¦recovery¦steam | hrsg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.5000 | 0.6685 | 0.5505 | 0.5505 | [7 empty] | 3SF1600W62A01.1 | (HRSG #32)Cold Commissioning for HRSG #32 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Commissioning | 2009-04-23 | 2009-05-12 |  | commissioning | query_unknown | hrsg |  | hrsg | query | hrsg | match | true | false | 11 | 3 | 16.5939 | 0.5864 | 0.0300 | 0.0225 | hybrid | structured_no_phase | hrsg | [8 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860027 | REACTIVE POWER TEST OF STG | TEST | Steam Turbine & Generator |  |  |  | TEST for STG | [5 empty] | rule_query | other | specification | test | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5349 | 0.4405 | 0.4405 | [7 empty] | 1SF6500W62A16 | (STG TR) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2009-01-05 | 2009-01-18 | commissioning | commissioning | match | stg |  | stg | query | electrical¦gsut_uat¦stg | match | true | false | 16 | 2 | 11.4338 | 0.7036 | 0.0293 | 0.0293 | hybrid | structured_cell_found_text_preferred | stg | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860028 | PSS TEST OF STG | TEST | Steam Turbine & Generator | Power Stability System |  |  | TEST for STG | [5 empty] | rule_query | other | specification | test | painting_specification | generator¦steam¦stg¦turbine | st¦stg | scoped | mismatch | not_applicable | match | rejected | deliverable_family_mismatch | 0.4000 | 0.5349 | 0.4405 | 0.4405 | [7 empty] | 1SF6500W62A16 | (STG TR) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2009-01-05 | 2009-01-18 | commissioning | commissioning | match | stg |  | stg | query | electrical¦gsut_uat¦stg | match | true | false | 19 | 1 | 11.8978 | 0.6998 | 0.0291 | 0.0291 | hybrid | structured_cell_found_text_preferred | stg | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860029 | SECONDARY RESPONSE TEST | TEST |  |  |  |  | TEST | [5 empty] | rule_query | other | report | test | test_report |  |  | scoped | mismatch | not_applicable | query_unscoped | rejected | deliverable_family_mismatch | 0.3333 | 0.4083 | 0.3558 | 0.3558 | [7 empty] | 0SF6500W62A04 | (Power Receiving) Protection Secondary & Primary Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-09-05 | 2008-09-11 | commissioning | commissioning | match |  |  |  |  | electrical | query_unscoped | true | false | 1 | 1 | 16.9776 | 0.4590 | 0.0328 | 0.0246 | hybrid | structured_no_system |  | commissioning | [7 empty] | no_rule |  |  | false | false | 0.00 | blocked_no_rule | rule_guard_rejected:deliverable_family_mismatch |  | 6210